## OP 22 CT Q1-2022
PG&E Interconnection Timeline Report | [8 empty] | Application Review: |  |  |  |  | Fast Track Initial Review: |  | Fast Track Supplemental Review: |  |  | Electrical Independence Test (EIT): |  |  | Scoping Meeting and Study Agreement: |  |  | System Impact Study (SIS): | [5 empty] | Draft Agreement: |  |  | Agreement Execution: |  |  |  | Material Modification: |  |  | Variance Request Review: |  |  | Net Generating Output Meter (NGOM): | [6 empty] | Minor Upgrades Design: | [5 empty] | Minor Upgrades Construction: | [5 empty] | Commissioning and In-Service:
Document Submission Frequency: Quarterly |  |  |  |  | Reporting Interval: 12/29/20 - 3/31/22 |  |  |  | ● 10 Business Days for initial application review [E.5.a.] (15 Business Days if Cost Envelope Option is selected [E.5.a.]) | [6 empty] | 20 Business Days [F.2.c.i.] |  |  | 20 Business Days [F.3.a.] |  |  | 5 Business Days [F.3.b.i.] |  |  | 60 Business Days [F.3.b.ii.] | [8 empty] | 90 Calendar Days [F.2.e.][F.3.2.ii.] |  |  |  | 10 Business Days [F.3.b.v] (20 Business Days if Cost Envelope Option is selected [F.3.b.v]) | [12 empty] | 60 Business Days (estimated timeline) | [5 empty] | 60 Business Days (estimated timeline) | [5 empty] | Mutually Agreeable Date with Customer
Proceeding Number: R.17-07-007; Decision Number: D.20-09-035; Ordering Paragraph (OP) Number from the Decision: 22 | [8 empty] | ● 10 Business Days for 1st deficiency cure review [E.5.b.i.] | [21 empty] | ● 15 Business Days for Fast Track [F.2.a] | [12 empty] | ● 20 Business Days to Design
[9 empty] | ● 5 Business Days for 2nd deficiency cure review [E.5.b.ii.] | [21 empty] | ● 30 Calendar Days for Detailed Study [F.3.e.i.] | [12 empty] | ● 20 Business Days to Install
Key | Utility | Zip Code | NEM Type | Project Type | Project Status | Technology Type | SizeTotal Proposed Gen | Cost Envelope Requested? | Application Received | Provide: 1st Written Notice/Invoice | Cycle Time A (Business Days to Acknowledge Interconnection Request Submission) | Application Deemed Complete | Cycle Time b (Business Days to Deem Complete) | Conduct: Initial Review (IR) | Cycle Time c (Time from Interconnection Request deemed complete to completion of initial review & provision of results) | Conduct: Supplemental Review (SR) | Conduct: Supplemental Review (SR) | Cycle Time d (Time from Supplemental Review start date to completion of Supplemental Review) | Conduct: Screens Q and R | Conduct: Screens Q and R | Cycle Time e (Time from Electrical Interdependence Test start date to its completion) | Scoping Meeting Date | Scoping Meeting Date | Cycle time f (Time from Electrical Interdependence Test completion to EIT results scoping meeting held) | DSA Agreement Executed by PG&E | Conduct: SIS | Cycle Time h (Time from System Impact Study start date to its completion date) | Scoping Meeting Date | Tendered DSA Agreement | Cycle Time g (Time from study scoping meeting until study agreement provided) | Tender Draft IA | Tender Draft IA | Cycle Time I (Time to provide Draft Generator Interconnection Agreement applicable milestone) | Tender Draft IA / AA Received | IA Negotiations/Customer Signature | Cycle Time J(a) (Time from Draft Generator Interconnection Agreement provided to date Generator Interconnection Agreement Executed) | Cycle Time J(b) (Time from Final Study Report date for Detailed Study to date Generator Interconnection Agreement Executed) | Receive Customer Changes | Determine Material Modifications | Cycle Time M (Time from request to consider modification to determination whether modification is material (F.3.b.v)) | Variance Request Received (typ. From cust) | Conduct: Variance Request Review | Cycle Time N (Time for responding to line-side taps variance requests (for Utilities that require a variance request)) | Conduct: Meter Review | Tender: Meter Invoice | Tender: Meter Invoice | Cycle Time O (Design and invoice of net generation output meter) | Move to FMO | FMO - PASS | Cycle Time P (Installation of net generation output meter) | SP&D Design Start | SP&D Deisgn End | Cycle Time Q(a) Time from customer agreement to proceed to final design and issuance of invoice SP&D | Tender EA Invoice | IT Design End | Cycle Time Q(b)Time from customer agreement to proceed to final design and issuance of invoice Telemetry | SP&D Construction Start | SP&D Construction Finish | Cycle Time R(a) Time from customer payment of invoice and completion of customer work to completion of upgrade construction SP&D | PG&E Construction Start IT | PG&E Construction Complete IT | Cycle Time R(b)Time from customer payment of invoice and completion of customer work to completion of upgrade construction Telemetry | PPI Authorization Letter | PPI Completion | Cycle Time S (Time for scheduling of commissioning test) | FMO - PASS (Move to FMO) | FMO schedule Inspection FMO order | Cycle Time S(b) This is for projects that do not require PPI | FMO - PASS | Permission to Operate - Final (COD) | Permission to Operate - Conditional (COD) | Cycle time K(a)Time from when the customer notifies the utility it has completed all of its obligations under the agreements (F.5.b) including commissioning tests, to when the utility provides the customer Permission to Operate | Conduct Pre Paralell Inspection (PPI) | Cycle time K(b) This cycle time is for projects that require PPI | Cycle Time L (Total time from submission of Interconnection Request to Permission to Operate (Not in Rule 21, tracked for informational purposes))
1 | PGE | 94804 | NEM | EXPNEM | Withdrawn | Solar PV | 111.324 |  | 2020-12-29 | 2020-12-29 | 0 | 2021-01-28 | 20 | [27 empty] | 2020-12-29 | 0
2 | PGE | 95746 | NEM | EXPNEM | Commercial | Solar PV | 32.89 |  | 2020-12-29 | 2020-12-29 | 0 | 2020-12-29 | 0 | 2021-01-19 | 13 | [15 empty] | 2021-01-19 | 2021-01-19 | 0 | 2021-01-19 | 2021-01-25 | 4 | [5 empty] | 0 | [5 empty] | 2021-03-23 | 2021-12-22 | 190 | [15 empty] | 2021-03-23 | 2021-12-14 | 184 | 2021-12-22 |  | 2022-01-12 | 15
3 | PGE | 93630 | NEM | EXPNEM | IA in Progress | Solar PV | 94.943 |  | 2020-12-29 | 2020-12-29 | 0 | 2020-12-30 | 1 | 2021-01-11 | 7 | [15 empty] | 2021-01-11 | 2021-01-11 | 0 | 2021-01-11 | 2021-01-14 | 3 |  |  |  |  | 2020-12-29 | 2021-01-19 | 13 |  |  |  |  | 2022-03-29 |  |  | 2021-03-02 | 2021-04-27 | 40 |  |  |  | 2021-08-16 | 2022-02-14 | 125 | [6 empty] | 2022-03-29 | 2022-03-31 | 2
4 | PGE | 95207 | NEM | EXPNEM | Withdrawn | Solar PV | 43.2 |  | 2020-12-29 | 2021-01-11 | 8 | 2021-02-11 | 30 | 2021-02-26 | 10 | [15 empty] | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | [7 empty] | 0
5 | PGE | 95453 | NEM | VNEMMASH | Implementation | Solar PV | 113.676 |  | 2020-12-29 | 2021-01-13 | 10 | 2021-03-31 | 63 | 2021-04-05 | 3 | [15 empty] | 2021-04-05 | 2021-04-23 | 14 | 2021-04-23 | 2021-05-20 | 19 |  |  |  |  | 2020-12-29 | 2021-04-29 | 84
6 | PGE | 94028 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 57.325 |  | 2020-12-29 | 2021-01-05 | 4 | 2021-01-05 | 4 | 2021-01-07 | 2 | [15 empty] | 2021-01-05 | 2021-01-05 | 0 | 2021-01-05 | 2021-02-17 | 29 | [5 empty] | 0 |  |  | 2021-01-12 | 2021-01-12 | 0
7 | PGE | 95327 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 207.052 |  | 2020-12-29 | 2021-01-12 | 9 | 2021-01-22 | 16 | 2021-02-17 | 17 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-05-11 | 83 |  |  |  |  | 2020-12-29 | 0 | [5 empty] | 2021-09-20 | 2021-09-27 | 5 | [15 empty] | 2021-09-20 | 2021-09-20 | 0 | 2021-09-27 | 2021-09-28 |  | 1 |  |  | 189
8 | PGE | 93230 | NEM | EXPNEM | Withdrawn | Solar PV | 1320 |  | 2020-12-29 | 2020-12-31 | 2 | 2021-01-13 | 10 | [5 empty] | 2021-01-13 | 2021-02-05 | 16 | 2021-02-05 | [19 empty] | 0
9 | PGE | 95540 | Non-NEM | Non-Export | Implementation | Storage | 357.5 |  | 2020-12-30 | 2020-12-31 | 1 | 2021-01-27 | 18 | 2021-05-12 | 74 | [15 empty] | 2021-02-01 | 2021-02-01 | 0 | 2021-02-01 | 2021-05-25 | 80 |  |  |  |  | 2020-12-30 | 0
10 | PGE | 95691 | NEM | EXPNEM | IA in Progress | Solar PV | 420 |  | 2020-12-30 | 2021-01-28 | 19 | 2021-04-08 | 68 | [17 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | [6 empty] | 2020-12-30 | 0
11 | PGE | 94503 | NEM | EXPNEM | IA in Progress | Solar PV | 480 |  | 2020-12-30 | 2021-01-11 | 7 | 2021-01-28 | 19 | 2021-04-29 | 64 | [15 empty] | 2021-04-29 | 2021-04-29 | 0 | 2021-04-29 | [6 empty] | 2020-12-30 | 0
12 | PGE | 93662 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2020-12-30 | 2021-01-13 | 9 | 2021-01-13 | 9 | 2021-02-03 | 14 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-06-28 | 101 |  |  |  |  | 2020-12-30 | 2021-01-27 | 18 |  |  |  |  | 2021-07-06 | 2021-07-13 | 5 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-13 |  | 2021-07-14 | 1
13 | PGE | 95536 | Non-NEM | Non-Export | Commercial | Storage | 140 |  | 2020-12-30 | 2020-12-31 | 1 | 2021-01-27 | 18 | 2021-03-02 | 23 | [15 empty] | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | 2021-06-28 | 83 |  |  |  |  | 2020-12-30 | 2021-02-05 | 25 |  |  |  |  | 2021-12-30 | 2022-01-07 | 6 | [15 empty] | 2021-12-30 | 2021-12-30 | 0 | 2022-01-07 |  | 2022-01-13 | 4 | 2021-12-02 | 30 | 0
14 | PGE | 95336 | NEM | EXPNEM | Withdrawn | Solar PV | 125 |  | 2020-12-30 | 2020-12-31 | 1 | 2021-01-05 | 3 | 2021-01-11 | 4 | [26 empty] | 0
15 | PGE | 95521 | Non-NEM | Non-Export | Commercial | Storage | 140 |  | 2020-12-30 | 2020-12-31 | 1 | 2021-01-27 | 18 | 2021-07-28 | 127 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | 2021-08-17 | 14 |  |  |  |  | 2020-12-30 | 2021-04-14 | 72 |  |  |  |  | 2022-03-08 | 2022-03-18 | 8 | [15 empty] | 2022-03-08 | 2022-03-08 | 0 | 2022-03-18 |  | 2022-03-24 | 4 | 2022-01-31 | 37 | 0
16 | PGE | 94127 | NEM | EXPNEM | Commercial | Solar PV | 90.079 |  | 2020-12-30 | 2020-12-31 | 1 | 2021-03-30 | 61 | 2021-05-04 | 25 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | 2021-07-26 | 57 | [5 empty] | 0 | [5 empty] | 2021-07-31 | 2021-08-05 | 3 | [15 empty] | 2021-07-31 | 2021-08-02 | 0 | 2021-08-05 |  | 2021-08-11 | 4
17 | PGE | 94010 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.454 |  | 2020-12-31 | 2021-01-07 | 4 | 2021-01-07 | 4 | 2021-01-28 | 14 | [15 empty] | 2021-01-07 | 2021-01-07 | 0 | 2021-01-07 | 2021-02-16 | 26 | [5 empty] | 0 | [5 empty] | 2021-02-16 | 2021-02-17 | 1 | [15 empty] | 2021-02-16 | 2021-02-17 | 1 | 2021-02-17 |  | 2021-02-17 | 0
19 | PGE | 95401 | NEM | EXPNEM | Implementation | Solar PV | 58.04 |  | 2020-12-31 | 2021-01-14 | 9 | 2021-01-14 | 9 | 2021-02-11 | 19 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2022-03-17 | 276 | [5 empty] | 0
20 | PGE | 95219 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-01-04 | 2021-01-05 | 1 | 2021-01-11 | 5 | 2021-01-21 | 7 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-06-03 | 93 |  |  |  |  | 2021-01-04 | 2021-09-28 | 186 |  |  |  |  | 2022-03-31 |  |  | 2021-10-21 | 2021-10-21 | 0 | [12 empty] | 2022-03-31
21 | PGE | 94513 | NEM | EXPNEM | Implementation | Solar PV | 131.497 |  | 2021-01-04 | 2021-01-14 | 8 | 2021-01-14 | 8 | 2021-02-04 | 14 | [15 empty] | 2021-02-04 | 2021-02-04 | 0 | 2021-02-04 | 2021-03-21 | 30 |  |  |  |  | 2021-01-04 | 2021-03-01 | 38 |  |  |  |  | 2021-07-20 | 2021-07-29 | 7 | 2021-06-14 | 2021-10-22 | 92 |  |  |  | 2021-11-16 | 2021-12-02 | 22 | [6 empty] | 2021-07-20 | 2021-12-23 | 108 | 2021-07-29 | 2021-07-29 |  | 0 |  |  | 144
22 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 700 |  | 2021-01-04 | 2021-01-15 | 9 | 2021-01-15 | 9 | 2021-02-04 | 13 | [15 empty] | 2021-02-04 | 2021-02-04 | 0 | 2021-02-04 | 2021-02-05 | 1 |  |  |  |  | 2021-02-04 | 2021-02-09 | 3 |  |  |  |  | 2021-12-22 | 2021-12-30 | 6 | 2021-03-08 | 2021-05-19 | 52 |  |  |  | 2021-11-03 | 2021-12-17 | 29 | [6 empty] | 2021-12-22 | 2021-12-23 | 1 | 2021-12-30 |  | 2021-12-30 | 0
23 | PGE | 95020 | NEM | EXPNEM | Commercial | Solar PV | 99.9 |  | 2021-01-04 | 2021-01-07 | 3 | 2021-01-15 | 9 | 2021-02-02 | 11 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-02 | 0 | [5 empty] | 0 | [5 empty] | 2021-02-03 | 2021-02-09 | 4 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-09 |  | 2021-02-10 | 1
24 | PGE | 94509 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 52.49 |  | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04 | 0
25 | PGE | 94509 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 61.773 |  | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04 | 0
26 | PGE | 94509 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 65.263 |  | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04 | 0
27 | PGE | 94509 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.444 |  | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04 | 0
28 | PGE | 94509 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 63.867 |  | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04 | 0
29 | PGE | 94509 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 62.122 |  | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04 | 0
30 | PGE | 94509 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 41.88 |  | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04 | 0
31 | PGE | 94509 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 63.169 |  | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04 | 0
32 | PGE | 94509 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 57.585 |  | 2021-01-04 | 2021-01-19 | 10 | [26 empty] | 2021-07-15 |  |  | 2021-01-04 | 0
33 | PGE | 95623 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 |  | 2021-01-05 | 2021-01-08 | 3 | 2021-01-08 | 3 | 2021-01-11 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-02-17 | 26 | [5 empty] | 0 | [5 empty] | 2021-02-17 | 2021-02-17 | 0 | [15 empty] | 2021-02-17 | 2021-02-17 | 0 | 2021-02-17 |  | 2021-02-17 | 0
34 | PGE | 93662 | NEM | EXPNEM | Commercial | Solar PV | 62.5 |  | 2021-01-05 | 2021-01-06 | 1 | 2021-01-19 | 9 | 2021-02-18 | 21 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-05-26 | 69 |  | 2021-08-19 | 2021-08-26 | 5 | 2021-01-05 | 2021-01-20 | 10 |  |  |  |  | 2021-07-16 | 2021-07-20 | 2 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-20 |  | 2021-07-26 | 4
35 | PGE | 93701 | NEM | EXPNEM | Commercial | Solar PV | 85.573 |  | 2021-01-05 | 2021-01-06 | 1 | 2021-01-07 | 2 | 2021-01-08 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-03-10 | 41 |  |  |  |  | 2021-01-05 | 0 | [5 empty] | 2021-03-12 | 2021-04-21 | 28 | [15 empty] | 2021-03-12 | 2021-04-21 | 28 | 2021-04-21 |  | 2021-04-23 | 2
36 | PGE | 93308 | NEM | EXPNEM | Commercial | Solar PV | 53.808 |  | 2021-01-05 | 2021-01-06 | 1 | 2021-01-06 | 1 | 2021-01-21 | 10 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-04-09 | 55 | [5 empty] | 0 | [5 empty] | 2021-04-12 | 2021-04-19 | 5 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-19 |  | 2021-04-27 | 6
37 | PGE | 95746 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-01-05 | 2021-01-20 | 10 | 2021-01-28 | 16 | 2021-02-02 | 3 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-04 | 2 | [5 empty] | 0 | [5 empty] | 2021-02-08 | 2021-02-08 | 0 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 |  | 2021-02-10 | 2
38 | PGE | 93212 | NEM | EXPNEM | Commercial | Solar PV | 31.886 |  | 2021-01-05 | 2021-01-06 | 1 | 2021-01-27 | 15 | 2021-02-11 | 11 | [15 empty] | 2021-02-11 | 2021-02-16 | 2 | 2021-02-16 | 2021-02-23 | 5 |  |  |  |  | 2021-01-05 | 2021-08-18 | 157 |  |  |  |  | 2021-09-17 | 2021-09-30 | 9 | 2021-03-17 | 2021-06-03 | 55 |  |  |  | 2021-06-03 | 2021-07-14 | 28 | [6 empty] | 2021-09-17 | 2021-09-20 | 1 | 2021-09-30 |  | 2021-10-07 | 5
39 | PGE | 93662 | NEM | EXPNEM | Commercial | Solar PV | 83.3 |  | 2021-01-05 | 2021-01-19 | 9 | 2021-01-19 | 9 | 2021-02-02 | 10 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-06-28 | 102 |  |  |  |  | 2021-01-05 | 2021-01-28 | 16 |  |  |  |  | 2021-07-06 | 2021-07-13 | 5 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-13 |  | 2021-07-13 | 0
40 | PGE | 95694 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-01-05 | 2021-01-06 | 1 | 2021-01-13 | 6 | 2021-02-02 | 13 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-02 | 0 |  |  |  |  | 2021-01-05 | 2021-01-20 | 10 |  |  |  |  | 2021-11-16 | 2021-11-22 | 4 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-22 |  | 2021-11-29 | 3
41 | PGE | 93314 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-01-05 | 2021-01-19 | 9 | 2021-01-19 | 9 | 2021-02-08 | 14 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-03-01 | 14 | [5 empty] | 0 | [5 empty] | 2021-03-23 | 2021-04-01 | 7 | [15 empty] | 2021-03-23 | 2021-03-24 | 1 | 2021-04-01 |  | 2021-04-01 | 0
42 | PGE | 93314 | NEM | VNEMMASH | Implementation | Solar PV | 433.597 |  | 2021-01-05 | 2021-01-12 | 5 | 2021-01-12 | 5 | 2021-02-19 | 26 |  |  |  | 2021-03-02 | 2021-04-23 | 38 | 2021-04-23 |  |  | 2021-04-23 | 2021-07-16 | 58 |  |  |  | 2021-07-16 | 2021-07-16 | 0 | 2021-07-16 | 2021-07-27 | 7 |  |  |  |  | 2021-08-18 | 2021-08-18 | 0 |  | 2021-08-18 | 2021-08-18 | 0 |  |  |  | 2021-09-08 | 2021-10-22 | 32 |  |  |  | 2021-11-05 | 2022-01-17 | 47
43 | PGE | 95341 | NEM | VNEMMASH | Implementation | Solar PV | 530 |  | 2021-01-05 | 2021-01-12 | 5 | 2021-01-12 | 5 | 2021-02-24 | 29 | [15 empty] | 2021-02-24 | 2021-02-24 | 0 | 2021-02-24 | 2021-05-05 | 50 | [5 empty] | 0 |  | 2021-06-17 | 2021-08-18 | 2021-08-18 | 43
44 | PGE | 93280 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 2600.5 |  | 2021-01-06 | 2021-01-07 | 1 | 2021-01-27 | 14 | [5 empty] | 2021-01-27 | 2021-03-04 | 25 | 2021-03-04 | 2021-03-04 | 0 | 2021-03-25 | 2021-06-21 | 61 | 2021-03-04 | 2021-03-08 | 2 | 2021-07-29 | 2021-07-29 | 0 | 2021-07-29 | 2021-08-18 | 14 | [5 empty] | 0 | [8 empty] | 2021-09-03 |  |  | 2021-09-03 | 2021-11-24 | 59
46 | PGE | 95519 | NEM | EXPNEM | IA in Progress | Solar PV | 493.369 |  | 2021-01-06 | 2021-01-07 | 1 | 2021-02-23 | 32 | 2021-03-09 | 10 | [15 empty] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | 2022-02-09 | 234 |  |  |  |  | 2021-12-13 | 0 | [5 empty] | 2022-03-15 | [17 empty] | 2022-03-15 | 2022-03-16 | 1
47 | PGE | 93230 | NEM | EXPNEM | Implementation | Solar PV | 1625 |  | 2021-01-06 | 2021-01-07 | 1 | 2021-01-20 | 9 | 2021-03-02 | 28 | 2021-03-08 | 2021-04-01 | 18 | 2021-05-03 | 2021-05-12 | 7 | 2021-05-12 | 2021-05-13 | 1 | 2021-05-21 | 2021-08-10 | 55 | 2021-05-13 | 2021-05-13 | 0 | 2021-08-19 | 2021-08-27 | 6 | 2021-08-27 | 2021-10-27 | 42 | [5 empty] | 0 | [8 empty] | 2021-12-13 | 2022-04-04 | 79
48 | PGE | 93465 | NEM | EXPNEM | Withdrawn | Solar PV | 52.675 |  | 2021-01-06 | 2021-01-19 | 8 | 2021-01-19 | 8 | 2021-02-08 | 14 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | [7 empty] | 0
50 | PGE | 95603 | NEM | EXPNEM | IA in Progress | Solar PV | 53.35 |  | 2021-01-07 | 2021-01-08 | 1 | 2021-01-08 | 1 | 2021-01-26 | 11 | [15 empty] | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 2021-01-29 | 3 |  |  |  |  | 2021-01-07 | 2021-02-08 | 21
51 | PGE | 94590 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-01-07 | 2021-01-08 | 1 | 2021-01-08 | 1 | 2021-02-08 | 20 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-02-12 | 4 |  |  |  |  | 2021-01-07 | 2021-02-09 | 22 |  |  |  |  | 2022-02-04 | 2022-02-10 | 4 | 2021-10-19 | 2021-11-02 | 10 | [12 empty] | 2022-02-04 | 2022-02-04 | 0 | 2022-02-10 |  | 2022-02-17 | 5
52 | PGE | 95231 | NEM | EXPNEM | Implementation | Solar PV | 112.682 |  | 2021-01-07 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-28 | 11 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23 | 2021-08-23 | 0 |  |  |  |  | 2021-01-07 | 0 |  | 2021-09-08 | [6 empty] | 2021-09-08 | 2022-02-02 | 101 |  |  |  | 2022-03-28 |  | 12
53 | PGE | 93304 | NEM | EXPNEM | Commercial | Solar PV | 168.87 |  | 2021-01-07 | 2021-01-08 | 1 | 2021-01-11 | 2 | 2021-02-20 | 27 | [15 empty] | 2021-02-20 | 2021-02-20 | 0 | 2021-02-20 | 2021-08-18 | 125 |  |  |  |  | 2021-01-07 | 2021-03-03 | 37 |  |  |  |  | 2021-08-21 | 2021-11-17 | 60 | [15 empty] | 2021-08-21 | 2021-11-10 | 56 | 2021-11-17 |  | 2021-11-22 | 3
54 | PGE | 95448 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.741 |  | 2021-01-07 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-03-09 | 38 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-03-10 | 39 | [5 empty] | 0 | [5 empty] | 2021-03-10 | 2021-03-10 | 0 | [15 empty] | 2021-03-10 | 2021-03-10 | 0 | 2021-03-10 |  | 2021-03-13 | 2
55 | PGE | 95020 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 41.331 |  | 2021-01-07 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-14 | 2 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-05-17 | 87 |  |  |  |  | 2021-01-07 | 2021-05-17 | 90 |  |  |  |  | 2021-05-20 | 2021-05-21 | 1 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-21 |  | 2021-05-21 | 0
56 | PGE | 93662 | NEM | EXPNEM | Commercial | Solar PV | 62.5 |  | 2021-01-07 | 2021-01-21 | 9 | 2021-01-21 | 9 | 2021-03-10 | 33 | [15 empty] | 2021-03-10 | 2021-03-10 | 0 | 2021-03-10 | 2021-06-28 | 77 |  |  |  |  | 2021-01-07 | 2021-02-02 | 17 |  |  |  |  | 2021-07-14 | 2021-07-20 | 4 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-20 |  | 2021-07-22 | 2
57 | PGE | 95206 | NEM | EXPNEM | Implementation | Solar PV | 54.229 |  | 2021-01-07 | 2021-01-21 | 9 | 2021-01-21 | 9 | 2021-02-10 | 14 | [15 empty] | 2021-02-10 | 2021-02-10 | 0 | 2021-02-10 | 2021-03-03 | 14 |  |  |  |  | 2021-01-07 | 2021-05-28 | 99 | [7 empty] | 2021-06-22 | 2021-10-21 | 85
59 | PGE | 94506 | NEM | EXPNEM | Implementation | Solar PV | 82.656 |  | 2021-01-08 | 2021-01-22 | 9 | 2021-01-22 | 9 | 2021-03-03 | 27 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-06-15 | 73 |  |  |  |  | 2021-03-12 | 2021-03-15 | 1 |  |  |  |  | 2022-02-03 | [17 empty] | 2022-02-03 | 2022-02-03 | 0
60 | PGE | 93618 | NEM | EXPNEM | Commercial | Solar PV | 60 |  | 2021-01-08 | 2021-01-22 | 9 | 2021-01-22 | 9 | 2021-02-11 | 14 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-22 | 6 |  |  |  |  | 2021-01-08 | 2021-02-02 | 16 |  |  |  |  | 2021-05-01 | 2021-05-10 | 5 | [15 empty] | 2021-05-01 | 2021-05-03 | 0 | 2021-05-10 |  | 2021-05-10 | 0
61 | PGE | 93250 | NEM | EXPNEM | Commercial | Solar PV | 83.3 |  | 2021-01-08 | 2021-01-23 | 9 | 2021-01-23 | 9 | 2021-02-06 | 10 | [15 empty] | 2021-02-06 | 2021-02-06 | 0 | 2021-02-06 | 2021-06-02 | 80 |  |  |  |  | 2021-01-08 | 2021-02-02 | 16 |  |  |  |  | 2021-07-20 | 2021-07-27 | 5 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-27 |  | 2021-07-29 | 2
62 | PGE | 94517 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-01-08 | 2021-01-16 | 5 | 2021-02-24 | 31 | 2021-03-15 | 13 | [15 empty] | 2021-02-24 | 2021-02-24 | 0 | 2021-02-24 | 2021-03-10 | 10 | [5 empty] | 0 | [5 empty] | 2021-03-15 | 2021-03-15 | 0 | [15 empty] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 |  | 2021-03-22 | 5
63 | PGE | 95521 | Non-NEM | Non-Export | Commercial | Storage | 350 |  | 2021-01-08 | 2021-01-11 | 1 | 2021-02-03 | 17 | 2021-04-30 | 61 | [15 empty] | 2021-04-30 | 2021-04-30 | 0 | 2021-04-30 | 2021-05-06 | 4 |  |  |  |  | 2021-01-08 | 2021-04-12 | 64 |  |  |  |  | 2021-12-21 | 2022-01-06 | 12 | [15 empty] | 2021-12-21 | 2021-12-22 | 1 | 2022-01-06 |  | 2022-01-07 | 1
64 | PGE | 93250 | NEM | EXPNEM | Commercial | Solar PV | 62.5 |  | 2021-01-08 | 2021-01-23 | 9 | 2021-01-23 | 9 | 2021-02-09 | 11 | [15 empty] | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | 2021-07-06 | 102 |  |  |  |  | 2021-01-08 | 2021-02-02 | 16 |  |  |  |  | 2021-07-06 | 2021-07-14 | 6 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-14 |  | 2021-07-14 | 0
65 | PGE | 94903 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 74.404 |  | 2021-01-08 | 2021-01-14 | 4 | 2021-01-18 | 5 | 2021-04-06 | 54 | [25 empty] | 2021-01-08 | 0 |  | 2021-01-19
66 | PGE | 95111 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 172.8 |  | 2021-01-08 | 2021-01-22 | 9 | 2021-06-25 | 117 | [5 empty] | 2021-06-25 | 2021-07-26 | 20 | 2021-07-26 | [18 empty] | 2021-01-08 | 0
67 | PGE | 95037 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 37.68 |  | 2021-01-08 | 2021-01-14 | 4 | 2021-01-21 | 8 | 2021-01-25 | 2 | [15 empty] | 2021-01-14 | 2021-01-14 | 0 | 2021-01-14 | 2021-10-15 | 191 | [5 empty] | 0 | [5 empty] | 2021-11-01 | 2021-11-01 | 0 | [15 empty] | 2021-11-01 | 2021-11-01 | 0 | 2021-11-01 |  | 2021-11-02 | 1
68 | PGE | 95501 | Non-NEM | Non-Export | Commercial | Storage | 140 |  | 2021-01-08 | 2021-01-11 | 1 | 2021-02-03 | 17 | 2021-03-30 | 38 | [15 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-04-12 | 9 |  |  |  |  | 2021-01-08 | 0 | [5 empty] | 2021-12-01 | 2021-12-09 | 6 | [15 empty] | 2021-12-01 | 2021-12-02 | 1 | 2021-12-09 |  | 2021-12-09 | 0 | 2021-11-30 | 7 | 0
69 | PGE | 95020 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-01-08 | 2021-01-12 | 2 | 2021-01-12 | 2 | 2021-02-25 | 30 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-26 | 21 |  |  |  |  | 2021-01-08 | 0 | [5 empty] | 2021-05-24 | 2021-06-02 | 6 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-06-02 |  | 2021-06-04 | 2
70 | PGE | 94559 | NEM | NEM Paired Storage | Implementation | ENGN, Solar PV, Storage | 910.673 |  | 2021-01-08 | 2021-01-20 | 7 | 2021-03-31 | 56 | 2021-05-10 | 28 | [15 empty] | 2021-05-10 | 2021-05-11 | 1 | 2021-05-11 | 2021-11-04 | 124 |  |  |  |  | 2021-01-08 | 0
71 | PGE | 94508 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.399 |  | 2021-01-09 | 2021-01-16 | 5 | 2021-01-16 | 5 | 2021-02-04 | 12 | [15 empty] | 2021-01-16 | 2021-01-16 | 0 | 2021-01-16 | 2021-02-16 | 19 | [5 empty] | 0 | [5 empty] | 2022-02-07 | 2022-02-14 | 5 | [15 empty] | 2022-02-07 | 2022-02-07 | 0 | 2022-02-14 |  | 2022-02-14 | 0
72 | PGE | 95148 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 |  | 2021-01-08 | 2021-01-14 | 4 | 2021-01-14 | 4 | 2021-02-03 | 13 | [15 empty] | 2021-01-14 | 2021-01-14 | 0 | 2021-01-14 | 2021-02-03 | 13 | [5 empty] | 0 | [5 empty] | 2021-02-03 | 2021-02-09 | 4 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-09 |  | 2021-02-09 | 0
73 | PGE | 94080 | NEM | EXPNEM | IA in Progress | Solar PV | 150 |  | 2021-01-09 | 2021-01-11 | 0 | 2021-01-13 | 2 | 2021-03-15 | 41 | [15 empty] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | 2021-07-28 | 95 |  |  |  |  | 2021-02-23 | 2021-02-23 | 0
74 | PGE | 95687 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 62.048 |  | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10 | 0
75 | PGE | 95687 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.292 |  | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10 | 0
76 | PGE | 95687 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 38.78 |  | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10 | 0
77 | PGE | 95687 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.292 |  | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10 | 0
79 | PGE | 95687 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 62.048 |  | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10 | 0
80 | PGE | 95687 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 42.054 |  | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10 | 0
81 | PGE | 95687 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 35.045 |  | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10 | 0
82 | PGE | 95687 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.292 |  | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10 | 0
83 | PGE | 95648 | NEM | EXPNEM | IA in Progress | Solar PV | 32.032 |  | 2021-01-11 | 2021-01-12 | 1 | 2021-01-12 | 1 | 2021-01-27 | 10 | [15 empty] | 2021-01-27 | 2021-01-27 | 0 | 2021-01-27 | [6 empty] | 2021-01-11 | 2021-01-26 | 10
84 | PGE | 95648 | NEM | EXPNEM | Implementation | Solar PV | 66.6 |  | 2021-01-11 | 2021-01-12 | 1 | 2021-01-19 | 5 | 2021-02-03 | 11 | 2021-02-03 | 2021-03-18 | 30 | 2021-03-23 | 2021-03-25 | 2 | 2021-03-25 |  |  | 2021-03-25 | 2021-06-22 | 62 |  |  |  | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-06-23 | 1 |  |  |  |  | 2021-01-11 | 2021-01-26 | 10
85 | PGE | 95242 | NEM | EXPNEM | Implementation | Solar PV | 40.1 |  | 2021-01-11 | 2021-01-26 | 10 | 2021-01-26 | 10 | 2021-02-18 | 16 | [15 empty] | 2021-02-16 | 2021-02-16 | 0 | 2021-02-16 | 2021-02-22 | 4 |  |  |  |  | 2021-01-11 | 2021-02-03 | 16
86 | PGE | 95037 | NEM | EXPNEM | Commercial | Solar PV | 37.099 |  | 2021-01-11 | 2021-01-12 | 1 | 2021-03-30 | 54 | 2021-08-09 | 92 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-09-13 | 24 |  |  |  |  | 2021-01-11 | 2021-02-05 | 18 |  |  |  |  | 2021-09-13 | 2021-10-12 | 21 | [15 empty] | 2021-09-13 | 2021-10-05 | 16 | 2021-10-12 |  | 2021-10-19 | 5
87 | PGE | 95648 | NEM | EXPNEM | Implementation | Solar PV | 91.918 |  | 2021-01-11 | 2021-01-12 | 1 | 2021-01-19 | 5 | 2021-02-03 | 11 | 2021-02-03 | 2021-03-18 | 30 | 2021-03-24 | 2021-03-25 | 1 | 2021-03-25 | [8 empty] | 2021-09-15 | 2021-09-21 | 4 | 2021-09-21 | 2021-09-23 | 2 |  |  |  |  | 2021-01-11 | 2021-02-02 | 15
88 | PGE | 95648 | NEM | EXPNEM | Implementation | Solar PV | 55.708 |  | 2021-01-11 | 2021-01-12 | 1 | 2021-01-19 | 5 | 2021-02-02 | 10 | 2021-02-02 | 2021-03-19 | 32 | 2021-03-24 | 2021-03-25 | 1 | 2021-03-25 | [8 empty] | 2021-09-15 | 2021-09-21 | 4 | 2021-09-21 | 2021-09-23 | 2 |  |  |  |  | 2021-01-11 | 2021-02-02 | 15
89 | PGE | 95442 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.409 |  | 2021-01-11 | 2021-01-16 | 4 | 2021-01-16 | 4 | 2021-02-01 | 9 | [15 empty] | 2021-01-16 | 2021-01-16 | 0 | 2021-01-16 | 2021-01-19 | 0 | [5 empty] | 0 | [5 empty] | 2021-02-01 | 2021-02-01 | 0 | [15 empty] | 2021-02-01 | 2021-02-01 | 0 | 2021-02-01 |  | 2021-02-01 | 0
90 | PGE | 95448 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.714 |  | 2021-01-11 | 2021-01-19 | 5 | 2021-02-05 | 18 | 2021-02-22 | 10 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | 2021-02-08 | 1 | [5 empty] | 0 | [5 empty] | 2021-02-22 | 2021-03-03 | 7 | [15 empty] | 2021-02-22 | 2021-02-23 | 1 | 2021-03-03 |  | 2021-03-06 | 2
91 | PGE | 95521 | Non-NEM | Non-Export | Implementation | Storage | 280 |  | 2021-01-11 | 2021-01-12 | 1 | 2021-02-03 | 16 | 2021-03-01 | 17 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-05-27 | 63 |  |  |  |  | 2021-01-11 | 0
92 | PGE | 93308 | NEM | NEMMT | Implementation | Solar PV | 663.66 |  | 2021-01-11 | 2021-01-26 | 10 | 2021-02-19 | 27 | 2021-03-11 | 14 | 2021-03-11 | 2021-04-08 | 20 | 2021-04-08 | 2021-05-11 | 23 | 2021-05-11 | 2021-05-11 |  | 2021-05-11 | 2021-08-05 | 63 | 2021-05-11 |  |  | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | 2021-11-03 | 63 |  |  |  |  | 2021-01-11 | 2021-02-03 | 16 | 2021-12-31 | 2022-01-03 | 2022-01-03 | 1
93 | PGE | 95210 | NEM | EXPNEM | Commercial | Solar PV | 95.8 |  | 2021-01-11 | 2021-01-12 | 1 | 2021-01-13 | 2 | 2021-01-29 | 11 | [15 empty] | 2021-01-29 | 2021-02-14 | 10 | 2021-02-14 | 2021-02-18 | 2 | [5 empty] | 0 | [5 empty] | 2021-05-07 | 2021-05-18 | 7 | [15 empty] | 2021-05-07 | 2021-05-10 | 1 | 2021-05-18 |  | 2021-05-21 | 3
94 | PGE | 93308 | NEM | EXPNEM | Implementation | Solar PV | 3858.508 |  | 2021-02-16 | 2021-02-17 | 1 | 2021-03-03 | 11 | [5 empty] | 2021-03-04 | 2021-04-07 | 24 | 2021-04-07 | 2021-04-07 | 0 | 2021-05-03 | 2021-07-12 | 48 | 2021-04-07 | 2021-04-08 | 1 | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13 | 2021-08-16 | 24 |  |  |  |  | 2021-02-16 | 0 | [11 empty] | 2021-09-01 | 2022-03-07 15:43 | 134
95 | PGE | 93210 | NEM | EXPNEM | Implementation | Solar PV | 520 |  | 2021-02-01 | 2021-02-12 | 9 | 2021-02-25 | 17 | 2021-03-03 | 4 | 2021-03-03 | 2021-03-31 | 20 | [12 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | 2021-06-04 | 46 | [5 empty] | 0 | [8 empty] | 2021-11-10 | 2021-11-23 | 8
96 | PGE | 93705 | NEM | EXPNEM | Commercial | Solar PV | 31.404 |  | 2021-01-28 | 2021-01-28 | 0 | 2021-02-04 | 5 | 2021-02-11 | 5 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-11 | 0 | [5 empty] | 0 | [5 empty] | 2021-08-23 | 2021-09-02 | 8 | [15 empty] | 2021-08-23 | 2021-08-24 | 1 | 2021-09-02 |  | 2021-09-13 | 6
97 | PGE | 95304 | NEM | EXPNEM | Commercial | Solar PV | 200 |  | 2021-01-21 | 2021-01-22 | 1 | 2021-01-22 | 1 | 2021-02-12 | 15 | [15 empty] | 2021-02-12 | 2021-02-12 | 0 | 2021-02-12 | 2021-02-17 | 2 | [5 empty] | 0 | [5 empty] | 2021-06-02 | 2021-06-10 | 6 | [15 empty] | 2021-06-02 | 2021-06-03 | 1 | 2021-06-10 |  | 2021-06-17 | 5
98 | PGE | 95377 | NEM | EXPNEM | Commercial | Solar PV | 250 |  | 2021-01-27 | 2021-01-28 | 1 | 2021-01-29 | 2 | 2021-02-14 | 10 | [15 empty] | 2021-02-14 | 2021-02-14 | 0 | 2021-02-14 | 2021-02-18 | 2 | [5 empty] | 0 | [5 empty] | 2021-08-10 | 2021-08-17 | 5 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-17 |  | 2021-08-24 | 5
99 | PGE | 93611 | NEM | EXPNEM | Commercial | Solar PV | 127.683 |  | 2021-02-11 | 2021-02-12 | 1 | 2021-02-16 | 2 | 2021-02-20 | 3 | [15 empty] | 2021-02-20 | 2021-02-20 | 0 | 2021-02-20 | 2021-02-24 | 2 |  |  |  |  | 2021-02-11 | 0 | [5 empty] | 2021-07-22 | 2021-08-11 | 14 | [15 empty] | 2021-07-22 | 2021-08-05 | 10 | 2021-08-11 |  | 2021-08-18 | 5
100 | PGE | 93727 | NEM | EXPNEM | Commercial | Solar PV, Storage | 94.803 |  | 2021-01-14 | 2021-01-15 | 1 | 2021-02-18 | 23 | 2021-03-01 | 7 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-03 | 2 | [5 empty] | 0 | [5 empty] | 2021-10-11 | 2021-12-02 | 35 | [15 empty] | 2021-10-11 | 2021-11-24 | 31 | 2021-12-02 |  | 2021-12-14 | 8
101 | PGE | 94508 | NEM | EXPNEM | Commercial | Solar PV | 33.06 |  | 2021-02-03 | 2021-02-04 | 1 | 2021-02-04 | 1 | 2021-02-18 | 9 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-05-26 | 69 | [5 empty] | 0 | [5 empty] | 2021-06-08 | 2021-07-22 | 31 | [15 empty] | 2021-06-08 | 2021-07-22 | 31 | 2021-07-22 |  | 2021-07-28 | 4
102 | PGE | 95370 | NEM | EXPNEM | Commercial | Solar PV | 63.135 |  | 2021-02-11 | 2021-02-12 | 1 | 2021-02-16 | 2 | 2021-03-03 | 11 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-08 | 3 | [5 empty] | 0 | [5 empty] | 2021-05-12 | 2021-05-19 | 5 | [15 empty] | 2021-05-12 | 2021-05-13 | 1 | 2021-05-19 |  | 2021-05-26 | 5
103 | PGE | 95340 | NEM | EXPNEM | Commercial | Solar PV | 770 |  | 2021-02-18 | 2021-02-23 | 3 | 2021-02-23 | 3 | 2021-03-01 | 4 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-11 | 8 | [5 empty] | 0 | [5 empty] | 2021-12-16 | 2021-12-28 | 8 | 2021-05-18 | 2021-08-16 | 62 |  |  |  | 2021-08-16 | 2021-12-08 | 78 | [6 empty] | 2021-12-16 | 2021-12-17 | 1 | 2021-12-28 |  | 2021-12-30 | 2
104 | PGE | 94597 | NEM | EXPNEM | Withdrawn | Solar PV | 31.062 |  | 2021-02-04 | 2021-02-16 | 7 | 2021-02-16 | 7 | 2021-03-12 | 18 | [15 empty] | 2021-03-12 | 2021-03-12 | 0 | 2021-03-12 | 2021-03-12 | 0 | [5 empty] | 0 | [5 empty] | 2021-07-19 | [17 empty] | 2021-07-19 | 2021-07-27 | 6
105 | PGE | 95363 | NEM | EXPNEM | Withdrawn | Solar PV | 316.555 |  | 2021-01-28 | 2021-02-03 | 4 | 2021-02-17 | 13 | 2021-03-08 | 13 | [15 empty] | 2021-03-08 | 2021-03-17 | 7 | 2021-03-17 | 2021-03-18 | 1 |  |  |  |  | 2021-01-28 | 0
106 | PGE | 93648 | NEM | EXPNEM | Commercial | Solar PV | 103.592 |  | 2021-02-26 | 2021-03-01 | 1 | 2021-03-04 | 4 | 2021-03-23 | 13 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | 2021-03-24 | 1 |  |  |  |  | 2021-02-26 | 2021-05-28 | 65 |  |  |  |  | 2021-08-13 | 2021-08-20 | 5 | [15 empty] | 2021-08-13 | 2021-08-13 | 0 | 2021-08-20 |  | 2021-08-27 | 5
107 | PGE | 95203 | NEM | EXPNEM | IA in Progress | Solar PV | 40.733 |  | 2021-02-12 | 2021-02-16 | 1 | 2021-02-16 | 1 | 2021-03-02 | 10 | [15 empty] | 2021-03-02 | 2021-03-03 | 1 | 2021-03-03 | 2021-03-26 | 17 | [5 empty] | 0 | [5 empty] | 2022-02-07 | 2022-02-17 | 8 | 2021-07-06 | 2021-12-07 | 106 |  |  |  | 2022-03-18 |  | 18 | [6 empty] | 2022-02-07 | 2022-02-07 | 0 | 2022-02-17 | 2022-02-23 |  | 3 |  |  | 259
108 | PGE | 95492 | NEM | EXPNEM | Withdrawn | Solar PV | 260.887 |  | 2021-02-26 | 2021-03-02 | 2 | 2021-03-09 | 7 | 2021-03-29 | 14 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-03-29 | 0 |  |  |  |  | 2021-02-26 | 0
109 | PGE | 93727 | NEM | EXPNEM | Commercial | Solar PV, Storage | 94.803 |  | 2021-01-14 | 2021-01-15 | 1 | 2021-02-01 | 11 | 2021-02-11 | 8 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-16 | 2 |  |  |  |  | 2021-01-14 | 2021-01-28 | 9 |  |  |  |  | 2021-07-14 | 2021-09-29 | 54 | 2021-04-09 | 2021-05-05 | 18 |  |  |  | 2021-05-05 | 2021-05-05 | 1 | [6 empty] | 2021-07-14 | 2021-09-22 | 49 | 2021-09-29 |  | 2021-10-06 | 5
110 | PGE | 95215 | NEM | EXPNEM | Commercial | Solar PV | 86.965 |  | 2021-01-26 | 2021-01-26 | 0 | 2021-01-28 | 2 | 2021-08-18 | 141 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-02 | 8 |  |  |  |  | 2021-01-26 | 2021-02-03 | 6 |  |  |  |  | 2021-08-21 | 2021-08-30 | 5 | 2021-05-18 | 2021-11-22 | 130 |  |  |  | 2021-11-12 |  | 15 | [6 empty] | 2021-08-21 | 2021-08-23 | 0 | 2021-08-30 | 2021-09-07 | 2022-03-30 | 5 |  |  | 156
111 | PGE | 95023 | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-01-20 | 2021-01-28 | 6 | 2021-01-29 | 7 | 2021-01-29 | 0 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-01 | 4 |  |  |  |  | 2021-01-20 | 2021-02-05 | 12 |  |  |  |  | 2021-07-08 | 2021-07-23 | 11 | [15 empty] | 2021-07-08 | 2021-07-19 | 7 | 2021-07-23 |  | 2021-07-23 | 0
112 | PGE | 93307 | NEM | EXPNEM | Commercial | Solar PV | 69.6 |  | 2021-01-14 | 2021-01-28 | 9 | 2021-01-28 | 9 | 2021-02-18 | 14 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-23 | 23 |  |  |  |  | 2021-01-14 | 2021-02-05 | 15 |  |  |  |  | 2021-05-11 | 2021-05-19 | 6 | [15 empty] | 2021-05-11 | 2021-05-12 | 1 | 2021-05-19 |  | 2021-05-19 | 0
113 | PGE | 94806 | NEM | EXPNEM | Commercial | Solar PV | 164.17 |  | 2021-01-28 | 2021-01-29 | 1 | 2021-02-01 | 2 | 2021-03-15 | 29 | [15 empty] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | 2021-12-06 | 184 |  |  |  |  | 2021-01-28 | 2021-02-05 | 6 |  |  |  |  | 2022-01-31 | 2022-02-08 | 6 | [15 empty] | 2022-01-31 | 2022-02-01 | 1 | 2022-02-08 |  | 2022-02-11 | 3
114 | PGE | 95369 | NEM | EXPNEM | Commercial | Solar PV | 185.596 |  | 2021-02-03 | 2021-02-04 | 1 | 2021-02-10 | 5 | 2021-02-25 | 10 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-03 | 4 |  |  |  |  | 2021-02-03 | 2021-02-09 | 4 |  |  |  |  | 2021-05-11 | 2021-05-20 | 7 | [15 empty] | 2021-05-11 | 2021-05-12 | 1 | 2021-05-20 |  | 2021-05-27 | 5
115 | PGE | 94566 | NEM | EXPNEM | Commercial | Solar PV | 79.852 |  | 2021-01-28 | 2021-02-08 | 7 | 2021-02-08 | 7 | 2021-03-03 | 16 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-04 | 1 |  |  |  |  | 2021-01-28 | 2021-02-09 | 8 |  |  |  |  | 2022-02-08 | 2022-02-15 | 5 | 2021-07-01 | 2021-10-21 | 78 |  |  |  | 2021-11-16 | 2022-01-11 | 37 | [6 empty] | 2022-02-08 | 2022-02-08 | 0 | 2022-02-15 |  | 2022-02-16 | 1
116 | PGE | 93625 | NEM | EXPNEM | Implementation | Solar PV | 66.6 |  | 2021-01-28 | 2021-02-05 | 6 | 2021-02-10 | 9 | 2021-02-17 | 4 | [15 empty] | 2021-02-17 | 2021-02-17 | 0 | 2021-02-17 | 2021-03-16 | 19 |  |  |  |  | 2021-01-28 | 2021-02-09 | 8 | [7 empty] | 2021-09-20 | 2022-02-03 | 94
117 | PGE | 93446 | NEM | EXPNEM | Commercial | Solar PV | 48.582 |  | 2021-02-03 | 2021-02-04 | 1 | 2021-02-14 | 7 | 2021-03-05 | 13 | [15 empty] | 2021-03-05 | 2021-03-05 | 0 | 2021-03-05 | 2021-03-09 | 2 |  |  |  |  | 2021-02-03 | 2021-02-16 | 8 |  |  |  |  | 2021-05-06 | 2021-05-17 | 7 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-17 |  | 2021-05-20 | 3
118 | PGE | 95236 | NEM | EXPNEM | IA in Progress | Solar PV | 147.625 |  | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 0 | 2021-02-11 | 12 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-22 | 6 |  |  |  |  | 2021-01-26 | 2021-03-01 | 23
119 | PGE | 95632 | NEM | EXPNEM | Commercial | Solar PV | 175 |  | 2021-01-25 | 2021-01-26 | 1 | 2021-01-28 | 3 | 2021-02-12 | 11 | [15 empty] | 2021-02-12 | 2021-02-12 | 0 | 2021-02-12 | 2021-02-17 | 2 |  |  |  |  | 2021-01-25 | 2021-03-12 | 33 |  |  |  |  | 2021-05-24 | 2021-06-03 | 7 | [15 empty] | 2021-05-24 | 2021-05-26 | 2 | 2021-06-03 |  | 2021-06-09 | 4
120 | PGE | 95650 | NEM | EXPNEM | IA in Progress | Solar PV | 32.77 |  | 2021-01-28 | 2021-01-29 | 1 | 2021-02-04 | 5 | 2021-03-04 | 19 | [15 empty] | 2021-03-04 | 2021-03-04 | 0 | 2021-03-04 | 2021-03-11 | 5 |  |  |  |  | 2021-01-29 | 2021-03-17 | 32 |  |  |  |  | 2022-03-30 | [17 empty] | 2022-03-30 | 2022-03-30 | 0
121 | PGE | 95301 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-01-29 | 2021-02-09 | 7 | 2021-02-10 | 8 | 2021-03-02 | 13 | [15 empty] | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | 2021-03-05 | 3 |  |  |  |  | 2021-01-29 | 2021-04-29 | 63 |  |  |  |  | 2021-03-05 | 2021-05-07 | 45 | [15 empty] | 2021-03-05 | 2021-05-07 | 45 | 2021-05-07 |  | 2021-05-07 | 0
122 | PGE | 93460 | NEM | EXPNEM | Commercial | Solar PV | 47.82 |  | 2021-01-15 | 2021-01-19 | 1 | 2021-01-28 | 8 | 2021-02-02 | 3 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-18 | 11 | [5 empty] | 0 | [5 empty] | 2021-02-22 | 2021-02-26 | 4 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-26 |  | 2021-03-03 | 3
123 | PGE | 93726 | NEM | EXPNEM | Commercial | Solar PV | 56.866 |  | 2021-01-14 | 2021-01-15 | 1 | 2021-01-29 | 10 | 2021-02-11 | 9 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-03-11 | 19 |  |  |  |  | 2021-01-14 | 2021-01-28 | 9 |  |  |  |  | 2021-03-15 | 2021-03-24 | 7 | [15 empty] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-24 |  | 2021-03-25 | 1
124 | PGE | 94577 | NEM | EXPNEM | Commercial | Solar PV | 31.024 |  | 2021-02-02 | 2021-02-03 | 1 | 2021-02-03 | 1 | 2021-02-26 | 16 | [15 empty] | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-03-15 | 11 | [5 empty] | 0 | [5 empty] | 2021-03-18 | 2021-03-24 | 4 | [15 empty] | 2021-03-18 | 2021-03-19 | 1 | 2021-03-24 |  | 2021-03-25 | 1
125 | PGE | 95451 | NEM | EXPNEM | Commercial | Solar PV | 68.358 |  | 2021-01-13 | 2021-01-28 | 10 | 2021-01-28 | 10 | 2021-02-18 | 14 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-10 | 14 | [5 empty] | 0 | [5 empty] | 2021-03-13 | 2021-03-25 | 8 | [15 empty] | 2021-03-13 | 2021-03-15 | 0 | 2021-03-25 |  | 2021-03-25 | 0
126 | PGE | 95206 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-02-11 | 2021-02-16 | 2 | 2021-03-09 | 17 | 2021-03-24 | 11 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-03-26 | 2 |  |  |  |  | 2021-02-17 | 0 | [5 empty] | 2021-03-29 | 2021-04-02 | 4 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-04-02 |  | 2021-04-05 | 1
128 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 70.479 |  | 2021-01-18 | 2021-01-20 | 1 | 2021-03-09 | 34 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-03-31 | 3 |  |  |  |  | 2021-03-02 | 2021-03-12 | 8 |  |  |  |  | 2021-04-02 | 2021-04-12 | 6 | [15 empty] | 2021-04-02 | 2021-04-05 | 1 | 2021-04-12 |  | 2021-04-19 | 5
131 | PGE | 95120 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 33.05 |  | 2021-01-14 | 2021-01-25 | 6 | 2021-01-25 | 6 | 2021-02-04 | 8 | [15 empty] | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | 2021-02-04 | 8 | [5 empty] | 0
134 | PGE | 95070 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 40.356 |  | 2021-02-11 | 2021-02-22 | 6 | 2021-03-11 | 19 | 2021-03-17 | 4 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-02-26 | 4 | [5 empty] | 0 | [5 empty] | 2021-08-19 | 2021-08-19 | 0 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 |  | 2021-08-19 | 0
135 | PGE | 95472 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.2 |  | 2021-01-28 | 2021-02-10 | 9 | 2021-03-17 | 33 | 2021-03-25 | 6 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-21 | 2 | [5 empty] | 0 | [5 empty] | 2022-02-22 | 2022-02-22 | 0 | 2021-06-30 | 2021-11-01 | 86 |  |  |  | 2021-12-27 | 2022-02-14 | 35 | [6 empty] | 2022-02-22 | 2022-02-22 | 0 | 2022-02-22 |  | 2022-02-23 | 1
136 | PGE | 94941 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.356 |  | 2021-03-23 | 2021-04-06 | 10 | 2021-04-06 | 10 | 2021-04-07 | 1 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | 2021-03-23 | 0 | [5 empty] | 0 |  |  | 2021-04-29 | 2021-04-29 | 0 | 2021-04-23 | 2021-07-27 | 65 | [15 empty] | 2021-04-23 | 2021-07-20 | 60 | 2021-07-27 |  | 2021-07-27 | 0
139 | PGE | 93619 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 |  | 2021-02-04 | 2021-02-10 | 4 | 2021-04-14 | 48 | 2021-04-23 | 7 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-29 | 24 | [5 empty] | 0 | [5 empty] | 2021-04-23 | 2021-04-24 | 0 | [15 empty] | 2021-04-23 | 2021-04-24 | 0 | 2021-04-24 |  | 2021-04-27 | 1
140 | PGE | 95691 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.8 |  | 2021-03-30 | 2021-04-09 | 8 | 2021-05-21 | 38 | 2021-05-26 | 3 | [15 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-03-30 | 0 | [5 empty] | 0 | [5 empty] | 2021-05-26 | 2021-05-26 | 0 | [15 empty] | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 |  | 2021-05-27 | 1
141 | PGE | 94062 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 53.626 |  | 2021-02-11 | 2021-02-22 | 6 | 2021-03-11 | 19 | 2021-03-22 | 7 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-01 | 5 |  |  |  |  | 2021-04-22 | 2021-05-07 | 11 |  |  |  |  | 2022-03-07 | 2022-03-08 | 1 | 2021-06-10 | 2021-09-13 | 65 |  |  |  | 2021-10-06 | 2021-11-15 | 27 | [6 empty] | 2022-03-07 | 2022-03-08 | 1 | 2022-03-08 |  | 2022-03-08 | 0
144 | PGE | 94507 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 39.988 |  | 2021-02-05 | 2021-02-21 | 9 | 2021-03-16 | 26 | 2021-03-24 | 6 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-16 | 0 |  |  |  |  | 2021-05-19 | 2021-05-28 | 7 |  |  |  |  | 2021-03-24 | 2021-06-25 | 66 | [15 empty] | 2021-03-24 | 2021-06-15 | 58 | 2021-06-25 |  | 2021-06-28 | 1
145 | PGE | 94549 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 39.857 |  | 2021-01-15 | 2021-01-25 | 5 | 2021-01-25 | 5 | 2021-01-26 | 1 | [15 empty] | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | 2021-01-28 | 3 | [5 empty] | 0 | [5 empty] | 2021-01-28 | 2021-01-28 | 0 | [15 empty] | 2021-01-28 | 2021-01-28 | 0 | 2021-01-28 |  | 2021-01-30 | 1
146 | PGE | 95961 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2020-12-29 | 2021-01-12 | 9 | 2021-01-28 | 20 | 2021-02-02 | 3 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-03 | 1 | [5 empty] | 0 | [5 empty] | 2021-02-11 | 2021-02-11 | 0 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 |  | 2021-02-17 | 3
147 | PGE | 94949 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 |  | 2021-01-21 | 2021-02-03 | 9 | 2021-02-03 | 9 | 2021-02-09 | 4 | [15 empty] | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | 2021-02-09 | 0 | [5 empty] | 0 | [5 empty] | 2021-02-12 | 2021-02-12 | 0 | [15 empty] | 2021-02-12 | 2021-02-12 | 0 | 2021-02-12 |  | 2021-02-17 | 2
148 | PGE | 95070 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-01-15 | 2021-01-28 | 8 | 2021-01-28 | 8 | 2021-02-08 | 7 | [15 empty] | 2021-01-28 | 2021-01-28 | 0 | 2021-01-28 | 2021-02-08 | 7 | [5 empty] | 0 | [5 empty] | 2021-02-08 | 2021-02-16 | 5 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-16 |  | 2021-02-17 | 1
150 | PGE | 94556 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-02-11 | 2021-02-23 | 7 | 2021-02-23 | 7 | 2021-02-26 | 3 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-02-23 | 0 | [5 empty] | 0 | [5 empty] | 2021-02-26 | 2021-02-28 | 0 | [15 empty] | 2021-02-26 | 2021-02-28 | 0 | 2021-02-28 |  | 2021-03-06 | 5
152 | PGE | 94525 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 |  | 2021-02-16 | 2021-03-01 | 9 | 2021-03-01 | 9 | 2021-03-02 | 1 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-03 | 2 | [5 empty] | 0 | [5 empty] | 2021-03-04 | 2021-03-04 | 0 | [15 empty] | 2021-03-04 | 2021-03-04 | 0 | 2021-03-04 |  | 2021-03-06 | 1
153 | PGE | 93422 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 |  | 2021-02-08 | 2021-02-23 | 10 | 2021-02-23 | 10 | 2021-03-03 | 6 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-02 | 5 | [5 empty] | 0 | [5 empty] | 2021-03-08 | 2021-03-08 | 0 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 |  | 2021-03-11 | 3
154 | PGE | 93463 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 |  | 2021-02-08 | 2021-02-23 | 10 | 2021-02-23 | 10 | 2021-03-03 | 6 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-03 | 6 | [5 empty] | 0 | [5 empty] | 2021-03-08 | 2021-03-08 | 0 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 |  | 2021-03-11 | 3
155 | PGE | 95688 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-02-18 | 2021-03-03 | 9 | 2021-03-03 | 9 | 2021-03-04 | 1 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-08 | 3 |  |  |  |  | 2021-02-18 | 2021-03-03 | 9 |  |  |  |  | 2021-03-08 | 2021-03-08 | 0 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 |  | 2021-03-13 | 4
157 | PGE | 94010 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.92 |  | 2021-02-11 | 2021-02-23 | 7 | 2021-02-25 | 9 | 2021-03-09 | 8 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-02 | 3 | [5 empty] | 0 | [5 empty] | 2021-03-09 | 2021-03-10 | 1 | [15 empty] | 2021-03-09 | 2021-03-10 | 1 | 2021-03-10 |  | 2021-03-13 | 2
159 | PGE | 94583 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-02-11 | 2021-02-23 | 7 | 2021-02-23 | 7 | 2021-02-25 | 2 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-08 | 9 | [5 empty] | 0 | [5 empty] | 2021-03-11 | 2021-03-11 | 0 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 |  | 2021-03-13 | 1
161 | PGE | 95070 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.337 |  | 2021-01-25 | 2021-02-08 | 10 | 2021-02-08 | 10 | 2021-02-26 | 13 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-03-02 | 15 | [5 empty] | 0 | [5 empty] | 2021-03-17 | 2021-03-17 | 0 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 |  | 2021-03-19 | 2
162 | PGE | 94558 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.741 |  | 2021-02-08 | 2021-02-23 | 10 | 2021-02-23 | 10 | 2021-03-01 | 4 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-02 | 5 | [5 empty] | 0 | [5 empty] | 2021-03-17 | 2021-03-17 | 0 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 |  | 2021-03-19 | 2
163 | PGE | 95110 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-02-23 | 2021-03-06 | 8 | 2021-03-06 | 8 | 2021-03-08 | 0 | [15 empty] | 2021-03-06 | 2021-03-06 | 0 | 2021-03-06 | 2021-03-23 | 11 | [5 empty] | 0 | [5 empty] | 2021-03-23 | 2021-03-23 | 0 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 |  | 2021-03-27 | 3
165 | PGE | 94566 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.646 |  | 2021-02-08 | 2021-02-16 | 5 | 2021-03-02 | 15 | 2021-03-06 | 3 | [15 empty] | 2021-03-06 | 2021-03-06 | 0 | 2021-03-06 | 2021-03-10 | 2 | [5 empty] | 0 | [5 empty] | 2021-03-24 | 2021-03-25 | 1 | [15 empty] | 2021-03-24 | 2021-03-25 | 1 | 2021-03-25 |  | 2021-03-30 | 3
166 | PGE | 95973 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.393 |  | 2021-01-14 | 2021-01-23 | 5 | 2021-02-25 | 28 | 2021-03-16 | 13 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-16 | 0 | [5 empty] | 0 | [5 empty] | 2021-03-29 | 2021-03-29 | 0 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 |  | 2021-03-30 | 1
167 | PGE | 94903 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.75 |  | 2021-03-01 | 2021-03-13 | 9 | 2021-03-13 | 9 | 2021-03-16 | 1 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-29 | 10 | [5 empty] | 0 | [5 empty] | 2021-03-29 | 2021-03-29 | 0 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 |  | 2021-04-03 | 4
168 | PGE | 94070 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 |  | 2021-03-01 | 2021-03-13 | 9 | 2021-03-13 | 9 | 2021-03-23 | 6 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-29 | 10 | [5 empty] | 0 | [5 empty] | 2021-03-29 | 2021-03-29 | 0 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 |  | 2021-04-03 | 4
170 | PGE | 95370 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 46.533 |  | 2021-03-02 | 2021-03-13 | 8 | 2021-03-13 | 8 | 2021-03-24 | 7 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-31 | 12 | [5 empty] | 0 | [5 empty] | 2021-03-31 | 2021-03-31 | 0 | [15 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 |  | 2021-04-03 | 2
171 | PGE | 93422 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-03-01 | 2021-03-13 | 9 | 2021-03-13 | 9 | 2021-03-23 | 6 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-29 | 10 | [5 empty] | 0 | [5 empty] | 2021-03-31 | 2021-04-01 | 1 | [15 empty] | 2021-03-31 | 2021-04-01 | 1 | 2021-04-01 |  | 2021-04-03 | 1
173 | PGE | 94010 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.36 |  | 2021-03-15 | 2021-03-27 | 9 | 2021-03-27 | 9 | 2021-04-03 | 5 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | 2021-03-30 | 1 | [5 empty] | 0 | [5 empty] | 2021-04-03 | 2021-04-05 | 0 | [15 empty] | 2021-04-03 | 2021-04-05 | 0 | 2021-04-05 |  | 2021-04-10 | 4
176 | PGE | 94957 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 |  | 2021-03-19 | 2021-04-02 | 10 | 2021-04-02 | 10 | 2021-04-08 | 4 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-03-19 | 0 | [5 empty] | 0 | [5 empty] | 2021-04-08 | 2021-04-08 | 0 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 |  | 2021-04-10 | 1
177 | PGE | 94904 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.699 |  | 2021-03-24 | 2021-04-07 | 10 | 2021-04-07 | 10 | 2021-04-09 | 2 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-03-24 | 0 | [5 empty] | 0 | [5 empty] | 2021-04-09 | 2021-04-09 | 0 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 |  | 2021-04-10 | 0
178 | PGE | 95765 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-02-08 | 2021-02-16 | 5 | 2021-03-17 | 26 | 2021-03-22 | 3 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-03-24 | 2 | [5 empty] | 0 | [5 empty] | 2021-04-12 | 2021-04-12 | 0 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 |  | 2021-04-13 | 1
179 | PGE | 94010 | NEM | NEMMT | Implementation | FUCE, Storage | 1400 |  | 2021-02-10 | 2021-02-22 | 7 | 2021-03-21 | 26 | 2021-04-08 | 13 | 2021-04-08 | 2021-05-06 | 20 | [12 empty] | 2021-05-20 | 2021-06-04 | 10 | 2021-06-04 | 2021-10-08 | 88 |  |  |  |  | 2021-03-21 | 2021-03-25 | 3 |  |  |  |  | 2021-12-22 | 2021-12-28 | 4 | 2022-01-13 |  | 64 | [12 empty] | 2021-12-22 | 2021-12-23 | 1 | 2021-12-28 | 2021-12-31 |  | 3 |  |  | 225
180 | PGE | 95422 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-01-21 | 2021-01-25 | 2 | 2021-03-03 | 28 | 2021-03-22 | 13 | [15 empty] | 2021-03-22 | 2021-03-23 | 1 | 2021-03-23 | 2021-07-09 | 76 |  |  |  |  | 2021-01-21 | 2021-04-02 | 50 |  |  |  |  | 2022-03-28 | [17 empty] | 2022-03-28 | 2022-03-30 | 2 |  |  |  |  | 2022-03-17 |  | 0
181 | PGE | 95476 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 46.538 |  | 2021-03-10 | 2021-03-24 | 10 | 2021-03-24 | 10 | 2021-04-12 | 13 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-03-30 | 4 | [5 empty] | 0 |  | 2021-03-24 | 2021-03-24 | 2021-03-24 | 0 | 2021-06-07 | 2021-06-15 | 6 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-15 |  | 2021-06-15 | 0
182 | PGE | 94103 | Non-NEM | Continuous Uncompensated Export | Withdrawn | Solar PV | 625 |  | 2021-02-19 | 2021-02-22 | 1 | 2021-02-24 | 3 | 2021-03-15 | 13 | [15 empty] | 2021-03-15 | 2021-03-31 | 12 | 2021-03-31 | [7 empty] | 0 |  | 2021-03-31
184 | PGE | 94588 | NEM | EXPNEM | Implementation | Solar PV | 783.3 |  | 2021-03-18 | 2021-04-01 | 10 | 2021-05-28 | 51 | 2021-07-29 | 42 | [15 empty] | 2021-07-29 | 2021-07-29 | 0 | 2021-07-29 | 2021-09-07 | 27 |  |  |  |  | 2021-03-18 | 2021-06-16 | 63
185 | PGE | 94588 | NEM | EXPNEM | Implementation | Solar PV | 333.2 |  | 2021-03-18 | 2021-04-01 | 10 | 2021-05-06 | 35 | 2021-07-09 | 44 | [15 empty] | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09 | 2021-09-07 | 41 |  |  |  |  | 2021-03-18 | 2021-06-16 | 63
186 | PGE | 95415 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 109.804 |  | 2021-03-22 | 2021-04-01 | 8 | 2021-09-07 | 118 | 2021-11-12 | 47 | [15 empty] | 2021-11-12 | 2021-11-23 | 7 | 2021-11-23 | 2021-11-23 | 0 | [5 empty] | 0 | [8 empty] | 2021-07-16 | 2021-11-18 | 87
187 | PGE | 94601 | NEM | EXPNEM | Commercial | Solar PV | 98.136 |  | 2021-03-25 | 2021-04-05 | 7 | 2021-10-15 | 143 | 2021-10-19 | 2 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2022-02-03 | 73 | [5 empty] | 0 | [5 empty] | 2022-03-02 | 2022-03-08 | 4 | [15 empty] | 2022-03-02 | 2022-03-02 | 0 | 2022-03-08 |  | 2022-03-11 | 3
188 | PGE | 94954 | NEM | EXPNEM | Implementation | Solar PV | 240 |  | 2021-03-29 | 2021-04-06 | 6 | 2021-05-10 | 30 | 2021-07-16 | 47 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-16 | 2021-08-12 | 19 |  |  |  |  | 2021-03-29 | 2021-08-13 | 97
189 | PGE | 93622 | NEM | EXPNEM | Implementation | Solar PV | 830 |  | 2021-03-26 | 2021-04-07 | 8 | 2021-08-04 | 91 | 2021-08-24 | 14 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | 2021-10-11 | 33 | [5 empty] | 0
190 | PGE | 95928 | NEM | EXPNEM | Commercial | Solar PV | 36.913 |  | 2021-03-31 | 2021-04-07 | 5 | 2021-07-07 | 68 | 2021-07-26 | 13 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-07-27 | 1 |  |  |  |  | 2021-03-31 | 2021-07-23 | 80 |  |  |  |  | 2021-07-27 | 2021-08-02 | 4 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-08-02 |  | 2021-08-02 | 0
191 | PGE | 94611 | NEM | EXPNEM | Application Review in Progress | Solar PV | 150.795 |  | 2021-03-31 | 2021-04-12 | 8 | [30 empty] | 0
192 | PGE | 94577 | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-01-15 | 2021-01-19 | 1 | 2021-07-29 | 135 | 2021-09-07 | 27 | [15 empty] | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 | 2021-09-15 | 4 |  |  |  |  | 2021-08-09 | 2021-08-19 | 8 |  |  |  |  | 2021-09-30 | 2021-12-03 | 43 | [15 empty] | 2021-09-30 | 2021-12-02 | 42 | 2021-12-03 |  | 2021-12-09 | 4
193 | PGE | 95370 | NEM | EXPNEM | Application Review in Progress | Solar PV | 35.713 |  | 2021-01-19 | 2021-01-20 | 1 | [30 empty] | 0
194 | PGE | 95982 | NEM | EXPNEM | IA in Progress | Solar PV | 359.184 |  | 2021-01-22 | 2021-01-25 | 1 | 2022-03-04 | 281 | 2022-03-22 | 12 | [15 empty] | 2022-03-22 | 2022-03-23 | 1 | 2022-03-23 | [6 empty] | 2021-01-22 | 0
195 | PGE | 93933 | NEM | EXPNEM | Withdrawn | Solar PV | 86.4 |  | 2021-01-24 | 2021-01-26 | 1 | 2021-07-23 | 126 | 2021-10-11 | 55 | [15 empty] | 2021-10-11 | 2021-10-11 | 0 | 2021-10-11 | [6 empty] | 2021-01-24 | 0
196 | PGE | 95945 | NEM | EXPNEM | Withdrawn | Solar PV | 32.88 |  | 2021-01-19 | 2021-01-26 | 5 | 2021-02-19 | 22 | 2021-05-04 | 52 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | 2021-06-17 | 31 | [5 empty] | 0
197 | PGE | 93309 | NEM | EXPNEM | Commercial | Solar PV | 43.128 |  | 2021-01-27 | 2021-01-27 | 0 | 2021-04-19 | 57 | 2021-04-27 | 6 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-09-01 | 3 |  |  |  |  | 2021-01-27 | 2021-05-28 | 86 |  |  |  |  | 2021-07-26 | 2021-09-30 | 47 | [15 empty] | 2021-07-26 | 2021-09-24 | 43 | 2021-09-30 |  | 2021-10-01 | 1
199 | PGE | 93721 | NEM | EXPNEM | Application Review in Progress | Solar PV | 52.78 |  | 2021-01-28 | 2021-01-29 | 1 | [30 empty] | 0
200 | PGE | 95694 | NEM | EXPNEM | Commercial | Solar PV | 62.5 |  | 2021-01-15 | 2021-02-01 | 10 | 2021-11-29 | 218 | 2021-12-13 | 10 | [15 empty] | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13 | 2022-01-28 | 33 | [5 empty] | 0 | [5 empty] | 2022-01-28 | 2022-02-09 | 8 | [15 empty] | 2022-01-28 | 2022-01-31 | 1 | 2022-02-09 |  | 2022-02-11 | 2
201 | PGE | 95963 | NEM | EXPNEM | Commercial | Solar PV | 30.277 |  | 2021-02-03 | 2021-02-04 | 1 | 2021-06-03 | 84 | 2021-06-18 | 11 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-18 | 2021-06-21 | 1 | [5 empty] | 0 | [5 empty] | 2021-06-22 | 2021-07-12 | 13 | [15 empty] | 2021-06-22 | 2021-07-12 | 13 | 2021-07-12 |  | 2021-07-12 | 0
202 | PGE | 95020 | NEM | EXPNEM | Withdrawn | Solar PV | 299.7 |  | 2021-02-04 | 2021-02-05 | 1 | [29 empty] | 2021-02-04 | 0
203 | PGE | 95002 | NEM | EXPNEM | Application Review in Progress | Solar PV | 44.198 |  | 2021-02-05 | 2021-02-08 | 1 | [30 empty] | 0
204 | PGE | 95602 | NEM | EXPNEM | Implementation | Solar PV | 37.009 |  | 2021-01-28 | 2021-02-09 | 8 | 2021-04-21 | 58 | 2021-04-26 | 3 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-05-14 | 14 |  |  |  |  | 2021-05-19 | 2021-05-28 | 7 |  |  |  |  | 2021-06-16 | 2021-06-30 | 10 | 2021-06-30 | 2021-11-02 | 87 | [12 empty] | 2021-06-16 | 2021-06-24 | 6 | 2021-06-30 | 2021-07-07 |  | 4 |  |  | 111
205 | PGE | 94539 | NEM | EXPNEM | IA in Progress | Solar PV | 114.365 |  | 2021-02-09 | 2021-02-10 | 1 | 2021-08-13 | 130 | 2021-08-24 | 7 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | [7 empty] | 0
206 | PGE | 93612 | NEM | EXPNEM | Implementation | Solar PV | 36.312 |  | 2021-02-01 | 2021-02-10 | 7 | 2021-08-17 | 138 | 2021-08-30 | 9 | [15 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-09-01 | 2 |  |  |  |  | 2021-02-01 | 2021-09-02 | 150 |  |  |  |  | 2021-10-01 | [17 empty] | 2021-10-01 | 2022-03-24 | 119
207 | PGE | 95957 | NEM | EXPNEM | Commercial | Solar PV | 36 |  | 2021-02-16 | 2021-02-17 | 1 | 2021-06-09 | 80 | 2021-06-17 | 6 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-12-06 | 117 |  |  |  |  | 2021-02-16 | 2021-06-16 | 85 |  |  |  |  | 2021-12-08 | 2021-12-22 | 10 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-22 |  | 2021-12-27 | 3
208 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 187.5 |  | 2021-02-04 | 2021-02-17 | 8 | 2021-04-21 | 53 | 2021-05-27 | 26 | [15 empty] | 2021-05-27 | 2021-06-09 | 8 | 2021-06-09 | 2021-06-09 | 0 |  |  |  |  | 2021-02-04 | 2021-05-07 | 65 |  |  |  |  | 2021-06-10 | 2021-06-17 | 5 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-17 |  | 2021-06-17 | 0
209 | PGE | 93306 | NEM | EXPNEM | Commercial | Solar PV | 341.862 |  | 2021-02-15 | 2021-02-18 | 2 | 2021-04-30 | 53 | 2021-05-16 | 10 | 2021-05-16 | 2021-06-14 | 19 | [12 empty] | 2021-06-14 | 2021-06-14 | 0 | 2021-06-14 | 2021-08-30 | 54 |  |  |  |  | 2021-02-15 | 2021-05-10 | 59 |  |  |  |  | 2021-10-06 | 2021-10-28 | 16 | [15 empty] | 2021-10-06 | 2021-10-06 | 0 | 2021-10-28 |  | 2021-11-02 | 3
210 | PGE | 93706 | NEM | EXPNEM | IA in Progress | Solar PV | 38.779 |  | 2021-02-23 | 2021-02-24 | 1 | 2021-11-26 | 192 | 2021-12-14 | 11 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2021-12-15 | 1 |  |  |  |  | 2021-08-18 | 0 | [5 empty] | 2022-02-28 | [17 empty] | 2022-02-28 | 2022-03-10 | 8
211 | PGE | 93725 | NEM | EXPNEM | Commercial | Solar PV | 60 |  | 2021-02-24 | 2021-02-25 | 1 | 2021-06-10 | 75 | 2021-06-17 | 5 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-09-23 | 68 | [5 empty] | 0 | [5 empty] | 2021-10-06 | 2021-11-23 | 33 | [15 empty] | 2021-10-06 | 2021-11-16 | 28 | 2021-11-23 |  | 2021-12-02 | 5
212 | PGE | 94608 | NEM | EXPNEM | Withdrawn | Solar PV | 395.208 |  | 2021-02-12 | 2021-02-27 | 9 | [29 empty] | 2021-02-12 | 0
213 | PGE | 95340 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-02-15 | 2021-03-01 | 9 | 2021-05-03 | 54 | 2021-05-24 | 15 | [15 empty] | 2021-05-24 | 2021-06-10 | 12 | 2021-06-10 | 2021-06-25 | 11 |  |  |  |  | 2021-05-24 | 2021-06-03 | 7 | 2021-08-13 |  |  |  | 2021-07-21 | 2021-09-01 | 30 | [15 empty] | 2021-07-21 | 2021-09-01 | 30 | 2021-09-01 |  | 2021-09-02 | 1
214 | PGE | 95932 | NEM | EXPNEM | Implementation | Solar PV | 240 |  | 2021-02-16 | 2021-03-02 | 10 | 2021-05-04 | 55 | [5 empty] | 2021-05-04 | 2021-06-16 | 30 | 2021-06-16 | 2021-06-16 |  | 2021-06-16 | 2021-08-31 | 55 | 2021-06-16 |  |  | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 | 2021-09-07 | 4 |  |  |  |  | 2021-02-16 | 0 | [8 empty] | 2021-09-27 | 2021-12-29 | 63 |  |  |  | 2022-02-07 | 2022-04-11 | 45
215 | PGE | 93612 | NEM | EXPNEM | IA in Progress | Solar PV | 268.003 |  | 2021-03-01 | 2021-03-04 | 3 | 2021-05-11 | 51 | 2021-06-16 | 25 | [15 empty] | 2021-06-16 | 2021-06-17 | 1 | 2021-06-17 | 2021-06-17 | 0 | [5 empty] | 0 | [8 empty] | 2021-07-26 | 2022-01-07 | 114
216 | PGE | 95449 | NEM | EXPNEM | Implementation | ENGN | 79.788 |  | 2021-02-24 | 2021-03-05 | 7 | 2021-04-21 | 40 | 2021-10-21 | 128 | [15 empty] | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21 | 2021-11-03 | 9 |  |  |  |  | 2021-04-20 | 2021-05-07 | 13 | [7 empty] | 2021-11-29 | 2022-04-04 | 89
217 | PGE | 95240 | NEM | EXPNEM | Study in Progress | Solar PV | 60.455 |  | 2021-03-05 | 2021-03-08 | 1 | 2022-02-07 | 234 | 2022-03-16 | 26 | 2022-03-16 | [25 empty] | 0
218 | PGE | 93630 | NEM | EXPNEM | Commercial | Solar PV | 336 |  | 2021-02-23 | 2021-03-08 | 9 | 2021-05-12 | 56 | 2021-05-25 | 9 | [15 empty] | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-07-06 | 28 | [5 empty] | 0 |  | 2021-06-16 |  |  |  | 2022-03-01 | 2022-03-08 | 5 | 2021-09-01 | 2021-09-13 | 7 |  |  |  | 2021-09-22 | 2022-02-09 | 96 | [6 empty] | 2022-03-01 | 2022-03-01 | 0 | 2022-03-08 |  | 2022-03-14 | 4
219 | PGE | 95920 | NEM | EXPNEM | Withdrawn | Solar PV | 50.848 |  | 2021-02-23 | 2021-03-09 | 10 | 2021-04-27 | 45 | 2021-05-24 | 19 | 2021-05-24 | 2021-06-28 | 24 | 2021-06-28 | 2021-07-22 | 17 | 2021-07-22 | 2021-08-04 | 9 |  |  |  | 2021-08-04 | [12 empty] | 2021-02-23 | 0
220 | PGE | 93314 | NEM | EXPNEM | Implementation | Solar PV | 540 |  | 2021-02-23 | 2021-03-09 | 10 | 2021-05-03 | 49 | 2021-05-20 | 13 | 2021-05-24 | 2021-06-30 | 26 | 2021-07-12 | 2021-08-09 | 20 | 2021-08-09 | 08/10/2021 |  | 2021-08-10 | 2021-11-09 | 66 | 08/10/2021 |  |  | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | 2021-11-24 | 10 | [5 empty] | 0 | [8 empty] | 2022-01-19 | 2022-02-16 | 20 |  |  |  | 2022-03-11 |  | 23
221 | PGE | 94043 | NEM | EXPNEM | Application Review in Progress | Solar PV | 65.56 |  | 2021-03-08 | 2021-03-10 | 2 | [29 empty] | 2021-03-08 | 0
222 | PGE | 95629 | NEM | EXPNEM | Commercial | Solar PV | 47.56 |  | 2021-03-05 | 2021-03-10 | 3 | 2021-06-09 | 67 | 2021-06-17 | 6 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2022-02-16 | 168 | [5 empty] | 0 | [5 empty] | 2022-02-16 | 2022-02-25 | 6 | [15 empty] | 2022-02-16 | 2022-02-16 | 0 | 2022-02-25 |  | 2022-03-01 | 2
224 | PGE | 94133 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-03-09 | 2021-03-11 | 2 | 2021-04-15 | 27 | 2021-09-14 | 105 | [15 empty] | 2021-09-14 | 2021-09-14 | 0 | 2021-09-14 | 2021-10-08 | 18 | [5 empty] | 0 | [5 empty] | 2021-10-18 | 2021-10-27 | 7 | [15 empty] | 2021-10-18 | 2021-10-18 | 0 | 2021-10-27 |  | 2021-11-01 | 3
225 | PGE | 94085 | NEM | EXPNEM | Withdrawn | Solar PV | 323.042 |  | 2021-03-10 | 2021-03-12 | 2 | [29 empty] | 2021-03-10 | 0
226 | PGE | 93454 | NEM | EXPNEM | Commercial | Solar PV | 84.418 |  | 2021-02-26 | 2021-03-12 | 10 | 2021-05-07 | 50 | 2021-07-14 | 46 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-16 | 2 |  |  |  |  | 2021-07-02 | 2021-07-12 | 5 |  |  |  |  | 2021-07-16 | 2021-07-22 | 4 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-22 |  | 2021-07-22 | 0
227 | PGE | 95901 | NEM | EXPNEM | Commercial | Solar PV | 460 |  | 2021-03-01 | 2021-03-13 | 9 | 2021-05-06 | 48 | 2021-06-07 | 21 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-06-08 | 1 |  |  |  |  | 2021-03-01 | 0 | [5 empty] | 2022-02-18 | 2022-03-01 | 6 | 2021-08-16 | 2021-10-11 | 39 |  |  |  | 2021-12-10 | 2022-02-08 | 41 | [6 empty] | 2022-02-18 | 2022-02-22 | 1 | 2022-03-01 |  | 2022-03-02 | 1
228 | PGE | 94089 | NEM | EXPNEM | Commercial | Solar PV | 33.411 |  | 2021-03-11 | 2021-03-15 | 2 | 2021-05-19 | 49 | 2021-06-07 | 12 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-06-11 | 4 | [5 empty] | 0 | [5 empty] | 2021-07-15 | 2021-07-20 | 3 | [15 empty] | 2021-07-15 | 2021-07-16 | 1 | 2021-07-20 |  | 2021-07-27 | 5
229 | PGE | 95131 | NEM | EXPNEM | IA in Progress | Solar PV | 88.013 |  | 2021-03-12 | 2021-03-16 | 2 | 2022-02-03 | 227 | 2022-02-17 | 10 | [15 empty] | 2022-02-17 | 2022-02-17 | 0 | 2022-02-17 | 2022-03-08 | 12 |  |  |  |  | 2021-03-12 | 0
230 | PGE | 93706 | NEM | EXPNEM | Commercial | Solar PV | 287.5 |  | 2021-03-03 | 2021-03-17 | 10 | 2021-04-20 | 34 | 2021-05-10 | 14 | [15 empty] | 2021-05-10 | 2021-05-17 | 5 | 2021-05-17 | 2021-05-17 | 0 |  |  |  |  | 2021-03-03 | 2021-05-05 | 45 |  |  |  |  | 2021-09-10 | 2021-11-01 | 36 | 2021-07-26 | 2021-08-31 | 26 |  |  |  | 2021-09-13 | 2021-01-23 | 3 | [6 empty] | 2021-09-10 | 2021-10-28 | 34 | 2021-11-01 |  | 2021-11-02 | 1
232 | PGE | 95776 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-03-12 | 2021-03-17 | 3 | 2021-11-08 | 168 | 2021-11-22 | 9 | [15 empty] | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22 | 2021-12-20 | 18 |  |  |  |  | 2021-03-12 | 0 | [5 empty] | 2021-12-29 | 2022-01-13 | 11 | [15 empty] | 2021-12-29 | 2022-01-10 | 8 | 2022-01-13 |  | 2022-01-19 | 3
233 | PGE | 93940 | NEM | EXPNEM | Commercial | Solar PV | 42.802 |  | 2021-03-12 | 2021-03-17 | 3 | 2021-07-20 | 90 | 2021-08-02 | 9 | [15 empty] | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | 2021-08-12 | 8 | [5 empty] | 0 | [5 empty] | 2021-08-12 | 2021-08-26 | 10 | [15 empty] | 2021-08-12 | 2021-08-20 | 6 | 2021-08-26 |  | 2021-09-10 | 10
234 | PGE | 95131 | NEM | EXPNEM | IA in Progress | Solar PV | 53.849 |  | 2021-03-12 | 2021-03-17 | 3 | 2022-02-02 | 226 | 2022-02-22 | 13 | [15 empty] | 2022-02-22 | 2022-02-22 | 0 | 2022-02-22 | 2022-03-14 | 14 |  |  |  |  | 2021-03-12 | 0
235 | PGE | 93306 | NEM | EXPNEM | IA in Progress | Solar PV | 548.77 |  | 2021-03-17 | 2021-03-18 | 1 | 2021-04-15 | 21 | 2021-06-04 | 35 | [15 empty] | 2021-06-04 | 2021-06-04 | 0 | 2021-06-04 | 2021-06-18 | 10 |  |  |  |  | 2021-03-17 | 0
236 | PGE | 95035 | NEM | EXPNEM | IA in Progress | Solar PV | 531.086 |  | 2021-03-14 | 2021-03-18 | 3 | 2021-06-03 | 57 | 2021-07-09 | 25 | [15 empty] | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12 | [7 empty] | 0
237 | PGE | 93305 | NEM | EXPNEM | Withdrawn | Solar PV | 500 |  | 2021-03-17 | 2021-03-18 | 1 | [29 empty] | 2021-03-17 | 0
238 | PGE | 95032 | NEM | EXPNEM | Implementation | Solar PV | 335.644 |  | 2021-03-04 | 2021-03-18 | 10 | 2021-05-03 | 42 | 2021-06-21 | 34 | 2021-06-21 | 2021-08-09 | 34 | [12 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-24 | 11 |  |  |  |  | 2021-03-04 | 0
239 | PGE | 95776 | NEM | EXPNEM | Application Review in Progress | Solar PV | 136.1 |  | 2021-03-17 | 2021-03-18 | 1 | [29 empty] | 2021-03-17 | 0
240 | PGE | 95020 | NEM | EXPNEM | Commercial | Solar PV | 299.7 |  | 2021-03-05 | 2021-03-19 | 10 | 2021-06-16 | 72 | 2021-07-26 | 27 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-07-27 | 1 |  |  |  |  | 2021-03-05 | 2021-05-03 | 41 |  |  |  |  | 2022-03-08 | 2022-03-16 | 6 | [15 empty] | 2022-03-08 | 2022-03-08 | 0 | 2022-03-16 |  | 2022-03-18 | 2
241 | PGE | 95365 | NEM | EXPNEM | Withdrawn | Solar PV | 187.5 |  | 2021-03-05 | 2021-03-19 | 10 | 2021-08-12 | 112 | 2021-09-02 | 15 | [15 empty] | 2021-09-02 | 2021-09-03 | 1 | 2021-09-03 | [6 empty] | 2021-03-05 | 2021-08-24 | 120
243 | PGE | 94063 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-03-17 | 2021-03-19 | 2 | 2021-05-13 | 41 | 2021-06-03 | 14 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-14 | 7 |  |  |  |  | 2021-06-24 | 2021-07-09 | 10 |  |  |  |  | 2021-08-09 | 2021-08-12 | 3 | 2021-09-29 | 2021-10-01 | 2 |  |  |  | 2021-10-19 | 2021-11-05 | 13 | [6 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-12 |  | 2021-08-19 | 5
244 | PGE | 93446 | NEM | EXPNEM | Commercial | Solar PV | 33.128 |  | 2021-03-17 | 2021-03-19 | 2 | 2021-04-20 | 24 | 2021-07-06 | 53 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-07-27 | 15 | [5 empty] | 0 | [5 empty] | 2021-08-04 | 2021-08-12 | 6 | [15 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-12 |  | 2021-08-16 | 2
245 | PGE | 93906 | NEM | EXPNEM | IA in Progress | Solar PV | 351.986 |  | 2021-03-17 | 2021-03-19 | 2 | 2021-05-05 | 35 | 2021-07-02 | 41 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | [6 empty] | 2021-04-12 | 0
246 | PGE | 95616 | NEM | EXPNEM | IA in Progress | Solar PV | 396.286 |  | 2021-03-18 | 2021-03-22 | 2 | 2021-04-27 | 28 | 2021-05-20 | 17 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | [6 empty] | 2021-03-18 | 2021-07-23 | 89
247 | PGE | 93631 | NEM | EXPNEM | IA in Progress | Solar PV | 780 |  | 2021-03-18 | 2021-03-22 | 2 | 2021-04-16 | 21 | 2021-05-12 | 18 | 2021-05-12 | 2021-06-01 | 13 | [12 empty] | 2021-06-01 | 2021-06-01 | 0 | 2021-06-01 | [6 empty] | 2021-03-18 | 2021-05-07 | 36
248 | PGE | 95320 | NEM | EXPNEM | Implementation | Solar PV | 150 |  | 2021-03-09 | 2021-03-23 | 10 | 2021-06-21 | 73 | 2021-07-07 | 11 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | 2021-07-09 | 2 |  |  |  |  | 2021-03-09 | 2021-07-08 | 85 | [7 empty] | 2021-09-30 | 2022-01-27 | 81 |  |  |  | 2022-04-05 |  | 6
249 | PGE | 93940 | NEM | EXPNEM | Withdrawn | Solar PV | 43.78 |  | 2021-03-20 | 2021-03-23 | 1 | 2021-07-21 | 85 | 2021-10-29 | 71 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | [7 empty] | 0
250 | PGE | 94587 | NEM | EXPNEM | Commercial | Solar PV | 200 |  | 2021-03-22 | 2021-03-24 | 2 | 2021-05-05 | 32 | 2021-07-09 | 45 | [15 empty] | 2021-07-09 | 2021-07-10 | 0 | 2021-07-10 | 2021-08-19 | 28 |  |  |  |  | 2021-09-21 | 2021-09-23 | 2 |  |  |  |  | 2022-01-19 | 2022-01-26 | 5 | [15 empty] | 2022-01-19 | 2022-01-19 | 0 | 2022-01-26 |  | 2022-02-02 | 5
251 | PGE | 94587 | NEM | EXPNEM | Commercial | Solar PV | 181.876 |  | 2021-03-23 | 2021-03-24 | 1 | 2021-06-07 | 53 | 2021-07-30 | 38 | [15 empty] | 2021-07-30 | 2021-07-30 | 0 | 2021-07-30 | 2021-08-19 | 14 |  |  |  |  | 2021-07-16 | 2021-09-07 | 36 |  |  |  |  | 2022-01-19 | 2022-02-10 | 16 | [15 empty] | 2022-01-19 | 2022-02-10 | 16 | 2022-02-10 |  | 2022-02-14 | 2
252 | PGE | 94085 | NEM | EXPNEM | Commercial | Solar PV | 83.3 |  | 2021-03-23 | 2021-03-24 | 1 | 2021-05-18 | 40 | 2021-06-07 | 13 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-06-11 | 4 |  |  |  |  | 2021-06-18 | 2021-07-02 | 10 |  |  |  |  | 2021-09-30 | 2021-10-07 | 5 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-10-07 |  | 2021-10-14 | 5
253 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 183.3 |  | 2021-03-22 | 2021-03-24 | 2 | 2021-05-03 | 30 | 2021-06-01 | 20 | [15 empty] | 2021-06-01 | 2021-06-07 | 4 | 2021-06-07 | 2021-07-21 | 31 |  |  |  |  | 2021-03-22 | 2021-09-22 | 129 |  |  |  |  | 2022-01-13 | 2022-01-20 | 4 | 2021-07-20 | 2021-11-08 | 78 |  |  |  | 2022-01-18 |  | 61 | [6 empty] | 2022-01-13 | 2022-01-13 | 0 | 2022-01-20 |  | 2022-01-26 | 4
254 | PGE | 93280 | NEM | EXPNEM | Application Review in Progress | Solar PV | 168 |  | 2021-03-12 | 2021-03-25 | 9 | [30 empty] | 0
255 | PGE | 94558 | NEM | EXPNEM | Application Review in Progress | Solar PV | 46.08 |  | 2021-03-23 | 2021-03-25 | 2 | [29 empty] | 2021-03-23 | 0
256 | PGE | 94568 | NEM | EXPNEM | Commercial | Solar PV | 323.852 |  | 2021-03-23 | 2021-03-25 | 2 | 2021-04-20 | 20 | 2021-06-30 | 50 | [15 empty] | 2021-06-30 | 2021-07-07 | 4 | 2021-07-07 | 2021-07-08 | 1 | [5 empty] | 0 | [5 empty] | 2021-10-15 | 2021-10-21 | 4 | [15 empty] | 2021-10-15 | 2021-10-15 | 0 | 2021-10-21 |  | 2021-10-28 | 5
257 | PGE | 93311 | NEM | EXPNEM | IA in Progress | Solar PV | 121.259 |  | 2021-03-24 | 2021-03-26 | 2 | 2021-04-28 | 25 | 2021-05-11 | 9 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2022-02-22 | 197 |  |  |  |  | 2021-03-24 | 2021-07-19 | 81
259 | PGE | 93726 | NEM | EXPNEM | Implementation | Solar PV | 86.4 |  | 2021-03-15 | 2021-03-29 | 10 | 2021-05-07 | 39 | 2021-05-18 | 7 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | 2021-11-10 | 123 |  |  |  |  | 2021-03-15 | 0
260 | PGE | 93930 | NEM | EXPNEM | Commercial | Solar PV | 47.304 |  | 2021-03-23 | 2021-03-29 | 4 | 2021-05-14 | 38 | 2021-06-02 | 12 | [15 empty] | 2021-06-02 | 2021-06-07 | 3 | 2021-06-07 | 2021-06-08 | 1 | [5 empty] | 0 |  | 2021-06-17 |  |  |  | 2021-06-18 | 2021-06-29 | 7 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-29 |  | 2021-06-30 | 1
262 | PGE | 95492 | NEM | EXPNEM | Withdrawn | Solar PV | 506.226 |  | 2021-03-17 | 2021-03-31 | 10 | [29 empty] | 2021-03-17 | 0
263 | PGE | 93212 | NEM | EXPNEM | Implementation | Solar PV | 516 |  | 2021-03-17 | 2021-03-31 | 10 | 2021-05-27 | 51 | 2021-06-17 | 14 | 2021-06-17 | 2021-07-16 | 20 | [12 empty] | 2021-07-16 | 2021-08-19 | 24 | 2021-08-19 | 2021-08-27 | 6 |  |  |  |  | 2021-05-04 | 2021-05-26 | 16 |  |  |  |  | 2022-03-03 | 2022-03-15 | 8 | 2021-10-04 | 2022-01-27 | 79 |  |  |  | 2022-03-09 |  | 25 | [6 empty] | 2022-03-03 | 2022-03-11 | 6 | 2022-03-15 | 2022-03-16 |  | 1 |  |  | 252
266 | PGE | 94022 | NEM | EXPNEM | Commercial | Solar PV | 114.669 |  | 2021-03-30 | 2021-03-31 | 1 | 2021-04-22 | 17 | 2021-06-18 | 40 | [15 empty] | 2021-06-18 | 2021-06-21 | 1 | 2021-06-21 | 2021-08-12 | 37 |  |  |  |  | 2021-05-27 | 2021-06-07 | 6 |  |  |  |  | 2021-09-03 | 2021-09-15 | 7 | [15 empty] | 2021-09-03 | 2021-09-07 | 1 | 2021-09-15 |  | 2021-09-24 | 7
267 | PGE | 94804 | NEM | EXPNEM | Withdrawn | Solar PV | 124.183 |  | 2021-01-11 | 2021-01-14 | 3 | 2021-01-28 | 12 | [28 empty] | 0
268 | PGE | 94804 | NEM | EXPNEM | Withdrawn | Solar PV | 92.482 |  | 2021-01-11 | 2021-01-14 | 3 | 2021-01-28 | 12 | [28 empty] | 0
269 | PGE | 94804 | NEM | EXPNEM | Withdrawn | Solar PV | 88.073 |  | 2021-01-11 | 2021-01-20 | 6 | 2021-01-28 | 12 | [28 empty] | 0
270 | PGE | 94545 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-02-11 | 2021-02-12 | 1 | 2021-02-16 | 2 | 2021-05-11 | 60 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2021-05-20 | 7 | [5 empty] | 0 | [5 empty] | 2021-06-23 | 2021-08-26 | 45 | [15 empty] | 2021-06-23 | 2021-08-18 | 39 | 2021-08-26 |  | 2021-08-30 | 2
271 | PGE | 93206 | NEM | EXPNEM | Commercial | Solar PV | 875 |  | 2021-01-26 | 2021-02-08 | 9 | 2021-02-19 | 17 | [5 empty] | 2021-02-08 | 2021-03-10 | 21 | 2021-03-10 |  |  | 2021-03-10 | 2021-06-10 | 65 |  |  |  | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-08-20 | 50 |  |  |  |  | 2021-01-26 | 2021-09-21 | 166 | 2021-02-10 |  |  |  | 2021-11-23 | 2021-12-20 | 17 | [15 empty] | 2021-11-23 | 2021-12-08 | 9 | 2021-12-20 |  | 2021-12-22 | 2
272 | PGE | 93627 | NEM | EXPNEM | Implementation | Solar PV | 900 |  | 2021-02-26 | 2021-03-02 | 2 | 2021-03-09 | 7 | [5 empty] | 2021-03-09 | 2021-04-02 | 18 | 2021-04-02 |  |  | 2021-04-02 | 2021-06-08 | 46 |  |  |  | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-07-12 | 23 | [5 empty] | 0
273 | PGE | 93465 | NEM | EXPNEM | Commercial | Solar PV | 65.59 |  | 2021-03-04 | 2021-03-08 | 2 | 2021-03-12 | 6 | 2021-04-30 | 35 | [15 empty] | 2021-04-30 | 2021-05-03 | 1 | 2021-05-03 | 2021-12-14 | 155 | [5 empty] | 0 | [5 empty] | 2021-12-14 | 2021-12-29 | 11 | [15 empty] | 2021-12-14 | 2021-12-15 | 1 | 2021-12-29 |  | 2021-12-30 | 1
274 | PGE | 95965 | NEM | EXPNEM | IA in Progress | Solar PV | 360.183 |  | 2021-03-09 | 2021-03-11 | 2 | 2021-03-15 | 4 | 2021-04-23 | 29 | [15 empty] | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | 2021-05-11 | 12 |  |  |  |  | 2021-03-09 | 2021-08-13 | 111 |  |  |  |  | 2021-11-21 | [17 empty] | 2021-11-21 | 2021-11-22 | 0
275 | PGE | 94583 | NEM | EXPNEM | Implementation | Solar PV | 587.5 |  | 2021-01-29 | 2021-01-29 | 0 | 2021-03-18 | 33 | 2021-05-18 | 43 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | 2021-09-23 | 89 |  |  |  |  | 2021-01-29 | 0
276 | PGE | 95540 | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-02-22 | 2021-02-24 | 2 | 2021-03-24 | 22 | 2021-04-28 | 25 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | [7 empty] | 0
277 | PGE | 94080 | Non-NEM | Break Before Make | Commercial | ENGN | 3500 |  | 2021-03-02 | 2021-03-05 | 3 | 2021-03-24 | 16 | [5 empty] | 2021-03-24 | 2021-04-20 | 19 | 2021-04-20 | [19 empty] | 0
278 | PGE | 94521 | NEM | EXPNEM | IA in Progress | Solar PV | 37.186 |  | 2021-03-17 | 2021-03-19 | 2 | 2021-03-24 | 5 | 2021-05-24 | 43 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24 | 2022-02-03 | 176 | [5 empty] | 0 | [5 empty] | 2022-03-30 | [17 empty] | 2022-03-30 | 2022-03-30 | 0
279 | PGE | 93206 | NEM | EXPNEM | Implementation | Solar PV | 480 |  | 2021-02-18 | 2021-03-04 | 10 | 2021-03-26 | 26 | 2021-04-15 | 14 | 2021-04-15 | 2021-05-20 | 25 | 2021-06-03 | 2021-06-28 | 17 | 2021-06-28 | 2021-06-28 |  | 2021-06-28 | 2021-07-26 | 21 | 2021-06-28 |  |  | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-08-19 | 18 | [5 empty] | 0 | [8 empty] | 2021-10-18 | 2021-12-23 | 45 |  |  |  | 2022-03-15 |  | 21
280 | PGE | 93203 | NEM | EXPNEM | Implementation | Solar PV | 85.358 |  | 2021-02-18 | 2021-03-04 | 10 | 2021-03-26 | 26 | 2021-04-16 | 15 | [15 empty] | 2021-04-16 | 2021-04-23 | 5 | 2021-04-23 | 2021-06-02 | 27 | [5 empty] | 0
281 | PGE | 93301 | NEM | EXPNEM | IA in Progress | Solar PV | 348 |  | 2021-03-24 | 2021-03-26 | 2 | 2021-03-26 | 2 | 2021-06-19 | 59 | [15 empty] | 2021-06-19 | 2021-06-19 | 0 | 2021-06-19 | 2022-01-03 | 135 |  |  |  |  | 2021-03-24 | 2021-07-15 | 79
282 | PGE | 95987 | NEM | EXPNEM | Implementation | Solar PV | 125 |  | 2021-03-12 | 2021-03-26 | 10 | 2021-03-26 | 10 | 2021-06-16 | 57 | 2021-06-24 | 2021-07-21 | 18 | 2021-07-21 | 2021-08-18 | 20 | 2021-08-18 | 2021-08-18 |  | 2021-08-18 | 2021-11-09 | 60 | 2021-08-18 |  |  | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | 2021-11-10 | 1 | [5 empty] | 0 | [8 empty] | 2021-12-13 |  | 86
283 | PGE | 94583 | NEM | EXPNEM | Implementation | Solar PV | 687.5 |  | 2021-02-03 | 2021-02-04 | 1 | 2021-03-27 | 36 | 2021-05-18 | 36 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | 2021-09-23 | 89 |  |  |  |  | 2021-02-03 | 0
284 | PGE | 94583 | NEM | EXPNEM | Implementation | Solar PV | 337.5 |  | 2021-02-03 | 2021-02-04 | 1 | 2021-03-27 | 36 | 2021-04-16 | 14 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | 2021-09-23 | 111 |  |  |  |  | 2021-02-03 | 0
285 | PGE | 96013 | NEM | EXPNEM | Commercial | Solar PV | 37.598 |  | 2021-03-17 | 2021-03-19 | 2 | 2021-03-29 | 8 | 2021-04-22 | 18 | [15 empty] | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 | 2021-04-26 | 2 | [5 empty] | 0 | [5 empty] | 2021-06-12 | 2021-06-18 | 4 | [15 empty] | 2021-06-12 | 2021-06-14 | 0 | 2021-06-18 |  | 2021-06-25 | 5
287 | PGE | 94804 | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-03-12 | 2021-03-17 | 3 | 2021-03-30 | 12 | 2021-05-10 | 29 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | [6 empty] | 2021-03-12 | 0
288 | PGE | 94952 | NEM | EXPNEM | IA in Progress | Solar PV | 110 |  | 2021-03-29 | 2021-03-30 | 1 | 2021-03-30 | 1 | 2021-04-16 | 13 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | [6 empty] | 2021-03-29 | 2021-05-26 | 42
289 | PGE | 94901 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-03-29 | 2021-03-30 | 1 | 2021-03-30 | 1 | 2021-11-24 | 167 | [15 empty] | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 2021-11-28 | 0 |  |  |  |  | 2021-04-12 | 2021-04-29 | 13 |  |  |  |  | 2022-02-22 | 2022-03-03 | 7 | [15 empty] | 2022-02-22 | 2022-02-22 | 0 | 2022-03-03 |  | 2022-03-09 | 4
290 | PGE | 93306 | NEM | EXPNEM | IA in Progress | Solar PV | 236.419 |  | 2021-03-24 | 2021-03-30 | 4 | 2021-03-30 | 4 | 2021-04-16 | 13 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | [6 empty] | 2021-03-24 | 0
291 | PGE | 94561 | NEM | EXPNEM | Commercial | Solar PV | 52.108 |  | 2021-02-18 | 2021-02-19 | 1 | 2021-03-31 | 29 | 2021-04-16 | 12 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | 2021-07-02 | 54 | [5 empty] | 0 | [5 empty] | 2021-07-13 | 2021-07-21 | 6 | [15 empty] | 2021-07-13 | 2021-07-13 | 0 | 2021-07-21 |  | 2021-07-28 | 5
292 | PGE | 93210 | NEM | EXPNEM | Implementation | Solar PV | 1250 |  | 2021-03-11 | 2021-03-12 | 1 | 2021-03-31 | 14 | [5 empty] | 2021-03-31 | 2021-04-14 | 10 | 2021-04-14 | 2021-04-19 | 3 | 2021-04-21 | 2021-06-23 | 44 | 2021-04-19 | 2021-04-19 | 0 | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12 | 2021-09-08 | 41 |  |  |  |  | 2021-03-11 | 0 | [8 empty] | 2021-08-20 |  |  | 2021-08-20
293 | PGE | 94804 | NEM | EXPNEM | Withdrawn | Solar PV | 1125 |  | 2021-03-12 | 2021-03-15 | 1 | 2021-03-31 | 13 | 2021-04-16 | 12 | [25 empty] | 2021-03-12 | 0
294 | PGE | 95991 | NEM | EXPNEM | Implementation | Solar PV | 275 |  | 2021-03-17 | 2021-03-31 | 10 | 2021-03-31 | 10 | 2021-04-16 | 12 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-11-23 | 128 | [5 empty] | 0 | [5 empty] | 2022-03-16 | 2022-03-29 | 9 | [15 empty] | 2022-03-16 | 2022-03-16 | 0 | 2022-03-29
295 | PGE | 93305 | NEM | EXPNEM | IA in Progress | Solar PV | 500 |  | 2021-03-17 | 2021-03-18 | 1 | 2021-04-01 | 11 | 2021-04-19 | 12 | 2021-04-19 | 2021-05-26 | 27 | 2021-06-24 | 2021-07-23 | 20 | 2021-07-23 | 07/29/2021 |  | 2021-07-29 | 2021-10-21 | 61 | 07/29/2021 |  |  | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21 | [6 empty] | 2021-03-17 | 0
296 | PGE | 93640 | NEM | EXPNEM | Implementation | Solar PV | 1937.5 |  | 2021-03-29 | 2021-03-31 | 2 | 2021-04-07 | 7 | 2021-05-28 | 37 | 2021-06-09 | 2021-07-08 | 20 | [12 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-12 | 2 |  |  |  |  | 2021-03-29 | 2021-05-07 | 29 | [7 empty] | 2021-10-20 |  |  | 2021-10-20 |  |  | 2022-03-29 |  | 11
297 | PGE | 93309 | NEM | EXPNEM | Implementation | Solar PV | 445.259 |  | 2021-03-24 | 2021-04-05 | 8 | 2021-04-07 | 10 | 2021-04-27 | 14 | [15 empty] | 2021-04-27 | 2021-04-27 | 0 | 2021-04-27 | 2021-05-14 | 13 |  |  |  |  | 2021-03-24 | 2021-05-28 | 47 | [7 empty] | 2021-06-08 | 2021-10-21 | 95 |  |  |  | 2021-11-01 | 2022-02-05 | 66
298 | PGE | 93301 | NEM | EXPNEM | Implementation | Solar PV | 492.045 |  | 2021-03-26 | 2021-04-06 | 7 | 2021-04-07 | 8 | 2021-04-20 | 9 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-05-19 | 21 |  |  |  |  | 2021-03-26 | 0 | [8 empty] | 2021-06-08 | 2021-10-04 | 82 |  |  |  | 2021-10-26 | 2021-12-04 | 26
299 | PGE | 95969 | NEM | EXPNEM | Commercial | Solar PV | 35.045 |  | 2021-03-11 | 2021-03-15 | 2 | 2021-04-08 | 20 | 2021-04-22 | 10 | [15 empty] | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 | 2021-05-05 | 9 |  |  |  |  | 2021-03-11 | 2021-04-29 | 35 |  |  |  |  | 2021-06-18 | 2021-06-24 | 4 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-24 |  | 2021-07-01 | 5
301 | PGE | 93434 | NEM | EXPNEM | IA in Progress | Solar PV | 114.285 |  | 2021-03-28 | 2021-03-30 | 1 | 2021-04-09 | 9 | 2021-04-21 | 8 | [15 empty] | 2021-04-21 | 2021-04-21 | 0 | 2021-04-21 | 2022-03-11 | 224 |  |  |  |  | 2021-03-28 | 2021-04-16 | 14 |  |  |  |  | 2022-03-11 | 2022-03-24 | 9 | [15 empty] | 2022-03-11 | 2022-03-11 | 0 | 2022-03-24
302 | PGE | 94063 | NEM | EXPNEM | Commercial | Solar PV | 114.667 |  | 2021-02-11 | 2021-03-01 | 11 | 2021-04-11 | 40 | 2021-05-07 | 19 | [15 empty] | 2021-05-07 | 2021-05-07 | 0 | 2021-05-07 | 2021-05-07 | 0 |  |  |  |  | 2021-02-11 | 0 |  | 2021-05-04 | 2021-05-20 | 2021-05-20 | 12 | 2021-12-21 | 2021-12-28 | 5 | [15 empty] | 2021-12-21 | 2021-12-21 | 0 | 2021-12-28 |  | 2021-12-29 | 1
304 | PGE | 93446 | NEM | EXPNEM | Commercial | Solar PV | 200 |  | 2021-03-25 | 2021-03-26 | 1 | 2021-04-13 | 13 | 2021-05-03 | 14 | [15 empty] | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | 2021-11-05 | 131 | [5 empty] | 0 | [5 empty] | 2021-11-09 | 2021-11-17 | 5 | [15 empty] | 2021-11-09 | 2021-11-09 | 0 | 2021-11-17 |  | 2021-11-22 | 3
305 | PGE | 94086 | NEM | EXPNEM | Commercial | Solar PV | 368.528 |  | 2021-01-15 | 2021-01-19 | 1 | 2021-03-12 | 38 | 2021-06-03 | 58 | [15 empty] | 2021-06-03 | 2021-06-14 | 7 | 2021-06-14 | 2021-08-09 | 39 | [5 empty] | 0 | [5 empty] | 2021-08-12 | 2021-08-18 | 4 | [15 empty] | 2021-08-12 | 2021-08-12 | 0 | 2021-08-18 |  | 2021-08-19 | 1
306 | PGE | 93308 | NEM | EXPNEM | IA in Progress | Solar PV | 100.548 |  | 2021-02-16 | 2021-02-17 | 1 | 2021-03-08 | 14 | 2021-03-22 | 10 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-07-06 | 49 |  |  |  |  | 2021-02-16 | 2021-05-28 | 73
307 | PGE | 93727 | NEM | EXPNEM | Commercial | Solar PV | 36.513 |  | 2021-03-09 | 2021-03-23 | 10 | 2021-03-23 | 10 | 2021-04-09 | 13 | [15 empty] | 2021-04-09 | 2021-06-28 | 55 | 2021-06-28 | 2021-07-19 | 14 | [5 empty] | 0 | [5 empty] | 2021-07-21 | 2021-08-17 | 19 | [15 empty] | 2021-07-21 | 2021-08-10 | 14 | 2021-08-17 |  | 2021-08-18 | 1
308 | PGE | 94928 | NEM | EXPNEM | Commercial | Solar PV | 1700 |  | 2021-03-04 | 2021-03-08 | 2 | 2021-03-24 | 14 | 2021-04-12 | 13 | 2021-05-10 | 2021-06-08 | 20 | [12 empty] | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-08-24 | 54 |  |  |  |  | 2021-04-06 | 2021-07-09 | 66 |  |  |  |  | 2022-03-23 | 2022-03-31 | 6 | 2021-09-01 |  |  | 2021-09-01 | 2021-10-28 07:51 | 42 |  |  |  | 2022-01-20 | 2022-03-18 | 42 |  |  |  | 2022-03-23 | 2022-03-23 | 0 | 2022-03-31 |  | 2022-03-31 | 0
309 | PGE | 95032 | NEM | EXPNEM | IA in Progress | Solar PV | 216 |  | 2021-02-23 | 2021-02-24 | 1 | 2021-02-25 | 2 | 2021-03-18 | 15 | 2021-03-18 | 2021-04-29 | 30 | [12 empty] | 2021-04-29 | 2021-04-29 | 0 | 2021-04-29 | [6 empty] | 2021-02-23 | 0 | [17 empty] | 1//19 | 1//19
310 | PGE | 95928 | NEM | EXPNEM | Implementation | Solar PV | 62.5 |  | 2021-01-26 | 2021-01-26 | 0 | 2021-02-02 | 5 | 2021-03-19 | 32 | 2021-03-19 | 2021-04-16 | 20 | 2021-04-16 | 2021-06-29 | 51 | 2021-06-29 | 2021-07-19 | 13 |  |  |  | 2021-07-19 |  |  | 2022-02-28 | 2022-03-01 | 1 | 2022-03-01 | 2022-03-02 | 1 |  |  |  |  | 2020-02-04 | 2021-09-09 | 404 | [16 empty] | 1//19 | 1//19
311 | PGE | 95032 | NEM | EXPNEM | Implementation | Solar PV | 160 |  | 2021-03-01 | 2021-03-02 | 1 | 2021-03-02 | 1 | 2021-03-19 | 13 | 2021-03-19 | 2021-05-06 | 34 | 2021-07-09 | 2021-08-05 | 19 | 2021-08-05 | 08/12/2021 |  | 2021-08-12 | 2021-11-22 | 73 | 08/12/2021 |  |  | 2021-11-22 | 2021-11-22 |  | 2021-11-22 | 2022-01-06 | 34 | 31 |  |  |  | 2021-03-01 | 0 | [17 empty] | 1//19 | 1//19
312 | PGE | 95963 | NEM | EXPNEM | Withdrawn | Solar PV | 156 |  | 2021-02-19 | 2021-02-22 | 1 | 2021-03-09 | 12 | 2021-03-31 | 16 | 2021-03-31 | 2021-04-29 | 21 | 2021-05-05 | 2021-07-02 | 41 | 2021-07-02 | 2021-07-02 |  | 2021-07-02 | 2021-09-28 | 63 | 2021-07-02 |  |  | 2021-09-28 | 2021-09-28 | 0 | 2021-09-28 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
313 | PGE | 93618 | NEM | EXPNEM | Withdrawn | Solar PV | 828.528 |  | 2021-02-24 | 2021-03-05 | 7 | 2021-03-16 | 14 | 2021-04-02 | 13 | 2021-04-02 | 2021-04-16 | 10 | [12 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
314 | PGE | 93630 | NEM | EXPNEM | Commercial | Solar PV | 133.2 |  | 2021-02-11 | 2021-02-24 | 8 | 2021-03-12 | 20 | 2021-03-26 | 10 | [15 empty] | 2021-03-26 | 2021-04-29 | 24 | 2021-04-29 | 2021-06-30 | 43 |  |  |  |  | 2021-02-11 | 2021-07-12 | 104 |  |  |  |  | 2021-08-23 | 2021-09-01 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-23 | 2021-08-23 | 0 | 2021-09-01 |  | 2021-09-02 | 1
315 | PGE | 95242 | NEM | EXPNEM | Commercial | Solar PV | 31.461 |  | 2021-01-12 | 2021-01-13 | 1 | 2021-01-19 | 4 | 2021-02-02 | 10 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-11-18 | 202 | [5 empty] | 0 | [5 empty] | 2021-11-22 | 2021-11-30 | 4 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-22 | 2021-11-22 | 0 | 2021-11-30 |  | 2021-12-03 | 3
316 | PGE | 95950 | NEM | EXPNEM | Commercial | Solar PV | 132 |  | 2021-01-15 | 2021-01-19 | 1 | 2021-01-19 | 1 | 2021-02-03 | 11 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-07-02 | 105 | [5 empty] | 0 | [5 empty] | 2021-07-12 | 2021-07-20 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-12 | 2021-07-12 | 0 | 2021-07-20 |  | 2021-07-27 | 5
317 | PGE | 94804 | NEM | EXPNEM | Withdrawn | Solar PV | 146.8 |  | 2021-01-11 | 2021-01-20 | 6 | 2021-01-28 | 12 | 2021-02-05 | 6 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
318 | PGE | 94804 | NEM | EXPNEM | Withdrawn | Solar PV | 153.25 |  | 2021-01-11 | 2021-01-14 | 3 | 2021-02-02 | 15 | 2021-02-05 | 3 | [15 empty] | 2021-02-05 | 2021-02-08 | 1 | 2021-02-08 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
320 | PGE | 95227 | NEM | EXPNEM | Commercial | Solar PV | 71.771 |  | 2021-01-14 | 2021-01-29 | 10 | 2021-01-29 | 10 | 2021-02-19 | 14 | [15 empty] | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | 2021-05-20 | 64 |  |  |  |  | 2021-05-01 | 2021-05-10 | 5 |  |  |  |  | 2021-12-01 | 2021-12-08 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-01 | 2021-12-02 | 1 | 2021-12-08 |  | 2021-12-15 | 5
321 | PGE | 95126 | NEM | EXPNEM | Withdrawn | Solar PV | 30.159 |  | 2021-01-22 | 2021-01-30 | 5 | 2021-01-30 | 5 | 2021-02-19 | 13 | [15 empty] | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | 2021-08-25 | 131 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
322 | PGE | 95334 | NEM | EXPNEM | Commercial | Solar PV | 125 |  | 2021-01-15 | 2021-02-01 | 10 | 2021-02-01 | 10 | 2021-02-22 | 14 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-08-09 | 118 |  |  |  |  | 2021-01-15 | 2021-07-29 | 135 |  |  |  |  | 2021-08-27 | 2021-09-02 | 4 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-27 | 2021-08-27 | 0 | 2021-09-02 |  | 2021-09-07 | 2
323 | PGE | 95076 | NEM | EXPNEM | Commercial | Solar PV | 85.795 |  | 2021-02-03 | 2021-02-17 | 9 | 2021-02-23 | 13 | 2021-03-01 | 4 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-12-02 | 192 | [5 empty] | 0 | [5 empty] | 2021-12-16 | 2021-12-30 | 10 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-16 | 2021-12-16 | 0 | 2021-12-30 |  | 2022-01-05 | 4
324 | PGE | 93630 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-02-11 | 2021-02-12 | 1 | 2021-02-18 | 4 | 2021-03-02 | 8 | [15 empty] | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | 2021-08-24 | 123 |  |  |  |  | 2021-02-11 | 2021-07-15 | 107 |  |  |  |  | 2021-08-24 | 2021-09-14 | 14 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-24 | 2021-09-08 | 10 | 2021-09-14 |  | 2021-09-29 | 11
325 | PGE | 95403 | NEM | EXPNEM | Commercial | Solar PV | 72.381 |  | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 0 | 2021-03-03 | 25 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-05-24 | 58 |  |  |  |  | 2021-01-26 | 2021-05-10 | 73 |  |  |  |  | 2022-02-23 | 2022-03-03 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-02-23 | 2022-03-01 | 4 | 2022-03-03 |  | 2022-03-04 | 1
326 | PGE | 93925 | NEM | EXPNEM | Commercial | Solar PV | 84.718 |  | 2021-01-13 | 2021-01-28 | 10 | 2021-02-13 | 21 | 2021-03-07 | 14 | [15 empty] | 2021-03-07 | 2021-03-07 | 0 | 2021-03-07 | 2021-05-24 | 55 |  |  |  |  | 2021-01-13 | 0 | [5 empty] | 2021-12-13 | 2021-12-23 | 8 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-13 | 2021-12-14 | 1 | 2021-12-23 |  | 2021-12-29 | 4
327 | PGE | 94063 | NEM | EXPNEM | Commercial | Solar PV | 540 |  | 2021-01-15 | 2021-01-24 | 4 | 2021-01-24 | 4 | 2021-03-08 | 29 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-04-16 | 29 |  |  |  |  | 2021-01-15 | 2021-05-05 | 76 |  |  |  |  | 2021-12-09 | 2021-12-20 | 7 | 2021-06-03 | 2021-06-03 | 0 |  |  |  | 2021-06-03 | 2021-06-03 | 1 | 1//19 | 1//19 |  |  |  |  | 2021-12-09 | 2021-12-09 | 0 | 2021-12-20 |  | 2021-12-22 | 2
328 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 90.375 |  | 2021-02-22 | 2021-02-23 | 1 | 2021-02-26 | 4 | 2021-03-08 | 6 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-07-12 | 88 |  |  |  |  | 2021-02-22 | 2021-05-07 | 54 |  |  |  |  | 2021-07-16 | 2021-07-23 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-16 | 2021-07-16 | 0 | 2021-07-23 |  | 2021-07-29 | 4
329 | PGE | 95220 | NEM | EXPNEM | Commercial | Solar PV | 46.382 |  | 2021-02-22 | 2021-02-24 | 2 | 2021-02-26 | 4 | 2021-03-08 | 6 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-05-18 | 51 | [5 empty] | 0 | [5 empty] | 2021-05-26 | 2021-06-03 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-26 | 2021-05-26 | 0 | 2021-06-03 |  | 2021-06-10 | 5
330 | PGE | 93721 | NEM | EXPNEM | Commercial | Solar PV | 187.5 |  | 2021-02-04 | 2021-02-16 | 7 | 2021-02-16 | 7 | 2021-02-19 | 3 | [15 empty] | 2021-02-19 | 2021-03-09 | 12 | 2021-03-09 | 2021-05-07 | 43 |  |  |  |  | 2021-02-04 | 2021-09-08 | 150 |  |  |  |  | 2021-12-10 | 2022-01-10 | 21 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-10 | 2022-01-10 | 21 | 2022-01-10 |  | 2022-01-10 | 0
331 | PGE | 94928 | NEM | EXPNEM | Commercial | Solar PV | 43.741 |  | 2021-02-24 | 2021-02-25 | 1 | 2021-03-01 | 3 | 2021-03-18 | 13 | [15 empty] | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18 | 2021-04-20 | 23 | [5 empty] | 0 | [5 empty] | 2021-04-27 | 2021-05-06 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-27 | 2021-04-29 | 2 | 2021-05-06 |  | 2021-05-07 | 1
332 | PGE | 95020 | NEM | EXPNEM | Withdrawn | Solar PV | 280.516 |  | 2021-02-09 | 2021-02-10 | 1 | 2021-03-02 | 14 | 2021-03-19 | 13 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | [6 empty] | 2021-02-09 | 0 | [17 empty] | 1//19 | 1//19
333 | PGE | 95112 | NEM | EXPNEM | Withdrawn | Solar PV | 32.109 |  | 2021-02-18 | 2021-02-19 | 1 | 2021-03-02 | 8 | 2021-03-19 | 13 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
334 | PGE | 95321 | NEM | EXPNEM | Implementation | Solar PV | 166.5 |  | 2021-02-16 | 2021-03-02 | 10 | 2021-03-02 | 10 | 2021-03-19 | 13 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2022-03-22 | 254 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
335 | PGE | 95229 | NEM | EXPNEM | Commercial | Solar PV | 54.148 |  | 2021-02-25 | 2021-02-26 | 1 | 2021-03-03 | 4 | 2021-03-22 | 13 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-04-24 | 24 |  |  |  |  | 2021-02-25 | 0 | [5 empty] | 2021-04-27 | 2021-06-03 | 26 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-27 | 2021-04-27 | 0 | 2021-06-03 |  | 2021-06-08 | 3
336 | PGE | 94043 | NEM | EXPNEM | Commercial | Solar PV | 136 |  | 2021-03-02 | 2021-03-04 | 2 | 2021-03-04 | 2 | 2021-03-22 | 12 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-06-03 | 52 | [5 empty] | 0 | [5 empty] | 2021-11-09 | 2021-11-19 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-09 | 2021-11-09 | 0 | 2021-11-19 |  | 2021-11-24 | 3
337 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-02 | 2021-03-04 | 2 | 2021-03-10 | 6 | 2021-03-24 | 10 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-04-21 | 20 | [5 empty] | 0 | [5 empty] | 2021-08-17 | 2021-08-24 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-17 | 2021-08-17 | 0 | 2021-08-24 |  | 2021-08-30 | 4
338 | PGE | 95060 | NEM | EXPNEM | Commercial | Solar PV | 65.159 |  | 2021-02-26 | 2021-03-02 | 2 | 2021-03-12 | 10 | 2021-03-24 | 8 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-04-26 | 23 | [5 empty] | 0 | [5 empty] | 2021-04-28 | 2021-05-11 | 9 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-28 | 2021-04-29 | 1 | 2021-05-11 |  | 2021-05-18 | 5
339 | PGE | 95945 | NEM | EXPNEM | Commercial | Solar PV | 45.6 |  | 2021-02-02 | 2021-02-11 | 7 | 2021-02-11 | 7 | 2021-03-25 | 29 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-06-16 | 58 | [5 empty] | 0 | [5 empty] | 2021-07-28 | 2021-12-02 | 87 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-28 | 2021-08-17 | 14 | 2021-12-02 | 2021-08-30 | 2021-12-02 | 1 |  |  | 146
340 | PGE | 94043 | NEM | EXPNEM | Commercial | Solar PV | 74.396 |  | 2021-03-02 | 2021-03-04 | 2 | 2021-03-08 | 4 | 2021-03-25 | 13 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-06-21 | 61 | [5 empty] | 0 | [5 empty] | 2021-10-22 | 2021-11-10 | 13 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-22 | 2021-10-22 | 0 | 2021-11-10 |  | 2021-11-16 | 3
341 | PGE | 93212 | NEM | EXPNEM | Implementation | Solar PV | 480 |  | 2021-01-29 | 2021-02-12 | 10 | 2021-02-24 | 17 | 2021-02-26 | 2 | 2021-02-26 | 2021-03-25 | 19 | [12 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-04-15 | 15 | [5 empty] | 0 | [8 empty] | 2021-06-08 | 2021-06-18 | 8 | [6 empty] | 1//19 | 1//19
342 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-02 | 2021-03-04 | 2 | 2021-03-09 | 5 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-08-19 | 102 | [5 empty] | 0 | [5 empty] | 2021-08-21 | 2021-09-01 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-21 | 2021-08-24 | 1 | 2021-09-01 |  | 2021-09-09 | 5
343 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-02 | 2021-03-04 | 2 | 2021-03-09 | 5 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-21 | 18 | [5 empty] | 0 | [5 empty] | 2021-08-23 | 2021-09-01 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-23 | 2021-08-24 | 1 | 2021-09-01 |  | 2021-09-16 | 10
344 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-02 | 2021-03-04 | 2 | 2021-03-09 | 5 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-21 | 18 | [5 empty] | 0 | [5 empty] | 2021-08-23 | 2021-09-01 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-23 | 2021-08-24 | 1 | 2021-09-01 |  | 2021-09-16 | 10
345 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-02 | 2021-03-04 | 2 | 2021-03-11 | 7 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-21 | 18 | [5 empty] | 0 | [5 empty] | 2021-08-24 | 2021-09-01 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-24 | 2021-08-24 | 0 | 2021-09-01 |  | 2021-09-16 | 10
346 | PGE | 95965 | NEM | EXPNEM | Commercial | Solar PV | 38.78 |  | 2021-03-09 | 2021-03-11 | 2 | 2021-03-11 | 2 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-07-22 | 82 |  |  |  |  | 2021-03-09 | 2021-08-09 | 107 |  |  |  |  | 2021-12-13 | 2021-12-23 | 8 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-13 | 2021-12-20 | 5 | 2021-12-23 |  | 2022-01-12 | 14
347 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-02 | 2021-03-04 | 2 | 2021-03-12 | 8 | 2021-03-26 | 10 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-08-19 | 102 | [5 empty] | 0 | [5 empty] | 2021-08-24 | 2021-09-01 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-24 | 2021-08-24 | 0 | 2021-09-01 |  | 2021-09-09 | 5
348 | PGE | 95377 | NEM | EXPNEM | IA in Progress | Solar PV | 420 |  | 2021-02-16 | 2021-02-17 | 1 | 2021-03-11 | 17 | 2021-03-27 | 11 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | 2021-04-29 | 23 | [5 empty] | 0 | [8 empty] | 2021-07-30 | 2021-12-14 | 93 | [6 empty] | 1//19 | 1//19
349 | PGE | 95501 | NEM | EXPNEM | IA in Progress | Solar PV | 56.965 |  | 2021-01-25 | 2021-01-26 | 1 | 2021-03-01 | 24 | 2021-03-29 | 20 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | [6 empty] | 2021-01-25 | 0 | [17 empty] | 1//19 | 1//19
350 | PGE | 95033 | NEM | EXPNEM | Withdrawn | Solar PV | 75.259 |  | 2021-03-01 | 2021-03-02 | 1 | 2021-03-12 | 9 | 2021-03-29 | 11 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | [6 empty] | 2021-03-01 | 0 | [17 empty] | 1//19 | 1//19
351 | PGE | 93280 | NEM | EXPNEM | Implementation | Solar PV | 230 |  | 2021-02-14 | 2021-03-01 | 9 | 2021-03-15 | 19 | 2021-03-29 | 10 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-06-22 | 60 | [5 empty] | 0 | [5 empty] | 2022-03-30 |  |  | 2021-07-20 | 2021-11-15 | 82 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 2022-03-30 | 2022-03-31 | 1
352 | PGE | 93648 | NEM | EXPNEM | Commercial | Solar PV | 590 |  | 2021-03-12 | 2021-03-16 | 2 | 2021-03-16 | 2 | 2021-03-30 | 10 | 2021-06-17 | 2021-07-16 | 20 | [12 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-07-19 | 77 |  |  |  |  | 2021-03-12 | 2021-04-16 | 25 |  |  |  |  | 2022-01-11 | 2022-01-19 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-01-11 | 2022-01-11 | 0 | 2022-01-19 |  | 2022-01-24 | 3
353 | PGE | 94930 | NEM | EXPNEM | Commercial | Solar PV | 61.126 |  | 2021-02-24 | 2021-02-26 | 2 | 2021-03-17 | 15 | 2021-03-30 | 9 | [15 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-04-20 | 15 |  |  |  |  | 2021-03-12 | 2021-07-01 | 78 |  |  |  |  | 2021-07-06 | 2021-07-08 | 2 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-06 | 2021-07-06 | 0 | 2021-07-08 |  | 2021-07-09 | 1
354 | PGE | 93637 | NEM | EXPNEM | Commercial | Solar PV | 650.576 |  | 2021-02-16 | 2021-02-17 | 1 | 2021-03-16 | 20 | 2021-03-31 | 11 | [15 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | 2021-04-15 | 11 |  |  |  |  | 2021-02-16 | 2021-07-19 | 107 |  |  |  |  | 2021-09-23 | 2021-09-29 | 4 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-23 | 2021-09-23 | 0 | 2021-09-29 |  | 2021-10-06 | 5
355 | PGE | 95901 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-02-15 | 2021-02-16 | 0 | 2021-03-18 | 22 | 2021-04-01 | 10 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | 2021-10-14 | 137 | [5 empty] | 0 | [5 empty] | 2021-10-21 | 2021-10-28 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-21 | 2021-10-21 | 0 | 2021-10-28 |  | 2021-11-03 | 4
356 | PGE | 95377 | NEM | EXPNEM | Commercial | Solar PV | 30.159 |  | 2021-03-08 | 2021-03-10 | 2 | 2021-03-24 | 12 | 2021-04-01 | 6 | [15 empty] | 2021-04-01 | 2021-04-02 | 1 | 2021-04-02 | 2021-04-15 | 9 | [5 empty] | 0 | [5 empty] | 2021-04-19 | 2021-04-27 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-19 | 2021-04-19 | 0 | 2021-04-27 |  | 2021-04-30 | 3
357 | PGE | 93249 | NEM | EXPNEM | Withdrawn | Solar PV | 66.6 |  | 2021-02-24 | 2021-02-26 | 2 | 2021-03-18 | 16 | 2021-04-02 | 11 | [15 empty] | 2021-04-02 | 2021-04-02 | 0 | 2021-04-02 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
358 | PGE | 95032 | NEM | EXPNEM | IA in Progress | Solar PV | 156 |  | 2021-02-23 | 2021-02-24 | 1 | 2021-02-24 | 1 | 2021-04-05 | 28 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-09-24 | 121 |  |  |  |  | 2021-02-23 | 0 | [17 empty] | 1//19 | 1//19
359 | PGE | 94043 | NEM | EXPNEM | Commercial | Solar PV | 32.907 |  | 2021-03-08 | 2021-03-10 | 2 | 2021-03-17 | 7 | 2021-04-05 | 13 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-05-14 | 29 | [5 empty] | 0 | [5 empty] | 2021-06-07 | 2021-06-16 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-07 | 2021-06-07 | 0 | 2021-06-16 |  | 2021-06-23 | 5
360 | PGE | 94513 | NEM | EXPNEM | Commercial | Solar PV | 86.4 |  | 2021-03-10 | 2021-03-12 | 2 | 2021-03-17 | 5 | 2021-04-05 | 13 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-07-15 | 71 |  |  |  |  | 2021-03-10 | 2021-06-07 | 62 |  |  |  |  | 2021-07-20 | 2021-07-28 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-20 | 2021-07-20 | 0 | 2021-07-28 |  | 2021-08-11 | 10
361 | PGE | 95695 | NEM | EXPNEM | Commercial | Solar PV | 38.527 |  | 2021-03-23 | 2021-03-25 | 2 | 2021-03-25 | 2 | 2021-04-05 | 7 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-11-17 | 158 | [5 empty] | 0 | [5 empty] | 2021-11-21 | 2021-11-30 | 4 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-21 | 2021-11-22 | 0 | 2021-11-30 |  | 2021-12-03 | 3
362 | PGE | 96011 | NEM | EXPNEM | Commercial | Solar PV | 48.857 |  | 2021-03-18 | 2021-03-22 | 2 | 2021-03-26 | 6 | 2021-04-05 | 6 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-07-22 | 76 | [5 empty] | 0 | [5 empty] | 2021-07-31 | 2021-08-19 | 13 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-31 | 2021-08-17 | 11 | 2021-08-19 |  | 2021-08-23 | 2
363 | PGE | 95076 | NEM | EXPNEM | Commercial | Solar PV | 466.6 |  | 2021-03-25 | 2021-03-29 | 2 | 2021-03-31 | 4 | 2021-04-05 | 3 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-05-19 | 32 | [5 empty] | 0 | [5 empty] | 2021-05-21 | 2021-05-26 | 3 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-21 | 2021-05-21 | 0 | 2021-05-26 |  | 2021-06-02 | 4
364 | PGE | 94085 | NEM | EXPNEM | Commercial | Solar PV | 75.885 |  | 2021-03-04 | 2021-03-05 | 1 | 2021-03-19 | 11 | 2021-04-06 | 12 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-04-29 | 17 | [5 empty] | 0 | [5 empty] | 2021-05-04 | 2021-05-13 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-04 | 2021-05-05 | 1 | 2021-05-13 |  | 2021-05-19 | 4
365 | PGE | 93314 | NEM | EXPNEM | Withdrawn | Solar PV | 31.5 |  | 2021-03-17 | 2021-03-19 | 2 | 2021-03-23 | 4 | 2021-04-06 | 10 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
366 | PGE | 95361 | NEM | EXPNEM | Commercial | Solar PV | 35.852 |  | 2021-03-26 | 2021-03-29 | 1 | 2021-03-29 | 1 | 2021-04-06 | 6 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-05-07 | 23 | [5 empty] | 0 | [5 empty] | 2021-11-15 | 2021-12-16 | 21 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-15 | 2021-12-10 | 17 | 2021-12-16 |  | 2021-12-22 | 4
367 | PGE | 94546 | NEM | EXPNEM | Commercial | Solar PV | 62.5 |  | 2021-03-12 | 2021-03-17 | 3 | 2021-03-19 | 5 | 2021-04-07 | 13 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-21 | 10 | [5 empty] | 0 | [5 empty] | 2021-10-06 | 2021-10-14 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-06 | 2021-10-07 | 1 | 2021-10-14 |  | 2021-10-25 | 7
368 | PGE | 95991 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-03-15 | 2021-03-18 | 3 | 2021-03-23 | 6 | 2021-04-07 | 11 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-16 | 7 |  |  |  |  | 2021-03-15 | 0 | [5 empty] | 2021-06-18 | 2021-06-30 | 8 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-18 | 2021-06-21 | 1 | 2021-06-30 |  | 2021-07-16 | 11
369 | PGE | 94538 | NEM | EXPNEM | IA in Progress | Solar PV | 765.9 |  | 2021-03-11 | 2021-03-15 | 2 | 2021-03-24 | 9 | 2021-04-08 | 11 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | 2022-02-08 | 211 |  |  |  |  | 2021-03-11 | 0 | [17 empty] | 1//19 | 1//19
370 | PGE | 93722 | NEM | EXPNEM | Commercial | Solar PV | 55.067 |  | 2021-03-18 | 2021-03-22 | 2 | 2021-04-02 | 11 | 2021-04-08 | 4 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | 2021-04-13 | 3 | [5 empty] | 0 | [5 empty] | 2021-04-15 | 2021-04-22 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-15 | 2021-04-15 | 0 | 2021-04-22 |  | 2021-04-29 | 5
371 | PGE | 93706 | NEM | EXPNEM | Implementation | Solar PV | 969.737 |  | 2021-02-02 | 2021-02-17 | 10 | 2021-03-09 | 24 | 2021-03-23 | 10 | 2021-03-23 | 2021-04-09 | 13 | [12 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | 2021-04-28 | 13 | [5 empty] | 0 |  | 2021-05-25 | [6 empty] | 2021-06-22 | 2021-12-07 | 115 |  |  |  | 2022-01-05 | 2022-03-03 | 41 | 1//19 | 1//19
372 | PGE | 93308 | NEM | EXPNEM | IA in Progress | Solar PV | 89.259 |  | 2021-03-02 | 2021-03-04 | 2 | 2021-03-08 | 4 | 2021-04-12 | 25 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
373 | PGE | 95207 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-03-16 | 2021-03-30 | 10 | 2021-03-30 | 10 | 2021-04-12 | 9 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-09-16 | 110 | [5 empty] | 0 | [5 empty] | 2021-09-17 | 2021-12-28 | 69 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-17 | 2021-12-20 | 63 | 2021-12-28 |  | 2021-12-29 | 1
374 | PGE | 95619 | NEM | EXPNEM | Commercial | Solar PV | 89.207 |  | 2021-03-08 | 2021-03-10 | 2 | 2021-03-26 | 14 | 2021-04-13 | 12 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-07-19 | 67 | [5 empty] | 0 | [5 empty] | 2021-07-23 | 2021-09-02 | 29 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-23 | 2021-08-27 | 25 | 2021-09-02 |  | 2021-09-13 | 6
375 | PGE | 93622 | NEM | EXPNEM | Commercial | Solar PV | 648.528 |  | 2021-01-26 | 2021-02-09 | 10 | 2021-03-01 | 23 | 2021-03-11 | 8 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | 2021-04-01 | 15 | [5 empty] | 0 |  | 2021-05-25 |  |  |  | 2022-02-23 | 2022-03-04 | 7 | 2021-06-17 | 2021-08-11 | 38 |  |  |  | 2021-08-13 | 2022-01-09 | 11 | 1//19 | 1//19 |  |  |  |  | 2022-02-23 | 2022-02-23 | 0 | 2022-03-04 |  | 2022-03-10 | 4
376 | PGE | 95482 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-01-22 | 2021-02-26 | 24 | 2021-03-15 | 35 | 2021-04-01 | 13 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | 2021-04-02 | 1 | [5 empty] | 0 | [5 empty] | 2021-04-27 | 2021-05-27 | 22 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-27 | 2021-05-21 | 18 | 2021-05-27 |  | 2021-05-27 | 0
377 | PGE | 95333 | NEM | EXPNEM | Commercial | Solar PV | 95.8 |  | 2021-01-18 | 2021-01-25 | 4 | 2021-01-25 | 4 | 2021-02-11 | 13 | [15 empty] | 2021-02-19 | 2021-03-19 | 20 | 2021-03-19 | 2021-04-13 | 17 |  |  |  |  | 2021-01-18 | 2021-07-27 | 132 |  |  |  |  | 2021-09-07 | 2021-09-15 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-07 | 2021-09-08 | 1 | 2021-09-15 |  | 2021-09-15 | 0
378 | PGE | 95521 | NEM | EXPNEM | Commercial | Solar PV | 85.387 |  | 2021-01-14 | 2021-01-15 | 1 | 2021-01-19 | 2 | 2021-02-01 | 9 | [15 empty] | 2021-02-01 | 2021-02-01 | 0 | 2021-02-01 | 2021-05-11 | 70 |  |  |  |  | 2021-01-14 | 2021-05-26 | 92 |  |  |  |  | 2021-12-22 | 2022-01-27 | 25 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-22 | 2022-01-27 | 25 | 2022-01-27 |  | 2022-02-25 | 20
379 | PGE | 95901 | NEM | EXPNEM | Implementation | Solar PV | 490 |  | 2021-01-13 | 2021-01-20 | 4 | 2021-01-20 | 4 | 2021-02-03 | 10 | 2021-02-03 | 2021-03-17 | 29 | 2021-03-17 | 2021-03-23 | 4 | 2021-03-23 | [8 empty] | 2021-08-16 | 2021-08-18 | 2 | 2021-08-18 | 2021-08-19 | 1 |  |  |  |  | 2021-01-13 | 2021-02-01 | 12 | [7 empty] | 2021-09-20 | 2021-12-28 | 67 | [6 empty] | 1//19 | 1//19
380 | PGE | 95901 | NEM | EXPNEM | Implementation | Solar PV | 720 |  | 2021-01-15 | 2021-01-21 | 3 | 2021-01-21 | 3 | [5 empty] | 2021-01-21 | 2021-02-25 | 24 | 2021-02-25 | [8 empty] | 2021-08-16 | 2021-08-18 | 2 | 2021-08-18 | 2021-08-19 | 1 |  |  |  |  | 2021-01-15 | 2021-02-02 | 11 | [16 empty] | 1//19 | 1//19
381 | PGE | 95320 | NEM | EXPNEM | Commercial | Solar PV | 44.337 |  | 2021-01-19 | 2021-01-28 | 7 | 2021-01-28 | 7 | 2021-03-22 | 36 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-05-19 | 42 |  |  |  |  | 2021-01-19 | 2021-02-05 | 13 |  |  |  |  | 2021-09-07 | 2021-09-16 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-07 | 2021-09-08 | 1 | 2021-09-16 |  | 2021-09-16 | 0
382 | PGE | 94545 | NEM | EXPNEM | Commercial | Solar PV | 41.968 |  | 2021-02-01 | 2021-02-02 | 1 | 2021-02-10 | 7 | 2021-03-22 | 27 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-04-19 | 20 |  |  |  |  | 2021-02-01 | 2021-02-08 | 5 |  |  |  |  | 2021-08-03 | 2021-08-27 | 18 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-03 | 2021-08-03 | 0 | 2021-08-27 |  | 2021-09-09 | 8
383 | PGE | 95037 | NEM | EXPNEM | Withdrawn | Solar PV, Storage | 33.54 |  | 2021-01-21 | 2021-02-04 | 10 | [29 empty] | 2021-01-21 | 2021-02-09 | 13 | [16 empty] | 1//19 | 1//19
384 | PGE | 95240 | NEM | EXPNEM | Commercial | Solar PV | 400 |  | 2021-02-03 | 2021-02-03 | 0 | 2021-02-22 | 12 | 2021-03-03 | 7 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-12-15 | 199 |  |  |  |  | 2021-02-03 | 2021-02-09 | 4 |  |  |  |  | 2021-12-16 | 2021-12-28 | 8 | 2021-06-16 | 2021-10-12 | 82 |  |  |  |  | 2022-02-01 |  | 1//19 | 1//19 |  |  |  |  | 2021-12-16 | 2021-12-16 | 0 | 2021-12-28 |  | 2021-12-29 | 1
385 | PGE | 95240 | NEM | EXPNEM | IA in Progress | Solar PV | 41.219 |  | 2021-01-12 | 2021-01-13 | 1 | 2021-02-04 | 16 | 2021-03-24 | 33 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | [6 empty] | 2021-01-12 | 2021-02-09 | 19 | [16 empty] | 1//19 | 1//19
386 | PGE | 95448 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-01-28 | 2021-01-29 | 1 | 2021-01-29 | 1 | 2021-02-11 | 9 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-05-12 | 63 |  |  |  |  | 2021-01-28 | 2021-02-11 | 10 |  |  |  |  | 2021-06-19 | 2021-07-14 | 16 | 2021-10-05 | 2021-10-05 | 0 |  |  |  | 2021-10-14 | 2021-12-02 | 32 | 1//19 | 1//19 |  |  |  |  | 2021-06-19 | 2021-07-09 | 13 | 2021-07-14 | 2021-07-21 | 2021-12-08 | 5 |  |  | 121
387 | PGE | 95317 | NEM | EXPNEM | Implementation | Solar PV | 38.78 |  | 2021-01-21 | 2021-01-29 | 6 | 2021-02-12 | 16 | 2021-02-26 | 9 | [15 empty] | 2021-02-26 | 2021-03-16 | 12 | 2021-03-16 | 2021-04-09 | 18 |  |  |  |  | 2021-01-21 | 2021-02-11 | 15 |  |  |  |  | 2021-05-17 | 2021-05-24 | 5 | 2021-05-18 | 2021-08-19 | 65 |  |  |  | 2022-01-19 |  | 6 | 1//19 | 1//19 |  |  |  |  | 2021-05-17 | 2021-05-17 | 0 | 2021-05-24 | 2021-06-17 |  | 17 |  |  | 103
388 | PGE | 93727 | NEM | EXPNEM | Withdrawn | Solar PV | 200 |  | 2021-02-04 | 2021-02-05 | 1 | 2021-02-12 | 6 | 2021-02-22 | 5 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-05-05 | 52 |  |  |  |  | 2021-02-04 | 2021-02-16 | 7 | [16 empty] | 1//19 | 1//19
389 | PGE | 93622 | NEM | EXPNEM | Commercial | Solar PV | 49.794 |  | 2021-02-02 | 2021-02-11 | 7 | 2021-02-11 | 7 | 2021-02-26 | 10 | [15 empty] | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-05-18 | 57 |  |  |  |  | 2021-02-02 | 2021-02-16 | 9 |  |  |  |  | 2021-06-15 | 2021-06-24 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-15 | 2021-06-16 | 1 | 2021-06-24 |  | 2021-06-24 | 0
390 | PGE | 94954 | NEM | EXPNEM | Withdrawn | Solar PV | 94.844 |  | 2021-02-10 | 2021-02-23 | 8 | 2021-02-23 | 8 | 2021-03-11 | 12 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | [6 empty] | 2021-02-10 | 2021-02-23 | 8 | [16 empty] | 1//19 | 1//19
391 | PGE | 94545 | NEM | EXPNEM | Commercial | Solar PV | 172.8 |  | 2021-02-18 | 2021-02-19 | 1 | 2021-02-25 | 5 | 2021-04-15 | 35 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-26 | 7 |  |  |  |  | 2021-02-18 | 2021-02-25 | 5 |  |  |  |  | 2021-06-22 | 2021-06-29 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-22 | 2021-06-22 | 0 | 2021-06-29 |  | 2021-06-30 | 1
392 | PGE | 95385 | NEM | EXPNEM | IA in Progress | Solar PV | 46.625 |  | 2021-02-09 | 2021-02-10 | 1 | 2021-02-25 | 11 | 2021-03-11 | 10 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | 2021-12-31 | 205 |  |  |  |  | 2021-02-09 | 2021-02-25 | 11 |  |  |  |  | 2021-12-31 | 2022-02-03 | 23 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-31 | 2022-01-28 | 19 | 2022-02-03
393 | PGE | 93301 | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-02-23 | 2021-02-24 | 1 | 2021-02-26 | 3 | 2021-03-26 | 20 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-08-13 | 98 |  |  |  |  | 2021-02-23 | 2021-03-01 | 4 |  |  |  |  | 2021-08-13 | 2021-08-25 | 8 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-13 | 2021-08-16 | 1 | 2021-08-25 |  | 2021-09-07 | 8
394 | PGE | 95616 | NEM | EXPNEM | Study in Progress | Solar PV | 104.7 |  | 2021-02-02 | 2021-02-03 | 1 | 2021-03-01 | 18 | 2021-03-17 | 12 | 2021-03-17 | 2021-04-14 | 20 | 2021-05-06 | 2021-06-10 | 24 | 2021-06-10 | 2021-06-25 | 11 |  |  |  | 2021-06-25 | [12 empty] | 2021-02-02 | 2021-07-09 | 110 | [16 empty] | 1//19 | 1//19
395 | PGE | 93420 | NEM | EXPNEM | Commercial | Solar PV | 625 |  | 2021-01-13 | 2021-01-14 | 1 | 2021-01-20 | 4 | 2021-02-02 | 9 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-10-04 | 170 |  |  |  |  | 2021-01-13 | 2021-03-02 | 32 |  |  |  |  | 2021-10-19 | 2021-11-17 | 20 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-19 | 2021-11-12 | 17 | 2021-11-17 |  | 2021-11-23 | 4
396 | PGE | 93420 | NEM | EXPNEM | Commercial | Solar PV | 183.3 |  | 2021-01-13 | 2021-01-14 | 1 | 2021-01-20 | 4 | 2021-02-02 | 9 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-09-23 | 163 |  |  |  |  | 2021-01-13 | 2021-03-02 | 32 |  |  |  |  | 2021-10-07 | 2021-12-15 | 46 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-07 | 2021-12-06 | 39 | 2021-12-15 |  | 2021-12-20 | 3
397 | PGE | 95336 | NEM | EXPNEM | Implementation | Solar PV | 125 |  | 2021-01-13 | 2021-01-21 | 5 | 2021-02-25 | 29 | 2021-04-28 | 44 | 2021-04-28 | 2021-05-26 | 20 | 2021-06-28 | 2021-07-23 | 18 | 2021-07-23 | 2021-08-06 | 10 | 2021-08-06 | 2021-10-25 | 57 | 2021-08-06 |  |  | 2021-10-26 | 2021-10-27 | 1 | 2021-10-27 | 2021-11-09 | 9 |  |  |  |  | 2021-02-25 | 2021-03-04 | 5 | [16 empty] | 1//19 | 1//19
398 | PGE | 95037 | NEM | EXPNEM | Commercial | Solar PV | 154.954 |  | 2021-02-08 | 2021-02-08 | 0 | 2021-03-08 | 19 | 2021-05-10 | 45 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2021-05-11 | 1 |  |  |  |  | 2021-02-08 | 2021-03-04 | 17 |  |  |  |  | 2021-11-21 | 2021-12-02 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-21 | 2021-11-21 | 0 | 2021-12-02 |  | 2021-12-09 | 5
399 | PGE | 95333 | NEM | EXPNEM | Commercial | Solar PV | 125 |  | 2021-02-18 | 2021-03-04 | 10 | 2021-03-23 | 23 | 2021-03-30 | 5 | [15 empty] | 2021-05-14 | 2021-05-14 | 0 | 2021-05-14 | 2021-06-01 | 11 |  |  |  |  | 2021-02-18 | 2021-03-05 | 11 |  |  |  |  | 2021-06-22 | 2021-06-29 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-22 | 2021-06-22 | 0 | 2021-06-29 |  | 2021-06-30 | 1
400 | PGE | 95333 | NEM | EXPNEM | Commercial | Solar PV | 247.461 |  | 2021-02-19 | 2021-03-05 | 10 | 2021-03-23 | 22 | 2021-03-30 | 5 | [15 empty] | 2021-03-30 | 2021-05-03 | 24 | 2021-05-03 | 2021-05-27 | 18 |  |  |  |  | 2021-02-19 | 2021-03-05 | 10 |  |  |  |  | 2021-01-08 | 2021-06-29 | 119 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-01-08 | 2021-06-22 | 114 | 2021-06-29 |  | 2021-06-30 | 1
401 | PGE | 95242 | NEM | EXPNEM | Commercial | Solar PV | 53.611 |  | 2021-02-18 | 2021-03-04 | 10 | 2021-03-04 | 10 | 2021-03-23 | 13 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | 2021-04-05 | 9 |  |  |  |  | 2021-02-18 | 2021-03-05 | 11 |  |  |  |  | 2022-02-11 | 2022-02-17 | 4 | 2021-07-02 | 2021-11-08 | 89 |  |  |  | 2021-11-30 | 2022-02-07 | 48 | 1//19 | 1//19 |  |  |  |  | 2022-02-11 | 2022-02-11 | 0 | 2022-02-17 |  | 2022-02-18 | 1
402 | PGE | 93637 | NEM | EXPNEM | Commercial | Solar PV | 45.572 |  | 2021-01-21 | 2021-01-22 | 1 | 2021-03-01 | 26 | 2021-03-08 | 5 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-08-25 | 120 |  |  |  |  | 2021-01-21 | 2021-03-08 | 31 |  |  |  |  | 2021-08-28 | 2021-09-07 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-28 | 2021-08-30 | 0 | 2021-09-07 |  | 2021-09-15 | 6
403 | PGE | 94015 | NEM | EXPNEM | Commercial | Solar PV | 146.495 |  | 2021-02-22 | 2021-02-23 | 1 | 2021-03-03 | 7 | 2021-06-12 | 71 | [15 empty] | 2021-06-12 | 2021-06-12 | 0 | 2021-06-12 | 2021-06-18 | 4 |  |  |  |  | 2021-02-22 | 2021-04-29 | 48 |  |  |  |  | 2021-06-11 | 2021-12-08 | 123 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-11 | 2021-11-30 | 117 | 2021-12-08 |  | 2021-12-15 | 5
404 | PGE | 93610 | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-02-23 | 2021-03-09 | 10 | 2021-03-09 | 10 | 2021-03-29 | 14 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-06-03 | 20 |  |  |  |  | 2021-02-23 | 2021-03-12 | 13 | [16 empty] | 1//19 | 1//19
405 | PGE | 95020 | NEM | EXPNEM | IA in Progress | Solar PV | 666 |  | 2021-01-29 | 2021-02-01 | 1 | 2021-03-10 | 27 | 2021-04-13 | 24 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | [6 empty] | 2021-01-29 | 2021-05-07 | 69 | [16 empty] | 1//19 | 1//19
406 | PGE | 95304 | NEM | EXPNEM | Commercial | Solar PV | 437.5 |  | 2021-01-28 | 2021-02-10 | 9 | 2021-02-22 | 16 | 2021-03-05 | 9 | [15 empty] | 2021-03-05 | 2021-03-05 | 0 | 2021-03-05 | 2021-04-05 | 21 |  |  |  |  | 2021-01-28 | 2021-05-07 | 70 |  |  |  |  | 2021-12-03 | 2021-12-17 | 10 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-03 | 2021-12-03 | 0 | 2021-12-17 |  | 2021-12-24 | 5
407 | PGE | 94587 | NEM | EXPNEM | IA in Progress | Solar PV | 36 |  | 2021-02-17 | 2021-02-18 | 1 | 2021-03-01 | 8 | 2021-03-19 | 14 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-04-09 | 15 |  |  |  |  | 2021-02-17 | 2021-03-12 | 17 |  |  |  |  | 2022-03-31 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 2022-03-31
408 | PGE | 95920 | NEM | EXPNEM | IA in Progress | Solar PV | 125 |  | 2021-02-11 | 2021-03-12 | 20 | 2021-03-26 | 30 | 2021-04-16 | 15 | 2021-04-16 | 2021-06-25 | 49 | 2021-07-02 | 2021-07-22 | 13 | 2021-07-22 | 2021-07-22 |  | 2021-07-22 | 2021-11-17 | 85 | 2021-07-22 |  |  | 2021-11-17 | 2021-11-17 | 0 | 2021-11-17 | 2022-03-28 | 89 |  |  |  |  | 2021-02-11 | 2021-03-15 | 21 | [16 empty] | 1//19 | 1//19
409 | PGE | 94538 | NEM | EXPNEM | Withdrawn | Solar PV | 600 |  | 2021-01-29 | 2021-02-01 | 1 | 2021-03-09 | 26 | 2021-03-27 | 13 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | [6 empty] | 2021-01-29 | 2021-03-15 | 30 | [16 empty] | 1//19 | 1//19
410 | PGE | 95122 | NEM | EXPNEM | IA in Progress | Solar PV | 633.3 |  | 2021-01-29 | 2021-02-01 | 1 | 2021-03-09 | 26 | 2021-04-13 | 25 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | [6 empty] | 2021-01-29 | 2021-03-15 | 30 | [16 empty] | 1//19 | 1//19
412 | PGE | 94578 | NEM | EXPNEM | Withdrawn | Solar PV | 766.6 |  | 2021-01-29 | 2021-02-01 | 1 | 2021-03-16 | 31 | 2021-07-08 | 80 | [15 empty] | 2021-07-08 | 2021-07-09 | 1 | 2021-07-09 | [6 empty] | 2021-01-29 | 2021-03-18 | 33 | [16 empty] | 1//19 | 1//19
413 | PGE | 93725 | NEM | EXPNEM | Commercial | Solar PV | 34.8 |  | 2021-03-03 | 2021-03-17 | 10 | 2021-05-26 | 60 | 2021-06-10 | 10 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-08-02 | 36 |  |  |  |  | 2021-03-03 | 2021-03-24 | 15 |  |  |  |  | 2021-10-26 | 2021-11-02 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-26 | 2021-10-26 | 0 | 2021-11-02 |  | 2021-11-03 | 1
414 | PGE | 95236 | NEM | EXPNEM | Commercial | Solar PV | 43.421 |  | 2021-03-03 | 2021-03-17 | 10 | 2021-05-10 | 48 | 2021-08-16 | 68 | [15 empty] | 2021-08-16 | 2021-08-25 | 7 | 2021-08-25 | 2021-09-01 | 5 |  |  |  |  | 2021-03-03 | 2021-03-25 | 16 |  |  |  |  | 2021-09-09 | 2021-11-16 | 47 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-09 | 2021-09-09 | 0 | 2021-11-16 |  | 2021-11-17 | 1
415 | PGE | 93446 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-04 | 2021-03-18 | 10 | 2021-04-24 | 36 | 2021-05-10 | 10 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2021-05-10 | 0 |  |  |  |  | 2021-03-04 | 2021-03-25 | 15 |  |  |  |  | 2021-06-11 | 2021-06-28 | 11 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-11 | 2021-06-24 | 9 | 2021-06-28 |  | 2021-06-29 | 1
416 | PGE | 93460 | NEM | EXPNEM | Commercial | Solar PV | 31.024 |  | 2021-03-04 | 2021-03-18 | 10 | 2021-05-03 | 42 | 2021-06-03 | 22 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-23 | 14 |  |  |  |  | 2021-03-04 | 2021-05-07 | 46 |  |  |  |  | 2021-06-30 | 2021-07-12 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-30 | 2021-07-01 | 1 | 2021-07-12 |  | 2021-07-13 | 1
417 | PGE | 95620 | NEM | EXPNEM | Commercial | Solar PV | 120 |  | 2021-03-05 | 2021-03-19 | 10 | 2021-05-24 | 56 | 2021-06-29 | 25 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | 2021-08-04 | 25 |  |  |  |  | 2021-03-05 | 2021-03-25 | 14 |  |  |  |  | 2021-09-13 | 2021-09-20 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-13 | 2021-09-13 | 0 | 2021-09-20 |  | 2021-09-21 | 1
418 | PGE | 93445 | NEM | EXPNEM | IA in Progress | Solar PV | 375 |  | 2021-03-11 | 2021-03-15 | 2 | 2021-03-18 | 5 | 2021-05-20 | 45 | [15 empty] | 2021-05-20 | 2021-06-08 | 12 | 2021-06-08 | [6 empty] | 2021-03-11 | 2021-03-25 | 10 | [16 empty] | 1//19 | 1//19
419 | PGE | 95112 | NEM | EXPNEM | IA in Progress | Solar PV | 800 |  | 2021-01-29 | 2021-02-01 | 1 | 2021-03-25 | 38 | 2021-06-07 | 51 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [6 empty] | 2021-01-29 | 2021-03-25 | 38 | [16 empty] | 1//19 | 1//19
420 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 78.716 |  | 2021-03-05 | 2021-03-19 | 10 | 2021-03-19 | 10 | 2021-04-05 | 11 | [15 empty] | 2021-06-25 | 2021-06-25 | 0 | 2021-06-25 | 2021-06-29 | 2 |  |  |  |  | 2021-03-05 | 2021-03-25 | 14 |  |  |  |  | 2021-06-30 | 2021-07-12 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-30 | 2021-07-01 | 1 | 2021-07-12 |  | 2021-07-13 | 1
421 | PGE | 93637 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-01-27 | 2021-01-28 | 1 | 2021-02-03 | 5 | 2021-02-20 | 11 | [15 empty] | 2021-02-20 | 2021-02-20 | 0 | 2021-02-20 | 2021-08-24 | 129 |  |  |  |  | 2021-01-27 | 2021-06-15 | 97 |  |  |  |  | 2021-08-27 | 2021-09-07 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-27 | 2021-08-30 | 1 | 2021-09-07 |  | 2021-09-14 | 5
422 | PGE | 94545 | NEM | EXPNEM | IA in Progress | Solar PV | 78.723 |  | 2021-03-12 | 2021-03-16 | 2 | 2021-03-23 | 7 | 2021-04-07 | 11 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-08-10 | 87 |  |  |  |  | 2021-03-12 | 2021-03-25 | 9 |  |  |  |  | 2022-03-24 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 2022-03-24 | 2022-03-24 | 0
423 | PGE | 93637 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-02-22 | 2021-02-26 | 4 | 2021-03-11 | 13 | 2021-03-27 | 11 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | 2021-04-20 | 16 |  |  |  |  | 2021-02-22 | 2021-03-29 | 25 |  |  |  |  | 2021-10-18 | 2022-03-15 | 101 | 2021-07-09 |  | 193 |  |  |  | 2021-08-02 |  | 177 | 1//19 | 1//19 |  |  |  |  | 2021-10-18 | 2022-03-08 | 96 | 2022-03-15 |  | 2022-03-17 | 2
424 | PGE | 93652 | NEM | EXPNEM | Commercial | Solar PV | 250 |  | 2021-03-10 | 2021-03-24 | 10 | 2021-03-24 | 10 | 2021-04-13 | 14 | [15 empty] | 2021-04-13 | 2021-05-18 | 25 | 2021-05-18 | 2021-06-08 | 14 |  |  |  |  | 2021-03-10 | 2021-03-31 | 15 |  |  |  |  | 2021-07-30 | 2021-08-10 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-30 | 2021-08-02 | 1 | 2021-08-10 |  | 2021-08-11 | 1
425 | PGE | 95008 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-03-09 | 2021-03-10 | 1 | 2021-03-16 | 5 | 2021-04-02 | 13 | [15 empty] | 2021-04-02 | 2021-04-02 | 0 | 2021-04-02 | 2021-04-05 | 1 |  |  |  |  | 2021-03-09 | 2021-04-29 | 37 | [16 empty] | 1//19 | 1//19
426 | PGE | 95236 | NEM | EXPNEM | Implementation | Solar PV | 420 |  | 2021-03-09 | 2021-03-23 | 10 | 2021-07-02 | 82 | 2021-07-20 | 11 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-07-23 | 3 |  |  |  |  | 2021-03-09 | 2021-06-18 | 72 | [7 empty] | 2021-09-16 | 2022-02-24 | 111 |  |  |  | 2022-03-29 |  | 11 | 1//19 | 1//19
427 | PGE | 95304 | NEM | EXPNEM | IA in Progress | Solar PV | 96 |  | 2021-02-09 | 2021-02-10 | 1 | 2021-03-24 | 30 | 2021-04-06 | 9 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2022-03-25 | 245 |  |  |  |  | 2021-02-09 | 2021-04-02 | 37 | [16 empty] | 1//19 | 1//19
428 | PGE | 95376 | NEM | EXPNEM | Commercial | Solar PV | 600 |  | 2021-03-19 | 2021-03-23 | 2 | 2021-03-29 | 6 | 2021-04-06 | 6 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-12-16 | 176 |  |  |  |  | 2021-03-19 | 2021-05-10 | 36 |  |  |  |  | 2021-12-31 | 2022-01-19 | 12 | 2021-11-09 | 2021-11-10 | 1 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-31 | 2022-01-10 | 6 | 2022-01-19 |  | 2022-01-21 | 2
429 | PGE | 95376 | NEM | EXPNEM | Commercial | Solar PV | 248.576 |  | 2021-03-19 | 2021-03-23 | 2 | 2021-03-30 | 7 | 2021-04-06 | 5 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2022-01-12 | 195 |  |  |  |  | 2021-03-19 | 2021-05-07 | 35 |  |  |  |  | 2022-01-12 | 2022-01-18 | 3 | 2021-11-09 | 2021-11-10 | 1 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 2022-01-12 | 2022-01-12 | 0 | 2022-01-18 |  | 2022-01-31 | 9
430 | PGE | 93301 | NEM | EXPNEM | Commercial | Solar PV | 237.128 |  | 2021-03-11 | 2021-03-25 | 10 | 2021-05-24 | 52 | 2021-06-28 | 24 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-07-09 | 8 |  |  |  |  | 2021-03-11 | 2021-04-05 | 17 |  |  |  |  | 2021-08-18 | 2021-08-25 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-18 | 2021-08-18 | 0 | 2021-08-25 |  | 2021-08-26 | 1
431 | PGE | 93611 | NEM | EXPNEM | Commercial | Solar PV | 37.529 |  | 2021-03-12 | 2021-03-26 | 10 | 2021-05-25 | 52 | 2021-06-08 | 9 | [15 empty] | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-06-14 | 4 |  |  |  |  | 2021-03-12 | 2021-04-05 | 16 |  |  |  |  | 2021-07-26 | 2021-08-12 | 13 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-26 | 2021-08-05 | 8 | 2021-08-12 |  | 2021-08-13 | 1
432 | PGE | 96080 | NEM | EXPNEM | IA in Progress | Solar PV | 97.072 |  | 2021-03-23 | 2021-03-25 | 2 | 2021-04-14 | 16 | 2021-05-04 | 14 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | [6 empty] | 2021-03-23 | 2021-04-05 | 9 | [16 empty] | 1//19 | 1//19
433 | PGE | 95973 | NEM | EXPNEM | Commercial | Solar PV | 38.528 |  | 2021-02-22 | 2021-02-23 | 1 | 2021-03-25 | 23 | 2021-04-05 | 7 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-05-10 | 25 |  |  |  |  | 2021-02-22 | 2021-06-17 | 82 |  |  |  |  | 2021-07-02 | 2021-07-23 | 14 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-02 | 2021-07-15 | 8 | 2021-07-23 |  | 2021-08-04 | 8
434 | PGE | 95236 | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-03-23 | 2021-03-25 | 2 | 2021-03-25 | 2 | 2021-04-06 | 8 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-05-19 | 31 |  |  |  |  | 2021-03-23 | 2021-04-05 | 9 |  |  |  |  | 2021-08-03 | 2021-08-10 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-03 | 2021-08-03 | 0 | 2021-08-10 |  | 2021-08-13 | 3
435 | PGE | 95236 | NEM | EXPNEM | Commercial | Solar PV | 142.054 |  | 2021-03-23 | 2021-03-25 | 2 | 2021-03-25 | 2 | 2021-04-06 | 8 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-05-19 | 31 |  |  |  |  | 2021-03-23 | 2021-04-05 | 9 |  |  |  |  | 2021-11-04 | 2021-12-31 | 38 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-04 | 2021-12-13 | 24 | 2021-12-31 |  | 2022-01-05 | 3
436 | PGE | 94545 | NEM | EXPNEM | IA in Progress | Solar PV | 52.163 |  | 2021-03-12 | 2021-03-16 | 2 | 2021-03-25 | 9 | 2021-04-12 | 12 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-08-10 | 84 |  |  |  |  | 2021-03-12 | 2021-04-05 | 16 |  |  |  |  | 2022-03-31 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 2022-03-31 | 2022-03-31 | 0
437 | PGE | 95317 | NEM | EXPNEM | Commercial | Solar PV | 720 |  | 2021-02-16 | 2021-03-02 | 10 | 2021-05-10 | 59 | 2021-06-01 | 15 | 2021-06-01 | 2021-06-21 | 14 | [12 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-07-20 | 20 |  |  |  |  | 2021-02-16 | 2021-04-12 | 39 |  |  |  |  | 2022-01-26 | 2022-02-02 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-01-26 | 2022-01-26 | 0 | 2022-02-02 |  | 2022-02-03 | 1
439 | PGE | 93609 | NEM | EXPNEM | Commercial | Solar PV | 85.259 |  | 2021-02-24 | 2021-03-10 | 10 | 2021-03-27 | 22 | 2021-04-16 | 14 | [15 empty] | 2021-04-16 | 2021-06-02 | 32 | 2021-06-02 | 2021-06-07 | 3 |  |  |  |  | 2021-02-24 | 2021-04-12 | 33 |  |  |  |  | 2022-02-15 | 2022-02-24 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-02-15 | 2022-02-16 | 1 | 2022-02-24 |  | 2022-02-25 | 1
440 | PGE | 95131 | NEM | EXPNEM | Commercial | Solar PV | 40.153 |  | 2021-03-22 | 2021-03-24 | 2 | 2021-03-30 | 6 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-08-19 | 88 |  |  |  |  | 2021-03-22 | 2021-04-12 | 15 |  |  |  |  | 2021-10-29 | 2021-11-09 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-29 | 2021-10-29 | 0 | 2021-11-09 |  | 2021-11-12 | 2
441 | PGE | 93434 | NEM | EXPNEM | IA in Progress | Solar PV | 220 |  | 2021-03-28 | 2021-03-29 | 0 | 2021-03-30 | 1 | 2021-04-16 | 13 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | [6 empty] | 2021-03-28 | 2021-04-12 | 10 | [16 empty] | 1//19 | 1//19
442 | PGE | 93434 | NEM | EXPNEM | Commercial | Solar PV | 250 |  | 2021-03-28 | 2021-03-30 | 1 | 2021-03-30 | 1 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2022-03-11 | 228 |  |  |  |  | 2021-03-28 | 2021-04-12 | 10 |  |  |  |  | 2022-03-11 | 2022-03-24 | 9 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-03-11 | 2022-03-14 | 1 | 2022-03-24 |  | 2022-03-28 | 2
443 | PGE | 93647 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-02-15 | 2021-02-26 | 8 | 2021-02-26 | 8 | 2021-03-15 | 11 | [15 empty] | 2021-03-15 | 2021-06-01 | 55 | 2021-06-01 | 2021-07-07 | 25 |  |  |  |  | 2021-02-15 | 2021-05-18 | 65 |  |  |  |  | 2021-08-03 | 2021-08-19 | 12 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-03 | 2021-08-12 | 7 | 2021-08-19 |  | 2021-08-20 | 1
444 | PGE | 95236 | NEM | EXPNEM | Implementation | Solar PV | 46.625 |  | 2021-03-18 | 2021-04-01 | 10 | 2021-06-30 | 73 | 2021-07-16 | 11 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-16 | 2021-07-20 | 2 |  |  |  |  | 2021-03-18 | 2021-04-13 | 18 | [7 empty] | 2021-12-14 |  | 85 | [6 empty] | 1//19 | 1//19
445 | PGE | 93263 | NEM | EXPNEM | Commercial | Solar PV | 120 |  | 2021-03-17 | 2021-03-31 | 10 | 2021-05-03 | 33 | [5 empty] | 2021-05-03 | 2021-05-25 | 16 | 2021-05-25 | 2021-05-25 |  | 2021-05-25 | 2021-08-19 | 63 | 2021-05-25 |  |  | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-09-03 | 11 |  |  |  |  | 2021-03-17 | 2021-04-13 | 19 |  |  |  |  | 2021-12-14 | 2021-12-23 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-14 | 2021-12-15 | 1 | 2021-12-23 |  | 2021-12-24 | 1
446 | PGE | 94591 | NEM | EXPNEM | IA in Progress | Solar PV | 66.536 |  | 2021-03-24 | 2021-03-26 | 2 | 2021-03-30 | 4 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-29 | 10 |  |  |  |  | 2021-03-24 | 2021-04-13 | 14 | [16 empty] | 1//19 | 1//19
447 | PGE | 94591 | NEM | EXPNEM | IA in Progress | Solar PV | 59.764 |  | 2021-03-24 | 2021-03-26 | 2 | 2021-03-30 | 4 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | [6 empty] | 2021-03-24 | 2021-05-07 | 32 | [16 empty] | 1//19 | 1//19
448 | PGE | 94591 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-03-24 | 2021-03-26 | 2 | 2021-03-30 | 4 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-29 | 10 |  |  |  |  | 2021-03-24 | 2021-05-07 | 32 | [16 empty] | 1//19 | 1//19
449 | PGE | 95901 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-03-17 | 2021-03-30 | 9 | 2021-03-30 | 9 | 2021-04-19 | 14 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-04-28 | 7 |  |  |  |  | 2021-03-17 | 2021-04-13 | 19 |  |  |  |  | 2022-02-22 | 2022-03-02 | 6 | 2021-06-01 | 2021-10-26 | 103 |  |  |  | 2021-10-28 | 2022-02-11 | 72 | 1//19 | 1//19 |  |  |  |  | 2022-02-22 | 2022-02-23 | 1 | 2022-03-02 |  | 2022-03-03 | 1
450 | PGE | 94591 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-03-25 | 2021-03-26 | 1 | 2021-03-31 | 4 | 2021-05-21 | 37 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | [6 empty] | 2021-03-25 | 2021-05-07 | 31 | [16 empty] | 1//19 | 1//19
451 | PGE | 94544 | NEM | EXPNEM | Commercial | Solar PV | 76.296 |  | 2021-03-30 | 2021-03-31 | 1 | 2021-04-01 | 2 | 2021-06-02 | 43 | [15 empty] | 2021-06-02 | 2021-06-03 | 1 | 2021-06-03 | 2021-06-09 | 4 |  |  |  |  | 2021-03-30 | 2021-05-07 | 28 |  |  |  |  | 2021-08-18 | 2021-08-26 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-18 | 2021-08-19 | 1 | 2021-08-26 |  | 2021-08-30 | 2
452 | PGE | 93637 | NEM | EXPNEM | Implementation | Solar PV | 93.552 |  | 2021-03-25 | 2021-04-01 | 5 | 2021-04-05 | 7 | 2021-06-21 | 54 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-07-07 | 11 |  |  |  |  | 2021-03-25 | 2021-04-13 | 13 | [16 empty] | 1//19 | 1//19
453 | PGE | 94510 | NEM | EXPNEM | Commercial | Solar PV | 48.72 |  | 2020-12-30 | 2021-01-06 | 4 | 2021-03-12 | 49 | 2021-04-05 | 16 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-05-21 | 34 |  |  |  |  | 2021-04-01 | 2021-04-13 | 8 |  |  |  |  | 2021-08-20 | 2021-08-24 | 2 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-20 | 2021-08-20 | 0 | 2021-08-24 |  | 2021-08-27 | 3
454 | PGE | 93280 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-03-19 | 2021-04-02 | 10 | 2021-05-25 | 47 | 2021-06-03 | 6 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-10 | 5 |  |  |  |  | 2021-03-19 | 2021-04-14 | 18 |  |  |  |  | 2021-06-22 | 2021-06-29 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-22 | 2021-06-22 | 0 | 2021-06-29 |  | 2021-06-30 | 1
455 | PGE | 93242 | NEM | EXPNEM | Commercial | Solar PV | 300 |  | 2021-03-04 | 2021-03-17 | 9 | 2021-05-24 | 57 | 2021-06-08 | 10 | [15 empty] | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-07-07 | 20 |  |  |  |  | 2021-03-04 | 2021-04-14 | 29 |  |  |  |  | 2021-10-04 | 2021-10-11 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-04 | 2021-10-04 | 0 | 2021-10-11 |  | 2021-10-12 | 1
456 | PGE | 96080 | NEM | EXPNEM | IA in Progress | Solar PV | 125 |  | 2021-03-23 | 2021-04-06 | 10 | 2021-04-20 | 20 | 2021-06-22 | 44 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | [6 empty] | 2021-03-23 | 2021-04-14 | 16 | [16 empty] | 1//19 | 1//19
457 | PGE | 93280 | NEM | EXPNEM | Implementation | Solar PV | 43.593 |  | 2021-02-19 | 2021-03-05 | 10 | 2021-03-22 | 21 | 2021-05-10 | 35 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2021-06-01 | 15 |  |  |  |  | 2021-02-19 | 2021-04-14 | 38 | [16 empty] | 1//19 | 1//19
458 | PGE | 95206 | NEM | EXPNEM | IA in Progress | Solar PV, Storage | 1617.44 |  | 2021-03-03 | 2021-03-05 | 2 | 2021-03-31 | 20 | 2021-06-04 | 46 | 2021-06-15 | 2021-07-12 | 18 | 2021-09-28 | 2021-10-26 | 20 | 2021-10-26 | 2021-11-02 | 5 | 2021-12-16 | 2022-03-10 | 58 | 2021-11-02 | 2021-11-03 | 1 | 2022-03-24 | [9 empty] | 2021-03-03 | 2021-04-14 | 30 | [16 empty] | 1//19 | 1//19
459 | PGE | 94559 | NEM | EXPNEM | IA in Progress | Solar PV | 68.44 |  | 2021-03-17 | 2021-03-19 | 2 | 2021-04-02 | 12 | 2021-05-03 | 21 | [15 empty] | 2021-05-03 | 2021-05-04 | 1 | 2021-05-04 | 2021-06-16 | 30 |  |  |  |  | 2021-03-17 | 2021-04-14 | 20 | [16 empty] | 1//19 | 1//19
460 | PGE | 95361 | NEM | EXPNEM | Implementation | Solar PV | 110 |  | 2021-03-26 | 2021-04-06 | 7 | 2021-04-07 | 8 | 2021-05-13 | 26 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13 | 2021-05-17 | 2 |  |  |  |  | 2021-04-06 | 2021-04-14 | 6 | [16 empty] | 1//19 | 1//19
461 | PGE | 93908 | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-01-14 | 2021-01-15 | 1 | 2021-01-19 | 2 | 2021-01-26 | 5 | [15 empty] | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 2021-04-06 | 49 |  |  |  |  | 2021-01-14 | 2021-01-28 | 9 |  |  |  |  | 2021-04-09 | 2021-04-15 | 4 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-09 | 2021-04-12 | 1 | 2021-04-15 |  | 2021-04-19 | 2
462 | PGE | 94005 | NEM | EXPNEM | Commercial | Solar PV | 258.2 |  | 2021-03-09 | 2021-03-11 | 2 | 2021-03-17 | 6 | 2021-03-26 | 7 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-05 | 6 | [5 empty] | 0 | [5 empty] | 2021-04-06 | 2021-04-13 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-06 | 2021-04-07 | 1 | 2021-04-13 |  | 2021-04-16 | 3
463 | PGE | 94022 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.588 |  | 2021-03-25 | 2021-04-07 | 9 | 2021-04-07 | 9 | 2021-04-12 | 3 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-03-25 | 0 | [5 empty] | 0 |  |  | 2021-04-07 | 2021-04-20 | 9 | [12 empty] | 1//19 | 1//19
465 | PGE | 93301 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 933.1 |  | 2021-03-18 | 2021-04-01 | 10 | 2021-06-22 | 67 | 2021-07-26 | 23 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | [6 empty] | 2021-03-18 | 0 | [17 empty] | 1//19 | 1//19
466 | PGE | 95746 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.135 |  | 2021-03-18 | 2021-04-01 | 10 | 2021-04-24 | 26 | 2021-05-03 | 5 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | 2021-04-09 | 6 |  |  |  |  | 2021-05-03 | 2021-05-17 | 10 |  | 2021-05-03 | 2021-05-03 | 0 | 2021-06-04 | 2021-07-13 | 26 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-04 | 2021-06-28 | 16 | 2021-07-13 |  | 2021-07-14 | 1
467 | PGE | 93308 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 929 |  | 2021-03-17 | 2021-04-02 | 12 | 2021-06-22 | 68 | 2021-07-08 | 11 | 2021-07-27 | 2021-08-09 | 9 | [12 empty] | 2021-12-03 | 2021-12-03 | 0 | 2021-12-03 | [6 empty] | 2021-03-17 | 2021-05-10 | 38 | [16 empty] | 1//19 | 1//19
468 | PGE | 94553 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 |  | 2021-03-26 | 2021-04-09 | 10 | 2021-04-19 | 16 | 2021-05-06 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-03-26 | 0 | [5 empty] | 0 | [5 empty] | 2021-05-06 | 2021-05-06 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 |  | 2021-05-07 | 1
469 | PGE | 94611 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 32.424 |  | 2021-01-20 | 2021-02-03 | 10 | 2021-09-21 | 170 | 2021-09-30 | 7 | [15 empty] | 2021-02-03 | 2021-02-03 |  | 2021-02-03 | 2021-09-06 | 154 | [5 empty] | 0 | [5 empty] | 2021-09-30 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-30 | 2021-09-30 | 0
470 | PGE | 95032 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 87.158 |  | 2021-02-04 | 2021-02-05 | 1 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
471 | PGE | 95746 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.016 |  | 2021-01-25 | 2021-02-08 | 10 | 2021-05-26 | 86 | 2021-06-02 | 4 | [15 empty] | 2021-05-14 | 2021-05-14 |  | 2021-05-14 | 2021-05-14 | 1 | [5 empty] | 0 | [5 empty] | 2021-06-02 | 2021-06-02 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 |  | 2021-06-02 | 0
473 | PGE | 94941 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 46.393 |  | 2021-02-03 | 2021-02-18 | 10 | 2021-05-21 | 76 | 2021-05-26 | 3 | [15 empty] | 2021-05-21 | 2021-05-21 |  | 2021-05-21 | 2021-05-23 | 1 | [5 empty] | 0 | [5 empty] | 2021-06-07 | 2021-06-07 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 |  | 2021-06-07 | 0
474 | PGE | 94043 | NEM | NEM Paired Storage | Study in Progress | ENGN, Solar PV, Storage | 2503 |  | 2021-02-08 | 2021-02-22 | 9 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
475 | PGE | 94901 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.54 |  | 2021-02-08 | 2021-02-23 | 10 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
476 | PGE | 95035 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 405.19 |  | 2021-02-11 | 2021-02-24 | 8 | 2022-02-01 | 245 | [27 empty] | 2021-02-11 | 2021-05-25 | 72 | [16 empty] | 1//19 | 1//19
477 | PGE | 95035 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 399.09 |  | 2021-02-11 | 2021-02-24 | 8 | 2022-02-01 | 245 | [27 empty] | 2021-02-11 | 2021-05-25 | 72 | [16 empty] | 1//19 | 1//19
478 | PGE | 95669 | NEM | EXPNEM | Commercial | Solar PV, Storage | 349.179 |  | 2021-02-16 | 2021-02-26 | 8 | 2021-05-26 | 71 | 2021-06-30 | 24 | [15 empty] | 2021-06-30 | 2021-06-30 | 0 | 2021-06-30 | 2021-10-15 | 75 |  |  |  |  | 2021-02-16 | 2021-08-13 | 126 |  |  |  |  | 2021-10-21 | 2021-10-29 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-21 | 2021-10-21 | 0 | 2021-10-29 |  | 2021-11-03 | 3
480 | PGE | 95746 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 41.393 |  | 2021-02-26 | 2021-03-12 | 10 | 2021-04-23 | 40 | 2021-04-26 | 1 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-03-29 | 0 | [5 empty] | 0 | [5 empty] | 2021-04-26 | 2021-04-26 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 |  | 2021-04-26 | 0
481 | PGE | 93239 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1395.292 |  | 2021-03-04 | 2021-03-17 | 9 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
484 | PGE | 94027 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 37.6 |  | 2021-03-15 | 2021-03-26 | 9 | 2021-06-07 | 59 | 2021-06-15 | 6 | [15 empty] | 2021-03-26 | 2021-03-26 |  | 2021-03-26 | 2021-04-30 | 26 | [5 empty] | 0 | [5 empty] | 2021-06-15 | 2021-06-17 | 2 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-15 | 2021-06-15 | 0 | 2021-06-17 |  | 2021-06-17 | 0
485 | PGE | 93308 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1203.9 |  | 2021-03-17 | 2021-03-31 | 10 | 2021-06-22 | 68 | 2021-07-08 | 11 | 2021-07-27 | 2021-08-09 | 9 | [12 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | [6 empty] | 2021-03-17 | 0 | [17 empty] | 1//19 | 1//19
486 | PGE | 96080 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 271.598 |  | 2021-03-17 | 2021-03-31 | 10 | 2021-06-04 | 56 | 2021-07-23 | 34 | [15 empty] | 2021-07-23 | 2021-07-23 | 0 | 2021-07-23 | 2021-08-09 | 11 | [5 empty] | 0 | [5 empty] | 2022-02-01 | 2022-03-08 | 24 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-02-01 | 2022-03-02 | 20 | 2022-03-08 |  | 2022-03-09 | 1
487 | PGE | 95014 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 39.195 |  | 2021-03-25 | 2021-03-31 | 4 | 2021-06-17 | 59 | 2021-07-12 | 16 | [15 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | 2021-06-21 | 57 |  | 2021-08-31 | 2021-10-06 | 25 |  | 0 | [5 empty] | 2021-07-12 | 2021-07-12 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 |  | 2021-07-12 | 0
488 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1572 |  | 2021-02-03 | 2021-02-05 | 2 | 2021-02-10 | 5 | 2021-04-16 | 46 | 2021-04-23 | 2021-06-22 | 41 | [12 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-09-20 | 62 |  |  |  |  | 2021-02-03 | 0 | [8 empty] | 2021-12-23 |  |  | 2021-12-23 | [5 empty] | 1//19 | 1//19
489 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1872 |  | 2021-02-03 | 2021-02-05 | 2 | 2021-02-17 | 9 | 2021-04-20 | 44 | 2021-04-24 | 2021-06-24 | 42 | [12 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-24 | 2021-10-05 | 71 |  |  |  |  | 2021-02-03 | 0 | [8 empty] | 2021-12-23 |  |  | 2021-12-23 | [5 empty] | 1//19 | 1//19
490 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1542.8 |  | 2021-02-03 | 2021-02-05 | 2 | 2021-02-17 | 9 | 2021-04-20 | 44 | 2021-04-23 | 2021-06-23 | 42 | [12 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-09-21 | 62 |  |  |  |  | 2021-02-03 | 0 | [8 empty] | 2021-12-23 |  |  | 2021-12-23 | [5 empty] | 1//19 | 1//19
492 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1359.5 |  | 2021-01-29 | 2021-02-05 | 5 | 2021-04-07 | 47 | 2021-04-28 | 15 | 2021-05-10 | 2021-06-24 | 32 | [12 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-24 | 2021-09-21 | 61 |  |  |  |  | 2021-01-29 | 0 | [17 empty] | 1//19 | 1//19
493 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1280.3 |  | 2021-01-29 | 2021-02-05 | 5 | 2021-04-07 | 47 | 2021-04-28 | 15 | 2021-06-02 | 2021-06-30 | 20 | [12 empty] | 2021-06-30 | 2021-06-30 | 0 | 2021-06-30 | 2021-10-05 | 67 |  |  |  |  | 2021-01-29 | 0 | [17 empty] | 1//19 | 1//19
494 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1272 |  | 2021-02-03 | 2021-02-08 | 3 | 2021-04-07 | 44 | 2021-04-28 | 15 | 2021-05-07 | 2021-06-21 | 30 | [12 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-09-21 | 64 |  |  |  |  | 2021-02-03 | 0 | [17 empty] | 1//19 | 1//19
495 | PGE | 94945 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 |  | 2021-03-26 | 2021-04-07 | 8 | 2021-04-07 | 8 | 2021-04-30 | 17 | [26 empty] | 0 | [5 empty] | 2021-04-30 | 2021-04-30 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-30 | 2021-04-30 | 0 | 2021-04-30 |  | 2021-05-03 | 1
496 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1309.5 |  | 2021-01-29 | 2021-02-13 | 10 | 2021-04-09 | 49 | 2021-05-07 | 20 | 2021-05-28 | 2021-06-28 | 20 | [12 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-10-05 | 69 |  |  |  |  | 2021-01-29 | 0 | [17 empty] | 1//19 | 1//19
497 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1405.3 |  | 2021-02-03 | 2021-02-16 | 8 | 2021-04-10 | 46 | 2021-05-07 | 19 | 2021-06-01 | 2021-06-29 | 20 | [12 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | 2021-10-05 | 68 |  |  |  |  | 2021-02-03 | 0 | [17 empty] | 1//19 | 1//19
499 | PGE | 94549 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.559 |  | 2021-03-31 | 2021-04-14 | 10 | 2021-04-14 | 10 | 2021-04-22 | 6 | [15 empty] | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 | 2021-06-08 | 32 |  |  |  |  | 2021-03-31 | 2021-06-03 | 45 |  |  |  |  | 2021-06-08 | 2021-06-14 | 4 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-08 | 2021-06-14 | 4 | 2021-06-08 |  | 2021-06-08 | 1
500 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1547 |  | 2021-02-03 | 2021-02-04 | 1 | 2021-02-10 | 5 | 2021-04-08 | 40 | 2021-04-14 | 2021-06-22 | 48 | [12 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-09-20 | 62 |  |  |  |  | 2021-02-03 | 0 | [8 empty] | 2021-12-23 |  |  | 2021-12-23 | [5 empty] | 1//19 | 1//19
501 | PGE | 93923 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 39.248 |  | 2021-03-27 | 2021-04-06 | 6 | 2021-04-06 | 6 | 2021-04-08 | 2 | [26 empty] | 0 | [17 empty] | 1//19 | 1//19
502 | PGE | 93619 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 647.732 |  | 2021-02-08 | 2021-02-10 | 2 | 2021-03-10 | 21 | 2021-03-31 | 15 | 2021-04-09 | 2021-05-03 | 16 | [12 empty] | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | 2021-07-30 | 62 |  |  |  |  | 2021-02-08 | 0 |  | 2022-02-09 | 2022-02-09 | 2022-02-09 | 0 |  |  |  | 2021-09-22 |  |  | 2021-09-22 | [5 empty] | 1//19 | 1//19
503 | PGE | 96080 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 39.229 |  | 2021-03-25 | 2021-03-31 | 4 | 2021-04-01 | 5 | 2021-04-21 | 14 | [15 empty] | 2021-03-31 | 2021-04-01 | 1 | 2021-04-01 | 2021-04-01 | 0 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
505 | PGE | 95949 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 39.4 |  | 2021-01-07 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-15 | 3 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
506 | PGE | 95663 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.828 |  | 2021-02-10 | 2021-02-18 | 5 | 2021-02-18 | 5 | 2021-02-22 | 2 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-05-11 | 58 | [5 empty] | 0 | [5 empty] | 2021-05-11 | 2021-05-13 | 2 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-11 | 2021-05-13 | 2 | 2021-05-13 |  | 2021-05-13 | 0
507 | PGE | 94022 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.877 |  | 2021-02-03 | 2021-02-06 | 2 | 2021-02-19 | 11 | 2021-03-03 | 8 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-07-08 | 89 | [5 empty] | 0 | [5 empty] | 2021-07-08 | 2021-07-08 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 |  | 2021-07-09 | 1
511 | PGE | 94558 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 45.177 |  | 2021-02-08 | 2021-02-23 | 10 | 2021-03-16 | 25 | 2021-03-22 | 4 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-22 | 4 | [5 empty] | 0 | [5 empty] | 2021-04-28 | 2021-04-28 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 |  | 2021-04-28 | 0
512 | PGE | 94062 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.49 |  | 2021-02-09 | 2021-02-24 | 10 | 2021-03-16 | 24 | 2021-03-24 | 6 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-05-21 | 48 | [5 empty] | 0 | [5 empty] | 2021-05-26 | 2021-05-26 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 |  | 2021-05-27 | 1
513 | PGE | 93901 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.728 |  | 2021-03-05 | 2021-03-19 | 10 | 2021-03-19 | 10 | 2021-03-22 | 1 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-06-07 | 55 | [5 empty] | 0 | [5 empty] | 2021-06-09 | 2021-06-09 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 |  | 2021-06-09 | 0
514 | PGE | 95650 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 36.39 |  | 2021-03-08 | 2021-03-19 | 9 | 2021-04-08 | 23 | 2021-04-09 | 1 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-05-06 | 34 |  | 2021-09-03 | 2021-09-16 | 8 |  | 0 | [5 empty] | 2022-03-31 | 2022-03-31 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-03-31 | 2022-03-31 | 0 | 2022-03-31 |  | 2022-03-31 | 0
515 | PGE | 94074 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 31.997 |  | 2021-03-09 | 2021-03-20 | 8 | 2021-03-20 | 8 | 2021-05-19 | 42 | [15 empty] | 2021-03-20 | 2021-03-20 | 0 | 2021-03-20 | 2021-12-03 | 178 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
518 | PGE | 95247 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 30.08 |  | 2021-03-11 | 2021-03-24 | 9 | [19 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
521 | PGE | 94507 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 42.716 |  | 2021-03-12 | 2021-03-25 | 9 | 2021-03-25 | 9 | 2021-03-29 | 2 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-04-20 | 18 | [5 empty] | 0 | [5 empty] | 2021-04-20 | 2021-04-20 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 |  | 2021-04-20 | 0
523 | PGE | 94526 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.715 |  | 2021-03-15 | 2021-03-27 | 9 | 2021-04-15 | 23 | 2021-04-20 | 3 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | 2021-04-16 | 14 | [5 empty] | 0 | [5 empty] | 2021-04-20 | 2021-09-22 | 108 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-20 | 2021-07-20 | 63 | 2021-09-22 |  | 2021-09-22 | 0
524 | PGE | 94574 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 38.545 |  | 2021-03-15 | 2021-03-29 | 10 | 2021-03-29 | 10 | 2021-04-15 | 13 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-04-21 | 17 | [5 empty] | 0 | [5 empty] | 2021-11-22 | 2022-01-27 | 45 | 2021-12-30 |  | 74 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-22 | 2022-01-14 | 37 | 2022-01-27 | 2022-01-31 |  | 2 |  |  | 223
526 | PGE | 95425 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 |  | 2021-03-16 | 2021-03-29 | 9 | 2021-03-29 | 9 | 2021-03-30 | 1 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-05-05 | 27 | [5 empty] | 0 | [5 empty] | 2021-05-05 | 2021-05-05 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 |  | 2021-05-05 | 0
528 | PGE | 95030 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 38.86 |  | 2021-03-22 | 2021-04-05 | 10 | 2021-05-05 | 32 | 2021-05-24 | 13 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-04-15 | 8 | [5 empty] | 0 | [5 empty] | 2021-05-28 | 2021-05-28 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 |  | 2021-05-28 | 0
532 | PGE | 94534 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-03-24 | 2021-04-07 | 10 | 2021-04-07 | 10 | 2021-04-20 | 9 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-07 | 0 | [5 empty] | 0 | [5 empty] | 2021-04-20 | 2021-04-21 | 1 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-20 | 2021-04-21 | 1 | 2021-04-21 |  | 2021-04-21 | 0
533 | PGE | 95762 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-03-24 | 2021-04-07 | 10 | 2021-04-07 | 10 | 2021-04-09 | 2 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-05-11 | 24 |  |  |  |  | 2021-03-24 | 2021-04-15 | 16 |  |  |  |  | 2021-05-11 | 2021-05-21 | 8 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-11 | 2021-05-12 | 1 | 2021-05-21 |  | 2021-05-21 | 0
534 | PGE | 95682 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 42.497 |  | 2021-03-25 | 2021-04-08 | 10 | 2021-04-15 | 15 | 2021-04-16 | 1 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | 2021-05-10 | 22 |  |  |  |  | 2021-03-25 | 2021-04-21 | 19 |  |  |  |  | 2021-05-10 | 2021-05-17 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-10 | 2021-05-10 | 0 | 2021-05-17 |  | 2021-05-17 | 0
535 | PGE | 95065 | NEM | NEM Paired Storage | Commercial | OTHR, Solar PV, Storage | 30.246 |  | 2021-01-27 | 2021-02-10 | 10 | 2021-04-06 | 48 | 2021-04-08 | 2 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | 2021-11-05 | 148 | [5 empty] | 0 | [5 empty] | 2021-11-05 | 2021-11-08 | 1 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-05 | 2021-11-08 | 1 | 2021-11-08 |  | 2021-11-08 | 0
537 | PGE | 94920 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.08 |  | 2021-03-30 | 2021-04-12 | 9 | 2021-04-12 | 9 | 2021-04-20 | 6 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-04-20 | 6 | [5 empty] | 0 | [5 empty] | 2021-10-22 | 2021-10-22 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 |  | 2021-10-22 | 0
538 | PGE | 95618 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 56.873 |  | 2021-02-23 | 2021-03-06 | 8 | 2021-03-06 | 8 | 2021-03-18 | 8 | [15 empty] | 2021-03-06 | 2021-03-06 | 0 | 2021-03-06 | 2021-04-01 | 18 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
540 | PGE | 94550 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31 |  | 2021-02-02 | 2021-02-16 | 9 | 2021-03-17 | 30 | 2021-03-25 | 6 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-04-09 | 17 | [5 empty] | 0 | [5 empty] | 2021-08-31 | 2021-08-31 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 |  | 2021-08-31 | 0
541 | PGE | 93901 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 51.699 |  | 2021-01-12 | 2021-01-23 | 7 | 2021-03-03 | 34 | 2021-03-23 | 14 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | 2021-11-03 | 158 |  |  |  |  | 2021-01-12 | 2021-03-05 | 36 |  |  |  |  | 2021-11-19 | 2021-12-16 | 17 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-19 | 2021-12-07 | 10 | 2021-12-16 |  | 2021-12-20 | 2
542 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1447 |  | 2021-01-29 | 2021-02-02 | 2 | 2021-02-10 | 8 | 2021-04-08 | 40 | 2021-04-14 | 2021-06-22 | 48 | [12 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-09-22 | 64 |  |  |  |  | 2021-01-29 | 2021-03-23 | 36 |  |  |  |  | 2022-03-24 | 2022-03-28 | 2 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-03-24 | 2022-03-25 | 1 | 2022-03-28
543 | PGE | 94027 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 96.54 |  | 2021-03-17 | 2021-03-31 | 10 | 2021-05-14 | 42 | 2021-06-02 | 12 | [15 empty] | 2021-06-02 | 2021-06-09 | 5 | 2021-06-09 | 2021-06-25 | 12 |  |  |  |  | 2021-03-17 | 2021-04-13 | 19 |  |  |  |  | 2021-07-07 | 2021-07-15 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-07 | 2021-07-15 | 6 | 2021-07-15 |  | 2021-07-16 | 1
545 | PGE | 95120 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 37.345 |  | 2021-03-23 | 2021-04-06 | 10 | 2021-04-06 | 10 | 2021-04-09 | 3 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-04-07 | 1 |  |  |  |  | 2021-03-23 | 2021-04-14 | 16 |  |  |  |  | 2021-04-23 | 2021-04-28 | 3 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-23 | 2021-04-23 | 0 | 2021-04-28 |  | 2021-04-28 | 0
546 | PGE | 95476 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 |  | 2021-03-12 | 2021-03-26 | 10 | 2021-03-26 | 10 | 2021-03-29 | 1 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-07 | 8 | [5 empty] | 0 | [5 empty] | 2021-04-13 | 2021-09-20 | 111 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-13 | 2021-09-13 | 106 | 2021-09-20 |  | 2021-09-20 | 0
547 | PGE | 95470 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-03-23 | 2021-04-06 | 10 | 2021-04-07 | 11 | 2021-04-09 | 2 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-04-06 | 0 | [5 empty] | 0 | [5 empty] | 2021-04-09 | 2021-04-09 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 |  | 2021-04-10 | 0
548 | PGE | 95492 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 |  | 2021-03-19 | 2021-04-02 | 10 | 2021-04-08 | 14 | 2021-04-09 | 1 | [15 empty] | 2021-04-02 | 2021-04-02 | 0 | 2021-04-02 | 2021-04-08 | 4 | [5 empty] | 0 | [5 empty] | 2021-04-09 | 2021-04-09 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 |  | 2021-04-10 | 0
550 | PGE | 94547 | Non-NEM | NEMFC | Commercial | FUCE | 262.5 |  | 2021-03-08 | 2021-03-11 | 3 | 2021-03-11 | 3 | 2021-04-16 | 26 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | 2021-04-05 | 17 |  |  |  |  | 2021-03-08 | 2021-05-27 | 58 |  |  |  |  | 2021-12-21 | 2021-12-23 | 2 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-21 | 2021-12-21 | 0 | 2021-12-23 |  | 2021-12-24 | 1
551 | PGE | 95448 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 59.575 |  | 2021-03-31 | 2021-04-16 | 12 | 2021-04-16 | 12 | 2021-05-13 | 19 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
552 | PGE | 94305 | NEM | NEMMT | IA in Progress | Solar PV, Storage | 31.34 |  | 2021-01-21 | 2021-02-04 | 10 | 2021-05-21 | 85 | 2021-06-02 | 7 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-06-03 | 8 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
553 | PGE | 95667 | NEM | NEMMT | Withdrawn | Solar PV, Storage | 894.727 |  | 2021-02-08 | 2021-02-22 | 9 | [29 empty] | 2021-02-08 | 0 | [8 empty] | 2021-03-29 | 2021-07-16 | 77 |  |  |  | 2021-11-03 | 2021-11-03 | 1 | 1//19 | 1//19
554 | PGE | 94080 | Non-NEM | NEMFC | IA in Progress | FUCE | 300 |  | 2021-02-17 | 2021-03-02 | 9 | 2021-05-13 | 61 | 2021-06-28 | 31 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
556 | PGE | 94590 | NEM | NEMMT | IA in Progress | ENGN, FUCE | 900 |  | 2021-03-16 | 2021-03-30 | 10 | 2021-07-23 | 91 | [5 empty] | 2021-07-23 | 2021-08-13 | 15 | 2021-08-13 | 2021-08-13 |  | 2021-08-16 | 2021-11-24 | 73 | 2021-08-13 |  |  | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
557 | PGE | 93450 | NEM | NEMMT | Study in Progress | Solar PV, Turbine | 11003 |  | 2021-01-12 | 2021-01-12 | 0 | 2021-02-03 | 15 | [5 empty] | 2021-02-03 | 2021-03-03 | 19 | 2021-03-03 | 2021-03-18 | 11 | 2021-05-20 | 2022-03-07 | 199 | 2021-03-18 | 2021-04-07 | 14 | [10 empty] | 2021-01-12 | 0 | [17 empty] | 1//19 | 1//19
558 | PGE | 93251 | NEM | NEMMT | Study in Progress | Solar PV, Storage, Turbine | 107640 |  | 2020-12-29 | 2021-01-04 | 3 | 2021-02-10 | 29 | [5 empty] | 2021-02-10 | 2021-03-22 | 27 | 2021-03-22 | 2021-04-12 | 15 | 2021-06-09 |  |  | 2021-04-12 | 2021-05-03 | 15 | [11 empty] | 0 | [17 empty] | 1//19 | 1//19
559 | PGE | 95625 | NEM | NEMMT | Implementation | ENGN, Solar PV, Storage | 4744 |  | 2021-01-29 | 2021-02-01 | 1 | 2021-02-17 | 12 | [5 empty] | 2021-02-17 | 2021-03-15 | 18 | 2021-03-15 | 2021-03-17 | 2 | 2021-03-29 | 2021-08-31 | 109 | 2021-03-17 | 2021-03-17 | 0 | 2021-10-01 | 2021-10-01 | 0 | 2021-10-01 | 2021-10-27 | 18 |  |  |  |  | 2021-01-29 | 0 | [8 empty] | 2021-10-19 |  |  | 2021-10-19 | 2022-01-05 08:18 | 51 |  |  |  | 1//19 | 1//19
560 | PGE | 94533 | NEM | NEMMT | Implementation | FUCE, Solar PV, WIND | 6689.431 |  | 2021-02-08 | 2021-02-22 | 9 | 2021-02-22 | 9 | [5 empty] | 2021-02-22 | 2021-04-30 | 49 | 2021-04-30 | 2021-04-30 | 0 | 2021-06-15 | 2021-09-24 | 71 | 2021-04-30 | 2021-05-06 | 4 | 2021-10-14 | 2021-10-19 | 3 | 2021-10-19 | 2021-11-08 | 14 | [5 empty] | 0 |  | 2021-08-10 | 2021-08-24 | 2021-11-05 | 10 | [12 empty] | 1//19 | 1//19
561 | PGE | 94583 | NEM | NEMMT | IA in Progress | FUCE, Solar PV, Storage | 2992.749 |  | 2021-02-11 | 2021-02-16 | 2 | 2021-03-03 | 13 | [5 empty] | 2021-03-03 | 2021-06-07 | 67 | 2021-06-07 | 2021-07-14 | 26 | 2021-08-23 | 2022-01-04 | 92 | 2021-07-14 | 2021-07-14 | 0 | 2022-01-24 | 2022-02-22 | 20 | 2022-02-22 | [6 empty] | 2021-02-11 | 0 | [8 empty] | 2022-03-01 |  |  | 2022-03-01 | [5 empty] | 1//19 | 1//19
562 | PGE | 95403 | NEM | NEMMT | Implementation | FUCE, Solar PV | 1350 |  | 2021-02-01 | 2021-02-17 | 11 | 2021-03-27 | 38 | [5 empty] | 2021-03-27 | 2021-04-23 | 19 | 2021-04-23 |  |  | 2021-04-23 | 2021-07-12 | 54 |  |  |  | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-12-02 | 99 |  |  |  |  | 2021-07-19 | 2021-08-05 | 13 | [10 empty] | 2021-12-27 | 2022-03-14 14:29 | 56 |  |  |  | 1//19 | 1//19
563 | PGE | 94080 | NEM | NEMMT | IA in Progress | FUCE, Solar PV | 769 |  | 2021-02-09 | 2021-02-22 | 8 | 2021-03-29 | 33 | 2021-07-07 | 70 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | [6 empty] | 2021-09-16 | 2021-09-22 | 4 | [16 empty] | 1//19 | 1//19
564 | PGE | 93280 | NEM | NEMMT | Commercial | FUCE, Solar PV | 249.5 |  | 2021-01-21 | 2021-02-04 | 10 | 2021-02-12 | 16 | 2021-03-05 | 14 | 2021-03-05 | 2021-04-02 | 20 | 2021-04-02 | 2021-05-07 | 25 | 2021-05-07 | 2021-05-24 | 11 | 2021-05-24 | 2021-08-06 | 55 | 2021-05-24 |  |  | 2021-10-18 | 2021-10-21 | 3 | 2021-10-21 | 2021-12-01 | 26 |  |  |  |  | 2021-01-21 | 0 |  | 2021-06-17 | [6 empty] | 2021-05-05 | 2021-05-05 | 0 |  |  |  | 2021-05-05 | 2021-05-05 | 1 | 1//19 | 1//19 | [7 empty] | 0 |  | 2022-02-28 | 0 | 2022-02-25 | 0 | 0
565 | PGE | 95033 | NEM | NEMMT | Commercial | Solar PV, Storage | 30.104 |  | 2021-03-05 | 2021-03-17 | 8 | 2021-03-17 | 8 | 2021-03-22 | 3 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-04-19 | 23 | [5 empty] | 0 | [5 empty] | 2021-04-19 | 2021-04-23 | 4 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-19 | 2021-04-19 | 0 | 2021-04-23 |  | 2021-04-23 | 0
566 | PGE | 95449 | Non-NEM | Non-Export | Commercial | Storage | 140 |  | 2021-02-09 | 2021-02-11 | 2 | 2021-03-03 | 15 | 2021-04-20 | 34 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-08-09 | 77 |  |  |  |  | 2021-03-04 | 2021-03-04 | 0 |  |  |  |  | 2021-12-15 | 2021-12-22 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-15 | 2021-12-15 | 0 | 2021-12-22 |  | 2021-12-24 | 2 | 2021-12-01 | 17 | 0
567 | PGE | 95449 | Non-NEM | Non-Export | Commercial | Storage | 140 |  | 2021-02-10 | 2021-02-11 | 1 | 2021-03-03 | 14 | 2021-05-19 | 55 | [15 empty] | 2021-05-19 | 2021-05-19 | 0 | 2021-05-19 | 2021-08-16 | 61 |  |  |  |  | 2021-02-10 | 2021-03-05 | 16 |  |  |  |  | 2021-12-15 | 2021-12-22 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-15 | 2021-12-15 | 0 | 2021-12-22 |  | 2021-12-24 | 2 | 2021-12-15 | 7 | 0
568 | PGE | 96080 | Non-NEM | Non-Export | Commercial | Storage | 350 |  | 2021-01-13 | 2021-01-14 | 1 | 2021-02-03 | 14 | 2021-05-27 | 80 | [15 empty] | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-08-10 | 51 | [5 empty] | 0 | [5 empty] | 2021-12-21 | 2021-12-30 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-21 | 2021-12-24 | 3 | 2021-12-30 |  | 2021-12-31 | 1 | 2021-12-20 | 9 | 0
569 | PGE | 95945 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-01-15 | 2021-01-19 | 1 | 2021-02-03 | 12 | 2021-06-10 | 89 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-08-30 | 56 |  |  |  |  | 2021-07-09 | 2021-08-06 | 20 | [16 empty] | 1//19 | 1//19
570 | PGE | 95726 | Non-NEM | Non-Export | Commercial | Storage | 350 |  | 2021-02-09 | 2021-02-11 | 2 | 2021-03-03 | 15 | 2021-04-19 | 33 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-06-07 | 34 | [5 empty] | 0 | [5 empty] | 2022-03-11 | 2022-03-25 | 10 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-03-11 | 2022-03-14 | 1 | 2022-03-25 |  | 2022-03-30 | 3 | 2022-03-10 | 14 | 0
571 | PGE | 95709 | Non-NEM | Non-Export | Commercial | Storage | 350 |  | 2021-02-09 | 2021-02-11 | 2 | 2021-03-03 | 15 | 2021-06-23 | 79 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-09-30 | 69 | [5 empty] | 0 | [5 empty] | 2022-01-19 | 2022-02-04 | 12 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-01-19 | 2022-01-19 | 0 | 2022-02-04 |  | 2022-02-08 | 2
572 | PGE | 95449 | Non-NEM | Non-Export | Commercial | Storage | 140 |  | 2021-02-23 | 2021-02-24 | 1 | 2021-03-10 | 11 | 2021-04-15 | 26 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-08-09 | 80 |  |  |  |  | 2021-02-23 | 2021-05-21 | 63 |  |  |  |  | 2021-12-08 | 2021-12-22 | 10 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-08 | 2021-12-08 | 0 | 2021-12-22 |  | 2021-12-22 | 0
573 | PGE | 95606 | Non-NEM | Non-Export | Implementation | ENGN, Solar PV | 21944.2 |  | 2021-02-22 | 2021-02-23 | 1 | 2021-03-17 | 17 | 2021-04-15 | 21 | 2021-05-05 | 2021-06-04 | 21 | [12 empty] | 2021-06-04 | 2021-06-23 | 13 | 2021-06-23 | 2021-08-19 | 40 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
574 | PGE | 95134 | Non-NEM | Non-Export | Withdrawn | Storage | 3000 |  | 2021-03-22 | 2021-03-23 | 1 | 2021-03-31 | 7 | [28 empty] | 0 | [17 empty] | 1//19 | 1//19
575 | PGE | 94560 | Non-NEM | Non-Export | Withdrawn | Storage – EV | 153.6 |  | 2021-02-08 | 2021-02-09 | 1 | 2021-02-24 | 11 | 2021-03-01 | 3 | [26 empty] | 0 | [17 empty] | 1//19 | 1//19
576 | PGE | 94566 | Non-NEM | Non-Export | Withdrawn | Storage | 1287 |  | 2021-02-20 | 2021-02-22 | 0 | 2021-03-03 | 7 | 2021-03-24 | 15 | 2021-04-07 | 2021-05-05 | 20 | [12 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-06-22 | 33 |  |  |  |  | 2021-02-20 | 0 | [17 empty] | 1//19 | 1//19
577 | PGE | 95501 | Non-NEM | Non-Export | Implementation | Storage | 980 |  | 2021-01-04 | 2021-01-05 | 1 | 2021-02-03 | 21 | 2021-07-20 | 116 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-08-16 | 135 |  |  |  |  | 2021-01-04 | 0 | [17 empty] | 1//19 | 1//19
578 | PGE | 95304 | Non-NEM | Non-Export | Commercial | ENGN, Solar PV | 766.6 |  | 2021-01-12 | 2021-01-14 | 2 | 2021-01-27 | 10 | 2021-03-01 | 22 | [15 empty] | 2021-03-19 | 2021-03-22 | 1 | 2021-03-22 | 2021-06-24 | 67 | [5 empty] | 0 | [5 empty] | 2021-10-21 | 2021-11-01 | 7 | 2021-08-05 | 2022-04-03 | 167 |  |  |  | 2022-04-03 | 2022-04-03 | 1 | 1//19 | 1//19 |  |  |  |  | 2021-10-21 | 2021-10-22 | 1 | 2021-11-01 |  | 2021-11-01 | 0
579 | PGE | 93657 | Non-NEM | Non-Export | Implementation | Storage | 1287 |  | 2021-02-20 | 2021-02-22 | 0 | 2021-03-03 | 7 | 2021-03-24 | 15 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-06-22 | 63 |  |  |  |  | 2021-02-20 | 0 | [17 empty] | 1//19 | 1//19
580 | PGE | 95540 | Non-NEM | Non-Export | Withdrawn | Storage | 140 |  | 2021-02-26 | 2021-03-01 | 1 | 2021-03-24 | 18 | [17 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
581 | PGE | 95623 | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2021-03-03 | 2021-03-05 | 2 | 2021-03-24 | 15 | 2021-05-07 | 32 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-07-02 | 69 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
582 | PGE | 94063 | Non-NEM | Non-Export | Commercial | Storage | 715 |  | 2021-02-18 | 2021-02-19 | 1 | 2021-03-03 | 9 | 2021-04-13 | 29 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-05-04 | 15 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 2021-09-24 | 2021-10-04 | 6 |  |  |  | 2021-10-21 |  | 2021-10-21 | 1 | 2021-10-21 | 0 | 0
583 | PGE | 95709 | Non-NEM | Non-Export | Implementation | Storage | 420 |  | 2021-02-17 | 2021-02-18 | 1 | 2021-03-10 | 15 | 2021-04-14 | 25 | [15 empty] | 2021-04-14 | 2021-04-14 | 0 | 2021-04-14 | 2021-07-13 | 62 |  |  |  |  | 2021-02-17 | 2021-05-07 | 57 | [16 empty] | 1//19 | 1//19
584 | PGE | 95521 | Non-NEM | Non-Export | Withdrawn | Storage | 70 |  | 2021-01-05 | 2021-01-06 | 1 | 2021-01-27 | 15 | 2021-03-09 | 28 | [15 empty] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | [6 empty] | 2021-01-05 | 2021-02-05 | 22 | [16 empty] | 1//19 | 1//19
585 | PGE | 95969 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-01-15 | 2021-01-19 | 1 | 2021-02-03 | 12 | 2021-03-11 | 25 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | 2021-06-02 | 58 |  |  |  |  | 2021-01-15 | 2021-02-09 | 16 |  |  |  |  | 2022-01-11 | 2022-01-20 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-01-11 | 2022-01-12 | 1 | 2022-01-20 |  | 2022-01-21 | 1 | 2021-12-29 | 16 | 0
586 | PGE | 95223 | Non-NEM | Non-Export | IA in Progress | Storage | 210 |  | 2021-02-11 | 2021-02-16 | 2 | 2021-03-03 | 13 | 2021-06-23 | 79 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | [6 empty] | 2021-02-11 | 2021-03-16 | 22 | [16 empty] | 1//19 | 1//19
587 | PGE | 93660 | Non-NEM | RESBCT | Implementation | Solar PV | 3500 |  | 2021-03-30 | 2021-03-30 | 0 | 2021-04-21 | 16 | [5 empty] | 2021-04-21 | 2021-05-11 | 14 | 2021-05-11 | 2021-05-11 | 0 | 2021-05-19 | 2021-10-20 | 107 | 2021-05-11 | 2021-05-12 | 1 | 2021-10-25 | 2021-10-25 | 0 | 2021-10-25 | 2021-11-15 | 14 | [5 empty] | 0 | [8 empty] | 2022-03-16 |  | 20 | [6 empty] | 1//19 | 1//19
588 | PGE | 93250 | Non-NEM | RESBCT | Implementation | Solar PV | 2341.786 |  | 2021-02-16 | 2021-02-17 | 1 | 2021-02-24 | 6 | [5 empty] | 2021-03-03 | 2021-03-24 | 15 | 2021-03-24 | [8 empty] | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 | 2021-09-28 | 19 |  |  |  |  | 2021-02-16 | 0 | [8 empty] | 2022-03-11 |  | 23 | 2021-10-07 | 2021-12-28 11:20 | 59 |  |  |  | 1//19 | 1//19
589 | PGE | 95765 | Non-NEM | RESBCT | Implementation | Solar PV | 2782.651 |  | 2021-03-08 | 2021-03-09 | 1 | 2021-03-24 | 12 | 2021-04-13 | 14 | 2021-04-28 | 2021-07-01 | 45 | 2021-07-30 | 2021-08-26 | 19 | 2021-08-26 | 2021-08-26 | 0 | 2021-08-30 | 2021-11-15 | 53 | 2021-08-26 | 2021-08-26 | 0 | 2021-12-13 | 2021-12-14 | 1 | 2021-12-14 | 2022-02-10 | 41 |  |  |  |  | 2021-03-08 | 0 | [17 empty] | 1//19 | 1//19
590 | PGE | 93241 | NEM | VNEM | Commercial | Solar PV | 38.28 |  | 2021-03-24 | 2021-04-05 | 8 | 2021-04-29 | 26 | 2021-05-11 | 8 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2021-08-31 | 78 |  |  |  |  | 2021-03-24 | 2021-05-25 | 44 |  | 2021-05-11 | 2021-05-11 | 0 | 2021-09-09 | 2021-09-20 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-09 | 2021-09-10 | 1 | 2021-09-20 |  | 2021-10-05 | 11
591 | PGE | 94965 | NEM | VNEM | Study in Progress | Solar PV | 30.26 |  | 2021-01-22 | 2021-02-05 | 10 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
592 | PGE | 95912 | NEM | VNEM | Application Review in Progress | Solar PV | 31.024 |  | 2021-02-27 | 2021-03-10 | 7 | [26 empty] | 2021-08-24 | 2021-09-16 | 16 |  | 0 | [17 empty] | 1//19 | 1//19
593 | PGE | 94621 | NEM | VNEM | Commercial | Solar PV | 86.4 |  | 2021-03-15 | 2021-03-23 | 6 | 2021-06-16 | 66 | 2021-09-03 | 56 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-20 | 10 |  |  |  |  | 2021-06-17 | 2021-07-02 | 11 |  |  |  |  | 2021-09-24 | 2021-09-30 | 4 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-24 | 2021-09-24 | 0 | 2021-09-30 |  | 2021-10-04 | 2
594 | PGE | 93234 | NEM | VNEM | Commercial | Solar PV | 38.78 |  | 2021-01-25 | 2021-02-08 | 10 | 2021-03-12 | 33 | 2021-03-24 | 8 | [15 empty] | 2021-03-24 | 2021-04-14 | 15 | 2021-04-14 | 2021-09-16 | 108 |  |  |  |  | 2021-01-25 | 0 |  | 2021-08-06 | 2021-08-12 | 2021-08-18 | 4 | 2021-10-16 | 2021-10-28 | 8 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-16 | 2021-10-18 | 0 | 2021-10-28 |  | 2021-11-02 | 3
595 | PGE | 93455 | NEM | VNEM | Commercial | Solar PV | 217.549 |  | 2021-03-01 | 2021-03-10 | 7 | 2021-03-18 | 13 | 2021-04-29 | 30 | [15 empty] | 2021-04-29 | 2021-05-14 | 11 | 2021-05-14 | 2021-07-12 | 39 |  |  |  |  | 2021-03-01 | 2021-07-02 | 88 |  | 2021-07-02 | 2021-07-02 | 0 | 2021-08-20 | 2021-09-01 | 8 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-20 | 2021-08-20 | 0 | 2021-09-01 |  | 2021-09-02 | 1
596 | PGE | 95035 | NEM | VNEM | Commercial | Solar PV | 35.595 |  | 2021-03-12 | 2021-03-22 | 6 | 2021-06-23 | 72 | 2021-07-13 | 13 | [15 empty] | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13 | 2021-07-23 | 8 |  |  |  |  | 2021-03-12 | 2021-04-01 | 14 |  |  |  |  | 2021-09-02 | 2021-09-10 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-02 | 2021-09-02 | 0 | 2021-09-10 |  | 2021-09-15 | 3
597 | PGE | 94030 | NEM | VNEM | Commercial | Solar PV | 150 |  | 2021-01-20 | 2021-02-03 | 10 | 2021-03-05 | 31 | 2021-03-25 | 14 | [15 empty] | 2021-03-25 | 2021-04-15 | 15 | 2021-04-15 | 2021-06-15 | 42 |  |  |  |  | 2021-03-05 | 2021-03-08 | 1 |  | 2021-03-11 | 2021-03-11 | 0 | 2021-08-20 | 2021-08-31 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-20 | 2021-08-23 | 1 | 2021-08-31 |  | 2021-09-16 | 11
598 | PGE | 93927 | NEM | VNEMMASH | IA in Progress | Solar PV | 30.402 |  | 2021-02-18 | 2021-03-05 | 11 | 2021-03-16 | 18 | 2021-03-16 | 0 | [15 empty] | 2021-03-16 | 2021-04-06 | 15 | 2021-04-06 | [6 empty] | 2021-02-18 | 2021-03-12 | 16 | [16 empty] | 1//19 | 1//19
599 | PGE | 96007 | NEM | VNEMMASH | IA in Progress | Solar PV | 52.493 |  | 2021-02-26 | 2021-03-10 | 8 | 2021-03-16 | 12 | 2021-05-28 | 53 | [15 empty] | 2021-05-28 | 2021-06-08 | 6 | 2021-06-08 | [6 empty] | 2021-02-26 | 2021-03-23 | 17 | [16 empty] | 1//19 | 1//19
600 | PGE | 93637 | NEM | VNEMMASH | Application Accepted | Solar PV | 43.53 |  | 2021-02-17 | 2021-03-05 | 12 | 2021-03-10 | 15 | 2021-04-02 | 17 | [15 empty] | 2021-04-02 | 2021-06-28 | 60 | 2021-06-28 | [6 empty] | 2021-02-17 | 2021-05-27 | 71 | [16 empty] | 1//19 | 1//19
601 | PGE | 93434 | NEM | VNEMMASH | Implementation | Solar PV | 39.976 |  | 2021-02-26 | 2021-03-11 | 9 | 2021-05-10 | 51 | 2021-07-02 | 38 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-11-08 | 89 |  |  |  |  | 2021-02-26 | 2021-05-26 | 63 | 2021-12-03 | [15 empty] | 1//19 | 1//19
602 | PGE | 93434 | NEM | VNEMMASH | Implementation | Solar PV | 38.78 |  | 2021-02-26 | 2021-03-12 | 10 | 2021-05-10 | 51 | 2021-07-02 | 38 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-11-08 | 89 |  |  |  |  | 2021-02-26 | 2021-05-26 | 63 | 2021-12-03 | [6 empty] | 2021-11-18 | 2022-03-23 | 86 |  |  |  | 2022-03-23 |  | 15 | 1//19 | 1//19
603 | PGE | 93434 | NEM | VNEMMASH | Implementation | Solar PV | 39.976 |  | 2021-02-26 | 2021-03-12 | 10 | 2021-05-10 | 51 | 2021-07-28 | 55 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | 2021-07-29 | 1 |  |  |  |  | 2021-02-26 | 2021-05-26 | 63 | 2021-12-03 | [6 empty] | 2021-12-15 |  | 84 | [6 empty] | 1//19 | 1//19
605 | PGE | 93434 | NEM | VNEMMASH | Implementation | Solar PV | 39.976 |  | 2021-02-26 | 2021-03-12 | 10 | 2021-05-10 | 51 | 2021-07-28 | 55 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | 2021-07-29 | 1 |  |  |  |  | 2021-02-26 | 2021-05-26 | 63 | 2021-12-03 | [6 empty] | 2021-12-15 |  | 84 | [6 empty] | 1//19 | 1//19
606 | PGE | 93458 | NEM | VNEMMASH | Implementation | Solar PV | 39.976 |  | 2021-02-26 | 2021-03-12 | 10 | 2021-03-31 | 23 | 2021-04-21 | 15 | [15 empty] | 2021-04-21 | 2021-05-26 | 25 | 2021-05-26 | 2021-06-10 | 10 |  |  |  |  | 2021-02-26 | 2021-05-26 | 63 | 2022-01-05 | [6 empty] | 2021-12-07 | 2022-04-08 | 87 | [6 empty] | 1//19 | 1//19
607 | PGE | 93458 | NEM | VNEMMASH | Implementation | Solar PV | 39.976 |  | 2021-02-26 | 2021-03-12 | 10 | 2021-03-31 | 23 | 2021-04-21 | 15 | [15 empty] | 2021-04-21 | 2021-05-26 | 25 | 2021-05-26 | 2021-06-10 | 10 |  |  |  |  | 2021-02-26 | 2021-05-26 | 63 | 2022-01-05 | [15 empty] | 1//19 | 1//19
608 | PGE | 93401 | NEM | VNEMMASH | Withdrawn | Solar PV | 42.168 |  | 2021-02-24 | 2021-03-09 | 9 | 2021-03-11 | 11 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-04-16 | 15 | 2021-04-16 | [6 empty] | 2021-02-24 | 2021-03-16 | 14 | [16 empty] | 1//19 | 1//19
609 | PGE | 93401 | NEM | VNEMMASH | Withdrawn | Solar PV | 34.179 |  | 2021-02-24 | 2021-03-09 | 9 | 2021-03-11 | 11 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-04-16 | 15 | 2021-04-16 | [6 empty] | 2021-02-24 | 2021-03-16 | 14 | [16 empty] | 1//19 | 1//19
610 | PGE | 93401 | NEM | VNEMMASH | Withdrawn | Solar PV | 34.179 |  | 2021-02-24 | 2021-03-09 | 9 | 2021-03-11 | 11 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-04-16 | 15 | 2021-04-16 | [6 empty] | 2021-02-24 | 2021-03-16 | 14 | [16 empty] | 1//19 | 1//19
611 | PGE | 96021 | NEM | VNEMMASH | IA in Progress | Solar PV | 34.121 |  | 2021-02-24 | 2021-03-09 | 9 | 2021-03-15 | 13 | 2021-04-02 | 14 | [15 empty] | 2021-04-02 | 2021-04-08 | 4 | 2021-04-08 | [6 empty] | 2021-02-24 | 2021-07-28 | 108 | [16 empty] | 1//19 | 1//19
612 | PGE | 96007 | NEM | VNEMMASH | IA in Progress | Solar PV | 37.983 |  | 2021-02-26 | 2021-03-10 | 8 | 2021-03-16 | 12 | 2021-03-26 | 8 | [15 empty] | 2021-03-26 | 2021-04-16 | 15 | 2021-04-16 | [6 empty] | 2021-02-26 | 2021-05-06 | 49 | [16 empty] | 1//19 | 1//19
613 | PGE | 96080 | NEM | VNEMMASH | IA in Progress | Solar PV | 43.53 |  | 2021-03-02 | 2021-03-09 | 5 | 2021-03-17 | 11 | 2021-03-31 | 10 | [15 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | [6 empty] | 2021-03-02 | 2021-03-31 | 21 | [16 empty] | 1//19 | 1//19
614 | PGE | 96080 | NEM | VNEMMASH | IA in Progress | Solar PV | 37.983 |  | 2021-03-02 | 2021-03-09 | 5 | 2021-03-16 | 10 | 2021-04-01 | 12 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | [6 empty] | 2021-03-02 | 2021-03-31 | 21 | [16 empty] | 1//19 | 1//19
615 | PGE | 95422 | NEM | VNEMMASH | IA in Progress | Solar PV | 30.402 |  | 2021-02-17 | 2021-03-05 | 12 | 2021-03-15 | 18 | 2021-03-24 | 7 | [15 empty] | 2021-03-24 | 2021-04-14 | 15 | 2021-04-14 | [6 empty] | 2021-02-17 | 2021-05-27 | 71 | [16 empty] | 1//19 | 1//19
616 | PGE | 95422 | NEM | VNEMMASH | IA in Progress | Solar PV | 63.72 |  | 2021-02-17 | 2021-03-05 | 12 | 2021-03-15 | 18 | 2021-03-24 | 7 | [15 empty] | 2021-03-24 | 2021-04-14 | 15 | 2021-04-14 | [6 empty] | 2021-02-17 | 2021-03-11 | 16 |  | 2021-03-24 | 2021-04-07 | 10 | [12 empty] | 1//19 | 1//19
617 | PGE | 94043 | NEM | VNEMSOMAH | Implementation | Solar PV | 68.358 |  | 2021-02-02 | 2021-02-17 | 10 | 2021-02-22 | 13 | 2021-03-16 | 16 | [15 empty] | 2021-03-16 | 2021-04-21 | 26 | 2021-04-21 | 2021-09-09 | 98 |  |  |  |  | 2021-02-02 | 2021-02-24 | 15 |  | 2021-04-20 | 2021-04-21 | 1 | [12 empty] | 1//19 | 1//19
618 | PGE | 95012 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 75.636 |  | 2021-01-28 | 2021-02-11 | 10 | 2021-03-16 | 32 | 2021-05-05 | 36 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | [6 empty] | 2021-01-28 | 2021-03-18 | 34 |  | 2021-04-21 | 2021-04-21 | 0 | [12 empty] | 1//19 | 1//19
619 | PGE | 95401 | NEM | VNEMSOMAH | Implementation | Solar PV | 60.446 |  | 2021-01-12 | 2021-01-27 | 10 | 2021-03-16 | 43 | 2021-03-28 | 8 | [15 empty] | 2021-05-14 | 2021-05-18 | 2 | 2021-05-18 | 2022-01-27 | 175 |  |  |  |  | 2021-01-12 | 2021-03-23 | 48 | [16 empty] | 1//19 | 1//19
620 | PGE | 95037 | NEM | VNEMSOMAH | Implementation | Solar PV | 95.363 |  | 2021-03-02 | 2021-03-15 | 9 | 2021-03-17 | 11 | 2021-04-14 | 20 | [15 empty] | 2021-04-14 | 2021-04-14 | 0 | 2021-04-14 | 2021-05-26 | 30 |  |  |  |  | 2021-03-26 | 2021-04-12 | 11 |  | 2021-04-14 | 2021-04-27 | 9 | [12 empty] | 1//19 | 1//19
621 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 64.705 |  | 2021-03-30 | 2021-04-08 | 7 | 2021-04-16 | 13 | 2021-05-07 | 15 | [15 empty] | 2021-05-07 | 2021-05-07 | 0 | 2021-05-07 | [6 empty] | 2021-03-30 | 2021-05-25 | 40 | [16 empty] | 1//19 | 1//19
622 | PGE | 95112 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 41.246 |  | 2021-02-02 | 2021-02-17 | 10 | [29 empty] | 2021-02-02 | 0 | [17 empty] | 1//19 | 1//19
623 | PGE | 95116 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 65.629 |  | 2021-02-09 | 2021-02-23 | 9 | [29 empty] | 2021-02-09 | 0 | [17 empty] | 1//19 | 1//19
624 | PGE | 95210 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 58.04 |  | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 | 0 | [17 empty] | 1//19 | 1//19
625 | PGE | 95210 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 43.53 |  | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 | 0 | [17 empty] | 1//19 | 1//19
626 | PGE | 95210 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 43.53 |  | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 | 0 | [17 empty] | 1//19 | 1//19
627 | PGE | 95210 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 43.53 |  | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 | 0 | [17 empty] | 1//19 | 1//19
628 | PGE | 95210 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 43.53 |  | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 | 0 | [17 empty] | 1//19 | 1//19
629 | PGE | 95210 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 43.53 |  | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 | 0 | [17 empty] | 1//19 | 1//19
630 | PGE | 95210 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 43.53 |  | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 | 0 | [17 empty] | 1//19 | 1//19
631 | PGE | 95210 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 43.53 |  | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 | 0 | [17 empty] | 1//19 | 1//19
632 | PGE | 95210 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 43.53 |  | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 | 0 | [17 empty] | 1//19 | 1//19
633 | PGE | 95210 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 39.172 |  | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 | 0 | [17 empty] | 1//19 | 1//19
634 | PGE | 95210 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 38.052 |  | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 | 0 | [17 empty] | 1//19 | 1//19
635 | PGE | 93721 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 34.867 |  | 2021-02-15 | 2021-03-05 | 13 | [29 empty] | 2021-02-15 | 0 | [17 empty] | 1//19 | 1//19
636 | PGE | 93721 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 34.8 |  | 2021-02-15 | 2021-03-05 | 13 | [29 empty] | 2021-02-15 | 0 | [17 empty] | 1//19 | 1//19
637 | PGE | 93721 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 34.281 |  | 2021-02-15 | 2021-03-05 | 13 | [29 empty] | 2021-02-15 | 0 | [17 empty] | 1//19 | 1//19
638 | PGE | 93721 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 34.22 |  | 2021-02-14 | 2021-03-05 | 13 | [29 empty] | 2021-02-14 | 0 | [17 empty] | 1//19 | 1//19
639 | PGE | 93721 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 33.93 |  | 2021-02-14 | 2021-03-05 | 13 | [29 empty] | 2021-02-14 | 0 | [17 empty] | 1//19 | 1//19
640 | PGE | 93721 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 33.35 |  | 2021-02-14 | 2021-03-05 | 13 | [29 empty] | 2021-02-14 | 0 | [17 empty] | 1//19 | 1//19
641 | PGE | 94509 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 46.766 |  | 2021-01-04 | 2021-01-12 | 6 | 2021-01-12 | 6 | [5 empty] | 2021-01-12 | 2021-01-23 | 7 | 2021-01-23 | [18 empty] | 2021-01-04 | 0 | [17 empty] | 1//19 | 1//19
642 | PGE | 95112 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 65.584 |  | 2021-02-08 | 2021-02-23 | 10 | 2021-03-30 | 35 | [5 empty] | 2021-03-30 | 2021-06-08 | 49 | 2021-06-08 | 2021-06-18 | 8 | 2021-06-18 | 2021-09-14 | 60 | 2021-06-18 | 2021-06-18 | 0 | 2021-09-14 | 2021-09-14 | 0 | 2021-09-14 | [6 empty] | 2021-02-08 | 0 | [17 empty] | 1//19 | 1//19
643 | PGE | 95112 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 43.2 |  | 2021-02-02 | 2021-02-12 | 8 | 2021-04-02 | 42 | [5 empty] | 2021-04-02 | 2021-06-18 | 54 | 2021-06-18 | 2021-06-18 | 0 | 2021-06-18 | 2021-09-17 | 63 | 2021-06-18 | 2021-06-18 | 0 | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | 2021-10-05 | 12 |  |  |  |  | 2021-02-02 | 2021-05-27 | 81 | [16 empty] | 1//19 | 1//19
644 | PGE | 95111 | NEM | VNEMSOMAH | Implementation | Solar PV | 115.42 |  | 2021-02-16 | 2021-03-05 | 13 | 2021-04-05 | 34 | 2021-04-26 | 15 | [15 empty] | 2021-04-26 | 2021-05-14 | 14 | 2021-05-14 | 2021-08-04 | 56 |  |  |  |  | 2021-02-16 | 2021-07-08 | 100 |  | 2021-07-08 | 2021-07-08 | 0 | [12 empty] | 1//19 | 1//19
645 | PGE | 95492 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 68.358 |  | 2021-03-12 | 2021-03-23 | 7 | 2021-04-13 | 22 | 2021-05-04 | 15 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | [6 empty] | 2021-03-12 | 2021-06-11 | 64 |  | 2021-06-25 | 2021-07-04 | 5 | [12 empty] | 1//19 | 1//19
646 | PGE | 94025 | NEM | VNEMSOMAH | Implementation | Solar PV | 95.363 |  | 2021-03-12 | 2021-03-26 | 10 | 2021-04-13 | 22 | 2021-05-04 | 15 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | 2021-09-09 | 89 |  |  |  |  | 2021-03-12 | 2021-05-07 | 40 |  | 2021-05-04 | 2021-05-04 | 0 | [12 empty] | 1//19 | 1//19
647 | PGE | 93930 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 69.12 |  | 2021-02-17 | 2021-03-05 | 12 | 2021-03-05 | 12 | 2021-03-25 | 14 | [25 empty] | 2021-02-17 | 2021-03-11 | 16 | [16 empty] | 1//19 | 1//19
648 | PGE | 94952 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.179 |  | 2021-03-12 | 2021-03-23 | 7 | 2021-03-26 | 10 | 2021-04-01 | 4 | [15 empty] | 2021-04-01 | 2021-04-22 | 15 | 2021-04-22 | 2022-01-27 | 193 |  |  |  |  | 2021-03-12 | 2021-06-15 | 66 | [16 empty] | 1//19 | 1//19
649 | PGE | 95112 | NEM | VNEMSOMAH | Implementation | Solar PV | 86.4 |  | 2021-02-26 | 2021-03-10 | 8 | 2021-03-16 | 12 | 2021-04-05 | 14 | [15 empty] | 2021-04-05 | 2021-04-26 | 15 | 2021-04-26 | 2021-07-27 | 64 |  |  |  |  | 2021-04-26 | 2021-05-03 | 5 |  | 2021-04-26 | 2021-04-26 | 0 | [12 empty] | 1//19 | 1//19
650 | PGE | 95401 | NEM | VNEMSOMAH | Implementation | Solar PV | 61.783 |  | 2021-01-12 | 2021-01-27 | 10 | 2021-03-16 | 43 | 2021-03-28 | 8 | [15 empty] | 2021-05-14 | 2021-05-18 | 2 | 2021-05-18 | 2022-01-17 | 167 |  |  |  |  | 2021-01-12 | 2021-04-05 | 57 | [16 empty] | 1//19 | 1//19
651 | PGE | 94118 | NEM | VNEMSOMAH | Implementation | Solar PV | 100 |  | 2021-01-25 | 2021-02-08 | 10 | 2021-04-07 | 51 | 2021-04-28 | 15 | [15 empty] | 2021-04-28 | 2021-05-13 | 11 | 2021-05-13 | 2021-12-28 | 157 |  |  |  |  | 2021-01-25 | 2021-04-07 | 51 | 2021-07-09 | [15 empty] | 1//19 | 1//19
652 | PGE | 94952 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 52.868 |  | 2021-03-12 | 2021-03-23 | 7 | 2021-03-26 | 10 | 2021-04-09 | 10 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | 2022-01-27 | 202 |  |  |  |  | 2021-03-12 | 2021-07-09 | 83 |  | 2021-07-04 | 2021-07-04 | 0 | [12 empty] | 1//19 | 1//19
653 | PGE | 94086 | NEM | VNEMSOMAH | Commercial | Solar PV | 100.91 |  | 2021-02-11 | 2021-02-24 | 8 | 2021-02-24 | 8 | 2021-03-16 | 14 | [15 empty] | 2021-03-16 | 2021-04-06 | 15 | 2021-04-06 | 2021-09-21 | 117 |  |  |  |  | 2021-02-24 | 2021-02-25 | 1 |  | 2021-03-04 | 2021-03-12 | 6 | 2021-10-08 | 2021-10-13 | 3 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-08 | 2021-10-08 | 0 | 2021-10-13 |  | 2021-10-19 | 4
654 | PGE | 94086 | NEM | VNEMSOMAH | Commercial | Solar PV | 100.91 |  | 2021-02-11 | 2021-02-26 | 10 | 2021-02-26 | 10 | 2021-03-17 | 13 | [15 empty] | 2021-03-17 | 2021-04-06 | 14 | 2021-04-06 | 2021-09-21 | 117 |  |  |  |  | 2021-02-26 | 2021-03-01 | 1 |  | 2021-03-04 | 2021-03-12 | 6 | 2021-10-08 | 2021-10-13 | 3 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-08 | 2021-10-08 | 0 | 2021-10-13 |  | 2021-10-19 | 4
655 | PGE | 94086 | NEM | VNEMSOMAH | Commercial | Solar PV | 72.22 |  | 2021-02-11 | 2021-02-26 | 10 | 2021-02-26 | 10 | 2021-03-17 | 13 | [15 empty] | 2021-03-17 | 2021-04-06 | 14 | 2021-04-06 | 2021-09-21 | 117 |  |  |  |  | 2021-03-09 | 2021-03-10 | 1 |  | 2021-03-12 | 2021-03-12 | 0 | 2021-10-08 | 2021-10-13 | 3 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-08 | 2021-10-08 | 0 | 2021-10-13 |  | 2021-10-19 | 4
656 | PGE | 94040 | NEM | VNEMSOMAH | Implementation | Solar PV | 115.42 |  | 2021-02-12 | 2021-03-03 | 12 | 2021-03-05 | 14 | 2021-04-12 | 26 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-07-27 | 74 |  |  |  |  | 2021-02-12 | 2021-03-10 | 17 |  | 2021-03-24 | 2021-04-07 | 10 | [12 empty] | 1//19 | 1//19
657 | PGE | 95130 | NEM | VNEMSOMAH | Implementation | Solar PV | 111.038 |  | 2021-03-04 | 2021-03-15 | 7 | 2021-03-15 | 7 | 2021-04-12 | 20 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-09-09 | 105 |  |  |  |  | 2021-03-04 | 2021-04-05 | 22 |  | 2021-04-12 | 2021-04-12 | 0 | [12 empty] | 1//19 | 1//19
659 | PGE | 95476 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-02-08 | 2021-02-08 | 0 | 2021-03-03 | 16 | 2021-04-06 | 24 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-04-30 | 18 | [5 empty] | 0 | [5 empty] | 2021-11-18 | 2021-12-02 | 8 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-18 | 2021-11-19 | 1 | 2021-12-02 |  | 2021-12-02 | 0
660 | PGE | 93950 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-02-17 | 2021-02-17 | 0 | 2021-03-03 | 10 | 2021-04-20 | 34 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-04-23 | 3 | [5 empty] | 0 | [5 empty] | 2021-11-15 | 2021-11-30 | 9 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-15 | 2021-11-16 | 1 | 2021-11-30 |  | 2021-11-30 | 0
661 | PGE | 94403 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-02-17 | 2021-02-18 | 1 | 2021-03-03 | 10 | 2021-04-19 | 33 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-04-20 | 1 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
662 | PGE | 93960 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-02-17 | 2021-02-18 | 1 | 2021-03-03 | 10 | 2021-04-23 | 37 | [15 empty] | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | 2021-04-27 | 2 | [5 empty] | 0 | [5 empty] | 2021-09-13 | 2021-09-24 | 9 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-13 | 2021-09-13 | 0 | 2021-09-24 |  | 2021-09-24 | 0
663 | PGE | 93644 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-02-17 | 2021-02-18 | 1 | 2021-03-03 | 10 | 2021-04-13 | 29 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-04-23 | 8 | [5 empty] | 0 | [5 empty] | 2021-11-10 | 2021-12-02 | 13 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-10 | 2021-11-15 | 2 | 2021-12-02 |  | 2021-12-03 | 1
664 | PGE | 94952 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-02-17 | 2021-02-18 | 1 | 2021-03-03 | 10 | 2021-04-07 | 25 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-25 | 12 | [5 empty] | 0 | [5 empty] | 2021-09-08 | 2021-09-16 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-08 | 2021-09-09 | 1 | 2021-09-16 |  | 2021-09-16 | 0
665 | PGE | 93722 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-02-18 | 2021-02-19 | 1 | 2021-03-03 | 9 | 2021-03-25 | 16 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-03-31 | 4 | [5 empty] | 0 | [5 empty] | 2021-11-09 | 2021-12-16 | 24 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-09 | 2021-12-08 | 18 | 2021-12-16 |  | 2021-12-17 | 1
666 | PGE | 94720 | Non-NEM | Make Before Break | Decommissioned | ENGN | 4562 |  | 2021-02-22 | 2021-02-23 | 1 | 2021-03-30 | 26 | 2021-06-11 | 52 | [15 empty] | 2021-06-24 | 2021-09-10 | 54 | 2021-09-10 | 2021-09-27 | 11 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19 | [7 empty] | 2021-09-28 | 2021-09-30 |  | 3 | 9/27/2021 | 4 | 155
667 | PGE | 93458 | NEM | VNEMMASH | Implementation | Solar PV | 37.598 |  | 2021-02-26 | 2021-03-11 | 9 | 2021-05-11 | 52 | 2021-06-16 | 25 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | 2021-09-14 | 62 |  |  |  |  | 2021-02-26 | 2021-05-26 | 63 | 2022-01-05 | [15 empty] | 1//19 | 1//19
668 | PGE | 95404 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 54.65 |  | 2021-03-02 | 2021-03-09 | 5 | 2021-06-04 | 67 | 2021-06-04 | 0 | [18 empty] | 2021-03-03 | [7 empty] | 0 | [5 empty] | 2021-06-04 | 2021-06-04 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-04 |  |  | 2021-06-04 |  | 2021-06-04 | 0
669 | PGE | 93710 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-03-11 | 2021-03-19 | 6 | 2021-03-31 | 14 | 2021-04-26 | 18 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-04-28 | 2 | [5 empty] | 0 | [5 empty] | 2021-11-24 | 2022-01-09 | 30 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-24 | 2022-01-06 | 29 | 2022-01-09 |  | 2022-01-10 | 0
670 | PGE | 95111 | Non-NEM | Make Before Break | Study in Progress | ENGN, Turbine | 30358.8 |  | 2021-03-19 | 2021-03-19 | 0 | 2021-03-31 | 8 | 2021-04-30 | 22 | 2021-08-02 | 2021-08-17 | 11 | 2021-09-09 | 2021-10-07 | 20 | 2021-10-07 | 2021-10-19 | 8 | 2021-10-29 |  |  | 2021-10-19 | 2021-10-19 | 0 | [11 empty] | 0 | [17 empty] | 1//19 | 1//19
671 | PGE | 93453 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 32.641 |  | 2021-03-19 | 2021-03-24 | 3 | 2021-04-07 | 13 | 2021-04-23 | 12 | [18 empty] | 2021-03-19 | [7 empty] | 0 | [5 empty] | 2021-05-14 | 2021-06-08 | 16 | 2021-05-03 | 2021-08-09 | 68 |  |  |  | 2021-10-18 | 2021-12-17 | 41 | 1//19 | 1//19 |  |  |  |  | 2021-05-14 | 2021-06-08 | 16 | 2021-06-08 | 2021-06-08 |  | 0 |  |  | 56
672 | PGE | 95337 | NEM | EXPNEM | Commercial | Solar PV | 30.402 |  | 2021-03-22 | 2021-04-05 | 10 | 2021-07-07 | 75 | 2021-07-21 | 10 | [15 empty] | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | 2021-07-26 | 3 | [5 empty] | 0 | [5 empty] | 2021-07-28 | 2021-08-27 | 22 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-28 | 2021-08-23 | 18 | 2021-08-27 |  | 2021-08-31 | 2
673 | PGE | 94040 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-03-23 | 2021-03-23 | 0 | 2021-04-07 | 11 | 2021-06-23 | 54 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-07-14 | 14 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
674 | PGE | 95076 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.5 |  | 2021-03-23 | 2021-04-06 | 10 | 2021-05-05 | 31 | 2021-05-24 | 13 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-05-18 | 9 | [5 empty] | 0 | [5 empty] | 2021-05-24 | 2021-05-24 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24 |  | 2021-05-25 | 1
675 | PGE | 95030 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.355 |  | 2021-03-25 | 2021-04-02 | 6 | [19 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | 2022-01-14 | 177 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
676 | PGE | 93311 | Non-NEM | RESBCT | Implementation | Solar PV | 4500 |  | 2021-03-25 | 2021-03-26 | 1 | 2021-03-31 | 4 | [5 empty] | 2021-03-31 | 2021-04-28 | 20 | 2021-04-28 | 2021-04-28 | 0 | 2021-05-06 | 2021-09-17 | 93 | 2021-04-28 | 2021-04-29 | 1 | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | 2021-10-12 | 17 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
677 | PGE | 93446 | NEM | EXPNEM | IA in Progress | Solar PV | 114.141 |  | 2021-03-25 | 2021-03-26 | 1 | 2021-05-03 | 27 | 2021-05-11 | 6 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
678 | PGE | 94612 | NEM | EXPNEM | Commercial | Solar PV | 60.318 |  | 2021-03-27 | 2021-04-07 | 7 | 2021-07-12 | 73 | 2021-07-14 | 2 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-27 | 9 |  |  |  |  | 2021-03-27 | 2021-09-13 | 117 |  |  |  |  | 2021-11-02 | 2021-11-17 | 10 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-02 | 2021-11-02 | 0 | 2021-11-17 |  | 2021-11-22 | 3
679 | PGE | 93308 | NEM | EXPNEM | Commercial | Solar PV | 40.979 |  | 2021-03-29 | 2021-04-06 | 6 | 2021-05-03 | 25 | 2021-05-18 | 11 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | 2021-05-25 | 5 | [5 empty] | 0 | [5 empty] | 2021-06-02 | 2021-06-10 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-02 | 2021-06-03 | 1 | 2021-06-10 |  | 2021-06-17 | 5
680 | PGE | 93309 | NEM | EXPNEM | Commercial | Solar PV | 57.927 |  | 2021-03-29 | 2021-04-12 | 10 | 2021-06-05 | 48 | 2021-06-23 | 12 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-07-19 | 17 |  |  |  |  | 2021-03-29 | 2021-06-16 | 56 |  |  |  |  | 2021-12-09 | 2021-12-17 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-09 | 2021-12-09 | 0 | 2021-12-17 |  | 2021-12-29 | 8
681 | PGE | 95448 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.612 |  | 2021-03-31 | 2021-04-14 | 10 | 2021-04-14 | 10 | 2021-06-11 | 41 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
682 | PGE | 95404 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 44.948 |  | 2021-04-01 | 2021-04-15 | 10 | 2021-04-15 | 10 | 2021-04-21 | 4 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | 2021-04-01 | 0 |  |  |  |  | 2021-04-01 | 0 | [5 empty] | 2021-04-29 | 2021-05-05 | 4 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-29 | 2021-04-29 | 0 | 2021-05-05 |  | 2021-05-05 | 0
683 | PGE | 95674 | NEM | EXPNEM | Implementation | Solar PV | 166.6 |  | 2021-04-01 | 2021-04-05 | 2 | 2021-05-21 | 36 | 2021-06-08 | 11 | 2021-06-08 | 2021-07-06 | 19 | 2021-07-06 | 2021-07-20 | 10 | 2021-07-20 | 2021-07-20 |  | 2021-07-20 | 2021-10-11 | 60 | 2021-07-20 |  |  | 2021-10-11 | 2021-10-11 | 0 | 2021-10-11 | 2021-10-14 | 3 |  |  |  |  | 2021-04-01 | 2021-08-27 | 104 |  |  |  |  | 2022-03-30 |  |  | 2021-11-05 | 2022-01-07 | 41 |  |  |  | 2022-01-28 | 2022-03-16 | 33 | 1//19 | 1//19 |  |  |  |  | 2022-03-30 | 2022-03-30 | 0
684 | PGE | 93610 | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-04-01 | 2021-04-13 | 8 | 2021-04-23 | 16 | 2021-05-11 | 12 | 2021-05-11 | 2021-06-01 | 14 | [12 empty] | 2021-06-01 | 2021-06-02 | 1 | 2021-06-02 | 2021-06-03 | 1 |  |  |  |  | 2021-04-01 | 2021-05-07 | 26 | [16 empty] | 1//19 | 1//19
685 | PGE | 95945 | Non-NEM | Non-Export | Withdrawn | Storage | 140 |  | 2021-04-01 | 2021-04-02 | 1 | 2021-04-21 | 14 | 2021-06-11 | 36 | [15 empty] | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-09-13 | 64 |  |  |  |  | 2021-04-01 | 0 | [17 empty] | 1//19 | 1//19
686 | PGE | 95340 | NEM | EXPNEM | Implementation | Solar PV | 420 |  | 2021-04-01 | 2021-04-15 | 10 | 2021-04-22 | 15 | 2021-05-11 | 13 | 2021-05-11 | 2021-06-03 | 16 | [12 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-11 | 6 | [5 empty] | 0 | [8 empty] | 2021-11-05 | 2021-11-17 | 7 |  |  |  | 2022-03-21 | 2022-04-08 | 14 | 1//19 | 1//19
687 | PGE | 95035 | NEM | EXPNEM | IA in Progress | Solar PV | 47.27 |  | 2021-04-01 | 2021-04-02 | 1 | 2021-04-07 | 4 | 2021-04-26 | 13 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-06-01 | 25 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
688 | PGE | 95762 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 310.231 |  | 2021-04-01 | 2021-04-13 | 8 | 2021-10-29 | 148 | 2021-11-22 | 15 | 2021-11-22 | 2022-02-01 | 48 | 2022-02-01 | 2022-02-24 | 16 | 2022-02-24 | [18 empty] | 2021-04-01 | 0 |  | 2021-10-14 | [15 empty] | 1//19 | 1//19
689 | PGE | 95726 | Non-NEM | Non-Export | Implementation | Storage | 715 |  | 2021-03-25 | 2021-04-05 | 7 | 2021-04-14 | 14 | 2021-05-20 | 26 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2021-07-21 | 42 |  |  |  |  | 2021-04-01 | 2021-07-09 | 69 | [16 empty] | 1//19 | 1//19
690 | PGE | 93631 | NEM | EXPNEM | Implementation | Solar PV | 34.179 |  | 2021-04-02 | 2021-04-14 | 8 | 2021-07-19 | 74 | 2021-07-23 | 4 | [15 empty] | 2021-07-23 | 2021-07-23 | 0 | 2021-07-23 | 2021-08-06 | 10 |  |  |  |  | 2021-04-02 | 2021-08-06 | 88 | [7 empty] | 2021-09-17 | 2021-11-09 | 37 |  |  |  | 2021-11-10 | 2021-12-17 | 24 | 1//19 | 1//19
691 | PGE | 95317 | NEM | EXPNEM | Implementation | Solar PV | 38.78 |  | 2021-04-02 | 2021-04-14 | 8 | 2021-06-03 | 43 | 2021-06-21 | 12 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-07-13 | 15 |  |  |  |  | 2021-04-02 | 2021-07-02 | 64 |  |  |  |  | 2021-09-13 | 2021-09-21 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-13 | 2021-09-13 | 0 | 2021-09-21 | 2022-01-18 |  | 81 |  |  | 200
692 | PGE | 93923 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 43.04 |  | 2021-04-02 | 2021-04-14 | 8 | 2021-04-14 | 8 | 2021-04-20 | 4 | [15 empty] | 2021-04-14 | 2021-04-14 | 0 | 2021-04-14 | 2021-04-20 | 4 | [5 empty] | 0 | [5 empty] | 2021-04-22 | 2021-04-22 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 |  | 2021-04-23 | 1
693 | PGE | 93280 | NEM | EXPNEM | Withdrawn | Solar PV | 1560 |  | 2021-04-02 | 2021-04-02 | 0 | 2021-04-14 | 8 | 2021-05-20 | 26 | [25 empty] | 2021-04-02 | 0 | [17 empty] | 1//19 | 1//19
694 | PGE | 95126 | NEM | VNEMSOMAH | Implementation | Solar PV | 50.396 |  | 2021-04-02 | 2021-04-08 | 4 | 2021-04-16 | 10 | 2021-05-21 | 25 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-07-27 | 45 |  |  |  |  | 2021-04-02 | 2021-06-24 | 58 | [16 empty] | 1//19 | 1//19
695 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 33.614 |  | 2021-04-02 | 2021-04-13 | 7 | 2021-04-13 | 7 | 2021-05-06 | 17 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 | [6 empty] | 2021-04-02 | 2021-05-26 | 38 | [16 empty] | 1//19 | 1//19
696 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.179 |  | 2021-04-02 | 2021-04-13 | 7 | 2021-04-13 | 7 | 2021-05-06 | 17 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 | [6 empty] | 2021-04-02 | 2021-05-26 | 38 | [16 empty] | 1//19 | 1//19
697 | PGE | 94928 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 38.018 |  | 2021-04-02 | 2021-04-13 | 7 | 2021-04-13 | 7 | 2021-07-16 | 66 | [15 empty] | 2021-07-16 | 2021-08-27 | 30 | 2021-08-27 | [6 empty] | 2021-04-02 | 2021-07-19 | 74 | [16 empty] | 1//19 | 1//19
698 | PGE | 94928 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 30.402 |  | 2021-04-02 | 2021-04-13 | 7 | 2021-04-13 | 7 | 2021-05-06 | 17 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 | [6 empty] | 2021-04-02 | 2021-07-19 | 74 | [16 empty] | 1//19 | 1//19
699 | PGE | 93618 | NEM | EXPNEM | Commercial | Solar PV | 31.804 |  | 2021-04-02 | 2021-04-05 | 1 | 2021-04-05 | 1 | 2021-04-09 | 4 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | 2021-04-12 | 1 |  |  |  |  | 2021-07-07 | 2021-07-08 | 1 |  |  |  |  | 2021-08-20 | 2021-08-27 | 5 | 2021-06-15 | 2022-02-15 | 169 |  |  |  | 2021-11-30 | 2022-03-21 | 78 | 1//19 | 1//19 |  |  |  |  | 2021-08-20 | 2021-08-20 | 0 | 2021-08-27 | 2021-10-07 | 2022-03-24 | 28 |  |  | 131
700 | PGE | 93446 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-04-02 | 2021-04-14 | 8 | 2021-05-10 | 26 | 2021-06-28 | 34 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-06-29 | 1 | [5 empty] | 0 | [5 empty] | 2021-09-10 | 2021-09-23 | 9 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-10 | 2021-09-12 | 0 | 2021-09-23 |  | 2021-09-23 | 0
701 | PGE | 93309 | NEM | EXPNEM | Commercial | Solar PV | 101.728 |  | 2021-04-02 | 2021-04-12 | 6 | 2021-05-11 | 27 | 2021-06-25 | 32 | [15 empty] | 2021-07-13 | 2021-07-20 | 5 | 2021-07-20 | 2021-08-18 | 21 |  |  |  |  | 2021-04-02 | 0 |  | 2021-08-27 |  |  |  | 2021-11-08 | 2021-11-16 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-08 | 2021-11-09 | 1 | 2021-11-16 |  | 2021-11-17 | 1
702 | PGE | 93309 | NEM | EXPNEM | Commercial | Solar PV | 178.024 |  | 2021-04-02 | 2021-04-05 | 1 | 2021-05-06 | 24 | 2021-06-30 | 38 | [15 empty] | 2021-06-30 | 2021-07-06 | 3 | 2021-07-06 | 2021-07-16 | 8 | [5 empty] | 0 | [5 empty] | 2021-12-20 | 2021-12-28 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-20 | 2021-12-21 | 1 | 2021-12-28 |  | 2021-12-30 | 2
703 | PGE | 95476 | NEM | VNEM | Commercial | Solar PV | 34.639 |  | 2021-04-05 | 2021-04-14 | 7 | 2021-05-07 | 24 | 2021-06-09 | 22 | [15 empty] | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | 2021-06-14 | 3 |  |  |  |  | 2021-06-17 | 2021-06-17 | 0 |  | 2021-06-16 | 2021-06-16 | 0 | 2021-07-28 | 2021-08-03 | 4 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-28 | 2021-07-29 | 1 | 2021-08-03 |  | 2021-08-10 | 5
704 | PGE | 94608 | NEM | VNEM | Commercial | Solar PV | 54.828 |  | 2021-04-05 | 2021-04-14 | 7 | 2021-05-25 | 36 | 2021-06-11 | 12 | [15 empty] | 2021-06-11 | 2021-07-29 | 33 | 2021-07-29 | 2021-07-30 | 1 |  |  |  |  | 2021-06-04 | 2021-06-04 | 0 |  | 2021-06-04 | 2021-06-11 | 5 | 2021-08-03 | 2021-08-10 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-03 | 2021-08-03 | 0 | 2021-08-10 |  | 2021-08-12 | 2
705 | PGE | 94566 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 36.461 |  | 2021-04-05 | 2021-04-15 | 8 | 2021-04-15 | 8 | 2021-04-19 | 2 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-04-05 | 0 |  |  |  |  | 2021-04-05 | 2021-06-14 | 49 | [16 empty] | 1//19 | 1//19
706 | PGE | 94515 | Non-NEM | Non-Export | Implementation | Storage | 429 |  | 2021-04-05 | 2021-04-19 | 10 | 2021-05-12 | 27 | 2021-08-23 | 71 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23 | 2021-08-30 | 5 |  |  |  |  | 2021-06-14 | 2021-07-09 | 18 | [16 empty] | 1//19 | 1//19
707 | PGE | 96022 | NEM | EXPNEM | IA in Progress | Solar PV | 123.798 |  | 2021-04-05 | 2021-04-16 | 9 | 2021-05-10 | 25 | 2021-06-01 | 15 | [15 empty] | 2021-06-01 | 2021-06-01 | 0 | 2021-06-01 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
708 | PGE | 95360 | NEM | EXPNEM | Study in Progress | Solar PV | 1875 |  | 2021-04-05 | 2021-04-06 | 1 | 2021-05-12 | 27 | 2021-06-11 | 21 | 2021-07-06 | 2021-08-03 | 20 | 2021-09-03 | 2021-10-04 | 20 | 2021-10-04 |  |  | 2021-10-13 | 2022-02-08 | 80 | 2021-10-04 | 2021-10-12 | 7 | [10 empty] | 2021-04-05 | 0 | [17 empty] | 1//19 | 1//19
709 | PGE | 95448 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 32.178 |  | 2021-04-05 | 2021-04-15 | 8 | 2021-04-23 | 14 | 2021-04-27 | 2 | [26 empty] | 0 | [17 empty] | 1//19 | 1//19
710 | PGE | 95205 | NEM | EXPNEM | Commercial | Solar PV | 133.2 |  | 2021-04-06 | 2021-04-08 | 2 | 2021-04-14 | 6 | 2021-04-28 | 10 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-06-30 | 44 | [5 empty] | 0 | [5 empty] | 2021-07-15 | 2021-07-22 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-15 | 2021-07-15 | 0 | 2021-07-22 |  | 2021-07-29 | 5
711 | PGE | 95762 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.341 |  | 2021-04-06 | 2021-04-20 | 10 | 2021-04-20 | 10 | 2021-05-11 | 15 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-04-20 | 0 |  |  |  |  | 2021-04-06 | 2021-05-25 | 35 |  |  |  |  | 2021-05-28 | 2021-05-28 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 |  | 2021-05-28 | 0
712 | PGE | 95037 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.54 |  | 2021-04-06 | 2021-04-08 | 2 | 2021-06-08 | 44 | 2021-07-07 | 20 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | 2021-10-21 | 75 |  |  |  |  | 2021-04-06 | 2021-04-15 | 7 |  |  |  |  | 2021-10-21 | 2021-10-26 | 3 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-21 | 2021-10-22 | 1 | 2021-10-26 |  | 2021-10-27 | 1
713 | PGE | 95501 | Non-NEM | Non-Export | Implementation | Storage | 420 |  | 2021-04-06 | 2021-04-08 | 2 | 2021-05-12 | 26 | 2021-10-12 | 106 | [15 empty] | 2021-10-12 | 2021-10-12 | 0 | 2021-10-12 | 2022-01-13 | 64 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
714 | PGE | 95112 | Non-NEM | NEMFC | Implementation | FUCE | 525 |  | 2021-04-06 | 2021-04-20 | 10 | 2021-06-09 | 45 | 2021-10-21 | 94 | [15 empty] | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21 | 2021-12-17 | 38 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
715 | PGE | 94920 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 43.732 |  | 2021-04-06 | 2021-04-20 | 10 | 2021-04-20 | 10 | 2021-05-06 | 12 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-05-05 | 11 | [5 empty] | 0 | [5 empty] | 2021-12-13 | 2021-12-14 | 1 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-13 | 2021-12-14 | 1 | 2021-12-14 |  | 2021-12-14 | 0
716 | PGE | 95112 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 66.513 |  | 2021-04-06 | 2021-04-20 | 10 | 2021-04-22 | 12 | 2021-05-27 | 25 | [15 empty] | 2021-05-27 | 2021-05-28 | 1 | 2021-05-28 | [6 empty] | 2021-04-06 | 0 |  | 2021-06-11 | 2021-06-25 | 2021-06-25 | 10 | [12 empty] | 1//19 | 1//19
717 | PGE | 95035 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.119 |  | 2021-04-07 | 2021-04-20 | 9 | 2021-04-20 | 9 | 2021-05-06 | 12 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-07 | 0 |  |  |  |  | 2021-04-07 | 0 | [5 empty] | 2021-05-17 | 2021-05-18 | 1 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-17 | 2021-05-18 | 1 | 2021-05-18 |  | 2021-05-18 | 0
718 | PGE | 95138 | NEM | EXPNEM | Implementation | Solar PV | 912.4 |  | 2021-04-07 | 2021-04-21 | 10 | 2021-12-02 | 165 | 2022-02-24 | 58 | [15 empty] | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-09 | 9 |  |  |  |  | 2021-04-07 | 2021-05-25 | 34 | 2021-05-25 | [15 empty] | 1//19 | 1//19
719 | PGE | 94583 | NEM | VNEMSOMAH | Implementation | Solar PV | 72.22 |  | 2021-04-07 | 2021-04-13 | 4 | 2021-04-14 | 5 | 2021-08-04 | 78 | [15 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | 2021-12-28 | 100 |  |  |  |  | 2021-04-07 | 2021-07-19 | 71 | 2021-04-29 | 2021-08-02 | 2021-08-04 | 65 | [12 empty] | 1//19 | 1//19
720 | PGE | 94583 | NEM | VNEMSOMAH | Implementation | Solar PV | 72.22 |  | 2021-04-07 | 2021-04-13 | 4 | 2021-04-14 | 5 | 2021-08-04 | 78 | [15 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | 2021-12-28 | 100 |  |  |  |  | 2021-04-07 | 0 |  | 2021-04-29 | 2021-05-13 | 2021-05-13 | 10 | [12 empty] | 1//19 | 1//19
721 | PGE | 95602 | NEM | SNEM | Application Review in Progress | Solar PV | 6570 |  | 2021-04-07 | 2021-04-14 | 5 | [22 empty] | 2021-04-07 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
722 | PGE | 93311 | NEM | EXPNEM | Commercial | Solar PV | 72.55 |  | 2021-04-07 | 2021-04-08 | 1 | 2021-04-16 | 7 | 2021-04-27 | 7 | [15 empty] | 2021-04-27 | 2021-04-30 | 3 | 2021-04-30 | 2021-08-16 | 74 |  |  |  |  | 2021-04-07 | 2021-04-15 | 6 |  |  |  |  | 2021-08-31 | 2021-09-22 | 15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-31 | 2021-09-16 | 11 | 2021-09-22 |  | 2021-09-27 | 3
723 | PGE | 94720 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 564.698 |  | 2021-04-07 | 2021-04-22 | 11 | 2021-06-17 | 50 | 2021-07-08 | 14 | 2021-07-27 | 2021-08-25 | 21 | [12 empty] | 2021-09-01 | 2021-09-16 | 10 | 2021-09-16 | [6 empty] | 2021-04-07 | 0 | [17 empty] | 1//19 | 1//19
724 | PGE | 95501 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 1930 |  | 2021-04-08 | 2021-04-14 | 4 | 2021-04-28 | 14 | [5 empty] | 2021-07-02 | 2021-07-28 | 17 | 2021-07-28 | 2021-07-28 |  | 2021-07-28 | 2021-10-18 | 59 | 2021-07-28 | [13 empty] | 0 | [17 empty] | 1//19 | 1//19
725 | PGE | 95330 | NEM | EXPNEM | Commercial | Solar PV | 224.463 |  | 2021-04-08 | 2021-04-09 | 1 | 2021-04-08 | 0 | 2021-04-29 | 15 | [15 empty] | 2021-04-29 | 2021-05-03 | 2 | 2021-05-03 | 2021-08-23 | 78 |  |  |  |  | 2021-04-08 | 2021-05-07 | 21 |  |  |  |  | 2021-08-24 | 2021-09-01 | 6 | 2021-08-05 |  | 174 |  |  |  | 2021-09-04 | 2021-09-04 | 1 | 1//19 | 1//19 |  |  |  |  | 2021-08-24 | 2021-08-25 | 1 | 2021-09-01 |  | 2021-09-09 | 5
727 | PGE | 95603 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 43.2 |  | 2021-04-08 | 2021-04-17 | 6 | 2021-11-18 | 156 | 2021-12-10 | 14 | [15 empty] | 2021-12-10 | 2021-12-31 | 15 | 2021-12-31 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
728 | PGE | 93311 | NEM | EXPNEM | Application Review in Progress | Solar PV | 528.528 |  | 2021-04-08 | 2021-04-22 | 10 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
729 | PGE | 95030 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 125.563 |  | 2021-04-08 | 2021-04-16 | 6 | 2021-07-20 | 71 | 2021-08-10 | 15 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | 2021-05-11 | 17 | [5 empty] | 0 | [5 empty] | 2021-08-10 | 2021-08-12 | 2 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-10 | 2021-08-11 | 1 | 2021-08-12 |  | 2021-08-12 | 0
730 | PGE | 94801 | NEM | EXPNEM | Commercial | Solar PV | 91.863 |  | 2021-04-09 | 2021-04-12 | 1 | 2021-04-13 | 2 | 2021-04-28 | 11 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-04-29 | 1 | [5 empty] | 0 | [5 empty] | 2021-05-03 | 2021-05-11 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-03 | 2021-05-04 | 1 | 2021-05-11 |  | 2021-05-14 | 3
731 | PGE | 94597 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.52 |  | 2021-04-09 | 2021-04-22 | 9 | 2021-04-22 | 9 | 2021-04-26 | 2 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | 2021-04-09 | 0 | [5 empty] | 0 | [5 empty] | 2021-04-26 | 2021-04-26 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 |  | 2021-04-26 | 0
732 | PGE | 95776 | NEM | EXPNEM | IA in Progress | Solar PV | 39.739 |  | 2021-04-09 | 2021-04-12 | 1 | 2021-05-11 | 22 | 2021-05-24 | 9 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24 | 2022-01-28 | 172 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
733 | PGE | 94506 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 |  | 2021-04-09 | 2021-04-13 | 2 | 2021-04-13 | 2 | 2021-04-14 | 1 | [18 empty] | 2021-04-09 | 2021-04-09 | 0 | [5 empty] | 0 | [5 empty] | 2021-04-14 | 2021-06-03 | 35 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-14 | 2021-06-01 | 33 | 2021-06-03 |  | 2021-06-03 | 0
734 | PGE | 94565 | NEM | EXPNEM | Commercial | Solar PV | 36.83 |  | 2021-04-09 | 2021-04-12 | 1 | 2021-07-01 | 58 | 2021-07-27 | 17 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-08-20 | 18 |  |  |  |  | 2021-04-12 | 2021-08-18 | 90 |  |  |  |  | 2021-08-20 | 2021-09-02 | 9 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-20 | 2021-08-27 | 5 | 2021-09-02 |  | 2021-09-13 | 6
735 | PGE | 95969 | Non-NEM | Non-Export | Withdrawn | Storage | 490 |  | 2021-04-09 | 2021-04-14 | 3 | 2021-04-21 | 8 | 2021-06-15 | 38 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-15 | [6 empty] | 2021-04-09 | 0 | [17 empty] | 1//19 | 1//19
736 | PGE | 94027 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 33.376 |  | 2021-04-09 | 2021-04-22 | 9 | 2021-05-05 | 18 | 2021-05-18 | 9 | [15 empty] | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 | 2021-04-23 | 1 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
737 | PGE | 94022 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 36.403 |  | 2021-04-09 | 2021-04-22 | 9 | 2021-05-05 | 18 | 2021-05-17 | 8 | [15 empty] | 2022-03-02 | 2022-03-02 | 0 | 2022-03-02 | 2022-03-14 | 8 | [5 empty] | 0 | [5 empty] | 2022-02-23 | 2022-02-27 | 2 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-02-23 | 2022-02-27 | 2 | 2022-02-27 |  | 2022-03-14 | 10
738 | PGE | 95030 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.007 |  | 2021-04-09 | 2021-04-13 | 2 | 2021-08-20 | 93 | 2021-08-25 | 3 | [18 empty] | 2021-05-13 | 2021-05-13 | 0 | [5 empty] | 0 | [5 empty] | 2021-08-25 | 2021-08-25 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 |  | 2021-08-25 | 0
739 | PGE | 93434 | NEM | VNEM | Commercial | Solar PV | 46.946 |  | 2021-04-11 | 2021-04-15 | 3 | 2021-07-01 | 57 | 2021-08-06 | 25 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | 2021-08-09 | 1 |  |  |  |  | 2021-07-07 | 2021-07-19 | 8 |  | 2021-08-02 | 2021-08-06 | 4 | 2021-09-25 | 2021-10-06 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-25 | 2021-09-27 | 0 | 2021-10-06 |  | 2021-10-12 | 4
740 | PGE | 94952 | NEM | EXPNEM | Commercial | Solar PV | 193.173 |  | 2021-04-12 | 2021-04-12 | 0 | 2021-04-26 | 10 | 2021-05-12 | 12 | [15 empty] | 2021-05-12 | 2021-05-12 | 0 | 2021-05-12 | 2021-05-17 | 3 |  |  |  |  | 2021-04-12 | 2021-05-10 | 20 |  |  |  |  | 2021-05-19 | 2021-06-16 | 19 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-19 | 2021-06-09 | 14 | 2021-06-16 |  | 2021-06-23 | 5
741 | PGE | 94062 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.48 |  | 2021-04-12 | 2021-04-16 | 4 | 2021-04-22 | 8 | 2021-05-05 | 9 | [18 empty] | 2021-04-12 | 2021-04-12 | 0 | [5 empty] | 0 | [5 empty] | 2021-05-05 | 2021-05-05 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 |  | 2021-05-05 | 0
742 | PGE | 94608 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-04-12 | 2021-05-05 | 17 | 2021-06-10 | 42 | 2021-06-16 | 4 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | 2021-07-02 | 12 |  |  |  |  | 2021-07-08 | 2021-07-19 | 7 |  |  |  |  | 2021-08-20 | 2021-11-04 | 53 | 2021-07-20 | 2021-11-07 | 78 |  |  |  | 2022-02-23 |  | 35 | 1//19 | 1//19 |  |  |  |  | 2021-08-20 | 2021-10-29 | 49 | 2021-11-04 |  | 2021-11-10 | 4
743 | PGE | 93244 | NEM | EXPNEM | Commercial | Solar PV | 125 |  | 2021-04-12 | 2021-04-23 | 9 | 2021-06-10 | 42 | [17 empty] | 2021-07-02 | 2021-07-19 | 10 | 2021-07-19 | 2021-07-19 | 0 |  |  |  |  | 2021-04-12 | 2021-06-16 | 46 |  |  |  |  | 2021-08-02 | 2022-03-24 | 162 | 2021-07-16 | 2021-11-29 | 92 |  |  |  | 2022-01-03 | 2022-02-09 | 27 | 1//19 | 1//19 |  |  |  |  | 2021-08-02 | 2022-03-07 | 149 | 2022-03-24 | 2021-08-16 | 2022-03-25 | 2 |  |  | 88
744 | PGE | 95963 | NEM | EXPNEM | Commercial | Solar PV | 43.875 |  | 2021-04-12 | 2021-04-28 | 12 | 2021-05-24 | 30 | 2021-06-08 | 10 | [15 empty] | 2021-06-08 | 2021-06-28 | 14 | 2021-06-28 | 2021-08-13 | 33 |  |  |  |  | 2021-04-12 | 2021-07-15 | 66 | 2021-08-06 |  |  |  | 2021-08-13 | 2021-09-20 | 25 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-13 | 2021-09-03 | 15 | 2021-09-20 |  | 2021-09-20 | 0
745 | PGE | 93206 | NEM | EXPNEM | Implementation | Solar PV | 900 |  | 2021-04-13 | 2021-04-28 | 11 | 2021-04-29 | 12 | [5 empty] | 2021-04-29 | 2021-06-04 | 25 | 2021-06-04 | 2021-06-04 |  | 2021-06-04 | 2021-09-01 | 64 | 2021-06-04 |  |  | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01 | 2022-03-04 | 126 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
746 | PGE | 95648 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.559 |  | 2021-04-13 | 2021-04-26 | 9 | 2021-04-26 | 9 | 2021-05-11 | 11 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-05-24 | 20 | [5 empty] | 0 | [5 empty] | 2021-05-25 | 2021-05-26 | 1 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-25 | 2021-05-26 | 1 | 2021-05-26 |  | 2021-05-26 | 0
747 | PGE | 93266 | NEM | EXPNEM | Commercial | Solar PV | 300 |  | 2021-04-13 | 2021-04-19 | 4 | 2021-05-20 | 27 | 2021-06-09 | 13 | 2021-06-09 | 2021-07-07 | 19 | [12 empty] | 2021-07-07 | 2021-07-12 | 3 | 2021-07-12 | 2021-07-12 | 0 |  |  |  |  | 2021-04-13 | 2021-05-10 | 19 |  |  |  |  | 2022-03-08 | 2022-03-16 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-03-08 | 2022-03-09 | 1 | 2022-03-16 |  | 2022-03-16 | 0
748 | PGE | 94062 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 37.8 |  | 2021-04-13 | 2021-04-14 | 1 | 2021-04-14 | 1 | 2021-04-30 | 12 | [15 empty] | 2021-04-23 | 2021-04-23 |  | 2021-05-28 | 2021-04-30 | 6 | [5 empty] | 0 | [5 empty] | 2021-06-01 | 2021-06-01 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-01 | 2021-06-01 | 0 | 2021-06-01 |  | 2021-06-01 | 0
749 | PGE | 93656 | NEM | EXPNEM | Commercial | Solar PV | 165.405 |  | 2021-04-13 | 2021-04-28 | 11 | 2021-05-21 | 28 | 2021-06-04 | 9 | [15 empty] | 2021-06-04 | 2021-06-04 | 0 | 2021-06-04 | 2021-06-07 | 1 |  |  |  |  | 2021-04-13 | 2021-06-03 | 36 |  |  |  |  | 2021-07-30 | 2021-08-09 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-30 | 2021-08-02 | 1 | 2021-08-09 |  | 2021-08-09 | 0
750 | PGE | 95545 | NEM | EXPNEM | Withdrawn | Solar PV | 31.024 |  | 2021-04-13 | 2021-04-15 | 2 | 2021-05-06 | 17 | 2021-07-09 | 44 | [15 empty] | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09 | [6 empty] | 2021-04-13 | 2021-06-15 | 44 | [16 empty] | 1//19 | 1//19
751 | PGE | 95545 | NEM | EXPNEM | Withdrawn | Solar PV | 31.024 |  | 2021-04-13 | 2021-04-15 | 2 | 2021-04-28 | 11 | 2021-05-13 | 11 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13 | [6 empty] | 2021-04-13 | 2021-07-29 | 75 | [16 empty] | 1//19 | 1//19
752 | PGE | 95341 | NEM | EXPNEM | Commercial | Solar PV | 40.1 |  | 2021-04-13 | 2021-04-14 | 1 | 2021-04-29 | 12 | 2021-05-12 | 9 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13 | 2021-05-24 | 7 |  |  |  |  | 2021-08-09 | 2021-08-18 | 7 | 2021-09-27 |  |  |  | 2021-06-05 | 2021-10-28 | 101 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-05 | 2021-10-21 | 96 | 2021-10-28 |  | 2021-10-28 | 0
753 | PGE | 95640 | NEM | EXPNEM | Commercial | Solar PV | 36 |  | 2021-04-13 | 2021-04-14 | 1 | 2021-04-14 | 1 | 2021-04-28 | 10 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-05-03 | 3 | [5 empty] | 0 | [5 empty] | 2021-07-23 | 2021-07-29 | 4 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-23 | 2021-07-23 | 0 | 2021-07-29 |  | 2021-08-10 | 8
754 | PGE | 95746 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.36 |  | 2021-04-13 | 2021-04-26 | 9 | 2021-04-26 | 9 | 2021-05-11 | 11 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-04-13 | 0 | [5 empty] | 0 | [5 empty] | 2021-05-11 | 2021-05-12 | 1 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-11 | 2021-05-12 | 1 | 2021-05-12 |  | 2021-05-12 | 0
755 | PGE | 94539 | NEM | EXPNEM | Commercial | Solar PV | 52.33 |  | 2021-04-13 | 2021-04-14 | 1 | 2021-04-23 | 8 | 2021-04-26 | 1 | [15 empty] | 2021-04-26 | 2021-05-12 | 12 | 2021-05-12 | 2021-05-14 | 2 |  |  |  |  | 2021-04-13 | 2021-05-10 | 19 |  |  |  |  | 2021-08-05 | 2021-08-18 | 9 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-05 | 2021-08-18 | 9 | 2021-08-18 |  | 2021-08-23 | 3
756 | PGE | 95669 | NEM | EXPNEM | Implementation | Solar PV | 200 |  | 2021-04-13 | 2021-04-14 | 1 | 2021-04-19 | 4 | 2021-05-04 | 11 | 2021-05-04 | 2021-06-01 | 19 | 2021-06-10 | 2021-07-08 | 19 | 2021-07-08 | 2021-07-14 | 4 | 2021-07-14 | 2021-10-06 | 61 | 2021-07-14 |  |  | 2021-10-06 | 2021-10-06 | 0 | 2021-10-06 | 2021-11-19 | 31 |  |  |  |  | 2021-04-13 | 2021-05-10 | 19 | [16 empty] | 1//19 | 1//19
757 | PGE | 95476 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 69.278 |  | 2021-04-13 | 2021-04-20 | 5 | 2021-04-30 | 13 | 2021-06-16 | 32 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | [6 empty] | 2021-04-13 | 0 | [17 empty] | 1//19 | 1//19
758 | PGE | 95236 | NEM | EXPNEM | Implementation | Solar PV | 31.024 |  | 2021-04-14 | 2021-04-23 | 7 | 2021-05-25 | 29 | [17 empty] | 2021-07-22 | 2021-08-24 | 23 | 2021-08-24 | 2022-03-28 | 148 |  |  |  |  | 2021-04-14 | 2021-06-18 | 46 |  |  |  |  | 2022-03-31 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 2022-03-31
759 | PGE | 93907 | NEM | EXPNEM | Implementation | Solar PV | 300 |  | 2021-04-14 | 2021-04-27 | 9 | 2021-06-08 | 38 | [5 empty] | 2021-06-08 | 2021-07-06 | 19 | 2021-07-06 | 2021-07-06 |  | 2021-07-06 | 2021-11-09 | 91 | 2021-07-06 |  |  | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | 2021-12-07 | 17 | [5 empty] | 0 | [8 empty] | 2022-04-06 |  | 5 | [6 empty] | 1//19 | 1//19
760 | PGE | 95304 | NEM | EXPNEM | Application Review in Progress | Solar PV | 37.858 |  | 2021-04-14 | 2021-04-26 | 8 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
761 | PGE | 95448 | NEM | EXPNEM | Implementation | Solar PV | 33.504 |  | 2021-04-14 | 2021-04-26 | 8 | 2021-06-10 | 40 | 2021-07-07 | 18 | [15 empty] | 2021-07-07 | 2021-07-16 | 7 | 2021-07-16 | 2021-07-16 | 0 |  |  |  |  | 2021-04-14 | 0 |  | 2021-06-17 | [15 empty] | 1//19 | 1//19
762 | PGE | 93726 | NEM | EXPNEM | Commercial | Solar PV | 215.661 |  | 2021-04-14 | 2021-04-15 | 1 | 2021-05-13 | 21 | 2021-05-28 | 11 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | 2021-07-12 | 29 |  |  |  |  | 2021-04-14 | 2021-06-17 | 45 |  |  |  |  | 2021-11-08 | 2021-12-02 | 15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-08 | 2021-11-23 | 10 | 2021-12-02 |  | 2021-12-09 | 5
763 | PGE | 93286 | NEM | EXPNEM | Implementation | Solar PV | 375 |  | 2021-04-14 | 2021-04-27 | 9 | 2021-08-31 | 97 | 2021-10-06 | 25 | 2021-10-06 | 2021-11-02 | 19 | [12 empty] | 2021-11-02 | 2021-11-03 | 1 | 2021-11-03 | 2022-01-19 | 51 |  |  |  |  | 2021-04-14 | 0 |  | 2021-09-08 | [15 empty] | 1//19 | 1//19
764 | PGE | 93230 | NEM | EXPNEM | Withdrawn | Solar PV | 2760 |  | 2021-04-14 | 2021-04-16 | 2 | 2021-04-21 | 5 | 2021-06-16 | 39 | [25 empty] | 2021-04-14 | 0 | [17 empty] | 1//19 | 1//19
765 | PGE | 95501 | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2021-04-14 | 2021-04-16 | 2 | 2021-05-12 | 20 | 2021-07-15 | 44 | [15 empty] | 2021-07-15 | 2021-07-16 | 1 | 2021-07-16 | 2021-10-14 | 63 |  |  |  |  | 2021-04-14 | 0 | [17 empty] | 1//19 | 1//19
766 | PGE | 93307 | NEM | EXPNEM | Application Review in Progress | Solar PV | 272.254 |  | 2021-04-15 | 2021-04-28 | 9 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
767 | PGE | 93446 | NEM | EXPNEM | Commercial | Solar PV | 300 |  | 2021-04-15 | 2021-04-28 | 9 | 2021-06-04 | 35 | 2021-06-14 | 6 | [15 empty] | 2021-06-14 | 2021-07-01 | 13 | 2021-07-01 | 2021-12-03 | 106 | [5 empty] | 0 | [5 empty] | 2021-12-03 | 2021-12-20 | 11 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-03 | 2021-12-06 | 1 | 2021-12-20 |  | 2021-12-20 | 0
768 | PGE | 95955 | NEM | EXPNEM | IA in Progress | Solar PV | 88.18 |  | 2021-04-15 | 2021-04-16 | 1 | 2021-04-28 | 9 | 2021-05-19 | 15 | 2021-05-19 | 2021-07-09 | 35 | [12 empty] | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09 | 2021-11-12 | 88 | [5 empty] | 0 | [5 empty] | 2021-12-27 | 2022-01-12 | 12 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-27 | 2021-12-28 | 1 | 2022-01-12 | 2022-01-13 |  | 1 |  |  | 189
769 | PGE | 94583 | NEM | EXPNEM | Withdrawn | Solar PV | 240 |  | 2021-04-15 | 2021-04-16 | 1 | 2021-05-04 | 13 | 2021-06-28 | 38 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | [6 empty] | 2021-04-15 | 2021-05-28 | 31 | [7 empty] | 2022-02-07 | 2022-02-07 | 0 |  |  |  | 2022-02-07 | 2022-02-07 | 1 | 1//19 | 1//19
770 | PGE | 94583 | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-04-15 | 2021-04-16 | 1 | 2021-05-04 | 13 | 2021-07-08 | 45 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [6 empty] | 2021-04-15 | 2021-05-18 | 23 | [16 empty] | 1//19 | 1//19
771 | PGE | 95215 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2043.114 |  | 2021-04-15 | 2021-04-20 | 3 | 2021-05-05 | 14 | 2021-07-31 | 60 | 2021-08-30 | 2021-10-13 | 31 | 2021-11-08 | 2021-12-08 | 19 | 2021-12-08 | 2021-12-08 | 0 | 2022-01-04 |  |  | 2021-12-08 | 2021-12-08 | 0 | [10 empty] | 2021-04-15 | 0 |  | 2021-07-21 | 2021-07-22 |  | 1 | [12 empty] | 1//19 | 1//19
772 | PGE | 93638 | Non-NEM | Non-Export | Withdrawn | ENGN | 4500 |  | 2021-04-15 | 2021-04-16 | 1 | 2021-04-21 | 4 | 2021-05-24 | 23 | 2021-07-16 | 2021-08-17 | 22 | [12 empty] | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
773 | PGE | 94558 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-04-16 | 2021-04-16 | 0 | 2021-04-28 | 8 | 2021-07-02 | 46 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-10-07 | 67 | [5 empty] | 0 | [5 empty] | 2021-11-12 | 2021-11-18 | 4 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-12 | 2021-11-12 | 0 | 2021-11-18 |  | 2021-11-19 | 1
774 | PGE | 94598 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-04-16 | 2021-04-27 | 7 | 2021-05-07 | 15 | 2021-05-10 | 1 | [15 empty] | 2021-04-27 | 2021-04-27 | 0 | 2021-04-27 | 2021-05-07 | 8 | [5 empty] | 0 | [5 empty] | 2021-05-10 | 2021-05-10 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 |  | 2021-05-10 | 0
775 | PGE | 93660 | NEM | EXPNEM | Commercial | Solar PV | 62.5 |  | 2021-04-16 | 2021-04-19 | 1 | 2021-05-21 | 25 | 2021-06-05 | 9 | [15 empty] | 2021-06-05 | 2021-06-05 | 0 | 2021-06-05 | 2021-06-11 | 4 |  |  |  |  | 2021-04-16 | 2021-06-15 | 41 |  |  |  |  | 2021-11-03 | 2021-11-12 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-03 | 2021-11-03 | 0 | 2021-11-12 |  | 2021-11-19 | 5
776 | PGE | 95206 | NEM | EXPNEM | IA in Progress | Solar PV | 342.352 |  | 2021-04-16 | 2021-04-29 | 9 | 2022-02-02 | 201 | 2022-02-07 | 3 | [15 empty] | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
777 | PGE | 95677 | NEM | EXPNEM | Commercial | Solar PV | 98.987 |  | 2021-04-16 | 2021-04-19 | 1 | 2021-04-22 | 4 | 2021-05-04 | 8 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | 2021-07-01 | 41 |  |  |  |  | 2021-04-16 | 2021-07-23 | 68 |  |  |  |  | 2021-07-12 | 2021-07-22 | 8 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-12 | 2021-07-12 | 0 | 2021-07-22 |  | 2021-07-29 | 5
778 | PGE | 95348 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-04-16 | 2021-04-19 | 1 | 2021-06-16 | 42 | 2021-07-01 | 11 | [15 empty] | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01 | 2021-10-28 | 83 |  |  |  |  | 2021-04-16 | 2021-06-24 | 48 |  |  |  |  | 2021-10-18 | 2021-11-01 | 10 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-18 | 2021-10-29 | 9 | 2021-11-01 |  | 2021-11-03 | 2
779 | PGE | 95677 | NEM | VNEMSOMAH | Implementation | Solar PV | 86.4 |  | 2021-04-16 | 2021-04-30 | 10 | 2021-06-11 | 39 | 2021-07-02 | 15 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-11-22 | 98 |  |  |  |  | 2021-06-28 | 2021-07-15 | 12 |  | 2021-07-19 | 2021-07-19 | 0 | [12 empty] | 1//19 | 1//19
780 | PGE | 93245 | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-04-16 | 2021-04-30 | 10 | 2021-07-15 | 62 | 2021-09-08 | 38 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | [6 empty] | 2021-04-16 | 2021-07-02 | 54 | [16 empty] | 1//19 | 1//19
781 | PGE | 93631 | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2021-04-16 | 2021-04-19 | 1 | 2021-04-19 | 1 | 2021-04-23 | 4 | [15 empty] | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | 2022-02-24 | 211 |  |  |  |  | 2021-04-16 | 2021-05-07 | 15 | [16 empty] | 1//19 | 1//19
782 | PGE | 95206 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2012.104 |  | 2021-04-19 | 2021-04-19 | 0 | 2021-05-05 | 12 | 2021-08-03 | 62 | 2021-08-30 | 2021-10-13 | 31 | 2021-11-08 | 2021-12-08 | 19 | 2021-12-08 | [18 empty] | 2021-04-19 | 0 |  | 2021-07-22 | 2021-07-22 |  | 0 | [12 empty] | 1//19 | 1//19
783 | PGE | 93638 | NEM | EXPNEM | Commercial | Solar PV | 170 |  | 2021-04-19 | 2021-04-19 | 0 | 2021-06-10 | 37 | 2021-06-29 | 13 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | 2021-08-19 | 36 |  |  |  |  | 2021-04-19 | 2021-09-07 | 98 |  |  |  |  | 2021-12-06 | 2021-12-16 | 8 | 2021-09-30 | 2021-09-30 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-06 | 2021-12-07 | 1 | 2021-12-16 |  | 2021-12-21 | 3
784 | PGE | 93638 | NEM | EXPNEM | Commercial | Solar PV | 196 |  | 2021-04-19 | 2021-04-19 | 0 | 2021-06-10 | 37 | 2021-06-29 | 13 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | 2021-08-25 | 40 |  |  |  |  | 2021-04-19 | 2021-08-05 | 76 |  |  |  |  | 2022-02-18 | 2022-02-28 | 5 | 2021-11-15 | 2021-11-15 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 2022-02-18 | 2022-02-18 | 0 | 2022-02-28 |  | 2022-03-03 | 3
785 | PGE | 94928 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-04-19 | 2021-04-21 | 2 | 2021-05-05 | 12 | 2021-07-06 | 42 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-09-20 | 53 | [5 empty] | 0 | [5 empty] | 2021-10-20 | 2021-11-04 | 11 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-20 | 2021-10-20 | 0 | 2021-11-04 |  | 2021-11-04 | 0
786 | PGE | 95242 | Non-NEM | NEMFC | Withdrawn | FUCE | 1470 |  | 2021-04-20 | 2021-05-04 | 10 | 2021-05-06 | 12 | 2021-07-27 | 56 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-10-22 | 62 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
787 | PGE | 95020 | NEM | EXPNEM | IA in Progress | Solar PV | 300 |  | 2021-04-20 | 2021-05-04 | 10 | 2021-05-14 | 18 | 2021-08-09 | 59 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-07-13 | 28 |  |  |  |  | 2021-06-17 | 2021-07-02 | 11 |  |  |  |  | 2021-11-05 | 2022-01-18 | 48 | 2021-09-01 | 2022-01-04 | 84 |  |  |  | 2022-03-08 |  | 26 | 1//19 | 1//19 |  |  |  |  | 2021-11-05 | 2022-01-06 | 41 | 2022-01-18 | 2022-01-19 |  | 1 |  |  | 189
788 | PGE | 93631 | NEM | EXPNEM | Commercial | Solar PV | 240 |  | 2021-04-20 | 2021-04-21 | 1 | 2021-04-28 | 6 | 2021-05-10 | 8 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2021-11-12 | 130 |  |  |  |  | 2021-04-20 | 2021-05-07 | 13 |  |  |  |  | 2021-11-12 | 2021-12-03 | 13 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-12 | 2021-11-24 | 8 | 2021-12-03 |  | 2021-12-09 | 4
789 | PGE | 93618 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-04-20 | 2021-04-21 | 1 | 2021-04-27 | 5 | 2021-05-10 | 9 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2022-02-25 | 201 |  |  |  |  | 2021-04-20 | 2021-05-10 | 14 | [16 empty] | 1//19 | 1//19
790 | PGE | 93618 | NEM | EXPNEM | IA in Progress | Solar PV | 117.475 |  | 2021-04-20 | 2021-04-21 | 1 | 2021-04-28 | 6 | 2021-05-12 | 10 | [15 empty] | 2021-05-12 | 2021-05-12 | 0 | 2021-05-12 | 2021-06-11 | 21 | [5 empty] | 0 | [8 empty] | 2021-07-16 | 2021-12-08 | 99 |  |  |  | 2022-01-13 |  | 64 | 1//19 | 1//19
792 | PGE | 93673 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-04-20 | 2021-04-21 | 1 | 2021-04-28 | 6 | 2021-05-11 | 9 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2021-11-24 | 137 |  |  |  |  | 2021-04-20 | 2021-05-07 | 13 |  |  |  |  | 2021-11-26 | 2021-12-06 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-26 | 2021-11-29 | 0 | 2021-12-06 |  | 2021-12-10 | 4
793 | PGE | 93662 | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2021-04-20 | 2021-04-21 | 1 | 2021-04-28 | 6 | 2021-05-11 | 9 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2022-02-24 | 199 |  |  |  |  | 2021-04-20 | 2021-05-07 | 13 | [16 empty] | 1//19 | 1//19
794 | PGE | 95050 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 279.436 |  | 2021-04-21 | 2021-05-06 | 11 | 2021-06-15 | 38 | 2021-07-28 | 30 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | 2021-08-09 | 8 | [5 empty] | 0 |  | 2021-07-08 | 2021-07-21 | 2021-07-28 | 9 | [12 empty] | 1//19 | 1//19
795 | PGE | 94040 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.564 |  | 2021-04-21 | 2021-04-26 | 3 | 2021-05-20 | 21 | 2021-05-24 | 2 | [18 empty] | 2021-05-20 | 2021-05-20 | 0 | [5 empty] | 0 | [5 empty] | 2021-09-09 | 2021-09-09 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 |  | 2021-09-09 | 0
796 | PGE | 94087 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-04-21 | 2021-04-29 | 6 | 2021-05-04 | 9 | 2021-05-25 | 15 | [15 empty] | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-06-14 | 13 | [5 empty] | 0 | [5 empty] | 2021-06-14 | 2021-06-23 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-14 | 2021-06-15 | 1 | 2021-06-23 |  | 2021-06-24 | 1
797 | PGE | 95963 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-04-21 | 2021-04-22 | 1 | 2021-06-18 | 41 | 2021-07-08 | 13 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-15 | 5 |  |  |  |  | 2021-04-21 | 2021-05-18 | 19 |  |  |  |  | 2021-07-15 | 2021-07-20 | 3 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-15 | 2021-07-16 | 1 | 2021-07-20 |  | 2021-07-27 | 5
798 | PGE | 93420 | NEM | EXPNEM | Implementation | Solar PV | 61.513 |  | 2021-04-21 | 2021-05-04 | 9 | 2022-01-20 | 189 | 2022-02-17 | 20 | [15 empty] | 2022-02-17 | 2022-02-17 | 0 | 2022-02-17 | 2022-03-07 | 11 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
799 | PGE | 95687 | Non-NEM | NEMFC | Implementation | FUCE | 262.5 |  | 2021-04-22 | 2021-05-06 | 10 | 2021-05-06 | 10 | 2021-05-27 | 15 | [15 empty] | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-10-11 | 94 |  |  |  |  | 2021-04-22 | 0 | [17 empty] | 1//19 | 1//19
800 | PGE | 94538 | NEM | EXPNEM | Implementation | Solar PV | 89.246 |  | 2021-04-22 | 2021-05-04 | 8 | 2021-05-17 | 17 | 2021-06-28 | 29 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-07-12 | 9 |  |  |  |  | 2021-04-22 | 2021-09-08 | 96 | 2021-07-29 |  |  |  | 2021-09-10 | 2021-09-21 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-10 | 2021-09-13 | 1 | 2021-09-21
801 | PGE | 93420 | Non-NEM | Non-Export | Withdrawn | Storage | 420 |  | 2021-04-22 | 2021-04-23 | 1 | 2021-05-19 | 19 | 2021-06-18 | 21 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-18 | 2021-06-23 | 3 |  |  |  |  | 2021-04-22 | 0 | [17 empty] | 1//19 | 1//19
802 | PGE | 95441 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 36.12 |  | 2021-04-22 | 2021-04-27 | 3 | 2021-04-27 | 3 | 2021-04-28 | 1 | [18 empty] | 2021-04-22 | 2021-04-27 | 3 | [5 empty] | 0 | [5 empty] | 2021-04-28 | 2021-05-05 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-04-28 | 2021-04-28 | 0 | 2021-05-05 |  | 2021-05-06 | 1
803 | PGE | 95404 | NEM | EXPNEM | Commercial | Solar PV | 326.971 |  | 2021-04-22 | 2021-04-23 | 1 | 2021-04-30 | 6 | 2021-05-19 | 13 | [15 empty] | 2021-05-19 | 2021-05-19 | 0 | 2021-05-19 | 2021-05-25 | 4 |  |  |  |  | 2021-04-22 | 2021-05-07 | 11 |  |  |  |  | 2022-01-27 | 2022-02-16 | 14 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-01-27 | 2022-01-27 | 0 | 2022-02-16 |  | 2022-02-22 | 3
804 | PGE | 95688 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.38 |  | 2021-04-22 | 2021-04-30 | 6 | 2021-05-05 | 9 | 2021-05-14 | 7 | [15 empty] | 2021-04-30 | 2021-04-30 | 0 | 2021-04-30 | 2021-05-12 | 8 | [5 empty] | 0 | [5 empty] | 2021-05-14 | 2021-05-14 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-14 | 2021-05-14 | 0 | 2021-05-14 |  | 2021-05-17 | 1
805 | PGE | 93454 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-04-22 | 2021-04-23 | 1 | 2021-05-03 | 7 | 2021-05-21 | 14 | [15 empty] | 2021-05-21 | 2021-06-16 | 17 | 2021-06-16 | 2022-01-17 | 147 | [5 empty] | 0 | [5 empty] | 2022-01-18 | 2022-01-26 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-01-18 | 2022-01-19 | 1 | 2022-01-26 |  | 2022-01-27 | 1
806 | PGE | 95320 | NEM | EXPNEM | Commercial | Solar PV | 86 |  | 2021-04-22 | 2021-05-04 | 8 | 2021-05-04 | 8 | 2021-05-26 | 16 | [15 empty] | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 | 2021-08-24 | 62 |  |  |  |  | 2021-05-26 | 2021-09-08 | 72 |  |  |  |  | 2021-10-05 | 2021-10-19 | 10 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-05 | 2021-10-14 | 7 | 2021-10-19 |  | 2021-10-19 | 0
807 | PGE | 94574 | NEM | EXPNEM | Commercial | Solar PV | 116.6 |  | 2021-04-22 | 2021-04-26 | 2 | 2021-06-02 | 28 | 2021-06-21 | 13 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-23 | 2 | [5 empty] | 0 | [5 empty] | 2021-07-17 | 2021-07-28 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-17 | 2021-07-19 | 0 | 2021-07-28 |  | 2021-10-27 | 64
809 | PGE | 95602 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 38.019 |  | 2021-04-22 | 2021-05-03 | 7 | 2021-05-03 | 7 | 2021-05-05 | 2 | [15 empty] | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | 2021-05-03 | 0 | [5 empty] | 0 | [5 empty] | 2021-05-05 | 2021-05-05 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 |  | 2021-05-10 | 3
810 | PGE | 95565 | Non-NEM | Non-Export | Implementation | Storage | 572 |  | 2021-04-22 | 2021-04-23 | 1 | 2021-05-19 | 19 | 2021-09-10 | 79 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | 2021-12-16 | 66 |  |  |  |  | 2021-04-22 | 2021-06-16 | 38 | [16 empty] | 1//19 | 1//19
811 | PGE | 95076 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.604 |  | 2021-04-23 | 2021-05-05 | 8 | 2021-06-22 | 41 | 2022-02-23 | 169 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-06-22 | 33 | [5 empty] | 0 | [5 empty] | 2022-02-23 | 2022-02-24 | 1 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-02-23 | 2022-02-24 | 1 | 2022-02-24 |  | 2022-02-24 | 0
812 | PGE | 94560 | NEM | EXPNEM | Commercial | Solar PV | 908.3 |  | 2021-04-23 | 2021-04-29 | 4 | 2021-04-30 | 5 | 2021-05-17 | 11 | 2021-07-07 | 2021-08-05 | 21 | [12 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | 2022-01-19 | 114 | [5 empty] | 0 | [5 empty] | 2022-01-20 | 2022-03-11 | 35 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-01-20 | 2022-03-11 | 35 | 2022-03-11 |  | 2022-03-11 | 0
813 | PGE | 93637 | NEM | EXPNEM | Commercial | Solar PV | 240 |  | 2021-04-23 | 2021-05-04 | 7 | 2021-05-17 | 16 | 2021-06-01 | 10 | [15 empty] | 2021-06-01 | 2021-06-10 | 7 | 2021-06-10 | 2021-08-18 | 48 |  |  |  |  | 2021-04-23 | 2021-06-17 | 38 |  |  |  |  | 2021-11-24 | 2021-12-02 | 4 | 2021-09-28 | 2021-09-28 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-24 | 2021-11-24 | 0 | 2021-12-02 |  | 2021-12-03 | 1
814 | PGE | 93637 | NEM | EXPNEM | Commercial | Solar PV | 240 |  | 2021-04-23 | 2021-05-04 | 7 | 2021-05-21 | 20 | 2021-06-02 | 7 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-08-25 | 59 |  |  |  |  | 2021-04-23 | 2021-06-17 | 38 |  |  |  |  | 2021-12-03 | 2021-12-14 | 7 | 2021-09-28 | 2021-09-28 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-03 | 2021-12-06 | 1 | 2021-12-14 |  | 2021-12-14 | 0
815 | PGE | 93638 | NEM | EXPNEM | Commercial | Solar PV | 320 |  | 2021-04-23 | 2021-05-04 | 7 | 2021-06-08 | 31 | 2021-06-23 | 11 | [15 empty] | 2021-08-03 | 2021-08-03 | 0 | 2021-08-03 | 2021-08-18 | 11 |  |  |  |  | 2021-04-23 | 2021-08-13 | 78 |  |  |  |  | 2022-02-16 | 2022-03-10 | 15 | 2021-11-10 | 2021-11-10 | 0 |  |  |  | 2022-01-22 | 2022-01-22 | 1 | 1//19 | 1//19 |  |  |  |  | 2022-02-16 | 2022-03-03 | 10 | 2022-03-10 |  | 2022-03-10 | 0
816 | PGE | 95206 | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-04-23 | 2021-04-26 | 1 | 2021-04-29 | 4 | 2021-05-20 | 15 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2021-05-24 | 2 |  |  |  |  | 2021-04-23 | 2021-05-10 | 11 |  |  |  |  | 2021-12-23 | 2021-12-30 | 5 | 2021-08-23 | 2022-02-23 | 127 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-23 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-31 |  | 1 |  |  | 174
817 | PGE | 96080 | Non-NEM | Non-Export | Commercial | Storage | 140 |  | 2021-04-23 | 2021-04-27 | 2 | 2021-05-19 | 18 | 2021-06-17 | 20 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-08-11 | 38 |  |  |  |  | 2021-04-23 | 0 | [5 empty] | 2022-02-16 | 2022-03-10 | 15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-02-16 | 2022-03-10 | 15 | 2022-03-10 |  | 2022-03-15 | 3
818 | PGE | 96080 | NEM | EXPNEM | Implementation | Solar PV | 375 |  | 2021-04-23 | 2021-05-05 | 8 | 2021-05-21 | 20 | 2021-06-28 | 25 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-09-24 | 62 |  |  |  |  | 2021-04-23 | 2021-06-03 | 28 | [16 empty] | 1//19 | 1//19
819 | PGE | 94605 | NEM | EXPNEM | Commercial | Solar PV | 300 |  | 2021-04-23 | 2021-04-26 | 1 | 2021-06-05 | 29 | 2021-06-16 | 7 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | 2021-10-12 | 82 |  | 2021-12-08 | 2021-12-29 | 15 |  | 0 | [5 empty] | 2021-11-03 | 2021-11-29 | 15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-03 | 2021-11-17 | 9 | 2021-11-29 |  | 2021-12-02 | 3
820 | PGE | 95125 | NEM | EXPNEM | Commercial | Solar PV | 30.45 |  | 2021-04-23 | 2021-05-04 | 7 | 2021-05-18 | 17 | 2021-06-03 | 11 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-16 | 9 |  |  |  |  | 2021-04-23 | 2021-05-28 | 25 |  |  |  |  | 2021-07-30 | 2021-08-25 | 18 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-30 | 2021-08-18 | 13 | 2021-08-25 |  | 2021-08-30 | 3
821 | PGE | 94024 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 38.23 |  | 2021-04-23 | 2021-05-05 | 8 | 2021-05-20 | 19 | 2021-05-24 | 2 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-05-25 | 14 | [5 empty] | 0 | [5 empty] | 2021-08-13 | 2021-08-23 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-13 | 2021-08-13 | 0 | 2021-08-23 |  | 2021-08-23 | 0
822 | PGE | 93637 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-04-23 | 2021-05-05 | 8 | 2021-06-02 | 27 | 2021-06-17 | 11 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-06-29 | 8 |  |  |  |  | 2021-04-23 | 2021-06-15 | 36 |  |  |  |  | 2022-02-17 | 2022-03-03 | 9 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-02-17 | 2022-03-03 | 9 | 2022-03-03 |  | 2022-03-03 | 0
823 | PGE | 94062 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 52.72 |  | 2021-04-23 | 2021-05-05 | 8 | 2021-05-26 | 23 | 2021-06-03 | 5 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-07-14 | 48 | [5 empty] | 0 | [5 empty] | 2021-07-30 | 2021-08-04 | 3 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-30 | 2021-07-30 | 0 | 2021-08-04 |  | 2021-08-05 | 1
824 | PGE | 93451 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 1804.932 |  | 2021-04-23 | 2021-04-27 | 2 | 2021-06-09 | 32 | 2021-10-18 | 91 | 2021-11-03 | 2021-12-30 | 38 | [22 empty] | 2021-04-23 | 0 | [17 empty] | 1//19 | 1//19
825 | PGE | 93637 | NEM | NEMMT | Implementation | Solar PV, Storage | 478 |  | 2021-04-23 | 2021-05-10 | 11 | 2021-06-15 | 36 | 2021-07-07 | 15 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | 2022-01-31 | 143 | [5 empty] | 0 |  | 2021-09-22 | 2021-10-01 | 2021-10-15 | 7 | [12 empty] | 1//19 | 1//19
826 | PGE | 95472 | NEM | EXPNEM | Commercial | Solar PV | 30.45 |  | 2021-04-23 | 2021-04-28 | 3 | 2021-05-24 | 21 | 2021-06-10 | 12 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-06-21 | 7 |  |  |  |  | 2021-04-23 | 2021-05-26 | 23 |  |  |  |  | 2021-12-06 | 2021-12-23 | 13 | 2021-08-16 | 2021-11-22 | 68 |  |  |  | 2021-11-24 | 2021-12-27 | 2 | 1//19 | 1//19 |  |  |  |  | 2021-12-06 | 2021-12-07 | 1 | 2021-12-23 | 2021-12-23 | 2021-12-29 | 0 |  |  | 168
827 | PGE | 95616 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-04-23 | 2021-04-26 | 1 | 2021-05-12 | 13 | 2021-07-12 | 41 | [15 empty] | 2021-07-12 | 2021-07-30 | 14 | 2021-07-30 | 2021-08-11 | 8 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
828 | PGE | 93614 | NEM | EXPNEM | Commercial | Solar PV | 69.457 |  | 2021-04-23 | 2021-05-05 | 8 | 2021-06-08 | 31 | 2021-06-22 | 10 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-06-29 | 5 | [5 empty] | 0 | [5 empty] | 2021-10-07 | 2021-10-14 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-07 | 2021-10-08 | 1 | 2021-10-14 |  | 2021-10-14 | 0
829 | PGE | 95423 | NEM | EXPNEM | Withdrawn | Solar PV | 32.505 |  | 2021-04-25 | 2021-05-06 | 8 | 2021-05-21 | 19 | 2021-06-09 | 12 | [25 empty] | 2021-04-25 | 0 | [17 empty] | 1//19 | 1//19
830 | PGE | 95116 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-04-25 | 2021-04-26 | 0 | 2021-05-12 | 12 | 2021-07-02 | 36 | [15 empty] | 2021-07-02 | 2021-07-23 | 14 | 2021-07-23 | 2021-08-11 | 13 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
831 | PGE | 94612 | NEM | EXPNEM | Commercial | Solar PV | 41.566 |  | 2021-04-26 | 2021-04-27 | 1 | 2021-08-09 | 73 | 2021-08-25 | 12 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | 2021-09-07 | 8 |  |  |  |  | 2021-05-07 | 2021-09-08 | 85 |  |  |  |  | 2022-01-25 | 2022-02-01 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-01-25 | 2022-01-25 | 0 | 2022-02-01 |  | 2022-02-07 | 4
832 | PGE | 94558 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 58.082 |  | 2021-04-26 | 2021-05-07 | 9 | 2021-05-13 | 13 | 2021-05-17 | 2 | [15 empty] | 2021-05-17 | 2021-05-17 | 0 | 2021-05-17 | 2021-11-02 | 118 |  |  |  |  | 2021-05-17 | 2021-05-28 | 9 |  |  |  |  | 2021-11-23 | 2022-02-01 | 47 | 2021-12-17 | 2022-03-24 | 68 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-23 | 2022-01-19 | 38 | 2022-02-01 | 2022-02-24 |  | 16 |  |  | 210
833 | PGE | 93622 | NEM | EXPNEM | Commercial | Solar PV | 30.165 |  | 2021-04-26 | 2021-04-27 | 1 | 2021-05-05 | 7 | 2021-05-21 | 12 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-08-31 | 70 | [5 empty] | 0 | [5 empty] | 2021-10-06 | 2021-10-14 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-06 | 2021-10-06 | 0 | 2021-10-14 |  | 2021-10-21 | 5
834 | PGE | 93637 | NEM | EXPNEM | Implementation | Solar PV | 530 |  | 2021-04-26 | 2021-05-07 | 9 | 2021-06-08 | 30 | 2021-06-24 | 12 | [15 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-24 | 2021-08-17 | 37 |  |  |  |  | 2021-08-17 | 2021-08-31 | 10 | [7 empty] | 2022-01-24 | 2022-03-08 | 31 | [6 empty] | 1//19 | 1//19
835 | PGE | 93638 | NEM | EXPNEM | Commercial | Solar PV | 520 |  | 2021-04-26 | 2021-05-10 | 10 | 2021-05-18 | 16 | 2021-06-07 | 13 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-08-25 | 56 |  |  |  |  | 2021-06-09 | 2021-06-17 | 6 |  |  |  |  | 2021-12-06 | 2021-12-16 | 8 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-06 | 2021-12-07 | 1 | 2021-12-16 |  | 2021-12-17 | 1
836 | PGE | 94720 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 2119.8 |  | 2021-04-26 | 2021-04-29 | 3 | 2021-05-26 | 22 | 2021-07-01 | 25 | 2021-07-22 | 2021-08-25 | 24 | [12 empty] | 2021-09-15 | [9 empty] | 2021-04-26 | 0 | [17 empty] | 1//19 | 1//19
837 | PGE | 93662 | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2021-04-26 | 2021-04-27 | 1 | 2021-04-27 | 1 | 2021-05-10 | 9 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2022-02-23 | 199 |  |  |  |  | 2021-04-26 | 2021-05-25 | 21 | [16 empty] | 1//19 | 1//19
838 | PGE | 94024 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 40.591 |  | 2021-04-26 | 2021-05-07 | 9 | 2021-05-07 | 9 | 2021-05-24 | 11 | [15 empty] | 2021-05-07 | 2021-05-07 | 0 | 2021-05-07 | 2021-05-11 | 2 | [5 empty] | 0 | [5 empty] | 2021-08-17 | 2021-08-24 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-17 | 2021-08-17 | 0 | 2021-08-24 |  | 2021-08-25 | 1
839 | PGE | 93618 | NEM | EXPNEM | Commercial | Solar PV | 58.738 |  | 2021-04-26 | 2021-04-27 | 1 | 2021-04-27 | 1 | 2021-05-10 | 9 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2021-12-01 | 141 |  |  |  |  | 2021-04-26 | 2021-05-25 | 21 |  |  |  |  | 2021-12-03 | 2021-12-22 | 13 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-03 | 2021-12-14 | 7 | 2021-12-22 |  | 2021-12-27 | 3
840 | PGE | 93242 | NEM | EXPNEM | IA in Progress | Solar PV | 46.99 |  | 2021-04-26 | 2021-04-27 | 1 | 2021-04-27 | 1 | 2021-05-10 | 9 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2022-02-10 | 191 |  |  |  |  | 2021-04-26 | 2021-05-26 | 22 | [16 empty] | 1//19 | 1//19
841 | PGE | 95946 | NEM | EXPNEM | Implementation | Solar PV | 34.179 |  | 2021-04-27 | 2021-04-28 | 1 | 2021-05-18 | 15 | 2021-06-09 | 15 | 2021-06-09 | 2021-07-08 | 20 | 2021-07-21 | 2021-08-18 | 20 | 2021-08-18 | 2021-08-18 |  | 2021-08-18 | 2021-11-10 | 61 | 2021-08-18 |  |  | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | 2021-12-16 | 23 |  |  |  |  | 2021-04-27 | 0 |  | 2021-05-25 | [6 empty] | 2022-01-20 |  | 59 | [6 empty] | 1//19 | 1//19
842 | PGE | 94538 | NEM | EXPNEM | Commercial | Solar PV | 65.188 |  | 2021-04-27 | 2021-04-28 | 1 | 2021-06-17 | 36 | 2021-07-09 | 15 | [15 empty] | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12 | 2021-09-21 | 50 | [5 empty] | 0 | [5 empty] | 2021-10-05 | 2021-10-13 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-05 | 2021-10-06 | 1 | 2021-10-13 |  | 2021-10-19 | 4
843 | PGE | 93637 | NEM | EXPNEM | Implementation | Solar PV | 192 |  | 2021-04-27 | 2021-05-03 | 4 | 2021-05-10 | 9 | 2021-06-03 | 17 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-08-25 | 58 |  |  |  |  | 2021-04-27 | 0 | [17 empty] | 1//19 | 1//19
844 | PGE | 94583 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-04-27 | 2021-05-03 | 4 | 2021-05-03 | 4 | 2021-05-20 | 13 | [26 empty] | 0 | [5 empty] | 2021-05-21 | 2021-05-21 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 |  | 2021-05-21 | 0
845 | PGE | 93637 | NEM | EXPNEM | Commercial | Solar PV | 410.518 |  | 2021-04-27 | 2021-05-03 | 4 | 2021-06-16 | 35 | 2021-06-28 | 8 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-08-16 | 34 |  |  |  |  | 2021-04-27 | 2021-08-27 | 86 |  |  |  |  | 2022-03-01 | 2022-03-08 | 5 | 2021-11-23 | 2021-11-23 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 2022-03-01 | 2022-03-01 | 0 | 2022-03-08 |  | 2022-03-08 | 0
846 | PGE | 95926 | NEM | EXPNEM | Withdrawn | Solar PV | 177.127 |  | 2021-04-27 | 2021-05-11 | 10 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
847 | PGE | 95422 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 206.6 |  | 2021-04-27 | 2021-05-10 | 9 | 2021-05-10 | 9 | 2021-08-16 | 68 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | 2021-10-11 | 39 |  |  |  |  | 2021-04-27 | 0 | [17 empty] | 1//19 | 1//19
848 | PGE | 93647 | NEM | EXPNEM | Application Review in Progress | Solar PV | 206.358 |  | 2021-04-27 | 2021-05-10 | 9 | [29 empty] | 2021-04-27 | 0 | [17 empty] | 1//19 | 1//19
849 | PGE | 93673 | NEM | EXPNEM | Commercial | Solar PV | 36 |  | 2021-04-27 | 2021-04-28 | 1 | 2021-04-28 | 1 | 2021-05-11 | 9 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2021-10-12 | 107 |  |  |  |  | 2021-04-27 | 2021-05-25 | 20 |  |  |  |  | 2021-10-19 | 2021-10-27 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-19 | 2021-10-19 | 0 | 2021-10-27 |  | 2021-11-01 | 3
850 | PGE | 93618 | NEM | EXPNEM | Commercial | Solar PV | 36 |  | 2021-04-27 | 2021-04-29 | 2 | 2021-04-29 | 2 | 2021-05-11 | 8 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2021-12-02 | 141 |  |  |  |  | 2021-04-27 | 2021-05-10 | 9 |  |  |  |  | 2021-12-03 | 2021-12-10 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-03 | 2021-12-06 | 1 | 2021-12-10 |  | 2021-12-17 | 5
851 | PGE | 93311 | NEM | EXPNEM | IA in Progress | Solar PV | 240 |  | 2021-04-27 | 2021-05-03 | 4 | 2021-05-03 | 4 | 2021-05-20 | 13 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2022-01-25 | 171 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
852 | PGE | 95205 | NEM | EXPNEM | Implementation | Solar PV | 56.869 |  | 2021-04-28 | 2021-05-03 | 3 | 2021-05-19 | 15 | 2021-06-02 | 9 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-08-02 | 42 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
853 | PGE | 95667 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-04-28 | 2021-04-28 | 0 | 2021-05-26 | 20 | 2021-06-30 | 24 | [15 empty] | 2021-06-30 | 2021-07-20 | 13 | 2021-07-20 | 2021-08-30 | 29 |  |  |  |  | 2021-04-28 | 2021-06-21 | 37 | [16 empty] | 1//19 | 1//19
854 | PGE | 95687 | Non-NEM | NEMFC | IA in Progress | FUCE | 262.5 |  | 2021-04-28 | 2021-05-12 | 10 | 2021-07-09 | 50 | 2021-09-02 | 39 | [15 empty] | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02 | 2021-10-27 | 38 |  |  |  |  | 2021-04-28 | 2021-07-19 | 56 | [16 empty] | 1//19 | 1//19
855 | PGE | 95133 | NEM | EXPNEM | Implementation | Solar PV | 34.082 |  | 2021-04-28 | 2021-05-03 | 3 | 2021-05-20 | 16 | 2021-06-10 | 14 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-06-17 | 5 |  |  |  |  | 2021-04-28 | 0 |  | 2021-08-26 | [15 empty] | 1//19 | 1//19
856 | PGE | 93422 | Non-NEM | Non-Export | Implementation | Storage | 929.5 |  | 2021-04-28 | 2021-05-03 | 3 | 2021-05-26 | 20 | 2021-06-17 | 15 | 2021-07-23 | 2021-08-20 | 20 | 2021-09-03 | 2021-09-27 | 15 | 2021-09-27 | 2021-09-27 |  | 2021-09-27 | 2021-11-15 | 36 | 2021-09-27 |  |  | 2021-12-14 | 2021-12-15 | 1 | 2021-12-15 | 2022-03-07 | 56 |  |  |  |  | 2021-04-28 | 2021-05-27 | 21 | [16 empty] | 1//19 | 1//19
857 | PGE | 93908 | NEM | NEM Paired Storage | Study in Progress | ENGN, Solar PV, Storage | 3443.5 |  | 2021-04-28 | 2021-05-06 | 6 | 2021-08-23 | 81 | 2021-09-13 | 14 | 2021-09-23 | 2021-11-30 | 45 | 2021-12-16 | 2022-01-13 | 20 | 2022-01-13 | 2022-01-20 | 4 |  |  |  | 2022-01-20 | [13 empty] | 0 | [17 empty] | 1//19 | 1//19
858 | PGE | 94561 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-04-28 | 2021-04-29 | 1 | 2021-05-28 | 22 | 2021-06-02 | 2 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-06-08 | 4 | [5 empty] | 0 | [5 empty] | 2021-06-10 | 2021-07-29 | 34 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-10 | 2021-07-21 | 28 | 2021-07-29 |  | 2021-08-04 | 4
859 | PGE | 93906 | NEM | NEMMT | IA in Progress | Solar PV, Storage | 2071.458 |  | 2021-04-28 | 2021-05-03 | 3 | 2021-05-26 | 20 | 2021-12-10 | 136 | 2022-02-04 | 2022-03-07 | 20 | [12 empty] | 2022-03-07 | 2022-03-07 | 0 | 2022-03-07 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
860 | PGE | 95361 | NEM | EXPNEM | Commercial | Solar PV | 53.84 |  | 2021-04-28 | 2021-04-29 | 1 | 2021-05-06 | 6 | 2021-05-25 | 13 | [15 empty] | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-05-27 | 2 |  |  |  |  | 2021-06-02 | 2021-06-15 | 9 |  |  |  |  | 2021-08-06 | 2021-08-20 | 10 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-06 | 2021-08-20 | 10 | 2021-08-20 |  | 2021-08-27 | 5
861 | PGE | 95032 | NEM | EXPNEM | Commercial | Solar PV | 31.024 |  | 2021-04-29 | 2021-04-29 | 0 | 2021-06-08 | 27 | 2021-06-29 | 15 | [26 empty] | 0 | [5 empty] | 2021-06-29 | 2021-07-15 | 11 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-29 | 2021-07-22 | 16 | 2021-07-15 |  | 2021-07-20 | 3
862 | PGE | 93263 | NEM | EXPNEM | Implementation | Solar PV | 600 |  | 2021-04-29 | 2021-05-11 | 8 | 2021-05-13 | 10 | [5 empty] | 2021-05-13 | 2021-06-11 | 20 | 2021-06-11 | 2021-06-11 |  | 2021-06-11 | 2021-09-03 | 61 | 2021-06-11 |  |  | 2021-09-03 | 2021-09-03 |  | 2021-09-03 | 2021-09-20 | 12 | 10 |  |  |  |  | 0 |  | 2021-10-08 | [6 empty] | 2021-11-11 | 2022-03-22 | 89 | [6 empty] | 1//19 | 1//19
863 | PGE | 95119 | NEM | EXPNEM | Application Review in Progress | Solar PV | 45.653 |  | 2021-04-29 | 2021-05-10 | 7 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
864 | PGE | 95334 | NEM | EXPNEM | Commercial | Solar PV | 187.5 |  | 2021-04-29 | 2021-04-29 | 0 | 2021-05-12 | 9 | 2021-05-28 | 12 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | 2021-06-09 | 7 |  |  |  |  | 2021-04-29 | 2021-05-26 | 19 |  |  |  |  | 2021-03-29 | 2021-09-09 | 115 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-03-29 | 2021-09-02 | 111 | 2021-09-09 |  | 2021-09-16 | 5
865 | PGE | 95688 | NEM | EXPNEM | IA in Progress | Solar PV | 180 |  | 2021-04-29 | 2021-05-10 | 7 | 2021-08-02 | 65 | 2021-08-18 | 12 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | [6 empty] | 2021-04-29 | 0 | [17 empty] | 1//19 | 1//19
866 | PGE | 93666 | NEM | EXPNEM | IA in Progress | Solar PV | 58.738 |  | 2021-04-29 | 2021-04-30 | 1 | 2021-04-30 | 1 | 2021-05-11 | 7 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2022-02-23 | 198 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
867 | PGE | 93622 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 37.5 |  | 2021-04-29 | 2021-05-12 | 9 | 2021-05-18 | 13 | 2021-06-03 | 11 | [15 empty] | 2021-06-03 | 2021-06-09 | 4 | 2021-06-09 | 2021-06-11 | 2 |  |  |  |  | 2021-04-29 | 2021-06-16 | 33 |  |  |  |  | 2021-09-10 | 2021-09-21 | 7 | 2022-01-10 | 2022-02-01 | 16 |  |  |  | 2022-02-01 |  | 51 | 1//19 | 1//19 |  |  |  |  | 2021-09-10 | 2021-09-13 | 1 | 2021-09-21 | 2021-09-22 |  | 1 |  |  | 101
868 | PGE | 93637 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-04-30 | 2021-04-30 | 0 | 2021-05-06 | 4 | 2021-05-24 | 12 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24 | 2021-06-01 | 5 |  |  |  |  | 2021-04-30 | 2021-05-25 | 17 |  |  |  |  | 2021-06-21 | 2021-06-29 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-21 | 2021-06-22 | 1 | 2021-06-29 |  | 2021-07-07 | 5
869 | PGE | 95912 | NEM | EXPNEM | Implementation | Solar PV | 156 |  | 2021-04-30 | 2021-05-04 | 2 | 2021-05-05 | 3 | 2021-05-19 | 10 | 2021-05-19 | 2021-06-23 | 24 | 2021-06-23 | 2021-07-16 | 16 | 2021-07-16 | 2021-07-16 |  | 2021-07-16 | 2021-09-23 | 50 | 2021-07-16 |  |  | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | 2021-11-19 | 40 |  |  |  |  | 2021-04-30 | 2021-05-25 | 17 | [16 empty] | 1//19 | 1//19
870 | PGE | 95688 | NEM | EXPNEM | IA in Progress | Solar PV | 540 |  | 2021-04-30 | 2021-05-03 | 1 | 2021-08-02 | 64 | 2021-08-18 | 12 | 2021-08-18 | 2021-09-28 | 28 | 2021-09-28 | 2021-10-20 | 16 | 2021-10-20 | 2021-10-20 |  | 2021-10-20 | 2022-01-04 | 55 | 2021-10-20 |  |  | 2022-01-04 | 2022-01-04 | 0 | 2022-01-04 | [6 empty] | 2021-04-30 | 0 | [17 empty] | 1//19 | 1//19
871 | PGE | 94110 | Non-NEM | Non-Export | Commercial | Solar PV | 65.7 |  | 2021-05-02 | 2021-05-04 | 1 | 2021-05-12 | 7 | 2021-05-13 | 1 | [15 empty] | 2021-05-13 | 2021-05-24 | 7 | 2021-05-24 | 2021-06-29 | 25 | [5 empty] | 0 | [5 empty] | 2021-07-20 | 2021-07-22 | 2 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-20 | 2021-07-20 | 0 | 2021-07-22 |  | 2021-07-22 | 0
872 | PGE | 94028 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 40 |  | 2021-05-03 | 2021-05-11 | 6 | 2021-06-17 | 32 | 2021-06-18 | 1 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24 | [7 empty] | 0 |  | 2021-07-08 | [15 empty] | 1//19 | 1//19
873 | PGE | 93206 | NEM | EXPNEM | Commercial | Solar PV | 132 |  | 2021-05-03 | 2021-05-06 | 3 | 2021-07-08 | 46 | 2021-07-28 | 14 | [15 empty] | 2021-10-11 | 2021-10-29 | 14 | 2021-10-29 | 2021-10-29 | 0 | [5 empty] | 0 | [5 empty] | 2021-12-09 | 2021-12-21 | 8 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-09 | 2021-12-10 | 1 | 2021-12-21 |  | 2021-12-21 | 0
874 | PGE | 95937 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-05-03 | 2021-05-04 | 1 | 2021-05-04 | 1 | 2021-05-20 | 12 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2021-05-24 | 2 |  |  |  |  | 2021-05-03 | 2021-05-28 | 19 |  |  |  |  | 2021-09-29 | 2021-10-06 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-29 | 2021-09-29 | 0 | 2021-10-06 |  | 2021-10-13 | 5
875 | PGE | 96035 | NEM | EXPNEM | IA in Progress | Solar PV | 95.8 |  | 2021-05-04 | 2021-05-13 | 7 | 2021-05-21 | 13 | 2021-06-07 | 10 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [6 empty] | 2021-05-04 | 2021-06-03 | 21 | [16 empty] | 1//19 | 1//19
876 | PGE | 95236 | NEM | EXPNEM | Commercial | Solar PV | 140.742 |  | 2021-05-04 | 2021-05-14 | 8 | 2021-05-14 | 8 | 2021-06-02 | 12 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-06-24 | 16 |  |  |  |  | 2021-05-04 | 2021-05-28 | 18 |  |  |  |  | 2021-07-12 | 2021-07-19 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-12 | 2021-07-12 | 0 | 2021-07-19 |  | 2021-07-19 | 0
877 | PGE | 95519 | Non-NEM | Non-Export | Withdrawn | Storage | 140 |  | 2021-05-04 | 2021-05-04 | 0 | 2021-05-26 | 16 | 2021-06-21 | 17 | 2021-07-16 | 2021-08-19 | 24 | [12 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | [6 empty] | 2021-05-04 | 2021-06-15 | 29 | [16 empty] | 1//19 | 1//19 |  | 2021-08-25
878 | PGE | 95677 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-05-04 | 2021-05-12 | 6 | 2021-05-12 | 6 | 2021-05-13 | 1 | [18 empty] | 2021-05-04 | [7 empty] | 0 | [5 empty] | 2021-06-08 | 2021-08-02 | 38 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-08 | 2021-07-23 | 32 | 2021-08-02 |  | 2021-08-03 | 1
879 | PGE | 93612 | NEM | EXPNEM | Commercial | Solar PV | 118.695 |  | 2021-05-04 | 2021-05-05 | 1 | 2021-05-12 | 6 | 2021-05-19 | 5 | [15 empty] | 2021-05-19 | 2021-05-19 | 0 | 2021-05-19 | 2021-06-23 | 24 | [5 empty] | 0 | [5 empty] | 2021-07-30 | 2021-09-16 | 33 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-30 | 2021-09-14 | 31 | 2021-09-16 |  | 2021-09-23 | 5
880 | PGE | 95667 | Non-NEM | Non-Export | IA in Progress | Storage | 420 |  | 2021-05-04 | 2021-05-04 | 0 | 2021-05-26 | 16 | 2021-07-20 | 37 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
881 | PGE | 93609 | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-05-04 | 2021-05-10 | 4 | 2021-05-10 | 4 | 2021-06-09 | 21 | [15 empty] | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | [6 empty] | 2021-05-04 | 0 |  | 2021-05-17 | [6 empty] | 2021-05-13 | 2021-06-16 | 23 |  |  |  | 2021-10-19 | 2021-11-18 | 21 | 1//19 | 1//19
882 | PGE | 95035 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 247.184 |  | 2021-05-04 | 2021-05-18 | 10 | 2021-07-19 | 52 | 2021-08-09 | 15 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-10-19 | 50 | [5 empty] | 0 |  | 2021-08-02 | 2021-08-09 | 2021-08-09 | 5 |  |  |  | 2021-12-17 | 2021-12-20 | 1 | [6 empty] | 1//19 | 1//19
883 | PGE | 95035 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 185 |  | 2021-05-04 | 2021-05-18 | 10 | 2021-07-19 | 52 | 2021-08-16 | 20 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | 2021-10-19 | 45 | [5 empty] | 0 |  | 2021-07-19 | 2021-08-16 | 2021-08-16 | 20 |  |  |  | 2021-12-17 | 2021-12-20 | 1 | [6 empty] | 1//19 | 1//19
884 | PGE | 94545 | NEM | EXPNEM | Commercial | Solar PV | 440 |  | 2021-05-04 | 2021-05-05 | 1 | 2021-05-07 | 3 | 2021-07-12 | 44 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-09-10 | 43 | [5 empty] | 0 | [5 empty] | 2021-09-27 | 2021-10-05 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-27 | 2021-09-27 | 0 | 2021-10-05 |  | 2021-10-11 | 4
885 | PGE | 94404 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 49.179 |  | 2021-05-04 | 2021-05-12 | 6 | 2021-05-20 | 12 | 2021-05-20 | 0 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2021-05-21 | 1 | [5 empty] | 0 | [5 empty] | 2021-12-16 | 2021-12-16 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16 |  | 2021-12-16 | 0
886 | PGE | 93901 | NEM | NEMMT | IA in Progress | FUCE, Solar PV | 600 |  | 2021-05-05 | 2021-05-19 | 10 | 2021-09-13 | 90 | 2021-11-04 | 38 | 2021-11-04 | 2021-12-27 | 34 | [12 empty] | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27 | [6 empty] | 2021-05-05 | 2021-09-20 | 95 | 2021-11-01 | 2021-12-27 | 2021-12-27 | 37 | [12 empty] | 1//19 | 1//19
887 | PGE | 93638 | NEM | EXPNEM | Implementation | Solar PV | 300 |  | 2021-05-05 | 2021-05-14 | 7 | 2021-05-14 | 7 | 2021-06-09 | 17 | [15 empty] | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | 2021-07-01 | 16 |  |  |  |  | 2021-05-05 | 0 |  | 2021-05-17 | [15 empty] | 1//19 | 1//19
888 | PGE | 93609 | NEM | EXPNEM | Implementation | Solar PV | 45.45 |  | 2021-05-05 | 2021-05-14 | 7 | 2021-10-06 | 107 | 2021-10-11 | 3 | [15 empty] | 2021-10-11 | 2021-10-11 | 0 | 2021-10-11 | 2021-10-20 | 7 |  |  |  |  | 2021-07-07 | 0 | [8 empty] | 2022-03-17 | 2022-03-22 | 3 | [6 empty] | 1//19 | 1//19
889 | PGE | 95215 | NEM | EXPNEM | Study in Progress | Solar PV | 954.853 |  | 2021-05-06 | 2021-05-11 | 3 | 2021-11-03 | 126 | 2021-11-24 | 14 | 2021-11-24 | 2021-12-22 | 18 | 2021-12-23 | 2022-01-18 | 17 | 2022-01-18 | [18 empty] | 2021-05-06 | 0 |  | 2021-12-09 |  |  |  | 2022-02-04 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 2022-02-04 | 2022-02-04 | 0
890 | PGE | 93249 | NEM | EXPNEM | IA in Progress | Solar PV | 86.4 |  | 2021-05-06 | 2021-05-10 | 2 | 2021-06-15 | 27 | 2021-06-29 | 10 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | [6 empty] | 2021-05-06 | 2021-06-24 | 34 | [16 empty] | 1//19 | 1//19
891 | PGE | 93710 | Non-NEM | Non-Export | IA in Progress | Storage | 210 |  | 2021-05-06 | 2021-05-07 | 1 | 2021-05-26 | 14 | 2021-07-27 | 42 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-08-25 | 21 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
892 | PGE | 94544 | Non-NEM | NEMFC | Commercial | FUCE | 1050 |  | 2021-05-07 | 2021-05-14 | 5 | 2021-05-14 | 5 | 2021-08-13 | 63 | 2021-08-13 | 2021-09-02 | 14 | [12 empty] | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02 | 2021-12-08 | 65 |  |  |  |  | 2021-05-07 | 0 | [5 empty] | 2021-12-31 | 2022-03-29 | 60 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-31 | 2022-03-18 | 53 | 2022-03-29
893 | PGE | 95954 | Non-NEM | Non-Export | Withdrawn | Storage | 490 |  | 2021-05-07 | 2021-05-07 | 0 | 2021-05-26 | 13 | 2021-06-25 | 21 | [15 empty] | 2021-06-25 | 2021-06-28 | 1 | 2021-06-28 | [6 empty] | 2021-05-07 | 2021-05-27 | 14 | [16 empty] | 1//19 | 1//19
894 | PGE | 95476 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.23 |  | 2021-05-07 | 2021-05-12 | 3 | 2021-05-12 | 3 | 2021-05-13 | 1 | [15 empty] | 2021-08-13 | 2021-08-13 |  | 2021-08-13 | 2021-09-15 | 24 | [5 empty] | 0 | [5 empty] | 2021-09-16 | 2021-09-16 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 |  | 2021-09-16 | 0
895 | PGE | 93280 | NEM | VNEMMASH | Withdrawn | Solar PV | 114.8 |  | 2021-05-07 | 2021-05-14 | 5 | [29 empty] | 2021-05-07 | 0 | [17 empty] | 1//19 | 1//19
896 | PGE | 95928 | NEM | SNEM | Commercial | ENGN, Solar PV | 39.477 |  | 2021-05-07 | 2021-05-21 | 10 | 2021-06-16 | 27 | 2021-06-29 | 9 | [25 empty] | 2021-05-07 | 2021-06-28 | 35 |  |  |  |  | 2021-10-14 | 2021-10-18 | 2 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-14 | 2021-10-14 | 0 | 2021-10-18 |  | 2021-10-20 | 2
897 | PGE | 93243 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1187.5 |  | 2021-05-07 | 2021-05-10 | 1 | 2021-05-19 | 8 | 2021-06-30 | 29 | 2021-07-20 | 2021-08-27 | 28 | [12 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-11-29 | 62 |  |  |  |  | 2021-05-07 | 2021-06-15 | 26 | [7 empty] | 2022-01-27 |  | 54 | [6 empty] | 1//19 | 1//19
898 | PGE | 95206 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 61.126 |  | 2021-05-07 | 2021-05-14 | 5 | 2021-06-23 | 32 | 2021-07-15 | 15 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | [6 empty] | 2021-05-07 | 2021-09-20 | 93 |  | 2021-09-25 | [14 empty] | 1//19 | 1//19
899 | PGE | 94563 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-05-07 | 2021-05-12 | 3 | 2021-05-26 | 13 | 2021-06-09 | 9 | [18 empty] | 2021-05-07 | [6 empty] | 2021-05-07 | 2021-05-28 | 15 | [16 empty] | 1//19 | 1//19 | [7 empty] | 2021-05-26 |  | 2021-06-09 | 11
900 | PGE | 95227 | NEM | EXPNEM | Withdrawn | Solar PV | 31.078 |  | 2021-05-10 | 2021-05-13 | 3 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
901 | PGE | 95215 | NEM | EXPNEM | Commercial | Solar PV | 75.105 |  | 2021-05-10 | 2021-05-10 | 0 | 2021-10-27 | 119 | 2021-10-27 | 0 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-09-02 | 62 |  |  |  |  | 2021-05-10 | 2021-09-09 | 85 |  |  |  |  | 2021-10-27 | 2021-11-04 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-27 | 2021-10-28 | 1 | 2021-11-04 |  | 2021-11-09 | 3
902 | PGE | 95912 | NEM | EXPNEM | Implementation | Solar PV | 120 |  | 2021-05-10 | 2021-05-10 | 0 | 2021-06-04 | 18 | 2021-06-17 | 9 | 2021-06-17 | 2021-07-22 | 24 | 2021-06-04 | 2021-09-01 | 62 | 2021-09-01 | [8 empty] | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | 2022-03-29 | 20 |  |  |  |  | 2021-05-10 | 2021-06-15 | 25 | [16 empty] | 1//19 | 1//19
903 | PGE | 95949 | NEM | SNEM | Application Review in Progress | Solar PV | 1603.8 |  | 2021-05-10 | 2021-05-18 | 6 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
904 | PGE | 95682 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-05-10 | 2021-05-13 | 3 | 2021-05-20 | 8 | 2021-07-12 | 35 | [15 empty] | 2021-07-12 | 2021-07-15 | 3 | 2021-07-15 | 2021-07-16 | 1 |  |  |  |  | 2021-05-10 | 2021-06-17 | 27 |  |  |  |  | 2021-12-06 | 2021-12-17 | 9 | 2021-08-19 | 2021-10-11 | 36 |  |  |  | 2022-01-18 | 2022-03-04 | 33 | 1//19 | 1//19 |  |  |  |  | 2021-12-06 | 2021-12-07 | 1 | 2021-12-17 | 2021-12-21 | 2022-03-08 | 2 |  |  | 155
905 | PGE | 95682 | NEM | EXPNEM | Commercial | Solar PV | 171.802 |  | 2021-05-10 | 2021-05-12 | 2 | 2021-05-17 | 5 | 2021-06-09 | 16 | 2021-06-09 | 2021-07-08 | 20 | 2021-05-17 | 2021-08-17 | 64 | 2021-08-17 | 2021-08-17 |  | 2021-08-17 | 2021-11-10 | 62 | 2021-08-17 |  |  | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | 2021-11-12 | 1 |  |  |  |  | 2021-05-10 | 2021-05-26 | 12 |  |  |  |  | 2022-01-11 | 2022-01-24 | 8 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-01-11 | 2022-01-11 | 0 | 2022-01-24 | 2022-01-28 | 2022-03-29 | 4 |  |  | 182
907 | PGE | 94582 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 224.234 |  | 2021-05-11 | 2021-05-14 | 3 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
908 | PGE | 95134 | NEM | NEMMT | Withdrawn | FUCE, Storage | 306.488 |  | 2021-05-11 | 2021-05-17 | 4 | 2021-06-15 | 24 | [28 empty] | 0 | [17 empty] | 1//19 | 1//19
909 | PGE | 95240 | NEM | EXPNEM | Implementation | Solar PV | 51.478 |  | 2021-05-11 | 2021-05-18 | 5 | 2021-06-28 | 33 | 2021-08-06 | 28 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | 2021-08-17 | 7 | [5 empty] | 0 | [5 empty] | 2021-08-20 | 2021-08-27 | 5 | 2021-10-12 | 2022-03-01 | 96 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-20 | 2021-08-20 | 0 | 2021-08-27 | 2021-08-30 |  | 1 |  |  | 77
910 | PGE | 93721 | NEM | EXPNEM | IA in Progress | Solar PV | 39.976 |  | 2021-05-11 | 2021-05-14 | 3 | 2021-05-14 | 3 | 2021-07-20 | 45 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2022-03-23 | 170 |  |  |  |  | 2021-05-11 | 2021-09-22 | 93 |  |  |  |  | 2022-03-24 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 2022-03-24 | 2022-03-25 | 1
911 | PGE | 93313 | NEM | NEM Paired Storage | IA in Progress | ENGN, Solar PV | 2600 |  | 2021-05-11 | 2021-05-13 | 2 | 2021-05-26 | 11 | [5 empty] | 2021-05-26 | 2021-06-25 | 21 | 2021-06-25 | 2021-07-12 | 10 | 2021-07-26 | 2022-03-22 | 165 | 2021-07-12 | 2021-07-12 | 0 | [10 empty] | 2021-05-11 | 0 | [17 empty] | 1//19 | 1//19
912 | PGE | 93306 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 2537 |  | 2021-05-11 | 2021-05-13 | 2 | 2021-05-26 | 11 | [5 empty] | 2021-05-26 | 2021-08-23 | 61 | 2021-08-23 | 2021-08-23 | 0 | 2021-09-02 |  |  | 2021-08-23 | 2021-08-23 | 0 | [10 empty] | 2021-05-11 | 0 | [17 empty] | 1//19 | 1//19
913 | PGE | 93612 | NEM | EXPNEM | Implementation | Solar PV | 99.9 |  | 2021-05-12 | 2021-05-19 | 5 | 2021-05-20 | 6 | 2021-05-25 | 3 | [15 empty] | 2021-06-04 | 2021-06-04 | 0 | 2021-06-04 | 2021-06-07 | 1 |  |  |  |  | 2021-05-12 | 2021-05-28 | 12 | [16 empty] | 1//19 | 1//19
914 | PGE | 94563 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 57.054 |  | 2021-05-12 | 2021-05-21 | 7 | 2021-06-17 | 25 | 2021-06-30 | 9 | [15 empty] | 2021-06-30 | 2021-07-21 | 14 | 2021-07-21 | 2021-10-19 | 63 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
915 | PGE | 95060 | NEM | VNEMSOMAH | Implementation | Solar PV | 30.159 |  | 2021-05-12 | 2021-05-26 | 10 | 2021-06-08 | 18 | 2021-06-24 | 12 | [15 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-24 | 2021-07-07 | 8 |  |  |  |  | 2021-05-12 | 2021-06-15 | 23 | [16 empty] | 1//19 | 1//19
916 | PGE | 95124 | NEM | EXPNEM | Commercial | Solar PV | 125 |  | 2021-05-12 | 2021-05-14 | 2 | 2021-05-25 | 9 | 2021-06-10 | 11 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-06-14 | 2 | [5 empty] | 0 | [5 empty] | 2021-09-02 | 2021-09-14 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-02 | 2021-09-03 | 1 | 2021-09-14 |  | 2021-09-21 | 5
917 | PGE | 94010 | NEM | EXPNEM | Implementation | Solar PV | 199.172 |  | 2021-05-12 | 2021-05-24 | 8 | 2021-06-07 | 17 | 2021-06-16 | 7 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | 2021-07-06 | 13 |  |  |  |  | 2021-05-12 | 2021-06-16 | 24 | [16 empty] | 1//19 | 1//19
918 | PGE | 94574 | NEM | EXPNEM | IA in Progress | Solar PV | 180 |  | 2021-05-12 | 2021-05-17 | 3 | 2021-05-17 | 3 | 2021-09-23 | 90 | [15 empty] | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | [6 empty] | 2021-05-12 | 0 | [17 empty] | 1//19 | 1//19
919 | PGE | 93311 | NEM | EXPNEM | IA in Progress | Solar PV | 900 |  | 2021-05-12 | 2021-05-17 | 3 | 2021-06-23 | 29 | [5 empty] | 2021-07-05 | 2021-08-10 | 25 | 2021-08-10 |  |  | 2021-09-30 | 2021-12-28 | 60 | 2021-08-10 | 2021-08-13 | 4 | 2022-01-19 | 2022-01-19 | 0 | 2022-01-19 | 2022-03-21 | 42 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
920 | PGE | 95453 | Non-NEM | Non-Export | Implementation | Storage | 420 |  | 2021-05-12 | 2021-05-13 | 1 | 2021-06-02 | 14 | 2021-09-09 | 69 | [15 empty] | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 | 2022-01-06 | 82 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
921 | PGE | 93434 | NEM | VNEM | Commercial | Solar PV, Storage | 54.717 |  | 2021-05-12 | 2021-05-27 | 11 | 2021-07-01 | 35 | 2021-08-06 | 25 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | 2021-08-09 | 1 |  |  |  |  | 2021-08-04 | 2021-08-06 | 2 |  | 2021-08-06 | 2021-08-06 | 0 | 2021-09-25 | 2021-10-06 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-25 | 2021-09-27 | 0 | 2021-10-06 |  | 2021-10-12 | 4
922 | PGE | 94063 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 425 |  | 2021-05-13 | 2021-05-27 | 10 | 2021-11-29 | 136 | [28 empty] | 0 | [17 empty] | 1//19 | 1//19
923 | PGE | 95037 | NEM | EXPNEM | Commercial | Solar PV | 247.518 |  | 2021-05-13 | 2021-05-17 | 2 | 2021-05-17 | 2 | 2021-08-21 | 67 | [15 empty] | 2021-08-21 | 2021-08-21 | 0 | 2021-08-21 | 2021-08-24 | 1 |  |  |  |  | 2021-05-13 | 2021-05-28 | 11 |  |  |  |  | 2021-09-01 | 2021-09-09 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-01 | 2021-09-01 | 0 | 2021-09-09 |  | 2021-09-21 | 8
924 | PGE | 94063 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 516.6 |  | 2021-05-13 | 2021-05-27 | 10 | 2021-06-19 | 25 | 2021-07-12 | 14 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [7 empty] | 0 |  | 2021-06-29 | 2021-07-12 | 2021-07-12 | 8 | [12 empty] | 1//19 | 1//19
925 | PGE | 94577 | NEM | EXPNEM | Withdrawn | Solar PV | 66.6 |  | 2021-05-13 | 2021-05-13 | 0 | 2021-10-28 | 117 | [28 empty] | 0 | [17 empty] | 1//19 | 1//19
926 | PGE | 93301 | NEM | EXPNEM | Implementation | Solar PV | 1212 |  | 2021-05-13 | 2021-05-26 | 9 | 2021-06-09 | 18 | [5 empty] | 2021-06-14 | 2021-07-12 | 19 | 2021-07-12 | 2021-07-12 | 0 | 2021-08-03 | 2021-10-28 | 61 | 2021-07-12 | 2021-07-12 | 0 | 2021-11-01 | 2021-11-02 | 1 | 2021-11-02 | 2022-01-28 | 59 |  |  |  |  | 2021-05-13 | 0 | [8 empty] | 2021-12-22 |  |  | 2021-12-22 | 2022-03-09 09:30 | 56 |  |  |  | 1//19 | 1//19
928 | PGE | 95521 | NEM | VNEM | Commercial | Solar PV | 98.938 |  | 2021-05-13 | 2021-05-27 | 10 | 2021-10-04 | 99 | 2021-10-25 | 15 | [15 empty] | 2021-10-25 | 2021-10-25 | 0 | 2021-10-25 | 2021-11-05 | 9 | [5 empty] | 0 |  | 2021-10-14 | 2021-10-25 | 2021-10-25 | 7 | 2022-02-09 | 2022-02-17 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-02-09 | 2022-02-09 | 0 | 2022-02-17 |  | 2022-02-18 | 1
929 | PGE | 93725 | NEM | EXPNEM | Commercial | Solar PV | 644.705 |  | 2021-05-13 | 2021-05-18 | 3 | 2021-05-21 | 6 | 2021-06-04 | 9 | 2021-06-04 | 2021-07-02 | 20 | [12 empty] | 2021-07-02 | 2021-07-06 | 1 | 2021-07-06 | 2021-07-13 | 5 |  |  |  |  | 2021-05-13 | 0 | [5 empty] | 2021-12-10 | 2021-12-20 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-10 | 2021-12-10 | 0 | 2021-12-20 |  | 2021-12-23 | 3
930 | PGE | 95977 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 50.23 |  | 2021-05-13 | 2021-05-18 | 3 | 2021-05-27 | 10 | 2021-06-01 | 2 | [18 empty] | 2021-05-13 | [7 empty] | 0 | [5 empty] | 2021-06-01 | 2021-06-01 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-01 |  |  | 2021-06-01 |  | 2021-06-01 | 0
931 | PGE | 95361 | NEM | EXPNEM | Commercial | Solar PV | 72 |  | 2021-05-13 | 2021-05-27 | 10 | 2021-09-01 | 77 | 2021-09-15 | 9 | [15 empty] | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | 2021-09-16 | 1 | [5 empty] | 0 | [5 empty] | 2021-09-20 | 2021-09-28 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-20 | 2021-09-21 | 1 | 2021-09-28 |  | 2021-09-28 | 0
932 | PGE | 95422 | NEM | EXPNEM | IA in Progress | Solar PV | 641.076 |  | 2021-05-14 | 2021-05-18 | 2 | 2021-05-18 | 2 | 2021-08-19 | 65 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-09-14 | 17 |  |  |  |  | 2021-05-14 | 0 | [17 empty] | 1//19 | 1//19
933 | PGE | 95228 | Non-NEM | Non-Export | Withdrawn | Solar PV | 44.66 |  | 2021-05-14 | 2021-05-17 | 1 | 2021-06-02 | 12 | [28 empty] | 0 | [17 empty] | 1//19 | 1//19
934 | PGE | 93301 | Non-NEM | Non-Export | Implementation | Storage | 985 |  | 2021-05-14 | 2021-05-17 | 1 | 2021-05-26 | 8 | 2021-08-02 | 46 | 2021-08-18 | 2021-09-17 | 21 | [12 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | 2021-12-17 | 62 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
935 | PGE | 93703 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 4411.742 |  | 2021-05-14 | 2021-05-17 | 1 | 2021-05-26 | 8 | [5 empty] | 2021-06-14 | 2021-07-27 | 30 | 2021-07-27 | 2021-08-02 | 4 | 2021-08-17 | 2021-11-02 | 54 | 2021-08-02 | 2021-08-16 | 10 | 2021-12-29 | 2022-01-27 | 20 | 2022-01-27 | [7 empty] | 0 | [8 empty] | 2022-02-17 |  |  | 2022-02-17 | [5 empty] | 1//19 | 1//19
936 | PGE | 93673 | NEM | EXPNEM | Implementation | Solar PV | 865.259 |  | 2021-05-14 | 2021-05-28 | 10 | 2021-06-14 | 20 | 2021-07-01 | 13 | 2021-07-01 | 2021-07-30 | 20 | [12 empty] | 2021-07-30 | 2021-07-30 | 0 | 2021-07-30 | 2021-08-27 | 20 |  |  |  |  | 2021-07-23 | 2021-08-05 | 9 | 2021-07-09 | [6 empty] | 2021-11-17 |  | 102 | [6 empty] | 1//19 | 1//19
937 | PGE | 93314 | NEM | EXPNEM | Commercial | Solar PV | 250 |  | 2021-05-14 | 2021-05-24 | 6 | 2021-05-28 | 10 | 2021-06-07 | 5 | [15 empty] | 2021-06-07 | 2021-06-16 | 7 | 2021-06-16 | 2021-10-08 | 80 |  |  |  |  | 2021-05-14 | 2021-06-15 | 21 |  |  |  |  | 2021-11-02 | 2021-11-10 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-02 | 2021-11-03 | 1 | 2021-11-10 |  | 2021-11-10 | 0
938 | PGE | 95692 | NEM | EXPNEM | Implementation | Solar PV | 480 |  | 2021-05-14 | 2021-06-14 | 20 | 2021-07-09 | 38 | 2021-07-26 | 11 | 2021-07-26 | 2021-08-30 | 25 | 2021-08-31 | 2021-09-21 | 14 | 2021-09-21 | 2021-09-21 |  | 2021-09-21 | 2021-12-20 | 65 | 2021-09-21 |  |  | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | 2021-12-23 | 3 |  |  |  |  | 2021-07-09 | 2021-07-19 | 6 | [7 empty] | 2022-01-14 | 2022-02-15 | 22 | [6 empty] | 1//19 | 1//19
939 | PGE | 94027 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 40.75 |  | 2021-05-17 | 2021-05-19 | 2 | 2021-09-27 | 92 | 2021-09-28 | 1 | [18 empty] | 2021-05-19 | [7 empty] | 0 | [5 empty] | 2021-11-23 | 2021-11-23 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-23 |  |  | 2021-11-23 |  | 2021-11-23 | 0
940 | PGE | 95060 | NEM | NEMMT | IA in Progress | ENGN, Solar PV, Storage | 985 |  | 2021-05-17 | 2021-05-24 | 5 | 2021-05-24 | 5 | [5 empty] | 2021-05-24 | 2021-06-15 | 15 | 2021-06-15 | 2021-07-01 | 12 | 2021-08-04 | 2021-12-16 | 92 | 2021-07-01 | 2021-07-01 | 0 | 2021-12-17 | 2021-12-17 | 0 | 2021-12-17 | 2022-03-22 | 65 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
941 | PGE | 94515 | NEM | EXPNEM | IA in Progress | Solar PV | 151.403 |  | 2021-05-17 | 2021-05-20 | 3 | 2021-06-22 | 25 | 2021-07-12 | 13 | 2021-07-12 | 2021-08-11 | 22 | [12 empty] | 2021-08-11 | 2021-08-11 | 0 | 2021-08-11 | 2021-09-16 | 25 |  |  |  |  | 2021-05-17 | 2021-06-16 | 21 |  |  |  |  | 2021-12-14 | 2021-12-22 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-14 | 2021-12-14 | 0 | 2021-12-22 | 2022-03-03 |  | 49 |  |  | 200
942 | PGE | 93648 | NEM | EXPNEM | Commercial | Solar PV | 75 |  | 2021-05-17 | 2021-05-18 | 1 | 2021-05-18 | 1 | 2021-06-15 | 19 | [15 empty] | 2021-06-15 | 2021-06-17 | 2 | 2021-06-17 | 2021-06-17 | 0 |  |  |  |  | 2021-05-17 | 2021-05-28 | 9 |  |  |  |  | 2022-01-10 | 2022-01-19 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-01-10 | 2022-01-11 | 1 | 2022-01-19 |  | 2022-01-21 | 2
943 | PGE | 95691 | NEM | EXPNEM | Withdrawn | Solar PV | 50 |  | 2021-05-18 | 2021-05-20 | 2 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
944 | PGE | 95348 | NEM | EXPNEM | Commercial | Solar PV | 47.351 |  | 2021-05-18 | 2021-05-18 | 0 | 2021-06-05 | 12 | 2021-06-21 | 10 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-25 | 4 | [5 empty] | 0 | [5 empty] | 2021-09-10 | 2021-09-20 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-10 | 2021-09-12 | 0 | 2021-09-20 |  | 2021-09-27 | 5
945 | PGE | 95019 | NEM | VNEMSOMAH | Implementation | Solar PV | 64.643 |  | 2021-05-18 | 2021-05-25 | 5 | 2021-06-29 | 29 | 2021-08-05 | 26 | [15 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | 2021-09-30 | 39 |  |  |  |  | 2021-05-18 | 2021-06-16 | 20 |  | 2021-06-29 | 2021-06-29 | 0 | [12 empty] | 1//19 | 1//19
946 | PGE | 95019 | NEM | VNEMSOMAH | Implementation | Solar PV | 53.25 |  | 2021-05-18 | 2021-05-25 | 5 | 2021-06-30 | 30 | 2021-07-22 | 15 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | 2021-09-30 | 49 |  |  |  |  | 2021-05-18 | 2021-06-16 | 20 |  | 2021-06-30 | 2021-06-30 | 0 | [12 empty] | 1//19 | 1//19
947 | PGE | 95019 | NEM | VNEMSOMAH | Implementation | Solar PV | 41.375 |  | 2021-05-18 | 2021-06-02 | 10 | 2021-06-30 | 30 | 2021-08-05 | 25 | [15 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | 2021-09-30 | 39 |  |  |  |  | 2021-05-18 | 0 |  | 2021-07-23 | [15 empty] | 1//19 | 1//19
948 | PGE | 95019 | NEM | VNEMSOMAH | Implementation | Solar PV | 55.628 |  | 2021-05-18 | 2021-06-02 | 10 | 2021-06-30 | 30 | 2021-08-12 | 30 | [15 empty] | 2021-08-12 | 2021-08-12 | 0 | 2021-08-12 | 2021-09-30 | 34 |  |  |  |  | 2021-05-18 | 0 |  | 2021-07-23 | 2021-08-12 | 2021-08-12 | 14 | [12 empty] | 1//19 | 1//19
949 | PGE | 95019 | NEM | VNEMSOMAH | Implementation | Solar PV | 70.798 |  | 2021-05-18 | 2021-06-01 | 9 | 2021-06-29 | 29 | 2021-07-21 | 15 | [15 empty] | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | 2021-09-30 | 50 |  |  |  |  | 2021-05-18 | 0 |  | 2022-01-05 | [15 empty] | 1//19 | 1//19
950 | PGE | 95019 | NEM | VNEMSOMAH | Implementation | Solar PV | 54.229 |  | 2021-05-18 | 2021-06-02 | 10 | 2021-06-29 | 29 | 2021-08-05 | 26 | [15 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | 2021-09-30 | 39 |  |  |  |  | 2021-05-18 | 0 |  | 2021-07-19 | [15 empty] | 1//19 | 1//19
951 | PGE | 93637 | NEM | EXPNEM | Commercial | Solar PV | 74.573 |  | 2021-05-18 | 2021-06-02 | 10 | 2021-06-28 | 28 | [17 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-08-09 | 10 |  |  |  |  | 2021-05-18 | 0 |  | 2021-06-16 |  |  |  | 2021-07-19 | 2021-07-26 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-19 | 2021-07-19 | 0 | 2021-07-26 |  | 2021-08-09 | 10
952 | PGE | 95205 | NEM | EXPNEM | IA in Progress | Solar PV | 260.549 |  | 2021-05-18 | 2021-05-20 | 2 | 2021-05-26 | 6 | 2021-06-07 | 7 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [6 empty] | 2021-11-04 | 0 | [17 empty] | 1//19 | 1//19
953 | PGE | 94611 | NEM | EXPNEM | Withdrawn | Solar PV | 99.9 |  | 2021-05-18 | 2021-05-20 | 2 | 2021-08-04 | 54 | [28 empty] | 0 | [17 empty] | 1//19 | 1//19
954 | PGE | 95453 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 630 |  | 2021-05-18 | 2021-06-02 | 10 | 2021-06-02 | 10 | 2021-07-13 | 28 | 2021-07-30 | 2021-09-07 | 26 | [12 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | 2021-06-30 | 1 |  |  |  |  | 2021-05-18 | 2021-06-09 | 15 | [16 empty] | 1//19 | 1//19
955 | PGE | 93242 | NEM | EXPNEM | Commercial | Solar PV | 53.289 |  | 2021-05-19 | 2021-06-17 | 20 | 2021-06-18 | 21 | 2021-07-01 | 9 | [15 empty] | 2021-07-01 | 2021-07-07 | 3 | 2021-07-07 | 2021-07-07 | 0 |  |  |  |  | 2021-05-19 | 2021-06-07 | 12 |  |  |  |  | 2021-11-12 | 2021-11-23 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-12 | 2021-11-15 | 1 | 2021-11-23 |  | 2021-11-29 | 2
956 | PGE | 94901 | NEM | EXPNEM | Commercial | Solar PV | 37.306 |  | 2021-05-19 | 2021-05-20 | 1 | 2021-06-03 | 10 | 2021-06-21 | 12 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-09-16 | 61 | [5 empty] | 0 | [5 empty] | 2021-10-25 | 2021-11-05 | 9 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-25 | 2021-10-25 | 0 | 2021-11-05 |  | 2021-11-15 | 5
957 | PGE | 95236 | NEM | EXPNEM | Commercial | Solar PV | 31.024 |  | 2021-05-19 | 2021-05-27 | 6 | 2021-06-25 | 26 | 2021-07-12 | 10 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-07-12 | 0 | [5 empty] | 0 | [5 empty] | 2021-10-29 | 2021-11-08 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-29 | 2021-11-01 | 1 | 2021-11-08 |  | 2021-11-09 | 1
958 | PGE | 93249 | NEM | EXPNEM | Commercial | Solar PV | 80.637 |  | 2021-05-19 | 2021-05-21 | 2 | 2021-06-05 | 11 | 2021-06-23 | 12 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-07-08 | 10 |  |  |  |  | 2021-07-30 | 2021-08-13 | 10 |  |  |  |  | 2021-07-13 | 2021-08-13 | 23 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-13 | 2021-08-10 | 20 | 2021-08-13 |  | 2021-08-23 | 6
959 | PGE | 95691 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-05-19 | 2021-06-04 | 11 | 2021-06-21 | 22 | 2021-07-12 | 14 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-07-15 | 3 |  |  |  |  | 2021-05-19 | 2021-07-19 | 41 |  |  |  |  | 2021-10-13 | 2021-10-19 | 4 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-13 | 2021-10-13 | 0 | 2021-10-19 |  | 2021-11-08 | 14
960 | PGE | 94513 | Non-NEM | Non-Export | Implementation | Storage | 929.5 |  | 2021-05-19 | 2021-05-20 | 1 | 2021-06-23 | 24 | 2021-07-26 | 22 | 2021-08-02 | 2021-08-27 | 19 | [12 empty] | 2021-08-27 | 2021-09-01 | 3 | 2021-09-01 | 2021-11-24 | 58 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
961 | PGE | 95973 | NEM | EXPNEM | IA in Progress | Solar PV | 74.731 |  | 2021-05-20 | 2021-05-24 | 2 | 2021-06-01 | 7 | 2021-06-15 | 10 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-15 | 2021-06-16 | 1 |  |  |  |  | 2021-05-20 | 2021-06-15 | 17 | [16 empty] | 1//19 | 1//19
962 | PGE | 94954 | NEM | EXPNEM | IA in Progress | Solar PV | 248.292 |  | 2021-05-20 | 2021-06-03 | 9 | 2021-07-21 | 42 | 2021-08-04 | 10 | [15 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | [6 empty] | 2021-05-20 | 0 | [17 empty] | 1//19 | 1//19
963 | PGE | 95060 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-05-20 | 2021-05-24 | 2 | 2021-06-15 | 17 | 2021-07-01 | 12 | [15 empty] | 2021-07-01 | 2021-07-02 | 1 | 2021-07-02 | 2021-12-30 | 124 |  |  |  |  | 2021-05-20 | 2021-06-24 | 24 |  |  |  |  | 2021-11-18 | 2022-01-03 | 30 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-18 | 2022-01-03 | 30 | 2022-01-03 |  | 2022-01-05 | 2
964 | PGE | 94576 | NEM | EXPNEM | Commercial | Solar PV | 54.72 |  | 2021-05-20 | 2021-05-24 | 2 | 2021-06-17 | 19 | 2021-07-22 | 24 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | 2021-10-15 | 60 |  |  |  |  | 2021-05-20 | 2021-06-07 | 11 |  |  |  |  | 2021-10-20 | 2021-10-27 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-20 | 2021-10-20 | 0 | 2021-10-27 |  | 2021-11-01 | 3
965 | PGE | 94621 | Non-NEM | Non-Export | IA in Progress | Storage | 630 |  | 2021-05-20 | 2021-05-20 | 0 | 2021-06-16 | 18 | 2021-10-26 | 92 | [15 empty] | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
966 | PGE | 95126 | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2021-05-20 | 2021-05-20 | 0 | 2021-10-07 | 97 | 2021-10-19 | 8 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-10-29 | 8 |  | 2021-11-10 | 2021-11-29 | 14 |  | 0 | [17 empty] | 1//19 | 1//19
967 | PGE | 93619 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-05-20 | 2021-05-24 | 2 | 2021-06-03 | 9 | 2021-06-17 | 10 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-06-17 | 0 |  |  |  |  | 2021-05-20 | 2021-06-15 | 17 |  |  |  |  | 2021-09-07 | 2021-09-24 | 13 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-07 | 2021-09-16 | 7 | 2021-09-24 |  | 2021-10-01 | 5
968 | PGE | 95035 | NEM | EXPNEM | IA in Progress | Solar PV | 57.42 |  | 2021-05-20 | 2021-05-24 | 2 | 2021-06-05 | 10 | 2021-07-21 | 31 | [15 empty] | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
969 | PGE | 94022 | NEM | EXPNEM | Application Review in Progress | Solar PV | 73.552 |  | 2021-05-20 | 2021-05-27 | 5 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
970 | PGE | 93245 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-05-20 | 2021-05-24 | 2 | 2021-06-01 | 7 | 2021-06-17 | 12 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-12-14 | 123 |  |  |  |  | 2021-05-20 | 2021-06-16 | 18 |  |  |  |  | 2021-12-15 | 2022-02-08 | 38 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-15 | 2022-01-24 | 27 | 2022-02-08 |  | 2022-02-08 | 0
971 | PGE | 93618 | NEM | NEMMT | Application Accepted | Solar PV | 250 |  | 2021-05-20 | 2021-06-05 | 10 | 2021-07-06 | 31 | 2021-07-27 | 15 | 2021-07-27 | 2021-08-24 | 20 | [12 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | 2021-09-17 | 17 |  |  |  |  | 2021-05-20 | 0 |  | 2021-07-14 | 2021-07-27 | 2021-07-27 | 10 | 2021-09-17 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-17 | 2022-03-31 | 134
972 | PGE | 95126 | NEM | EXPNEM | Implementation | Solar PV | 162.5 |  | 2021-05-20 | 2021-06-01 | 7 | 2021-06-01 | 7 | 2021-07-12 | 28 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-10-29 | 78 |  |  |  |  | 2021-06-24 | 2021-07-13 | 12 | [16 empty] | 1//19 | 1//19
973 | PGE | 95126 | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2021-05-20 | 2021-06-01 | 7 | 2021-06-01 | 7 | 2021-08-09 | 48 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-10-29 | 58 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
974 | PGE | 94558 | NEM | EXPNEM | Commercial | Solar PV | 59.519 |  | 2021-05-21 | 2021-05-25 | 2 | 2021-06-22 | 21 | 2021-07-08 | 11 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-16 | 6 |  |  |  |  | 2021-05-21 | 2021-06-07 | 10 |  |  |  |  | 2021-11-01 | 2021-11-05 | 4 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-01 | 2021-11-01 | 0 | 2021-11-05 |  | 2021-11-12 | 4
975 | PGE | 94704 | NEM | EXPNEM | Withdrawn | Solar PV | 36.511 |  | 2021-05-21 | 2021-06-03 | 8 | 2021-07-09 | 33 |  |  | 2021-08-09 | 2021-09-01 | 17 | [12 empty] | 2021-09-01 | 2021-09-02 | 1 | 2021-09-02 | [7 empty] | 0 |  | 2021-07-23 | [15 empty] | 1//19 | 1//19
976 | PGE | 94558 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-05-21 | 2021-06-02 | 7 | 2021-06-29 | 26 | 2021-08-20 | 37 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-20 | 2021-08-30 | 6 |  |  |  |  | 2021-05-21 | 2021-08-13 | 58 |  |  |  |  | 2021-10-28 | 2021-11-04 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-28 | 2021-10-28 | 0 | 2021-11-04 |  | 2021-11-04 | 0
977 | PGE | 93654 | NEM | NEMMT | Implementation | Solar PV | 659.212 |  | 2021-05-21 | 2021-06-02 | 7 | 2021-08-20 | 63 | 2021-09-03 | 10 | 2021-09-03 | 2021-10-01 | 19 | [12 empty] | 2021-10-01 | 2021-10-13 | 8 | 2021-10-13 | 2022-01-19 | 66 |  |  |  |  | 2021-08-12 | 0 |  | 2021-08-24 | 2021-10-06 | 2021-10-13 | 30 | 2022-03-30 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 2022-03-30 | 2022-03-31 | 1
978 | PGE | 93307 | NEM | EXPNEM | Withdrawn | Solar PV | 150 |  | 2021-05-21 | 2021-06-03 | 8 | 2021-06-17 | 18 | 2021-07-02 | 11 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | [6 empty] | 2021-05-21 | 0 |  | 2021-07-01 | [15 empty] | 1//19 | 1//19
979 | PGE | 95127 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.408 |  | 2021-05-21 | 2021-05-24 | 1 | 2021-06-07 | 10 | 2021-06-09 | 2 | [18 empty] | 2021-05-21 | [7 empty] | 0 | [5 empty] | 2021-06-10 | 2021-06-10 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-10 |  |  | 2021-06-10 |  | 2021-06-10 | 0
980 | PGE | 93245 | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-05-21 | 2021-05-28 | 5 | 2021-05-28 | 5 | 2021-06-15 | 11 | 2021-06-15 | 2021-07-14 | 20 | [12 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-10-01 | 56 |  |  |  |  | 2021-05-21 | 2021-06-15 | 16 |  |  |  |  | 2021-10-01 | 2021-10-08 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-01 | 2021-10-01 | 0 | 2021-10-08 |  | 2021-10-15 | 5
981 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 90.925 |  | 2021-05-21 | 2021-06-01 | 6 | 2021-06-07 | 10 | 2021-06-21 | 10 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-30 | 7 |  |  |  |  | 2021-05-21 | 2021-06-15 | 16 |  |  |  |  | 2021-11-29 | 2021-12-09 | 8 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-29 | 2021-11-29 | 0 | 2021-12-09 |  | 2021-12-16 | 5
982 | PGE | 94558 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.305 |  | 2021-05-21 | 2021-05-25 | 2 | 2021-06-08 | 11 | 2021-06-08 | 0 | [18 empty] | 2021-05-21 | [6 empty] | 2021-05-21 | 0 | [5 empty] | 2021-06-17 | 2021-07-14 | 18 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-17 | 2021-07-01 | 10 | 2021-07-14 |  | 2021-07-14 | 0
983 | PGE | 94103 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-05-21 | 2021-06-04 | 9 | 2021-07-14 | 36 | 2021-07-14 | 0 | [15 empty] | 2021-07-14 | 2021-07-21 | 5 | 2021-07-21 | 2021-07-21 | 0 | [5 empty] | 0 | [5 empty] | 2021-07-29 | 2021-08-05 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-29 | 2021-07-29 | 0 | 2021-08-05 |  | 2021-08-13 | 6
984 | PGE | 93609 | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-05-21 | 2021-06-04 | 9 | 2021-06-15 | 16 | 2021-07-01 | 12 | 2021-07-01 | 2021-07-30 | 20 | [12 empty] | 2021-07-30 | 2021-07-30 | 0 | 2021-07-30 | [6 empty] | 2021-05-21 | 0 |  | 2021-07-09 | [15 empty] | 1//19 | 1//19
986 | PGE | 94923 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 |  | 2021-05-21 | 2021-05-25 | 2 | 2021-05-28 | 5 | 2021-06-02 | 2 | [18 empty] | 2021-05-21 | 2021-06-15 | 16 | [5 empty] | 0 | [5 empty] | 2021-06-15 | 2021-06-15 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-15 | 2021-06-15 | 0 | 2021-06-15 |  | 2021-06-15 | 0
987 | PGE | 95928 | NEM | EXPNEM | Withdrawn | Solar PV, WIND | 86.681 |  | 2021-05-21 | 2021-06-05 | 9 | 2021-07-09 | 33 | 2021-07-27 | 12 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
988 | PGE | 95928 | NEM | VNEMMASH | Application Review in Progress | Solar PV | 72.55 |  | 2021-05-21 | 2021-06-07 | 10 | [29 empty] | 2021-05-21 | 0 | [17 empty] | 1//19 | 1//19
989 | PGE | 93455 | NEM | EXPNEM | Commercial | Solar PV | 63.892 |  | 2021-05-21 | 2021-06-01 | 6 | 2021-06-15 | 16 | 2021-06-23 | 6 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2022-01-18 | 143 | [5 empty] | 0 | [5 empty] | 2022-01-18 | 2022-01-26 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-01-18 | 2022-01-19 | 1 | 2022-01-26 |  | 2022-01-27 | 1
990 | PGE | 93446 | NEM | EXPNEM | IA in Progress | Solar PV | 72.22 |  | 2021-05-21 | 2021-06-01 | 6 | 2021-06-16 | 17 | 2021-07-01 | 11 | [15 empty] | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
991 | PGE | 95928 | NEM | VNEMMASH | Application Review in Progress | Solar PV | 72.55 |  | 2021-05-21 | 2021-06-04 | 9 | [29 empty] | 2021-05-21 | 0 | [17 empty] | 1//19 | 1//19
992 | PGE | 94586 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.752 |  | 2021-05-21 | 2021-06-02 | 7 | 2021-06-02 | 7 | 2021-07-12 | 27 | [18 empty] | 2021-05-21 | 2021-05-21 | 0 | [5 empty] | 0 | [5 empty] | 2021-07-12 | 2021-10-29 | 78 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-12 | 2021-10-20 | 71 | 2021-10-29 |  | 2021-10-29 | 0
993 | PGE | 94112 | Non-NEM | Continuous Uncompensated Export | Withdrawn | Solar PV | 271.284 |  | 2021-05-21 | 2021-05-24 | 1 | 2021-06-02 | 7 | 2021-07-14 | 29 | [15 empty] | 2021-07-14 | 2021-07-28 | 10 | 2021-07-28 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
994 | PGE | 95928 | NEM | VNEMMASH | Application Review in Progress | Solar PV | 72.55 |  | 2021-05-21 | 2021-06-04 | 9 | [29 empty] | 2021-05-21 | 0 | [17 empty] | 1//19 | 1//19
995 | PGE | 94580 | NEM | NEMMT | Implementation | ENGN, Solar PV, Storage | 1792 |  | 2021-05-21 | 2021-05-28 | 5 | 2021-06-03 | 8 | 2021-07-23 | 35 | [15 empty] | 2021-07-29 | 2021-08-05 | 5 | 2021-08-05 | 2021-08-16 | 7 |  |  |  |  | 2021-05-21 | 0 | [8 empty] | 2021-12-29 |  | 75 | [6 empty] | 1//19 | 1//19
996 | PGE | 93314 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-05-24 | 2021-05-25 | 1 | 2021-06-09 | 11 | 2021-06-10 | 1 | [18 empty] | 2021-05-24 | [7 empty] | 0 | [5 empty] | 2021-06-10 | 2021-06-10 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-10 |  |  | 2021-06-10 |  | 2021-06-10 | 0
997 | PGE | 93280 | NEM | EXPNEM | Implementation | Solar PV | 470 |  | 2021-05-24 | 2021-06-07 | 9 | [7 empty] | 2021-06-08 | 2021-07-01 | 17 | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01 | 2021-09-27 | 60 | 2021-07-01 | 2021-07-01 | 0 | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-11-01 | 25 |  |  |  |  | 2021-05-24 | 0 |  | 2021-06-17 | [15 empty] | 1//19 | 1//19
998 | PGE | 93619 | NEM | EXPNEM | Implementation | Solar PV | 34.8 |  | 2021-05-24 | 2021-06-07 | 9 | 2021-08-04 | 50 | 2021-09-24 | 36 | [15 empty] | 2021-10-08 | 2021-10-08 | 0 | 2021-10-08 | 2021-10-12 | 2 | [5 empty] | 0 |  | 2021-10-01 | 2021-11-02 | 2021-11-02 | 22 | [12 empty] | 1//19 | 1//19
999 | PGE | 95605 | NEM | EXPNEM | Commercial | Solar PV | 249.258 |  | 2021-05-24 | 2021-06-03 | 7 | 2021-07-15 | 36 | 2021-08-10 | 18 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-10 | 2021-09-07 | 19 |  |  |  |  | 2021-05-24 | 2021-06-15 | 15 |  |  |  |  | 2021-10-14 | 2021-10-21 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-10-14 | 2021-10-14 | 0 | 2021-10-21 |  | 2021-10-28 | 5
1000 | PGE | 95973 | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2021-05-24 | 2021-06-04 | 8 | 2021-06-09 | 11 | 2021-06-15 | 4 | 2021-06-15 | 2021-07-14 | 20 | 2021-07-14 | 2021-08-09 | 18 | 2021-08-09 | 2021-08-09 |  | 2021-08-09 | 2021-11-24 | 78 | 2021-08-09 |  |  | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 2022-02-11 | 54 |  |  |  |  | 2021-05-24 | 2021-06-17 | 17 | [16 empty] | 1//19 | 1//19
1001 | PGE | 93313 | NEM | EXPNEM | Commercial | Solar PV | 90.477 |  | 2021-05-24 | 2021-06-02 | 6 | 2021-11-03 | 114 | 2021-11-19 | 11 | [15 empty] | 2021-11-19 | 2021-11-19 | 0 | 2021-11-19 | 2021-12-16 | 17 |  |  |  |  | 2021-05-24 | 2021-06-15 | 15 |  |  |  |  | 2022-03-01 | 2022-03-08 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-03-01 | 2022-03-01 | 0 | 2022-03-08 |  | 2022-03-10 | 2
1002 | PGE | 95946 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-05-24 | 2021-06-08 | 10 | 2021-06-18 | 18 | 2021-07-08 | 13 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-09-09 | 44 | [5 empty] | 0 | [5 empty] | 2021-09-17 | 2021-09-27 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-17 | 2021-09-20 | 1 | 2021-09-27 |  | 2021-10-01 | 4
1003 | PGE | 95046 | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-05-24 | 2021-06-04 | 8 | 2021-07-26 | 43 | 2021-08-19 | 18 | [15 empty] | 2021-08-19 | 2021-08-20 | 1 | 2021-08-20 | 2021-09-13 | 15 |  |  |  |  | 2021-05-24 | 2021-08-05 | 51 |  |  |  |  | 2021-11-19 | 2021-11-30 | 5 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-19 | 2021-11-21 | 0 | 2021-11-30 |  | 2021-11-30 | 0
1004 | PGE | 95928 | NEM | EXPNEM | Commercial | Solar PV | 40.269 |  | 2021-05-24 | 2021-06-02 | 6 | 2021-07-12 | 33 | 2021-07-26 | 10 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-08-04 | 7 | [5 empty] | 0 | [5 empty] | 2021-08-09 | 2021-08-13 | 4 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-09 | 2021-08-10 | 1 | 2021-08-13 |  | 2021-08-19 | 4
1005 | PGE | 93280 | NEM | EXPNEM | Study in Progress | Solar PV | 1560 |  | 2021-05-24 | 2021-05-25 | 1 | 2021-06-02 | 6 | 2021-07-26 | 37 | 2021-08-12 | 2021-09-10 | 20 | 2021-10-19 | 2021-11-12 | 17 | 2021-11-12 |  |  | 2021-11-23 | 2022-03-16 | 77 | 2021-11-12 | 2021-11-12 | 1 | [10 empty] | 2021-05-24 | 0 |  | 2021-08-06 | [15 empty] | 1//19 | 1//19
1006 | PGE | 93722 | NEM | EXPNEM | Implementation | Solar PV | 221.358 |  | 2021-05-25 | 2021-06-08 | 9 | 2021-06-15 | 14 | 2021-07-02 | 13 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-07-08 | 3 |  |  |  |  | 2021-05-25 | 2021-08-27 | 66 | 2021-08-06 |  |  |  | 2021-08-30 | 2021-09-16 | 12 | 2021-10-21 | 2022-02-28 | 88 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-30 | 2021-09-14 | 10 | 2021-09-16 | 2021-09-17 |  | 1 |  |  | 80
1007 | PGE | 95340 | NEM | EXPNEM | Commercial | Solar PV | 213.803 |  | 2021-05-25 | 2021-06-08 | 9 | 2021-06-15 | 14 | 2021-07-06 | 14 | [15 empty] | 2021-08-25 | 2021-08-30 | 3 | 2021-08-30 | 2021-08-31 | 1 |  |  |  |  | 2021-05-25 | 0 |  | 2021-07-09 |  |  |  | 2021-12-08 | 2021-12-20 | 8 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-08 | 2021-12-09 | 1 | 2021-12-20 |  | 2021-12-20 | 0
1008 | PGE | 93242 | NEM | EXPNEM | IA in Progress | Solar PV | 85.259 |  | 2021-05-25 | 2021-06-04 | 7 | 2021-06-09 | 10 | 2021-06-21 | 8 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-24 | 3 |  |  |  |  | 2021-05-25 | 2021-06-17 | 16 | [16 empty] | 1//19 | 1//19
1009 | PGE | 93706 | NEM | EXPNEM | Commercial | Solar PV | 60 |  | 2021-05-25 | 2021-06-08 | 9 | 2021-06-09 | 10 | 2021-06-18 | 7 | [15 empty] | 2021-06-18 | 2021-06-25 | 5 | 2021-06-25 | 2021-06-28 | 1 |  |  |  |  | 2021-05-25 | 2021-06-24 | 21 |  |  |  |  | 2021-12-20 | 2022-01-06 | 13 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-20 | 2021-12-30 | 8 | 2022-01-06 |  | 2022-01-07 | 1
1010 | PGE | 95376 | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-05-25 | 2021-06-08 | 9 | 2021-06-08 | 9 | 2021-06-23 | 11 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-11-08 | 96 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
1011 | PGE | 93648 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 30.402 |  | 2021-05-25 | 2021-06-11 | 12 | 2021-06-25 | 22 | 2021-07-19 | 15 | [15 empty] | 2021-07-19 | 2021-07-19 | 0 | 2021-07-19 | [6 empty] | 2021-05-25 | 0 |  | 2022-01-10 | [15 empty] | 1//19 | 1//19
1012 | PGE | 93648 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.179 |  | 2021-05-25 | 2021-06-11 | 12 | 2021-06-25 | 22 | 2021-07-19 | 15 | [15 empty] | 2021-07-19 | 2021-07-19 | 0 | 2021-07-19 | [6 empty] | 2021-05-25 | 0 |  | 2022-01-10 | [15 empty] | 1//19 | 1//19
1013 | PGE | 94560 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-05-26 | 2021-05-27 | 1 | 2021-06-09 | 9 | 2021-07-28 | 34 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | 2021-10-22 | 61 | [5 empty] | 0 | [5 empty] | 2021-11-30 | 2021-12-08 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-30 | 2021-11-30 | 0 | 2021-12-08 |  | 2021-12-09 | 1
1014 | PGE | 94538 | NEM | NEMMT | IA in Progress | Solar PV, Storage | 56.26 |  | 2021-05-25 | 2021-05-26 | 1 | 2021-06-16 | 15 | 2022-02-18 | 171 | [15 empty] | 2022-02-18 | 2022-02-18 | 0 | 2022-02-18 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
1015 | PGE | 95330 | NEM | EXPNEM | Withdrawn | Solar PV | 1466.6 |  | 2021-05-26 | 2021-06-04 | 6 | 2021-08-04 | 48 | 2021-09-08 | 24 | 2021-09-24 | 2021-10-25 | 21 | [22 empty] | 2021-08-10 | 0 | [17 empty] | 1//19 | 1//19
1016 | PGE | 95936 | Non-NEM | Non-Export | Commercial | Storage | 140 |  | 2021-05-26 | 2021-05-27 | 1 | 2021-06-23 | 19 | 2021-07-15 | 15 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-08-06 | 16 | [5 empty] | 0 | [5 empty] | 2022-03-04 | 2022-03-15 | 7 | [9 empty] | 1//19 | 1//19 |  | 2022-03-02 |  |  | 2022-03-04 | 2022-03-04 | 0 | 2022-03-15 |  | 2022-03-16 | 1
1017 | PGE | 95004 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 750 |  | 2021-05-26 | 2021-06-09 | 9 | 2021-08-18 | 58 | 2021-10-11 | 37 | [15 empty] | 2021-10-11 | 2021-10-11 | 0 | 2021-10-11 | 2022-01-18 | 67 | [5 empty] | 0 |  | 2021-09-10 | 2021-09-10 | 2021-10-11 | 0 | [12 empty] | 1//19 | 1//19
1018 | PGE | 95482 | NEM | VNEMMASH | Commercial | Solar PV | 41.246 |  | 2021-05-26 | 2021-06-10 | 10 | 2021-08-02 | 46 | 2021-08-23 | 15 | [15 empty] | 2021-08-23 | 2021-09-14 | 15 | 2021-09-14 | 2021-09-16 | 2 |  |  |  |  | 2021-08-05 | 2021-08-13 | 6 |  |  |  |  | 2022-01-25 | 2022-02-02 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-01-25 | 2022-01-26 | 1 | 2022-02-02 |  | 2022-02-09 | 5
1019 | PGE | 95482 | NEM | VNEMMASH | Commercial | Solar PV | 36.905 |  | 2021-05-26 | 2021-06-10 | 10 | 2021-08-02 | 46 | 2021-08-23 | 15 | [15 empty] | 2021-08-23 | 2021-09-14 | 15 | 2021-09-14 | 2021-09-16 | 2 | [5 empty] | 0 | [5 empty] | 2022-01-25 | 2022-02-02 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-01-25 | 2022-01-26 | 1 | 2022-02-02 |  | 2022-02-09 | 5
1020 | PGE | 95482 | NEM | VNEMMASH | Commercial | Solar PV | 55.756 |  | 2021-05-26 | 2021-06-10 | 10 | 2021-08-02 | 46 | 2021-08-23 | 15 | [15 empty] | 2021-08-23 | 2021-09-14 | 15 | 2021-09-14 | 2021-09-16 | 2 |  |  |  |  | 2021-08-05 | 2021-08-13 | 6 |  |  |  |  | 2022-01-25 | 2022-02-02 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-01-25 | 2022-01-26 | 1 | 2022-02-02 |  | 2022-02-09 | 5
1021 | PGE | 93721 | NEM | EXPNEM | Application Review in Progress | Solar PV | 32.125 |  | 2021-05-26 | 2021-06-04 | 6 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
1022 | PGE | 95540 | Non-NEM | Non-Export | IA in Progress | Storage | 630 |  | 2021-05-26 | 2021-05-27 | 1 | 2021-06-30 | 24 | 2021-09-17 | 55 | [15 empty] | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | [6 empty] | 2021-05-26 | 0 | [17 empty] | 1//19 | 1//19
1023 | PGE | 93408 | Non-NEM | Non-Export | Implementation | ENGN, Storage | 290 |  | 2021-05-27 | 2021-05-27 | 0 | 2021-06-23 | 18 | 2021-08-10 | 33 | [15 empty] | 2021-08-10 | 2021-08-25 | 11 | 2021-08-25 | 2021-11-23 | 62 |  |  |  |  | 2021-05-27 | 2021-07-07 | 27 | [16 empty] | 1//19 | 1//19
1024 | PGE | 94611 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.395 |  | 2021-05-27 | 2021-06-01 | 2 | 2021-06-04 | 5 | 2021-06-08 | 2 | [18 empty] | 2021-05-27 | [7 empty] | 0 | [5 empty] | 2021-06-08 | 2021-06-08 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-08 |  |  | 2021-06-08 |  | 2021-06-08 | 0
1025 | PGE | 95959 | NEM | VNEMMASH | Implementation | Solar PV | 37.758 |  | 2021-05-27 | 2021-06-11 | 10 | 2021-08-19 | 58 | 2021-09-08 | 13 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-12-21 | 71 |  |  |  |  | 2021-05-27 | 0 | [17 empty] | 1//19 | 1//19
1026 | PGE | 95032 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.232 |  | 2021-05-27 | 2021-06-01 | 2 | 2021-07-13 | 31 | 2021-07-15 | 2 | [18 empty] | 2021-05-27 | [7 empty] | 0 | [5 empty] | 2021-07-16 | 2021-07-16 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-16 |  |  | 2021-07-16 |  | 2021-07-16 | 0
1027 | PGE | 95330 | NEM | EXPNEM | Commercial | Solar PV | 32.401 |  | 2021-05-27 | 2021-06-07 | 6 | 2021-10-18 | 99 | 2021-10-21 | 3 | [15 empty] | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21 | 2021-12-06 | 29 |  |  |  |  | 2021-05-27 | 0 | [5 empty] | 2021-12-08 | 2021-12-17 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-08 | 2021-12-08 | 0 | 2021-12-17 |  | 2021-12-23 | 4
1028 | PGE | 95045 | NEM | EXPNEM | Implementation | Solar PV | 35.187 |  | 2021-05-28 | 2021-06-14 | 10 | 2021-06-17 | 13 | 2021-07-07 | 13 | [15 empty] | 2021-07-07 | 2021-07-26 | 13 | 2021-07-26 | 2021-08-13 | 14 |  |  |  |  | 2021-05-28 | 2021-07-02 | 24 |  |  |  |  | 2022-03-10 | 2022-03-24 | 10 |  | 2022-03-03 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 2022-03-10 | 2022-03-11 | 1 | 2022-03-24 | 2022-03-24 |  | 0 |  |  | 206
1029 | PGE | 95020 | NEM | EXPNEM | Commercial | Solar PV | 90 |  | 2021-05-28 | 2021-06-08 | 6 | 2021-07-02 | 24 | 2021-07-21 | 12 | [15 empty] | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | 2021-08-18 | 20 | [5 empty] | 0 | [5 empty] | 2021-08-27 | 2021-09-07 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-27 | 2021-08-27 | 0 | 2021-09-07 |  | 2021-09-13 | 4
1030 | PGE | 95422 | NEM | EXPNEM | Commercial | Solar PV | 98.329 |  | 2021-05-28 | 2021-06-23 | 17 | 2021-08-18 | 56 | 2021-09-29 | 29 | [15 empty] | 2021-09-29 | 2021-10-19 | 14 | 2021-10-19 | 2021-12-10 | 35 |  |  |  |  | 2021-05-28 | 0 |  | 2021-09-08 |  |  |  | 2022-02-08 | 2022-02-09 | 1 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-02-08 | 2022-02-09 | 1 | 2022-02-09 |  | 2022-02-09 | 0
1031 | PGE | 95959 | NEM | VNEMMASH | Implementation | Solar PV | 36.54 |  | 2021-05-28 | 2021-06-11 | 9 | 2021-08-19 | 57 | 2021-09-08 | 13 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-12-21 | 71 |  |  |  |  | 2021-05-28 | 0 | [17 empty] | 1//19 | 1//19
1032 | PGE | 95943 | NEM | EXPNEM | Commercial | Solar PV | 35.172 |  | 2021-05-28 | 2021-06-09 | 7 | 2021-10-28 | 106 | 2021-11-09 | 8 | [15 empty] | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | 2022-01-12 | 43 |  |  |  |  | 2021-05-28 | 2021-07-22 | 37 |  |  |  |  | 2022-01-13 | 2022-01-25 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-01-13 | 2022-01-14 | 1 | 2022-01-25 |  | 2022-01-28 | 3
1033 | PGE | 95650 | NEM | EXPNEM | Implementation | Solar PV | 66.6 |  | 2021-05-28 | 2021-06-09 | 7 | 2021-07-02 | 24 | 2021-08-30 | 40 | 2021-08-30 | 2021-10-04 | 24 | 2021-10-04 | 2021-10-27 | 17 | 2021-10-27 | 2021-10-27 |  | 2021-10-27 | 2022-02-08 | 75 | 2021-10-27 |  |  | 2022-02-08 | 2022-02-08 | 0 | 2022-02-08 | 2022-03-07 | 18 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
1034 | PGE | 95018 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 36.796 |  | 2021-05-28 | 2021-06-02 | 2 | 2021-06-02 | 2 | 2021-06-07 | 3 | [26 empty] | 0 | [5 empty] | 2022-02-09 | 2022-02-14 | 3 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2022-02-09 | 2022-02-14 | 3 | 2022-02-14 |  | 2022-02-14 | 0
1035 | PGE | 94517 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-05-30 | 2021-06-02 | 1 | 2021-07-12 | 28 | 2021-07-13 | 1 | [18 empty] | 2021-05-30 | [7 empty] | 0 | [5 empty] | 2021-07-14 | 2021-07-14 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-14 |  |  | 2021-07-14 |  | 2021-07-14 | 0
1036 | PGE | 93401 | NEM | EXPNEM | Implementation | Solar PV | 34.179 |  | 2021-06-01 | 2021-06-15 | 10 | 2021-08-02 | 43 | 2021-11-02 | 65 | [15 empty] | 2021-11-02 | 2021-11-15 | 8 | 2021-11-15 | 2021-11-15 | 0 |  |  |  |  | 2021-06-01 | 0 |  | 2021-09-02 |  |  |  | 2022-03-07 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 2022-03-07 | 2022-03-31 | 18
1037 | PGE | 93401 | NEM | EXPNEM | Implementation | Solar PV | 34.179 |  | 2021-06-01 | 2021-06-15 | 10 | 2021-08-25 | 60 | 2021-09-07 | 8 | [15 empty] | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-12-31 | 80 |  |  |  |  | 2021-06-01 | 2021-09-08 | 69 |  |  |  |  | 2022-03-07 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 2022-03-07 | 2022-03-31 | 18
1038 | PGE | 93401 | NEM | EXPNEM | Implementation | Solar PV | 42.472 |  | 2021-06-01 | 2021-06-09 | 6 | 2021-08-12 | 51 | 2021-08-25 | 9 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | 2021-11-15 | 56 |  |  |  |  | 2021-06-01 | 2021-09-07 | 68 |  |  |  |  | 2022-03-03 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 2022-03-03 | 2022-03-31 | 20
1039 | PGE | 93706 | NEM | EXPNEM | IA in Progress | Solar PV | 696 |  | 2021-06-01 | 2021-06-15 | 10 | 2021-07-26 | 38 | 2021-08-11 | 12 | 2021-08-11 | 2021-09-05 | 17 | [12 empty] | 2021-09-05 | 2021-09-05 | 0 | 2021-09-05 | 2021-10-20 | 31 | [5 empty] | 0 | [8 empty] | 2021-11-15 | 2022-03-07 | 77 | [6 empty] | 1//19 | 1//19
1040 | PGE | 95553 | NEM | EXPNEM | Commercial | Solar PV | 226.751 |  | 2021-06-01 | 2021-06-14 | 9 | 2021-06-30 | 21 | 2021-08-06 | 26 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | 2021-08-16 | 6 |  |  |  |  | 2021-06-01 | 0 | [5 empty] | 2021-12-10 | 2021-12-22 | 8 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-12-10 | 2021-12-10 | 0 | 2021-12-22 |  | 2021-12-22 | 0
1041 | PGE | 93204 | NEM | EXPNEM | Commercial | Solar PV | 36.186 |  | 2021-06-01 | 2021-06-09 | 6 | 2021-06-28 | 19 | 2021-07-08 | 7 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-08-16 | 27 |  |  |  |  | 2021-06-01 | 2021-07-19 | 33 |  |  |  |  | 2021-09-17 | 2021-09-23 | 4 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-17 | 2021-09-17 | 0 | 2021-09-23 |  | 2021-09-30 | 5
1043 | PGE | 94507 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.657 |  | 2021-06-01 | 2021-06-03 | 2 | 2021-06-15 | 10 | 2021-06-16 | 1 | [18 empty] | 2021-06-14 | [7 empty] | 0 | [5 empty] | 2021-06-16 | 2021-06-16 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-06-16 |  |  | 2021-06-16 |  | 2021-06-16 | 0
1044 | PGE | 93725 | NEM | EXPNEM | Implementation | Solar PV | 75.777 |  | 2021-06-02 | 2021-06-14 | 8 | 2021-06-14 | 8 | 2021-07-02 | 14 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-07-02 | 0 |  |  |  |  | 2021-06-02 | 0 |  | 2021-07-09 | [15 empty] | 1//19 | 1//19
1045 | PGE | 95632 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-06-02 | 2021-06-14 | 8 | 2021-06-16 | 10 | 2021-06-28 | 8 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-07-26 | 19 |  |  |  |  | 2021-06-02 | 2021-06-28 | 18 |  |  |  |  | 2021-07-26 | 2021-08-03 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-26 | 2021-07-27 | 1 | 2021-08-03 |  | 2021-08-04 | 1
1046 | PGE | 93706 | NEM | EXPNEM | Commercial | Solar PV | 229.645 |  | 2021-06-02 | 2021-06-09 | 5 | 2021-06-09 | 5 | 2021-06-24 | 11 | 2021-06-24 | 2021-07-06 | 7 | [12 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-07-08 | 2 | [5 empty] | 0 | [5 empty] | 2021-11-05 | 2021-11-12 | 4 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-11-05 | 2021-11-05 | 0 | 2021-11-12 |  | 2021-11-19 | 5
1047 | PGE | 94578 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 56.965 |  | 2021-06-02 | 2021-06-11 | 7 | 2021-06-11 | 7 | 2021-07-02 | 15 | [15 empty] | 2021-07-02 | 2021-07-26 | 15 | 2021-07-26 | [6 empty] | 2021-06-02 | 2021-09-23 | 79 |  | 2021-08-19 | 2021-08-19 | 0 | [12 empty] | 1//19 | 1//19
1048 | PGE | 95301 | NEM | EXPNEM | IA in Progress | Solar PV | 72.547 |  | 2021-06-02 | 2021-06-09 | 5 | 2021-08-25 | 59 | 2021-09-16 | 15 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | 2021-10-07 | 15 |  |  |  |  | 2021-06-02 | 2021-09-08 | 68 |  |  |  |  | 2022-02-15 | 2022-02-28 | 8 | 2021-11-16 | 2022-03-07 | 76 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 2022-02-15 | 2022-02-16 | 1 | 2022-02-28 | 2022-03-03 |  | 3 |  |  | 189
1049 | PGE | 94519 | Non-NEM | Non-Export | Withdrawn | Solar PV | 50 |  | 2021-06-02 | 2021-06-02 | 0 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
1050 | PGE | 93212 | Non-NEM | RESBCT | Implementation | Solar PV | 3125 |  | 2021-06-02 | 2021-06-04 | 2 | 2021-06-16 | 10 | [5 empty] | 2021-06-16 | 2021-07-12 | 17 | 2021-07-12 | 2021-07-12 | 0 | 2021-07-22 | 2021-10-05 | 52 | 2021-07-12 | 2021-07-12 | 0 | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-11-15 | 18 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19
1051 | PGE | 93907 | NEM | EXPNEM | Commercial | Solar PV | 60.868 |  | 2021-06-02 | 2021-06-10 | 6 | 2021-06-22 | 14 | 2021-07-14 | 15 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-22 | 6 | [5 empty] | 0 | [5 empty] | 2021-07-31 | 2021-08-10 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-31 | 2021-08-02 | 0 | 2021-08-10 |  | 2021-08-13 | 3
1052 | PGE | 95060 | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.3 |  | 2021-06-02 | 2021-06-10 | 6 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
1053 | PGE | 95060 | NEM | EXPNEM | Application Review in Progress | Solar PV | 40.002 |  | 2021-06-02 | 2021-06-10 | 6 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19
1054 | PGE | 95210 | NEM | VNEMSOMAH | Implementation | Solar PV | 277.81 |  | 2021-06-03 | 2021-06-17 | 10 | 2021-10-19 | 96 | 2021-11-09 | 15 | [15 empty] | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | 2021-12-30 | 34 |  |  |  |  | 2021-06-03 | 0 | [17 empty] | 1//19 | 1//19
1055 | PGE | 94601 | NEM | EXPNEM | IA in Progress | Solar PV | 168.227 |  | 2021-06-03 | 2021-06-15 | 8 | 2021-10-15 | 94 | 2021-10-20 | 3 | [15 empty] | 2021-10-20 | 2021-10-20 | 0 | 2021-10-20 | 2021-12-22 | 42 |  |  |  |  | 2021-07-14 | 2021-09-28 | 53 | [7 empty] | 2022-01-11 |  | 66 | [6 empty] | 1//19 | 1//19
1056 | PGE | 94924 | NEM | EXPNEM | IA in Progress | Solar PV | 57.177 |  | 2021-06-03 | 2021-06-17 | 10 | 2021-07-09 | 25 | 2021-07-26 | 11 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
1057 | PGE | 95503 | NEM | EXPNEM | Commercial | Solar PV | 38.78 |  | 2021-06-03 | 2021-06-11 | 6 | 2021-06-15 | 8 | 2021-07-06 | 14 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-07-14 | 6 | [5 empty] | 0 | [5 empty] | 2021-09-23 | 2021-10-18 | 17 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-23 | 2021-10-12 | 13 | 2021-10-18 |  | 2021-10-25 | 5
1058 | PGE | 93710 | NEM | EXPNEM | IA in Progress | ENGN, Solar PV | 437.796 |  | 2021-06-03 | 2021-06-17 | 10 | 2021-08-06 | 45 | 2021-08-23 | 11 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
1059 | PGE | 95070 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.29 |  | 2021-06-03 | 2021-06-07 | 2 | 2021-08-27 | 60 | 2021-08-31 | 2 | [18 empty] | 2021-06-11 | [7 empty] | 0 | [5 empty] | 2021-08-31 | 2021-08-31 | 0 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-31 |  |  | 2021-08-31 |  | 2021-08-31 | 0
1060 | PGE | 93446 | NEM | EXPNEM | Commercial | Solar PV | 35.005 |  | 2021-06-03 | 2021-06-11 | 6 | 2021-06-16 | 9 | 2021-07-08 | 15 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-09 | 1 | [5 empty] | 0 | [5 empty] | 2021-07-26 | 2021-08-04 | 7 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-26 | 2021-07-26 | 0 | 2021-08-04 |  | 2021-08-11 | 5
1061 | PGE | 95659 | NEM | EXPNEM | IA in Progress | Solar PV | 634.724 |  | 2021-06-03 | 2021-06-11 | 6 | 2021-11-10 | 112 | 2021-12-03 | 14 | 2021-12-03 | 2022-03-01 | 60 | [12 empty] | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19
1062 | PGE | 95037 | NEM | EXPNEM | IA in Progress | Solar PV | 312.5 |  | 2021-06-03 | 2021-06-11 | 6 | 2021-11-01 | 105 | 2021-12-22 | 34 | 2021-12-22 | 2022-02-10 | 35 | [12 empty] | 2022-02-10 | 2022-02-10 | 0 | 2022-02-10 | [6 empty] | 2021-06-03 | 0 | [17 empty] | 1//19 | 1//19
1063 | PGE | 95361 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 54.494 |  | 2021-06-03 | 2021-06-08 | 3 | 2021-06-16 | 9 | 2021-07-02 | 12 | [15 empty] | 2021-08-11 | 2021-08-11 | 0 | 2021-08-11 | 2021-08-11 | 0 | [5 empty] | 0 | [5 empty] | 2021-08-11 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 2021-08-11 | 2021-08-12 | 1
1064 | PGE | 94710 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-06-03 | 2021-06-11 | 6 | 2021-06-11 | 6 | 2021-06-17 | 4 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-07-16 | 20 | [5 empty] | 0 | [5 empty] | 2021-07-28 | 2021-08-05 | 6 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-07-28 | 2021-08-05 | 6 | 2021-08-05 |  | 2021-08-11 | 4
1065 | PGE | 93401 | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2021-06-04 | 2021-06-04 | 0 | 2021-06-30 | 18 | 2021-08-25 | 39 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | 2021-09-29 | 24 |  |  |  |  | 2021-06-04 | 2021-09-10 | 68 | [16 empty] | 1//19 | 1//19
1066 | PGE | 93311 | NEM | EXPNEM | Withdrawn | ENGN | 1000 |  | 2021-06-04 | 2021-06-22 | 12 | 2021-06-22 | 12 | 2021-07-09 | 12 | [26 empty] | 0 | [17 empty] | 1//19 | 1//19
1067 | PGE | 93711 | NEM | EXPNEM | Commercial | Solar PV | 44.37 |  | 2021-06-04 | 2021-06-12 | 5 | 2021-08-18 | 52 | 2021-09-08 | 14 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-09-08 | 0 | [5 empty] | 0 | [5 empty] | 2021-09-22 | 2022-01-10 | 75 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 2021-09-22 | 2022-01-10 | 75 | 2022-01-10 |  | 2022-01-13 | 3
1068 | PGE | 93245 | NEM | EXPNEM | Implementation | Solar PV | 266.145 |  | 2021-06-04 | 2021-06-15 | 7 | 2021-07-08 | 23 | 2021-08-10 | 23 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-10 | 2021-08-26 | 12 | [5 empty] | 0 | [8 empty] | 2021-10-04 | 2022-02-11 | 90 | [6 empty] | 1//19 | 1//19
1069 | PGE | 96013 | Non-NEM | Non-Export | Commercial | Storage | 140 |  | 2021-06-04 | 2021-06-04 | 0 | 2021-06-30 | 18 | 2021-07-20 | 13 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | 2022-01-26 | 125 |  |  |  |  | 2021-06-04 | 2021-07-14 | 27 |  |  |  |  | 2022-02-08 | 2022-03-02 | 15 | [9 empty] | 1//19 | 1//19 |  | 2021-07-26 |  |  | 2022-02-08 | 2022-02-23 | 10 | 2022-03-02 |  | 2022-03-02 | 0 | 2022-02-03 | 18 | 0
1070 | PGE | 95603 | NEM | VNEM | Implementation | Solar PV | 48.363 |  | 2021-06-04 | 2021-06-18 | 10 | 2021-12-13 | 131 | 2021-12-29 | 12 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 2022-01-31 | 22 | [5 empty] | 0 |  |  | 2022-01-27 | 2022-01-27 | 0 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1071 | PGE | 95603 | NEM | VNEM | Implementation | Solar PV | 57.71 |  | 2021-06-04 | 2021-06-18 | 10 | 2021-12-13 | 131 | 2021-12-29 | 12 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 2022-02-09 | 29 | [5 empty] | 0 |  |  | 2022-02-08 | 2022-02-08 | 0 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1072 | PGE | 95603 | NEM | VNEM | Implementation | Solar PV | 52.163 |  | 2021-06-04 | 2021-06-18 | 10 | 2021-12-13 | 131 | 2021-12-29 | 12 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 2022-02-08 | 28 | [5 empty] | 0 |  |  | 2022-01-27 | 2022-01-27 | 0 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1073 | PGE | 95446 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 32.436 |  | 2021-06-04 | 2021-06-18 | 10 | 2021-06-25 | 15 | 2021-07-19 | 15 | [15 empty] | 2021-07-19 | 2021-07-19 | 0 | 2021-07-19 | [6 empty] | 2021-07-21 | 2021-08-03 | 9 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1074 | PGE | 95446 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 52.163 |  | 2021-06-04 | 2021-06-18 | 10 | 2021-06-25 | 15 | 2021-07-19 | 15 | [15 empty] | 2021-07-19 | 2021-07-19 | 0 | 2021-07-19 | [6 empty] | 2021-07-21 | 2021-08-03 | 9 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1075 | PGE | 94954 | NEM | EXPNEM | Commercial | Solar PV | 31.791 |  | 2021-06-04 | 2021-06-12 | 5 | 2021-06-16 | 8 | 2021-07-06 | 13 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-07-21 | 11 | [5 empty] | 0 | [5 empty] | 2021-10-11 | 2021-10-18 | 5 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-11 | 2021-10-12 | 1 | 2021-10-18 |  | 2021-10-25 | 5 | 1//19
1076 | PGE | 94062 | NEM | SNEM Paired Storage | Implementation | Solar PV, Storage | 42.725 |  | 2021-06-06 | 2021-06-09 | 2 | 2021-08-21 | 54 | 2021-08-23 | 0 | [18 empty] | 2021-06-06 | [7 empty] | 0 | [5 empty] | 2021-08-23 | [11 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-23 | 2021-10-15 | 38 |  |  |  |  | 1//19
1077 | PGE | 94954 | NEM | EXPNEM | Implementation | Solar PV | 38.78 |  | 2021-06-07 | 2021-06-10 | 3 | 2021-09-03 | 63 | 2021-09-21 | 11 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | 2021-12-07 | 52 | [5 empty] | 0 | [5 empty] | 2022-03-04 | 2022-03-09 | 3 | 2021-12-29 | 2022-03-22 | 59 |  |  |  | 2022-03-22 |  | 16 | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-04 | 2022-03-04 | 0 | 2022-03-09 | 2022-03-11 |  | 2 | 1//19 |  | 192
1078 | PGE | 95126 | NEM | EXPNEM | Implementation | Solar PV | 162.5 |  | 2021-06-07 | 2021-06-16 | 7 | 2021-06-16 | 7 | 2021-10-19 | 87 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-10-29 | 8 |  |  |  |  | 2021-06-07 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1079 | PGE | 95695 | NEM | EXPNEM | IA in Progress | Solar PV | 55.575 |  | 2021-06-07 | 2021-06-12 | 4 | 2021-06-16 | 7 | 2021-07-07 | 14 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | 2021-08-04 | 20 |  |  |  |  | 2021-06-07 | 2021-06-18 | 9 |  |  |  |  | 2021-08-26 | 2021-09-01 | 4 | 2021-09-17 | 2022-01-27 | 90 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-26 | 2021-08-27 | 1 | 2021-09-01 |  |  |  | 1//19
1080 | PGE | 94519 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-06-07 | 2021-06-12 | 4 | 2021-08-30 | 59 | 2021-09-21 | 15 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | 2021-09-24 | 3 | [5 empty] | 0 | [5 empty] | 2021-11-04 | 2021-11-17 | 8 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-04 | 2021-11-11 | 4 | 2021-11-17 |  | 2021-12-06 | 11 | 1//19
1081 | PGE | 95123 | NEM | EXPNEM | IA in Progress | Solar PV | 98.286 |  | 2021-06-07 | 2021-06-12 | 4 | 2021-09-23 | 76 | 2021-10-08 | 11 | [15 empty] | 2021-10-08 | 2021-10-08 | 0 | 2021-10-08 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1082 | PGE | 95123 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-06-07 | 2021-06-12 | 4 | 2021-07-19 | 29 | 2021-08-04 | 12 | [15 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | 2021-08-30 | 18 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1083 | PGE | 94517 | NEM | EXPNEM | Application Review in Progress | Solar PV | 900 |  | 2021-06-07 | 2021-06-12 | 4 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1084 | PGE | 95695 | NEM | EXPNEM | IA in Progress | Solar PV | 58.63 |  | 2021-06-08 | 2021-06-12 | 3 | 2021-08-05 | 41 | 2021-08-24 | 13 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | 2021-08-31 | 5 |  |  |  |  | 2021-06-08 | 2021-07-28 | 35 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1085 | PGE | 93704 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-06-08 | 2021-06-15 | 5 | 2021-06-15 | 5 | 2021-06-18 | 3 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-18 | 2021-06-22 | 2 |  |  |  |  | 2021-06-08 | 2021-09-10 | 66 |  |  |  |  | 2021-12-02 | 2021-12-09 | 5 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-02 | 2021-12-02 | 0 | 2021-12-09 |  | 2021-12-16 | 5 | 1//19
1086 | PGE | 93710 | NEM | EXPNEM | Implementation | Solar PV | 38.138 |  | 2021-06-08 | 2021-07-01 | 17 | 2021-08-03 | 39 | 2021-08-13 | 8 | [15 empty] | 2021-08-13 | 2021-08-13 | 0 | 2021-08-13 | 2021-11-08 | 60 | [5 empty] | 0 |  | 2021-08-13 | 2021-11-18 | 2021-11-18 | 67 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1087 | PGE | 94574 | NEM | EXPNEM | Commercial | Solar PV | 133.3 |  | 2021-06-08 | 2021-06-15 | 5 | 2021-06-15 | 5 | 2021-07-27 | 29 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-08-06 | 8 | [5 empty] | 0 | [5 empty] | 2022-01-28 | 2022-02-10 | 9 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-28 | 2022-01-31 | 1 | 2022-02-10 |  | 2022-02-15 | 3 | 1//19
1088 | PGE | 95692 | NEM | EXPNEM | Implementation | Solar PV | 66.6 |  | 2021-06-08 | 2021-06-16 | 6 | 2021-06-22 | 10 | 2021-07-12 | 13 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-07-20 | 6 |  |  |  |  | 2021-06-08 | 0 | [5 empty] | 2022-03-25 |  |  | 2021-08-18 | 2022-01-10 | 98 |  |  |  | 2022-02-16 | 2022-03-14 | 18 | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-25 | 2022-03-25 | 0 |  |  |  |  | 1//19
1089 | PGE | 93307 | NEM | EXPNEM | Implementation | Solar PV | 540 |  | 2021-06-08 | 2021-06-18 | 8 | 2021-06-22 | 10 | 2021-06-29 | 5 | 2021-06-29 | 2021-07-27 | 19 | [12 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-08-01 | 3 | [5 empty] | 0 | [8 empty] | 2021-10-21 |  | 120 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1090 | PGE | 95376 | NEM | EXPNEM | Withdrawn | Solar PV | 1200 |  | 2021-06-09 | 2021-06-09 | 0 | 2021-08-04 | 39 | 2021-10-14 | 50 | [25 empty] | 2021-06-09 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1091 | PGE | 94539 | NEM | EXPNEM | Commercial | Solar PV | 86.4 |  | 2021-06-09 | 2021-06-15 | 4 | 2021-06-28 | 13 | 2021-07-15 | 12 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-07-16 | 1 | [5 empty] | 0 | [5 empty] | 2021-07-31 | 2021-10-18 | 54 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-07-31 | 2021-10-15 | 53 | 2021-10-18 |  | 2021-10-26 | 6 | 1//19
1092 | PGE | 93955 | NEM | EXPNEM | Commercial | Solar PV | 57.71 |  | 2021-06-09 | 2021-06-16 | 5 | 2021-07-27 | 33 | 2021-08-31 | 25 | [15 empty] | 2021-08-31 | 2021-09-02 | 2 | 2021-09-02 | 2021-09-06 | 1 | [5 empty] | 0 | [5 empty] | 2021-09-16 | 2021-09-21 | 3 | 2021-11-08 | 2022-03-16 | 88 |  |  |  | 2022-03-15 |  | 21 | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-16 | 2021-09-17 | 1 | 2021-09-21 |  | 2021-10-22 | 23 | 1//19
1093 | PGE | 93950 | NEM | EXPNEM | Commercial | Solar PV | 34.179 |  | 2021-06-09 | 2021-06-16 | 5 | 2021-08-04 | 39 | 2021-08-19 | 11 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-08-24 | 3 | [5 empty] | 0 | [5 empty] | 2021-09-13 | 2021-10-05 | 16 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-13 | 2021-09-30 | 13 | 2021-10-05 |  | 2021-10-12 | 5 | 1//19
1094 | PGE | 93656 | NEM | EXPNEM | Withdrawn | Solar PV | 1680 |  | 2021-06-09 | 2021-06-10 | 1 | 2021-06-16 | 5 | 2021-07-26 | 27 | 2021-08-12 | 2021-09-09 | 19 | [22 empty] | 2021-07-08 | 2021-07-21 | 9 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1095 | PGE | 93618 | NEM | EXPNEM | Implementation | Solar PV | 830 |  | 2021-06-10 | 2021-06-23 | 9 | 2021-07-22 | 29 | 2021-08-05 | 10 | [15 empty] | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02 | 2021-11-29 | 58 |  |  |  |  | 2021-06-10 | 0 |  | 2021-07-23 | [6 empty] | 2021-11-01 | 2022-02-16 | 73 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1096 | PGE | 94928 | NEM | NEMMT | Application Review in Progress | ENGN, Solar PV | 625 |  | 2021-06-10 | 2021-06-24 | 10 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1097 | PGE | 94945 | NEM | NEMMT | Application Review in Progress | ENGN, Solar PV | 625 |  | 2021-06-10 | 2021-06-24 | 10 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1098 | PGE | 95602 | NEM | EXPNEM | Implementation | Solar PV | 60 |  | 2021-06-10 | 2021-06-16 | 4 | 2021-06-29 | 13 | 2021-07-13 | 9 | [15 empty] | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13 | 2021-07-26 | 9 | [5 empty] | 0 | [5 empty] | 2022-03-22 | [11 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-22 | 2022-03-23 | 1 |  |  |  |  | 1//19
1099 | PGE | 93313 | NEM | EXPNEM | IA in Progress | Solar PV | 136 |  | 2021-06-10 | 2021-06-16 | 4 | 2021-06-18 | 6 | 2021-06-29 | 7 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | 2022-01-11 | 135 |  |  |  |  | 2021-06-10 | 2021-07-09 | 20 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1100 | PGE | 95603 | NEM | EXPNEM | Commercial | Solar PV | 43.964 |  | 2021-06-10 | 2021-06-16 | 4 | 2021-09-09 | 63 | 2021-09-15 | 4 | [15 empty] | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | 2021-10-12 | 19 |  |  |  |  | 2021-06-10 | 2021-09-10 | 64 |  |  |  |  | 2022-02-22 | 2022-03-25 | 23 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-22 | 2022-03-25 | 23 | 2022-03-25 |  | 2022-03-25 | 0 | 1//19
1101 | PGE | 94952 | NEM | NEMMT | IA in Progress | Solar PV, Storage | 8248.335 |  | 2021-06-10 | 2021-06-14 | 2 | 2021-06-23 | 9 | [5 empty] | 2021-07-15 | 2021-08-02 | 12 | 2021-08-02 | 2021-08-02 | 0 | 2021-08-16 | 2021-12-10 | 80 | 2021-08-02 | 2021-08-03 | 1 | 2021-12-16 | 2022-01-06 | 15 | 2022-01-06 | [6 empty] | 2021-06-10 | 2021-07-08 | 19 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1102 | PGE | 93612 | NEM | VNEM | IA in Progress | Solar PV | 520.277 |  | 2021-06-11 | 2021-06-21 | 6 | 2021-07-09 | 19 | 2021-07-30 | 15 | [15 empty] | 2021-07-30 | 2021-08-20 | 15 | 2021-08-20 | [6 empty] | 2021-06-11 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1103 | PGE | 94010 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 30.75 |  | 2021-06-11 | 2021-06-14 | 1 | 2021-10-21 | 92 | 2021-10-25 | 2 | [18 empty] | 2021-10-15 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1104 | PGE | 93612 | NEM | VNEM | Commercial | Solar PV | 49.035 |  | 2021-06-11 | 2021-06-21 | 6 | 2021-08-09 | 40 | 2021-08-30 | 15 | [15 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-09-02 | 3 | [5 empty] | 0 |  | 2021-09-10 |  |  |  | 2022-02-01 | 2022-03-25 | 37 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-01 | 2022-03-23 | 35 | 2022-03-25 |  | 2022-03-25 | 0 | 1//19
1105 | PGE | 93638 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 76.036 |  | 2021-06-11 | 2021-06-25 | 10 | 2021-06-30 | 13 | 2021-07-22 | 15 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | [6 empty] | 2021-06-11 | 2021-07-08 | 18 |  | 2021-07-22 | 2021-07-22 | 0 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1106 | PGE | 93638 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 76.036 |  | 2021-06-11 | 2021-06-25 | 10 | 2021-06-30 | 13 | 2021-07-22 | 15 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | [6 empty] | 2021-06-11 | 2021-07-08 | 18 |  | 2021-07-22 | 2021-07-22 | 0 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1107 | PGE | 94551 | NEM | EXPNEM | Commercial | Solar PV | 75.4 |  | 2021-06-11 | 2021-06-17 | 4 | 2021-07-12 | 20 | 2021-07-21 | 7 | [15 empty] | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | 2021-08-24 | 24 |  |  |  |  | 2021-08-24 | 2021-09-10 | 12 |  |  |  |  | 2021-10-19 | 2021-10-27 | 6 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-19 | 2021-10-19 | 0 | 2021-10-27 |  | 2021-11-01 | 3 | 1//19
1108 | PGE | 93638 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 76.006 |  | 2021-06-11 | 2021-06-25 | 10 | 2021-06-30 | 13 | 2021-07-22 | 15 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | [6 empty] | 2021-06-11 | 2021-07-08 | 18 |  | 2021-07-22 | 2021-07-22 | 0 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1109 | PGE | 93420 | NEM | VNEM | Commercial | Solar PV | 200 |  | 2021-06-11 | 2021-06-21 | 6 | 2021-07-26 | 30 | 2021-08-13 | 14 | [15 empty] | 2021-08-13 | 2021-08-13 | 0 | 2021-08-13 | 2021-10-07 | 38 | [5 empty] | 0 |  | 2021-08-30 | 2021-10-07 | 2021-10-11 | 27 | 2021-12-23 | 2021-12-30 | 5 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-23 | 2021-12-27 | 2 | 2021-12-30 |  | 2021-12-31 | 1 | 1//19
1110 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 64.643 |  | 2021-06-11 | 2021-06-25 | 10 | 2021-06-30 | 13 | 2021-07-22 | 15 | [15 empty] | 2021-07-22 | 2021-08-03 | 8 | 2021-08-03 | [6 empty] | 2021-06-11 | 2021-08-03 | 36 |  | 2021-08-03 | 2021-08-03 | 0 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1111 | PGE | 93635 | NEM | EXPNEM | Implementation | Solar PV | 162.5 |  | 2021-06-11 | 2021-06-22 | 7 | 2021-08-23 | 50 | 2021-09-02 | 8 | [15 empty] | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02 | 2021-09-09 | 4 |  |  |  |  | 2021-06-11 | 2021-09-07 | 60 | [7 empty] | 2021-11-08 | 2022-03-24 | 94 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1112 | PGE | 93455 | NEM | EXPNEM | Withdrawn | Solar PV | 500 |  | 2021-06-11 | 2021-06-21 | 6 | 2021-07-08 | 18 | 2021-07-22 | 10 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1113 | PGE | 94804 | NEM | EXPNEM | IA in Progress | Solar PV | 400 |  | 2021-06-11 | 2021-06-17 | 4 | 2021-06-17 | 4 | 2021-07-09 | 15 | [15 empty] | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1114 | PGE | 94804 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-06-11 | 2021-06-17 | 4 | 2021-06-18 | 5 | 2021-07-21 | 22 | [15 empty] | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1115 | PGE | 94582 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.15 |  | 2021-06-13 | 2021-06-15 | 1 | 2021-07-14 | 21 | 2021-07-20 | 4 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-15 | 2021-07-14 | 20 | [5 empty] | 0 | [5 empty] | 2021-07-20 | 2021-07-20 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 |  | 2021-07-20 | 0 | 1//19
1116 | PGE | 94549 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.232 |  | 2021-06-14 | 2021-06-16 | 2 | 2021-07-01 | 13 | 2021-07-06 | 2 | [15 empty] | 2021-06-14 | 2021-06-14 | 0 | 2021-06-14 | 2021-06-14 | 0 | [5 empty] | 0 | [5 empty] | 2021-07-06 | 2021-07-06 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 |  | 2021-07-06 | 0 | 1//19
1117 | PGE | 95126 | NEM | EXPNEM | IA in Progress | Solar PV | 75.463 |  | 2021-06-14 | 2021-06-17 | 3 | 2021-06-17 | 3 | 2021-07-09 | 15 | [15 empty] | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12 | 2021-11-04 | 82 |  |  |  |  | 2021-06-14 | 2021-07-09 | 18 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1118 | PGE | 95126 | NEM | EXPNEM | Implementation | Solar PV | 145.8 |  | 2021-06-14 | 2021-06-22 | 6 | 2021-06-22 | 6 | 2021-10-26 | 88 | [15 empty] | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26 | 2021-11-02 | 5 |  |  |  |  | 2021-06-14 | 0 | [8 empty] | 2022-02-17 |  | 39 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1119 | PGE | 94027 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 40.75 |  | 2021-06-14 | 2021-06-16 | 2 | 2021-08-17 | 45 | 2021-08-19 | 2 | [18 empty] | 2021-07-16 | [7 empty] | 0 | [5 empty] | 2021-08-19 | 2021-08-24 | 3 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-19 | 2021-08-19 | 0 | 2021-08-24 |  | 2021-08-25 | 1 | 1//19
1120 | PGE | 95062 | NEM | EXPNEM | Commercial | Solar PV | 109.873 |  | 2021-06-14 | 2021-06-17 | 3 | 2021-07-07 | 16 | 2021-08-25 | 35 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | 2021-08-25 | 0 |  |  |  |  | 2021-06-14 | 2021-07-28 | 31 |  |  |  |  | 2021-11-29 | 2021-12-07 | 6 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-29 | 2021-11-30 | 1 | 2021-12-07 |  | 2021-12-14 | 5 | 1//19
1121 | PGE | 94556 | NEM | EXPNEM | Withdrawn | Solar PV | 80.24 |  | 2021-06-14 | 2021-06-17 | 3 | 2021-06-17 | 3 | 2021-07-20 | 22 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-08-18 | 21 |  |  |  |  | 2021-06-14 | 2021-07-12 | 19 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1122 | PGE | 94556 | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-06-14 | 2021-06-18 | 4 | 2021-08-02 | 34 | 2021-08-16 | 10 | [15 empty] | 2021-08-16 | 2021-08-17 | 1 | 2021-08-17 | 2021-08-18 | 1 |  |  |  |  | 2021-06-14 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1123 | PGE | 94556 | NEM | EXPNEM | IA in Progress | Solar PV | 90.067 |  | 2021-06-14 | 2021-06-17 | 3 | 2021-06-21 | 5 | 2021-08-16 | 39 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | 2021-08-18 | 2 |  |  |  |  | 2021-06-14 | 2021-07-12 | 19 |  |  |  |  | 2022-02-14 | 2022-02-28 | 9 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-14 | 2022-02-14 | 0 | 2022-02-28 |  |  |  | 1//19
1124 | PGE | 94513 | NEM | EXPNEM | IA in Progress | Solar PV | 34.921 |  | 2021-06-14 | 2021-06-22 | 6 | 2021-06-23 | 7 | 2021-08-06 | 31 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1125 | PGE | 93446 | NEM | VNEM | Withdrawn | Solar PV | 82.82 |  | 2021-06-15 | 2021-06-25 | 8 | [29 empty] | 2021-06-15 | 0 |  | 2021-07-09 | [15 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1126 | PGE | 95993 | NEM | EXPNEM | Commercial | Solar PV | 320.808 |  | 2021-06-15 | 2021-06-17 | 2 | 2021-06-17 | 2 | 2021-07-20 | 22 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-07-20 | 0 |  |  |  |  | 2021-06-15 | 2021-08-13 | 42 |  |  |  |  | 2021-12-23 | 2022-01-12 | 14 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-23 | 2022-01-12 | 14 | 2022-01-12 |  | 2022-01-14 | 2 | 1//19
1127 | PGE | 95304 | NEM | EXPNEM | Withdrawn | Solar PV | 133.2 |  | 2021-06-15 | 2021-06-18 | 3 | [29 empty] | 2021-06-15 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1128 | PGE | 95336 | NEM | EXPNEM | Study in Progress | Solar PV | 533.3 |  | 2021-06-15 | 2021-06-18 | 3 | 2021-11-18 | 109 | 2021-12-06 | 10 | 2021-12-06 | 2022-01-03 | 20 | 2022-02-02 | 2022-02-28 | 17 | 2022-02-28 | [18 empty] | 2021-06-15 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1129 | PGE | 95304 | NEM | EXPNEM | Withdrawn | Solar PV | 66.6 |  | 2021-06-15 | 2021-06-18 | 3 | [29 empty] | 2021-06-15 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1131 | PGE | 94903 | NEM | EXPNEM | Implementation | Solar PV | 420 |  | 2021-06-15 | 2021-06-23 | 6 | 2021-07-01 | 12 | 2021-08-26 | 39 | 2021-08-26 | 2021-09-22 | 18 | 2021-09-22 | 2021-10-14 | 16 | 2021-10-14 | 2021-10-14 |  | 2021-10-14 | 2021-12-31 | 57 | 2021-10-14 |  |  | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | 2022-01-04 | 2 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1132 | PGE | 93637 | NEM | NEMMT | Implementation | ENGN, Solar PV | 1192 |  | 2021-06-15 | 2021-06-21 | 4 | 2021-07-07 | 15 | [5 empty] | 2021-07-12 | 2021-08-09 | 20 | 2021-08-09 | 2021-08-09 | 0 | 2021-08-19 | 2021-11-17 | 62 | 2021-08-09 | 2021-08-09 | 0 | 2021-12-06 | 2021-12-07 | 1 | 2021-12-07 | 2022-02-10 | 46 |  |  |  |  | 2021-06-15 | 0 | [8 empty] | 2022-01-24 |  |  | 2022-01-24 | [5 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1133 | PGE | 94577 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-06-15 | 2021-06-18 | 3 | 2021-06-22 | 5 | 2021-07-12 | 13 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-08-02 | 15 |  |  |  |  | 2021-06-15 | 2021-07-09 | 17 |  |  |  |  | 2021-11-10 | 2021-11-29 | 10 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-10 | 2021-11-29 | 10 | 2021-11-29 |  | 2021-12-03 | 4 | 1//19
1134 | PGE | 93652 | NEM | EXPNEM | Implementation | Solar PV | 228.528 |  | 2021-06-15 | 2021-06-23 | 6 | 2021-06-30 | 11 | 2021-08-06 | 26 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | 2021-08-27 | 15 |  |  |  |  | 2021-06-15 | 2021-08-13 | 42 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1135 | PGE | 94010 | NEM | EXPNEM | Commercial | Solar PV | 58.04 |  | 2021-06-15 | 2021-06-18 | 3 | 2021-08-02 | 33 | 2021-08-09 | 5 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-16 | 5 | [5 empty] | 0 | [5 empty] | 2021-09-10 | 2021-09-15 | 3 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-10 | 2021-09-10 | 0 | 2021-09-15 |  | 2021-09-22 | 5 | 1//19
1136 | PGE | 95603 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-06-16 | 2021-06-21 | 3 | 2021-06-29 | 9 | 2021-07-14 | 10 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-11-03 | 79 | [5 empty] | 0 | [5 empty] | 2021-11-08 | 2021-11-30 | 13 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-08 | 2021-11-18 | 7 | 2021-11-30 |  | 2021-12-02 | 2 | 1//19
1137 | PGE | 93307 | NEM | EXPNEM | IA in Progress | Solar PV | 31.32 |  | 2021-06-16 | 2021-06-30 | 10 | 2022-03-07 | 181 | 2022-03-22 | 11 | [15 empty] | 2022-03-22 | 2022-03-22 | 0 | 2022-03-22 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1138 | PGE | 94539 | NEM | EXPNEM | Withdrawn | Solar PV | 57.71 |  | 2021-06-16 | 2021-06-21 | 3 | 2021-06-30 | 10 | [5 empty] | 2021-06-30 | 2021-07-27 | 18 | 2021-07-27 | [19 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1139 | PGE | 94538 | NEM | EXPNEM | IA in Progress | Solar PV | 700 |  | 2021-06-16 | 2021-06-24 | 6 | 2021-10-13 | 83 | 2021-12-17 | 44 | [15 empty] | 2021-12-17 | 2021-12-17 | 0 | 2021-12-17 | [6 empty] | 2021-06-16 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1140 | PGE | 95340 | NEM | EXPNEM | Implementation | Solar PV | 120 |  | 2021-06-16 | 2021-06-28 | 8 | 2021-07-08 | 15 | 2021-07-26 | 12 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-08-16 | 15 | [5 empty] | 0 | [8 empty] | 2021-10-22 | 2022-03-09 | 94 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1141 | PGE | 94571 | NEM | EXPNEM | IA in Progress | Solar PV | 31.024 |  | 2021-06-16 | 2021-06-22 | 4 | 2021-12-06 | 118 | 2022-01-12 | 27 | [15 empty] | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | 2022-02-14 | 22 |  |  |  |  | 2021-07-17 | 0 | [5 empty] | 2022-03-07 | [11 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-07 | 2022-03-09 | 2 |  |  |  |  | 1//19
1142 | PGE | 95694 | NEM | EXPNEM | IA in Progress | Solar PV | 720 |  | 2021-06-16 | 2021-06-22 | 4 | 2021-09-13 | 61 | 2021-10-04 | 15 | 2021-10-04 | 2021-11-04 | 23 | 2021-11-15 | 2021-12-21 | 24 | 2021-12-21 | 12/21/2021 |  | 2021-12-21 | 2022-03-24 | 68 | 12/21/2021 |  |  | 2022-03-24 | 2022-03-24 | 0 | 2022-03-24 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1143 | PGE | 93402 | NEM | VNEM | Study in Progress | Solar PV | 200 |  | 2021-06-16 | 2021-06-25 | 7 | 2021-08-12 | 40 | 2021-09-01 | 14 | [26 empty] | 0 |  | 2021-07-09 | [15 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1144 | PGE | 94538 | Non-NEM | Non-Export | Withdrawn | Storage | 145 |  | 2021-06-17 | 2021-06-17 | 0 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1145 | PGE | 95062 | NEM | VNEMSOMAH | Implementation | Solar PV | 166.032 |  | 2021-06-17 | 2021-07-01 | 10 | 2021-07-30 | 30 | 2021-09-10 | 29 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | 2021-11-15 | 45 |  |  |  |  | 2021-06-17 | 0 |  |  | 2021-10-25 | 2021-11-02 | 6 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1146 | PGE | 93449 | NEM | VNEM | Implementation | Solar PV | 300 |  | 2021-06-17 | 2021-07-01 | 10 | 2021-08-05 | 34 | 2021-09-09 | 24 | [15 empty] | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 | 2021-12-22 | 71 |  |  |  |  | 2021-06-17 | 0 |  |  | 2021-12-27 | 2021-12-27 | 0 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1147 | PGE | 95251 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 41.099 |  | 2021-06-17 | 2021-06-21 | 2 | 2021-06-30 | 9 | 2021-07-07 | 4 | [18 empty] | 2021-06-17 | [6 empty] | 2021-06-17 | 0 | [8 empty] | 2021-11-18 | 2022-03-15 | 80 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1148 | PGE | 93249 | NEM | EXPNEM | Implementation | Solar PV | 3000 |  | 2021-06-17 | 2021-06-17 | 0 | 2021-06-30 | 9 | [5 empty] | 2021-07-19 | 2021-08-18 | 22 | 2021-08-18 | 2021-08-18 | 0 | 2021-08-26 | 2021-11-23 | 61 | 2021-08-18 | 2021-08-18 | 0 | 2021-12-17 | 2021-12-20 | 1 | 2021-12-20 | 2022-03-21 | 63 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1149 | PGE | 95691 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-06-17 | 2021-06-22 | 3 | 2021-06-22 | 3 | 2021-07-12 | 13 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-08-19 | 28 | [5 empty] | 0 | [5 empty] | 2021-10-18 | 2021-12-02 | 30 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-18 | 2021-11-23 | 25 | 2021-12-02 |  | 2021-12-08 | 4 | 1//19
1150 | PGE | 93311 | NEM | EXPNEM | IA in Progress | Solar PV | 480.146 |  | 2021-06-18 | 2021-06-22 | 2 | 2021-06-30 | 8 | 2021-07-12 | 7 | 2021-07-12 | 2021-08-09 | 20 | [12 empty] | 2021-08-09 | 2021-08-20 | 9 | 2021-08-20 | 2021-09-08 | 12 | [5 empty] | 0 | [5 empty] | 2022-02-03 | 2022-02-15 | 8 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-03 | 2022-02-04 | 1 | 2022-02-15 | 2022-02-16 |  | 1 | 1//19 |  | 167
1151 | PGE | 95301 | NEM | EXPNEM | Study in Progress | Solar PV | 971.537 |  | 2021-06-18 | 2021-06-30 | 8 | 2021-08-12 | 38 | 2021-09-17 | 25 | 2021-09-17 | 2021-10-22 | 25 | 2021-10-28 | 2021-11-30 | 20 | 2021-11-30 | [18 empty] | 2021-06-18 | 2021-08-19 | 43 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1152 | PGE | 94580 | NEM | EXPNEM | IA in Progress | Solar PV | 40.32 |  | 2021-06-18 | 2021-07-02 | 10 | 2021-09-10 | 58 | 2021-09-13 | 1 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1153 | PGE | 94010 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 48.618 |  | 2021-06-22 | 2021-06-22 | 0 | 2021-10-07 | 75 | 2021-10-11 | 2 | [18 empty] | 2021-08-23 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1154 | PGE | 93612 | NEM | VNEM | IA in Progress | Solar PV | 576.251 |  | 2021-06-18 | 2021-06-25 | 5 | 2021-08-03 | 31 | 2021-08-25 | 16 | 2021-08-25 | 2021-09-16 | 15 | [12 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | [7 empty] | 0 |  | 2022-01-05 | [15 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1155 | PGE | 93612 | NEM | VNEM | IA in Progress | Solar PV | 520.008 |  | 2021-06-18 | 2021-06-25 | 5 | 2021-09-16 | 62 | 2021-09-22 | 4 | [15 empty] | 2021-09-22 | 2021-09-22 | 0 | 2021-09-22 | [7 empty] | 0 |  | 2022-01-05 | [15 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1156 | PGE | 94062 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.065 |  | 2021-06-18 | 2021-06-22 | 2 | 2022-03-16 | 186 | 2022-03-18 | 2 | [18 empty] | 2021-06-18 | [7 empty] | 0 | [5 empty] | 2022-03-18 | 2022-03-18 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-18 |  |  | 2022-03-18 |  | 2022-03-18 | 0 | 1//19
1157 | PGE | 95374 | NEM | EXPNEM | Commercial | Solar PV | 62.5 |  | 2021-06-18 | 2021-06-28 | 6 | 2021-07-01 | 9 | 2021-08-16 | 31 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | 2021-10-19 | 45 |  |  |  |  | 2021-06-18 | 2021-08-25 | 47 |  |  |  |  | 2021-11-01 | 2021-11-09 | 6 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-01 | 2021-11-01 | 0 | 2021-11-09 |  | 2021-11-10 | 1 | 1//19
1158 | PGE | 93722 | NEM | EXPNEM | Withdrawn | Solar PV | 42.054 |  | 2021-06-18 | 2021-06-24 | 4 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1159 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 103.603 |  | 2021-06-18 | 2021-06-30 | 8 | 2021-07-07 | 12 | 2021-07-23 | 12 | [15 empty] | 2021-07-28 | 2021-07-29 | 1 | 2021-07-29 | 2021-08-11 | 9 | [5 empty] | 0 | [5 empty] | 2021-12-13 | 2021-12-21 | 6 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-13 | 2021-12-14 | 1 | 2021-12-21 |  | 2021-12-24 | 3 | 1//19
1160 | PGE | 93654 | NEM | EXPNEM | Commercial | Solar PV | 34.179 |  | 2021-06-18 | 2021-06-28 | 6 | 2021-07-01 | 9 | 2021-07-08 | 4 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-08 | 0 | [5 empty] | 0 | [5 empty] | 2021-09-27 | 2021-10-04 | 5 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-27 | 2021-10-04 | 5 | 2021-10-04 |  | 2021-10-05 | 1 | 1//19
1161 | PGE | 94022 | NEM | EXPNEM | IA in Progress | Solar PV | 83.436 |  | 2021-06-20 | 2021-06-23 | 2 | 2021-07-02 | 9 | 2021-07-22 | 13 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | [6 empty] | 2021-06-20 | 2021-07-30 | 28 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1162 | PGE | 94957 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.486 |  | 2021-06-21 | 2021-06-23 | 2 | 2021-06-23 | 2 | 2021-06-23 | 0 | [18 empty] | 2021-06-21 | [7 empty] | 0 | [5 empty] | 2021-06-25 | 2021-06-25 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-06-25 |  |  | 2021-06-25 |  | 2021-06-25 | 0 | 1//19
1163 | PGE | 94040 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.173 |  | 2021-06-21 | 2021-06-24 | 3 | 2021-06-24 | 3 | 2021-06-25 | 1 | [18 empty] | 2021-06-21 | [7 empty] | 0 | [5 empty] | 2021-06-29 | 2021-06-29 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-06-29 |  |  | 2021-06-29 |  | 2021-06-29 | 0 | 1//19
1164 | PGE | 95688 | NEM | EXPNEM | Commercial | Solar PV | 52.163 |  | 2021-06-21 | 2021-06-23 | 2 | 2021-07-07 | 11 | 2021-07-20 | 9 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-10-19 | 64 |  |  |  |  | 2021-06-21 | 2021-08-13 | 38 |  |  |  |  | 2021-10-25 | 2021-11-01 | 5 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-25 | 2021-10-26 | 1 | 2021-11-01 |  | 2021-11-03 | 2 | 1//19
1165 | PGE | 95694 | NEM | EXPNEM | IA in Progress | Solar PV | 336 |  | 2021-06-21 | 2021-06-29 | 6 | 2021-07-13 | 15 | 2021-08-27 | 33 | [15 empty] | 2021-08-25 | 2021-08-27 | 2 | 2021-08-27 | [6 empty] | 2021-06-21 | 0 |  | 2021-08-13 | [15 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1166 | PGE | 93401 | NEM | VNEM | Withdrawn | Solar PV | 49.692 |  | 2021-06-21 | 2021-07-06 | 10 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1167 | PGE | 95030 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 42.01 |  | 2021-06-21 | 2021-06-24 | 3 | 2021-08-12 | 37 | 2021-08-18 | 4 | [18 empty] | 2021-06-29 | [7 empty] | 0 | [5 empty] | 2021-08-18 | 2021-08-23 | 3 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-18 | 2021-08-19 | 1 | 2021-08-23 |  | 2021-08-25 | 2 | 1//19
1168 | PGE | 95377 | NEM | EXPNEM | IA in Progress | Solar PV | 428.274 |  | 2021-06-21 | 2021-06-24 | 3 | 2021-08-16 | 39 | 2021-09-07 | 15 | 2021-09-07 | 2021-10-05 | 20 | 2021-10-08 | 2021-11-01 | 16 | 2021-11-01 | [8 empty] | 2021-11-01 | 2021-11-10 | 7 | 2021-11-10 | [6 empty] | 2021-06-21 | 2021-08-27 | 48 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1169 | PGE | 95207 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 163.772 |  | 2021-06-22 | 2021-06-24 | 2 | 2021-09-17 | 61 | 2021-11-08 | 36 | [15 empty] | 2021-11-08 | 2021-11-08 | 0 | 2021-11-08 | 2021-11-17 | 6 |  |  |  |  | 2021-06-22 | 0 |  | 2022-01-25 | 2022-01-25 | 2022-02-07 | 0 |  |  |  | 2021-09-27 | 2021-12-03 | 46 |  |  |  | 2021-12-03 | 2021-12-03 | 1 | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1170 | PGE | 94565 | NEM | EXPNEM | IA in Progress | Solar PV | 293.899 |  | 2021-06-22 | 2021-06-25 | 3 | 2021-06-25 | 3 | 2021-07-15 | 13 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2022-01-21 | 131 |  |  |  |  | 2021-06-22 | 2021-08-13 | 37 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1171 | PGE | 94024 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.47 |  | 2021-06-22 | 2021-06-25 | 3 | 2021-09-22 | 64 | 2021-09-24 | 2 | [18 empty] | 2021-07-13 | [7 empty] | 0 | [5 empty] | 2021-09-27 | 2021-09-28 | 1 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-27 | 2021-09-28 | 1 | 2021-09-28 |  | 2021-09-29 | 1 | 1//19
1172 | PGE | 95439 | NEM | EXPNEM | Withdrawn | Solar PV | 37.2 |  | 2021-06-22 | 2021-06-29 | 5 | 2021-07-09 | 12 | 2021-08-06 | 20 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | 2021-08-26 | 14 | [5 empty] | 0 | [5 empty] | 2022-02-01 | [11 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-01 | 2022-02-01 | 0 |  |  |  |  | 1//19
1173 | PGE | 95965 | Non-NEM | Continuous Uncompensated Export | Implementation | ENGN, Micro Turbine | 130 |  | 2021-06-22 | 2021-06-22 | 0 | 2021-07-07 | 10 | 2021-09-21 | 53 | [15 empty] | 2021-10-25 | 2021-10-27 | 2 | 2021-10-27 | 2022-01-26 | 61 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1174 | PGE | 94028 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.12 |  | 2021-06-22 | 2021-06-28 | 4 | 2022-03-17 | 185 | 2022-03-20 | 1 | [18 empty] | 2021-07-07 | [7 empty] | 0 | [5 empty] | 2022-03-20 | 2022-03-20 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-20 |  |  | 2022-03-20 |  | 2022-03-20 | 0 | 1//19
1175 | PGE | 95490 | Non-NEM | Non-Export | Implementation | ENGN, Storage | 830 |  | 2021-06-22 | 2021-06-23 | 1 | 2021-07-14 | 15 | 2021-11-15 | 86 | [15 empty] | 2021-11-15 | 2021-11-17 | 2 | 2021-11-17 | 2022-02-14 | 60 |  |  |  |  | 2021-06-22 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1176 | PGE | 93402 | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-06-22 | 2021-06-25 | 3 | 2021-08-13 | 37 | 2021-10-08 | 39 | [15 empty] | 2021-10-08 | 2021-10-08 | 0 | 2021-10-08 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1177 | PGE | 93308 | NEM | EXPNEM | Commercial | Solar PV | 47.431 |  | 2021-06-23 | 2021-06-28 | 3 | 2021-07-07 | 9 | 2021-07-22 | 11 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | 2021-08-05 | 10 | [5 empty] | 0 | [5 empty] | 2021-08-05 | 2021-08-12 | 5 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-05 | 2021-08-05 | 0 | 2021-08-12 |  | 2021-08-18 | 4 | 1//19
1178 | PGE | 95336 | Non-NEM | Non-Export | Withdrawn | Solar PV | 420 |  | 2021-06-23 | 2021-06-23 | 0 | 2021-06-30 | 5 | [28 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1180 | PGE | 95620 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-06-23 | 2021-06-28 | 3 | 2021-07-14 | 14 | 2021-07-20 | 4 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-10-15 | 62 |  |  |  |  | 2021-06-23 | 2021-07-15 | 15 |  |  |  |  | 2021-10-21 | 2021-11-04 | 10 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-21 | 2021-11-01 | 7 | 2021-11-04 |  | 2021-11-10 | 4 | 1//19
1181 | PGE | 93206 | NEM | EXPNEM | Application Accepted | Solar PV | 62.5 |  | 2021-06-23 | 2021-07-01 | 6 | 2021-07-14 | 14 | 2021-07-26 | 8 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | [6 empty] | 2022-03-14 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1183 | PGE | 95376 | NEM | EXPNEM | Commercial | Solar PV | 129.6 |  | 2021-06-23 | 2021-06-29 | 4 | 2021-07-08 | 10 | 2021-08-18 | 29 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | 2021-09-07 | 13 | [5 empty] | 0 | [5 empty] | 2021-12-15 | 2021-12-23 | 6 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-15 | 2021-12-15 | 0 | 2021-12-23 |  | 2021-12-28 | 3 | 1//19
1184 | PGE | 95603 | NEM | EXPNEM | Commercial | Solar PV | 36 |  | 2021-06-24 | 2021-06-30 | 4 | 2021-08-04 | 28 | 2021-08-19 | 11 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-09-07 | 12 | [5 empty] | 0 | [5 empty] | 2022-03-07 | 2022-03-25 | 14 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-07 | 2022-03-08 | 1 | 2022-03-25 |  | 2022-03-30 | 3 | 1//19
1185 | PGE | 95360 | NEM | EXPNEM | Implementation | Solar PV | 500 |  | 2021-06-24 | 2021-07-07 | 8 | 2021-07-15 | 14 | 2021-08-12 | 20 | [15 empty] | 2021-08-23 | 2021-09-10 | 13 | 2021-09-10 | 2021-09-10 | 0 |  |  |  |  | 2021-06-24 | 0 |  | 2021-08-05 | [6 empty] | 2021-09-24 | 2022-02-24 | 105 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1186 | PGE | 96007 | Non-NEM | Non-Export | Implementation | ENGN, Storage | 170 |  | 2021-06-24 | 2021-06-24 | 0 | 2021-07-21 | 18 | 2021-09-17 | 41 | [15 empty] | 2021-09-17 | 2021-10-05 | 12 | 2021-10-05 | 2021-10-14 | 7 |  |  |  |  | 2021-06-24 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1187 | PGE | 95070 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.195 |  | 2021-06-24 | 2021-06-30 | 4 | 2021-09-13 | 55 | 2021-09-14 | 1 | [18 empty] | 2021-06-30 | [7 empty] | 0 | [5 empty] | 2021-09-14 | 2021-09-14 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-14 |  |  | 2021-09-14 |  | 2021-09-14 | 0 | 1//19
1188 | PGE | 94062 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 35.12 |  | 2021-06-25 | 2021-07-08 | 8 | 2021-10-29 | 88 | 2021-11-03 | 3 | [18 empty] | 2021-07-30 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1189 | PGE | 93291 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 423.302 |  | 2021-06-17 | 2021-06-28 | 7 | 2021-07-21 | 23 | [5 empty] | 2021-09-08 | 2021-10-05 | 19 | 2021-10-05 | 2021-12-10 | 45 | 2022-01-31 |  |  | 2021-12-10 | 2021-12-10 | 0 | [10 empty] | 2021-06-25 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1190 | PGE | 93245 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-06-25 | 2021-06-30 | 3 | 2021-07-19 | 15 | 2021-07-23 | 4 | [15 empty] | 2021-07-23 | 2021-07-23 | 0 | 2021-07-23 | 2021-08-26 | 24 |  |  |  |  | 2021-06-25 | 0 | [5 empty] | 2021-12-07 | 2021-12-16 | 7 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-07 | 2021-12-08 | 1 | 2021-12-16 |  | 2021-12-17 | 1 | 1//19
1191 | PGE | 95497 | NEM | EXPNEM | IA in Progress | Solar PV | 38.018 |  | 2021-06-25 | 2021-06-29 | 2 | 2021-11-12 | 97 | 2021-11-29 | 9 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2021-12-10 | 9 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1192 | PGE | 95746 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 30.464 |  | 2021-06-25 | 2021-07-07 | 7 | 2021-07-09 | 9 | 2021-07-12 | 1 | [15 empty] | 2021-06-25 | 2021-07-07 | 7 | 2021-07-07 | 2021-07-13 | 4 |  |  |  |  | 2021-06-25 | 0 | [5 empty] | 2021-07-13 | 2021-07-13 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13 |  |  |  | 1//19
1193 | PGE | 93635 | NEM | EXPNEM | IA in Progress | Solar PV | 395.854 |  | 2021-06-25 | 2021-06-30 | 3 | 2021-07-26 | 20 | 2021-08-09 | 10 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-23 | 10 |  |  |  |  | 2021-06-25 | 2021-08-05 | 28 | [7 empty] | 2021-10-21 | 2022-01-04 | 49 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1194 | PGE | 95501 | Non-NEM | Non-Export | Commercial | Storage | 490 |  | 2021-06-25 | 2021-06-25 | 0 | 2021-07-21 | 17 | 2021-12-03 | 93 | 2021-12-22 | 2022-02-16 | 39 | [12 empty] | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16 | 2022-02-22 | 3 |  |  |  |  | 2021-06-25 | 0 | [5 empty] | 2022-03-07 | 2022-03-17 | 8 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-07 | 2022-03-11 | 4 | 2022-03-17 |  | 2022-03-18 | 1 | 1//19
1195 | PGE | 95124 | NEM | EXPNEM | Implementation | Solar PV | 56.324 |  | 2021-06-25 | 2021-07-02 | 5 | 2021-07-02 | 5 | 2021-07-20 | 11 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-07-26 | 4 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1196 | PGE | 93458 | NEM | EXPNEM | Commercial | Solar PV | 45.384 |  | 2021-06-25 | 2021-07-02 | 5 | 2021-07-15 | 13 | 2021-07-27 | 8 | [15 empty] | 2021-07-27 | 2021-07-30 | 3 | 2021-07-30 | 2021-08-06 | 5 |  |  |  |  | 2021-06-25 | 0 |  | 2021-07-23 |  |  |  | 2021-11-29 | 2021-12-14 | 11 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-29 | 2021-11-30 | 1 | 2021-12-14 |  | 2021-12-15 | 1 | 1//19
1197 | PGE | 93615 | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-06-28 | 2021-06-30 | 2 | 2021-07-01 | 3 | 2021-07-07 | 3 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | 2021-10-06 | 64 |  |  |  |  | 2021-06-28 | 2021-08-06 | 28 | [7 empty] | 2021-07-26 | 2021-12-12 | 96 |  |  |  |  | 2022-01-26 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1198 | PGE | 94556 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-06-28 | 2021-07-07 | 6 | 2021-07-07 | 6 | 2021-07-07 | 0 | [18 empty] | 2021-06-28 | [7 empty] | 0 | [5 empty] | 2021-07-08 | 2021-07-08 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-07-08 |  |  | 2021-07-08 |  | 2021-07-08 | 0 | 1//19
1199 | PGE | 95492 | NEM | EXPNEM | Commercial | Solar PV | 139.826 |  | 2021-06-28 | 2021-07-12 | 9 | 2021-11-02 | 89 | 2021-11-26 | 15 | [15 empty] | 2021-11-26 | 2021-11-26 | 0 | 2021-11-26 | 2021-11-30 | 1 |  |  |  |  | 2021-06-28 | 0 | [5 empty] | 2022-03-07 | 2022-03-16 | 7 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-07 | 2022-03-07 | 0 | 2022-03-16 |  | 2022-03-21 | 3 | 1//19
1200 | PGE | 94558 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-06-28 | 2021-06-30 | 2 | 2021-08-05 | 27 | 2021-08-20 | 11 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-20 | 2021-08-30 | 6 |  |  |  |  | 2021-06-28 | 2021-08-13 | 33 |  |  |  |  | 2021-10-28 | 2021-11-04 | 5 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-28 | 2021-10-28 | 0 | 2021-11-04 |  | 2021-11-04 | 0 | 1//19
1201 | PGE | 95422 | NEM | EXPNEM | Commercial | Solar PV | 145.153 |  | 2021-06-28 | 2021-06-30 | 2 | 2021-07-22 | 17 | 2021-08-12 | 15 | [15 empty] | 2021-08-12 | 2021-08-12 | 0 | 2021-08-12 | 2021-08-18 | 4 |  |  |  |  | 2021-06-28 | 2021-07-13 | 10 |  |  |  |  | 2022-02-04 | 2022-03-24 | 33 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-04 | 2022-03-09 | 22 | 2022-03-24 |  | 2022-03-28 | 2 | 1//19
1202 | PGE | 95492 | NEM | EXPNEM | IA in Progress | Solar PV | 627.287 |  | 2021-06-28 | 2021-07-13 | 10 | 2021-07-13 | 10 | 2021-08-31 | 35 | [15 empty] | 2021-08-31 | 2021-09-03 | 3 | 2021-09-03 | [6 empty] | 2021-06-28 | 0 | [8 empty] | 2021-11-17 | 2022-03-31 | 93 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1204 | PGE | 95215 | NEM | EXPNEM | IA in Progress | Solar PV | 72.441 |  | 2021-06-29 | 2021-07-01 | 2 | 2021-07-15 | 11 | 2021-09-02 | 35 | 2021-09-02 | 2021-10-01 | 20 | 2021-11-08 | 2021-12-06 | 17 | 2021-12-06 | 2021-12-06 |  | 2021-12-06 | 2022-03-22 | 77 | 2021-12-06 |  |  | 2022-03-22 | 2022-03-24 | 2 | 2022-03-24 | [6 empty] | 2021-06-29 | 2021-09-07 | 48 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1205 | PGE | 95695 | NEM | EXPNEM | Commercial | Solar PV | 52.163 |  | 2021-06-29 | 2021-07-06 | 4 | 2021-07-06 | 4 | 2021-07-20 | 10 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-10-22 | 67 |  |  |  |  | 2021-06-29 | 2021-07-23 | 17 |  |  |  |  | 2021-11-05 | 2021-11-12 | 4 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-05 | 2021-11-05 | 0 | 2021-11-12 |  | 2021-11-19 | 5 | 1//19
1206 | PGE | 95219 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-06-29 | 2021-07-09 | 7 | 2021-07-12 | 8 | 2021-08-05 | 18 | [15 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | 2021-08-06 | 1 | [5 empty] | 0 | [5 empty] | 2021-12-28 | 2022-01-05 | 6 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-28 | 2021-12-28 | 0 | 2022-01-05 |  | 2022-01-05 | 0 | 1//19
1207 | PGE | 94551 | NEM | EXPNEM | Commercial | Solar PV | 126.998 |  | 2021-06-29 | 2021-07-06 | 4 | 2021-07-13 | 9 | 2021-08-10 | 20 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-10 | 2022-01-13 | 108 |  |  |  |  | 2021-06-29 | 2021-07-19 | 13 |  |  |  |  | 2022-01-19 | 2022-01-28 | 7 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-19 | 2022-01-20 | 1 | 2022-01-28 |  | 2022-02-03 | 4 | 1//19
1208 | PGE | 94520 | NEM | EXPNEM | Implementation | Solar PV | 600 |  | 2021-06-29 | 2021-07-12 | 8 | 2021-07-15 | 11 | 2021-07-27 | 8 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-11-04 | 71 |  |  |  |  | 2021-06-29 | 2021-07-19 | 13 |  |  |  |  | 2021-11-04 | 2021-11-16 | 7 | 2021-09-21 | 2021-09-21 | 0 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-04 | 2021-11-05 | 1 | 2021-11-16 | 2021-11-18 |  | 2 | 1//19 |  | 99
1209 | PGE | 95407 | NEM | EXPNEM | Withdrawn | Solar PV | 57.443 |  | 2021-06-29 | 2021-07-07 | 5 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1210 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-06-29 | 2021-07-14 | 10 | 2021-07-14 | 10 | 2021-07-30 | 12 | [15 empty] | 2021-07-30 | 2021-08-02 | 1 | 2021-08-02 | 2021-08-02 | 0 |  |  |  |  | 2021-06-29 | 0 |  | 2021-07-28 |  |  |  | 2021-12-14 | 2021-12-22 | 6 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-14 | 2021-12-14 | 0 | 2021-12-22 |  | 2021-12-22 | 0 | 1//19
1211 | PGE | 93610 | NEM | EXPNEM | Implementation | Solar PV | 500 |  | 2021-06-29 | 2021-07-14 | 10 | 2021-09-17 | 56 | 2021-10-08 | 15 | [15 empty] | 2021-10-08 | 2021-10-08 | 0 | 2021-10-08 | 2021-10-13 | 3 | [5 empty] | 0 | [8 empty] | 2021-11-04 |  | 110 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1212 | PGE | 93722 | NEM | EXPNEM | Commercial | Solar PV | 31.909 |  | 2021-06-29 | 2021-07-07 | 5 | 2021-07-15 | 11 | 2021-07-20 | 3 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-09-07 | 34 | [5 empty] | 0 | [5 empty] | 2021-09-17 | 2021-09-30 | 9 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-17 | 2021-09-24 | 5 | 2021-09-30 |  | 2021-10-07 | 5 | 1//19
1213 | PGE | 95126 | NEM | EXPNEM | Commercial | Solar PV | 30.23 |  | 2021-06-29 | 2021-07-07 | 5 | 2021-11-15 | 96 | 2021-12-02 | 11 | [15 empty] | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02 | 2022-01-11 | 28 | [5 empty] | 0 | [5 empty] | 2022-01-26 | 2022-02-03 | 6 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-26 | 2022-01-26 | 0 | 2022-02-03 |  | 2022-02-09 | 4 | 1//19
1214 | PGE | 94558 | NEM | EXPNEM | Commercial | Solar PV | 129.827 |  | 2021-06-29 | 2021-07-13 | 9 | 2021-07-30 | 22 | 2021-08-19 | 14 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-09-07 | 12 | [5 empty] | 0 | [5 empty] | 2021-09-23 | 2021-10-07 | 10 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-23 | 2021-10-01 | 6 | 2021-10-07 |  | 2021-10-14 | 5 | 1//19
1215 | PGE | 95361 | NEM | EXPNEM | Withdrawn | Solar PV | 38.78 |  | 2021-06-30 | 2021-07-14 | 9 | 2021-08-21 | 36 | 2021-09-08 | 11 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-10-20 | 30 |  |  |  |  | 2021-06-30 | 2021-09-10 | 50 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1216 | PGE | 95030 | NEM | EXPNEM | IA in Progress | Solar PV | 549.991 |  | 2021-06-30 | 2021-07-08 | 5 | 2021-08-03 | 23 | 2021-09-08 | 25 | 2021-09-08 | 2021-09-27 | 13 | 2021-10-04 | 2021-11-03 | 22 | 2021-11-03 | 2021-11-10 | 5 | 2021-11-10 | 2022-02-10 | 67 | 2021-11-10 |  |  | 2022-02-10 | 2022-02-11 | 1 | 2022-02-11 | [6 empty] | 2021-06-30 | 2021-07-28 | 19 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1217 | PGE | 95422 | NEM | EXPNEM | Commercial | Solar PV | 131.105 |  | 2021-06-30 | 2021-07-08 | 5 | 2021-08-18 | 34 | 2021-09-03 | 12 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-11-05 | 44 |  |  |  |  | 2021-06-30 | 0 | [5 empty] | 2022-02-04 | 2022-02-25 | 14 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-04 | 2022-02-07 | 1 | 2022-02-25 |  | 2022-03-02 | 3 | 1//19
1218 | PGE | 95070 | NEM | EXPNEM | IA in Progress | Solar PV | 240 |  | 2021-06-30 | 2021-07-08 | 5 | 2021-07-13 | 8 | 2021-07-29 | 12 | [15 empty] | 2021-07-29 | 2021-07-29 | 0 | 2021-07-29 | 2021-08-11 | 9 |  |  |  |  | 2021-06-30 | 2021-08-06 | 26 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1219 | PGE | 95401 | NEM | EXPNEM | Withdrawn | Solar PV | 381.322 |  | 2021-06-30 | 2021-07-09 | 6 | 2021-08-16 | 32 | 2021-09-03 | 14 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | [6 empty] | 2021-08-16 | 2021-08-27 | 9 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1220 | PGE | 95131 | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-03-12 | 2021-03-23 | 7 | 2021-06-16 | 67 | 2021-07-23 | 26 | [15 empty] | 2021-07-23 | 2021-07-23 | 0 | 2021-07-23 | 2022-03-14 | 160 |  |  |  |  | 2021-03-12 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1221 | PGE | 95614 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 34.2 |  | 2021-03-22 | 2021-04-05 | 10 | 2021-04-07 | 12 | 2021-04-09 | 2 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1222 | PGE | 93446 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-04-09 | 2021-04-22 | 9 | 2021-10-15 | 132 | 2021-11-21 | 24 | [15 empty] | 2021-11-21 | 2021-11-21 | 0 | 2021-11-21 | 2022-03-17 | 79 |  |  |  |  | 2021-08-26 | 0 | [5 empty] | 2022-03-18 | 2022-03-30 | 8 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-18 | 2022-03-21 | 1 | 2022-03-30 |  |  |  | 1//19
1223 | PGE | 93401 | NEM | NEMMT | Application Review in Progress | ENGN, Solar PV | 625 |  | 2021-06-10 | 2021-06-23 | 9 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1224 | PGE | 93308 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-06-11 | 2021-07-16 | 24 | 2021-08-17 | 46 | 2021-08-20 | 3 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-20 | 2021-08-23 | 1 | [5 empty] | 0 | [5 empty] | 2021-08-23 | 2021-08-30 | 5 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-23 | 2021-08-23 | 0 | 2021-08-30 |  | 2021-09-07 | 5 | 1//19
1225 | PGE | 93636 | NEM | EXPNEM | Withdrawn | Solar PV | 36.133 |  | 2021-06-22 | 2021-07-07 | 10 | [22 empty] | 2021-06-22 | [6 empty] | 2021-06-22 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1226 | PGE | 93635 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-06-28 | 2021-06-29 | 1 | 2021-07-28 | 21 | 2021-09-02 | 26 | [15 empty] | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02 | 2021-09-08 | 3 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1227 | PGE | 93249 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-06-30 | 2021-07-01 | 1 | 2021-07-28 | 19 | 2021-08-26 | 21 | [15 empty] | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | 2021-09-05 | 6 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1228 | PGE | 94560 | Non-NEM | Non-Export | Implementation | Storage | 96 |  | 2021-07-01 | 2021-07-07 | 3 | 2021-07-07 | 3 | 2021-08-03 | 19 | 2021-08-12 | 2021-10-07 | 39 | [12 empty] | 2021-12-06 | 2021-12-07 | 1 | 2021-12-07 | 2022-03-10 | 65 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1229 | PGE | 93230 | NEM | EXPNEM | Commercial | Solar PV | 37.006 |  | 2021-07-01 | 2021-07-14 | 8 | 2021-07-22 | 14 | 2021-08-09 | 12 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-11 | 2 |  |  |  |  | 2021-07-01 | 2021-07-29 | 19 |  |  |  |  | 2021-08-13 | 2021-08-27 | 10 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-13 | 2021-08-16 | 1 | 2021-08-27 |  | 2021-08-27 | 0 | 1//19
1230 | PGE | 93652 | NEM | EXPNEM | Commercial | Solar PV | 250 |  | 2021-07-01 | 2021-07-15 | 9 | 2021-07-21 | 13 | 2021-08-09 | 13 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-12-22 | 93 |  |  |  |  | 2021-07-01 | 2021-07-29 | 19 |  |  |  |  | 2022-01-24 | 2022-02-03 | 8 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-24 | 2022-01-24 | 0 | 2022-02-03 |  | 2022-02-04 | 1 | 1//19
1231 | PGE | 95619 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 36.387 |  | 2021-07-01 | 2021-07-06 | 2 | 2021-07-09 | 5 | 2021-07-13 | 2 | [15 empty] | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01 | 2021-07-01 | 0 |  |  |  |  | 2021-07-01 | 0 | [8 empty] | 2021-08-16 | 2022-03-08 | 141 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1232 | PGE | 93727 | Non-NEM | Non-Export | Implementation | ENGN | 1429 |  | 2021-07-01 | 2021-07-16 | 10 | 2021-08-04 | 23 | 2021-10-22 | 56 | [15 empty] | 2021-11-15 | 2021-11-17 | 2 | 2021-11-17 | 2021-12-22 | 23 | [5 empty] | 0 | [11 empty] | 2022-03-01 |  | 23 |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1233 | PGE | 95602 | NEM | EXPNEM | Application Submitted | Solar PV | 52.2 |  | 2021-07-01 | 2021-07-16 | 10 | [22 empty] | 2021-07-01 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1234 | PGE | 94960 | NEM | EXPNEM | Withdrawn | Solar PV | 76.547 |  | 2021-07-01 | 2021-07-13 | 7 | 2021-08-03 | 22 | 2021-08-23 | 14 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1235 | PGE | 94506 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-07-02 | 2021-07-14 | 7 | 2021-08-10 | 26 | 2021-08-10 | 0 | [18 empty] | 2021-07-02 | [6 empty] | 2021-07-02 | 2021-08-30 | 40 |  |  |  |  | 2021-08-30 | 2021-09-08 | 6 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-30 | 2021-08-30 | 0 | 2021-09-08 |  | 2021-09-09 | 1 | 1//19
1236 | PGE | 95112 | NEM | EXPNEM | IA in Progress | Solar PV | 192 |  | 2021-07-02 | 2021-07-13 | 6 | 2021-07-14 | 7 | 2021-09-07 | 38 | [15 empty] | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-09-08 | 1 |  |  |  |  | 2021-07-02 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1237 | PGE | 95648 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 998.26 |  | 2021-07-02 | 2021-07-19 | 10 | 2021-08-04 | 22 | 2021-09-08 | 24 | [15 empty] | 2021-09-08 | 2021-09-23 | 11 | 2021-09-23 | 2021-10-04 | 7 | [5 empty] | 0 | [5 empty] | 2021-11-15 | 2022-03-13 | 80 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-15 | 2022-02-28 | 71 | 2022-03-13 |  | 2022-03-14 | 0 | 1//19
1238 | PGE | 95667 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-07-02 | 2021-07-15 | 8 | 2021-07-30 | 19 | 2021-08-30 | 21 | [15 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-09-01 | 2 |  |  |  |  | 2021-07-02 | 0 | [5 empty] | 2021-10-19 | 2021-10-29 | 8 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-19 | 2021-10-20 | 1 | 2021-10-29 |  | 2021-10-29 | 0 | 1//19
1239 | PGE | 93313 | NEM | EXPNEM | Implementation | Solar PV | 816 |  | 2021-07-02 | 2021-07-16 | 9 | 2021-07-23 | 14 | 2021-08-09 | 11 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-23 | 10 | [5 empty] | 0 | [8 empty] | 2022-02-02 | 2022-02-15 | 9 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1240 | PGE | 94027 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 306.642 |  | 2021-07-02 | 2021-07-19 | 10 | 2022-01-10 | 131 | 2022-02-01 | 15 | [15 empty] | 2022-02-01 | 2022-02-01 | 0 | 2022-02-01 | [7 empty] | 0 |  | 2022-02-24 | [15 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1241 | PGE | 95969 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.4 |  | 2021-07-05 | 2021-07-15 | 7 | 2021-08-06 | 23 | 2021-08-10 | 2 | [18 empty] | 2021-07-27 | [7 empty] | 0 | [5 empty] | 2021-08-10 | 2021-08-10 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-10 |  |  | 2021-08-10 |  | 2021-08-10 | 0 | 1//19
1242 | PGE | 93635 | NEM | EXPNEM | Withdrawn | Solar PV | 181.47 |  | 2021-07-05 | 2021-07-16 | 8 | 2021-07-22 | 12 | [27 empty] | 2021-07-05 | 2021-08-09 | 24 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1243 | PGE | 95620 | NEM | EXPNEM | IA in Progress | Solar PV | 34.179 |  | 2021-07-05 | 2021-07-16 | 8 | 2022-01-12 | 132 | 2022-01-31 | 12 | [15 empty] | 2022-01-31 | 2022-02-03 | 3 | 2022-02-03 | [6 empty] | 2021-07-05 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1244 | PGE | 95230 | NEM | EXPNEM | Implementation | Solar PV | 375 |  | 2021-07-05 | 2021-07-19 | 9 | 2021-08-05 | 22 | 2021-08-18 | 9 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | 2021-09-07 | 13 |  |  |  |  | 2021-07-05 | 2021-08-18 | 31 |  |  |  |  | 2022-03-28 |  |  | 2021-10-22 | 2021-11-24 | 22 |  |  |  | 2022-02-26 | 2022-02-18 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-28 | 2022-03-30 | 2 |  |  |  |  | 1//19
1245 | PGE | 95030 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.232 |  | 2021-07-06 | 2021-07-15 | 7 | 2021-07-15 | 7 | 2021-07-19 | 2 | [18 empty] | 2021-07-06 | [7 empty] | 0 | [5 empty] | 2021-07-20 | 2021-07-22 | 2 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-07-20 | 2021-07-20 | 0 | 2021-07-22 |  | 2021-07-26 | 2 | 1//19
1246 | PGE | 95423 | NEM | EXPNEM | Implementation | Solar PV | 31.381 |  | 2021-07-06 | 2021-07-19 | 9 | 2021-10-06 | 65 | 2021-10-21 | 11 | [15 empty] | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21 | 2021-11-04 | 10 |  |  |  |  | 2021-07-06 | 0 | [5 empty] | 2022-01-14 | 2022-03-31 | 52 | 2021-12-01 | 2022-04-05 | 88 |  |  |  | 2022-04-05 |  | 6 | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-14 | 2022-03-23 | 46 | 2022-03-31 |  |  |  | 1//19
1247 | PGE | 96022 | NEM | EXPNEM | Implementation | Solar PV | 51.589 |  | 2021-07-06 | 2021-07-13 | 5 | 2021-09-13 | 48 | 2021-10-04 | 15 | [15 empty] | 2021-10-04 | 2021-10-25 | 15 | 2021-10-25 | 2021-11-16 | 15 |  |  |  |  | 2021-07-06 | 2021-09-07 | 44 | [7 empty] | 2021-12-17 |  | 82 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1248 | PGE | 93401 | Non-NEM | Non-Export | Implementation | Storage | 643.5 |  | 2021-07-06 | 2021-07-07 | 1 | 2021-07-28 | 16 | 2021-09-30 | 45 | [15 empty] | 2021-07-30 | 2021-07-30 | 0 | 2021-07-30 | 2021-10-27 | 62 |  |  |  |  | 2021-07-06 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1249 | PGE | 93635 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-07-06 | 2021-07-20 | 10 | 2021-09-20 | 53 | [17 empty] | 2021-09-24 | 2021-10-05 | 7 | 2021-10-05 | 2021-11-30 | 37 |  |  |  |  | 2021-07-06 | 2021-08-27 | 38 |  |  |  |  | 2021-12-02 | 2021-12-08 | 4 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-02 | 2021-12-03 | 1 | 2021-12-08 |  | 2021-12-09 | 1 | 1//19
1250 | PGE | 95123 | NEM | EXPNEM | Implementation | Solar PV | 86.4 |  | 2021-07-06 | 2021-07-20 | 10 | 2021-09-08 | 45 | 2021-09-29 | 15 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | 2021-10-28 | 21 |  |  |  |  | 2021-07-06 | 0 |  | 2022-02-03 | 2022-02-07 | 2022-02-07 | 2 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1251 | PGE | 95123 | NEM | EXPNEM | Implementation | Solar PV | 86.4 |  | 2021-07-06 | 2021-07-20 | 10 | 2021-09-25 | 57 | 2021-10-15 | 14 | [15 empty] | 2021-10-15 | 2021-10-15 | 0 | 2021-10-15 | 2021-10-28 | 9 |  |  |  |  | 2021-07-06 | 0 |  | 2022-02-04 | 2022-02-07 | 2022-02-07 | 1 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1252 | PGE | 95123 | NEM | EXPNEM | Implementation | Solar PV | 73.256 |  | 2021-07-06 | 2021-07-20 | 10 | 2021-09-25 | 57 | 2021-10-15 | 14 | [15 empty] | 2021-10-15 | 2021-10-15 | 0 | 2021-10-15 | 2021-10-28 | 9 |  |  |  |  | 2021-07-06 | 0 |  | 2022-02-04 | 2022-02-07 | 2022-02-07 | 1 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1253 | PGE | 95033 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.987 |  | 2021-07-06 | 2021-07-13 | 5 | 2021-07-22 | 12 | 2021-08-04 | 9 | [15 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | 2021-08-09 | 3 |  |  |  |  | 2021-07-06 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-07-29 |  | 2021-08-09 | 8 | 1//19
1254 | PGE | 93630 | NEM | EXPNEM | Implementation | Solar PV | 180 |  | 2021-07-06 | 2021-07-09 | 3 | 2021-07-20 | 10 | 2021-08-02 | 9 | 2021-08-02 | 2021-08-30 | 20 | [12 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-10-21 | 37 |  |  |  |  | 2021-07-06 | 2021-07-28 | 16 | [7 empty] | 2021-11-15 |  | 104 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1255 | PGE | 94303 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 48.827 |  | 2021-07-06 | 2021-07-19 | 9 | 2021-08-09 | 24 | 2021-08-27 | 14 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | [6 empty] | 2021-07-06 | 0 |  |  | 2021-10-01 | 2021-10-15 | 10 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1256 | PGE | 94806 | NEM | VNEM | Implementation | Solar PV | 35.67 |  | 2021-07-07 | 2021-07-21 | 10 | 2021-08-06 | 22 | 2021-08-27 | 15 | [15 empty] | 2021-08-27 | 2021-09-20 | 15 | 2021-09-20 | 2021-12-22 | 64 |  |  |  |  | 2021-07-07 | 0 |  |  | 2021-11-04 | 2021-11-04 | 0 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1257 | PGE | 94806 | NEM | VNEM | Implementation | Solar PV | 35.38 |  | 2021-07-07 | 2021-07-21 | 10 | 2021-08-06 | 22 | 2021-08-27 | 15 | [15 empty] | 2021-08-27 | 2021-09-20 | 15 | 2021-09-20 | 2021-12-22 | 64 |  |  |  |  | 2021-07-07 | 0 |  |  | 2021-11-04 | 2021-11-04 | 0 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1258 | PGE | 94806 | NEM | VNEM | IA in Progress | Solar PV | 35.67 |  | 2021-07-07 | 2021-07-21 | 10 | 2021-08-06 | 22 | 2021-08-27 | 15 | [15 empty] | 2021-08-27 | 2021-09-20 | 15 | 2021-09-20 | [6 empty] | 2021-07-07 | 0 |  |  | 2021-11-04 | 2021-11-04 | 0 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1259 | PGE | 94806 | NEM | VNEM | IA in Progress | Solar PV | 53.36 |  | 2021-07-07 | 2021-07-21 | 10 | 2021-08-06 | 22 | 2021-08-27 | 15 | [15 empty] | 2021-08-27 | 2021-09-20 | 15 | 2021-09-20 | [6 empty] | 2021-07-07 | 0 |  |  | 2021-11-04 | 2021-11-04 | 0 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1260 | PGE | 95401 | NEM | VNEMSOMAH | Implementation | Solar PV | 63.292 |  | 2021-07-07 | 2021-07-13 | 4 | 2021-07-26 | 13 | 2021-08-16 | 15 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | 2022-03-09 | 141 |  |  |  |  | 2021-07-07 | 0 |  | 2021-08-06 | [15 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1261 | PGE | 95401 | NEM | VNEMSOMAH | Implementation | Solar PV | 62.872 |  | 2021-07-07 | 2021-07-13 | 4 | 2021-07-26 | 13 | 2021-08-16 | 15 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | 2022-03-09 | 141 |  |  |  |  | 2021-07-07 | 0 |  | 2021-08-06 | [15 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1262 | PGE | 93230 | NEM | EXPNEM | Implementation | Solar PV | 120 |  | 2021-07-07 | 2021-07-13 | 4 | 2021-08-05 | 21 | [17 empty] | 2021-08-17 | 2021-08-17 | 0 | 2021-08-17 | 2021-11-03 | 55 |  |  |  |  | 2021-07-07 | 0 |  | 2021-07-23 | [15 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1263 | PGE | 95926 | NEM | EXPNEM | IA in Progress | Solar PV | 83.3 |  | 2021-07-07 | 2021-07-13 | 4 | 2021-08-09 | 23 | [5 empty] | 2021-08-09 | 2021-09-17 | 28 | 2021-09-17 | 2021-09-17 |  | 2021-09-17 | 2021-11-23 | 48 | 2021-09-17 | [13 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1264 | PGE | 93646 | NEM | EXPNEM | Implementation | Solar PV | 139.15 |  | 2021-07-07 | 2021-07-19 | 8 | 2021-10-11 | 67 | 2021-10-21 | 8 | [15 empty] | 2021-10-21 | 2021-10-25 | 2 | 2021-10-25 | 2021-10-27 | 2 |  |  |  |  | 2021-07-23 | 2021-08-04 | 8 | 2021-10-14 | [6 empty] | 2021-11-15 | 2022-02-25 | 71 |  |  |  | 2022-04-12 |  | 1 | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1265 | PGE | 95457 | NEM | EXPNEM | Commercial | Solar PV | 434.952 |  | 2021-07-07 | 2021-07-13 | 4 | 2021-07-21 | 10 | 2021-08-25 | 25 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | 2021-09-08 | 9 |  |  |  |  | 2021-07-07 | 2021-07-29 | 16 |  |  |  |  | 2022-02-07 | 2022-02-25 | 13 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-07 | 2022-02-07 | 0 | 2022-02-25 |  | 2022-02-28 | 1 | 1//19
1266 | PGE | 94062 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.545 |  | 2021-07-07 | 2021-07-16 | 7 | [22 empty] | 2021-07-07 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1267 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 37.598 |  | 2021-07-07 | 2021-07-20 | 9 | 2021-08-02 | 18 | 2021-08-23 | 15 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23 | 2022-01-27 | 108 |  |  |  |  | 2021-07-07 | 2021-08-13 | 27 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1268 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 63.182 |  | 2021-07-07 | 2021-07-20 | 9 | 2021-08-02 | 18 | 2021-11-05 | 68 | [15 empty] | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05 | 2022-01-27 | 55 |  |  |  |  | 2021-07-07 | 2021-09-10 | 46 |  | 2021-09-24 | 2021-09-24 | 0 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1269 | PGE | 95008 | NEM | VNEMSOMAH | Implementation | Solar PV | 75.43 |  | 2021-07-07 | 2021-07-16 | 7 | 2021-07-26 | 13 | 2021-09-13 | 34 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-12-13 | 62 |  |  |  |  | 2021-07-07 | 0 |  | 2021-08-06 | [15 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1270 | PGE | 95008 | NEM | VNEMSOMAH | Implementation | Solar PV | 66.259 |  | 2021-07-07 | 2021-07-16 | 7 | 2021-07-26 | 13 | 2021-08-16 | 15 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | 2021-12-13 | 81 |  |  |  |  | 2021-07-07 | 0 |  | 2021-08-06 | [15 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1271 | PGE | 94115 | Non-NEM | Continuous Uncompensated Export | Commercial | ENGN, Solar PV | 66.6 |  | 2021-07-07 | 2021-07-08 | 1 | 2021-07-14 | 5 | 2021-09-27 | 52 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-26 | 21 | [5 empty] | 0 | [5 empty] | 2021-10-29 | 2021-11-03 | 3 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-29 | 2021-10-30 | 0 | 2021-11-03 |  | 2021-11-03 | 0 | 1//19
1272 | PGE | 94028 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 38.27 |  | 2021-07-07 | 2021-07-16 | 7 | 2022-01-18 | 134 | 2022-01-21 | 3 | [18 empty] | 2021-07-07 | [7 empty] | 0 | [5 empty] | 2022-03-17 | 2022-03-17 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-17 |  |  | 2022-03-17 |  | 2022-03-17 | 0 | 1//19
1273 | PGE | 95642 | Non-NEM | Non-Export | Withdrawn | ENGN | 170 |  | 2021-07-08 | 2021-07-08 | 0 | 2021-07-21 | 9 | 2021-08-25 | 25 | 2021-09-30 | 2021-11-03 | 24 | [22 empty] | 2021-08-04 | 2021-08-06 | 2 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1274 | PGE | 95376 | NEM | EXPNEM | Commercial | Solar PV | 43.53 |  | 2021-07-08 | 2021-07-13 | 3 | 2021-07-26 | 12 | 2021-08-11 | 12 | [15 empty] | 2021-08-11 | 2021-08-11 | 0 | 2021-08-11 | 2021-08-20 | 7 | [5 empty] | 0 | [5 empty] | 2021-09-10 | 2021-09-20 | 6 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-10 | 2021-09-12 | 0 | 2021-09-20 |  | 2021-10-19 | 21 | 1//19
1275 | PGE | 95035 | NEM | VNEM | Commercial | Solar PV | 33.39 |  | 2021-07-08 | 2021-07-15 | 5 | 2021-08-24 | 33 | 2021-09-13 | 13 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-09-17 | 4 |  |  |  |  | 2021-07-08 | 0 |  | 2021-08-06 | 2021-08-24 | 2021-08-25 | 12 | 2021-12-03 | 2021-12-09 | 4 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-03 | 2021-12-06 | 1 | 2021-12-09 |  | 2021-12-10 | 1 | 1//19
1276 | PGE | 95035 | NEM | VNEM | Commercial | Solar PV | 32.445 |  | 2021-07-08 | 2021-07-15 | 5 | 2021-08-24 | 33 | 2021-09-15 | 15 | [15 empty] | 2021-09-15 | 2021-10-06 | 15 | 2021-10-06 | 2021-10-14 | 6 |  |  |  |  | 2021-07-08 | 0 |  | 2021-08-06 | 2021-10-19 | 2021-10-19 | 51 | 2021-12-03 | 2022-01-13 | 29 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-03 | 2022-01-06 | 24 | 2022-01-13 |  | 2022-01-14 | 1 | 1//19
1277 | PGE | 94566 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-07-09 | 2021-07-17 | 5 | 2021-07-17 | 5 | 2021-07-20 | 1 | [18 empty] | 2021-07-09 | [6 empty] | 2021-07-09 | 2021-08-20 | 30 |  |  |  |  | 2021-08-20 | 2021-08-27 | 5 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-20 | 2021-08-20 | 0 | 2021-08-27 |  | 2021-08-31 | 2 | 1//19
1278 | PGE | 93242 | NEM | EXPNEM | Withdrawn | Solar PV | 1560 |  | 2021-07-09 | 2021-07-09 | 0 | 2021-07-21 | 8 | 2021-08-13 | 17 | [25 empty] | 2021-07-09 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1279 | PGE | 94588 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 850 |  | 2021-07-09 | 2021-07-19 | 6 | 2021-09-24 | 54 | 2021-11-29 | 43 | 2021-12-06 | 2022-01-05 | 22 | [12 empty] | 2022-01-05 | 2022-01-05 | 0 | 2022-01-05 | 2022-01-10 | 3 |  |  |  |  | 2021-07-09 | 0 |  | 2021-09-07 | 2022-02-14 | 2022-02-14 | 110 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1280 | PGE | 93923 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 37.957 |  | 2021-07-11 | 2021-07-19 | 5 | 2021-07-19 | 5 | 2021-07-19 | 0 | [18 empty] | 2021-07-11 | [7 empty] | 0 | [5 empty] | 2021-07-19 | 2021-07-19 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-07-19 |  |  | 2021-07-19 |  | 2021-07-19 | 0 | 1//19
1281 | PGE | 94027 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-07-12 | 2021-07-19 | 5 | 2021-07-19 | 5 | 2021-07-21 | 2 | [18 empty] | 2021-07-12 | [6 empty] | 2021-07-12 | 0 | [5 empty] | 2021-10-19 | 2021-10-19 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-19 |  |  | 2021-10-19 |  | 2021-10-19 | 0 | 1//19
1282 | PGE | 95123 | NEM | EXPNEM | Implementation | Solar PV | 52.163 |  | 2021-07-12 | 2021-07-26 | 10 | 2021-09-08 | 41 | 2021-09-29 | 15 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | 2021-10-28 | 21 |  |  |  |  | 2021-07-12 | 0 |  | 2021-12-09 | 2021-12-10 | 2021-12-10 | 1 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1283 | PGE | 94804 | NEM | EXPNEM | IA in Progress | Solar PV | 814.048 |  | 2021-07-12 | 2021-07-14 | 2 | 2021-08-06 | 19 | 2021-08-25 | 13 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | [6 empty] | 2021-07-12 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1284 | PGE | 94014 | NEM | EXPNEM | Commercial | Solar PV | 34.179 |  | 2021-07-12 | 2021-07-15 | 3 | 2021-08-02 | 15 | 2021-08-09 | 5 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-10 | 1 | [5 empty] | 0 | [5 empty] | 2021-08-18 | 2021-08-24 | 4 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-18 | 2021-08-19 | 1 | 2021-08-24 |  | 2021-08-27 | 3 | 1//19
1285 | PGE | 95322 | NEM | EXPNEM | Implementation | Solar PV | 240 |  | 2021-07-12 | 2021-07-22 | 8 | 2021-10-25 | 74 | 2021-11-09 | 11 | [15 empty] | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | 2022-02-03 | 58 |  |  |  |  | 2022-03-31 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1286 | PGE | 95501 | Non-NEM | Non-Export | Withdrawn | Storage | 350 |  | 2021-07-12 | 2021-07-13 | 1 | 2021-07-28 | 12 | 2021-08-18 | 15 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | [6 empty] | 2021-07-12 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1287 | PGE | 95501 | Non-NEM | Non-Export | Withdrawn | Storage | 560 |  | 2021-07-12 | 2021-07-13 | 1 | 2021-07-28 | 12 | 2021-08-23 | 18 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1288 | PGE | 95762 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.964 |  | 2021-07-12 | 2021-07-20 | 6 | 2021-10-26 | 75 | 2021-10-27 | 1 | [18 empty] | 2021-07-12 | [7 empty] | 0 | [5 empty] | 2021-10-27 | 2021-10-27 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-27 |  |  | 2021-10-27 |  | 2021-10-27 | 0 | 1//19
1289 | PGE | 93620 | NEM | EXPNEM | Implementation | Solar PV | 975 |  | 2021-07-12 | 2021-07-19 | 5 | 2021-07-30 | 14 | 2021-08-17 | 12 | 2021-08-17 | 2021-09-22 | 25 | 2021-09-22 | 2021-10-13 | 15 | 2021-10-13 | 2021-10-22 | 7 | 2021-10-22 | 2022-02-02 | 74 | 2021-10-22 |  |  | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-09 | 5 |  |  |  |  | 2021-07-12 | 2021-08-13 | 24 | [7 empty] | 2022-03-15 | 2022-03-31 | 12 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1290 | PGE | 95240 | NEM | EXPNEM | Application Review in Progress | Solar PV | 636 |  | 2021-07-12 | 2021-07-26 | 10 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1291 | PGE | 94549 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-07-12 | 2021-07-20 | 6 | 2021-08-04 | 17 | 2021-08-04 | 0 | [18 empty] | 2021-07-12 | [7 empty] | 0 | [5 empty] | 2021-08-04 | 2021-08-04 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-04 |  |  | 2021-08-04 |  | 2021-08-04 | 0 | 1//19
1292 | PGE | 95337 | NEM | EXPNEM | Implementation | Solar PV | 96.768 |  | 2021-07-12 | 2021-07-19 | 5 | 2021-07-22 | 8 | 2021-08-10 | 13 | 2021-08-10 | 2021-09-07 | 19 | 2021-09-08 | 2021-10-05 | 19 | 2021-10-05 | 2021-10-05 |  | 2021-10-05 | 2022-01-19 | 77 | 2021-10-05 |  |  | 2022-01-19 | 2022-01-19 | 0 | 2022-01-19 | 2022-01-21 | 2 |  |  |  |  | 2021-07-12 | 2021-08-09 | 20 |  |  |  |  | 2022-01-28 | 2022-02-02 | 3 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-28 | 2022-01-28 | 0 | 2022-02-02 | 2022-02-03 |  | 1 | 1//19 |  | 143
1293 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 46.536 |  | 2021-07-12 | 2021-07-15 | 3 | 2021-07-31 | 14 | 2021-08-09 | 5 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-09-08 | 21 | [5 empty] | 0 | [5 empty] | 2021-10-21 | 2021-10-28 | 5 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-21 | 2021-10-21 | 0 | 2021-10-28 |  | 2021-11-03 | 4 | 1//19
1294 | PGE | 95691 | NEM | EXPNEM | Commercial | Solar PV | 105.56 |  | 2021-07-13 | 2021-07-15 | 2 | 2021-07-23 | 8 | 2021-08-10 | 12 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-10 | 2021-08-18 | 6 |  |  |  |  | 2021-07-13 | 2021-07-28 | 11 |  |  |  |  | 2022-03-04 | 2022-03-10 | 4 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-04 | 2022-03-04 | 0 | 2022-03-10 |  | 2022-03-17 | 5 | 1//19
1295 | PGE | 94027 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 35.08 |  | 2021-07-13 | 2021-07-27 | 10 | 2021-10-13 | 65 | 2021-10-15 | 2 | [18 empty] | 2021-07-13 | 2021-07-16 | 3 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1296 | PGE | 95407 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 115.42 |  | 2021-07-13 | 2021-07-27 | 10 | 2021-08-05 | 17 | 2021-08-26 | 15 | [15 empty] | 2021-08-26 | 2021-09-16 | 14 | 2021-09-16 | [6 empty] | 2021-07-13 | 2021-08-25 | 31 |  | 2021-08-26 | 2021-09-16 | 14 | [12 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1297 | PGE | 93262 | NEM | EXPNEM | Implementation | Solar PV | 300 |  | 2021-07-13 | 2021-07-20 | 5 | 2021-07-20 | 5 | 2021-08-16 | 19 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | 2021-08-17 | 1 |  |  |  |  | 2021-07-13 | 2021-08-13 | 23 | [7 empty] | 2021-09-08 | 2022-01-04 | 80 |  |  |  | 2022-01-04 | 2022-03-02 | 41 | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1298 | PGE | 94062 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 45.116 |  | 2021-07-14 | 2021-07-21 | 5 | 2021-07-21 | 5 | 2021-07-22 | 1 | [18 empty] | 2021-07-14 | [6 empty] | 2021-07-14 | 0 | [5 empty] | 2021-07-22 | 2021-07-22 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-07-22 |  |  | 2021-07-22 |  | 2021-07-22 | 0 | 1//19
1299 | PGE | 95231 | NEM | EXPNEM | Application Review in Progress | Solar PV | 35.09 |  | 2021-07-14 | 2021-07-16 | 2 | [29 empty] | 2021-07-14 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1300 | PGE | 94608 | NEM | EXPNEM | IA in Progress | Solar PV | 51.939 |  | 2021-07-14 | 2021-07-20 | 4 | 2021-08-04 | 15 | 2021-10-05 | 43 | [15 empty] | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | 2021-10-07 | 2 |  |  |  |  | 2021-07-14 | 2021-09-28 | 53 |  |  |  |  | 2022-01-26 |  |  | 2021-12-10 | 2021-12-10 | 0 |  |  |  | 2021-12-27 |  | 77 | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-26 | 2022-01-26 | 0 |  |  |  |  | 1//19
1301 | PGE | 95913 | NEM | EXPNEM | Commercial | Solar PV | 34.29 |  | 2021-07-14 | 2021-07-20 | 4 | 2021-07-20 | 4 | 2021-08-09 | 14 | [15 empty] | 2021-08-09 | 2021-08-16 | 5 | 2021-08-16 | 2021-08-16 | 0 |  |  |  |  | 2021-07-14 | 0 |  | 2021-08-06 |  |  |  | 2021-08-09 | 2021-08-16 | 5 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-09 | 2021-08-10 | 1 | 2021-08-16 |  | 2021-08-16 | 0 | 1//19
1302 | PGE | 93635 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-07-14 | 2021-07-23 | 7 | 2021-08-31 | 34 | 2021-09-15 | 10 | [15 empty] | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | 2021-09-15 | 0 |  |  |  |  | 2021-07-14 | 2021-09-10 | 41 |  |  |  |  | 2021-09-15 | 2021-10-05 | 14 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-15 | 2021-09-28 | 9 | 2021-10-05 |  | 2021-10-05 | 0 | 1//19
1303 | PGE | 95501 | Non-NEM | Non-Export | Implementation | Storage | 420 |  | 2021-07-14 | 2021-07-14 | 0 | 2021-08-11 | 20 | 2021-10-08 | 41 | [15 empty] | 2021-10-08 | 2021-10-08 | 0 | 2021-10-08 | 2021-10-27 | 13 |  |  |  |  | 2021-07-14 | 0 | [8 empty] | 2022-01-06 |  | 69 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1304 | PGE | 94028 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.66 |  | 2021-07-14 | 2021-07-22 | 6 | 2021-09-27 | 52 | 2021-09-28 | 1 | [18 empty] | 2021-07-14 | [7 empty] | 0 | [5 empty] | 2021-09-28 | 2021-09-28 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-28 |  |  | 2021-09-28 |  | 2021-09-28 | 0 | 1//19
1305 | PGE | 95322 | NEM | EXPNEM | Implementation | Solar PV | 437.5 |  | 2021-07-14 | 2021-07-26 | 8 | 2021-08-10 | 19 | 2021-08-31 | 15 | [15 empty] | 2021-08-31 | 2021-09-22 | 15 | 2021-09-22 | 2021-12-17 | 59 |  |  |  |  | 2021-07-14 | 0 |  | 2021-08-13 | [15 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1306 | PGE | 94585 | NEM | EXPNEM | Commercial | Solar PV | 56.472 |  | 2021-07-15 | 2021-07-26 | 7 | 2021-11-30 | 94 | 2021-12-13 | 9 | [15 empty] | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13 | 2021-12-13 | 0 |  |  |  |  | 2021-07-15 | 0 | [5 empty] | 2021-12-14 | 2021-12-22 | 6 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-14 | 2021-12-15 | 1 | 2021-12-22 |  | 2021-12-28 | 4 | 1//19
1307 | PGE | 93635 | NEM | EXPNEM | Withdrawn | Solar PV | 33.3 |  | 2021-07-15 | 2021-07-27 | 8 | 2021-07-27 | 8 | 2021-08-17 | 15 | [15 empty] | 2021-08-17 | 2021-08-17 | 0 | 2021-08-17 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1308 | PGE | 95125 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.309 |  | 2021-07-15 | 2021-07-22 | 5 | 2021-08-04 | 14 | 2021-08-06 | 2 | [18 empty] | 2021-07-15 | [7 empty] | 0 | [5 empty] | 2021-08-06 | 2021-08-06 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-06 |  |  | 2021-08-06 |  | 2021-08-06 | 0 | 1//19
1309 | PGE | 93706 | NEM | EXPNEM | Implementation | Solar PV | 666.6 |  | 2021-07-15 | 2021-07-28 | 9 | 2021-08-12 | 20 | 2021-08-27 | 11 | 2021-08-27 | 2021-09-23 | 18 | 2021-09-23 | 2021-10-04 | 7 | 2021-10-04 | 2021-10-04 |  | 2021-10-04 | 2021-12-03 | 45 | 2021-10-04 |  |  | 2021-12-03 | 2021-12-03 | 0 | 2021-12-03 | 2022-03-31 | 82 |  |  |  |  | 2021-07-15 | 2021-08-13 | 21 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1310 | PGE | 96080 | NEM | EXPNEM | Commercial | Solar PV | 129.767 |  | 2021-07-15 | 2021-08-03 | 13 | 2021-08-20 | 26 | 2021-09-08 | 12 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-09-09 | 1 |  |  |  |  | 2021-07-15 | 0 | [5 empty] | 2021-10-15 | 2022-03-25 | 110 | 2021-10-20 | 2022-02-15 | 80 |  |  |  | 2022-02-23 | 2022-03-22 | 19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-15 | 2022-03-24 | 109 | 2022-03-25 | 2021-12-03 | 2022-03-29 | 3 | 1//19 |  | 97
1311 | PGE | 95685 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 42.775 |  | 2021-07-15 | 2021-07-23 | 6 | 2021-10-08 | 60 | 2021-10-12 | 2 | [18 empty] | 2021-09-21 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1312 | PGE | 95322 | NEM | EXPNEM | Commercial | Solar PV | 125 |  | 2021-07-15 | 2021-07-28 | 9 | 2021-08-12 | 20 | 2021-08-27 | 11 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-08-30 | 1 |  |  |  |  | 2021-07-15 | 2021-09-10 | 40 |  |  |  |  | 2021-09-21 | 2021-09-30 | 7 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-21 | 2021-09-21 | 0 | 2021-09-30 |  | 2021-09-30 | 0 | 1//19
1313 | PGE | 93637 | NEM | EXPNEM | Implementation | FUCE | 999.5 |  | 2021-07-16 | 2021-07-26 | 6 | 2021-07-26 | 6 | 2021-08-16 | 15 | 2021-08-16 | 2021-09-20 | 24 | 2021-09-23 | 2021-10-19 | 18 | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2022-02-16 | 87 | 2021-10-19 |  |  | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16 | 2022-03-14 | 17 |  |  |  |  | 2021-07-16 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1314 | PGE | 95648 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 32.47 |  | 2021-07-16 | 2021-07-26 | 6 | 2021-08-12 | 19 | 2021-08-13 | 1 | [18 empty] | 2021-08-11 | [7 empty] | 0 | [5 empty] | 2021-08-16 | 2021-08-16 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-16 |  |  | 2021-08-16 |  | 2021-08-16 | 0 | 1//19
1315 | PGE | 95965 | NEM | EXPNEM | Commercial | Solar PV | 300 |  | 2021-07-16 | 2021-07-26 | 6 | 2021-08-16 | 21 | 2021-09-01 | 12 | [15 empty] | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01 | 2022-01-19 | 95 | [5 empty] | 0 | [5 empty] | 2022-02-14 | 2022-02-22 | 5 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-14 | 2022-02-15 | 1 | 2022-02-22 |  | 2022-02-28 | 4 | 1//19
1316 | PGE | 95476 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-07-16 | 2021-07-26 | 6 | 2021-08-04 | 13 | 2021-08-18 | 10 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | 2021-08-20 | 2 |  |  |  |  | 2021-07-16 | 2021-08-13 | 20 |  |  |  |  | 2021-08-20 | 2021-08-26 | 4 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-20 | 2021-08-23 | 1 | 2021-08-26 |  | 2021-08-30 | 2 | 1//19
1317 | PGE | 95020 | NEM | EXPNEM | Commercial | Solar PV | 33.24 |  | 2021-07-16 | 2021-07-26 | 6 | 2021-11-08 | 80 | 2021-12-22 | 29 | [15 empty] | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22 | 2021-12-27 | 3 |  |  |  |  | 2021-07-16 | 0 | [5 empty] | 2022-02-23 | 2022-03-22 | 19 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-23 | 2022-03-10 | 11 | 2022-03-22 |  | 2022-03-24 | 2 | 1//19
1318 | PGE | 93242 | NEM | EXPNEM | Implementation | Solar PV | 170 |  | 2021-07-16 | 2021-07-29 | 9 | 2021-08-05 | 14 | 2021-08-20 | 11 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-20 | 2021-09-17 | 19 |  |  |  |  | 2021-07-16 | 2021-08-13 | 20 | [7 empty] | 2021-10-04 | 2022-01-25 | 77 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1319 | PGE | 94080 | NEM | EXPNEM | Implementation | Solar PV | 125.259 |  | 2021-07-16 | 2021-07-29 | 9 | 2021-07-29 | 9 | 2021-08-09 | 7 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-11-05 | 63 |  |  |  |  | 2021-07-16 | 2021-08-23 | 26 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1320 | PGE | 95020 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.022 |  | 2021-07-19 | 2021-07-27 | 6 | 2021-07-27 | 6 | 2021-07-28 | 1 | [18 empty] | 2021-07-19 | [6 empty] | 2021-07-19 | 0 | [5 empty] | 2021-11-27 | 2021-11-27 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-27 |  |  | 2021-11-27 |  | 2021-11-27 | 0 | 1//19
1321 | PGE | 93307 | NEM | EXPNEM | Study in Progress | Solar PV | 1240.07 |  | 2021-07-19 | 2021-07-26 | 5 | 2021-08-04 | 12 | 2021-09-14 | 28 | 2021-10-01 | 2021-11-05 | 25 | 2021-12-03 | 2022-01-07 | 25 | 2022-01-07 | 2022-01-12 | 3 | 2022-01-20 |  |  | 2022-01-12 | 2022-01-12 | 0 | [10 empty] | 2021-07-19 | 2021-09-07 | 35 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1322 | PGE | 95336 | NEM | EXPNEM | Study in Progress | Solar PV | 420 |  | 2021-07-19 | 2021-07-26 | 5 | 2021-10-21 | 67 | 2021-11-18 | 19 | 2021-11-18 | 2021-12-17 | 19 | 2021-12-28 | 2022-01-25 | 19 | 2022-01-25 | [19 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1323 | PGE | 93230 | NEM | EXPNEM | IA in Progress | Solar PV | 3950 |  | 2021-07-19 | 2021-07-29 | 8 | 2021-09-16 | 42 | [5 empty] | 2021-09-16 | 2021-10-21 | 25 | 2021-10-21 | 2021-10-22 | 1 | 2021-11-15 | 2022-02-11 | 61 | 2021-10-22 | 2021-10-27 | 3 | 2022-02-18 | 2022-03-07 | 10 | 2022-03-07 | 2022-03-11 | 4 | [5 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1324 | PGE | 93280 | NEM | VNEMMASH | Implementation | Solar PV | 64.86 |  | 2021-07-20 | 2021-07-20 | 0 | 2021-11-02 | 74 | 2021-11-05 | 3 | [15 empty] | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05 | 2021-12-14 | 24 |  |  |  |  | 2021-11-01 | 0 | [8 empty] | 2021-12-22 | 2022-03-09 | 54 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1325 | PGE | 94904 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.6 |  | 2021-07-20 | 2021-07-29 | 7 | [22 empty] | 2021-07-20 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1326 | PGE | 94404 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.375 |  | 2021-07-20 | 2021-07-29 | 7 | [22 empty] | 2021-07-20 | [6 empty] | 2021-07-20 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1327 | PGE | 93263 | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-07-20 | 2021-07-26 | 4 | 2021-09-03 | 33 | 2021-09-30 | 18 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | 2021-12-16 | 52 |  |  |  |  | 2021-07-20 | 2021-08-27 | 28 | [7 empty] | 2021-11-02 |  | 112 | [6 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1328 | PGE | 94558 | NEM | EXPNEM | IA in Progress | Solar PV | 43.31 |  | 2021-07-20 | 2021-07-27 | 5 | 2021-09-29 | 50 | 2021-11-01 | 23 | [15 empty] | 2021-11-01 | 2021-11-01 | 0 | 2021-11-01 | 2021-11-25 | 16 | [5 empty] | 0 | [5 empty] | 2022-03-09 | 2022-03-17 | 6 | 2021-12-17 | 2022-04-01 | 74 |  |  |  | 2022-04-12 |  | 1 | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-09 | 2022-03-10 | 1 | 2022-03-17 | 2022-03-24 |  | 5 | 1//19 |  | 171
1329 | PGE | 95111 | NEM | EXPNEM | Application Review in Progress | Solar PV | 167.863 |  | 2021-07-20 | 2021-07-28 | 6 | [29 empty] | 2021-07-20 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1330 | PGE | 94558 | NEM | EXPNEM | Commercial | Solar PV | 32.095 |  | 2021-07-20 | 2021-08-03 | 10 | 2021-08-16 | 19 | 2021-09-03 | 14 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-07 | 1 |  |  |  |  | 2021-07-20 | 2021-09-07 | 34 |  |  |  |  | 2021-09-20 | 2021-09-28 | 6 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-20 | 2021-09-20 | 0 | 2021-09-28 |  | 2021-10-05 | 5 | 1//19
1331 | PGE | 94111 | NEM | EXPNEM | IA in Progress | Solar PV | 94.059 |  | 2021-07-21 | 2021-07-28 | 5 | 2021-11-17 | 83 | 2021-12-01 | 8 | [15 empty] | 2021-12-01 | 2021-12-01 | 0 | 2021-12-01 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1332 | PGE | 94513 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-07-21 | 2021-07-30 | 7 | 2021-08-13 | 17 | 2021-08-13 | 0 | [18 empty] | 2021-07-21 | [7 empty] | 0 | [5 empty] | 2021-08-13 | 2021-08-13 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-13 |  |  | 2021-08-13 |  | 2021-08-13 | 0 | 1//19
1333 | PGE | 95122 | NEM | EXPNEM | IA in Progress | Solar PV | 144.967 |  | 2021-07-21 | 2021-07-28 | 5 | 2021-10-02 | 51 | 2021-11-23 | 35 | [15 empty] | 2021-11-23 | 2021-11-23 | 0 | 2021-11-23 | [6 empty] | 2021-07-21 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1334 | PGE | 93301 | NEM | EXPNEM | Application Review in Progress | Solar PV | 402.52 |  | 2021-07-21 | 2021-07-28 | 5 | [29 empty] | 2021-07-21 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1335 | PGE | 95125 | NEM | EXPNEM | Commercial | Solar PV | 58.623 |  | 2021-07-21 | 2021-07-29 | 6 | 2021-08-26 | 26 | 2021-09-09 | 9 | [15 empty] | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 | 2021-09-09 | 0 | [5 empty] | 0 |  | 2021-10-01 | 2021-10-06 | 2021-10-06 | 3 | 2021-12-13 | 2021-12-21 | 6 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-13 | 2021-12-14 | 1 | 2021-12-21 |  | 2021-12-21 | 0 | 1//19
1336 | PGE | 95401 | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 |  | 2021-07-22 | 2021-08-02 | 7 | [29 empty] | 2021-07-22 | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1337 | PGE | 94534 | NEM | EXPNEM | IA in Progress | ENGN, Solar PV | 227.661 |  | 2021-07-22 | 2021-07-29 | 5 | 2021-11-03 | 73 | 2021-11-19 | 11 | [15 empty] | 2021-11-19 | 2021-11-19 | 0 | 2021-11-19 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1338 | PGE | 94404 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.204 |  | 2021-07-22 | 2021-07-22 | 0 | 2021-08-12 | 15 | 2021-09-07 | 17 | [18 empty] | 2021-07-22 | [7 empty] | 0 | [5 empty] | 2021-09-07 | 2021-09-07 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-07 |  |  | 2021-09-07 |  | 2021-09-07 | 0 | 1//19
1339 | PGE | 94560 | NEM | EXPNEM | Withdrawn | Solar PV | 1000 |  | 2021-07-22 | 2021-07-30 | 6 | 2021-08-11 | 14 | 2021-09-09 | 20 | 2021-09-14 | 2021-10-12 | 20 | [12 empty] | 2021-10-12 | 2021-10-12 | 0 | 2021-10-12 | 2021-10-19 | 5 |  |  |  |  | 2021-07-22 | 2021-08-09 | 12 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1340 | PGE | 95334 | NEM | EXPNEM | Commercial | Solar PV | 32.269 |  | 2021-07-22 | 2021-07-23 | 1 | 2021-09-24 | 45 | 2021-10-07 | 9 | [15 empty] | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-10-22 | 11 |  |  |  |  | 2021-07-22 | 2021-09-28 | 47 |  |  |  |  | 2021-10-27 | 2021-11-04 | 6 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-27 | 2021-10-28 | 1 | 2021-11-04 |  | 2021-11-04 | 0 | 1//19
1341 | PGE | 93711 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-07-23 | 2021-08-02 | 6 | 2021-08-20 | 20 | 2021-08-26 | 4 | [18 empty] | 2021-08-10 | [6 empty] | 2021-07-23 | 2021-09-13 | 35 |  |  |  |  | 2021-09-13 | 2021-09-13 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-13 |  |  | 2021-09-13 |  | 2021-09-13 | 0 | 1//19
1342 | PGE | 95521 | Non-NEM | Non-Export | Implementation | Storage | 280 |  | 2021-07-23 | 2021-07-23 | 0 | 2021-08-11 | 13 | 2021-09-08 | 19 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-09-10 | 2 |  |  |  |  | 2021-07-23 | 0 | [8 empty] | 2021-10-19 | 2022-04-07 | 118 |  |  |  | 2022-04-07 |  | 4 | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1343 | PGE | 93648 | NEM | EXPNEM | Implementation | Solar PV | 956.275 |  | 2021-07-23 | 2021-08-05 | 9 | 2021-09-14 | 36 | 2021-09-24 | 8 | 2021-09-24 | 2021-10-22 | 20 | [12 empty] | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | 2022-01-21 | 61 |  |  |  |  | 2021-07-23 | 0 |  | 2022-03-07 | [15 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1344 | PGE | 95668 | NEM | EXPNEM | Commercial | Solar PV | 35.139 |  | 2021-07-23 | 2021-08-03 | 7 | 2021-09-13 | 35 | 2021-09-15 | 2 | [15 empty] | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | 2021-10-06 | 15 |  |  |  |  | 2021-07-23 | 2021-09-22 | 42 |  |  |  |  | 2021-10-25 | 2021-11-18 | 17 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-25 | 2021-11-15 | 14 | 2021-11-18 |  | 2021-11-18 | 0 | 1//19
1345 | PGE | 93426 | Non-NEM | Non-Export | Withdrawn | Storage | 929.5 |  | 2021-07-23 | 2021-07-23 | 0 | 2021-08-11 | 13 | 2021-10-19 | 48 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | [6 empty] | 2021-07-23 | 2021-08-27 | 25 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1346 | PGE | 94608 | NEM | EXPNEM | Commercial | Solar PV | 91.69 |  | 2021-07-23 | 2021-08-02 | 6 | 2021-08-21 | 20 | 2021-09-29 | 26 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | 2021-12-01 | 42 |  |  |  |  | 2021-07-23 | 2021-09-07 | 31 |  |  |  |  | 2021-12-29 | 2022-01-05 | 5 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-29 | 2021-12-29 | 0 | 2022-01-05 |  | 2022-01-06 | 1 | 1//19
1347 | PGE | 94558 | NEM | EXPNEM | Withdrawn | Solar PV | 600 |  | 2021-07-23 | 2021-08-03 | 7 | [29 empty] | 2021-07-23 | 2021-08-04 | 8 | [16 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1348 | PGE | 94030 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 45.226 |  | 2021-07-23 | 2021-08-03 | 7 | 2021-08-16 | 16 | 2021-08-16 | 0 | [18 empty] | 2021-07-23 | [7 empty] | 0 | [5 empty] | 2021-08-16 | 2021-08-16 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-16 |  |  | 2021-08-16 |  | 2021-08-16 | 0 | 1//19
1349 | PGE | 93309 | NEM | VNEM | Application Review in Progress | Solar PV | 100 |  | 2021-07-23 | 2021-07-26 | 1 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1350 | PGE | 94028 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 37.95 |  | 2021-07-24 | 2021-08-03 | 6 | 2021-08-03 | 6 | 2021-08-05 | 2 | [18 empty] | 2021-07-24 | [7 empty] | 0 | [5 empty] | 2021-08-05 | 2021-08-05 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-05 |  |  | 2021-08-05 |  | 2021-08-05 | 0 | 1//19
1351 | PGE | 94503 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.428 |  | 2021-07-26 | 2021-08-03 | 6 | 2021-08-03 | 6 | 2021-08-05 | 2 | [18 empty] | 2021-07-26 | [7 empty] | 0 | [5 empty] | 2021-08-05 | 2021-08-05 | 0 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-05 |  |  | 2021-08-05 |  | 2021-08-05 | 0 | 1//19
1352 | PGE | 95403 | NEM | EXPNEM | Commercial | Solar PV | 41.882 |  | 2021-07-26 | 2021-08-04 | 7 | 2021-08-18 | 17 | 2021-09-08 | 14 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-09-13 | 3 | [5 empty] | 0 | [5 empty] | 2021-10-26 | 2021-11-03 | 6 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-26 | 2021-10-27 | 1 | 2021-11-03 |  | 2021-11-04 | 1 | 1//19
1353 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 32.858 |  | 2021-07-26 | 2021-08-04 | 7 | 2021-08-04 | 7 | 2021-08-17 | 9 | [15 empty] | 2021-08-17 | 2021-08-18 | 1 | 2021-08-18 | 2021-09-17 | 21 |  |  |  |  | 2021-07-26 | 2021-08-17 | 16 |  |  |  |  | 2021-11-04 | 2021-11-14 | 5 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-04 | 2021-11-04 | 0 | 2021-11-14 |  | 2021-11-15 | 0 | 1//19
1354 | PGE | 95403 | NEM | EXPNEM | Commercial | Solar PV | 62.5 |  | 2021-07-26 | 2021-08-03 | 6 | 2021-09-01 | 27 | 2021-09-22 | 14 | [15 empty] | 2021-09-22 | 2021-09-22 | 0 | 2021-09-22 | 2021-09-24 | 2 | [5 empty] | 0 | [5 empty] | 2021-11-02 | 2021-11-10 | 6 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-02 | 2021-11-02 | 0 | 2021-11-10 |  | 2021-11-18 | 5 | 1//19
1355 | PGE | 95932 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-07-26 | 2021-08-03 | 6 | 2021-08-13 | 14 | 2021-08-31 | 12 | [15 empty] | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 | 2021-12-29 | 82 | [5 empty] | 0 | [5 empty] | 2021-12-30 | 2022-01-20 | 14 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-30 | 2022-01-14 | 11 | 2022-01-20 |  | 2022-01-26 | 4 | 1//19
1356 | PGE | 93622 | NEM | EXPNEM | IA in Progress | Solar PV | 816 |  | 2021-07-26 | 2021-08-09 | 10 | 2021-09-08 | 31 | 2021-09-29 | 15 | 2021-09-29 | 2021-11-03 | 25 | 2021-09-08 | 2021-12-06 | 60 | 2021-12-06 | 2021-12-06 |  | 2021-12-06 | 2022-03-09 | 68 | 2021-12-06 |  |  | 2022-03-09 | 2022-03-09 | 0 | 2022-03-09 | [7 empty] | 0 |  | 2021-09-10 | [15 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1357 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 33.249 |  | 2021-07-26 | 2021-08-04 | 7 | 2021-08-24 | 21 | 2021-11-10 | 55 | [15 empty] | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | 2021-12-02 | 13 |  |  |  |  | 2021-07-26 | 2021-09-08 | 31 |  |  |  |  | 2021-12-28 | 2022-01-06 | 7 | [9 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-28 | 2021-12-28 | 0 | 2022-01-06 |  | 2022-01-06 | 0 | 1//19
1358 | PGE | 95203 | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 |  | 2021-07-26 | 2021-08-04 | 7 | 2021-08-06 | 9 | 2021-08-19 | 9 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | [7 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1360 | PGE | 94025 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 225 |  | 2021-07-27 | 2021-08-03 | 5 | 2021-08-03 | 5 | [28 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1361 | PGE | 94040 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 40.1 |  | 2021-07-27 | 2021-08-02 | 4 | 2022-03-16 | 160 | [28 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1362 | PGE | 94022 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 48.766 |  | 2021-07-27 | 2021-08-04 | 6 | [30 empty] | 0 | [17 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1363 | PGE | 95677 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 2581.081 |  | 2021-07-27 | 2021-07-27 | 0 | 2021-08-25 | 21 | [5 empty] | 2021-08-25 | 2021-09-23 | 20 | 2021-09-23 | 2021-09-23 | 0 | 2021-09-30 | 2022-01-20 | 76 | 2021-09-23 | 2021-09-24 | 1 | 2022-01-26 | 2022-01-27 | 1 | 2022-01-27 | [7 empty] | 0 | [8 empty] | 2022-03-17 |  |  | 2022-03-17 | [5 empty] | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1364 | PGE | 95060 | NEM | EXPNEM | Commercial | Solar PV | 71.669 |  | 2021-07-27 | 2021-08-02 | 4 | 2021-08-24 | 20 | 2021-09-08 | 10 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-11-19 | 51 | [5 empty] | 0 | [5 empty] | 2021-11-23 | 2021-12-07 | 8 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-23 | 2021-11-23 | 0 | 2021-12-07 |  | 2021-12-13 | 4 | 1//19
1365 | PGE | 93301 | NEM | EXPNEM | Withdrawn | Solar PV | 34.9 |  | 2021-07-27 | 2021-08-09 | 9 | 2021-09-28 | 44 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1366 | PGE | 94806 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-07-27 | 2021-07-27 | 0 | 2021-08-11 | 11 | 2021-09-08 | 19 | [15 empty] | 2021-09-08 | 2021-09-23 | 11 | 2021-09-23 | 2021-10-18 | 17 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1367 | PGE | 93301 | NEM | EXPNEM | Withdrawn | Solar PV | 39.045 |  | 2021-07-27 | 2021-08-09 | 9 | 2021-09-13 | 33 | 2021-09-30 | 13 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | 2021-11-15 | 31 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1368 | PGE | 94539 | NEM | EXPNEM | Commercial | Solar PV | 57.71 |  | 2021-07-27 | 2021-08-03 | 5 | 2021-08-05 | 7 | 2021-08-17 | 8 | [15 empty] | 2021-08-17 | 2021-08-17 | 0 | 2021-08-17 | 2021-08-17 | 0 | [5 empty] | 0 | [5 empty] | 2021-08-20 | 2021-08-31 | 7 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-20 | 2021-08-20 | 0 | 2021-08-31 |  | 2021-09-07 | 4 | 1//19
1369 | PGE | 93635 | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-07-27 | 2021-08-09 | 9 | 2021-08-09 | 9 | [17 empty] | 2021-09-10 | 2021-09-17 | 5 | 2021-09-17 | 2021-09-17 | 0 |  |  |  |  | 2021-07-27 | 0 |  | 2021-08-13 | [6 empty] | 2021-11-08 | 2022-01-20 | 49 | 1//19 | 1//19 |  | 2022-03-11 |  | 23 | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1370 | PGE | 95991 | NEM | NEMMT | Withdrawn | ENGN, Solar PV | 863.2 |  | 2021-07-28 | 2021-08-11 | 10 | 2021-10-09 | 51 | 2021-10-29 | 14 | 2021-10-29 | 2021-12-08 | 25 | [12 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1371 | PGE | 95461 | NEM | EXPNEM | Implementation | Solar PV | 172.8 |  | 2021-07-28 | 2021-08-03 | 4 | 2021-08-03 | 4 | 2021-08-20 | 13 | 2021-08-20 | 2021-09-27 | 25 | 2021-10-04 | 2021-10-26 | 16 | 2021-10-26 | 2021-10-26 |  | 2021-10-26 | 2022-01-26 | 67 | 2021-10-26 |  |  | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | 2022-03-15 | 33 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1372 | PGE | 95912 | NEM | EXPNEM | Withdrawn | Solar PV | 60.6 |  | 2021-07-28 | 2021-08-03 | 4 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1373 | PGE | 94010 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.49 |  | 2021-07-28 | 2021-08-05 | 6 | [22 empty] | 2022-03-02 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1374 | PGE | 93646 | NEM | EXPNEM | Implementation | Solar PV | 50 |  | 2021-07-28 | 2021-08-09 | 8 | 2021-08-09 | 8 | 2021-09-17 | 28 | [15 empty] | 2021-09-17 | 2021-10-06 | 13 | 2021-10-06 | 2021-10-06 | 0 |  |  |  |  | 2021-07-28 | 0 |  | 2021-08-13 | [6 empty] | 2021-11-01 | 2021-11-30 | 18 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1375 | PGE | 94010 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 43.625 |  | 2021-07-28 | 2021-08-05 | 6 | 2021-09-24 | 41 | 2022-01-12 | 75 | [18 empty] | 2021-08-26 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1376 | PGE | 93646 | NEM | EXPNEM | Implementation | Solar PV | 30.354 |  | 2021-07-28 | 2021-08-09 | 8 | 2021-08-09 | 8 | 2021-08-23 | 10 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23 | 2021-09-22 | 21 |  |  |  |  | 2021-07-28 | 0 |  | 2021-08-13 | [6 empty] | 2021-09-17 | 2021-11-29 | 48 | 1//19 | 1//19 |  | 2022-03-09 |  | 25 | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1377 | PGE | 94010 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-07-28 | 2021-08-05 | 6 | 2021-08-19 | 16 | 2021-08-22 | 1 | [18 empty] | 2021-07-28 | [7 empty] | 0 | [5 empty] | 2021-08-22 | 2021-08-22 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-22 |  |  | 2021-08-22 |  | 2021-08-22 | 0 | 1//19
1378 | PGE | 94085 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 438.168 |  | 2021-07-29 | 2021-08-04 | 4 | [29 empty] | 2021-07-29 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1379 | PGE | 94035 | Non-NEM | Non-Export | Implementation | Solar PV | 3891.183 |  | 2021-07-29 | 2021-07-30 | 1 | 2021-09-01 | 24 | [5 empty] | 2021-09-01 | 2021-09-30 | 20 | 2021-09-30 | 2021-09-30 | 0 | 2021-10-04 | 2022-01-11 | 68 | 2021-09-30 | 2021-09-30 | 0 | 2022-01-21 | 2022-01-21 | 0 | 2022-01-21 | 2022-02-11 | 15 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1380 | PGE | 94526 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-07-29 | 2021-08-06 | 6 | 2021-08-06 | 6 | 2021-08-09 | 1 | [18 empty] | 2021-07-29 | [7 empty] | 0 | [5 empty] | 2021-08-09 | 2021-08-09 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-09 |  |  | 2021-08-09 |  | 2021-08-09 | 0 | 1//19
1381 | PGE | 95970 | NEM | EXPNEM | Implementation | Solar PV | 244.488 |  | 2021-07-29 | 2021-08-05 | 5 | 2021-09-07 | 27 | 2021-09-27 | 14 | 2021-09-27 | 2021-10-22 | 19 | 2021-10-26 | 2021-11-18 | 16 | 2021-11-18 | 2021-11-18 |  | 2021-11-29 | 2022-03-07 | 71 | 2021-11-18 |  |  | 2022-03-07 | 2022-03-07 | 0 | 2022-03-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1382 | PGE | 93635 | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-07-29 | 2021-08-04 | 4 | 2021-08-11 | 9 | 2021-08-27 | 12 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-09-02 | 4 |  |  |  |  | 2021-07-29 | 2021-09-07 | 27 | [7 empty] | 2021-11-08 | 2022-03-25 | 95 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1383 | PGE | 94561 | NEM | EXPNEM | Withdrawn | Solar PV | 35.487 |  | 2021-07-29 | 2021-08-04 | 4 | 2021-08-09 | 7 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1384 | PGE | 93301 | NEM | EXPNEM | Implementation | Solar PV | 407.612 |  | 2021-07-29 | 2021-08-04 | 4 | 2021-10-20 | 58 | 2021-10-27 | 5 | [15 empty] | 2021-10-27 | 2021-10-27 | 0 | 2021-10-27 | 2021-11-11 | 10 |  |  |  |  | 2021-07-29 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1385 | PGE | 94574 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-07-29 | 2021-08-06 | 6 | 2021-08-20 | 16 | 2021-09-01 | 8 | [18 empty] | 2021-07-29 | [7 empty] | 0 | [5 empty] | 2021-09-01 | 2021-09-01 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-01 |  |  | 2021-09-01 |  | 2021-09-01 | 0 | 1//19
1386 | PGE | 93203 | NEM | EXPNEM | Implementation | Solar PV | 489.177 |  | 2021-07-29 | 2021-08-05 | 5 | 2021-10-20 | 58 | 2021-11-02 | 9 | [15 empty] | 2021-11-02 | 2021-11-02 | 0 | 2021-11-02 | 2021-11-15 | 8 |  |  |  |  | 2021-07-29 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1387 | PGE | 95955 | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-07-30 | 2021-08-04 | 3 | 2021-08-06 | 5 | 2021-08-25 | 13 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | 2022-03-29 | 148 |  |  |  |  | 2021-07-30 | 0 | [5 empty] | 2022-03-29 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-29 | 2022-03-30 | 1 |  |  |  |  | 1//19
1388 | PGE | 95322 | NEM | EXPNEM | IA in Progress | Solar PV | 312.5 |  | 2021-07-30 | 2021-08-04 | 3 | 2021-08-18 | 13 | 2021-09-03 | 12 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-10-07 | 23 |  |  |  |  | 2021-07-30 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1389 | PGE | 94609 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.97 |  | 2021-07-30 | 2021-08-07 | 5 | 2021-08-07 | 5 | 2021-08-07 | 0 | [18 empty] | 2021-07-30 | [7 empty] | 0 | [5 empty] | 2021-08-07 | 2021-08-07 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-07 |  |  | 2021-08-07 |  | 2021-08-07 | 0 | 1//19
1390 | PGE | 93309 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-07-30 | 2021-08-07 | 5 | 2021-08-24 | 17 | 2021-08-26 | 2 | [18 empty] | 2021-07-30 | [7 empty] | 0 | [5 empty] | 2021-08-26 | 2021-08-26 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-26 |  |  | 2021-08-26 |  | 2021-08-26 | 0 | 1//19
1391 | PGE | 93422 | NEM | NEMMT | Study in Progress | ENGN, Solar PV | 1264.8 |  | 2021-07-30 | 2021-08-03 | 2 | 2021-08-18 | 13 | 2021-09-16 | 20 | 2021-09-30 | 2021-12-10 | 48 | 2022-01-27 | 2022-02-18 | 16 | 2022-02-18 | 2022-02-25 | 4 | 2022-03-18 |  |  | 2022-02-25 | 2022-02-25 | 0 |  |  |  | 2021-07-30 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1392 | PGE | 95407 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-08-01 | 2021-08-11 | 7 | 2021-08-24 | 16 | 2021-09-15 | 15 | [15 empty] | 2021-09-15 | 2021-09-16 | 1 | 2021-09-16 | 2021-11-15 | 41 | [5 empty] | 0 | [5 empty] | 2021-11-23 | 2021-12-02 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-23 | 2021-11-23 | 0 | 2021-12-02 |  | 2021-12-09 | 5 | 1//19
1393 | PGE | 94506 | NEM | EXPNEM | IA in Progress | Solar PV | 41.094 |  | 2021-08-02 | 2021-08-04 | 2 | 2021-08-09 | 5 | 2021-08-30 | 15 | [15 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-09-02 | 3 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1394 | PGE | 95650 | NEM | SNEM Paired Storage | Withdrawn | Solar PV, Storage | 35.116 |  | 2021-08-02 | 2021-08-09 | 5 | 2021-08-09 | 5 | 2021-08-11 | 2 | [18 empty] | 2021-08-02 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1395 | PGE | 95207 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100 |  | 2021-08-02 | 2021-08-04 | 2 | 2021-08-09 | 5 | 2021-09-10 | 23 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | [6 empty] | 2021-08-02 | 0 |  |  | 2021-10-18 | 2021-10-18 | 0 |  |  |  | 2021-09-08 | 2022-04-03 | 144 | 1//19 | 1//19 |  | 2022-04-03 | 2022-04-03 | 1 | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1396 | PGE | 93905 | NEM | EXPNEM | Commercial | Solar PV | 140.252 |  | 2021-08-02 | 2021-08-04 | 2 | 2021-08-13 | 9 | 2021-08-31 | 12 | [15 empty] | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 | 2021-10-29 | 42 |  |  |  |  | 2021-08-02 | 2021-09-07 | 25 |  |  |  |  | 2021-11-03 | 2021-11-12 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-03 | 2021-11-04 | 1 | 2021-11-12 |  | 2021-11-15 | 1 | 1//19
1397 | PGE | 93401 | NEM | EXPNEM | Commercial | Solar PV | 101.57 |  | 2021-08-02 | 2021-08-05 | 3 | 2021-08-11 | 7 | 2021-08-27 | 12 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-09-10 | 9 |  |  |  |  | 2021-08-02 | 0 | [5 empty] | 2021-12-13 | 2022-01-05 | 17 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-13 | 2021-12-13 | 0 | 2022-01-05 |  | 2022-01-10 | 3 | 1//19
1398 | PGE | 94578 | NEM | EXPNEM | IA in Progress | Solar PV | 733.3 |  | 2021-08-02 | 2021-08-04 | 2 | 2021-08-28 | 19 | 2021-09-08 | 6 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | [6 empty] | 2021-08-02 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1399 | PGE | 95765 | NEM | EXPNEM | Study in Progress | Solar PV | 500 |  | 2021-08-02 | 2021-08-11 | 7 | 2021-12-21 | 97 | 2022-01-06 | 12 | 2022-01-06 | 2022-03-04 | 39 | [15 empty] | 2021-08-02 | [6 empty] | 2021-08-02 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1400 | PGE | 94558 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-08-03 | 2021-08-05 | 2 | 2021-08-05 | 2 | 2021-08-24 | 13 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | 2021-12-20 | 80 |  |  |  |  | 2021-08-03 | 2021-08-13 | 8 |  |  |  |  | 2021-12-23 | 2021-12-30 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-23 | 2021-12-23 | 0 | 2021-12-30 |  | 2021-12-31 | 1 | 1//19
1401 | PGE | 95943 | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 |  | 2021-08-03 | 2021-08-16 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1402 | PGE | 95317 | NEM | EXPNEM | IA in Progress | Solar PV | 840 |  | 2021-08-03 | 2021-08-17 | 10 | 2021-09-08 | 25 | 2021-09-29 | 15 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | [6 empty] | 2021-08-03 | 0 |  | 2021-09-10 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1403 | PGE | 93907 | NEM | EXPNEM | IA in Progress | Solar PV | 125 |  | 2021-08-04 | 2021-08-06 | 2 | 2021-08-16 | 8 | 2021-10-12 | 40 | [15 empty] | 2021-10-12 | 2021-10-12 | 0 | 2021-10-12 | 2021-10-12 | 0 |  |  |  |  | 2021-08-04 | 2021-09-10 | 26 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1404 | PGE | 93955 | NEM | EXPNEM | Implementation | Solar PV | 34.179 |  | 2021-08-04 | 2021-08-10 | 4 | 2021-08-26 | 16 | 2021-09-24 | 20 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | 2021-10-04 | 6 | [5 empty] | 0 | [5 empty] | 2021-12-14 | 2021-12-23 | 7 | 2022-03-01 | 2022-03-09 | 6 | 1//19 | 1//19 |  | 2022-03-10 |  | 24 | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-14 | 2021-12-15 | 1 | 2021-12-23 | 2021-12-23 |  | 0 | 1//19 |  | 97
1405 | PGE | 93710 | Non-NEM | Non-Export | Implementation | Solar PV | 3500 |  | 2021-08-04 | 2021-08-04 | 0 | 2021-09-01 | 20 | 2021-09-23 | 15 | 2021-10-28 | 2021-11-30 | 20 | [12 empty] | 2021-11-30 | 2021-11-30 | 0 | 2021-11-30 | 2022-02-22 | 58 |  |  |  |  | 2021-08-04 | 2021-09-10 | 26 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1406 | PGE | 94041 | NEM | EXPNEM | IA in Progress | Solar PV | 81.967 |  | 2021-08-04 | 2021-08-10 | 4 | 2021-08-27 | 17 | 2021-10-11 | 30 | [15 empty] | 2021-10-11 | 2021-10-11 | 0 | 2021-10-11 | 2021-11-16 | 25 |  |  |  |  | 2021-08-04 | 0 | [5 empty] | 2021-12-30 | 2022-01-06 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-30 | 2021-12-30 | 0 | 2022-01-06 | 2022-01-10 |  | 2 | 1//19 |  | 109
1407 | PGE | 95060 | NEM | EXPNEM | Commercial | Solar PV | 48.973 |  | 2021-08-04 | 2021-08-10 | 4 | 2021-08-24 | 14 | 2021-09-08 | 10 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-09-09 | 1 | [5 empty] | 0 | [5 empty] | 2021-09-23 | 2021-11-03 | 29 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-23 | 2021-10-04 | 7 | 2021-11-03 |  | 2021-11-08 | 3 | 1//19
1408 | PGE | 93727 | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 |  | 2021-08-04 | 2021-08-17 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1409 | PGE | 93638 | NEM | VNEMSOMAH | Implementation | Solar PV | 38.4 |  | 2021-08-04 | 2021-08-06 | 2 | 2021-08-31 | 19 | 2021-09-17 | 12 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | 2022-03-16 | 123 |  |  |  |  | 2021-08-04 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1410 | PGE | 93230 | NEM | EXPNEM | Commercial | Solar PV | 125 |  | 2021-08-04 | 2021-08-17 | 9 | 2021-09-30 | 40 | 2021-10-19 | 13 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-10-29 | 8 |  |  |  |  | 2021-08-04 | 0 | [5 empty] | 2022-01-12 | 2022-01-21 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-12 | 2022-01-12 | 0 | 2022-01-21 |  | 2022-01-24 | 1 | 1//19
1411 | PGE | 95317 | NEM | EXPNEM | Implementation | Solar PV | 120 |  | 2021-08-04 | 2021-08-10 | 4 | 2021-08-11 | 5 | 2021-08-31 | 14 | [15 empty] | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 | 2021-09-09 | 6 |  |  |  |  | 2021-08-04 | 2021-08-24 | 14 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1412 | PGE | 93224 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 18150.32 |  | 2021-08-04 | 2021-08-04 | 0 | 2021-09-09 | 25 | [5 empty] | 2021-09-09 | [22 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1413 | PGE | 95334 | NEM | EXPNEM | IA in Progress | Solar PV | 551.02 |  | 2021-08-04 | 2021-08-11 | 5 | 2021-09-17 | 31 | 2021-10-30 | 30 | [15 empty] | 2021-10-30 | 2021-10-29 | 0 | 2021-10-29 | 2022-01-20 | 55 |  |  |  |  | 2021-08-04 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1414 | PGE | 93907 | NEM | EXPNEM | IA in Progress | Solar PV | 225 |  | 2021-08-04 | 2021-08-11 | 5 | 2021-08-18 | 10 | 2021-10-12 | 38 | [15 empty] | 2021-10-12 | 2021-10-12 | 0 | 2021-10-12 | 2021-10-18 | 4 |  |  |  |  | 2021-08-04 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1415 | PGE | 95932 | NEM | EXPNEM | Application Accepted | Solar PV | 199.295 |  | 2021-08-05 | 2021-08-11 | 4 | 2021-11-03 | 63 | 2021-11-03 | 0 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | [6 empty] | 2021-08-05 | 2021-09-22 | 33 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1416 | PGE | 93230 | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-08-05 | 2021-08-16 | 7 | 2021-09-30 | 39 | 2021-10-15 | 11 | [15 empty] | 2021-10-15 | 2021-10-15 | 0 | 2021-10-15 | 2021-10-29 | 10 |  |  |  |  | 2021-08-05 | 0 | [5 empty] | 2022-01-12 | 2022-01-21 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-12 | 2022-01-12 | 0 | 2022-01-21 |  | 2022-01-24 | 1 | 1//19
1417 | PGE | 95932 | NEM | EXPNEM | IA in Progress | Solar PV | 200 |  | 2021-08-05 | 2021-08-11 | 4 | 2021-08-18 | 9 | 2021-09-23 | 25 | [15 empty] | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | [6 empty] | 2021-08-05 | 2021-09-10 | 25 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1418 | PGE | 95932 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-08-05 | 2021-08-11 | 4 | 2021-08-19 | 10 | 2021-10-06 | 33 | [15 empty] | 2021-10-06 | 2021-10-06 | 0 | 2021-10-06 | 2021-10-19 | 9 |  |  |  |  | 2021-08-05 | 2021-08-24 | 13 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1419 | PGE | 94574 | NEM | EXPNEM | Study in Progress | Solar PV | 41.47 |  | 2021-08-05 | 2021-08-11 | 4 | [30 empty] | 0 | [8 empty] | 2021-08-05 | 2021-11-16 | 71 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1420 | PGE | 93654 | NEM | EXPNEM | IA in Progress | Solar PV | 778.129 |  | 2021-08-05 | 2021-08-11 | 4 | 2021-08-16 | 7 | 2021-09-03 | 14 | 2021-09-03 | 2021-10-04 | 20 | [12 empty] | 2021-10-04 | 2021-10-05 | 1 | 2021-10-05 | 2021-10-13 | 6 |  |  |  |  | 2021-08-05 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1421 | PGE | 94704 | NEM | EXPNEM | IA in Progress | Solar PV | 204 |  | 2021-08-05 | 2021-08-19 | 10 | 2021-09-13 | 26 | 2021-11-09 | 41 | 2021-11-09 | 2021-12-07 | 17 | [12 empty] | 2021-12-07 | 2021-12-07 | 0 | 2021-12-07 | 2022-02-23 | 54 |  |  |  |  | 2021-08-05 | 0 |  | 2021-10-14 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1422 | PGE | 94589 | NEM | EXPNEM | Implementation | Solar PV | 532 |  | 2021-08-05 | 2021-08-18 | 9 | 2021-11-17 | 72 | 2022-01-05 | 33 | [15 empty] | 2022-01-05 | 2022-01-05 | 0 | 2022-01-05 | 2022-02-23 | 33 |  |  |  |  | 2021-08-05 | 0 |  | 2021-12-14 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1423 | PGE | 93380 | Non-NEM | RESBCT | Withdrawn | Solar PV | 4000 |  | 2021-08-06 | 2021-08-06 | 0 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1424 | PGE | 95203 | NEM | EXPNEM | Commercial | Solar PV | 60 |  | 2021-08-06 | 2021-08-11 | 3 | 2021-09-03 | 20 | 2021-09-27 | 15 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-12 | 11 | [5 empty] | 0 | [5 empty] | 2021-10-15 | 2021-10-22 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-15 | 2021-10-15 | 0 | 2021-10-22 |  | 2021-10-28 | 4 | 1//19
1425 | PGE | 93637 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-08-06 | 2021-08-11 | 3 | 2021-08-16 | 6 | 2021-09-03 | 14 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-10 | 4 | [5 empty] | 0 | [5 empty] | 2021-12-27 | 2022-01-05 | 7 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-27 | 2021-12-27 | 0 | 2022-01-05 |  | 2022-01-06 | 1 | 1//19
1426 | PGE | 93654 | NEM | VNEMMASH | IA in Progress | Solar PV | 47.1 |  | 2021-08-06 | 2021-08-11 | 3 | 2021-09-13 | 25 | 2021-09-16 | 3 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | [6 empty] | 2021-08-06 | 0 |  |  | 2021-11-05 | 2021-11-05 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1427 | PGE | 94506 | NEM | EXPNEM | Withdrawn | Solar PV | 250 |  | 2021-08-06 | 2021-08-13 | 5 | 2021-08-24 | 12 | 2021-09-03 | 8 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-07 | 1 |  |  |  |  | 2021-08-06 | 2021-09-07 | 21 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1428 | PGE | 95618 | NEM | EXPNEM | Commercial | Solar PV | 81.587 |  | 2021-08-06 | 2021-08-11 | 3 | 2021-08-27 | 15 | 2021-09-20 | 15 | [15 empty] | 2021-09-20 | 2021-09-20 | 0 | 2021-09-20 | 2021-09-21 | 1 | [5 empty] | 0 | [5 empty] | 2021-10-06 | 2021-10-13 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-06 | 2021-10-11 | 3 | 2021-10-13 |  | 2021-10-19 | 4 | 1//19
1429 | PGE | 95607 | NEM | EXPNEM | IA in Progress | Solar PV | 31.337 |  | 2021-08-06 | 2021-08-12 | 4 | 2022-01-18 | 112 | 2022-02-01 | 10 | [15 empty] | 2022-02-01 | 2022-02-01 | 0 | 2022-02-01 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1430 | PGE | 95482 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 500.5 |  | 2021-08-09 | 2021-08-20 | 9 | 2021-09-10 | 23 | 2021-10-27 | 33 | [15 empty] | 2021-11-08 | 2021-11-10 | 2 | 2021-11-10 | 2021-11-17 | 4 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1431 | PGE | 94022 | NEM | EXPNEM | Application Review in Progress | Solar PV | 152.592 |  | 2021-08-09 | 2021-08-12 | 3 | [29 empty] | 2021-08-09 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1432 | PGE | 93446 | NEM | EXPNEM | Commercial | Solar PV | 37.658 |  | 2021-08-09 | 2021-08-17 | 6 | 2021-08-23 | 10 | 2021-09-07 | 10 | [15 empty] | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-09-09 | 2 |  |  |  |  | 2021-08-09 | 0 | [5 empty] | 2021-10-22 | 2021-11-01 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-22 | 2021-10-22 | 0 | 2021-11-01 |  | 2021-11-01 | 0 | 1//19
1433 | PGE | 94583 | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-08-09 | 2021-08-12 | 3 | 2021-08-17 | 6 | 2021-10-05 | 34 | [15 empty] | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | [6 empty] | 2021-08-09 | 2021-08-24 | 11 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1434 | PGE | 94022 | NEM | EXPNEM | IA in Progress | Solar PV | 196 |  | 2021-08-09 | 2021-08-12 | 3 | 2022-02-23 | 136 | 2022-03-23 | 20 | [15 empty] | 2022-03-23 | 2022-03-24 | 1 | 2022-03-24 | [6 empty] | 2021-08-09 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1435 | PGE | 95667 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-08-09 | 2021-08-09 | 0 | 2021-09-08 | 21 | 2021-09-29 | 15 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | 2021-12-28 | 61 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1436 | PGE | 94089 | NEM | EXPNEM | Study in Progress | Solar PV | 235.573 |  | 2021-08-09 | 2021-08-12 | 3 | 2021-12-08 | 83 | 2021-12-28 | 14 | 2021-12-28 | 2022-01-25 | 19 | 2022-02-07 | 2022-03-04 | 18 | 2022-03-04 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1437 | PGE | 94949 | NEM | EXPNEM | IA in Progress | Solar PV | 199.8 |  | 2021-08-09 | 2021-08-12 | 3 | 2021-08-25 | 12 | 2021-09-16 | 15 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | 2021-09-21 | 3 |  |  |  |  | 2021-08-09 | 2021-08-24 | 11 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1438 | PGE | 93610 | NEM | EXPNEM | Implementation | Solar PV | 220 |  | 2021-08-09 | 2021-08-23 | 10 | 2021-09-15 | 26 | 2021-10-06 | 15 | [15 empty] | 2021-10-06 | 2021-10-06 | 0 | 2021-10-06 | 2021-10-21 | 11 |  |  |  |  | 2021-12-27 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1439 | PGE | 94597 | NEM | EXPNEM | Commercial | Solar PV | 31.062 |  | 2021-08-09 | 2021-08-20 | 9 | 2021-08-25 | 12 | 2021-08-30 | 3 | [26 empty] | 0 | [5 empty] | 2021-08-31 | 2021-09-08 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-08-31 | 2021-09-01 | 1 | 2021-09-08 |  | 2021-09-08 | 0 | 1//19
1440 | PGE | 94526 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-08-10 | 2021-08-10 | 0 | 2021-09-24 | 32 | 2021-09-27 | 1 | [18 empty] | 2021-08-10 | [7 empty] | 0 | [5 empty] | 2021-09-27 | 2021-09-27 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-27 |  |  | 2021-09-27 |  | 2021-09-27 | 0 | 1//19
1441 | PGE | 93720 | NEM | EXPNEM | Commercial | Solar PV | 720.8 |  | 2021-08-10 | 2021-08-20 | 8 | 2021-08-23 | 9 | 2021-09-01 | 7 | [15 empty] | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01 | 2021-09-15 | 9 |  |  |  |  | 2021-08-10 | 2021-09-07 | 19 |  |  |  |  | 2022-03-03 | 2022-03-10 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-03 | 2022-03-04 | 1 | 2022-03-10 |  | 2022-03-14 | 2 | 1//19
1442 | PGE | 93380 | Non-NEM | RESBCT | Withdrawn | Solar PV | 4000 |  | 2021-08-10 | 2021-08-11 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1443 | PGE | 95961 | NEM | EXPNEM | Implementation | Solar PV | 132 |  | 2021-08-10 | 2021-08-13 | 3 | 2021-08-13 | 3 | 2021-09-03 | 15 | 2021-09-03 | 2021-10-07 | 23 | 2021-10-12 | 2021-11-09 | 20 | 2021-11-09 | 2021-11-09 |  | 2021-11-09 | 2022-02-23 | 77 | 2021-11-09 |  |  | 2022-02-23 | 2022-03-16 | 15 | 2022-03-16 | 2022-03-18 | 2 |  |  |  |  | 2021-08-10 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1444 | PGE | 95935 | NEM | EXPNEM | IA in Progress | Solar PV | 86.909 |  | 2021-08-10 | 2021-08-16 | 4 | 2021-08-24 | 10 | 2021-09-10 | 12 | 2021-09-10 | 2021-10-09 | 20 | 2021-11-09 | 2021-12-07 | 17 | 2021-12-07 | 2021-12-07 |  | 2021-12-07 | 2022-02-14 | 50 | 2021-12-07 |  |  | 2022-02-14 | 2022-02-14 | 0 | 2022-02-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1445 | PGE | 95901 | NEM | EXPNEM | IA in Progress | Solar PV | 36 |  | 2021-08-10 | 2021-08-16 | 4 | 2021-08-20 | 8 | 2021-09-08 | 12 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2022-01-13 | 88 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1446 | PGE | 95453 | NEM | VNEM | Implementation | Solar PV | 52.161 |  | 2021-08-10 | 2021-08-24 | 10 | 2021-09-29 | 35 | 2021-10-20 | 15 | [15 empty] | 2021-10-20 | 2021-11-10 | 15 | 2021-11-10 | 2021-11-16 | 3 |  |  |  |  | 2021-08-10 | 0 |  |  | 2021-12-29 | 2021-12-30 | 1 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1447 | PGE | 95453 | NEM | VNEM | Implementation | Solar PV | 46.2 |  | 2021-08-10 | 2021-08-24 | 10 | 2021-09-29 | 35 | 2021-10-20 | 15 | [15 empty] | 2021-10-20 | 2021-11-10 | 15 | 2021-11-10 | 2021-11-16 | 3 |  |  |  |  | 2021-08-10 | 0 |  |  | 2021-12-29 | 2021-12-30 | 1 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1448 | PGE | 95453 | NEM | VNEM | Implementation | Solar PV | 54.292 |  | 2021-08-10 | 2021-08-24 | 10 | 2021-09-29 | 35 | 2021-11-12 | 31 | [15 empty] | 2021-11-12 | 2021-11-12 | 0 | 2021-11-12 | 2022-01-12 | 41 |  |  |  |  | 2021-08-10 | 0 |  |  | 2021-12-29 | 2021-12-30 | 1 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1449 | PGE | 95453 | NEM | VNEM | Implementation | Solar PV | 54.292 |  | 2021-08-10 | 2021-08-24 | 10 | 2021-09-29 | 35 | 2021-10-20 | 15 | [15 empty] | 2021-10-20 | 2021-11-10 | 15 | 2021-11-10 | 2021-11-16 | 3 |  |  |  |  | 2021-08-10 | 0 |  |  | 2021-12-29 | 2021-12-30 | 1 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1450 | PGE | 93309 | NEM | EXPNEM | Implementation | Solar PV | 215.388 |  | 2021-08-11 | 2021-08-23 | 8 | 2021-08-25 | 10 | 2021-09-10 | 11 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | 2021-09-17 | 5 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1451 | PGE | 93905 | NEM | EXPNEM | Commercial | Solar PV | 86.4 |  | 2021-08-11 | 2021-08-16 | 3 | 2021-09-29 | 34 | 2021-10-27 | 20 | [15 empty] | 2021-10-27 | 2021-10-27 | 0 | 2021-10-27 | 2021-12-15 | 32 | [5 empty] | 0 | [5 empty] | 2021-12-21 | 2021-12-28 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-21 | 2021-12-21 | 0 | 2021-12-28 |  | 2021-12-30 | 2 | 1//19
1452 | PGE | 95525 | Non-NEM | Non-Export | Implementation | Storage | 350 |  | 2021-08-11 | 2021-08-12 | 1 | 2021-09-01 | 15 | 2021-11-15 | 51 | [15 empty] | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2022-03-28 | 91 |  |  |  |  | 2021-08-11 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1453 | PGE | 95970 | NEM | EXPNEM | Implementation | Solar PV | 133.2 |  | 2021-08-11 | 2021-08-16 | 3 | 2021-08-23 | 8 | 2021-09-10 | 13 | 2021-09-10 | 2021-10-14 | 24 | 2021-10-19 | 2021-11-17 | 20 | 2021-11-17 | 2021-11-17 |  | 2021-11-17 | 2022-03-04 | 78 | 2021-11-17 |  |  | 2022-03-07 | 2022-03-07 | 0 | 2022-03-07 | 2022-03-11 | 4 |  |  |  |  | 2021-08-11 | 2021-09-10 | 21 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1454 | PGE | 94549 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.262 |  | 2021-08-12 | 2021-08-24 | 8 | 2021-10-15 | 45 | 2021-11-04 | 14 | [18 empty] | 2021-10-15 | [7 empty] | 0 | [5 empty] | 2021-11-04 | 2021-11-04 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-04 | 2021-11-04 | 0 | 2021-11-04 |  | 2021-11-12 | 5 | 1//19
1455 | PGE | 95776 | NEM | EXPNEM | IA in Progress | Solar PV | 89.91 |  | 2021-08-12 | 2021-08-20 | 6 | 2021-08-20 | 6 | 2021-09-08 | 12 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-10-01 | 17 | [5 empty] | 0 | [5 empty] | 2022-03-10 | 2022-03-29 | 13 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-10 | 2022-03-24 | 10 | 2022-03-29 |  |  |  | 1//19
1456 | PGE | 95912 | NEM | EXPNEM | Withdrawn | Solar PV | 125 |  | 2021-08-12 | 2021-08-25 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1457 | PGE | 95762 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.988 |  | 2021-08-12 | 2021-08-25 | 9 | 2021-09-13 | 21 | 2021-09-14 | 1 | [18 empty] | 2021-08-12 | [7 empty] | 0 | [5 empty] | 2021-09-14 | 2021-09-14 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-14 |  |  | 2021-09-14 |  | 2021-09-14 | 0 | 1//19
1458 | PGE | 94507 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 32.191 |  | 2021-08-13 | 2021-08-25 | 8 | 2022-03-16 | 147 | 2022-03-18 | 2 | [18 empty] | 2021-08-13 | [7 empty] | 0 | [5 empty] | 2022-03-18 | 2022-03-18 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-18 |  |  | 2022-03-18 |  | 2022-03-18 | 0 | 1//19
1459 | PGE | 94559 | NEM | EXPNEM | Study in Progress | Solar PV | 39.737 |  | 2021-08-13 | 2021-08-27 | 10 | 2022-01-12 | 104 | 2022-02-17 | 25 | 2022-02-17 | 2022-03-17 | 19 | [23 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1460 | PGE | 95340 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 42.725 |  | 2021-08-13 | 2021-08-17 | 2 | 2021-09-13 | 20 | 2021-09-14 | 1 | [18 empty] | 2021-08-13 | 2021-08-13 | 0 | [5 empty] | 0 | [5 empty] | 2021-09-14 | 2021-09-14 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-14 |  |  | 2021-09-14 |  | 2021-09-14 | 0 | 1//19
1461 | PGE | 95134 | NEM | EXPNEM | IA in Progress | Solar PV | 61.111 |  | 2021-08-13 | 2021-08-23 | 6 | 2021-08-27 | 10 | 2021-09-17 | 14 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1462 | PGE | 93401 | NEM | EXPNEM | IA in Progress | Solar PV | 200 |  | 2021-08-13 | 2021-08-23 | 6 | 2021-12-09 | 80 | 2021-12-27 | 12 | [15 empty] | 2021-12-27 | 2021-12-28 | 1 | 2021-12-28 | [6 empty] | 2021-08-13 | 0 |  | 2022-02-10 | 2022-02-25 | 2022-03-09 | 10 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1463 | PGE | 95616 | NEM | EXPNEM | Commercial | Solar PV | 38.253 |  | 2021-08-13 | 2021-08-23 | 6 | 2021-08-24 | 7 | 2021-09-09 | 11 | [15 empty] | 2021-09-09 | 2021-09-13 | 2 | 2021-09-13 | 2021-09-14 | 1 | [5 empty] | 0 | [5 empty] | 2021-11-04 | 2021-11-10 | 4 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-04 | 2021-11-04 | 0 | 2021-11-10 |  | 2021-11-12 | 1 | 1//19
1464 | PGE | 94062 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 39.176 |  | 2021-08-13 | 2021-08-25 | 8 | 2021-09-24 | 29 | 2021-09-28 | 2 | [18 empty] | 2021-08-13 | [7 empty] | 0 | [5 empty] | 2021-12-10 | 2022-02-15 | 46 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-10 | 2022-02-15 | 46 | 2022-02-15 |  | 2022-02-17 | 2 | 1//19
1465 | PGE | 94402 | NEM | EXPNEM | Commercial | Solar PV | 78.283 |  | 2021-08-13 | 2021-08-24 | 7 | 2021-09-20 | 25 | 2021-10-05 | 11 | [15 empty] | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | 2021-11-10 | 26 | [5 empty] | 0 | [5 empty] | 2021-12-01 | 2021-12-09 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-01 | 2021-12-02 | 1 | 2021-12-09 |  | 2021-12-16 | 5 | 1//19
1466 | PGE | 94110 | NEM | EXPNEM | Study in Progress | Solar PV | 43.2 |  | 2021-08-13 | 2021-08-23 | 6 | 2021-09-17 | 24 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1467 | PGE | 93455 | NEM | EXPNEM | Implementation | Solar PV | 500 |  | 2021-08-14 | 2021-08-19 | 3 | 2021-08-23 | 5 | 2021-11-16 | 59 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-19 | 3 | [5 empty] | 0 | [5 empty] | 2021-12-20 | 2021-12-29 | 7 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-20 | 2021-12-23 | 3 | 2021-12-29 | 2021-12-30 |  | 1 | 1//19 |  | 94
1468 | PGE | 95407 | NEM | EXPNEM | IA in Progress | Solar PV | 328.367 |  | 2021-08-16 | 2021-08-25 | 7 | 2021-10-11 | 39 | 2021-12-08 | 39 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | 2021-12-09 | 1 |  |  |  |  | 2021-08-16 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1469 | PGE | 95321 | Non-NEM | Non-Export | Study in Progress | Storage | 210 |  | 2021-08-16 | 2021-08-17 | 1 | 2021-09-08 | 16 | 2021-10-11 | 23 | 2021-10-29 | 2021-12-20 | 33 | 2022-01-24 | 2022-02-17 | 18 | 2022-02-17 | 2022-02-17 | 0 | 2022-02-18 |  |  | 2022-02-17 | 2022-02-17 | 0 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1470 | PGE | 95945 | NEM | EXPNEM | Commercial | Solar PV | 32.88 |  | 2021-08-16 | 2021-08-18 | 2 | 2021-10-20 | 46 | 2021-11-03 | 10 | [15 empty] | 2021-11-03 | 2021-11-03 | 0 | 2021-11-03 | 2021-11-23 | 13 | [5 empty] | 0 | [5 empty] | 2021-11-23 | 2021-12-02 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-23 | 2021-11-23 | 0 | 2021-12-02 |  | 2021-12-02 | 0 | 1//19
1472 | PGE | 93728 | NEM | EXPNEM | Commercial | Solar PV | 55.889 |  | 2021-08-16 | 2021-08-25 | 7 | 2021-08-25 | 7 | 2021-09-03 | 7 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2022-03-02 | 122 | [5 empty] | 0 | [5 empty] | 2022-03-03 | 2022-03-22 | 13 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-03 | 2022-03-17 | 10 | 2022-03-22 |  | 2022-03-24 | 2 | 1//19
1473 | PGE | 94523 | NEM | EXPNEM | Implementation | Solar PV | 66.6 |  | 2021-08-16 | 2021-08-30 | 10 | 2021-09-07 | 15 | 2021-09-21 | 10 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | 2021-09-23 | 2 |  |  |  |  | 2021-08-16 | 2021-09-10 | 18 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1474 | PGE | 95376 | NEM | EXPNEM | Commercial | Solar PV | 45.452 |  | 2021-08-17 | 2021-08-25 | 6 | 2021-09-16 | 21 | 2021-10-05 | 13 | [15 empty] | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | 2021-10-08 | 3 | [5 empty] | 0 | [5 empty] | 2021-12-06 | 2021-12-16 | 8 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-06 | 2021-12-07 | 1 | 2021-12-16 |  | 2021-12-21 | 3 | 1//19
1475 | PGE | 94574 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-08-17 | 2021-08-25 | 6 | 2021-09-22 | 25 | 2021-10-22 | 22 | [15 empty] | 2021-10-22 | 2021-10-25 | 1 | 2021-10-25 | 2021-12-03 | 26 |  |  |  |  | 2021-08-17 | 2021-09-10 | 17 |  |  |  |  | 2022-01-13 | 2022-01-26 | 8 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-13 | 2022-01-13 | 0 | 2022-01-26 |  | 2022-02-02 | 5 | 1//19
1476 | PGE | 95616 | NEM | EXPNEM | Implementation | Solar PV | 33.884 |  | 2021-08-17 | 2021-08-25 | 6 | 2021-08-25 | 6 | 2021-09-17 | 16 | [15 empty] | 2021-09-17 | 2021-09-23 | 4 | 2021-09-23 | 2021-09-23 | 0 | [5 empty] | 0 |  | 2021-10-22 |  |  |  | 2021-11-01 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-01 | 2021-11-01 | 0 |  |  |  |  | 1//19
1477 | PGE | 95674 | NEM | EXPNEM | Commercial | Solar PV | 53.184 |  | 2021-08-17 | 2021-08-25 | 6 | 2021-09-06 | 13 | 2021-10-14 | 27 | [15 empty] | 2021-10-14 | 2021-10-14 | 0 | 2021-10-14 | 2022-01-25 | 69 |  |  |  |  | 2021-08-17 | 0 | [5 empty] | 2022-01-27 | 2022-02-03 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-27 | 2022-01-27 | 0 | 2022-02-03 |  | 2022-02-09 | 4 | 1//19
1478 | PGE | 95501 | Non-NEM | Non-Export | Implementation | Storage | 420 |  | 2021-08-17 | 2021-08-18 | 1 | 2021-09-08 | 15 | 2021-12-10 | 64 | 2022-01-12 | 2022-02-09 | 19 | [12 empty] | 2022-02-09 | 2022-02-09 | 0 | 2022-02-09 | 2022-03-30 | 34 |  |  |  |  | 2021-08-17 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1479 | PGE | 93654 | NEM | EXPNEM | Implementation | Solar PV | 126.15 |  | 2021-08-17 | 2021-08-31 | 10 | 2021-09-20 | 23 | 2021-12-29 | 69 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 2022-01-04 | 4 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1480 | PGE | 93263 | NEM | EXPNEM | Implementation | Solar PV | 120 |  | 2021-08-17 | 2021-08-23 | 4 | 2021-09-10 | 17 | 2021-09-21 | 7 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | 2021-09-29 | 6 |  |  |  |  | 2021-08-17 | 2021-09-14 | 19 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1481 | PGE | 94544 | NEM | NEMMT | Commercial | Solar PV, Storage | 55.9 |  | 2021-08-17 | 2021-08-25 | 6 | 2021-08-25 | 6 | 2021-10-05 | 28 | [15 empty] | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | 2022-01-27 | 78 | [5 empty] | 0 | [5 empty] | 2022-01-28 | 2022-02-07 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-28 | 2022-01-28 | 0 | 2022-02-07 |  | 2022-02-07 | 0 | 1//19
1482 | PGE | 93313 | NEM | EXPNEM | Commercial | Solar PV | 44.04 |  | 2021-08-18 | 2021-08-24 | 4 | 2021-08-25 | 5 | 2021-09-10 | 11 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | 2021-11-24 | 52 | [5 empty] | 0 | [5 empty] | 2021-11-24 | 2021-12-07 | 7 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-24 | 2021-11-29 | 1 | 2021-12-07 |  | 2021-12-07 | 0 | 1//19
1483 | PGE | 94903 | Non-NEM | NEMFC | Application Review in Progress | FUCE, Storage | 892.5 |  | 2021-08-18 | 2021-09-01 | 10 | [29 empty] | 2021-08-18 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1484 | PGE | 94027 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 32.01 |  | 2021-08-19 | 2021-08-30 | 7 | 2021-10-07 | 34 | 2021-10-11 | 2 | [18 empty] | 2021-08-19 | [7 empty] | 0 | [5 empty] | 2022-03-19 | 2022-03-19 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-19 |  |  | 2022-03-19 |  | 2022-03-19 | 0 | 1//19
1486 | PGE | 95060 | NEM | EXPNEM | Commercial | Solar PV | 40.252 |  | 2021-08-19 | 2021-08-27 | 6 | 2021-09-01 | 9 | 2021-09-08 | 4 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2022-01-24 | 94 | [5 empty] | 0 | [5 empty] | 2022-01-25 | 2022-02-02 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-25 | 2022-01-26 | 1 | 2022-02-02 |  | 2022-02-08 | 4 | 1//19
1487 | PGE | 93280 | NEM | EXPNEM | Withdrawn | Solar PV | 840 |  | 2021-08-19 | 2021-08-30 | 7 | 2021-08-31 | 8 | 2021-09-20 | 13 | [15 empty] | 2021-09-20 | [9 empty] | 2021-08-19 | 0 |  | 2021-09-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1488 | PGE | 95926 | NEM | EXPNEM | IA in Progress | Solar PV | 133.3 |  | 2021-08-19 | 2021-08-27 | 6 | 2021-09-01 | 9 | 2021-09-17 | 11 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | 2022-02-03 | 95 |  |  |  |  | 2021-08-19 | 2021-09-09 | 14 |  |  |  |  | 2022-02-04 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-04 | 2022-02-04 | 0 |  |  |  |  | 1//19
1489 | PGE | 93266 | NEM | EXPNEM | Implementation | Solar PV | 385.259 |  | 2021-08-19 | 2021-08-24 | 3 | 2021-08-24 | 3 | 2021-09-08 | 10 | 2021-09-10 | 2021-10-05 | 17 | [12 empty] | 2021-09-08 | 2021-09-27 | 13 | 2021-09-27 | 2021-10-05 | 6 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1490 | PGE | 93635 | NEM | EXPNEM | Implementation | Solar PV | 181.47 |  | 2021-08-19 | 2021-08-25 | 4 | 2021-09-28 | 27 | 2021-10-25 | 19 | [15 empty] | 2021-10-25 | 2021-10-25 | 0 | 2021-10-25 | 2021-10-26 | 1 |  |  |  |  | 2021-08-19 | 0 | [8 empty] | 2021-12-17 |  | 82 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1491 | PGE | 93727 | NEM | EXPNEM | IA in Progress | Solar PV | 219.518 |  | 2021-08-19 | 2021-08-27 | 6 | 2021-10-09 | 35 | 2021-10-27 | 12 | [15 empty] | 2021-10-27 | 2021-10-27 | 0 | 2021-10-27 | [6 empty] | 2021-08-19 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1492 | PGE | 93250 | NEM | EXPNEM | Implementation | Solar PV | 290 |  | 2021-08-19 | 2021-08-25 | 4 | 2021-08-30 | 7 | 2021-09-15 | 11 | [15 empty] | 2021-12-10 | 2021-12-10 | 0 | 2021-12-10 | 2021-12-15 | 3 |  |  |  |  | 2021-08-19 | 2021-09-08 | 13 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1493 | PGE | 93427 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.887 |  | 2021-08-19 | 2021-08-31 | 8 | 2021-09-16 | 19 | 2021-09-16 | 0 | [18 empty] | 2021-08-19 | [7 empty] | 0 | [5 empty] | 2021-09-16 | 2021-09-16 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-16 |  |  | 2021-09-16 |  | 2021-09-16 | 0 | 1//19
1494 | PGE | 93703 | NEM | EXPNEM | IA in Progress | Solar PV | 146 |  | 2021-08-19 | 2021-08-27 | 6 | 2021-09-01 | 9 | 2021-09-21 | 13 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [6 empty] | 2021-08-19 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1495 | PGE | 93263 | NEM | EXPNEM | Commercial | Solar PV | 246.28 |  | 2021-08-19 | 2021-08-24 | 3 | 2021-09-22 | 23 | 2021-10-07 | 11 | [15 empty] | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-12-14 | 45 |  |  |  |  | 2021-08-19 | 2021-09-23 | 24 |  |  |  |  | 2022-03-08 | 2022-03-15 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-08 | 2022-03-08 | 0 | 2022-03-15 |  | 2022-03-15 | 0 | 1//19
1496 | PGE | 94952 | NEM | EXPNEM | IA in Progress | Solar PV | 30.159 |  | 2021-08-19 | 2021-08-30 | 7 | 2021-11-08 | 56 | 2021-11-24 | 11 | [15 empty] | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 2021-11-30 | 2 |  |  |  |  | 2021-08-19 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1497 | PGE | 93725 | NEM | EXPNEM | Implementation | Solar PV | 53.289 |  | 2021-08-19 | 2021-09-02 | 10 | 2021-11-10 | 58 | 2021-11-18 | 5 | [15 empty] | 2021-11-18 | 2021-11-18 | 0 | 2021-11-18 | 2021-11-18 | 0 |  |  |  |  | 2021-08-19 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1498 | PGE | 94024 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.99 |  | 2021-08-19 | 2021-09-02 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1499 | PGE | 95076 | NEM | EXPNEM | Implementation | Solar PV | 133.2 |  | 2021-08-19 | 2021-08-31 | 8 | 2021-10-04 | 31 | 2021-10-19 | 11 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-12-20 | 41 |  |  |  |  | 2021-08-19 | 0 | [5 empty] | 2022-01-13 | 2022-01-26 | 8 | 2022-04-06 |  | 5 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-13 | 2022-01-14 | 1 | 2022-01-26 | 2022-01-31 |  | 3 | 1//19 |  | 112
1500 | PGE | 95695 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-08-20 | 2021-08-28 | 5 | 2021-10-27 | 47 | 2021-11-09 | 9 | [15 empty] | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | 2021-12-27 | 31 | [5 empty] | 0 | [5 empty] | 2022-01-05 | 2022-01-12 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-05 | 2022-01-05 | 0 | 2022-01-12 |  | 2022-01-14 | 2 | 1//19
1501 | PGE | 93420 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.131 |  | 2021-08-20 | 2021-09-01 | 8 | 2022-03-16 | 142 | 2022-03-23 | 5 | [18 empty] | 2021-08-20 | [7 empty] | 0 | [5 empty] | 2022-03-23 | 2022-03-23 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-23 |  |  | 2022-03-23 |  | 2022-03-23 | 0 | 1//19
1502 | PGE | 93401 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 44.178 |  | 2021-08-20 | 2021-09-01 | 8 | 2021-10-22 | 44 | 2021-10-25 | 1 | [18 empty] | 2021-08-20 | [7 empty] | 0 | [5 empty] | 2021-10-22 | 2021-10-25 | 1 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-22 |  |  | 2021-10-25 |  | 2021-10-25 | 0 | 1//19
1503 | PGE | 94533 | Non-NEM | Non-Export | IA in Progress | Storage | 9029.4 |  | 2021-08-20 | 2021-08-20 | 0 | 2021-09-09 | 13 | 2021-12-01 | 56 | [15 empty] | 2021-12-01 | 2021-12-01 | 0 | 2021-12-01 | [6 empty] | 2021-09-10 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1504 | PGE | 95709 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.375 |  | 2021-08-20 | 2021-09-01 | 8 | 2021-09-01 | 8 | 2021-09-07 | 3 | [18 empty] | 2021-08-20 | [7 empty] | 0 | [5 empty] | 2021-09-07 | 2021-09-07 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-07 |  |  | 2021-09-07 |  | 2021-09-07 | 0 | 1//19
1505 | PGE | 93635 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-08-20 | 2021-08-26 | 4 | 2021-08-30 | 6 | 2021-09-13 | 9 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-09-13 | 0 |  |  |  |  | 2021-08-20 | 2021-09-09 | 13 |  |  |  |  | 2021-09-30 | 2021-10-07 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-30 | 2021-09-30 | 0 | 2021-10-07 |  | 2021-10-07 | 0 | 1//19
1506 | PGE | 95691 | NEM | EXPNEM | Commercial | Solar PV | 36 |  | 2021-08-20 | 2021-08-28 | 5 | 2021-09-09 | 13 | 2021-09-23 | 10 | [15 empty] | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | 2021-11-22 | 41 |  |  |  |  | 2021-08-20 | 2021-09-09 | 13 |  |  |  |  | 2021-12-28 | 2022-01-26 | 20 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-28 | 2022-01-18 | 14 | 2022-01-26 |  | 2022-02-01 | 4 | 1//19
1507 | PGE | 93630 | NEM | VNEM | Commercial | Solar PV | 39.976 |  | 2021-08-20 | 2021-08-25 | 3 | 2021-09-01 | 8 | 2021-09-13 | 7 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-09-14 | 1 |  |  |  |  | 2021-08-20 | 2021-09-14 | 16 |  | 2021-09-13 | 2021-09-13 | 0 | 2021-10-25 | 2021-10-29 | 4 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-25 | 2021-10-25 | 0 | 2021-10-29 |  | 2021-11-01 | 1 | 1//19
1508 | PGE | 93620 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-08-20 | 2021-08-27 | 5 | 2021-09-01 | 8 | 2021-09-16 | 10 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | 2021-09-28 | 8 |  |  |  |  | 2021-08-20 | 2021-09-10 | 14 |  |  |  |  | 2022-02-22 | 2022-03-04 | 8 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-22 | 2022-03-04 | 8 | 2022-03-04 |  | 2022-03-04 | 0 | 1//19
1509 | PGE | 95334 | NEM | EXPNEM | Study in Progress | Solar PV | 276 |  | 2021-08-20 | 2021-08-31 | 7 | 2021-10-06 | 32 | 2021-10-27 | 15 | 2021-10-27 | 2021-12-15 | 32 | 2021-12-15 | 2022-01-14 | 22 | 2022-01-14 | 2022-01-28 | 9 |  |  |  | 2022-01-28 | [12 empty] | 2021-08-20 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1510 | PGE | 94544 | NEM | EXPNEM | Application Review in Progress | Solar PV | 312.82 |  | 2021-08-21 | 2021-08-28 | 5 | [29 empty] | 2021-08-21 | 2021-09-09 | 12 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1511 | PGE | 95472 | NEM | EXPNEM | Commercial | Solar PV | 50.209 |  | 2021-08-22 | 2021-08-31 | 6 | 2021-09-20 | 19 | 2021-10-11 | 15 | [15 empty] | 2021-10-11 | 2021-10-11 | 0 | 2021-10-11 | 2021-10-15 | 4 | [5 empty] | 0 | [5 empty] | 2021-11-15 | 2021-11-18 | 3 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-15 | 2021-11-15 | 0 | 2021-11-18 |  | 2021-11-19 | 1 | 1//19
1512 | PGE | 95448 | NEM | EXPNEM | Commercial | Solar PV | 30.159 |  | 2021-08-23 | 2021-08-30 | 5 | 2021-09-03 | 9 | 2021-09-27 | 15 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-14 | 13 | [5 empty] | 0 | [5 empty] | 2022-01-03 | 2022-01-12 | 7 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-03 | 2022-01-03 | 0 | 2022-01-12 |  | 2022-01-14 | 2 | 1//19
1513 | PGE | 96056 | NEM | EXPNEM | Commercial | Solar PV | 115.456 |  | 2021-08-23 | 2021-08-30 | 5 | 2021-10-05 | 30 | 2021-10-20 | 11 | [15 empty] | 2021-10-20 | 2021-10-20 | 0 | 2021-10-20 | 2021-12-15 | 37 |  |  |  |  | 2021-08-23 | 0 | [5 empty] | 2021-12-16 | 2022-01-12 | 19 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-16 | 2022-01-06 | 15 | 2022-01-12 |  | 2022-01-14 | 2 | 1//19
1514 | PGE | 95334 | NEM | EXPNEM | Study in Progress | Solar PV | 840 |  | 2021-08-23 | 2021-08-31 | 6 | 2021-09-10 | 13 | 2021-09-27 | 11 | 2021-09-27 | 2021-10-29 | 24 | 2021-10-29 | 2021-11-30 | 19 | 2021-11-30 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1515 | PGE | 93463 | NEM | EXPNEM | Implementation | Solar PV | 40.252 |  | 2021-08-23 | 2021-08-31 | 6 | 2021-09-01 | 7 | 2021-09-14 | 8 | [15 empty] | 2021-09-14 | 2021-09-14 | 0 | 2021-09-14 | 2021-09-20 | 4 |  |  |  |  | 2021-08-23 | 2021-09-10 | 13 | [7 empty] | 2021-10-05 | 2022-01-12 | 67 | 1//19 | 1//19 |  | 2022-02-10 | 2022-04-05 | 38 | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1517 | PGE | 95361 | NEM | EXPNEM | Commercial | Solar PV | 44.494 |  | 2021-08-23 | 2021-09-02 | 8 | 2021-09-13 | 14 | 2021-09-27 | 10 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-01 | 4 | [5 empty] | 0 | [5 empty] | 2021-10-01 | 2021-11-02 | 22 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-01 | 2021-10-22 | 15 | 2021-11-02 |  | 2021-11-02 | 0 | 1//19
1518 | PGE | 93702 | NEM | EXPNEM | IA in Progress | Solar PV | 288 |  | 2021-08-24 | 2021-08-30 | 4 | 2021-09-22 | 20 | 2021-10-05 | 9 | [15 empty] | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | 2022-02-15 | 91 |  |  |  |  | 2021-08-24 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1519 | PGE | 94027 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 78.035 |  | 2021-08-24 | 2021-09-07 | 9 | 2021-10-18 | 38 | 2021-10-21 | 3 | [18 empty] | 2021-08-24 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1520 | PGE | 93704 | NEM | EXPNEM | Commercial | Solar PV | 147.207 |  | 2021-08-24 | 2021-08-30 | 4 | 2021-09-20 | 18 | 2021-10-07 | 13 | [15 empty] | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2022-03-15 | 108 |  |  |  |  | 2021-08-24 | 2021-09-20 | 18 |  |  |  |  | 2022-03-02 | 2022-03-09 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-02 | 2022-03-02 | 0 | 2022-03-09 |  | 2022-03-21 | 8 | 1//19
1521 | PGE | 95222 | NEM | SNEM | Application Submitted | Solar PV | 7392 |  | 2021-08-24 | 2021-09-01 | 6 | [22 empty] | 2021-08-24 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1522 | PGE | 93726 | NEM | EXPNEM | IA in Progress | Solar PV | 240 |  | 2021-08-24 | 2021-08-30 | 4 | 2021-08-30 | 4 | 2021-09-21 | 15 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [6 empty] | 2021-08-24 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1523 | PGE | 93721 | NEM | EXPNEM | IA in Progress | Solar PV | 192 |  | 2021-08-24 | 2021-08-30 | 4 | 2021-08-30 | 4 | 2021-09-21 | 15 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | 2022-02-14 | 100 |  |  |  |  | 2021-08-24 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1524 | PGE | 93722 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-08-24 | 2021-08-30 | 4 | 2021-09-08 | 10 | 2021-09-22 | 10 | [15 empty] | 2021-09-22 | 2021-09-22 | 0 | 2021-09-22 | [6 empty] | 2021-08-24 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1525 | PGE | 95020 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.009 |  | 2021-08-25 | 2021-09-07 | 8 | 2021-09-29 | 24 | 2021-10-04 | 3 | [18 empty] | 2021-08-25 | [7 empty] | 0 | [5 empty] | 2021-10-07 | 2021-10-07 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-07 |  |  | 2021-10-07 |  | 2021-10-07 | 0 | 1//19
1526 | PGE | 95965 | NEM | EXPNEM | Application Review in Progress | Solar PV | 241.512 |  | 2021-08-25 | 2021-09-08 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1527 | PGE | 95215 | NEM | EXPNEM | Commercial | Solar PV | 57.873 |  | 2021-08-25 | 2021-08-31 | 4 | 2021-09-07 | 8 | 2021-10-13 | 26 | [15 empty] | 2021-10-13 | 2021-10-13 | 0 | 2021-10-13 | 2021-11-05 | 17 | [5 empty] | 0 | [5 empty] | 2022-03-16 | 2022-03-23 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-16 | 2022-03-17 | 1 | 2022-03-23 |  | 2022-03-25 | 2 | 1//19
1528 | PGE | 93631 | NEM | EXPNEM | Implementation | Solar PV | 150 |  | 2021-08-25 | 2021-09-09 | 10 | 2021-09-10 | 11 | 2021-09-27 | 11 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-09-29 | 2 |  |  |  |  | 2021-08-25 | 2021-09-23 | 20 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1529 | PGE | 95466 | NEM | EXPNEM | Application Review in Progress | Solar PV | 34.348 |  | 2021-08-25 | 2021-08-31 | 4 | [29 empty] | 2021-08-25 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1530 | PGE | 95695 | NEM | EXPNEM | Implementation | Solar PV | 150 |  | 2021-08-25 | 2021-09-03 | 7 | 2021-09-10 | 11 | 2021-09-27 | 11 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-09-29 | 2 |  |  |  |  | 2021-08-25 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1531 | PGE | 93307 | NEM | EXPNEM | IA in Progress | Solar PV | 330 |  | 2021-08-25 | 2021-08-31 | 4 | 2021-09-07 | 8 | 2021-09-27 | 14 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | [6 empty] | 2021-09-01 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1532 | PGE | 95466 | NEM | EXPNEM | Application Review in Progress | Solar PV | 104.35 |  | 2021-08-25 | 2021-08-31 | 4 | [29 empty] | 2021-08-25 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1533 | PGE | 93380 | Non-NEM | RESBCT | Study in Progress | Solar PV | 5000 |  | 2021-08-25 | 2021-08-25 | 0 | 2021-09-08 | 9 | [5 empty] | 2021-09-08 | 2021-10-05 | 19 | 2021-10-05 | 2021-10-14 | 7 | 2021-12-03 | 2022-03-17 | 72 | 2021-10-14 | 2021-10-14 | 0 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1535 | PGE | 95203 | NEM | EXPNEM | IA in Progress | Solar PV | 89.406 |  | 2021-08-25 | 2021-09-01 | 5 | 2022-01-12 | 96 | 2022-01-27 | 10 | 2022-01-27 | 2022-03-08 | 27 | [12 empty] | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 | 2022-03-15 | 5 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1536 | PGE | 94533 | NEM | EXPNEM | IA in Progress | Solar PV | 58.856 |  | 2021-08-25 | 2021-09-01 | 5 | 2022-02-17 | 121 | 2022-03-08 | 12 | [15 empty] | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 | 2022-03-23 | 11 |  |  |  |  | 2021-08-25 | 0 | [5 empty] | 2022-03-23 | 2022-03-29 | 4 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-23 | 2022-03-23 | 0 | 2022-03-29 |  |  |  | 1//19
1537 | PGE | 93301 | NEM | EXPNEM | Application Review in Progress | Solar PV | 165.528 |  | 2021-08-25 | 2021-09-07 | 8 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1538 | PGE | 94560 | NEM | EXPNEM | Commercial | Solar PV | 375 |  | 2021-08-25 | 2021-09-01 | 5 | 2021-09-15 | 14 | 2021-09-30 | 11 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | 2021-10-15 | 11 |  |  |  |  | 2021-08-25 | 2021-09-20 | 17 |  |  |  |  | 2022-01-21 | 2022-01-26 | 3 | 2021-10-27 | 2022-03-04 | 88 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-21 | 2022-01-23 | 0 | 2022-01-26 |  | 2022-02-02 | 5 | 1//19
1539 | PGE | 93446 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.925 |  | 2021-08-25 | 2021-09-08 | 9 | 2021-09-22 | 19 | 2021-09-23 | 1 | [18 empty] | 2021-09-09 | [7 empty] | 0 | [5 empty] | 2021-11-19 | 2021-11-19 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-19 |  |  | 2021-11-19 |  | 2021-11-19 | 0 | 1//19
1540 | PGE | 93706 | NEM | EXPNEM | IA in Progress | Solar PV | 206 |  | 2021-08-25 | 2021-09-02 | 6 | 2021-09-02 | 6 | 2021-09-21 | 12 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [6 empty] | 2021-08-25 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1541 | PGE | 93702 | NEM | EXPNEM | IA in Progress | Solar PV | 231.357 |  | 2021-08-25 | 2021-09-02 | 6 | 2021-09-02 | 6 | 2021-09-21 | 12 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [6 empty] | 2021-08-25 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1542 | PGE | 95361 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-08-25 | 2021-09-02 | 6 | 2021-09-10 | 11 | 2021-10-13 | 23 | [15 empty] | 2021-10-13 | 2021-10-13 | 0 | 2021-10-13 | [6 empty] | 2021-08-25 | 2021-09-14 | 13 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1543 | PGE | 93901 | NEM | EXPNEM | Implementation | Solar PV | 200 |  | 2021-08-26 | 2021-09-07 | 7 | 2021-09-14 | 12 | 2021-10-04 | 14 | [15 empty] | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04 | 2021-12-28 | 58 | [5 empty] | 0 | [8 empty] | 2022-04-06 |  | 5 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1544 | PGE | 95969 | NEM | EXPNEM | IA in Progress | Solar PV | 200 |  | 2021-08-26 | 2021-09-02 | 5 | 2021-10-22 | 40 | 2021-11-08 | 11 | [15 empty] | 2021-11-08 | 2021-11-08 | 0 | 2021-11-08 | [6 empty] | 2021-08-26 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1545 | PGE | 93702 | NEM | EXPNEM | IA in Progress | Solar PV | 252 |  | 2021-08-26 | 2021-09-02 | 5 | 2021-09-02 | 5 | 2021-09-21 | 12 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [6 empty] | 2021-08-26 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1546 | PGE | 93926 | NEM | EXPNEM | Implementation | Solar PV | 276 |  | 2021-08-26 | 2021-09-09 | 9 | 2021-09-14 | 12 | 2021-10-22 | 28 | [15 empty] | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | 2021-12-30 | 46 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1547 | PGE | 95060 | NEM | EXPNEM | IA in Progress | Solar PV | 45.572 |  | 2021-08-26 | 2021-09-02 | 5 | 2021-10-27 | 43 | 2021-11-18 | 15 | [15 empty] | 2021-11-18 | 2021-11-18 | 0 | 2021-11-18 | [6 empty] | 2021-08-26 | 2021-09-10 | 10 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1548 | PGE | 93705 | NEM | EXPNEM | IA in Progress | Solar PV | 192 |  | 2021-08-26 | 2021-09-02 | 5 | 2021-09-02 | 5 | 2021-09-22 | 13 | [15 empty] | 2021-09-22 | 2021-09-22 | 0 | 2021-09-22 | [6 empty] | 2021-08-26 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1549 | PGE | 93960 | NEM | EXPNEM | Implementation | Solar PV | 180 |  | 2021-08-26 | 2021-09-07 | 7 | 2021-09-14 | 12 | 2021-10-08 | 18 | [15 empty] | 2021-10-08 | 2021-10-08 | 0 | 2021-10-08 | 2021-12-30 | 56 | [5 empty] | 0 | [8 empty] | 2022-04-06 |  | 5 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1551 | PGE | 95993 | Non-NEM | RESBCT | Study in Progress | Solar PV | 106.368 |  | 2021-08-26 | 2021-08-27 | 1 | 2021-09-15 | 13 | 2021-10-05 | 14 | 2021-10-18 | 2021-11-22 | 24 | 2021-12-17 | 2022-01-07 | 15 | 2022-01-07 | 2022-01-07 | 0 | 2022-01-11 |  |  | 2022-01-07 | 2022-01-07 | 0 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1552 | PGE | 95616 | NEM | VNEM | Application Review in Progress | Solar PV | 116.08 |  | 2021-08-27 | 2021-09-13 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1553 | PGE | 95120 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.2 |  | 2021-08-27 | 2021-09-08 | 7 | [22 empty] | 2021-08-27 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1554 | PGE | 93446 | NEM | EXPNEM | Application Review in Progress | Solar PV | 88.2 |  | 2021-08-27 | 2021-09-07 | 6 | [30 empty] | 0 | [8 empty] | 2022-01-12 |  | 65 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1555 | PGE | 94566 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 3084.193 |  | 2021-08-27 | 2021-09-13 | 10 | 2021-10-06 | 27 | [5 empty] | 2021-10-08 | 2021-11-10 | 23 | 2021-11-10 | [18 empty] | 2021-08-27 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1556 | PGE | 95360 | NEM | EXPNEM | IA in Progress | Solar PV | 840 |  | 2021-08-27 | 2021-09-13 | 10 | 2021-09-14 | 11 | 2021-10-13 | 21 | 2021-10-13 | 2021-11-24 | 29 | 2021-11-24 | 2021-12-17 | 15 | 2021-12-17 | 2021-12-17 |  | 2021-12-17 | 2022-03-16 | 64 | 2021-12-17 | [13 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1557 | PGE | 93380 | Non-NEM | RESBCT | Study in Progress | Solar PV | 5000 |  | 2021-08-27 | 2021-08-30 | 1 | 2021-09-08 | 7 | [5 empty] | 2021-09-08 | 2021-10-05 | 19 | 2021-10-05 | 2021-10-14 | 7 | 2021-12-03 | 2022-03-17 | 72 | 2021-10-14 | 2021-10-14 | 0 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1558 | PGE | 93311 | Non-NEM | RESBCT | IA in Progress | Solar PV | 5000 |  | 2021-08-27 | 2021-08-30 | 1 | 2021-09-22 | 17 | [5 empty] | 2021-09-22 | 2021-10-20 | 20 | 2021-10-20 | 2021-10-25 | 3 | 2021-12-13 | 2022-03-08 | 59 | 2021-10-25 | 2021-10-25 | 0 | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1559 | PGE | 93638 | NEM | VNEMSOMAH | Implementation | Solar PV | 38.4 |  | 2021-08-27 | 2021-08-30 | 1 | 2021-08-31 | 2 | 2021-09-17 | 12 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | 2022-03-16 | 123 |  |  |  |  | 2021-08-27 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1560 | PGE | 93638 | NEM | VNEMSOMAH | Implementation | Solar PV | 38.4 |  | 2021-08-27 | 2021-08-30 | 1 | 2021-08-31 | 2 | 2021-09-17 | 12 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | 2022-03-16 | 123 |  |  |  |  | 2021-08-27 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1561 | PGE | 93638 | NEM | VNEMSOMAH | Implementation | Solar PV | 38.4 |  | 2021-08-27 | 2021-08-30 | 1 | 2021-08-31 | 2 | 2021-09-17 | 12 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | 2022-03-16 | 123 |  |  |  |  | 2021-08-27 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1562 | PGE | 93307 | NEM | EXPNEM | Application Review in Progress | Solar PV | 54.292 |  | 2021-08-27 | 2021-09-02 | 4 | [29 empty] | 2021-08-27 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1563 | PGE | 95121 | NEM | EXPNEM | IA in Progress | Solar PV | 72.22 |  | 2021-08-30 | 2021-09-07 | 5 | 2021-10-05 | 25 | 2021-10-20 | 11 | [15 empty] | 2021-10-20 | 2021-10-21 | 1 | 2021-10-21 | 2022-01-10 | 54 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1564 | PGE | 94509 | NEM | EXPNEM | Implementation | Solar PV | 86.65 |  | 2021-08-30 | 2021-09-13 | 9 | 2021-09-22 | 16 | 2021-10-13 | 15 | [15 empty] | 2021-11-17 | 2021-12-06 | 11 | 2021-12-06 | 2021-12-06 | 0 | [5 empty] | 0 | [5 empty] | 2022-03-03 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-03 | 2022-03-03 | 0 |  |  |  |  | 1//19
1565 | PGE | 95472 | NEM | EXPNEM | Commercial | Solar PV | 34.179 |  | 2021-08-30 | 2021-09-07 | 5 | 2021-09-07 | 5 | 2021-09-24 | 13 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | 2021-10-14 | 14 |  |  |  |  | 2021-08-30 | 2021-09-10 | 8 |  |  |  |  | 2021-11-21 | 2021-11-30 | 4 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-21 | 2021-11-21 | 0 | 2021-11-30 |  | 2021-12-03 | 3 | 1//19
1566 | PGE | 93926 | NEM | EXPNEM | IA in Progress | Solar PV | 390 |  | 2021-08-30 | 2021-09-02 | 3 | 2021-09-03 | 4 | 2021-09-21 | 11 | 2021-09-21 | 2021-11-24 | 45 | 2021-11-24 | 2021-12-20 | 16 | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2022-03-30 | 73 | 2021-12-20 |  |  | 2022-03-30 | [10 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1567 | PGE | 94087 | NEM | EXPNEM | IA in Progress | Solar PV | 125 |  | 2021-08-30 | 2021-09-07 | 5 | 2021-09-21 | 15 | 2021-10-12 | 15 | [15 empty] | 2021-10-12 | 2021-10-12 | 0 | 2021-10-12 | 2021-11-02 | 15 |  |  |  |  | 2021-08-30 | 2021-09-10 | 8 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1568 | PGE | 95003 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-08-30 | 2021-09-13 | 9 | 2021-09-13 | 9 | 2021-09-13 | 0 | [18 empty] | 2021-08-30 | [7 empty] | 0 | [5 empty] | 2021-09-13 | 2021-09-13 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-13 |  |  | 2021-09-13 |  | 2021-09-13 | 0 | 1//19
1569 | PGE | 93930 | NEM | EXPNEM | Implementation | Solar PV | 336 |  | 2021-08-30 | 2021-09-13 | 9 | 2021-09-14 | 10 | 2021-11-03 | 36 | [15 empty] | 2021-11-03 | 2021-11-03 | 0 | 2021-11-03 | 2021-12-30 | 38 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1570 | PGE | 93901 | NEM | EXPNEM | Implementation | Solar PV | 220 |  | 2021-08-31 | 2021-09-13 | 8 | 2021-09-14 | 9 | 2021-09-30 | 12 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | 2021-12-15 | 51 |  |  |  |  | 2021-08-31 | 2021-09-21 | 14 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1571 | PGE | 93314 | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-08-31 | 2021-09-13 | 8 | 2021-09-13 | 8 | 2021-09-21 | 6 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | 2021-11-18 | 41 |  |  |  |  | 2021-08-31 | 2021-09-21 | 14 |  |  |  |  | 2021-12-20 | 2021-12-28 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-20 | 2021-12-20 | 0 | 2021-12-28 |  | 2021-12-29 | 1 | 1//19
1574 | PGE | 95030 | NEM | EXPNEM | Commercial | Solar PV | 34.9 |  | 2021-08-31 | 2021-09-07 | 4 | 2021-11-26 | 59 | 2021-12-06 | 5 | [15 empty] | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-22 | 12 | [5 empty] | 0 | [5 empty] | 2021-12-22 | 2021-12-30 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-22 | 2021-12-23 | 1 | 2021-12-30 |  | 2021-12-31 | 1 | 1//19
1575 | PGE | 93242 | NEM | EXPNEM | Study in Progress | Solar PV | 1560 |  | 2021-08-31 | 2021-09-01 | 1 | 2021-10-21 | 36 | [5 empty] | 2021-10-21 | 2021-11-17 | 18 | 2021-11-17 | 2021-11-18 | 1 | 2022-01-05 | 2022-03-31 | 59 | 2021-11-18 | 2021-12-02 | 8 | [10 empty] | 2021-08-31 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1576 | PGE | 93908 | NEM | EXPNEM | Implementation | Solar PV | 136 |  | 2021-08-31 | 2021-09-13 | 8 | 2021-09-14 | 9 | 2021-09-30 | 12 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | 2021-12-15 | 51 |  |  |  |  | 2021-08-31 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1577 | PGE | 94103 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-09-01 | 2021-09-15 | 9 | 2021-10-14 | 30 | 2021-10-20 | 4 | [15 empty] | 2021-10-20 | 2021-10-20 | 0 | 2021-10-20 | 2021-11-04 | 11 | [5 empty] | 0 | [5 empty] | 2021-11-10 | 2021-11-18 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-10 | 2021-11-12 | 1 | 2021-11-18 |  | 2021-11-24 | 4 | 1//19
1578 | PGE | 93703 | NEM | EXPNEM | Implementation | Solar PV | 82.146 |  | 2021-09-01 | 2021-09-16 | 10 | 2021-09-27 | 17 | 2021-10-18 | 15 | [15 empty] | 2021-10-18 | 2021-10-18 | 0 | 2021-10-18 | 2022-01-13 | 60 | [5 empty] | 0 | [8 empty] | 2022-02-11 |  | 43 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1579 | PGE | 93720 | NEM | EXPNEM | Implementation | Solar PV | 344.924 |  | 2021-09-01 | 2021-09-16 | 10 | 2021-09-27 | 17 | 2021-10-18 | 15 | [15 empty] | 2021-10-18 | 2021-10-18 | 0 | 2021-10-18 | 2021-11-23 | 25 | [5 empty] | 0 | [8 empty] | 2022-03-11 |  | 23 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1580 | PGE | 95616 | NEM | EXPNEM | Commercial | Solar PV | 51.508 |  | 2021-09-01 | 2021-09-15 | 9 | 2021-10-05 | 23 | 2021-10-20 | 11 | [15 empty] | 2021-10-20 | 2021-10-20 | 0 | 2021-10-20 | 2021-10-27 | 5 | [5 empty] | 0 | [5 empty] | 2021-11-02 | 2021-11-09 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-02 | 2021-11-02 | 0 | 2021-11-09 |  | 2021-11-15 | 3 | 1//19
1581 | PGE | 95616 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-09-01 | 2021-09-15 | 9 | 2021-09-17 | 11 | 2021-10-20 | 23 | [15 empty] | 2021-10-20 | 2021-10-20 | 0 | 2021-10-20 | 2021-10-26 | 4 | [5 empty] | 0 | [5 empty] | 2021-11-02 | 2021-11-09 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-02 | 2021-11-02 | 0 | 2021-11-09 |  | 2021-11-23 | 9 | 1//19
1582 | PGE | 95020 | NEM | EXPNEM | IA in Progress | Solar PV | 75.278 |  | 2021-09-02 | 2021-09-15 | 8 | 2021-10-12 | 27 | 2021-12-07 | 37 | [15 empty] | 2021-12-07 | 2021-12-07 | 0 | 2021-12-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1583 | PGE | 93268 | NEM | EXPNEM | Commercial | Solar PV | 95.822 |  | 2021-09-02 | 2021-09-09 | 4 | 2021-10-12 | 27 | 2021-10-22 | 8 | [15 empty] | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | 2022-02-22 | 82 |  |  |  |  | 2021-09-02 | 0 | [5 empty] | 2022-02-01 | 2022-02-27 | 17 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-01 | 2022-02-24 | 16 | 2022-02-27 |  | 2022-03-03 | 3 | 1//19
1584 | PGE | 94510 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.599 |  | 2021-09-02 | 2021-09-15 | 8 | 2021-10-08 | 25 | 2021-10-11 | 1 | [18 empty] | 2021-09-02 | [6 empty] | 2021-09-02 | 0 | [5 empty] | 2021-10-18 | 2021-10-18 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-18 |  |  | 2021-10-18 |  | 2021-10-18 | 0 | 1//19
1585 | PGE | 95258 | NEM | EXPNEM | Implementation | Solar PV | 270 |  | 2021-09-02 | 2021-09-17 | 10 | 2021-11-03 | 43 | 2022-01-03 | 40 | [15 empty] | 2022-01-03 | 2022-01-03 | 0 | 2022-01-03 | 2022-01-05 | 2 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1586 | PGE | 95240 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-09-02 | 2021-09-17 | 10 | 2021-09-22 | 13 | 2021-10-13 | 15 | [15 empty] | 2021-10-13 | 2021-11-03 | 15 | 2021-11-03 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1587 | PGE | 94591 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.028 |  | 2021-09-02 | 2021-09-15 | 8 | 2021-10-08 | 25 | 2021-10-11 | 1 | [18 empty] | 2021-09-02 | [7 empty] | 0 | [5 empty] | 2021-10-11 | 2021-10-11 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-11 |  |  | 2021-10-11 |  | 2021-10-11 | 0 | 1//19
1588 | PGE | 93710 | NEM | EXPNEM | Commercial | Solar PV | 175 |  | 2021-09-02 | 2021-09-15 | 8 | 2021-10-15 | 30 | 2021-10-29 | 10 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | 2021-11-01 | 1 | [5 empty] | 0 | [5 empty] | 2021-12-16 | 2022-01-11 | 18 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-16 | 2022-01-05 | 14 | 2022-01-11 |  | 2022-01-13 | 2 | 1//19
1589 | PGE | 95341 | NEM | EXPNEM | IA in Progress | Solar PV | 840 |  | 2021-09-02 | 2021-09-16 | 9 | 2021-09-27 | 16 | 2021-11-01 | 25 | [15 empty] | 2021-11-01 | 2021-11-01 | 0 | 2021-11-01 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1590 | PGE | 93960 | NEM | EXPNEM | IA in Progress | Solar PV | 500 |  | 2021-09-02 | 2021-09-14 | 7 | 2021-09-14 | 7 | [5 empty] | 2021-09-17 | 2021-10-11 | 16 | 2021-10-11 | 2021-10-11 |  | 2021-10-11 | 2022-02-23 | 98 | 2021-10-11 |  |  | 2022-02-23 | 2022-02-23 | 0 | 2022-02-23 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1591 | PGE | 95304 | NEM | EXPNEM | IA in Progress | Solar PV | 135.897 |  | 2021-09-02 | 2021-09-15 | 8 | 2021-10-12 | 27 | 2021-10-26 | 10 | [15 empty] | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26 | 2021-11-05 | 8 |  |  |  |  | 2021-09-02 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1592 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 72.22 |  | 2021-09-03 | 2021-09-08 | 2 | 2021-09-15 | 7 | 2021-10-06 | 15 | [15 empty] | 2021-10-06 | 2021-10-27 | 15 | 2021-10-27 | [6 empty] | 2021-09-03 | 0 |  | 2021-12-20 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1593 | PGE | 93725 | NEM | EXPNEM | Withdrawn | Solar PV | 40.252 |  | 2021-09-03 | 2021-09-15 | 7 | 2021-12-16 | 70 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1594 | PGE | 94533 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100 |  | 2021-09-07 | 2021-09-08 | 1 | 2021-09-13 | 4 | 2021-10-01 | 14 | [15 empty] | 2021-10-01 | 2021-10-01 | 0 | 2021-10-01 | [6 empty] | 2021-09-07 | 2021-09-14 | 5 |  | 2021-09-17 | 2021-10-01 | 10 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1595 | PGE | 93720 | NEM | EXPNEM | Commercial | Solar PV | 591.6 |  | 2021-09-07 | 2021-09-14 | 5 | 2021-09-16 | 7 | 2021-09-24 | 6 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | 2021-10-01 | 5 |  |  |  |  | 2021-09-07 | 2021-09-21 | 10 |  |  |  |  | 2022-01-24 | 2022-02-04 | 9 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-24 | 2022-01-24 | 0 | 2022-02-04 |  | 2022-02-04 | 0 | 1//19
1596 | PGE | 94533 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100 |  | 2021-09-07 | 2021-09-08 | 1 | 2021-09-13 | 4 | 2021-10-01 | 14 | [15 empty] | 2021-10-01 | 2021-10-01 | 0 | 2021-10-01 | [6 empty] | 2021-09-07 | 2021-09-14 | 5 |  | 2021-09-17 | 2021-10-01 | 10 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1597 | PGE | 93727 | NEM | EXPNEM | Commercial | Solar PV | 34.8 |  | 2021-09-07 | 2021-09-13 | 4 | 2021-09-13 | 4 | 2021-09-29 | 12 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | 2021-10-27 | 20 | [5 empty] | 0 | [5 empty] | 2021-12-31 | 2022-01-18 | 11 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-31 | 2022-01-18 | 11 | 2022-01-18 |  | 2022-01-19 | 1 | 1//19
1598 | PGE | 94533 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100 |  | 2021-09-07 | 2021-09-08 | 1 | 2021-09-13 | 4 | 2021-10-01 | 14 | [15 empty] | 2021-10-01 | 2021-10-01 | 0 | 2021-10-01 | [6 empty] | 2021-09-07 | 2021-09-14 | 5 |  | 2021-09-17 | 2021-10-01 | 10 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1599 | PGE | 95062 | NEM | EXPNEM | Implementation | Solar PV | 240 |  | 2021-09-07 | 2021-09-08 | 1 | 2021-09-13 | 4 | 2021-09-28 | 11 | [15 empty] | 2021-09-28 | 2021-09-28 | 0 | 2021-09-28 | 2022-02-22 | 100 |  |  |  |  | 2021-09-07 | 2021-09-20 | 9 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1600 | PGE | 94533 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 43.2 |  | 2021-09-08 | 2021-09-10 | 2 | 2021-09-13 | 3 | 2021-10-01 | 14 | [15 empty] | 2021-10-01 | 2021-10-01 | 0 | 2021-10-01 | [6 empty] | 2021-09-10 | 2021-09-14 | 2 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1601 | PGE | 95125 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 85.601 |  | 2021-09-08 | 2021-09-22 | 10 | 2021-10-04 | 18 | 2021-10-25 | 15 | [15 empty] | 2021-10-25 | 2021-11-16 | 15 | 2021-11-16 | [6 empty] | 2021-09-08 | 0 |  |  | 2021-12-15 | 2021-12-15 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1602 | PGE | 95125 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 41.349 |  | 2021-09-08 | 2021-09-22 | 10 | 2021-10-04 | 18 | 2021-10-25 | 15 | [15 empty] | 2021-10-25 | 2021-11-16 | 15 | 2021-11-16 | [6 empty] | 2021-09-08 | 0 |  |  | 2021-11-16 | 2021-11-16 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1603 | PGE | 94546 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 93.276 |  | 2021-09-08 | 2021-09-22 | 10 | 2021-10-04 | 18 | 2021-11-18 | 32 | [15 empty] | 2021-11-18 | 2021-11-18 | 0 | 2021-11-18 | [6 empty] | 2021-09-08 | 0 |  |  | 2021-12-08 | 2021-12-08 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1604 | PGE | 94546 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 61.126 |  | 2021-09-08 | 2021-09-22 | 10 | 2021-10-04 | 18 | 2021-11-18 | 32 | [15 empty] | 2021-11-18 | 2021-11-18 | 0 | 2021-11-18 | [6 empty] | 2021-09-08 | 0 |  |  | 2021-12-08 | 2021-12-08 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1605 | PGE | 93901 | NEM | EXPNEM | Implementation | Solar PV | 150 |  | 2021-09-08 | 2021-09-14 | 4 | 2021-09-15 | 5 | 2021-11-05 | 37 | [15 empty] | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05 | 2021-12-15 | 25 |  |  |  |  | 2021-09-08 | 2021-09-22 | 10 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1606 | PGE | 93308 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-09-08 | 2021-09-20 | 8 | 2021-09-20 | 8 | 2021-09-23 | 3 | [15 empty] | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | 2021-09-24 | 1 | [5 empty] | 0 | [5 empty] | 2021-10-20 | 2022-03-17 | 101 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-20 | 2022-03-15 | 99 | 2022-03-17 |  | 2022-03-18 | 1 | 1//19
1607 | PGE | 95120 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 40.163 |  | 2021-09-08 | 2021-09-08 | 0 | 2021-12-07 | 61 | 2021-12-13 | 4 | [18 empty] | 2021-09-08 | [7 empty] | 0 | [5 empty] | 2021-12-07 | 2021-12-13 | 4 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-07 |  |  | 2021-12-13 |  | 2021-12-13 | 0 | 1//19
1608 | PGE | 95120 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.621 |  | 2021-09-08 | 2021-09-17 | 7 | 2021-09-17 | 7 | 2021-09-19 | 0 | [18 empty] | 2021-09-08 | [7 empty] | 0 | [5 empty] | 2021-09-19 | 2021-09-19 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-19 |  |  | 2021-09-19 |  | 2021-09-19 | 0 | 1//19
1609 | PGE | 95650 | NEM | EXPNEM | Implementation | Solar PV | 34.179 |  | 2021-09-08 | 2021-09-22 | 10 | 2021-11-16 | 48 | 2021-12-02 | 10 | [15 empty] | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02 | 2022-03-10 | 68 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1610 | PGE | 95492 | NEM | EXPNEM | Study in Progress | Solar PV | 1200 |  | 2021-09-09 | 2021-09-13 | 2 | 2021-12-10 | 63 | 2021-12-31 | 15 | 2022-01-06 | 2022-02-02 | 18 | [23 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1611 | PGE | 94107 | Non-NEM | Non-Export | Implementation | ENGN | 60 |  | 2021-09-09 | 2021-09-09 | 0 | 2021-09-22 | 9 | 2021-10-05 | 9 | [15 empty] | 2021-10-22 | 2021-10-27 | 3 | 2021-10-27 | 2022-01-12 | 52 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1613 | PGE | 93611 | NEM | VNEMMASH | Implementation | Solar PV | 39.875 |  | 2021-09-09 | 2021-09-15 | 4 | 2021-12-01 | 56 | 2021-12-08 | 5 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | 2021-12-14 | 4 | [5 empty] | 0 |  | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1615 | PGE | 93611 | NEM | VNEMMASH | Implementation | Solar PV | 50.025 |  | 2021-09-09 | 2021-09-15 | 4 | 2021-12-01 | 56 | 2021-12-08 | 5 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | 2021-12-14 | 4 | [5 empty] | 0 |  | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1617 | PGE | 95667 | NEM | EXPNEM | Implementation | Solar PV | 178.024 |  | 2021-09-09 | 2021-09-15 | 4 | 2021-10-04 | 17 | 2021-10-21 | 13 | [15 empty] | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21 | 2021-11-09 | 13 | [5 empty] | 0 | [8 empty] | 2021-12-01 | 2022-03-18 | 76 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1618 | PGE | 95220 | NEM | EXPNEM | Study in Progress | Solar PV | 840 |  | 2021-09-09 | 2021-09-13 | 2 | 2021-11-23 | 52 | 2021-12-09 | 10 | 2021-12-09 | 2022-01-07 | 21 | 2022-01-07 | 2022-02-02 | 17 | 2022-02-02 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1619 | PGE | 95540 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 630 |  | 2021-09-09 | 2021-09-10 | 1 | 2021-09-29 | 14 | 2021-11-16 | 33 | 2021-12-07 | 2022-01-05 | 21 | 2022-02-18 | 2022-03-15 | 16 | 2022-03-15 | 2022-03-29 | 10 |  |  |  | 2022-03-29 |  |  | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | 2021-10-11 | 7 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1620 | PGE | 94551 | NEM | EXPNEM | Withdrawn | Solar PV | 500 |  | 2021-09-09 | 2021-09-13 | 2 | 2021-09-13 | 2 | 2021-09-29 | 12 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | [6 empty] | 2021-09-15 | 2021-09-22 | 5 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1621 | PGE | 95616 | NEM | EXPNEM | Implementation | Solar PV | 131.66 |  | 2021-09-10 | 2021-09-15 | 3 | 2021-09-23 | 9 | 2021-10-07 | 10 | [15 empty] | 2021-10-07 | 2021-10-08 | 1 | 2021-10-08 | 2022-01-10 | 63 |  |  |  |  | 2021-09-10 | 2021-09-22 | 8 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1622 | PGE | 95648 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-09-10 | 2021-09-24 | 10 | 2021-09-24 | 10 | 2021-09-28 | 2 | [18 empty] | 2021-09-10 | [6 empty] | 2021-09-10 | 0 | [5 empty] | 2021-11-03 | 2021-11-03 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-03 |  |  | 2021-11-03 |  | 2021-11-03 | 0 | 1//19
1623 | PGE | 95202 | NEM | EXPNEM | Implementation | Solar PV | 82.454 |  | 2021-09-10 | 2021-09-15 | 3 | 2021-09-15 | 3 | 2021-09-30 | 11 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | 2021-10-14 | 10 |  |  |  |  | 2021-09-10 | 2021-09-22 | 8 | [7 empty] | 2022-02-08 |  | 46 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1624 | PGE | 93245 | NEM | EXPNEM | Implementation | Solar PV | 80 |  | 2021-09-10 | 2021-09-15 | 3 | 2021-09-29 | 13 | 2021-10-19 | 14 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2022-01-11 | 57 |  |  |  |  | 2021-09-10 | 0 | [8 empty] | 2022-02-15 |  | 41 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1625 | PGE | 95236 | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2021-09-10 | 2021-09-15 | 3 | 2022-03-02 | 118 | 2022-03-17 | 11 | 2022-03-17 | [24 empty] | 2021-09-10 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1626 | PGE | 95403 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.287 |  | 2021-09-10 | 2021-09-24 | 10 | 2021-11-02 | 37 | 2021-11-03 | 1 | [18 empty] | 2021-09-10 | [7 empty] | 0 | [5 empty] | 2021-11-03 | 2021-11-03 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-03 |  |  | 2021-11-03 |  | 2021-11-03 | 0 | 1//19
1627 | PGE | 94024 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.63 |  | 2021-09-13 | 2021-09-27 | 10 | 2021-10-25 | 30 | 2021-10-27 | 2 | [18 empty] | 2021-10-19 | [7 empty] | 0 | [5 empty] | 2021-10-27 | 2021-10-27 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-27 |  |  | 2021-10-27 |  | 2021-10-27 | 0 | 1//19
1628 | PGE | 95376 | NEM | EXPNEM | Withdrawn | Solar PV | 95.8 |  | 2021-09-13 | 2021-09-17 | 4 | [29 empty] | 2021-09-13 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1629 | PGE | 93908 | NEM | EXPNEM | Withdrawn | Solar PV | 39.596 |  | 2021-09-13 | 2021-09-27 | 10 | 2021-11-03 | 37 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1630 | PGE | 93427 | NEM | EXPNEM | Implementation | Solar PV | 72 |  | 2021-09-14 | 2021-09-28 | 10 | 2021-12-17 | 65 | 2022-01-07 | 15 | [15 empty] | 2022-01-07 | 2022-01-31 | 15 | 2022-01-31 | 2022-02-14 | 10 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1631 | PGE | 95658 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 32.668 |  | 2021-09-14 | 2021-09-27 | 9 | 2021-10-07 | 17 | 2021-10-11 | 2 | [18 empty] | 2021-09-14 | [7 empty] | 0 | [5 empty] | 2021-10-11 | 2021-10-11 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-11 |  |  | 2021-10-11 |  | 2021-10-11 | 0 | 1//19
1632 | PGE | 93427 | NEM | EXPNEM | IA in Progress | Solar PV | 210 |  | 2021-09-14 | 2021-09-28 | 10 | 2021-10-05 | 15 | 2022-03-23 | 116 | [15 empty] | 2022-03-23 | 2022-03-23 | 0 | 2022-03-23 | [6 empty] | 2021-10-07 | 0 |  | 2021-10-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1633 | PGE | 94503 | NEM | NEM Paired Storage | Implementation | ENGN, Solar PV, Storage | 140 |  | 2021-09-14 | 2021-09-17 | 3 | 2021-09-17 | 3 | 2021-10-18 | 21 | [15 empty] | 2021-10-18 | 2021-10-18 | 0 | 2021-10-18 | 2021-11-19 | 23 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1634 | PGE | 93612 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-09-15 | 2021-09-20 | 3 | 2021-09-20 | 3 | 2021-09-29 | 7 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | 2021-11-19 | 36 | [5 empty] | 0 | [5 empty] | 2021-11-19 | 2021-11-30 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-19 | 2021-11-22 | 1 | 2021-11-30 |  | 2021-11-30 | 0 | 1//19
1635 | PGE | 94526 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-09-15 | 2021-09-27 | 8 | 2021-10-26 | 29 | 2021-10-28 | 2 | [18 empty] | 2021-09-15 | [7 empty] | 0 | [5 empty] | 2021-10-28 | 2021-10-28 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-28 |  |  | 2021-10-28 |  | 2021-10-28 | 0 | 1//19
1636 | PGE | 94022 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.025 |  | 2021-09-15 | 2021-09-15 | 0 | 2021-12-03 | 54 | 2021-12-07 | 2 | [26 empty] | 0 | [5 empty] | 2021-12-07 | 2021-12-08 | 1 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-07 | 2021-12-07 | 0 | 2021-12-08 |  | 2021-12-09 | 1 | 1//19
1637 | PGE | 94556 | NEM | EXPNEM | Implementation | Solar PV | 92.318 |  | 2021-09-15 | 2021-09-20 | 3 | 2021-09-20 | 3 | 2021-10-06 | 12 | [15 empty] | 2021-10-06 | 2021-10-06 | 0 | 2021-10-06 | 2021-10-28 | 16 |  |  |  |  | 2021-09-15 | 2021-09-23 | 6 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1638 | PGE | 93706 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-09-15 | 2021-09-17 | 2 | 2021-09-17 | 2 | 2021-09-28 | 7 | [15 empty] | 2021-09-28 | 2021-09-28 | 0 | 2021-09-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1639 | PGE | 95228 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-09-16 | 2021-09-23 | 5 | 2021-09-23 | 5 | 2021-09-27 | 2 | [18 empty] | 2021-09-16 | [7 empty] | 0 | [5 empty] | 2021-09-28 | 2021-09-28 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-28 |  |  | 2021-09-28 |  | 2021-09-28 | 0 | 1//19
1640 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-09-16 | 2021-09-27 | 7 | 2021-10-26 | 28 | 2021-11-15 | 13 | [15 empty] | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-16 | 1 |  |  |  |  | 2021-09-16 | 0 | [5 empty] | 2021-12-21 | 2021-12-29 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-21 | 2021-12-22 | 1 | 2021-12-29 |  | 2021-12-29 | 0 | 1//19
1641 | PGE | 95111 | NEM | VNEMSOMAH | Implementation | Solar PV | 185.821 |  | 2021-09-16 | 2021-09-23 | 5 | 2021-10-08 | 16 | 2021-11-30 | 34 | [15 empty] | 2021-11-30 | 2021-11-30 | 0 | 2021-11-30 | 2021-12-08 | 6 |  |  |  |  | 2021-09-16 | 0 |  | 2021-11-17 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1642 | PGE | 96007 | NEM | NEMMT | Withdrawn | FUCE, Solar PV | 500 |  | 2021-09-16 | 2021-09-29 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1643 | PGE | 95929 | NEM | EXPNEM | IA in Progress | Solar PV | 1010.281 |  | 2021-09-16 | 2021-09-30 | 10 | 2021-11-03 | 34 | 2021-11-29 | 15 | [15 empty] | 2021-11-29 | 2021-11-30 | 1 | 2021-11-30 | [6 empty] | 2021-09-16 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1646 | PGE | 95035 | NEM | EXPNEM | IA in Progress | Solar PV | 166.5 |  | 2021-09-16 | 2021-09-30 | 10 | 2021-10-20 | 24 | 2022-01-07 | 54 | [15 empty] | 2022-01-07 | 2022-01-07 | 0 | 2022-01-07 | [7 empty] | 0 |  | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1647 | PGE | 94578 | NEM | VNEMMASH | IA in Progress | Solar PV | 43.2 |  | 2021-09-16 | 2021-09-30 | 10 | 2021-12-16 | 62 | 2022-01-05 | 14 | [15 empty] | 2022-01-05 | 2022-01-27 | 15 | 2022-01-27 | 2022-03-11 | 30 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1648 | PGE | 93230 | NEM | EXPNEM | Withdrawn | Solar PV | 2125 |  | 2021-09-17 | 2021-09-20 | 1 | 2021-10-20 | 23 | [5 empty] | 2021-10-29 | 2021-11-29 | 18 | 2021-11-29 | 2021-11-30 | 1 |  |  |  | 2021-11-30 | [13 empty] | 0 |  | 2021-11-01 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1649 | PGE | 94063 | NEM | EXPNEM | IA in Progress | Solar PV | 172.8 |  | 2021-09-17 | 2021-10-01 | 10 | 2021-10-01 | 10 | 2021-10-13 | 8 | [15 empty] | 2021-10-13 | 2021-10-13 | 0 | 2021-10-13 | [6 empty] | 2021-09-17 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1650 | PGE | 94063 | NEM | EXPNEM | Withdrawn | Solar PV | 86.4 |  | 2021-09-17 | 2021-09-20 | 1 | 2021-09-20 | 1 | 2021-09-22 | 2 | [15 empty] | 2021-09-22 | 2021-09-22 | 0 | 2021-09-22 | [6 empty] | 2021-09-17 | 2021-09-23 | 4 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1651 | PGE | 95228 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 60.02 |  | 2021-09-17 | 2021-09-27 | 6 | 2021-10-04 | 11 | 2021-10-22 | 14 | [15 empty] | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | 2021-10-23 | 0 |  |  |  |  | 2021-09-29 | 0 | [5 empty] | 2021-10-27 | 2021-11-02 | 4 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-27 | 2021-10-28 | 1 | 2021-11-02 |  | 2021-11-03 | 1 | 1//19
1652 | PGE | 95202 | NEM | EXPNEM | Application Review in Progress | Solar PV | 242 |  | 2021-09-17 | 2021-09-20 | 1 | [29 empty] | 2021-09-17 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1653 | PGE | 93308 | NEM | EXPNEM | Implementation | Solar PV | 166 |  | 2021-09-17 | 2021-09-29 | 8 | 2021-09-29 | 8 | 2021-10-11 | 8 | [15 empty] | 2021-10-11 | 2021-10-26 | 11 | 2021-10-26 | 2021-10-26 | 0 |  |  |  |  | 2021-09-17 | 0 |  | 2021-10-01 |  |  |  | 2022-02-08 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-08 | 2022-02-08 | 0 |  |  |  |  | 1//19
1654 | PGE | 93308 | NEM | EXPNEM | Implementation | Solar PV | 170 |  | 2021-09-17 | 2021-09-29 | 8 | 2021-09-29 | 8 | 2021-10-11 | 8 | [15 empty] | 2021-10-11 | 2021-10-26 | 11 | 2021-10-26 | 2021-10-26 | 0 |  |  |  |  | 2021-09-17 | 0 |  | 2021-10-01 |  |  |  | 2022-02-08 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-08 | 2022-02-08 | 0 |  |  |  |  | 1//19
1655 | PGE | 95336 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 3000 |  | 2021-09-17 | 2021-09-20 | 1 | 2021-11-10 | 38 | [5 empty] | 2021-11-10 | 2021-12-08 | 17 | 2021-12-08 | 2021-12-22 | 10 | 2022-01-11 |  |  | 2021-12-22 | 2021-12-22 | 0 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1656 | PGE | 93725 | NEM | EXPNEM | Implementation | Solar PV | 38.78 |  | 2021-09-20 | 2021-09-30 | 8 | 2021-10-05 | 11 | 2021-10-11 | 4 | [15 empty] | 2021-10-11 | 2021-10-26 | 11 | 2021-10-26 | 2021-10-26 | 0 |  |  |  |  | 2021-09-20 | 0 |  | 2021-10-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1657 | PGE | 93615 | NEM | EXPNEM | Commercial | Solar PV | 56.415 |  | 2021-09-21 | 2021-09-23 | 2 | 2021-09-23 | 2 | 2021-10-05 | 8 | [15 empty] | 2021-10-05 | 2021-10-22 | 13 | 2021-10-22 | 2021-11-01 | 6 | [5 empty] | 0 | [5 empty] | 2021-11-01 | 2021-11-09 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-01 | 2021-11-01 | 0 | 2021-11-09 |  | 2021-11-09 | 0 | 1//19
1658 | PGE | 93656 | NEM | EXPNEM | IA in Progress | Solar PV | 1680 |  | 2021-09-21 | 2021-09-23 | 2 | 2021-10-06 | 11 | [5 empty] | 2021-11-04 | 2021-11-30 | 15 | 2021-11-30 | 2021-12-08 | 6 | 2021-12-20 | 2022-03-09 | 55 | 2021-12-08 | 2021-12-10 | 2 | 2022-03-09 | 2022-03-28 | 13 | 2022-03-28 | [6 empty] | 2021-09-21 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1659 | PGE | 94598 | NEM | EXPNEM | Implementation | Solar PV | 150 |  | 2021-09-21 | 2021-10-02 | 8 | 2021-10-02 | 8 | 2021-11-15 | 29 | [15 empty] | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-18 | 3 |  |  |  |  | 2021-09-21 | 0 | [8 empty] | 2021-12-14 | 2021-12-14 | 0 | 1//19 | 1//19 |  | 2022-02-08 | 2022-04-09 | 44 | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1660 | PGE | 94109 | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-09-21 | 2021-10-05 | 10 | 2021-12-16 | 59 | 2021-12-31 | 11 | [15 empty] | 2021-12-31 | 2022-01-24 | 15 | 2022-01-24 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1661 | PGE | 93727 | NEM | EXPNEM | IA in Progress | Solar PV | 111 |  | 2021-09-21 | 2021-10-05 | 10 | 2021-12-01 | 48 | 2021-12-22 | 15 | [15 empty] | 2021-12-22 | 2022-01-12 | 15 | 2022-01-12 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1662 | PGE | 93436 | NEM | EXPNEM | Implementation | Solar PV | 75 |  | 2021-09-22 | 2021-09-22 | 0 | 2021-10-22 | 22 | 2021-11-02 | 7 | [15 empty] | 2021-11-02 | 2021-11-02 | 0 | 2021-11-02 | 2022-02-01 | 61 |  |  |  |  | 2021-10-22 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1664 | PGE | 95401 | NEM | EXPNEM | Commercial | Solar PV | 46.4 |  | 2021-09-22 | 2021-10-06 | 10 | 2021-12-01 | 47 | 2021-12-22 | 15 | [15 empty] | 2021-12-22 | 2021-12-27 | 3 | 2021-12-27 | 2021-12-30 | 3 | [5 empty] | 0 | [5 empty] | 2022-02-22 | 2022-03-02 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-22 | 2022-02-22 | 0 | 2022-03-02 |  | 2022-03-02 | 0 | 1//19
1665 | PGE | 95379 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 59.313 |  | 2021-09-22 | 2021-09-30 | 6 | 2021-10-08 | 12 | 2021-10-29 | 15 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | 2022-01-26 | 59 |  |  |  |  | 2021-09-22 | 0 |  | 2021-10-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1666 | PGE | 95379 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 35.9 |  | 2021-09-22 | 2021-09-30 | 6 | 2021-10-08 | 12 | 2021-10-29 | 15 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | 2022-01-26 | 59 |  |  |  |  | 2021-09-22 | 0 |  | 2021-10-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1667 | PGE | 94019 | NEM | VNEMSOMAH | Implementation | Solar PV | 37.832 |  | 2021-09-22 | 2021-09-27 | 3 | 2021-10-05 | 9 | 2021-10-22 | 13 | [15 empty] | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | 2022-02-10 | 75 |  |  |  |  | 2021-09-22 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1668 | PGE | 93308 | NEM | EXPNEM | Implementation | Solar PV | 352.056 |  | 2021-09-22 | 2021-09-24 | 2 | 2021-09-28 | 4 | 2021-10-11 | 9 | [15 empty] | 2021-10-11 | 2021-10-26 | 11 | 2021-10-26 | 2021-10-26 | 0 |  |  |  |  | 2021-09-22 | 0 | [5 empty] | 2022-02-08 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-08 | 2022-02-08 | 0 |  |  |  |  | 1//19
1669 | PGE | 94019 | NEM | VNEMSOMAH | Implementation | Solar PV | 37.832 |  | 2021-09-22 | 2021-09-27 | 3 | 2021-10-05 | 9 | 2021-10-22 | 13 | [15 empty] | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | 2022-02-10 | 75 |  |  |  |  | 2021-09-22 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1670 | PGE | 94019 | NEM | VNEMSOMAH | Implementation | Solar PV | 37.832 |  | 2021-09-22 | 2021-09-27 | 3 | 2021-10-05 | 9 | 2021-11-19 | 32 | [15 empty] | 2021-11-19 | 2021-11-19 | 0 | 2021-11-19 | 2022-02-10 | 56 |  |  |  |  | 2021-09-22 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1671 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 116.058 |  | 2021-09-22 | 2021-09-24 | 2 | 2021-10-12 | 14 | 2021-10-15 | 3 | [15 empty] | 2021-10-15 | 2021-10-15 | 0 | 2021-10-15 | 2021-10-20 | 3 | [5 empty] | 0 | [5 empty] | 2021-10-25 | 2021-12-17 | 36 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-25 | 2021-12-17 | 36 | 2021-12-17 |  | 2021-12-17 | 0 | 1//19
1672 | PGE | 94506 | NEM | VNEM | Application Review in Progress | Solar PV | 250 |  | 2021-09-23 | 2021-10-06 | 9 | [29 empty] | 2021-09-23 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1673 | PGE | 95620 | NEM | EXPNEM | Study in Progress | Solar PV | 658.3 |  | 2021-09-23 | 2021-10-06 | 9 | 2021-10-20 | 19 | 2021-11-10 | 15 | 2021-11-10 | 2021-12-20 | 25 | 2021-12-20 | 2022-01-24 | 24 | 2022-01-24 | 2022-01-24 | 0 | 2022-01-24 |  |  | 2022-01-24 | 2022-01-24 | 0 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1674 | PGE | 95215 | NEM | EXPNEM | Withdrawn | Solar PV | 32.87 |  | 2021-09-23 | 2021-10-05 | 8 | 2021-10-05 | 8 | 2021-10-22 | 13 | 2021-10-15 | 2021-11-10 | 18 | 2021-11-10 | 2021-12-07 | 16 | 2021-12-07 | 2022-01-07 | 23 |  |  |  | 2022-01-07 | [13 empty] | 0 |  | 2021-10-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1675 | PGE | 95360 | NEM | EXPNEM | Implementation | Solar PV | 140.115 |  | 2021-09-23 | 2021-09-28 | 3 | 2021-09-28 | 3 | 2021-10-15 | 13 | [15 empty] | 2021-11-01 | 2021-11-10 | 7 | 2021-11-10 | 2021-11-10 | 0 |  |  |  |  | 2021-09-23 | 0 |  | 2021-10-14 | [6 empty] | 2021-11-17 | 2022-03-21 | 85 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1676 | PGE | 95519 | Non-NEM | Inadvertent Export | Implementation | Storage | 420 |  | 2021-09-23 | 2021-09-24 | 1 | 2021-10-13 | 14 | 2021-11-16 | 23 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2022-02-15 | 62 |  |  |  |  | 2021-09-23 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1677 | PGE | 93280 | NEM | EXPNEM | Implementation | Solar PV | 240 |  | 2021-09-24 | 2021-10-08 | 10 | 2021-10-08 | 10 | 2021-10-29 | 15 | [15 empty] | 2021-10-29 | 2021-11-22 | 15 | 2021-11-22 | 2021-11-30 | 4 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1678 | PGE | 95320 | NEM | EXPNEM | Commercial | Solar PV | 88.928 |  | 2021-09-24 | 2021-09-28 | 2 | 2021-10-19 | 17 | 2021-11-05 | 13 | [15 empty] | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05 | 2022-01-31 | 57 |  |  |  |  | 2021-09-24 | 0 | [5 empty] | 2022-01-31 | 2022-02-08 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-31 | 2022-01-31 | 0 | 2022-02-08 |  | 2022-02-09 | 1 | 1//19
1679 | PGE | 95076 | NEM | EXPNEM | Implementation | Solar PV | 31.024 |  | 2021-09-24 | 2021-10-07 | 9 | 2021-11-01 | 26 | 2021-11-23 | 15 | [15 empty] | 2021-11-23 | 2021-11-23 | 0 | 2021-11-23 | 2021-12-01 | 4 | [5 empty] | 0 | [5 empty] | 2022-01-20 | 2022-02-01 | 8 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-20 | 2022-01-21 | 1 | 2022-02-01 | 2022-02-02 |  | 1 | 1//19 |  | 89
1682 | PGE | 94538 | Non-NEM | Inadvertent Export | Commercial | Storage | 140.65 |  | 2021-09-26 | 2021-09-27 | 0 | 2021-11-03 | 27 | 2022-01-05 | 42 | [15 empty] | 2022-01-05 | 2022-01-05 | 0 | 2022-01-05 | 2022-03-23 | 53 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-03-22 |  | 2022-03-23 | 2 | 1//19
1684 | PGE | 94563 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 30.232 |  | 2021-09-27 | 2021-10-01 | 4 | 2021-10-14 | 13 | 2021-10-14 | 0 | [18 empty] | 2021-09-27 | [6 empty] | 2021-09-27 | 0 | [5 empty] | 2021-11-02 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-02 | 2021-11-02 | 0 |  |  |  |  | 1//19
1685 | PGE | 95988 | NEM | EXPNEM | Withdrawn | Solar PV | 550 |  | 2021-09-27 | 2021-10-11 | 10 | [29 empty] | 2021-09-27 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1686 | PGE | 94558 | NEM | EXPNEM | Commercial | Solar PV | 51.694 |  | 2021-09-27 | 2021-09-28 | 1 | 2021-10-01 | 4 | 2021-10-15 | 10 | [15 empty] | 2021-10-15 | 2021-10-15 | 0 | 2021-10-15 | 2022-03-11 | 100 | [5 empty] | 0 | [5 empty] | 2022-03-11 | 2022-03-29 | 12 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-11 | 2022-03-14 | 1 | 2022-03-29 |  | 2022-03-30 | 1 | 1//19
1687 | PGE | 93706 | NEM | EXPNEM | Implementation | Solar PV | 244.589 |  | 2021-09-27 | 2021-10-02 | 4 | 2021-10-26 | 21 | 2021-11-05 | 8 | [15 empty] | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05 | 2021-11-09 | 2 |  |  |  |  | 2021-09-27 | 0 | [8 empty] | 2021-12-07 | 2022-03-31 | 81 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1688 | PGE | 93609 | NEM | EXPNEM | Implementation | Solar PV | 146.753 |  | 2021-09-27 | 2021-09-30 | 3 | 2021-10-15 | 14 | 2021-10-26 | 7 | [15 empty] | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26 | 2021-10-29 | 3 |  |  |  |  | 2021-10-20 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1690 | PGE | 95691 | NEM | VNEM | Commercial | Solar PV | 40.372 |  | 2021-09-28 | 2021-09-29 | 1 | 2021-11-23 | 39 | 2021-12-14 | 13 | [15 empty] | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | 2022-03-02 | 25 | [5 empty] | 0 |  |  | 2022-01-10 | 2022-01-10 | 0 | 2022-03-17 | 2022-03-17 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-17 | 2022-03-17 | 0 | 2022-03-17 |  | 2022-03-21 | 2 | 1//19
1691 | PGE | 95691 | NEM | VNEM | Commercial | Solar PV | 40.372 |  | 2021-09-28 | 2021-09-29 | 1 | 2021-11-23 | 39 | 2021-12-14 | 13 | [15 empty] | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | 2022-03-02 | 25 | [5 empty] | 0 |  |  | 2022-01-10 | 2022-01-10 | 0 | 2022-03-09 | 2022-03-10 | 1 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-09 | 2022-03-10 | 1 | 2022-03-10 |  | 2022-03-14 | 2 | 1//19
1692 | PGE | 95370 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 429 |  | 2021-09-28 | 2021-10-12 | 10 | 2021-11-17 | 35 | 2021-12-20 | 21 | 2021-12-20 | 2022-01-28 | 28 | 2022-03-14 | [22 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1693 | PGE | 95365 | NEM | EXPNEM | Implementation | Solar PV | 187.5 |  | 2021-09-28 | 2021-10-11 | 9 | 2021-10-15 | 13 | 2021-12-08 | 35 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | 2021-12-27 | 13 |  |  |  |  | 2021-09-28 | 0 | [5 empty] | 2022-03-30 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-30 | 2022-03-30 | 0 |  |  |  |  | 1//19
1694 | PGE | 95912 | NEM | EXPNEM | Commercial | Solar PV | 54.77 |  | 2021-09-28 | 2021-10-06 | 6 | 2021-10-11 | 9 | 2021-10-25 | 10 | [15 empty] | 2021-10-25 | 2021-10-25 | 0 | 2021-10-25 | 2021-11-24 | 21 | [5 empty] | 0 | [5 empty] | 2021-11-29 | 2021-12-08 | 7 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-29 | 2021-11-30 | 1 | 2021-12-08 |  | 2021-12-08 | 0 | 1//19
1695 | PGE | 95128 | NEM | EXPNEM | Implementation | Solar PV | 904.446 |  | 2021-09-28 | 2021-10-08 | 8 | 2021-10-08 | 8 | 2021-11-16 | 26 | [15 empty] | 2021-11-16 | 2021-12-02 | 10 | 2021-12-02 | 2021-12-02 | 0 |  |  |  |  | 2021-09-28 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1696 | PGE | 94549 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.08 |  | 2021-09-28 | 2021-10-01 | 3 | 2022-03-08 | 110 | 2022-03-09 | 1 | [26 empty] | 0 | [5 empty] | 2022-03-09 | 2022-03-09 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-09 |  |  | 2022-03-09 |  | 2022-03-09 | 0 | 1//19
1697 | PGE | 94558 | NEM | EXPNEM | IA in Progress | Solar PV | 133.2 |  | 2021-09-28 | 2021-09-30 | 2 | 2021-10-04 | 4 | 2021-10-19 | 11 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1698 | PGE | 94558 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.204 |  | 2021-09-29 | 2021-09-30 | 1 | 2021-10-28 | 21 | 2021-11-01 | 2 | [18 empty] | 2021-09-29 | [7 empty] | 0 | [5 empty] | 2021-11-02 | 2021-11-02 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-02 |  |  | 2021-11-02 |  | 2021-11-03 | 1 | 1//19
1699 | PGE | 96021 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 49.411 |  | 2021-09-29 | 2021-10-13 | 10 | 2021-10-19 | 14 | 2021-11-09 | 15 | [15 empty] | 2021-11-09 | 2021-12-03 | 15 | 2021-12-03 | [6 empty] | 2021-09-29 | 0 |  |  | 2021-12-29 | 2021-12-29 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1700 | PGE | 96021 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 45.634 |  | 2021-09-29 | 2021-10-13 | 10 | 2021-10-19 | 14 | 2021-11-09 | 15 | [15 empty] | 2021-11-09 | [9 empty] | 2021-09-29 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1701 | PGE | 95327 | NEM | EXPNEM | Commercial | Solar PV | 39.46 |  | 2021-09-29 | 2021-10-11 | 8 | 2021-10-20 | 15 | 2021-11-03 | 10 | [15 empty] | 2021-11-03 | 2021-11-03 | 0 | 2021-11-03 | 2021-11-05 | 2 | [5 empty] | 0 | [5 empty] | 2021-11-23 | 2021-11-30 | 3 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-23 | 2021-11-23 | 0 | 2021-11-30 |  | 2021-12-06 | 4 | 1//19
1702 | PGE | 93727 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 1331.879 |  | 2021-09-29 | 2021-10-13 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1703 | PGE | 94952 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 342 |  | 2021-09-29 | 2021-10-13 | 10 | 2021-11-08 | 28 | 2022-02-15 | 67 | [15 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | [6 empty] | 2021-09-29 | 0 |  |  | 2022-02-15 | 2022-02-15 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1704 | PGE | 94513 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 117.6 |  | 2021-09-30 | 2021-10-11 | 7 | [22 empty] | 2021-09-30 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1706 | PGE | 95301 | NEM | NEM Paired Storage | Study in Progress | ENGN, Solar PV, Storage | 8385.2 |  | 2021-09-30 | 2021-09-30 | 0 | 2021-10-20 | 14 | [5 empty] | 2022-01-19 | 2022-02-11 | 17 | 2022-02-11 | 2022-02-18 | 5 | 2022-03-01 |  |  | 2022-02-18 | 2022-02-18 | 0 | [10 empty] | 2021-09-30 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1707 | PGE | 93446 | NEM | EXPNEM | IA in Progress | Solar PV | 35.5 |  | 2021-09-30 | 2021-10-06 | 4 | 2021-11-15 | 31 | 2021-12-02 | 11 | [15 empty] | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1708 | PGE | 95019 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.49 |  | 2021-09-30 | 2021-10-14 | 10 | 2021-10-19 | 13 | 2021-12-03 | 30 | [15 empty] | 2021-12-03 | 2021-12-03 | 0 | 2021-12-03 | [6 empty] | 2021-09-30 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1709 | PGE | 94586 | Non-NEM | Continuous Uncompensated Export | Withdrawn | Solar PV | 57.71 |  | 2021-09-30 | 2021-10-01 | 1 | 2021-10-06 | 4 | 2021-11-19 | 31 | [15 empty] | 2021-11-19 | 2021-12-14 | 15 | 2021-12-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1710 | PGE | 94027 | NEM | SNEM Paired Storage | Implementation | Solar PV, Storage | 72.405 |  | 2021-09-30 | 2021-10-04 | 2 | 2022-03-24 | 120 | 2022-03-28 | 2 | [26 empty] | 0 | [5 empty] | 2022-03-28 | 2022-03-29 | 1 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-28 | 2022-03-28 | 0 | 2022-03-29 |  |  |  | 1//19
1711 | PGE | 94566 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 32.781 |  | 2021-09-30 | 2021-10-04 | 2 | 2021-10-20 | 14 | 2021-10-23 | 2 | [18 empty] | 2021-09-30 | [6 empty] | 2021-09-30 | 0 | [5 empty] | 2021-11-11 | 2021-11-22 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-11 | 2021-11-11 | 0 | 2021-11-22 |  | 2021-11-24 | 2 | 1//19
1712 | PGE | 93727 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 3065.042 |  | 2021-09-30 | 2021-10-04 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1713 | PGE | 95035 | NEM | NEMMT | Implementation | ENGN, Solar PV | 482 |  | 2021-09-30 | 2021-10-04 | 2 | 2021-10-20 | 14 | 2022-02-25 | 87 | [15 empty] | 2022-02-25 | 2022-03-23 | 18 | 2022-03-23 | 2022-03-28 | 3 |  |  |  |  | 2021-09-30 | 0 |  | 2021-12-07 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1714 | PGE | 94904 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-01-27 | 2021-02-08 | 8 | 2021-02-08 | 8 | 2021-02-09 | 1 | [18 empty] | 2021-01-27 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-02-08 |  | 2021-03-10 | 23 | 1//19
1715 | PGE | 94062 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-02-16 | 2021-02-25 | 7 | 2021-02-25 | 7 | 2021-03-03 | 4 | [18 empty] | 2021-02-16 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-02-25 |  | 2021-03-08 | 8 | 1//19
1716 | PGE | 95070 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-02-25 | 2021-03-08 | 7 | 2021-03-08 | 7 | 2021-03-11 | 3 | [18 empty] | 2021-02-25 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-03-08 |  | 2021-04-09 | 25 | 1//19
1717 | PGE | 94563 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-03-03 | 2021-03-16 | 9 | 2021-04-01 | 21 | 2021-04-07 | 4 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-07 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-03-16 |  | 2021-04-13 | 21 | 1//19
1718 | PGE | 94044 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-03-11 | 2021-03-25 | 10 | 2021-03-25 | 10 | 2021-04-07 | 9 | [18 empty] | 2021-03-11 | 2021-05-05 | 39 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-01 |  | 2021-05-06 | 4 | 1//19
1719 | PGE | 94941 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-03-15 | 2021-03-30 | 11 | 2021-04-09 | 19 | 2021-04-14 | 3 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | 2021-05-14 | 25 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-12 |  | 2021-06-07 | 19 | 1//19
1720 | PGE | 95448 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-03-17 | 2021-03-31 | 10 | 2021-05-07 | 37 | 2021-05-14 | 5 | [18 empty] | 2021-03-17 | 2021-07-22 | 89 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-06-24 |  | 2021-07-22 | 21 | 1//19
1721 | PGE | 94526 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-04-16 | 2021-04-30 | 10 | 2021-04-30 | 10 | 2021-05-04 | 2 | [18 empty] | 2021-04-16 | 2021-05-04 | 12 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-04 |  | 2021-05-12 | 7 | 1//19
1722 | PGE | 94941 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-04-26 | 2021-05-10 | 10 | 2021-05-25 | 21 | 2021-06-02 | 5 | [18 empty] | 2021-04-26 | 2021-06-02 | 26 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-06-02 |  | 2021-06-04 | 3 | 1//19
1723 | PGE | 95713 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-04-26 | 2021-05-10 | 10 | 2021-05-24 | 20 | 2021-06-01 | 5 | [15 empty] | 2021-06-01 | 2021-06-01 | 0 | 2021-06-01 | 2021-06-01 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-10 |  | 2021-06-01 | 17 | 1//19
1724 | PGE | 94803 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-05-18 | 2021-05-25 | 5 | 2021-05-25 | 5 | 2021-09-13 | 76 | [15 empty] | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-09-03 | 71 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-26 |  | 2021-09-13 | 13 | 1//19
1725 | PGE | 94563 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-06-02 | 2021-06-16 | 10 | 2021-06-16 | 10 | 2021-06-30 | 10 | [18 empty] | 2021-06-02 | 2021-06-30 | 20 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-06-30 |  | 2021-06-30 | 1 | 1//19
1726 | PGE | 95667 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-06-24 | 2021-07-09 | 10 | 2021-07-09 | 10 | 2021-07-23 | 10 | [15 empty] | 2021-07-23 | 2021-07-28 | 3 | 2021-07-28 | 2021-07-28 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-07-09 |  | 2021-07-28 | 14 | 1//19
1727 | PGE | 94025 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-07-28 | 2021-08-03 | 4 | 2021-08-12 | 11 | 2021-08-13 | 1 | [15 empty] | 2021-08-13 | 2021-08-13 | 0 | 2021-08-13 | 2021-10-05 | 36 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-06 |  | 2021-10-06 | 1 | 1//19
1728 | PGE | 95949 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-08-12 | 2021-08-24 | 8 | 2021-08-24 | 8 | 2021-09-08 | 10 | [18 empty] | 2021-08-12 | 2021-09-22 | 28 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-09-22 |  | 2021-09-22 | 1 | 1//19
1729 | PGE | 95018 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-08-25 | 2021-09-09 | 10 | 2021-09-09 | 10 | 2021-09-10 | 1 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | 2021-09-10 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-09-09 |  | 2021-09-16 | 6 | 1//19
1730 | PGE | 95229 | Non-NEM | Inadvertent Export | Commercial | Storage | 5 |  | 2021-09-21 | 2021-10-05 | 10 | 2021-10-19 | 20 | 2021-10-26 | 5 | [18 empty] | 2021-09-21 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-19 |  | 2021-11-02 | 11 | 1//19
1731 | PGE | 94536 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-03-11 | 2021-03-25 | 10 | 2021-03-25 | 10 | 2021-04-14 | 14 | [18 empty] | 2021-03-11 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-03-04 |  | 2022-03-28 | 17 | 1//19
1732 | PGE | 94941 | Non-NEM | Non-Export | IA in Progress | Storage | 5 |  | 2021-03-19 | 2021-04-01 | 9 | 2021-04-01 | 9 | 2021-04-07 | 4 | [18 empty] | 2021-03-19 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1733 | PGE | 95006 | Non-NEM | Non-Export | IA in Progress | Storage | 5 |  | 2021-04-12 | 2021-04-17 | 4 | 2021-04-17 | 4 | 2021-04-19 | 0 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-04-19 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1734 | PGE | 94970 | Non-NEM | Non-Export | Study in Progress | Storage | 5 |  | 2021-04-05 | 2021-04-19 | 10 | 2021-05-20 | 33 | 2021-06-03 | 9 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-06-03 | 32 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1735 | PGE | 94558 | Non-NEM | Non-Export | Study in Progress | Storage | 5.5 |  | 2021-08-17 | 2021-08-31 | 10 | 2021-09-15 | 20 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1736 | PGE | 95018 | Non-NEM | Non-Export | Application Accepted | Storage | 10 |  | 2021-02-03 | 2021-02-16 | 8 | 2021-02-16 | 8 | 2021-02-16 | 0 | [18 empty] | 2021-02-03 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1737 | PGE | 93644 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-22 | 2021-04-05 | 10 | 2021-12-08 | 181 | 2021-12-23 | 11 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | 2022-01-05 | 20 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-02-11 |  | 2022-02-11 | 1 | 1//19
1738 | PGE | 95959 | Non-NEM | Non-Export | Application Accepted | Storage | 10 |  | 2021-04-04 | 2021-04-14 | 7 | 2021-04-14 | 7 | 2021-04-25 | 7 | [15 empty] | 2021-04-25 | 2021-04-25 | 0 | 2021-04-25 | 2021-06-29 | 45 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1739 | PGE | 95070 | Non-NEM | Non-Export | Withdrawn | Storage | 10 |  | 2021-03-03 | 2021-03-17 | 10 | [22 empty] | 2021-03-03 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1740 | PGE | 96021 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-07 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-26 | 9 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-03-11 | 40 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-13 |  | 2021-10-20 | 6 | 1//19
1741 | PGE | 95650 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-07 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-14 | 2 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-02-12 | 22 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-07-30 |  | 2021-08-11 | 9 | 1//19
1742 | PGE | 94010 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-15 | 2021-01-26 | 6 | 2021-01-29 | 9 | 2021-02-01 | 1 | [15 empty] | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 2021-08-07 | 135 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-13 |  | 2021-08-13 | 1 | 1//19
1743 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-20 | 2021-01-26 | 4 | 2021-01-26 | 4 | 2021-01-26 | 0 | [18 empty] | 2021-01-20 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-01-26 |  | 2021-02-09 | 11 | 1//19
1744 | PGE | 94549 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-21 | 2021-01-26 | 3 | 2021-01-26 | 3 | 2021-01-28 | 2 | [18 empty] | 2021-01-21 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-01-26 |  | 2021-02-09 | 11 | 1//19
1745 | PGE | 95633 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-25 | 2021-02-05 | 9 | 2021-02-05 | 9 | 2021-02-12 | 5 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | 2021-03-30 | 36 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-05 |  | 2021-05-05 | 1 | 1//19
1746 | PGE | 94028 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-25 | 2021-02-08 | 10 | 2021-02-08 | 10 | 2021-02-12 | 4 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-04-13 | 45 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-07-12 |  | 2021-07-12 | 1 | 1//19
1747 | PGE | 94903 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-25 | 2021-02-03 | 7 | 2021-03-01 | 24 | 2021-03-03 | 2 | [18 empty] | 2021-01-25 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-02-03 |  | 2021-03-10 | 26 | 1//19
1748 | PGE | 95006 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-25 | 2021-02-03 | 7 | 2021-02-03 | 7 | 2021-02-04 | 1 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-02-11 | 6 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-07-30 |  | 2021-07-30 | 1 | 1//19
1749 | PGE | 94939 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-25 | 2021-02-03 | 7 | 2021-02-03 | 7 | 2021-02-05 | 2 | [18 empty] | 2021-01-25 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-02-03 |  | 2021-02-11 | 7 | 1//19
1750 | PGE | 93420 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-26 | 2021-02-03 | 6 | 2021-02-03 | 6 | 2021-02-04 | 1 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-02-03 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-02-03 |  | 2021-04-06 | 45 | 1//19
1751 | PGE | 95667 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-26 | 2021-02-08 | 9 | 2021-02-08 | 9 | 2021-02-08 | 0 | [18 empty] | 2021-01-26 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-02-08 |  | 2021-03-03 | 18 | 1//19
1752 | PGE | 94062 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-01 | 2021-02-08 | 5 | 2021-02-08 | 5 | 2021-02-12 | 4 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-03-25 | 32 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-28 |  | 2021-05-28 | 1 | 1//19
1753 | PGE | 95726 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-01 | 2021-02-13 | 9 | 2021-02-13 | 9 | 2021-02-23 | 5 | [15 empty] | 2021-02-13 | 2021-02-13 | 0 | 2021-02-13 | 2021-04-02 | 33 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-04-11 |  | 2021-04-11 | 0 | 1//19
1754 | PGE | 93460 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-02 | 2021-02-13 | 8 | 2021-02-13 | 8 | 2021-02-24 | 6 | [18 empty] | 2021-02-02 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-06-02 |  | 2021-06-03 | 2 | 1//19
1755 | PGE | 94901 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-02 | 2021-02-16 | 9 | 2021-02-16 | 9 | 2021-02-16 | 0 | [15 empty] | 2021-02-16 | 2021-02-16 | 0 | 2021-02-16 | 2021-03-17 | 21 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-11 |  | 2021-10-20 | 8 | 1//19
1756 | PGE | 94028 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-03 | 2021-02-16 | 8 | 2021-02-16 | 8 | 2021-02-18 | 2 | [18 empty] | 2021-02-03 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-02-16 |  | 2021-02-23 | 6 | 1//19
1757 | PGE | 95667 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-04 | 2021-02-18 | 9 | 2021-02-18 | 9 | 2021-03-10 | 14 | [15 empty] | 2021-02-18 | 2021-02-18 |  | 2021-02-18 | 2021-03-07 | 12 | [5 empty] | 0 | [5 empty] | 2021-04-01 | 2021-04-01 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 |  | 2021-04-01 | 0 | 1//19
1758 | PGE | 95762 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-05 | 2021-02-22 | 10 | 2021-02-22 | 10 | 2021-02-25 | 3 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-06-24 | 87 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-07-08 |  | 2021-07-08 | 1 | 1//19
1759 | PGE | 95070 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-05 | 2021-02-22 | 10 | 2021-02-22 | 10 | 2021-03-02 | 6 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-02 | 6 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-03-02 |  | 2021-03-12 | 9 | 1//19
1760 | PGE | 93420 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-10 | 2021-02-22 | 7 | 2021-02-22 | 7 | 2021-02-22 | 0 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-01 | 5 |  |  |  |  | 2021-03-17 | 2021-03-24 | 5 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-02-22 |  | 2021-04-06 | 32 | 1//19
1761 | PGE | 95425 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-12 | 2021-02-23 | 6 | 2021-02-23 | 6 | 2021-04-05 | 29 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-05-27 | 67 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-20 |  | 2021-09-08 | 14 | 1//19
1762 | PGE | 95728 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-14 | 2021-02-23 | 5 | 2021-02-23 | 5 | 2021-02-23 | 0 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-05-26 | 66 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-24 |  | 2021-08-24 | 1 | 1//19
1763 | PGE | 95248 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-17 | 2021-02-25 | 6 | 2021-02-25 | 6 | 2021-03-03 | 4 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-18 | 15 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-03 |  | 2021-08-09 | 5 | 1//19
1764 | PGE | 95945 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-18 | 2021-02-25 | 5 | 2021-02-25 | 5 | 2021-03-16 | 13 | [18 empty] | 2021-02-18 | [6 empty] | 2021-02-18 | 2021-03-24 | 24 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-02-25 |  | 2021-03-25 | 21 | 1//19
1765 | PGE | 95521 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-21 | 2021-02-25 | 3 | 2021-02-26 | 4 | 2021-03-01 | 1 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-17 | 12 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-02-25 |  | 2021-03-30 | 24 | 1//19
1766 | PGE | 95603 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-22 | 2021-03-03 | 7 | 2021-03-03 | 7 | 2021-03-08 | 3 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-03 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-03-09 |  | 2021-03-10 | 2 | 1//19
1767 | PGE | 95975 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-25 | 2021-03-08 | 7 | 2021-03-08 | 7 | 2021-03-09 | 1 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-04-19 | 30 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-06-22 |  | 2021-07-09 | 14 | 1//19
1768 | PGE | 95120 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-26 | 2021-03-09 | 7 | 2021-03-09 | 7 | 2021-03-22 | 9 | [15 empty] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | 2021-03-30 | 15 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-09-29 |  | 2021-09-29 | 1 | 1//19
1769 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-26 | 2021-03-09 | 7 | 2021-03-09 | 7 | 2021-03-11 | 2 | [18 empty] | 2021-02-26 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-03-09 |  | 2021-03-17 | 7 | 1//19
1770 | PGE | 93420 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-03 | 2021-03-12 | 7 | 2021-03-17 | 10 | 2021-03-23 | 4 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-18 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-24 |  | 2021-08-24 | 1 | 1//19
1771 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-03 | 2021-03-15 | 8 | 2021-03-15 | 8 | 2021-03-17 | 2 | [18 empty] | 2021-03-03 | 2021-03-03 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-04-07 |  | 2021-04-07 | 1 | 1//19
1772 | PGE | 94553 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-04 | 2021-03-17 | 9 | 2021-03-17 | 9 | 2021-03-23 | 4 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-24 | 5 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-04-01 |  | 2021-04-07 | 5 | 1//19
1773 | PGE | 95667 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-05 | 2021-03-22 | 11 | 2021-07-08 | 87 | 2021-07-28 | 14 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-26 | 12 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-07-08 |  | 2021-07-28 | 15 | 1//19
1774 | PGE | 94941 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-08 | 2021-03-22 | 10 | 2021-03-22 | 10 | 2021-03-29 | 5 | [15 empty] | 2021-03-29 | 2021-04-01 | 3 | 2021-04-01 | 2021-04-13 | 8 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-04-29 |  | 2021-04-29 | 1 | 1//19
1775 | PGE | 94549 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-10 | 2021-03-24 | 10 | 2021-03-24 | 10 | 2021-04-01 | 6 | [18 empty] | 2021-03-10 | 2021-03-25 | 11 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-03-25 |  | 2021-04-07 | 10 | 1//19
1776 | PGE | 95685 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-10 | 2021-03-24 | 10 | 2021-03-24 | 10 | 2021-04-01 | 6 | [18 empty] | 2021-03-10 | 2021-03-25 | 11 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-03-10 |  | 2021-05-04 | 40 | 1//19
1777 | PGE | 95018 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-11 | 2021-03-25 | 10 | 2021-03-25 | 10 | 2021-04-01 | 5 | [18 empty] | 2021-03-11 | 2021-03-11 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-04-07 |  | 2021-05-05 | 21 | 1//19
1778 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-11 | 2021-03-25 | 10 | 2021-03-25 | 10 | 2021-04-06 | 8 | [18 empty] | 2021-03-11 | 2021-03-11 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-05 |  | 2021-05-05 | 1 | 1//19
1779 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-11 | 2021-03-25 | 10 | 2021-03-25 | 10 | 2021-04-06 | 8 | [18 empty] | 2021-03-11 | 2021-03-11 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-05 |  | 2021-05-05 | 1 | 1//19
1780 | PGE | 94402 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-17 | 2021-03-31 | 10 | 2021-03-31 | 10 | 2021-04-07 | 5 | [18 empty] | 2021-03-17 | 2021-03-17 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-06 |  | 2021-05-06 | 1 | 1//19
1781 | PGE | 93401 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-24 | 2021-04-07 | 10 | 2021-04-07 | 10 | 2021-04-09 | 2 | [18 empty] | 2021-03-24 | 2021-07-06 | 72 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-03-24 |  | 2021-07-06 | 75 | 1//19
1782 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-25 | 2021-04-08 | 10 | 2021-04-08 | 10 | 2021-04-16 | 6 | [18 empty] | 2021-03-25 | 2021-03-25 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-07 |  | 2021-05-07 | 1 | 1//19
1783 | PGE | 93420 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-26 | 2021-04-02 | 5 | 2021-04-02 | 5 | 2021-04-09 | 5 | [18 empty] | 2021-03-26 | 2021-04-02 | 5 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-04-09 |  | 2021-04-15 | 5 | 1//19
1784 | PGE | 95501 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-28 | 2021-04-09 | 9 | 2021-04-29 | 23 | 2021-05-05 | 4 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-06-29 | 38 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-09-06 |  | 2021-09-09 | 4 | 1//19
1785 | PGE | 95614 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-01 | 2021-04-14 | 9 | 2021-04-14 | 9 | 2021-04-20 | 4 | [15 empty] | 2021-04-14 | 2021-04-14 | 0 | 2021-04-14 | 2021-05-03 | 13 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-04-14 |  | 2021-06-02 | 36 | 1//19
1786 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-05 | 2021-04-16 | 9 | 2021-04-16 | 9 | 2021-04-21 | 3 | [18 empty] | 2021-04-05 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-04-16 |  | 2021-04-29 | 10 | 1//19
1787 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-06 | 2021-04-17 | 8 | 2021-05-03 | 19 | 2021-05-03 | 0 | [18 empty] | 2021-04-06 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-03 |  | 2021-05-11 | 7 | 1//19
1788 | PGE | 95959 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-15 | 2021-04-29 | 10 | 2021-05-12 | 19 | 2021-05-12 | 0 | [18 empty] | 2021-04-15 | 2021-05-12 | 19 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-12 |  | 2021-05-12 | 1 | 1//19
1789 | PGE | 93446 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-19 | 2021-05-03 | 10 | 2021-05-07 | 14 | 2021-06-04 | 19 | [18 empty] | 2021-04-19 | 2021-06-04 | 33 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-19 |  | 2021-10-27 | 7 | 1//19
1790 | PGE | 95065 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-22 | 2021-05-06 | 10 | 2021-05-12 | 14 | 2021-05-12 | 0 | [18 empty] | 2021-04-22 | 2021-05-12 | 14 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-12 |  | 2021-05-12 | 1 | 1//19
1791 | PGE | 94708 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-26 | 2021-05-10 | 10 | 2021-05-25 | 21 | 2021-06-16 | 15 | [18 empty] | 2021-04-26 | 2021-06-16 | 36 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-06-16 |  | 2021-06-16 | 1 | 1//19
1792 | PGE | 94552 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-27 | 2021-05-11 | 10 | 2021-05-18 | 15 | 2021-05-26 | 6 | [18 empty] | 2021-04-27 | 2021-05-26 | 21 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-26 |  | 2021-05-28 | 3 | 1//19
1793 | PGE | 95667 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-28 | 2021-05-12 | 10 | 2021-05-12 | 10 | 2021-05-20 | 6 | [18 empty] | 2021-04-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-12 |  | 2021-05-20 | 7 | 1//19
1794 | PGE | 95959 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-30 | 2021-05-14 | 10 | 2021-05-14 | 10 | 2021-05-18 | 2 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | 2021-06-22 | 24 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-06-22 |  | 2021-06-23 | 2 | 1//19
1795 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-10 | 2021-05-24 | 10 | 2021-05-24 | 10 | 2021-06-09 | 11 | [18 empty] | 2021-05-10 | 2021-06-09 | 21 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-06-28 |  | 2021-06-30 | 3 | 1//19
1796 | PGE | 95003 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-14 | 2021-05-25 | 7 | 2021-06-03 | 13 | 2021-06-08 | 3 | [15 empty] | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-06-08 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-06-08 |  | 2021-06-08 | 1 | 1//19
1797 | PGE | 95004 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-14 | 2021-05-25 | 7 | 2021-06-03 | 13 | 2021-06-07 | 2 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-06-07 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-25 |  | 2021-06-07 | 10 | 1//19
1798 | PGE | 95065 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-18 | 2021-05-28 | 8 | 2021-05-28 | 8 | 2021-06-02 | 2 | [15 empty] | 2021-06-02 | 2021-06-17 | 11 | 2021-06-17 | 2021-06-01 | 3 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-18 |  | 2021-06-17 | 23 | 1//19
1799 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-20 | 2021-06-01 | 7 | 2021-06-15 | 17 | 2021-06-24 | 7 | [15 empty] | 2021-06-24 | 2021-06-25 | 1 | 2021-06-25 | 2021-06-25 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-06-25 |  | 2021-06-25 | 1 | 1//19
1800 | PGE | 95688 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-24 | 2021-06-04 | 8 | 2021-07-30 | 47 | 2021-08-11 | 8 | [15 empty] | 2021-07-30 | 2021-07-30 | 0 | 2021-07-30 | 2021-08-11 | 8 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-12 |  | 2021-08-12 | 1 | 1//19
1801 | PGE | 95120 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-25 | 2021-06-01 | 4 | 2021-06-01 | 4 | 2021-06-11 | 8 | [15 empty] | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-09-21 | 70 | [5 empty] | 0 | [5 empty] | 2021-09-21 | 2021-09-29 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-21 | 2021-09-29 | 6 | 2021-09-29 |  | 2021-09-29 | 0 | 1//19
1802 | PGE | 95066 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-06-14 | 2021-06-25 | 9 | 2021-06-25 | 9 | 2021-06-30 | 3 | [18 empty] | 2021-06-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-06-30 |  | 2021-07-28 | 21 | 1//19
1803 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-06-16 | 2021-06-21 | 3 | 2021-06-22 | 4 | 2021-06-23 | 1 | [18 empty] | 2021-06-16 | 2021-06-21 | 3 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-07-09 |  | 2021-07-09 | 1 | 1//19
1804 | PGE | 95060 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-06-17 | 2021-06-21 | 2 | 2021-06-21 | 2 | 2021-06-23 | 2 | [18 empty] | 2021-06-17 | 2021-06-29 | 8 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-06-29 |  | 2021-06-29 | 1 | 1//19
1805 | PGE | 95709 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-06-24 | 2021-06-29 | 3 | 2021-07-12 | 11 | 2021-07-14 | 2 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-14 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-07-14 |  | 2021-07-14 | 1 | 1//19
1806 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-01 | 2021-07-06 | 2 | 2021-07-07 | 3 | 2021-07-08 | 1 | [15 empty] | 2021-07-08 | 2021-07-13 | 3 | 2021-07-13 | 2021-07-13 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-07-06 |  | 2021-07-14 | 7 | 1//19
1807 | PGE | 93637 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-01 | 2021-07-06 | 2 | 2021-07-06 | 2 | 2021-07-26 | 14 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-07-28 | 2 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-09-27 |  | 2021-09-27 | 1 | 1//19
1808 | PGE | 94605 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-08 | 2021-07-13 | 3 | 2021-07-13 | 3 | 2021-07-20 | 5 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-07-20 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-07-20 |  | 2021-07-20 | 1 | 1//19
1809 | PGE | 95503 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-13 | 2021-07-15 | 2 | 2021-07-15 | 2 | 2021-08-02 | 12 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-10-29 | 75 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-29 |  | 2021-10-29 | 1 | 1//19
1810 | PGE | 95709 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-20 | 2021-07-30 | 8 | 2021-07-30 | 8 | 2021-08-13 | 10 | [15 empty] | 2021-08-13 | 2021-08-13 | 0 | 2021-08-13 | 2021-08-13 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-07-30 |  | 2021-08-13 | 11 | 1//19
1811 | PGE | 93637 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-26 | 2021-08-04 | 7 | 2021-08-19 | 18 | 2021-09-07 | 12 | [15 empty] | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-09-29 | 16 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-27 |  | 2021-10-28 | 2 | 1//19
1812 | PGE | 93637 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-26 | 2021-07-29 | 3 | 2021-08-23 | 20 | 2021-09-13 | 14 | [15 empty] | 2021-09-13 | 2021-09-29 | 12 | 2021-09-29 | 2021-09-29 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-11-04 |  | 2021-11-04 | 1 | 1//19
1813 | PGE | 93446 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-28 | 2021-08-03 | 4 | 2021-08-03 | 4 | 2021-08-04 | 1 | [18 empty] | 2021-07-28 | 2021-08-05 | 6 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-07-28 |  | 2021-08-23 | 19 | 1//19
1814 | PGE | 95005 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-30 | 2021-08-03 | 2 | 2021-08-03 | 2 | 2021-08-04 | 1 | [18 empty] | 2021-07-30 | 2021-07-30 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-07-30 |  | 2021-09-28 | 43 | 1//19
1815 | PGE | 93465 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-04 | 2021-08-13 | 7 | 2021-08-17 | 9 | 2021-08-18 | 1 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | 2021-08-19 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-19 |  | 2021-08-19 | 1 | 1//19
1816 | PGE | 94951 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-05 | 2021-08-10 | 3 | 2021-08-10 | 3 | 2021-08-31 | 15 | [15 empty] | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 | 2021-08-31 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-17 |  | 2021-08-31 | 11 | 1//19
1817 | PGE | 94611 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-09 | 2021-08-12 | 3 | 2021-08-12 | 3 | 2021-08-17 | 3 | [15 empty] | 2021-08-17 | 2021-08-17 | 0 | 2021-08-17 | 2021-08-17 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-09 |  | 2021-08-17 | 7 | 1//19
1818 | PGE | 95409 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-18 | 2021-09-01 | 10 | 2021-09-16 | 20 | 2021-10-20 | 24 | [15 empty] | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01 | 2021-10-04 | 22 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-09-01 |  | 2021-10-20 | 36 | 1//19
1819 | PGE | 95409 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-18 | 2021-08-24 | 4 | 2021-08-24 | 4 | 2021-11-08 | 53 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | 2021-09-24 | 22 | [5 empty] | 0 | [5 empty] | 2021-10-03 | 2021-10-03 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-03 |  |  | 2021-10-03 |  | 2021-11-08 | 25 | 1//19
1820 | PGE | 94028 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-20 | 2021-08-24 | 2 | 2021-08-24 | 2 | 2021-09-13 | 13 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-09-13 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-24 |  | 2021-09-21 | 21 | 1//19
1821 | PGE | 95476 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-20 | 2021-09-03 | 10 | 2021-09-03 | 10 | 2021-09-27 | 15 | [18 empty] | 2021-08-20 | 2021-08-20 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-09-03 |  | 2021-09-27 | 16 | 1//19
1822 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-24 | 2021-09-08 | 10 | 2021-09-08 | 10 | 2021-09-13 | 3 | [18 empty] | 2021-08-24 | 2021-08-24 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-18 |  | 2021-10-18 | 1 | 1//19
1823 | PGE | 94611 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-26 | 2021-08-30 | 2 | 2021-08-30 | 2 | 2021-09-03 | 4 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-03 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-30 |  | 2021-09-14 | 12 | 1//19
1824 | PGE | 95033 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-08 | 2021-10-15 | 27 | 2021-10-15 | 27 | 2021-10-18 | 1 | [18 empty] | 2021-09-07 | 2021-09-08 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-15 |  | 2021-10-22 | 6 | 1//19
1825 | PGE | 94038 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-13 | 2021-10-15 | 24 | 2021-10-15 | 24 | 2021-10-26 | 7 | [15 empty] | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26 | 2021-10-26 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-15 |  | 2021-10-26 | 8 | 1//19
1826 | PGE | 95076 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-14 | 2021-10-15 | 23 | 2021-10-20 | 26 | 2021-11-01 | 8 | [18 empty] | 2021-09-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-15 |  | 2021-11-10 | 19 | 1//19
1827 | PGE | 95570 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-16 | 2021-09-28 | 8 | 2021-10-08 | 16 | 2021-10-14 | 4 | [15 empty] | 2021-10-14 | 2021-10-14 | 0 | 2021-10-14 | 2021-10-14 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-25 |  | 2021-11-15 | 16 | 1//19
1828 | PGE | 95370 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-17 | 2021-09-21 | 2 | 2021-09-22 | 3 | 2021-10-07 | 11 | [15 empty] | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-10-11 | 2 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-09-21 |  | 2021-10-12 | 16 | 1//19
1829 | PGE | 95018 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-19 | 2021-10-15 | 19 | 2021-10-15 | 19 | 2021-10-19 | 2 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-10-19 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-15 |  | 2021-10-28 | 10 | 1//19
1830 | PGE | 95014 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-10-01 | 2021-10-04 | 1 | 2021-10-08 | 5 | 2021-10-08 | 0 | [18 empty] | 2021-09-30 | 2021-10-01 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-04 |  | 2021-10-08 | 5 | 1//19
1831 | PGE | 95033 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2020-12-30 | 2021-01-08 | 6 | 2021-01-08 | 6 | 2021-01-11 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-01-20 | 7 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1832 | PGE | 95030 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2020-12-30 | 2021-01-08 | 6 | 2021-01-08 | 6 | 2021-01-11 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-01-20 | 7 | [5 empty] | 0 | [5 empty] | 2022-02-07 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 |  | 2022-02-08 | 2 | 1//19
1833 | PGE | 94611 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-07 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-19 | 4 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-11-23 | 219 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-12-01 |  | 2021-12-16 | 12 | 1//19
1834 | PGE | 93446 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-11 | 2021-01-22 | 8 | 2021-01-22 | 8 | 2021-02-01 | 6 | [15 empty] | 2021-01-22 | 2021-01-22 | 0 | 2021-01-22 | 2021-02-01 | 6 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1835 | PGE | 94586 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-01-13 | 2021-01-25 | 7 | 2021-01-25 | 7 | 2021-01-25 | 0 | [15 empty] | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | 2021-02-11 | 13 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1836 | PGE | 94611 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-01-15 | 2021-01-25 | 5 | 2021-01-25 | 5 | [17 empty] | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1837 | PGE | 94605 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-02-01 | 2021-02-10 | 7 | 2021-02-10 | 7 | 2021-02-24 | 9 | [15 empty] | 2021-02-10 | 2021-02-10 | 0 | 2021-02-10 | 2021-11-11 | 191 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1838 | PGE | 95667 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-02-05 | 2021-02-22 | 10 | 2021-02-22 | 10 | 2021-04-09 | 34 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-04-23 | 44 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1839 | PGE | 95971 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-02-12 | 2021-02-22 | 5 | 2021-02-22 | 5 | 2021-03-03 | 7 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-05-25 | 66 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1840 | PGE | 93465 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-03 | 2021-03-15 | 8 | 2021-03-17 | 10 | 2021-03-23 | 4 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-18 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-02-15 |  | 2022-02-15 | 262 | 1//19
1841 | PGE | 94960 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-03-18 | 2021-04-01 | 10 | 2021-04-01 | 10 | 2021-04-07 | 4 | [18 empty] | 2021-03-18 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1842 | PGE | 93454 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-03-25 | 2021-03-29 | 2 | 2021-04-15 | 15 | 2021-04-25 | 6 | [15 empty] | 2021-04-25 | 2021-04-25 | 0 | 2021-04-25 | 2021-08-02 | 68 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1843 | PGE | 96061 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-03-28 | 2021-04-09 | 9 | 2021-05-12 | 32 | 2021-06-09 | 19 | [15 empty] | 2021-04-12 | 2021-04-12 |  | 2021-04-12 | 2021-06-15 | 47 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1844 | PGE | 95667 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-04-06 | 2021-04-13 | 5 | 2021-04-13 | 5 | 2021-04-13 | 0 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1845 | PGE | 93420 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-04-22 | 2021-05-06 | 10 | 2021-05-17 | 17 | 2021-06-08 | 15 | [18 empty] | 2021-04-22 | 2021-06-08 | 32 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1846 | PGE | 94062 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-23 | 2021-05-07 | 10 | 2021-05-12 | 13 | 2021-07-02 | 36 | [18 empty] | 2021-04-23 | 2021-07-02 | 49 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-07 | 2022-01-07 |  | 2022-01-07 |  | 2022-01-07 | 1 | 1//19
1847 | PGE | 94929 | Non-NEM | Non-Export | Application Accepted | Storage | 10 |  | 2021-05-02 | 2021-05-14 | 9 | 2021-05-14 | 9 | 2021-05-17 | 1 | [15 empty] | 2021-05-17 | 2021-05-17 | 0 | 2021-05-17 | 2022-01-11 | 165 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1848 | PGE | 95503 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-05-25 | 2021-06-01 | 4 | 2021-06-28 | 23 | 2021-07-15 | 12 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-07-20 | 3 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1849 | PGE | 95327 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-06-01 | 2021-06-14 | 9 | 2021-06-14 | 9 | 2021-06-30 | 12 | [15 empty] | 2021-06-30 | 2021-06-30 | 0 | 2021-06-30 | 2021-07-27 | 18 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-12-10 |  | 2021-12-10 | 1 | 1//19
1850 | PGE | 94037 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-06-02 | 2021-06-16 | 10 | 2021-06-16 | 10 | 2021-06-23 | 5 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | 2021-10-05 | 77 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1851 | PGE | 95503 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-06-12 | 2021-06-24 | 8 | 2021-06-24 | 8 | 2021-07-16 | 15 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-16 | 2021-07-20 | 2 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1852 | PGE | 95553 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-06-16 | 2021-06-29 | 9 | 2021-06-29 | 9 | 2021-07-20 | 14 | [15 empty] | 2021-07-20 | 2021-07-22 | 2 | 2021-07-22 | 2021-07-27 | 3 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-02-08 |  | 2022-02-08 | 1 | 1//19
1853 | PGE | 95633 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-06-28 | 2021-07-02 | 4 | 2021-07-02 | 4 | 2021-07-16 | 9 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-16 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1854 | PGE | 94611 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-07-12 | 2021-07-26 | 10 | 2021-07-26 | 10 | 2021-08-03 | 6 | [15 empty] | 2021-08-03 | 2021-08-03 | 1 | 2021-07-26 | 2021-09-08 | 31 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1855 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-12 | 2021-07-27 | 11 | 2021-07-27 | 11 | 2021-07-30 | 3 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-07-30 | 3 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-02-23 |  | 2022-02-23 | 1 | 1//19
1856 | PGE | 96022 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-07-21 | 2021-07-26 | 3 | 2021-07-26 | 3 | 2021-08-09 | 10 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2022-02-14 | 140 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1857 | PGE | 95634 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-08-10 | 2021-08-17 | 5 | 2021-09-09 | 21 | 2021-09-13 | 2 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-09-14 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1858 | PGE | 95503 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-08-10 | 2021-08-13 | 3 | 2021-09-28 | 34 | 2021-09-29 | 1 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | 2022-01-05 | 67 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1859 | PGE | 95333 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-08-25 | 2021-08-27 | 2 | 2021-09-14 | 13 | 2021-09-29 | 11 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | 2021-09-14 | 2 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1860 | PGE | 93670 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-08-25 | 2021-09-07 | 8 | 2021-09-07 | 8 | 2021-09-14 | 5 | [15 empty] | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-09-29 | 16 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1861 | PGE | 95573 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-09-02 | 2021-09-03 | 1 | 2021-09-03 | 1 | 2021-09-27 | 15 | [15 empty] | 2021-09-27 | 2021-09-30 | 3 | 2021-09-30 | 2021-10-12 | 8 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1862 | PGE | 95464 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-09-02 | 2021-09-15 | 8 | 2021-09-16 | 9 | 2021-09-24 | 6 | [18 empty] | 2021-09-01 | 2021-09-02 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1863 | PGE | 95452 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-09-03 | 2021-09-15 | 7 | 2021-09-16 | 8 | 2021-09-24 | 6 | [18 empty] | 2021-09-01 | 2021-09-03 | 2 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1864 | PGE | 95453 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-09-06 | 2021-09-13 | 4 | 2021-09-15 | 6 | 2021-09-24 | 7 | [18 empty] | 2021-09-01 | 2021-09-06 | 2 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1865 | PGE | 95425 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-08 | 2021-09-22 | 10 | 2021-09-22 | 10 | 2021-10-05 | 9 | [15 empty] | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | 2021-10-05 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1866 | PGE | 94549 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-10 | 2021-09-24 | 10 | 2021-09-24 | 10 | 2021-10-13 | 13 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | 2021-10-13 | 13 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1867 | PGE | 94611 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-09-16 | 2021-09-16 | 0 | 2021-09-23 | 5 | 2021-10-13 | 14 | [18 empty] | 2021-09-16 | 2021-09-27 | 7 |  |  |  |  | 2021-09-16 | 2021-10-12 | 18 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1868 | PGE | 93608 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-17 | 2021-09-20 | 1 | 2021-09-29 | 8 | 2021-10-04 | 3 | [18 empty] | 2021-09-15 | 2021-09-17 | 2 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1869 | PGE | 93667 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-20 | 2021-10-04 | 10 | 2021-10-04 | 10 | 2021-10-07 | 3 | [15 empty] | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-10-07 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-11-17 |  | 2021-12-13 | 19 | 1//19
1870 | PGE | 95524 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-21 | 2021-10-04 | 9 | 2021-10-11 | 14 | 2021-10-14 | 3 | [15 empty] | 2021-10-14 | 2021-10-14 | 0 | 2021-10-14 | 2021-10-14 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-03-15 |  | 2022-03-21 | 5 | 1//19
1871 | PGE | 95503 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-21 | 2021-10-05 | 10 | 2021-10-05 | 10 | 2021-10-26 | 15 | [18 empty] | 2021-09-20 | 2021-10-05 | 11 | [5 empty] | 0 | [5 empty] | 2022-03-08 | 2022-03-08 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 |  | 2022-03-09 | 1 | 1//19
1872 | PGE | 95570 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-21 | 2021-10-05 | 10 | 2021-10-05 | 10 | 2021-10-12 | 5 | [18 empty] | 2021-09-21 | 2021-09-21 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1873 | PGE | 94556 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-23 | 2021-10-07 | 10 | 2021-10-07 | 10 | 2021-10-13 | 4 | [15 empty] | 2021-10-13 | 2021-10-13 | 0 | 2021-10-13 | 2021-10-13 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-26 |  | 2021-12-13 | 35 | 1//19
1874 | PGE | 93608 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-27 | 2021-10-08 | 9 | 2021-10-26 | 21 | 2021-10-29 | 3 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | 2021-10-29 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-12-09 |  | 2021-12-09 | 1 | 1//19
1875 | PGE | 93608 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-28 | 2021-10-04 | 4 | 2021-10-14 | 12 | 2021-10-18 | 2 | [18 empty] | 2021-09-21 | 2021-09-28 | 5 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-12-15 |  | 2021-12-15 | 1 | 1//19
1876 | PGE | 93608 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-30 | 2021-10-12 | 8 | 2021-10-26 | 18 | 2021-10-29 | 3 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | 2021-10-29 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-12-21 |  | 2021-12-21 | 1 | 1//19
1877 | PGE | 95501 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-06-24 | 2021-07-08 | 9 | 2021-07-08 | 9 | 2021-07-23 | 11 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-09-25 | 55 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-01-24 |  | 2022-01-24 | 1 | 1//19
1878 | PGE | 93292 | Non-NEM | Non-Export | Implementation | Storage | 10 |  | 2021-08-31 | 2021-09-03 | 3 | 2021-09-03 | 3 | 2021-09-15 | 7 | [15 empty] | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | 2021-10-06 | 15 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1879 | PGE | 94578 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-09-16 | 2021-09-21 | 3 | 2021-09-21 | 3 | 2021-09-23 | 2 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | 2021-09-29 | 6 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-01-05 |  | 2022-01-05 | 1 | 1//19
1880 | PGE | 95503 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-18 | 0 |  | 2021-09-21 | 1 | 2021-09-28 | 5 | [15 empty] | 2021-09-28 | 2021-09-28 | 0 | 2021-09-28 | 2021-09-28 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-01-24 |  | 2022-01-24 | 1 | 1//19
1881 | PGE | 95549 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-09-22 | 2021-09-24 | 2 | 2021-09-24 | 2 | 2021-09-28 | 2 | [15 empty] | 2021-09-28 | 2021-09-28 | 0 | 2021-09-28 | 2021-09-28 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1882 | PGE | 95006 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-01-07 | 2021-01-15 | 6 | 2021-01-15 | 6 | 2021-01-15 | 0 | [18 empty] | 2021-01-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1883 | PGE | 93953 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-01 | 2021-04-13 | 8 | 2021-04-13 | 8 | 2021-04-16 | 3 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | 2021-04-16 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-04-13 |  | 2021-04-16 | 4 | 1//19
1884 | PGE | 95713 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-05-25 | 2021-05-28 | 3 | 2021-06-03 | 6 | 2021-06-07 | 2 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1885 | PGE | 95033 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-09-17 | 2021-10-01 | 10 | 2021-10-01 | 10 | [20 empty] | 2021-09-16 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1886 | PGE | 95672 | Non-NEM | Inadvertent Export | Withdrawn | Storage | 10 |  | 2021-09-20 | 2021-10-04 | 10 | 2021-10-04 | 10 | [20 empty] | 2021-09-20 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1887 | PGE | 95503 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-09-20 | 2021-09-23 | 3 | 2021-09-23 | 3 | 2021-09-28 | 3 | [18 empty] | 2021-09-20 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1888 | PGE | 95503 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-09-23 | 2021-10-06 | 9 | 2021-10-06 | 9 | 2021-10-27 | 15 | [18 empty] | 2021-09-23 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1889 | PGE | 93670 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-09-29 | 2021-10-13 | 10 | 2021-10-25 | 18 | 2021-10-25 | 0 | [18 empty] | 2021-08-30 | 2021-09-29 | 21 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1890 | PGE | 95521 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-29 | 2021-10-13 | 10 | 2021-10-13 | 10 | 2021-12-14 | 41 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2021-12-14 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1891 | PGE | 95519 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-29 | 2021-10-13 | 10 | 2021-10-13 | 10 | 2021-11-03 | 15 | [18 empty] | 2021-09-29 | [7 empty] | 0 | [5 empty] | 2021-12-14 | 2021-12-14 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 |  | 2021-12-14 | 0 | 1//19
1892 | PGE | 93608 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-29 | 2021-10-01 | 2 | 2021-10-15 | 12 | 2021-10-18 | 1 | [18 empty] | 2021-09-15 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-03-30 |  | 2022-03-30 | 1 | 1//19
1893 | PGE | 95407 | Non-NEM | Non-Export | Study in Progress | Solar PV | 11.52 |  | 2021-02-23 | 2021-03-09 | 10 | 2021-03-09 | 10 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1894 | PGE | 95684 | Non-NEM | Non-Export | Application Accepted | Storage | 15 |  | 2021-04-01 | 2021-04-15 | 10 | 2021-04-15 | 10 | 2021-04-20 | 3 | [26 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1895 | PGE | 95667 | Non-NEM | Non-Export | Implementation | Storage | 15 |  | 2021-04-05 | 2021-04-14 | 7 | 2021-04-14 | 7 | 2021-04-25 | 7 | [15 empty] | 2021-04-25 | 2021-04-25 | 0 | 2021-04-25 | 2021-12-23 | 167 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1896 | PGE | 95762 | Non-NEM | Non-Export | Application Accepted | Storage | 15 |  | 2021-05-01 | 2021-05-14 | 9 | 2021-05-14 | 9 | 2021-05-18 | 2 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | 2022-01-05 | 160 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1897 | PGE | 95667 | Non-NEM | Non-Export | Application Accepted | Storage | 15 |  | 2021-05-12 | 2021-05-26 | 10 | 2021-07-01 | 35 | 2021-07-15 | 9 | [15 empty] | 2021-07-15 | 2021-07-15 | 1 | 2021-07-01 | 2021-07-16 | 10 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1898 | PGE | 95667 | Non-NEM | Non-Export | Application Accepted | Storage | 15 |  | 2021-05-12 | 2021-05-26 | 10 | 2021-07-06 | 37 | 2021-07-15 | 7 | [15 empty] | 2021-07-15 | 2021-07-15 | 1 | 2021-06-30 | 2021-07-16 | 11 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1899 | PGE | 95667 | Non-NEM | Non-Export | Application Accepted | Storage | 15 |  | 2021-07-09 | 2021-07-13 | 2 | 2021-07-16 | 5 | 2021-07-19 | 1 | [15 empty] | 2021-07-19 | 2021-08-02 | 10 | 2021-08-02 | 2021-10-30 | 63 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1900 | PGE | 95667 | Non-NEM | Inadvertent Export | Application Accepted | Storage | 15 |  | 2021-09-21 | 2021-10-04 | 9 | 2021-10-21 | 22 | 2021-10-27 | 4 | [15 empty] | 2021-10-27 | 2021-10-27 | 0 | 2021-10-27 | 2021-10-27 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1901 | PGE | 95125 | Non-NEM | Non-Export | Application Review in Progress | Storage | 15 |  | 2021-03-30 | 2021-04-08 | 7 | [22 empty] | 2021-03-30 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1902 | PGE | 95409 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-07 | 2021-01-20 | 8 | 2021-01-20 | 8 | 2021-01-21 | 1 | [18 empty] | 2021-01-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-01-21 |  | 2021-01-29 | 7 | 1//19
1903 | PGE | 95667 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-08 | 2021-01-21 | 8 | 2021-01-21 | 8 | 2021-01-22 | 1 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-04-12 | 56 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-04-12 |  | 2021-04-12 | 1 | 1//19
1904 | PGE | 95549 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-08 | 2021-01-21 | 8 | 2021-01-21 | 8 | 2021-01-22 | 1 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-07-01 | 113 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-18 |  | 2021-10-18 | 1 | 1//19
1905 | PGE | 94020 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-08 | 2021-01-21 | 8 | 2021-01-21 | 8 | 2021-01-21 | 0 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-07-01 | 113 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-26 |  | 2021-08-26 | 1 | 1//19
1906 | PGE | 94066 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-27 | 2021-02-08 | 8 | 2021-03-12 | 31 | 2021-03-26 | 10 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-20 | 17 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-04-20 |  | 2021-05-02 | 9 | 1//19
1907 | PGE | 94611 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-29 | 2021-02-10 | 8 | 2021-02-10 | 8 | 2021-02-18 | 5 | [15 empty] | 2021-02-10 | 2021-02-10 | 0 | 2021-02-10 | 2021-02-12 | 2 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-02-10 |  | 2021-02-23 | 10 | 1//19
1908 | PGE | 95650 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-02-01 | 2021-02-13 | 9 | 2021-02-13 | 9 | 2021-03-08 | 14 | [15 empty] | 2021-02-13 | 2021-02-13 | 0 | 2021-02-13 | 2021-08-06 | 121 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-10 |  | 2021-08-10 | 1 | 1//19
1909 | PGE | 95682 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-02-03 | 2021-02-13 | 7 | 2021-02-13 | 7 | 2021-02-23 | 5 | [15 empty] | 2021-02-13 | 2021-02-13 | 0 | 2021-02-13 | 2021-08-03 | 118 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-03 |  | 2021-08-03 | 1 | 1//19
1910 | PGE | 95682 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-02-10 | 2021-02-22 | 7 | 2021-02-22 | 7 | 2021-02-23 | 1 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-05-25 | 66 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-07 |  | 2021-10-07 | 1 | 1//19
1911 | PGE | 95945 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-02-26 | 2021-03-01 | 1 | 2021-03-01 | 1 | 2021-03-18 | 13 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-08-30 | 128 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-30 |  | 2021-09-02 | 4 | 1//19
1912 | PGE | 93953 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-02-26 | 2021-03-09 | 7 | 2021-03-09 | 7 | 2021-03-10 | 1 | [18 empty] | 2021-02-26 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-03-09 |  | 2021-04-12 | 25 | 1//19
1913 | PGE | 95975 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-03-15 | 2021-03-29 | 10 | 2021-03-29 | 10 | 2021-03-30 | 1 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-04-21 | 17 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-04-27 |  | 2021-04-27 | 1 | 1//19
1914 | PGE | 95650 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-03-16 | 2021-03-30 | 10 | 2021-04-14 | 21 | 2021-04-19 | 3 | [15 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-05-05 | 26 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-05 |  | 2021-05-06 | 2 | 1//19
1915 | PGE | 94062 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-04-02 | 2021-04-14 | 8 | 2021-04-14 | 8 | 2021-04-28 | 10 | [15 empty] | 2021-04-14 | 2021-04-14 |  | 2021-04-14 | 2021-04-28 | 11 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-06 |  | 2021-08-06 | 1 | 1//19
1916 | PGE | 95223 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-05-10 | 2021-05-24 | 10 | 2021-06-07 | 19 | 2021-06-07 | 0 | [18 empty] | 2021-05-10 | 2021-06-07 | 19 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-06-02 |  | 2021-06-07 | 4 | 1//19
1917 | PGE | 94708 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-06-14 | 2021-06-17 | 3 | 2021-06-17 | 3 | 2021-06-22 | 3 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-06-22 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-06-17 |  | 2021-06-25 | 7 | 1//19
1918 | PGE | 95685 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-07-12 | 2021-07-15 | 3 | 2021-07-15 | 3 | 2021-08-02 | 12 | [15 empty] | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | 2021-08-02 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-07-15 |  | 2021-08-02 | 13 | 1//19
1919 | PGE | 94951 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-08-11 | 2021-08-13 | 2 | 2021-08-25 | 10 | 2021-08-26 | 1 | [15 empty] | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | 2021-10-13 | 33 | [5 empty] | 0 | [5 empty] | 2021-10-13 | 2021-10-20 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-13 | 2021-10-13 | 0 | 2021-10-20 |  | 2021-10-20 | 0 | 1//19
1920 | PGE | 95959 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-08-25 | 2021-08-30 | 3 | 2021-08-30 | 3 | 2021-09-07 | 5 | [15 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-09-27 | 19 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-30 |  | 2021-09-28 | 22 | 1//19
1921 | PGE | 95044 | Non-NEM | Inadvertent Export | Commercial | Storage | 15 |  | 2021-09-27 | 2021-10-11 | 10 | 2021-10-11 | 10 | 2021-10-13 | 2 | [15 empty] | 2021-10-13 | 2021-10-13 | 0 | 2021-10-13 | 2021-10-13 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-11 |  | 2021-10-15 | 5 | 1//19
1922 | PGE | 95664 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2020-12-29 | 2021-01-08 | 7 | 2021-01-08 | 7 | 2021-01-11 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-01-28 | 13 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1923 | PGE | 95442 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2020-12-30 | 2021-01-11 | 7 | 2021-01-11 | 7 | 2021-01-13 | 2 | [15 empty] | 2021-01-11 | 2021-01-11 | 0 | 2021-01-11 | 2022-01-13 | 255 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-01-11 |  | 2022-01-24 | 10 | 1//19
1924 | PGE | 93401 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-01-01 | 2021-01-11 | 5 | 2021-01-11 | 5 | 2021-01-11 | 0 | [15 empty] | 2021-01-11 | 2021-01-11 | 0 | 2021-01-11 | 2022-01-12 | 254 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1925 | PGE | 95658 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-01 | 2021-01-11 | 5 | 2021-01-11 | 5 | 2021-01-11 | 0 | [15 empty] | 2021-01-11 | 2021-01-11 | 0 | 2021-01-11 | 2022-01-14 | 256 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-01-24 |  | 2022-01-31 | 6 | 1//19
1926 | PGE | 95651 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-08 | 2021-01-22 | 9 | 2021-01-22 | 9 | 2021-01-25 | 1 | [15 empty] | 2021-01-22 | 2021-01-22 | 0 | 2021-01-22 | 2021-12-01 | 216 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-11-03 |  | 2022-01-06 | 47 | 1//19
1927 | PGE | 95682 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-01-14 | 2021-01-25 | 6 | 2021-03-16 | 41 | 2021-03-17 | 1 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2022-03-25 | 259 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1928 | PGE | 95549 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-15 | 2021-01-19 | 1 | 2021-01-29 | 9 | 2021-02-01 | 1 | [15 empty] | 2021-01-29 | 2021-01-29 | 0 | 2021-01-29 | 2022-01-31 | 253 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-02-07 |  | 2022-02-07 | 1 | 1//19
1929 | PGE | 95521 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-01-15 | 2021-01-26 | 6 | 2021-02-05 | 14 | 2021-02-08 | 1 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | 2022-02-15 | 259 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1930 | PGE | 95603 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-01-16 | 2021-01-26 | 5 | 2021-02-05 | 13 | 2021-02-08 | 1 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | 2022-02-10 | 256 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1931 | PGE | 95762 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-08 | 2021-02-19 | 8 | 2021-02-19 | 8 | 2021-02-22 | 1 | [15 empty] | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | 2021-05-25 | 67 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1932 | PGE | 95633 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-10 | 2021-02-22 | 7 | 2021-02-22 | 7 | 2021-02-23 | 1 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-05-25 | 66 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1933 | PGE | 95713 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-10 | 2021-02-22 | 7 | 2021-02-22 | 7 | 2021-02-23 | 1 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2022-02-22 | 253 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1934 | PGE | 95682 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-12 | 2021-02-23 | 6 | 2021-02-23 | 6 | 2021-02-23 | 0 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-05-26 | 66 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1935 | PGE | 95470 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-18 | 2021-02-25 | 5 | 2021-02-25 | 5 | 2021-02-26 | 1 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2022-03-04 | 258 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1936 | PGE | 95651 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-24 | 2021-03-01 | 3 | 2021-03-01 | 3 | 2021-03-02 | 1 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2022-03-09 | 259 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1937 | PGE | 95762 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-24 | 2021-03-01 | 3 | 2021-03-01 | 3 | 2021-03-02 | 1 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-10-06 | 154 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1938 | PGE | 95682 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-03-04 | 2021-03-09 | 3 | 2021-03-09 | 3 | 2021-03-11 | 2 | [15 empty] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | 2021-09-27 | 141 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1939 | PGE | 95667 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-03-16 | 2021-03-30 | 10 | 2021-06-25 | 72 | 2021-07-15 | 13 | [15 empty] | 2021-06-25 | 2021-06-25 | 0 | 2021-06-25 | 2021-07-28 | 22 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1940 | PGE | 95658 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-03-16 | 2021-03-30 | 10 | 2021-05-25 | 50 | 2021-05-28 | 3 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1941 | PGE | 95070 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-03-17 | 2021-03-31 | 10 | 2021-03-31 | 10 | 2021-04-06 | 4 | [15 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | 2021-07-07 | 68 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1942 | PGE | 94062 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-03-18 | 2021-04-01 | 10 | 2021-04-01 | 10 | 2021-04-07 | 4 | [26 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-12-21 |  | 2021-12-22 | 2 | 1//19
1943 | PGE | 95472 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-03-25 | 2021-04-08 | 10 | 2021-04-08 | 10 | 2021-04-14 | 4 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | 2021-07-28 | 77 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1944 | PGE | 95762 | Non-NEM | Non-Export | Application Accepted | Storage | 15 |  | 2021-03-28 | 2021-04-08 | 8 | 2021-04-08 | 8 | 2021-04-25 | 11 | [15 empty] | 2021-04-25 | 2021-04-25 | 0 | 2021-04-25 | 2021-07-28 | 65 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1945 | PGE | 96003 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-04-01 | 2021-04-15 | 10 | 2021-04-15 | 10 | 2021-04-22 | 5 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-11-01 | 139 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1946 | PGE | 95728 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-04-10 | 2021-04-17 | 5 | 2021-04-17 | 5 | 2021-04-21 | 2 | [15 empty] | 2021-04-17 | 2021-04-17 | 0 | 2021-04-17 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1947 | PGE | 94062 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-04-13 | 2021-04-17 | 3 | 2021-04-17 | 3 | 2022-01-04 | 180 | [15 empty] | 2022-01-04 | 2022-01-04 | 0 | 2022-01-04 | 2022-01-13 | 7 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-04-17 |  | 2022-01-18 | 197 | 1//19
1948 | PGE | 95476 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-06-18 | 2021-06-22 | 2 | 2021-06-22 | 2 | 2021-09-01 | 50 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1949 | PGE | 94022 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-07-07 | 2021-07-12 | 3 | 2021-07-12 | 3 | 2021-07-14 | 2 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-14 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1950 | PGE | 95682 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-07-08 | 2021-07-13 | 3 | 2021-07-13 | 3 | 2021-07-20 | 5 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-23 | 7 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1951 | PGE | 95070 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-07-11 | 2021-07-15 | 3 | 2021-07-15 | 3 | 2021-07-29 | 10 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-07-26 | 7 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1952 | PGE | 95672 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-07-12 | 2021-07-15 | 3 | 2021-07-15 | 3 | 2021-07-20 | 3 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-07-19 | 2 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1953 | PGE | 95667 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-07-14 | 2021-07-28 | 10 | 2021-07-28 | 10 | 2021-08-17 | 14 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1954 | PGE | 95651 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-08-10 | 2021-08-16 | 4 | 2021-08-16 | 4 | 2021-09-07 | 15 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1955 | PGE | 95667 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-09-01 | 2021-09-03 | 2 | 2021-09-03 | 2 | 2021-09-08 | 2 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-29 | 17 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1956 | PGE | 95472 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-09-01 | 2021-09-03 | 2 | 2021-09-03 | 2 | 2021-09-22 | 12 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-23 | 13 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1957 | PGE | 95033 | Non-NEM | Non-Export | Withdrawn | Storage | 15 |  | 2021-09-02 | 2021-09-17 | 10 | 2021-09-17 | 10 | 2021-10-07 | 14 | [15 empty] | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-10-30 | 16 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1958 | PGE | 95667 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-09-01 | 2021-09-10 | 6 | 2021-09-30 | 20 | 2021-10-19 | 13 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-12-09 | 34 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1959 | PGE | 93925 | Non-NEM | Inadvertent Export | Commercial | Storage | 15 |  | 2021-09-02 | 2021-09-16 | 9 | 2021-09-23 | 14 | 2021-09-27 | 2 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | 2021-12-16 | 62 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-02-23 |  | 2022-02-23 | 1 | 1//19
1960 | PGE | 95006 | Non-NEM | Non-Export | Implementation | Storage | 15 |  | 2021-05-14 | 2021-05-26 | 8 | 2021-07-23 | 48 | 2021-07-26 | 1 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-11-04 | 72 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1961 | PGE | 94043 | Non-NEM | Non-Export | Implementation | Storage | 15 |  | 2021-05-26 | 2021-06-02 | 4 | 2021-06-02 | 4 | 2021-06-11 | 7 | [15 empty] | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-10-20 | 91 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1962 | PGE | 95682 | Non-NEM | Non-Export | Implementation | Storage | 15 |  | 2021-09-01 | 2021-09-07 | 3 | 2021-09-07 | 3 | 2021-09-07 | 0 | [15 empty] | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-09-27 | 14 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1963 | PGE | 95404 | Non-NEM | Non-Export | Study in Progress | Storage | 15 |  | 2021-09-02 | 2021-09-17 | 10 | 2021-10-01 | 20 | 2021-10-22 | 15 | [15 empty] | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | 2022-01-19 | 59 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1964 | PGE | 94122 | Non-NEM | Non-Export | IA in Progress | Solar PV | 15.048 |  | 2021-07-14 | 2021-07-20 | 4 | 2021-07-27 | 9 | 2021-08-10 | 10 | [15 empty] | 2021-08-10 | 2021-08-11 | 1 | 2021-08-11 | 2022-02-07 | 123 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1965 | PGE | 94061 | Non-NEM | Non-Export | Study in Progress | Storage | 17.68 |  | 2021-03-30 | 2021-04-07 | 6 | 2021-04-07 | 6 | 2021-04-09 | 2 | [18 empty] | 2021-03-30 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1966 | PGE | 93405 | Non-NEM | Non-Export | Application Accepted | Storage | 20 |  | 2021-03-25 | 2021-03-29 | 2 | 2021-04-12 | 12 | 2021-04-19 | 5 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-04-23 | 4 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1967 | PGE | 93614 | Non-NEM | Non-Export | Commercial | Storage | 20 |  | 2021-01-08 | 2021-01-22 | 9 | 2021-01-22 | 9 | 2021-02-10 | 13 | [15 empty] | 2021-01-22 | 2021-01-22 | 0 | 2021-01-22 | 2021-03-10 | 32 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-07-21 |  | 2021-08-04 | 11 | 1//19
1968 | PGE | 95070 | Non-NEM | Non-Export | Commercial | Storage | 20 |  | 2021-04-26 | 2021-05-10 | 10 | 2021-05-26 | 22 | 2021-05-26 | 0 | [15 empty] | 2021-05-10 | 2021-05-10 |  | 2021-05-10 | 2021-05-21 | 10 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-29 |  | 2021-10-29 | 1 | 1//19
1969 | PGE | 94062 | Non-NEM | Non-Export | IA in Progress | Storage | 20 |  | 2021-09-03 | 2021-09-20 | 10 | 2021-09-20 | 10 | 2021-10-06 | 12 | [15 empty] | 2021-10-06 | 2021-10-06 | 0 | 2021-10-06 | 2021-10-06 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1970 | PGE | 95014 | Non-NEM | Break Before Make | Commercial | ENGN | 21 |  | 2021-02-12 | 2021-02-18 | 3 | 2021-02-18 | 3 | 2021-03-01 | 7 | [26 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1971 | PGE | 95030 | Non-NEM | Break Before Make | Commercial | ENGN | 22 |  | 2021-01-28 | 2021-02-03 | 4 | 2021-02-10 | 9 | 2021-03-01 | 12 | [26 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1972 | PGE | 94103 | Non-NEM | Non-Export | Commercial | Solar PV | 22.831 |  | 2021-04-12 | 2021-04-26 | 10 | 2021-05-17 | 25 | 2021-07-09 | 37 | [15 empty] | 2021-07-23 | 2021-07-23 | 0 | 2021-07-23 | 2021-07-30 | 5 | [5 empty] | 0 | [5 empty] | 2021-09-08 | 2021-09-15 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-09-08 | 2021-09-08 | 0 | 2021-09-15 |  | 2021-09-16 | 1 | 1//19
1973 | PGE | 93940 | Non-NEM | Break Before Make | Commercial | ENGN | 24 |  | 2021-03-12 | 2021-03-24 | 8 | 2021-03-26 | 10 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1974 | PGE | 94904 | Non-NEM | Non-Export | Commercial | Storage | 25 |  | 2021-03-23 | 2021-04-06 | 10 | 2021-04-06 | 10 | 2021-04-14 | 6 | [18 empty] | 2021-03-23 | 2021-05-18 | 40 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-05-27 |  | 2021-06-10 | 11 | 1//19
1975 | PGE | 94028 | Non-NEM | Non-Export | Commercial | Storage | 25 |  | 2021-08-09 | 2021-08-17 | 6 | 2021-08-17 | 6 | 2021-08-18 | 1 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | 2021-08-19 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-08-17 |  | 2021-08-24 | 6 | 1//19
1976 | PGE | 95033 | Non-NEM | Non-Export | Study in Progress | Storage | 25 |  | 2021-01-07 | 2021-01-12 | 3 | 2021-01-21 | 9 | 2021-01-22 | 1 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-01-29 | 12 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1977 | PGE | 95446 | Non-NEM | Non-Export | IA in Progress | Storage | 28.95 |  | 2021-09-22 | 2021-10-06 | 10 | 2021-10-06 | 10 | [21 empty] | 2022-01-10 | [6 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1978 | PGE | 94565 | Non-NEM | Continuous Uncompensated Export | Application Accepted | ENGN, Turbine |  |  | 2021-03-04 | 2021-03-08 | 2 | 2021-04-07 | 24 | [20 empty] | 2021-03-04 | [6 empty] | 2021-03-04 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1979 | PGE | 96088 | Non-NEM | Non-Export | Commercial | Storage |  |  | 2021-04-27 | 2021-05-11 | 10 | 2021-05-14 | 13 | 2021-06-07 | 15 | [18 empty] | 2021-04-27 | 2021-06-18 | 37 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-06-18 |  | 2021-06-18 | 1 | 1//19
1980 | PGE | 94710 | Non-NEM | Non-Export | Implementation | ENGN |  |  | 2021-01-08 | 2021-01-11 | 1 | 2021-01-21 | 8 | 2021-02-11 | 15 | 2021-03-09 | 2021-04-06 | 20 | [12 empty] | 2021-05-18 | 2021-06-09 | 15 | 2021-06-09 | 2021-06-18 | 7 | [5 empty] | 0 | [8 empty] | 2021-08-10 | 2022-01-21 | 113 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1981 | PGE | 95603 | Non-NEM | Continuous Uncompensated Export | Implementation | Solar PV |  |  | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 0 | [17 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-04-13 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1982 | PGE | 94089 | Non-NEM | Make Before Break | Study in Progress | ENGN |  |  | 2021-04-09 | 2021-04-14 | 3 | 2021-04-28 | 13 | 2021-05-21 | 17 | [25 empty] | 2021-04-09 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1983 | PGE | 95445 | Non-NEM | Non-Export | Withdrawn | Storage | 10 |  | 2020-12-30 | 2021-01-08 | 6 | 2021-01-08 | 6 | 2021-01-20 | 7 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-02-08 | 20 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1984 | PGE | 93422 | Non-NEM | Non-Export | Withdrawn | Storage | 10 |  | 2021-01-25 | 2021-02-08 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1985 | PGE | 93405 | Non-NEM | Non-Export | Withdrawn | Storage | 20 |  | 2021-02-12 | 2021-02-23 | 6 | 2021-02-23 | 6 | 2021-02-24 | 1 | [18 empty] | 2021-02-12 | [6 empty] | 2021-02-24 | 2021-02-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1986 | PGE | 95667 | Non-NEM | Non-Export | Withdrawn | Storage | 15 |  | 2021-02-26 | 2021-03-01 | 1 | 2021-03-01 | 1 | 2021-03-02 | 1 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1987 | PGE | 96022 | Non-NEM | Non-Export | Withdrawn | Storage | 25 |  | 2021-03-04 | 2021-03-16 | 8 | 2021-03-16 | 8 | 2021-03-23 | 5 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1988 | PGE | 95014 | Non-NEM | Non-Export | Withdrawn | Storage | 20 |  | 2021-03-09 | 2021-03-24 | 11 | 2021-03-24 | 11 | 2021-04-06 | 9 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1989 | PGE | 93654 | NEM | EXPNEM | Withdrawn | Solar PV | 41.76 |  | 2021-03-12 | 2021-03-26 | 10 | 2021-05-25 | 52 | 2021-06-10 | 11 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | [6 empty] | 2021-07-22 | 2021-07-30 | 6 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1990 | PGE | 93638 | Non-NEM | Non-Export | Withdrawn | ENGN |  |  | 2021-03-19 | 2021-03-19 | 0 | [29 empty] | 2021-03-19 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1991 | PGE | 95321 | Non-NEM | Non-Export | Withdrawn | Storage | 15 |  | 2021-03-23 | 2021-04-06 | 10 | 2021-04-06 | 10 | 2021-04-22 | 12 | [26 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1992 | PGE | 95014 | NEM | NEMMT | Implementation | FUCE, OTHR, Solar PV, Storage | 2400 |  | 2021-03-29 | 2021-03-30 | 1 | 2021-04-16 | 14 | 2021-05-07 | 15 | 2021-05-28 | 2021-07-08 | 27 | [12 empty] | 2021-07-08 | 2021-07-12 | 2 | 2021-07-12 | 2021-10-13 | 66 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1993 | PGE | 95033 | Non-NEM | Non-Export | Withdrawn | Storage | 10 |  | 2021-04-06 | 2021-04-17 | 8 | [22 empty] | 2021-04-06 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1994 | PGE | 95682 | Non-NEM | Non-Export | Withdrawn | Storage | 10 |  | 2021-05-19 | 2021-05-26 | 5 | 2021-05-26 | 5 | 2021-05-27 | 1 | [15 empty] | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1995 | PGE | 93637 | Non-NEM | Non-Export | Withdrawn | Storage | 10 |  | 2021-06-16 | 2021-06-22 | 4 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1996 | PGE | 93637 | Non-NEM | Non-Export | Withdrawn | Storage | 10 |  | 2021-06-16 | 2021-06-22 | 4 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1997 | PGE | 93637 | Non-NEM | Non-Export | Withdrawn | Storage | 10 |  | 2021-06-16 | 2021-06-22 | 4 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1998 | PGE | 94806 | Non-NEM | Non-Export | Withdrawn | Storage | 5 |  | 2021-06-22 | 2021-07-05 | 8 | 2021-07-05 | 8 | 2021-07-09 | 3 | [15 empty] | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
1999 | PGE | 95135 | Non-NEM | Non-Export | Withdrawn | Solar PV, Storage | 15 |  | 2021-07-06 | 2021-07-08 | 2 | [22 empty] | 2021-07-06 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2000 | PGE | 93637 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 36.423 |  | 2021-08-18 | 2021-08-30 | 8 | 2021-12-22 | 86 | 2021-12-27 | 3 | [18 empty] | 2021-08-18 | [7 empty] | 0 | [5 empty] | 2021-12-27 | 2021-12-27 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-27 |  |  | 2021-12-27 |  | 2021-12-27 | 0 | 1//19
2001 | PGE | 95667 | Non-NEM | Non-Export | Withdrawn | Storage | 15 |  | 2021-08-24 | 2021-08-27 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2002 | PGE | 95123 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.35 |  | 2021-08-25 | 2021-09-08 | 9 | 2022-01-18 | 99 | 2022-01-24 | 4 | [18 empty] | 2021-08-25 | [7 empty] | 0 | [5 empty] | 2022-03-18 | 2022-03-18 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-18 |  |  | 2022-03-18 |  | 2022-03-21 | 1 | 1//19
2003 | PGE | 96104 | Non-NEM | RESBCT | Withdrawn | Solar PV | 0.222 |  | 2021-08-28 | 0 | [31 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2004 | PGE | 94580 | Non-NEM | Non-Export | Withdrawn | Solar PV, Storage, WIND | 14.28 |  | 2021-08-28 | 0 | [31 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2005 | PGE | 95219 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 36.373 |  | 2021-09-09 | 2021-09-21 | 8 | 2021-10-22 | 31 | 2021-12-06 | 28 | [18 empty] | 2021-09-09 | [7 empty] | 0 | [5 empty] | 2021-12-06 | 2021-12-06 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-06 |  |  | 2021-12-06 |  | 2021-12-06 | 0 | 1//19
2006 | PGE | 94028 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.823 |  | 2021-09-10 | 2021-09-24 | 10 | [22 empty] | 2021-09-10 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2007 | PGE | 95573 | Non-NEM | Inadvertent Export | Withdrawn | Storage | 10 |  | 2021-09-15 | 2021-09-27 | 8 | 2021-09-27 | 8 | 2021-10-14 | 13 | [18 empty] | 2021-09-14 | 2021-09-15 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2008 | PGE | 95602 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.232 |  | 2021-09-15 | 2021-09-15 | 0 | 2021-10-15 | 22 | 2021-10-18 | 1 | [18 empty] | 2021-09-15 | [7 empty] | 0 | [5 empty] | 2021-10-18 | 2021-10-18 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-18 |  |  | 2021-10-18 |  | 2021-10-18 | 0 | 1//19
2009 | PGE | 94803 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.423 |  | 2021-09-22 | 2021-09-28 | 4 | 2021-10-26 | 24 | 2021-11-29 | 21 | [18 empty] | 2021-09-22 | [7 empty] | 0 | [5 empty] | 2021-11-29 | 2021-11-29 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-29 |  |  | 2021-11-29 |  | 2021-11-29 | 0 | 1//19
2010 | PGE | 93446 | NEM | EXPNEM | Implementation | Solar PV | 30.015 |  | 2021-09-22 | 2021-10-06 | 10 | 2021-11-22 | 42 | 2021-12-15 | 15 | [15 empty] | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 2021-12-15 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2012 | PGE | 94503 | Non-NEM | Break Before Make | Application Review in Progress | ENGN | 72 |  | 2021-09-30 | 2021-10-05 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2013 | PGE | 93243 | NEM | EXPNEM | Study in Progress | Solar PV | 1250 |  | 2021-10-01 | 2021-10-04 | 1 | 2021-10-13 | 8 | [5 empty] | 2021-10-13 | 2022-03-25 | 112 | 2022-03-25 | [5 empty] | 2022-03-25 | 2022-03-25 | 1 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2014 | PGE | 95066 | NEM | VNEMSOMAH | Implementation | Solar PV | 52.768 |  | 2021-10-01 | 2021-10-14 | 9 | 2021-10-22 | 15 | 2022-01-10 | 53 | [15 empty] | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | 2022-02-11 | 23 |  |  |  |  | 2021-10-01 | 0 |  | 2021-10-24 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2015 | PGE | 95066 | NEM | VNEMSOMAH | Implementation | Solar PV | 32.78 |  | 2021-10-01 | 2021-10-14 | 9 | 2021-10-22 | 15 | 2022-01-10 | 53 | [15 empty] | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | 2022-02-11 | 23 |  |  |  |  | 2021-10-01 | 0 |  | 2021-11-01 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2016 | PGE | 95376 | NEM | EXPNEM | Study in Progress | Solar PV | 95.8 |  | 2021-10-01 | 2021-10-13 | 8 | 2021-12-10 | 47 | 2021-12-29 | 13 | 2021-12-29 | 2022-01-27 | 20 | 2022-01-27 | 2022-02-24 | 19 | 2022-02-24 | [18 empty] | 2021-10-01 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2017 | PGE | 94801 | NEM | EXPNEM | Study in Progress | Solar PV | 2640 |  | 2021-10-01 | 2021-10-01 | 0 | 2021-10-27 | 18 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2018 | PGE | 93660 | Non-NEM | RESBCT | Withdrawn | Solar PV | 988.418 |  | 2021-10-01 | 2021-10-04 | 1 | 2021-10-13 | 8 | 2021-11-01 | 13 | [26 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2019 | PGE | 94401 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 62.643 |  | 2021-10-01 | 2021-10-12 | 7 | 2021-11-04 | 24 | 2021-11-17 | 8 | [15 empty] | 2021-11-17 | 2021-11-29 | 6 | 2021-11-29 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2020 | PGE | 95953 | NEM | VNEMMASH | Implementation | Solar PV | 35.454 |  | 2021-10-01 | 2021-10-04 | 1 | 2021-10-25 | 16 | 2021-11-10 | 12 | [15 empty] | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | 2022-01-27 | 52 |  |  |  |  | 2021-10-01 | 2021-12-16 | 51 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2021 | PGE | 95953 | NEM | VNEMMASH | Implementation | Solar PV | 38.018 |  | 2021-10-01 | 2021-10-04 | 1 | 2021-10-25 | 16 | 2021-11-10 | 12 | [15 empty] | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | 2022-01-27 | 52 |  |  |  |  | 2021-10-01 | 2021-11-29 | 38 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2022 | PGE | 94403 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-10-01 | 2021-10-12 | 7 | 2021-11-08 | 26 | 2021-11-16 | 5 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | [6 empty] | 2021-12-08 | 2021-12-29 | 15 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2023 | PGE | 95032 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.662 |  | 2021-10-01 | 2021-10-01 | 0 | 2021-10-21 | 14 | 2021-10-25 | 2 | [18 empty] | 2021-10-01 | [6 empty] | 2021-10-01 | 0 | [5 empty] | 2021-11-18 | 2021-11-18 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-18 |  |  | 2021-11-18 |  | 2021-11-18 | 0 | 1//19
2024 | PGE | 95205 | NEM | EXPNEM | Implementation | Solar PV | 97.071 |  | 2021-10-01 | 2021-10-07 | 4 | 2021-10-07 | 4 | 2021-11-19 | 30 | [15 empty] | 2021-11-19 | 2021-11-29 | 4 | 2021-11-29 | 2021-11-30 | 1 | [5 empty] | 0 | [5 empty] | 2022-03-30 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-30 | [6 empty] | 1//19
2025 | PGE | 93710 | NEM | EXPNEM | Implementation | Solar PV | 312 |  | 2021-10-02 | 2021-10-13 | 7 | 2021-10-13 | 7 | 2021-11-01 | 13 | [15 empty] | 2021-11-01 | 2021-11-01 | 0 | 2021-11-01 | 2022-03-10 | 88 |  |  |  |  | 2021-10-02 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2026 | PGE | 93703 | NEM | EXPNEM | IA in Progress | Solar PV | 192 |  | 2021-10-02 | 2021-10-04 | 0 | 2021-10-05 | 1 | 2021-10-19 | 10 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | [6 empty] | 2021-10-02 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2027 | PGE | 93725 | NEM | EXPNEM | IA in Progress | Solar PV | 312 |  | 2021-10-02 | 2021-10-15 | 9 | 2021-10-15 | 9 | 2021-10-25 | 6 | [15 empty] | 2021-10-25 | 2021-10-25 | 0 | 2021-10-25 | [6 empty] | 2021-10-02 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2028 | PGE | 93701 | NEM | EXPNEM | Implementation | Solar PV | 180 |  | 2021-10-02 | 2021-10-11 | 5 | 2021-10-11 | 5 | 2021-10-20 | 7 | [15 empty] | 2021-10-20 | 2021-10-20 | 0 | 2021-10-20 | 2022-01-31 | 69 |  |  |  |  | 2021-10-02 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2029 | PGE | 93704 | NEM | EXPNEM | IA in Progress | Solar PV | 195.759 |  | 2021-10-02 | 2021-10-15 | 9 | 2021-10-15 | 9 | 2021-11-04 | 14 | [15 empty] | 2021-11-04 | 2021-11-30 | 15 | 2021-11-30 | [6 empty] | 2021-10-02 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2030 | PGE | 95076 | NEM | VNEMSOMAH | Implementation | Solar PV | 66.959 |  | 2021-10-04 | 2021-10-06 | 2 | 2021-10-08 | 4 | 2021-11-23 | 31 | [15 empty] | 2021-11-23 | 2021-11-23 | 0 | 2021-11-23 | 2022-02-10 | 54 |  |  |  |  | 2021-10-04 | 2021-11-23 | 35 |  | 2021-11-23 | 2021-11-23 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2031 | PGE | 95912 | NEM | EXPNEM | Commercial | Solar PV | 125 |  | 2021-10-04 | 2021-10-11 | 5 | 2021-10-12 | 6 | 2021-11-30 | 32 | [15 empty] | 2021-11-30 | 2021-12-01 | 1 | 2021-12-01 | 2021-12-02 | 1 |  |  |  |  | 2021-12-01 | 2021-12-02 | 1 |  |  |  |  | 2022-02-17 | 2022-03-01 | 7 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-17 | 2022-02-17 | 0 | 2022-03-01 |  | 2022-03-01 | 0 | 1//19
2032 | PGE | 94954 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 786.5 |  | 2021-10-04 | 2021-10-17 | 9 | 2021-11-05 | 24 | 2021-12-22 | 30 | 2021-12-22 | 2022-01-14 | 17 | [12 empty] | 2022-01-14 | 2022-02-07 | 15 | 2022-02-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2033 | PGE | 94589 | NEM | VNEMSOMAH | Implementation | Solar PV | 100.91 |  | 2021-10-04 | 2021-10-06 | 2 | 2021-10-08 | 4 | 2021-11-10 | 23 | [15 empty] | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | 2021-12-02 | 13 |  |  |  |  | 2021-10-04 | 2021-11-03 | 22 |  | 2021-11-05 | 2021-11-10 | 3 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2034 | PGE | 94589 | NEM | VNEMSOMAH | Implementation | Solar PV | 103.993 |  | 2021-10-04 | 2021-10-06 | 2 | 2021-10-08 | 4 | 2021-11-10 | 23 | [15 empty] | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | 2022-01-12 | 42 |  |  |  |  | 2021-10-04 | 2021-11-03 | 22 |  | 2021-11-05 | 2021-11-10 | 3 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2035 | PGE | 93446 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-10-04 | 2021-10-15 | 9 | 2021-10-28 | 18 | 2021-11-19 | 15 | [15 empty] | 2021-11-19 | 2021-11-19 | 0 | 2021-11-19 | 2021-12-29 | 26 |  |  |  |  | 2021-10-04 | 0 | [5 empty] | 2021-12-31 | 2022-01-11 | 7 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-31 | 2022-01-03 | 1 | 2022-01-11 |  | 2022-01-12 | 1 | 1//19
2036 | PGE | 94517 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-10-04 | 2021-10-07 | 3 | 2021-10-07 | 3 | 2021-10-13 | 4 | [15 empty] | 2021-10-13 | 2021-10-13 | 0 | 2021-10-13 | 2021-10-13 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2037 | PGE | 95948 | NEM | EXPNEM | IA in Progress | Solar PV | 214.508 |  | 2021-10-04 | 2021-10-06 | 2 | 2021-10-14 | 8 | 2021-10-28 | 10 | [15 empty] | 2021-10-28 | 2021-10-28 | 0 | 2021-10-28 | [6 empty] | 2021-10-14 | 2021-10-27 | 9 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2038 | PGE | 93243 | NEM | EXPNEM | Application Review in Progress | Solar PV | 875 |  | 2021-10-04 | 2021-10-18 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2039 | PGE | 95503 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-10-05 | 2021-10-08 | 3 | 2021-10-08 | 3 | 2021-10-14 | 4 | [15 empty] | 2021-10-14 | 2021-10-14 | 0 | 2021-10-14 | 2021-10-14 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2040 | PGE | 93402 | NEM | VNEM | Commercial | Solar PV | 200 |  | 2021-10-05 | 2021-10-15 | 8 | 2021-10-20 | 11 | 2021-12-13 | 35 | [15 empty] | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13 | 2021-12-15 | 2 | [5 empty] | 0 | [5 empty] | 2022-03-22 | 2022-03-28 | 4 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-22 | 2022-03-23 | 1 | 2022-03-28 |  | 2022-03-29 | 1 | 1//19
2041 | PGE | 95959 | NEM | EXPNEM | IA in Progress | Solar PV | 137.349 |  | 2021-10-05 | 2021-10-12 | 5 | 2021-10-27 | 16 | 2021-11-10 | 10 | 2021-11-10 | 2022-01-25 | 50 | [12 empty] | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2042 | PGE | 94903 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 37.598 |  | 2021-10-05 | 2021-10-19 | 10 | 2021-10-21 | 12 | 2021-11-12 | 15 | [15 empty] | 2021-11-12 | 2021-11-12 | 0 | 2021-11-12 | [6 empty] | 2021-10-05 | 2021-12-15 | 48 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2043 | PGE | 95117 | NEM | EXPNEM | Withdrawn | Solar PV | 34.65 |  | 2021-10-05 | 2021-10-13 | 6 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2044 | PGE | 95361 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.163 |  | 2021-10-05 | 2021-10-05 | 0 | [22 empty] | 2021-10-05 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2045 | PGE | 94571 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-10-05 | 2021-10-12 | 5 | 2021-10-12 | 5 | 2021-10-28 | 12 | [15 empty] | 2021-10-28 | 2021-11-01 | 2 | 2021-11-01 | 2021-11-05 | 4 | [5 empty] | 0 | [5 empty] | 2021-11-05 | 2022-02-03 | 60 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-05 | 2022-02-03 | 60 | 2022-02-03 |  | 2022-02-03 | 0 | 1//19
2046 | PGE | 94571 | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.3 |  | 2021-10-05 | 2021-10-13 | 6 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2047 | PGE | 94558 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 159.12 |  | 2021-10-05 | 2021-10-08 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2048 | PGE | 94903 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 37.598 |  | 2021-10-05 | 2021-10-19 | 10 | 2021-10-21 | 12 | 2021-11-12 | 15 | [15 empty] | 2021-11-12 | 2021-11-12 | 0 | 2021-11-12 | [6 empty] | 2021-10-05 | 2021-12-15 | 48 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2049 | PGE | 93701 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-10-05 | 2021-10-12 | 5 | 2021-10-12 | 5 | 2021-10-22 | 8 | [15 empty] | 2021-10-22 | 2021-10-25 | 1 | 2021-10-25 | [6 empty] | 2021-10-05 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2050 | PGE | 93727 | NEM | EXPNEM | Implementation | Solar PV | 216 |  | 2021-10-05 | 2021-10-12 | 5 | 2021-10-12 | 5 | 2021-10-25 | 9 | [15 empty] | 2021-10-25 | 2021-10-25 | 0 | 2021-10-25 | 2022-03-10 | 93 |  |  |  |  | 2021-10-05 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2051 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 86.4 |  | 2021-10-05 | 2021-10-07 | 2 | 2021-10-07 | 2 | 2021-10-14 | 5 | [15 empty] | 2021-10-14 | 2021-10-14 | 0 | 2021-10-14 | 2021-10-15 | 1 | [5 empty] | 0 | [5 empty] | 2021-10-25 | 2021-11-03 | 7 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-10-25 | 2021-10-25 | 0 | 2021-11-03 |  | 2021-11-03 | 0 | 1//19
2052 | PGE | 95240 | NEM | EXPNEM | Study in Progress | Solar PV | 600 |  | 2021-10-05 | 2021-10-17 | 8 | 2021-11-04 | 22 | 2022-01-18 | 49 | 2022-01-18 | 2022-02-15 | 20 | 2022-02-15 | 2022-03-08 | 14 | 2022-03-08 | [18 empty] | 2021-10-05 | 2021-11-29 | 36 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2053 | PGE | 93711 | NEM | EXPNEM | Application Accepted | Solar PV | 255.598 |  | 2021-10-05 | 2021-10-07 | 2 | 2021-10-07 | 2 | 2021-10-20 | 9 | [25 empty] | 2021-10-05 | 0 |  | 2021-10-18 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2054 | PGE | 95361 | NEM | EXPNEM | Implementation | Solar PV | 1392.353 |  | 2021-10-05 | 2021-10-05 | 0 | 2021-10-20 | 11 | 2021-11-16 | 18 | [15 empty] | 2021-11-29 | 2021-12-02 | 3 | 2021-12-02 | 2022-02-17 | 54 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2055 | PGE | 95212 | NEM | EXPNEM | Study in Progress | Solar PV | 98.083 |  | 2021-10-06 | 2021-10-11 | 3 | 2021-12-09 | 43 | 2021-12-23 | 10 | 2021-12-23 | 2022-01-25 | 22 | 2022-01-25 | 2022-02-14 | 14 | 2022-02-14 | [18 empty] | 2021-10-06 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2056 | PGE | 94945 | NEM | EXPNEM | IA in Progress | Solar PV | 36 |  | 2021-10-06 | 2021-10-07 | 1 | 2021-10-07 | 1 | 2021-10-21 | 10 | [15 empty] | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2057 | PGE | 95070 | NEM | EXPNEM | Application Review in Progress | Solar PV | 36.149 |  | 2021-10-06 | 2021-10-07 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2058 | PGE | 93705 | NEM | EXPNEM | Implementation | Solar PV | 180 |  | 2021-10-06 | 2021-10-18 | 8 | 2021-10-18 | 8 | 2021-11-01 | 10 | [15 empty] | 2021-11-01 | 2021-11-01 | 0 | 2021-11-01 | 2022-03-10 | 88 |  |  |  |  | 2021-10-06 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2059 | PGE | 95415 | NEM | EXPNEM | Application Review in Progress | Solar PV | 36 |  | 2021-10-06 | 2021-10-18 | 8 | [29 empty] | 2021-10-06 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2060 | PGE | 94563 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-10-06 | 2021-10-06 | 0 | 2021-11-18 | 30 | 2021-11-22 | 2 | [18 empty] | 2021-10-06 | [6 empty] | 2021-10-06 | 0 | [5 empty] | 2022-02-25 | 2022-03-06 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-25 | 2022-02-27 | 0 | 2022-03-06 |  | 2022-03-10 | 3 | 1//19
2062 | PGE | 93309 | NEM | EXPNEM | Implementation | Solar PV | 1200 |  | 2021-10-06 | 2021-10-08 | 2 | 2021-10-13 | 5 | [5 empty] | 2021-10-19 | 2021-11-15 | 18 | 2021-11-15 |  |  | 2021-11-23 | 2022-02-11 | 55 | 2021-11-22 | 2021-11-15 | 262 | 2022-03-16 | 2022-03-21 | 3 | 2022-03-21 | 2022-03-28 | 5 | [5 empty] | 0 |  | 2021-12-01 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2063 | PGE | 95377 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 280 |  | 2021-10-06 | 2021-10-07 | 1 | 2021-11-03 | 20 | 2021-11-24 | 14 | 2021-12-17 | 2022-01-12 | 18 | 2022-02-10 | 2022-03-04 | 15 | 2022-03-04 | 2022-03-09 | 3 |  |  |  | 2022-03-09 | 2022-03-10 | 1 | [10 empty] | 2021-10-06 | 2021-11-09 | 24 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2064 | PGE | 93401 | NEM | VNEM | Study in Progress | Solar PV | 42.586 |  | 2021-10-06 | 2021-10-20 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2065 | PGE | 93644 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 36.223 |  | 2021-10-07 | 2021-10-08 | 1 | 2021-12-01 | 36 | 2021-12-03 | 2 | [18 empty] | 2021-10-07 | [7 empty] | 0 | [5 empty] | 2021-12-03 | 2021-12-03 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-03 |  |  | 2021-12-03 |  | 2021-12-03 | 0 | 1//19
2066 | PGE | 95020 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.393 |  | 2021-10-07 | 2021-10-08 | 1 | 2021-12-14 | 45 | 2021-12-20 | 4 | [26 empty] | 0 | [5 empty] | 2021-12-20 | 2021-12-20 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-20 |  |  | 2021-12-20 |  | 2021-12-20 | 0 | 1//19
2067 | PGE | 95521 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-10-07 | 2021-10-21 | 10 | 2021-10-21 | 10 | 2021-11-05 | 11 | [18 empty] | 2021-10-06 | 2021-10-21 | 11 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2068 | PGE | 95037 | NEM | EXPNEM | Application Review in Progress | Solar PV | 259.89 |  | 2021-10-07 | 2021-10-15 | 6 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2069 | PGE | 95991 | NEM | EXPNEM | Study in Progress | Solar PV | 364.492 |  | 2021-10-07 | 2021-10-14 | 5 | 2021-10-26 | 13 | 2021-11-15 | 13 | 2021-11-15 | 2022-02-02 | 54 | [22 empty] | 2021-10-07 | 2021-11-04 | 20 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2070 | PGE | 93637 | NEM | EXPNEM | Study in Progress | Solar PV | 4954.17 |  | 2021-10-07 | 2021-10-08 | 1 | 2021-10-13 | 4 | [5 empty] | 2021-10-18 | 2021-11-16 | 20 | 2021-11-16 | 2021-11-30 | 8 | 2022-02-15 |  |  | 2021-11-30 | 2021-12-17 | 13 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2071 | PGE | 94503 | Non-NEM | Break Before Make | Application Review in Progress | ENGN |  |  | 2021-10-07 | 2021-10-12 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2072 | PGE | 95501 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 10 |  | 2021-10-07 | 2021-10-20 | 9 | [22 empty] | 2021-10-04 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2073 | PGE | 95338 | NEM | EXPNEM | Implementation | Solar PV | 62.5 |  | 2021-10-07 | 2021-10-11 | 2 | 2021-10-27 | 14 | 2021-11-10 | 10 | [15 empty] | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | 2021-11-16 | 3 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2074 | PGE | 93727 | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.2 |  | 2021-10-07 | 2021-10-18 | 7 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2075 | PGE | 93309 | NEM | EXPNEM | Commercial | Solar PV | 33.128 |  | 2021-10-07 | 2021-10-15 | 6 | 2021-10-25 | 12 | 2021-10-27 | 2 | [15 empty] | 2021-10-27 | 2021-10-27 | 0 | 2021-10-27 | 2021-11-19 | 16 | [5 empty] | 0 | [5 empty] | 2021-11-30 | 2021-12-28 | 20 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-30 | 2021-12-17 | 13 | 2021-12-28 |  | 2021-12-29 | 1 | 1//19
2076 | PGE | 93309 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-10-07 | 2021-10-15 | 6 | 2021-10-19 | 8 | 2021-10-21 | 2 | [15 empty] | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21 | 2021-11-19 | 20 | [5 empty] | 0 | [5 empty] | 2021-11-30 | 2021-12-28 | 20 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-30 | 2021-12-17 | 13 | 2021-12-28 |  | 2021-12-29 | 1 | 1//19
2077 | PGE | 94928 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 5750.204 |  | 2021-10-08 | 2021-10-08 | 0 | 2021-10-27 | 13 | [5 empty] | 2021-10-27 | 2021-11-23 | 18 | 2021-11-23 | 2021-11-23 | 0 | 2021-12-09 | 2022-03-21 | 70 | 2021-11-23 | 2021-11-23 | 0 | [11 empty] | 0 |  | 2021-11-29 | 2021-11-29 | 2021-11-29 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2078 | PGE | 94612 | NEM | EXPNEM | Withdrawn | Solar PV | 37.196 |  | 2021-10-08 | 2021-10-14 | 4 | 2021-10-27 | 13 | 2021-11-15 | 12 | [26 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2079 | PGE | 94562 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 53.892 |  | 2021-10-08 | 2021-10-22 | 10 | 2021-10-22 | 10 | 2021-11-12 | 14 | [15 empty] | 2022-01-10 | 2022-01-28 | 13 | 2022-01-28 | 2022-01-28 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2080 | PGE | 94930 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 30.402 |  | 2021-10-08 | 2021-10-18 | 6 | 2021-11-02 | 17 | 2021-11-24 | 15 | [15 empty] | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | [6 empty] | 2021-10-08 | 0 |  | 2021-12-13 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2081 | PGE | 94558 | NEM | EXPNEM | Commercial | Solar PV | 34.179 |  | 2021-10-08 | 2021-10-19 | 7 | 2021-10-19 | 7 | 2021-10-26 | 5 | [15 empty] | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26 | 2021-10-29 | 3 | [5 empty] | 0 | [5 empty] | 2021-11-17 | 2021-11-30 | 7 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-17 | 2021-11-17 | 0 | 2021-11-30 |  | 2021-12-01 | 1 | 1//19
2082 | PGE | 93656 | NEM | EXPNEM | Study in Progress | Solar PV | 2375 |  | 2021-10-08 | 2021-10-12 | 2 | 2021-10-20 | 8 | [5 empty] | 2021-11-17 | 2021-12-17 | 20 | 2021-12-17 | 2021-12-22 | 3 |  |  |  | 2021-12-22 | [13 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2083 | PGE | 94949 | NEM | SNEM Paired Storage | Withdrawn | Solar PV, Storage | 45.15 |  | 2021-10-08 | 2021-10-11 | 1 | [22 empty] | 2021-10-08 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2084 | PGE | 93245 | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-10-08 | 2021-10-22 | 10 | 2021-12-08 | 40 | 2021-12-28 | 14 | [15 empty] | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28 | 2021-12-29 | 1 |  |  |  |  | 2021-11-10 | 2021-12-06 | 15 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2085 | PGE | 95035 | NEM | EXPNEM | IA in Progress | Solar PV | 180.797 |  | 2021-10-08 | 2021-10-18 | 6 | 2021-12-21 | 49 | 2022-02-25 | 46 | [15 empty] | 2022-02-25 | 2022-02-25 | 0 | 2022-02-25 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2086 | PGE | 95341 | NEM | EXPNEM | Study in Progress | Solar PV | 4125 |  | 2021-10-08 | 2021-10-12 | 2 | 2021-10-20 | 8 | [5 empty] | 2021-11-01 | 2021-11-30 | 18 | 2021-11-30 | 2021-12-07 | 5 | 2021-12-13 | 2022-03-11 | 62 | 2021-12-07 | 2021-12-08 | 1 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2087 | PGE | 93725 | NEM | EXPNEM | Implementation | Solar PV | 227.075 |  | 2021-10-09 | 2021-10-19 | 6 | 2021-10-19 | 6 | 2021-11-01 | 9 | [15 empty] | 2021-11-01 | 2021-11-02 | 1 | 2021-11-02 | 2022-03-22 | 95 |  |  |  |  | 2021-10-09 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2088 | PGE | 93940 | NEM | EXPNEM | IA in Progress | Solar PV | 58.645 |  | 2021-10-11 | 2021-10-18 | 5 | 2021-11-02 | 16 | 2021-12-10 | 25 | [15 empty] | 2021-12-10 | 2021-12-10 | 0 | 2021-12-10 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2089 | PGE | 93940 | NEM | EXPNEM | IA in Progress | Solar PV | 105.02 |  | 2021-10-11 | 2021-10-25 | 10 | 2021-11-05 | 19 | 2021-12-14 | 24 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2090 | PGE | 94603 | NEM | EXPNEM | Implementation | Solar PV | 91.26 |  | 2021-10-11 | 2021-10-14 | 3 | 2021-10-14 | 3 | 2021-10-18 | 2 | [15 empty] | 2021-10-18 | 2021-10-18 | 0 | 2021-10-18 | 2021-11-09 | 16 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2091 | PGE | 94550 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 38.396 |  | 2021-10-11 | 2021-10-21 | 8 | 2022-01-05 | 59 | 2022-01-06 | 1 | [26 empty] | 0 | [5 empty] | 2022-01-06 | 2022-01-06 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-06 |  |  | 2022-01-06 |  | 2022-01-06 | 0 | 1//19
2092 | PGE | 95112 | NEM | EXPNEM | Withdrawn | Solar PV | 633.3 |  | 2021-10-11 | 2021-10-14 | 3 | 2021-11-05 | 19 | 2021-12-16 | 26 | [15 empty] | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2093 | PGE | 94010 | NEM | EXPNEM | Commercial | Solar PV | 58.883 |  | 2021-10-11 | 2021-10-25 | 10 | 2021-11-10 | 22 | 2021-12-27 | 30 | [15 empty] | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27 | 2022-01-03 | 5 | [5 empty] | 0 | [5 empty] | 2022-01-21 | 2022-01-27 | 4 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-21 | 2022-01-21 | 0 | 2022-01-27 |  | 2022-02-04 | 6 | 1//19
2094 | PGE | 93940 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-10-11 | 2021-10-14 | 3 | 2021-10-14 | 3 | 2021-10-28 | 10 | [15 empty] | 2021-10-28 | 2021-11-01 | 2 | 2021-11-01 | [6 empty] | 2021-10-11 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2095 | PGE | 93940 | NEM | EXPNEM | IA in Progress | Solar PV | 40.354 |  | 2021-10-11 | 2021-10-14 | 3 | 2021-10-14 | 3 | 2021-10-28 | 10 | [15 empty] | 2021-10-28 | 2021-11-01 | 2 | 2021-11-01 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2096 | PGE | 93420 | NEM | EXPNEM | Implementation | Solar PV | 120.756 |  | 2021-10-11 | 2021-10-13 | 2 | 2021-12-07 | 38 | 2022-01-21 | 32 | [15 empty] | 2022-01-21 | 2022-01-21 | 0 | 2022-01-21 | 2022-02-16 | 18 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2097 | PGE | 94025 | NEM | EXPNEM | Implementation | Solar PV | 170.14 |  | 2021-10-11 | 2021-10-13 | 2 | 2021-10-21 | 8 | 2021-10-21 | 0 | [15 empty] | 2021-10-21 | 2021-10-22 | 1 | 2021-10-22 | 2022-01-03 | 48 |  |  |  |  | 2021-10-11 | 2021-12-06 | 37 |  |  |  |  | 2022-01-26 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-26 | 2022-01-26 | 0 |  |  |  |  | 1//19
2098 | PGE | 93206 | NEM | EXPNEM | IA in Progress | Solar PV | 150 |  | 2021-10-11 | 2021-10-25 | 10 | 2021-11-04 | 18 | [5 empty] | 2021-11-04 | 2021-12-07 | 20 | 2021-12-07 | 2021-12-07 |  | 2021-12-07 | 2022-03-28 | 80 | 2021-12-07 |  |  | 2022-03-28 | 2022-03-30 | 2 | 2022-03-30 | [6 empty] | 2021-10-11 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2099 | PGE | 94507 | NEM | EXPNEM | Implementation | Solar PV | 193.9 |  | 2021-10-11 | 2021-10-22 | 9 | 2021-11-01 | 15 | 2021-11-16 | 10 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-12-08 | 14 |  |  |  |  | 2021-10-11 | 2021-11-22 | 29 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2100 | PGE | 94025 | NEM | EXPNEM | Implementation | Solar PV | 172.823 |  | 2021-10-12 | 2021-10-22 | 8 | 2021-11-19 | 27 | 2021-12-13 | 14 | [15 empty] | 2021-12-13 | 2021-12-28 | 11 | 2021-12-28 | 2022-01-27 | 21 |  |  |  |  | 2021-10-12 | 0 |  | 2022-02-16 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2101 | PGE | 94947 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-10-12 | 2021-10-22 | 8 | 2021-10-25 | 9 | 2021-11-01 | 5 | [18 empty] | 2021-10-11 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-11-01 |  | 2021-11-01 | 1 | 1//19
2102 | PGE | 93940 | NEM | EXPNEM | IA in Progress | Solar PV | 37.75 |  | 2021-10-12 | 2021-10-13 | 1 | 2021-10-13 | 1 | 2021-10-26 | 9 | [15 empty] | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26 | [6 empty] | 2021-10-12 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2103 | PGE | 95035 | NEM | VNEM | Implementation | Solar PV | 37.8 |  | 2021-10-12 | 2021-10-19 | 5 | 2021-10-22 | 8 | 2021-11-09 | 12 | [15 empty] | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | 2021-12-08 | 18 |  |  |  |  | 2021-10-12 | 0 |  | 2021-11-01 | 2021-11-09 | 2021-12-09 | 6 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2104 | PGE | 95060 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 980 |  | 2021-10-12 | 2021-10-13 | 1 | 2021-12-15 | 43 | 2022-01-27 | 30 | [15 empty] | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2105 | PGE | 95603 | NEM | EXPNEM | Implementation | Solar PV | 40.891 |  | 2021-10-12 | 2021-10-26 | 10 | 2021-10-26 | 10 | 2021-11-08 | 9 | [15 empty] | 2021-11-08 | 2021-11-08 | 0 | 2021-11-08 | 2022-01-25 | 52 | [5 empty] | 0 | [5 empty] | 2022-03-18 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-18 | 2022-03-21 | 1 |  |  |  |  | 1//19
2106 | PGE | 93311 | NEM | EXPNEM | Study in Progress | ENGN | 1000 |  | 2021-10-12 | 2021-10-15 | 3 | 2021-10-15 | 3 | 2021-10-31 | 10 | 2021-10-31 | 2021-11-30 | 18 | 2021-11-30 | 2021-12-29 | 21 | 2021-12-29 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2107 | PGE | 93940 | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-10-12 | 2021-10-14 | 2 | 2021-10-14 | 2 | 2021-10-28 | 10 | [15 empty] | 2021-10-28 | 2021-11-01 | 2 | 2021-11-01 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2108 | PGE | 93705 | NEM | EXPNEM | IA in Progress | Solar PV | 230 |  | 2021-10-12 | 2021-10-26 | 10 | 2021-11-02 | 15 | 2021-11-09 | 5 | [15 empty] | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | [6 empty] | 2021-10-12 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2109 | PGE | 95304 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 1304.8 |  | 2021-10-12 | 2021-10-12 | 0 | 2021-11-10 | 21 | 2021-12-31 | 34 | [25 empty] | 2021-10-12 | 2021-12-15 | 43 | 2021-12-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2110 | PGE | 94558 | NEM | EXPNEM | Commercial | Solar PV | 31.868 |  | 2021-10-12 | 2021-10-22 | 8 | 2021-11-17 | 25 | 2021-12-06 | 11 | [15 empty] | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-08 | 2 | [5 empty] | 0 | [5 empty] | 2021-12-22 | 2022-01-05 | 10 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-22 | 2021-12-22 | 0 | 2022-01-05 |  | 2022-01-06 | 1 | 1//19
2111 | PGE | 93901 | NEM | EXPNEM | Implementation | Solar PV | 300 |  | 2021-10-12 | 2021-10-18 | 4 | 2021-10-21 | 7 | 2021-10-28 | 5 | [15 empty] | 2021-10-28 | 2021-11-17 | 13 | 2021-11-17 | 2021-12-31 | 30 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2112 | PGE | 95112 | NEM | EXPNEM | Implementation | Solar PV | 93.5 |  | 2021-10-12 | 2021-10-26 | 10 | 2022-01-04 | 57 | 2022-01-24 | 13 | [15 empty] | 2022-01-24 | 2022-01-24 | 0 | 2022-01-24 | 2022-01-27 | 3 |  |  |  |  | 2021-10-12 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2113 | PGE | 94710 | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 |  | 2021-10-12 | 2021-10-26 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2114 | PGE | 93706 | NEM | EXPNEM | Commercial | Solar PV | 52.882 |  | 2021-10-12 | 2021-10-13 | 1 | 2021-10-15 | 3 | 2021-11-08 | 16 | [15 empty] | 2021-11-08 | 2021-11-08 | 0 | 2021-11-08 | 2021-11-19 | 8 | [5 empty] | 0 | [5 empty] | 2021-11-22 | 2021-12-23 | 21 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-22 | 2021-12-16 | 16 | 2021-12-23 |  | 2021-12-24 | 1 | 1//19
2115 | PGE | 95503 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-10-12 | 2021-10-25 | 9 | 2021-11-15 | 23 | 2021-12-02 | 11 | [18 empty] | 2021-10-11 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2116 | PGE | 94080 | NEM | EXPNEM | Implementation | Solar PV | 60 |  | 2021-10-12 | 2021-10-13 | 1 | 2021-11-01 | 14 | 2021-11-16 | 10 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-19 | 3 |  |  |  |  | 2021-10-12 | 2021-12-15 | 43 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2117 | PGE | 93637 | NEM | EXPNEM | Implementation | Solar PV | 420 |  | 2021-10-12 | 2021-10-14 | 2 | 2021-10-14 | 2 | 2021-10-29 | 11 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | 2021-11-29 | 18 |  |  |  |  | 2021-10-12 | 2021-10-27 | 11 | [7 empty] | 2022-03-31 | 2022-04-06 | 4 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2118 | PGE | 94583 | Non-NEM | Inadvertent Export | Application Accepted | Storage | 929.5 |  | 2021-10-13 | 2021-10-13 | 0 | 2021-11-24 | 29 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2119 | PGE | 94563 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-10-12 | 2021-10-13 | 1 | 2021-10-13 | 1 | 2021-10-14 | 1 | [18 empty] | 2021-10-12 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-02-09 |  | 2022-02-09 | 1 | 1//19
2120 | PGE | 94133 | NEM | EXPNEM | Implementation | Solar PV | 72 |  | 2021-10-13 | 2021-10-15 | 2 | 2021-11-29 | 30 | 2021-12-13 | 10 | [15 empty] | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13 | 2022-03-28 | 73 |  |  |  |  | 2021-11-29 | 2021-12-15 | 12 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2121 | PGE | 94588 | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-10-13 | 2021-10-14 | 1 | 2021-10-26 | 9 | 2021-10-28 | 2 | [15 empty] | 2021-10-28 | 2021-10-28 | 0 | 2021-10-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2122 | PGE | 94566 | NEM | EXPNEM | Study in Progress | Solar PV | 483.1 |  | 2021-10-13 | 2021-10-27 | 10 | 2021-12-13 | 40 | 2022-02-14 | 44 | 2022-02-14 | 2022-03-21 | 24 | [23 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2123 | PGE | 93420 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-10-13 | 2021-10-27 | 10 | 2021-11-04 | 16 | 2021-11-18 | 9 | [18 empty] | 2021-10-13 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2124 | PGE | 94566 | NEM | EXPNEM | Withdrawn | Solar PV | 400 |  | 2021-10-13 | 2021-10-26 | 9 | 2021-11-19 | 26 | [28 empty] | 0 |  | 2021-12-13 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2125 | PGE | 94566 | NEM | EXPNEM | Withdrawn | Solar PV | 524.8 |  | 2021-10-13 | 2021-10-27 | 10 | 2021-10-27 | 10 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2126 | PGE | 95209 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2330 |  | 2021-10-14 | 2021-10-14 | 0 | 2021-11-17 | 23 | [5 empty] | 2021-12-03 | 2022-01-05 | 23 | 2022-01-05 | 2022-01-13 | 6 | 2022-01-25 |  |  | 2022-01-13 | 2022-01-20 | 4 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2127 | PGE | 93640 | NEM | EXPNEM | Implementation | Solar PV | 840 |  | 2021-10-14 | 2021-10-14 | 0 | 2021-10-21 | 5 | 2021-12-23 | 42 | [15 empty] | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23 | 2022-01-04 | 8 |  |  |  |  | 2021-10-14 | 2021-10-27 | 9 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2128 | PGE | 95409 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-10-14 | 2021-10-15 | 1 | 2022-01-10 | 59 | 2022-01-31 | 14 | [15 empty] | 2021-10-14 | 2021-10-14 | 0 | 2021-10-14 | 2021-10-14 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-14 |  | 2022-01-31 | 78 | 1//19
2129 | PGE | 93720 | NEM | EXPNEM | Implementation | Solar PV | 312.5 |  | 2021-10-14 | 2021-10-18 | 2 | 2021-10-18 | 2 | 2021-11-08 | 15 | [15 empty] | 2021-11-08 | 2021-12-02 | 15 | 2021-12-02 | 2022-03-09 | 67 |  |  |  |  | 2021-10-14 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2130 | PGE | 95901 | NEM | EXPNEM | IA in Progress | Solar PV | 480 |  | 2021-10-14 | 2021-10-18 | 2 | 2021-11-05 | 16 | 2021-11-22 | 10 | 2021-11-22 | 2022-02-15 | 58 | [12 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | [6 empty] | 2021-10-14 | 2021-11-01 | 12 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2131 | PGE | 94538 | NEM | EXPNEM | Application Review in Progress | Solar PV | 500 |  | 2021-10-14 | 2021-10-18 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2132 | PGE | 95337 | NEM | EXPNEM | Study in Progress | Solar PV | 200 |  | 2021-10-14 | 2021-10-28 | 10 | 2021-10-28 | 10 | 2021-12-09 | 27 | 2021-12-09 | 2022-01-06 | 20 | 2022-01-06 | 2022-02-04 | 20 | 2022-02-04 | [18 empty] | 2021-10-14 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2133 | PGE | 93203 | Non-NEM | Inadvertent Export | Application Accepted | Storage | 929.5 |  | 2021-10-14 | 2021-10-15 | 1 | 2021-11-24 | 28 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2134 | PGE | 94588 | NEM | EXPNEM | IA in Progress | Solar PV | 225 |  | 2021-10-15 | 2021-10-28 | 9 | 2021-11-16 | 21 | 2021-12-21 | 23 | [15 empty] | 2021-12-21 | 2021-12-21 | 0 | 2021-12-21 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2135 | PGE | 93249 | Non-NEM | Non-Export | Implementation | Solar PV | 747.708 |  | 2021-10-15 | 2021-10-18 | 1 | 2021-10-27 | 8 | 2021-12-08 | 27 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | 2022-03-04 | 60 |  |  |  |  | 2021-11-04 | 2021-12-03 | 18 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2136 | PGE | 93654 | NEM | EXPNEM | Withdrawn | Solar PV | 44.593 |  | 2021-10-15 | 2021-10-22 | 5 | 2022-02-23 | 88 | 2022-03-11 | 12 | [15 empty] | 2022-03-11 | 2022-03-11 | 0 | 2022-03-11 | [6 empty] | 2021-10-15 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2137 | PGE | 93405 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-10-15 | 2021-10-26 | 7 | 2021-11-10 | 18 | 2021-11-16 | 3 | [15 empty] | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26 | 2022-01-07 | 50 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-26 |  | 2022-01-07 | 54 | 1//19
2138 | PGE | 94062 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 41.289 |  | 2021-10-18 | 2021-10-18 | 0 | 2021-11-05 | 14 | 2021-11-07 | 0 | [18 empty] | 2021-10-18 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2139 | PGE | 95242 | NEM | EXPNEM | Study in Progress | Solar PV | 125 |  | 2021-10-18 | 2021-10-27 | 7 | 2021-11-12 | 18 | 2021-12-01 | 11 | 2021-12-01 | 2021-12-27 | 18 | 2021-12-27 | 2022-01-19 | 16 | 2022-01-19 | [18 empty] | 2021-10-18 | 2021-12-06 | 32 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2140 | PGE | 95020 | NEM | EXPNEM | Implementation | Solar PV | 473.704 |  | 2021-10-18 | 2021-10-28 | 8 | 2021-10-28 | 8 | 2021-11-12 | 10 | [15 empty] | 2021-11-12 | 2021-11-12 | 0 | 2021-11-12 | 2021-11-12 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2141 | PGE | 93446 | NEM | EXPNEM | Commercial | Solar PV | 31.88 |  | 2021-10-18 | 2021-11-01 | 10 | 2021-12-01 | 29 | 2021-12-15 | 10 | [15 empty] | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 2021-12-21 | 4 | [5 empty] | 0 | [5 empty] | 2022-01-21 | 2022-02-02 | 8 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-21 | 2022-01-24 | 1 | 2022-02-02 |  | 2022-02-02 | 0 | 1//19
2142 | PGE | 95236 | NEM | EXPNEM | Implementation | Solar PV | 40.388 |  | 2021-10-18 | 2021-10-21 | 3 | 2021-10-21 | 3 | 2021-11-24 | 23 | [15 empty] | 2021-11-24 | 2021-11-29 | 1 | 2021-11-29 | 2022-03-02 | 65 |  |  |  |  | 2021-10-18 | 2021-11-02 | 11 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2143 | PGE | 94080 | Non-NEM | Inadvertent Export | Withdrawn | Solar PV | 215.378 |  | 2021-10-18 | 2021-10-18 | 0 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2144 | PGE | 95991 | NEM | EXPNEM | Implementation | Solar PV | 133.2 |  | 2021-10-18 | 2021-10-20 | 2 | 2021-11-04 | 13 | 2021-11-16 | 7 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2022-02-16 | 63 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2145 | PGE | 96007 | NEM | EXPNEM | Commercial | Solar PV | 32.436 |  | 2021-10-18 | 2021-10-21 | 3 | 2021-10-29 | 9 | 2021-11-12 | 9 | [15 empty] | 2021-11-12 | 2021-11-12 | 0 | 2021-11-12 | 2021-11-12 | 0 | [5 empty] | 0 | [5 empty] | 2021-11-15 | 2021-12-06 | 13 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-15 | 2021-12-02 | 11 | 2021-12-06 |  | 2021-12-06 | 0 | 1//19
2146 | PGE | 94590 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 37.598 |  | 2021-10-18 | 2021-10-19 | 1 | 2021-12-31 | 51 | 2022-01-20 | 13 | [15 empty] | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | [6 empty] | 2021-10-18 | 2021-12-14 | 38 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2147 | PGE | 94112 | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 |  | 2021-10-18 | 2021-10-27 | 7 | 2021-12-23 | 45 | 2022-01-11 | 13 | [15 empty] | 2022-01-11 | 2022-01-11 | 0 | 2022-01-11 | 2022-01-18 | 4 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2148 | PGE | 94587 | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2021-10-18 | 2021-10-19 | 1 | 2021-10-19 | 1 | 2021-10-22 | 3 | [15 empty] | 2021-10-22 | 2021-10-27 | 3 | 2021-10-27 | 2021-10-29 | 2 | [5 empty] | 0 | [5 empty] | 2022-03-17 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-17 | 2022-03-22 | 3 |  |  |  |  | 1//19
2149 | PGE | 94061 | NEM | EXPNEM | Study in Progress | Solar PV | 33.3 |  | 2021-10-19 | 2021-11-02 | 10 | 2021-11-02 | 10 | 2021-11-19 | 12 | 2021-11-19 | 2021-12-20 | 19 | 2021-12-20 | 2022-01-19 | 21 | 2022-01-19 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2150 | PGE | 95205 | NEM | EXPNEM | Study in Progress | Solar PV | 133.2 |  | 2021-10-19 | 2021-11-02 | 10 | 2022-03-14 | 99 | 2022-03-28 | 10 | 2022-03-28 | [24 empty] | 2021-10-19 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2151 | PGE | 95205 | NEM | EXPNEM | Application Review in Progress | Solar PV | 133.2 |  | 2021-10-19 | 2021-11-02 | 10 | [29 empty] | 2021-10-19 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2152 | PGE | 94536 | NEM | EXPNEM | Commercial | Solar PV | 106.314 |  | 2021-10-19 | 2021-10-22 | 3 | 2021-10-29 | 8 | 2021-12-15 | 30 | [15 empty] | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 2021-12-29 | 10 | [5 empty] | 0 | [5 empty] | 2022-01-10 | 2022-01-19 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-10 | 2022-01-10 | 0 | 2022-01-19 |  | 2022-01-19 | 0 | 1//19
2153 | PGE | 95987 | NEM | EXPNEM | Application Accepted | Solar PV | 1486.251 |  | 2021-10-19 | 2021-10-25 | 4 | 2021-11-03 | 11 | [27 empty] | 2021-10-19 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2154 | PGE | 94062 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 46.105 |  | 2021-10-19 | 2021-10-21 | 2 | [22 empty] | 2021-10-19 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2155 | PGE | 95301 | Non-NEM | RESBCT | Study in Progress | Solar PV | 782.366 |  | 2021-10-19 | 2021-10-19 | 0 | 2021-11-17 | 20 | 2021-12-16 | 19 | 2022-01-06 | 2022-02-15 | 27 | [23 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2156 | PGE | 93635 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 75.974 |  | 2021-10-19 | 2021-10-21 | 2 | 2021-11-05 | 13 | 2021-11-29 | 13 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | [6 empty] | 2021-10-19 | 2021-12-03 | 30 |  | 2021-12-03 | 2021-12-03 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2157 | PGE | 93635 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 75.974 |  | 2021-10-19 | 2021-10-21 | 2 | 2021-11-05 | 13 | 2021-11-30 | 14 | [15 empty] | 2021-11-30 | 2021-11-30 | 0 | 2021-11-30 | [6 empty] | 2021-10-19 | 2021-12-15 | 38 |  | 2021-12-22 | 2021-12-22 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2158 | PGE | 93245 | NEM | EXPNEM | Implementation | Solar PV | 50 |  | 2021-10-19 | 2021-10-21 | 2 | 2021-10-21 | 2 | 2021-11-04 | 10 | [15 empty] | 2021-11-04 | 2021-11-29 | 14 | 2021-11-29 | 2022-01-14 | 34 |  |  |  |  | 2021-10-19 | 0 |  | 2021-11-01 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2159 | PGE | 93405 | Non-NEM | Inadvertent Export | Withdrawn | Storage | 10 |  | 2021-10-20 | 0 |  | 2021-12-16 | 38 | 2021-12-27 | 7 | [15 empty] | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27 | 2021-12-27 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2160 | PGE | 94597 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 40.163 |  | 2021-10-20 | 2021-10-21 | 1 | 2021-11-30 | 26 | 2021-12-02 | 2 | [18 empty] | 2021-10-20 | [7 empty] | 0 | [5 empty] | 2021-12-02 | 2021-12-02 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-02 |  |  | 2021-12-02 |  | 2021-12-02 | 0 | 1//19
2161 | PGE | 94062 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 40 |  | 2021-10-20 | 2021-10-26 | 4 | 2022-03-28 | 108 | 2022-03-30 | 2 | [18 empty] | 2021-10-20 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2162 | PGE | 95134 | Non-NEM | NEMFC | Implementation | FUCE | 200 |  | 2021-10-20 | 2021-11-02 | 9 | 2021-11-16 | 18 | 2021-12-09 | 15 | [15 empty] | 2021-12-09 | 2021-12-09 | 0 | 2021-12-09 | 2022-03-10 | 63 |  |  |  |  | 2021-11-16 | 2021-11-16 | 0 |  | 2021-12-14 | 2021-12-14 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2163 | PGE | 94404 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-10-20 | 2021-10-27 | 5 | 2021-12-09 | 33 | 2022-02-15 | 47 | [15 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2164 | PGE | 94538 | NEM | VNEM | IA in Progress | Solar PV | 33.075 |  | 2021-10-20 | 2021-11-03 | 10 | 2021-11-15 | 17 | 2021-12-08 | 15 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | [6 empty] | 2021-10-20 | 0 |  |  | 2022-03-12 | 2022-03-12 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2165 | PGE | 93648 | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-10-20 | 2021-10-21 | 1 | 2022-03-01 | 89 | 2022-03-14 | 9 | [15 empty] | 2022-03-14 | 2022-03-14 | 0 | 2022-03-14 | [6 empty] | 2021-10-20 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2166 | PGE | 94538 | NEM | VNEM | Implementation | Solar PV | 30.24 |  | 2021-10-20 | 2021-10-25 | 3 | 2021-10-27 | 5 | 2021-11-16 | 13 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2022-01-12 | 39 |  |  |  |  | 2021-10-20 | 2021-12-16 | 38 |  | 2021-12-20 | 2021-12-20 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2167 | PGE | 95935 | NEM | EXPNEM | Commercial | Solar PV | 33.909 |  | 2021-10-20 | 2021-11-02 | 9 | 2021-11-08 | 13 | 2021-11-16 | 5 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-18 | 2 | [5 empty] | 0 | [5 empty] | 2021-11-24 | 2021-12-01 | 3 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-24 | 2021-11-29 | 1 | 2021-12-01 |  | 2021-12-02 | 1 | 1//19
2168 | PGE | 93420 | NEM | EXPNEM | Implementation | Solar PV | 56.041 |  | 2021-10-21 | 2021-10-22 | 1 | 2021-10-25 | 2 | 2021-11-23 | 20 | [15 empty] | 2021-11-23 | 2021-11-23 | 0 | 2021-11-23 | 2021-11-30 | 3 | [5 empty] | 0 | [8 empty] | 2021-12-21 |  | 80 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2169 | PGE | 93263 | NEM | EXPNEM | IA in Progress | Solar PV | 550 |  | 2021-10-21 | 2021-10-28 | 5 | 2021-10-28 | 5 | 2021-11-29 | 19 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2170 | PGE | 93720 | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-10-21 | 2021-10-22 | 1 | 2021-10-22 | 1 | 2021-10-28 | 4 | [15 empty] | 2021-10-28 | 2021-11-17 | 13 | 2021-11-17 | [6 empty] | 2021-10-21 | 0 |  | 2021-11-01 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2171 | PGE | 93446 | NEM | EXPNEM | Study in Progress | Solar PV | 533.3 |  | 2021-10-21 | 2021-10-22 | 1 | 2022-01-19 | 60 | 2022-02-01 | 9 | 2022-02-01 | 2022-03-09 | 25 | 2022-03-11 | [22 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2172 | PGE | 93212 | NEM | EXPNEM | Study in Progress | Solar PV | 2000 |  | 2021-10-21 | 2021-10-22 | 1 | 2021-11-03 | 9 | [5 empty] | 2022-02-01 | 2022-02-24 | 16 | 2022-02-24 |  |  | 2022-03-30 |  |  | 2022-02-24 | 2022-03-28 | 1 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2173 | PGE | 93727 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 1488 |  | 2021-10-21 | 2021-10-27 | 4 | 2021-12-15 | 36 | [5 empty] | 2022-02-02 | 2022-03-03 | 20 | 2022-03-03 | 2022-03-08 | 3 |  |  |  | 2022-03-08 | 2022-03-25 | 13 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2174 | PGE | 95236 | NEM | EXPNEM | Study in Progress | Solar PV | 38.995 |  | 2021-10-21 | 2021-10-29 | 6 | 2021-11-23 | 22 | 2021-12-10 | 11 | 2021-12-10 | 2022-01-12 | 23 | 2022-01-12 | 2022-02-09 | 19 | 2022-02-09 | [18 empty] | 2021-10-21 | 2021-12-15 | 36 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2175 | PGE | 93638 | NEM | EXPNEM | IA in Progress | Solar PV | 39.976 |  | 2021-10-21 | 2021-11-04 | 10 | 2022-02-08 | 74 | 2022-03-02 | 15 | [15 empty] | 2022-03-02 | 2022-03-02 | 0 | 2022-03-02 | [6 empty] | 2021-10-21 | 2021-12-03 | 28 | 2021-11-19 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2176 | PGE | 94549 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-10-28 | 2021-10-28 | 0 | 2021-10-28 | 0 | 2021-11-18 | 14 | [15 empty] | 2021-11-18 | 2021-11-18 | 0 | 2021-11-18 | 2021-11-18 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-10-28 |  | 2021-11-18 | 16 | 1//19
2177 | PGE | 95472 | NEM | EXPNEM | Implementation | Solar PV | 62.541 |  | 2021-10-22 | 2021-11-02 | 7 | 2021-11-05 | 10 | 2021-11-29 | 13 | 2021-11-29 | 2021-12-27 | 20 | 2021-12-27 | 2022-01-12 | 12 | 2022-01-12 | 2022-01-12 |  | 2022-01-12 | 2022-02-17 | 27 | 2022-01-12 |  |  | 2022-02-17 | 2022-02-17 | 0 | 2022-02-17 | 2022-03-17 | 19 |  |  |  |  | 2021-10-22 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2178 | PGE | 95969 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 490 |  | 2021-10-22 | 2021-10-22 | 0 | 2021-11-10 | 13 | 2021-12-20 | 25 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | [6 empty] | 2021-10-22 | 2021-12-07 | 29 | [7 empty] | 2022-03-30 | 2022-04-01 | 2 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2179 | PGE | 95320 | NEM | EXPNEM | Implementation | Solar PV | 359.986 |  | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | 0 | 2021-11-30 | 24 | [15 empty] | 2021-11-30 | 2021-11-30 | 0 | 2021-11-30 | 2021-12-14 | 10 |  |  |  |  | 2021-10-22 | 2021-11-03 | 8 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2180 | PGE | 95954 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 490 |  | 2021-10-22 | 2021-10-22 | 0 | 2021-11-10 | 13 | 2021-12-20 | 25 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | [6 empty] | 2021-10-22 | 2021-12-07 | 29 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2181 | PGE | 95472 | NEM | EXPNEM | Study in Progress | Solar PV | 93.654 |  | 2021-10-22 | 2021-11-05 | 10 | 2021-11-30 | 24 | 2021-12-21 | 15 | 2021-12-21 | 2022-01-19 | 20 | 2022-01-19 | 2022-02-16 | 20 | 2022-02-16 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2182 | PGE | 95304 | NEM | EXPNEM | Study in Progress | Solar PV | 720 |  | 2021-10-22 | 2021-11-01 | 6 | 2021-11-05 | 10 | 2021-12-01 | 15 | 2021-12-01 | 2022-01-07 | 27 | 2022-01-07 | 2022-02-01 | 16 | 2022-02-01 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2183 | PGE | 94561 | NEM | EXPNEM | Implementation | Solar PV | 31.966 |  | 2021-10-22 | 2021-10-28 | 4 | 2021-10-28 | 4 | 2021-11-15 | 11 | [15 empty] | 2021-11-12 | 2021-11-12 | 0 | 2021-11-12 | 2021-11-15 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2184 | PGE | 95403 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.6 |  | 2021-10-22 | 2021-10-28 | 4 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2185 | PGE | 94550 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 38.394 |  | 2021-10-24 | 2021-10-25 | 0 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2186 | PGE | 95605 | NEM | EXPNEM | Application Review in Progress | Solar PV | 273.552 |  | 2021-10-24 | 2021-11-01 | 5 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2187 | PGE | 94941 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-10-25 | 2021-11-30 | 23 | 2021-12-02 | 25 | 2021-12-16 | 10 | [18 empty] | 2021-10-25 | 2021-10-25 | 0 | [5 empty] | 0 | [5 empty] | 2021-12-16 | 2021-12-17 | 1 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-16 | 2021-12-17 | 1 | 2021-12-17 |  | 2021-12-20 | 1 | 1//19
2188 | PGE | 95032 | NEM | EXPNEM | Commercial | Solar PV | 31.074 |  | 2021-10-25 | 2021-11-03 | 7 | 2021-11-12 | 13 | 2021-11-30 | 10 | [15 empty] | 2021-11-30 | 2021-11-30 | 0 | 2021-11-30 | 2021-12-01 | 1 | [5 empty] | 0 | [5 empty] | 2021-12-01 | 2021-12-23 | 16 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-01 | 2021-12-03 | 2 | 2021-12-23 |  | 2021-12-24 | 1 | 1//19
2189 | PGE | 96080 | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-10-25 | 2021-11-15 | 14 | 2021-12-07 | 28 | 2021-12-28 | 15 | [15 empty] | 2021-12-28 | 2021-12-29 | 1 | 2021-12-29 | 2022-01-26 | 19 |  |  |  |  | 2021-10-25 | 2021-12-16 | 35 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2190 | PGE | 95691 | NEM | VNEM | Implementation | Solar PV | 100.395 |  | 2021-10-25 | 2021-10-27 | 2 | 2021-11-01 | 5 | 2021-11-19 | 13 | [15 empty] | 2021-11-19 | 2021-11-19 | 0 | 2021-11-19 | 2022-01-14 | 38 |  |  |  |  | 2021-11-16 | 2021-11-29 | 7 |  | 2021-11-19 | 2021-11-19 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2191 | PGE | 94568 | NEM | EXPNEM | Implementation | Solar PV | 99.9 |  | 2021-10-25 | 2021-10-27 | 2 | 2021-10-27 | 2 | 2021-12-13 | 30 | [15 empty] | 2021-12-13 | 2021-12-24 | 9 | 2021-12-24 | 2021-12-24 | 0 |  |  |  |  | 2021-10-25 | 0 |  | 2021-11-01 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2192 | PGE | 95619 | Non-NEM | Break Before Make | Commercial | ENGN | 200 |  | 2021-10-26 | 2021-11-09 | 10 | 2021-12-21 | 37 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2193 | PGE | 96003 | NEM | EXPNEM | Commercial | Solar PV | 33.174 |  | 2021-10-26 | 2021-11-03 | 6 | 2021-11-03 | 6 | 2021-11-19 | 11 | [15 empty] | 2021-11-19 | 2021-11-29 | 4 | 2021-11-29 | 2021-11-30 | 1 |  |  |  |  | 2021-10-26 | 2021-11-29 | 21 |  |  |  |  | 2021-11-30 | 2021-12-07 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-30 | 2021-12-01 | 1 | 2021-12-07 |  | 2021-12-08 | 1 | 1//19
2194 | PGE | 93635 | NEM | EXPNEM | Withdrawn | Solar PV | 86 |  | 2021-10-26 | 2021-11-02 | 5 | 2021-11-02 | 5 | 2021-11-19 | 12 | [15 empty] | 2021-11-19 | 2021-12-14 | 15 | 2021-12-14 | 2022-02-23 | 49 |  |  |  |  | 2021-10-26 | 0 |  | 2021-12-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2195 | PGE | 95138 | NEM | EXPNEM | Implementation | Solar PV | 485.259 |  | 2021-10-26 | 2021-10-27 | 1 | 2021-10-27 | 1 | 2021-11-22 | 17 | [15 empty] | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22 | 2022-02-28 | 66 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2196 | PGE | 95138 | NEM | EXPNEM | IA in Progress | Solar PV | 139.03 |  | 2021-10-26 | 2021-11-03 | 6 | 2021-11-03 | 6 | 2022-01-18 | 50 | 2022-01-18 | 2022-03-14 | 38 | [12 empty] | 2022-03-14 | 2022-03-14 | 0 | 2022-03-14 | 2022-03-30 | 12 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2197 | PGE | 95667 | Non-NEM | Break Before Make | Commercial | ENGN | 150 |  | 2021-10-26 | 2021-11-09 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2198 | PGE | 95138 | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2021-10-26 | 2021-11-01 | 4 | 2021-11-04 | 7 | 2021-11-19 | 10 | 2021-11-19 | 2021-12-24 | 23 | [12 empty] | 2021-12-24 | 2021-12-28 | 2 | 2021-12-28 | 2022-01-25 | 19 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2199 | PGE | 94538 | NEM | EXPNEM | Implementation | Solar PV | 162.5 |  | 2021-10-26 | 2021-11-03 | 6 | 2022-01-03 | 46 | 2022-01-07 | 4 | [15 empty] | 2022-01-07 | 2022-01-07 | 0 | 2022-01-07 | 2022-01-27 | 13 |  |  |  |  | 2021-10-26 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2200 | PGE | 94538 | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-10-26 | 2021-11-04 | 7 | 2021-11-04 | 7 | 2021-12-31 | 38 | [15 empty] | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | 2022-01-26 | 17 |  |  |  |  | 2021-10-26 | 2021-12-09 | 29 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2201 | PGE | 94066 | NEM | EXPNEM | Implementation | Solar PV | 81.005 |  | 2021-10-26 | 2021-11-03 | 6 | 2021-12-02 | 24 | 2021-12-16 | 10 | [15 empty] | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16 | 2022-01-24 | 26 |  |  |  |  | 2021-10-26 | 2021-11-30 | 22 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2202 | PGE | 93263 | NEM | EXPNEM | Implementation | Solar PV | 95.8 |  | 2021-10-26 | 2021-11-03 | 6 | 2021-11-03 | 6 | 2021-11-19 | 11 | [15 empty] | 2021-11-19 | 2021-11-24 | 3 | 2021-11-24 | 2022-02-09 | 52 |  |  |  |  | 2021-10-26 | 2021-11-29 | 21 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2203 | PGE | 95304 | NEM | EXPNEM | Implementation | Solar PV | 96.096 |  | 2021-10-26 | 2021-11-05 | 8 | 2021-11-05 | 8 | 2021-11-22 | 10 | [15 empty] | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22 | 2021-11-29 | 3 |  |  |  |  | 2021-10-26 | 2021-11-29 | 21 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2204 | PGE | 95304 | NEM | EXPNEM | Implementation | Solar PV | 62.5 |  | 2021-10-26 | 2021-11-05 | 8 | 2021-11-05 | 8 | 2021-11-22 | 10 | [15 empty] | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22 | 2021-11-29 | 3 |  |  |  |  | 2021-10-26 | 2021-11-29 | 21 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2205 | PGE | 95436 | NEM | EXPNEM | Study in Progress | Solar PV | 49.549 |  | 2021-10-26 | 2021-11-03 | 6 | 2021-11-29 | 21 | 2021-12-15 | 12 | 2021-12-15 | 2022-01-10 | 18 | 2022-01-10 | 2022-02-08 | 20 | 2022-02-08 | [18 empty] | 2021-10-26 | 2021-12-15 | 33 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2206 | PGE | 95451 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 41.387 |  | 2021-10-26 | 2021-10-29 | 3 | 2021-10-29 | 3 | 2021-11-03 | 3 | [18 empty] | 2021-10-26 | [7 empty] | 0 | [8 empty] | 2021-12-29 |  | 75 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2207 | PGE | 93727 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 3218 |  | 2021-10-26 | 2021-10-27 | 1 | 2021-12-15 | 33 | [28 empty] | 0 | [8 empty] | 2022-02-14 |  | 42 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2208 | PGE | 95472 | NEM | EXPNEM | Implementation | Solar PV | 161.008 |  | 2021-10-26 | 2021-11-03 | 6 | 2021-11-04 | 7 | 2022-01-13 | 47 | [15 empty] | 2022-01-13 | 2022-01-13 | 0 | 2022-01-13 | 2022-03-07 | 35 |  |  |  |  | 2021-10-26 | 2021-12-01 | 23 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2209 | PGE | 93640 | NEM | EXPNEM | Application Accepted | Solar PV | 907.612 |  | 2021-10-26 | 2021-11-05 | 8 | 2021-12-27 | 41 | [27 empty] | 2021-10-26 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2210 | PGE | 94062 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 33.012 |  | 2021-10-26 | 2021-11-05 | 8 | 2021-11-12 | 12 | 2022-01-21 | 47 | [15 empty] | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05 | 2021-11-12 | 4 |  |  |  |  | 2021-10-26 | 2021-11-29 | 21 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2211 | PGE | 94706 | NEM | EXPNEM | IA in Progress | Solar PV | 100.425 |  | 2021-10-27 | 2021-11-08 | 8 | 2021-11-12 | 11 | 2021-11-17 | 3 | [15 empty] | 2021-11-17 | 2021-11-17 | 0 | 2021-11-17 | [6 empty] | 2021-10-27 | 2021-12-06 | 25 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2212 | PGE | 94526 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.375 |  | 2021-10-27 | 2021-10-29 | 2 | 2021-10-29 | 2 | 2021-11-02 | 2 | [18 empty] | 2021-10-27 | [7 empty] | 0 | [5 empty] | 2021-11-23 | 2021-11-23 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-23 |  |  | 2021-11-23 |  | 2021-11-23 | 0 | 1//19
2213 | PGE | 94566 | NEM | EXPNEM | Withdrawn | Solar PV | 495.7 |  | 2021-10-27 | 2021-11-05 | 7 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2214 | PGE | 95912 | NEM | EXPNEM | Withdrawn | Solar PV | 60.708 |  | 2021-10-27 | 2021-10-29 | 2 | 2021-12-17 | 34 | 2022-01-05 | 13 | 2022-01-05 | [25 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2215 | PGE | 94560 | NEM | EXPNEM | Implementation | Solar PV | 987.5 |  | 2021-10-27 | 2021-10-29 | 2 | 2021-11-10 | 10 | 2021-12-20 | 25 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | 2022-01-10 | 15 |  |  |  |  | 2021-10-27 | 2021-12-02 | 23 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2216 | PGE | 93638 | NEM | VNEM | Withdrawn | Solar PV | 61.78 |  | 2021-10-27 | 2021-11-10 | 10 | [22 empty] | 2021-10-27 | [6 empty] | 2021-10-27 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2217 | PGE | 94043 | NEM | EXPNEM | Implementation | Solar PV | 226.969 |  | 2021-10-27 | 2021-11-02 | 4 | 2021-11-02 | 4 | 2021-11-19 | 12 | [15 empty] | 2021-11-19 | 2021-11-30 | 5 | 2021-11-30 | 2022-02-16 | 55 |  |  |  |  | 2021-10-27 | 0 |  | 2021-12-14 |  |  |  | 2022-03-23 | 2022-03-31 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-23 | 2022-03-24 | 1 | 2022-03-31 | 2022-03-31 |  | 0 | 1//19 |  | 106
2218 | PGE | 93242 | NEM | EXPNEM | Implementation | Solar PV | 95.947 |  | 2021-10-27 | 2021-11-03 | 5 | 2021-12-13 | 30 | 2021-12-27 | 10 | [15 empty] | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27 | 2021-12-27 | 0 |  |  |  |  | 2021-10-27 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2219 | PGE | 95037 | NEM | EXPNEM | Implementation | Solar PV | 266.6 |  | 2021-10-27 | 2021-10-29 | 2 | 2021-11-08 | 8 | 2021-12-22 | 29 | [15 empty] | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22 | 2022-01-13 | 16 |  |  |  |  | 2021-11-08 | 2021-11-30 | 13 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2220 | PGE | 95361 | NEM | EXPNEM | Withdrawn | Solar PV | 96.475 |  | 2021-10-27 | 2021-10-29 | 2 | 2021-10-29 | 2 | 2021-11-18 | 13 | [15 empty] | 2021-12-07 | 2021-12-24 | 13 | 2021-12-24 | [6 empty] | 2021-10-27 | 0 |  | 2021-12-14 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2221 | PGE | 94801 | NEM | EXPNEM | Application Review in Progress | Solar PV | 800 |  | 2021-10-27 | 2021-11-04 | 6 | [29 empty] | 2021-10-27 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2222 | PGE | 95206 | NEM | EXPNEM | Commercial | Solar PV | 46.265 |  | 2021-10-27 | 2021-10-29 | 2 | 2021-10-29 | 2 | 2021-11-12 | 9 | [15 empty] | 2021-11-12 | 2021-11-15 | 1 | 2021-11-15 | 2021-12-30 | 31 |  |  |  |  | 2021-10-27 | 0 |  | 2021-12-14 |  |  |  | 2022-03-18 | 2022-03-29 | 7 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-18 | 2022-03-21 | 1 | 2022-03-29 |  | 2022-03-29 | 0 | 1//19
2223 | PGE | 93955 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 168.78 |  | 2021-10-28 | 2021-10-29 | 1 | 2021-11-17 | 13 | 2022-02-08 | 56 | [15 empty] | 2022-02-08 | 2022-02-08 | 0 | 2022-02-08 | [7 empty] | 0 |  |  | 2021-11-17 | 2021-11-17 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2224 | PGE | 94080 | NEM | EXPNEM | Commercial | Solar PV | 120.364 |  | 2021-10-28 | 2021-11-12 | 10 | 2021-12-07 | 25 | 2021-12-17 | 8 | [15 empty] | 2021-12-17 | 2021-12-17 | 0 | 2021-12-17 | 2022-01-07 | 15 | [5 empty] | 0 | [5 empty] | 2022-01-18 | 2022-01-26 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-18 | 2022-01-18 | 0 | 2022-01-26 |  | 2022-01-27 | 1 | 1//19
2225 | PGE | 95448 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.5 |  | 2021-10-28 | 2021-11-03 | 4 | 2021-11-17 | 13 | 2021-11-17 | 0 | [18 empty] | 2021-10-28 | [7 empty] | 0 | [5 empty] | 2021-11-17 | 2021-11-17 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-17 |  |  | 2021-11-17 |  | 2021-11-17 | 0 | 1//19
2226 | PGE | 93432 | NEM | EXPNEM | Implementation | Solar PV | 30.763 |  | 2021-10-28 | 2021-11-12 | 10 | 2021-11-12 | 10 | 2021-12-02 | 12 | [15 empty] | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02 | 2022-01-13 | 30 | [5 empty] | 0 | [5 empty] | 2022-01-13 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-13 | 2022-03-28 | 50 |  |  |  |  | 1//19
2227 | PGE | 93301 | NEM | EXPNEM | Commercial | Solar PV | 34.8 |  | 2021-10-28 | 2021-11-01 | 2 | 2021-12-13 | 29 | 2022-01-11 | 21 | [15 empty] | 2022-01-11 | 2022-01-11 | 0 | 2022-01-11 | 2022-01-12 | 1 | [5 empty] | 0 | [5 empty] | 2022-01-12 | 2022-03-03 | 34 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-12 | 2022-02-25 | 30 | 2022-03-03 |  | 2022-03-03 | 0 | 1//19
2228 | PGE | 93239 | Non-NEM | Inadvertent Export | Withdrawn | Solar PV | 33 |  | 2021-10-28 | 2021-10-29 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2229 | PGE | 94027 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 36.168 |  | 2021-10-28 | 2021-11-01 | 2 | 2021-11-04 | 5 | 2021-11-05 | 1 | [18 empty] | 2021-10-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2230 | PGE | 95521 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 15 |  | 2021-10-28 | 2021-11-12 | 10 | 2021-11-19 | 15 | 2021-11-29 | 4 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2022-03-02 | 65 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2231 | PGE | 93908 | NEM | EXPNEM | Implementation | Solar PV | 410.518 |  | 2021-10-29 | 2021-11-05 | 5 | 2021-11-09 | 7 | 2021-12-30 | 34 | [15 empty] | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-02-10 | 29 |  |  |  |  | 2021-10-29 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2232 | PGE | 95205 | NEM | EXPNEM | Study in Progress | Solar PV | 780 |  | 2021-10-29 | 2021-11-02 | 2 | 2021-11-02 | 2 | 2021-11-18 | 11 | 2022-02-07 | 2022-03-07 | 19 | 2022-03-09 | [21 empty] | 2021-10-29 | 0 |  | 2021-12-01 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2233 | PGE | 95627 | NEM | EXPNEM | Study in Progress | Solar PV | 180 |  | 2021-10-29 | 2021-11-15 | 10 | 2021-12-07 | 24 | 2021-12-28 | 15 | 2021-12-28 | 2022-01-26 | 20 | 2022-01-26 | 2022-02-24 | 20 | 2022-02-24 | [18 empty] | 2021-10-29 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2234 | PGE | 94801 | NEM | VNEMSOMAH | Implementation | Solar PV | 100 |  | 2021-10-29 | 2021-11-04 | 4 | 2021-11-29 | 18 | 2021-12-16 | 13 | [15 empty] | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16 | 2021-12-22 | 4 | [5 empty] | 0 |  | 2022-01-07 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2235 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100.91 |  | 2021-10-29 | 2021-11-15 | 10 | 2021-11-29 | 18 | 2021-12-20 | 15 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | [6 empty] | 2021-10-29 | 2021-12-15 | 30 |  | 2021-12-20 | 2021-12-20 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2236 | PGE | 95337 | NEM | EXPNEM | Study in Progress | Solar PV | 600 |  | 2021-10-29 | 2021-11-01 | 1 | 2021-11-01 | 1 | 2021-12-23 | 35 | 2022-01-04 | 2022-01-31 | 18 | 2022-01-31 | 2022-02-22 | 15 | 2022-02-22 | [18 empty] | 2022-01-05 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2237 | PGE | 95361 | NEM | EXPNEM | Study in Progress | ENGN, Solar PV | 875 |  | 2021-10-29 | 2021-11-15 | 10 | 2022-03-28 | 101 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2238 | PGE | 95337 | NEM | EXPNEM | Study in Progress | Solar PV | 698.573 |  | 2021-10-29 | 2021-11-15 | 10 | 2022-01-14 | 52 | 2022-02-08 | 16 | 2022-02-08 | 2022-03-07 | 18 | 2022-03-07 | 2022-03-28 | 15 | 2022-03-28 | [18 empty] | 2022-01-14 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2239 | PGE | 93662 | NEM | EXPNEM | IA in Progress | Solar PV | 354.723 |  | 2021-10-29 | 2021-11-10 | 8 | 2021-11-29 | 18 | 2021-12-27 | 20 | [15 empty] | 2021-12-27 | 2021-12-28 | 1 | 2021-12-28 | [6 empty] | 2021-10-29 | 2021-11-29 | 18 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2240 | PGE | 94062 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 48.625 |  | 2021-10-29 | 2021-11-03 | 3 | 2021-12-13 | 28 | 2021-12-15 | 2 | [18 empty] | 2021-10-29 | [7 empty] | 0 | [5 empty] | 2021-12-15 | 2021-12-15 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-15 |  |  | 2021-12-15 |  | 2021-12-15 | 0 | 1//19
2241 | PGE | 94030 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.423 |  | 2021-11-01 | 2021-11-05 | 4 | [22 empty] | 2021-11-01 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2243 | PGE | 95422 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 357.5 |  | 2021-11-08 | 2021-11-22 | 9 | 2021-12-24 | 31 | 2022-01-11 | 12 | [15 empty] | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22 | 2022-01-12 | 35 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2244 | PGE | 93923 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-11-01 | 2021-11-04 | 3 | 2021-11-04 | 3 | [17 empty] | 2021-11-04 | 2021-11-04 | 0 | 2021-11-04 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2245 | PGE | 93230 | NEM | EXPNEM | Implementation | Solar PV | 299.834 |  | 2021-11-01 | 2021-11-12 | 8 | 2021-11-16 | 10 | 2021-12-02 | 10 | [15 empty] | 2021-12-02 | 2021-12-06 | 2 | 2021-12-06 | 2022-01-11 | 26 |  |  |  |  | 2021-11-01 | 0 | [8 empty] | 2022-03-04 |  | 28 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2246 | PGE | 94538 | NEM | NEMMT | Application Review in Progress | ENGN, Solar PV | 851.568 |  | 2021-11-01 | 2021-11-16 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2247 | PGE | 93204 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 730 |  | 2021-11-01 | 2021-11-02 | 1 | 2022-02-07 | 66 | 2022-02-28 | 14 | [15 empty] | 2022-02-28 | 2022-02-28 | 0 | 2022-02-28 | [6 empty] | 2022-02-04 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2248 | PGE | 93711 | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 |  | 2021-11-01 | 2021-11-08 | 5 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2249 | PGE | 93420 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-11-02 | 2021-11-02 | 0 | 2021-11-03 | 1 | 2021-11-09 | 4 | [18 empty] | 2021-11-02 | 2021-11-02 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2250 | PGE | 94520 | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 |  | 2021-11-02 | 2021-11-05 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2251 | PGE | 94585 | NEM | EXPNEM | IA in Progress | Solar PV | 44.98 |  | 2021-11-02 | 2021-11-08 | 4 | 2021-12-24 | 35 | 2022-01-12 | 13 | [15 empty] | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2252 | PGE | 94611 | Non-NEM | Non-Export | IA in Progress | ENGN, Solar PV | 4.85 |  | 2021-11-02 | 2021-11-15 | 8 | 2021-11-15 | 8 | 2022-01-25 | 48 | [15 empty] | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2253 | PGE | 93610 | NEM | EXPNEM | Study in Progress | Solar PV | 840 |  | 2021-11-02 | 2021-11-17 | 10 | 2021-11-17 | 10 | 2021-12-29 | 28 | 2021-12-29 | 2022-01-27 | 20 | 2022-01-27 | 2022-02-17 | 15 | 2022-02-17 | [18 empty] | 2021-12-01 | 2021-12-15 | 10 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2254 | PGE | 95340 | NEM | EXPNEM | Study in Progress | Solar PV | 456 |  | 2021-11-02 | 2021-11-12 | 7 | 2021-11-23 | 14 | 2021-12-08 | 9 | 2021-12-08 | 2022-01-03 | 18 | 2022-01-04 | 2022-01-27 | 16 | 2022-01-27 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2255 | PGE | 93726 | NEM | EXPNEM | Implementation | Solar PV | 75 |  | 2021-11-02 | 2021-11-04 | 2 | 2022-02-01 | 61 | 2022-02-03 | 2 | [15 empty] | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | 2022-03-29 | 37 |  |  |  |  | 2021-11-02 | 2021-12-15 | 28 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2256 | PGE | 94621 | NEM | EXPNEM | Commercial | Solar PV | 86.881 |  | 2021-11-02 | 2021-11-03 | 1 | 2021-11-10 | 6 | 2021-11-16 | 3 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2022-01-13 | 40 | [5 empty] | 0 | [5 empty] | 2022-01-13 | 2022-01-25 | 7 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-13 | 2022-01-14 | 1 | 2022-01-25 |  | 2022-01-26 | 1 | 1//19
2257 | PGE | 94551 | NEM | EXPNEM | IA in Progress | Solar PV | 41.502 |  | 2021-11-02 | 2021-11-04 | 2 | 2022-01-26 | 57 | 2022-02-11 | 12 | [15 empty] | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2258 | PGE | 93610 | NEM | EXPNEM | Study in Progress | Solar PV | 840 |  | 2021-11-02 | 2021-11-15 | 8 | 2021-12-13 | 26 | 2022-01-03 | 15 | 2022-01-03 | 2022-01-27 | 17 | 2022-01-27 | 2022-02-24 | 19 | 2022-02-24 | 2022-02-24 | 0 |  |  |  | 2022-02-24 | [13 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2259 | PGE | 95682 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-10-15 | 2021-11-02 | 12 | 2021-11-02 | 12 | 2021-11-08 | 4 | [18 empty] | 2021-10-15 | 2021-10-15 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-11-02 |  | 2021-12-13 | 30 | 1//19
2260 | PGE | 95901 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 260 |  | 2021-11-02 | 2021-11-17 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2261 | PGE | 93420 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-02 | 2021-11-18 | 11 | 2021-11-23 | 14 | 2021-12-13 | 12 | [18 empty] | 2021-11-02 | 2021-11-02 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2262 | PGE | 94539 | NEM | EXPNEM | Implementation | Solar PV | 205.581 |  | 2021-11-02 | 2021-11-04 | 2 | 2021-11-09 | 5 | 2021-11-24 | 10 | [15 empty] | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 2022-01-11 | 32 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2263 | PGE | 93422 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-11-02 | 2021-11-17 | 10 | 2021-12-02 | 19 | 2021-12-21 | 13 | [18 empty] | 2021-11-02 | 2021-12-02 | 19 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2264 | PGE | 95681 | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 |  | 2021-11-02 | 2021-11-04 | 2 | 2021-11-04 | 2 | 2021-11-18 | 9 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 2022-01-14 | 12 | [5 empty] | 0 | [8 empty] | 2022-02-15 |  | 41 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2265 | PGE | 95338 | NEM | EXPNEM | Implementation | Solar PV | 49.771 |  | 2021-11-02 | 2021-11-04 | 2 | 2021-11-04 | 2 | 2021-11-19 | 10 | [15 empty] | 2021-11-19 | 2021-11-30 | 5 | 2021-11-30 | 2021-12-06 | 4 |  |  |  |  | 2021-11-02 | 0 |  | 2021-11-30 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2266 | PGE | 93420 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-11-02 | 2021-11-17 | 10 | 2021-12-02 | 19 | 2021-12-20 | 12 | [18 empty] | 2021-11-02 | 2021-11-02 | 0 | [5 empty] | 0 | [5 empty] | 2021-12-20 | 2021-12-21 | 1 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-20 | 2021-12-21 | 1 | 2021-12-21 |  | 2021-12-23 | 2 | 1//19
2267 | PGE | 94565 | NEM | EXPNEM | Commercial | Solar PV | 52.163 |  | 2021-11-02 | 2021-11-04 | 2 | 2021-11-29 | 16 | 2021-12-28 | 21 | [15 empty] | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28 | 2022-01-11 | 10 | [5 empty] | 0 | [5 empty] | 2022-02-10 | 2022-03-15 | 22 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-10 | 2022-03-03 | 14 | 2022-03-15 |  | 2022-03-16 | 1 | 1//19
2268 | PGE | 95338 | NEM | EXPNEM | IA in Progress | Solar PV | 49.916 |  | 2021-11-02 | 2021-11-04 | 2 | 2021-11-04 | 2 | 2021-12-02 | 17 | [15 empty] | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02 | [6 empty] | 2021-11-02 | 2021-12-14 | 27 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2269 | PGE | 95110 | NEM | EXPNEM | Withdrawn | Solar PV | 33.983 |  | 2021-11-02 | 2021-11-04 | 2 | 2021-12-09 | 24 | 2021-12-28 | 13 | [15 empty] | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28 | 2022-01-11 | 10 | [5 empty] | 0 | [5 empty] | 2022-01-26 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-26 | 2022-01-26 | 0 |  |  |  |  | 1//19
2270 | PGE | 95338 | NEM | EXPNEM | IA in Progress | Solar PV | 119.778 |  | 2021-11-02 | 2021-11-04 | 2 | 2021-11-04 | 2 | 2021-12-21 | 30 | [15 empty] | 2021-12-21 | 2021-12-21 | 0 | 2021-12-21 | [6 empty] | 2021-11-02 | 2021-11-19 | 12 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2271 | PGE | 95762 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.204 |  | 2021-11-03 | 2021-11-05 | 2 | 2021-12-15 | 27 | 2021-12-16 | 1 | [18 empty] | 2021-11-03 | [7 empty] | 0 | [5 empty] | 2021-12-16 | 2021-12-16 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-16 |  |  | 2021-12-16 |  | 2021-12-16 | 0 | 1//19
2272 | PGE | 95018 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05 | 0 | 2021-11-19 | 9 | [15 empty] | 2021-11-19 | 2021-11-19 | 0 | 2021-11-19 | 2021-11-19 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-11-05 |  | 2021-11-19 | 11 | 1//19
2273 | PGE | 93722 | NEM | EXPNEM | IA in Progress | Solar PV | 724.754 |  | 2021-11-03 | 2021-11-17 | 9 | 2021-12-28 | 36 | 2022-01-14 | 13 | [15 empty] | 2022-01-14 | 2022-01-14 | 0 | 2022-01-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2274 | PGE | 94544 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-03 | 2021-11-18 | 10 | 2021-11-19 | 11 | 2021-12-02 | 7 | [18 empty] | 2021-11-03 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-11-18 |  | 2021-12-02 | 11 | 1//19
2275 | PGE | 95912 | NEM | EXPNEM | IA in Progress | Solar PV | 250.103 |  | 2021-11-03 | 2021-11-18 | 10 | 2021-11-18 | 10 | 2021-12-13 | 15 | [15 empty] | 2021-12-13 | 2021-12-29 | 12 | 2021-12-29 | [6 empty] | 2021-11-03 | 2021-12-15 | 27 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2276 | PGE | 93420 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-11-03 | 2021-11-04 | 1 | 2021-11-04 | 1 | 2021-11-10 | 4 | [18 empty] | 2021-11-03 | 2021-11-08 | 3 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2277 | PGE | 95066 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-03 | 2021-11-18 | 10 | 2021-11-23 | 13 | 2021-12-16 | 15 | [18 empty] | 2021-11-03 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-11-23 |  | 2021-12-16 | 18 | 1//19
2278 | PGE | 93422 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-11-03 | 2021-11-04 | 1 | 2021-11-08 | 3 | 2021-11-10 | 2 | [18 empty] | 2021-11-03 | 2021-11-08 | 3 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2279 | PGE | 94704 | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-11-03 | 2021-11-05 | 2 | 2021-12-07 | 21 | 2021-12-22 | 11 | [15 empty] | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22 | 2022-01-06 | 11 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2280 | PGE | 93636 | NEM | EXPNEM | Commercial | Solar PV | 30.33 |  | 2021-11-03 | 2021-11-08 | 3 | 2021-12-01 | 17 | 2021-12-10 | 7 | [15 empty] | 2021-12-10 | 2021-12-10 | 0 | 2021-12-10 | 2021-12-15 | 3 |  |  |  |  | 2021-11-04 | 2021-12-06 | 19 |  |  |  |  | 2022-01-14 | 2022-01-26 | 7 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-14 | 2022-01-14 | 0 | 2022-01-26 |  | 2022-01-26 | 0 | 1//19
2281 | PGE | 93280 | NEM | EXPNEM | Implementation | Solar PV | 840 |  | 2021-11-03 | 2021-11-18 | 10 | 2021-11-22 | 12 | 2021-12-02 | 6 | [15 empty] | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02 | 2021-12-03 | 1 | [5 empty] | 0 | [8 empty] | 2022-01-27 |  | 54 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2282 | PGE | 95912 | NEM | EXPNEM | IA in Progress | Solar PV | 250.103 |  | 2021-11-03 | 2021-11-10 | 5 | 2021-12-17 | 29 | 2022-01-05 | 13 | [15 empty] | 2022-01-05 | 2022-01-05 | 0 | 2022-01-05 | [6 empty] | 2021-11-03 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2283 | PGE | 95932 | NEM | EXPNEM | IA in Progress | Solar PV | 110.933 |  | 2021-11-03 | 2021-11-05 | 2 | 2021-12-27 | 35 | 2022-01-11 | 11 | [15 empty] | 2022-01-11 | 2022-01-11 | 0 | 2022-01-11 | [6 empty] | 2021-11-03 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2284 | PGE | 94577 | NEM | EXPNEM | Commercial | Solar PV | 37.913 |  | 2021-11-03 | 2021-11-04 | 1 | 2021-11-09 | 4 | 2021-11-29 | 11 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2022-01-12 | 32 | [5 empty] | 0 | [5 empty] | 2022-01-12 | 2022-01-25 | 8 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-12 | 2022-01-13 | 1 | 2022-01-25 |  | 2022-01-26 | 1 | 1//19
2285 | PGE | 94607 | NEM | EXPNEM | Implementation | Solar PV | 500 |  | 2021-11-03 | 2021-11-05 | 2 | 2021-11-09 | 4 | 2021-11-10 | 1 | [15 empty] | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | 2021-12-31 | 34 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2286 | PGE | 95361 | NEM | EXPNEM | Study in Progress | Solar PV | 160.303 |  | 2021-11-03 | 2021-11-15 | 7 | 2021-12-02 | 18 | 2021-12-30 | 20 | 2021-12-30 | 2022-01-28 | 20 | 2022-01-28 | 2022-02-23 | 17 | 2022-02-23 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2287 | PGE | 94558 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.35 |  | 2021-11-04 | 2021-11-09 | 3 | 2021-12-21 | 30 | 2021-12-28 | 5 | [18 empty] | 2021-11-04 | [7 empty] | 0 | [5 empty] | 2022-02-17 | 2022-03-01 | 7 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-17 | 2022-03-01 | 7 | 2022-03-01 |  | 2022-03-02 | 1 | 1//19
2288 | PGE | 94404 | NEM | EXPNEM | Implementation | Solar PV | 66.6 |  | 2021-11-04 | 2021-11-16 | 7 | 2021-11-29 | 14 | 2021-12-14 | 11 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2022-02-08 | 39 |  |  |  |  | 2021-11-04 | 2021-12-15 | 26 | 2021-12-15 | 2022-02-15 | 2022-02-15 | 43 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2289 | PGE | 93647 | NEM | EXPNEM | Withdrawn | Solar PV | 44.95 |  | 2021-11-04 | 0 | [30 empty] | 2021-11-04 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2290 | PGE | 93612 | NEM | EXPNEM | IA in Progress | Solar PV | 244.589 |  | 2021-11-04 | 2021-11-05 | 1 | 2021-11-08 | 2 | 2021-11-15 | 4 | [15 empty] | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | [6 empty] | 2021-11-04 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2291 | PGE | 94066 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 3799.4 |  | 2021-11-04 | 2021-11-04 | 0 | 2021-12-29 | 36 | [5 empty] | 2022-01-28 | 2022-02-22 | 16 | 2022-02-22 | 2022-03-04 | 8 | 2022-03-24 |  |  | 2022-03-04 | 2022-03-10 | 4 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2292 | PGE | 93313 | NEM | EXPNEM | Implementation | Solar PV | 701.428 |  | 2021-11-04 | 2021-11-05 | 1 | 2021-11-10 | 4 | 2021-11-29 | 10 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2022-01-12 | 32 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2293 | PGE | 93230 | NEM | EXPNEM | Study in Progress | Solar PV | 4125 |  | 2021-11-04 | 2021-11-04 | 0 | 2021-12-01 | 16 | [5 empty] | 2021-12-24 | 2022-01-25 | 21 | 2022-01-25 | 2022-01-25 | 0 |  |  |  | 2022-01-25 | [13 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2294 | PGE | 93940 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-11-04 | 2021-11-16 | 7 | 2021-11-19 | 10 | 2022-02-09 | 55 | [15 empty] | 2021-12-31 | 2022-01-04 | 2 | 2022-01-04 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2295 | PGE | 93721 | NEM | VNEM | IA in Progress | Solar PV | 54.951 |  | 2021-11-04 | 2021-11-08 | 2 | 2022-03-02 | 79 | 2022-03-16 | 10 | [15 empty] | 2022-03-16 | 2022-03-16 | 0 | 2022-03-16 | [7 empty] | 0 |  |  | 2022-03-16 | 2022-03-16 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2296 | PGE | 95334 | NEM | EXPNEM | Application Review in Progress | Solar PV | 180.93 |  | 2021-11-04 | 2021-11-16 | 7 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2297 | PGE | 95138 | NEM | EXPNEM | Implementation | Solar PV | 133.3 |  | 2021-11-04 | 2021-11-08 | 2 | 2021-11-08 | 2 | 2021-11-24 | 11 | [15 empty] | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 2021-12-02 | 4 |  |  |  |  | 2021-11-04 | 2021-12-02 | 17 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2298 | PGE | 95131 | NEM | EXPNEM | IA in Progress | Solar PV | 633.3 |  | 2021-11-04 | 2021-11-19 | 10 | 2021-11-19 | 10 | 2021-12-31 | 28 | [15 empty] | 2021-12-31 | 2022-01-24 | 15 | 2022-01-24 | [6 empty] | 2021-11-04 | 2021-12-15 | 26 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2299 | PGE | 95409 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-11-04 | 2021-11-15 | 6 | 2021-11-23 | 12 | 2021-12-03 | 6 | [18 empty] | 2021-11-03 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2300 | PGE | 95912 | NEM | EXPNEM | Study in Progress | Solar PV | 342.883 |  | 2021-11-04 | 2021-11-09 | 3 | 2021-12-27 | 34 | 2022-01-12 | 12 | 2022-01-12 | 2022-02-18 | 26 | 2022-02-18 | [22 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2301 | PGE | 95932 | NEM | EXPNEM | Application Review in Progress | Solar PV | 121.018 |  | 2021-11-04 | 2021-11-09 | 3 | [29 empty] | 2021-11-04 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2302 | PGE | 95912 | NEM | EXPNEM | Application Review in Progress | Solar PV | 114.967 |  | 2021-11-04 | 2021-11-08 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2303 | PGE | 95540 | NEM | EXPNEM | IA in Progress | Solar PV | 58.99 |  | 2021-11-04 | 2021-11-16 | 7 | 2021-11-16 | 7 | 2021-12-09 | 15 | [15 empty] | 2021-12-09 | 2021-12-30 | 15 | 2021-12-30 | [6 empty] | 2021-11-04 | 2021-12-14 | 25 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2304 | PGE | 95726 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-11-05 | 2021-11-09 | 2 | 2021-11-09 | 2 | 2021-11-16 | 4 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-16 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2305 | PGE | 95449 | NEM | EXPNEM | IA in Progress | Solar PV | 103.102 |  | 2021-11-05 | 2021-11-19 | 9 | 2022-01-13 | 46 | 2022-02-04 | 15 | [15 empty] | 2022-02-04 | 2022-02-04 | 0 | 2022-02-04 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2306 | PGE | 95403 | NEM | EXPNEM | Implementation | Solar PV | 172.8 |  | 2021-11-05 | 2021-11-10 | 3 | 2021-11-10 | 3 | 2021-11-29 | 10 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2021-12-07 | 6 |  |  |  |  | 2021-11-05 | 2021-12-06 | 18 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2307 | PGE | 93654 | NEM | EXPNEM | Implementation | Solar PV | 30.16 |  | 2021-11-05 | 2021-11-09 | 2 | 2022-01-18 | 48 | 2022-03-01 | 29 | [15 empty] | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | 2022-03-02 | 1 |  |  |  |  | 2021-11-05 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2308 | PGE | 95065 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-05 | 2021-11-15 | 5 | 2021-11-15 | 5 | 2021-11-16 | 1 | [18 empty] | 2021-11-05 | 2021-11-05 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-11-15 |  | 2021-11-29 | 11 | 1//19
2309 | PGE | 93230 | NEM | EXPNEM | IA in Progress | Solar PV | 147.168 |  | 2021-11-05 | 2021-11-16 | 6 | 2021-12-02 | 16 | 2021-12-17 | 11 | [15 empty] | 2021-12-17 | 2021-12-17 | 0 | 2021-12-17 | [6 empty] | 2021-11-05 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2310 | PGE | 95003 | Non-NEM | Inadvertent Export | Commercial | Storage | 5 |  | 2021-11-05 | 2021-11-08 | 1 | 2021-11-08 | 1 | 2021-11-16 | 5 | [18 empty] | 2021-11-05 | 2021-11-05 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-11-05 |  | 2021-11-16 | 8 | 1//19
2311 | PGE | 95425 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-11-05 | 2021-11-17 | 7 | 2021-11-24 | 12 | 2021-12-03 | 5 | [18 empty] | 2021-11-05 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-12-03 |  | 2021-12-03 | 1 | 1//19
2312 | PGE | 95376 | NEM | EXPNEM | IA in Progress | Solar PV | 1100 |  | 2021-11-05 | 2021-11-09 | 2 | 2021-11-24 | 12 | 2022-01-11 | 32 | 2022-01-28 | 2022-02-28 | 20 | [12 empty] | 2022-02-28 | 2022-03-03 | 3 | 2022-03-03 | [6 empty] | 2021-11-05 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2313 | PGE | 95521 | NEM | VNEMMASH | Implementation | Solar PV | 189.835 |  | 2021-11-05 | 2021-11-15 | 5 | 2021-12-15 | 25 | 2022-01-05 | 15 | [15 empty] | 2022-01-05 | 2022-01-05 | 0 | 2022-01-05 | 2022-03-29 | 57 | [5 empty] | 0 |  | 2022-02-22 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2314 | PGE | 93625 | NEM | EXPNEM | Implementation | Solar PV | 856.526 |  | 2021-11-05 | 2021-11-10 | 3 | 2021-11-12 | 4 | 2021-12-03 | 13 | 2021-12-14 | 2022-01-06 | 17 | [12 empty] | 2022-01-06 | 2022-01-06 | 0 | 2022-01-06 | 2022-02-03 | 19 |  |  |  |  | 2021-11-11 | 2021-12-13 | 19 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2315 | PGE | 93625 | NEM | EXPNEM | Implementation | Solar PV | 813.333 |  | 2021-11-05 | 2021-11-10 | 3 | 2021-11-12 | 4 | 2021-12-03 | 13 | 2021-12-14 | 2022-01-06 | 17 | [12 empty] | 2022-01-06 | 2022-01-06 | 0 | 2022-01-06 | 2022-02-03 | 19 |  |  |  |  | 2021-11-12 | 2021-12-13 | 19 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2316 | PGE | 95407 | NEM | VNEMSOMAH | Implementation | Solar PV | 66.601 |  | 2021-11-05 | 2021-11-09 | 2 | 2021-11-22 | 10 | 2021-12-14 | 14 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2022-01-27 | 31 |  |  |  |  | 2021-11-05 | 0 |  |  | 2022-01-11 | 2022-01-11 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2317 | PGE | 95407 | NEM | VNEMSOMAH | Implementation | Solar PV | 36.619 |  | 2021-11-05 | 2021-11-09 | 2 | 2021-11-22 | 10 | 2021-12-14 | 14 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2022-01-27 | 31 |  |  |  |  | 2021-11-05 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2318 | PGE | 95422 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-11-05 | 2021-11-09 | 2 | 2021-11-09 | 2 | 2021-11-12 | 2 | [18 empty] | 2021-11-04 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2319 | PGE | 93460 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-11-06 | 2021-11-15 | 4 | 2021-11-18 | 7 | 2021-11-29 | 5 | [18 empty] | 2021-11-04 | 2021-11-06 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-02-24 |  | 2022-02-24 | 1 | 1//19
2321 | PGE | 93453 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-07 | 2021-11-19 | 8 | 2021-11-19 | 8 | 2021-11-23 | 2 | [15 empty] | 2021-11-23 | 2021-11-23 | 0 | 2021-11-23 | 2021-11-23 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2322 | PGE | 93647 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-11-08 | 2021-11-09 | 1 | 2021-11-16 | 5 | 2021-11-29 | 7 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2021-12-01 | 2 |  |  |  |  | 2021-11-08 | 2021-12-13 | 22 |  |  |  |  | 2022-03-11 | 2022-03-23 | 8 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-11 | 2022-03-15 | 2 | 2022-03-23 |  | 2022-03-24 | 1 | 1//19
2323 | PGE | 95521 | Non-NEM | Inadvertent Export | Commercial | Storage | 5 |  | 2021-11-08 | 2021-11-19 | 8 | 2021-11-19 | 8 | 2021-12-01 | 6 | [15 empty] | 2021-12-01 | 2021-12-01 | 0 | 2021-12-01 | 2021-12-01 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-11-19 |  | 2021-12-27 | 27 | 1//19
2324 | PGE | 95020 | NEM | EXPNEM | Commercial | Solar PV | 264 |  | 2021-11-08 | 2021-11-16 | 5 | 2021-11-29 | 12 | 2021-12-13 | 10 | [15 empty] | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13 | 2021-12-14 | 1 |  |  |  |  | 2021-11-08 | 2021-12-13 | 22 |  |  |  |  | 2022-03-11 | 2022-03-17 | 4 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-11 | 2022-03-11 | 0 | 2022-03-17 |  | 2022-03-18 | 1 | 1//19
2325 | PGE | 93420 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-11-08 | 2021-11-19 | 8 | 2021-11-22 | 9 | 2021-12-03 | 7 | [18 empty] | 2021-11-08 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-02-25 |  | 2022-02-25 | 1 | 1//19
2326 | PGE | 93465 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-11-08 | 2021-11-19 | 8 | 2021-11-22 | 9 | 2021-12-03 | 7 | [18 empty] | 2021-11-08 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2327 | PGE | 95138 | NEM | EXPNEM | IA in Progress | Solar PV | 260 |  | 2021-11-08 | 2021-11-10 | 2 | 2021-11-10 | 2 | 2021-11-29 | 10 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2328 | PGE | 93933 | NEM | EXPNEM | IA in Progress | Solar PV | 601.224 |  | 2021-11-08 | 2021-11-16 | 5 | 2021-11-16 | 5 | 2021-12-14 | 18 | [15 empty] | 2021-12-14 | 2021-12-16 | 2 | 2021-12-16 | [6 empty] | 2021-11-08 | 2021-12-15 | 24 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2329 | PGE | 93204 | NEM | EXPNEM | Implementation | Solar PV | 62.5 |  | 2021-11-08 | 2021-11-10 | 2 | 2021-11-10 | 2 | 2021-11-15 | 2 | [15 empty] | 2021-11-15 | 2021-12-07 | 14 | 2021-12-07 | 2021-12-08 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2330 | PGE | 94558 | NEM | EXPNEM | Application Review in Progress | Solar PV | 652.994 |  | 2021-11-08 | 2021-11-09 | 1 | [29 empty] | 2021-11-08 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2331 | PGE | 93201 | NEM | EXPNEM | Study in Progress | Solar PV | 800 |  | 2021-11-09 | 2021-11-22 | 8 | 2021-12-07 | 17 | 2021-12-24 | 13 | 2021-12-24 | 2022-01-25 | 21 | 2022-01-25 | 2022-02-15 | 15 | 2022-02-15 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2332 | PGE | 94114 | NEM | VNEM | IA in Progress | Solar PV | 52.163 |  | 2021-11-09 | 2021-11-24 | 10 | 2022-01-06 | 39 | 2022-01-28 | 15 | [15 empty] | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2333 | PGE | 93901 | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.2 |  | 2021-11-09 | 2021-11-16 | 4 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2334 | PGE | 93426 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-11-09 | 2021-11-23 | 9 | 2021-11-23 | 9 | 2021-12-14 | 13 | [18 empty] | 2021-11-09 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2335 | PGE | 93307 | NEM | EXPNEM | Implementation | Solar PV | 230.852 |  | 2021-11-09 | 2021-11-15 | 3 | 2021-11-15 | 3 | 2021-11-29 | 8 | [15 empty] | 2021-11-29 | 2021-12-01 | 2 | 2021-12-01 | 2021-12-01 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2336 | PGE | 93901 | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.2 |  | 2021-11-09 | 2021-11-16 | 4 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2337 | PGE | 95616 | NEM | EXPNEM | Commercial | Solar PV | 50.092 |  | 2021-11-09 | 2021-11-10 | 1 | 2021-11-12 | 2 | 2021-11-30 | 10 | [15 empty] | 2021-11-30 | 2021-11-30 | 0 | 2021-11-30 | 2022-01-26 | 40 | [5 empty] | 0 | [5 empty] | 2022-01-27 | 2022-02-03 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-27 | 2022-01-27 | 0 | 2022-02-03 |  | 2022-02-03 | 0 | 1//19
2338 | PGE | 95131 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 482.24 |  | 2021-11-09 | 2021-11-10 | 1 | 2022-01-18 | 46 | 2022-03-14 | 38 | [15 empty] | 2022-03-14 | 2022-03-14 | 0 | 2022-03-14 | [6 empty] | 2021-11-09 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2339 | PGE | 94585 | NEM | EXPNEM | Implementation | Solar PV | 200 |  | 2021-11-09 | 2021-11-19 | 7 | 2021-12-23 | 29 | 2022-01-11 | 13 | [15 empty] | 2022-01-11 | 2022-01-11 | 0 | 2022-01-11 | 2022-01-25 | 9 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2340 | PGE | 94565 | NEM | VNEM | Application Review in Progress | Solar PV | 86.4 |  | 2021-11-09 | 2021-11-17 | 5 | [30 empty] | 0 |  | 2022-03-31 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2341 | PGE | 95616 | NEM | EXPNEM | IA in Progress | Solar PV | 146.17 |  | 2021-11-09 | 2021-11-23 | 9 | 2021-12-21 | 27 | 2022-01-11 | 15 | [15 empty] | 2022-01-11 | 2022-01-11 | 0 | 2022-01-11 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2342 | PGE | 95126 | NEM | EXPNEM | Implementation | Solar PV | 30.236 |  | 2021-11-09 | 2021-11-19 | 7 | 2022-01-03 | 36 | 2022-01-25 | 15 | [15 empty] | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | 2022-01-28 | 3 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2343 | PGE | 93446 | NEM | EXPNEM | Application Accepted | Solar PV | 33.3 |  | 2021-11-09 | 2021-11-19 | 7 | 2022-02-22 | 70 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2344 | PGE | 93401 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-09 | 2021-11-10 | 1 | 2021-11-10 | 1 | 2021-11-16 | 3 | [18 empty] | 2021-11-08 | 2021-11-08 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-03-18 |  | 2022-03-18 | 1 | 1//19
2345 | PGE | 93203 | NEM | EXPNEM | Implementation | Solar PV | 900 |  | 2021-11-09 | 2021-11-15 | 3 | 2021-11-16 | 4 | 2021-12-29 | 29 | 2021-12-29 | 2022-01-28 | 21 | [12 empty] | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | 2022-02-11 | 10 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2346 | PGE | 94089 | NEM | EXPNEM | IA in Progress | Solar PV | 233.2 |  | 2021-11-09 | 2021-11-15 | 3 | 2021-11-15 | 3 | 2021-11-30 | 9 | [15 empty] | 2021-11-30 | 2021-11-30 | 0 | 2021-11-30 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2347 | PGE | 94510 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.111 |  | 2021-11-09 | 2021-11-15 | 3 | 2021-12-13 | 21 | 2021-12-20 | 5 | [18 empty] | 2021-11-09 | [7 empty] | 0 | [5 empty] | 2021-12-20 | 2021-12-20 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-20 |  |  | 2021-12-20 |  | 2021-12-20 | 0 | 1//19
2348 | PGE | 95338 | NEM | EXPNEM | Implementation | Solar PV | 57.874 |  | 2021-11-09 | 2021-11-16 | 4 | 2021-11-29 | 11 | 2022-01-11 | 31 | [15 empty] | 2022-01-11 | 2022-01-11 | 0 | 2022-01-11 | 2022-02-23 | 29 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2349 | PGE | 94577 | NEM | EXPNEM | IA in Progress | Solar PV | 1250 |  | 2021-11-09 | 2021-11-15 | 3 | 2021-12-01 | 13 | 2022-02-09 | 49 | [15 empty] | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2350 | PGE | 93212 | NEM | EXPNEM | Study in Progress | Solar PV | 801.632 |  | 2021-11-10 | 2021-11-23 | 8 | 2021-12-07 | 16 | 2021-12-24 | 13 | 2021-12-24 | 2022-01-25 | 21 | 2022-01-25 | 2022-02-15 | 15 | 2022-02-15 | 2022-02-22 | 4 |  |  |  | 2022-02-22 | [13 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2351 | PGE | 94952 | NEM | EXPNEM | Study in Progress | Solar PV | 43.2 |  | 2021-11-10 | 2021-11-16 | 3 | 2021-12-01 | 12 | 2021-12-15 | 10 | 2021-12-29 | 2022-01-25 | 18 | 2022-02-08 | 2022-03-04 | 17 | 2022-03-04 | 2022-03-04 | 0 |  |  |  | 2022-03-04 | [13 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2352 | PGE | 94541 | NEM | EXPNEM | Study in Progress | Solar PV | 127.195 |  | 2021-11-10 | 2021-11-16 | 3 | 2022-02-08 | 60 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2353 | PGE | 93201 | NEM | EXPNEM | IA in Progress | Solar PV | 601.224 |  | 2021-11-10 | 2021-11-19 | 6 | 2021-11-24 | 9 | 2021-12-13 | 11 | 2021-12-13 | 2022-01-10 | 20 | [12 empty] | 2022-01-10 | 2022-01-13 | 3 | 2022-01-13 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2354 | PGE | 94536 | NEM | EXPNEM | Implementation | Solar PV | 79.292 |  | 2021-11-10 | 2021-11-15 | 2 | 2021-11-17 | 4 | 2021-12-27 | 26 | [15 empty] | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27 | 2022-03-02 | 45 |  |  |  |  | 2021-11-17 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2355 | PGE | 95128 | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2021-11-10 | 2021-11-15 | 2 | 2022-02-02 | 56 | 2022-02-24 | 15 | [15 empty] | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-14 | 12 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2356 | PGE | 93280 | NEM | EXPNEM | IA in Progress | Solar PV | 601.224 |  | 2021-11-10 | 2021-11-24 | 9 | 2021-11-29 | 10 | 2021-12-14 | 11 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2357 | PGE | 93908 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2161.5 |  | 2021-11-10 | 2021-11-17 | 4 | 2021-12-08 | 17 | 2022-02-15 | 48 | 2022-02-28 | 2022-03-31 | 23 | [22 empty] | 2021-11-10 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2358 | PGE | 93908 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 2661.5 |  | 2021-11-10 | 2021-11-17 | 4 | 2021-12-08 | 17 | 2022-01-27 | 35 | 2022-02-25 | 2022-03-31 | 24 | [12 empty] | 2022-03-31 | [9 empty] | 2021-11-10 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2359 | PGE | 94612 | NEM | EXPNEM | IA in Progress | Solar PV | 59.764 |  | 2021-11-10 | 2021-11-15 | 2 | 2021-11-16 | 3 | 2021-12-02 | 10 | [15 empty] | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2360 | PGE | 94577 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 2631.072 |  | 2021-11-10 | 2021-11-12 | 1 | 2021-12-01 | 12 | [20 empty] | 2021-11-10 | [7 empty] | 0 |  | 2022-03-31 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2361 | PGE | 95020 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 2026 |  | 2021-11-10 | 2021-11-17 | 4 | 2021-12-01 | 12 | 2022-01-14 | 32 | [25 empty] | 2021-12-08 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2362 | PGE | 93401 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-10 | 2021-11-15 | 2 | 2021-11-15 | 2 | 2021-11-16 | 1 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-16 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-02-01 |  | 2022-02-01 | 1 | 1//19
2363 | PGE | 94612 | NEM | EXPNEM | IA in Progress | Solar PV | 50.529 |  | 2021-11-10 | 2021-11-15 | 2 | 2021-11-16 | 3 | 2021-12-02 | 10 | [15 empty] | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2364 | PGE | 94065 | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-11-10 | 2021-11-15 | 2 | 2021-11-17 | 4 | 2021-11-18 | 1 | [15 empty] | 2021-11-18 | 2021-12-10 | 14 | 2021-12-10 | 2022-03-22 | 70 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2365 | PGE | 95442 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-10 | 2021-11-15 | 2 | 2021-11-17 | 4 | 2021-12-09 | 14 | [18 empty] | 2021-11-10 | 2021-11-10 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2366 | PGE | 95404 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.705 |  | 2021-11-10 | 2021-11-17 | 4 | 2021-11-20 | 6 | 2021-11-21 | 0 | [18 empty] | 2021-11-10 | [6 empty] | 2021-11-10 | 2021-12-01 | 12 |  |  |  |  | 2021-12-02 | 2021-12-02 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-02 |  |  | 2021-12-02 |  | 2021-12-02 | 0 | 1//19
2367 | PGE | 93401 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 69.472 |  | 2021-11-10 | 2021-11-29 | 10 | 2021-12-07 | 16 | 2022-01-24 | 33 | [15 empty] | 2022-01-24 | 2022-02-14 | 15 | 2022-02-14 | [6 empty] | 2021-11-10 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2368 | PGE | 94558 | NEM | EXPNEM | Implementation | Solar PV | 72 |  | 2021-11-10 | 2021-11-23 | 8 | 2021-12-02 | 13 | 2021-12-16 | 10 | [15 empty] | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16 | 2021-12-20 | 2 |  |  |  |  | 2021-11-10 | 2021-12-16 | 23 | [7 empty] | 2022-01-19 |  | 60 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2369 | PGE | 95452 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-11-10 | 2021-11-17 | 4 | 2021-11-17 | 4 | 2021-11-17 | 0 | [18 empty] | 2021-11-10 | [7 empty] | 0 | [5 empty] | 2021-11-17 | 2021-11-17 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-17 |  |  | 2021-11-17 |  | 2021-11-17 | 0 | 1//19
2370 | PGE | 94549 | Non-NEM | Non-Export | Withdrawn | Storage | 10 |  | 2021-11-11 | 2021-11-29 | 9 | 2021-12-16 | 22 | [20 empty] | 2021-11-10 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2371 | PGE | 93446 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-11-11 | 2021-11-15 | 1 | 2021-11-15 | 1 | 2021-11-18 | 3 | [15 empty] | 2021-11-18 | 2021-11-18 | 0 | 2021-11-18 | 2021-11-18 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2372 | PGE | 93453 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-11-11 | 2021-11-15 | 1 | 2021-11-18 | 4 | 2021-11-29 | 5 | [18 empty] | 2021-11-11 | 2021-11-11 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2373 | PGE | 95497 | NEM | EXPNEM | Study in Progress | Solar PV | 86.4 |  | 2021-11-11 | 2021-11-23 | 7 | 2022-03-07 | 77 | [27 empty] | 2021-11-11 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2375 | PGE | 93454 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-11-11 | 2021-11-15 | 1 | 2021-11-15 | 1 | 2021-11-16 | 1 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-16 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2376 | PGE | 96092 | NEM | EXPNEM | Study in Progress | Solar PV | 772.134 |  | 2021-11-11 | 2021-11-12 | 0 | 2022-03-15 | 83 | [27 empty] | 2022-03-15 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2377 | PGE | 96092 | NEM | EXPNEM | Withdrawn | Solar PV | 1654.572 |  | 2021-11-11 | 2021-11-12 | 0 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2378 | PGE | 96092 | NEM | EXPNEM | Study in Progress | Solar PV | 527.483 |  | 2021-11-11 | 2021-11-12 | 0 | 2021-11-12 | 0 | 2021-12-07 | 15 | 2021-12-07 | 2022-01-18 | 29 | 2022-01-18 | 2022-02-16 | 21 | 2022-02-16 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2379 | PGE | 93710 | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-11-11 | 2021-11-22 | 6 | 2021-12-24 | 28 | 2022-01-18 | 16 | [15 empty] | 2022-01-18 | 2022-01-18 | 0 | 2022-01-18 | 2022-02-04 | 13 |  |  |  |  | 2021-11-11 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2380 | PGE | 93710 | NEM | EXPNEM | Implementation | Solar PV | 30.003 |  | 2021-11-11 | 2021-11-15 | 1 | 2021-11-30 | 10 | 2021-12-14 | 10 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2021-12-16 | 2 |  |  |  |  | 2021-11-11 | 2021-12-15 | 21 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2381 | PGE | 93241 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 30.402 |  | 2021-11-11 | 2021-11-29 | 9 | 2021-12-09 | 17 | 2021-12-30 | 15 | [15 empty] | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | [6 empty] | 2021-11-11 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2382 | PGE | 93241 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 63.182 |  | 2021-11-11 | 2021-11-29 | 9 | 2021-12-09 | 17 | 2021-12-30 | 15 | [15 empty] | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | [6 empty] | 2021-11-11 | 0 |  |  | 2022-01-28 | 2022-01-28 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2383 | PGE | 95497 | NEM | EXPNEM | Study in Progress | Solar PV | 37.598 |  | 2021-11-11 | 2021-11-15 | 1 | 2022-03-17 | 85 | [27 empty] | 2021-11-11 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2384 | PGE | 93460 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-12 | 2021-11-15 | 1 | 2021-11-15 | 1 | 2021-12-27 | 28 | [15 empty] | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27 | 2021-12-27 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-12-15 |  | 2022-01-05 | 16 | 1//19
2385 | PGE | 95202 | NEM | EXPNEM | IA in Progress | Solar PV | 280 |  | 2021-11-12 | 2021-11-15 | 1 | 2021-12-24 | 28 | 2022-01-14 | 15 | 2022-01-14 | 2022-03-01 | 30 | [12 empty] | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | [6 empty] | 2021-11-12 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2386 | PGE | 93242 | NEM | EXPNEM | Implementation | Solar PV | 150 |  | 2021-11-12 | 2021-11-29 | 9 | 2021-12-02 | 12 | 2021-12-22 | 14 | [15 empty] | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22 | 2021-12-27 | 3 |  |  |  |  | 2021-11-12 | 2021-12-16 | 22 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2387 | PGE | 95602 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 1192.682 |  | 2021-11-12 | 2021-11-15 | 1 | 2022-02-04 | 57 | 2022-02-28 | 15 | 2022-02-28 | [25 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2388 | PGE | 95602 | NEM | EXPNEM | IA in Progress | Solar PV | 203.456 |  | 2021-11-12 | 2021-11-15 | 1 | 2022-01-20 | 46 | 2022-02-03 | 10 | [15 empty] | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2389 | PGE | 96092 | NEM | EXPNEM | Withdrawn | Solar PV | 1145.473 |  | 2021-11-12 | 2021-11-15 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2390 | PGE | 94945 | NEM | EXPNEM | IA in Progress | Solar PV | 384.928 |  | 2021-11-12 | 2021-11-16 | 2 | 2022-01-04 | 35 | 2022-01-19 | 10 | 2022-01-19 | 2022-02-16 | 20 | [12 empty] | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2391 | PGE | 94945 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1135.29 |  | 2021-11-12 | 2021-11-30 | 10 | [30 empty] | 0 |  | 2022-03-07 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2392 | PGE | 95993 | NEM | EXPNEM | Implementation | Solar PV | 31.724 |  | 2021-11-12 | 2021-11-29 | 9 | 2022-01-06 | 37 | 2022-01-26 | 13 | [15 empty] | 2022-01-26 | 2022-02-02 | 5 | 2022-02-02 | 2022-02-02 | 0 |  |  |  |  | 2021-11-12 | 0 |  | 2022-01-21 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2393 | PGE | 95385 | NEM | EXPNEM | Study in Progress | Solar PV | 316.555 |  | 2021-11-12 | 2021-11-16 | 2 | 2021-11-22 | 6 | 2022-01-13 | 36 | 2022-01-13 | 2022-02-17 | 24 | 2022-02-17 | 2022-03-11 | 15 | 2022-03-11 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2394 | PGE | 95464 | NEM | EXPNEM | IA in Progress | Solar PV | 457.42 |  | 2021-11-13 | 2021-11-17 | 2 | 2021-11-17 | 2 | 2021-12-06 | 11 | 2021-12-06 | 2022-01-03 | 20 | [12 empty] | 2022-01-03 | 2022-01-03 | 0 | 2022-01-03 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2395 | PGE | 93427 | NEM | EXPNEM | Application Accepted | Solar PV | 33.3 |  | 2021-11-13 | 2021-11-30 | 9 | 2021-11-30 | 9 | [27 empty] | 2021-11-13 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2396 | PGE | 95404 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 31.068 |  | 2021-11-14 | 2021-11-17 | 2 | 2021-11-24 | 7 | 2021-11-24 | 0 | [18 empty] | 2021-11-17 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2397 | PGE | 95030 | NEM | EXPNEM | Withdrawn | Solar PV | 32.453 |  | 2021-11-15 | 2021-12-01 | 10 | 2021-12-01 | 10 | 2021-12-22 | 15 | 2021-12-22 | [25 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2398 | PGE | 93401 | NEM | NEMMT | Study in Progress | Solar PV, Storage | 884.284 |  | 2021-11-15 | 2021-12-01 | 10 | 2022-01-26 | 49 | [27 empty] | 2021-11-15 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2399 | PGE | 95682 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-15 | 2021-11-18 | 3 | 2021-11-22 | 5 | 2021-12-06 | 8 | [18 empty] | 2021-11-15 | 2021-11-18 | 3 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-11-18 |  | 2021-12-06 | 13 | 1//19
2400 | PGE | 95361 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.179 |  | 2021-11-15 | 2021-11-17 | 2 | 2021-11-29 | 8 | 2021-12-20 | 15 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | [6 empty] | 2021-11-15 | 2021-12-15 | 20 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2401 | PGE | 95762 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 15 |  | 2021-11-15 | 2021-12-01 | 10 | 2021-12-01 | 10 | 2021-12-09 | 6 | [15 empty] | 2021-12-01 | 2021-12-01 |  | 2021-12-01 | 2022-03-02 | 66 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2402 | PGE | 93706 | NEM | EXPNEM | IA in Progress | Solar PV | 40.252 |  | 2021-11-15 | 2021-11-23 | 6 | 2021-12-28 | 29 | 2022-01-31 | 23 | [15 empty] | 2022-01-31 | 2022-02-02 | 2 | 2022-02-02 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2403 | PGE | 94954 | NEM | EXPNEM | Implementation | Solar PV | 62.5 |  | 2021-11-15 | 2021-11-29 | 8 | 2021-11-29 | 8 | 2021-12-15 | 12 | [15 empty] | 2021-12-15 | 2021-12-27 | 8 | 2021-12-27 | 2021-12-27 | 0 | [5 empty] | 0 |  | 2021-12-14 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2404 | PGE | 93631 | NEM | EXPNEM | Implementation | Solar PV | 38.956 |  | 2021-11-15 | 2021-11-17 | 2 | 2021-11-30 | 9 | 2021-12-06 | 4 | [15 empty] | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-15 | 7 |  |  |  |  | 2021-11-15 | 2021-12-15 | 20 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2405 | PGE | 94568 | NEM | EXPNEM | Implementation | Solar PV | 50 |  | 2021-11-15 | 2021-11-29 | 8 | 2021-11-29 | 8 | 2022-01-03 | 25 | 2022-01-03 | 2022-01-31 | 19 | [12 empty] | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | 2022-02-11 | 9 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2406 | PGE | 94080 | NEM | NEMMT | IA in Progress | Solar PV, Storage | 789.853 |  | 2021-11-16 | 2021-12-02 | 10 | 2022-01-31 | 51 | 2022-03-22 | 35 | [15 empty] | 2022-03-22 | 2022-03-22 | 0 | 2022-03-22 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2407 | PGE | 95695 | NEM | EXPNEM | Withdrawn | TRBS | 6250 |  | 2021-11-10 | 2021-11-16 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2408 | PGE | 94901 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-16 | 2021-11-19 | 3 | 2021-12-01 | 9 | 2021-12-03 | 2 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-16 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2409 | PGE | 96056 | NEM | EXPNEM | IA in Progress | Solar PV | 75.294 |  | 2021-11-16 | 2021-11-17 | 1 | 2021-12-21 | 23 | 2022-01-26 | 25 | [15 empty] | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2410 | PGE | 95446 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-16 | 2021-11-22 | 4 | 2021-11-22 | 4 | 2021-12-03 | 7 | [15 empty] | 2021-12-03 | 2021-12-03 | 0 | 2021-12-03 | 2021-12-03 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-12-03 |  | 2021-12-03 | 1 | 1//19
2411 | PGE | 95913 | NEM | EXPNEM | Implementation | Solar PV | 361.092 |  | 2021-11-16 | 2021-12-01 | 9 | 2021-12-14 | 18 | 2022-01-11 | 20 | [15 empty] | 2022-01-11 | 2022-01-11 | 0 | 2022-01-11 | 2022-03-08 | 38 | [5 empty] | 0 |  | 2022-01-06 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2412 | PGE | 94707 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.987 |  | 2021-11-16 | 2021-11-16 | 0 | 2021-11-19 | 3 | 2021-11-20 | 0 | [18 empty] | 2021-11-16 | [7 empty] | 0 | [5 empty] | 2021-11-20 | 2021-11-20 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-11-20 |  |  | 2021-11-20 |  | 2021-11-20 | 0 | 1//19
2413 | PGE | 93454 | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2021-11-16 | 2021-11-24 | 6 | 2021-11-30 | 8 | 2022-02-04 | 47 | [15 empty] | 2022-02-04 | 2022-02-04 | 0 | 2022-02-04 | 2022-03-24 | 33 | [5 empty] | 0 | [5 empty] | 2022-03-30 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-30 | 2022-03-30 | 0 |  |  |  |  | 1//19
2414 | PGE | 95376 | NEM | EXPNEM | Withdrawn | Solar PV | 1200 |  | 2021-11-17 | 2021-11-19 | 2 | 2021-12-08 | 13 | 2021-12-29 | 15 | 2022-01-12 | 2022-02-09 | 19 | [22 empty] | 2021-11-17 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2415 | PGE | 95695 | NEM | EXPNEM | IA in Progress | Solar PV | 57.217 |  | 2021-11-09 | 2021-11-19 | 7 | 2022-02-22 | 70 | 2022-03-08 | 10 | [15 empty] | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 | [6 empty] | 2021-12-14 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2416 | PGE | 94404 | NEM | EXPNEM | Application Review in Progress | Solar PV | 95.827 |  | 2021-11-17 | 2021-11-23 | 4 | [29 empty] | 2021-11-17 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2417 | PGE | 94404 | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 |  | 2021-11-17 | 2021-11-23 | 4 | [29 empty] | 2021-11-17 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2418 | PGE | 94402 | NEM | EXPNEM | IA in Progress | Solar PV | 110.801 |  | 2021-11-17 | 2021-11-19 | 2 | 2022-02-24 | 67 | 2022-03-07 | 7 | [15 empty] | 2022-03-07 | 2022-03-07 | 0 | 2022-03-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2419 | PGE | 94404 | NEM | EXPNEM | Application Review in Progress | Solar PV | 80.639 |  | 2021-11-17 | 2021-11-30 | 7 | [29 empty] | 2021-11-17 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2420 | PGE | 94401 | NEM | EXPNEM | Implementation | Solar PV | 63.081 |  | 2021-11-17 | 2021-11-18 | 1 | 2021-11-22 | 3 | 2021-12-08 | 10 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | 2022-02-02 | 39 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2421 | PGE | 93727 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-11-17 | 2021-11-30 | 7 | 2021-11-30 | 7 | 2021-12-14 | 10 | [15 empty] | 2021-12-14 | 2021-12-16 | 2 | 2021-12-16 | [6 empty] | 2021-11-17 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2422 | PGE | 93405 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-11-17 | 2021-11-19 | 2 | 2021-12-14 | 17 | 2021-12-29 | 11 | [18 empty] | 2021-11-17 | 2021-12-16 | 19 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2423 | PGE | 95076 | NEM | EXPNEM | Implementation | Solar PV | 59.45 |  | 2021-11-17 | 2021-12-03 | 10 | 2021-12-07 | 12 | 2021-12-23 | 12 | [15 empty] | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23 | 2022-03-14 | 55 |  |  |  |  | 2021-11-17 | 2021-12-16 | 19 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2424 | PGE | 93703 | NEM | EXPNEM | IA in Progress | Solar PV | 83.3 |  | 2021-11-17 | 2021-12-03 | 10 | 2021-12-03 | 10 | 2021-12-23 | 14 | [15 empty] | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23 | [6 empty] | 2021-11-17 | 2021-12-16 | 19 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2425 | PGE | 93206 | NEM | EXPNEM | Study in Progress | Solar PV | 501.02 |  | 2021-11-17 | 2021-11-29 | 6 | 2021-12-15 | 18 | [5 empty] | 2021-12-15 | 2022-01-11 | 19 | 2022-01-11 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2426 | PGE | 95032 | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 |  | 2021-11-17 | 2021-12-02 | 9 | [29 empty] | 2021-11-17 | 0 |  | 2022-01-25 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2427 | PGE | 94526 | Non-NEM | Inadvertent Export | Commercial | Storage | 5 |  | 2021-11-17 | 2021-12-02 | 9 | 2021-12-15 | 18 | 2021-12-23 | 6 | [18 empty] | 2021-11-17 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-12-02 |  | 2021-12-23 | 16 | 1//19
2428 | PGE | 94610 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 500.5 |  | 2021-11-17 | 2021-11-29 | 6 | 2021-11-29 | 6 | 2021-12-20 | 15 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | 2022-02-22 | 44 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2429 | PGE | 94545 | NEM | EXPNEM | Application Review in Progress | Solar PV | 48.875 |  | 2021-11-17 | 2021-11-18 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2430 | PGE | 93203 | NEM | EXPNEM | Application Review in Progress | Solar PV | 993.487 |  | 2021-11-17 | 2021-12-02 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2431 | PGE | 93230 | NEM | EXPNEM | Implementation | Solar PV | 47.677 |  | 2021-11-17 | 2021-11-19 | 2 | 2021-11-24 | 5 | 2021-12-14 | 12 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2021-12-28 | 10 |  |  |  |  | 2021-11-17 | 0 | [5 empty] | 2022-03-30 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-30 | 2022-03-30 | 0 |  |  |  |  | 1//19
2432 | PGE | 93940 | NEM | EXPNEM | Implementation | Solar PV | 57.71 |  | 2021-11-17 | 2021-12-03 | 10 | 2021-12-07 | 12 | 2022-02-24 | 55 | [15 empty] | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-09 | 9 |  |  |  |  | 2021-11-17 | 2021-12-16 | 19 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2433 | PGE | 94574 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.08 |  | 2021-11-17 | 2021-11-22 | 3 | 2021-11-24 | 5 | 2021-11-29 | 1 | [18 empty] | 2021-11-17 | [7 empty] | 0 | [5 empty] | 2022-01-14 | 2022-02-08 | 16 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-14 | 2022-02-08 | 16 | 2022-02-08 |  | 2022-02-10 | 2 | 1//19
2434 | PGE | 95619 | NEM | NEM Paired Storage | IA in Progress | ENGN, Solar PV, Storage | 865.4 |  | 2021-11-17 | 2021-11-18 | 1 | 2021-11-18 | 1 | 2021-12-09 | 13 | [15 empty] | 2022-01-11 | 2022-02-02 | 15 | 2022-02-02 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2435 | PGE | 95023 | NEM | EXPNEM | Withdrawn | Solar PV | 875 |  | 2021-11-18 | 2021-11-22 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2436 | PGE | 94558 | NEM | EXPNEM | IA in Progress | Solar PV | 69.189 |  | 2021-11-18 | 2021-11-22 | 2 | 2022-03-07 | 73 | 2022-03-22 | 11 | [15 empty] | 2022-03-22 | 2022-03-22 | 0 | 2022-03-22 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2437 | PGE | 95746 | NEM | EXPNEM | Withdrawn | Solar PV | 37.599 |  | 2021-11-18 | 2021-11-29 | 5 | 2021-11-29 | 5 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2438 | PGE | 95403 | NEM | EXPNEM | Implementation | Solar PV | 300 |  | 2021-11-18 | 2021-11-30 | 6 | 2021-11-30 | 6 | 2021-12-15 | 11 | [15 empty] | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 2021-12-16 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2439 | PGE | 94403 | NEM | EXPNEM | IA in Progress | Solar PV | 86.4 |  | 2021-11-18 | 2021-11-19 | 1 | 2021-11-19 | 1 | 2021-12-29 | 26 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2440 | PGE | 93266 | NEM | EXPNEM | Implementation | Solar PV | 840 |  | 2021-11-18 | 2021-11-29 | 5 | 2021-11-29 | 5 | 2021-12-14 | 11 | 2021-12-14 | 2022-01-07 | 18 | 2022-01-07 | 2022-01-26 | 12 | 2022-01-26 | 2022-01-26 |  | 2022-01-26 | 2022-03-15 | 35 | 2022-01-26 |  |  | 2022-03-15 | 2022-03-18 | 3 | 2022-03-18 | 2022-03-21 | 1 |  |  |  |  | 2021-11-18 | 0 |  | 2021-12-14 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2441 | PGE | 95003 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-18 | 2021-11-19 | 1 | 2021-12-01 | 7 | 2021-12-15 | 10 | [18 empty] | 2021-11-18 | 2021-11-18 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-11-19 |  | 2021-12-15 | 19 | 1//19
2442 | PGE | 93458 | NEM | VNEMMASH | Application Review in Progress | Solar PV | 39.976 |  | 2021-11-18 | 2021-11-19 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2443 | PGE | 93908 | NEM | EXPNEM | Implementation | Solar PV | 360 |  | 2021-11-18 | 2021-11-22 | 2 | 2021-11-29 | 5 | 2021-12-01 | 2 | [15 empty] | 2021-12-01 | 2021-12-01 | 0 | 2021-12-01 | 2022-02-11 | 51 |  |  |  |  | 2021-11-18 | 2021-12-15 | 17 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2444 | PGE | 95131 | Non-NEM | NEMFC | IA in Progress | FUCE | 1100 |  | 2021-11-18 | 2021-12-03 | 9 | 2022-01-24 | 44 | 2022-02-25 | 23 | [15 empty] | 2022-02-25 | 2022-02-25 | 0 | 2022-02-25 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2445 | PGE | 94010 | NEM | EXPNEM | Implementation | Solar PV | 31.9 |  | 2021-11-18 | 2021-11-24 | 4 | 2021-12-13 | 15 | 2022-02-15 | 45 | [15 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | 2022-02-15 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2446 | PGE | 93654 | NEM | EXPNEM | IA in Progress | Solar PV | 71.79 |  | 2021-11-18 | 2021-11-22 | 2 | 2021-12-06 | 10 | 2021-12-16 | 8 | [15 empty] | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16 | [6 empty] | 2021-11-18 | 0 | [8 empty] | 2022-01-25 | 2022-02-23 | 21 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2447 | PGE | 94608 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 864.427 |  | 2021-11-18 | 2021-12-04 | 9 | [29 empty] | 2021-11-18 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2448 | PGE | 93420 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 32.61 |  | 2021-11-18 | 2021-11-22 | 2 | 2021-12-09 | 13 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2449 | PGE | 93624 | NEM | EXPNEM | Study in Progress | Solar PV | 1907.237 |  | 2021-11-18 | 2021-11-19 | 1 | 2021-12-08 | 12 | 2021-12-27 | 13 | 2022-01-18 | 2022-02-10 | 17 | 2022-02-18 | 2022-03-14 | 15 | 2022-03-14 | 2022-03-24 | 8 |  |  |  | 2022-03-24 | 2022-03-31 | 5 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2450 | PGE | 93239 | NEM | EXPNEM | Implementation | Solar PV | 31.664 |  | 2021-11-18 | 2021-11-22 | 2 | 2021-12-02 | 8 | 2021-12-15 | 9 | [15 empty] | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 2022-02-02 | 34 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2451 | PGE | 93725 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 1600 |  | 2021-11-18 | 2021-11-19 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2452 | PGE | 93624 | NEM | EXPNEM | Implementation | Solar PV | 625 |  | 2021-11-18 | 2021-11-30 | 6 | 2021-11-30 | 6 | 2021-12-15 | 11 | 2021-12-15 | 2022-01-07 | 17 | [12 empty] | 2022-01-07 | 2022-01-10 | 1 | 2022-01-10 | 2022-03-04 | 37 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2453 | PGE | 95570 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-11-19 | 2021-11-24 | 3 | 2021-11-24 | 3 | 2021-12-03 | 5 | [15 empty] | 2021-12-03 | 2021-12-03 | 0 | 2021-12-03 | 2021-12-03 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2454 | PGE | 95210 | NEM | EXPNEM | IA in Progress | Solar PV | 31.139 |  | 2021-11-19 | 2021-11-29 | 4 | 2022-03-09 | 74 | 2022-03-28 | 13 | [15 empty] | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2455 | PGE | 94806 | NEM | EXPNEM | IA in Progress | Solar PV | 81.757 |  | 2021-11-19 | 2021-12-02 | 7 | 2022-03-09 | 74 | 2022-03-28 | 13 | [15 empty] | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2456 | PGE | 94941 | Non-NEM | Non-Export | Implementation | Storage | 10 |  | 2021-11-19 | 2021-11-24 | 3 | 2021-11-24 | 3 | [20 empty] | 2021-11-19 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2457 | PGE | 93725 | NEM | EXPNEM | IA in Progress | Solar PV | 187.5 |  | 2021-11-19 | 2021-11-22 | 1 | 2022-01-04 | 30 | 2022-01-25 | 14 | 2022-01-25 | 2022-02-11 | 13 | [12 empty] | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | [6 empty] | 2021-11-19 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2458 | PGE | 95963 | NEM | VNEMSOMAH | Implementation | Solar PV | 36.448 |  | 2021-11-19 | 2021-11-29 | 4 | 2021-12-01 | 6 | 2021-12-20 | 13 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | 2022-01-27 | 27 |  |  |  |  | 2021-11-19 | 2021-12-14 | 15 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2459 | PGE | 95963 | NEM | VNEMSOMAH | Implementation | Solar PV | 38.018 |  | 2021-11-19 | 2021-11-29 | 4 | 2021-12-01 | 6 | 2021-12-20 | 13 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | 2022-01-27 | 27 |  |  |  |  | 2021-11-19 | 2021-12-14 | 15 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2460 | PGE | 93720 | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-11-19 | 2021-11-30 | 5 | 2021-11-30 | 5 | 2021-12-07 | 5 | [15 empty] | 2021-12-07 | 2021-12-07 | 0 | 2021-12-07 | 2021-12-08 | 1 |  |  |  |  | 2021-11-19 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2461 | PGE | 93306 | NEM | EXPNEM | Commercial | Solar PV | 72.22 |  | 2021-11-19 | 2021-11-29 | 4 | 2021-12-02 | 7 | 2021-12-16 | 10 | [15 empty] | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16 | 2021-12-30 | 10 | [5 empty] | 0 | [5 empty] | 2022-02-03 | 2022-02-11 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-03 | 2022-02-03 | 0 | 2022-02-11 |  | 2022-02-11 | 0 | 1//19
2462 | PGE | 94566 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.375 |  | 2021-11-20 | 2021-11-24 | 2 | 2021-11-24 | 2 | 2022-01-18 | 36 | [18 empty] | 2021-11-20 | [7 empty] | 0 | [5 empty] | 2022-01-18 | 2022-01-18 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-18 |  |  | 2022-01-18 |  | 2022-01-18 | 0 | 1//19
2463 | PGE | 93203 | Non-NEM | Non-Export | IA in Progress | Storage | 929.5 |  | 2021-11-22 | 2021-11-22 | 0 | 2022-01-19 | 39 | [17 empty] | 2022-01-21 | 2022-01-21 | 0 | 2022-01-21 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2464 | PGE | 93206 | Non-NEM | Non-Export | Application Accepted | Storage | 858 |  | 2021-11-22 | 2021-11-22 | 0 | 2021-12-08 | 10 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2465 | PGE | 93203 | Non-NEM | Non-Export | IA in Progress | Storage | 929.5 |  | 2021-11-22 | 2021-11-22 | 0 | 2022-01-19 | 39 | [17 empty] | 2022-01-21 | 2022-01-21 | 0 | 2022-01-21 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2466 | PGE | 95556 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-11-22 | 2021-11-23 | 1 | 2021-11-23 | 1 | 2021-11-29 | 2 | [18 empty] | 2021-11-18 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2467 | PGE | 94533 | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-11-22 | 2021-11-30 | 4 | 2021-12-02 | 6 | 2021-12-17 | 11 | [15 empty] | 2021-12-17 | 2021-12-17 | 0 | 2021-12-17 | [6 empty] | 2021-11-22 | 2021-12-16 | 16 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2468 | PGE | 94549 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-22 | 2021-11-23 | 1 | 2021-11-23 | 1 | 2021-12-13 | 12 | [18 empty] | 2021-11-22 | 2021-11-22 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-11-22 |  | 2021-12-13 | 16 | 1//19
2469 | PGE | 93311 | NEM | EXPNEM | IA in Progress | Solar PV | 751.224 |  | 2021-11-22 | 2021-11-29 | 3 | 2021-12-01 | 5 | [5 empty] | 2021-12-01 | 2021-12-29 | 20 | 2021-12-29 | 2021-12-29 |  | 2022-01-03 | 2022-03-14 | 51 | 2021-12-29 |  |  | 2022-03-14 | 2022-03-14 | 0 | 2022-03-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2470 | PGE | 93204 | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-11-22 | 2021-12-08 | 10 | 2021-12-08 | 10 | 2021-12-30 | 16 | [15 empty] | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2472 | PGE | 93460 | Non-NEM | Inadvertent Export | Withdrawn | Storage | 25 |  | 2021-11-22 | 2021-11-24 | 2 | 2021-11-24 | 2 | 2021-12-10 | 10 | [15 empty] | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2473 | PGE | 94945 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 649.409 |  | 2021-11-22 | 2021-12-08 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2474 | PGE | 94945 | NEM | EXPNEM | IA in Progress | Solar PV | 276.132 |  | 2021-11-22 | 2021-11-23 | 1 | 2021-11-23 | 1 | 2021-12-10 | 11 | [15 empty] | 2021-12-10 | 2021-12-10 | 0 | 2021-12-10 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2475 | PGE | 93720 | NEM | EXPNEM | Application Review in Progress | Solar PV | 50 |  | 2021-11-22 | 2021-12-03 | 7 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2476 | PGE | 93308 | NEM | EXPNEM | Commercial | Solar PV | 54.81 |  | 2021-11-22 | 2021-12-08 | 10 | 2021-12-13 | 13 | 2021-12-27 | 10 | [15 empty] | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27 | 2022-03-18 | 57 | [5 empty] | 0 | [5 empty] | 2022-03-18 | 2022-03-29 | 7 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-18 | 2022-03-21 | 1 | 2022-03-29 |  | 2022-03-30 | 1 | 1//19
2477 | PGE | 93420 | Non-NEM | Inadvertent Export | Implementation | Storage | 25 |  | 2021-11-23 | 2021-11-24 | 1 | 2021-11-24 | 1 | 2021-12-10 | 10 | [15 empty] | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 2021-11-29 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2478 | PGE | 93420 | Non-NEM | Inadvertent Export | Withdrawn | Storage | 10 |  | 2021-11-23 | 2021-11-24 | 1 | 2021-11-24 | 1 | 2021-12-13 | 11 | [18 empty] | 2021-11-22 | 2021-11-22 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2479 | PGE | 93426 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-23 | 2021-11-24 | 1 | 2021-11-24 | 1 | 2021-12-13 | 11 | [18 empty] | 2021-11-22 | 2021-11-22 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2480 | PGE | 93280 | NEM | EXPNEM | Study in Progress | Solar PV | 601.224 |  | 2021-11-23 | 2021-12-09 | 10 | 2022-01-12 | 34 | [5 empty] | 2022-01-12 | 2022-02-10 | 20 | 2022-02-10 | [18 empty] | 2021-11-23 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2481 | PGE | 93422 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-23 | 2021-11-24 | 1 | 2021-11-24 | 1 | 2021-12-13 | 11 | [18 empty] | 2021-11-23 | 2021-11-23 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2482 | PGE | 93924 | Non-NEM | Inadvertent Export | Withdrawn | Storage | 10 |  | 2021-11-23 | 2021-11-24 | 1 | 2021-11-24 | 1 | 2021-11-30 | 2 | [18 empty] | 2021-11-22 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2483 | PGE | 96002 | NEM | EXPNEM | Application Review in Progress | Solar PV | 50 |  | 2021-11-23 | 2021-12-02 | 5 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2484 | PGE | 93612 | NEM | EXPNEM | Commercial | Solar PV | 53.626 |  | 2021-11-23 | 2021-11-29 | 2 | 2021-11-29 | 2 | 2021-12-06 | 5 | [15 empty] | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2022-01-21 | 33 |  |  |  |  | 2021-11-23 | 2021-12-15 | 14 |  |  |  |  | 2022-01-21 | 2022-01-27 | 4 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-21 | 2022-01-24 | 1 | 2022-01-27 |  | 2022-01-28 | 1 | 1//19
2485 | PGE | 96002 | NEM | EXPNEM | Application Review in Progress | Solar PV | 50 |  | 2021-11-23 | 2021-12-06 | 7 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2486 | PGE | 93619 | NEM | EXPNEM | Study in Progress | Solar PV | 48.51 |  | 2021-11-23 | 2021-12-06 | 7 | 2022-03-05 | 69 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2487 | PGE | 93460 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-11-23 | 2021-11-29 | 2 | 2021-12-31 | 26 | 2022-01-19 | 12 | [18 empty] | 2021-11-19 | 2021-11-23 | 2 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2488 | PGE | 94550 | NEM | EXPNEM | IA in Progress | Solar PV | 157.679 |  | 2021-11-23 | 2021-12-09 | 10 | 2021-12-15 | 14 | 2022-01-26 | 29 | 2022-01-26 | 2022-03-01 | 23 | [12 empty] | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2489 | PGE | 93662 | NEM | EXPNEM | Implementation | Solar PV | 443.735 |  | 2021-11-23 | 2021-12-06 | 7 | 2022-01-18 | 37 | 2022-02-02 | 11 | [15 empty] | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-03-31 | 40 |  |  |  |  | 2021-11-23 | 2021-12-16 | 15 | 2022-01-05 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2490 | PGE | 94538 | NEM | EXPNEM | Study in Progress | Solar PV | 402.52 |  | 2021-11-23 | 2021-12-09 | 10 | 2022-03-07 | 70 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2491 | PGE | 95320 | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 |  | 2021-11-23 | 2021-11-24 | 1 | [29 empty] | 2021-11-23 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2492 | PGE | 93405 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 0 | 2021-12-13 | 11 | [18 empty] | 2021-11-13 | 2021-11-13 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-02-25 |  | 2022-03-07 | 7 | 1//19
2494 | PGE | 93654 | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-11-24 | 2021-12-10 | 10 | 2021-12-10 | 10 | 2021-12-22 | 8 | [15 empty] | 2021-12-22 | 2022-01-12 | 15 | 2022-01-12 | [6 empty] | 2021-11-24 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2495 | PGE | 93610 | NEM | EXPNEM | Study in Progress | Solar PV | 760 |  | 2021-11-24 | 2021-11-29 | 1 | 2022-02-04 | 49 | 2022-02-18 | 10 | 2022-02-18 | 2022-03-17 | 18 | 2022-03-17 | [22 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2497 | PGE | 94710 | NEM | EXPNEM | Application Accepted | Solar PV | 34.627 |  | 2021-11-24 | 2021-12-01 | 3 | 2022-03-09 | 71 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2498 | PGE | 94957 | NEM | EXPNEM | IA in Progress | Solar PV | 73.4 |  | 2021-11-24 | 2021-12-10 | 10 | 2021-12-10 | 10 | 2022-03-07 | 59 | [15 empty] | 2022-03-07 | 2022-03-11 | 4 | 2022-03-11 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2499 | PGE | 94533 | NEM | VNEM | Implementation | Solar PV | 38.629 |  | 2021-11-24 | 2021-11-30 | 2 | 2021-12-10 | 10 | 2021-12-31 | 15 | [15 empty] | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | 2022-01-27 | 18 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2500 | PGE | 94533 | NEM | VNEM | Implementation | Solar PV | 33.75 |  | 2021-11-24 | 2021-11-30 | 2 | 2021-12-10 | 10 | 2021-12-31 | 15 | [15 empty] | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | 2022-01-27 | 18 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2501 | PGE | 93422 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-24 | 2021-11-30 | 2 | 2021-11-30 | 2 | 2021-12-20 | 14 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | 2021-12-20 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-03-24 |  | 2022-03-24 | 1 | 1//19
2502 | PGE | 94404 | NEM | EXPNEM | IA in Progress | Solar PV | 164.41 |  | 2021-11-26 | 2021-12-06 | 5 | 2021-12-06 | 5 | 2021-12-27 | 15 | [15 empty] | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2503 | PGE | 94403 | NEM | EXPNEM | IA in Progress | Solar PV | 99.9 |  | 2021-11-26 | 2021-11-29 | 0 | 2021-12-01 | 2 | 2021-12-22 | 15 | 2021-12-22 | 2022-01-18 | 18 | [12 empty] | 2022-01-18 | 2022-01-18 | 0 | 2022-01-18 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2504 | PGE | 94403 | NEM | EXPNEM | Study in Progress | Solar PV | 312.5 |  | 2021-11-26 | 2021-12-10 | 9 | 2021-12-16 | 13 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2505 | PGE | 94404 | NEM | EXPNEM | IA in Progress | Solar PV | 248.79 |  | 2021-11-26 | 2021-12-10 | 9 | 2021-12-14 | 11 | 2021-12-29 | 11 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2506 | PGE | 94404 | NEM | EXPNEM | IA in Progress | Solar PV | 200 |  | 2021-11-26 | 2021-11-29 | 0 | 2021-11-29 | 0 | 2021-12-13 | 10 | [15 empty] | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2507 | PGE | 94403 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-11-26 | 2021-12-06 | 5 | 2021-12-06 | 5 | 2021-12-23 | 13 | [15 empty] | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2508 | PGE | 94404 | NEM | EXPNEM | IA in Progress | Solar PV | 150 |  | 2021-11-26 | 2021-12-10 | 9 | 2021-12-16 | 13 | 2022-01-06 | 15 | [15 empty] | 2022-01-06 | 2022-01-11 | 3 | 2022-01-11 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2509 | PGE | 94403 | NEM | EXPNEM | IA in Progress | Solar PV | 230.087 |  | 2021-11-26 | 2021-12-10 | 9 | 2021-12-14 | 11 | 2022-02-15 | 44 | [15 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2510 | PGE | 94404 | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-11-26 | 2021-11-30 | 1 | 2021-12-02 | 3 | 2021-12-03 | 1 | [15 empty] | 2021-12-03 | 2021-12-06 | 1 | 2021-12-06 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2511 | PGE | 94402 | NEM | EXPNEM | IA in Progress | Solar PV | 99.9 |  | 2021-11-26 | 2021-12-01 | 2 | 2021-12-03 | 4 | 2021-12-14 | 7 | 2021-12-14 | 2022-01-07 | 18 | [12 empty] | 2022-01-07 | 2022-01-07 | 0 | 2022-01-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2512 | PGE | 93453 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-27 | 2021-12-09 | 8 | 2021-12-09 | 8 | 2021-12-29 | 14 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 2021-12-29 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2513 | PGE | 94566 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-11-27 | 2021-12-01 | 2 | 2021-12-01 | 2 | 2021-12-28 | 19 | [18 empty] | 2021-11-27 | [7 empty] | 0 | [5 empty] | 2021-12-28 | 2021-12-28 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-28 |  |  | 2021-12-28 |  | 2021-12-28 | 0 | 1//19
2514 | PGE | 95135 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 32.158 |  | 2021-11-27 | 2021-11-27 | 0 | 2021-11-30 | 1 | 2021-12-20 | 14 | [18 empty] | 2021-11-27 | [7 empty] | 0 | [5 empty] | 2021-12-20 | 2021-12-20 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-20 |  |  | 2021-12-20 |  | 2021-12-20 | 0 | 1//19
2515 | PGE | 93308 | Non-NEM | Non-Export | IA in Progress | Solar PV | 1246.18 |  | 2021-11-23 | 2021-12-01 | 4 | 2021-12-15 | 14 | 2022-01-19 | 24 | [15 empty] | 2022-01-19 | 2022-01-19 | 0 | 2022-01-19 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2516 | PGE | 93654 | NEM | NEMMT | Withdrawn | ENGN, Solar PV, Storage | 4123.1 |  | 2021-11-29 | 2021-12-08 | 7 | [29 empty] | 2021-11-29 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2517 | PGE | 93420 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-11-29 | 2021-12-08 | 7 | 2021-12-17 | 14 | 2022-01-07 | 15 | [18 empty] | 2021-11-29 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2518 | PGE | 93234 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 37.926 |  | 2021-11-29 | 2021-12-03 | 4 | 2021-12-10 | 9 | 2021-12-31 | 15 | [15 empty] | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | [6 empty] | 2021-11-29 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2519 | PGE | 94558 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.97 |  | 2021-11-29 | 2021-12-01 | 2 | 2021-12-08 | 7 | 2022-01-27 | 35 | [26 empty] | 0 | [5 empty] | 2022-01-27 | 2022-01-27 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-27 |  |  | 2022-01-27 |  | 2022-01-27 | 0 | 1//19
2520 | PGE | 93234 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 45.542 |  | 2021-11-29 | 2021-12-03 | 4 | 2021-12-10 | 9 | 2021-12-31 | 15 | [15 empty] | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | [6 empty] | 2021-11-29 | 0 |  | 2021-12-15 | 2021-12-29 |  | 10 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2521 | PGE | 93309 | NEM | VNEM | IA in Progress | Solar PV | 300 |  | 2021-11-29 | 2021-12-02 | 3 | 2021-12-17 | 14 | 2022-01-05 | 13 | [15 empty] | 2022-01-05 | 2022-01-05 | 0 | 2022-01-05 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2522 | PGE | 93619 | NEM | EXPNEM | Implementation | Solar PV | 36 |  | 2021-11-29 | 2021-12-02 | 3 | 2021-12-06 | 5 | 2021-12-30 | 18 | [15 empty] | 2021-12-30 | 2022-01-06 | 5 | 2022-01-06 | 2022-01-07 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2524 | PGE | 95920 | NEM | EXPNEM | IA in Progress | Solar PV | 63.994 |  | 2021-11-29 | 2021-11-29 | 0 | 2022-02-25 | 62 | 2022-03-17 | 14 | [15 empty] | 2022-03-17 | 2022-03-17 | 0 | 2022-03-17 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2525 | PGE | 93308 | NEM | EXPNEM | IA in Progress | Solar PV | 996.944 |  | 2021-11-29 | 2021-12-01 | 2 | 2021-12-15 | 12 | 2022-01-14 | 22 | [15 empty] | 2022-01-14 | 2022-01-14 | 0 | 2022-01-14 | [6 empty] | 2021-11-29 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2526 | PGE | 93314 | NEM | EXPNEM | Study in Progress | Solar PV | 701.428 |  | 2021-11-29 | 2021-12-13 | 10 | 2021-12-27 | 20 | [5 empty] | 2021-12-27 | 2022-02-01 | 25 | 2022-02-01 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2527 | PGE | 93307 | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2021-11-29 | 2021-12-01 | 2 | 2021-12-01 | 2 | [5 empty] | 2021-12-01 | 2021-12-29 | 20 | 2021-12-29 | 2021-12-29 |  | 2021-12-29 | 2022-03-11 | 53 | 2021-12-29 |  |  | 2022-03-11 | 2022-03-11 | 0 | 2022-03-11 | [6 empty] | 2021-11-29 | 0 |  | 2021-12-14 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2528 | PGE | 93711 | NEM | EXPNEM | Commercial | Solar PV | 40.6 |  | 2021-11-29 | 2021-12-01 | 2 | 2021-12-02 | 3 | 2021-12-15 | 9 | [15 empty] | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 2021-12-20 | 3 |  |  |  |  | 2021-11-29 | 2021-12-16 | 13 |  |  |  |  | 2022-01-26 | 2022-02-03 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-26 | 2022-02-03 | 6 | 2022-02-03 |  | 2022-02-03 | 0 | 1//19
2529 | PGE | 95695 | NEM | EXPNEM | Withdrawn | TRBS | 5000 |  | 2021-11-30 | 2021-12-01 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2530 | PGE | 95128 | NEM | EXPNEM | Implementation | Solar PV | 300 |  | 2021-11-30 | 2021-12-07 | 5 | 2021-12-07 | 5 | 2021-12-21 | 10 | [15 empty] | 2021-12-21 | 2021-12-21 | 0 | 2021-12-21 | 2021-12-24 | 3 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2531 | PGE | 93422 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-30 | 2021-12-01 | 1 | 2021-12-01 | 1 | 2021-12-20 | 13 | [18 empty] | 2021-11-23 | 2021-11-23 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2532 | PGE | 95138 | NEM | EXPNEM | IA in Progress | Solar PV | 420 |  | 2021-11-30 | 2021-12-07 | 5 | 2021-12-07 | 5 | 2021-12-22 | 11 | [15 empty] | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22 | [7 empty] | 0 |  | 2022-01-06 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2533 | PGE | 93609 | NEM | EXPNEM | Study in Progress | Solar PV | 45.45 |  | 2021-11-30 | 2021-12-06 | 4 | 2021-12-06 | 4 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2534 | PGE | 95123 | NEM | VNEM | Application Review in Progress | Solar PV | 200 |  | 2021-11-30 | 2021-12-13 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2535 | PGE | 94556 | Non-NEM | Non-Export | Study in Progress | Solar PV, Storage | 10 |  | 2021-11-30 | 2021-12-07 | 5 | 2021-12-07 | 5 | [20 empty] | 2021-11-30 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2536 | PGE | 93311 | NEM | EXPNEM | IA in Progress | Solar PV | 186.955 |  | 2021-11-30 | 2021-12-01 | 1 | 2022-01-14 | 33 | 2022-02-28 | 29 | [15 empty] | 2022-02-28 | 2022-02-28 | 0 | 2022-02-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2537 | PGE | 93311 | NEM | EXPNEM | Implementation | Solar PV | 100.107 |  | 2021-11-30 | 2021-12-01 | 1 | 2021-12-01 | 1 | 2021-12-15 | 10 | [15 empty] | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 2021-12-23 | 6 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2538 | PGE | 94022 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.16 |  | 2021-11-30 | 2021-12-02 | 2 | 2022-03-16 | 74 | 2022-03-17 | 1 | [26 empty] | 0 | [5 empty] | 2022-03-17 | 2022-03-25 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-17 | 2022-03-18 | 1 | 2022-03-25 |  | 2022-03-29 | 2 | 1//19
2539 | PGE | 93610 | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-11-30 | 2021-12-02 | 2 | 2021-12-02 | 2 | 2021-12-20 | 12 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | 2021-12-27 | 5 |  |  |  |  | 2021-11-30 | 2021-12-16 | 12 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2540 | PGE | 95540 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-30 | 2021-12-10 | 8 | 2021-12-10 | 8 | 2021-12-13 | 1 | [18 empty] | 2021-11-30 | 2021-11-30 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2541 | PGE | 94070 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 32.913 |  | 2021-11-30 | 2021-12-02 | 2 | 2022-03-29 | 83 | 2022-03-31 | 2 | [26 empty] | 0 | [5 empty] | 2022-03-31 | 2022-03-31 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-31 |  |  | 2022-03-31 |  | 2022-03-31 | 0 | 1//19
2542 | PGE | 93460 | NEM | EXPNEM | Implementation | Solar PV | 39.027 |  | 2021-12-01 | 2021-12-07 | 4 | 2021-12-15 | 10 | 2022-01-05 | 15 | [15 empty] | 2022-01-05 | 2022-01-05 | 0 | 2022-01-05 | 2022-02-15 | 28 |  |  |  |  | 2021-12-01 | 0 |  | 2021-12-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2543 | PGE | 95249 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 44.173 |  | 2021-12-01 | 2021-12-15 | 10 | 2021-12-27 | 18 | 2022-01-18 | 15 | [15 empty] | 2022-01-18 | 2022-02-04 | 13 | 2022-02-04 | [6 empty] | 2021-12-01 | 0 |  |  | 2022-02-04 | 2022-02-04 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2544 | PGE | 95249 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 35.22 |  | 2021-12-01 | 2021-12-15 | 10 | 2021-12-27 | 18 | 2022-01-18 | 15 | [15 empty] | 2022-01-18 | 2022-02-04 | 13 | 2022-02-04 | [6 empty] | 2021-12-01 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2545 | PGE | 95320 | NEM | EXPNEM | Study in Progress | Solar PV | 150 |  | 2021-12-01 | 2021-12-15 | 10 | 2022-01-07 | 27 | 2022-01-24 | 10 | 2022-01-24 | 2022-02-18 | 19 | 2022-02-18 | 2022-03-14 | 15 | 2022-03-14 | [18 empty] | 2021-12-01 | 0 |  | 2021-12-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2546 | PGE | 93420 | Non-NEM | Non-Export | IA in Progress | ENGN, Storage | 1530 |  | 2021-12-01 | 2021-12-02 | 1 | 2021-12-15 | 10 | 2022-01-27 | 30 | [15 empty] | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | [6 empty] | 2021-12-01 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2547 | PGE | 93711 | NEM | EXPNEM | Implementation | Solar PV | 81.78 |  | 2021-12-01 | 2021-12-03 | 2 | 2022-01-20 | 35 | 2022-01-28 | 6 | [15 empty] | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | 2022-02-01 | 2 | [5 empty] | 0 | [5 empty] | 2022-03-14 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-14 | 2022-03-30 | 12 |  |  |  |  | 1//19
2548 | PGE | 95037 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 53.188 |  | 2021-12-01 | 2021-12-15 | 10 | 2021-12-27 | 18 | 2022-02-25 | 42 | [15 empty] | 2022-02-25 | 2022-02-25 | 0 | 2022-02-25 | [6 empty] | 2021-12-01 | 0 |  |  | 2022-02-25 | 2022-02-25 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2549 | PGE | 95365 | NEM | EXPNEM | Implementation | Solar PV | 133.2 |  | 2021-12-01 | 2021-12-03 | 2 | 2022-01-03 | 23 | 2022-01-18 | 10 | 2022-01-18 | 2022-02-10 | 17 | [12 empty] | 2022-02-10 | 2022-02-10 | 0 | 2022-02-10 | 2022-02-17 | 5 |  |  |  |  | 2021-12-01 | 0 | [8 empty] | 2022-03-08 |  | 26 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2550 | PGE | 95037 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.179 |  | 2021-12-01 | 2021-12-15 | 10 | 2021-12-27 | 18 | 2022-01-18 | 15 | [15 empty] | 2022-01-18 | 2022-02-08 | 15 | 2022-02-08 | [6 empty] | 2021-12-01 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2551 | PGE | 93611 | NEM | EXPNEM | Implementation | Solar PV | 50 |  | 2021-12-01 | 2021-12-06 | 3 | 2022-02-14 | 52 | 2022-02-24 | 7 | [15 empty] | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-21 | 17 |  |  |  |  | 2021-12-01 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2552 | PGE | 94027 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 32.131 |  | 2021-12-01 | 2021-12-01 | 0 | 2022-02-18 | 56 | 2022-02-24 | 3 | [26 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2553 | PGE | 95642 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-12-01 | 2021-12-10 | 7 | 2021-12-10 | 7 | 2021-12-29 | 13 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 2021-12-29 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-12-10 |  | 2022-01-19 | 29 | 1//19
2554 | PGE | 94526 | Non-NEM | Inadvertent Export | Commercial | Storage | 5 |  | 2021-12-01 | 2021-12-07 | 4 | 2021-12-07 | 4 | 2021-12-21 | 10 | [15 empty] | 2021-12-21 | 2021-12-21 | 0 | 2021-12-21 | 2021-12-21 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-12-01 |  | 2021-12-21 | 15 | 1//19
2555 | PGE | 95668 | NEM | EXPNEM | Implementation | Solar PV | 66.6 |  | 2021-12-02 | 2021-12-03 | 1 | 2021-12-15 | 9 | 2021-12-29 | 10 | 2021-12-29 | 2022-02-17 | 35 | [12 empty] | 2022-02-17 | 2022-02-17 | 0 | 2022-02-17 | 2022-02-24 | 4 |  |  |  |  | 2021-12-14 | 0 | [8 empty] | 2022-03-21 |  | 17 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2556 | PGE | 94551 | NEM | EXPNEM | IA in Progress | Solar PV | 471.432 |  | 2021-12-02 | 2021-12-16 | 10 | 2021-12-16 | 10 | 2021-12-31 | 11 | [15 empty] | 2021-12-31 | 2022-01-24 | 15 | 2022-01-24 | [6 empty] | 2021-12-02 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2557 | PGE | 93245 | NEM | EXPNEM | Implementation | Solar PV | 44.006 |  | 2021-12-02 | 2021-12-03 | 1 | 2022-01-13 | 30 | 2022-01-26 | 8 | [15 empty] | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | 2022-01-27 | 1 |  |  |  |  | 2021-12-02 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2558 | PGE | 95932 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 58.705 |  | 2021-12-02 | 2021-12-14 | 8 | 2022-01-03 | 22 | 2022-01-25 | 15 | [15 empty] | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | [6 empty] | 2021-12-02 | 0 |  | 2021-12-14 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2559 | PGE | 95932 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 59.281 |  | 2021-12-02 | 2021-12-14 | 8 | 2022-01-03 | 22 | 2022-01-25 | 15 | [15 empty] | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | [6 empty] | 2021-12-02 | 0 |  | 2021-12-14 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2560 | PGE | 95932 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 70.44 |  | 2021-12-02 | 2021-12-14 | 8 | 2022-01-03 | 22 | 2022-01-25 | 15 | [15 empty] | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | [6 empty] | 2021-12-02 | 0 |  | 2021-12-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2561 | PGE | 95682 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 643.5 |  | 2021-12-02 | 2021-12-09 | 5 | 2021-12-29 | 19 | 2022-01-19 | 14 | [15 empty] | 2022-01-19 | 2022-01-19 | 0 | 2022-01-19 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2562 | PGE | 93311 | NEM | EXPNEM | Implementation | Solar PV | 400.816 |  | 2021-12-02 | 2021-12-07 | 3 | 2021-12-07 | 3 | 2022-01-05 | 21 | [15 empty] | 2022-01-05 | 2022-01-05 | 0 | 2022-01-05 | 2022-03-07 | 41 |  |  |  |  | 2021-12-02 | 0 |  | 2021-12-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2563 | PGE | 95131 | NEM | EXPNEM | IA in Progress | Solar PV | 476.175 |  | 2021-12-02 | 2021-12-06 | 2 | 2021-12-06 | 2 | 2021-12-20 | 10 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | [6 empty] | 2021-12-02 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2564 | PGE | 93436 | NEM | EXPNEM | Study in Progress | Solar PV | 200.408 |  | 2021-12-02 | 2021-12-08 | 4 | 2021-12-08 | 4 | [5 empty] | 2021-12-08 | 2022-01-05 | 20 | 2022-01-05 | [18 empty] | 2021-12-02 | 0 |  | 2021-12-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2565 | PGE | 95519 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-12-02 | 2021-12-06 | 2 | 2022-01-19 | 33 | 2022-01-20 | 1 | [18 empty] | 2021-11-01 | 2021-12-02 | 20 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2566 | PGE | 93662 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 31.381 |  | 2021-12-02 | 2021-12-07 | 3 | 2021-12-10 | 6 | 2021-12-31 | 15 | [15 empty] | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | [6 empty] | 2021-12-02 | 2021-12-27 | 17 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2567 | PGE | 95569 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 15 |  | 2021-12-02 | 2021-12-16 | 10 | 2021-12-16 | 10 | 2021-12-24 | 6 | [15 empty] | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16 | 2022-01-25 | 27 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2568 | PGE | 93940 | NEM | EXPNEM | Commercial | Solar PV | 43.78 |  | 2021-12-03 | 2021-12-17 | 10 | 2021-12-17 | 10 | 2022-01-07 | 15 | [15 empty] | 2022-01-07 | 2022-01-18 | 6 | 2022-01-18 | 2022-02-07 | 14 | [5 empty] | 0 | [5 empty] | 2022-02-07 | 2022-02-16 | 7 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-07 | 2022-02-07 | 0 | 2022-02-16 |  | 2022-02-18 | 2 | 1//19
2569 | PGE | 95677 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-12-03 | 2021-12-17 | 10 | 2022-01-03 | 21 | 2022-01-24 | 14 | [15 empty] | 2022-01-24 | 2022-01-24 | 0 | 2022-01-24 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2570 | PGE | 95945 | NEM | VNEM | Application Review in Progress | Solar PV | 46.32 |  | 2021-12-03 | 2021-12-07 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2571 | PGE | 95134 | NEM | EXPNEM | IA in Progress | Solar PV | 467.322 |  | 2021-12-03 | 2021-12-07 | 2 | 2021-12-07 | 2 | 2021-12-23 | 12 | [15 empty] | 2021-12-23 | 2022-01-11 | 13 | 2022-01-11 | [6 empty] | 2021-12-03 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2572 | PGE | 95963 | NEM | EXPNEM | Withdrawn | Solar PV | 100 |  | 2021-12-03 | 2021-12-07 | 2 | 2021-12-10 | 5 | 2021-12-29 | 13 | 2021-12-29 | [25 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2573 | PGE | 95963 | NEM | EXPNEM | Study in Progress | Solar PV | 241.711 |  | 2021-12-03 | 2021-12-07 | 2 | 2021-12-13 | 6 | 2021-12-29 | 12 | 2021-12-29 | 2022-02-23 | 38 | 2022-02-23 | 2022-03-21 | 18 | 2022-03-21 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2574 | PGE | 94611 | Non-NEM | Non-Export | Study in Progress | HYDR | 29.84 |  | 2021-12-03 | 2021-12-07 | 2 | 2021-12-07 | 2 | 2022-01-28 | 37 | 2022-02-07 | 2022-03-04 | 18 | 2022-03-14 | [22 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2575 | PGE | 94063 | NEM | EXPNEM | IA in Progress | Solar PV | 299.7 |  | 2021-12-03 | 2021-12-06 | 1 | 2021-12-22 | 13 | 2022-01-07 | 12 | [15 empty] | 2022-01-07 | 2022-01-07 | 0 | 2022-01-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2576 | PGE | 95963 | NEM | EXPNEM | Study in Progress | Solar PV | 491.397 |  | 2021-12-03 | 2021-12-07 | 2 | 2021-12-13 | 6 | 2021-12-29 | 12 | 2021-12-29 | 2022-02-23 | 38 | 2022-02-23 | 2022-03-21 | 18 | 2022-03-21 | [18 empty] | 2021-12-03 | 2021-12-29 | 18 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2577 | PGE | 95037 | NEM | EXPNEM | Withdrawn | Solar PV | 360 |  | 2021-12-03 | 2021-12-10 | 5 | 2021-12-10 | 5 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2578 | PGE | 95963 | NEM | EXPNEM | Study in Progress | Solar PV | 693.907 |  | 2021-12-03 | 2021-12-07 | 2 | 2021-12-15 | 8 | 2021-12-29 | 10 | 2021-12-29 | 2022-02-23 | 38 | 2022-02-23 | 2022-03-21 | 18 | 2022-03-21 | [18 empty] | 2021-12-03 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2579 | PGE | 94403 | NEM | EXPNEM | IA in Progress | Solar PV | 703.235 |  | 2021-12-03 | 2021-12-13 | 6 | 2022-01-03 | 21 | 2022-01-21 | 13 | [15 empty] | 2022-01-21 | 2022-01-25 | 2 | 2022-01-25 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2580 | PGE | 95521 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-12-03 | 2021-12-06 | 1 | 2022-01-19 | 32 | 2022-01-20 | 1 | [18 empty] | 2021-12-03 | 2021-12-03 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2581 | PGE | 95963 | NEM | EXPNEM | Study in Progress | Solar PV | 72.622 |  | 2021-12-03 | 2021-12-17 | 10 | 2022-01-25 | 36 | 2022-02-15 | 15 | 2022-02-15 | [25 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2582 | PGE | 94530 | NEM | EXPNEM | IA in Progress | Solar PV | 149.464 |  | 2021-12-03 | 2021-12-06 | 1 | 2021-12-06 | 1 | 2022-02-24 | 56 | [15 empty] | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2584 | PGE | 95521 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-12-03 | 2021-12-16 | 9 | 2021-12-16 | 9 | 2022-03-21 | 65 | [18 empty] | 2021-12-03 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2585 | PGE | 93420 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-12-04 | 2021-12-14 | 6 | 2021-12-14 | 6 | 2021-12-30 | 12 | [18 empty] | 2021-12-03 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2586 | PGE | 94611 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-12-04 | 2021-12-17 | 9 | 2021-12-27 | 15 | 2022-01-10 | 10 | [18 empty] | 2021-12-03 | 2021-12-04 | 0 | [5 empty] | 0 | [5 empty] | 2022-01-10 | 2022-01-10 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 |  | 2022-01-11 | 1 | 1//19
2587 | PGE | 95626 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 31.423 |  | 2021-12-04 | 2021-12-06 | 0 | 2021-12-06 | 0 | 2021-12-29 | 17 | [18 empty] | 2021-12-04 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2588 | PGE | 93422 | Non-NEM | Inadvertent Export | Withdrawn | Solar PV, Storage | 10 |  | 2021-12-04 | 2021-12-07 | 1 | [22 empty] | 2021-12-02 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2589 | PGE | 93426 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-12-04 | 2021-12-17 | 9 | 2021-12-17 | 9 | 2021-12-27 | 6 | [15 empty] | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27 | 2021-12-27 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2590 | PGE | 95973 | NEM | EXPNEM | Study in Progress | Solar PV | 187.5 |  | 2021-12-05 | 2021-12-10 | 4 | 2021-12-10 | 4 | 2021-12-29 | 13 | 2021-12-29 | 2022-03-01 | 42 | 2022-03-01 | 2022-03-25 | 18 | 2022-03-25 | [18 empty] | 2021-12-17 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2591 | PGE | 95973 | NEM | EXPNEM | Study in Progress | Solar PV | 187.5 |  | 2021-12-05 | 2021-12-10 | 4 | 2021-12-10 | 4 | 2021-12-29 | 13 | 2021-12-29 | 2022-03-01 | 42 | 2022-03-01 | 2022-03-25 | 18 | 2022-03-25 | [18 empty] | 2021-12-17 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2592 | PGE | 94565 | Non-NEM | Non-Export | Withdrawn | Solar PV, Storage | 5.76 |  | 2021-12-05 | 2021-12-17 | 9 | [22 empty] | 2021-12-05 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2593 | PGE | 93933 | NEM | EXPNEM | IA in Progress | Solar PV | 75 |  | 2021-12-06 | 2021-12-20 | 10 | 2021-12-27 | 15 | 2022-01-14 | 14 | [15 empty] | 2022-01-14 | 2022-01-14 | 0 | 2022-01-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2594 | PGE | 94403 | NEM | EXPNEM | IA in Progress | Solar PV | 124.395 |  | 2021-12-06 | 2021-12-20 | 10 | 2021-12-20 | 10 | 2022-02-24 | 46 | [15 empty] | 2022-02-24 | 2022-03-17 | 15 | 2022-03-17 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2595 | PGE | 94403 | NEM | EXPNEM | IA in Progress | Solar PV | 150 |  | 2021-12-06 | 2021-12-20 | 10 | 2021-12-20 | 10 | 2022-01-10 | 15 | [15 empty] | 2022-01-10 | 2022-01-31 | 14 | 2022-01-31 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2596 | PGE | 94402 | NEM | EXPNEM | IA in Progress | Solar PV | 199.8 |  | 2021-12-06 | 2021-12-20 | 10 | 2021-12-20 | 10 | 2022-01-10 | 15 | [15 empty] | 2022-01-10 | 2022-01-31 | 14 | 2022-01-31 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2597 | PGE | 94403 | NEM | EXPNEM | IA in Progress | Solar PV | 120.046 |  | 2021-12-06 | 2021-12-10 | 4 | 2021-12-10 | 4 | 2021-12-28 | 12 | 2021-12-20 | 2022-01-14 | 19 | [12 empty] | 2022-01-14 | 2022-02-03 | 13 | 2022-02-03 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2598 | PGE | 93933 | NEM | EXPNEM | Implementation | Solar PV | 115.42 |  | 2021-12-06 | 2021-12-06 | 0 | 2021-12-07 | 1 | 2022-01-11 | 25 | [15 empty] | 2022-01-11 | 2022-01-11 | 0 | 2022-01-11 | 2022-01-17 | 3 |  |  |  |  | 2021-12-06 | 0 | [5 empty] | 2022-01-18 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-18 | 2022-01-18 | 0 |  |  |  |  | 1//19
2599 | PGE | 94401 | NEM | EXPNEM | IA in Progress | Solar PV | 166.5 |  | 2021-12-06 | 2021-12-10 | 4 | 2021-12-10 | 4 | 2022-02-04 | 39 | [15 empty] | 2022-02-04 | 2022-02-04 | 0 | 2022-02-04 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2600 | PGE | 95134 | NEM | EXPNEM | IA in Progress | Solar PV | 626 |  | 2021-12-06 | 2021-12-20 | 10 | 2021-12-20 | 10 | 2022-01-10 | 15 | [15 empty] | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | [6 empty] | 2021-12-06 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2601 | PGE | 95023 | NEM | EXPNEM | Study in Progress | Solar PV | 437.5 |  | 2021-12-06 | 2021-12-07 | 1 | 2021-12-07 | 1 | 2021-12-22 | 11 | 2021-12-22 | 2022-02-17 | 40 | 2022-02-17 | 2022-03-11 | 15 | 2022-03-11 | [18 empty] | 2021-12-06 | 2021-12-16 | 8 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2602 | PGE | 94402 | NEM | EXPNEM | IA in Progress | Solar PV | 150 |  | 2021-12-06 | 2021-12-10 | 4 | 2021-12-10 | 4 | 2021-12-21 | 7 | [15 empty] | 2021-12-21 | 2022-01-07 | 13 | 2022-01-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2603 | PGE | 94401 | NEM | EXPNEM | Study in Progress | Solar PV | 187.5 |  | 2021-12-06 | 2021-12-08 | 2 | 2021-12-09 | 3 | 2022-03-14 | 65 | 2022-03-14 | [25 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2604 | PGE | 93204 | NEM | EXPNEM | Study in Progress | Solar PV | 150 |  | 2021-12-06 | 2021-12-07 | 1 | 2022-01-12 | 27 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2605 | PGE | 93446 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-12-06 | 2021-12-07 | 1 | 2021-12-07 | 1 | 2021-12-23 | 12 | [18 empty] | 2021-12-06 | 2021-12-06 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2606 | PGE | 93307 | NEM | EXPNEM | IA in Progress | Solar PV | 75.259 |  | 2021-12-06 | 2021-12-07 | 1 | 2021-12-15 | 7 | 2021-12-29 | 10 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2607 | PGE | 93637 | NEM | EXPNEM | Implementation | Solar PV | 39.899 |  | 2021-12-06 | 2021-12-08 | 2 | 2021-12-08 | 2 | 2021-12-23 | 11 | [15 empty] | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23 | 2022-01-13 | 15 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2608 | PGE | 95685 | NEM | VNEM | Implementation | Solar PV | 45.661 |  | 2021-12-06 | 2021-12-07 | 1 | 2021-12-31 | 19 | 2022-01-20 | 13 | [15 empty] | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | 2022-02-04 | 11 | [5 empty] | 0 |  |  | 2022-01-20 | 2022-01-20 | 0 | 2022-03-23 | 2022-03-30 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-23 | 2022-03-24 | 1 | 2022-03-30 |  |  |  | 1//19
2609 | PGE | 93704 | NEM | EXPNEM | Implementation | Solar PV | 179.156 |  | 2021-12-06 | 2021-12-08 | 2 | 2021-12-20 | 10 | 2021-12-29 | 7 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 2022-03-10 | 49 |  |  |  |  | 2021-12-06 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2610 | PGE | 95065 | NEM | EXPNEM | IA in Progress | Solar PV | 63.722 |  | 2021-12-06 | 2021-12-08 | 2 | 2021-12-08 | 2 | 2022-01-19 | 29 | [15 empty] | 2022-01-19 | 2022-01-19 | 0 | 2022-01-19 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2611 | PGE | 93960 | NEM | EXPNEM | Study in Progress | Solar PV | 801.632 |  | 2021-12-06 | 2021-12-08 | 2 | 2021-12-08 | 2 | [5 empty] | 2021-12-15 | 2022-01-14 | 22 | 2022-01-14 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2612 | PGE | 95073 | NEM | EXPNEM | IA in Progress | Solar PV | 64.88 |  | 2021-12-06 | 2021-12-08 | 2 | 2021-12-08 | 2 | 2022-01-19 | 29 | [15 empty] | 2022-01-19 | 2022-01-19 | 0 | 2022-01-19 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2613 | PGE | 94568 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 687.611 |  | 2021-12-06 | 2021-12-16 | 8 | 2022-01-26 | 36 | 2022-03-16 | 34 | [15 empty] | 2022-03-16 | 2022-03-18 | 2 | 2022-03-18 | [6 empty] | 2021-12-06 | 0 |  | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2614 | PGE | 93660 | Non-NEM | RESBCT | Study in Progress | Solar PV | 988.418 |  | 2021-12-06 | 2021-12-06 | 0 | 2021-12-22 | 12 | [5 empty] | 2021-12-22 | 2022-01-12 | 15 | 2022-01-12 | 2022-01-17 | 2 | 2022-01-27 |  |  | 2022-01-17 | 2022-01-18 | 0 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2615 | PGE | 93638 | NEM | EXPNEM | Withdrawn | Solar PV | 166.5 |  | 2021-12-06 | 2021-12-10 | 4 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2616 | PGE | 93622 | NEM | EXPNEM | Study in Progress | Solar PV | 972.915 |  | 2021-12-06 | 2021-12-07 | 1 | 2022-01-18 | 30 | 2022-02-01 | 10 | 2022-02-01 | 2022-02-25 | 17 | 2022-02-25 | 2022-03-18 | 15 | 2022-03-18 | [18 empty] | 2021-12-06 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2617 | PGE | 95133 | NEM | EXPNEM | IA in Progress | Solar PV | 126.414 |  | 2021-12-06 | 2021-12-08 | 2 | 2021-12-08 | 2 | 2021-12-24 | 12 | [15 empty] | 2021-12-24 | 2021-12-24 | 0 | 2021-12-24 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2618 | PGE | 95033 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 30.729 |  | 2021-12-06 | 2021-12-08 | 2 | 2022-02-04 | 43 | 2022-02-07 | 1 | [18 empty] | 2021-12-06 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2619 | PGE | 95376 | NEM | EXPNEM | IA in Progress | Solar PV | 150 |  | 2021-12-07 | 2021-12-21 | 10 | 2022-01-04 | 20 | 2022-01-26 | 15 | [15 empty] | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2620 | PGE | 95361 | NEM | EXPNEM | Study in Progress | Solar PV | 246.616 |  | 2021-12-07 | 2021-12-10 | 3 | 2021-12-10 | 3 | 2022-02-18 | 49 | 2022-02-18 | 2022-03-17 | 18 | 2022-03-17 | [21 empty] | 2022-02-04 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2621 | PGE | 94609 | NEM | EXPNEM | Study in Progress | Solar PV | 44.884 |  | 2021-12-07 | 2021-12-20 | 9 | 2022-03-21 | 72 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2622 | PGE | 95361 | NEM | EXPNEM | Application Accepted | Solar PV | 83.3 |  | 2021-12-07 | 2021-12-10 | 3 | 2022-02-02 | 40 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2623 | PGE | 95134 | NEM | EXPNEM | IA in Progress | Solar PV | 540 |  | 2021-12-07 | 2021-12-20 | 9 | 2022-01-18 | 29 | 2022-02-07 | 14 | [15 empty] | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | [6 empty] | 2021-12-07 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2624 | PGE | 95361 | NEM | EXPNEM | Study in Progress | Solar PV | 33.3 |  | 2021-12-07 | 2021-12-10 | 3 | 2021-12-10 | 3 | 2022-02-18 | 49 | 2022-02-18 | 2022-03-17 | 18 | 2022-03-17 | [21 empty] | 2022-02-04 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2625 | PGE | 95134 | NEM | EXPNEM | IA in Progress | Solar PV | 852 |  | 2021-12-07 | 2021-12-21 | 10 | 2021-12-21 | 10 | 2022-01-10 | 14 | [15 empty] | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | [6 empty] | 2021-12-07 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2626 | PGE | 94574 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.857 |  | 2021-12-07 | 2021-12-07 | 0 | 2021-12-09 | 2 | 2021-12-09 | 0 | [18 empty] | 2021-12-07 | [7 empty] | 0 | [5 empty] | 2021-12-16 | 2021-12-16 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2021-12-16 |  |  | 2021-12-16 |  | 2021-12-16 | 0 | 1//19
2627 | PGE | 93610 | NEM | EXPNEM | Implementation | Solar PV | 660 |  | 2021-12-07 | 2021-12-10 | 3 | 2021-12-13 | 4 | 2022-02-03 | 37 | [15 empty] | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | 2022-02-10 | 5 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2628 | PGE | 95926 | NEM | EXPNEM | Study in Progress | Solar PV | 875 |  | 2021-12-07 | 2021-12-08 | 1 | 2022-01-05 | 21 | 2022-01-20 | 10 | 2022-01-20 | 2022-03-11 | 35 | 2022-03-11 | 2022-03-28 | 11 | 2022-03-28 | 2022-03-28 | 0 |  |  |  | 2022-03-28 | [12 empty] | 2021-12-07 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2629 | PGE | 93420 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-12-07 | 2021-12-08 | 1 | 2021-12-08 | 1 | 2021-12-24 | 12 | [18 empty] | 2021-12-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-02-25 |  | 2022-02-25 | 1 | 1//19
2630 | PGE | 95073 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 40.175 |  | 2021-12-08 | 2021-12-09 | 1 | 2022-02-04 | 41 | 2022-02-08 | 2 | [18 empty] | 2021-12-08 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2631 | PGE | 93304 | NEM | EXPNEM | IA in Progress | Solar PV | 150 |  | 2021-12-08 | 2021-12-22 | 10 | 2021-12-22 | 10 | 2022-01-12 | 15 | [15 empty] | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2632 | PGE | 95695 | NEM | EXPNEM | Implementation | Solar PV | 33.06 |  | 2021-12-08 | 2021-12-14 | 4 | 2021-12-14 | 4 | 2022-02-11 | 42 | [15 empty] | 2022-02-11 | 2022-02-15 | 2 | 2022-02-15 | 2022-02-15 | 0 |  |  |  |  | 2021-12-08 | 0 |  | 2021-12-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2633 | PGE | 93401 | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2021-12-08 | 2021-12-09 | 1 | 2021-12-09 | 1 | 2022-01-13 | 25 | [15 empty] | 2022-01-13 | 2022-01-13 | 0 | 2022-01-13 | 2022-01-24 | 6 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2634 | PGE | 93280 | NEM | EXPNEM | Implementation | Solar PV | 501.02 |  | 2021-12-08 | 2021-12-14 | 4 | 2021-12-16 | 6 | 2022-01-04 | 13 | [15 empty] | 2022-01-04 | 2022-01-13 | 7 | 2022-01-13 | 2022-01-27 | 9 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2635 | PGE | 93304 | NEM | EXPNEM | IA in Progress | Solar PV | 73.553 |  | 2021-12-08 | 2021-12-08 | 0 | 2022-01-27 | 35 | 2022-01-31 | 2 | [15 empty] | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2636 | PGE | 93405 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-12-08 | 2021-12-14 | 4 | 2021-12-14 | 4 | 2021-12-29 | 11 | [18 empty] | 2021-12-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2637 | PGE | 93638 | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2021-12-08 | 2021-12-09 | 1 | 2021-12-10 | 2 | 2021-12-23 | 9 | 2021-12-23 | 2022-01-18 | 17 | [12 empty] | 2022-01-18 | 2022-01-18 | 0 | 2022-01-18 | 2022-01-27 | 7 |  |  |  |  | 2021-12-10 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2638 | PGE | 95928 | NEM | EXPNEM | IA in Progress | Solar PV | 260 |  | 2021-12-08 | 2021-12-10 | 2 | 2022-02-17 | 50 | 2022-03-07 | 11 | [15 empty] | 2022-03-07 | 2022-03-07 | 0 | 2022-03-07 | [6 empty] | 2022-02-08 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2639 | PGE | 95492 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 36.3 |  | 2021-12-08 | 2021-12-09 | 1 | 2022-03-19 | 70 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2640 | PGE | 95338 | NEM | EXPNEM | IA in Progress | Solar PV | 36 |  | 2021-12-08 | 2021-12-21 | 9 | 2021-12-21 | 9 | 2022-03-31 | 70 | [15 empty] | 2022-03-31 | [9 empty] | 2021-12-08 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2641 | PGE | 93654 | NEM | NEMMT | Study in Progress | ENGN, Solar PV, Storage | 2744.5 |  | 2021-12-08 | 2021-12-09 | 1 | 2021-12-29 | 15 | [5 empty] | 2021-12-29 | 2022-01-27 | 20 | 2022-01-27 | 2022-02-02 | 4 | 2022-02-09 |  |  | 2022-02-02 | 2022-02-02 | 0 | [10 empty] | 2021-12-08 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2642 | PGE | 94103 | Non-NEM | Inadvertent Export | Withdrawn | Solar PV | 130.635 |  | 2021-12-08 | 2021-12-21 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2643 | PGE | 94530 | NEM | EXPNEM | Implementation | Solar PV | 53.35 |  | 2021-12-08 | 2021-12-22 | 10 | 2021-12-22 | 10 | 2022-01-12 | 15 | [15 empty] | 2022-01-12 | 2022-02-03 | 15 | 2022-02-03 | 2022-02-13 | 6 |  |  |  |  | 2021-12-08 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2644 | PGE | 94539 | NEM | EXPNEM | IA in Progress | Solar PV | 33.128 |  | 2021-12-08 | 2021-12-22 | 10 | 2021-12-22 | 10 | 2022-01-05 | 10 | [15 empty] | 2022-01-05 | 2022-01-18 | 8 | 2022-01-18 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2645 | PGE | 94598 | Non-NEM | Non-Export | Withdrawn | Storage | 7.68 |  | 2021-12-08 | 2021-12-09 | 1 | [22 empty] | 2021-12-08 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2646 | PGE | 94577 | NEM | EXPNEM | Study in Progress | Solar PV | 39.832 |  | 2021-12-08 | 2021-12-13 | 3 | 2021-12-13 | 3 | [28 empty] | 0 |  | 2022-01-11 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2647 | PGE | 95320 | NEM | EXPNEM | Study in Progress | Solar PV | 840 |  | 2021-12-08 | 2021-12-13 | 3 | 2021-12-13 | 3 | 2022-01-11 | 21 | 2022-01-11 | 2022-02-04 | 17 | 2022-02-04 | 2022-02-28 | 15 | 2022-02-28 | 2022-02-28 | 0 | 2022-03-01 |  |  | 2022-02-28 | 2022-02-28 | 0 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2648 | PGE | 94559 | NEM | EXPNEM | Implementation | Solar PV | 360 |  | 2021-12-08 | 2021-12-13 | 3 | 2021-12-13 | 3 | 2022-01-21 | 28 | [15 empty] | 2022-01-21 | 2022-01-27 | 4 | 2022-01-27 | 2022-01-27 | 0 |  |  |  |  | 2021-12-08 | 0 |  | 2021-12-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2649 | PGE | 93401 | NEM | VNEM | Application Review in Progress | Solar PV | 68.13 |  | 2021-12-08 | 2021-12-10 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2650 | PGE | 95242 | NEM | EXPNEM | IA in Progress | Solar PV | 333 |  | 2021-12-08 | 2021-12-22 | 10 | 2022-02-01 | 38 | 2022-03-23 | 35 | [15 empty] | 2022-03-23 | 2022-03-28 | 3 | 2022-03-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2651 | PGE | 95215 | NEM | EXPNEM | Study in Progress | Solar PV | 576 |  | 2021-12-08 | 2021-12-15 | 5 | 2022-01-12 | 25 | 2022-02-01 | 13 | 2022-02-01 | 2022-02-28 | 18 | 2022-02-28 | 2022-03-24 | 18 | 2022-03-24 | 2022-03-24 | 0 | 2022-03-24 |  |  | 2022-03-24 | 2022-03-24 | 0 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2652 | PGE | 95215 | NEM | EXPNEM | IA in Progress | Solar PV | 360 |  | 2021-12-08 | 2021-12-14 | 4 | 2022-02-07 | 42 | 2022-03-01 | 15 | [15 empty] | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2653 | PGE | 93301 | NEM | EXPNEM | IA in Progress | Solar PV | 185.259 |  | 2021-12-08 | 2021-12-10 | 2 | 2021-12-10 | 2 | 2021-12-20 | 6 | [15 empty] | 2021-12-20 | 2022-01-06 | 13 | 2022-01-06 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2654 | PGE | 94124 | Non-NEM | Non-Export | Study in Progress | Solar PV | 26.598 |  | 2021-12-08 | 2021-12-22 | 10 | 2022-03-03 | 59 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2655 | PGE | 95476 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.743 |  | 2021-12-08 | 2021-12-09 | 1 | 2021-12-09 | 1 | 2021-12-09 | 0 | [18 empty] | 2021-12-08 | [6 empty] | 2021-12-08 | 0 | [5 empty] | 2022-03-22 | 2022-03-25 | 3 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-22 | 2022-03-25 | 3 | 2022-03-25 |  | 2022-03-28 | 1 | 1//19
2656 | PGE | 95482 | NEM | EXPNEM | Study in Progress | Solar PV | 655.386 |  | 2021-12-08 | 2021-12-22 | 10 | 2022-02-04 | 41 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2657 | PGE | 95076 | NEM | EXPNEM | Withdrawn | Solar PV | 625 |  | 2021-12-08 | 0 | [31 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2658 | PGE | 94515 | NEM | EXPNEM | IA in Progress | Solar PV | 127.882 |  | 2021-12-08 | 2021-12-20 | 8 | 2022-01-06 | 21 | 2022-02-15 | 27 | [15 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | [6 empty] | 2021-12-08 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2659 | PGE | 95926 | NEM | EXPNEM | Study in Progress | Solar PV | 875 |  | 2021-12-08 | 2021-12-21 | 9 | 2022-03-09 | 63 | 2022-03-23 | 10 | 2022-03-23 | 2022-03-24 | 1 | 2022-03-09 | 2022-03-24 | 11 | 2022-03-24 | 2022-03-28 | 2 |  |  |  | 2022-03-28 | [12 empty] | 2021-12-08 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2660 | PGE | 95482 | NEM | EXPNEM | Implementation | Solar PV | 346.047 |  | 2021-12-08 | 2021-12-22 | 10 | 2022-01-21 | 31 | 2022-02-08 | 12 | [15 empty] | 2022-02-08 | 2022-02-08 | 0 | 2022-02-08 | 2022-02-28 | 13 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2661 | PGE | 95973 | NEM | EXPNEM | Study in Progress | Solar PV | 875 |  | 2021-12-08 | 2021-12-21 | 9 | 2021-12-21 | 9 | 2022-01-04 | 10 | 2022-01-04 | 2022-03-09 | 44 | 2022-03-09 | 2022-03-24 | 11 | 2022-03-24 | [18 empty] | 2021-12-08 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2662 | PGE | 96080 | NEM | EXPNEM | Application Review in Progress | Solar PV | 437.5 |  | 2021-12-08 | 2021-12-21 | 9 | [29 empty] | 2021-12-08 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2663 | PGE | 95938 | NEM | EXPNEM | IA in Progress | Solar PV | 500 |  | 2021-12-08 | 2021-12-22 | 10 | 2022-01-04 | 19 | 2022-01-26 | 15 | 2022-01-26 | 2022-03-31 | 45 | [12 empty] | 2022-03-31 | [9 empty] | 2021-12-08 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2664 | PGE | 94087 | NEM | EXPNEM | IA in Progress | Solar PV | 157.519 |  | 2021-12-08 | 2021-12-22 | 10 | 2021-12-28 | 14 | 2022-02-11 | 32 | [15 empty] | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2665 | PGE | 93280 | NEM | EXPNEM | Study in Progress | Solar PV | 150 |  | 2021-12-09 | 2021-12-13 | 2 | 2021-12-14 | 3 | [5 empty] | 2021-12-14 | 2022-01-10 | 19 | 2022-01-10 | [18 empty] | 2021-12-09 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2666 | PGE | 95758 | Non-NEM | RESBCT | Withdrawn | Solar PV | 5000 |  | 2021-12-09 | 0 | [31 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2667 | PGE | 94087 | NEM | EXPNEM | IA in Progress | Solar PV | 211.572 |  | 2021-12-09 | 2021-12-15 | 4 | 2021-12-15 | 4 | 2021-12-29 | 10 | [15 empty] | 2021-12-29 | 2022-01-14 | 12 | 2022-01-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2668 | PGE | 93401 | NEM | EXPNEM | IA in Progress | Solar PV | 101.249 |  | 2021-12-09 | 2021-12-15 | 4 | 2021-12-15 | 4 | 2022-01-03 | 13 | [15 empty] | 2022-01-03 | 2022-01-24 | 14 | 2022-01-24 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2669 | PGE | 95962 | Non-NEM | RESBCT | IA in Progress | HYDR |  |  | 2021-12-02 | 2021-12-03 | 1 | 2021-12-07 | 3 | [17 empty] | 2021-12-07 | 2021-12-10 | 3 | 2021-12-10 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2670 | PGE | 95076 | NEM | EXPNEM | IA in Progress | Solar PV | 150 |  | 2021-12-09 | 2021-12-13 | 2 | 2022-01-03 | 17 | 2022-01-25 | 15 | [15 empty] | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2671 | PGE | 95060 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-12-09 | 2021-12-14 | 3 | 2021-12-20 | 7 | 2022-01-13 | 18 | [15 empty] | 2022-01-13 | 2022-01-13 | 0 | 2022-01-13 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2672 | PGE | 95207 | NEM | VNEM | IA in Progress | Solar PV | 300 |  | 2021-12-09 | 2021-12-13 | 2 | 2021-12-31 | 16 | 2022-01-20 | 13 | [15 empty] | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2673 | PGE | 93725 | NEM | EXPNEM | Study in Progress | Solar PV | 1500 |  | 2021-12-09 | 2021-12-13 | 2 | 2022-02-24 | 53 | 2022-03-11 | 11 | 2022-03-29 | [25 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2674 | PGE | 95688 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-12-09 | 2021-12-13 | 2 | 2021-12-15 | 4 | 2021-12-30 | 11 | [15 empty] | 2021-12-30 | 2022-01-05 | 4 | 2022-01-05 | [6 empty] | 2022-01-05 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2675 | PGE | 94062 | NEM | EXPNEM | IA in Progress | Solar PV | 517.216 |  | 2021-12-09 | 2021-12-14 | 3 | 2022-01-04 | 18 | 2022-01-21 | 12 | [15 empty] | 2022-01-21 | 2022-01-24 | 1 | 2022-01-24 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2676 | PGE | 95119 | NEM | EXPNEM | Implementation | Solar PV | 83.3 |  | 2021-12-09 | 2021-12-15 | 4 | 2021-12-15 | 4 | 2021-12-30 | 11 | [15 empty] | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-03-28 | 60 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2677 | PGE | 95688 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-12-09 | 2021-12-23 | 10 | 2021-12-23 | 10 | 2022-01-20 | 19 | [15 empty] | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2678 | PGE | 95687 | NEM | EXPNEM | IA in Progress | Solar PV | 170 |  | 2021-12-09 | 2021-12-23 | 10 | 2021-12-23 | 10 | 2022-01-20 | 19 | [15 empty] | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2679 | PGE | 93706 | NEM | EXPNEM | Implementation | Solar PV | 57.687 |  | 2021-12-09 | 2021-12-13 | 2 | 2021-12-16 | 5 | 2021-12-22 | 4 | [15 empty] | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22 | 2022-03-31 | 69 | [5 empty] | 0 | [8 empty] | 2022-01-31 |  | 52 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2680 | PGE | 95112 | NEM | EXPNEM | IA in Progress | Solar PV | 75 |  | 2021-12-09 | 2021-12-15 | 4 | 2022-03-02 | 57 | 2022-03-22 | 14 | [15 empty] | 2022-03-22 | 2022-03-22 | 0 | 2022-03-22 | [6 empty] | 2021-12-09 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2681 | PGE | 94063 | NEM | EXPNEM | IA in Progress | Solar PV | 322.016 |  | 2021-12-09 | 2021-12-17 | 6 | 2022-01-04 | 18 | 2022-03-02 | 39 | [15 empty] | 2022-03-02 | 2022-03-02 | 0 | 2022-03-02 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2682 | PGE | 95688 | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2021-12-09 | 2021-12-13 | 2 | 2021-12-15 | 4 | 2021-12-30 | 11 | [15 empty] | 2021-12-30 | 2022-01-05 | 4 | 2022-01-05 | [6 empty] | 2022-01-05 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2683 | PGE | 95688 | NEM | EXPNEM | IA in Progress | Solar PV | 96 |  | 2021-12-09 | 2021-12-10 | 1 | 2021-12-13 | 2 | 2021-12-29 | 12 | [15 empty] | 2021-12-29 | 2022-01-05 | 5 | 2022-01-05 | [6 empty] | 2022-01-05 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2684 | PGE | 95688 | NEM | EXPNEM | IA in Progress | Solar PV | 156 |  | 2021-12-09 | 2021-12-23 | 10 | 2021-12-23 | 10 | 2022-01-20 | 19 | [15 empty] | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2685 | PGE | 95687 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-12-09 | 2021-12-23 | 10 | 2021-12-23 | 10 | 2022-01-21 | 20 | [15 empty] | 2022-01-21 | 2022-01-21 | 0 | 2022-01-21 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2686 | PGE | 95131 | NEM | EXPNEM | IA in Progress | Solar PV | 133.2 |  | 2021-12-09 | 2021-12-15 | 4 | 2021-12-15 | 4 | 2021-12-31 | 12 | [15 empty] | 2021-12-31 | 2022-01-19 | 12 | 2022-01-19 | [6 empty] | 2021-12-09 | 0 |  | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2687 | PGE | 96092 | NEM | EXPNEM | Study in Progress | Solar PV | 250 |  | 2021-12-10 | 2021-12-24 | 10 | 2022-01-21 | 29 | 2022-02-08 | 12 | 2022-02-08 | 2022-03-21 | 28 | 2022-03-21 | 2022-03-21 | 0 | 2022-03-21 | [18 empty] | 2021-12-10 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2688 | PGE | 96092 | NEM | EXPNEM | Study in Progress | Solar PV | 62.5 |  | 2021-12-10 | 2021-12-24 | 10 | 2021-12-24 | 10 | 2022-01-14 | 15 | 2022-01-14 | 2022-03-21 | 44 | 2022-03-21 | 2022-03-28 | 5 | 2022-03-28 | [18 empty] | 2021-12-10 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2689 | PGE | 96092 | NEM | EXPNEM | Study in Progress | Solar PV | 125 |  | 2021-12-10 | 2021-12-24 | 10 | 2022-01-21 | 29 | 2022-02-08 | 12 | 2022-02-08 | 2022-03-21 | 28 | 2022-03-21 | 2022-03-28 | 5 | 2022-03-28 | [18 empty] | 2021-12-10 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2690 | PGE | 95901 | NEM | EXPNEM | IA in Progress | Solar PV | 437.5 |  | 2021-12-10 | 2021-12-24 | 10 | 2022-02-07 | 40 | 2022-03-01 | 15 | [15 empty] | 2022-03-01 | 2022-03-22 | 15 | 2022-03-22 | [6 empty] | 2021-12-10 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2691 | PGE | 96080 | NEM | EXPNEM | IA in Progress | Solar PV | 375 |  | 2021-12-10 | 2021-12-24 | 10 | 2022-02-07 | 40 | 2022-03-01 | 15 | [15 empty] | 2022-03-01 | 2022-03-22 | 15 | 2022-03-22 | [6 empty] | 2021-12-10 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2692 | PGE | 95695 | NEM | EXPNEM | Study in Progress | Solar PV | 562.5 |  | 2021-12-10 | 2021-12-14 | 2 | 2022-01-04 | 17 | 2022-01-20 | 11 | 2022-01-20 | 2022-03-21 | 41 | 2022-03-21 | [21 empty] | 2021-12-10 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2693 | PGE | 95973 | NEM | EXPNEM | Study in Progress | Solar PV | 312.5 |  | 2021-12-10 | 2021-12-17 | 5 | 2021-12-27 | 11 | 2022-01-10 | 10 | 2022-01-10 | 2022-03-11 | 42 | 2022-03-11 | [21 empty] | 2021-12-10 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2694 | PGE | 95076 | NEM | EXPNEM | Application Accepted | Solar PV | 995.7 |  | 2021-12-10 | 2021-12-15 | 3 | 2022-02-16 | 47 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2695 | PGE | 93455 | NEM | EXPNEM | Commercial | Solar PV | 47.337 |  | 2021-12-10 | 2021-12-15 | 3 | 2021-12-15 | 3 | 2022-01-21 | 26 | [15 empty] | 2022-01-21 | 2022-01-21 | 0 | 2022-01-21 | 2022-01-21 | 0 | [5 empty] | 0 | [5 empty] | 2022-01-21 | 2022-02-02 | 8 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-21 | 2022-01-24 | 1 | 2022-02-02 |  | 2022-02-02 | 0 | 1//19
2696 | PGE | 95525 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-12-10 | 2021-12-14 | 2 | 2021-12-14 | 2 | 2021-12-22 | 6 | [15 empty] | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22 | 2021-12-22 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2697 | PGE | 95917 | NEM | EXPNEM | IA in Progress | Solar PV | 51.829 |  | 2021-12-10 | 2021-12-24 | 10 | 2021-12-24 | 10 | 2022-01-11 | 12 | [15 empty] | 2022-01-11 | 2022-02-02 | 15 | 2022-02-02 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2698 | PGE | 93206 | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2021-12-10 | 2021-12-20 | 6 | 2022-02-23 | 51 | 2022-03-10 | 11 | [15 empty] | 2022-03-10 | 2022-03-10 | 0 | 2022-03-10 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2699 | PGE | 95917 | NEM | EXPNEM | IA in Progress | Solar PV | 31.102 |  | 2021-12-10 | 2021-12-24 | 10 | 2021-12-24 | 10 | 2022-01-11 | 12 | [15 empty] | 2022-01-11 | 2022-02-02 | 15 | 2022-02-02 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2700 | PGE | 93308 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-12-10 | 2021-12-14 | 2 | 2021-12-27 | 11 | 2022-01-10 | 10 | [15 empty] | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | 2022-01-10 | 0 |  |  |  |  | 2021-12-27 | 0 | [5 empty] | 2022-03-08 | 2022-03-16 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-08 | 2022-03-14 | 4 | 2022-03-16 |  | 2022-03-17 | 1 | 1//19
2701 | PGE | 95320 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 514.6 |  | 2021-12-10 | 2021-12-22 | 8 | 2022-01-19 | 27 | 2022-02-24 | 25 | [25 empty] | 2021-12-10 | 0 |  | 2022-01-21 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2702 | PGE | 93706 | NEM | EXPNEM | Implementation | Solar PV | 209.791 |  | 2021-12-10 | 2021-12-21 | 7 | 2022-01-04 | 17 | 2022-01-19 | 10 | [15 empty] | 2022-01-19 | 2022-01-19 | 0 | 2022-01-19 | 2022-02-14 | 18 | [5 empty] | 0 | [8 empty] | 2022-03-21 |  | 17 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2703 | PGE | 94402 | NEM | EXPNEM | Application Review in Progress | Solar PV | 364.601 |  | 2021-12-10 | 2021-12-22 | 8 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2704 | PGE | 95117 | Non-NEM | Non-Export | IA in Progress | Solar PV | 34.65 |  | 2021-12-11 | 2021-12-11 | 0 | 2021-12-15 | 2 | 2022-02-08 | 38 | [15 empty] | 2022-02-08 | 2022-02-08 | 0 | 2022-02-08 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2705 | PGE | 94546 | NEM | EXPNEM | Application Review in Progress | Solar PV | 50.682 |  | 2021-12-12 | 2021-12-16 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2706 | PGE | 94303 | NEM | EXPNEM | Application Review in Progress | Solar PV | 36.762 |  | 2021-12-12 | 2021-12-15 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2707 | PGE | 94806 | NEM | EXPNEM | Application Review in Progress | Solar PV | 61.746 |  | 2021-12-12 | 2021-12-16 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2708 | PGE | 94014 | NEM | EXPNEM | Application Review in Progress | Solar PV | 32.479 |  | 2021-12-12 | 2021-12-14 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2709 | PGE | 94103 | NEM | EXPNEM | Application Review in Progress | Solar PV | 88.515 |  | 2021-12-12 | 2021-12-14 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2710 | PGE | 94704 | NEM | EXPNEM | Application Review in Progress | Solar PV | 92.441 |  | 2021-12-12 | 2021-12-14 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2711 | PGE | 95123 | NEM | EXPNEM | Application Review in Progress | Solar PV | 39.261 |  | 2021-12-12 | 2021-12-15 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2712 | PGE | 94118 | NEM | EXPNEM | Application Review in Progress | Solar PV | 88.515 |  | 2021-12-12 | 2021-12-14 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2713 | PGE | 94520 | NEM | EXPNEM | Application Review in Progress | Solar PV | 45.328 |  | 2021-12-12 | 2021-12-14 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2714 | PGE | 95076 | NEM | EXPNEM | Implementation | Solar PV | 125 |  | 2021-12-13 | 2021-12-14 | 1 | 2021-12-22 | 7 | 2022-01-14 | 17 | [15 empty] | 2022-01-14 | 2022-01-14 | 0 | 2022-01-14 | 2022-02-10 | 18 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2715 | PGE | 95012 | NEM | EXPNEM | IA in Progress | Solar PV | 240 |  | 2021-12-13 | 2021-12-14 | 1 | 2021-12-22 | 7 | 2022-01-20 | 20 | [15 empty] | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2716 | PGE | 94960 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.232 |  | 2021-12-13 | 2021-12-13 | 0 | 2022-01-28 | 33 | 2022-01-31 | 1 | [18 empty] | 2021-12-13 | [7 empty] | 0 | [5 empty] | 2022-01-31 | 2022-01-31 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-31 |  |  | 2022-01-31 |  | 2022-01-31 | 0 | 1//19
2717 | PGE | 95062 | NEM | EXPNEM | Implementation | Solar PV | 30.023 |  | 2021-12-13 | 2021-12-21 | 6 | 2022-01-25 | 30 | 2022-02-09 | 11 | [15 empty] | 2022-02-09 | 2022-02-09 | 0 | 2022-02-09 | 2022-02-17 | 6 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2718 | PGE | 93455 | NEM | EXPNEM | IA in Progress | Solar PV | 179.1 |  | 2021-12-13 | 2021-12-27 | 10 | 2022-01-10 | 20 | 2022-01-26 | 11 | [15 empty] | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2719 | PGE | 93422 | NEM | EXPNEM | Implementation | Micro Turbine, Solar PV | 66.6 |  | 2021-12-13 | 2021-12-13 | 0 | 2021-12-15 | 2 | 2022-01-03 | 13 | [15 empty] | 2022-01-03 | 2022-01-03 | 0 | 2022-01-03 | 2022-01-06 | 3 |  |  |  |  | 2021-12-13 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2720 | PGE | 93420 | Non-NEM | Break Before Make | Withdrawn | Storage | 10 |  | 2021-12-13 | 2021-12-27 | 10 | [22 empty] | 2021-11-02 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2721 | PGE | 94566 | NEM | EXPNEM | Implementation | Solar PV | 53.35 |  | 2021-12-13 | 2021-12-27 | 10 | 2021-12-27 | 10 | 2022-02-25 | 42 | [15 empty] | 2022-02-25 | 2022-02-25 | 0 | 2022-02-25 | 2022-03-03 | 4 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2722 | PGE | 95333 | NEM | EXPNEM | Implementation | Solar PV | 437.5 |  | 2021-12-13 | 2021-12-27 | 10 | 2022-01-28 | 33 | 2022-02-15 | 12 | [15 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | 2022-03-01 | 9 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2723 | PGE | 93245 | NEM | EXPNEM | Implementation | Solar PV | 240 |  | 2021-12-13 | 2021-12-15 | 2 | 2021-12-28 | 11 | 2022-01-07 | 8 | [15 empty] | 2022-01-07 | 2022-01-12 | 3 | 2022-01-12 | 2022-02-11 | 21 |  |  |  |  | 2021-12-13 | 0 |  | 2022-01-06 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2724 | PGE | 93725 | NEM | EXPNEM | Implementation | Solar PV | 183.441 |  | 2021-12-13 | 2021-12-14 | 1 | 2021-12-16 | 3 | 2021-12-29 | 9 | 2021-12-29 | 2022-01-26 | 19 | [12 empty] | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | 2022-02-01 | 4 |  |  |  |  | 2021-12-13 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2726 | PGE | 94545 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 3249.86 |  | 2021-12-13 | 2021-12-16 | 3 | 2022-01-19 | 26 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2727 | PGE | 93635 | NEM | EXPNEM | IA in Progress | Solar PV | 41.031 |  | 2021-12-13 | 2021-12-16 | 3 | 2021-12-16 | 3 | 2021-12-31 | 11 | [15 empty] | 2021-12-31 | 2022-01-24 | 15 | 2022-01-24 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2728 | PGE | 93660 | NEM | EXPNEM | IA in Progress | Solar PV | 36 |  | 2021-12-13 | 2021-12-16 | 3 | 2021-12-16 | 3 | 2022-01-04 | 13 | [15 empty] | 2022-01-04 | 2022-01-24 | 13 | 2022-01-24 | [6 empty] | 2021-12-13 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2729 | PGE | 93637 | NEM | EXPNEM | Study in Progress | Solar PV | 240 |  | 2021-12-13 | 2021-12-15 | 2 | 2021-12-17 | 4 | [5 empty] | 2021-12-17 | 2022-01-07 | 15 | 2022-01-07 | [18 empty] | 2021-12-13 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2730 | PGE | 94585 | NEM | NEMMT | Application Accepted | ENGN, Solar PV, WIND | 1200 |  | 2021-12-13 | 2021-12-16 | 3 | 2022-01-12 | 22 | [20 empty] | 2021-12-13 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2731 | PGE | 94510 | NEM | EXPNEM | Study in Progress | Solar PV | 125 |  | 2021-12-13 | 2021-12-27 | 10 | 2022-02-08 | 40 | [27 empty] | 2022-01-19 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2732 | PGE | 94590 | NEM | EXPNEM | IA in Progress | Solar PV | 58.634 |  | 2021-12-13 | 2021-12-27 | 10 | 2021-12-27 | 10 | 2022-01-18 | 15 | [15 empty] | 2022-01-18 | 2022-02-08 | 15 | 2022-02-08 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2733 | PGE | 95472 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 49.411 |  | 2021-12-13 | 2021-12-15 | 2 | 2021-12-31 | 14 | 2022-01-20 | 13 | 2022-01-20 | 2022-02-16 | 19 | [12 empty] | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16 | [6 empty] | 2021-12-13 | 2021-12-17 | 4 |  | 2022-02-16 | 2022-02-16 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2734 | PGE | 95076 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 491.512 |  | 2021-12-14 | 2021-12-28 | 10 | 2022-02-09 | 40 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2735 | PGE | 93307 | NEM | EXPNEM | Implementation | Solar PV | 38.78 |  | 2021-12-14 | 2022-01-06 | 17 | 2021-12-28 | 10 | 2022-01-28 | 22 | [15 empty] | 2022-01-28 | 2022-02-14 | 11 | 2022-02-14 | 2022-03-31 | 32 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2736 | PGE | 93401 | NEM | EXPNEM | IA in Progress | Solar PV | 200.518 |  | 2021-12-14 | 2021-12-21 | 5 | 2021-12-21 | 5 | 2022-01-26 | 25 | [15 empty] | 2022-01-26 | 2022-02-11 | 12 | 2022-02-11 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2737 | PGE | 95407 | NEM | EXPNEM | Implementation | Solar PV | 85.556 |  | 2021-12-14 | 2021-12-21 | 5 | 2021-12-21 | 5 | 2022-01-04 | 10 | [15 empty] | 2022-01-04 | 2022-01-24 | 13 | 2022-01-24 | 2022-01-27 | 3 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2738 | PGE | 95912 | NEM | EXPNEM | Implementation | Solar PV | 66.6 |  | 2021-12-14 | 2021-12-16 | 2 | 2021-12-16 | 2 | 2022-01-03 | 12 | [15 empty] | 2022-01-03 | 2022-01-03 | 0 | 2022-01-03 | 2022-02-01 | 20 |  |  |  |  | 2021-12-14 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2739 | PGE | 93660 | NEM | EXPNEM | Implementation | Solar PV | 145.672 |  | 2021-12-14 | 2021-12-28 | 10 | 2022-01-03 | 14 | 2022-01-31 | 19 | [15 empty] | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | 2022-03-18 | 33 |  |  |  |  | 2021-12-14 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2740 | PGE | 95066 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-12-14 | 2021-12-23 | 7 | 2022-01-06 | 17 | 2022-01-25 | 12 | [18 empty] | 2021-12-14 | [6 empty] | 2021-12-14 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-12-23 |  | 2022-01-25 | 24 | 1//19
2741 | PGE | 93620 | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-12-14 | 2021-12-16 | 2 | 2021-12-16 | 2 | 2022-02-01 | 32 | [15 empty] | 2022-02-01 | 2022-02-01 | 0 | 2022-02-01 | [6 empty] | 2021-12-14 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2742 | PGE | 93420 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-12-14 | 2021-12-28 | 10 | 2021-12-28 | 10 | 2022-01-18 | 14 | [18 empty] | 2021-12-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2743 | PGE | 95687 | NEM | EXPNEM | IA in Progress | Solar PV | 360 |  | 2021-12-14 | 2021-12-16 | 2 | 2021-12-16 | 2 | 2022-02-28 | 50 | [15 empty] | 2022-02-28 | 2022-02-28 | 0 | 2022-02-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2744 | PGE | 95203 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 66.256 |  | 2021-12-14 | 2021-12-17 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2745 | PGE | 93624 | NEM | EXPNEM | Implementation | Solar PV | 38.956 |  | 2021-12-14 | 2021-12-28 | 10 | 2021-12-28 | 10 | 2022-01-04 | 5 | [15 empty] | 2022-01-04 | 2022-01-04 | 0 | 2022-01-04 | 2022-01-05 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2746 | PGE | 95203 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 30.913 |  | 2021-12-14 | 2021-12-17 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2747 | PGE | 93727 | NEM | EXPNEM | Study in Progress | Solar PV | 908.176 |  | 2021-12-14 | 2021-12-21 | 5 | 2022-01-18 | 24 | 2022-01-31 | 9 | 2022-02-01 | 2022-02-25 | 17 | 2022-02-25 | 2022-03-21 | 16 | 2022-03-21 | 2022-03-21 | 0 |  |  |  | 2022-03-21 | [13 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2748 | PGE | 93905 | NEM | EXPNEM | IA in Progress | Solar PV | 40.384 |  | 2021-12-14 | 2021-12-28 | 10 | 2022-01-14 | 23 | 2022-01-27 | 8 | [15 empty] | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2749 | PGE | 94028 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.741 |  | 2021-12-15 | 2021-12-29 | 10 | 2022-01-20 | 25 | 2022-01-24 | 2 | [18 empty] | 2021-12-15 | [7 empty] | 0 | [5 empty] | 2022-01-24 | 2022-01-24 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-24 |  |  | 2022-01-24 |  | 2022-01-24 | 0 | 1//19
2750 | PGE | 95926 | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-12-15 | 2021-12-22 | 5 | 2021-12-28 | 9 | 2022-01-13 | 12 | 2022-01-13 | 2022-03-02 | 32 | [12 empty] | 2022-03-02 | 2022-03-02 | 0 | 2022-03-02 | [6 empty] | 2021-12-15 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2751 | PGE | 95333 | NEM | EXPNEM | IA in Progress | Solar PV | 220 |  | 2021-12-15 | 2021-12-29 | 10 | 2022-01-26 | 29 | 2022-02-16 | 15 | [15 empty] | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16 | [6 empty] | 2021-12-15 | 0 |  | 2022-01-06 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2752 | PGE | 94602 | NEM | EXPNEM | IA in Progress | Solar PV | 57.71 |  | 2021-12-15 | 2021-12-29 | 10 | 2021-12-29 | 10 | 2022-01-20 | 15 | [15 empty] | 2022-01-20 | 2022-01-21 | 1 | 2022-01-21 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2753 | PGE | 93280 | NEM | EXPNEM | Study in Progress | Solar PV | 360 |  | 2021-12-15 | 2021-12-29 | 10 | 2022-01-04 | 14 | [5 empty] | 2022-01-04 | 2022-01-31 | 18 | 2022-01-31 | [18 empty] | 2021-12-15 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2754 | PGE | 95687 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-12-15 | 2021-12-20 | 3 | 2021-12-20 | 3 | 2022-01-04 | 11 | [15 empty] | 2022-01-04 | 2022-01-05 | 1 | 2022-01-05 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2755 | PGE | 95482 | NEM | EXPNEM | Withdrawn | Solar PV | 100 |  | 2021-12-15 | 2021-12-21 | 4 | 2022-01-05 | 15 | 2022-01-19 | 9 | [15 empty] | 2022-01-19 | 2022-01-19 | 0 | 2022-01-19 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2756 | PGE | 93901 | NEM | EXPNEM | IA in Progress | Solar PV | 113.288 |  | 2021-12-15 | 2021-12-17 | 2 | 2022-02-04 | 36 | 2022-03-01 | 16 | [15 empty] | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | [6 empty] | 2021-12-15 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2757 | PGE | 94124 | NEM | EXPNEM | Study in Progress | Solar PV | 83.3 |  | 2021-12-15 | 2021-12-20 | 3 | 2022-03-29 | 72 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2758 | PGE | 94928 | NEM | EXPNEM | Withdrawn | Solar PV | 95.8 |  | 2021-12-15 | 2021-12-29 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2759 | PGE | 93635 | NEM | EXPNEM | Application Review in Progress | Solar PV | 62.5 |  | 2021-12-15 | 2021-12-27 | 8 | [29 empty] | 2021-12-15 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2760 | PGE | 93631 | NEM | EXPNEM | Study in Progress | Solar PV | 125 |  | 2021-12-15 | 2021-12-28 | 9 | 2022-03-30 | 73 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2761 | PGE | 95603 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.122 |  | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 0 | 2022-01-03 | 13 | [18 empty] | 2021-12-15 | [7 empty] | 0 | [5 empty] | 2022-01-04 | 2022-01-04 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-04 |  |  | 2022-01-04 |  | 2022-01-04 | 0 | 1//19
2762 | PGE | 94945 | NEM | EXPNEM | Study in Progress | Solar PV | 500 |  | 2021-12-15 | 2021-12-20 | 3 | 2021-12-20 | 3 | 2022-01-03 | 10 | 2022-01-03 | 2022-01-28 | 18 | 2022-01-28 | 2022-02-22 | 16 | 2022-02-22 | [18 empty] | 2021-12-15 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2763 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 35.22 |  | 2021-12-15 | 2021-12-23 | 6 | 2022-01-18 | 23 | 2022-02-08 | 15 | [15 empty] | 2022-02-08 | 2022-02-08 | 0 | 2022-02-08 | [6 empty] | 2021-12-15 | 0 |  | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2764 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 38.018 |  | 2021-12-15 | 2021-12-23 | 6 | 2022-01-18 | 23 | 2022-02-08 | 15 | [15 empty] | 2022-02-08 | 2022-02-08 | 0 | 2022-02-08 | [6 empty] | 2021-12-15 | 0 |  | 2022-02-10 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2765 | PGE | 94066 | NEM | EXPNEM | Study in Progress | Solar PV | 501.275 |  | 2021-12-15 | 2021-12-17 | 2 | 2021-12-28 | 9 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2766 | PGE | 94403 | NEM | EXPNEM | Application Review in Progress | Solar PV | 341.891 |  | 2021-12-15 | 2021-12-29 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2767 | PGE | 95949 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-12-16 | 2021-12-16 | 0 | 2022-02-15 | 42 | 2022-03-14 | 18 | [18 empty] | 2021-12-16 | [7 empty] | 0 | [5 empty] | 2022-03-14 | 2022-03-14 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-14 |  |  | 2022-03-14 |  | 2022-03-14 | 0 | 1//19
2768 | PGE | 94549 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-12-16 | 2021-12-30 | 10 | 2021-12-30 | 10 | 2022-01-18 | 12 | [18 empty] | 2021-12-16 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2021-12-30 |  | 2022-01-18 | 14 | 1//19
2769 | PGE | 93312 | NEM | EXPNEM | IA in Progress | Solar PV | 300.612 |  | 2021-12-16 | 2021-12-29 | 9 | 2021-12-29 | 9 | 2022-01-21 | 16 | [15 empty] | 2022-01-21 | 2022-01-24 | 1 | 2022-01-24 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2770 | PGE | 95341 | NEM | EXPNEM | IA in Progress | Solar PV | 801.632 |  | 2021-12-16 | 2021-12-30 | 10 | 2022-01-24 | 26 | 2022-02-14 | 15 | [15 empty] | 2022-02-14 | 2022-02-14 | 0 | 2022-02-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2771 | PGE | 95687 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-12-16 | 2021-12-29 | 9 | 2022-01-13 | 20 | 2022-02-01 | 12 | [15 empty] | 2022-02-01 | 2022-02-16 | 11 | 2022-02-16 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2772 | PGE | 93618 | NEM | EXPNEM | Implementation | Solar PV | 32.87 |  | 2021-12-16 | 2021-12-29 | 9 | 2022-01-05 | 14 | 2022-01-25 | 13 | [15 empty] | 2022-01-25 | 2022-02-10 | 12 | 2022-02-10 | 2022-03-18 | 25 | [5 empty] | 0 |  | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2773 | PGE | 94520 | NEM | EXPNEM | Implementation | Solar PV | 45.613 |  | 2021-12-16 | 2021-12-17 | 1 | 2022-01-25 | 27 | 2022-03-09 | 30 | [15 empty] | 2022-03-09 | 2022-03-09 | 0 | 2022-03-09 | 2022-03-10 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2774 | PGE | 93245 | NEM | EXPNEM | Study in Progress | Solar PV | 113.937 |  | 2021-12-16 | 2021-12-30 | 10 | 2022-03-16 | 62 | [27 empty] | 2021-12-16 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2775 | PGE | 93446 | NEM | EXPNEM | IA in Progress | Solar PV | 120.756 |  | 2021-12-16 | 2021-12-30 | 10 | 2022-01-28 | 30 | 2022-02-15 | 12 | [15 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2776 | PGE | 94538 | NEM | VNEM | Implementation | Solar PV | 33.075 |  | 2021-12-16 | 2021-12-20 | 2 | 2021-12-31 | 11 | 2022-01-05 | 3 | [18 empty] | 2021-12-16 | 2021-12-16 | 0 |  |  |  |  | 2021-12-16 | 2021-12-23 | 5 |  | 2022-01-05 | 2022-01-05 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2777 | PGE | 95966 | NEM | EXPNEM | Study in Progress | Solar PV | 3691.6 |  | 2021-12-16 | 2021-12-21 | 3 | 2021-12-29 | 9 | [5 empty] | 2021-12-29 | 2022-01-27 | 20 | 2022-01-27 | 2022-01-27 | 0 | 2022-02-01 |  |  | 2022-01-27 | 2022-01-27 | 0 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2778 | PGE | 96092 | NEM | EXPNEM | Application Accepted | Solar PV | 1654.572 |  | 2021-12-16 | 2021-12-22 | 4 | 2022-01-05 | 14 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2779 | PGE | 93245 | NEM | EXPNEM | Implementation | Solar PV | 180 |  | 2021-12-16 | 2021-12-22 | 4 | 2022-01-24 | 26 | 2022-02-02 | 7 | [15 empty] | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-07 | 3 |  |  |  |  | 2021-12-16 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2780 | PGE | 93636 | NEM | EXPNEM | Study in Progress | Solar PV | 200 |  | 2021-12-16 | 2021-12-21 | 3 | 2022-01-11 | 18 | 2022-02-02 | 15 | 2022-02-02 | 2022-03-03 | 20 | 2022-03-03 | 2022-03-26 | 16 | 2022-03-26 | [18 empty] | 2021-12-16 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2781 | PGE | 95687 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-12-16 | 2021-12-20 | 2 | 2021-12-27 | 7 | 2022-01-11 | 11 | [15 empty] | 2022-01-11 | 2022-01-11 | 0 | 2022-01-11 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2782 | PGE | 95003 | NEM | EXPNEM | Study in Progress | Solar PV | 66.6 |  | 2021-12-17 | 2021-12-31 | 10 | 2022-01-07 | 15 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2783 | PGE | 93234 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 56.935 |  | 2021-12-17 | 2021-12-23 | 4 | 2022-01-14 | 20 | 2022-02-07 | 15 | [15 empty] | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | [6 empty] | 2021-12-17 | 0 |  | 2021-12-31 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2784 | PGE | 94903 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-12-17 | 2021-12-27 | 6 | 2021-12-27 | 6 | 2022-01-06 | 8 | [18 empty] | 2021-12-17 | 2021-12-27 | 6 | [5 empty] | 0 | [5 empty] | 2022-01-26 | 2022-01-27 | 1 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-26 | 2022-01-27 | 1 | 2022-01-27 |  | 2022-02-01 | 3 | 1//19
2785 | PGE | 93306 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.741 |  | 2021-12-17 | 2021-12-31 | 10 | 2021-12-31 | 10 | 2022-01-04 | 2 | [18 empty] | 2021-12-17 | [7 empty] | 0 | [5 empty] | 2022-01-04 | 2022-01-04 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-04 |  |  | 2022-01-04 |  | 2022-01-04 | 0 | 1//19
2786 | PGE | 95387 | NEM | EXPNEM | Study in Progress | Solar PV | 150 |  | 2021-12-17 | 2021-12-20 | 1 | 2022-01-05 | 13 | 2022-02-03 | 20 | 2022-02-03 | 2022-03-04 | 20 | 2022-03-08 | 2022-03-29 | 15 | 2022-03-29 | [18 empty] | 2021-12-17 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2787 | PGE | 94513 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-12-17 | 2021-12-30 | 9 | 2021-12-30 | 9 | 2022-01-18 | 12 | [15 empty] | 2022-01-18 | 2022-01-18 | 0 | 2022-01-18 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2788 | PGE | 94010 | NEM | EXPNEM | IA in Progress | Solar PV | 32.614 |  | 2021-12-17 | 2021-12-23 | 4 | 2021-12-29 | 8 | 2022-01-11 | 9 | [15 empty] | 2022-01-11 | 2022-01-11 | 0 | 2022-01-11 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2789 | PGE | 95765 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.35 |  | 2021-12-18 | 2022-01-03 | 10 | 2022-01-03 | 10 | 2022-01-25 | 15 | [18 empty] | 2021-12-18 | [7 empty] | 0 | [5 empty] | 2022-01-25 | 2022-01-25 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-25 |  |  | 2022-01-25 |  | 2022-01-25 | 0 | 1//19
2791 | PGE | 95765 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 35.163 |  | 2021-12-18 | 2022-01-03 | 10 | 2022-02-10 | 37 | 2022-02-14 | 2 | [18 empty] | 2021-12-18 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2792 | PGE | 95128 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2830 |  | 2021-12-18 | 2021-12-21 | 1 | 2021-12-21 | 1 | [5 empty] | 2021-12-21 | 2022-01-12 | 16 | 2022-01-12 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2793 | PGE | 95138 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2724 |  | 2021-12-18 | 2021-12-23 | 3 | 2022-01-12 | 17 | [5 empty] | 2022-01-18 | 2022-02-17 | 22 | 2022-02-17 | [18 empty] | 2021-12-18 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2794 | PGE | 95035 | NEM | NEMMT | Study in Progress | FUCE, Solar PV, Storage | 1144 |  | 2021-12-18 | 2021-12-29 | 7 | 2022-01-18 | 20 | [5 empty] | 2022-01-18 | 2022-02-17 | 22 | 2022-02-17 | [18 empty] | 2021-12-18 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2795 | PGE | 95112 | NEM | NEMMT | Study in Progress | FUCE, Solar PV, Storage | 2525.5 |  | 2021-12-18 | 2021-12-22 | 2 | 2022-01-26 | 26 | [5 empty] | 2022-01-26 | 2022-02-28 | 22 | 2022-02-28 | 2022-03-03 | 3 | 2022-03-07 |  |  | 2022-03-03 | 2022-03-03 | 0 | [10 empty] | 2021-12-18 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2796 | PGE | 95046 | NEM | EXPNEM | Implementation | Solar PV | 564 |  | 2021-12-18 | 2021-12-23 | 3 | 2021-12-23 | 3 | 2022-01-11 | 13 | [15 empty] | 2022-01-11 | 2022-01-11 | 0 | 2022-01-11 | 2022-02-10 | 21 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2797 | PGE | 95111 | NEM | EXPNEM | IA in Progress | Solar PV | 160 |  | 2021-12-18 | 2021-12-30 | 8 | 2022-01-18 | 20 | 2022-02-04 | 13 | [15 empty] | 2022-02-04 | 2022-02-09 | 3 | 2022-02-09 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2798 | PGE | 95037 | NEM | EXPNEM | IA in Progress | Solar PV | 913.625 |  | 2021-12-18 | 2021-12-23 | 3 | 2022-01-21 | 23 | 2022-02-07 | 11 | 2022-02-07 | 2022-03-26 | 33 | [12 empty] | 2022-03-26 | 2022-03-26 | 0 | 2022-03-26 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2799 | PGE | 95993 | NEM | EXPNEM | Implementation | Solar PV | 34.179 |  | 2021-12-20 | 2022-01-03 | 10 | 2022-01-03 | 10 | 2022-01-20 | 12 | [15 empty] | 2022-01-20 | 2022-02-10 | 15 | 2022-02-10 | 2022-03-18 | 25 |  |  |  |  | 2021-12-20 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2800 | PGE | 93301 | NEM | EXPNEM | IA in Progress | Solar PV | 57.71 |  | 2021-12-20 | 2022-01-03 | 10 | 2022-01-03 | 10 | 2022-01-10 | 5 | [15 empty] | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | 2022-02-14 | 24 |  |  |  |  | 2022-01-04 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2801 | PGE | 93638 | NEM | EXPNEM | IA in Progress | Solar PV | 62.431 |  | 2021-12-20 | 2021-12-24 | 4 | 2022-01-07 | 14 | 2022-01-24 | 10 | [15 empty] | 2022-01-24 | 2022-01-24 | 0 | 2022-01-24 | [6 empty] | 2021-12-27 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2802 | PGE | 95317 | NEM | EXPNEM | Study in Progress | Solar PV | 59.964 |  | 2021-12-20 | 2022-01-03 | 10 | 2022-02-10 | 37 | [27 empty] | 2021-12-20 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2803 | PGE | 95336 | NEM | EXPNEM | Study in Progress | Solar PV | 93.238 |  | 2021-12-20 | 2022-01-03 | 10 | 2022-01-03 | 10 | 2022-02-15 | 30 | 2022-02-15 | 2022-03-15 | 19 | 2022-03-15 | [21 empty] | 2021-12-20 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2804 | PGE | 95688 | NEM | EXPNEM | IA in Progress | Solar PV | 330.617 |  | 2021-12-20 | 2021-12-24 | 4 | 2021-12-30 | 8 | 2022-01-18 | 12 | [15 empty] | 2022-01-18 | 2022-01-18 | 0 | 2022-01-18 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2805 | PGE | 93308 | NEM | EXPNEM | IA in Progress | Solar PV | 300 |  | 2021-12-20 | 2021-12-24 | 4 | 2022-01-04 | 11 | 2022-01-05 | 1 | [15 empty] | 2022-01-05 | 2022-01-05 | 0 | 2022-01-05 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2806 | PGE | 93960 | NEM | EXPNEM | IA in Progress | Solar PV | 96 |  | 2021-12-20 | 2021-12-24 | 4 | 2021-12-30 | 8 | 2022-01-20 | 14 | [15 empty] | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | [6 empty] | 2021-12-20 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2807 | PGE | 95688 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-12-20 | 2022-01-03 | 10 | 2022-01-03 | 10 | 2022-01-25 | 15 | [15 empty] | 2022-01-25 | 2022-02-15 | 15 | 2022-02-15 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2808 | PGE | 94920 | NEM | EXPNEM | IA in Progress | Solar PV | 101.964 |  | 2021-12-20 | 2022-01-03 | 10 | 2022-01-14 | 19 | 2022-02-16 | 22 | [15 empty] | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2809 | PGE | 95340 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-12-21 | 2021-12-27 | 4 | 2021-12-30 | 7 | 2022-01-18 | 12 | [15 empty] | 2022-01-18 | 2022-02-02 | 11 | 2022-02-02 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2810 | PGE | 93657 | NEM | EXPNEM | IA in Progress | Solar PV | 35.045 |  | 2021-12-21 | 2021-12-28 | 5 | 2022-01-18 | 19 | 2022-01-28 | 8 | [15 empty] | 2022-01-28 | 2022-02-14 | 11 | 2022-02-14 | [6 empty] | 2021-12-21 | 0 |  | 2022-01-06 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2811 | PGE | 93722 | NEM | EXPNEM | Application Review in Progress | Solar PV | 32.698 |  | 2021-12-21 | 2022-01-03 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2812 | PGE | 95409 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.423 |  | 2021-12-21 | 2022-01-04 | 10 | 2022-01-04 | 10 | 2022-01-22 | 12 | [18 empty] | 2021-12-21 | [7 empty] | 0 | [5 empty] | 2022-01-22 | 2022-01-22 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-22 |  |  | 2022-01-22 |  | 2022-01-22 | 0 | 1//19
2813 | PGE | 96080 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 38.018 |  | 2021-12-21 | 2021-12-31 | 8 | 2022-01-13 | 17 | 2022-02-04 | 15 | [15 empty] | 2022-02-04 | 2022-02-04 | 0 | 2022-02-04 | [6 empty] | 2021-12-21 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2814 | PGE | 96080 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 60.804 |  | 2021-12-21 | 2021-12-31 | 8 | 2022-01-13 | 17 | 2022-02-04 | 15 | [15 empty] | 2022-02-04 | 2022-02-04 | 0 | 2022-02-04 | [6 empty] | 2021-12-21 | 0 |  |  | 2022-02-15 | 2022-02-17 | 2 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2815 | PGE | 93454 | NEM | EXPNEM | IA in Progress | Solar PV | 133.3 |  | 2021-12-21 | 2022-01-03 | 9 | 2022-02-08 | 34 | 2022-02-28 | 13 | [15 empty] | 2022-02-28 | 2022-03-17 | 13 | 2022-03-17 | [6 empty] | 2022-01-13 | 0 |  | 2022-03-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2816 | PGE | 95033 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-12-21 | 2022-01-04 | 10 | 2022-01-04 | 10 | 2022-01-06 | 2 | [15 empty] | 2022-01-06 | 2022-01-06 | 0 | 2022-01-06 | 2022-01-06 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-01-04 |  | 2022-01-10 | 5 | 1//19
2817 | PGE | 95136 | NEM | EXPNEM | IA in Progress | Solar PV | 292.76 |  | 2021-12-21 | 2022-01-03 | 9 | 2022-01-03 | 9 | 2022-02-15 | 30 | [15 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2818 | PGE | 93654 | NEM | EXPNEM | IA in Progress | Solar PV | 848.589 |  | 2021-12-21 | 2022-01-03 | 9 | 2022-01-19 | 20 | 2022-02-03 | 11 | 2022-02-03 | 2022-03-02 | 18 | [12 empty] | 2022-03-02 | 2022-03-23 | 15 | 2022-03-23 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2819 | PGE | 95403 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 41.643 |  | 2021-12-21 | 2021-12-23 | 2 | 2022-01-11 | 15 | 2022-02-02 | 15 | [15 empty] | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | [6 empty] | 2021-12-21 | 0 |  |  | 2022-02-02 | 2022-02-02 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2820 | PGE | 95403 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 37.926 |  | 2021-12-21 | 2022-01-04 | 10 | 2022-01-21 | 22 | 2022-02-11 | 15 | [15 empty] | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | [6 empty] | 2021-12-21 | 0 |  | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2821 | PGE | 95403 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 37.926 |  | 2021-12-21 | 2022-01-04 | 10 | 2022-01-21 | 22 | 2022-02-11 | 15 | [15 empty] | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | [6 empty] | 2021-12-21 | 0 |  | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2822 | PGE | 95403 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 37.926 |  | 2021-12-21 | 2021-12-23 | 2 | 2022-01-11 | 15 | [27 empty] | 2021-12-21 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2823 | PGE | 95403 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 53.188 |  | 2021-12-21 | 2022-01-04 | 10 | 2022-01-21 | 22 | 2022-02-11 | 15 | [15 empty] | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | [6 empty] | 2021-12-21 | 0 |  | 2022-01-05 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2824 | PGE | 95403 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 53.188 |  | 2021-12-21 | 2022-01-04 | 10 | 2022-01-21 | 22 | 2022-02-11 | 15 | [15 empty] | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | [6 empty] | 2021-12-21 | 0 |  | 2022-01-05 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2825 | PGE | 93230 | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.3 |  | 2021-12-22 | 2022-01-04 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2826 | PGE | 93230 | NEM | EXPNEM | Study in Progress | Solar PV | 387.4 |  | 2021-12-22 | 2022-01-05 | 10 | 2022-03-22 | 62 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2827 | PGE | 95687 | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-12-22 | 2021-12-29 | 5 | 2022-01-04 | 9 | 2022-01-20 | 11 | [15 empty] | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2828 | PGE | 93930 | NEM | EXPNEM | IA in Progress | Solar PV | 111.855 |  | 2021-12-22 | 2021-12-27 | 3 | 2022-02-24 | 44 | 2022-03-10 | 10 | [15 empty] | 2022-03-10 | 2022-03-10 | 0 | 2022-03-10 | [6 empty] | 2021-12-28 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2829 | PGE | 95687 | NEM | EXPNEM | IA in Progress | Solar PV | 480 |  | 2021-12-22 | 2022-01-05 | 10 | 2022-01-20 | 20 | 2022-02-10 | 15 | [15 empty] | 2022-02-10 | 2022-02-10 | 0 | 2022-02-10 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2830 | PGE | 95304 | NEM | EXPNEM | Study in Progress | Solar PV | 580.504 |  | 2021-12-22 | 2021-12-24 | 2 | 2022-01-13 | 16 | 2022-01-28 | 10 | 2022-01-28 | 2022-02-25 | 19 | 2022-02-25 | 2022-03-21 | 16 | 2022-03-21 | [18 empty] | 2021-12-22 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2831 | PGE | 94553 | NEM | EXPNEM | Implementation | Solar PV | 62.5 |  | 2021-12-22 | 2021-12-27 | 3 | 2021-12-27 | 3 | 2022-01-11 | 11 | [15 empty] | 2022-01-11 | 2022-01-11 | 0 | 2022-01-11 | 2022-03-04 | 36 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2832 | PGE | 95006 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-12-22 | 2022-01-04 | 9 | 2022-03-17 | 59 | 2022-03-17 | 0 | [18 empty] | 2021-12-22 | [7 empty] | 0 | [5 empty] | 2022-03-17 | 2022-03-17 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-17 |  |  | 2022-03-17 |  | 2022-03-17 | 0 | 1//19
2833 | PGE | 94560 | Non-NEM | Continuous Uncompensated Export | IA in Progress | Solar PV | 133.2 |  | 2021-12-22 | 2021-12-22 | 0 | 2021-12-29 | 5 | 2022-03-14 | 51 | [15 empty] | 2022-03-14 | 2022-03-14 | 0 | 2022-03-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2834 | PGE | 95334 | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-12-22 | 2021-12-27 | 3 | 2022-01-13 | 16 | 2022-02-11 | 20 | [15 empty] | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | 2022-02-14 | 1 |  |  |  |  | 2021-12-22 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2835 | PGE | 93646 | NEM | EXPNEM | IA in Progress | Solar PV | 400.816 |  | 2021-12-22 | 2022-01-03 | 8 | 2022-01-03 | 8 | 2022-01-25 | 15 | [15 empty] | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2836 | PGE | 95334 | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-12-22 | 2021-12-27 | 3 | 2021-12-30 | 6 | 2022-01-13 | 10 | [15 empty] | 2022-01-13 | 2022-01-13 | 0 | 2022-01-13 | 2022-01-28 | 10 |  |  |  |  | 2021-12-22 | 0 | [5 empty] | 2022-03-29 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-29 | 2022-03-30 | 1 |  |  |  |  | 1//19
2837 | PGE | 94565 | NEM | EXPNEM | Implementation | Solar PV | 101.728 |  | 2021-12-22 | 2022-01-05 | 10 | 2022-02-18 | 41 | 2022-03-14 | 15 | [15 empty] | 2022-03-14 | 2022-03-14 | 0 | 2022-03-14 | 2022-03-16 | 2 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2838 | PGE | 95020 | NEM | EXPNEM | Study in Progress | Solar PV | 1872 |  | 2021-12-23 | 2021-12-27 | 2 | 2022-01-12 | 14 | [5 empty] | 2022-01-13 | 2022-02-04 | 15 | 2022-02-04 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2839 | PGE | 95987 | NEM | EXPNEM | IA in Progress | Solar PV | 47.351 |  | 2021-12-23 | 2022-01-06 | 10 | 2022-02-18 | 40 | 2022-03-14 | 15 | [15 empty] | 2022-03-14 | 2022-03-14 | 0 | 2022-03-14 | [6 empty] | 2021-12-23 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2840 | PGE | 95120 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.423 |  | 2021-12-23 | 2022-01-04 | 8 | 2022-01-04 | 8 | 2022-01-26 | 15 | [18 empty] | 2021-12-23 | [7 empty] | 0 | [5 empty] | 2022-01-26 | 2022-01-26 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-26 |  |  | 2022-01-26 |  | 2022-01-26 | 0 | 1//19
2841 | PGE | 93432 | NEM | EXPNEM | Withdrawn | Solar PV | 30.402 |  | 2021-12-23 | 2021-12-24 | 1 | 2022-01-18 | 17 | 2022-01-28 | 8 | [15 empty] | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | 2022-01-31 | 1 |  |  |  |  | 2021-12-23 | 0 | [5 empty] | 2022-02-01 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-01 | 2022-02-02 | 1 |  |  |  |  | 1//19
2842 | PGE | 93280 | NEM | EXPNEM | IA in Progress | Solar PV | 58.133 |  | 2021-12-23 | 2021-12-27 | 2 | 2021-12-29 | 4 | 2022-01-13 | 11 | [15 empty] | 2022-01-13 | 2022-01-13 | 0 | 2022-01-13 | [6 empty] | 2021-12-28 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2843 | PGE | 93721 | NEM | EXPNEM | Withdrawn | Solar PV | 133.2 |  | 2021-12-23 | 2021-12-24 | 1 | 2022-01-07 | 11 | 2022-01-26 | 12 | [15 empty] | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2844 | PGE | 95367 | NEM | EXPNEM | Study in Progress | Solar PV | 60 |  | 2021-12-23 | 2021-12-27 | 2 | 2021-12-27 | 2 | 2022-03-18 | 57 | 2022-03-18 | [25 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2845 | PGE | 95205 | NEM | EXPNEM | IA in Progress | Solar PV | 590 |  | 2021-12-23 | 2022-01-06 | 10 | 2022-01-06 | 10 | 2022-03-11 | 44 | [15 empty] | 2022-03-11 | [10 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2846 | PGE | 94028 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23 | 0 | 2022-01-07 | 11 | [18 empty] | 2021-12-23 | [7 empty] | 0 | [5 empty] | 2022-01-07 | 2022-01-07 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-07 |  |  | 2022-01-07 |  | 2022-01-07 | 0 | 1//19
2847 | PGE | 95020 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-12-23 | 2022-01-04 | 8 | 2022-01-04 | 8 | 2022-01-06 | 2 | [18 empty] | 2021-12-23 | [7 empty] | 0 | [5 empty] | 2022-01-06 | 2022-01-06 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-06 |  |  | 2022-01-06 |  | 2022-01-06 | 0 | 1//19
2848 | PGE | 94550 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 34.963 |  | 2021-12-23 | 2022-01-04 | 8 | 2022-01-04 | 8 | 2022-01-06 | 2 | [18 empty] | 2021-12-23 | [6 empty] | 2021-12-23 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2849 | PGE | 95070 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 41.853 |  | 2021-12-23 | 2022-01-05 | 9 | 2022-01-05 | 9 | 2022-01-07 | 2 | [18 empty] | 2021-12-23 | [7 empty] | 0 | [5 empty] | 2022-01-07 | 2022-01-13 | 4 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-07 | 2022-01-09 | 0 | 2022-01-13 |  | 2022-01-18 | 2 | 1//19
2850 | PGE | 94957 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.163 |  | 2021-12-23 | 2022-01-05 | 9 | 2022-01-05 | 9 | 2022-01-25 | 13 | [18 empty] | 2021-12-23 | [7 empty] | 0 | [5 empty] | 2022-01-25 | 2022-01-25 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-25 |  |  | 2022-01-25 |  | 2022-01-25 | 0 | 1//19
2851 | PGE | 93601 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.35 |  | 2021-12-23 | 2022-01-05 | 9 | 2022-01-05 | 9 | 2022-02-07 | 22 | [18 empty] | 2021-12-23 | [7 empty] | 0 | [5 empty] | 2022-03-21 | 2022-03-21 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-21 |  |  | 2022-03-21 |  | 2022-03-22 | 1 | 1//19
2854 | PGE | 94549 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 40.163 |  | 2021-12-24 | 2022-01-06 | 9 | 2022-01-06 | 9 | 2022-02-09 | 23 | [18 empty] | 2021-12-24 | [7 empty] | 0 | [5 empty] | 2022-02-09 | 2022-02-09 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-09 |  |  | 2022-02-09 |  | 2022-02-09 | 0 | 1//19
2856 | PGE | 94506 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.423 |  | 2021-12-24 | 2022-01-06 | 9 | 2022-01-06 | 9 | 2022-02-09 | 23 | [18 empty] | 2021-12-24 | [7 empty] | 0 | [5 empty] | 2022-02-09 | 2022-02-09 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-09 |  |  | 2022-02-09 |  | 2022-02-09 | 0 | 1//19
2857 | PGE | 95926 | NEM | EXPNEM | Study in Progress | Solar PV | 72.419 |  | 2021-12-27 | 2021-12-28 | 1 | 2022-02-01 | 25 | 2022-02-23 | 15 | 2022-02-23 | [24 empty] | 2021-12-27 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2858 | PGE | 95126 | NEM | EXPNEM | Study in Progress | Solar PV | 289.504 |  | 2021-12-27 | 2022-01-07 | 9 | 2022-03-24 | 61 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2860 | PGE | 94708 | Non-NEM | Inadvertent Export | Commercial | Storage | 5 |  | 2021-12-28 | 2022-01-11 | 10 | 2022-01-11 | 10 | 2022-01-12 | 1 | [15 empty] | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | 2022-01-12 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-01-11 |  | 2022-01-19 | 7 | 1//19
2861 | PGE | 96021 | NEM | EXPNEM | Study in Progress | Solar PV | 39.352 |  | 2021-12-28 | 2021-12-31 | 3 | 2022-01-04 | 5 | 2022-02-07 | 23 | 2022-02-07 | [24 empty] | 2021-12-28 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2863 | PGE | 94089 | NEM | EXPNEM | Application Review in Progress | Solar PV | 136.807 |  | 2021-12-28 | 2022-01-11 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2864 | PGE | 95032 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.641 |  | 2021-12-28 | 2022-01-07 | 8 | 2022-01-07 | 8 | 2022-01-07 | 0 | [18 empty] | 2021-12-28 | [6 empty] | 2021-12-28 | 0 | [5 empty] | 2022-01-26 | 2022-01-26 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-26 |  |  | 2022-01-26 |  | 2022-01-26 | 0 | 1//19
2865 | PGE | 94089 | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-12-28 | 2022-01-05 | 6 | 2022-01-05 | 6 | 2022-01-10 | 3 | [15 empty] | 2022-01-10 | 2022-01-20 | 7 | 2022-01-20 | 2022-01-20 | 0 |  |  |  |  | 2022-01-18 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2866 | PGE | 94559 | NEM | EXPNEM | Implementation | Solar PV | 90.377 |  | 2021-12-28 | 2022-01-05 | 6 | 2022-01-05 | 6 | 2022-01-28 | 16 | [15 empty] | 2022-01-27 | 2022-02-03 | 5 | 2022-02-03 | 2022-02-22 | 12 | [5 empty] | 0 | [5 empty] | 2022-03-01 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-01 | 2022-03-01 | 0 |  |  |  |  | 1//19
2867 | PGE | 93427 | NEM | EXPNEM | IA in Progress | Solar PV | 115.42 |  | 2021-12-28 | 2022-01-03 | 4 | 2022-01-19 | 15 | 2022-02-01 | 9 | [15 empty] | 2022-02-01 | 2022-02-01 | 0 | 2022-02-01 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2868 | PGE | 95448 | NEM | EXPNEM | Study in Progress | Solar PV | 42.381 |  | 2021-12-28 | 2022-01-03 | 4 | 2022-01-03 | 4 | [5 empty] | 2022-01-03 | 2022-01-28 | 18 | 2022-01-28 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2869 | PGE | 93427 | NEM | EXPNEM | IA in Progress | Solar PV | 249.754 |  | 2021-12-28 | 2022-01-11 | 10 | 2022-01-25 | 19 | 2022-02-15 | 15 | [15 empty] | 2022-02-15 | 2022-02-16 | 1 | 2022-02-16 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2870 | PGE | 94929 | NEM | EXPNEM | Study in Progress | Solar PV | 59.33 |  | 2021-12-28 | 2022-01-05 | 6 | 2022-03-18 | 56 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2871 | PGE | 94533 | NEM | EXPNEM | IA in Progress | Solar PV | 180 |  | 2021-12-28 | 2021-12-31 | 3 | 2022-01-04 | 5 | 2022-03-01 | 38 | [15 empty] | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | [6 empty] | 2021-12-28 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2872 | PGE | 93427 | NEM | EXPNEM | Application Review in Progress | Solar PV | 245.373 |  | 2021-12-28 | 2022-01-03 | 4 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2873 | PGE | 95367 | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2021-12-28 | 2022-01-11 | 10 | 2022-01-26 | 20 | 2022-02-16 | 15 | [15 empty] | 2022-02-16 | 2022-03-10 | 15 | 2022-03-10 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2874 | PGE | 95367 | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2021-12-28 | 2022-01-11 | 10 | 2022-01-11 | 10 | 2022-01-26 | 10 | 2022-01-26 | 2022-02-24 | 20 | 2022-02-24 | 2022-03-23 | 19 | 2022-03-23 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2875 | PGE | 95536 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 15 |  | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 0 | 2022-01-03 | 3 | [15 empty] | 2022-01-03 | 2022-01-03 | 0 | 2022-01-03 | 2022-03-02 | 40 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2876 | PGE | 93245 | NEM | EXPNEM | Implementation | Solar PV | 150 |  | 2021-12-29 | 2022-01-11 | 9 | 2022-01-11 | 9 | 2022-02-24 | 30 | [15 empty] | 2022-02-24 | 2022-02-28 | 2 | 2022-02-28 | 2022-02-28 | 0 |  |  |  |  | 2021-12-29 | 0 |  | 2022-01-11 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2878 | PGE | 94022 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 45.525 |  | 2021-12-29 | 2022-01-10 | 8 | 2022-01-10 | 8 | 2022-02-11 | 23 | [18 empty] | 2021-12-29 | [7 empty] | 0 | [5 empty] | 2022-02-11 | 2022-02-11 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-11 |  |  | 2022-02-11 |  | 2022-02-11 | 0 | 1//19
2879 | PGE | 95360 | NEM | EXPNEM | Application Review in Progress | Solar PV | 120 |  | 2021-12-29 | 2022-01-12 | 10 | [29 empty] | 2021-12-29 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2880 | PGE | 95928 | NEM | EXPNEM | Implementation | Solar PV | 297.49 |  | 2021-12-29 | 2021-12-30 | 1 | 2022-01-19 | 14 | 2022-02-03 | 11 | [15 empty] | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | 2022-02-09 | 4 |  |  |  |  | 2021-12-29 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2881 | PGE | 95204 | NEM | EXPNEM | IA in Progress | Solar PV | 46.11 |  | 2021-12-29 | 2022-01-10 | 8 | 2022-01-25 | 18 | 2022-02-11 | 13 | [15 empty] | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2882 | PGE | 93308 | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2021-12-29 | 2022-01-04 | 4 | 2022-01-04 | 4 | 2022-01-06 | 2 | [15 empty] | 2022-01-06 | 2022-01-06 | 0 | 2022-01-06 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2883 | PGE | 94526 | NEM | EXPNEM | IA in Progress | Solar PV | 45.572 |  | 2021-12-29 | 2021-12-31 | 2 | 2022-01-18 | 13 | 2022-03-07 | 33 | [15 empty] | 2022-03-07 | 2022-03-07 | 0 | 2022-03-07 | [6 empty] | 2021-12-29 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2884 | PGE | 95476 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 15 |  | 2021-12-30 | 2022-01-12 | 9 | 2022-02-18 | 35 | 2022-03-03 | 8 | [15 empty] | 2022-02-18 | 2022-02-18 | 0 | 2022-02-18 | 2022-03-03 | 8 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2885 | PGE | 93455 | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 |  | 2021-12-30 | 2022-01-13 | 10 | 2022-01-27 | 19 | 2022-03-11 | 30 | [15 empty] | 2022-03-11 | 2022-03-24 | 9 | 2022-03-24 | 2022-03-31 | 5 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2886 | PGE | 95928 | NEM | EXPNEM | Study in Progress | Solar PV | 150 |  | 2021-12-30 | 2022-01-13 | 10 | 2022-03-14 | 50 | [27 empty] | 2021-12-30 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2887 | PGE | 95694 | NEM | EXPNEM | Application Review in Progress | Solar PV | 111.278 |  | 2021-12-30 | 2022-01-13 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2888 | PGE | 95073 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 68.358 |  | 2021-12-30 | 2022-01-13 | 10 | 2022-02-01 | 22 | 2022-02-23 | 15 | [15 empty] | 2022-02-23 | 2022-02-23 | 0 | 2022-02-23 | [6 empty] | 2021-12-30 | 0 |  |  | 2022-02-23 | 2022-02-23 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2889 | PGE | 95695 | NEM | EXPNEM | Application Review in Progress | Solar PV | 187.5 |  | 2021-12-30 | 2022-01-10 | 7 | [29 empty] | 2021-12-30 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2890 | PGE | 93640 | NEM | EXPNEM | Study in Progress | Solar PV | 987.5 |  | 2021-12-30 | 2021-12-31 | 1 | 2022-01-12 | 9 | 2022-03-03 | 34 | 2022-03-03 | 2022-03-29 | 18 | [22 empty] | 2021-12-30 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2891 | PGE | 93640 | NEM | EXPNEM | Study in Progress | Solar PV | 987.5 |  | 2021-12-30 | 2021-12-31 | 1 | 2022-01-12 | 9 | 2022-03-03 | 34 | 2022-03-03 | 2022-03-29 | 18 | [22 empty] | 2021-12-30 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2892 | PGE | 95212 | NEM | EXPNEM | Application Review in Progress | Solar PV | 195.956 |  | 2021-12-30 | 2022-01-13 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2894 | PGE | 93640 | NEM | EXPNEM | Study in Progress | Solar PV | 750 |  | 2021-12-30 | 2021-12-31 | 1 | 2022-01-14 | 11 | 2022-02-01 | 11 | 2022-02-01 | 2022-03-02 | 20 | 2022-03-02 | 2022-03-23 | 15 | 2022-03-23 | [18 empty] | 2021-12-30 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2895 | PGE | 95612 | NEM | EXPNEM | Application Review in Progress | Solar PV | 36.312 |  | 2021-12-30 | 2022-01-13 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2896 | PGE | 93308 | NEM | EXPNEM | IA in Progress | Solar PV | 83.702 |  | 2021-12-30 | 2022-01-13 | 10 | 2022-01-21 | 15 | 2022-02-07 | 11 | [15 empty] | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2897 | PGE | 93308 | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-12-30 | 2022-01-13 | 10 | 2022-01-24 | 16 | 2022-02-07 | 10 | [15 empty] | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2898 | PGE | 95612 | NEM | EXPNEM | Withdrawn | Solar PV | 36.312 |  | 2021-12-31 | 2022-01-13 | 9 | 2022-01-13 | 9 | [27 empty] | 2021-12-31 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2899 | PGE | 96080 | NEM | EXPNEM | Study in Progress | Solar PV | 32.011 |  | 2021-12-31 | 2022-01-14 | 10 | 2022-01-14 | 10 | 2022-02-07 | 15 | 2022-02-07 | [24 empty] | 2021-12-31 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2900 | PGE | 95938 | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | 0 | 2022-01-19 | 12 | [15 empty] | 2022-01-19 | 2022-01-19 | 0 | 2022-01-19 | [6 empty] | 2021-12-31 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2901 | PGE | 95973 | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | 0 | 2022-01-18 | 11 | 2022-01-18 | 2022-03-02 | 30 | [12 empty] | 2022-03-02 | 2022-03-02 | 0 | 2022-03-02 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2902 | PGE | 94596 | Non-NEM | Non-Export | Application Accepted | Solar PV | 185.192 |  | 2021-12-31 | 2022-01-04 | 2 | 2022-01-12 | 8 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2903 | PGE | 95963 | NEM | EXPNEM | IA in Progress | Solar PV | 30.639 |  | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | 0 | 2022-01-19 | 12 | [15 empty] | 2022-01-19 | 2022-01-19 | 0 | 2022-01-19 | [6 empty] | 2021-12-31 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2904 | PGE | 94503 | NEM | EXPNEM | Implementation | Solar PV | 480 |  | 2021-12-31 | 2022-01-12 | 8 | 2022-01-12 | 8 | 2022-02-01 | 13 | [15 empty] | 2022-02-01 | 2022-02-01 | 0 | 2022-02-01 | 2022-02-01 | 0 |  |  |  |  | 2021-12-31 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2905 | PGE | 95932 | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-12-31 | 2022-01-12 | 8 | 2022-01-12 | 8 | 2022-01-31 | 12 | [15 empty] | 2022-01-31 | 2022-02-16 | 12 | 2022-02-16 | [6 empty] | 2021-12-31 | 0 |  | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2906 | PGE | 94503 | NEM | EXPNEM | Implementation | Solar PV | 660 |  | 2021-12-31 | 2022-01-12 | 8 | 2022-01-12 | 8 | 2022-01-31 | 12 | [15 empty] | 2022-01-31 | 2022-02-01 | 1 | 2022-02-01 | 2022-02-01 | 0 |  |  |  |  | 2021-12-31 | 0 |  | 2022-03-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2907 | PGE | 95938 | NEM | EXPNEM | Study in Progress | Solar PV | 33.3 |  | 2021-12-31 | 2022-01-11 | 7 | 2022-01-31 | 20 | 2022-02-14 | 10 | 2022-02-14 | 2022-03-29 | 30 | 2022-03-29 | [21 empty] | 2021-12-31 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2908 | PGE | 94574 | NEM | NEMMT | Application Accepted | FUCE, Solar PV, Storage | 1715 |  | 2021-12-31 | 2022-01-04 | 2 | 2022-02-02 | 22 | [27 empty] | 2021-12-31 | 0 | [8 empty] | 2022-04-05 | 2022-04-07 | 2 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2909 | PGE | 93446 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 1446.5 |  | 2021-12-31 | 2022-01-04 | 2 | 2022-03-01 | 40 | 2022-03-22 | 15 | 2022-03-22 | [24 empty] | 2021-12-31 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2910 | PGE | 93446 | NEM | EXPNEM | IA in Progress | Solar PV | 389.006 |  | 2021-12-31 | 2022-01-12 | 8 | 2022-01-12 | 8 | 2022-01-27 | 10 | [15 empty] | 2022-01-27 | 2022-02-04 | 6 | 2022-02-04 | [6 empty] | 2021-12-31 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2912 | PGE | 93608 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-12-28 | 2022-01-03 | 4 | 2022-01-03 | 4 | 2022-01-13 | 8 | [18 empty] | 2021-12-28 | 2021-12-29 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-03-21 |  | 2022-03-21 | 1 | 1//19
2913 | PGE | 94538 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1798.9 |  | 2021-10-19 | 2021-10-27 | 6 | 2021-12-15 | 38 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2914 | PGE | 93249 | NEM | NEMMT | Withdrawn | FUCE, Solar PV | 28650 |  | 2021-12-02 | 2021-12-02 | 0 | 2022-01-19 | 33 | [5 empty] | 2022-01-19 | 2022-03-04 | 31 | 2022-03-04 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2915 | PGE | 93306 | NEM | VNEM | Study in Progress | Solar PV | 134.823 |  | 2021-12-17 | 2021-12-31 | 10 | 2022-02-09 | 37 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2916 | PGE | 95334 | NEM | EXPNEM | Application Review in Progress | Solar PV | 187.5 |  | 2021-12-23 | 2022-01-06 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2917 | PGE | 93422 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-12-16 | 2021-12-24 | 6 | 2021-12-24 | 6 | 2021-12-27 | 1 | [18 empty] | 2021-12-16 | 2021-12-24 | 6 | [5 empty] | 0 | [5 empty] | 2022-01-26 | 2022-01-27 | 1 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-26 | 2022-01-27 | 1 | 2022-01-27 |  | 2022-02-01 | 3 | 1//19
2918 | PGE | 95441 | NEM | EXPNEM | Commercial | Solar PV | 56.906 |  | 2021-12-14 | 2021-12-23 | 7 | 2021-12-23 | 7 | 2022-01-07 | 11 | [15 empty] | 2022-01-07 | 2022-01-11 | 2 | 2022-01-11 | 2022-01-11 | 0 | [5 empty] | 0 | [5 empty] | 2022-01-12 | 2022-01-26 | 9 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-12 | 2022-01-12 | 0 | 2022-01-26 |  | 2022-01-27 | 1 | 1//19
2919 | PGE | 93960 | NEM | NEMMT | Study in Progress | Solar PV, Storage, WIND | 3198.65 |  | 2021-12-22 | 2021-12-22 | 0 | 2022-01-05 | 10 | [5 empty] | 2022-01-05 | 2022-02-16 | 29 | 2022-02-16 | 2022-02-17 | 1 |  |  |  | 2022-02-17 | [12 empty] | 2021-12-22 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2920 | PGE | 95112 | NEM | EXPNEM | Study in Progress | Solar PV | 66.6 |  | 2021-12-15 | 2021-12-21 | 4 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2921 | PGE | 93656 | NEM | NEMMT | Study in Progress | Solar PV, Storage | 138.166 |  | 2021-12-10 | 2021-12-13 | 1 | 2022-03-04 | 58 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2922 | PGE | 95472 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 37.632 |  | 2021-12-28 | 2022-01-03 | 4 | 2022-02-09 | 30 | 2022-03-14 | 22 | [15 empty] | 2022-03-14 | 2022-03-14 | 0 | 2022-03-14 | 2022-03-16 | 2 |  |  |  |  | 2021-12-28 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2923 | PGE | 94704 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 538.367 |  | 2021-12-22 | 2022-01-05 | 10 | 2022-01-24 | 22 | [28 empty] | 0 |  |  | 2022-01-24 | [8 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2924 | PGE | 93637 | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-12-13 | 2021-12-27 | 10 | 2022-02-03 | 37 | 2022-02-24 | 14 | [15 empty] | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-03 | 5 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2925 | PGE | 93446 | NEM | EXPNEM | Implementation | Solar PV | 53.35 |  | 2021-12-13 | 2021-12-27 | 10 | 2021-12-27 | 10 | 2022-02-11 | 33 | [15 empty] | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | 2022-02-15 | 2 | [5 empty] | 0 | [8 empty] | 2022-03-25 |  | 13 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2926 | PGE | 93923 | Non-NEM | Non-Export | Study in Progress | Storage | 3.84 |  | 2021-12-16 | 2021-12-30 | 10 | 2021-12-30 | 10 | 2022-01-28 | 20 | [18 empty] | 2021-12-15 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2927 | PGE | 95334 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-12-20 | 2021-12-31 | 9 | 2022-01-04 | 11 | 2022-01-24 | 13 | [15 empty] | 2022-01-24 | 2022-01-24 | 0 | 2022-01-24 | 2022-03-21 | 39 |  |  |  |  | 2021-12-20 | 0 | [5 empty] | 2022-03-24 | 2022-03-29 | 3 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-24 | 2022-03-25 | 1 | 2022-03-29 |  | 2022-03-31 | 2 | 1//19
2928 | PGE | 95726 | NEM | EXPNEM | Implementation | Solar PV | 98.329 |  | 2021-12-12 | 2021-12-24 | 9 | 2022-01-20 | 27 | 2022-02-10 | 15 | [15 empty] | 2022-02-10 | 2022-02-10 | 0 | 2022-02-10 | 2022-02-25 | 10 |  |  |  |  | 2021-12-12 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2929 | PGE | 94401 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 241.771 |  | 2021-12-27 | 2021-12-30 | 3 | 2022-01-20 | 17 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2930 | PGE | 94568 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 125.1 |  | 2021-12-14 | 2021-12-21 | 5 | 2022-01-20 | 26 | 2022-03-16 | 38 | 2022-03-28 | [17 empty] | 2021-12-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2931 | PGE | 94568 | NEM | NEMMT | IA in Progress | Solar PV, Storage | 118.3 |  | 2021-12-14 | 2021-12-28 | 10 | 2022-01-24 | 28 | 2022-02-16 | 17 | [15 empty] | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16 | [7 empty] | 0 |  | 2022-01-31 | 2022-02-02 | 2022-02-16 | 2 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2932 | PGE | 95453 | NEM | EXPNEM | Implementation | Solar PV | 330 |  | 2021-12-14 | 2021-12-17 | 3 | 2021-12-27 | 9 | 2022-03-07 | 48 | [15 empty] | 2022-03-07 | 2022-03-07 | 0 | 2022-03-07 | 2022-03-16 | 7 |  |  |  |  | 2021-12-14 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2933 | PGE | 95453 | NEM | EXPNEM | IA in Progress | Solar PV | 132 |  | 2021-12-14 | 2021-12-27 | 9 | 2022-02-03 | 36 | 2022-02-25 | 15 | 2022-02-25 | 2022-03-24 | 19 | [12 empty] | 2022-03-24 | 2022-03-24 | 0 | 2022-03-24 | [6 empty] | 2021-12-14 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2934 | PGE | 94507 | Non-NEM | Non-Export | IA in Progress | Storage | 7.68 |  | 2021-12-14 | 2021-12-14 | 0 | 2021-12-16 | 2 | 2021-12-21 | 3 | [15 empty] | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 2021-12-15 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2935 | PGE | 95963 | NEM | EXPNEM | Study in Progress | Solar PV | 79.763 |  | 2021-12-16 | 2021-12-20 | 2 | 2021-12-20 | 2 | 2022-01-03 | 10 | 2022-01-05 | 2022-02-22 | 32 | 2022-02-24 | 2022-03-21 | 17 | 2022-03-21 | 2022-03-29 | 6 |  |  |  | 2022-03-29 | [13 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2936 | PGE | 95060 | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 |  | 2021-12-18 | 2021-12-23 | 3 | 2022-01-28 | 28 | 2022-02-15 | 12 | [15 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | [6 empty] | 2021-12-27 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2937 | PGE | 93446 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-12-14 | 2021-12-24 | 8 | 2021-12-24 | 8 | 2021-12-27 | 1 | [18 empty] | 2021-12-13 | 2021-12-24 | 9 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2938 | PGE | 95037 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 1150 |  | 2021-12-20 | 2022-01-03 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2939 | PGE | 93654 | NEM | EXPNEM | Implementation | Solar PV | 47.332 |  | 2021-12-14 | 2021-12-15 | 1 | 2021-12-17 | 3 | 2021-12-29 | 8 | 2022-01-19 | 2022-02-03 | 11 | [12 empty] | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | 2022-02-25 | 15 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2940 | PGE | 93630 | NEM | EXPNEM | IA in Progress | Solar PV | 642.832 |  | 2021-12-16 | 2021-12-17 | 1 | 2021-12-17 | 1 | 2022-01-03 | 11 | 2022-01-03 | 2022-01-28 | 18 | [12 empty] | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | [6 empty] | 2021-12-16 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2941 | PGE | 93311 | NEM | VNEM | Application Review in Progress | Solar PV | 58.04 |  | 2021-12-14 | 2021-12-27 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2942 | PGE | 94547 | NEM | NEMMT | Study in Progress | FUCE, Solar PV | 300 |  | 2021-12-20 | 2021-12-29 | 7 | 2021-12-29 | 7 | 2022-01-13 | 11 | 2022-01-14 | 2022-02-04 | 14 | 2022-02-04 | 2022-02-28 | 15 | 2022-02-28 | 2022-03-01 | 1 |  |  |  | 2022-03-01 | [13 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2943 | PGE | 95688 | NEM | EXPNEM | IA in Progress | Solar PV | 510 |  | 2021-12-14 | 2021-12-16 | 2 | 2021-12-27 | 9 | 2022-01-11 | 11 | [15 empty] | 2022-01-11 | 2022-01-11 | 0 | 2022-01-11 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2944 | PGE | 94538 | NEM | EXPNEM | Application Review in Progress | Solar PV | 300.221 |  | 2021-12-14 | 2021-12-28 | 10 | [29 empty] | 2021-12-14 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2945 | PGE | 95076 | NEM | EXPNEM | Withdrawn | Solar PV | 191.062 |  | 2021-12-30 | 2022-01-13 | 10 | 2022-01-28 | 20 | 2022-02-18 | 15 | [15 empty] | 2022-02-18 | [10 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2946 | PGE | 95460 | NEM | EXPNEM | Withdrawn | Solar PV | 183.3 |  | 2021-12-27 | 2021-12-28 | 1 | 2022-01-03 | 5 | 2022-03-07 | 43 | [26 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2947 | PGE | 94010 | NEM | EXPNEM | Application Review in Progress | Solar PV | 341.891 |  | 2021-12-15 | 2021-12-20 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2948 | PGE | 94534 | NEM | EXPNEM | IA in Progress | Solar PV | 175.486 |  | 2021-12-28 | 2021-12-29 | 1 | 2021-12-29 | 1 | 2022-01-18 | 13 | [15 empty] | 2022-01-18 | 2022-01-18 | 0 | 2022-01-18 | [6 empty] | 2021-12-28 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2949 | PGE | 94534 | NEM | EXPNEM | IA in Progress | Solar PV | 312 |  | 2021-12-28 | 2021-12-29 | 1 | 2021-12-29 | 1 | 2022-01-18 | 13 | [15 empty] | 2022-01-18 | 2022-01-18 | 0 | 2022-01-18 | [6 empty] | 2021-12-28 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2950 | PGE | 94080 | NEM | EXPNEM | Implementation | Solar PV | 215.378 |  | 2021-12-15 | 2021-12-29 | 10 | 2022-02-23 | 48 | 2022-03-16 | 15 | [15 empty] | 2022-03-16 | 2022-03-21 | 3 | 2022-03-21 | 2022-03-24 | 3 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2951 | PGE | 95060 | NEM | EXPNEM | Study in Progress | Solar PV | 130.48 |  | 2021-12-27 | 2022-01-10 | 10 | 2022-03-28 | 63 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2952 | PGE | 93905 | NEM | EXPNEM | IA in Progress | Solar PV | 36.54 |  | 2021-12-18 | 2021-12-30 | 8 | 2021-12-30 | 8 | 2022-01-21 | 15 | [15 empty] | 2022-01-21 | 2022-01-21 | 0 | 2022-01-21 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2953 | PGE | 93455 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 51.356 |  | 2021-12-17 | 2021-12-20 | 1 | 2022-01-05 | 13 | 2022-01-24 | 12 | [15 empty] | 2022-01-24 | 2022-01-24 | 0 | 2022-01-24 | 2022-01-24 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2954 | PGE | 94558 | NEM | EXPNEM | Implementation | Solar PV | 50 |  | 2021-12-28 | 2022-01-11 | 10 | 2022-01-11 | 10 | 2022-02-02 | 15 | [15 empty] | 2022-02-02 | 2022-02-03 | 1 | 2022-02-03 | 2022-02-14 | 7 |  |  |  |  | 2021-12-28 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2955 | PGE | 93640 | NEM | EXPNEM | Withdrawn | Solar PV | 317414.24 |  | 2021-12-22 | 2021-12-28 | 4 | 2022-01-26 | 24 | [5 empty] | 2022-01-26 | 2022-03-01 | 23 | 2022-03-01 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2956 | PGE | 93636 | NEM | EXPNEM | Commercial | Solar PV | 250 |  | 2021-12-30 | 2022-01-10 | 7 | 2022-01-26 | 18 | 2022-02-09 | 10 | [15 empty] | 2022-02-09 | 2022-02-09 | 0 | 2022-02-09 | 2022-02-15 | 4 | [5 empty] | 0 | [5 empty] | 2022-02-16 | 2022-02-24 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-16 | 2022-02-17 | 1 | 2022-02-24 |  | 2022-02-25 | 1 | 1//19
2957 | PGE | 93638 | NEM | EXPNEM | IA in Progress | Solar PV | 187.5 |  | 2021-12-20 | 2022-01-03 | 10 | 2022-01-03 | 10 | 2022-01-21 | 13 | 2022-01-21 | 2022-02-18 | 20 | [12 empty] | 2022-02-18 | 2022-02-24 | 3 | 2022-02-24 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2958 | PGE | 93210 | NEM | EXPNEM | Application Review in Progress | Solar PV | 862.5 |  | 2021-12-21 | 2022-01-04 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2959 | PGE | 93455 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 242.006 |  | 2021-12-29 | 2022-01-12 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2960 | PGE | 95023 | NEM | EXPNEM | Implementation | Solar PV | 400.816 |  | 2021-12-20 | 2021-12-30 | 8 | 2021-12-30 | 8 | 2022-01-04 | 3 | [15 empty] | 2022-01-04 | 2022-01-13 | 7 | 2022-01-13 | 2022-03-15 | 41 |  |  |  |  | 2021-12-20 | 0 |  | 2022-01-06 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2961 | PGE | 96092 | NEM | EXPNEM | Application Accepted | Solar PV | 1145.473 |  | 2021-12-20 | 2021-12-22 | 2 | 2022-01-05 | 12 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2962 | PGE | 94030 | NEM | EXPNEM | IA in Progress | Solar PV | 280.756 |  | 2021-12-27 | 2022-01-05 | 7 | 2022-01-05 | 7 | 2022-01-24 | 12 | [15 empty] | 2022-01-24 | 2022-01-24 | 0 | 2022-01-24 | [7 empty] | 0 |  | 2022-01-11 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2963 | PGE | 93263 | NEM | EXPNEM | IA in Progress | Solar PV | 687.5 |  | 2021-12-20 | 2022-01-03 | 10 | 2022-01-03 | 10 | 2022-01-25 | 15 | [15 empty] | 2022-01-25 | 2022-02-15 | 15 | 2022-02-15 | [6 empty] | 2021-12-20 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2964 | PGE | 93280 | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-12-20 | 2022-01-03 | 10 | 2022-01-03 | 10 | 2022-01-25 | 15 | [15 empty] | 2022-01-25 | 2022-02-15 | 15 | 2022-02-15 | [6 empty] | 2021-12-20 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2965 | PGE | 93280 | NEM | EXPNEM | IA in Progress | Solar PV | 375 |  | 2021-12-20 | 2021-12-21 | 1 | 2022-01-05 | 12 | 2022-01-27 | 15 | [15 empty] | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | [6 empty] | 2021-12-20 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2966 | PGE | 93280 | NEM | EXPNEM | IA in Progress | Solar PV | 875 |  | 2021-12-20 | 2021-12-21 | 1 | 2021-12-27 | 5 | 2022-01-11 | 11 | [15 empty] | 2022-01-11 | 2022-01-11 | 0 | 2022-01-11 | [6 empty] | 2021-12-20 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2967 | PGE | 93250 | NEM | EXPNEM | IA in Progress | Solar PV | 562.5 |  | 2021-12-20 | 2021-12-21 | 1 | 2022-01-05 | 12 | 2022-01-27 | 15 | [15 empty] | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | [6 empty] | 2021-12-20 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2968 | PGE | 93263 | NEM | EXPNEM | IA in Progress | Solar PV | 125 |  | 2021-12-20 | 2021-12-21 | 1 | 2021-12-27 | 5 | 2022-01-10 | 10 | [15 empty] | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | [6 empty] | 2021-12-20 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2969 | PGE | 93250 | NEM | EXPNEM | IA in Progress | Solar PV | 187.5 |  | 2021-12-20 | 2021-12-21 | 1 | 2021-12-27 | 5 | 2022-01-10 | 10 | [15 empty] | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | [6 empty] | 2021-12-20 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2970 | PGE | 93250 | NEM | EXPNEM | IA in Progress | Solar PV | 375 |  | 2021-12-20 | 2021-12-21 | 1 | 2022-01-05 | 12 | 2022-01-27 | 15 | [15 empty] | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | [6 empty] | 2021-12-20 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2971 | PGE | 93420 | Non-NEM | Inadvertent Export | Commercial | Storage | 5 |  | 2021-12-20 | 2021-12-21 | 1 | 2021-12-21 | 1 | 2021-12-27 | 4 | [18 empty] | 2021-12-17 | 2021-12-17 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-02-03 |  | 2022-02-03 | 1 | 1//19
2972 | PGE | 95988 | NEM | EXPNEM | IA in Progress | Solar PV | 74.59 |  | 2021-12-20 | 2021-12-31 | 9 | 2022-02-15 | 40 | 2022-03-04 | 12 | [15 empty] | 2022-03-04 | 2022-03-04 | 0 | 2022-03-04 | [6 empty] | 2021-12-20 | 0 |  | 2022-01-11 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2973 | PGE | 93280 | NEM | EXPNEM | IA in Progress | Solar PV | 875 |  | 2021-12-20 | 2021-12-21 | 1 | 2022-01-05 | 12 | 2022-01-27 | 15 | [15 empty] | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | [6 empty] | 2021-12-20 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2974 | PGE | 94533 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-12-28 | 2022-01-10 | 9 | 2022-02-07 | 28 | 2022-03-01 | 15 | [15 empty] | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | [6 empty] | 2021-12-28 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2975 | PGE | 93250 | NEM | EXPNEM | IA in Progress | Solar PV | 437.5 |  | 2021-12-20 | 2021-12-21 | 1 | 2022-01-05 | 12 | 2022-01-27 | 15 | [15 empty] | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | [6 empty] | 2021-12-20 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2976 | PGE | 95037 | NEM | EXPNEM | IA in Progress | Solar PV | 145.259 |  | 2021-12-18 | 2021-12-23 | 3 | 2022-01-11 | 16 | 2022-01-26 | 10 | [15 empty] | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | [6 empty] | 2021-12-18 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2977 | PGE | 95119 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-12-18 | 2021-12-23 | 3 | 2022-01-11 | 16 | 2022-01-26 | 10 | [15 empty] | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | [6 empty] | 2021-12-18 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2978 | PGE | 95125 | NEM | EXPNEM | IA in Progress | Solar PV | 276 |  | 2021-12-18 | 2021-12-30 | 8 | 2022-01-18 | 20 | 2022-03-23 | 45 | [15 empty] | 2022-03-23 | 2022-03-23 | 0 | 2022-03-23 | [6 empty] | 2021-12-18 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2979 | PGE | 94019 | NEM | EXPNEM | IA in Progress | Solar PV | 296.468 |  | 2021-12-20 | 2022-01-03 | 10 | 2022-02-16 | 41 | 2022-03-24 | 25 | [15 empty] | 2022-03-24 | 2022-03-24 | 0 | 2022-03-24 | [6 empty] | 2021-12-20 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2980 | PGE | 95570 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 10 |  | 2021-12-21 | 2022-01-04 | 10 | [22 empty] | 2021-12-20 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2981 | PGE | 93908 | NEM | EXPNEM | Study in Progress | Solar PV | 241.512 |  | 2021-12-21 | 2022-01-03 | 9 | 2022-01-19 | 20 | [27 empty] | 2022-01-04 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2982 | PGE | 95060 | NEM | EXPNEM | Implementation | Solar PV | 31.186 |  | 2021-12-22 | 2022-01-05 | 10 | 2022-02-04 | 31 | 2022-02-28 | 15 | [15 empty] | 2022-02-28 | 2022-02-28 | 0 | 2022-02-28 | 2022-03-18 | 14 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2983 | PGE | 93314 | NEM | EXPNEM | IA in Progress | Solar PV | 115.42 |  | 2021-12-21 | 2022-01-03 | 9 | 2022-01-03 | 9 | 2022-01-10 | 5 | [15 empty] | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2984 | PGE | 94536 | NEM | VNEM | Application Review in Progress | Solar PV | 400 |  | 2021-12-23 | 2021-12-24 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2985 | PGE | 96080 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 42.978 |  | 2021-12-21 | 2021-12-31 | 8 | 2022-01-13 | 17 | 2022-02-04 | 15 | [15 empty] | 2022-02-04 | 2022-02-04 | 0 | 2022-02-04 | [6 empty] | 2021-12-21 | 0 |  |  | 2022-02-15 | 2022-02-17 | 2 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2986 | PGE | 95134 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1387.5 |  | 2021-12-29 | 2021-12-30 | 1 | 2022-01-26 | 19 | [27 empty] | 2021-12-29 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2987 | PGE | 95409 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-12-22 | 2022-01-03 | 8 | 2022-01-03 | 8 | 2022-01-05 | 2 | [18 empty] | 2021-12-21 | 2021-12-22 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2988 | PGE | 93245 | NEM | EXPNEM | Implementation | Solar PV | 205.259 |  | 2021-12-28 | 2022-01-03 | 4 | 2022-01-03 | 4 | 2022-01-31 | 19 | [15 empty] | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | 2022-02-28 | 19 |  |  |  |  | 2021-12-28 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2989 | PGE | 95330 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2539.1 |  | 2021-12-22 | 2021-12-23 | 1 | 2022-03-01 | 47 | [5 empty] | 2022-03-01 | 2022-03-28 | 19 | 2022-03-28 | [5 empty] | 2022-03-28 | 2022-03-28 | 1 | [11 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2990 | PGE | 95695 | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-12-23 | 2021-12-27 | 2 | 2022-01-18 | 17 | 2022-03-17 | 41 | [15 empty] | 2022-03-17 | 2022-03-17 | 0 | 2022-03-17 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2991 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 41.795 |  | 2021-12-23 | 2021-12-24 | 1 | 2022-01-10 | 12 | 2022-01-31 | 14 | [15 empty] | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [6 empty] | 2021-12-23 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2992 | PGE | 95401 | NEM | EXPNEM | Implementation | Solar PV | 349.55 |  | 2021-12-27 | 2021-12-28 | 1 | 2021-12-28 | 1 | 2022-01-03 | 4 | [15 empty] | 2022-01-03 | 2022-01-05 | 2 | 2022-01-05 | 2022-01-20 | 10 |  |  |  |  | 2021-12-27 | 0 | [5 empty] | 2022-01-21 | 2022-02-01 | 7 | 2022-02-08 |  | 46 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-21 | 2022-01-21 | 0 | 2022-02-01 | 2022-02-02 |  | 1 | 1//19 |  | 26
2993 | PGE | 93608 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-12-28 | 2022-01-10 | 9 | 2022-01-21 | 17 | 2022-02-02 | 8 | [18 empty] | 2021-12-28 | 2021-12-28 | 0 | [5 empty] | 0 | [5 empty] | 2022-02-16 | 2022-02-17 | 1 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-16 | 2022-02-17 | 1 | 2022-02-17 |  | 2022-02-17 | 0 | 1//19
2994 | PGE | 93722 | NEM | VNEM | IA in Progress | Solar PV | 186.204 |  | 2021-12-30 | 2022-01-13 | 10 | 2022-02-01 | 22 | 2022-02-23 | 15 | [15 empty] | 2022-02-23 | 2022-02-23 | 0 | 2022-02-23 | 2022-03-07 | 8 |  |  |  |  | 2021-12-30 | 0 |  |  | 2022-02-23 | 2022-02-23 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2995 | PGE | 95330 | NEM | EXPNEM | Study in Progress | Solar PV | 588.164 |  | 2021-12-29 | 2022-01-12 | 10 | 2022-03-10 | 49 | 2022-03-29 | 13 | 2022-03-29 | [24 empty] | 2021-12-29 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2996 | PGE | 95131 | NEM | EXPNEM | Implementation | Solar PV | 869.259 |  | 2021-12-30 | 2022-01-10 | 7 | 2022-01-28 | 20 | 2022-02-14 | 11 | [15 empty] | 2022-02-14 | 2022-02-14 | 0 | 2022-02-14 | 2022-02-22 | 5 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2997 | PGE | 95134 | NEM | EXPNEM | IA in Progress | Solar PV | 454.226 |  | 2021-12-30 | 2022-01-13 | 10 | 2022-02-04 | 25 | 2022-02-28 | 15 | [15 empty] | 2022-02-28 | 2022-02-28 | 0 | 2022-02-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2998 | PGE | 94558 | NEM | VNEM | Application Review in Progress | Solar PV | 278.108 |  | 2021-12-29 | 2022-01-12 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
2999 | PGE | 93608 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-12-30 | 2022-01-03 | 2 | 2022-01-03 | 2 | 2022-01-13 | 8 | [18 empty] | 2021-12-30 | 2021-12-28 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-02-16 |  | 2022-02-16 | 1 | 1//19
3000 | PGE | 94085 | NEM | EXPNEM | Application Review in Progress | Solar PV | 40.252 |  | 2021-12-29 | 2022-01-11 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3001 | PGE | 93711 | NEM | VNEM | Application Review in Progress | Solar PV | 182.942 |  | 2021-12-29 | 2022-01-12 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3002 | PGE | 94533 | NEM | EXPNEM | Study in Progress | Solar PV | 276 |  | 2021-12-31 | 2022-01-14 | 10 | 2022-01-31 | 20 | [27 empty] | 2021-12-31 | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3003 | PGE | 93422 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-12-31 | 2022-01-13 | 9 | 2022-01-13 | 9 | 2022-02-04 | 15 | [18 empty] | 2021-12-29 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3004 | PGE | 93618 | NEM | EXPNEM | IA in Progress | Solar PV | 275 |  | 2021-12-31 | 2022-01-14 | 10 | 2022-02-25 | 38 | 2022-03-18 | 15 | [15 empty] | 2022-03-18 | [10 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3006 | PGE | 95008 | NEM | SNEM Paired Storage | Withdrawn | Solar PV, Storage | 30.22 |  | 2021-04-06 | 2021-04-09 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3007 | PGE | 95762 | NEM | EXPNEM | Withdrawn | Solar PV | 31.4 |  | 2021-09-27 | 2021-10-08 | 9 | 2021-10-08 | 9 | 2021-10-29 | 15 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3008 | PGE | 94568 | NEM | EXPNEM | Application Review in Progress | Solar PV | 47.926 |  | 2021-10-14 | 2021-10-22 | 6 | [22 empty] | 2021-10-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3009 | PGE | 94563 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.163 |  | 2021-11-24 | 2021-11-29 | 1 | 2021-12-17 | 15 | 2022-01-20 | 23 | [18 empty] | 2021-11-24 | [7 empty] | 0 | [5 empty] | 2022-01-20 | 2022-01-20 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-20 |  |  | 2022-01-20 |  | 2022-01-20 | 0 | 1//19
3010 | PGE | 94549 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 32.68 |  | 2021-11-30 | 2021-11-30 | 0 | 2021-12-02 | 2 | 2021-12-06 | 2 | [18 empty] | 2021-11-30 | [6 empty] | 2021-11-30 | 2021-11-30 | 1 |  |  |  |  | 2022-03-14 | 2022-03-25 | 9 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-14 | 2022-03-14 | 0 | 2022-03-25 |  | 2022-03-29 | 2 | 1//19
3011 | PGE | 95060 | NEM | NEMMT | IA in Progress | FUCE, OTHR, Solar PV | 171.104 |  | 2021-12-07 | 2021-12-10 | 3 | 2021-12-22 | 11 | 2022-03-15 | 57 | [15 empty] | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3012 | PGE | 95304 | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-12-08 | 2021-12-22 | 10 | 2021-12-22 | 10 | 2022-01-26 | 24 | [15 empty] | 2022-01-26 | 2022-02-16 | 15 | 2022-02-16 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3013 | PGE | 94118 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-12-09 | 2021-12-22 | 9 | 2022-01-11 | 23 | 2022-01-27 | 11 | [15 empty] | 2022-01-27 | 2022-02-11 | 11 | 2022-02-11 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3014 | PGE | 94086 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 800 |  | 2022-02-11 | 2022-02-25 | 9 | 2022-03-24 | 28 | [27 empty] | 2022-02-11 | 2022-02-11 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3015 | PGE | 93631 | NEM | EXPNEM | Study in Progress | Solar PV | 5760 |  | 2022-01-17 | 2022-01-24 | 4 | 2022-02-09 | 16 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3016 | PGE | 95062 | NEM | EXPNEM | Application Review in Progress | Solar PV | 62.5 |  | 2022-03-21 | 0 | [30 empty] | 2022-03-21 | 2022-03-21 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3017 | PGE | 94086 | NEM | EXPNEM | IA in Progress | Solar PV | 166.4 |  | 2022-01-20 | 2022-01-25 | 3 | 2022-02-10 | 15 | 2022-03-04 | 15 | [15 empty] | 2022-03-04 | 2022-03-04 | 0 | 2022-03-04 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3018 | PGE | 95726 | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2022-01-05 | 2022-01-14 | 7 | 2022-01-31 | 17 | 2022-02-23 | 16 | [15 empty] | 2022-02-23 | 2022-02-23 | 0 | 2022-02-23 | 2022-02-25 | 2 |  |  |  |  | 2022-01-05 | 2022-01-05 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3019 | PGE | 94530 | NEM | EXPNEM | Study in Progress | Solar PV | 375 |  | 2022-01-25 | 2022-02-04 | 8 | 2022-02-04 | 8 | [27 empty] | 2022-01-25 | 2022-01-25 | 1 | 2022-02-09 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3020 | PGE | 94901 | NEM | EXPNEM | IA in Progress | Solar PV | 312.5 |  | 2022-01-25 | 2022-02-04 | 8 | 2022-02-04 | 8 | 2022-02-25 | 14 | [15 empty] | 2022-02-25 | 2022-03-17 | 14 | 2022-03-17 | [6 empty] | 2022-01-25 | 2022-01-25 | 1 | 2022-02-09 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3021 | PGE | 93455 | NEM | EXPNEM | IA in Progress | Solar PV | 306.889 |  | 2022-01-25 | 2022-02-02 | 6 | 2022-02-17 | 17 | 2022-03-08 | 12 | [15 empty] | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 | [6 empty] | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3022 | PGE | 94014 | NEM | EXPNEM | Study in Progress | Solar PV | 187.5 |  | 2022-01-25 | 2022-02-03 | 7 | 2022-02-17 | 17 | [27 empty] | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3023 | PGE | 95073 | NEM | EXPNEM | IA in Progress | Solar PV | 144.276 |  | 2022-01-21 | 2022-02-02 | 8 | 2022-02-02 | 8 | 2022-03-17 | 30 | [15 empty] | 2022-03-17 | 2022-03-17 | 0 | 2022-03-17 | [6 empty] | 2022-01-21 | 2022-01-21 | 1 | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3024 | PGE | 95062 | NEM | EXPNEM | Application Accepted | Solar PV | 150 |  | 2022-03-09 | 2022-03-22 | 9 | 2022-03-22 | 9 | [27 empty] | 2022-03-09 | 2022-03-09 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3025 | PGE | 95376 | NEM | EXPNEM | Study in Progress | Solar PV | 1875 |  | 2022-01-25 | 2022-01-25 | 0 | 2022-02-09 | 11 | 2022-03-04 | 16 | 2022-03-28 | [24 empty] | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3026 | PGE | 94566 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 816.5 |  | 2022-02-09 | 2022-02-24 | 10 | 2022-02-24 | 10 | [27 empty] | 2022-02-09 | 2022-02-09 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3027 | PGE | 95973 | NEM | SNEM Paired Storage | Withdrawn | Solar PV, Storage | 36.085 |  | 2022-01-20 | 2022-01-27 | 5 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3028 | PGE | 94530 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2022-03-10 | 2022-03-15 | 3 | 2022-03-15 | 3 | 2022-03-21 | 4 | [18 empty] | 2022-03-10 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-03-15 |  | 2022-03-21 | 5 | 1//19
3029 | PGE | 94566 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 720.8 |  | 2022-02-10 | 2022-02-23 | 8 | [29 empty] | 2022-02-10 | 2022-02-10 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3030 | PGE | 94566 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 849.8 |  | 2022-02-10 | 2022-02-24 | 9 | 2022-02-24 | 9 | [27 empty] | 2022-02-10 | 2022-02-10 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3031 | PGE | 93442 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 43.28 |  | 2022-01-14 | 2022-01-25 | 6 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3032 | PGE | 95701 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2022-01-24 | 2022-01-26 | 2 | 2022-01-31 | 5 | 2022-02-02 | 2 | [18 empty] | 2022-01-24 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-01-26 |  | 2022-02-02 | 6 | 1//19
3033 | PGE | 94530 | NEM | EXPNEM | Implementation | Solar PV | 46.061 |  | 2022-01-20 | 2022-01-20 | 0 | 2022-02-04 | 11 | 2022-02-18 | 10 | [15 empty] | 2022-02-18 | 2022-02-18 | 0 | 2022-02-18 | 2022-03-07 | 10 | [5 empty] | 0 |  | 2022-02-10 | 2022-02-18 | 2022-02-18 | 6 | 2022-03-25 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-25 | 2022-03-25 | 0 |  |  |  |  | 1//19
3034 | PGE | 93720 | NEM | EXPNEM | Implementation | Solar PV | 242.735 |  | 2022-01-06 | 2022-01-20 | 9 | 2022-01-20 | 9 | 2022-02-07 | 12 | [15 empty] | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-11 | 4 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3035 | PGE | 95242 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.35 |  | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 0 | 2022-01-12 | 20 | [18 empty] | 2021-12-15 | [7 empty] | 0 | [5 empty] | 2022-01-12 | 2022-01-12 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-12 |  |  | 2022-01-12 |  | 2022-01-12 | 0 | 1//19
3036 | PGE | 95762 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.423 |  | 2021-12-16 | 2021-12-30 | 10 | 2021-12-30 | 10 | 2022-01-11 | 8 | [18 empty] | 2021-12-16 | [7 empty] | 2022-02-23 | [5 empty] | 2022-02-23 | 2022-02-23 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-23 |  |  | 2022-02-23 |  | 2022-02-24 | 1 | 1//19
3037 | PGE | 95252 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 40.35 |  | 2021-12-16 | 2021-12-31 | 11 | 2021-12-31 | 11 | 2022-01-25 | 16 | [18 empty] | 2021-12-16 | [7 empty] | 0 | [5 empty] | 2022-01-25 | 2022-01-25 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-25 |  |  | 2022-01-25 |  | 2022-01-25 | 0 | 1//19
3038 | PGE | 94903 | NEM | EXPNEM | IA in Progress | Solar PV | 233.1 |  | 2022-02-08 | 2022-02-09 | 1 | 2022-02-09 | 1 | 2022-02-24 | 10 | [15 empty] | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3039 | PGE | 94401 | NEM | EXPNEM | Application Review in Progress | Solar PV | 243.9 |  | 2022-01-10 | 2022-01-11 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3040 | PGE | 93725 | NEM | EXPNEM | Implementation | Solar PV | 74.767 |  | 2022-01-06 | 2022-01-06 | 0 | 2022-01-06 | 0 | 2022-01-18 | 7 | [15 empty] | 2022-01-18 | 2022-01-18 | 0 | 2022-01-18 | 2022-01-19 | 1 |  |  |  |  | 2022-01-06 | 2022-01-06 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3041 | PGE | 95401 | NEM | EXPNEM | IA in Progress | Solar PV | 95.483 |  | 2022-01-19 | 2022-01-20 | 1 | 2022-01-28 | 7 | 2022-02-14 | 11 | [15 empty] | 2022-02-14 | 2022-02-14 | 0 | 2022-02-14 | [6 empty] | 2022-01-19 | 2022-01-19 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3042 | PGE | 95401 | NEM | EXPNEM | IA in Progress | Solar PV | 91.944 |  | 2022-01-19 | 2022-01-20 | 1 | 2022-01-28 | 7 | 2022-02-14 | 11 | [15 empty] | 2022-02-14 | 2022-02-14 | 0 | 2022-02-14 | [6 empty] | 2022-01-19 | 2022-01-19 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3043 | PGE | 94517 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.872 |  | 2021-12-17 | 2021-12-31 | 10 | 2021-12-31 | 10 | 2022-01-20 | 13 | [18 empty] | 2021-12-17 | [6 empty] | 2021-12-17 | 2021-12-17 | 1 |  |  |  |  | 2022-03-15 | 2022-03-15 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-15 |  |  | 2022-03-15 |  | 2022-03-15 | 0 | 1//19
3044 | PGE | 95404 | NEM | EXPNEM | IA in Progress | Solar PV | 67.354 |  | 2022-01-11 | 2022-01-26 | 10 | 2022-02-02 | 15 | 2022-02-22 | 13 | [15 empty] | 2022-02-22 | 2022-02-22 | 0 | 2022-02-22 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3045 | PGE | 95407 | NEM | EXPNEM | IA in Progress | Solar PV | 331.056 |  | 2022-01-11 | 2022-01-26 | 10 | 2022-02-02 | 15 | 2022-02-16 | 10 | [15 empty] | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16 | [6 empty] | 2022-01-11 | 2022-01-11 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3046 | PGE | 95403 | NEM | EXPNEM | Study in Progress | Solar PV | 69.849 |  | 2022-01-25 | 2022-02-04 | 8 | 2022-02-04 | 8 | 2022-02-23 | 12 | [25 empty] | 2022-01-25 | 2022-01-25 | 1 | 2022-02-09 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3047 | PGE | 95404 | NEM | EXPNEM | IA in Progress | Solar PV | 67.354 |  | 2022-01-11 | 2022-01-26 | 10 | 2022-02-18 | 27 | 2022-03-14 | 15 | [15 empty] | 2022-03-14 | 2022-03-14 | 0 | 2022-03-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3048 | PGE | 95404 | NEM | EXPNEM | IA in Progress | Solar PV | 44.675 |  | 2022-01-11 | 2022-01-26 | 10 | 2022-02-10 | 21 | 2022-03-21 | 26 | [15 empty] | 2022-03-21 | 2022-03-21 | 0 | 2022-03-21 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3049 | PGE | 95409 | NEM | EXPNEM | IA in Progress | Solar PV | 139.698 |  | 2022-01-11 | 2022-01-25 | 9 | 2022-01-25 | 9 | 2022-02-15 | 15 | [15 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3050 | PGE | 95405 | NEM | EXPNEM | IA in Progress | Solar PV | 155.734 |  | 2022-01-11 | 2022-01-25 | 9 | 2022-01-25 | 9 | 2022-02-15 | 15 | [15 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | [6 empty] | 2022-01-11 | 2022-01-11 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3051 | PGE | 95403 | NEM | EXPNEM | IA in Progress | Solar PV | 149.677 |  | 2022-01-18 | 2022-01-19 | 1 | 2022-01-28 | 8 | 2022-02-14 | 11 | [15 empty] | 2022-02-14 | 2022-02-14 | 0 | 2022-02-14 | [6 empty] | 2022-01-18 | 2022-01-18 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3052 | PGE | 95401 | NEM | EXPNEM | IA in Progress | Solar PV | 134.709 |  | 2022-01-18 | 2022-01-19 | 1 | 2022-01-28 | 8 | 2022-03-14 | 30 | [15 empty] | 2022-03-14 | 2022-03-14 | 0 | 2022-03-14 | [6 empty] | 2022-01-18 | 2022-01-18 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3053 | PGE | 95010 | NEM | EXPNEM | Application Review in Progress | Solar PV | 228.888 |  | 2022-01-24 | 2022-02-07 | 10 | [29 empty] | 2022-01-24 | 2022-01-24 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3054 | PGE | 95403 | NEM | EXPNEM | IA in Progress | Solar PV | 65.47 |  | 2022-01-18 | 2022-01-19 | 1 | 2022-01-19 | 1 | 2022-01-31 | 8 | [15 empty] | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3055 | PGE | 95401 | NEM | EXPNEM | Study in Progress | Solar PV | 523.4 |  | 2022-01-25 | 2022-02-04 | 8 | 2022-02-04 | 8 | [27 empty] | 2022-01-25 | 2022-01-25 | 1 | 2022-02-09 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3056 | PGE | 93212 | NEM | EXPNEM | Application Review in Progress | Solar PV | 56.965 |  | 2022-02-14 | 2022-03-01 | 10 | [29 empty] | 2022-02-14 | 2022-02-14 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3057 | PGE | 94089 | NEM | EXPNEM | Study in Progress | Solar PV | 421.274 |  | 2022-01-13 | 2022-01-21 | 5 | 2022-01-25 | 7 | 2022-03-23 | 40 | 2022-03-23 | [24 empty] | 2022-01-13 | 2022-01-13 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3058 | PGE | 95248 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2022-01-04 | 2022-01-19 | 10 | 2022-01-19 | 10 | 2022-02-04 | 12 | [18 empty] | 2021-11-16 | 2022-01-04 | 33 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3059 | PGE | 93461 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.846 |  | 2022-02-14 | 2022-02-15 | 1 | [22 empty] | 2022-02-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3060 | PGE | 95033 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.512 |  | 2022-03-16 | 2022-03-30 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3061 | PGE | 95405 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 599.246 |  | 2022-01-27 | 2022-02-07 | 7 | [29 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3062 | PGE | 95409 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 529.396 |  | 2022-01-11 | 2022-01-24 | 8 | 2022-01-24 | 8 | [27 empty] | 2022-01-11 | 2022-01-11 | 1 | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3063 | PGE | 94605 | NEM | EXPNEM | Application Review in Progress | Solar PV | 105.621 |  | 2022-01-10 | 2022-01-24 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3064 | PGE | 95403 | NEM | EXPNEM | Study in Progress | Solar PV | 348.498 |  | 2022-01-25 | 2022-01-26 | 1 | 2022-03-17 | 36 | [27 empty] | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3065 | PGE | 93305 | NEM | EXPNEM | Implementation | Solar PV | 50 |  | 2022-01-26 | 2022-02-03 | 6 | 2022-02-09 | 10 | 2022-03-03 | 15 | [15 empty] | 2022-03-03 | 2022-03-03 | 0 | 2022-03-03 | 2022-03-14 | 7 |  |  |  |  | 2022-01-26 | 2022-01-26 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3066 | PGE | 95020 | NEM | EXPNEM | IA in Progress | Solar PV | 69.849 |  | 2022-01-11 | 2022-01-12 | 1 | 2022-01-25 | 9 | 2022-02-10 | 12 | [15 empty] | 2022-02-10 | 2022-02-10 | 0 | 2022-02-10 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3067 | PGE | 95020 | NEM | EXPNEM | IA in Progress | Solar PV | 69.711 |  | 2022-01-11 | 2022-01-12 | 1 | 2022-01-25 | 9 | 2022-02-10 | 12 | [15 empty] | 2022-02-10 | 2022-02-10 | 0 | 2022-02-10 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3068 | PGE | 95020 | NEM | EXPNEM | IA in Progress | Solar PV | 41.366 |  | 2022-01-11 | 2022-01-12 | 1 | 2022-01-25 | 9 | 2022-02-24 | 21 | [15 empty] | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3069 | PGE | 95407 | NEM | EXPNEM | IA in Progress | Solar PV | 205.206 |  | 2022-01-11 | 2022-01-26 | 10 | 2022-01-28 | 12 | 2022-02-18 | 15 | [15 empty] | 2022-02-18 | 2022-03-14 | 15 | 2022-03-14 | [6 empty] | 2022-01-11 | 2022-01-11 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3070 | PGE | 95020 | NEM | EXPNEM | Study in Progress | Solar PV | 49.892 |  | 2022-01-11 | 2022-01-21 | 7 | 2022-01-21 | 7 | [27 empty] | 2022-01-11 | 2022-01-11 | 1 | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3071 | PGE | 95020 | NEM | EXPNEM | IA in Progress | Solar PV | 827.64 |  | 2022-01-19 | 2022-01-26 | 5 | 2022-02-03 | 11 | 2022-02-17 | 10 | [15 empty] | 2022-02-17 | 2022-02-17 | 0 | 2022-02-17 | [6 empty] | 2022-01-19 | 2022-01-19 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3072 | PGE | 95407 | NEM | EXPNEM | IA in Progress | Solar PV | 209.547 |  | 2022-01-11 | 2022-01-26 | 10 | 2022-01-28 | 12 | 2022-02-16 | 13 | [15 empty] | 2022-02-16 | 2022-03-10 | 15 | 2022-03-10 | [6 empty] | 2022-01-11 | 2022-01-11 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3073 | PGE | 95422 | NEM | EXPNEM | IA in Progress | Solar PV | 53.634 |  | 2022-01-11 | 2022-01-19 | 5 | 2022-02-15 | 24 | 2022-03-08 | 14 | [15 empty] | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 | [6 empty] | 2022-01-11 | 2022-01-11 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3074 | PGE | 95453 | NEM | EXPNEM | IA in Progress | Solar PV | 43.02 |  | 2022-01-11 | 2022-01-20 | 6 | 2022-02-01 | 14 | 2022-02-17 | 12 | [15 empty] | 2022-02-17 | 2022-02-17 | 0 | 2022-02-17 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3075 | PGE | 94509 | NEM | EXPNEM | Application Review in Progress | Solar PV | 46.536 |  | 2022-01-07 | 2022-01-24 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3076 | PGE | 95453 | NEM | EXPNEM | IA in Progress | Solar PV | 69.849 |  | 2022-01-19 | 2022-02-02 | 10 | 2022-02-10 | 16 | 2022-03-04 | 15 | [15 empty] | 2022-03-04 | 2022-03-04 | 0 | 2022-03-04 | [6 empty] | 2022-01-19 | 2022-01-19 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3077 | PGE | 93212 | NEM | EXPNEM | Study in Progress | Solar PV | 101.728 |  | 2022-02-14 | 2022-03-01 | 10 | 2022-03-01 | 10 | [27 empty] | 2022-02-14 | 2022-02-14 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3078 | PGE | 95946 | NEM | EXPNEM | IA in Progress | Solar PV | 69.849 |  | 2022-01-11 | 2022-01-14 | 3 | 2022-01-14 | 3 | 2022-02-18 | 24 | [15 empty] | 2022-02-18 | 2022-02-18 | 0 | 2022-02-18 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3079 | PGE | 95688 | NEM | EXPNEM | IA in Progress | Solar PV | 205.259 |  | 2022-01-05 | 2022-01-18 | 8 | 2022-03-01 | 37 | 2022-03-21 | 14 | [15 empty] | 2022-03-21 | 2022-03-21 | 0 | 2022-03-21 | [6 empty] | 2022-01-05 | 2022-01-05 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3080 | PGE | 95946 | NEM | EXPNEM | IA in Progress | Solar PV | 67.354 |  | 2022-01-11 | 2022-01-14 | 3 | 2022-01-14 | 3 | 2022-02-18 | 24 | [15 empty] | 2022-02-18 | 2022-02-18 | 0 | 2022-02-18 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3081 | PGE | 95945 | NEM | EXPNEM | IA in Progress | Solar PV | 159.199 |  | 2022-01-11 | 2022-01-13 | 2 | 2022-01-25 | 9 | 2022-03-15 | 34 | [15 empty] | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | [6 empty] | 2022-01-11 | 2022-01-11 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3082 | PGE | 95945 | NEM | EXPNEM | IA in Progress | Solar PV | 44.675 |  | 2022-01-11 | 2022-01-13 | 2 | 2022-01-14 | 3 | 2022-02-18 | 24 | [15 empty] | 2022-02-18 | 2022-02-18 | 0 | 2022-02-18 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3083 | PGE | 93212 | NEM | EXPNEM | IA in Progress | Solar PV | 157.326 |  | 2022-02-14 | 2022-02-28 | 9 | 2022-03-15 | 20 | 2022-03-26 | 8 | [15 empty] | 2022-03-26 | 2022-03-26 | 0 | 2022-03-26 | [6 empty] | 2022-02-14 | 2022-02-14 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3084 | PGE | 93212 | NEM | EXPNEM | Application Review in Progress | Solar PV | 500 |  | 2022-02-14 | 2022-03-01 | 10 | [29 empty] | 2022-02-14 | 2022-02-14 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3085 | PGE | 93212 | NEM | EXPNEM | IA in Progress | Solar PV | 200.408 |  | 2022-02-14 | 2022-03-01 | 10 | 2022-03-01 | 10 | 2022-03-22 | 15 | [15 empty] | 2022-03-22 | [9 empty] | 2022-02-14 | 2022-02-14 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3086 | PGE | 95945 | NEM | EXPNEM | IA in Progress | Solar PV | 82.764 |  | 2022-01-27 | 2022-02-08 | 8 | 2022-02-11 | 11 | 2022-03-07 | 15 | [15 empty] | 2022-03-07 | 2022-03-07 | 0 | 2022-03-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3087 | PGE | 95945 | NEM | EXPNEM | IA in Progress | Solar PV | 139.698 |  | 2022-01-11 | 2022-01-20 | 6 | 2022-03-04 | 36 | 2022-03-23 | 13 | [15 empty] | 2022-03-23 | 2022-03-23 | 0 | 2022-03-23 | [6 empty] | 2022-01-11 | 2022-01-11 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3088 | PGE | 93212 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 300 |  | 2022-02-15 | 2022-03-02 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3089 | PGE | 93612 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 108.963 |  | 2022-01-10 | 2022-01-12 | 2 | 2022-02-24 | 31 | 2022-03-09 | 9 | [15 empty] | 2022-03-09 | 2022-03-09 | 0 | 2022-03-09 | [6 empty] | 2022-01-10 | 2022-01-10 | 1 |  | 2022-03-09 | 2022-03-09 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3090 | PGE | 93212 | NEM | EXPNEM | Application Review in Progress | Solar PV | 375 |  | 2022-02-15 | 2022-03-02 | 10 | [29 empty] | 2022-02-15 | 2022-02-15 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3091 | PGE | 95945 | NEM | EXPNEM | Application Review in Progress | Solar PV | 112.042 |  | 2022-01-11 | 2022-01-19 | 5 | [29 empty] | 2022-01-11 | 2022-01-11 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3092 | PGE | 95472 | NEM | EXPNEM | IA in Progress | Solar PV | 42.607 |  | 2022-01-24 | 2022-02-02 | 7 | 2022-02-02 | 7 | 2022-03-09 | 24 | [15 empty] | 2022-03-09 | 2022-03-09 | 0 | 2022-03-09 | [6 empty] | 2022-01-24 | 2022-01-24 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3093 | PGE | 95242 | NEM | EXPNEM | Application Review in Progress | Solar PV | 32.788 |  | 2022-03-22 | 0 | [30 empty] | 2022-03-22 | 2022-03-22 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3094 | PGE | 94533 | NEM | EXPNEM | Application Review in Progress | Solar PV | 216 |  | 2022-01-26 | 2022-02-09 | 10 | [29 empty] | 2022-01-26 | 2022-01-26 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3095 | PGE | 95442 | NEM | EXPNEM | Study in Progress | Solar PV | 60 |  | 2022-01-20 | 2022-02-01 | 8 | 2022-02-01 | 8 | 2022-02-22 | 14 | 2022-02-22 | 2022-03-21 | 19 | 2022-03-21 | [22 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3096 | PGE | 94070 | NEM | EXPNEM | IA in Progress | Solar PV | 62.413 |  | 2022-01-03 | 2022-01-04 | 1 | 2022-01-11 | 6 | 2022-01-26 | 10 | [15 empty] | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | [6 empty] | 2022-01-03 | 2022-01-03 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3097 | PGE | 94538 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 706.1 |  | 2022-02-07 | 2022-02-17 | 8 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3098 | PGE | 95642 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 277.43 |  | 2022-01-14 | 2022-01-26 | 7 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3099 | PGE | 93203 | NEM | EXPNEM | Study in Progress | Solar PV | 450 |  | 2022-02-18 | 2022-03-07 | 10 | 2022-03-31 | 28 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3100 | PGE | 95111 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2022-01-25 | 2022-02-08 | 10 | 2022-02-08 | 10 | 2022-02-28 | 13 | [15 empty] | 2022-02-28 | 2022-03-21 | 15 | 2022-03-21 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3101 | PGE | 93610 | NEM | EXPNEM | IA in Progress | Solar PV | 60.679 |  | 2022-01-07 | 2022-01-20 | 8 | 2022-01-20 | 8 | 2022-02-04 | 11 | [15 empty] | 2022-02-04 | 2022-02-04 | 0 | 2022-02-04 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3102 | PGE | 96065 | NEM | EXPNEM | Application Review in Progress | Solar PV | 57.946 |  | 2022-01-06 | 2022-01-20 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3103 | PGE | 95928 | NEM | EXPNEM | Application Review in Progress | Solar PV, Turbine | 390 |  | 2022-01-07 | 2022-01-19 | 7 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3104 | PGE | 95205 | NEM | EXPNEM | Study in Progress | Solar PV | 283.2 |  | 2022-01-10 | 2022-01-24 | 9 | 2022-01-24 | 9 | 2022-02-18 | 19 | 2022-02-18 | 2022-03-21 | 20 | 2022-03-21 | [22 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3105 | PGE | 94720 | Non-NEM | Non-Export | Application Accepted | Solar PV, Storage | 2236.8 |  | 2021-12-22 | 2022-01-06 | 11 | 2022-02-23 | 43 | [27 empty] | 2022-01-06 | 2022-01-06 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3106 | PGE | 95240 | NEM | EXPNEM | Study in Progress | Solar PV | 56.982 |  | 2022-02-01 | 2022-02-03 | 2 | 2022-02-11 | 8 | 2022-03-02 | 12 | 2022-03-02 | 2022-03-29 | 19 | 2022-03-29 | [21 empty] | 2022-02-01 | 2022-02-01 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3107 | PGE | 94901 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 498.825 |  | 2022-02-10 | 2022-02-11 | 1 | 2022-02-11 | 1 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3108 | PGE | 94901 | NEM | EXPNEM | IA in Progress | Solar PV | 300 |  | 2022-02-10 | 2022-02-24 | 9 | 2022-02-24 | 9 | 2022-03-11 | 11 | [15 empty] | 2022-03-11 | 2022-03-11 | 0 | 2022-03-11 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3109 | PGE | 94903 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 829.684 |  | 2022-02-08 | 2022-02-22 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3110 | PGE | 95667 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2022-01-13 | 2022-01-24 | 6 | 1/24/2022 |  | 2022-01-27 | 4 | [18 empty] | 2021-12-29 | 2022-01-13 | 11 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3111 | PGE | 95640 | NEM | EXPNEM | Study in Progress | Solar PV | 206 |  | 2022-01-05 | 2022-01-20 | 10 | 2022-02-28 | 36 | 2022-03-15 | 11 | 2022-03-15 | [24 empty] | 2022-01-05 | 2022-01-05 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3112 | PGE | 95202 | NEM | EXPNEM | IA in Progress | Solar PV | 199.8 |  | 2022-01-07 | 2022-01-13 | 4 | 2022-01-13 | 4 | 2022-01-28 | 10 | [15 empty] | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3113 | PGE | 95206 | NEM | EXPNEM | IA in Progress | Solar PV | 30.446 |  | 2022-01-07 | 2022-01-13 | 4 | 2022-01-13 | 4 | 2022-01-27 | 9 | [15 empty] | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3114 | PGE | 95076 | NEM | EXPNEM | Application Accepted | Solar PV | 1000 |  | 2022-02-18 | 2022-02-22 | 1 | 2022-03-30 | 27 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3115 | PGE | 93239 | NEM | EXPNEM | IA in Progress | Solar PV | 200 |  | 2022-01-04 | 2022-01-05 | 1 | 2022-01-11 | 5 | 2022-03-02 | 34 | [15 empty] | 2022-03-02 | 2022-03-02 | 0 | 2022-03-02 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3116 | PGE | 95667 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 15 |  | 2022-01-05 | 2022-01-13 | 6 | 2022-01-13 | 6 | 2022-02-04 | 15 | [18 empty] | 2022-02-01 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3117 | PGE | 93455 | NEM | EXPNEM | Study in Progress | Solar PV | 133.3 |  | 2022-01-26 | 2022-01-27 | 1 | 2022-03-25 | 41 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3118 | PGE | 93630 | NEM | EXPNEM | Application Review in Progress | Solar PV | 125 |  | 2022-01-03 | 2022-01-03 | 0 | [29 empty] | 2022-01-03 | 2022-01-03 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3119 | PGE | 95977 | NEM | EXPNEM | Application Review in Progress | Solar PV | 34.179 |  | 2022-01-04 | 2022-01-06 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3120 | PGE | 93254 | Non-NEM | Non-Export | Application Accepted | Solar PV | 50 |  | 2022-01-25 | 2022-01-25 | 0 | 2022-02-16 | 16 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3121 | PGE | 93420 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2022-01-05 | 2022-01-19 | 9 | 1/19/2022 |  | 2022-01-24 | 4 | [18 empty] | 2022-01-03 | 2022-01-05 | 2 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3122 | PGE | 94027 | NEM | EXPNEM | Implementation | Solar PV | 30.712 |  | 2022-01-03 | 2022-01-12 | 7 | 2022-01-12 | 7 | 2022-01-28 | 11 | 2022-01-28 | 2022-02-24 | 18 | [12 empty] | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-08 | 8 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3123 | PGE | 94062 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 37.6 |  | 2022-01-05 | 2022-01-19 | 9 | 2022-02-11 | 26 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3124 | PGE | 95403 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 38.018 |  | 2022-01-03 | 2022-01-04 | 1 | 2022-01-14 | 9 | 2022-02-04 | 14 | [15 empty] | 2022-02-04 | 2022-02-04 | 0 | 2022-02-04 | [6 empty] | 2022-01-03 | 2022-01-03 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3125 | PGE | 95403 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 38.018 |  | 2022-01-03 | 2022-01-04 | 1 | 2022-01-14 | 9 | 2022-02-04 | 14 | [15 empty] | 2022-02-04 | 2022-02-04 | 0 | 2022-02-04 | [6 empty] | 2022-01-03 | 2022-01-03 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3126 | PGE | 93612 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 66.564 |  | 2022-01-03 | 2022-01-12 | 7 | 2022-01-25 | 15 | 2022-02-09 | 11 | [15 empty] | 2022-02-09 | 2022-02-09 | 0 | 2022-02-09 | [6 empty] | 2022-01-03 | 2022-01-03 | 1 | 2022-03-04 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3127 | PGE | 95215 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1674.244 |  | 2022-01-10 | 2022-01-25 | 10 | 2022-02-16 | 26 | [28 empty] | 2022-03-17 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3128 | PGE | 93436 | Non-NEM | Non-Export | Study in Progress | Micro Turbine | 4560 |  | 2022-01-04 | 2022-01-06 | 2 | 2022-01-19 | 10 | 2022-02-14 | 18 | 2022-02-23 | 2022-03-30 | 25 | [23 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3129 | PGE | 95405 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2022-01-04 | 2022-01-04 | 0 | 2022-01-05 | 1 | 2022-01-10 | 3 | [18 empty] | 2022-01-04 | 2022-01-04 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-01-04 |  | 2022-01-28 | 19 | 1//19
3130 | PGE | 94070 | NEM | EXPNEM | Study in Progress | Solar PV | 312.5 |  | 2022-01-25 | 2022-02-07 | 9 | 2022-02-07 | 9 | [27 empty] | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3131 | PGE | 94704 | NEM | EXPNEM | Study in Progress | Solar PV | 36.511 |  | 2022-01-04 | 2022-01-05 | 1 | 2022-03-29 | 58 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3132 | PGE | 95240 | NEM | EXPNEM | Implementation | Solar PV | 56.982 |  | 2022-01-18 | 2022-01-21 | 3 | 2022-01-21 | 3 | 2022-03-03 | 28 | [15 empty] | 2022-03-03 | 2022-03-03 | 0 | 2022-03-03 | 2022-03-07 | 2 |  |  |  |  | 2022-01-18 | 2022-01-18 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3133 | PGE | 95008 | NEM | EXPNEM | IA in Progress | Solar PV | 375 |  | 2022-01-25 | 2022-02-07 | 9 | 2022-02-07 | 9 | 2022-03-01 | 15 | [15 empty] | 2022-03-01 | 2022-03-22 | 15 | 2022-03-22 | [6 empty] | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3134 | PGE | 93212 | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.393 |  | 2022-02-14 | 2022-03-01 | 10 | [29 empty] | 2022-02-14 | 2022-02-14 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3135 | PGE | 93454 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2022-01-05 | 2022-01-20 | 10 | 2022-02-02 | 19 | 2022-02-14 | 8 | [18 empty] | 2022-01-04 | 2022-01-05 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3136 | PGE | 94920 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 63.39 |  | 2022-02-16 | 2022-02-17 | 1 | 2022-02-17 | 1 | 2022-03-08 | 12 | [15 empty] | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 | [6 empty] | 2022-02-16 | 2022-02-16 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3137 | PGE | 95492 | NEM | VNEMSOMAH | Implementation | Solar PV | 42.091 |  | 2022-01-04 | 2022-01-06 | 2 | 2022-01-25 | 14 | 2022-02-11 | 13 | [15 empty] | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | 2022-03-09 | 17 |  |  |  |  | 2022-01-04 | 2022-01-04 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3138 | PGE | 94103 | NEM | EXPNEM | IA in Progress | Solar PV | 130.635 |  | 2022-01-04 | 2022-01-19 | 10 | 2022-01-19 | 10 | 2022-02-09 | 15 | [15 empty] | 2022-02-09 | 2022-02-25 | 11 | 2022-02-25 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3139 | PGE | 95492 | NEM | VNEMSOMAH | Implementation | Solar PV | 42.091 |  | 2022-01-04 | 2022-01-06 | 2 | 2022-01-25 | 14 | 2022-02-11 | 13 | [15 empty] | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | 2022-03-09 | 17 |  |  |  |  | 2022-01-04 | 2022-01-04 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3140 | PGE | 95336 | NEM | EXPNEM | Study in Progress | Solar PV | 104.179 |  | 2022-01-04 | 2022-01-19 | 10 | 2022-03-22 | 53 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3141 | PGE | 94901 | NEM | EXPNEM | Study in Progress | Solar PV | 333 |  | 2022-02-10 | 2022-02-25 | 10 | 2022-03-07 | 16 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3142 | PGE | 94133 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 83.128 |  | 2022-01-07 | 2022-01-07 | 0 | 2022-01-12 | 3 | [27 empty] | 2022-01-07 | 2022-01-07 | 1 |  | 2022-02-02 | 2022-02-02 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3143 | PGE | 95528 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 15 |  | 2022-01-05 | 2022-01-20 | 10 | 2022-01-20 | 10 | 2022-01-26 | 4 | [15 empty] | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3144 | PGE | 93401 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 50 |  | 2022-01-05 | 2022-01-12 | 5 | 2022-01-28 | 16 | 2022-02-18 | 15 | [15 empty] | 2022-02-18 | 2022-02-18 | 0 | 2022-02-18 | [6 empty] | 2022-01-05 | 2022-01-05 | 1 | 2022-01-21 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3145 | PGE | 93901 | NEM | EXPNEM | Study in Progress | Solar PV | 600 |  | 2022-01-05 | 2022-01-13 | 6 | 2022-01-13 | 6 | 2022-02-24 | 28 | 2022-03-11 | [24 empty] | 2022-01-05 | 2022-01-05 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3146 | PGE | 94010 | NEM | EXPNEM | IA in Progress | Solar PV | 58.199 |  | 2022-01-12 | 2022-01-13 | 1 | 2022-01-13 | 1 | 2022-01-25 | 7 | [15 empty] | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3147 | PGE | 95442 | NEM | EXPNEM | Study in Progress | Solar PV | 60 |  | 2022-01-20 | 2022-02-02 | 9 | 2022-02-02 | 9 | 2022-02-22 | 13 | 2022-02-22 | 2022-03-21 | 19 | 2022-03-21 | [22 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3148 | PGE | 95376 | NEM | EXPNEM | Study in Progress | Solar PV | 83.3 |  | 2022-01-05 | 2022-01-20 | 10 | 2022-01-20 | 10 | 2022-02-09 | 14 | 2022-02-09 | 2022-03-10 | 20 | 2022-03-10 | 2022-03-31 | 15 | 2022-03-31 | [18 empty] | 2022-01-05 | 2022-01-05 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3149 | PGE | 95650 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 39.43 |  | 2022-01-07 | 2022-01-20 | 8 | 2022-02-04 | 19 | 2022-02-04 | 0 | [18 empty] | 2022-01-07 | [7 empty] | 0 | [5 empty] | 2022-02-04 | 2022-02-04 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-04 |  |  | 2022-02-04 |  | 2022-02-04 | 0 | 1//19
3150 | PGE | 93711 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100 |  | 2022-01-05 | 2022-01-06 | 1 | 2022-01-14 | 7 | 2022-01-31 | 10 | [15 empty] | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [6 empty] | 2022-01-05 | 2022-01-05 | 1 |  | 2022-01-31 | 2022-01-31 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3151 | PGE | 95407 | NEM | EXPNEM | Study in Progress | Solar PV | 279.396 |  | 2022-01-11 | 2022-01-14 | 3 | 2022-03-18 | 46 | [27 empty] | 2022-01-11 | 2022-01-11 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3152 | PGE | 93640 | NEM | EXPNEM | Implementation | Solar PV | 750 |  | 2022-01-05 | 2022-01-07 | 2 | 2022-01-07 | 2 | 2022-01-24 | 10 | [15 empty] | 2022-01-24 | 2022-01-24 | 0 | 2022-01-24 | 2022-02-01 | 6 |  |  |  |  | 2022-01-05 | 2022-01-05 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3153 | PGE | 93619 | NEM | EXPNEM | IA in Progress | Solar PV | 300 |  | 2022-02-01 | 2022-02-07 | 4 | 2022-02-23 | 15 | 2022-03-09 | 10 | [15 empty] | 2022-03-09 | 2022-03-09 | 0 | 2022-03-09 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3154 | PGE | 93434 | NEM | EXPNEM | IA in Progress | Solar PV | 750 |  | 2022-01-05 | 2022-01-14 | 7 | 2022-03-04 | 40 | 2022-03-17 | 9 | [15 empty] | 2022-03-17 | 2022-03-17 | 0 | 2022-03-17 | [6 empty] | 2022-02-23 | 2022-02-23 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3155 | PGE | 94521 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2022-01-07 | 2022-01-24 | 10 | 2022-01-24 | 10 | 2022-02-14 | 15 | [15 empty] | 2022-02-14 | 2022-02-14 | 0 | 2022-02-14 | [6 empty] | 2022-01-07 | 2022-01-07 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3156 | PGE | 93449 | NEM | EXPNEM | IA in Progress | Solar PV | 239.671 |  | 2022-01-06 | 2022-01-19 | 8 | 2022-01-19 | 8 | 2022-02-08 | 14 | [15 empty] | 2022-02-08 | 2022-03-01 | 14 | 2022-03-01 | [6 empty] | 2022-01-06 | 2022-01-06 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3157 | PGE | 95448 | NEM | EXPNEM | IA in Progress | Solar PV | 127.068 |  | 2022-01-21 | 2022-02-04 | 10 | 2022-02-28 | 25 | 2022-03-21 | 15 | [15 empty] | 2022-03-21 | 2022-03-21 | 0 | 2022-03-21 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3158 | PGE | 95570 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 10 |  | 2022-01-06 | 2022-01-21 | 10 | [22 empty] | 2022-01-05 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3159 | PGE | 95651 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 15 |  | 2022-01-05 | 2022-01-06 | 1 | 2022-01-06 | 1 | 2022-01-10 | 2 | [15 empty] | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | 2022-01-18 | 5 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3160 | PGE | 95076 | NEM | EXPNEM | Application Review in Progress | Solar PV | 500 |  | 2022-02-18 | 2022-03-07 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3161 | PGE | 95039 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 3250 |  | 2022-02-04 | 2022-02-11 | 5 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3162 | PGE | 93251 | Non-NEM | Non-Export | IA in Progress | Solar PV | 1494 |  | 2022-01-06 | 2022-01-10 | 2 | 2022-01-19 | 8 | 2022-02-09 | 15 | [15 empty] | 2022-02-09 | 2022-02-24 | 10 | 2022-02-24 | [7 empty] | 2022-01-21 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3163 | PGE | 93901 | NEM | EXPNEM | Application Review in Progress | Solar PV | 56.965 |  | 2022-01-25 | 2022-02-08 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3164 | PGE | 93449 | NEM | EXPNEM | IA in Progress | Solar PV | 383.531 |  | 2022-01-19 | 2022-01-28 | 7 | 2022-02-10 | 16 | 2022-03-15 | 22 | [15 empty] | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | [7 empty] | 2022-02-11 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3165 | PGE | 95060 | NEM | EXPNEM | IA in Progress | Solar PV | 108 |  | 2022-01-06 | 2022-01-06 | 0 | 2022-01-11 | 3 | 2022-01-25 | 9 | [15 empty] | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3166 | PGE | 93203 | NEM | EXPNEM | IA in Progress | Solar PV | 825 |  | 2022-01-06 | 2022-01-10 | 2 | 2022-01-12 | 4 | 2022-02-03 | 15 | [15 empty] | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3167 | PGE | 93204 | Non-NEM | Continuous Uncompensated Export | Withdrawn | Micro Turbine | 2000 |  | 2022-01-06 | 2022-01-07 | 1 | [22 empty] | 2022-01-06 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3168 | PGE | 95320 | NEM | EXPNEM | Implementation | Solar PV | 60 |  | 2022-01-07 | 2022-01-10 | 1 | 2022-02-01 | 16 | 2022-02-23 | 15 | 2022-02-23 | 2022-03-08 | 9 | [12 empty] | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 | 2022-03-11 | 3 | [5 empty] | 2022-02-01 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3169 | PGE | 95126 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 108.963 |  | 2022-01-06 | 2022-01-07 | 1 | 2022-01-18 | 7 | 2022-02-04 | 13 | [15 empty] | 2022-02-04 | 2022-02-04 | 0 | 2022-02-04 | [6 empty] | 2022-01-06 | 2022-01-06 | 1 |  | 2022-02-07 | 2022-02-07 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3170 | PGE | 94566 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 11535.874 |  | 2022-01-14 | 2022-01-25 | 6 | 2022-02-23 | 26 | [5 empty] | 2022-03-11 | [22 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3171 | PGE | 95304 | NEM | EXPNEM | Study in Progress | Solar PV | 1920 |  | 2022-01-07 | 2022-01-10 | 1 | 2022-01-19 | 7 | 2022-02-25 | 26 | 2022-03-21 | 2022-03-28 | 5 | [23 empty] | 2022-02-24 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3172 | PGE | 93449 | NEM | EXPNEM | Application Review in Progress | Solar PV | 171.936 |  | 2022-01-11 | 2022-01-12 | 1 | [29 empty] | 2022-01-11 | 2022-01-11 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3173 | PGE | 94572 | NEM | EXPNEM | Study in Progress | Solar PV | 178.378 |  | 2022-01-07 | 2022-01-10 | 1 | 2022-01-10 | 1 | 2022-01-25 | 10 | 2022-01-25 | 2022-02-18 | 18 | 2022-02-18 | 2022-03-14 | 15 | 2022-03-14 | 2022-03-24 | 8 |  |  |  | 2022-03-24 | [12 empty] | 2022-01-07 | 2022-01-07 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3174 | PGE | 94133 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 108.963 |  | 2022-01-07 | 2022-01-07 | 0 | 2022-01-12 | 3 | [27 empty] | 2022-01-07 | 2022-01-07 | 1 |  | 2022-02-02 | 2022-02-02 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3175 | PGE | 95667 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.328 |  | 2022-01-07 | 2022-01-20 | 8 | [22 empty] | 2022-01-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3176 | PGE | 93454 | NEM | EXPNEM | Study in Progress | Solar PV | 602 |  | 2022-01-21 | 2022-02-04 | 10 | 2022-03-22 | 41 | [27 empty] | 2022-01-21 | 2022-01-21 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3177 | PGE | 94558 | NEM | EXPNEM | Application Review in Progress | Solar PV | 125 |  | 2022-02-28 | 2022-03-14 | 10 | [29 empty] | 2022-02-28 | 2022-02-28 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3178 | PGE | 93646 | NEM | VNEM | IA in Progress | Solar PV | 30.511 |  | 2022-01-07 | 2022-01-21 | 9 | 2022-02-08 | 21 | 2022-02-15 | 5 | [15 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | [6 empty] | 2022-01-07 | 2022-01-07 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3179 | PGE | 93646 | NEM | VNEM | IA in Progress | Solar PV | 78.164 |  | 2022-01-07 | 2022-01-21 | 9 | 2022-02-08 | 21 | 2022-02-15 | 5 | [15 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | [6 empty] | 2022-01-07 | 2022-01-07 | 1 | 2022-03-16 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3180 | PGE | 93304 | NEM | EXPNEM | Study in Progress | Solar PV | 57.723 |  | 2022-01-07 | 2022-01-24 | 10 | 2022-03-01 | 35 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3181 | PGE | 93646 | NEM | VNEM | IA in Progress | Solar PV | 112.5 |  | 2022-03-03 | 2022-03-04 | 1 | 2022-03-18 | 11 | 2022-03-28 | 6 | [15 empty] | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28 | [6 empty] | 2022-03-03 | 2022-03-03 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3182 | PGE | 95060 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2022-01-07 | 2022-01-12 | 3 | 2022-01-14 | 5 | 2022-02-07 | 15 | [15 empty] | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3183 | PGE | 95076 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 69.399 |  | 2022-01-07 | 2022-01-24 | 10 | 2022-02-07 | 20 | 2022-03-01 | 15 | [15 empty] | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | [6 empty] | 2022-01-07 | 2022-01-07 | 1 | 2022-02-04 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3184 | PGE | 93646 | NEM | VNEM | IA in Progress | Solar PV | 49.287 |  | 2022-01-07 | 2022-01-21 | 9 | 2022-02-08 | 21 | 2022-02-15 | 5 | [15 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | [6 empty] | 2022-01-07 | 2022-01-07 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3185 | PGE | 93646 | NEM | VNEM | Application Review in Progress | Solar PV | 62.5 |  | 2022-03-10 | 2022-03-14 | 2 | [22 empty] | 2022-03-10 | [6 empty] | 2022-03-10 | 2022-03-10 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3186 | PGE | 95112 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 201.975 |  | 2022-01-13 | 2022-01-28 | 10 | [29 empty] | 2022-01-28 | 2022-01-28 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3187 | PGE | 93635 | NEM | EXPNEM | IA in Progress | Solar PV | 84.189 |  | 2022-01-09 | 2022-01-20 | 7 | 2022-01-20 | 7 | 2022-02-09 | 14 | [15 empty] | 2022-02-09 | 2022-03-29 | 33 | 2022-03-29 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3188 | PGE | 95128 | NEM | EXPNEM | IA in Progress | Solar PV | 177.063 |  | 2022-01-10 | 2022-01-11 | 1 | 2022-01-19 | 6 | 2022-02-08 | 14 | [15 empty] | 2022-02-08 | 2022-02-08 | 0 | 2022-02-08 | [6 empty] | 2022-01-10 | 2022-01-10 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3189 | PGE | 94806 | NEM | EXPNEM | Implementation | Solar PV | 95.41 |  | 2022-01-10 | 2022-01-24 | 9 | 2022-01-28 | 13 | 2022-03-04 | 24 | [15 empty] | 2022-03-04 | 2022-03-04 | 0 | 2022-03-04 | 2022-03-10 | 4 | [5 empty] | 0 | [5 empty] | 2022-03-29 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-29 | 2022-03-29 | 0 |  |  |  |  | 1//19
3190 | PGE | 95404 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.179 |  | 2022-01-10 | 2022-01-25 | 10 | 2022-02-01 | 15 | 2022-02-23 | 15 | [15 empty] | 2022-02-23 | 2022-02-23 | 0 | 2022-02-23 | [6 empty] | 2022-01-10 | 2022-01-10 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3191 | PGE | 93428 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 5 |  | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | 0 | 2022-01-21 | 8 | [18 empty] | 2022-01-10 | 2022-01-10 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3192 | PGE | 95404 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 38.018 |  | 2022-01-10 | 2022-01-25 | 10 | 2022-02-01 | 15 | 2022-02-23 | 15 | [15 empty] | 2022-02-23 | 2022-02-23 | 0 | 2022-02-23 | [6 empty] | 2022-01-10 | 2022-01-10 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3193 | PGE | 95128 | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2022-01-10 | 2022-01-14 | 4 | 2022-01-14 | 4 | 2022-02-01 | 11 | [15 empty] | 2022-02-01 | 2022-02-01 | 0 | 2022-02-01 | 2022-03-09 | 25 |  |  |  |  | 2022-01-10 | 2022-01-10 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3194 | PGE | 95128 | NEM | EXPNEM | Implementation | Solar PV | 482.002 |  | 2022-01-10 | 2022-01-18 | 5 | 2022-01-18 | 5 | 2022-02-23 | 25 | [15 empty] | 2022-02-23 | 2022-02-23 | 0 | 2022-02-23 | 2022-03-09 | 10 |  |  |  |  | 2022-01-10 | 2022-01-10 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3195 | PGE | 95776 | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 |  | 2022-01-26 | 2022-02-09 | 10 | [29 empty] | 2022-01-26 | 2022-01-26 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3196 | PGE | 93630 | NEM | EXPNEM | Implementation | Solar PV | 50 |  | 2022-01-10 | 2022-01-13 | 3 | 2022-02-02 | 16 | 2022-02-15 | 9 | [15 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | 2022-02-28 | 8 |  |  |  |  | 2022-01-10 | 2022-01-10 | 1 |  |  |  |  | 2022-03-28 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-28 | 2022-03-30 | 2 |  |  |  |  | 1//19
3197 | PGE | 95501 | NEM | EXPNEM | IA in Progress | Solar PV | 80.008 |  | 2022-01-13 | 2022-01-27 | 9 | 2022-01-27 | 9 | 2022-02-17 | 15 | [15 empty] | 2022-02-17 | 2022-02-17 | 0 | 2022-02-17 | [6 empty] | 2022-02-17 | 2022-02-17 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3198 | PGE | 93636 | NEM | EXPNEM | IA in Progress | Solar PV | 166.5 |  | 2022-01-12 | 2022-01-25 | 8 | 2022-01-25 | 8 | 2022-02-15 | 15 | [15 empty] | 2022-02-15 | 2022-03-09 | 15 | 2022-03-09 | 2022-03-28 | 13 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3199 | PGE | 95549 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2022-01-16 | 2022-01-28 | 8 | 2022-01-28 | 8 | 2022-02-03 | 4 | [15 empty] | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | 2022-02-03 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3200 | PGE | 94107 | NEM | EXPNEM | IA in Progress | Solar PV | 133.2 |  | 2022-01-10 | 2022-01-13 | 3 | 2022-01-20 | 7 | 2022-01-31 | 7 | [15 empty] | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3201 | PGE | 95403 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 30.402 |  | 2022-01-10 | 2022-01-24 | 9 | 2022-02-07 | 19 | 2022-03-01 | 15 | [15 empty] | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | [6 empty] | 2022-01-10 | 2022-01-10 | 1 | 2022-03-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3202 | PGE | 94928 | NEM | VNEMSOMAH | Implementation | Solar PV | 34.179 |  | 2022-01-10 | 2022-01-12 | 2 | 2022-01-24 | 9 | 2022-02-11 | 14 | [15 empty] | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | 2022-03-09 | 17 |  |  |  |  | 2022-01-10 | 2022-01-10 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3203 | PGE | 94553 | NEM | EXPNEM | Implementation | Solar PV | 39.762 |  | 2022-01-11 | 2022-01-14 | 3 | 2022-01-14 | 3 | 2022-02-01 | 11 | [15 empty] | 2022-02-01 | 2022-02-02 | 1 | 2022-02-02 | 2022-02-02 | 0 | [5 empty] | 0 |  | 2022-01-21 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3204 | PGE | 95695 | NEM | EXPNEM | IA in Progress | Solar PV | 632.477 |  | 2022-01-11 | 2022-01-12 | 1 | 2022-01-12 | 1 | 2022-01-27 | 10 | [15 empty] | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3205 | PGE | 95060 | NEM | EXPNEM | Application Review in Progress | Solar PV | 170 |  | 2022-01-11 | 2022-01-12 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3206 | PGE | 94028 | NEM | EXPNEM | Study in Progress | Solar PV | 907.2 |  | 2022-01-11 | 2022-01-14 | 3 | 2022-01-14 | 3 | 2022-02-01 | 11 | 2022-02-28 | 2022-03-28 | 20 | [22 empty] | 2022-01-11 | 2022-01-11 | 1 | 2022-01-18 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3207 | PGE | 95501 | NEM | EXPNEM | IA in Progress | Solar PV | 70.007 |  | 2022-01-11 | 2022-01-26 | 10 | 2022-01-26 | 10 | 2022-03-30 | 44 | [15 empty] | 2022-03-30 | [9 empty] | 2022-03-03 | 2022-03-03 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3208 | PGE | 94122 | NEM | EXPNEM | Application Review in Progress | Solar PV | 193.931 |  | 2022-01-11 | 2022-01-26 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3209 | PGE | 94551 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1650 |  | 2022-01-12 | 2022-01-20 | 5 | 2022-02-23 | 28 | [28 empty] | 2022-03-18 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3210 | PGE | 95501 | NEM | EXPNEM | IA in Progress | Solar PV | 45.572 |  | 2022-01-11 | 2022-01-26 | 10 | 2022-01-26 | 10 | 2022-02-15 | 14 | [15 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3211 | PGE | 93705 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 55.147 |  | 2022-01-13 | 2022-01-14 | 1 | 2022-01-26 | 8 | 2022-02-03 | 6 | [15 empty] | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | [6 empty] | 2022-01-13 | 2022-01-13 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3212 | PGE | 93705 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 53.872 |  | 2022-01-13 | 2022-01-14 | 1 | 2022-01-26 | 8 | 2022-02-03 | 6 | [15 empty] | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | [6 empty] | 2022-01-13 | 2022-01-13 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3213 | PGE | 93908 | NEM | EXPNEM | Implementation | Solar PV | 43.2 |  | 2022-01-11 | 2022-01-21 | 7 | 2022-02-01 | 14 | 2022-03-08 | 24 | [15 empty] | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 | 2022-03-11 | 3 | [5 empty] | 0 |  | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3214 | PGE | 95113 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 823.39 |  | 2022-01-11 | 2022-01-26 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3215 | PGE | 95492 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 32.671 |  | 2022-01-11 | 2022-01-26 | 10 | 2022-02-01 | 14 | [27 empty] | 2022-01-11 | 2022-01-11 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3216 | PGE | 96080 | NEM | EXPNEM | Implementation | Solar PV | 260.204 |  | 2022-01-12 | 2022-01-24 | 7 | 2022-01-24 | 7 | 2022-02-10 | 13 | [15 empty] | 2022-02-10 | 2022-02-23 | 8 | 2022-02-23 | 2022-02-23 | 0 |  |  |  |  | 2022-01-12 | 2022-01-12 | 1 | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3217 | PGE | 95492 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 32.78 |  | 2022-01-11 | 2022-01-26 | 10 | 2022-02-01 | 14 | 2022-02-23 | 15 | [15 empty] | 2022-02-23 | 2022-02-23 | 0 | 2022-02-23 | [6 empty] | 2022-01-11 | 2022-01-11 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3218 | PGE | 93307 | NEM | EXPNEM | Commercial | Solar PV | 33.817 |  | 2022-01-11 | 2022-01-25 | 9 | 2022-01-25 | 9 | 2022-01-31 | 4 | [15 empty] | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | 2022-02-14 | 10 | [5 empty] | 0 | [5 empty] | 2022-02-14 | 2022-02-22 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-14 | 2022-02-15 | 1 | 2022-02-22 |  | 2022-02-22 | 0 | 1//19
3219 | PGE | 93722 | NEM | EXPNEM | IA in Progress | Solar PV | 38.28 |  | 2022-01-12 | 2022-01-27 | 10 | 2022-02-24 | 29 | 2022-03-17 | 15 | [15 empty] | 2022-03-17 | [10 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3220 | PGE | 95901 | NEM | EXPNEM | Study in Progress | Solar PV | 104.426 |  | 2022-01-12 | 2022-01-14 | 2 | 2022-03-21 | 46 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3221 | PGE | 95320 | NEM | EXPNEM | Withdrawn | Solar PV | 250 |  | 2022-01-12 | 2022-02-01 | 13 | 2022-02-01 | 13 | 2022-02-22 | 14 | [25 empty] | 2022-01-12 | 2022-01-12 | 1 | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3222 | PGE | 94928 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 31.074 |  | 2022-01-12 | 2022-01-14 | 2 | 2022-01-26 | 9 | 2022-02-16 | 15 | [15 empty] | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16 | [6 empty] | 2022-01-12 | 2022-01-12 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3223 | PGE | 95376 | NEM | EXPNEM | Implementation | Solar PV | 135.906 |  | 2022-01-25 | 2022-01-27 | 2 | 2022-01-27 | 2 | 2022-02-18 | 16 | [15 empty] | 2022-02-18 | 2022-02-18 | 0 | 2022-02-18 | 2022-03-01 | 6 |  |  |  |  | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3224 | PGE | 94928 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 73.342 |  | 2022-01-12 | 2022-01-14 | 2 | 2022-01-26 | 9 | 2022-03-15 | 33 | [15 empty] | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | [6 empty] | 2022-01-12 | 2022-01-12 | 1 |  | 2022-02-22 | 2022-02-22 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3225 | PGE | 95912 | NEM | EXPNEM | Implementation | Solar PV | 249.015 |  | 2022-01-20 | 2022-01-28 | 6 | 2022-02-09 | 14 | 2022-02-25 | 11 | [15 empty] | 2022-02-25 | 2022-02-25 | 0 | 2022-02-25 | 2022-02-28 | 1 |  |  |  |  | 2022-01-20 | 2022-01-20 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3226 | PGE | 96007 | NEM | EXPNEM | Application Review in Progress | Solar PV | 38.4 |  | 2022-02-08 | 2022-02-22 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3227 | PGE | 93609 | NEM | EXPNEM | Application Review in Progress | Solar PV | 92.928 |  | 2022-01-12 | 2022-01-27 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3228 | PGE | 95045 | NEM | NEMMT | Application Accepted | ENGN, FUCE, Solar PV | 3580 |  | 2022-01-12 | 2022-01-14 | 2 | 2022-02-02 | 14 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3229 | PGE | 95030 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.464 |  | 2022-01-14 | 2022-01-25 | 6 | 2022-03-10 | 37 | 2022-03-24 | 10 | [18 empty] | 2022-01-12 | [7 empty] | 0 | [5 empty] | 2022-03-24 | 2022-03-24 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-24 |  |  | 2022-03-24 |  | 2022-03-24 | 0 | 1//19
3230 | PGE | 93454 | NEM | EXPNEM | Commercial | Solar PV | 71.134 |  | 2022-01-12 | 2022-01-13 | 1 | 2022-01-28 | 11 | 2022-02-11 | 10 | [15 empty] | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | 2022-02-23 | 7 | [5 empty] | 2022-02-07 | [5 empty] | 2022-02-24 | 2022-03-03 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-24 | 2022-02-24 | 0 | 2022-03-03 |  | 2022-03-03 | 0 | 1//19
3231 | PGE | 95231 | NEM | EXPNEM | IA in Progress | Solar PV | 216 |  | 2022-01-13 | 2022-01-27 | 9 | 2022-02-17 | 24 | 2022-03-08 | 12 | [15 empty] | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3232 | PGE | 93706 | NEM | EXPNEM | IA in Progress | Solar PV | 49.695 |  | 2022-01-13 | 2022-01-21 | 5 | 2022-03-04 | 34 | 2022-03-14 | 6 | [15 empty] | 2022-03-14 | 2022-03-14 | 0 | 2022-03-14 | [7 empty] | 2022-03-10 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3233 | PGE | 93608 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2022-01-24 | 2022-02-07 | 10 | 2022-02-08 | 11 | 2022-02-11 | 3 | [18 empty] | 2022-01-24 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-03-30 |  | 2022-03-30 | 1 | 1//19
3234 | PGE | 95361 | NEM | EXPNEM | Study in Progress | Solar PV | 150 |  | 2022-01-13 | 2022-01-18 | 2 | 2022-03-02 | 32 | 2022-03-17 | 11 | 2022-03-17 | [24 empty] | 2022-01-13 | 2022-01-13 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3235 | PGE | 93274 | NEM | EXPNEM | Study in Progress | Solar PV | 815.474 |  | 2022-01-18 | 2022-01-25 | 5 | 2022-03-14 | 38 | 2022-03-31 | 13 | [26 empty] | 2022-03-17 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3236 | PGE | 95207 | NEM | EXPNEM | IA in Progress | Solar PV | 289.51 |  | 2022-01-13 | 2022-01-19 | 3 | 2022-01-19 | 3 | 2022-03-07 | 32 | [15 empty] | 2022-03-07 | 2022-03-07 | 0 | 2022-03-07 | [6 empty] | 2022-01-13 | 2022-01-13 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3237 | PGE | 94612 | NEM | EXPNEM | Withdrawn | Solar PV | 37.196 |  | 2022-01-19 | 2022-01-28 | 7 | 2022-02-01 | 9 | 2022-02-23 | 15 | [15 empty] | 2022-02-23 | [10 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3238 | PGE | 94806 | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2022-01-13 | 2022-01-28 | 10 | 2022-01-28 | 10 | 2022-02-11 | 10 | [15 empty] | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | [6 empty] | 2022-01-13 | 2022-01-13 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3239 | PGE | 95128 | NEM | EXPNEM | IA in Progress | Solar PV | 252.11 |  | 2022-01-14 | 2022-01-24 | 5 | 2022-01-24 | 5 | 2022-02-24 | 22 | [15 empty] | 2022-03-11 | 2022-03-30 | 13 | 2022-03-30 | [6 empty] | 2022-01-14 | 2022-01-14 | 1 | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3240 | PGE | 94904 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.007 |  | 2022-03-02 | 2022-03-11 | 7 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3241 | PGE | 94027 | Non-NEM | Non-Export | Application Accepted | Storage | 928 |  | 2022-02-10 | 2022-02-10 | 0 | 2022-02-23 | 8 | [20 empty] | 2022-02-10 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3242 | PGE | 93610 | NEM | EXPNEM | Application Review in Progress | Solar PV | 660 |  | 2022-01-13 | 2022-01-28 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3243 | PGE | 95304 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 1991.8 |  | 2022-01-25 | 2022-01-25 | 0 | 2022-02-16 | 16 | [5 empty] | 2022-03-21 | [21 empty] | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3244 | PGE | 93460 | NEM | EXPNEM | Application Review in Progress | Solar PV | 164.925 |  | 2022-01-26 | 2022-02-09 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3245 | PGE | 94806 | NEM | EXPNEM | Study in Progress | Solar PV | 122 |  | 2022-02-23 | 2022-03-09 | 10 | 2022-03-09 | 10 | [27 empty] | 2022-02-23 | 2022-02-23 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3246 | PGE | 94063 | NEM | EXPNEM | Implementation | Solar PV | 166.564 |  | 2022-01-14 | 2022-01-24 | 5 | 2022-02-11 | 19 | 2022-03-01 | 11 | [15 empty] | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | 2022-03-03 | 2 |  |  |  |  | 2022-01-14 | 2022-01-14 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3247 | PGE | 94063 | NEM | EXPNEM | IA in Progress | Solar PV | 89.897 |  | 2022-01-14 | 2022-01-31 | 10 | 2022-01-31 | 10 | 2022-02-15 | 11 | [15 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | [6 empty] | 2022-01-14 | 2022-01-14 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3248 | PGE | 95667 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.423 |  | 2022-01-14 | 2022-01-14 | 0 | 2022-03-03 | 32 | 2022-03-07 | 2 | [18 empty] | 2022-01-14 | [7 empty] | 0 | [5 empty] | 2022-03-07 | 2022-03-07 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-07 |  |  | 2022-03-07 |  | 2022-03-07 | 0 | 1//19
3249 | PGE | 95320 | NEM | EXPNEM | Study in Progress | Solar PV | 300 |  | 2022-01-14 | 2022-01-31 | 10 | 2022-02-08 | 16 | 2022-02-28 | 13 | 2022-02-28 | 2022-03-25 | 19 | 2022-02-25 | [21 empty] | 2022-01-14 | 2022-01-14 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3250 | PGE | 95376 | NEM | EXPNEM | Study in Progress | Solar PV | 1875 |  | 2022-01-25 | 2022-01-25 | 0 | 2022-02-09 | 11 | 2022-03-04 | 16 | 2022-03-28 | [24 empty] | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3251 | PGE | 95020 | NEM | EXPNEM | Implementation | Solar PV | 708.3 |  | 2022-01-14 | 2022-01-24 | 5 | 2022-01-24 | 5 | 2022-02-07 | 10 | [15 empty] | 2022-02-07 | 2022-02-11 | 4 | 2022-02-11 | 2022-02-11 | 0 |  |  |  |  | 2022-01-14 | 2022-01-14 | 1 | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3252 | PGE | 95912 | NEM | EXPNEM | Study in Progress | Solar PV | 123.911 |  | 2022-01-17 | 2022-01-24 | 4 | 2022-01-26 | 6 | 2022-02-11 | 12 | 2022-02-11 | 2022-03-28 | 30 | 2022-03-28 | [21 empty] | 2022-01-17 | 2022-01-17 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3253 | PGE | 93721 | NEM | EXPNEM | Study in Progress | Solar PV | 66.6 |  | 2022-02-14 | 2022-02-16 | 2 | 2022-03-28 | 29 | [27 empty] | 2022-02-14 | 2022-02-14 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3254 | PGE | 95973 | NEM | EXPNEM | IA in Progress | Solar PV | 171.603 |  | 2022-01-14 | 2022-01-24 | 5 | 2022-01-24 | 5 | 2022-02-10 | 13 | 2022-02-10 | 2022-03-02 | 13 | [12 empty] | 2022-03-02 | 2022-03-02 | 0 | 2022-03-02 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3255 | PGE | 95726 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2022-01-14 | 2022-01-31 | 10 | 2022-02-15 | 21 | 2022-02-23 | 5 | [18 empty] | 2022-01-14 | 2022-01-14 | 0 | [5 empty] | 0 | [5 empty] | 2022-02-23 | 2022-02-23 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-23 | 2022-02-23 | 0 | 2022-02-23 |  | 2022-02-23 | 0 | 1//19
3256 | PGE | 94523 | NEM | EXPNEM | Study in Progress | Solar PV | 99.9 |  | 2022-01-14 | 2022-01-31 | 10 | 2022-02-08 | 16 | [27 empty] | 2022-01-14 | 2022-01-14 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3257 | PGE | 94538 | NEM | EXPNEM | IA in Progress | Solar PV | 95.8 |  | 2022-01-14 | 2022-01-31 | 10 | 2022-02-08 | 16 | 2022-02-18 | 8 | [15 empty] | 2022-02-18 | 2022-03-14 | 15 | 2022-03-14 | [6 empty] | 2022-01-14 | 2022-01-14 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3258 | PGE | 93635 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 480 |  | 2022-01-14 | 2022-01-26 | 7 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3259 | PGE | 95310 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.428 |  | 2022-01-15 | 2022-01-25 | 5 | 2022-01-25 | 5 | 2022-01-26 | 1 | [18 empty] | 2022-01-15 | [7 empty] | 0 | [5 empty] | 2022-01-26 | 2022-01-26 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-26 |  |  | 2022-01-26 |  | 2022-01-26 | 0 | 1//19
3260 | PGE | 94574 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 39.984 |  | 2022-01-15 | 2022-01-25 | 5 | [22 empty] | 2022-01-15 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3261 | PGE | 95203 | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 |  | 2022-01-18 | 2022-01-31 | 9 | 2022-01-31 | 9 | 2022-03-29 | 40 | [15 empty] | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29 | [6 empty] | 2022-01-18 | 2022-01-18 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3262 | PGE | 95682 | Non-NEM | Inadvertent Export | Commercial | Storage | 15 |  | 2022-02-11 | 2022-02-11 | 0 | 2022-03-04 | 14 | 2022-03-08 | 2 | [18 empty] | 2022-02-11 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-02-11 |  | 2022-03-08 | 18 | 1//19
3263 | PGE | 95912 | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2022-01-17 | 2022-01-19 | 1 | 2022-01-19 | 1 | 2022-02-02 | 10 | 2022-02-02 | 2022-03-21 | 32 | 2022-03-21 | [21 empty] | 2022-01-17 | 2022-01-17 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3264 | PGE | 95765 | NEM | EXPNEM | Application Review in Progress | Solar PV | 92.779 |  | 2022-01-17 | 2022-01-31 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3265 | PGE | 95376 | NEM | EXPNEM | Implementation | Solar PV | 129.1 |  | 2022-01-18 | 2022-01-25 | 5 | 2022-02-07 | 14 | 2022-02-22 | 10 | [15 empty] | 2022-02-22 | 2022-02-22 | 0 | 2022-02-22 | 2022-02-25 | 3 |  |  |  |  | 2022-01-18 | 2022-01-18 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3266 | PGE | 93720 | NEM | EXPNEM | Study in Progress | Solar PV | 809.29 |  | 2022-01-17 | 2022-01-20 | 2 | 2022-02-22 | 24 | 2022-03-09 | 11 | 2022-03-09 | [24 empty] | 2022-01-17 | 2022-01-17 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3267 | PGE | 94025 | NEM | EXPNEM | IA in Progress | Solar PV | 175 |  | 2022-01-31 | 2022-02-01 | 1 | 2022-02-25 | 18 | 2022-03-23 | 18 | [15 empty] | 2022-03-23 | 2022-03-23 | 0 | 2022-03-23 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3268 | PGE | 95987 | NEM | EXPNEM | Study in Progress | Solar PV | 42.593 |  | 2022-01-17 | 2022-01-31 | 9 | 2022-01-31 | 9 | 2022-02-22 | 15 | 2022-02-22 | [24 empty] | 2022-01-17 | 2022-01-17 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3269 | PGE | 95765 | NEM | EXPNEM | Application Review in Progress | Solar PV | 92.779 |  | 2022-01-19 | 2022-02-02 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3270 | PGE | 95762 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2022-03-03 | 2022-03-07 | 2 | 2022-03-21 | 12 | [20 empty] | 2022-03-03 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3271 | PGE | 94553 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 682 |  | 2022-01-17 | 2022-01-26 | 6 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3272 | PGE | 95501 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2022-01-17 | 2022-01-25 | 5 | 2022-01-25 | 5 | 2022-02-01 | 5 | [18 empty] | 2022-01-17 | 2022-01-17 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3273 | PGE | 90045 | NEM | EXPNEM | Application Review in Progress | Solar PV | 750 |  | 2022-02-16 | 2022-03-02 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3274 | PGE | 94565 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 782 |  | 2022-01-17 | 2022-01-26 | 6 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3275 | PGE | 94596 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 214.875 |  | 2022-01-17 | 2022-01-26 | 6 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3276 | PGE | 95685 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 5 |  | 2022-01-17 | 2022-01-25 | 5 | 2022-01-25 | 5 | 2022-02-14 | 14 | [15 empty] | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3277 | PGE | 93721 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 993 |  | 2022-01-17 | 2022-01-26 | 6 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3278 | PGE | 93648 | NEM | EXPNEM | IA in Progress | Solar PV | 215.636 |  | 2022-01-18 | 2022-01-18 | 0 | 2022-01-18 | 0 | 2022-01-26 | 6 | [15 empty] | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3279 | PGE | 93648 | NEM | EXPNEM | IA in Progress | Solar PV | 180 |  | 2022-01-18 | 2022-01-18 | 0 | 2022-01-19 | 1 | 2022-01-26 | 5 | [15 empty] | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3280 | PGE | 93648 | NEM | EXPNEM | IA in Progress | Solar PV | 256.369 |  | 2022-01-18 | 2022-01-18 | 0 | 2022-01-18 | 0 | 2022-01-28 | 8 | [15 empty] | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3281 | PGE | 94941 | NEM | EXPNEM | IA in Progress | Solar PV | 209.933 |  | 2022-01-26 | 2022-02-09 | 10 | 2022-03-07 | 27 | 2022-03-28 | 15 | [15 empty] | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28 | [6 empty] | 2022-01-26 | 2022-01-26 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3282 | PGE | 94131 | NEM | VNEM | Study in Progress | Solar PV | 34.22 |  | 2022-02-24 | 2022-02-24 | 0 | 2022-03-14 | 12 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3283 | PGE | 93230 | NEM | EXPNEM | Application Accepted | Solar PV | 1476 |  | 2022-03-02 | 2022-03-03 | 1 | 2022-03-16 | 10 | [27 empty] | 2022-03-02 | 2022-03-02 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3284 | PGE | 95377 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2022-01-18 | 2022-01-31 | 9 | 2022-01-31 | 9 | 2022-02-22 | 15 | [15 empty] | 2022-02-22 | 2022-03-01 | 5 | 2022-03-01 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3285 | PGE | 94588 | NEM | EXPNEM | Application Review in Progress | Solar PV | 854.743 |  | 2022-01-18 | 2022-02-01 | 10 | [29 empty] | 2022-01-18 | 2022-01-18 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3286 | PGE | 94952 | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2022-01-18 | 2022-02-01 | 10 | 2022-02-01 | 10 | 2022-03-16 | 30 | 2022-03-16 | [24 empty] | 2022-01-18 | 2022-01-18 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3287 | PGE | 95023 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 498.906 |  | 2022-01-18 | 2022-01-19 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3288 | PGE | 94080 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 316 |  | 2022-01-18 | 2022-01-31 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3289 | PGE | 95993 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 956 |  | 2022-01-18 | 2022-01-28 | 8 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3290 | PGE | 93405 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2022-01-18 | 2022-01-31 | 9 | 2022-01-31 | 9 | 2022-01-31 | 0 | [18 empty] | 2022-01-18 | [7 empty] | 0 | [5 empty] | 2022-02-04 | 2022-02-04 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-04 |  |  | 2022-02-04 |  | 2022-02-04 | 0 | 1//19
3291 | PGE | 94606 | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2022-01-27 | 2022-02-08 | 8 | 2022-02-08 | 8 | 2022-02-23 | 10 | [15 empty] | 2022-02-23 | 2022-03-09 | 10 | 2022-03-09 | [6 empty] | 2022-01-27 | 2022-01-27 | 1 | 2022-03-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3292 | PGE | 96080 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 605.043 |  | 2022-01-18 | 2022-01-28 | 8 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3293 | PGE | 94605 | NEM | EXPNEM | Study in Progress | Solar PV | 120 |  | 2022-01-27 | 2022-02-08 | 8 | 2022-02-08 | 8 | 2022-02-23 | 10 | [25 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3294 | PGE | 95695 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 911 |  | 2022-01-18 | 2022-01-28 | 8 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3295 | PGE | 94132 | NEM | EXPNEM | Application Review in Progress | Solar PV | 375 |  | 2022-01-18 | 2022-02-01 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3296 | PGE | 94945 | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.128 |  | 2022-03-01 | 2022-03-14 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3297 | PGE | 94621 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2022-01-27 | 2022-02-08 | 8 | 2022-02-08 | 8 | 2022-03-23 | 30 | [15 empty] | 2022-03-23 | [9 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3298 | PGE | 94062 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.126 |  | 2022-01-18 | 2022-01-27 | 7 | [22 empty] | 2022-01-18 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3299 | PGE | 93620 | NEM | EXPNEM | IA in Progress | Solar PV | 139.698 |  | 2022-01-25 | 2022-02-08 | 10 | 2022-02-08 | 10 | 2022-03-02 | 15 | [15 empty] | 2022-03-02 | 2022-03-04 | 2 | 2022-03-04 | [6 empty] | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3300 | PGE | 93245 | NEM | EXPNEM | Application Accepted | Solar PV | 7431.255 |  | 2022-01-19 | 2022-01-19 | 0 | 2022-02-16 | 20 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3301 | PGE | 95035 | NEM | EXPNEM | Implementation | Solar PV | 166.564 |  | 2022-01-19 | 2022-02-01 | 9 | 2022-02-01 | 9 | 2022-02-16 | 11 | [15 empty] | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16 | 2022-02-16 | 0 |  |  |  |  | 2022-01-19 | 2022-01-19 | 1 | 2022-02-16 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3302 | PGE | 95112 | NEM | EXPNEM | Implementation | Solar PV | 113.918 |  | 2022-01-18 | 2022-01-25 | 5 | 2022-01-27 | 7 | 2022-02-11 | 11 | [15 empty] | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | 2022-02-17 | 4 |  |  |  |  | 2022-01-18 | 2022-01-18 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3303 | PGE | 94608 | NEM | EXPNEM | IA in Progress | Solar PV | 312.934 |  | 2022-01-19 | 2022-01-24 | 3 | 2022-01-24 | 3 | 2022-03-05 | 28 | [15 empty] | 2022-03-05 | 2022-03-05 | 0 | 2022-03-05 | [6 empty] | 2022-01-19 | 2022-01-19 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3304 | PGE | 95112 | NEM | EXPNEM | Application Accepted | Solar PV | 216.564 |  | 2022-01-19 | 2022-01-28 | 7 | 2022-01-28 | 7 | [27 empty] | 2022-01-19 | 2022-01-19 | 1 | 2022-02-09 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3305 | PGE | 94089 | NEM | EXPNEM | IA in Progress | Solar PV | 99.9 |  | 2022-01-19 | 2022-01-24 | 3 | 2022-01-24 | 3 | 2022-02-09 | 12 | 2022-02-09 | 2022-03-17 | 25 | [12 empty] | 2022-03-17 | 2022-03-17 | 0 | 2022-03-17 | [6 empty] | 2022-01-19 | 2022-01-19 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3306 | PGE | 95112 | NEM | EXPNEM | IA in Progress | Solar PV | 113.918 |  | 2022-01-18 | 2022-01-31 | 9 | 2022-01-31 | 9 | 2022-02-17 | 13 | [15 empty] | 2022-02-17 | 2022-03-11 | 15 | 2022-03-11 | [6 empty] | 2022-01-18 | 2022-01-18 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3307 | PGE | 95035 | NEM | EXPNEM | IA in Progress | Solar PV | 266.564 |  | 2022-01-19 | 2022-02-02 | 10 | 2022-02-14 | 18 | 2022-03-08 | 15 | [15 empty] | 2022-03-08 | 2022-03-29 | 15 | 2022-03-29 | [6 empty] | 2022-01-19 | 2022-01-19 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3308 | PGE | 94608 | NEM | EXPNEM | Implementation | Solar PV | 131.028 |  | 2022-01-19 | 2022-01-24 | 3 | 2022-01-24 | 3 | 2022-02-08 | 11 | [15 empty] | 2022-02-08 | 2022-02-08 | 0 | 2022-02-08 | 2022-03-03 | 16 |  |  |  |  | 2022-01-19 | 2022-01-19 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3309 | PGE | 93953 | NEM | EXPNEM | Study in Progress | Solar PV | 185.775 |  | 2022-01-19 | 2022-02-02 | 10 | 2022-03-27 | 46 | [27 empty] | 2022-01-19 | 2022-01-19 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3310 | PGE | 94089 | NEM | EXPNEM | Application Accepted | Solar PV | 129.971 |  | 2022-01-19 | 2022-01-26 | 5 | 2022-01-26 | 5 | [27 empty] | 2022-01-19 | 2022-01-19 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3311 | PGE | 94303 | NEM | EXPNEM | Study in Progress | Solar PV | 282.291 |  | 2022-01-19 | 2022-02-02 | 10 | 2022-03-09 | 34 | 2022-03-30 | 15 | [25 empty] | 2022-01-19 | 2022-01-19 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3312 | PGE | 94040 | NEM | EXPNEM | Study in Progress | Solar PV | 358.3 |  | 2022-01-19 | 2022-02-02 | 10 | 2022-03-08 | 33 | 2022-03-29 | 15 | 2022-03-29 | [24 empty] | 2022-01-19 | 2022-01-19 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3313 | PGE | 94040 | NEM | EXPNEM | Study in Progress | Solar PV | 62.5 |  | 2022-01-19 | 2022-02-02 | 10 | 2022-03-09 | 34 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3314 | PGE | 93662 | NEM | EXPNEM | Implementation | Solar PV | 60 |  | 2022-01-19 | 2022-01-27 | 6 | 2022-01-27 | 6 | 2022-02-03 | 5 | [15 empty] | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | 2022-02-07 | 2 |  |  |  |  | 2022-01-19 | 2022-01-19 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3315 | PGE | 95204 | NEM | EXPNEM | Application Review in Progress | Solar PV | 300 |  | 2022-01-19 | 2022-01-20 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3316 | PGE | 93454 | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2022-01-19 | 2022-01-21 | 2 | 2022-01-21 | 2 | 2022-02-11 | 15 | [15 empty] | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3317 | PGE | 94608 | NEM | EXPNEM | IA in Progress | Solar PV | 85.906 |  | 2022-01-27 | 2022-02-08 | 8 | 2022-02-08 | 8 | 2022-03-23 | 30 | [15 empty] | 2022-03-23 | 2022-03-24 | 1 | 2022-03-24 | [6 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3318 | PGE | 93631 | NEM | EXPNEM | Application Review in Progress | Solar PV | 46.536 |  | 2022-01-19 | 2022-01-28 | 7 | [29 empty] | 2022-01-19 | 2022-01-19 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3319 | PGE | 95476 | Non-NEM | Non-Export | Application Accepted | ENGN, Micro Turbine | 330 |  | 2022-01-19 | 2022-01-19 | 0 | 2022-02-23 | 24 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3320 | PGE | 93635 | NEM | EXPNEM | Implementation | Solar PV | 75 |  | 2022-01-19 | 2022-02-02 | 10 | 2022-02-08 | 14 | 2022-03-21 | 28 | [15 empty] | 2022-03-21 | 2022-03-21 | 0 | 2022-03-21 | 2022-03-24 | 3 |  |  |  |  | 2022-01-19 | 2022-01-19 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3321 | PGE | 94601 | NEM | EXPNEM | Application Review in Progress | Solar PV | 72 |  | 2022-01-27 | 2022-01-28 | 1 | [29 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3322 | PGE | 94028 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2022-01-19 | 2022-01-19 | 0 | 2022-01-19 | 0 | 2022-01-31 | 8 | [18 empty] | 2022-01-19 | [7 empty] | 0 | [5 empty] | 2022-01-31 | 2022-01-31 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-01-31 |  |  | 2022-01-31 |  | 2022-01-31 | 0 | 1//19
3323 | PGE | 95112 | NEM | EXPNEM | Implementation | Solar PV | 47.56 |  | 2022-01-21 | 2022-01-28 | 5 | 2022-01-28 | 5 | 2022-02-11 | 10 | [15 empty] | 2022-02-11 | 2022-03-10 | 18 | 2022-03-10 | 2022-03-16 | 4 |  |  |  |  | 2022-01-21 | 2022-01-21 | 1 | 2022-02-08 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3324 | PGE | 94515 | NEM | EXPNEM | Application Review in Progress | Solar PV | 104.351 |  | 2022-01-19 | 2022-02-02 | 10 | [29 empty] | 2022-01-19 | 2022-01-19 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3325 | PGE | 95242 | NEM | NEMMT | Study in Progress | FUCE, Solar PV, Storage | 4695 |  | 2022-01-24 | 2022-01-28 | 4 | 2022-03-09 | 31 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3326 | PGE | 95222 | NEM | EXPNEM | Application Review in Progress | Solar PV | 99.384 |  | 2022-01-19 | 2022-01-27 | 6 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3327 | PGE | 94610 | NEM | EXPNEM | IA in Progress | Solar PV | 72 |  | 2022-01-27 | 2022-01-28 | 1 | 2022-01-28 | 1 | 2022-02-08 | 7 | [15 empty] | 2022-02-08 | 2022-02-08 | 0 | 2022-02-08 | [6 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3328 | PGE | 95616 | Non-NEM | Non-Export | Application Review in Progress | Solar PV | 699.453 |  | 2022-03-14 | 2022-03-17 | 3 | [22 empty] | 2022-03-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3329 | PGE | 94803 | NEM | EXPNEM | IA in Progress | Solar PV | 57.429 |  | 2022-01-20 | 2022-01-31 | 7 | 2022-02-18 | 21 | 2022-03-29 | 26 | [15 empty] | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29 | [6 empty] | 2022-01-20 | 2022-01-20 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3330 | PGE | 94550 | NEM | EXPNEM | Study in Progress | Solar PV | 400 |  | 2022-01-25 | 2022-02-04 | 8 | 2022-02-04 | 8 | 2022-02-25 | 14 | 2022-02-25 | 2022-03-24 | 19 | 2022-03-24 | [21 empty] | 2022-01-25 | 2022-01-25 | 1 | 2022-02-09 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3331 | PGE | 93622 | NEM | EXPNEM | Study in Progress | Solar PV | 975 |  | 2022-01-21 | 2022-01-31 | 6 | 2022-02-22 | 21 | 2022-03-08 | 10 | 2022-03-08 | [24 empty] | 2022-01-21 | 2022-01-21 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3332 | PGE | 94513 | NEM | EXPNEM | Commercial | Solar PV | 53.35 |  | 2022-01-20 | 2022-02-01 | 8 | 2022-02-01 | 8 | 2022-02-16 | 11 | [15 empty] | 2022-02-16 | 2022-02-23 | 4 | 2022-02-23 | 2022-02-23 | 0 | [5 empty] | 0 | [5 empty] | 2022-02-23 | 2022-03-03 | 6 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-23 | 2022-02-24 | 1 | 2022-03-03 |  | 2022-03-03 | 0 | 1//19
3333 | PGE | 94619 | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2022-01-27 | 2022-01-28 | 1 | 2022-01-28 | 1 | 2022-02-24 | 18 | [15 empty] | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | [6 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3334 | PGE | 94605 | NEM | EXPNEM | IA in Progress | Solar PV | 72 |  | 2022-01-27 | 2022-01-28 | 1 | 2022-03-07 | 26 | 2022-03-11 | 4 | [15 empty] | 2022-03-11 | 2022-03-11 | 0 | 2022-03-11 | [6 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3335 | PGE | 93274 | NEM | EXPNEM | Study in Progress | Solar PV | 815.474 |  | 2022-01-20 | 2022-01-24 | 2 | 2022-03-16 | 38 | 2022-03-25 | 7 | 2022-03-25 | [25 empty] | 0 |  | 2022-03-17 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3336 | PGE | 93635 | NEM | EXPNEM | Study in Progress | Solar PV | 32.508 |  | 2022-02-03 | 2022-02-14 | 7 | 2022-03-29 | 37 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3337 | PGE | 94607 | NEM | EXPNEM | IA in Progress | Solar PV | 131.812 |  | 2022-01-27 | 2022-01-28 | 1 | 2022-03-07 | 26 | 2022-03-11 | 4 | [15 empty] | 2022-03-11 | 2022-03-11 | 0 | 2022-03-11 | [6 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3338 | PGE | 94603 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2022-01-27 | 2022-02-07 | 7 | 2022-03-08 | 27 | 2022-03-09 | 1 | [15 empty] | 2022-03-09 | 2022-03-09 | 0 | 2022-03-09 | [6 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3339 | PGE | 94619 | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2022-01-27 | 2022-02-08 | 8 | 2022-02-18 | 16 | 2022-03-11 | 14 | [15 empty] | 2022-03-11 | 2022-03-11 | 0 | 2022-03-11 | [6 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3340 | PGE | 94608 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2022-01-27 | 2022-02-08 | 8 | 2022-02-08 | 8 | 2022-02-24 | 11 | [15 empty] | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | [6 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3341 | PGE | 93635 | NEM | EXPNEM | Study in Progress | Solar PV | 521.3 |  | 2022-02-03 | 2022-02-17 | 10 | 2022-03-29 | 37 | [28 empty] | 2022-02-17 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3342 | PGE | 93635 | NEM | EXPNEM | Study in Progress | Solar PV | 288 |  | 2022-02-03 | 2022-02-15 | 8 | 2022-03-29 | 37 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3343 | PGE | 94605 | NEM | EXPNEM | Study in Progress | Solar PV | 50 |  | 2022-01-27 | 2022-02-07 | 7 | 2022-03-16 | 33 | [27 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3344 | PGE | 93727 | NEM | EXPNEM | Application Review in Progress | Solar PV | 441.512 |  | 2022-03-15 | 2022-03-17 | 2 | [29 empty] | 2022-03-15 | 2022-03-15 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3345 | PGE | 94621 | NEM | EXPNEM | IA in Progress | Solar PV | 232 |  | 2022-01-27 | 2022-02-08 | 8 | 2022-02-18 | 16 | 2022-03-08 | 11 | [15 empty] | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 | [6 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3346 | PGE | 94022 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 36.337 |  | 2022-01-21 | 2022-01-21 | 0 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3347 | PGE | 95682 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2022-01-21 | 2022-01-21 | 0 | 2022-01-21 | 0 | 2022-02-01 | 7 | [18 empty] | 2022-01-21 | [6 empty] | 2022-01-21 | 2022-01-21 | 1 |  |  |  |  | 2022-02-07 | 2022-02-07 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-07 |  |  | 2022-02-07 |  | 2022-02-07 | 0 | 1//19
3348 | PGE | 93618 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 2125 |  | 2022-01-21 | 2022-01-24 | 1 | 2022-02-16 | 18 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3349 | PGE | 93280 | NEM | EXPNEM | IA in Progress | Solar PV | 298.836 |  | 2022-01-21 | 2022-01-26 | 3 | 2022-03-07 | 30 | 2022-03-21 | 10 | [15 empty] | 2022-03-21 | 2022-03-21 | 0 | 2022-03-21 | [6 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3350 | PGE | 95762 | NEM | EXPNEM | Application Review in Progress | Solar PV | 50.864 |  | 2022-02-07 | 2022-02-22 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3351 | PGE | 95133 | NEM | EXPNEM | Application Review in Progress | Solar PV | 97.889 |  | 2022-02-07 | 2022-02-22 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3352 | PGE | 93203 | NEM | EXPNEM | Application Review in Progress | Solar PV | 825.695 |  | 2022-01-21 | 2022-02-04 | 10 | [29 empty] | 2022-01-21 | 2022-01-21 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3353 | PGE | 94544 | NEM | VNEM | Application Review in Progress | Solar PV | 165.528 |  | 2022-01-21 | 2022-02-04 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3354 | PGE | 95472 | NEM | EXPNEM | Implementation | Solar PV | 60 |  | 2022-01-21 | 2022-02-01 | 7 | 2022-02-04 | 10 | 2022-02-22 | 11 | [15 empty] | 2022-02-22 | 2022-02-22 | 0 | 2022-02-22 | 2022-02-28 | 4 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3355 | PGE | 94544 | NEM | VNEM | Application Review in Progress | Solar PV | 294.264 |  | 2022-01-21 | 2022-02-04 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3356 | PGE | 94544 | NEM | VNEM | Application Review in Progress | Solar PV | 165.528 |  | 2022-01-21 | 2022-02-04 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3357 | PGE | 93203 | NEM | EXPNEM | Application Review in Progress | Solar PV | 825.695 |  | 2022-01-21 | 2022-02-04 | 10 | [29 empty] | 2022-01-21 | 2022-01-21 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3358 | PGE | 93304 | NEM | EXPNEM | Study in Progress | Solar PV | 825.695 |  | 2022-01-21 | 2022-02-03 | 9 | 2022-03-24 | 43 | [5 empty] | 2022-03-24 | [21 empty] | 2022-01-21 | 2022-01-21 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3359 | PGE | 94566 | NEM | NEMMT | Study in Progress | FUCE, Solar PV, Storage | 3012.1 |  | 2022-01-21 | 2022-01-24 | 1 | 2022-02-09 | 13 | [5 empty] | 2022-02-18 | 2022-03-22 | 21 | 2022-03-22 | 2022-03-28 | 4 |  |  |  | 2022-03-28 | [12 empty] | 2022-01-21 | 2022-01-21 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3360 | PGE | 93727 | NEM | VNEM | IA in Progress | Solar PV | 34.22 |  | 2022-01-21 | 2022-01-21 | 0 | 2022-03-18 | 39 | 2022-03-28 | 6 | [15 empty] | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28 | [7 empty] | 2022-03-17 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3361 | PGE | 95139 | NEM | VNEM | Application Review in Progress | Solar PV | 386.208 |  | 2022-01-21 | 2022-02-04 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3362 | PGE | 95139 | NEM | VNEM | Application Review in Progress | Solar PV | 296.468 |  | 2022-01-21 | 2022-02-04 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3363 | PGE | 95139 | NEM | VNEM | Application Review in Progress | Solar PV | 183.237 |  | 2022-01-21 | 2022-02-04 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3364 | PGE | 94118 | NEM | EXPNEM | Application Accepted | Solar PV | 145.584 |  | 2022-01-21 | 2022-02-02 | 8 | 2022-02-03 | 9 | [27 empty] | 2022-01-21 | 2022-01-21 | 1 | 2022-03-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3365 | PGE | 93662 | NEM | EXPNEM | Implementation | Solar PV | 75.259 |  | 2022-01-21 | 2022-02-01 | 7 | 2022-02-15 | 17 | 2022-02-24 | 6 | [15 empty] | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-01 | 3 |  |  |  |  | 2022-01-21 | 2022-01-21 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3366 | PGE | 93313 | NEM | EXPNEM | Application Review in Progress | Solar PV | 825.695 |  | 2022-01-21 | 2022-02-03 | 9 | [29 empty] | 2022-01-21 | 2022-01-21 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3367 | PGE | 95991 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 35 |  | 2022-02-11 | 0 | [31 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3368 | PGE | 95112 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2022-01-25 | 2022-02-08 | 10 | 2022-03-07 | 28 | 2022-03-28 | 15 | [15 empty] | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3369 | PGE | 93313 | NEM | EXPNEM | Study in Progress | Solar PV | 825.695 |  | 2022-01-21 | 2022-02-02 | 8 | 2022-03-23 | 42 | [5 empty] | 2022-03-23 | [21 empty] | 2022-01-21 | 2022-01-21 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3370 | PGE | 93618 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 750 |  | 2022-01-21 | 2022-02-04 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3371 | PGE | 93280 | NEM | EXPNEM | IA in Progress | Solar PV | 540 |  | 2022-01-21 | 2022-02-01 | 7 | 2022-03-07 | 30 | 2022-03-28 | 15 | [15 empty] | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28 | [6 empty] | 2022-02-02 | 2022-02-02 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3372 | PGE | 95122 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2022-01-25 | 2022-02-08 | 10 | 2022-02-08 | 10 | 2022-02-28 | 13 | [15 empty] | 2022-02-28 | 2022-03-21 | 15 | 2022-03-21 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3373 | PGE | 94303 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.49 |  | 2022-01-21 | 2022-01-25 | 2 | 2022-02-02 | 8 | 2022-02-22 | 13 | 2022-02-22 | 2022-03-18 | 18 | [12 empty] | 2022-03-18 | 2022-03-18 | 0 | 2022-03-18 | [6 empty] | 2022-01-21 | 2022-01-21 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3374 | PGE | 95008 | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 |  | 2022-01-25 | 2022-01-28 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3375 | PGE | 95361 | NEM | EXPNEM | Application Review in Progress | Solar PV | 825.695 |  | 2022-01-21 | 2022-02-01 | 7 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3376 | PGE | 93263 | NEM | EXPNEM | IA in Progress | Solar PV | 34.22 |  | 2022-01-21 | 2022-02-04 | 10 | 2022-02-24 | 23 | 2022-03-17 | 15 | [15 empty] | 2022-03-17 | [10 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3377 | PGE | 95620 | NEM | EXPNEM | Application Review in Progress | Solar PV | 825.695 |  | 2022-01-21 | 2022-01-31 | 6 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3378 | PGE | 93263 | NEM | EXPNEM | IA in Progress | Solar PV | 540 |  | 2022-01-21 | 2022-02-02 | 8 | 2022-03-07 | 30 | 2022-03-21 | 10 | [15 empty] | 2022-03-21 | 2022-03-21 | 0 | 2022-03-21 | [6 empty] | 2022-02-02 | 2022-02-02 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3379 | PGE | 93263 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 9000 |  | 2022-01-24 | 2022-01-28 | 4 | 2022-03-30 | 46 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3380 | PGE | 95247 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2022-01-25 | 2022-02-08 | 10 | 2022-02-11 | 13 | 2022-02-24 | 8 | [18 empty] | 2022-01-24 | 2022-01-25 | 1 | [5 empty] | 0 | [5 empty] | 2022-02-24 | 2022-03-02 | 4 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-24 | 2022-03-02 | 4 | 2022-03-02 |  | 2022-03-02 | 0 | 1//19
3381 | PGE | 95666 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2022-01-22 | 2022-01-26 | 2 | 2022-01-26 | 2 | 2022-02-14 | 13 | [18 empty] | 2022-01-22 | 2022-01-22 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3382 | PGE | 94086 | NEM | EXPNEM | Application Review in Progress | Solar PV | 287.069 |  | 2022-02-22 | 2022-03-02 | 6 | [29 empty] | 2022-02-22 | 2022-02-22 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3383 | PGE | 93312 | NEM | EXPNEM | Study in Progress | Solar PV | 38.28 |  | 2022-01-24 | 2022-01-26 | 2 | 2022-03-29 | 45 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3384 | PGE | 93907 | NEM | EXPNEM | Implementation | Solar PV | 46.235 |  | 2022-01-24 | 2022-02-02 | 7 | 2022-02-02 | 7 | 2022-02-24 | 15 | [15 empty] | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-02-25 | 1 |  |  |  |  | 2022-01-24 | 2022-01-24 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3385 | PGE | 94595 | NEM | EXPNEM | IA in Progress | Solar PV | 573.345 |  | 2022-01-24 | 2022-02-02 | 7 | 2022-02-02 | 7 | 2022-03-10 | 25 | [15 empty] | 2022-03-10 | 2022-03-10 | 0 | 2022-03-10 | [6 empty] | 2022-01-24 | 2022-01-24 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3386 | PGE | 94595 | NEM | EXPNEM | IA in Progress | Solar PV | 187.5 |  | 2022-01-24 | 2022-01-26 | 2 | 2022-01-26 | 2 | 2022-03-10 | 30 | [15 empty] | 2022-03-10 | 2022-03-10 | 0 | 2022-03-10 | [6 empty] | 2022-01-24 | 2022-01-24 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3387 | PGE | 94605 | NEM | EXPNEM | Study in Progress | Solar PV | 96 |  | 2022-01-27 | 2022-02-08 | 8 | 2022-02-08 | 8 | [27 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3388 | PGE | 95404 | NEM | EXPNEM | IA in Progress | Solar PV | 114.752 |  | 2022-01-25 | 2022-02-04 | 8 | 2022-02-04 | 8 | 2022-03-15 | 26 | [15 empty] | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | [6 empty] | 2022-01-25 | 2022-01-25 | 1 | 2022-02-09 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3389 | PGE | 94607 | NEM | EXPNEM | Study in Progress | Solar PV | 96 |  | 2022-01-27 | 2022-02-09 | 9 | 2022-03-31 | 44 | [27 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3390 | PGE | 96021 | NEM | EXPNEM | Implementation | Solar PV | 360 |  | 2022-01-25 | 2022-02-08 | 10 | 2022-02-08 | 10 | 2022-03-02 | 15 | [15 empty] | 2022-03-02 | 2022-03-17 | 11 | 2022-03-17 | 2022-03-24 | 5 | [5 empty] | 2022-03-09 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3391 | PGE | 93666 | NEM | EXPNEM | Implementation | Solar PV | 150 |  | 2022-01-25 | 2022-02-03 | 7 | 2022-02-07 | 9 | 2022-02-14 | 5 | [15 empty] | 2022-02-14 | 2022-02-14 | 0 | 2022-02-14 | 2022-02-16 | 2 |  |  |  |  | 2022-02-07 | 2022-02-07 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3392 | PGE | 94941 | NEM | EXPNEM | IA in Progress | Solar PV | 254.056 |  | 2022-01-26 | 2022-02-09 | 10 | 2022-03-07 | 27 | 2022-03-28 | 15 | [15 empty] | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28 | [6 empty] | 2022-01-26 | 2022-01-26 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3393 | PGE | 93210 | NEM | EXPNEM | Study in Progress | Solar PV | 30.948 |  | 2022-01-25 | 2022-02-08 | 10 | 2022-02-11 | 13 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3394 | PGE | 94603 | NEM | EXPNEM | Study in Progress | Solar PV | 72 |  | 2022-01-27 | 2022-02-09 | 9 | 2022-03-31 | 44 | [27 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3395 | PGE | 94706 | NEM | EXPNEM | Study in Progress | Solar PV | 269.755 |  | 2022-02-04 | 2022-02-08 | 2 | 2022-02-08 | 2 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3396 | PGE | 94706 | NEM | EXPNEM | Study in Progress | Solar PV | 234.369 |  | 2022-02-04 | 2022-02-08 | 2 | 2022-02-08 | 2 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3397 | PGE | 93280 | NEM | EXPNEM | Implementation | Solar PV | 107.302 |  | 2022-01-25 | 2022-02-03 | 7 | 2022-02-08 | 10 | 2022-02-10 | 2 | [15 empty] | 2022-02-10 | 2022-02-10 | 0 | 2022-02-10 | 2022-03-11 | 20 |  |  |  |  | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3398 | PGE | 95681 | NEM | EXPNEM | Implementation | Solar PV | 99.9 |  | 2022-01-25 | 2022-01-26 | 1 | 2022-02-01 | 5 | 2022-02-23 | 15 | [15 empty] | 2022-02-23 | 2022-02-23 | 0 | 2022-02-23 | 2022-02-28 | 3 | [5 empty] | 2022-02-01 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3399 | PGE | 95230 | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2022-02-11 | 2022-02-28 | 10 | 2022-03-21 | 25 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3400 | PGE | 94605 | NEM | EXPNEM | IA in Progress | Solar PV | 241.921 |  | 2022-01-25 | 2022-02-04 | 8 | 2022-02-11 | 13 | 2022-03-02 | 12 | [15 empty] | 2022-03-02 | 2022-03-02 | 0 | 2022-03-02 | [6 empty] | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3401 | PGE | 94596 | NEM | EXPNEM | IA in Progress | Solar PV | 101.728 |  | 2022-01-25 | 2022-02-08 | 10 | 2022-02-08 | 10 | 2022-03-16 | 25 | [15 empty] | 2022-03-16 | 2022-03-16 | 0 | 2022-03-16 | [6 empty] | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3402 | PGE | 94618 | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2022-01-27 | 2022-02-09 | 9 | 2022-03-31 | 44 | [27 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3403 | PGE | 93280 | NEM | EXPNEM | Study in Progress | Solar PV | 3125 |  | 2022-01-26 | 2022-01-28 | 2 | 2022-03-02 | 24 | [5 empty] | 2022-03-02 | 2022-03-25 | 17 | 2022-03-25 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3404 | PGE | 94558 | NEM | EXPNEM | Application Review in Progress | Solar PV | 237.837 |  | 2022-01-25 | 2022-02-08 | 10 | [29 empty] | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3405 | PGE | 94602 | NEM | EXPNEM | Study in Progress | Solar PV | 136 |  | 2022-01-27 | 2022-02-09 | 9 | 2022-03-25 | 40 | [27 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3406 | PGE | 93651 | NEM | EXPNEM | IA in Progress | Solar PV | 34.179 |  | 2022-03-11 | 2022-03-14 | 1 | 2022-03-18 | 5 | 2022-03-30 | 8 | [15 empty] | 2022-03-30 | 2022-03-30 | 0 | 2022-03-30 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3407 | PGE | 94558 | NEM | EXPNEM | Application Review in Progress | Solar PV | 118.919 |  | 2022-01-25 | 2022-02-08 | 10 | [29 empty] | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3408 | PGE | 94603 | NEM | EXPNEM | Study in Progress | Solar PV | 122 |  | 2022-01-27 | 2022-02-09 | 9 | 2022-02-22 | 17 | [27 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3409 | PGE | 94558 | NEM | EXPNEM | Application Review in Progress | Solar PV | 49.692 |  | 2022-02-10 | 2022-02-22 | 7 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3410 | PGE | 94601 | NEM | EXPNEM | Study in Progress | Solar PV | 267.259 |  | 2022-01-27 | 2022-02-10 | 10 | 2022-03-09 | 28 | [27 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3411 | PGE | 94558 | NEM | SNEM Paired Storage | Implementation | Solar PV, Storage | 57.8 |  | 2022-02-08 | 2022-02-08 | 0 | 2022-02-14 | 4 | 2022-02-14 | 0 | [18 empty] | 2022-02-08 | [7 empty] | 0 | [5 empty] | 2022-02-14 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-14 | 2022-02-15 | 1 |  |  |  |  | 1//19
3412 | PGE | 93637 | NEM | EXPNEM | Study in Progress | Solar PV | 840 |  | 2022-01-25 | 2022-02-02 | 6 | 2022-02-02 | 6 | [27 empty] | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3413 | PGE | 93637 | NEM | EXPNEM | IA in Progress | Solar PV | 83.878 |  | 2022-01-25 | 2022-02-03 | 7 | 2022-02-03 | 7 | 2022-02-22 | 12 | [15 empty] | 2022-02-22 | 2022-02-22 | 0 | 2022-02-22 | [6 empty] | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3414 | PGE | 93638 | NEM | EXPNEM | IA in Progress | Solar PV | 200 |  | 2022-01-25 | 2022-02-03 | 7 | 2022-02-03 | 7 | 2022-02-25 | 15 | [15 empty] | 2022-02-25 | 2022-02-25 | 0 | 2022-02-25 | [6 empty] | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3415 | PGE | 93638 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2022-01-25 | 2022-02-07 | 9 | 2022-02-07 | 9 | 2022-03-18 | 28 | [15 empty] | 2022-03-18 | 2022-03-18 | 0 | 2022-03-18 | [6 empty] | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3416 | PGE | 93637 | NEM | EXPNEM | IA in Progress | Solar PV | 83.878 |  | 2022-01-25 | 2022-02-07 | 9 | 2022-02-07 | 9 | 2022-02-22 | 10 | [15 empty] | 2022-02-22 | 2022-02-22 | 0 | 2022-02-22 | [6 empty] | 2022-01-25 | 2022-01-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3417 | PGE | 94607 | NEM | EXPNEM | Study in Progress | Solar PV | 203.356 |  | 2022-01-27 | 2022-02-10 | 10 | 2022-02-10 | 10 | [27 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3418 | PGE | 94603 | NEM | EXPNEM | Study in Progress | Solar PV | 135.906 |  | 2022-01-27 | 2022-02-10 | 10 | 2022-03-09 | 28 | [27 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3419 | PGE | 93454 | Non-NEM | Non-Export | Withdrawn | Solar PV | 4950 |  | 2022-01-27 | 0 | [30 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3420 | PGE | 94601 | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2022-01-27 | 2022-02-10 | 10 | 2022-03-09 | 28 | [27 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3421 | PGE | 94089 | NEM | EXPNEM | Application Review in Progress | Solar PV | 125.64 |  | 2022-01-26 | 2022-02-09 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3422 | PGE | 94603 | NEM | EXPNEM | Application Review in Progress | Solar PV | 170 |  | 2022-01-28 | 2022-02-11 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3423 | PGE | 94621 | NEM | EXPNEM | Application Review in Progress | Solar PV | 208 |  | 2022-01-27 | 2022-02-10 | 10 | [29 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3424 | PGE | 94618 | NEM | EXPNEM | Application Review in Progress | Solar PV | 42.091 |  | 2022-01-26 | 2022-02-09 | 10 | [29 empty] | 2022-01-26 | 2022-01-26 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3425 | PGE | 94086 | NEM | EXPNEM | Implementation | Solar PV | 30.619 |  | 2022-01-26 | 2022-02-09 | 10 | 2022-02-17 | 16 | 2022-03-11 | 15 | [15 empty] | 2022-03-11 | 2022-03-11 | 0 | 2022-03-11 | 2022-03-14 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3426 | PGE | 95134 | NEM | EXPNEM | Study in Progress | Solar PV | 200 |  | 2022-02-09 | 2022-02-18 | 7 | 2022-02-25 | 11 | [27 empty] | 2022-02-09 | 2022-02-09 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3427 | PGE | 94606 | NEM | EXPNEM | Application Review in Progress | Solar PV | 57.71 |  | 2022-01-27 | 2022-02-10 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3428 | PGE | 95118 | NEM | EXPNEM | IA in Progress | Solar PV | 54.686 |  | 2022-01-27 | 2022-02-10 | 10 | 2022-03-02 | 23 | 2022-03-23 | 15 | [15 empty] | 2022-03-23 | 2022-03-23 | 0 | 2022-03-23 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3429 | PGE | 94403 | NEM | EXPNEM | IA in Progress | Solar PV | 79.852 |  | 2022-01-27 | 2022-02-10 | 10 | 2022-02-18 | 16 | 2022-03-14 | 15 | [15 empty] | 2022-03-14 | 2022-03-14 | 0 | 2022-03-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3430 | PGE | 93307 | NEM | EXPNEM | IA in Progress | Solar PV | 175 |  | 2022-01-26 | 2022-02-09 | 10 | 2022-02-09 | 10 | 2022-02-11 | 2 | [15 empty] | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | [6 empty] | 2022-01-26 | 2022-01-26 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3431 | PGE | 94544 | NEM | EXPNEM | IA in Progress | Solar PV | 113.598 |  | 2022-01-27 | 2022-02-09 | 9 | 2022-02-09 | 9 | 2022-02-18 | 7 | [15 empty] | 2022-02-18 | 2022-02-18 | 0 | 2022-02-18 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3432 | PGE | 93620 | NEM | EXPNEM | Application Review in Progress | Solar PV | 82.742 |  | 2022-02-07 | 2022-02-09 | 2 | [29 empty] | 2022-02-07 | 2022-02-07 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3433 | PGE | 94403 | NEM | EXPNEM | IA in Progress | Solar PV | 97.148 |  | 2022-01-27 | 2022-02-09 | 9 | 2022-02-09 | 9 | 2022-03-03 | 15 | [15 empty] | 2022-03-03 | 2022-03-03 | 0 | 2022-03-03 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3434 | PGE | 94544 | NEM | EXPNEM | Application Review in Progress | Solar PV | 79.852 |  | 2022-01-27 | 2022-02-10 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3435 | PGE | 93933 | NEM | EXPNEM | Application Review in Progress | Solar PV | 86.044 |  | 2022-01-26 | 2022-02-08 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3436 | PGE | 95361 | NEM | EXPNEM | Application Review in Progress | Solar PV | 59.538 |  | 2022-01-27 | 2022-01-28 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3437 | PGE | 94133 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 120 |  | 2022-02-16 | 2022-03-03 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3438 | PGE | 94559 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 32.779 |  | 2022-01-26 | 2022-02-04 | 7 | 2022-03-01 | 23 | [27 empty] | 2022-01-26 | 2022-01-26 | 1 | 2022-02-11 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3439 | PGE | 93422 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 33.86 |  | 2022-01-27 | 2022-02-03 | 5 | 2022-02-08 | 8 | 2022-02-09 | 1 | [18 empty] | 2022-01-27 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3440 | PGE | 94602 | Non-NEM | Inadvertent Export | Application Accepted | Storage | 10 |  | 2022-01-27 | 2022-02-01 | 3 | 2022-02-04 | 6 | 2022-02-08 | 2 | [18 empty] | 2022-01-27 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3441 | PGE | 94560 | NEM | EXPNEM | Implementation | Solar PV | 466.5 |  | 2022-01-27 | 2022-02-08 | 8 | 2022-02-08 | 8 | 2022-02-17 | 7 | [15 empty] | 2022-02-17 | 2022-02-17 | 0 | 2022-02-17 | 2022-03-18 | 20 |  |  |  |  | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3442 | PGE | 94606 | NEM | VNEM | Application Review in Progress | Solar PV | 36.787 |  | 2022-01-27 | 2022-01-28 | 1 | [22 empty] | 2022-01-27 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3443 | PGE | 94558 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.437 |  | 2022-01-28 | 2022-02-04 | 5 | 2022-02-04 | 5 | 2022-02-08 | 2 | [18 empty] | 2022-01-28 | [7 empty] | 0 | [5 empty] | 2022-02-08 | 2022-03-03 | 16 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-08 | 2022-03-03 | 16 | 2022-03-03 |  | 2022-03-07 | 2 | 1//19
3444 | PGE | 93454 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2022-01-28 | 2022-02-08 | 7 | 2022-02-08 | 7 | 2022-02-09 | 1 | [18 empty] | 2022-01-27 | 2022-01-28 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3445 | PGE | 93622 | NEM | EXPNEM | Application Accepted | Solar PV | 1500 |  | 2022-01-27 | 2022-01-27 | 0 | 2022-02-09 | 9 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3446 | PGE | 93637 | NEM | EXPNEM | Application Review in Progress | Solar PV | 164.833 |  | 2022-01-27 | 2022-02-04 | 6 | [29 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3447 | PGE | 93662 | NEM | EXPNEM | Implementation | Solar PV | 53.595 |  | 2022-01-27 | 2022-02-08 | 8 | 2022-02-08 | 8 | 2022-02-15 | 5 | [15 empty] | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | 2022-02-15 | 0 |  |  |  |  | 2022-01-27 | 2022-01-27 | 1 | 2022-02-10 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3448 | PGE | 94080 | NEM | EXPNEM | Application Review in Progress | Solar PV | 76.918 |  | 2022-01-27 | 2022-02-10 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3449 | PGE | 94028 | NEM | EXPNEM | IA in Progress | Solar PV | 56.903 |  | 2022-01-27 | 2022-02-10 | 10 | 2022-02-10 | 10 | 2022-02-28 | 11 | [15 empty] | 2022-02-28 | 2022-03-21 | 15 | 2022-03-21 | [6 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3450 | PGE | 93638 | NEM | EXPNEM | Application Review in Progress | Solar PV | 48.896 |  | 2022-01-27 | 2022-02-10 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3451 | PGE | 95963 | NEM | EXPNEM | Study in Progress | Solar PV | 300 |  | 2022-02-08 | 2022-02-16 | 6 | 2022-02-22 | 9 | 2022-03-17 | 17 | 2022-03-17 | 2022-03-24 | 5 | 2022-02-22 | 2022-03-24 | 22 | 2022-03-24 | [19 empty] | 0 |  | 2022-03-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3452 | PGE | 93610 | NEM | EXPNEM | Application Review in Progress | Solar PV | 90 |  | 2022-01-27 | 2022-02-08 | 8 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3453 | PGE | 94010 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 4845 |  | 2022-02-08 | 2022-02-11 | 3 | 2022-03-16 | 25 | [5 empty] | 2022-03-25 | [22 empty] | 2022-03-31 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3454 | PGE | 95415 | NEM | NEMMT | Application Review in Progress | Solar PV, Storage | 750 |  | 2022-03-03 | 2022-03-17 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3455 | PGE | 93249 | NEM | EXPNEM | Study in Progress | Solar PV | 4140 |  | 2022-01-27 | 2022-01-31 | 2 | 2022-03-02 | 23 | [5 empty] | 2022-03-02 | 2022-03-25 | 17 | 2022-03-25 | [18 empty] | 2022-01-27 | 2022-01-27 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3456 | PGE | 93637 | NEM | EXPNEM | Study in Progress | Solar PV | 110 |  | 2022-03-02 | 2022-03-16 | 10 | 2022-03-18 | 12 | [27 empty] | 2022-03-02 | 2022-03-02 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3457 | PGE | 94562 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 654.396 |  | 2022-01-28 | 2022-01-31 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3458 | PGE | 95492 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 975 |  | 2022-01-27 | 2022-01-31 | 2 | 2022-02-16 | 14 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3459 | PGE | 94562 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 465.228 |  | 2022-01-28 | 2022-02-03 | 4 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3460 | PGE | 95472 | NEM | EXPNEM | Application Accepted | Solar PV | 64.67 |  | 2022-02-08 | 2022-02-22 | 9 | 2022-03-30 | 35 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3461 | PGE | 93454 | NEM | EXPNEM | Study in Progress | Solar PV | 5000 |  | 2022-01-28 | 2022-02-01 | 2 | 2022-02-23 | 17 | [27 empty] | 2022-01-28 | 2022-01-28 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3462 | PGE | 94903 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2022-01-28 | 2022-02-10 | 9 | 2022-02-10 | 9 | 2022-02-28 | 11 | [18 empty] | 2022-01-28 | [7 empty] | 0 | [5 empty] | 2022-02-28 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-28 | 2022-02-28 | 0 | 2022-02-10 |  | 2022-02-28 | 13 | 1//19
3463 | PGE | 93640 | NEM | EXPNEM | Application Review in Progress | Solar PV | 825.695 |  | 2022-02-07 | 2022-02-22 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3464 | PGE | 95677 | NEM | EXPNEM | Study in Progress | Solar PV | 120 |  | 2022-03-08 | 2022-03-21 | 9 | 2022-03-21 | 9 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3465 | PGE | 95677 | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2022-03-08 | 2022-03-21 | 9 | 2022-03-21 | 9 | [27 empty] | 2022-03-08 | 2022-03-08 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3466 | PGE | 93646 | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2022-02-07 | 2022-02-16 | 7 | 2022-03-07 | 19 | 2022-03-17 | 8 | [15 empty] | 2022-03-17 | 2022-03-17 | 0 | 2022-03-17 | 2022-03-28 | 7 |  |  |  |  | 2022-02-07 | 2022-02-07 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3467 | PGE | 95409 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.398 |  | 2022-01-28 | 2022-02-04 | 5 | 2022-02-04 | 5 | 2022-02-08 | 2 | [18 empty] | 2022-01-28 | [7 empty] | 0 | [5 empty] | 2022-02-08 | 2022-02-08 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-02-08 |  |  | 2022-02-08 |  | 2022-02-08 | 0 | 1//19
3468 | PGE | 95776 | NEM | EXPNEM | Application Accepted | Solar PV | 735.029 |  | 2022-01-28 | 2022-02-01 | 2 | 2022-03-02 | 22 | [27 empty] | 2022-01-28 | 2022-01-28 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3469 | PGE | 95401 | NEM | EXPNEM | IA in Progress | Solar PV | 130.94 |  | 2022-01-28 | 2022-02-10 | 9 | 2022-02-10 | 9 | 2022-03-23 | 28 | [15 empty] | 2022-03-23 | 2022-03-23 | 0 | 2022-03-23 | [6 empty] | 2022-01-28 | 2022-01-28 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3470 | PGE | 94542 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2022-03-08 | 2022-03-22 | 10 | 2022-03-22 | 10 | [17 empty] | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 | 2022-03-08 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3471 | PGE | 93908 | NEM | EXPNEM | Commercial | Solar PV | 39.596 |  | 2022-02-18 | 2022-02-22 | 1 | 2022-03-08 | 11 | 2022-03-22 | 10 | [15 empty] | 2022-03-22 | 2022-03-22 | 0 | 2022-03-22 | 2022-03-24 | 2 | [5 empty] | 0 | [5 empty] | 2022-03-24 | 2022-03-31 | 5 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-24 | 2022-03-24 | 0 | 2022-03-31 |  | 2022-03-31 | 0 | 1//19
3472 | PGE | 93654 | NEM | VNEM | Application Review in Progress | Solar PV | 240 |  | 2022-02-01 | 2022-02-15 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3473 | PGE | 93242 | NEM | EXPNEM | Application Review in Progress | Solar PV | 95.8 |  | 2022-01-31 | 2022-02-08 | 6 | [29 empty] | 2022-01-31 | 2022-01-31 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3474 | PGE | 93242 | NEM | EXPNEM | Implementation | Solar PV | 50 |  | 2022-01-31 | 2022-02-11 | 9 | 2022-02-11 | 9 | 2022-03-22 | 26 | [15 empty] | 2022-03-22 | 2022-03-22 | 0 | 2022-03-22 | 2022-03-23 | 1 |  |  |  |  | 2022-01-31 | 2022-01-31 | 1 | 2022-02-11 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3475 | PGE | 93242 | NEM | EXPNEM | Application Review in Progress | Solar PV | 83.3 |  | 2022-01-31 | 2022-02-11 | 9 | [29 empty] | 2022-01-31 | 2022-01-31 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3476 | PGE | 93308 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 6452.2 |  | 2022-03-21 | 2022-03-24 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3477 | PGE | 95677 | NEM | EXPNEM | Application Review in Progress | Solar PV | 312.5 |  | 2022-01-31 | 2022-02-10 | 8 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3478 | PGE | 95215 | Non-NEM | Non-Export | Withdrawn | Solar PV | 240 |  | 2022-01-31 | 2022-02-04 | 4 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3479 | PGE | 94061 | NEM | EXPNEM | IA in Progress | Solar PV | 125 |  | 2022-01-31 | 2022-02-01 | 1 | 2022-02-01 | 1 | 2022-02-10 | 7 | [15 empty] | 2022-02-10 | 2022-02-10 | 0 | 2022-02-10 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3480 | PGE | 93610 | NEM | EXPNEM | Application Review in Progress | Solar PV | 375 |  | 2022-02-17 | 2022-03-01 | 7 | [29 empty] | 2022-02-17 | 2022-02-17 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3481 | PGE | 94947 | NEM | EXPNEM | Study in Progress | Solar PV | 50 |  | 2022-02-02 | 2022-02-07 | 3 | 2022-03-07 | 22 | [27 empty] | 2022-02-02 | 2022-02-02 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3482 | PGE | 94063 | NEM | EXPNEM | Study in Progress | Solar PV | 223.299 |  | 2022-01-31 | 2022-02-01 | 1 | 2022-03-29 | 40 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3483 | PGE | 95361 | NEM | EXPNEM | IA in Progress | Solar PV | 40.1 |  | 2022-02-03 | 2022-02-17 | 10 | 2022-02-23 | 13 | 2022-03-09 | 10 | [15 empty] | 2022-03-09 | 2022-03-09 | 0 | 2022-03-09 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3484 | PGE | 95037 | NEM | EXPNEM | IA in Progress | Solar PV | 900 |  | 2022-02-01 | 2022-02-10 | 7 | 2022-02-22 | 14 | 2022-03-09 | 11 | [15 empty] | 2022-03-09 | 2022-03-09 | 0 | 2022-03-09 | [6 empty] | 2022-02-17 | 2022-02-17 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3485 | PGE | 93307 | NEM | EXPNEM | IA in Progress | Solar PV | 200.408 |  | 2022-02-01 | 2022-02-09 | 6 | 2022-02-09 | 6 | 2022-02-15 | 4 | [15 empty] | 2022-02-15 | 2022-03-04 | 12 | 2022-03-04 | [6 empty] | 2022-02-01 | 2022-02-01 | 1 | 2022-02-11 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3486 | PGE | 94602 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.282 |  | 2022-03-29 | 0 | [23 empty] | 2022-03-29 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3487 | PGE | 93239 | Non-NEM | Inadvertent Export | Application Accepted | Storage | 929.5 |  | 2022-02-01 | 2022-02-10 | 7 | 2022-03-23 | 35 | [27 empty] | 2022-02-01 | 2022-02-01 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3488 | PGE | 93720 | NEM | EXPNEM | Implementation | Solar PV | 125 |  | 2022-02-01 | 2022-02-10 | 7 | 2022-02-15 | 10 | 2022-02-25 | 7 | [15 empty] | 2022-02-25 | 2022-02-25 | 0 | 2022-02-25 | 2022-03-31 | 24 |  |  |  |  | 2022-02-01 | 2022-02-01 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3489 | PGE | 95991 | NEM | EXPNEM | Application Accepted | Solar PV | 150 |  | 2022-02-02 | 2022-02-10 | 6 | 2022-02-16 | 10 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3490 | PGE | 94086 | NEM | EXPNEM | IA in Progress | Solar PV | 179.342 |  | 2022-02-01 | 2022-02-11 | 8 | 2022-02-11 | 8 | 2022-03-07 | 15 | [15 empty] | 2022-03-07 | 2022-03-07 | 0 | 2022-03-07 | [6 empty] | 2022-02-01 | 2022-02-01 | 1 | 2022-03-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3491 | PGE | 94086 | NEM | EXPNEM | IA in Progress | Solar PV | 145.259 |  | 2022-02-01 | 2022-02-11 | 8 | 2022-02-11 | 8 | 2022-03-07 | 15 | [15 empty] | 2022-03-07 | 2022-03-07 | 0 | 2022-03-07 | [6 empty] | 2022-02-01 | 2022-02-01 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3492 | PGE | 95901 | NEM | EXPNEM | IA in Progress | Solar PV | 333 |  | 2022-02-01 | 2022-02-11 | 8 | 2022-02-11 | 8 | 2022-03-07 | 15 | [15 empty] | 2022-03-07 | 2022-03-28 | 15 | 2022-03-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3493 | PGE | 95066 | NEM | EXPNEM | Application Review in Progress | Solar PV | 362.268 |  | 2022-02-01 | 2022-02-15 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3494 | PGE | 93460 | NEM | EXPNEM | Application Accepted | Solar PV | 1430.687 |  | 2022-02-08 | 2022-02-23 | 10 | 2022-03-16 | 25 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3495 | PGE | 95901 | NEM | EXPNEM | IA in Progress | Solar PV | 84.567 |  | 2022-02-01 | 2022-02-11 | 8 | 2022-02-11 | 8 | 2022-03-07 | 15 | [15 empty] | 2022-03-07 | 2022-03-28 | 15 | 2022-03-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3496 | PGE | 93638 | NEM | EXPNEM | Application Review in Progress | Solar PV | 124.8 |  | 2022-02-07 | 2022-02-22 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3497 | PGE | 93420 | NEM | EXPNEM | Application Review in Progress | Solar PV | 89.344 |  | 2022-02-08 | 2022-02-18 | 8 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3498 | PGE | 95220 | NEM | EXPNEM | Application Review in Progress | Solar PV | 65.579 |  | 2022-02-24 | 2022-03-02 | 4 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3499 | PGE | 94010 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 55.97 |  | 2022-02-07 | 2022-02-17 | 8 | 2022-02-17 | 8 | [27 empty] | 2022-02-07 | 2022-02-07 | 1 | 2022-02-11 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3500 | PGE | 95918 | NEM | EXPNEM | IA in Progress | Solar PV | 58.444 |  | 2022-02-01 | 2022-02-02 | 1 | 2022-02-04 | 3 | 2022-02-28 | 15 | [15 empty] | 2022-02-28 | 2022-02-28 | 0 | 2022-02-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3501 | PGE | 94539 | NEM | EXPNEM | IA in Progress | Solar PV | 189.223 |  | 2022-02-02 | 2022-02-14 | 8 | 2022-02-14 | 8 | 2022-03-23 | 26 | [15 empty] | 2022-03-23 | 2022-03-23 | 0 | 2022-03-23 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3502 | PGE | 95901 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 516 |  | 2022-02-02 | 2022-02-14 | 8 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3503 | PGE | 93906 | NEM | EXPNEM | Implementation | Solar PV | 82.426 |  | 2022-02-07 | 2022-02-14 | 5 | 2022-02-14 | 5 | 2022-03-23 | 26 | [15 empty] | 2022-03-23 | 2022-03-23 | 0 | 2022-03-23 | 2022-03-30 | 5 |  |  |  |  | 2022-02-07 | 2022-02-07 | 1 | 2022-03-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3504 | PGE | 95340 | NEM | EXPNEM | IA in Progress | Solar PV | 175 |  | 2022-02-02 | 2022-02-16 | 10 | 2022-03-07 | 22 | 2022-03-28 | 15 | [15 empty] | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28 | [6 empty] | 2022-02-02 | 2022-02-02 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3505 | PGE | 94563 | NEM | EXPNEM | IA in Progress | Solar PV | 76.296 |  | 2022-02-02 | 2022-02-09 | 5 | 2022-02-09 | 5 | 2022-02-25 | 11 | [15 empty] | 2022-02-25 | 2022-03-16 | 13 | 2022-03-16 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3506 | PGE | 93241 | NEM | EXPNEM | IA in Progress | Solar PV | 747.708 |  | 2022-02-02 | 2022-02-14 | 8 | 2022-03-01 | 18 | 2022-03-16 | 11 | [15 empty] | 2022-03-16 | 2022-03-16 | 0 | 2022-03-16 | [6 empty] | 2022-02-02 | 2022-02-02 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3507 | PGE | 93405 | Non-NEM | Non-Export | Application Accepted | Storage | 10 |  | 2022-02-09 | 2022-03-01 | 13 | 2022-03-01 | 13 | [20 empty] | 2022-02-09 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3508 | PGE | 93908 | NEM | EXPNEM | Study in Progress | Solar PV | 132.214 |  | 2022-02-03 | 2022-02-14 | 7 | 2022-02-14 | 7 | 2022-03-08 | 15 | 2022-03-08 | [24 empty] | 2022-02-03 | 2022-02-03 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3509 | PGE | 95060 | NEM | EXPNEM | Application Review in Progress | Solar PV | 149.835 |  | 2022-03-30 | 0 | [30 empty] | 2022-03-30 | 2022-03-30 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3510 | PGE | 93203 | NEM | EXPNEM | Study in Progress | Solar PV | 747.708 |  | 2022-02-02 | 2022-02-03 | 1 | 2022-02-11 | 7 | [5 empty] | 2022-02-11 | 2022-03-07 | 15 | 2022-03-07 | [18 empty] | 2022-02-02 | 2022-02-02 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3511 | PGE | 95317 | NEM | EXPNEM | Application Review in Progress | Solar PV | 480 |  | 2022-02-23 | 2022-03-08 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3512 | PGE | 93307 | NEM | EXPNEM | Study in Progress | Solar PV | 747.708 |  | 2022-02-02 | 2022-02-04 | 2 | 2022-02-10 | 6 | [5 empty] | 2022-02-10 | 2022-03-07 | 16 | 2022-03-07 | [19 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3513 | PGE | 95366 | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.128 |  | 2022-02-02 | 2022-02-11 | 7 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3514 | PGE | 94563 | NEM | EXPNEM | IA in Progress | Solar PV | 67.234 |  | 2022-02-02 | 2022-02-09 | 5 | 2022-02-09 | 5 | 2022-02-25 | 11 | [15 empty] | 2022-02-25 | 2022-03-16 | 13 | 2022-03-16 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3515 | PGE | 93962 | NEM | EXPNEM | IA in Progress | Solar PV | 146.792 |  | 2022-02-08 | 2022-02-22 | 9 | 2022-03-07 | 18 | 2022-03-21 | 10 | [15 empty] | 2022-03-21 | 2022-03-21 | 0 | 2022-03-21 | [6 empty] | 2022-02-08 | 2022-02-08 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3516 | PGE | 94563 | NEM | EXPNEM | IA in Progress | Solar PV | 50.864 |  | 2022-02-02 | 2022-02-14 | 8 | 2022-02-14 | 8 | 2022-03-30 | 31 | [15 empty] | 2022-03-30 | 2022-03-30 | 0 | 2022-03-30 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3517 | PGE | 94563 | NEM | EXPNEM | IA in Progress | Solar PV | 126.296 |  | 2022-02-02 | 2022-02-14 | 8 | 2022-02-14 | 8 | 2022-03-30 | 31 | [15 empty] | 2022-03-30 | 2022-03-30 | 0 | 2022-03-30 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3518 | PGE | 93436 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 724.846 |  | 2022-02-08 | 2022-02-10 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3519 | PGE | 95030 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 45.34 |  | 2022-02-03 | 2022-02-09 | 4 | 2022-02-09 | 4 | 2022-02-11 | 2 | [18 empty] | 2022-02-03 | [6 empty] | 2022-02-03 | 2022-02-03 | 1 |  |  |  |  | 2022-03-16 | 2022-03-17 | 1 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-16 | 2022-03-16 | 0 | 2022-03-17 |  | 2022-03-24 | 5 | 1//19
3520 | PGE | 94574 | NEM | EXPNEM | IA in Progress | Solar PV | 50.518 |  | 2022-02-03 | 2022-02-16 | 9 | 2022-03-10 | 24 | 2022-03-31 | 15 | [15 empty] | 2022-03-31 | [10 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3521 | PGE | 94087 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.464 |  | 2022-02-08 | 2022-02-14 | 4 | 2022-03-30 | 35 | 2022-03-31 | 1 | [18 empty] | 2022-02-18 | [7 empty] | 0 | [5 empty] | 2022-03-31 | 2022-03-31 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-31 |  |  | 2022-03-31 |  | 2022-03-31 | 0 | 1//19
3522 | PGE | 93923 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.579 |  | 2022-02-03 | 2022-02-10 | 5 | [22 empty] | 2022-03-24 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3523 | PGE | 95448 | NEM | EXPNEM | Study in Progress | Solar PV | 60 |  | 2022-02-03 | 2022-02-04 | 1 | 2022-02-04 | 1 | 2022-02-22 | 11 | 2022-02-22 | 2022-03-22 | 20 | 2022-03-22 | [22 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3524 | PGE | 95485 | NEM | EXPNEM | Withdrawn | Solar PV | 30.48 |  | 2022-02-03 | 2022-02-16 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3525 | PGE | 94952 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.179 |  | 2022-02-04 | 2022-02-07 | 1 | 2022-02-11 | 5 | 2022-03-14 | 20 | [15 empty] | 2022-03-14 | 2022-03-14 | 0 | 2022-03-14 | [6 empty] | 2022-02-04 | 2022-02-04 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3526 | PGE | 94563 | NEM | EXPNEM | IA in Progress | Solar PV | 76.296 |  | 2022-02-03 | 2022-02-16 | 9 | 2022-02-16 | 9 | 2022-03-10 | 15 | [15 empty] | 2022-03-10 | 2022-03-31 | 15 | 2022-03-31 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3527 | PGE | 94025 | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 |  | 2022-02-03 | 2022-02-17 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3528 | PGE | 95228 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2022-02-07 | 2022-02-16 | 7 | 2022-02-16 | 7 | 2022-03-07 | 12 | 2022-03-07 | 2022-03-31 | 18 | [12 empty] | 2022-03-31 | 2022-03-31 | 0 | 2022-03-31 | [6 empty] | 2022-02-16 | 2022-02-16 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3529 | PGE | 93654 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 102.964 |  | 2022-02-04 | 2022-02-07 | 1 | 2022-02-14 | 6 | 2022-03-01 | 10 | [15 empty] | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | [6 empty] | 2022-02-04 | 2022-02-04 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3530 | PGE | 93725 | NEM | EXPNEM | Study in Progress | Solar PV | 150 |  | 2022-02-17 | 2022-03-04 | 10 | 2022-03-29 | 27 | [27 empty] | 2022-02-17 | 2022-02-17 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3531 | PGE | 95205 | NEM | EXPNEM | IA in Progress | Solar PV | 32.288 |  | 2022-02-07 | 2022-02-18 | 9 | 2022-02-18 | 9 | 2022-03-07 | 10 | [15 empty] | 2022-03-07 | 2022-03-07 | 0 | 2022-03-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3532 | PGE | 95301 | NEM | VNEM | Application Review in Progress | Solar PV | 161.834 |  | 2022-02-08 | 2022-02-10 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3533 | PGE | 93436 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 376.48 |  | 2022-02-08 | 2022-02-09 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3534 | PGE | 94588 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 445.656 |  | 2022-02-08 | 2022-02-10 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3535 | PGE | 94591 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 376.48 |  | 2022-02-08 | 2022-02-10 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3536 | PGE | 95301 | NEM | VNEM | Application Review in Progress | Solar PV | 161.834 |  | 2022-02-08 | 2022-02-10 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3537 | PGE | 95301 | NEM | VNEM | Application Review in Progress | Solar PV | 77.399 |  | 2022-02-08 | 2022-02-10 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3538 | PGE | 93436 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 573.844 |  | 2022-02-08 | 2022-02-10 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3539 | PGE | 93436 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 390.667 |  | 2022-02-08 | 2022-02-10 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3540 | PGE | 93630 | NEM | EXPNEM | Study in Progress | Solar PV | 40.482 |  | 2022-02-04 | 2022-02-11 | 5 | 2022-02-11 | 5 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3541 | PGE | 94536 | NEM | EXPNEM | Application Review in Progress | Solar PV | 37.117 |  | 2022-02-08 | 2022-02-23 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3542 | PGE | 93263 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2022-02-04 | 2022-02-09 | 3 | 2022-02-09 | 3 | 2022-02-15 | 4 | [15 empty] | 2022-02-15 | 2022-03-04 | 12 | 2022-03-04 | [6 empty] | 2022-02-04 | 2022-02-04 | 1 | 2022-02-11 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3543 | PGE | 94801 | NEM | EXPNEM | Application Review in Progress | ENGN, Solar PV | 720 |  | 2022-02-16 | 2022-03-03 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3544 | PGE | 94595 | NEM | VNEM | Application Review in Progress | Solar PV | 46.631 |  | 2022-03-02 | 2022-03-03 | 1 | [22 empty] | 2022-03-02 | [6 empty] | 2022-03-02 | 2022-03-02 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3545 | PGE | 94706 | NEM | EXPNEM | Study in Progress | Solar PV | 200 |  | 2022-02-04 | 2022-02-08 | 2 | 2022-02-08 | 2 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3546 | PGE | 94706 | NEM | EXPNEM | Study in Progress | Solar PV | 49.046 |  | 2022-02-04 | 2022-02-08 | 2 | 2022-02-08 | 2 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3547 | PGE | 94706 | NEM | EXPNEM | IA in Progress | Solar PV | 107.085 |  | 2022-02-17 | 2022-03-04 | 10 | 2022-03-04 | 10 | 2022-03-25 | 15 | [15 empty] | 2022-03-25 | 2022-03-25 | 0 | 2022-03-25 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3548 | PGE | 94903 | NEM | EXPNEM | Application Review in Progress | Solar PV | 900 |  | 2022-02-14 | 2022-02-14 | 0 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3549 | PGE | 94507 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 37.4 |  | 2022-02-17 | 2022-03-10 | 14 | 2022-03-23 | 23 | 2022-03-23 | 0 | [18 empty] | 2022-03-14 | [7 empty] | 0 | [5 empty] | 2022-03-23 | 2022-03-23 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-23 |  |  | 2022-03-23 |  | 2022-03-23 | 0 | 1//19
3550 | PGE | 95928 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 511.126 |  | 2022-02-08 | 2022-02-09 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3551 | PGE | 95928 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 493.832 |  | 2022-02-08 | 2022-02-09 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3552 | PGE | 95928 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 725.784 |  | 2022-02-08 | 2022-02-09 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3553 | PGE | 95928 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 725.784 |  | 2022-02-08 | 2022-02-09 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3554 | PGE | 95928 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 428.362 |  | 2022-02-08 | 2022-02-09 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3555 | PGE | 95991 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 625.726 |  | 2022-02-08 | 2022-02-09 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3556 | PGE | 95991 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 744.876 |  | 2022-02-08 | 2022-02-09 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3557 | PGE | 95991 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 1243.013 |  | 2022-02-08 | 2022-02-09 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3558 | PGE | 95991 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 1315.23 |  | 2022-02-08 | 2022-02-10 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3559 | PGE | 95991 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 625.726 |  | 2022-02-08 | 2022-02-09 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3560 | PGE | 93420 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2022-02-09 | 2022-02-14 | 3 | 2022-02-14 | 3 | 2022-02-17 | 3 | [18 empty] | 2022-02-09 | 2022-02-07 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3561 | PGE | 95963 | NEM | EXPNEM | Study in Progress | Solar PV | 66.049 |  | 2022-02-10 | 2022-02-11 | 1 | 2022-03-08 | 17 | 2022-03-23 | 11 | 2022-03-23 | 2022-03-24 | 1 | 2022-03-24 | 2022-03-29 | 3 | 2022-03-29 | 2022-03-29 | 0 |  |  |  | 2022-03-29 | [13 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3562 | PGE | 94563 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2022-02-08 | 2022-02-09 | 1 | 2022-02-09 | 1 | 2022-02-25 | 11 | [15 empty] | 2022-02-09 | 2022-02-09 | 0 | 2022-02-09 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3563 | PGE | 94515 | NEM | EXPNEM | Application Review in Progress | Solar PV | 108 |  | 2022-02-08 | 2022-02-23 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3564 | PGE | 94549 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.15 |  | 2022-02-09 | 2022-03-01 | 13 | 2022-03-10 | 20 | 2022-03-11 | 1 | [18 empty] | 2022-02-09 | [7 empty] | 0 | [5 empty] | 2022-03-11 | 2022-03-11 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-11 |  |  | 2022-03-11 |  | 2022-03-11 | 0 | 1//19
3565 | PGE | 94583 | NEM | EXPNEM | Application Review in Progress | Solar PV | 68.358 |  | 2022-02-08 | 2022-02-22 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3566 | PGE | 95928 | NEM | EXPNEM | Application Review in Progress | Solar PV, WIND | 86.681 |  | 2022-02-08 | 2022-02-23 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3567 | PGE | 95492 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 54.167 |  | 2022-02-08 | 2022-02-23 | 10 | 2022-03-10 | 21 | [27 empty] | 2022-02-08 | 2022-02-08 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3568 | PGE | 95492 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 48.012 |  | 2022-02-08 | 2022-02-23 | 10 | 2022-03-10 | 21 | [27 empty] | 2022-02-08 | 2022-02-08 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3569 | PGE | 93725 | NEM | EXPNEM | Application Review in Progress | Solar PV | 300 |  | 2022-03-28 | 0 | [31 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3570 | PGE | 93609 | NEM | EXPNEM | Application Review in Progress | Solar PV | 840 |  | 2022-02-08 | 2022-02-22 | 9 | [30 empty] | 2022-03-07 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3571 | PGE | 96035 | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 |  | 2022-02-08 | 2022-02-09 | 1 | 2022-02-09 | 1 | 2022-03-01 | 13 | [15 empty] | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | [6 empty] | 2022-02-08 | 2022-02-08 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3572 | PGE | 95938 | Non-NEM | Non-Export | Withdrawn | Solar PV | 41.76 |  | 2022-02-08 | 2022-02-11 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3573 | PGE | 93312 | NEM | EXPNEM | IA in Progress | Solar PV | 180 |  | 2022-02-08 | 2022-02-22 | 9 | 2022-02-22 | 9 | 2022-03-15 | 15 | [15 empty] | 2022-03-15 | [10 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3574 | PGE | 95963 | NEM | EXPNEM | Implementation | Solar PV | 36 |  | 2022-02-24 | 2022-03-05 | 6 | 2022-03-28 | 22 | 2022-03-30 | 2 | [15 empty] | 2022-03-30 | 2022-03-30 | 0 | 2022-03-30 | 2022-03-31 | 1 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3575 | PGE | 94040 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 1470 |  | 2022-02-17 | 2022-03-04 | 10 | 2022-03-04 | 10 | [5 empty] | 2022-03-04 | 2022-03-28 | 16 | 2022-03-28 | 2022-03-28 | 0 |  |  |  | 2022-03-28 | [12 empty] | 2022-02-17 | 2022-02-17 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3576 | PGE | 95963 | NEM | EXPNEM | Application Review in Progress | Solar PV | 187.5 |  | 2022-02-08 | 2022-02-18 | 8 | [29 empty] | 2022-02-08 | 2022-02-08 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3577 | PGE | 93308 | NEM | EXPNEM | IA in Progress | Solar PV | 240 |  | 2022-02-08 | 2022-02-23 | 10 | 2022-02-23 | 10 | 2022-03-16 | 15 | [15 empty] | 2022-03-16 | [10 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3578 | PGE | 94901 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 823.684 |  | 2022-02-08 | 2022-02-23 | 10 | 2022-02-23 | 10 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3579 | PGE | 93454 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 248.292 |  | 2022-02-09 | 2022-02-24 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3580 | PGE | 94509 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 159.315 |  | 2022-02-09 | 2022-02-24 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3581 | PGE | 93722 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 185.867 |  | 2022-02-09 | 2022-02-24 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3582 | PGE | 93711 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 283.047 |  | 2022-02-09 | 2022-02-23 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3583 | PGE | 93711 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 292.321 |  | 2022-02-09 | 2022-02-23 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3584 | PGE | 94509 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 331.056 |  | 2022-02-09 | 2022-02-24 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3585 | PGE | 93454 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 248.292 |  | 2022-02-09 | 2022-02-24 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3586 | PGE | 93722 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 283.516 |  | 2022-02-09 | 2022-02-24 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3587 | PGE | 93308 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 510.172 |  | 2022-02-09 | 2022-02-24 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3588 | PGE | 93711 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 283.516 |  | 2022-02-09 | 2022-02-23 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3589 | PGE | 93611 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 345.472 |  | 2022-02-09 | 2022-02-23 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3590 | PGE | 95376 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 477.944 |  | 2022-02-09 | 2022-02-24 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3591 | PGE | 93611 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 345.472 |  | 2022-02-09 | 2022-02-23 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3592 | PGE | 95762 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2022-02-09 | 2022-02-14 | 3 | 2022-02-14 | 3 | 2022-03-08 | 15 | [18 empty] | 2022-02-09 | 2022-03-08 | 18 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-02-17 |  | 2022-03-08 | 14 | 1//19
3593 | PGE | 93307 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 313.762 |  | 2022-02-10 | 2022-02-11 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3594 | PGE | 95963 | NEM | EXPNEM | IA in Progress | Solar PV | 125 |  | 2022-02-09 | 2022-02-24 | 10 | 2022-02-24 | 10 | 2022-03-15 | 13 | [15 empty] | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | [6 empty] | 2022-02-09 | 2022-02-09 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3595 | PGE | 93721 | NEM | EXPNEM | Application Review in Progress | Solar PV | 113.93 |  | 2022-02-09 | 2022-02-23 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3596 | PGE | 94040 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1770 |  | 2022-02-17 | 2022-02-18 | 1 | 2022-03-30 | 28 | [27 empty] | 2022-02-17 | 2022-02-17 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3597 | PGE | 93308 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2022-02-09 | 2022-02-24 | 10 | 2022-03-02 | 14 | 2022-03-23 | 15 | [15 empty] | 2022-03-23 | [10 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3598 | PGE | 95117 | NEM | EXPNEM | Application Review in Progress | Solar PV | 50 |  | 2022-02-09 | 2022-02-18 | 7 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3599 | PGE | 93280 | NEM | EXPNEM | IA in Progress | Solar PV | 160 |  | 2022-02-09 | 2022-02-24 | 10 | 2022-03-09 | 19 | 2022-03-23 | 10 | [15 empty] | 2022-03-23 | 2022-03-23 | 0 | 2022-03-23 | [6 empty] | 2022-02-09 | 2022-02-09 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3600 | PGE | 93401 | NEM | EXPNEM | Implementation | Solar PV | 66.256 |  | 2022-02-09 | 2022-02-17 | 6 | 2022-02-17 | 6 | 2022-03-08 | 12 | [15 empty] | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 | 2022-03-14 | 4 | [5 empty] | 0 |  | 2022-03-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3601 | PGE | 95003 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 20 |  | 2022-02-09 | 2022-02-24 | 10 | 2022-02-24 | 10 | [20 empty] | 2022-02-09 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3602 | PGE | 93312 | NEM | EXPNEM | IA in Progress | Solar PV | 214.36 |  | 2022-02-09 | 2022-02-17 | 6 | 2022-03-17 | 25 | 2022-03-23 | 4 | [15 empty] | 2022-03-23 | 2022-03-23 | 0 | 2022-03-23 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3603 | PGE | 93312 | NEM | EXPNEM | IA in Progress | Solar PV | 270.323 |  | 2022-02-09 | 2022-02-22 | 8 | 2022-02-23 | 9 | 2022-03-28 | 23 | [15 empty] | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3604 | PGE | 93725 | NEM | EXPNEM | Application Accepted | Solar PV | 122.294 |  | 2022-02-14 | 2022-02-25 | 8 | 2022-03-16 | 21 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3605 | PGE | 93432 | NEM | EXPNEM | Implementation | Solar PV | 30.008 |  | 2022-02-09 | 2022-02-10 | 1 | 2022-02-11 | 2 | 2022-03-01 | 11 | [15 empty] | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | 2022-03-01 | 0 |  |  |  |  | 2022-02-09 | 2022-02-09 | 1 |  |  |  |  | 2022-03-08 |  |  | 2022-03-23 |  | 15 | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-08 | 2022-03-09 | 1 | 2022-03-10 | 2022-03-10 | 2022-03-10 | 1 | 1//19 |  | 20
3606 | PGE | 93309 | NEM | EXPNEM | IA in Progress | Solar PV | 143.453 |  | 2022-02-09 | 2022-02-24 | 10 | 2022-02-24 | 10 | 2022-03-15 | 13 | [15 empty] | 2022-03-15 | [10 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3607 | PGE | 94085 | NEM | EXPNEM | Application Review in Progress | Solar PV | 133.2 |  | 2022-03-17 | 2022-03-31 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3608 | PGE | 93307 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 283.516 |  | 2022-02-10 | 2022-02-14 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3609 | PGE | 93657 | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2022-03-07 | 2022-03-14 | 5 | 2022-03-14 | 5 | 2022-03-24 | 8 | [15 empty] | 2022-03-24 | [10 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3610 | PGE | 95501 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2022-02-11 | 2022-02-25 | 9 | 2022-02-25 | 9 | 2022-03-29 | 22 | [18 empty] | 2022-02-11 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3611 | PGE | 93313 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 238.972 |  | 2022-02-10 | 2022-02-15 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3612 | PGE | 93313 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 313.762 |  | 2022-02-10 | 2022-02-15 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3613 | PGE | 93313 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 283.516 |  | 2022-02-10 | 2022-02-15 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3614 | PGE | 95010 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 428.362 |  | 2022-02-10 | 2022-02-11 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3615 | PGE | 94544 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 398.116 |  | 2022-02-10 | 2022-02-11 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3616 | PGE | 95519 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 15 |  | 2022-02-16 | 2022-03-01 | 8 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3617 | PGE | 93307 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 248.292 |  | 2022-02-10 | 2022-02-15 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3618 | PGE | 93313 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 313.762 |  | 2022-02-10 | 2022-02-15 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3619 | PGE | 95010 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 428.362 |  | 2022-02-10 | 2022-02-11 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3620 | PGE | 95010 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 428.362 |  | 2022-02-10 | 2022-02-10 | 0 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3621 | PGE | 93307 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 345.472 |  | 2022-02-10 | 2022-02-14 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3622 | PGE | 93307 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 292.321 |  | 2022-02-10 | 2022-02-15 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3623 | PGE | 95010 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 428.362 |  | 2022-02-10 | 2022-02-11 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3624 | PGE | 95010 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 428.362 |  | 2022-02-10 | 2022-02-11 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3625 | PGE | 94544 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 388.796 |  | 2022-02-10 | 2022-02-11 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3626 | PGE | 94903 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 622.212 |  | 2022-02-11 | 2022-02-14 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3627 | PGE | 93307 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 248.292 |  | 2022-02-10 | 2022-02-15 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3628 | PGE | 93313 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 366.28 |  | 2022-02-10 | 2022-02-15 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3629 | PGE | 93307 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 292.321 |  | 2022-02-10 | 2022-02-15 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3630 | PGE | 93313 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 194.718 |  | 2022-02-10 | 2022-02-15 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3631 | PGE | 95010 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 428.362 |  | 2022-02-10 | 2022-02-11 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3632 | PGE | 95010 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 428.362 |  | 2022-02-10 | 2022-02-11 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3633 | PGE | 95010 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 428.362 |  | 2022-02-10 | 2022-02-10 | 0 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3634 | PGE | 94903 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 398.116 |  | 2022-02-11 | 2022-02-14 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3635 | PGE | 95010 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 428.362 |  | 2022-02-10 | 2022-02-11 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3636 | PGE | 95010 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 428.362 |  | 2022-02-10 | 2022-02-11 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3637 | PGE | 94903 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 362.892 |  | 2022-02-11 | 2022-02-14 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3638 | PGE | 94903 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 595.48 |  | 2022-02-11 | 2022-02-14 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3639 | PGE | 94903 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 625.726 |  | 2022-02-11 | 2022-02-14 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3640 | PGE | 95139 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.423 |  | 2022-02-10 | 2022-03-01 | 12 | 2022-03-01 | 12 | 2022-03-03 | 2 | [18 empty] | 2022-02-10 | [7 empty] | 0 | [5 empty] | 2022-03-03 | 2022-03-03 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-03 |  |  | 2022-03-03 |  | 2022-03-03 | 0 | 1//19
3641 | PGE | 96021 | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2022-02-10 | 2022-02-25 | 10 | 2022-02-25 | 10 | 2022-03-18 | 15 | [15 empty] | 2022-03-18 | 2022-03-18 | 0 | 2022-03-18 | [6 empty] | 2022-02-10 | 2022-02-10 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3642 | PGE | 95650 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.916 |  | 2022-02-10 | 2022-03-01 | 12 | 2022-03-01 | 12 | 2022-03-02 | 1 | [18 empty] | 2022-02-10 | [7 empty] | 0 | [5 empty] | 2022-03-02 | 2022-03-02 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-02 |  |  | 2022-03-02 |  | 2022-03-02 | 0 | 1//19
3643 | PGE | 95409 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 5 |  | 2022-02-10 | 2022-02-24 | 9 | [22 empty] | 2022-02-10 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3644 | PGE | 95945 | Non-NEM | Inadvertent Export | Application Accepted | Storage | 420 |  | 2022-02-10 | 2022-02-10 | 0 | 2022-03-02 | 13 | [27 empty] | 2022-02-10 | 2022-02-10 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3645 | PGE | 95076 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2022-02-10 | 2022-03-02 | 13 | 2022-03-02 | 13 | 2022-03-02 | 0 | [18 empty] | 2022-02-10 | [7 empty] | 0 | [5 empty] | 2022-03-02 | 2022-03-02 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-02 |  |  | 2022-03-02 |  | 2022-03-02 | 0 | 1//19
3646 | PGE | 95449 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1625 |  | 2022-03-10 | 2022-03-16 | 4 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3647 | PGE | 93706 | NEM | EXPNEM | Implementation | Solar PV | 55.125 |  | 2022-02-15 | 2022-02-17 | 2 | 2022-02-17 | 2 | 2022-03-04 | 10 | [15 empty] | 2022-03-04 | 2022-03-04 | 0 | 2022-03-04 | 2022-03-05 | 0 |  |  |  |  | 2022-02-15 | 2022-02-15 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3648 | PGE | 95602 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 52.91 |  | 2022-02-26 | 2022-03-09 | 7 | [22 empty] | 2022-02-26 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3649 | PGE | 93725 | NEM | EXPNEM | Study in Progress | Solar PV | 89.88 |  | 2022-02-17 | 2022-03-04 | 10 | 2022-03-04 | 10 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3650 | PGE | 93401 | NEM | EXPNEM | IA in Progress | Solar PV | 235.259 |  | 2022-03-04 | 2022-03-04 | 0 | 2022-03-09 | 3 | 2022-03-22 | 9 | [15 empty] | 2022-03-22 | 2022-03-22 | 0 | 2022-03-22 | [6 empty] | 2022-03-04 | 2022-03-04 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3651 | PGE | 93304 | NEM | EXPNEM | Application Review in Progress | Solar PV | 495.417 |  | 2022-02-10 | 2022-02-24 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3652 | PGE | 94903 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 362.892 |  | 2022-02-11 | 2022-02-14 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3653 | PGE | 94903 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 398.116 |  | 2022-02-11 | 2022-02-14 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3654 | PGE | 94903 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 362.892 |  | 2022-02-11 | 2022-02-14 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3655 | PGE | 95746 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 248.292 |  | 2022-02-11 | 2022-02-28 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3656 | PGE | 95746 | NEM | VNEM | Application Review in Progress | Solar PV | 61.956 |  | 2022-02-11 | 2022-02-28 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3657 | PGE | 94903 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 445.656 |  | 2022-02-11 | 2022-02-14 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3658 | PGE | 94903 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 362.892 |  | 2022-02-11 | 2022-02-14 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3659 | PGE | 94903 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 460.072 |  | 2022-02-11 | 2022-02-14 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3660 | PGE | 94903 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 339.385 |  | 2022-02-11 | 2022-02-14 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3661 | PGE | 94903 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 220.585 |  | 2022-02-11 | 2022-02-14 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3662 | PGE | 95746 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 248.292 |  | 2022-02-11 | 2022-02-28 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3663 | PGE | 95746 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 213.704 |  | 2022-02-11 | 2022-02-28 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3664 | PGE | 92703 | NEM | VNEM | Withdrawn | Solar PV, Storage | 274.196 |  | 2022-02-11 | 0 | [31 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3665 | PGE | 94577 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 396.526 |  | 2022-02-11 | 2022-02-28 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3666 | PGE | 94577 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1903.572 |  | 2022-02-11 | 2022-02-17 | 4 | 2022-03-23 | 27 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3667 | PGE | 92703 | NEM | VNEM | Withdrawn | Solar PV, Storage | 248.292 |  | 2022-02-11 | 0 | [31 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3668 | PGE | 94521 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 248.292 |  | 2022-02-11 | 2022-02-28 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3669 | PGE | 94577 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 331.056 |  | 2022-02-11 | 2022-02-28 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3670 | PGE | 94577 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 331.056 |  | 2022-02-11 | 2022-02-28 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3671 | PGE | 92703 | NEM | VNEM | Withdrawn | Solar PV, Storage | 194.539 |  | 2022-02-11 | 0 | [31 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3672 | PGE | 94521 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 238.972 |  | 2022-02-11 | 2022-02-28 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3673 | PGE | 94521 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 261.88 |  | 2022-02-11 | 2022-02-28 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3674 | PGE | 94577 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 413.82 |  | 2022-02-11 | 2022-02-28 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3675 | PGE | 94577 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 331.056 |  | 2022-02-11 | 2022-02-28 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3676 | PGE | 94577 | NEM | VNEM | Application Review in Progress | Solar PV, Storage | 331.056 |  | 2022-02-11 | 2022-02-28 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3677 | PGE | 95762 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2022-02-12 | 2022-03-02 | 11 | 2022-03-02 | 11 | 2022-03-09 | 5 | [18 empty] | 2022-02-12 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-03-02 |  | 2022-03-09 | 6 | 1//19
3678 | PGE | 94558 | NEM | EXPNEM | Application Review in Progress | Solar PV | 79.742 |  | 2022-02-11 | 2022-02-28 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3679 | PGE | 95677 | NEM | EXPNEM | Application Review in Progress | Solar PV | 216 |  | 2022-03-08 | 2022-03-21 | 9 | [29 empty] | 2022-03-08 | 2022-03-08 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3680 | PGE | 94903 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 393.367 |  | 2022-02-18 | 2022-03-07 | 10 | 2022-03-11 | 14 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3681 | PGE | 93725 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 8088.4 |  | 2022-02-11 | 2022-02-18 | 5 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3682 | PGE | 95602 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2022-02-28 | 2022-03-11 | 9 | 2022-03-11 | 9 | 2022-03-31 | 14 | [18 empty] | 2022-02-28 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-03-11 |  | 2022-03-31 | 15 | 1//19
3683 | PGE | 93625 | NEM | EXPNEM | Implementation | Solar PV | 48.667 |  | 2022-02-11 | 2022-02-24 | 8 | 2022-02-24 | 8 | 2022-03-11 | 11 | [15 empty] | 2022-03-11 | 2022-03-11 | 0 | 2022-03-11 | 2022-03-11 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3684 | PGE | 94062 | NEM | EXPNEM | Study in Progress | Solar PV | 150 |  | 2022-03-23 | 2022-03-24 | 1 | 2022-03-28 | 3 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3685 | PGE | 94402 | NEM | VNEM | Study in Progress | Solar PV | 200 |  | 2022-02-16 | 2022-02-17 | 1 | 2022-02-25 | 6 | 2022-03-15 | 12 | 2022-03-15 | [25 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3686 | PGE | 93427 | NEM | EXPNEM | Application Accepted | Solar PV | 39.2 |  | 2022-02-14 | 2022-02-28 | 9 | 2022-02-28 | 9 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3687 | PGE | 95439 | NEM | EXPNEM | Implementation | Solar PV | 37.2 |  | 2022-02-14 | 2022-02-25 | 8 | 2022-03-09 | 16 | 2022-03-24 | 11 | [15 empty] | 2022-03-24 | 2022-03-24 | 0 | 2022-03-24 | 2022-03-28 | 2 | [5 empty] | 0 | [5 empty] | 2022-03-28 | [5 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-28 | 2022-03-28 | 0 |  |  |  |  | 1//19
3688 | PGE | 94538 | NEM | EXPNEM | Application Review in Progress | Solar PV | 187.356 |  | 2022-02-14 | 2022-02-15 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3689 | PGE | 95333 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2022-02-17 | 2022-02-28 | 6 | 2022-02-28 | 6 | 2022-03-17 | 13 | [18 empty] | 2022-02-17 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3690 | PGE | 95490 | NEM | EXPNEM | IA in Progress | Solar PV | 300 |  | 2022-02-14 | 2022-02-28 | 9 | 2022-03-10 | 17 | 2022-03-29 | 13 | [15 empty] | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29 | [6 empty] | 2022-03-29 | 2022-03-29 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3691 | PGE | 93706 | NEM | EXPNEM | Application Review in Progress | Solar PV | 875 |  | 2022-02-15 | 2022-03-02 | 10 | [29 empty] | 2022-02-15 | 2022-02-15 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3692 | PGE | 95476 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 46.175 |  | 2022-02-15 | 2022-03-02 | 10 | [22 empty] | 2022-02-15 | [6 empty] | 2022-02-15 | 2022-02-15 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3693 | PGE | 94954 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 38.152 |  | 2022-02-14 | 2022-02-15 | 1 | 2022-02-24 | 7 | 2022-03-15 | 13 | [15 empty] | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | [6 empty] | 2022-02-14 | 2022-02-14 | 1 |  | 2022-03-15 | 2022-03-15 | 0 | [6 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3694 | PGE | 95525 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 15 |  | 2022-02-15 | 2022-02-18 | 3 | 2022-02-18 | 3 | 2022-03-08 | 11 | [15 empty] | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 | 2022-03-08 | 0 | [5 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3695 | PGE | 94563 | Non-NEM | Non-Export | Study in Progress | Storage | 20 |  | 2022-02-15 | 2022-02-18 | 3 | 2022-02-18 | 3 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3696 | PGE | 95236 | NEM | EXPNEM | Application Review in Progress | Solar PV | 200 |  | 2022-02-15 | 2022-03-01 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3697 | PGE | 94019 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 58.963 |  | 2022-02-23 | 2022-02-25 | 2 | 2022-03-15 | 14 | [27 empty] | 2022-02-23 | 2022-02-23 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3698 | PGE | 94019 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 51.054 |  | 2022-02-23 | 2022-02-25 | 2 | 2022-03-08 | 9 | 2022-03-28 | 14 | [15 empty] | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28 | [6 empty] | 2022-02-23 | 2022-02-23 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3699 | PGE | 94019 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 42.091 |  | 2022-02-23 | 2022-02-25 | 2 | 2022-03-08 | 9 | 2022-03-28 | 14 | [15 empty] | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28 | [6 empty] | 2022-02-23 | 2022-02-23 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3700 | PGE | 95912 | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2022-02-15 | 2022-03-02 | 10 | 2022-03-10 | 16 | 2022-03-31 | 15 | [15 empty] | 2022-03-31 | 2022-03-31 | 0 | 2022-03-31 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3701 | PGE | 94061 | NEM | EXPNEM | Study in Progress | Solar PV | 97.087 |  | 2022-02-15 | 2022-03-02 | 10 | 2022-03-02 | 10 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3702 | PGE | 94061 | NEM | EXPNEM | Study in Progress | Solar PV | 121.358 |  | 2022-02-15 | 2022-03-02 | 10 | 2022-03-02 | 10 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3703 | PGE | 94061 | NEM | EXPNEM | Application Review in Progress | Solar PV | 139.158 |  | 2022-02-16 | 2022-03-02 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3704 | PGE | 94562 | NEM | EXPNEM | Application Review in Progress | Solar PV | 80.504 |  | 2022-02-15 | 2022-02-17 | 2 | [29 empty] | 2022-02-15 | 2022-02-15 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3705 | PGE | 93706 | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2022-02-15 | 2022-02-28 | 8 | 2022-03-07 | 13 | 2022-03-21 | 10 | [15 empty] | 2022-03-21 | 2022-03-21 | 0 | 2022-03-21 | 2022-03-30 | 7 |  |  |  |  | 2022-02-15 | 2022-02-15 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3706 | PGE | 94022 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 74.77 |  | 2022-03-10 | 2022-03-22 | 8 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3707 | PGE | 94061 | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2022-02-15 | 2022-03-01 | 9 | 2022-03-01 | 9 | 2022-03-21 | 14 | [15 empty] | 2022-03-21 | [10 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3708 | PGE | 94063 | NEM | EXPNEM | Study in Progress | Solar PV | 150 |  | 2022-02-15 | 2022-03-01 | 9 | 2022-03-01 | 9 | 2022-03-21 | 14 | 2022-03-21 | [25 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3709 | PGE | 93311 | NEM | EXPNEM | Application Review in Progress | Solar PV | 495.417 |  | 2022-02-16 | 2022-03-03 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3710 | PGE | 94062 | NEM | EXPNEM | Application Review in Progress | Solar PV | 375 |  | 2022-03-23 | 0 | [31 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3711 | PGE | 94061 | NEM | EXPNEM | Application Review in Progress | Solar PV | 75 |  | 2022-02-15 | 2022-02-28 | 8 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3712 | PGE | 94612 | NEM | VNEM | Application Review in Progress | Solar PV | 48.263 |  | 2022-03-09 | 2022-03-22 | 9 | [22 empty] | 2022-03-09 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3713 | PGE | 94577 | NEM | NEMMT | Application Accepted | OTHR, Solar PV | 490 |  | 2022-02-16 | 2022-02-18 | 2 | 2022-03-16 | 19 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3714 | PGE | 93711 | NEM | EXPNEM | Withdrawn | Solar PV | 700 |  | 2022-02-17 | 0 | [31 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3715 | PGE | 93313 | Non-NEM | Non-Export | Commercial | Storage | 929.5 |  | 2022-02-16 | 2022-02-18 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3716 | PGE | 94583 | NEM | EXPNEM | Application Review in Progress | Solar PV | 115.842 |  | 2022-02-16 | 2022-03-02 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3717 | PGE | 93654 | NEM | EXPNEM | Application Accepted | Solar PV | 125 |  | 2022-02-16 | 2022-03-01 | 8 | 2022-03-01 | 8 | 2022-03-23 | 16 | [25 empty] | 2022-02-16 | 2022-02-16 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3718 | PGE | 95369 | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2022-02-16 | 2022-03-01 | 8 | 2022-03-01 | 8 | 2022-03-15 | 10 | [15 empty] | 2022-03-15 | 2022-03-16 | 1 | 2022-03-16 | 2022-03-18 | 2 |  |  |  |  | 2022-02-16 | 2022-02-16 | 1 | 2022-03-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3719 | PGE | 94022 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 41.42 |  | 2022-02-16 | 2022-03-02 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3720 | PGE | 94063 | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 |  | 2022-03-23 | 2022-03-29 | 4 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3721 | PGE | 95650 | NEM | EXPNEM | IA in Progress | Solar PV | 64.167 |  | 2022-02-22 | 2022-02-23 | 1 | 2022-02-24 | 2 | 2022-03-11 | 11 | [15 empty] | 2022-03-11 | 2022-03-11 | 0 | 2022-03-11 | [6 empty] | 2022-02-22 | 2022-02-22 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3722 | PGE | 94559 | NEM | EXPNEM | Application Review in Progress | Solar PV | 165.528 |  | 2022-02-17 | 2022-02-17 | 0 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3723 | PGE | 95333 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 10 |  | 2022-03-18 | 2022-03-31 | 9 | [22 empty] | 2022-03-18 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3724 | PGE | 93725 | NEM | EXPNEM | Study in Progress | Solar PV | 300 |  | 2022-02-17 | 2022-03-04 | 10 | 2022-03-04 | 10 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3725 | PGE | 95650 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.668 |  | 2022-02-17 | 2022-03-02 | 8 | [22 empty] | 2022-02-17 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3726 | PGE | 93725 | NEM | EXPNEM | IA in Progress | Solar PV | 47.818 |  | 2022-02-17 | 2022-03-04 | 10 | 2022-03-04 | 10 | 2022-03-15 | 7 | [15 empty] | 2022-03-15 | [10 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3727 | PGE | 95726 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2022-03-14 | 2022-03-28 | 10 | 2022-03-28 | 10 | [20 empty] | 2022-03-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3728 | PGE | 93725 | NEM | EXPNEM | Study in Progress | Solar PV | 120 |  | 2022-02-17 | 2022-03-04 | 10 | 2022-03-10 | 14 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3729 | PGE | 93725 | NEM | EXPNEM | IA in Progress | Solar PV | 156.603 |  | 2022-02-17 | 2022-03-04 | 10 | 2022-03-17 | 19 | 2022-03-29 | 8 | [15 empty] | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3730 | PGE | 94605 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.544 |  | 2022-02-17 | 2022-03-02 | 8 | 2022-03-21 | 21 | 2022-03-24 | 3 | [18 empty] | 2022-02-17 | [7 empty] | 0 | [5 empty] | 2022-03-24 | 2022-03-24 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-24 |  |  | 2022-03-24 |  | 2022-03-24 | 0 | 1//19
3732 | PGE | 95421 | Non-NEM | Non-Export | Application Review in Progress | Storage | 10 |  | 2022-02-17 | 2022-03-04 | 10 | [22 empty] | 2022-02-17 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3733 | PGE | 95369 | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 |  | 2022-02-17 | 2022-03-04 | 10 | [29 empty] | 2022-02-17 | 2022-02-17 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3734 | PGE | 95138 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.163 |  | 2022-02-18 | 2022-03-02 | 7 | 2022-03-02 | 7 | 2022-03-04 | 2 | [18 empty] | 2022-02-18 | [7 empty] | 0 | [5 empty] | 2022-03-04 | 2022-03-16 | 8 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-04 | 2022-03-07 | 1 | 2022-03-16 |  | 2022-03-21 | 3 | 1//19
3735 | PGE | 93720 | NEM | EXPNEM | Application Review in Progress | Solar PV | 45.281 |  | 2022-03-20 | 0 | [31 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3736 | PGE | 95033 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2022-02-18 | 2022-02-18 | 0 | 2022-02-18 | 0 | 2022-03-11 | 14 | [18 empty] | 2022-02-18 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-02-18 |  | 2022-03-11 | 16 | 1//19
3737 | PGE | 95133 | NEM | EXPNEM | IA in Progress | Solar PV | 724.536 |  | 2022-02-18 | 2022-03-02 | 7 | 2022-03-02 | 7 | 2022-03-23 | 15 | [15 empty] | 2022-03-23 | 2022-03-23 | 0 | 2022-03-23 | [6 empty] | 2022-03-10 | 2022-03-10 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3738 | PGE | 95348 | NEM | EXPNEM | Application Review in Progress | Solar PV | 72.79 |  | 2022-03-16 | 2022-03-30 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3739 | PGE | 95369 | NEM | EXPNEM | Application Review in Progress | Solar PV | 250 |  | 2022-02-22 | 2022-03-08 | 10 | [29 empty] | 2022-02-22 | 2022-02-22 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3740 | PGE | 93723 | NEM | EXPNEM | Study in Progress | Solar PV | 38.753 |  | 2022-02-28 | 2022-03-10 | 8 | 2022-03-10 | 8 | [27 empty] | 2022-02-28 | 2022-02-28 | 1 | 2022-03-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3741 | PGE | 94534 | NEM | EXPNEM | Application Review in Progress | Solar PV | 309.991 |  | 2022-02-22 | 2022-03-05 | 8 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3742 | PGE | 95448 | NEM | EXPNEM | Application Accepted | Solar PV | 41.88 |  | 2022-02-18 | 2022-03-04 | 9 | 2022-03-28 | 25 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3743 | PGE | 90011 | NEM | EXPNEM | Application Review in Progress | Solar PV | 1000 |  | 2022-02-19 | 0 | [31 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3744 | PGE | 96104 | Non-NEM | Export | Withdrawn | Solar PV | 0.182 |  | 2022-02-19 | 0 | [31 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3745 | PGE | 95476 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 42.725 |  | 2022-02-22 | 2022-03-04 | 8 | 2022-02-22 | 0 | [20 empty] | 2022-02-22 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3746 | PGE | 95070 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.15 |  | 2022-02-23 | 2022-03-05 | 7 | 2022-03-05 | 7 | 2022-03-10 | 3 | [18 empty] | 2022-02-23 | [7 empty] | 0 | [5 empty] | 2022-03-10 | 2022-03-10 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-10 |  |  | 2022-03-10 |  | 2022-03-10 | 0 | 1//19
3747 | PGE | 93618 | NEM | EXPNEM | Study in Progress | Solar PV | 96 |  | 2022-02-24 | 2022-03-08 | 8 | 2022-03-14 | 12 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3748 | PGE | 95112 | NEM | VNEM | Application Review in Progress | Solar PV | 32.382 |  | 2022-03-08 | 2022-03-09 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3749 | PGE | 95917 | NEM | EXPNEM | Application Review in Progress | Solar PV | 36 |  | 2022-02-22 | 2022-03-08 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3750 | PGE | 93721 | NEM | EXPNEM | Study in Progress | Solar PV | 133.2 |  | 2022-03-17 | 2022-03-28 | 7 | 2022-03-31 | 10 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3751 | PGE | 93401 | Non-NEM | Continuous Uncompensated Export | Application Accepted | ENGN, Solar PV | 363.2 |  | 2022-03-04 | 2022-03-08 | 2 | 2022-03-30 | 18 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3752 | PGE | 93618 | NEM | EXPNEM | IA in Progress | Solar PV | 90.323 |  | 2022-02-24 | 2022-03-08 | 8 | 2022-03-08 | 8 | 2022-03-22 | 10 | [15 empty] | 2022-03-22 | 2022-03-22 | 0 | 2022-03-22 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3753 | PGE | 95320 | NEM | EXPNEM | Application Review in Progress | Solar PV | 250 |  | 2022-02-22 | 2022-03-08 | 10 | [29 empty] | 2022-02-22 | 2022-02-22 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3754 | PGE | 93618 | NEM | EXPNEM | IA in Progress | Solar PV | 170 |  | 2022-02-24 | 2022-03-08 | 8 | 2022-03-08 | 8 | 2022-03-23 | 11 | [15 empty] | 2022-03-23 | [10 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3755 | PGE | 93618 | NEM | EXPNEM | Study in Progress | Solar PV | 420 |  | 2022-02-24 | 2022-03-08 | 8 | 2022-03-14 | 12 | 2022-03-25 | 9 | 2022-03-25 | [25 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3756 | PGE | 94563 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2022-03-14 | 2022-03-25 | 9 | 2022-03-25 | 9 | [20 empty] | 2022-03-14 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3757 | PGE | 93618 | NEM | EXPNEM | IA in Progress | Solar PV | 72 |  | 2022-02-24 | 2022-03-08 | 8 | 2022-03-08 | 8 | 2022-03-24 | 12 | [15 empty] | 2022-03-24 | 2022-03-24 | 0 | 2022-03-24 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3758 | PGE | 93618 | NEM | EXPNEM | Study in Progress | Solar PV | 480 |  | 2022-02-24 | 2022-03-08 | 8 | 2022-03-14 | 12 | [27 empty] | 2022-03-25 | 2022-03-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3759 | PGE | 93618 | NEM | EXPNEM | Study in Progress | Solar PV | 120 |  | 2022-02-24 | 2022-03-08 | 8 | 2022-03-14 | 12 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3760 | PGE | 93618 | NEM | EXPNEM | Study in Progress | Solar PV | 540 |  | 2022-02-24 | 2022-03-08 | 8 | 2022-03-14 | 12 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3761 | PGE | 95222 | NEM | EXPNEM | Application Review in Progress | Solar PV | 47.115 |  | 2022-03-05 | 2022-03-18 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3762 | PGE | 94024 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 41.38 |  | 2022-02-23 | 2022-03-07 | 8 | [22 empty] | 2022-03-09 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3763 | PGE | 94019 | NEM | VNEM | Application Review in Progress | Solar PV | 200 |  | 2022-02-24 | 2022-02-25 | 1 | [30 empty] | 2022-03-08 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3764 | PGE | 95901 | NEM | EXPNEM | Study in Progress | Solar PV | 240 |  | 2022-02-24 | 2022-02-24 | 0 | 2022-03-08 | 8 | 2022-03-23 | 11 | 2022-03-23 | [24 empty] | 2022-02-24 | 2022-02-24 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3765 | PGE | 94550 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 10 |  | 2022-03-13 | 2022-03-18 | 4 | [22 empty] | 2022-03-13 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3766 | PGE | 94599 | NEM | EXPNEM | Study in Progress | Solar PV | 556 |  | 2022-02-23 | 2022-03-09 | 10 | 2022-03-09 | 10 | [5 empty] | 2022-03-09 | [21 empty] | 2022-02-23 | 2022-02-23 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3767 | PGE | 95073 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 36.423 |  | 2022-02-23 | 2022-03-07 | 8 | 2022-03-07 | 8 | 2022-03-07 | 0 | [18 empty] | 2022-02-23 | [7 empty] | 0 | [5 empty] | 2022-03-07 | 2022-03-07 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-07 |  |  | 2022-03-07 |  | 2022-03-07 | 0 | 1//19
3768 | PGE | 93308 | NEM | NEMMT | Study in Progress | Solar PV, Turbine | 20000 |  | 2022-02-23 | 2022-03-03 | 6 | 2022-03-23 | 20 | [20 empty] | 2022-02-23 | [6 empty] | 2022-02-23 | 2022-02-23 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3769 | PGE | 94010 | Non-NEM | Inadvertent Export | Application Accepted | Storage | 35 |  | 2022-02-23 | 2022-03-01 | 4 | 2022-03-23 | 20 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3770 | PGE | 93307 | Non-NEM | Inadvertent Export | Commercial | Storage | 5 |  | 2022-02-26 | 2022-03-01 | 1 | 2022-03-14 | 10 | 2022-03-22 | 6 | [18 empty] | 2022-02-26 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-02-26 |  | 2022-03-22 | 17 | 1//19
3771 | PGE | 95688 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.72 |  | 2022-02-23 | 2022-03-04 | 7 | 2022-03-04 | 7 | 2022-03-23 | 13 | [15 empty] | 2022-03-23 | [10 empty] | 0 |  | 2022-03-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3772 | PGE | 95603 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 40.373 |  | 2022-02-23 | 2022-03-07 | 8 | 2022-03-07 | 8 | 2022-03-08 | 1 | [18 empty] | 2022-02-23 | [7 empty] | 0 | [5 empty] | 2022-03-08 | 2022-03-08 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-08 |  |  | 2022-03-08 |  | 2022-03-08 | 0 | 1//19
3773 | PGE | 94952 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 40.086 |  | 2022-02-24 | 2022-02-25 | 1 | 2022-03-08 | 8 | 2022-03-28 | 14 | [15 empty] | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28 | [6 empty] | 2022-02-24 | 2022-02-24 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3774 | PGE | 95018 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 10 |  | 2022-02-23 | 2022-03-09 | 10 | [22 empty] | 2022-02-23 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3775 | PGE | 93662 | NEM | EXPNEM | Application Accepted | Solar PV | 83.3 |  | 2022-02-23 | 2022-03-08 | 9 | 2022-03-08 | 9 | [27 empty] | 2022-02-23 | 2022-02-23 | 1 | 2022-03-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3776 | PGE | 95376 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1700 |  | 2022-03-03 | 2022-03-09 | 4 | 2022-03-30 | 19 | [27 empty] | 2022-03-03 | 2022-03-03 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3777 | PGE | 94024 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.056 |  | 2022-02-23 | 2022-03-07 | 8 | 2022-03-16 | 15 | 2022-03-18 | 2 | [18 empty] | 2022-02-23 | [6 empty] | 2022-02-23 | 2022-02-23 | 1 |  |  |  |  | 2022-03-29 | 2022-03-29 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-29 |  |  | 2022-03-29 |  | 2022-03-29 | 0 | 1//19
3778 | PGE | 95112 | NEM | VNEM | Application Review in Progress | Solar PV | 80.504 |  | 2022-03-08 | 2022-03-09 | 1 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3779 | PGE | 94931 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 51.074 |  | 2022-02-23 | 2022-02-24 | 1 | 2022-03-10 | 11 | 2022-03-31 | 15 | [15 empty] | 2022-03-31 | 2022-03-31 | 0 | 2022-03-31 | [6 empty] | 2022-02-23 | 2022-02-23 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3780 | PGE | 93263 | NEM | EXPNEM | Study in Progress | Solar PV | 50.864 |  | 2022-02-23 | 2022-03-09 | 10 | 2022-03-29 | 24 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3781 | PGE | 93242 | NEM | EXPNEM | IA in Progress | Solar PV | 83.3 |  | 2022-02-23 | 2022-03-09 | 10 | 2022-03-09 | 10 | 2022-03-30 | 15 | [15 empty] | 2022-03-30 | [9 empty] | 2022-02-23 | 2022-02-23 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3782 | PGE | 94070 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1980 |  | 2022-02-23 | 2022-03-03 | 6 | 2022-03-30 | 25 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3783 | PGE | 93204 | NEM | EXPNEM | Application Accepted | Solar PV | 150 |  | 2022-03-07 | 2022-03-18 | 9 | 2022-03-18 | 9 | [27 empty] | 2022-03-23 | 2022-03-23 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3784 | PGE | 95110 | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.983 |  | 2022-02-23 | 2022-03-09 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3785 | PGE | 94621 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 206.6 |  | 2022-02-24 | 2022-03-10 | 10 | 2022-03-10 | 10 | 2022-03-31 | 15 | [15 empty] | 2022-03-31 | 2022-03-31 | 0 | 2022-03-31 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3786 | PGE | 95667 | NEM | EXPNEM | IA in Progress | Solar PV | 125 |  | 2022-02-24 | 2022-03-08 | 8 | 2022-03-16 | 14 | 2022-03-30 | 10 | [15 empty] | 2022-03-30 | 2022-03-30 | 0 | 2022-03-30 | [6 empty] | 2022-02-24 | 2022-02-24 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3787 | PGE | 94074 | NEM | EXPNEM | Application Review in Progress | Solar PV | 44.43 |  | 2022-02-25 | 2022-03-09 | 8 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3788 | PGE | 94574 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 34.963 |  | 2022-02-24 | 2022-03-08 | 8 | 2022-03-31 | 25 | [20 empty] | 2022-02-24 | [6 empty] | 2022-02-24 | 2022-02-24 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3789 | PGE | 95618 | NEM | EXPNEM | Application Review in Progress | Solar PV | 1086.804 |  | 2022-02-24 | 2022-03-03 | 5 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3790 | PGE | 95136 | NEM | EXPNEM | Application Review in Progress | Solar PV | 83.3 |  | 2022-02-24 | 2022-03-10 | 10 | [29 empty] | 2022-02-24 | 2022-02-24 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3791 | PGE | 95030 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 42.234 |  | 2022-03-08 | 2022-03-08 | 0 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3792 | PGE | 93637 | NEM | EXPNEM | IA in Progress | Solar PV | 34.8 |  | 2022-02-28 | 2022-03-11 | 9 | 2022-03-21 | 15 | 2022-03-30 | 7 | [15 empty] | 2022-03-30 | 2022-03-30 | 0 | 2022-03-30 | [6 empty] | 2022-02-28 | 2022-02-28 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3793 | PGE | 94533 | Non-NEM | Non-Export | Withdrawn | Solar PV | 350 |  | 2022-02-28 | 2022-02-28 | 0 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3794 | PGE | 95405 | Non-NEM | Non-Export | Application Accepted | Micro Turbine | 130 |  | 2022-03-03 | 2022-03-09 | 4 | 2022-03-23 | 14 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3795 | PGE | 95037 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.685 |  | 2022-03-22 | 0 | [23 empty] | 2022-03-22 | [6 empty] | 2022-03-22 | 2022-03-22 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3796 | PGE | 95519 | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.2 |  | 2022-03-02 | 2022-03-14 | 8 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3797 | PGE | 93263 | NEM | EXPNEM | Study in Progress | Solar PV | 362.5 |  | 2022-02-25 | 2022-03-01 | 2 | 2022-03-30 | 23 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3798 | PGE | 94612 | Non-NEM | Non-Export | Application Accepted | Solar PV | 37.196 |  | 2022-02-25 | 2022-02-25 | 0 | 2022-03-02 | 3 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3799 | PGE | 94565 | NEM | EXPNEM | Application Review in Progress | Solar PV | 500 |  | 2022-03-09 | 2022-03-22 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3800 | PGE | 95030 | NEM | EXPNEM | Application Review in Progress | Solar PV | 965.7 |  | 2022-03-28 | 0 | [31 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3801 | PGE | 94025 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.375 |  | 2022-02-25 | 2022-03-09 | 8 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3802 | PGE | 95070 | NEM | EXPNEM | Application Review in Progress | Solar PV | 403.815 |  | 2022-02-25 | 2022-03-01 | 2 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3803 | PGE | 94044 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2022-03-07 | 2022-03-08 | 1 | 2022-03-08 | 1 | 2022-03-09 | 1 | [18 empty] | 2022-03-07 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-03-08 |  | 2022-03-21 | 10 | 1//19
3804 | PGE | 95963 | NEM | EXPNEM | Application Accepted | Solar PV | 186.03 |  | 2022-02-25 | 2022-03-09 | 8 | 2022-03-09 | 8 | [27 empty] | 2022-02-25 | 2022-02-25 | 1 | 2022-03-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3805 | PGE | 95340 | NEM | EXPNEM | Study in Progress | Solar PV | 45.572 |  | 2022-02-25 | 2022-03-11 | 10 | 2022-03-17 | 14 | [27 empty] | 2022-02-25 | 2022-02-25 | 1 | [10 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3806 | PGE | 94010 | Non-NEM | Non-Export | Study in Progress | Storage | 5 |  | 2022-02-27 | 2022-03-10 | 8 | 2022-03-10 | 8 | [20 empty] | 2022-02-27 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3807 | PGE | 94089 | NEM | EXPNEM | Application Review in Progress | Solar PV | 235.573 |  | 2022-02-27 | 2022-03-04 | 4 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3808 | PGE | 94089 | NEM | EXPNEM | Application Review in Progress | Solar PV | 287.466 |  | 2022-02-27 | 2022-03-11 | 9 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3809 | PGE | 94525 | NEM | EXPNEM | Application Review in Progress | Solar PV | 1500 |  | 2022-03-09 | 2022-03-14 | 3 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3810 | PGE | 95377 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 950 |  | 2022-03-08 | 2022-03-22 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3811 | PGE | 94949 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 45.15 |  | 2022-02-28 | 2022-03-09 | 7 | 2022-03-09 | 7 | 2022-03-12 | 2 | [18 empty] | 2022-02-28 | [6 empty] | 2022-02-28 | 2022-02-28 | 1 |  |  |  |  | 2022-03-29 | 2022-03-29 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-29 |  |  | 2022-03-29 |  | 2022-03-29 | 0 | 1//19
3812 | PGE | 95070 | NEM | EXPNEM | Application Review in Progress | Solar PV, Solar Thermal | 849.279 |  | 2022-02-28 | 2022-02-28 | 0 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3813 | PGE | 94544 | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2022-02-28 | 2022-03-09 | 7 | 2022-03-09 | 7 | 2022-03-25 | 12 | [15 empty] | 2022-03-25 | 2022-03-25 | 0 | 2022-03-25 | [7 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3814 | PGE | 93230 | NEM | EXPNEM | Application Accepted | Solar PV | 300 |  | 2022-02-28 | 2022-03-09 | 7 | 2022-03-16 | 12 | [28 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3815 | PGE | 95030 | NEM | EXPNEM | Application Review in Progress | Solar PV | 99.9 |  | 2022-02-28 | 2022-02-28 | 0 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3816 | PGE | 93245 | NEM | EXPNEM | Application Review in Progress | Solar PV | 240 |  | 2022-03-07 | 2022-03-21 | 10 | [30 empty] | 0 | [11 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3817 | PGE | 95033 | NEM | EXPNEM | Study in Progress | Solar PV | 86.64 |  | 2022-02-28 | 2022-03-10 | 8 | 2022-03-10 | 8 | 2022-03-28 | 12 | 2022-03-28 | [25 empty] | 0 |  | 2022-03-15 | [9 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3818 | PGE | 93610 | NEM | EXPNEM | Application Review in Progress | Solar PV | 62.5 |  | 2022-02-28 | 2022-03-14 | 10 | [29 empty] | 2022-02-28 | 2022-02-28 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3819 | PGE | 93610 | NEM | EXPNEM | Study in Progress | Solar PV | 50 |  | 2022-02-28 | 2022-03-14 | 10 | 2022-03-16 | 12 | [27 empty] | 2022-02-28 | 2022-02-28 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3820 | PGE | 93637 | NEM | EXPNEM | Study in Progress | Solar PV | 62.5 |  | 2022-02-28 | 2022-03-14 | 10 | 2022-03-16 | 12 | [27 empty] | 2022-02-28 | 2022-02-28 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3821 | PGE | 95963 | NEM | EXPNEM | Application Accepted | Solar PV | 130.206 |  | 2022-02-28 | 2022-03-11 | 9 | 2022-03-31 | 23 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3822 | PGE | 95963 | NEM | EXPNEM | Application Review in Progress | Solar PV | 133.272 |  | 2022-02-28 | 2022-03-14 | 10 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3823 | PGE | 95953 | NEM | EXPNEM | Study in Progress | Solar PV | 118.906 |  | 2022-02-28 | 2022-03-09 | 7 | 2022-03-18 | 14 | [27 empty] | 2022-02-28 | 2022-02-28 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3824 | PGE | 95991 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.163 |  | 2022-03-15 | 2022-03-28 | 9 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3825 | PGE | 95618 | NEM | EXPNEM | IA in Progress | Solar PV | 362.268 |  | 2022-02-28 | 2022-03-14 | 10 | 2022-03-14 | 10 | 2022-03-30 | 12 | [15 empty] | 2022-03-30 | [10 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3826 | PGE | 94599 | NEM | EXPNEM | IA in Progress | Solar PV | 145.127 |  | 2022-02-28 | 2022-03-02 | 2 | 2022-03-02 | 2 | 2022-03-17 | 11 | [15 empty] | 2022-03-17 | 2022-03-17 | 0 | 2022-03-17 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3827 | PGE | 94577 | NEM | EXPNEM | Implementation | Solar PV | 69.6 |  | 2022-03-01 | 2022-03-02 | 1 | 2022-03-02 | 1 | 2022-03-14 | 8 | [15 empty] | 2022-03-14 | 2022-03-14 | 0 | 2022-03-14 | 2022-03-17 | 3 | [5 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3828 | PGE | 95376 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 582.357 |  | 2022-03-07 | 2022-03-18 | 9 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3829 | PGE | 94708 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2022-03-02 | 2022-03-03 | 1 | 2022-03-03 | 1 | 2022-03-04 | 1 | [18 empty] | 2022-03-02 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-03-03 |  | 2022-03-14 | 8 | 1//19
3830 | PGE | 95076 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 83.128 |  | 2022-03-01 | 2022-03-04 | 3 | 2022-03-10 | 7 | 2022-03-28 | 12 | [15 empty] | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28 | [6 empty] | 2022-03-01 | 2022-03-01 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3831 | PGE | 95076 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 50 |  | 2022-03-01 | 2022-03-04 | 3 | 2022-03-10 | 7 | 2022-03-28 | 12 | [15 empty] | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28 | [6 empty] | 2022-03-01 | 2022-03-01 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3832 | PGE | 94506 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 31.375 |  | 2022-03-01 | 2022-03-10 | 7 | 2022-03-01 | 0 | [20 empty] | 2022-03-01 | [6 empty] | 2022-03-01 | 2022-03-01 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3833 | PGE | 93631 | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.369 |  | 2022-03-04 | 2022-03-16 | 8 | [29 empty] | 2022-03-04 | 2022-03-04 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3834 | PGE | 94028 | NEM | EXPNEM | Application Review in Progress | Solar PV | 45.384 |  | 2022-03-02 | 2022-03-15 | 9 | [29 empty] | 2022-03-02 | 2022-03-02 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3835 | PGE | 95482 | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2022-03-02 | 2022-03-03 | 1 | 2022-03-08 | 4 | 2022-03-23 | 11 | [15 empty] | 2022-03-23 | 2022-03-23 | 0 | 2022-03-23 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3836 | PGE | 94109 | NEM | EXPNEM | Study in Progress | Solar PV | 44.412 |  | 2022-03-02 | 2022-03-16 | 10 | 2022-03-16 | 10 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3837 | PGE | 95425 | Non-NEM | Non-Export | Application Accepted | Micro Turbine | 65 |  | 2022-03-03 | 2022-03-09 | 4 | 2022-03-23 | 14 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3838 | PGE | 95490 | Non-NEM | Non-Export | Application Accepted | Micro Turbine | 65 |  | 2022-03-03 | 2022-03-09 | 4 | 2022-03-23 | 14 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3839 | PGE | 93637 | NEM | EXPNEM | Study in Progress | Solar PV | 156 |  | 2022-03-02 | 2022-03-15 | 9 | 2022-03-27 | 17 | [27 empty] | 2022-03-02 | 2022-03-02 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3840 | PGE | 93725 | NEM | EXPNEM | Study in Progress | Solar PV | 77.133 |  | 2022-03-02 | 2022-03-14 | 8 | 2022-03-31 | 21 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3841 | PGE | 95207 | NEM | VNEM | IA in Progress | Solar PV | 300 |  | 2022-03-02 | 2022-03-03 | 1 | 2022-03-11 | 7 | 2022-03-29 | 12 | [15 empty] | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3842 | PGE | 93638 | NEM | EXPNEM | Study in Progress | Solar PV | 156 |  | 2022-03-02 | 2022-03-15 | 9 | 2022-03-28 | 18 | [27 empty] | 2022-03-02 | 2022-03-02 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3843 | PGE | 93230 | NEM | EXPNEM | Application Review in Progress | Solar PV | 300 |  | 2022-03-18 | 2022-03-30 | 8 | [29 empty] | 2022-03-18 | 2022-03-18 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3844 | PGE | 93638 | NEM | EXPNEM | IA in Progress | Solar PV | 132 |  | 2022-03-02 | 2022-03-11 | 7 | 2022-03-11 | 7 | 2022-03-25 | 10 | [15 empty] | 2022-03-25 | 2022-03-25 | 0 | 2022-03-25 | [6 empty] | 2022-03-02 | 2022-03-02 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3845 | PGE | 94595 | NEM | VNEM | Application Review in Progress | Solar PV | 32.78 |  | 2022-03-02 | 2022-03-03 | 1 | [22 empty] | 2022-03-02 | [6 empty] | 2022-03-02 | 2022-03-02 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3846 | PGE | 93637 | NEM | EXPNEM | Study in Progress | Solar PV | 60 |  | 2022-03-02 | 2022-03-16 | 10 | 2022-03-29 | 19 | [27 empty] | 2022-03-02 | 2022-03-02 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3847 | PGE | 94611 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 45.598 |  | 2022-03-02 | 2022-03-14 | 8 | [22 empty] | 2022-03-02 | [6 empty] | 2022-03-02 | 2022-03-02 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3848 | PGE | 93637 | NEM | EXPNEM | Application Review in Progress | Solar PV | 36 |  | 2022-03-02 | 2022-03-16 | 10 | [29 empty] | 2022-03-02 | 2022-03-02 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3849 | PGE | 95112 | NEM | EXPNEM | Study in Progress | Solar PV | 72.22 |  | 2022-03-03 | 2022-03-09 | 4 | 2022-03-28 | 17 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3850 | PGE | 94588 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2022-03-09 | 2022-03-16 | 5 | 2022-03-16 | 5 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3851 | PGE | 93455 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.163 |  | 2022-03-22 | 0 | [23 empty] | 2022-03-22 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3852 | PGE | 94923 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2022-03-03 | 2022-03-07 | 2 | 2022-03-07 | 2 | [20 empty] | 2022-03-03 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3853 | PGE | 93454 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2022-03-04 | 2022-03-11 | 5 | 2022-03-11 | 5 | 2022-03-14 | 1 | [18 empty] | 2022-03-04 | 2022-03-03 | 1 | [5 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3854 | PGE | 95620 | NEM | VNEMMASH | Application Review in Progress | Solar PV | 50 |  | 2022-03-04 | 2022-03-18 | 10 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3855 | PGE | 91789 | NEM | EXPNEM | Study in Progress | Solar PV | 66.6 |  | 2022-03-03 | 2022-03-09 | 4 | 2022-03-28 | 17 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3856 | PGE | 94801 | NEM | EXPNEM | Application Review in Progress | Solar PV | 34.22 |  | 2022-03-04 | 2022-03-17 | 9 | [29 empty] | 2022-03-04 | 2022-03-04 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3857 | PGE | 95131 | NEM | EXPNEM | Study in Progress | Solar PV | 60.318 |  | 2022-03-04 | 2022-03-18 | 10 | 2022-03-18 | 10 | [27 empty] | 2022-03-04 | 2022-03-04 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3858 | PGE | 94510 | NEM | NEMMT | Application Review in Progress | ENGN, FUCE | 5000 |  | 2022-03-23 | 0 | [30 empty] | 2022-03-23 | 2022-03-23 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3859 | PGE | 94523 | NEM | EXPNEM | Application Review in Progress | Solar PV | 144.11 |  | 2022-03-03 | 2022-03-17 | 10 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3860 | PGE | 95503 | NEM | VNEMMASH | Application Review in Progress | Solar PV | 100 |  | 2022-03-29 | 2022-03-30 | 1 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3861 | PGE | 94014 | NEM | EXPNEM | IA in Progress | Solar PV | 121.471 |  | 2022-03-03 | 2022-03-07 | 2 | 2022-03-17 | 10 | 2022-03-31 | 10 | [15 empty] | 2022-03-31 | 2022-03-31 | 0 | 2022-03-31 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3862 | PGE | 94014 | NEM | EXPNEM | IA in Progress | Solar PV | 118.076 |  | 2022-03-03 | 2022-03-07 | 2 | 2022-03-17 | 10 | 2022-03-31 | 10 | [15 empty] | 2022-03-31 | [10 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3863 | PGE | 95667 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 15 |  | 2022-03-04 | 2022-03-07 | 1 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3864 | PGE | 95633 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 15 |  | 2022-03-04 | 2022-03-07 | 1 | 2022-03-31 | 19 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3865 | PGE | 95334 | NEM | NEM Paired Storage | Application Review in Progress | ENGN, Solar PV, Storage | 10276.88 |  | 2022-03-07 | 2022-03-11 | 4 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3866 | PGE | 93727 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 9766.88 |  | 2022-03-04 | 2022-03-11 | 5 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3867 | PGE | 94513 | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 |  | 2022-03-15 | 2022-03-29 | 10 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3868 | PGE | 93401 | Non-NEM | Continuous Uncompensated Export | Application Accepted | Solar PV | 228.65 |  | 2022-03-04 | 2022-03-08 | 2 | 2022-03-30 | 18 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3869 | PGE | 95407 | NEM | EXPNEM | Application Accepted | Solar PV | 1920 |  | 2022-03-04 | 2022-03-11 | 5 | 2022-03-23 | 13 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3870 | PGE | 94583 | NEM | EXPNEM | Study in Progress | Solar PV | 46.405 |  | 2022-03-15 | 2022-03-28 | 9 | 2022-03-28 | 9 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3871 | PGE | 95415 | NEM | EXPNEM | Study in Progress | Solar PV | 31.024 |  | 2022-03-04 | 2022-03-18 | 10 | 2022-03-18 | 10 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3872 | PGE | 95215 | NEM | EXPNEM | Study in Progress | Solar PV | 240 |  | 2022-03-04 | 2022-03-16 | 8 | 2022-03-25 | 15 | [27 empty] | 2022-03-04 | 2022-03-04 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3873 | PGE | 94028 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.356 |  | 2022-03-05 | 2022-03-15 | 6 | [22 empty] | 2022-03-24 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3874 | PGE | 95370 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.398 |  | 2022-03-05 | 2022-03-15 | 6 | 2022-03-05 | 0 | 2022-03-17 | 8 | [18 empty] | 2022-03-05 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 2022-03-17 | 2022-03-17 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-17 |  |  | 2022-03-17 |  | 2022-03-17 | 0 | 1//19
3875 | PGE | 95039 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1100 |  | 2022-03-18 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3876 | PGE | 94005 | NEM | EXPNEM | Application Review in Progress | Solar PV | 937.5 |  | 2022-03-07 | 2022-03-14 | 5 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3877 | PGE | 95682 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.163 |  | 2022-03-07 | 2022-03-17 | 8 | [22 empty] | 2022-03-07 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3878 | PGE | 94525 | NEM | EXPNEM | Application Review in Progress | Solar PV | 97.259 |  | 2022-03-07 | 2022-03-21 | 10 | [29 empty] | 2022-03-07 | 2022-03-07 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3879 | PGE | 95377 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 400 |  | 2022-03-07 | 2022-03-18 | 9 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3880 | PGE | 93631 | NEM | EXPNEM | Study in Progress | Solar PV | 50 |  | 2022-03-08 | 2022-03-21 | 9 | 2022-03-21 | 9 | [27 empty] | 2022-03-08 | 2022-03-08 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3881 | PGE | 93249 | NEM | EXPNEM | Application Review in Progress | Solar PV | 2875 |  | 2022-03-07 | 2022-03-14 | 5 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3882 | PGE | 95460 | NEM | EXPNEM | Application Review in Progress | Solar PV | 183.3 |  | 2022-03-22 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3883 | PGE | 94549 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2022-03-09 | 2022-03-15 | 4 | 2022-03-15 | 4 | 2022-03-29 | 10 | [18 empty] | 2022-03-09 | 2022-03-08 | 1 | [5 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 2022-03-15 |  | 2022-03-30 | 12 | 1//19
3884 | PGE | 94583 | NEM | EXPNEM | Study in Progress | Solar PV | 42.068 |  | 2022-03-15 | 2022-03-28 | 9 | 2022-03-28 | 9 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3885 | PGE | 93906 | NEM | EXPNEM | Study in Progress | Solar PV | 168.537 |  | 2022-03-14 | 2022-03-25 | 9 | 2022-03-25 | 9 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3886 | PGE | 95372 | NEM | EXPNEM | Study in Progress | Solar PV | 53.057 |  | 2022-03-08 | 2022-03-15 | 5 | 2022-03-24 | 12 | [27 empty] | 2022-03-24 | 2022-03-24 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3887 | PGE | 95033 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2022-03-08 | 2022-03-11 | 3 | 2022-03-11 | 3 | 2022-03-30 | 13 | [18 empty] | 2022-03-08 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3888 | PGE | 94608 | NEM | VNEM | Study in Progress | Solar PV | 76.679 |  | 2022-03-08 | 2022-03-10 | 2 | 2022-03-17 | 7 | [20 empty] | 2022-03-08 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3889 | PGE | 95228 | NEM | EXPNEM | Application Review in Progress | Solar PV | 236.408 |  | 2022-03-08 | 2022-03-22 | 10 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3890 | PGE | 95938 | NEM | EXPNEM | IA in Progress | Solar PV | 41.76 |  | 2022-03-08 | 2022-03-18 | 8 | 2022-03-18 | 8 | 2022-03-30 | 8 | [15 empty] | 2022-03-30 | [9 empty] | 2022-03-08 | 2022-03-08 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3891 | PGE | 95020 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.621 |  | 2022-03-09 | 2022-03-23 | 10 | [22 empty] | 2022-03-24 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3892 | PGE | 94062 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 42.725 |  | 2022-03-09 | 2022-03-23 | 10 | 2022-03-23 | 10 | [20 empty] | 2022-03-09 | [6 empty] | 2022-03-09 | 2022-03-09 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3893 | PGE | 94506 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.198 |  | 2022-03-21 | 2022-03-23 | 2 | [22 empty] | 2022-03-21 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3894 | PGE | 93657 | NEM | EXPNEM | Application Review in Progress | Solar PV | 944.265 |  | 2022-03-09 | 2022-03-23 | 10 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3895 | PGE | 94954 | NEM | EXPNEM | Application Review in Progress | Solar PV | 180 |  | 2022-03-09 | 2022-03-22 | 9 | [29 empty] | 2022-03-09 | 2022-03-09 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3896 | PGE | 93721 | NEM | EXPNEM | Study in Progress | Solar PV | 34.8 |  | 2022-03-17 | 2022-03-23 | 4 | 2022-03-28 | 7 | [27 empty] | 2022-03-17 | 2022-03-17 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3897 | PGE | 93727 | NEM | EXPNEM | Application Review in Progress | Solar PV | 86 |  | 2022-03-09 | 2022-03-22 | 9 | [29 empty] | 2022-03-09 | 2022-03-09 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3898 | PGE | 93723 | NEM | EXPNEM | Application Review in Progress | Solar PV | 60 |  | 2022-03-09 | 2022-03-18 | 7 | [29 empty] | 2022-03-09 | 2022-03-09 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3899 | PGE | 93706 | NEM | EXPNEM | Application Review in Progress | Solar PV | 303.95 |  | 2022-03-09 | 2022-03-23 | 10 | [29 empty] | 2022-03-09 | 2022-03-09 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3900 | PGE | 95065 | NEM | EXPNEM | Study in Progress | Solar PV | 146.071 |  | 2022-03-09 | 2022-03-23 | 10 | 2022-03-23 | 10 | [27 empty] | 2022-03-09 | 2022-03-09 | 1 | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3901 | PGE | 95333 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2022-03-11 | 2022-03-21 | 6 | 2022-03-21 | 6 | [20 empty] | 2022-03-11 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3902 | PGE | 94803 | NEM | EXPNEM | Application Review in Progress | Solar PV | 436.481 |  | 2022-03-15 | 2022-03-29 | 10 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3903 | PGE | 93657 | NEM | EXPNEM | Application Review in Progress | Solar PV | 965.556 |  | 2022-03-09 | 2022-03-23 | 10 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3904 | PGE | 93637 | NEM | EXPNEM | IA in Progress | Solar PV | 721.536 |  | 2022-03-09 | 2022-03-11 | 2 | 2022-03-11 | 2 | 2022-03-25 | 10 | [15 empty] | 2022-03-25 | 2022-03-25 | 0 | 2022-03-25 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3905 | PGE | 95124 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.198 |  | 2022-03-10 | 2022-03-23 | 9 | [22 empty] | 2022-03-10 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3906 | PGE | 93401 | NEM | VNEM | Application Review in Progress | Solar PV | 71.04 |  | 2022-03-10 | 2022-03-22 | 8 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 | [7 empty] | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 | [8 empty] | 1//19
3907 | PGE | 94025 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 40.242 |  | 2022-03-10 | 2022-03-23 | 9 | 2022-03-24 | 10 | 2022-03-28 | 2 | [18 empty] | 2022-03-23 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 2022-03-28 | 2022-03-28 | 0 |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 2022-03-28 |  |  | 2022-03-28 |  | 2022-03-28 | 0 | 1//19
3908 | PGE | 93427 | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.3 |  | 2022-03-11 | 2022-03-14 | 1 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3909 | PGE | 95030 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 40.163 |  | 2022-03-10 | 2022-03-23 | 9 | 2022-03-23 | 9 | [20 empty] | 2022-03-10 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3910 | PGE | 95333 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2022-03-15 | 2022-03-16 | 1 | 2022-03-28 | 9 | [20 empty] | 2022-03-15 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3911 | PGE | 93450 | Non-NEM | Make Before Break | Study in Progress | ENGN | 38000 |  | 2022-03-15 | 2022-03-17 | 2 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3912 | PGE | 93401 | NEM | EXPNEM | Study in Progress | Solar PV | 60.302 |  | 2022-03-15 | 2022-03-22 | 5 | 2022-03-22 | 5 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3913 | PGE | 93401 | NEM | EXPNEM | Application Review in Progress | Solar PV | 75.128 |  | 2022-03-24 | 2022-03-30 | 4 | [29 empty] | 2022-03-24 | 2022-03-24 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3914 | PGE | 93245 | NEM | EXPNEM | IA in Progress | Solar PV | 31.889 |  | 2022-03-11 | 2022-03-21 | 6 | 2022-03-21 | 6 | 2022-03-31 | 8 | [15 empty] | 2022-03-31 | 2022-03-31 | 0 | 2022-03-31 | [6 empty] | 2022-03-11 | 2022-03-11 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3915 | PGE | 93446 | NEM | EXPNEM | Study in Progress | Solar PV | 34.179 |  | 2022-03-11 | 2022-03-16 | 3 | 2022-03-31 | 14 | [27 empty] | 2022-03-11 | 2022-03-11 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3916 | PGE | 95341 | NEM | EXPNEM | Application Review in Progress | Solar PV | 180 |  | 2022-03-11 | 2022-03-22 | 7 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3917 | PGE | 95333 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 10 |  | 2022-03-11 | 2022-03-22 | 7 | [22 empty] | 2022-03-22 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3918 | PGE | 95225 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.46 |  | 2022-03-13 | 2022-03-30 | 12 | [22 empty] | 2022-03-18 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3919 | PGE | 93307 | NEM | EXPNEM | Application Review in Progress | Solar PV | 1980 |  | 2022-03-14 | 2022-03-18 | 4 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3920 | PGE | 93618 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2022-03-14 | 2022-03-16 | 2 | 2022-03-16 | 2 | 2022-03-28 | 8 | [15 empty] | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3921 | PGE | 93932 | NEM | EXPNEM | Application Review in Progress | Solar PV | 37.926 |  | 2022-03-14 | 2022-03-28 | 10 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3922 | PGE | 93711 | NEM | EXPNEM | Application Review in Progress | Solar PV | 700 |  | 2022-03-15 | 2022-03-29 | 10 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3923 | PGE | 94544 | NEM | EXPNEM | Application Review in Progress | Solar PV | 116.6 |  | 2022-03-29 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3924 | PGE | 95236 | NEM | EXPNEM | Application Review in Progress | Solar PV | 123.701 |  | 2022-03-15 | 2022-03-29 | 10 | [29 empty] | 2022-03-15 | 2022-03-15 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3925 | PGE | 93610 | NEM | EXPNEM | Application Review in Progress | Solar PV | 480 |  | 2022-03-21 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3926 | PGE | 95070 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 37.701 |  | 2022-03-17 | 2022-03-29 | 8 | [22 empty] | 2022-03-17 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3927 | PGE | 90731 | Non-NEM | Non-Export | Application Review in Progress | Storage | 50 |  | 2022-03-31 | 0 | [23 empty] | 2022-03-31 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3928 | PGE | 95476 | NEM | EXPNEM | Application Review in Progress | Solar PV | 49.622 |  | 2022-03-15 | 2022-03-17 | 2 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3929 | PGE | 95616 | NEM | EXPNEM | Application Review in Progress | Solar PV | 35.912 |  | 2022-03-15 | 2022-03-22 | 5 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3930 | PGE | 95033 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2022-03-15 | 2022-03-23 | 6 | 2022-03-23 | 6 | 2022-03-28 | 3 | [15 empty] | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28 | 2022-03-28 | 0 | [5 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3931 | PGE | 95135 | Non-NEM | Non-Export | Application Review in Progress | Storage | 5 |  | 2022-03-16 | 2022-03-30 | 10 | [22 empty] | 2022-03-16 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3932 | PGE | 95988 | NEM | EXPNEM | Application Review in Progress | Solar PV | 550 |  | 2022-03-18 | 2022-03-21 | 1 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3933 | PGE | 94621 | NEM | EXPNEM | Application Review in Progress | Solar PV | 86.4 |  | 2022-03-17 | 2022-03-23 | 4 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3934 | PGE | 95304 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.232 |  | 2022-03-22 | 0 | [23 empty] | 2022-03-22 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3935 | PGE | 93706 | NEM | EXPNEM | Study in Progress | Solar PV | 31.708 |  | 2022-03-17 | 2022-03-31 | 10 | 2022-03-31 | 10 | [27 empty] | 2022-03-17 | 2022-03-17 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3936 | PGE | 93635 | NEM | EXPNEM | IA in Progress | Solar PV | 88.298 |  | 2022-03-17 | 2022-03-18 | 1 | 2022-03-18 | 1 | 2022-03-30 | 8 | [15 empty] | 2022-03-30 | 2022-03-30 | 0 | 2022-03-30 | [6 empty] | 2022-03-17 | 2022-03-17 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3937 | PGE | 94939 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.75 |  | 2022-03-22 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3938 | PGE | 95658 | NEM | EXPNEM | Application Accepted | Solar PV | 37.12 |  | 2022-03-17 | 2022-03-21 | 2 | 2022-03-23 | 4 | [27 empty] | 2022-03-17 | 2022-03-17 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3939 | PGE | 95207 | NEM | EXPNEM | Application Review in Progress | Solar PV | 86.4 |  | 2022-03-22 | 0 | [30 empty] | 2022-03-22 | 2022-03-22 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3940 | PGE | 95612 | NEM | EXPNEM | Application Review in Progress | Solar PV | 32.975 |  | 2022-03-18 | 2022-03-24 | 4 | [29 empty] | 2022-03-18 | 2022-03-18 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3941 | PGE | 94507 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.99 |  | 2022-03-18 | 2022-03-31 | 9 | [22 empty] | 2022-03-18 | [6 empty] | 2022-03-18 | 2022-03-18 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3942 | PGE | 95961 | NEM | EXPNEM | Study in Progress | Solar PV | 500 |  | 2022-03-18 | 2022-03-23 | 3 | 2022-03-23 | 3 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3943 | PGE | 94533 | NEM | EXPNEM | Study in Progress | Solar PV | 35.034 |  | 2022-03-18 | 2022-03-31 | 9 | 2022-03-31 | 9 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3944 | PGE | 93455 | NEM | EXPNEM | Application Review in Progress | Solar PV | 39.045 |  | 2022-03-18 | 2022-03-31 | 9 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3945 | PGE | 94954 | NEM | EXPNEM | Application Review in Progress | Solar PV | 4000 |  | 2022-03-18 | 2022-03-18 | 0 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3946 | PGE | 94549 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.316 |  | 2022-03-18 | 2022-03-31 | 9 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3947 | PGE | 93706 | NEM | EXPNEM | Study in Progress | Solar PV | 875 |  | 2022-03-18 | 2022-03-23 | 3 | 2022-03-28 | 6 | [27 empty] | 2022-03-18 | 2022-03-18 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3948 | PGE | 95076 | NEM | EXPNEM | Application Review in Progress | Solar PV | 194.749 |  | 2022-03-19 | 2022-03-31 | 8 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3949 | PGE | 93711 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.398 |  | 2022-03-19 | 2022-03-31 | 8 | [22 empty] | 2022-03-19 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3950 | PGE | 94801 | Non-NEM | Non-Export | Application Review in Progress | Solar PV, Storage | 500 |  | 2022-03-19 | 2022-03-21 | 0 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3951 | PGE | 94022 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 40.007 |  | 2022-03-21 | 0 | [23 empty] | 2022-03-21 | [6 empty] | 2022-03-21 | 2022-03-21 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3952 | PGE | 93405 | NEM | EXPNEM | Application Review in Progress | Solar PV | 157.323 |  | 2022-03-21 | 2022-03-28 | 5 | [29 empty] | 2022-03-21 | 2022-03-21 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3953 | PGE | 94010 | NEM | EXPNEM | Application Review in Progress | Solar PV | 86.4 |  | 2022-03-21 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3954 | PGE | 94560 | NEM | EXPNEM | Application Review in Progress | Solar PV | 187.5 |  | 2022-03-21 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3955 | PGE | 95304 | NEM | EXPNEM | Study in Progress | Solar PV | 127.033 |  | 2022-03-21 | 2022-03-31 | 8 | 2022-03-31 | 8 | [28 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3956 | PGE | 96055 | NEM | EXPNEM | Application Review in Progress | Solar PV | 71.413 |  | 2022-03-21 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3957 | PGE | 94134 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 5 |  | 2022-03-22 | 2022-03-23 | 1 | 2022-03-25 | 3 | [20 empty] | 2022-03-22 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3958 | PGE | 94551 | NEM | EXPNEM | Application Review in Progress | Solar PV | 73.552 |  | 2022-03-28 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3959 | PGE | 93306 | NEM | EXPNEM | Application Review in Progress | Solar PV | 38.08 |  | 2022-03-22 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3960 | PGE | 94122 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 5 |  | 2022-03-22 | 2022-03-30 | 6 | 2022-03-30 | 6 | [20 empty] | 2022-03-22 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3961 | PGE | 95306 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.423 |  | 2022-03-28 | 0 | [23 empty] | 2022-03-28 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3962 | PGE | 94591 | NEM | VNEM | Application Review in Progress | Solar PV | 130.94 |  | 2022-03-23 | 2022-03-24 | 1 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3963 | PGE | 93654 | NEM | EXPNEM | Application Review in Progress | Solar PV | 44.593 |  | 2022-03-23 | 0 | [30 empty] | 2022-03-23 | 2022-03-23 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3964 | PGE | 95461 | NEM | EXPNEM | Application Review in Progress | Solar PV | 312.5 |  | 2022-03-29 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3965 | PGE | 95138 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 823.038 |  | 2022-03-30 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3966 | PGE | 94563 | Non-NEM | Non-Export | Application Review in Progress | Storage | 5 |  | 2022-03-23 | 0 | [23 empty] | 2022-03-23 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3967 | PGE | 95020 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.373 |  | 2022-03-23 | 0 | [23 empty] | 2022-03-23 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3968 | PGE | 93656 | NEM | EXPNEM | Application Review in Progress | Solar PV | 250 |  | 2022-03-23 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3969 | PGE | 94526 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.595 |  | 2022-03-23 | 0 | [23 empty] | 2022-03-23 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3970 | PGE | 94506 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.398 |  | 2022-03-23 | 0 | [23 empty] | 2022-03-23 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3971 | PGE | 95020 | NEM | EXPNEM | Application Review in Progress | Solar PV | 120 |  | 2022-03-29 | 0 | [30 empty] | 2022-03-29 | 2022-03-29 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3972 | PGE | 95020 | NEM | EXPNEM | Application Review in Progress | Solar PV | 60 |  | 2022-03-29 | 0 | [30 empty] | 2022-03-29 | 2022-03-29 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3973 | PGE | 95020 | NEM | EXPNEM | Application Review in Progress | Solar PV | 144 |  | 2022-03-29 | 0 | [30 empty] | 2022-03-29 | 2022-03-29 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3974 | PGE | 95125 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.872 |  | 2022-03-23 | 0 | [23 empty] | 2022-03-23 | [6 empty] | 2022-03-23 | 2022-03-23 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3975 | PGE | 94596 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.163 |  | 2022-03-23 | 0 | [23 empty] | 2022-03-23 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3976 | PGE | 94549 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.65 |  | 2022-03-24 | 0 | [23 empty] | 2022-03-24 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3977 | PGE | 94920 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.407 |  | 2022-03-24 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3978 | PGE | 95020 | NEM | EXPNEM | Application Review in Progress | Solar PV | 196 |  | 2022-03-29 | 0 | [30 empty] | 2022-03-29 | 2022-03-29 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3979 | PGE | 95020 | NEM | EXPNEM | Application Review in Progress | Solar PV | 86 |  | 2022-03-29 | 0 | [30 empty] | 2022-03-29 | 2022-03-29 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3980 | PGE | 94904 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.398 |  | 2022-03-25 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3981 | PGE | 93611 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.398 |  | 2022-03-25 | 0 | [23 empty] | 2022-03-25 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3982 | PGE | 93306 | NEM | EXPNEM | Application Review in Progress | Solar PV | 38.08 |  | 2022-03-25 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3983 | PGE | 95932 | NEM | EXPNEM | Application Review in Progress | Solar PV | 50 |  | 2022-03-25 | 0 | [30 empty] | 2022-03-25 | 2022-03-25 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3984 | PGE | 94598 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.163 |  | 2022-03-25 | 0 | [23 empty] | 2022-03-25 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3985 | PGE | 95207 | NEM | VNEM | Application Review in Progress | Solar PV | 600 |  | 2022-03-25 | 2022-03-29 | 2 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3986 | PGE | 95023 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.198 |  | 2022-03-25 | 0 | [23 empty] | 2022-03-25 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3987 | PGE | 95953 | NEM | EXPNEM | Application Review in Progress | Solar PV | 119.344 |  | 2022-03-25 | 2022-03-28 | 1 | [29 empty] | 2022-03-25 | 2022-03-25 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3988 | PGE | 95227 | NEM | EXPNEM | Application Review in Progress | Solar PV | 46.94 |  | 2022-03-25 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3989 | PGE | 95436 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.845 |  | 2022-03-25 | 0 | [23 empty] | 2022-03-25 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3990 | PGE | 95020 | NEM | EXPNEM | Application Review in Progress | Solar PV | 144 |  | 2022-03-29 | 0 | [30 empty] | 2022-03-29 | 2022-03-29 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3991 | PGE | 95472 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.398 |  | 2022-03-26 | 0 | [23 empty] | 2022-03-26 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3992 | PGE | 95423 | NEM | EXPNEM | Application Review in Progress | Solar PV | 32.505 |  | 2022-03-26 | 2022-03-28 | 0 | [30 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3993 | PGE | 95032 | Non-NEM | Non-Export | Application Review in Progress | Storage | 10 |  | 2022-03-27 | 0 | [23 empty] | 2022-03-29 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3994 | PGE | 95409 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.423 |  | 2022-03-27 | 0 | [23 empty] | 2022-03-27 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3995 | PGE | 95361 | NEM | EXPNEM | Application Review in Progress | Solar PV | 95.856 |  | 2022-03-28 | 0 | [30 empty] | 2022-03-28 | 2022-03-28 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3996 | PGE | 95020 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.578 |  | 2022-03-28 | 0 | [23 empty] | 2022-03-28 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3997 | PGE | 93460 | NEM | EXPNEM | Application Review in Progress | Solar PV | 49.97 |  | 2022-03-29 | 0 | [30 empty] | 2022-03-29 | 2022-03-29 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3998 | PGE | 94947 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 40.398 |  | 2022-03-29 | 0 | [23 empty] | 2022-03-29 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
3999 | PGE | 95254 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.48 |  | 2022-03-29 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
4000 | PGE | 95409 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 10 |  | 2022-03-29 | 0 | [23 empty] | 2022-03-29 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
4001 | PGE | 95949 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.48 |  | 2022-03-29 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
4002 | PGE | 93673 | NEM | EXPNEM | Application Review in Progress | Solar PV | 58.738 |  | 2022-03-29 | 0 | [30 empty] | 2022-03-29 | 2022-03-29 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
4003 | PGE | 94002 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.398 |  | 2022-03-30 | 0 | [23 empty] | 2022-03-30 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
4004 | PGE | 95492 | NEM | EXPNEM | Application Review in Progress | Solar PV | 45.056 |  | 2022-03-30 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
4005 | PGE | 93422 | Non-NEM | Non-Export | Application Review in Progress | Storage | 10 |  | 2022-03-30 | 0 | [23 empty] | 2022-03-30 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
4006 | PGE | 95003 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.127 |  | 2022-03-30 | 0 | [23 empty] | 2022-03-30 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
4007 | PGE | 95667 | Non-NEM | Non-Export | Application Review in Progress | Storage | 929.5 |  | 2022-03-30 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
4008 | PGE | 95215 | NEM | EXPNEM | Application Review in Progress | Solar PV | 31.9 |  | 2022-03-31 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
4009 | PGE | 94010 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.398 |  | 2022-03-31 | 0 | [23 empty] | 2022-03-31 | [7 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
4010 | PGE | 95037 | NEM | EXPNEM | Application Review in Progress | Solar PV | 99.9 |  | 2022-03-31 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
4011 | PGE | 94534 | NEM | EXPNEM | Withdrawn | Solar PV | 84.807 |  | 2022-03-31 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
4012 | PGE | 93631 | NEM | EXPNEM | Application Review in Progress | Solar PV | 72 |  | 2022-03-31 | 0 | [30 empty] | 2022-03-31 | 2022-03-31 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
4013 | PGE | 93631 | NEM | EXPNEM | Application Review in Progress | Solar PV | 46.99 |  | 2022-03-31 | 0 | [30 empty] | 2022-03-31 | 2022-03-31 | 1 | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
4014 | PGE | 93280 | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.432 |  | 2022-03-31 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
4015 | PGE | 94534 | NEM | EXPNEM | Application Review in Progress | Solar PV | 84.807 |  | 2022-03-31 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19
4016 | PGE | 95377 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 250 |  | 2022-03-31 | 0 | [31 empty] | 0 |  | 1//19 | 1//19 | 1//19 |  | 1//19 | 1//19 |  |  |  |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 |  | 1//19 | 1//19 | 1//19 |  | 1//19

## Q4 19 Timelines Report
Notification No | Key | Utility | Zip Code | NEM Type | Project Type | Project Status | Technology Type | Size Total Proposed Gen | Cost Envelope Requested? | Application Received | Provide: 1st Written Notice/Invoice | Provide: NEM Deficiency Notice | Application Review | Provide: 1st Written Notice/Invoice | Cycle Time A (Business Days to Acknowledge Interconnection Request Submission) | Application Deemed Complete | Cycle Time B (Business Days to Deem Complete) | Conduct: Initial Review (IR) | Cycle Time C (Time from Interconnection Request Deemed Complete to Completion of Initial Review & Provision of Results) | Conduct: Supplemental Review (SR) | Conduct: Supplemental Review (SR) | Cycle Time D (Time from Supplemental Review Start Date to Completion of Supplemental Review) | Conduct: Screens Q and R | Conduct: Screens Q and R | Cycle Time E (Time from Electrical Interdependence Test Start Date to its Completion) | Scoping Meeting Date | Scoping Meeting Date | Cycle Time F (Time from Electrical Interdependence Test Completion to EIT Results Scoping Meeting Held) | DSA Agreement Executed by PG&E | Conduct: SIS | Cycle Time H (Time from System Impact Study Start Date to its Completion Date) | Scoping Meeting Date | Tendered DSA Agreement | Cycle Time G (Time from Study Scoping Meeting Until Study Agreement Provided) | Tender Draft IA | Tender Draft IA | Cycle Time I (Time to Provide Draft Generator Interconnection Agreement Applicable Milestone) | Tender Draft IA | IA Negotiations/Customer Signature | Cycle Time J(a) (Time from Draft Generator Interconnection Agreement Provided to Date Generator Interconnection Agreement Executed) | Cycle Time J(b) (Time from Final Study Report Date for Detailed Study to Date Generator Interconnection Agreement Executed) | Receive Customer Changes | Determine Material Modifications | Cycle Time M (Time from Request to Consider Modification to Determination Whether Modification is Material (F.3.b.v)) | Variance Request Received (Typ. From Cust) | Conduct: Variance Request Review | Variance Request Received (Typ. From Cust) | Conduct: Variance Request Review | Cycle Time N (Time for Responding to Line-Side Taps Variance Requests (for utilities that require a variance request)) | Conduct: Meter Review | Tender: Meter Invoice | Tender: Meter Invoice | Cycle Time O (Design and Invoice of Net Generation Output Meter) | Move to FMO | FMO - PASS | Cycle Time P (Installation of Net Generation Output Meter) | SP&D Design Start | SP&D Design End | Cycle Time Q(a) (Time from Customer Agreement to Proceed to Final Design and Issuance of Invoice SP&D) | Tender EA Invoice | IT Design End | Cycle Time Q(b) (Time from Customer Agreement to Proceed to Final Design and Issuance of Invoice Telemetry) | SP&D Construction Start | SP&D Construction Finish | Cycle Time R(a) (Time from Customer Payment of Invoice and Completion of Customer Work to Completion of Upgrade Construction SP&D) | PG&E Construction Start IT | PG&E Construction Complete IT | Cycle Time R(b) (Time from Customer Payment of Invoice and Completion of Customer Work to Completion of Upgrade Construction Telemetry) | PPI Authorization Letter | PPI Completion | Cycle Time S (Time for Scheduling of Commissioning Test) | FMO - PASS (Move to FMO) | FMO Schedule Inspection FMO Order | Cycle Time S(b) (This is for Projects that do not require PPI) | FMO - PASS | Permission to Operate - Conditional (COD) | Permission to Operate - Final (COD) | Cycle Time K(a) (Time from when the customer notifies the utility it has completed all of its obligations under the agreements (F.5.b) including commissioning tests, to when the utility provides the customer Permission to Operate - FMO Inspection: Task 7390 AFD FMO - PASS to Task 7502 AFD Permission to Parallel - Conditional or 7503 AFD Permission to Operate - Final (COD)) | Conduct Pre Paralell Inspection (PPI) | Cycle Time K(b) (This Cycle Time is for Projects that require PPI) | Cycle Time L (Total Time from Submission of Interconnection Request to Permission to Operate (Not in Rule 21, tracked for informational purposes))
120237417 | 1 | PGE | 94804 | NEM | EXPNEM | Withdrawn | Solar PV | 111.324 |  | 2020-12-29 |  | 2021-01-27 | 2020-12-29 | 2020-12-29 | 0 | 2021-01-28 | 20 | [27 empty] | 2020-12-29 |  | 2020-12-29
120237481 | 2 | PGE | 95746 | NEM | EXPNEM | IA in Progress | Solar PV | 32.89 |  | 2020-12-29 |  |  | 2020-12-29 | 2020-12-29 | 0 | 2020-12-29 | 0 | 2021-01-19 | 13 | [15 empty] | 2021-01-19 | 2021-01-19 | 0 | 2021-01-19 | 2021-01-25 | 4 | [13 empty] | 2021-12-13 | 2021-12-22 | 7 | [15 empty] | 2021-12-13 | 2021-12-14 | 1 | 2021-12-22
120237636 | 3 | PGE | 93630 | NEM | EXPNEM | IA in Progress | Solar PV | 94.943 |  | 2020-12-29 |  | 2020-12-29 | 2020-12-29 | 2020-12-29 | 0 | 2020-12-30 | 1 | 2021-01-11 | 7 | [15 empty] | 2021-01-11 | 2021-01-11 | 0 | 2021-01-11 | 2021-01-14 | 3 |  |  |  |  | 2020-12-29 | 2021-01-05 | 2020-12-29 | 2021-01-19 | 13 | [7 empty] | 2021-03-02 | 2021-04-27 | 40 |  |  |  | 2021-08-16 | 0 | 104
120237659 | 4 | PGE | 95207 | NEM | EXPNEM | Withdrawn | Solar PV | 43.2 |  | 2020-12-29 |  | 2021-01-11 | 2021-01-11 | 2021-01-11 | 8 | 2021-02-11 | 30 | 2021-02-26 | 10 | [15 empty] | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26
120239187 | 5 | PGE | 95453 | NEM | VNEMMASH | Implementation | Solar PV | 113.676 |  | 2020-12-29 |  | 2021-01-13 | 2021-01-13 | 2021-01-13 | 10 | 2021-03-31 | 63 | 2021-04-05 | 3 | [15 empty] | 2021-04-05 | 2021-04-23 | 14 | 2021-04-23 | 2021-05-20 | 19 |  |  |  |  | 2020-12-29 | 2021-04-29 | 2020-12-29 | 2021-04-29 | 84
120239245 | 6 | PGE | 94028 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 57.325 |  | 2020-12-29 |  | 2021-02-16 | 2021-01-05 | 2021-01-05 | 4 | 2021-01-05 | 4 | 2021-01-07 | 2 | [15 empty] | 2021-01-05 | 2021-01-05 | 0 | 2021-01-05 | 2021-02-17 | 29 | [10 empty] | 2021-01-12 | 2021-01-12 | 0
120239248 | 7 | PGE | 95327 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 207.052 |  | 2020-12-29 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 9 | 2021-01-22 | 16 | 2021-02-17 | 17 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-05-11 | 83 |  |  |  |  | 2020-12-29 |  | 2020-12-29 | [6 empty] | 2021-09-20 | 2021-09-27 | 5 | [15 empty] | 2021-09-20 | 2021-09-20 | 0 | 2021-09-27 | 2021-09-28 |  | 1 |  |  | 189
120239758 | 8 | PGE | 93230 | NEM | EXPNEM | Withdrawn | Solar PV | 1320 |  | 2020-12-29 | 2021-01-04 |  | 2020-12-31 | 2020-12-31 | 2 | 2021-01-13 | 10 | [5 empty] | 2021-01-13 | 2021-02-05 | 16 | 2021-02-05
120240818 | 9 | PGE | 95540 | Non-NEM | Non-Export | Implementation | Storage | 357.5 |  | 2020-12-30 | 2020-12-31 |  | 2020-12-31 | 2020-12-31 | 1 | 2021-01-27 | 18 | 2021-05-12 | 74 | [15 empty] | 2021-02-01 | 2021-02-01 | 0 | 2021-02-01 | 2021-05-25 | 80 |  |  |  |  | 2020-12-30 |  | 2020-12-30
120241984 | 10 | PGE | 95691 | NEM | EXPNEM | IA in Progress | Solar PV | 420 |  | 2020-12-30 |  | 2021-01-28 | 2021-01-28 | 2021-01-28 | 19 | 2021-04-08 | 68 | [17 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | [6 empty] | 2020-12-30 |  | 2020-12-30
120242187 | 11 | PGE | 94503 | NEM | EXPNEM | IA in Progress | Solar PV | 480 |  | 2020-12-30 |  | 2021-01-11 | 2021-01-11 | 2021-01-11 | 7 | 2021-01-28 | 19 | 2021-04-29 | 64 | [15 empty] | 2021-04-29 | 2021-04-29 | 0 | 2021-04-29 | [6 empty] | 2020-12-30 |  | 2020-12-30
120242240 | 12 | PGE | 93662 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2020-12-30 |  |  | 2021-01-13 | 2021-01-13 | 9 | 2021-01-13 | 9 | 2021-02-03 | 14 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-06-28 | 101 |  |  |  |  | 2020-12-30 | 2021-01-13 | 2020-12-30 | 2021-01-27 | 18 |  |  |  |  | 2021-07-06 | 2021-07-13 | 5 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-13 |  | 2021-07-14 | 1
120242384 | 13 | PGE | 95536 | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2020-12-30 | 2020-12-31 |  | 2020-12-31 | 2020-12-31 | 1 | 2021-01-27 | 18 | 2021-03-02 | 23 | [15 empty] | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | 2021-06-28 | 83 |  |  |  |  | 2020-12-30 | 2021-01-28 | 2020-12-30 | 2021-02-05 | 25 |  |  |  |  | 2021-12-30 | [17 empty] | 2021-12-30 | 2021-12-30 | 0 |  |  |  |  | 2021-12-02 |  | 0
120242433 | 14 | PGE | 95336 | NEM | EXPNEM | Withdrawn | Solar PV | 125 |  | 2020-12-30 |  | 2020-12-31 | 2020-12-31 | 2020-12-31 | 1 | 2021-01-05 | 3 | 2021-01-11 | 4
120242519 | 15 | PGE | 95521 | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2020-12-30 | 2020-12-31 |  | 2020-12-31 | 2020-12-31 | 1 | 2021-01-27 | 18 | 2021-07-28 | 127 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | 2021-08-17 | 14 |  |  |  |  | 2020-12-30 | 2021-04-06 | 2020-12-30 | 2021-04-14 | 72
120242688 | 16 | PGE | 94127 | NEM | EXPNEM | Commercial | Solar PV | 90.079 |  | 2020-12-30 |  | 2021-02-05 | 2020-12-31 | 2020-12-31 | 1 | 2021-03-30 | 61 | 2021-05-04 | 25 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | 2021-07-26 | 57 | [13 empty] | 2021-07-31 | 2021-08-05 | 3 | [15 empty] | 2021-07-31 | 2021-08-02 | 0 | 2021-08-05 |  | 2021-08-11 | 4
120243147 | 17 | PGE | 94010 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.454 |  | 2020-12-31 |  |  | 2021-01-07 | 2021-01-07 | 4 | 2021-01-07 | 4 | 2021-01-28 | 14 | [15 empty] | 2021-01-07 | 2021-01-07 | 0 | 2021-01-07 | 2021-02-16 | 26 | [13 empty] | 2021-02-16 | 2021-02-17 | 1 | [15 empty] | 2021-02-16 | 2021-02-17 | 1 | 2021-02-17 |  | 2021-02-17 | 0
120244060 | 19 | PGE | 95401 | NEM | EXPNEM | IA in Progress | Solar PV | 58.04 |  | 2020-12-31 |  |  | 2021-01-14 | 2021-01-14 | 9 | 2021-01-14 | 9 | 2021-02-11 | 19 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11
120253137 | 20 | PGE | 95219 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-01-04 |  | 2021-01-05 | 2021-01-05 | 2021-01-05 | 1 | 2021-01-11 | 5 | 2021-01-21 | 7 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-06-03 | 93 |  |  |  |  | 2021-01-04 | 2021-09-24 | 2021-01-04 | 2021-09-28 | 186 | [7 empty] | 2021-10-21 | 2021-10-21 | 0
120254145 | 21 | PGE | 94513 | NEM | EXPNEM | Implementation | Solar PV | 131.497 |  | 2021-01-04 |  |  | 2021-01-14 | 2021-01-14 | 8 | 2021-01-14 | 8 | 2021-02-04 | 14 | [15 empty] | 2021-02-04 | 2021-02-04 | 0 | 2021-02-04 | 2021-03-21 | 30 |  |  |  |  | 2021-01-04 | 2021-03-01 | 2021-01-04 | 2021-03-01 | 38 |  |  |  |  | 2021-07-20 | 2021-07-29 | 9 | 2021-06-14 | 2021-10-22 | 92 |  |  |  | 2021-11-16 | 0 | 40 | [6 empty] | 2021-12-22 | 2021-12-23 | 1 | 2021-07-29 | 2021-07-29 |  | 0 |  |  | 144
120254901 | 22 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 700 |  | 2021-01-04 |  |  | 2021-01-15 | 2021-01-15 | 9 | 2021-01-15 | 9 | 2021-02-04 | 13 | [15 empty] | 2021-02-04 | 2021-02-04 | 0 | 2021-02-04 | 2021-02-05 | 1 | [5 empty] | 2021-02-04 | 2021-02-04 | 2021-02-09 | 3 |  |  |  |  | 2021-12-22 | 2021-12-30 | 6 | 2021-03-08 | 2021-05-19 | 52 |  |  |  | 2021-11-03 | 2021-12-17 | 29 | [6 empty] | 2021-12-22 | 2021-12-23 | 1 | 2021-12-30 |  | 2021-12-30 | 0
120256497 | 23 | PGE | 95020 | NEM | EXPNEM | Commercial | Solar PV | 99.9 |  | 2021-01-04 |  | 2021-01-14 | 2021-01-07 | 2021-01-07 | 3 | 2021-01-15 | 9 | 2021-02-02 | 11 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-02 | 0 | [13 empty] | 2021-02-03 | 2021-02-09 | 4 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-09 |  | 2021-02-10 | 1
120257019 | 24 | PGE | 94509 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 52.49 |  | 2021-01-04 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 10 | [29 empty] | 2021-01-04 |  | 2021-01-04
120257082 | 25 | PGE | 94509 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 61.773 |  | 2021-01-04 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 10 | [29 empty] | 2021-01-04 |  | 2021-01-04
120257085 | 26 | PGE | 94509 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 65.263 |  | 2021-01-04 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 10 | [29 empty] | 2021-01-04 |  | 2021-01-04
120257087 | 27 | PGE | 94509 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.444 |  | 2021-01-04 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 10 | [29 empty] | 2021-01-04 |  | 2021-01-04
120257095 | 28 | PGE | 94509 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 63.867 |  | 2021-01-04 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 10 | [29 empty] | 2021-01-04 |  | 2021-01-04
120257143 | 29 | PGE | 94509 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 62.122 |  | 2021-01-04 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 10 | [29 empty] | 2021-01-04 |  | 2021-01-04
120257146 | 30 | PGE | 94509 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 41.88 |  | 2021-01-04 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 10 | [29 empty] | 2021-01-04 |  | 2021-01-04
120257149 | 31 | PGE | 94509 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 63.169 |  | 2021-01-04 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 10 | [29 empty] | 2021-01-04 |  | 2021-01-04
120257217 | 32 | PGE | 94509 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 57.585 |  | 2021-01-04 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 10 | [29 empty] | 2021-01-04 |  | 2021-01-04
120257840 | 33 | PGE | 95623 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 |  | 2021-01-05 |  | 2021-02-17 | 2021-01-08 | 2021-01-08 | 3 | 2021-01-08 | 3 | 2021-01-11 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-02-17 | 26 | [13 empty] | 2021-02-17 | 2021-02-17 | 0 | [15 empty] | 2021-02-17 | 2021-02-17 | 0 | 2021-02-17 |  | 2021-02-17 | 0
120258147 | 34 | PGE | 93662 | NEM | EXPNEM | Commercial | Solar PV | 62.5 |  | 2021-01-05 |  | 2021-01-06 | 2021-01-06 | 2021-01-06 | 1 | 2021-01-19 | 9 | 2021-02-18 | 21 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-05-26 | 69 |  |  |  |  | 2021-01-05 | 2021-01-06 | 2021-01-05 | 2021-01-20 | 10 |  |  |  |  | 2021-07-16 | 2021-07-20 | 2 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-20 |  | 2021-07-26 | 4
120258656 | 35 | PGE | 93701 | NEM | EXPNEM | Commercial | Solar PV | 85.573 |  | 2021-01-05 |  | 2021-01-06 | 2021-01-06 | 2021-01-06 | 1 | 2021-01-07 | 2 | 2021-01-08 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-03-10 | 41 |  |  |  |  | 2021-01-05 |  | 2021-01-05 | [6 empty] | 2021-03-12 | 2021-04-21 | 28 | [15 empty] | 2021-03-12 | 2021-04-21 | 28 | 2021-04-21 |  | 2021-04-23 | 2
120258859 | 36 | PGE | 93308 | NEM | EXPNEM | Commercial | Solar PV | 53.808 |  | 2021-01-05 |  | 2021-01-06 | 2021-01-06 | 2021-01-06 | 1 | 2021-01-06 | 1 | 2021-01-21 | 10 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-04-09 | 55 | [13 empty] | 2021-04-12 | 2021-04-19 | 5 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-19 |  | 2021-04-27 | 6
120258980 | 37 | PGE | 95746 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-01-05 |  | 2021-01-20 | 2021-01-20 | 2021-01-20 | 10 | 2021-01-28 | 16 | 2021-02-02 | 3 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-04 | 2 | [13 empty] | 2021-02-08 | 2021-02-08 | 0 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 |  | 2021-02-10 | 2
120260346 | 38 | PGE | 93212 | NEM | EXPNEM | Commercial | Solar PV | 31.886 |  | 2021-01-05 |  | 2021-01-06 | 2021-01-06 | 2021-01-06 | 1 | 2021-01-27 | 15 | 2021-02-11 | 11 | [15 empty] | 2021-02-11 | 2021-02-16 | 2 | 2021-02-16 | 2021-02-23 | 5 |  |  |  |  | 2021-01-05 | 2021-08-09 | 2021-01-05 | 2021-08-18 | 157 |  |  |  |  | 2021-09-17 | 2021-09-30 | 9 | 2021-03-17 | 2021-06-03 | 55 |  |  |  | 2021-06-03 | 2021-07-14 | 28 | [6 empty] | 2021-09-17 | 2021-09-20 | 1 | 2021-09-30 |  | 2021-10-07 | 5
120260620 | 39 | PGE | 93662 | NEM | EXPNEM | Commercial | Solar PV | 83.3 |  | 2021-01-05 |  | 2021-02-02 | 2021-01-19 | 2021-01-19 | 9 | 2021-01-19 | 9 | 2021-02-02 | 10 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-06-28 | 102 |  |  |  |  | 2021-01-05 | 2021-01-19 | 2021-01-05 | 2021-01-28 | 16 |  |  |  |  | 2021-07-06 | 2021-07-13 | 5 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-13 |  | 2021-07-13 | 0
120260704 | 40 | PGE | 95694 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-01-05 |  | 2021-01-12 | 2021-01-06 | 2021-01-06 | 1 | 2021-01-13 | 6 | 2021-02-02 | 13 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-02 | 0 |  |  |  |  | 2021-01-05 | 2021-01-06 | 2021-01-05 | 2021-01-20 | 10 |  |  |  |  | 2021-11-16 | 2021-11-22 | 4 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-22 |  | 2021-11-29 | 3
120261107 | 41 | PGE | 93314 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-01-05 |  |  | 2021-01-19 | 2021-01-19 | 9 | 2021-01-19 | 9 | 2021-02-08 | 14 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-03-01 | 14 | [13 empty] | 2021-03-23 | 2021-04-01 | 7 | [15 empty] | 2021-03-23 | 2021-03-24 | 1 | 2021-04-01 |  | 2021-04-01 | 0
120261917 | 42 | PGE | 93314 | NEM | VNEMMASH | Implementation | Solar PV | 433.597 |  | 2021-01-05 |  | 2021-07-26 | 2021-01-12 | 2021-01-12 | 5 | 2021-01-12 | 5 | 2021-02-19 | 26 |  |  |  | 2021-03-02 | 2021-04-23 | 38 | 2021-04-23 |  |  | 2021-04-23 | 2021-07-16 | 58 |  |  |  | 2021-07-16 | 2021-07-16 |  | 2021-07-16 | 2021-07-27 | 8 | 7 |  |  |  |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 0 |  | 2021-08-18 | 2021-08-18 | 0 |  |  |  | 2021-09-08 | 2021-10-22 | 32 |  |  |  | 2021-11-05 | 0 | 46
120262031 | 43 | PGE | 95341 | NEM | VNEMMASH | Implementation | Solar PV | 530 |  | 2021-01-05 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 5 | 2021-01-12 | 5 | 2021-02-24 | 29 | [15 empty] | 2021-02-24 | 2021-02-24 | 0 | 2021-02-24 | 2021-05-05 | 50 | [9 empty] | 2021-06-17 | 2021-08-18 | 2021-08-18 | 43
120262567 | 44 | PGE | 93280 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 2600.5 |  | 2021-01-06 | 2021-01-07 |  | 2021-01-07 | 2021-01-07 | 1 | 2021-01-27 | 14 | [5 empty] | 2021-01-27 | 2021-03-04 | 25 | 2021-03-04 | 2021-03-04 | 0 | 2021-03-25 | 2021-06-21 | 61 | 2021-03-04 | 2021-03-08 | 2 | 2021-07-29 | 2021-07-29 | 0 | 2021-07-29 | 2021-08-18 | 14 |  | 2021-07-15 | [17 empty] | 9/3/2021 | 2021-11-24 | 59
120300339 | 46 | PGE | 95519 | NEM | EXPNEM | IA in Progress | Solar PV | 493.369 |  | 2021-01-06 |  | 2021-02-22 | 2021-01-07 | 2021-01-07 | 1 | 2021-02-23 | 32 | 2021-03-09 | 10 | [15 empty] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | [6 empty] | 2021-12-13 | 2021-12-13 | 2021-12-13
120331569 | 47 | PGE | 93230 | NEM | EXPNEM | Implementation | Solar PV | 1625 |  | 2021-01-06 | 2021-01-07 |  | 2021-01-07 | 2021-01-07 | 1 | 2021-01-20 | 9 | 2021-03-02 | 28 | 2021-03-08 | 2021-04-01 | 18 | 2021-05-03 | 2021-05-12 | 7 | 2021-05-12 | 2021-05-13 | 1 | 2021-05-21 | 2021-08-10 | 55 | 2021-05-13 | 2021-05-13 | 0 | 2021-08-19 | 2021-08-27 | 6 | 2021-08-27 | 2021-10-27 | 42 |  | 2021-08-19 | 2021-08-26 | 5 | [12 empty] | 2021-12-13 |  | 23
120342553 | 48 | PGE | 93465 | NEM | EXPNEM | Withdrawn | Solar PV | 52.675 |  | 2021-01-06 |  |  | 2021-01-19 | 2021-01-19 | 8 | 2021-01-19 | 8 | 2021-02-08 | 14 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08
120400544 | 50 | PGE | 95603 | NEM | EXPNEM | IA in Progress | Solar PV | 53.35 |  | 2021-01-07 |  |  | 2021-01-08 | 2021-01-08 | 1 | 2021-01-08 | 1 | 2021-01-26 | 11 | [15 empty] | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 2021-01-29 | 3 |  |  |  |  | 2021-01-07 | 2021-02-02 | 2021-01-07 | 2021-02-08 | 21
120400551 | 51 | PGE | 94590 | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-01-07 |  |  | 2021-01-08 | 2021-01-08 | 1 | 2021-01-08 | 1 | 2021-02-08 | 20 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-02-12 | 4 |  |  |  |  | 2021-01-07 | 2021-02-04 | 2021-01-07 | 2021-02-09 | 22 | [7 empty] | 2021-10-19 | 2021-11-02 | 10
120400883 | 52 | PGE | 95231 | NEM | EXPNEM | Implementation | Solar PV | 112.682 |  | 2021-01-07 |  | 2021-11-23 | 2021-01-12 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-28 | 11 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23 | 2021-08-23 | 0 |  |  |  |  | 2021-01-07 |  | 2021-01-07 |  |  | 2021-09-08 | [6 empty] | 2021-09-08 |  | 88
120400937 | 53 | PGE | 93304 | NEM | EXPNEM | Commercial | Solar PV | 168.87 |  | 2021-01-07 |  | 2021-01-08 | 2021-01-08 | 2021-01-08 | 1 | 2021-01-11 | 2 | 2021-02-20 | 27 | [15 empty] | 2021-02-20 | 2021-02-20 | 0 | 2021-02-20 | 2021-08-18 | 125 |  |  |  |  | 2021-01-07 | 2021-03-02 | 2021-01-07 | 2021-03-03 | 37 |  |  |  |  | 2021-11-09 | 2021-11-17 | 5 | [15 empty] | 2021-11-09 | 2021-11-10 | 1 | 2021-11-17 |  | 2021-11-22 | 3
120401435 | 54 | PGE | 95448 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.741 |  | 2021-01-07 |  |  | 2021-01-12 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-03-09 | 38 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-03-10 | 39 | [13 empty] | 2021-03-10 | 2021-03-10 | 0 | [15 empty] | 2021-03-10 | 2021-03-10 | 0 | 2021-03-10 |  | 2021-03-13 | 2
120401572 | 55 | PGE | 95020 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 41.331 |  | 2021-01-07 |  |  | 2021-01-12 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-14 | 2 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-05-17 | 87 |  |  |  |  | 2021-01-07 | 2021-05-17 | 2021-01-07 | 2021-05-17 | 90 |  |  |  |  | 2021-05-20 | 2021-05-21 | 1 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-21 |  | 2021-05-21 | 0
120402483 | 56 | PGE | 93662 | NEM | EXPNEM | Commercial | Solar PV | 62.5 |  | 2021-01-07 |  |  | 2021-01-21 | 2021-01-21 | 9 | 2021-01-21 | 9 | 2021-03-10 | 33 | [15 empty] | 2021-03-10 | 2021-03-10 | 0 | 2021-03-10 | 2021-06-28 | 77 |  |  |  |  | 2021-01-07 | 2021-01-21 | 2021-01-07 | 2021-02-02 | 17 |  |  |  |  | 2021-07-14 | 2021-07-20 | 4 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-20 |  | 2021-07-22 | 2
120403977 | 57 | PGE | 95206 | NEM | EXPNEM | Implementation | Solar PV | 54.229 |  | 2021-01-07 |  |  | 2021-01-21 | 2021-01-21 | 9 | 2021-01-21 | 9 | 2021-02-10 | 14 | [15 empty] | 2021-02-10 | 2021-02-10 | 0 | 2021-02-10 | 2021-03-03 | 14 |  |  |  |  | 2021-01-07 | 2021-05-19 | 2021-01-07 | 2021-05-28 | 99 | [7 empty] | 2021-06-22 | 2021-10-21 | 85
120405542 | 59 | PGE | 94506 | NEM | EXPNEM | Implementation | Solar PV | 82.656 |  | 2021-01-08 |  |  | 2021-01-22 | 2021-01-22 | 9 | 2021-01-22 | 9 | 2021-03-03 | 27 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-06-15 | 73 | [5 empty] | 2021-03-12 | 2021-03-12 | 2021-03-15 | 1
120405864 | 60 | PGE | 93618 | NEM | EXPNEM | Commercial | Solar PV | 60 |  | 2021-01-08 |  |  | 2021-01-22 | 2021-01-22 | 9 | 2021-01-22 | 9 | 2021-02-11 | 14 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-22 | 6 |  |  |  |  | 2021-01-08 | 2021-01-22 | 2021-01-08 | 2021-02-02 | 16 |  |  |  |  | 2021-05-01 | 2021-05-10 | 5 | [15 empty] | 2021-05-01 | 2021-05-03 | 0 | 2021-05-10 |  | 2021-05-10 | 0
120406220 | 61 | PGE | 93250 | NEM | EXPNEM | Commercial | Solar PV | 83.3 |  | 2021-01-08 |  |  | 2021-01-23 | 2021-01-23 | 9 | 2021-01-23 | 9 | 2021-02-06 | 10 | [15 empty] | 2021-02-06 | 2021-02-06 | 0 | 2021-02-06 | 2021-06-02 | 80 |  |  |  |  | 2021-01-08 | 2021-01-23 | 2021-01-08 | 2021-02-02 | 16 |  |  |  |  | 2021-07-20 | 2021-07-27 | 5 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-27 |  | 2021-07-29 | 2
120406395 | 62 | PGE | 94517 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-01-08 |  | 2021-01-16 | 2021-01-16 | 2021-01-16 | 5 | 2021-02-24 | 31 | 2021-03-15 | 13 | [15 empty] | 2021-02-24 | 2021-02-24 | 0 | 2021-02-24 | 2021-03-10 | 10 | [13 empty] | 2021-03-15 | 2021-03-15 | 0 | [15 empty] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 |  | 2021-03-22 | 5
120406633 | 63 | PGE | 95521 | Non-NEM | Non-Export | IA in Progress | Storage | 350 |  | 2021-01-08 | 2021-01-11 |  | 2021-01-11 | 2021-01-11 | 1 | 2021-02-03 | 17 | 2021-04-30 | 61 | [15 empty] | 2021-04-30 | 2021-04-30 | 0 | 2021-04-30 | 2021-05-06 | 4 |  |  |  |  | 2021-01-08 | 2021-03-26 | 2021-01-08 | 2021-04-12 | 64 |  |  |  |  | 2021-12-21 | [17 empty] | 2021-12-21 | 2021-12-22 | 1
120406850 | 64 | PGE | 93250 | NEM | EXPNEM | Commercial | Solar PV | 62.5 |  | 2021-01-08 |  |  | 2021-01-23 | 2021-01-23 | 9 | 2021-01-23 | 9 | 2021-02-09 | 11 | [15 empty] | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | 2021-07-06 | 102 |  |  |  |  | 2021-01-08 | 2021-01-23 | 2021-01-08 | 2021-02-02 | 16 |  |  |  |  | 2021-07-06 | 2021-07-14 | 6 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-14 |  | 2021-07-14 | 0
120407430 | 65 | PGE | 94903 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 74.404 |  | 2021-01-08 |  | 2021-01-14 | 2021-01-14 | 2021-01-14 | 4 | 2021-01-18 | 5 | 2021-04-06 | 54 | [25 empty] | 2021-01-08 |  | 2021-01-08 |  |  | 2021-01-19
120407821 | 66 | PGE | 95111 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 172.8 |  | 2021-01-08 |  | 2021-01-25 | 2021-01-22 | 2021-01-22 | 9 | 2021-06-25 | 117 | [5 empty] | 2021-06-25 | 2021-07-26 | 20 | 2021-07-26 | [18 empty] | 2021-01-08 | 2021-09-13 | 2021-01-08
120407845 | 67 | PGE | 95037 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 37.68 |  | 2021-01-08 |  | 2021-01-14 | 2021-01-14 | 2021-01-14 | 4 | 2021-01-21 | 8 | 2021-01-25 | 2 | [15 empty] | 2021-01-14 | 2021-01-14 | 0 | 2021-01-14 | 2021-10-15 | 191 | [13 empty] | 2021-11-01 | 2021-11-01 | 0 | [15 empty] | 2021-11-01 | 2021-11-01 | 0 | 2021-11-01 |  | 2021-11-02 | 1
120407891 | 68 | PGE | 95501 | Non-NEM | Non-Export | Commercial | Storage | 140 |  | 2021-01-08 | 2021-01-12 |  | 2021-01-11 | 2021-01-11 | 1 | 2021-02-03 | 17 | 2021-03-30 | 38 | [15 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-04-12 | 9 |  |  |  |  | 2021-01-08 |  | 2021-01-08 | [6 empty] | 2021-12-01 | 2021-12-09 | 6 | [15 empty] | 2021-12-01 | 2021-12-02 | 1 | 2021-12-09 |  | 2021-12-09 | 0 | 2021-11-30 | 7 | 0
120407969 | 69 | PGE | 95020 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-01-08 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2 | 2021-01-12 | 2 | 2021-02-25 | 30 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-26 | 21 |  |  |  |  | 2021-01-08 |  | 2021-01-08 | [6 empty] | 2021-05-24 | 2021-06-02 | 6 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-06-02 |  | 2021-06-04 | 2
120407972 | 70 | PGE | 94559 | NEM | NEM Paired Storage | Implementation | ENGN, Solar PV, Storage | 910.673 |  | 2021-01-08 |  | 2021-03-30 | 2021-01-20 | 2021-01-20 | 7 | 2021-03-31 | 56 | 2021-05-10 | 28 | [15 empty] | 2021-05-10 | 2021-05-11 | 1 | 2021-05-11 | 2021-11-04 | 124 |  |  |  |  | 2021-01-08 |  | 2021-01-08
120408129 | 71 | PGE | 94508 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 30.399 |  | 2021-01-09 |  |  | 2021-01-16 | 2021-01-16 | 5 | 2021-01-16 | 5 | 2021-02-04 | 12 | [15 empty] | 2021-01-16 | 2021-01-16 | 0 | 2021-01-16 | 2021-02-16 | 19
120408133 | 72 | PGE | 95148 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 |  | 2021-01-08 |  |  | 2021-01-14 | 2021-01-14 | 4 | 2021-01-14 | 4 | 2021-02-03 | 13 | [15 empty] | 2021-01-14 | 2021-01-14 | 0 | 2021-01-14 | 2021-02-03 | 13 | [13 empty] | 2021-02-03 | 2021-02-09 | 4 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-09 |  | 2021-02-09 | 0
120408782 | 73 | PGE | 94080 | NEM | EXPNEM | IA in Progress | Solar PV | 150 |  | 2021-01-09 |  |  | 2021-01-11 | 2021-01-11 | 0 | 2021-01-13 | 2 | 2021-03-15 | 41 | [15 empty] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | 2021-07-28 | 95 | [5 empty] | 2021-02-23 | 2021-02-23 | 2021-02-23 | 0
120416915 | 74 | PGE | 95687 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 62.048 |  | 2021-01-10 |  | 2021-01-25 | 2021-01-25 | 2021-01-25 | 9 | [29 empty] | 2021-01-10 |  | 2021-01-10
120416916 | 75 | PGE | 95687 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.292 |  | 2021-01-10 |  | 2021-01-25 | 2021-01-25 | 2021-01-25 | 9 | [29 empty] | 2021-01-10 |  | 2021-01-10
120416928 | 76 | PGE | 95687 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 38.78 |  | 2021-01-10 |  | 2021-01-25 | 2021-01-25 | 2021-01-25 | 9 | [29 empty] | 2021-01-10 |  | 2021-01-10
120416929 | 77 | PGE | 95687 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.292 |  | 2021-01-10 |  | 2021-01-25 | 2021-01-25 | 2021-01-25 | 9 | [29 empty] | 2021-01-10 |  | 2021-01-10
120416934 | 79 | PGE | 95687 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 62.048 |  | 2021-01-10 |  | 2021-01-25 | 2021-01-25 | 2021-01-25 | 9 | [29 empty] | 2021-01-10 |  | 2021-01-10
120416970 | 80 | PGE | 95687 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 42.054 |  | 2021-01-10 |  | 2021-01-25 | 2021-01-25 | 2021-01-25 | 9 | [29 empty] | 2021-01-10 |  | 2021-01-10
120416971 | 81 | PGE | 95687 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 35.045 |  | 2021-01-10 |  | 2021-01-25 | 2021-01-25 | 2021-01-25 | 9 | [29 empty] | 2021-01-10 |  | 2021-01-10
120416981 | 82 | PGE | 95687 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.292 |  | 2021-01-10 |  | 2021-01-25 | 2021-01-25 | 2021-01-25 | 9 | [29 empty] | 2021-01-10 |  | 2021-01-10
120418460 | 83 | PGE | 95648 | NEM | EXPNEM | IA in Progress | Solar PV | 32.032 |  | 2021-01-11 |  |  | 2021-01-12 | 2021-01-12 | 1 | 2021-01-12 | 1 | 2021-01-27 | 10 | [15 empty] | 2021-01-27 | 2021-01-27 | 0 | 2021-01-27 | [6 empty] | 2021-01-11 | 2021-01-12 | 2021-01-11 | 2021-01-26 | 10
120418596 | 84 | PGE | 95648 | NEM | EXPNEM | Implementation | Solar PV | 66.6 |  | 2021-01-11 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 1 | 2021-01-19 | 5 | 2021-02-03 | 11 | 2021-02-03 | 2021-03-18 | 30 | 2021-03-23 | 2021-03-25 | 2 | 2021-03-25 |  |  | 2021-03-25 | 2021-06-22 | 62 |  |  |  | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-06-23 | 1 |  |  |  |  | 2021-01-11 | 2021-01-12 | 2021-01-11 | 2021-01-26 | 10
120418631 | 85 | PGE | 95242 | NEM | EXPNEM | Implementation | Solar PV | 40.1 |  | 2021-01-11 |  |  | 2021-01-26 | 2021-01-26 | 10 | 2021-01-26 | 10 | 2021-02-18 | 16 | [15 empty] | 2021-02-16 | 2021-02-16 | 0 | 2021-02-16 | 2021-02-22 | 4 |  |  |  |  | 2021-01-11 | 2021-01-26 | 2021-01-11 | 2021-02-03 | 16 | [7 empty] | 2020-12-11 | 2021-04-03 | 77 |  |  |  | 2021-04-03 | 2021-04-03 | 0
120418656 | 86 | PGE | 95037 | NEM | EXPNEM | Commercial | Solar PV | 37.099 |  | 2021-01-11 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 1 | 2021-03-30 | 54 | 2021-08-09 | 92 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-09-13 | 24 |  |  |  |  | 2021-01-11 | 2021-10-08 | 2021-01-11 | 2021-10-15 | 194 |  |  |  |  | 2021-10-05 | 2021-10-12 | 5 | [15 empty] | 2021-10-05 | 2021-10-05 | 0 | 2021-10-12 |  | 2021-10-19 | 5
120418864 | 87 | PGE | 95648 | NEM | EXPNEM | Implementation | Solar PV | 91.918 |  | 2021-01-11 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 1 | 2021-01-19 | 5 | 2021-02-03 | 11 | 2021-02-03 | 2021-03-18 | 30 | 2021-03-24 | 2021-03-25 | 1 | 2021-03-25 | [8 empty] | 2021-09-15 | 2021-09-21 | 4 | 2021-09-21 | 2021-09-23 | 2 |  |  |  |  | 2021-01-11 | 2021-01-27 | 2021-01-11 | 2021-02-02 | 15
120418897 | 88 | PGE | 95648 | NEM | EXPNEM | Implementation | Solar PV | 55.708 |  | 2021-01-11 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 1 | 2021-01-19 | 5 | 2021-02-02 | 10 | 2021-02-02 | 2021-03-19 | 32 | 2021-03-24 | 2021-03-25 | 1 | 2021-03-25 | [8 empty] | 2021-09-15 | 2021-09-21 | 4 | 2021-09-21 | 2021-09-23 | 2 |  |  |  |  | 2021-01-11 | 2021-01-27 | 2021-01-11 | 2021-02-02 | 15
120418953 | 89 | PGE | 95442 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.409 |  | 2021-01-11 |  |  | 2021-01-16 | 2021-01-16 | 4 | 2021-01-16 | 4 | 2021-02-01 | 9 | [15 empty] | 2021-01-16 | 2021-01-16 | 0 | 2021-01-16 | 2021-01-19 | 0 | [13 empty] | 2021-02-01 | 2021-02-01 | 0 | [15 empty] | 2021-02-01 | 2021-02-01 | 0 | 2021-02-01 |  | 2021-02-01 | 0
120419667 | 90 | PGE | 95448 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.714 |  | 2021-01-11 |  | 2021-02-01 | 2021-01-19 | 2021-01-19 | 5 | 2021-02-05 | 18 | 2021-02-22 | 10 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | 2021-02-08 | 1 | [13 empty] | 2021-02-22 | 2021-03-03 | 7 | [15 empty] | 2021-02-22 | 2021-02-23 | 1 | 2021-03-03 |  | 2021-03-06 | 2
120419685 | 91 | PGE | 95521 | Non-NEM | Non-Export | Implementation | Storage | 280 |  | 2021-01-11 | 2021-01-12 |  | 2021-01-12 | 2021-01-12 | 1 | 2021-02-03 | 16 | 2021-03-01 | 17 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-05-27 | 63 |  |  |  |  | 2021-01-11 |  | 2021-01-11
120419880 | 92 | PGE | 93308 | NEM | NEMMT | Implementation | Solar PV | 663.66 |  | 2021-01-11 |  | 2021-01-26 | 2021-01-26 | 2021-01-26 | 10 | 2021-02-19 | 27 | 2021-03-11 | 14 | 2021-03-11 | 2021-04-08 | 20 | 2021-04-08 | 2021-05-11 | 23 | 2021-05-11 |  |  |  | 2021-08-05 |  |  |  |  | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | 2021-11-03 | 63 |  |  |  |  | 2021-01-11 | 2021-01-26 | 2021-01-11 | 2021-02-03 | 16 | 2021-12-31
120419988 | 93 | PGE | 95210 | NEM | EXPNEM | Commercial | Solar PV | 95.8 |  | 2021-01-11 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 1 | 2021-01-13 | 2 | 2021-01-29 | 11 | [15 empty] | 2021-01-29 | 2021-02-14 | 10 | 2021-02-14 | 2021-02-18 | 2 | [13 empty] | 2021-05-07 | 2021-05-18 | 7 | [15 empty] | 2021-05-07 | 2021-05-10 | 1 | 2021-05-18 |  | 2021-05-21 | 3
120536314 | 94 | PGE | 93308 | NEM | EXPNEM | Implementation | Solar PV | 3858.508 |  | 2021-02-16 | 2021-02-18 |  | 2021-02-17 | 2021-02-17 | 1 | 2021-03-03 | 11 | [5 empty] | 2021-03-04 | 2021-04-07 | 24 | 2021-04-07 | 2021-04-07 | 0 | 2021-05-03 | 2021-07-12 | 48 | 2021-04-07 | 2021-04-08 | 1 | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13 | 2021-08-16 | 24 |  |  |  |  | 2021-02-16 | 2021-03-04 | 2021-02-16 | [12 empty] | 9/1/2021
120484500 | 95 | PGE | 93210 | NEM | EXPNEM | Implementation | Solar PV | 520 |  | 2021-02-01 |  | 2021-02-12 | 2021-02-12 | 2021-02-12 | 9 | 2021-02-25 | 17 | 2021-03-03 | 4 | 2021-03-03 | 2021-03-31 | 20 | [12 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | 2021-06-04 | 46 | [16 empty] | 2021-11-10 | 2021-11-23 | 8
120472984 | 96 | PGE | 93705 | NEM | EXPNEM | Commercial | Solar PV | 31.404 |  | 2021-01-28 |  | 2021-01-28 | 2021-01-28 | 2021-01-28 | 0 | 2021-02-04 | 5 | 2021-02-11 | 5 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-11 | 0 | [13 empty] | 2021-08-23 | 2021-09-02 | 8 | [15 empty] | 2021-08-23 | 2021-08-24 | 1 | 2021-09-02 |  | 2021-09-13 | 6
120454806 | 97 | PGE | 95304 | NEM | EXPNEM | Commercial | Solar PV | 200 |  | 2021-01-21 |  |  | 2021-01-22 | 2021-01-22 | 1 | 2021-01-22 | 1 | 2021-02-12 | 15 | [15 empty] | 2021-02-12 | 2021-02-12 | 0 | 2021-02-12 | 2021-02-17 | 2 | [13 empty] | 2021-06-02 | 2021-06-10 | 6 | [15 empty] | 2021-06-02 | 2021-06-03 | 1 | 2021-06-10 |  | 2021-06-17 | 5
120470690 | 98 | PGE | 95377 | NEM | EXPNEM | Commercial | Solar PV | 250 |  | 2021-01-27 |  | 2021-01-28 | 2021-01-28 | 2021-01-28 | 1 | 2021-01-29 | 2 | 2021-02-14 | 10 | [15 empty] | 2021-02-14 | 2021-02-14 | 0 | 2021-02-14 | 2021-02-18 | 2 | [13 empty] | 2021-08-10 | 2021-08-17 | 5 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-17 |  | 2021-08-24 | 5
120527951 | 99 | PGE | 93611 | NEM | EXPNEM | Commercial | Solar PV | 127.683 |  | 2021-02-11 |  | 2021-02-12 | 2021-02-12 | 2021-02-12 | 1 | 2021-02-16 | 2 | 2021-02-20 | 3 | [15 empty] | 2021-02-20 | 2021-02-20 | 0 | 2021-02-20 | 2021-02-24 | 2 |  |  |  |  | 2021-02-11 |  | 2021-02-11 | [6 empty] | 2021-08-05 | 2021-08-11 | 4 | [15 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-11 |  | 2021-08-18 | 5
120430502 | 100 | PGE | 93727 | NEM | EXPNEM | Commercial | Solar PV, Storage | 94.803 |  | 2021-01-14 |  | 2021-01-19 | 2021-01-15 | 2021-01-15 | 1 | 2021-02-18 | 23 | 2021-03-01 | 7 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-03 | 2 | [13 empty] | 2021-11-22 | 2021-12-02 | 6 | [15 empty] | 2021-11-22 | 2021-11-24 | 2 | 2021-12-02 |  | 2021-12-14 | 8
120496964 | 101 | PGE | 94508 | NEM | EXPNEM | Commercial | Solar PV | 33.06 |  | 2021-02-03 |  |  | 2021-02-04 | 2021-02-04 | 1 | 2021-02-04 | 1 | 2021-02-18 | 9 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-05-26 | 69 | [13 empty] | 2021-07-22 | 2021-07-22 | 0 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 |  | 2021-07-28 | 4
120528102 | 102 | PGE | 95370 | NEM | EXPNEM | Commercial | Solar PV | 63.135 |  | 2021-02-11 |  | 2021-02-12 | 2021-02-12 | 2021-02-12 | 1 | 2021-02-16 | 2 | 2021-03-03 | 11 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-08 | 3 | [13 empty] | 2021-05-12 | 2021-05-19 | 5 | [15 empty] | 2021-05-12 | 2021-05-13 | 1 | 2021-05-19 |  | 2021-05-26 | 5
120551262 | 103 | PGE | 95340 | NEM | EXPNEM | Commercial | Solar PV | 770 |  | 2021-02-18 |  |  | 2021-02-23 | 2021-02-23 | 3 | 2021-02-23 | 3 | 2021-03-01 | 4 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-11 | 8 | [13 empty] | 2021-12-16 | 2021-12-28 | 8 | 2021-05-18 | 2021-08-16 | 62 |  |  |  | 2021-08-16 | 2021-12-08 | 78 | [6 empty] | 2021-12-16 | 2021-12-17 | 1 | 2021-12-28 |  | 2021-12-30 | 2
120500354 | 104 | PGE | 94597 | NEM | EXPNEM | Withdrawn | Solar PV | 31.062 |  | 2021-02-04 |  | 2021-03-01 | 2021-02-16 | 2021-02-16 | 7 | 2021-02-16 | 7 | 2021-03-12 | 18 | [15 empty] | 2021-03-12 | 2021-03-12 | 0 | 2021-03-12 | 2021-03-12 | 0 | [13 empty] | 2021-07-27 | [17 empty] | 2021-07-27 | 2021-07-27 | 0
120475610 | 105 | PGE | 95363 | NEM | EXPNEM | Withdrawn | Solar PV | 316.555 |  | 2021-01-28 |  | 2021-04-26 | 2021-02-03 | 2021-02-03 | 4 | 2021-02-17 | 13 | 2021-03-08 | 13 | [15 empty] | 2021-03-08 | 2021-03-17 | 7 | 2021-03-17 | 2021-03-18 | 1 |  |  |  |  | 2021-01-28 |  | 2021-01-28
120580995 | 106 | PGE | 93648 | NEM | EXPNEM | Commercial | Solar PV | 103.592 |  | 2021-02-26 |  | 2021-03-01 | 2021-03-01 | 2021-03-01 | 1 | 2021-03-04 | 4 | 2021-03-23 | 13 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | 2021-03-24 | 1 |  |  |  |  | 2021-02-26 | 2021-05-17 | 2021-02-26 | 2021-05-28 | 65 |  |  |  |  | 2021-08-13 | 2021-08-20 | 5 | [15 empty] | 2021-08-13 | 2021-08-13 | 0 | 2021-08-20 |  | 2021-08-27 | 5
120531895 | 107 | PGE | 95203 | NEM | EXPNEM | IA in Progress | Solar PV | 40.733 |  | 2021-02-12 |  |  | 2021-02-16 | 2021-02-16 | 1 | 2021-02-16 | 1 | 2021-03-02 | 10 | [15 empty] | 2021-03-02 | 2021-03-03 | 1 | 2021-03-03 | 2021-03-26 | 17 | [16 empty] | 2021-07-06 | 2021-12-07 | 106
120582494 | 108 | PGE | 95492 | NEM | EXPNEM | Withdrawn | Solar PV | 260.887 |  | 2021-02-26 |  | 2021-03-02 | 2021-03-02 | 2021-03-02 | 2 | 2021-03-09 | 7 | 2021-03-29 | 14 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-03-29 | 0 |  |  |  |  | 2021-02-26 |  | 2021-02-26
120430750 | 109 | PGE | 93727 | NEM | EXPNEM | Commercial | Solar PV, Storage | 94.803 |  | 2021-01-14 |  | 2021-02-01 | 2021-01-15 | 2021-01-15 | 1 | 2021-02-01 | 11 | 2021-02-11 | 8 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-16 | 2 |  |  |  |  | 2021-01-14 | 2021-01-15 | 2021-01-14 | 2021-01-28 | 9 |  |  |  |  | 2021-09-21 | 2021-09-29 | 6 | 2021-04-09 | 2021-05-05 | 18 |  |  |  | 2021-05-05 | 2021-05-05 | 0 | [6 empty] | 2021-09-21 | 2021-09-22 | 1 | 2021-09-29 |  | 2021-10-06 | 5
120464628 | 110 | PGE | 95215 | NEM | EXPNEM | IA in Progress | Solar PV | 86.965 |  | 2021-01-26 |  | 2021-01-28 | 2021-01-26 | 2021-01-26 | 0 | 2021-01-28 | 2 | 2021-08-18 | 141 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-02 | 8 |  |  |  |  | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-02-03 | 6 |  |  |  |  | 2021-08-21 | 2021-08-30 | 5 | 2021-05-18 | 2021-11-22 | 130 |  |  |  | 2021-11-12 | 0 | 42 | [6 empty] | 2021-08-21 | 2021-08-23 | 0 | 2021-08-30 | 2021-09-07 |  | 5 |  |  | 156
120449765 | 111 | PGE | 95023 | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-01-20 |  | 2021-02-01 | 2021-01-28 | 2021-01-28 | 6 | 2021-01-29 | 7 | 2021-01-29 | 0 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-01 | 4 |  |  |  |  | 2021-01-20 | 2021-01-29 | 2021-01-20 | 2021-02-05 | 12 |  |  |  |  | 2021-07-19 | 2021-07-23 | 4 | [15 empty] | 2021-07-19 | 2021-07-19 | 0 | 2021-07-23 |  | 2021-07-23 | 0
120428509 | 112 | PGE | 93307 | NEM | EXPNEM | Commercial | Solar PV | 69.6 |  | 2021-01-14 |  |  | 2021-01-28 | 2021-01-28 | 9 | 2021-01-28 | 9 | 2021-02-18 | 14 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-23 | 23 |  |  |  |  | 2021-01-14 | 2021-01-28 | 2021-01-14 | 2021-02-05 | 15 |  |  |  |  | 2021-05-11 | 2021-05-19 | 6 | [15 empty] | 2021-05-11 | 2021-05-12 | 1 | 2021-05-19 |  | 2021-05-19 | 0
120475331 | 113 | PGE | 94806 | NEM | EXPNEM | IA in Progress | Solar PV | 164.17 |  | 2021-01-28 |  | 2021-01-29 | 2021-01-29 | 2021-01-29 | 1 | 2021-02-01 | 2 | 2021-03-15 | 29 | [15 empty] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | [6 empty] | 2021-01-28 | 2021-02-01 | 2021-01-28 | 2021-02-05 | 6
120496624 | 114 | PGE | 95369 | NEM | EXPNEM | Commercial | Solar PV | 185.596 |  | 2021-02-03 |  | 2021-02-08 | 2021-02-04 | 2021-02-04 | 1 | 2021-02-10 | 5 | 2021-02-25 | 10 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-03 | 4 |  |  |  |  | 2021-02-03 | 2021-02-04 | 2021-02-03 | 2021-02-09 | 4 |  |  |  |  | 2021-05-11 | 2021-05-20 | 7 | [15 empty] | 2021-05-11 | 2021-05-12 | 1 | 2021-05-20 |  | 2021-05-27 | 5
120475330 | 115 | PGE | 94566 | NEM | EXPNEM | Application Accepted | Solar PV | 65 |  | 2021-01-28 |  | 2021-03-01 | 2021-02-08 | 2021-02-08 | 7 | 2021-02-08 | 7 | 2021-03-03 | 16 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-04 | 1 |  |  |  |  | 2021-01-28 | 2021-02-08 | 2021-01-28 | 2021-02-09 | 8 | [7 empty] | 2021-07-01 | 2021-10-21 | 78 |  |  |  | 2021-11-16 | 2022-01-11 | 37
120475372 | 116 | PGE | 93625 | NEM | EXPNEM | Implementation | Solar PV | 66.6 |  | 2021-01-28 |  | 2021-04-13 | 2021-02-05 | 2021-02-05 | 6 | 2021-02-10 | 9 | 2021-02-17 | 4 | [15 empty] | 2021-02-17 | 2021-02-17 | 0 | 2021-02-17 | 2021-03-16 | 19 |  |  |  |  | 2021-01-28 | 2021-02-05 | 2021-01-28 | 2021-02-09 | 8 | [7 empty] | 2021-09-20 |  | 80
120496259 | 117 | PGE | 93446 | NEM | EXPNEM | Commercial | Solar PV | 48.582 |  | 2021-02-03 |  | 2021-02-10 | 2021-02-04 | 2021-02-04 | 1 | 2021-02-14 | 7 | 2021-03-05 | 13 | [15 empty] | 2021-03-05 | 2021-03-05 | 0 | 2021-03-05 | 2021-03-09 | 2 |  |  |  |  | 2021-02-03 | 2021-02-14 | 2021-02-03 | 2021-02-16 | 8 |  |  |  |  | 2021-05-06 | 2021-05-17 | 7 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-17 |  | 2021-05-20 | 3
120464575 | 118 | PGE | 95236 | NEM | EXPNEM | IA in Progress | Solar PV | 147.625 |  | 2021-01-26 |  |  | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 0 | 2021-02-11 | 12 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-22 | 6 |  |  |  |  | 2021-01-26 | 2021-02-26 | 2021-01-26 | 2021-03-01 | 23
120462488 | 119 | PGE | 95632 | NEM | EXPNEM | Commercial | Solar PV | 175 |  | 2021-01-25 |  | 2021-01-26 | 2021-01-26 | 2021-01-26 | 1 | 2021-01-28 | 3 | 2021-02-12 | 11 | [15 empty] | 2021-02-12 | 2021-02-12 | 0 | 2021-02-12 | 2021-02-17 | 2 |  |  |  |  | 2021-01-25 | 2021-03-10 | 2021-01-25 | 2021-03-12 | 33 |  |  |  |  | 2021-05-24 | 2021-06-03 | 7 | [15 empty] | 2021-05-24 | 2021-05-26 | 2 | 2021-06-03 |  | 2021-06-09 | 4
120474841 | 120 | PGE | 95650 | NEM | EXPNEM | IA in Progress | Solar PV | 32.77 |  | 2021-01-28 |  | 2021-01-29 | 2021-01-29 | 2021-01-29 | 1 | 2021-02-04 | 5 | 2021-03-04 | 19 | [15 empty] | 2021-03-04 | 2021-03-04 | 0 | 2021-03-04 | 2021-03-11 | 5 |  |  |  |  | 2021-01-29 | 2021-03-15 | 2021-01-29 | 2021-03-17 | 32
120479842 | 121 | PGE | 95301 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-01-29 |  | 2021-02-09 | 2021-02-09 | 2021-02-09 | 7 | 2021-02-10 | 8 | 2021-03-02 | 13 | [15 empty] | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | 2021-03-05 | 3 |  |  |  |  | 2021-01-29 | 2021-04-14 | 2021-01-29 | 2021-04-29 | 63 |  |  |  |  | 2021-05-07 | 2021-05-07 | 0 | [15 empty] | 2021-05-07 | 2021-05-07 | 0 | 2021-05-07 |  | 2021-05-07 | 0
120435037 | 122 | PGE | 93460 | NEM | EXPNEM | Commercial | Solar PV | 47.82 |  | 2021-01-15 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 1 | 2021-01-28 | 8 | 2021-02-02 | 3 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-18 | 11 | [13 empty] | 2021-02-22 | 2021-02-26 | 4 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-26 |  | 2021-03-03 | 3
120428756 | 123 | PGE | 93726 | NEM | EXPNEM | Commercial | Solar PV | 56.866 |  | 2021-01-14 |  | 2021-01-15 | 2021-01-15 | 2021-01-15 | 1 | 2021-01-29 | 10 | 2021-02-11 | 9 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-03-11 | 19 |  |  |  |  | 2021-01-14 | 2021-01-15 | 2021-01-14 | 2021-01-28 | 9 |  |  |  |  | 2021-03-15 | 2021-03-24 | 7 | [15 empty] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-24 |  | 2021-03-25 | 1
120493496 | 124 | PGE | 94577 | NEM | EXPNEM | Commercial | Solar PV | 31.024 |  | 2021-02-02 |  |  | 2021-02-03 | 2021-02-03 | 1 | 2021-02-03 | 1 | 2021-02-26 | 16 | [15 empty] | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-03-15 | 11 | [13 empty] | 2021-03-18 | 2021-03-24 | 4 | [15 empty] | 2021-03-18 | 2021-03-19 | 1 | 2021-03-24 |  | 2021-03-25 | 1
120426374 | 125 | PGE | 95451 | NEM | EXPNEM | Commercial | Solar PV | 68.358 |  | 2021-01-13 |  |  | 2021-01-28 | 2021-01-28 | 10 | 2021-01-28 | 10 | 2021-02-18 | 14 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-10 | 14 | [13 empty] | 2021-03-13 | 2021-03-25 | 8 | [15 empty] | 2021-03-13 | 2021-03-15 | 0 | 2021-03-25 |  | 2021-03-25 | 0
120529039 | 126 | PGE | 95206 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-02-11 |  | 2021-02-25 | 2021-02-16 | 2021-02-16 | 2 | 2021-03-09 | 17 | 2021-03-24 | 11 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-03-26 | 2 |  |  |  |  | 2021-02-17 |  | 2021-02-17 | [6 empty] | 2021-03-29 | 2021-04-02 | 4 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-04-02 |  | 2021-04-05 | 1
120443085 | 128 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 70.479 |  | 2021-01-18 |  | 2021-03-04 | 2021-01-20 | 2021-01-20 | 1 | 2021-03-09 | 34 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-03-31 | 3 |  |  |  |  | 2021-03-02 | 2021-03-09 | 2021-03-02 | 2021-03-12 | 8 |  |  |  |  | 2021-04-02 | 2021-04-12 | 6 | [15 empty] | 2021-04-02 | 2021-04-05 | 1 | 2021-04-12 |  | 2021-04-19 | 5
120430305 | 131 | PGE | 95120 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 33.05 |  | 2021-01-14 |  |  | 2021-01-25 | 2021-01-25 | 6 | 2021-01-25 | 6 | 2021-02-04 | 8 | [15 empty] | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | 2021-02-04 | 8
120527785 | 134 | PGE | 95070 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 40.356 |  | 2021-02-11 |  | 2021-02-22 | 2021-02-22 | 2021-02-22 | 6 | 2021-03-11 | 19 | 2021-03-17 | 4 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-02-26 | 4 | [13 empty] | 2021-08-19 | 2021-08-19 | 0 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 |  | 2021-08-19 | 0
120473401 | 135 | PGE | 95472 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 34.2 |  | 2021-01-28 |  | 2021-02-10 | 2021-02-10 | 2021-02-10 | 9 | 2021-03-17 | 33 | 2021-03-25 | 6 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-21 | 2 | [16 empty] | 2021-06-30 | 2021-11-01 | 86 |  |  |  | 2021-12-27 | 0 | 14
120681589 | 136 | PGE | 94941 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.356 |  | 2021-03-23 |  |  | 2021-04-06 | 2021-04-06 | 10 | 2021-04-06 | 10 | 2021-04-07 | 1 | [15 empty] | 2021-03-23 | 2021-03-23 |  | 2021-03-23 | 2021-03-23 | 1 | [10 empty] | 2021-04-29 | 2021-04-29 | 0 | 2021-07-19 | 2021-07-27 | 6 | [15 empty] | 2021-07-19 | 2021-07-20 | 1 | 2021-07-27 |  | 2021-07-27 | 0
120499344 | 139 | PGE | 93619 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 |  | 2021-02-04 |  | 2021-02-10 | 2021-02-10 | 2021-02-10 | 4 | 2021-04-14 | 48 | 2021-04-23 | 7 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-29 | 24 | [13 empty] | 2021-04-23 | 2021-04-24 | 0 | [15 empty] | 2021-04-23 | 2021-04-24 | 0 | 2021-04-24 |  | 2021-04-27 | 1
120711215 | 140 | PGE | 95691 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.8 |  | 2021-03-30 |  | 2021-04-09 | 2021-04-09 | 2021-04-09 | 8 | 2021-05-21 | 38 | 2021-05-26 | 3 | [15 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-03-30 | 0 | [13 empty] | 2021-05-26 | 2021-05-26 | 0 | [15 empty] | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 |  | 2021-05-27 | 1
120527063 | 141 | PGE | 94062 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 53.626 |  | 2021-02-11 |  | 2021-02-22 | 2021-02-22 | 2021-02-22 | 6 | 2021-03-11 | 19 | 2021-03-22 | 7 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-01 | 5 | [5 empty] | 2021-04-22 | 2021-04-22 | 2021-05-07 | 11 | [7 empty] | 2021-06-10 | 2021-09-13 | 65 |  |  |  | 2021-10-06 | 2021-11-15 | 27
120503943 | 144 | PGE | 94507 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 39.988 |  | 2021-02-05 |  | 2021-02-21 | 2021-02-21 | 2021-02-21 | 9 | 2021-03-16 | 26 | 2021-03-24 | 6 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-16 | 0 |  |  |  |  | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2021-05-28 | 7 |  |  |  |  | 2021-06-15 | 2021-06-25 | 8 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-25 |  | 2021-06-28 | 1
120432706 | 145 | PGE | 94549 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 39.857 |  | 2021-01-15 |  |  | 2021-01-25 | 2021-01-25 | 5 | 2021-01-25 | 5 | 2021-01-26 | 1 | [15 empty] | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | 2021-01-28 | 3 | [13 empty] | 2021-01-28 | 2021-01-28 | 0 | [15 empty] | 2021-01-28 | 2021-01-28 | 0 | 2021-01-28 |  | 2021-01-30 | 1
120237723 | 146 | PGE | 95961 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2020-12-29 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 9 | 2021-01-28 | 20 | 2021-02-02 | 3 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-03 | 1 | [13 empty] | 2021-02-11 | 2021-02-11 | 0 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 |  | 2021-02-17 | 3
120454746 | 147 | PGE | 94949 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 |  | 2021-01-21 |  |  | 2021-02-03 | 2021-02-03 | 9 | 2021-02-03 | 9 | 2021-02-09 | 4 | [15 empty] | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | 2021-02-09 | 0 | [13 empty] | 2021-02-12 | 2021-02-12 | 0 | [15 empty] | 2021-02-12 | 2021-02-12 | 0 | 2021-02-12 |  | 2021-02-17 | 2
120434709 | 148 | PGE | 95070 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-01-15 |  |  | 2021-01-28 | 2021-01-28 | 8 | 2021-01-28 | 8 | 2021-02-08 | 7 | [15 empty] | 2021-01-28 | 2021-01-28 | 0 | 2021-01-28 | 2021-02-08 | 7 | [13 empty] | 2021-02-08 | 2021-02-16 | 5 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-16 |  | 2021-02-17 | 1
120528378 | 150 | PGE | 94556 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-02-11 |  |  | 2021-02-23 | 2021-02-23 | 7 | 2021-02-23 | 7 | 2021-02-26 | 3 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-02-23 | 0 | [13 empty] | 2021-02-26 | 2021-02-28 | 0 | [15 empty] | 2021-02-26 | 2021-02-28 | 0 | 2021-02-28 |  | 2021-03-06 | 5
120537974 | 152 | PGE | 94525 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 |  | 2021-02-16 |  |  | 2021-03-01 | 2021-03-01 | 9 | 2021-03-01 | 9 | 2021-03-02 | 1 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-03 | 2 | [13 empty] | 2021-03-04 | 2021-03-04 | 0 | [15 empty] | 2021-03-04 | 2021-03-04 | 0 | 2021-03-04 |  | 2021-03-06 | 1
120506167 | 153 | PGE | 93422 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 |  | 2021-02-08 |  |  | 2021-02-23 | 2021-02-23 | 10 | 2021-02-23 | 10 | 2021-03-03 | 6 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-02 | 5 | [13 empty] | 2021-03-08 | 2021-03-08 | 0 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 |  | 2021-03-11 | 3
120506404 | 154 | PGE | 93463 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 |  | 2021-02-08 |  |  | 2021-02-23 | 2021-02-23 | 10 | 2021-02-23 | 10 | 2021-03-03 | 6 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-03 | 6 | [13 empty] | 2021-03-08 | 2021-03-08 | 0 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 |  | 2021-03-11 | 3
120552170 | 155 | PGE | 95688 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-02-18 |  |  | 2021-03-03 | 2021-03-03 | 9 | 2021-03-03 | 9 | 2021-03-04 | 1 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-08 | 3 |  |  |  |  | 2021-02-18 | 2021-03-03 | 2021-02-18 | 2021-03-03 | 9 |  |  |  |  | 2021-03-08 | 2021-03-08 | 0 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 |  | 2021-03-13 | 4
120529057 | 157 | PGE | 94010 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.92 |  | 2021-02-11 |  | 2021-02-24 | 2021-02-23 | 2021-02-23 | 7 | 2021-02-25 | 9 | 2021-03-09 | 8 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-02 | 3 | [13 empty] | 2021-03-09 | 2021-03-10 | 1 | [15 empty] | 2021-03-09 | 2021-03-10 | 1 | 2021-03-10 |  | 2021-03-13 | 2
120529081 | 159 | PGE | 94583 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-02-11 |  |  | 2021-02-23 | 2021-02-23 | 7 | 2021-02-23 | 7 | 2021-02-25 | 2 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-08 | 9 | [13 empty] | 2021-03-11 | 2021-03-11 | 0 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 |  | 2021-03-13 | 1
120462758 | 161 | PGE | 95070 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.337 |  | 2021-01-25 |  |  | 2021-02-08 | 2021-02-08 | 10 | 2021-02-08 | 10 | 2021-02-26 | 13 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-03-02 | 15 | [13 empty] | 2021-03-17 | 2021-03-17 | 0 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 |  | 2021-03-19 | 2
120508284 | 162 | PGE | 94558 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.741 |  | 2021-02-08 |  |  | 2021-02-23 | 2021-02-23 | 10 | 2021-02-23 | 10 | 2021-03-01 | 4 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-02 | 5 | [13 empty] | 2021-03-17 | 2021-03-17 | 0 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 |  | 2021-03-19 | 2
120569248 | 163 | PGE | 95110 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-02-23 |  |  | 2021-03-06 | 2021-03-06 | 8 | 2021-03-06 | 8 | 2021-03-08 | 0 | [15 empty] | 2021-03-06 | 2021-03-06 | 0 | 2021-03-06 | 2021-03-23 | 11 | [13 empty] | 2021-03-23 | 2021-03-23 | 0 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 |  | 2021-03-27 | 3
120506268 | 165 | PGE | 94566 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.646 |  | 2021-02-08 |  | 2021-02-16 | 2021-02-16 | 2021-02-16 | 5 | 2021-03-02 | 15 | 2021-03-06 | 3 | [15 empty] | 2021-03-06 | 2021-03-06 | 0 | 2021-03-06 | 2021-03-10 | 2 | [13 empty] | 2021-03-24 | 2021-03-25 | 1 | [15 empty] | 2021-03-24 | 2021-03-25 | 1 | 2021-03-25 |  | 2021-03-30 | 3
120428651 | 166 | PGE | 95973 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.393 |  | 2021-01-14 |  | 2021-01-23 | 2021-01-23 | 2021-01-23 | 5 | 2021-02-25 | 28 | 2021-03-16 | 13 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-16 | 0 | [13 empty] | 2021-03-29 | 2021-03-29 | 0 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 |  | 2021-03-30 | 1
120586339 | 167 | PGE | 94903 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.75 |  | 2021-03-01 |  |  | 2021-03-13 | 2021-03-13 | 9 | 2021-03-13 | 9 | 2021-03-16 | 1 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-29 | 10 | [13 empty] | 2021-03-29 | 2021-03-29 | 0 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 |  | 2021-04-03 | 4
120587077 | 168 | PGE | 94070 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 |  | 2021-03-01 |  | 2021-03-29 | 2021-03-13 | 2021-03-13 | 9 | 2021-03-13 | 9 | 2021-03-23 | 6 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-29 | 10 | [13 empty] | 2021-03-29 | 2021-03-29 | 0 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 |  | 2021-04-03 | 4
120591285 | 170 | PGE | 95370 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 46.533 |  | 2021-03-02 |  | 2021-03-31 | 2021-03-13 | 2021-03-13 | 8 | 2021-03-13 | 8 | 2021-03-24 | 7 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-31 | 12 | [13 empty] | 2021-03-31 | 2021-03-31 | 0 | [15 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 |  | 2021-04-03 | 2
120587295 | 171 | PGE | 93422 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-03-01 |  |  | 2021-03-13 | 2021-03-13 | 9 | 2021-03-13 | 9 | 2021-03-23 | 6 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-29 | 10 | [13 empty] | 2021-03-31 | 2021-04-01 | 1 | [15 empty] | 2021-03-31 | 2021-04-01 | 1 | 2021-04-01 |  | 2021-04-03 | 1
120642909 | 173 | PGE | 94010 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.36 |  | 2021-03-15 |  |  | 2021-03-27 | 2021-03-27 | 9 | 2021-03-27 | 9 | 2021-04-03 | 5 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | 2021-03-30 | 1 | [13 empty] | 2021-04-03 | 2021-04-05 | 0 | [15 empty] | 2021-04-03 | 2021-04-05 | 0 | 2021-04-05 |  | 2021-04-10 | 4
120665466 | 176 | PGE | 94957 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 |  | 2021-03-19 |  |  | 2021-04-02 | 2021-04-02 | 10 | 2021-04-02 | 10 | 2021-04-08 | 4 | [15 empty] | 2021-03-19 | 2021-03-19 |  | 2021-03-19 | 2021-03-19 | 1 | [13 empty] | 2021-04-08 | 2021-04-08 | 0 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 |  | 2021-04-10 | 1
120686618 | 177 | PGE | 94904 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.699 |  | 2021-03-24 |  |  | 2021-04-07 | 2021-04-07 | 10 | 2021-04-07 | 10 | 2021-04-09 | 2 | [15 empty] | 2021-03-24 | 2021-03-24 |  | 2021-03-24 | 2021-03-24 | 1 | [13 empty] | 2021-04-09 | 2021-04-09 | 0 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 |  | 2021-04-10 | 0
120506283 | 178 | PGE | 95765 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-02-08 |  | 2021-02-16 | 2021-02-16 | 2021-02-16 | 5 | 2021-03-17 | 26 | 2021-03-22 | 3 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-03-24 | 2 | [13 empty] | 2021-04-12 | 2021-04-12 | 0 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 |  | 2021-04-13 | 1
120525535 | 179 | PGE | 94010 | NEM | NEMMT | Implementation | FUCE, Storage | 1400 |  | 2021-02-10 |  | 2021-03-07 | 2021-02-22 | 2021-02-22 | 7 | 2021-03-21 | 26 | 2021-04-08 | 13 | 2021-04-08 | 2021-05-06 | 20 | [12 empty] | 2021-05-20 | 2021-06-04 | 10 | 2021-06-04 | 2021-10-08 | 88 | [5 empty] | 2021-03-21 | 2021-03-21 | 2021-03-25 | 3 |  |  |  |  | 2021-12-22 | 2021-12-28 | 4 | 2022-01-13 |  | 1 | [12 empty] | 2021-12-22 | 2021-12-23 | 1 | 2021-12-28 | 2021-12-31 |  | 3 |  |  | 225
120454393 | 180 | PGE | 95422 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-01-21 | 2021-01-25 |  | 2021-01-25 | 2021-01-25 | 2 | 2021-03-03 | 28 | 2021-03-22 | 13 | [15 empty] | 2021-03-22 | 2021-03-23 | 1 | 2021-03-23 | 2021-07-09 | 76 |  |  |  |  | 2021-01-21 | 2021-03-23 | 2021-01-21 | 2021-04-02 | 50
120632092 | 181 | PGE | 95476 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 46.538 |  | 2021-03-10 |  |  | 2021-03-24 | 2021-03-24 | 10 | 2021-03-24 | 10 | 2021-04-12 | 13 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-03-30 | 4 | [9 empty] | 2021-03-24 | 2021-03-24 | 2021-03-24 | 0 | 2021-06-07 | 2021-06-15 | 6 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-15 |  | 2021-06-15 | 0
120555694 | 182 | PGE | 94103 | Non-NEM | Continuous Uncompensated Export | Withdrawn | Solar PV | 625 |  | 2021-02-19 | 2021-02-22 |  | 2021-02-22 | 2021-02-22 | 1 | 2021-02-24 | 3 | 2021-03-15 | 13 | [15 empty] | 2021-03-15 | 2021-03-31 | 12 | 2021-03-31 | [11 empty] | 2021-03-31
120659150 | 184 | PGE | 94588 | NEM | EXPNEM | Implementation | Solar PV | 783.3 |  | 2021-03-18 |  | 2021-04-01 | 2021-04-01 | 2021-04-01 | 10 | 2021-05-28 | 51 | 2021-07-29 | 42 | [15 empty] | 2021-07-29 | 2021-07-29 | 0 | 2021-07-29 | 2021-09-07 | 27 |  |  |  |  | 2021-03-18 | 2021-06-04 | 2021-03-18 | 2021-06-16 | 63
120659151 | 185 | PGE | 94588 | NEM | EXPNEM | Implementation | Solar PV | 333.2 |  | 2021-03-18 |  | 2021-04-01 | 2021-04-01 | 2021-04-01 | 10 | 2021-05-06 | 35 | 2021-07-09 | 44 | [15 empty] | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09 | 2021-09-07 | 41 |  |  |  |  | 2021-03-18 | 2021-06-04 | 2021-03-18 | 2021-06-16 | 63
120673552 | 186 | PGE | 95415 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 109.804 |  | 2021-03-22 |  | 2021-06-11 | 2021-04-01 | 2021-04-01 | 8 | 2021-09-07 | 118 | 2021-11-12 | 47 | [15 empty] | 2021-11-12 | 2021-11-23 | 7 | 2021-11-23 | 2021-11-23 | 0 | [16 empty] | 2021-07-16 | 2021-11-18 | 87
120693209 | 187 | PGE | 94601 | NEM | EXPNEM | IA in Progress | Solar PV | 98.136 |  | 2021-03-25 |  | 2021-09-29 | 2021-04-05 | 2021-04-05 | 7 | 2021-10-15 | 143 | 2021-10-19 | 2 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19
120708558 | 188 | PGE | 94954 | NEM | EXPNEM | Implementation | Solar PV | 240 |  | 2021-03-29 |  | 2021-05-14 | 2021-04-06 | 2021-04-06 | 6 | 2021-05-10 | 30 | 2021-07-16 | 47 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-16 | 2021-08-12 | 19 |  |  |  |  | 2021-03-29 | 2021-08-03 | 2021-03-29 | 2021-08-13 | 97
120698495 | 189 | PGE | 93622 | NEM | EXPNEM | Implementation | Solar PV | 830 |  | 2021-03-26 |  | 2021-07-21 | 2021-04-07 | 2021-04-07 | 8 | 2021-08-04 | 91 | 2021-08-24 | 14 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | 2021-10-11 | 33
120717219 | 190 | PGE | 95928 | NEM | EXPNEM | Commercial | Solar PV | 36.913 |  | 2021-03-31 |  | 2021-07-09 | 2021-04-07 | 2021-04-07 | 5 | 2021-07-07 | 68 | 2021-07-26 | 13 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-07-27 | 1 |  |  |  |  | 2021-03-31 | 2021-07-12 | 2021-03-31 | 2021-07-23 | 80 |  |  |  |  | 2021-07-27 | 2021-08-02 | 4 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-08-02 |  | 2021-08-02 | 0
120720930 | 191 | PGE | 94611 | NEM | EXPNEM | Application Review in Progress | Solar PV | 150.795 |  | 2021-03-31 |  | 2021-04-12 | 2021-04-12 | 2021-04-12 | 8
120433597 | 192 | PGE | 94577 | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-01-15 |  | 2021-07-13 | 2021-01-19 | 2021-01-19 | 1 | 2021-07-29 | 135 | 2021-09-07 | 27 | [15 empty] | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 | 2021-09-15 | 4 | [5 empty] | 2021-08-09 | 2021-08-09 | 2021-08-19 | 8 |  |  |  |  | 2021-10-22 | 2021-12-03 | 27 | [15 empty] | 2021-10-22 | 2021-12-02 | 26 | 2021-12-03 |  | 2021-12-09 | 4
120445426 | 193 | PGE | 95370 | NEM | EXPNEM | Application Review in Progress | Solar PV | 35.713 |  | 2021-01-19 |  | 2021-01-20 | 2021-01-20 | 2021-01-20 | 1
120458867 | 194 | PGE | 95982 | NEM | EXPNEM | Application Review in Progress | Solar PV | 343.39 |  | 2021-01-22 |  | 2021-05-11 | 2021-01-25 | 2021-01-25 | 1 | [29 empty] | 2021-01-22 |  | 2021-01-22
120460496 | 195 | PGE | 93933 | NEM | EXPNEM | Withdrawn | Solar PV | 86.4 |  | 2021-01-24 |  | 2021-07-17 | 2021-01-26 | 2021-01-26 | 1 | 2021-07-23 | 126 | 2021-10-11 | 55 | [15 empty] | 2021-10-11 | 2021-10-11 | 0 | 2021-10-11 | [6 empty] | 2021-01-24 |  | 2021-01-24
120446515 | 196 | PGE | 95945 | NEM | EXPNEM | Withdrawn | Solar PV | 32.88 |  | 2021-01-19 |  | 2021-02-09 | 2021-01-26 | 2021-01-26 | 5 | 2021-02-19 | 22 | 2021-05-04 | 52 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | 2021-06-17 | 31
120468691 | 197 | PGE | 93309 | NEM | EXPNEM | Commercial | Solar PV | 43.128 |  | 2021-01-27 |  | 2021-04-15 | 2021-01-27 | 2021-01-27 | 0 | 2021-04-19 | 57 | 2021-04-27 | 6 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-09-01 | 3 |  |  |  |  | 2021-01-27 | 2021-05-14 | 2021-01-27 | 2021-05-28 | 86 |  |  |  |  | 2021-09-23 | 2021-09-30 | 5 | [15 empty] | 2021-09-23 | 2021-09-24 | 1 | 2021-09-30 |  | 2021-10-01 | 1
120475484 | 199 | PGE | 93721 | NEM | EXPNEM | Application Review in Progress | Solar PV | 52.78 |  | 2021-01-28 |  | 2021-01-29 | 2021-01-29 | 2021-01-29 | 1
120433179 | 200 | PGE | 95694 | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-01-15 |  | 2021-02-02 | 2021-02-01 | 2021-02-01 | 10 | 2021-11-29 | 218 | 2021-12-13 | 10 | [15 empty] | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13 | 2021-12-14 | 1 | [5 empty] | 2021-12-13 | 2021-12-13 | 2021-12-13 | 0
120496525 | 201 | PGE | 95963 | NEM | EXPNEM | Commercial | Solar PV | 30.277 |  | 2021-02-03 |  | 2021-02-04 | 2021-02-04 | 2021-02-04 | 1 | 2021-06-03 | 84 | 2021-06-18 | 11 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-18 | 2021-06-21 | 1 | [13 empty] | 2021-07-12 | 2021-07-12 | 0 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 |  | 2021-07-12 | 0
120500796 | 202 | PGE | 95020 | NEM | EXPNEM | Withdrawn | Solar PV | 299.7 |  | 2021-02-04 |  | 2021-02-05 | 2021-02-05 | 2021-02-05 | 1 | [29 empty] | 2021-02-04 |  | 2021-02-04
120503280 | 203 | PGE | 95002 | NEM | EXPNEM | Application Review in Progress | Solar PV | 44.198 |  | 2021-02-05 |  | 2021-02-08 | 2021-02-08 | 2021-02-08 | 1
120474956 | 204 | PGE | 95602 | NEM | EXPNEM | Implementation | Solar PV | 37.009 |  | 2021-01-28 |  | 2021-04-14 | 2021-02-09 | 2021-02-09 | 8 | 2021-04-21 | 58 | 2021-04-26 | 3 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-05-14 | 14 |  |  |  |  | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2021-05-28 | 7 |  |  |  |  | 2021-06-24 | 2021-06-30 | 4 | 2021-06-30 | 2021-11-02 | 87 | [12 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-30 | 2021-07-07 |  | 4 |  |  | 111
120511110 | 205 | PGE | 94539 | NEM | EXPNEM | IA in Progress | Solar PV | 114.365 |  | 2021-02-09 |  | 2021-08-09 | 2021-02-10 | 2021-02-10 | 1 | 2021-08-13 | 130 | 2021-08-24 | 7 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24
120486196 | 206 | PGE | 93612 | NEM | EXPNEM | Implementation | Solar PV | 36.312 |  | 2021-02-01 |  | 2021-02-11 | 2021-02-10 | 2021-02-10 | 7 | 2021-08-17 | 138 | 2021-08-30 | 9 | [15 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-09-01 | 2 |  |  |  |  | 2021-02-01 | 2021-08-17 | 2021-02-01 | 2021-09-02 | 150 |  |  |  |  | 2021-12-06 | [17 empty] | 2021-12-06 | 2021-12-07 | 1
120536259 | 207 | PGE | 95957 | NEM | EXPNEM | Commercial | Solar PV | 36 |  | 2021-02-16 |  | 2021-06-05 | 2021-02-17 | 2021-02-17 | 1 | 2021-06-09 | 80 | 2021-06-17 | 6 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-12-06 | 117 |  |  |  |  | 2021-02-16 | 2021-06-05 | 2021-02-16 | 2021-06-16 | 85 |  |  |  |  | 2021-12-08 | 2021-12-22 | 10 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-22 |  | 2021-12-27 | 3
120500854 | 208 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 187.5 |  | 2021-02-04 |  | 2021-04-16 | 2021-02-17 | 2021-02-17 | 8 | 2021-04-21 | 53 | 2021-05-27 | 26 | [15 empty] | 2021-05-27 | 2021-06-09 | 8 | 2021-06-09 | 2021-06-09 | 0 |  |  |  |  | 2021-02-04 | 2021-04-20 | 2021-02-04 | 2021-05-07 | 65 |  |  |  |  | 2021-06-10 | 2021-06-17 | 5 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-17 |  | 2021-06-17 | 0
120534633 | 209 | PGE | 93306 | NEM | EXPNEM | Commercial | Solar PV | 341.862 |  | 2021-02-15 |  | 2021-04-16 | 2021-02-18 | 2021-02-18 | 2 | 2021-04-30 | 53 | 2021-05-16 | 10 | 2021-05-16 | 2021-06-14 | 19 | [12 empty] | 2021-06-14 | 2021-06-14 | 0 | 2021-06-14 | 2021-08-30 | 54 |  |  |  |  | 2021-02-15 | 2021-04-30 | 2021-02-15 | 2021-05-10 | 59 |  |  |  |  | 2021-10-06 | 2021-10-28 | 16 | [15 empty] | 2021-10-06 | 2021-10-06 | 0 | 2021-10-28 |  | 2021-11-02 | 3
120570852 | 210 | PGE | 93706 | NEM | EXPNEM | IA in Progress | Solar PV | 38.779 |  | 2021-02-23 |  | 2021-11-19 | 2021-02-24 | 2021-02-24 | 1 | 2021-11-26 | 192 | 2021-12-14 | 11 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2021-12-15 | 1 |  |  |  |  | 2021-08-18 |  | 2021-08-18
120572497 | 211 | PGE | 93725 | NEM | EXPNEM | Commercial | Solar PV | 60 |  | 2021-02-24 |  | 2021-03-31 | 2021-02-25 | 2021-02-25 | 1 | 2021-06-10 | 75 | 2021-06-17 | 5 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-09-23 | 68 | [13 empty] | 2021-11-16 | 2021-11-23 | 5 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-23 |  | 2021-12-02 | 5
120531156 | 212 | PGE | 94608 | NEM | EXPNEM | Application Review in Progress | Solar PV | 395.208 |  | 2021-02-12 |  | 2021-03-04 | 2021-02-27 | 2021-02-27 | 9 | [29 empty] | 2021-02-12 |  | 2021-02-12
120534902 | 213 | PGE | 95340 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-02-15 |  | 2021-03-01 | 2021-03-01 | 2021-03-01 | 9 | 2021-05-03 | 54 | 2021-05-24 | 15 | [15 empty] | 2021-05-24 | 2021-06-10 | 12 | 2021-06-10 | 2021-06-25 | 11 | [5 empty] | 2021-05-24 | 2021-05-24 | 2021-06-03 | 7 | 2021-08-13 |  |  |  | 2021-08-31 | 2021-09-01 | 1 | [15 empty] | 2021-08-31 | 2021-09-01 | 1 | 2021-09-01 |  | 2021-09-02 | 1
120537256 | 214 | PGE | 95932 | NEM | EXPNEM | Implementation | Solar PV | 240 |  | 2021-02-16 |  | 2021-03-02 | 2021-03-02 | 2021-03-02 | 10 | 2021-05-04 | 55 | [5 empty] | 2021-05-04 | 2021-06-16 | 30 | 2021-06-16 |  |  |  | 2021-08-31 |  |  |  |  | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 | 2021-09-07 | 4 |  |  |  |  | 2021-02-16 |  | 2021-02-16 | [9 empty] | 2021-09-27 | 2021-12-29 | 63
120587464 | 215 | PGE | 93612 | NEM | EXPNEM | IA in Progress | Solar PV | 268.003 |  | 2021-03-01 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 3 | 2021-05-11 | 51 | 2021-06-16 | 25 | [15 empty] | 2021-06-16 | 2021-06-17 | 1 | 2021-06-17 | 2021-06-17 | 0 | [16 empty] | 2021-07-26 | 2022-01-07 | 114
120574009 | 216 | PGE | 95449 | NEM | EXPNEM | Implementation | ENGN, OTHR | 79.788 |  | 2021-02-24 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 7 | 2021-04-21 | 40 | 2021-10-21 | 128 | [15 empty] | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21 | 2021-11-03 | 9 |  |  |  |  | 2021-04-20 | 2021-04-21 | 2021-04-20 | 2021-05-07 | 13 | [7 empty] | 2021-11-29 |  | 33
120605545 | 217 | PGE | 95240 | NEM | EXPNEM | Application Review in Progress | Solar PV | 60.455 |  | 2021-03-05 |  | 2021-03-08 | 2021-03-08 | 2021-03-08 | 1
120569058 | 218 | PGE | 93706 | NEM | EXPNEM | Implementation | Solar PV | 336 |  | 2021-02-23 |  | 2021-04-30 | 2021-03-08 | 2021-03-08 | 9 | 2021-05-12 | 56 | 2021-05-25 | 9 | [15 empty] | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-07-06 | 28 | [9 empty] | 2021-06-16 | [6 empty] | 2021-09-01 | 2021-09-13 | 7 |  |  |  | 2021-09-22 | 0 | 78
120568229 | 219 | PGE | 95920 | NEM | EXPNEM | Withdrawn | Solar PV | 50.848 |  | 2021-02-23 |  | 2021-03-09 | 2021-03-09 | 2021-03-09 | 10 | 2021-04-27 | 45 | 2021-05-24 | 19 | 2021-05-24 | 2021-06-28 | 24 | 2021-06-28 | 2021-07-22 | 17 | 2021-07-22 | 2021-08-04 | 9 |  |  |  | 2021-08-04 | [12 empty] | 2021-02-23 |  | 2021-02-23
120567150 | 220 | PGE | 93314 | NEM | EXPNEM | Implementation | Solar PV | 540 |  | 2021-02-23 |  | 2021-04-27 | 2021-03-09 | 2021-03-09 | 10 | 2021-05-03 | 49 | 2021-05-20 | 13 | 2021-05-24 | 2021-06-30 | 26 | 2021-07-12 | 2021-08-09 | 20 | 2021-08-09 |  |  |  | 2021-11-09 |  |  |  |  | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | 2021-11-24 | 10
120612481 | 221 | PGE | 94043 | NEM | EXPNEM | Application Review in Progress | Solar PV | 65.56 |  | 2021-03-08 |  | 2021-03-10 | 2021-03-10 | 2021-03-10 | 2 | [29 empty] | 2021-03-08 |  | 2021-03-08
120608662 | 222 | PGE | 95629 | NEM | EXPNEM | IA in Progress | Solar PV | 47.56 |  | 2021-03-05 |  | 2021-05-20 | 2021-03-10 | 2021-03-10 | 3 | 2021-06-09 | 67 | 2021-06-17 | 6 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17
120618014 | 224 | PGE | 94133 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-03-09 |  | 2021-03-29 | 2021-03-11 | 2021-03-11 | 2 | 2021-04-15 | 27 | 2021-09-14 | 105 | [15 empty] | 2021-09-14 | 2021-09-14 | 0 | 2021-09-14 | 2021-10-08 | 18 | [13 empty] | 2021-10-18 | 2021-10-27 | 7 | [15 empty] | 2021-10-18 | 2021-10-18 | 0 | 2021-10-27 |  | 2021-11-01 | 3
120628386 | 225 | PGE | 94085 | NEM | EXPNEM | Application Review in Progress | Solar PV | 323.042 |  | 2021-03-10 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 2 | [29 empty] | 2021-03-10 |  | 2021-03-10
120581661 | 226 | PGE | 93454 | NEM | EXPNEM | Commercial | Solar PV | 84.418 |  | 2021-02-26 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 10 | 2021-05-07 | 50 | 2021-07-14 | 46 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-16 | 2 | [5 empty] | 2021-07-02 | 2021-07-02 | 2021-07-12 | 5 |  |  |  |  | 2021-07-16 | 2021-07-22 | 4 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-22 |  | 2021-07-22 | 0
120586983 | 227 | PGE | 95901 | NEM | EXPNEM | Implementation | Solar PV | 460 |  | 2021-03-01 |  | 2021-03-13 | 2021-03-13 | 2021-03-13 | 9 | 2021-05-06 | 48 | 2021-06-07 | 21 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-06-08 | 1 |  |  |  |  | 2021-03-01 |  | 2021-03-01 | [9 empty] | 2021-08-16 | 2021-10-11 | 39 |  |  |  | 2021-12-10 | 0 | 24
120636153 | 228 | PGE | 94089 | NEM | EXPNEM | Commercial | Solar PV | 33.411 |  | 2021-03-11 |  | 2021-05-17 | 2021-03-15 | 2021-03-15 | 2 | 2021-05-19 | 49 | 2021-06-07 | 12 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-06-11 | 4 | [13 empty] | 2021-07-15 | 2021-07-20 | 3 | [15 empty] | 2021-07-15 | 2021-07-16 | 1 | 2021-07-20 |  | 2021-07-27 | 5
120637984 | 229 | PGE | 95131 | NEM | EXPNEM | Application Review in Progress | Solar PV | 92.316 |  | 2021-03-12 |  | 2021-03-24 | 2021-03-16 | 2021-03-16 | 2 | [29 empty] | 2021-03-12 |  | 2021-03-12
120599986 | 230 | PGE | 93706 | NEM | EXPNEM | Commercial | Solar PV | 287.5 |  | 2021-03-03 |  | 2021-03-17 | 2021-03-17 | 2021-03-17 | 10 | 2021-04-20 | 34 | 2021-05-10 | 14 | [15 empty] | 2021-05-10 | 2021-05-17 | 5 | 2021-05-17 | 2021-05-17 | 0 |  |  |  |  | 2021-03-03 | 2021-04-20 | 2021-03-03 | 2021-05-05 | 45 |  |  |  |  | 2021-10-27 | 2021-11-01 | 3 | 2021-07-26 | 2021-08-31 | 26 |  |  |  | 2021-09-13 | 2021-10-23 | 30 | [6 empty] | 2021-10-27 | 2021-10-28 | 1 | 2021-11-01 |  | 2021-11-02 | 1
120640163 | 232 | PGE | 95776 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-03-12 |  | 2021-10-28 | 2021-03-17 | 2021-03-17 | 3 | 2021-11-08 | 168 | 2021-11-22 | 9 | [15 empty] | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22 | 2021-12-20 | 18 |  |  |  |  | 2021-03-12 |  | 2021-03-12 | [6 empty] | 2021-12-29 | [17 empty] | 2021-12-29 | 2021-12-29 | 0
120638036 | 233 | PGE | 93940 | NEM | EXPNEM | Commercial | Solar PV | 42.802 |  | 2021-03-12 |  | 2021-07-14 | 2021-03-17 | 2021-03-17 | 3 | 2021-07-20 | 90 | 2021-08-02 | 9 | [15 empty] | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | 2021-08-12 | 8 | [13 empty] | 2021-08-19 | 2021-08-26 | 5 | [15 empty] | 2021-08-19 | 2021-08-20 | 1 | 2021-08-26 |  | 2021-09-10 | 10
120637987 | 234 | PGE | 95131 | NEM | EXPNEM | Application Review in Progress | Solar PV | 55.546 |  | 2021-03-12 |  | 2021-04-16 | 2021-03-17 | 2021-03-17 | 3 | [29 empty] | 2021-03-12 |  | 2021-03-12
120651436 | 235 | PGE | 93306 | NEM | EXPNEM | IA in Progress | Solar PV | 548.77 |  | 2021-03-17 |  | 2021-03-18 | 2021-03-18 | 2021-03-18 | 1 | 2021-04-15 | 21 | 2021-06-04 | 35 | [15 empty] | 2021-06-04 | 2021-06-04 | 0 | 2021-06-04 | 2021-06-18 | 10 |  |  |  |  | 2021-03-17 |  | 2021-03-17
120642515 | 236 | PGE | 95035 | NEM | EXPNEM | IA in Progress | Solar PV | 531.086 |  | 2021-03-14 |  | 2021-05-26 | 2021-03-18 | 2021-03-18 | 3 | 2021-06-03 | 57 | 2021-07-09 | 25 | [15 empty] | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12
120651457 | 237 | PGE | 93305 | NEM | EXPNEM | Withdrawn | Solar PV | 500 |  | 2021-03-17 |  | 2021-03-18 | 2021-03-18 | 2021-03-18 | 1 | [29 empty] | 2021-03-17 |  | 2021-03-17
120603645 | 238 | PGE | 95032 | NEM | EXPNEM | Implementation | Solar PV | 335.644 |  | 2021-03-04 |  | 2021-03-18 | 2021-03-18 | 2021-03-18 | 10 | 2021-05-03 | 42 | 2021-06-21 | 34 | 2021-06-21 | 2021-08-09 | 34 | [12 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-24 | 11 |  |  |  |  | 2021-03-04 |  | 2021-03-04
120651376 | 239 | PGE | 95776 | NEM | EXPNEM | Application Review in Progress | Solar PV | 136.1 |  | 2021-03-17 |  | 2021-03-18 | 2021-03-18 | 2021-03-18 | 1 | [29 empty] | 2021-03-17 |  | 2021-03-17
120608844 | 240 | PGE | 95020 | NEM | EXPNEM | Implementation | Solar PV | 299.7 |  | 2021-03-05 |  | 2021-03-19 | 2021-03-19 | 2021-03-19 | 10 | 2021-06-16 | 72 | 2021-07-26 | 27 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-07-27 | 1 |  |  |  |  | 2021-03-05 | 2021-04-11 | 2021-03-05 | 2021-05-03 | 41
120608539 | 241 | PGE | 95365 | NEM | EXPNEM | Withdrawn | Solar PV | 187.5 |  | 2021-03-05 |  | 2021-03-19 | 2021-03-19 | 2021-03-19 | 10 | 2021-08-12 | 112 | 2021-09-02 | 15 | [15 empty] | 2021-09-02 | 2021-09-03 | 1 | 2021-09-03 | [6 empty] | 2021-03-05 | 2021-08-12 | 2021-03-05 | 2021-08-24 | 120
120651931 | 243 | PGE | 94063 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-03-17 |  | 2021-03-25 | 2021-03-19 | 2021-03-19 | 2 | 2021-05-13 | 41 | 2021-06-03 | 14 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-14 | 7 | [5 empty] | 2021-06-24 | 2021-06-24 | 2021-07-09 | 10 |  |  |  |  | 2021-08-09 | 2021-08-12 | 3 | 2021-09-29 | 2021-10-01 | 2 |  |  |  | 2021-10-19 | 2021-11-05 | 13 | [6 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-12 |  | 2021-08-19 | 5
120653625 | 244 | PGE | 93446 | NEM | EXPNEM | Commercial | Solar PV | 33.128 |  | 2021-03-17 |  | 2021-04-13 | 2021-03-19 | 2021-03-19 | 2 | 2021-04-20 | 24 | 2021-07-06 | 53 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-07-27 | 15 | [13 empty] | 2021-08-04 | 2021-08-12 | 6 | [15 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-12 |  | 2021-08-16 | 2
120654327 | 245 | PGE | 93906 | NEM | EXPNEM | IA in Progress | Solar PV | 351.986 |  | 2021-03-17 |  | 2021-04-14 | 2021-03-19 | 2021-03-19 | 2 | 2021-05-05 | 35 | 2021-07-02 | 41 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | [6 empty] | 2021-04-12 |  | 2021-04-12
120660151 | 246 | PGE | 95616 | NEM | EXPNEM | IA in Progress | Solar PV | 396.286 |  | 2021-03-18 |  | 2021-04-20 | 2021-03-22 | 2021-03-22 | 2 | 2021-04-27 | 28 | 2021-05-20 | 17 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | [6 empty] | 2021-03-18 | 2021-11-22 | 2021-03-18 | 2021-11-22 | 173
120658536 | 247 | PGE | 93631 | NEM | EXPNEM | IA in Progress | Solar PV | 780 |  | 2021-03-18 |  | 2021-04-14 | 2021-03-22 | 2021-03-22 | 2 | 2021-04-16 | 21 | 2021-05-12 | 18 | 2021-05-12 | 2021-06-01 | 13 | [12 empty] | 2021-06-01 | 2021-06-01 | 0 | 2021-06-01 | [6 empty] | 2021-03-18 | 2021-04-14 | 2021-03-18 | 2021-05-07 | 36
120617479 | 248 | PGE | 95320 | NEM | EXPNEM | Implementation | Solar PV | 150 |  | 2021-03-09 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 10 | 2021-06-21 | 73 | 2021-07-07 | 11 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | 2021-07-09 | 2 |  |  |  |  | 2021-03-09 | 2021-06-21 | 2021-03-09 | 2021-07-08 | 85 | [7 empty] | 2021-09-30 |  | 72
120668012 | 249 | PGE | 93940 | NEM | EXPNEM | Withdrawn | Solar PV | 43.78 |  | 2021-03-20 |  | 2021-07-14 | 2021-03-23 | 2021-03-23 | 1 | 2021-07-21 | 85 | 2021-10-29 | 71 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29
120673323 | 250 | PGE | 94587 | NEM | EXPNEM | IA in Progress | Solar PV | 200 |  | 2021-03-22 |  | 2021-03-24 | 2021-03-24 | 2021-03-24 | 2 | 2021-05-05 | 32 | 2021-07-09 | 45 | [15 empty] | 2021-07-09 | 2021-07-10 | 0 | 2021-07-10 | 2021-08-19 | 28 | [5 empty] | 2021-09-21 | 2021-09-21 | 2021-09-23 | 2
120677457 | 251 | PGE | 94587 | NEM | EXPNEM | IA in Progress | Solar PV | 181.876 |  | 2021-03-23 |  | 2021-03-24 | 2021-03-24 | 2021-03-24 | 1 | 2021-06-07 | 53 | 2021-07-30 | 38 | [15 empty] | 2021-07-30 | 2021-07-30 | 0 | 2021-07-30 | 2021-08-19 | 14 |  |  |  |  | 2021-07-16 | 2021-08-21 | 2021-07-16 | 2021-09-07 | 36
120677481 | 252 | PGE | 94085 | NEM | EXPNEM | Commercial | Solar PV | 83.3 |  | 2021-03-23 |  | 2021-05-03 | 2021-03-24 | 2021-03-24 | 1 | 2021-05-18 | 40 | 2021-06-07 | 13 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-06-11 | 4 | [5 empty] | 2021-06-18 | 2021-06-18 | 2021-07-02 | 10 |  |  |  |  | 2021-09-30 | 2021-10-07 | 5 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-10-07 |  | 2021-10-14 | 5
120674435 | 253 | PGE | 94804 | NEM | EXPNEM | IA in Progress | Solar PV | 183.3 |  | 2021-03-22 |  | 2021-03-31 | 2021-03-24 | 2021-03-24 | 2 | 2021-05-03 | 30 | 2021-06-01 | 20 | [15 empty] | 2021-06-01 | 2021-06-07 | 4 | 2021-06-07 | 2021-07-21 | 31 |  |  |  |  | 2021-03-22 | 2021-09-22 | 2021-03-22 | 2021-09-22 | 129 | [7 empty] | 2021-07-20 | 2021-11-08 | 78
120640079 | 254 | PGE | 93280 | NEM | EXPNEM | Application Review in Progress | Solar PV | 168 |  | 2021-03-12 |  | 2021-03-25 | 2021-03-25 | 2021-03-25 | 9
120681063 | 255 | PGE | 94558 | NEM | EXPNEM | Application Review in Progress | Solar PV | 46.08 |  | 2021-03-23 |  | 2021-09-17 | 2021-03-25 | 2021-03-25 | 2 | [29 empty] | 2021-03-23 |  | 2021-03-23
120680849 | 256 | PGE | 94568 | NEM | EXPNEM | Commercial | Solar PV | 323.852 |  | 2021-03-23 |  | 2021-03-30 | 2021-03-25 | 2021-03-25 | 2 | 2021-04-20 | 20 | 2021-06-30 | 50 | [15 empty] | 2021-06-30 | 2021-07-07 | 4 | 2021-07-07 | 2021-07-08 | 1 | [13 empty] | 2021-10-15 | 2021-10-21 | 4 | [15 empty] | 2021-10-15 | 2021-10-15 | 0 | 2021-10-21 |  | 2021-10-28 | 5
120685714 | 257 | PGE | 93311 | NEM | EXPNEM | IA in Progress | Solar PV | 121.259 |  | 2021-03-24 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2 | 2021-04-28 | 25 | 2021-05-11 | 9 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | [6 empty] | 2021-03-24 | 2021-07-15 | 2021-03-24 | 2021-07-19 | 81
120645642 | 259 | PGE | 93726 | NEM | EXPNEM | Implementation | Solar PV | 86.4 |  | 2021-03-15 |  | 2021-03-29 | 2021-03-29 | 2021-03-29 | 10 | 2021-05-07 | 39 | 2021-05-18 | 7 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | 2021-11-10 | 123 |  |  |  |  | 2021-03-15 |  | 2021-03-15
120677981 | 260 | PGE | 93930 | NEM | EXPNEM | Commercial | Solar PV | 47.304 |  | 2021-03-23 |  | 2021-05-13 | 2021-03-29 | 2021-03-29 | 4 | 2021-05-14 | 38 | 2021-06-02 | 12 | [15 empty] | 2021-06-02 | 2021-06-07 | 3 | 2021-06-07 | 2021-06-08 | 1 | [9 empty] | 2021-06-17 |  |  |  | 2021-06-18 | 2021-06-29 | 7 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-29 |  | 2021-06-30 | 1
120653330 | 262 | PGE | 95492 | NEM | EXPNEM | Withdrawn | Solar PV | 506.226 |  | 2021-03-17 |  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 10 | [29 empty] | 2021-03-17 |  | 2021-03-17
120652016 | 263 | PGE | 93212 | NEM | EXPNEM | Implementation | Solar PV | 516 |  | 2021-03-17 |  | 2021-04-01 | 2021-03-31 | 2021-03-31 | 10 | 2021-05-27 | 51 | 2021-06-17 | 14 | 2021-06-17 | 2021-07-16 | 20 | [12 empty] | 2021-07-16 | 2021-08-19 | 24 | 2021-08-19 | 2021-08-27 | 6 |  |  |  |  | 2021-05-04 | 2021-05-10 | 2021-05-04 | 2021-05-26 | 16
120713658 | 266 | PGE | 94022 | NEM | EXPNEM | Commercial | Solar PV | 114.669 |  | 2021-03-30 |  | 2021-04-14 | 2021-03-31 | 2021-03-31 | 1 | 2021-04-22 | 17 | 2021-06-18 | 40 | [15 empty] | 2021-06-18 | 2021-06-21 | 1 | 2021-06-21 | 2021-08-12 | 37 | [5 empty] | 2021-05-27 | 2021-05-27 | 2021-06-07 | 6 |  |  |  |  | 2021-09-03 | 2021-09-15 | 7 | [15 empty] | 2021-09-03 | 2021-09-07 | 1 | 2021-09-15 |  | 2021-09-24 | 7
120419686 | 267 | PGE | 94804 | NEM | EXPNEM | Withdrawn | Solar PV | 124.183 |  | 2021-01-11 |  | 2021-01-26 | 2021-01-14 | 2021-01-14 | 3 | 2021-01-28 | 12
120420143 | 268 | PGE | 94804 | NEM | EXPNEM | Withdrawn | Solar PV | 92.482 |  | 2021-01-11 |  | 2021-01-27 | 2021-01-14 | 2021-01-14 | 3 | 2021-01-28 | 12
120420187 | 269 | PGE | 94804 | NEM | EXPNEM | Withdrawn | Solar PV | 88.073 |  | 2021-01-11 |  | 2021-01-26 | 2021-01-20 | 2021-01-20 | 6 | 2021-01-28 | 12
120529179 | 270 | PGE | 94545 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-02-11 |  | 2021-02-12 | 2021-02-12 | 2021-02-12 | 1 | 2021-02-16 | 2 | 2021-05-11 | 60 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2021-05-20 | 7 | [13 empty] | 2021-08-18 | 2021-08-26 | 6 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-26 |  | 2021-08-30 | 2
120465673 | 271 | PGE | 93206 | NEM | EXPNEM | Commercial | Solar PV | 875 |  | 2021-01-26 |  | 2021-02-08 | 2021-02-08 | 2021-02-08 | 9 | 2021-02-19 | 17 | [5 empty] | 2021-02-08 | 2021-03-10 | 21 | 2021-03-10 |  |  | 2021-03-10 | 2021-06-10 | 65 |  |  |  | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-08-20 | 50 |  |  |  |  | 2021-01-26 | 2021-09-14 | 2021-01-26 | 2021-09-21 | 166 | 2021-02-10 |  |  |  | 2021-12-08 | 2021-12-20 | 8 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-20 |  | 2021-12-22 | 2
120582876 | 272 | PGE | 93627 | NEM | EXPNEM | Implementation | Solar PV | 900 |  | 2021-02-26 |  | 2021-03-02 | 2021-03-02 | 2021-03-02 | 2 | 2021-03-09 | 7 | [5 empty] | 2021-03-09 | 2021-04-02 | 18 | 2021-04-02 |  |  | 2021-04-02 | 2021-06-08 | 46 |  |  |  | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-07-12 | 23
120602200 | 273 | PGE | 93465 | NEM | EXPNEM | Commercial | Solar PV | 65.59 |  | 2021-03-04 |  | 2021-03-10 | 2021-03-08 | 2021-03-08 | 2 | 2021-03-12 | 6 | 2021-04-30 | 35 | [15 empty] | 2021-04-30 | 2021-05-03 | 1 | 2021-05-03 | 2021-12-14 | 155 | [13 empty] | 2021-12-14 | 2021-12-29 | 11 | [15 empty] | 2021-12-14 | 2021-12-15 | 1 | 2021-12-29 |  | 2021-12-30 | 1
120617291 | 274 | PGE | 95965 | NEM | EXPNEM | IA in Progress | Solar PV | 360.183 |  | 2021-03-09 |  | 2021-03-11 | 2021-03-11 | 2021-03-11 | 2 | 2021-03-15 | 4 | 2021-04-23 | 29 | [15 empty] | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | 2021-05-11 | 12 |  |  |  |  | 2021-03-09 | 2021-12-14 | 2021-03-09 | [6 empty] | 2021-11-21 | [17 empty] | 2021-11-21 | 2021-11-22 | 0
120477924 | 275 | PGE | 94583 | NEM | EXPNEM | Implementation | Solar PV | 587.5 |  | 2021-01-29 |  | 2021-01-29 | 2021-01-29 | 2021-01-29 | 0 | 2021-03-18 | 33 | 2021-05-18 | 43 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | 2021-09-23 | 89 |  |  |  |  | 2021-01-29 |  | 2021-01-29
120566066 | 276 | PGE | 95540 | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-02-22 |  | 2021-03-22 | 2021-02-24 | 2021-02-24 | 2 | 2021-03-24 | 22 | 2021-04-28 | 25 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-10-06 | 112
120593233 | 277 | PGE | 94080 | Non-NEM | Break Before Make | Commercial | ENGN | 3500 |  | 2021-03-02 | 2021-03-15 |  | 2021-03-05 | 2021-03-05 | 3 | 2021-03-24 | 16 | [5 empty] | 2021-03-24 | 2021-04-20 | 19 | 2021-04-20
120653009 | 278 | PGE | 94521 | NEM | EXPNEM | IA in Progress | Solar PV | 37.186 |  | 2021-03-17 |  | 2021-03-19 | 2021-03-19 | 2021-03-19 | 2 | 2021-03-24 | 5 | 2021-05-24 | 43 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24
120552303 | 279 | PGE | 93206 | NEM | EXPNEM | Implementation | Solar PV | 480 |  | 2021-02-18 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 10 | 2021-03-26 | 26 | 2021-04-15 | 14 | 2021-04-15 | 2021-05-20 | 25 | 2021-06-03 | 2021-06-28 | 17 | 2021-06-28 |  |  |  | 2021-07-26 |  |  |  |  | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-08-19 | 18 | [16 empty] | 2021-10-18 | 2021-12-23 | 45
120553257 | 280 | PGE | 93203 | NEM | EXPNEM | Implementation | Solar PV | 85.358 |  | 2021-02-18 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 10 | 2021-03-26 | 26 | 2021-04-16 | 15 | [15 empty] | 2021-04-16 | 2021-04-23 | 5 | 2021-04-23 | 2021-06-02 | 27
120685085 | 281 | PGE | 93301 | NEM | EXPNEM | IA in Progress | Solar PV | 348 |  | 2021-03-24 |  |  | 2021-03-26 | 2021-03-26 | 2 | 2021-03-26 | 2 | 2021-06-19 | 59 | [15 empty] | 2021-06-19 | 2021-06-19 | 0 | 2021-06-19 | [6 empty] | 2021-03-24 | 2021-11-17 | 2021-03-24 | 2021-12-08 | 179
120639109 | 282 | PGE | 95987 | NEM | EXPNEM | Implementation | Solar PV | 125 |  | 2021-03-12 |  |  | 2021-03-26 | 2021-03-26 | 10 | 2021-03-26 | 10 | 2021-06-16 | 57 | 2021-06-24 | 2021-07-21 | 18 | 2021-07-21 | 2021-08-18 | 20 | 2021-08-18 |  |  |  | 2021-11-09 |  |  |  |  | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | 2021-11-10 | 1 | [16 empty] | 2021-12-13 |  | 23
120498232 | 283 | PGE | 94583 | NEM | EXPNEM | Implementation | Solar PV | 687.5 |  | 2021-02-03 |  | 2021-02-04 | 2021-02-04 | 2021-02-04 | 1 | 2021-03-27 | 36 | 2021-05-18 | 36 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | 2021-09-23 | 89 |  |  |  |  | 2021-02-03 |  | 2021-02-03
120498193 | 284 | PGE | 94583 | NEM | EXPNEM | Implementation | Solar PV | 337.5 |  | 2021-02-03 |  | 2021-02-04 | 2021-02-04 | 2021-02-04 | 1 | 2021-03-27 | 36 | 2021-04-16 | 14 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | 2021-09-23 | 111 |  |  |  |  | 2021-02-03 |  | 2021-02-03
120653902 | 285 | PGE | 96013 | NEM | EXPNEM | Commercial | Solar PV | 37.598 |  | 2021-03-17 |  | 2021-03-25 | 2021-03-19 | 2021-03-19 | 2 | 2021-03-29 | 8 | 2021-04-22 | 18 | [15 empty] | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 | 2021-04-26 | 2 | [13 empty] | 2021-06-12 | 2021-06-18 | 4 | [15 empty] | 2021-06-12 | 2021-06-14 | 0 | 2021-06-18 |  | 2021-06-25 | 5
120640481 | 287 | PGE | 94804 | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-03-12 |  | 2021-03-17 | 2021-03-17 | 2021-03-17 | 3 | 2021-03-30 | 12 | 2021-05-10 | 29 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | [6 empty] | 2021-03-12 |  | 2021-03-12
120707801 | 288 | PGE | 94952 | NEM | EXPNEM | IA in Progress | Solar PV | 110 |  | 2021-03-29 |  |  | 2021-03-30 | 2021-03-30 | 1 | 2021-03-30 | 1 | 2021-04-16 | 13 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | [6 empty] | 2021-03-29 | 2021-05-11 | 2021-03-29 | 2021-05-26 | 42
120709190 | 289 | PGE | 94901 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-03-29 |  |  | 2021-03-30 | 2021-03-30 | 1 | 2021-03-30 | 1 | 2021-11-24 | 167 | [15 empty] | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 2021-11-28 | 0 | [5 empty] | 2021-04-12 | 2021-04-12 | 2021-04-29 | 13
120686200 | 290 | PGE | 93306 | NEM | EXPNEM | IA in Progress | Solar PV | 236.419 |  | 2021-03-24 |  | 2021-03-30 | 2021-03-30 | 2021-03-30 | 4 | 2021-03-30 | 4 | 2021-04-16 | 13 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | [6 empty] | 2021-03-24 |  | 2021-03-24
120553000 | 291 | PGE | 94561 | NEM | EXPNEM | Commercial | Solar PV | 52.108 |  | 2021-02-18 |  | 2021-03-30 | 2021-02-19 | 2021-02-19 | 1 | 2021-03-31 | 29 | 2021-04-16 | 12 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | 2021-07-02 | 54 | [13 empty] | 2021-07-13 | 2021-07-21 | 6 | [15 empty] | 2021-07-13 | 2021-07-13 | 0 | 2021-07-21 |  | 2021-07-28 | 5
120636357 | 292 | PGE | 93210 | NEM | EXPNEM | Implementation | Solar PV | 1250 |  | 2021-03-11 | 2021-03-15 | 2021-03-31 | 2021-03-12 | 2021-03-12 | 1 | 2021-03-31 | 14 | [5 empty] | 2021-03-31 | 2021-04-14 | 10 | 2021-04-14 | 2021-04-19 | 3 | 2021-04-21 | 2021-06-23 | 44 | 2021-04-19 | 2021-04-19 | 0 | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12 | 2021-09-08 | 41 |  |  |  |  | 2021-03-11 |  | 2021-03-11
120640522 | 293 | PGE | 94804 | NEM | EXPNEM | Withdrawn | Solar PV | 1125 |  | 2021-03-12 | 2021-03-15 |  | 2021-03-15 | 2021-03-15 | 1 | 2021-03-31 | 13 | 2021-04-16 | 12 | [25 empty] | 2021-03-12 |  | 2021-03-12
120651424 | 294 | PGE | 95991 | NEM | EXPNEM | Implementation | Solar PV | 275 |  | 2021-03-17 |  | 2021-04-15 | 2021-03-31 | 2021-03-31 | 10 | 2021-03-31 | 10 | 2021-04-16 | 12 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-11-23 | 128
120651437 | 295 | PGE | 93305 | NEM | EXPNEM | IA in Progress | Solar PV | 500 |  | 2021-03-17 |  | 2021-03-18 | 2021-03-18 | 2021-03-18 | 1 | 2021-04-01 | 11 | 2021-04-19 | 12 | 2021-04-19 | 2021-05-26 | 27 | 2021-06-24 | 2021-07-23 | 20 | 2021-07-23 |  |  |  | 2021-10-21 |  |  |  |  | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21 | [6 empty] | 2021-03-17 |  | 2021-03-17
120708334 | 296 | PGE | 93640 | NEM | EXPNEM | Implementation | Solar PV | 1937.5 |  | 2021-03-29 | 2021-03-31 |  | 2021-03-31 | 2021-03-31 | 2 | 2021-04-07 | 7 | 2021-05-28 | 37 | 2021-06-09 | 2021-07-08 | 20 | [12 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-12 | 2 |  |  |  |  | 2021-03-29 | 2021-04-21 | 2021-03-29 | 2021-05-07 | 29 | [7 empty] | 2022-01-12 |  | 2
120687625 | 297 | PGE | 93309 | NEM | EXPNEM | Implementation | Solar PV | 445.259 |  | 2021-03-24 |  |  | 2021-04-05 | 2021-04-05 | 8 | 2021-04-07 | 10 | 2021-04-27 | 14 | [15 empty] | 2021-04-27 | 2021-04-27 | 0 | 2021-04-27 | 2021-05-14 | 13 |  |  |  |  | 2021-03-24 | 2021-05-14 | 2021-03-24 | 2021-05-28 | 47 | [7 empty] | 2021-06-08 | 2021-10-21 | 95 |  |  |  | 2021-11-01 | 0 | 50
120698999 | 298 | PGE | 93301 | NEM | EXPNEM | Implementation | Solar PV | 492.045 |  | 2021-03-26 |  |  | 2021-04-06 | 2021-04-06 | 7 | 2021-04-07 | 8 | 2021-04-20 | 9 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-05-19 | 21 |  |  |  |  | 2021-03-26 | 2021-12-10 | 2021-03-26 | [9 empty] | 2021-06-08 | 2021-10-04 | 82 |  |  |  | 2021-10-26 | 0 | 54
120634278 | 299 | PGE | 95969 | NEM | EXPNEM | Commercial | Solar PV | 35.045 |  | 2021-03-11 |  | 2021-03-15 | 2021-03-15 | 2021-03-15 | 2 | 2021-04-08 | 20 | 2021-04-22 | 10 | [15 empty] | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 | 2021-05-05 | 9 |  |  |  |  | 2021-03-11 | 2021-04-12 | 2021-03-11 | 2021-04-29 | 35 |  |  |  |  | 2021-06-18 | 2021-06-24 | 4 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-24 |  | 2021-07-01 | 5
120704197 | 301 | PGE | 93434 | NEM | EXPNEM | IA in Progress | Solar PV | 114.285 |  | 2021-03-28 |  | 2021-03-30 | 2021-03-30 | 2021-03-30 | 1 | 2021-04-09 | 9 | 2021-04-21 | 8 | [15 empty] | 2021-04-21 | 2021-04-21 | 0 | 2021-04-21 | [6 empty] | 2021-03-28 | 2021-04-09 | 2021-03-28 | 2021-04-16 | 14
120528893 | 302 | PGE | 94063 | NEM | EXPNEM | Commercial | Solar PV | 114.667 |  | 2021-02-11 |  | 2021-03-31 | 2021-03-01 | 2021-03-01 | 11 | 2021-04-11 | 40 | 2021-05-07 | 19 | [15 empty] | 2021-05-07 | 2021-05-07 | 0 | 2021-05-07 | 2021-05-07 | 0 |  |  |  |  | 2021-02-11 |  | 2021-02-11 |  |  | 2021-05-04 | 2021-05-20 | 2021-05-20 | 12 | 2021-12-21 | 2021-12-28 | 5 | [15 empty] | 2021-12-21 | 2021-12-21 | 0 | 2021-12-28 |  | 2021-12-29 | 1
120691918 | 304 | PGE | 93446 | NEM | EXPNEM | Commercial | Solar PV | 200 |  | 2021-03-25 |  | 2021-04-09 | 2021-03-26 | 2021-03-26 | 1 | 2021-04-13 | 13 | 2021-05-03 | 14 | [15 empty] | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | 2021-11-05 | 131 | [13 empty] | 2021-11-09 | 2021-11-17 | 5 | [15 empty] | 2021-11-09 | 2021-11-09 | 0 | 2021-11-17 |  | 2021-11-22 | 3
120434315 | 305 | PGE | 94086 | NEM | EXPNEM | Commercial | Solar PV | 368.528 |  | 2021-01-15 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 1 | 2021-03-12 | 38 | 2021-06-03 | 58 | [15 empty] | 2021-06-03 | 2021-06-14 | 7 | 2021-06-14 | 2021-08-09 | 39 | [13 empty] | 2021-08-12 | 2021-08-18 | 4 | [15 empty] | 2021-08-12 | 2021-08-12 | 0 | 2021-08-18 |  | 2021-08-19 | 1
120536517 | 306 | PGE | 93308 | NEM | EXPNEM | IA in Progress | Solar PV | 100.548 |  | 2021-02-16 |  | 2021-02-17 | 2021-02-17 | 2021-02-17 | 1 | 2021-03-08 | 14 | 2021-03-22 | 10 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-07-06 | 49 |  |  |  |  | 2021-02-16 | 2021-05-18 | 2021-02-16 | 2021-05-28 | 73
120618122 | 307 | PGE | 93727 | NEM | EXPNEM | Commercial | Solar PV | 36.513 |  | 2021-03-09 |  |  | 2021-03-23 | 2021-03-23 | 10 | 2021-03-23 | 10 | 2021-04-09 | 13 | [15 empty] | 2021-04-09 | 2021-06-28 | 55 | 2021-06-28 | 2021-07-19 | 14 | [13 empty] | 2021-08-10 | 2021-08-17 | 5 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-17 |  | 2021-08-18 | 1
120603169 | 308 | PGE | 94928 | NEM | EXPNEM | Implementation | Solar PV | 1700 |  | 2021-03-04 | 2021-03-08 |  | 2021-03-08 | 2021-03-08 | 2 | 2021-03-24 | 14 | 2021-04-12 | 13 | 2021-05-10 | 2021-06-08 | 20 | [12 empty] | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-08-24 | 54 |  |  |  |  | 2021-04-06 | 2021-06-09 | 2021-04-06 | 2021-07-09 | 66 | [10 empty] | 9/1/2021 | 2021-10-28 | 42
120567198 | 309 | PGE | 95032 | NEM | EXPNEM | IA in Progress | Solar PV | 216 |  | 2021-02-23 |  | 2021-02-24 | 2021-02-24 | 2021-02-24 | 1 | 2021-02-25 | 2 | 2021-03-18 | 15 | 2021-03-18 | 2021-04-29 | 30 | [12 empty] | 2021-04-29 | 2021-04-29 | 0 | 2021-04-29 | [6 empty] | 2021-02-23 |  | 2021-02-23
120464204 | 310 | PGE | 95928 | NEM | EXPNEM | Study in Progress | Solar PV | 62.5 |  | 2021-01-26 |  | 2021-02-05 | 2021-01-26 | 2021-01-26 | 0 | 2021-02-02 | 5 | 2021-03-19 | 32 | 2021-03-19 | 2021-04-16 | 20 | 2021-04-16 | 2021-06-29 | 51 | 2021-06-29 | 2021-07-19 | 13 |  |  |  | 2021-07-19 | [12 empty] | 2020-02-04 | 2021-08-18 | 2020-02-04 | 2021-09-09 | 404
120587079 | 311 | PGE | 95032 | NEM | EXPNEM | IA in Progress | Solar PV | 160 |  | 2021-03-01 |  |  | 2021-03-02 | 2021-03-02 | 1 | 2021-03-02 | 1 | 2021-03-19 | 13 | 2021-03-19 | 2021-05-06 | 34 | 2021-07-09 | 2021-08-05 | 19 | 2021-08-05 |  |  |  | 2021-11-22 | [14 empty] | 2021-03-01 |  | 2021-03-01
120555916 | 312 | PGE | 95963 | NEM | EXPNEM | IA in Progress | Solar PV | 156 |  | 2021-02-19 |  | 2021-03-04 | 2021-02-22 | 2021-02-22 | 1 | 2021-03-09 | 12 | 2021-03-31 | 16 | 2021-03-31 | 2021-04-29 | 21 | 2021-05-05 | 2021-07-02 | 41 | 2021-07-02 |  |  |  | 2021-09-28 |  |  |  |  | 2021-09-28 | 2021-09-28 | 0 | 2021-09-28
120574886 | 313 | PGE | 93618 | NEM | EXPNEM | IA in Progress | Solar PV | 828.528 |  | 2021-02-24 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 7 | 2021-03-16 | 14 | 2021-04-02 | 13 | 2021-04-02 | 2021-04-16 | 10 | [12 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16
120528364 | 314 | PGE | 93630 | NEM | EXPNEM | Commercial | Solar PV | 133.2 |  | 2021-02-11 |  | 2021-02-24 | 2021-02-24 | 2021-02-24 | 8 | 2021-03-12 | 20 | 2021-03-26 | 10 | [15 empty] | 2021-03-26 | 2021-04-29 | 24 | 2021-04-29 | 2021-06-30 | 43 |  |  |  |  | 2021-02-11 | 2021-06-30 | 2021-02-11 | 2021-07-12 | 104 |  |  |  |  | 2021-08-23 | 2021-09-01 | 7 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-09-01 |  | 2021-09-02 | 1
120421368 | 315 | PGE | 95242 | NEM | EXPNEM | Commercial | Solar PV | 31.461 |  | 2021-01-12 |  | 2021-01-15 | 2021-01-13 | 2021-01-13 | 1 | 2021-01-19 | 4 | 2021-02-02 | 10 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-11-18 | 202 | [13 empty] | 2021-11-22 | 2021-11-30 | 4 | [15 empty] | 2021-11-22 | 2021-11-22 | 0 | 2021-11-30 |  | 2021-12-03 | 3
120433880 | 316 | PGE | 95950 | NEM | EXPNEM | Commercial | Solar PV | 132 |  | 2021-01-15 |  |  | 2021-01-19 | 2021-01-19 | 1 | 2021-01-19 | 1 | 2021-02-03 | 11 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-07-02 | 105 | [13 empty] | 2021-07-12 | 2021-07-20 | 6 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-20 |  | 2021-07-27 | 5
120420030 | 317 | PGE | 94804 | NEM | EXPNEM | Withdrawn | Solar PV | 146.8 |  | 2021-01-11 |  | 2021-01-26 | 2021-01-20 | 2021-01-20 | 6 | 2021-01-28 | 12 | 2021-02-05 | 6 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05
120419882 | 318 | PGE | 94804 | NEM | EXPNEM | Withdrawn | Solar PV | 153.25 |  | 2021-01-11 |  | 2021-02-02 | 2021-01-14 | 2021-01-14 | 3 | 2021-02-02 | 15 | 2021-02-05 | 3 | [15 empty] | 2021-02-05 | 2021-02-08 | 1 | 2021-02-08
120430865 | 320 | PGE | 95227 | NEM | EXPNEM | Commercial | Solar PV | 71.771 |  | 2021-01-14 |  |  | 2021-01-29 | 2021-01-29 | 10 | 2021-01-29 | 10 | 2021-02-19 | 14 | [15 empty] | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | 2021-05-20 | 64 | [5 empty] | 2021-11-17 | 2021-11-17 | 2021-11-17 | 0 |  |  |  |  | 2021-12-01 | 2021-12-08 | 5 | [15 empty] | 2021-12-01 | 2021-12-02 | 1 | 2021-12-08 |  | 2021-12-15 | 5
120457754 | 321 | PGE | 95126 | NEM | EXPNEM | Withdrawn | Solar PV | 30.159 |  | 2021-01-22 |  | 2021-02-19 | 2021-01-30 | 2021-01-30 | 5 | 2021-01-30 | 5 | 2021-02-19 | 13 | [15 empty] | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | 2021-08-25 | 131
120434090 | 322 | PGE | 95334 | NEM | EXPNEM | Commercial | Solar PV | 125 |  | 2021-01-15 |  |  | 2021-02-01 | 2021-02-01 | 10 | 2021-02-01 | 10 | 2021-02-22 | 14 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-08-09 | 118 |  |  |  |  | 2021-01-15 | 2021-07-20 | 2021-01-15 | 2021-07-29 | 135 |  |  |  |  | 2021-08-27 | 2021-09-02 | 4 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-09-02 |  | 2021-09-07 | 2
120497739 | 323 | PGE | 95076 | NEM | EXPNEM | Implementation | Solar PV | 85.795 |  | 2021-02-03 |  | 2021-02-17 | 2021-02-17 | 2021-02-17 | 9 | 2021-02-23 | 13 | 2021-03-01 | 4 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-12-02 | 192 | [13 empty] | 2021-12-16 | 2021-12-30 | 10 | 2019-08-26 | 2020-04-02 | 150 |  |  |  | 2021-01-19 | 2021-03-16 | 39 | [6 empty] | 2021-12-16 | 2021-12-16 | 0 | 2021-12-30
120528538 | 324 | PGE | 93630 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-02-11 |  | 2021-02-17 | 2021-02-12 | 2021-02-12 | 1 | 2021-02-18 | 4 | 2021-03-02 | 8 | [15 empty] | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | 2021-08-24 | 123 |  |  |  |  | 2021-02-11 | 2021-07-15 | 2021-02-11 | 2021-07-15 | 107 |  |  |  |  | 2021-09-08 | 2021-09-14 | 4 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-14 |  | 2021-09-29 | 11
120464733 | 325 | PGE | 95403 | NEM | EXPNEM | IA in Progress | Solar PV | 72.381 |  | 2021-01-26 |  |  | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 0 | 2021-03-03 | 25 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-05-24 | 58 |  |  |  |  | 2021-01-26 | 2021-04-27 | 2021-01-26 | 2021-05-10 | 73
120424651 | 326 | PGE | 93925 | NEM | EXPNEM | Commercial | Solar PV | 84.718 |  | 2021-01-13 |  | 2021-02-13 | 2021-01-28 | 2021-01-28 | 10 | 2021-02-13 | 21 | 2021-03-07 | 14 | [15 empty] | 2021-03-07 | 2021-03-07 | 0 | 2021-03-07 | 2021-05-24 | 55 |  |  |  |  | 2021-01-13 | 2021-11-01 | 2021-01-13 | 2021-11-17 | 214 |  |  |  |  | 2021-12-13 | 2021-12-23 | 8 | [15 empty] | 2021-12-13 | 2021-12-14 | 1 | 2021-12-23 |  | 2021-12-29 | 4
120434647 | 327 | PGE | 94063 | NEM | EXPNEM | Commercial | Solar PV | 540 |  | 2021-01-15 |  | 2021-01-24 | 2021-01-24 | 2021-01-24 | 4 | 2021-01-24 | 4 | 2021-03-08 | 29 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-04-16 | 29 |  |  |  |  | 2021-01-15 | 2021-04-15 | 2021-01-15 | 2021-05-05 | 76 |  |  |  |  | 2021-12-09 | 2021-12-20 | 7 | 2021-06-03 | 2021-06-03 | 0 |  |  |  | 2021-06-03 | 2021-06-03 | 0 | [6 empty] | 2021-12-09 | 2021-12-09 | 0 | 2021-12-20 |  | 2021-12-22 | 2
120565258 | 328 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 90.375 |  | 2021-02-22 |  | 2021-02-23 | 2021-02-23 | 2021-02-23 | 1 | 2021-02-26 | 4 | 2021-03-08 | 6 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-07-12 | 88 |  |  |  |  | 2021-02-22 | 2021-04-14 | 2021-02-22 | 2021-05-07 | 54 |  |  |  |  | 2021-07-16 | 2021-07-23 | 5 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-23 |  | 2021-07-29 | 4
120565772 | 329 | PGE | 95220 | NEM | EXPNEM | Commercial | Solar PV | 46.382 |  | 2021-02-22 |  | 2021-02-24 | 2021-02-24 | 2021-02-24 | 2 | 2021-02-26 | 4 | 2021-03-08 | 6 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-05-18 | 51 | [13 empty] | 2021-05-26 | 2021-06-03 | 5 | [15 empty] | 2021-05-26 | 2021-05-26 | 0 | 2021-06-03 |  | 2021-06-10 | 5
120501148 | 330 | PGE | 93721 | NEM | EXPNEM | Implementation | Solar PV | 187.5 |  | 2021-02-04 |  | 2021-02-18 | 2021-02-16 | 2021-02-16 | 7 | 2021-02-16 | 7 | 2021-02-19 | 3 | [15 empty] | 2021-02-19 | 2021-03-09 | 12 | 2021-03-09 | 2021-05-07 | 43 |  |  |  |  | 2021-02-04 | 2021-08-26 | 2021-02-04 | 2021-09-08 | 150 |  |  |  |  | 2021-12-23 | [17 empty] | 2021-12-23 | 2021-12-24 | 1
120572856 | 331 | PGE | 94928 | NEM | EXPNEM | Commercial | Solar PV | 43.741 |  | 2021-02-24 |  | 2021-02-25 | 2021-02-25 | 2021-02-25 | 1 | 2021-03-01 | 3 | 2021-03-18 | 13 | [15 empty] | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18 | 2021-04-20 | 23 | [13 empty] | 2021-04-27 | 2021-05-06 | 7 | [15 empty] | 2021-04-27 | 2021-04-29 | 2 | 2021-05-06 |  | 2021-05-07 | 1
120512571 | 332 | PGE | 95020 | NEM | EXPNEM | Withdrawn | Solar PV | 280.516 |  | 2021-02-09 |  | 2021-02-10 | 2021-02-10 | 2021-02-10 | 1 | 2021-03-02 | 14 | 2021-03-19 | 13 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | [6 empty] | 2021-02-09 |  | 2021-02-09
120543065 | 333 | PGE | 95112 | NEM | EXPNEM | IA in Progress | Solar PV | 32.109 |  | 2021-02-18 |  | 2021-02-19 | 2021-02-19 | 2021-02-19 | 1 | 2021-03-02 | 8 | 2021-03-19 | 13 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19
120536258 | 334 | PGE | 95321 | NEM | EXPNEM | IA in Progress | Solar PV | 166.5 |  | 2021-02-16 |  |  | 2021-03-02 | 2021-03-02 | 10 | 2021-03-02 | 10 | 2021-03-19 | 13 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19
120578478 | 335 | PGE | 95229 | NEM | EXPNEM | Commercial | Solar PV | 54.148 |  | 2021-02-25 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 1 | 2021-03-03 | 4 | 2021-03-22 | 13 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-04-24 | 24 |  |  |  |  | 2021-02-25 |  | 2021-02-25 | [6 empty] | 2021-04-27 | 2021-06-03 | 26 | [15 empty] | 2021-04-27 | 2021-04-27 | 0 | 2021-06-03 |  | 2021-06-08 | 3
120592230 | 336 | PGE | 94043 | NEM | EXPNEM | Commercial | Solar PV | 136 |  | 2021-03-02 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2 | 2021-03-04 | 2 | 2021-03-22 | 12 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-06-03 | 52 | [13 empty] | 2021-11-09 | 2021-11-19 | 7 | [15 empty] | 2021-11-09 | 2021-11-09 | 0 | 2021-11-19 |  | 2021-11-24 | 3
120591296 | 337 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-02 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2 | 2021-03-10 | 6 | 2021-03-24 | 10 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-04-21 | 20 | [13 empty] | 2021-08-17 | 2021-08-24 | 5 | [15 empty] | 2021-08-17 | 2021-08-17 | 0 | 2021-08-24 |  | 2021-08-30 | 4
120582604 | 338 | PGE | 95060 | NEM | EXPNEM | Commercial | Solar PV | 65.159 |  | 2021-02-26 |  | 2021-03-05 | 2021-03-02 | 2021-03-02 | 2 | 2021-03-12 | 10 | 2021-03-24 | 8 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-04-26 | 23 | [13 empty] | 2021-04-28 | 2021-05-11 | 9 | [15 empty] | 2021-04-28 | 2021-04-29 | 1 | 2021-05-11 |  | 2021-05-18 | 5
120491801 | 339 | PGE | 95945 | NEM | EXPNEM | Commercial | Solar PV | 45.6 |  | 2021-02-02 |  | 2021-02-16 | 2021-02-11 | 2021-02-11 | 7 | 2021-02-11 | 7 | 2021-03-25 | 29 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-06-16 | 58 | [13 empty] | 2021-08-16 | 2021-12-02 | 74 | [15 empty] | 2021-08-16 | 2021-08-17 | 1 | 2021-08-27 | 2021-08-30 | 2021-12-02 | 3 |  |  | 146
120591959 | 340 | PGE | 94043 | NEM | EXPNEM | Commercial | Solar PV | 74.396 |  | 2021-03-02 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2 | 2021-03-08 | 4 | 2021-03-25 | 13 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-06-21 | 61 | [13 empty] | 2021-10-22 | 2021-11-10 | 13 | [15 empty] | 2021-10-22 | 2021-10-22 | 0 | 2021-11-10 |  | 2021-11-16 | 3
120478306 | 341 | PGE | 93212 | NEM | EXPNEM | Implementation | Solar PV | 480 |  | 2021-01-29 |  |  | 2021-02-12 | 2021-02-12 | 10 | 2021-02-24 | 17 | 2021-02-26 | 2 | 2021-02-26 | 2021-03-25 | 19 | [12 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-04-15 | 15 | [16 empty] | 2021-06-08 | 2021-06-18 | 8
120591298 | 342 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-02 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2 | 2021-03-09 | 5 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-08-19 | 102 | [13 empty] | 2021-08-21 | 2021-09-01 | 7 | [15 empty] | 2021-08-21 | 2021-08-24 | 1 | 2021-09-01 |  | 2021-09-09 | 5
120591365 | 343 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-02 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2 | 2021-03-09 | 5 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-21 | 18 | [13 empty] | 2021-08-23 | 2021-09-01 | 7 | [15 empty] | 2021-08-23 | 2021-08-24 | 1 | 2021-09-01 |  | 2021-09-16 | 10
120591483 | 344 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-02 |  | 2021-03-09 | 2021-03-04 | 2021-03-04 | 2 | 2021-03-09 | 5 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-21 | 18 | [13 empty] | 2021-08-23 | 2021-09-01 | 7 | [15 empty] | 2021-08-23 | 2021-08-24 | 1 | 2021-09-01 |  | 2021-09-16 | 10
120591299 | 345 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-02 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2 | 2021-03-11 | 7 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-21 | 18 | [13 empty] | 2021-08-24 | 2021-09-01 | 6 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-09-01 |  | 2021-09-16 | 10
120617311 | 346 | PGE | 95965 | NEM | EXPNEM | IA in Progress | Solar PV | 38.78 |  | 2021-03-09 |  |  | 2021-03-11 | 2021-03-11 | 2 | 2021-03-11 | 2 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-07-22 | 82 |  |  |  |  | 2021-03-09 | 2021-07-30 | 2021-03-09 | 2021-08-09 | 107 |  |  |  |  | 2021-12-17 | 2021-12-23 | 4 | [15 empty] | 2021-12-17 | 2021-12-20 | 1 | 2021-12-23
120591488 | 347 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-02 |  | 2021-03-09 | 2021-03-04 | 2021-03-04 | 2 | 2021-03-12 | 8 | 2021-03-26 | 10 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-08-19 | 102 | [13 empty] | 2021-08-24 | 2021-09-01 | 6 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-09-01 |  | 2021-09-09 | 5
120537095 | 348 | PGE | 95377 | NEM | EXPNEM | IA in Progress | Solar PV | 420 |  | 2021-02-16 |  | 2021-02-17 | 2021-02-17 | 2021-02-17 | 1 | 2021-03-11 | 17 | 2021-03-27 | 11 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | 2021-04-29 | 23 | [16 empty] | 2021-07-30 | 2021-12-14 | 93
120463096 | 349 | PGE | 95501 | NEM | EXPNEM | IA in Progress | Solar PV | 56.965 |  | 2021-01-25 |  | 2021-01-26 | 2021-01-26 | 2021-01-26 | 1 | 2021-03-01 | 24 | 2021-03-29 | 20 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | [6 empty] | 2021-01-25 |  | 2021-01-25
120586926 | 350 | PGE | 95033 | NEM | EXPNEM | IA in Progress | Solar PV | 75.259 |  | 2021-03-01 |  | 2021-03-02 | 2021-03-02 | 2021-03-02 | 1 | 2021-03-12 | 9 | 2021-03-29 | 11 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | [6 empty] | 2021-03-01 |  | 2021-03-01
120534361 | 351 | PGE | 93280 | NEM | EXPNEM | Implementation | Solar PV | 230 |  | 2021-02-14 |  | 2021-03-01 | 2021-03-01 | 2021-03-01 | 9 | 2021-03-15 | 19 | 2021-03-29 | 10 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-06-22 | 60 | [16 empty] | 2021-07-20 | 2021-11-15 | 82
120637856 | 352 | PGE | 93648 | NEM | EXPNEM | Study in Progress | Solar PV | 590 |  | 2021-03-12 |  |  | 2021-03-16 | 2021-03-16 | 2 | 2021-03-16 | 2 | 2021-03-30 | 10 | 2021-06-17 | 2021-07-16 | 20 | [12 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | [6 empty] | 2021-03-12 | 2021-04-09 | 2021-03-12 | 2021-04-16 | 25
120572666 | 353 | PGE | 94930 | NEM | EXPNEM | Commercial | Solar PV | 61.126 |  | 2021-02-24 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 2 | 2021-03-17 | 15 | 2021-03-30 | 9 | [15 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-04-20 | 15 |  |  |  |  | 2021-03-12 | 2021-06-28 | 2021-03-12 | 2021-07-01 | 78 |  |  |  |  | 2021-07-06 | 2021-07-08 | 2 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-08 |  | 2021-07-09 | 1
120538175 | 354 | PGE | 93637 | NEM | EXPNEM | Commercial | Solar PV | 650.576 |  | 2021-02-16 |  | 2021-02-17 | 2021-02-17 | 2021-02-17 | 1 | 2021-03-16 | 20 | 2021-03-31 | 11 | [15 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | 2021-04-15 | 11 |  |  |  |  | 2021-02-16 | 2021-07-06 | 2021-02-16 | 2021-07-19 | 107 |  |  |  |  | 2021-09-23 | 2021-09-29 | 4 | [15 empty] | 2021-09-23 | 2021-09-23 | 0 | 2021-09-29 |  | 2021-10-06 | 5
120535220 | 355 | PGE | 95901 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-02-15 |  | 2021-03-11 | 2021-02-16 | 2021-02-16 | 0 | 2021-03-18 | 22 | 2021-04-01 | 10 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | 2021-10-14 | 137 | [13 empty] | 2021-10-21 | 2021-10-28 | 5 | [15 empty] | 2021-10-21 | 2021-10-21 | 0 | 2021-10-28 |  | 2021-11-03 | 4
120614007 | 356 | PGE | 95377 | NEM | EXPNEM | Commercial | Solar PV | 30.159 |  | 2021-03-08 |  | 2021-03-23 | 2021-03-10 | 2021-03-10 | 2 | 2021-03-24 | 12 | 2021-04-01 | 6 | [15 empty] | 2021-04-01 | 2021-04-02 | 1 | 2021-04-02 | 2021-04-15 | 9 | [13 empty] | 2021-04-19 | 2021-04-27 | 6 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-27 |  | 2021-04-30 | 3
120575034 | 357 | PGE | 93249 | NEM | EXPNEM | Withdrawn | Solar PV | 66.6 |  | 2021-02-24 |  | 2021-03-11 | 2021-02-26 | 2021-02-26 | 2 | 2021-03-18 | 16 | 2021-04-02 | 11 | [15 empty] | 2021-04-02 | 2021-04-02 | 0 | 2021-04-02
120567542 | 358 | PGE | 95032 | NEM | EXPNEM | IA in Progress | Solar PV | 156 |  | 2021-02-23 |  |  | 2021-02-24 | 2021-02-24 | 1 | 2021-02-24 | 1 | 2021-04-05 | 28 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-09-24 | 121 |  |  |  |  | 2021-02-23 |  | 2021-02-23
120612829 | 359 | PGE | 94043 | NEM | EXPNEM | Commercial | Solar PV | 32.907 |  | 2021-03-08 |  | 2021-03-10 | 2021-03-10 | 2021-03-10 | 2 | 2021-03-17 | 7 | 2021-04-05 | 13 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-05-14 | 29 | [13 empty] | 2021-06-07 | 2021-06-16 | 7 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-16 |  | 2021-06-23 | 5
120630314 | 360 | PGE | 94513 | NEM | EXPNEM | Commercial | Solar PV | 86.4 |  | 2021-03-10 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 2 | 2021-03-17 | 5 | 2021-04-05 | 13 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-07-15 | 71 |  |  |  |  | 2021-03-10 | 2021-05-25 | 2021-03-10 | 2021-06-07 | 62 |  |  |  |  | 2021-07-20 | 2021-07-28 | 6 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-28 |  | 2021-08-11 | 10
120677938 | 361 | PGE | 95695 | NEM | EXPNEM | Commercial | Solar PV | 38.527 |  | 2021-03-23 |  |  | 2021-03-25 | 2021-03-25 | 2 | 2021-03-25 | 2 | 2021-04-05 | 7 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-11-17 | 158 | [13 empty] | 2021-11-21 | 2021-11-30 | 4 | [15 empty] | 2021-11-21 | 2021-11-22 | 0 | 2021-11-30 |  | 2021-12-03 | 3
120658640 | 362 | PGE | 96011 | NEM | EXPNEM | Commercial | Solar PV | 48.857 |  | 2021-03-18 |  | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2 | 2021-03-26 | 6 | 2021-04-05 | 6 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-07-22 | 76 | [13 empty] | 2021-08-17 | 2021-08-19 | 2 | [15 empty] | 2021-08-17 | 2021-08-17 | 0 | 2021-08-19 |  | 2021-08-23 | 2
120692850 | 363 | PGE | 95076 | NEM | EXPNEM | Commercial | Solar PV | 466.6 |  | 2021-03-25 |  | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2 | 2021-03-31 | 4 | 2021-04-05 | 3 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-05-19 | 32 | [13 empty] | 2021-05-21 | 2021-05-26 | 3 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-26 |  | 2021-06-02 | 4
120602101 | 364 | PGE | 94085 | NEM | EXPNEM | Commercial | Solar PV | 75.885 |  | 2021-03-04 |  | 2021-03-16 | 2021-03-05 | 2021-03-05 | 1 | 2021-03-19 | 11 | 2021-04-06 | 12 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-04-29 | 17 | [13 empty] | 2021-05-04 | 2021-05-13 | 7 | [15 empty] | 2021-05-04 | 2021-05-05 | 1 | 2021-05-13 |  | 2021-05-19 | 4
120651491 | 365 | PGE | 93314 | NEM | EXPNEM | Withdrawn | Solar PV | 31.5 |  | 2021-03-17 |  | 2021-03-19 | 2021-03-19 | 2021-03-19 | 2 | 2021-03-23 | 4 | 2021-04-06 | 10 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06
120696257 | 366 | PGE | 95361 | NEM | EXPNEM | Commercial | Solar PV | 35.852 |  | 2021-03-26 |  |  | 2021-03-29 | 2021-03-29 | 1 | 2021-03-29 | 1 | 2021-04-06 | 6 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-05-07 | 23 | [13 empty] | 2021-12-09 | 2021-12-16 | 5 | [15 empty] | 2021-12-09 | 2021-12-10 | 1 | 2021-12-16 |  | 2021-12-22 | 4
120639801 | 367 | PGE | 94546 | NEM | EXPNEM | Commercial | Solar PV | 62.5 |  | 2021-03-12 |  | 2021-03-17 | 2021-03-17 | 2021-03-17 | 3 | 2021-03-19 | 5 | 2021-04-07 | 13 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-21 | 10 | [13 empty] | 2021-10-06 | 2021-10-14 | 6 | [15 empty] | 2021-10-06 | 2021-10-07 | 1 | 2021-10-14 |  | 2021-10-25 | 7
120644805 | 368 | PGE | 95991 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-03-15 |  | 2021-03-18 | 2021-03-18 | 2021-03-18 | 3 | 2021-03-23 | 6 | 2021-04-07 | 11 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-16 | 7 |  |  |  |  | 2021-03-15 |  | 2021-03-15 | [6 empty] | 2021-06-18 | 2021-06-30 | 8 | [15 empty] | 2021-06-18 | 2021-06-21 | 1 | 2021-06-30 |  | 2021-07-16 | 11
120633666 | 369 | PGE | 94538 | NEM | EXPNEM | IA in Progress | Solar PV | 765.9 |  | 2021-03-11 |  | 2021-03-15 | 2021-03-15 | 2021-03-15 | 2 | 2021-03-24 | 9 | 2021-04-08 | 11 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | [6 empty] | 2021-03-11 |  | 2021-03-11
120657788 | 370 | PGE | 93722 | NEM | EXPNEM | Commercial | Solar PV | 55.067 |  | 2021-03-18 |  | 2021-04-02 | 2021-03-22 | 2021-03-22 | 2 | 2021-04-02 | 11 | 2021-04-08 | 4 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | 2021-04-13 | 3 | [13 empty] | 2021-04-15 | 2021-04-22 | 5 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-22 |  | 2021-04-29 | 5
120494223 | 371 | PGE | 93706 | NEM | EXPNEM | Implementation | Solar PV | 969.737 |  | 2021-02-02 |  | 2021-03-10 | 2021-02-17 | 2021-02-17 | 10 | 2021-03-09 | 24 | 2021-03-23 | 10 | 2021-03-23 | 2021-04-09 | 13 | [12 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | 2021-04-28 | 13 | [9 empty] | 2021-05-25 | [6 empty] | 2021-06-22 | 2021-12-07 | 115 |  |  |  | 2022-01-05 | 0 | 7
120592266 | 372 | PGE | 93308 | NEM | EXPNEM | IA in Progress | Solar PV | 89.259 |  | 2021-03-02 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2 | 2021-03-08 | 4 | 2021-04-12 | 25 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12
120647081 | 373 | PGE | 95207 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-03-16 |  |  | 2021-03-30 | 2021-03-30 | 10 | 2021-03-30 | 10 | 2021-04-12 | 9 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-09-16 | 110 | [13 empty] | 2021-12-20 | 2021-12-28 | 6 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-28 |  | 2021-12-29 | 1
120611784 | 374 | PGE | 95619 | NEM | EXPNEM | Commercial | Solar PV | 89.207 |  | 2021-03-08 |  | 2021-03-23 | 2021-03-10 | 2021-03-10 | 2 | 2021-03-26 | 14 | 2021-04-13 | 12 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-07-19 | 67 | [13 empty] | 2021-08-27 | 2021-09-02 | 4 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-09-02 |  | 2021-09-13 | 6
120466057 | 375 | PGE | 93622 | NEM | EXPNEM | Implementation | Solar PV | 648.528 |  | 2021-01-26 |  | 2021-12-02 | 2021-02-09 | 2021-02-09 | 10 | 2021-03-01 | 23 | 2021-03-11 | 8 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | 2021-04-01 | 15 | [9 empty] | 2021-05-25 | [6 empty] | 2021-06-17 | 2021-08-11 | 38 |  |  |  | 2021-08-13 | 0 | 105
120456663 | 376 | PGE | 95482 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-01-22 |  | 2021-03-15 | 2021-02-26 | 2021-02-26 | 24 | 2021-03-15 | 35 | 2021-04-01 | 13 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | 2021-04-02 | 1 | [13 empty] | 2021-05-20 | 2021-05-27 | 5 | [15 empty] | 2021-05-20 | 2021-05-21 | 1 | 2021-05-27 |  | 2021-05-27 | 0
120442992 | 377 | PGE | 95333 | NEM | EXPNEM | Commercial | Solar PV | 95.8 |  | 2021-01-18 |  | 2021-03-16 | 2021-01-25 | 2021-01-25 | 4 | 2021-01-25 | 4 | 2021-02-11 | 13 | [15 empty] | 2021-02-19 | 2021-03-19 | 20 | 2021-03-19 | 2021-04-13 | 17 |  |  |  |  | 2021-01-18 | 2021-07-14 | 2021-01-18 | 2021-07-27 | 132 |  |  |  |  | 2021-09-07 | 2021-09-15 | 6 | [15 empty] | 2021-09-07 | 2021-09-08 | 1 | 2021-09-15 |  | 2021-09-15 | 0
120431263 | 378 | PGE | 95521 | NEM | EXPNEM | Commercial | Solar PV | 85.387 |  | 2021-01-14 |  | 2021-05-11 | 2021-01-15 | 2021-01-15 | 1 | 2021-01-19 | 2 | 2021-02-01 | 9 | [15 empty] | 2021-02-01 | 2021-02-01 | 0 | 2021-02-01 | 2021-05-11 | 70 |  |  |  |  | 2021-01-14 | 2021-05-11 | 2021-01-14 | 2021-05-26 | 92 |  |  |  |  | 2021-12-22 | [17 empty] | 2021-12-22 | 2021-12-23 | 1
120427579 | 379 | PGE | 95901 | NEM | EXPNEM | Implementation | Solar PV | 490 |  | 2021-01-13 |  |  | 2021-01-20 | 2021-01-20 | 4 | 2021-01-20 | 4 | 2021-02-03 | 10 | 2021-02-03 | 2021-03-17 | 29 | 2021-03-17 | 2021-03-23 | 4 | 2021-03-23 | [8 empty] | 2021-08-16 | 2021-08-18 | 2 | 2021-08-18 | 2021-08-19 | 1 |  |  |  |  | 2021-01-13 | 2021-01-20 | 2021-01-13 | 2021-02-01 | 12 | [7 empty] | 2021-09-20 | 2021-12-28 | 67
120433871 | 380 | PGE | 95901 | NEM | EXPNEM | Implementation | Solar PV | 720 |  | 2021-01-15 |  |  | 2021-01-21 | 2021-01-21 | 3 | 2021-01-21 | 3 | [5 empty] | 2021-01-21 | 2021-02-25 | 24 | 2021-02-25 | [8 empty] | 2021-08-16 | 2021-08-18 | 2 | 2021-08-18 | 2021-08-19 | 1 |  |  |  |  | 2021-01-15 | 2021-01-21 | 2021-01-15 | 2021-02-02 | 11
120446345 | 381 | PGE | 95320 | NEM | EXPNEM | Commercial | Solar PV | 44.337 |  | 2021-01-19 |  | 2021-01-28 | 2021-01-28 | 2021-01-28 | 7 | 2021-01-28 | 7 | 2021-03-22 | 36 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-05-19 | 42 |  |  |  |  | 2021-01-19 | 2021-01-28 | 2021-01-19 | 2021-02-05 | 13 |  |  |  |  | 2021-09-07 | 2021-09-16 | 7 | [15 empty] | 2021-09-07 | 2021-09-08 | 1 | 2021-09-16 |  | 2021-09-16 | 0
120487150 | 382 | PGE | 94545 | NEM | EXPNEM | Commercial | Solar PV | 41.968 |  | 2021-02-01 |  | 2021-07-29 | 2021-02-02 | 2021-02-02 | 1 | 2021-02-10 | 7 | 2021-03-22 | 27 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-04-19 | 20 |  |  |  |  | 2021-02-01 | 2021-02-02 | 2021-02-01 | 2021-02-08 | 5 |  |  |  |  | 2021-08-03 | 2021-08-27 | 18 | [15 empty] | 2021-08-03 | 2021-08-03 | 0 | 2021-08-27 |  | 2021-09-09 | 8
120452601 | 383 | PGE | 95037 | NEM | EXPNEM | Withdrawn | Solar PV, Storage | 33.54 |  | 2021-01-21 |  | 2021-02-08 | 2021-02-04 | 2021-02-04 | 10 | [29 empty] | 2021-01-21 | 2021-02-04 | 2021-01-21 | 2021-02-09 | 13
120495661 | 384 | PGE | 95240 | NEM | EXPNEM | Commercial | Solar PV | 400 |  | 2021-02-03 |  | 2021-02-11 | 2021-02-03 | 2021-02-03 | 0 | 2021-02-22 | 12 | 2021-03-03 | 7 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-12-15 | 199 |  |  |  |  | 2021-02-03 | 2021-10-18 | 2021-02-03 | 2021-11-01 | 189 |  |  |  |  | 2021-12-16 | 2021-12-28 | 8 | 2021-06-16 | 2021-10-12 | 82 | [12 empty] | 2021-12-16 | 2021-12-16 | 0 | 2021-12-28 |  | 2021-12-29 | 1
120423690 | 385 | PGE | 95240 | NEM | EXPNEM | IA in Progress | Solar PV | 41.219 |  | 2021-01-12 |  | 2021-01-13 | 2021-01-13 | 2021-01-13 | 1 | 2021-02-04 | 16 | 2021-03-24 | 33 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | [6 empty] | 2021-01-12 | 2021-02-05 | 2021-01-12 | 2021-02-09 | 19
120473793 | 386 | PGE | 95448 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-01-28 |  |  | 2021-01-29 | 2021-01-29 | 1 | 2021-01-29 | 1 | 2021-02-11 | 9 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-05-12 | 63 |  |  |  |  | 2021-01-28 | 2021-02-11 | 2021-01-28 | 2021-02-11 | 10 |  |  |  |  | 2021-06-19 | 2021-07-14 | 16 | 2021-10-05 | 2021-10-05 | 0 |  |  |  | 2021-10-14 | 2021-12-02 | 32 | [6 empty] | 2021-06-19 | 2021-07-09 | 13 | 2021-07-14 | 2021-07-21 | 2021-12-08 | 5 |  |  | 121
120453709 | 387 | PGE | 95317 | NEM | EXPNEM | Implementation | Solar PV | 38.78 |  | 2021-01-21 |  | 2021-03-15 | 2021-01-29 | 2021-01-29 | 6 | 2021-02-12 | 16 | 2021-02-26 | 9 | [15 empty] | 2021-02-26 | 2021-03-16 | 12 | 2021-03-16 | 2021-04-09 | 18 |  |  |  |  | 2021-01-21 | 2021-02-10 | 2021-01-21 | 2021-02-11 | 15 |  |  |  |  | 2021-05-17 | 2021-05-24 | 5 | 2021-05-18 | 2021-08-19 | 65 | [12 empty] | 2021-05-17 | 2021-05-17 | 0 | 2021-05-24 | 2021-06-17 |  | 17 |  |  | 103
120500120 | 388 | PGE | 93727 | NEM | EXPNEM | IA in Progress | Solar PV | 200 |  | 2021-02-04 |  | 2021-02-11 | 2021-02-05 | 2021-02-05 | 1 | 2021-02-12 | 6 | 2021-02-22 | 5 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-05-05 | 52 |  |  |  |  | 2021-02-04 | 2021-02-12 | 2021-02-04 | 2021-02-16 | 7
120493163 | 389 | PGE | 93622 | NEM | EXPNEM | Commercial | Solar PV | 49.794 |  | 2021-02-02 |  | 2021-02-16 | 2021-02-11 | 2021-02-11 | 7 | 2021-02-11 | 7 | 2021-02-26 | 10 | [15 empty] | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-05-18 | 57 |  |  |  |  | 2021-02-02 | 2021-02-11 | 2021-02-02 | 2021-02-16 | 9 |  |  |  |  | 2021-06-15 | 2021-06-24 | 7 | [15 empty] | 2021-06-15 | 2021-06-16 | 1 | 2021-06-24 |  | 2021-06-24 | 0
120524106 | 390 | PGE | 94954 | NEM | EXPNEM | Withdrawn | Solar PV | 94.844 |  | 2021-02-10 |  |  | 2021-02-23 | 2021-02-23 | 8 | 2021-02-23 | 8 | 2021-03-11 | 12 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | [6 empty] | 2021-02-10 | 2021-02-23 | 2021-02-10 | 2021-02-23 | 8
120553203 | 391 | PGE | 94545 | NEM | EXPNEM | Commercial | Solar PV | 172.8 |  | 2021-02-18 |  | 2021-02-19 | 2021-02-19 | 2021-02-19 | 1 | 2021-02-25 | 5 | 2021-04-15 | 35 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-26 | 7 |  |  |  |  | 2021-02-18 | 2021-02-25 | 2021-02-18 | 2021-02-25 | 5 |  |  |  |  | 2021-06-22 | 2021-06-29 | 5 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-29 |  | 2021-06-30 | 1
120511284 | 392 | PGE | 95385 | NEM | EXPNEM | IA in Progress | Solar PV | 46.625 |  | 2021-02-09 |  | 2021-02-19 | 2021-02-10 | 2021-02-10 | 1 | 2021-02-25 | 11 | 2021-03-11 | 10 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | 2021-12-31 | 205 |  |  |  |  | 2021-02-09 | 2021-02-25 | 2021-02-09 | 2021-02-25 | 11 |  |  |  |  | 2021-12-31 | [17 empty] | 2021-12-31
120566926 | 393 | PGE | 93301 | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-02-23 |  | 2021-02-24 | 2021-02-24 | 2021-02-24 | 1 | 2021-02-26 | 3 | 2021-03-26 | 20 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-08-13 | 98 |  |  |  |  | 2021-02-23 | 2021-02-26 | 2021-02-23 | 2021-03-01 | 4 |  |  |  |  | 2021-08-13 | 2021-08-25 | 8 | [15 empty] | 2021-08-13 | 2021-08-16 | 1 | 2021-08-25 |  | 2021-09-07 | 8
120493168 | 394 | PGE | 95616 | NEM | EXPNEM | Study in Progress | Solar PV | 104.7 |  | 2021-02-02 |  | 2021-02-24 | 2021-02-03 | 2021-02-03 | 1 | 2021-03-01 | 18 | 2021-03-17 | 12 | 2021-03-17 | 2021-04-14 | 20 | 2021-05-06 | 2021-06-10 | 24 | 2021-06-10 | 2021-06-25 | 11 |  |  |  | 2021-06-25 | [12 empty] | 2021-02-02 | 2021-06-11 | 2021-02-02 | 2021-07-09 | 110
120424390 | 395 | PGE | 93420 | NEM | EXPNEM | Commercial | Solar PV | 625 |  | 2021-01-13 |  | 2021-01-14 | 2021-01-14 | 2021-01-14 | 1 | 2021-01-20 | 4 | 2021-02-02 | 9 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-10-04 | 170 |  |  |  |  | 2021-01-13 | 2021-03-01 | 2021-01-13 | 2021-03-02 | 32 |  |  |  |  | 2021-11-12 | 2021-11-17 | 3 | [15 empty] | 2021-11-12 | 2021-11-12 | 0 | 2021-11-17 |  | 2021-11-23 | 4
120424357 | 396 | PGE | 93420 | NEM | EXPNEM | Commercial | Solar PV | 183.3 |  | 2021-01-13 |  | 2021-01-14 | 2021-01-14 | 2021-01-14 | 1 | 2021-01-20 | 4 | 2021-02-02 | 9 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-09-23 | 163 |  |  |  |  | 2021-01-13 | 2021-03-01 | 2021-01-13 | 2021-03-02 | 32 |  |  |  |  | 2021-12-06 | 2021-12-15 | 7 | [15 empty] | 2021-12-06 | 2021-12-06 | 0 | 2021-12-15 |  | 2021-12-20 | 3
120425293 | 397 | PGE | 95336 | NEM | EXPNEM | Implementation | Solar PV | 125 |  | 2021-01-13 |  | 2021-01-21 | 2021-01-21 | 2021-01-21 | 5 | 2021-02-25 | 29 | 2021-04-28 | 44 | 2021-04-28 | 2021-05-26 | 20 | 2021-06-28 | 2021-07-23 | 18 | 2021-07-23 | 2021-08-06 | 10 |  | 2021-10-25 |  | 2021-08-06 |  |  | 2021-10-26 | 2021-10-27 | 1 | 2021-10-27 | 2021-11-09 | 9 | [5 empty] | 2021-02-25 | 2021-02-25 | 2021-03-04 | 5
120506502 | 398 | PGE | 95037 | NEM | EXPNEM | Commercial | Solar PV | 154.954 |  | 2021-02-08 |  | 2021-02-16 | 2021-02-08 | 2021-02-08 | 0 | 2021-03-08 | 19 | 2021-05-10 | 45 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2021-05-11 | 1 |  |  |  |  | 2021-02-08 | 2021-03-04 | 2021-02-08 | 2021-03-04 | 17 |  |  |  |  | 2021-11-21 | 2021-12-02 | 6 | [15 empty] | 2021-11-21 | 2021-11-21 | 0 | 2021-12-02 |  | 2021-12-09 | 5
120552377 | 399 | PGE | 95333 | NEM | EXPNEM | Commercial | Solar PV | 125 |  | 2021-02-18 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 10 | 2021-03-23 | 23 | 2021-03-30 | 5 | [15 empty] | 2021-05-14 | 2021-05-14 | 0 | 2021-05-14 | 2021-06-01 | 11 |  |  |  |  | 2021-02-18 | 2021-03-04 | 2021-02-18 | 2021-03-05 | 11 |  |  |  |  | 2021-06-22 | 2021-06-29 | 5 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-29 |  | 2021-06-30 | 1
120556358 | 400 | PGE | 95333 | NEM | EXPNEM | Commercial | Solar PV | 247.461 |  | 2021-02-19 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 10 | 2021-03-23 | 22 | 2021-03-30 | 5 | [15 empty] | 2021-03-30 | 2021-05-03 | 24 | 2021-05-03 | 2021-05-27 | 18 |  |  |  |  | 2021-02-19 | 2021-03-05 | 2021-02-19 | 2021-03-05 | 10 |  |  |  |  | 2021-06-22 | 2021-06-29 | 5 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-29 |  | 2021-06-30 | 1
120552451 | 401 | PGE | 95242 | NEM | EXPNEM | Implementation | Solar PV | 53.611 |  | 2021-02-18 |  | 2021-03-23 | 2021-03-04 | 2021-03-04 | 10 | 2021-03-04 | 10 | 2021-03-23 | 13 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | 2021-04-05 | 9 |  |  |  |  | 2021-02-18 | 2021-03-04 | 2021-02-18 | 2021-03-05 | 11 | [7 empty] | 2021-07-02 | 2021-11-08 | 89 |  |  |  | 2021-11-30 | 0 | 32
120453909 | 402 | PGE | 93637 | NEM | EXPNEM | Commercial | Solar PV | 45.572 |  | 2021-01-21 |  | 2021-02-22 | 2021-01-22 | 2021-01-22 | 1 | 2021-03-01 | 26 | 2021-03-08 | 5 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-08-25 | 120 |  |  |  |  | 2021-01-21 | 2021-03-05 | 2021-01-21 | 2021-03-08 | 31 |  |  |  |  | 2021-08-28 | 2021-09-07 | 5 | [15 empty] | 2021-08-28 | 2021-08-30 | 0 | 2021-09-07 |  | 2021-09-15 | 6
120564923 | 403 | PGE | 94015 | NEM | EXPNEM | Commercial | Solar PV | 146.495 |  | 2021-02-22 |  | 2021-02-23 | 2021-02-23 | 2021-02-23 | 1 | 2021-03-03 | 7 | 2021-06-12 | 71 | [15 empty] | 2021-06-12 | 2021-06-12 | 0 | 2021-06-12 | 2021-06-18 | 4 |  |  |  |  | 2021-02-22 | 2021-04-12 | 2021-02-22 | 2021-04-29 | 48 |  |  |  |  | 2021-11-30 | 2021-12-08 | 6 | [15 empty] | 2021-11-30 | 2021-11-30 | 0 | 2021-12-08 |  | 2021-12-15 | 5
120568698 | 404 | PGE | 93610 | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-02-23 |  | 2021-03-24 | 2021-03-09 | 2021-03-09 | 10 | 2021-03-09 | 10 | 2021-03-29 | 14 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-06-03 | 20 |  |  |  |  | 2021-02-23 | 2021-03-09 | 2021-02-23 | 2021-03-12 | 13
120479413 | 405 | PGE | 95020 | NEM | EXPNEM | IA in Progress | Solar PV | 666.6 |  | 2021-01-29 |  | 2021-02-01 | 2021-02-01 | 2021-02-01 | 1 | 2021-03-10 | 27 | 2021-04-13 | 24 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | [6 empty] | 2021-01-29 | 2021-04-13 | 2021-01-29 | 2021-05-07 | 69
120474874 | 406 | PGE | 95304 | NEM | EXPNEM | Commercial | Solar PV | 437.5 |  | 2021-01-28 |  | 2021-02-10 | 2021-02-10 | 2021-02-10 | 9 | 2021-02-22 | 16 | 2021-03-05 | 9 | [15 empty] | 2021-03-05 | 2021-03-05 | 0 | 2021-03-05 | 2021-04-05 | 21 |  |  |  |  | 2021-01-28 | 2021-04-13 | 2021-01-28 | 2021-05-07 | 70 |  |  |  |  | 2021-12-03 | 2021-12-17 | 10 | [15 empty] | 2021-12-03 | 2021-12-03 | 0 | 2021-12-17 |  | 2021-12-24 | 5
120540245 | 407 | PGE | 94587 | NEM | EXPNEM | IA in Progress | Solar PV | 36 |  | 2021-02-17 |  | 2021-02-25 | 2021-02-18 | 2021-02-18 | 1 | 2021-03-01 | 8 | 2021-03-19 | 14 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-04-09 | 15 |  |  |  |  | 2021-02-17 | 2021-03-10 | 2021-02-17 | 2021-03-12 | 17
120527051 | 408 | PGE | 95920 | NEM | EXPNEM | IA in Progress | Solar PV | 125 |  | 2021-02-11 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 20 | 2021-03-26 | 30 | 2021-04-16 | 15 | 2021-04-16 | 2021-06-25 | 49 | 2021-07-02 | 2021-07-22 | 13 | 2021-07-22 |  |  |  | 2021-11-17 |  |  |  |  | 2021-11-17 | 2021-11-17 | 0 | 2021-11-17 | [6 empty] | 2021-02-11 | 2021-03-12 | 2021-02-11 | 2021-03-15 | 21
120479428 | 409 | PGE | 94538 | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-01-29 |  | 2021-02-01 | 2021-02-01 | 2021-02-01 | 1 | 2021-03-09 | 26 | 2021-03-27 | 13 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | [6 empty] | 2021-01-29 | 2021-03-11 | 2021-01-29 | 2021-03-15 | 30
120479518 | 410 | PGE | 95122 | NEM | EXPNEM | IA in Progress | Solar PV | 633.3 |  | 2021-01-29 |  | 2021-03-09 | 2021-02-01 | 2021-02-01 | 1 | 2021-03-09 | 26 | 2021-04-13 | 25 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | [6 empty] | 2021-01-29 | 2021-03-11 | 2021-01-29 | 2021-03-15 | 30
120479524 | 412 | PGE | 94578 | NEM | EXPNEM | Withdrawn | Solar PV | 766.6 |  | 2021-01-29 |  | 2021-03-10 | 2021-02-01 | 2021-02-01 | 1 | 2021-03-16 | 31 | 2021-07-08 | 80 | [15 empty] | 2021-07-08 | 2021-07-09 | 1 | 2021-07-09 | [6 empty] | 2021-01-29 | 2021-03-16 | 2021-01-29 | 2021-03-18 | 33
120597727 | 413 | PGE | 93725 | NEM | EXPNEM | Commercial | Solar PV | 34.8 |  | 2021-03-03 |  | 2021-03-18 | 2021-03-17 | 2021-03-17 | 10 | 2021-05-26 | 60 | 2021-06-10 | 10 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-08-02 | 36 |  |  |  |  | 2021-03-03 | 2021-03-18 | 2021-03-03 | 2021-03-24 | 15 |  |  |  |  | 2021-10-26 | 2021-11-02 | 5 | [15 empty] | 2021-10-26 | 2021-10-26 | 0 | 2021-11-02 |  | 2021-11-03 | 1
120598627 | 414 | PGE | 95236 | NEM | EXPNEM | Commercial | Solar PV | 43.421 |  | 2021-03-03 |  | 2021-03-18 | 2021-03-17 | 2021-03-17 | 10 | 2021-05-10 | 48 | 2021-08-16 | 68 | [15 empty] | 2021-08-16 | 2021-08-25 | 7 | 2021-08-25 | 2021-09-01 | 5 |  |  |  |  | 2021-03-03 | 2021-03-18 | 2021-03-03 | 2021-03-25 | 16 |  |  |  |  | 2021-09-09 | 2021-11-16 | 47 | [15 empty] | 2021-09-09 | 2021-09-09 | 0 | 2021-11-16 |  | 2021-11-17 | 1
120603535 | 415 | PGE | 93446 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-04 |  | 2021-03-18 | 2021-03-18 | 2021-03-18 | 10 | 2021-04-24 | 36 | 2021-05-10 | 10 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2021-05-10 | 0 |  |  |  |  | 2021-03-04 | 2021-03-18 | 2021-03-04 | 2021-03-25 | 15 |  |  |  |  | 2021-06-23 | 2021-06-28 | 3 | [15 empty] | 2021-06-23 | 2021-06-24 | 1 | 2021-06-28 |  | 2021-06-29 | 1
120604327 | 416 | PGE | 93460 | NEM | EXPNEM | Commercial | Solar PV | 31.024 |  | 2021-03-04 |  | 2021-03-18 | 2021-03-18 | 2021-03-18 | 10 | 2021-05-03 | 42 | 2021-06-03 | 22 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-23 | 14 |  |  |  |  | 2021-03-04 | 2021-04-19 | 2021-03-04 | 2021-05-07 | 46 |  |  |  |  | 2021-06-30 | 2021-07-12 | 7 | [15 empty] | 2021-06-30 | 2021-07-01 | 1 | 2021-07-12 |  | 2021-07-13 | 1
120608031 | 417 | PGE | 95620 | NEM | EXPNEM | Commercial | Solar PV | 120 |  | 2021-03-05 |  | 2021-03-19 | 2021-03-19 | 2021-03-19 | 10 | 2021-05-24 | 56 | 2021-06-29 | 25 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | 2021-08-04 | 25 |  |  |  |  | 2021-03-05 | 2021-03-19 | 2021-03-05 | 2021-03-25 | 14 |  |  |  |  | 2021-09-13 | 2021-09-20 | 5 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-20 |  | 2021-09-21 | 1
120633938 | 418 | PGE | 93445 | NEM | EXPNEM | IA in Progress | Solar PV | 375 |  | 2021-03-11 |  | 2021-03-15 | 2021-03-15 | 2021-03-15 | 2 | 2021-03-18 | 5 | 2021-05-20 | 45 | [15 empty] | 2021-05-20 | 2021-06-08 | 12 | 2021-06-08 | [6 empty] | 2021-03-11 | 2021-03-18 | 2021-03-11 | 2021-03-25 | 10
120479525 | 419 | PGE | 95112 | NEM | EXPNEM | IA in Progress | Solar PV | 800 |  | 2021-01-29 |  | 2021-03-22 | 2021-02-01 | 2021-02-01 | 1 | 2021-03-25 | 38 | 2021-06-07 | 51 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [6 empty] | 2021-01-29 | 2021-03-22 | 2021-01-29 | 2021-03-25 | 38
120606029 | 420 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 78.716 |  | 2021-03-05 |  |  | 2021-03-19 | 2021-03-19 | 10 | 2021-03-19 | 10 | 2021-04-05 | 11 | [15 empty] | 2021-06-25 | 2021-06-25 | 0 | 2021-06-25 | 2021-06-29 | 2 |  |  |  |  | 2021-03-05 | 2021-03-19 | 2021-03-05 | 2021-03-25 | 14 |  |  |  |  | 2021-06-30 | 2021-07-12 | 7 | [15 empty] | 2021-06-30 | 2021-07-01 | 1 | 2021-07-12 |  | 2021-07-13 | 1
120472149 | 421 | PGE | 93637 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-01-27 |  | 2021-01-28 | 2021-01-28 | 2021-01-28 | 1 | 2021-02-03 | 5 | 2021-02-20 | 11 | [15 empty] | 2021-02-20 | 2021-02-20 | 0 | 2021-02-20 | 2021-08-24 | 129 |  |  |  |  | 2021-01-27 | 2021-06-02 | 2021-01-27 | 2021-06-15 | 97 |  |  |  |  | 2021-08-27 | 2021-09-07 | 6 | [15 empty] | 2021-08-27 | 2021-08-30 | 1 | 2021-09-07 |  | 2021-09-14 | 5
120637799 | 422 | PGE | 94545 | NEM | EXPNEM | IA in Progress | Solar PV | 78.723 |  | 2021-03-12 |  | 2021-03-16 | 2021-03-16 | 2021-03-16 | 2 | 2021-03-23 | 7 | 2021-04-07 | 11 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-08-10 | 87 |  |  |  |  | 2021-03-12 | 2021-03-23 | 2021-03-12 | 2021-03-25 | 9
120559227 | 423 | PGE | 93637 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-02-22 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 4 | 2021-03-11 | 13 | 2021-03-27 | 11 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | 2021-04-20 | 16 |  |  |  |  | 2021-02-22 | 2021-03-27 | 2021-02-22 | 2021-03-29 | 25 |  |  |  |  | 2021-10-18 |  |  | 2021-07-09 |  | 130 |  |  |  | 2021-08-02 | 0 | 114 | [6 empty] | 2021-10-18 | 2021-10-18 | 0
120627586 | 424 | PGE | 93652 | NEM | EXPNEM | Commercial | Solar PV | 250 |  | 2021-03-10 |  |  | 2021-03-24 | 2021-03-24 | 10 | 2021-03-24 | 10 | 2021-04-13 | 14 | [15 empty] | 2021-04-13 | 2021-05-18 | 25 | 2021-05-18 | 2021-06-08 | 14 |  |  |  |  | 2021-03-10 | 2021-03-24 | 2021-03-10 | 2021-03-31 | 15 |  |  |  |  | 2021-07-30 | 2021-08-10 | 7 | [15 empty] | 2021-07-30 | 2021-08-02 | 1 | 2021-08-10 |  | 2021-08-11 | 1
120617304 | 425 | PGE | 95008 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-03-09 |  | 2021-03-10 | 2021-03-10 | 2021-03-10 | 1 | 2021-03-16 | 5 | 2021-04-02 | 13 | [15 empty] | 2021-04-02 | 2021-04-02 | 0 | 2021-04-02 | 2021-04-05 | 1 |  |  |  |  | 2021-03-09 | 2021-04-12 | 2021-03-09 | 2021-04-29 | 37
120617176 | 426 | PGE | 95236 | NEM | EXPNEM | Implementation | Solar PV | 420 |  | 2021-03-09 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 10 | 2021-07-02 | 82 | 2021-07-20 | 11 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-07-23 | 3 |  |  |  |  | 2021-03-09 | 2021-06-14 | 2021-03-09 | 2021-06-18 | 72 | [7 empty] | 2021-09-16 |  | 82
120511265 | 427 | PGE | 95304 | NEM | EXPNEM | IA in Progress | Solar PV | 96 |  | 2021-02-09 |  | 2021-02-10 | 2021-02-10 | 2021-02-10 | 1 | 2021-03-24 | 30 | 2021-04-06 | 9 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | [6 empty] | 2021-02-09 | 2021-03-24 | 2021-02-09 | 2021-04-02 | 37
120664033 | 428 | PGE | 95376 | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-03-19 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 2 | 2021-03-29 | 6 | 2021-04-06 | 6 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-12-16 | 176 |  |  |  |  | 2021-03-19 | 2021-04-29 | 2021-03-19 | 2021-05-10 | 36 |  |  |  |  | 2021-12-31 |  |  | 2021-11-09 | 2021-11-10 | 1 | [12 empty] | 2021-12-31
120664104 | 429 | PGE | 95376 | NEM | EXPNEM | IA in Progress | Solar PV | 248.576 |  | 2021-03-19 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 2 | 2021-03-30 | 7 | 2021-04-06 | 5 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | [6 empty] | 2021-03-19 | 2021-04-23 | 2021-03-19 | 2021-05-07 | 35 | [7 empty] | 2021-11-09 | 2021-11-10 | 1
120635852 | 430 | PGE | 93301 | NEM | EXPNEM | Commercial | Solar PV | 237.128 |  | 2021-03-11 |  | 2021-03-25 | 2021-03-25 | 2021-03-25 | 10 | 2021-05-24 | 52 | 2021-06-28 | 24 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-07-09 | 8 |  |  |  |  | 2021-03-11 | 2021-03-25 | 2021-03-11 | 2021-04-05 | 17 |  |  |  |  | 2021-08-18 | 2021-08-25 | 5 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-25 |  | 2021-08-26 | 1
120637807 | 431 | PGE | 93611 | NEM | EXPNEM | Commercial | Solar PV | 37.529 |  | 2021-03-12 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 10 | 2021-05-25 | 52 | 2021-06-08 | 9 | [15 empty] | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-06-14 | 4 |  |  |  |  | 2021-03-12 | 2021-03-26 | 2021-03-12 | 2021-04-05 | 16 |  |  |  |  | 2021-08-05 | 2021-08-12 | 5 | [15 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-12 |  | 2021-08-13 | 1
120680002 | 432 | PGE | 96080 | NEM | EXPNEM | IA in Progress | Solar PV | 97.072 |  | 2021-03-23 |  | 2021-03-25 | 2021-03-25 | 2021-03-25 | 2 | 2021-04-14 | 16 | 2021-05-04 | 14 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | [6 empty] | 2021-03-23 | 2021-03-25 | 2021-03-23 | 2021-04-05 | 9
120565427 | 433 | PGE | 95973 | NEM | EXPNEM | Commercial | Solar PV | 38.528 |  | 2021-02-22 |  | 2021-02-23 | 2021-02-23 | 2021-02-23 | 1 | 2021-03-25 | 23 | 2021-04-05 | 7 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-05-10 | 25 |  |  |  |  | 2021-02-22 | 2021-06-08 | 2021-02-22 | 2021-06-17 | 82 |  |  |  |  | 2021-07-02 | 2021-07-23 | 14 | [15 empty] | 2021-07-02 | 2021-07-15 | 8 | 2021-07-23 |  | 2021-08-04 | 8
120680695 | 434 | PGE | 95236 | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-03-23 |  |  | 2021-03-25 | 2021-03-25 | 2 | 2021-03-25 | 2 | 2021-04-06 | 8 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-05-19 | 31 |  |  |  |  | 2021-03-23 | 2021-03-25 | 2021-03-23 | 2021-04-05 | 9 |  |  |  |  | 2021-08-03 | 2021-08-10 | 5 | [15 empty] | 2021-08-03 | 2021-08-03 | 0 | 2021-08-10 |  | 2021-08-13 | 3
120680223 | 435 | PGE | 95236 | NEM | EXPNEM | IA in Progress | Solar PV | 142.054 |  | 2021-03-23 |  |  | 2021-03-25 | 2021-03-25 | 2 | 2021-03-25 | 2 | 2021-04-06 | 8 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-05-19 | 31 |  |  |  |  | 2021-03-23 | 2021-03-25 | 2021-03-23 | 2021-04-05 | 9 |  |  |  |  | 2021-12-13 | 2021-12-31 | 14 | [15 empty] | 2021-12-13 | 2021-12-13 | 0 | 2021-12-31
120637819 | 436 | PGE | 94545 | NEM | EXPNEM | IA in Progress | Solar PV | 52.163 |  | 2021-03-12 |  | 2021-03-24 | 2021-03-16 | 2021-03-16 | 2 | 2021-03-25 | 9 | 2021-04-12 | 12 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-08-10 | 84 |  |  |  |  | 2021-03-12 | 2021-03-25 | 2021-03-12 | 2021-04-05 | 16
120536909 | 437 | PGE | 95317 | NEM | EXPNEM | Implementation | Solar PV | 720 |  | 2021-02-16 |  | 2021-03-02 | 2021-03-02 | 2021-03-02 | 10 | 2021-05-10 | 59 | 2021-06-01 | 15 | 2021-06-01 | 2021-06-21 | 14 | [12 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-07-20 | 20 |  |  |  |  | 2021-02-16 | 2021-03-26 | 2021-02-16 | 2021-04-12 | 39
120572565 | 439 | PGE | 93609 | NEM | EXPNEM | Implementation | Solar PV | 85.259 |  | 2021-02-24 |  | 2021-03-10 | 2021-03-10 | 2021-03-10 | 10 | 2021-03-27 | 22 | 2021-04-16 | 14 | [15 empty] | 2021-04-16 | 2021-06-02 | 32 | 2021-06-02 | 2021-06-07 | 3 |  |  |  |  | 2021-02-24 | 2021-03-27 | 2021-02-24 | 2021-04-12 | 33
120672611 | 440 | PGE | 95131 | NEM | EXPNEM | Commercial | Solar PV | 40.153 |  | 2021-03-22 |  | 2021-03-24 | 2021-03-24 | 2021-03-24 | 2 | 2021-03-30 | 6 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-08-19 | 88 |  |  |  |  | 2021-03-22 | 2021-03-30 | 2021-03-22 | 2021-04-12 | 15 |  |  |  |  | 2021-10-29 | 2021-11-09 | 7 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-11-09 |  | 2021-11-12 | 2
120704078 | 441 | PGE | 93434 | NEM | EXPNEM | IA in Progress | Solar PV | 220 |  | 2021-03-28 |  | 2021-03-29 | 2021-03-29 | 2021-03-29 | 0 | 2021-03-30 | 1 | 2021-04-16 | 13 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | [6 empty] | 2021-03-28 | 2021-03-29 | 2021-03-28 | 2021-04-12 | 10
120704108 | 442 | PGE | 93434 | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-03-28 |  |  | 2021-03-30 | 2021-03-30 | 1 | 2021-03-30 | 1 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | [6 empty] | 2021-03-28 | 2021-03-30 | 2021-03-28 | 2021-04-12 | 10
120535166 | 443 | PGE | 93647 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-02-15 |  |  | 2021-02-26 | 2021-02-26 | 8 | 2021-02-26 | 8 | 2021-03-15 | 11 | [15 empty] | 2021-03-15 | 2021-06-01 | 55 | 2021-06-01 | 2021-07-07 | 25 |  |  |  |  | 2021-02-15 | 2021-05-04 | 2021-02-15 | 2021-05-18 | 65 |  |  |  |  | 2021-08-12 | 2021-08-19 | 5 | [15 empty] | 2021-08-12 | 2021-08-12 | 0 | 2021-08-19 |  | 2021-08-20 | 1
120658751 | 444 | PGE | 95236 | NEM | EXPNEM | Implementation | Solar PV | 46.625 |  | 2021-03-18 |  | 2021-04-01 | 2021-04-01 | 2021-04-01 | 10 | 2021-06-30 | 73 | 2021-07-16 | 11 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-16 | 2021-07-20 | 2 |  |  |  |  | 2021-03-18 | 2021-04-01 | 2021-03-18 | 2021-04-13 | 18 | [7 empty] | 2021-12-14 |  | 22
120654669 | 445 | PGE | 93263 | NEM | EXPNEM | Commercial | Solar PV | 120 |  | 2021-03-17 |  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 10 | 2021-05-03 | 33 | [5 empty] | 2021-05-03 | 2021-05-25 | 16 | 2021-05-25 |  |  |  | 2021-08-19 |  |  |  |  | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-09-03 | 11 |  |  |  |  | 2021-03-17 | 2021-03-31 | 2021-03-17 | 2021-04-13 | 19 |  |  |  |  | 2021-12-14 | 2021-12-23 | 7 | [15 empty] | 2021-12-14 | 2021-12-15 | 1 | 2021-12-23 |  | 2021-12-24 | 1
120686513 | 446 | PGE | 94591 | NEM | EXPNEM | IA in Progress | Solar PV | 66.536 |  | 2021-03-24 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2 | 2021-03-30 | 4 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-29 | 10 |  |  |  |  | 2021-03-24 | 2021-03-30 | 2021-03-24 | 2021-04-13 | 14
120686439 | 447 | PGE | 94591 | NEM | EXPNEM | IA in Progress | Solar PV | 59.764 |  | 2021-03-24 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2 | 2021-03-30 | 4 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | [6 empty] | 2021-03-24 | 2021-04-21 | 2021-03-24 | 2021-05-07 | 32
120686397 | 448 | PGE | 94591 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-03-24 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2 | 2021-03-30 | 4 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-29 | 10 |  |  |  |  | 2021-03-24 | 2021-04-21 | 2021-03-24 | 2021-05-07 | 32
120654840 | 449 | PGE | 95901 | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2021-03-17 |  |  | 2021-03-30 | 2021-03-30 | 9 | 2021-03-30 | 9 | 2021-04-19 | 14 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-04-28 | 7 |  |  |  |  | 2021-03-17 | 2021-03-30 | 2021-03-17 | 2021-04-13 | 19 | [7 empty] | 2021-06-01 | 2021-10-26 | 103 |  |  |  | 2021-10-28 | 0 | 52
120690266 | 450 | PGE | 94591 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-03-25 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 1 | 2021-03-31 | 4 | 2021-05-21 | 37 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | [6 empty] | 2021-03-25 | 2021-04-21 | 2021-03-25 | 2021-05-07 | 31
120714464 | 451 | PGE | 94544 | NEM | EXPNEM | Commercial | Solar PV | 76.296 |  | 2021-03-30 |  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 1 | 2021-04-01 | 2 | 2021-06-02 | 43 | [15 empty] | 2021-06-02 | 2021-06-03 | 1 | 2021-06-03 | 2021-06-09 | 4 |  |  |  |  | 2021-03-30 | 2021-04-21 | 2021-03-30 | 2021-05-07 | 28 |  |  |  |  | 2021-08-19 | 2021-08-26 | 5 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-26 |  | 2021-08-30 | 2
120689917 | 452 | PGE | 93637 | NEM | EXPNEM | Implementation | Solar PV | 93.552 |  | 2021-03-25 |  | 2021-04-01 | 2021-04-01 | 2021-04-01 | 5 | 2021-04-05 | 7 | 2021-06-21 | 54 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-07-07 | 11 |  |  |  |  | 2021-03-25 | 2021-04-01 | 2021-03-25 | 2021-04-13 | 13
120242513 | 453 | PGE | 94510 | NEM | EXPNEM | Commercial | Solar PV | 48.72 |  | 2020-12-30 |  | 2021-02-09 | 2021-01-06 | 2021-01-06 | 4 | 2021-03-12 | 49 | 2021-04-05 | 16 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-05-21 | 34 | [5 empty] | 2021-04-01 | 2021-04-01 | 2021-04-13 | 8 |  |  |  |  | 2021-08-20 | 2021-08-24 | 2 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-24 |  | 2021-08-27 | 3
120664216 | 454 | PGE | 93280 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-03-19 |  | 2021-04-02 | 2021-04-02 | 2021-04-02 | 10 | 2021-05-25 | 47 | 2021-06-03 | 6 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-10 | 5 |  |  |  |  | 2021-03-19 | 2021-04-02 | 2021-03-19 | 2021-04-14 | 18 |  |  |  |  | 2021-06-22 | 2021-06-29 | 5 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-29 |  | 2021-06-30 | 1
120602903 | 455 | PGE | 93242 | NEM | EXPNEM | Commercial | Solar PV | 300 |  | 2021-03-04 |  | 2021-03-17 | 2021-03-17 | 2021-03-17 | 9 | 2021-05-24 | 57 | 2021-06-08 | 10 | [15 empty] | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-07-07 | 20 |  |  |  |  | 2021-03-04 | 2021-04-05 | 2021-03-04 | 2021-04-14 | 29 |  |  |  |  | 2021-10-04 | 2021-10-11 | 5 | [15 empty] | 2021-10-04 | 2021-10-04 | 0 | 2021-10-11 |  | 2021-10-12 | 1
120680099 | 456 | PGE | 96080 | NEM | EXPNEM | IA in Progress | Solar PV | 125 |  | 2021-03-23 |  |  | 2021-04-06 | 2021-04-06 | 10 | 2021-04-20 | 20 | 2021-06-22 | 44 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | [6 empty] | 2021-03-23 | 2021-04-06 | 2021-03-23 | 2021-04-14 | 16
120554661 | 457 | PGE | 93280 | NEM | EXPNEM | Implementation | Solar PV | 43.593 |  | 2021-02-19 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 10 | 2021-03-22 | 21 | 2021-05-10 | 35 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2021-06-01 | 15 |  |  |  |  | 2021-02-19 | 2021-04-04 | 2021-02-19 | 2021-04-14 | 38
120597306 | 458 | PGE | 95206 | NEM | EXPNEM | Study in Progress | Solar PV, Storage | 1617.44 |  | 2021-03-03 | 2021-03-05 |  | 2021-03-05 | 2021-03-05 | 2 | 2021-03-31 | 20 | 2021-06-04 | 46 | 2021-06-15 | 2021-07-12 | 18 | 2021-09-28 | 2021-10-26 | 20 | 2021-10-26 | 2021-11-02 | 5 | 2021-12-16 |  |  | 2021-11-02 | 2021-11-03 | 1 | [10 empty] | 2021-03-03 | 2021-04-02 | 2021-03-03 | 2021-04-14 | 30
120652722 | 459 | PGE | 94559 | NEM | EXPNEM | IA in Progress | Solar PV | 68.44 |  | 2021-03-17 |  | 2021-03-19 | 2021-03-19 | 2021-03-19 | 2 | 2021-04-02 | 12 | 2021-05-03 | 21 | [15 empty] | 2021-05-03 | 2021-05-04 | 1 | 2021-05-04 | 2021-06-16 | 30 |  |  |  |  | 2021-03-17 | 2021-04-02 | 2021-03-17 | 2021-04-14 | 20
120695606 | 460 | PGE | 95361 | NEM | EXPNEM | Implementation | Solar PV | 110 |  | 2021-03-26 |  |  | 2021-04-06 | 2021-04-06 | 7 | 2021-04-07 | 8 | 2021-05-13 | 26 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13 | 2021-05-17 | 2 | [5 empty] | 2021-04-06 | 2021-04-06 | 2021-04-14 | 6
120431279 | 461 | PGE | 93908 | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-01-14 |  | 2021-01-15 | 2021-01-15 | 2021-01-15 | 1 | 2021-01-19 | 2 | 2021-01-26 | 5 | [15 empty] | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 2021-04-06 | 49 |  |  |  |  | 2021-01-14 | 2021-01-15 | 2021-01-14 | 2021-01-28 | 9 |  |  |  |  | 2021-04-09 | 2021-04-15 | 4 | [15 empty] | 2021-04-09 | 2021-04-12 | 1 | 2021-04-15 |  | 2021-04-19 | 2
120617738 | 462 | PGE | 94005 | NEM | EXPNEM | Commercial | Solar PV | 258.2 |  | 2021-03-09 |  | 2021-03-11 | 2021-03-11 | 2021-03-11 | 2 | 2021-03-17 | 6 | 2021-03-26 | 7 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-05 | 6 | [13 empty] | 2021-04-06 | 2021-04-13 | 5 | [15 empty] | 2021-04-06 | 2021-04-07 | 1 | 2021-04-13 |  | 2021-04-16 | 3
120693011 | 463 | PGE | 94022 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.588 |  | 2021-03-25 |  |  | 2021-04-07 | 2021-04-07 | 9 | 2021-04-07 | 9 | 2021-04-12 | 3 | [15 empty] | 2021-03-25 | 2021-03-25 |  | 2021-03-25 | 2021-03-25 | 1 | [10 empty] | 2021-04-07 | 2021-04-20 | 9
120656083 | 465 | PGE | 93301 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 933.1 |  | 2021-03-18 |  | 2021-04-01 | 2021-04-01 | 2021-04-01 | 10 | 2021-06-22 | 67 | 2021-07-26 | 23 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | [6 empty] | 2021-03-18 |  | 2021-03-18
120658306 | 466 | PGE | 95746 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.135 |  | 2021-03-18 |  | 2021-04-01 | 2021-04-01 | 2021-04-01 | 10 | 2021-04-24 | 26 | 2021-05-03 | 5 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | 2021-04-09 | 6 | [5 empty] | 2021-05-03 | 2021-05-03 | 2021-05-17 | 10 |  | 2021-05-03 | 2021-05-03 | 0 | 2021-06-26 | 2021-07-13 | 10 | [15 empty] | 2021-06-26 | 2021-06-28 | 0 | 2021-07-13 |  | 2021-07-14 | 1
120655618 | 467 | PGE | 93308 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 929 |  | 2021-03-17 |  | 2021-04-02 | 2021-04-02 | 2021-04-02 | 12 | 2021-06-22 | 68 | 2021-07-08 | 11 | 2021-07-27 | 2021-08-09 | 9 | [12 empty] | 2021-12-03 | 2021-12-03 | 0 | 2021-12-03 | [6 empty] | 2021-03-17 | 2021-04-29 | 2021-03-17 | 2021-05-10 | 38
120697311 | 468 | PGE | 94553 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 |  | 2021-03-26 |  | 2021-04-09 | 2021-04-09 | 2021-04-09 | 10 | 2021-04-19 | 16 | 2021-05-06 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 |  | 2021-03-26 | 2021-03-26 | 1 | [13 empty] | 2021-05-06 | 2021-05-06 | 0 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 |  | 2021-05-07 | 1
120449506 | 469 | PGE | 94611 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 32.424 |  | 2021-01-20 |  | 2021-02-03 | 2021-02-03 | 2021-02-03 | 10 | 2021-09-21 | 170 | 2021-09-30 | 7 | [15 empty] | 2021-09-06 | 2021-09-06 |  | 2021-09-06 | 2021-09-06 | 1 | [13 empty] | 2021-09-30 | [17 empty] | 2021-09-30 | 2021-09-30 | 0
120500786 | 470 | PGE | 95032 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 87.158 |  | 2021-02-04 |  | 2021-02-05 | 2021-02-05 | 2021-02-05 | 1
120461351 | 471 | PGE | 95746 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.016 |  | 2021-01-25 |  | 2021-02-08 | 2021-02-08 | 2021-02-08 | 10 | 2021-05-26 | 86 | 2021-06-02 | 4 | [15 empty] | 2021-05-14 | 2021-05-14 |  | 2021-05-14 | 2021-05-14 | 1 | [13 empty] | 2021-06-02 | 2021-06-02 | 0 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 |  | 2021-06-02 | 0
120497290 | 473 | PGE | 94941 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 46.393 |  | 2021-02-03 |  | 2021-02-18 | 2021-02-18 | 2021-02-18 | 10 | 2021-05-21 | 76 | 2021-05-26 | 3 | [15 empty] | 2021-05-23 | 2021-05-23 |  | 2021-05-23 | 2021-05-23 | 0 | [13 empty] | 2021-06-07 | 2021-06-07 | 0 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 |  | 2021-06-07 | 0
120506291 | 474 | PGE | 94043 | NEM | NEM Paired Storage | Study in Progress | ENGN, Solar PV, Storage | 2503 |  | 2021-02-08 |  | 2021-11-23 | 2021-02-22 | 2021-02-22 | 9
120506355 | 475 | PGE | 94901 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.54 |  | 2021-02-08 |  | 2021-05-09 | 2021-02-23 | 2021-02-23 | 10
120529036 | 476 | PGE | 95035 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 405.19 |  | 2021-02-11 |  | 2021-02-24 | 2021-02-24 | 2021-02-24 | 8 | [29 empty] | 2021-02-11 | 2021-05-07 | 2021-02-11 | 2021-05-25 | 72
120529038 | 477 | PGE | 95035 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 399.09 |  | 2021-02-11 |  | 2021-02-24 | 2021-02-24 | 2021-02-24 | 8 | [29 empty] | 2021-02-11 | 2021-05-07 | 2021-02-11 | 2021-05-25 | 72
120538562 | 478 | PGE | 95669 | NEM | EXPNEM | Commercial | Solar PV, Storage | 349.179 |  | 2021-02-16 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 8 | 2021-05-26 | 71 | 2021-06-30 | 24 | [15 empty] | 2021-06-30 | 2021-06-30 | 0 | 2021-06-30 | 2021-10-15 | 75 |  |  |  |  | 2021-02-16 | 2021-08-05 | 2021-02-16 | 2021-08-13 | 126 |  |  |  |  | 2021-10-21 | 2021-10-29 | 6 | [15 empty] | 2021-10-21 | 2021-10-21 | 0 | 2021-10-29 |  | 2021-11-03 | 3
120582937 | 480 | PGE | 95746 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 41.393 |  | 2021-02-26 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 10 | 2021-04-23 | 40 | 2021-04-26 | 1 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-03-29 | 0 | [13 empty] | 2021-04-26 | 2021-04-26 | 0 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 |  | 2021-04-26 | 0
120603633 | 481 | PGE | 93239 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1395.292 |  | 2021-03-04 |  | 2021-03-18 | 2021-03-17 | 2021-03-17 | 9
120645634 | 484 | PGE | 94027 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 37.6 |  | 2021-03-15 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 9 | 2021-06-07 | 59 | 2021-06-15 | 6 | [15 empty] | 2021-04-30 | 2021-04-30 |  | 2021-04-30 | 2021-04-30 | 1 | [13 empty] | 2021-06-15 | 2021-06-17 | 2 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-17 |  | 2021-06-17 | 0
120655749 | 485 | PGE | 93308 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1203.9 |  | 2021-03-17 |  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 10 | 2021-06-22 | 68 | 2021-07-08 | 11 | 2021-07-27 | 2021-08-09 | 9 | [12 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | [6 empty] | 2021-03-17 |  | 2021-03-17
120653359 | 486 | PGE | 96080 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 341.598 |  | 2021-03-17 |  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 10 | 2021-06-04 | 56 | 2021-07-23 | 34 | [15 empty] | 2021-07-23 | 2021-07-23 |  | 2021-07-23 | 2021-08-09 | 12
120691162 | 487 | PGE | 95014 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 39.195 |  | 2021-03-25 |  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 4 | 2021-06-17 | 59 | 2021-07-12 | 16 | [15 empty] | 2021-03-31 | 2021-03-31 |  | 2021-03-31 | 2021-06-21 | 59 | [13 empty] | 2021-07-12 | 2021-07-12 | 0 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 |  | 2021-07-12 | 0
120498076 | 488 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1572 |  | 2021-02-03 | 2021-02-05 |  | 2021-02-05 | 2021-02-05 | 2 | 2021-02-10 | 5 | 2021-04-16 | 46 | 2021-04-23 | 2021-06-22 | 41 | [12 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-09-20 | 62 |  |  |  |  | 2021-02-03 |  | 2021-02-03 | [6 empty] | 2020-12-21 | 2020-12-21 | 0 | [15 empty] | 2020-12-21 |  |  | 2020-12-21 |  | 2020-12-21 | 0
120498261 | 489 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1872 |  | 2021-02-03 | 2021-02-05 |  | 2021-02-05 | 2021-02-05 | 2 | 2021-02-17 | 9 | 2021-04-20 | 44 | 2021-04-24 | 2021-06-24 | 42 | [12 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-24 | 2021-10-05 | 71 |  |  |  |  | 2021-02-03 |  | 2021-02-03
120498260 | 490 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1542.8 |  | 2021-02-03 | 2021-02-05 |  | 2021-02-05 | 2021-02-05 | 2 | 2021-02-17 | 9 | 2021-04-20 | 44 | 2021-04-23 | 2021-06-23 | 42 | [12 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-09-21 | 62 |  |  |  |  | 2021-02-03 |  | 2021-02-03
120477883 | 492 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1359.5 |  | 2021-01-29 |  | 2021-02-05 | 2021-02-05 | 2021-02-05 | 5 | 2021-04-07 | 47 | 2021-04-28 | 15 | 2021-05-10 | 2021-06-24 | 32 | [12 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-24 | 2021-09-21 | 61 |  |  |  |  | 2021-01-29 |  | 2021-01-29
120477908 | 493 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1280.3 |  | 2021-01-29 |  | 2021-02-05 | 2021-02-05 | 2021-02-05 | 5 | 2021-04-07 | 47 | 2021-04-28 | 15 | 2021-06-02 | 2021-06-30 | 20 | [12 empty] | 2021-06-30 | 2021-06-30 | 0 | 2021-06-30 | 2021-10-05 | 67 |  |  |  |  | 2021-01-29 |  | 2021-01-29
120498202 | 494 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1272 |  | 2021-02-03 |  | 2021-02-08 | 2021-02-08 | 2021-02-08 | 3 | 2021-04-07 | 44 | 2021-04-28 | 15 | 2021-05-07 | 2021-06-21 | 30 | [12 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-09-21 | 64 |  |  |  |  | 2021-02-03 |  | 2021-02-03
120698794 | 495 | PGE | 94945 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 |  | 2021-03-26 |  |  | 2021-04-07 | 2021-04-07 | 8 | 2021-04-07 | 8 | 2021-04-30 | 17 | [34 empty] | 2021-04-30 | 2021-04-30 | 0 | [15 empty] | 2021-04-30 | 2021-04-30 | 0 | 2021-04-30 |  | 2021-05-03 | 1
120477970 | 496 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1309.5 |  | 2021-01-29 |  | 2021-02-13 | 2021-02-13 | 2021-02-13 | 10 | 2021-04-09 | 49 | 2021-05-07 | 20 | 2021-05-28 | 2021-06-28 | 20 | [12 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-10-05 | 69 |  |  |  |  | 2021-01-29 |  | 2021-01-29
120498209 | 497 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1405.3 |  | 2021-02-03 |  | 2021-02-16 | 2021-02-16 | 2021-02-16 | 8 | 2021-04-10 | 46 | 2021-05-07 | 19 | 2021-06-01 | 2021-06-29 | 20 | [12 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | 2021-10-05 | 68 |  |  |  |  | 2021-02-03 |  | 2021-02-03
120719402 | 499 | PGE | 94549 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.559 |  | 2021-03-31 |  |  | 2021-04-14 | 2021-04-14 | 10 | 2021-04-14 | 10 | 2021-04-22 | 6 | [15 empty] | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 | 2021-06-08 | 32 |  |  |  |  | 2021-03-31 | 2021-05-14 | 2021-03-31 | 2021-06-03 | 45 |  |  |  |  | 2021-06-14 | 2021-06-14 | 0 | [15 empty] | 2021-06-14 | 2021-06-14 | 0 | 2021-06-08 |  | 2021-06-08 | 1
120498201 | 500 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1547 |  | 2021-02-03 | 2021-02-05 |  | 2021-02-04 | 2021-02-04 | 1 | 2021-02-10 | 5 | 2021-04-08 | 40 | 2021-04-14 | 2021-06-22 | 48 | [12 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-09-20 | 62 |  |  |  |  | 2021-02-03 |  | 2021-02-03
120702082 | 501 | PGE | 93923 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 39.248 |  | 2021-03-27 |  |  | 2021-04-06 | 2021-04-06 | 6 | 2021-04-06 | 6 | 2021-04-08 | 2
120507290 | 502 | PGE | 93619 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 647.732 |  | 2021-02-08 | 2021-02-10 |  | 2021-02-10 | 2021-02-10 | 2 | 2021-03-10 | 21 | 2021-03-31 | 15 | 2021-04-09 | 2021-05-03 | 16 | [12 empty] | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | 2021-07-30 | 62 |  |  |  |  | 2021-02-08 |  | 2021-02-08
120690757 | 503 | PGE | 96080 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 39.229 |  | 2021-03-25 |  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 4 | 2021-04-01 | 5 | 2021-04-21 | 14 | [15 empty] | 2021-03-31 | 2021-04-01 | 1 | 2021-04-01 | 2021-04-01 | 0
120401062 | 505 | PGE | 95949 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 39.4 |  | 2021-01-07 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-15 | 3 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12
120525633 | 506 | PGE | 95663 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.828 |  | 2021-02-10 |  |  | 2021-02-18 | 2021-02-18 | 5 | 2021-02-18 | 5 | 2021-02-22 | 2 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-05-11 | 58 | [13 empty] | 2021-05-13 | 2021-05-13 | 0 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13 |  | 2021-05-13 | 0
120496371 | 507 | PGE | 94022 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.877 |  | 2021-02-03 |  | 2021-02-06 | 2021-02-06 | 2021-02-06 | 2 | 2021-02-19 | 11 | 2021-03-03 | 8 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-07-08 | 89 | [13 empty] | 2021-07-08 | 2021-07-08 | 0 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 |  | 2021-07-09 | 1
120506335 | 511 | PGE | 94558 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 45.177 |  | 2021-02-08 |  | 2021-02-23 | 2021-02-23 | 2021-02-23 | 10 | 2021-03-16 | 25 | 2021-03-22 | 4 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-22 | 4 | [13 empty] | 2021-04-28 | 2021-04-28 | 0 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 |  | 2021-04-28 | 0
120511112 | 512 | PGE | 94062 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.49 |  | 2021-02-09 |  | 2021-02-24 | 2021-02-24 | 2021-02-24 | 10 | 2021-03-16 | 24 | 2021-03-24 | 6 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-05-21 | 48 | [13 empty] | 2021-05-26 | 2021-05-26 | 0 | [15 empty] | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 |  | 2021-05-27 | 1
120606443 | 513 | PGE | 93901 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.728 |  | 2021-03-05 |  |  | 2021-03-19 | 2021-03-19 | 10 | 2021-03-19 | 10 | 2021-03-22 | 1 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-06-07 | 55 | [13 empty] | 2021-06-09 | 2021-06-09 | 0 | [15 empty] | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 |  | 2021-06-09 | 0
120611965 | 514 | PGE | 95650 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 36.39 |  | 2021-03-08 |  | 2021-03-19 | 2021-03-19 | 2021-03-19 | 9 | 2021-04-08 | 23 | 2021-04-09 | 1 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-05-06 | 34
120617582 | 515 | PGE | 94074 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 31.997 |  | 2021-03-09 |  |  | 2021-03-20 | 2021-03-20 | 8 | 2021-03-20 | 8 | 2021-05-19 | 42 | [15 empty] | 2021-03-20 | 2021-03-20 | 0 | 2021-03-20 | 2021-12-03 | 178
120636261 | 518 | PGE | 95247 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 30.08 |  | 2021-03-11 |  | 2021-03-24 | 2021-03-24 | 2021-03-24 | 9 | [19 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24
120638777 | 521 | PGE | 94507 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 42.716 |  | 2021-03-12 |  |  | 2021-03-25 | 2021-03-25 | 9 | 2021-03-25 | 9 | 2021-03-29 | 2 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-04-20 | 18 | [13 empty] | 2021-04-20 | 2021-04-20 | 0 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 |  | 2021-04-20 | 0
120644111 | 523 | PGE | 94526 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.715 |  | 2021-03-15 |  | 2021-04-20 | 2021-03-27 | 2021-03-27 | 9 | 2021-04-15 | 23 | 2021-04-20 | 3 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | 2021-04-16 | 14 | [13 empty] | 2021-07-19 | 2021-09-22 | 46 | [15 empty] | 2021-07-19 | 2021-07-20 | 1 | 2021-09-22 |  | 2021-09-22 | 0
120644697 | 524 | PGE | 94574 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 38.545 |  | 2021-03-15 |  | 2021-03-29 | 2021-03-29 | 2021-03-29 | 10 | 2021-03-29 | 10 | 2021-04-15 | 13 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-04-21 | 17 | [13 empty] | 2021-11-22 | 2021-12-01 | 5 | 2021-12-30 |  | 11 | [12 empty] | 2021-11-22 | 2021-11-22 | 0 | 2021-12-01
120646380 | 526 | PGE | 95425 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 |  | 2021-03-16 |  |  | 2021-03-29 | 2021-03-29 | 9 | 2021-03-29 | 9 | 2021-03-30 | 1 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-05-05 | 27 | [13 empty] | 2021-05-05 | 2021-05-05 | 0 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 |  | 2021-05-05 | 0
120675302 | 528 | PGE | 95030 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 38.86 |  | 2021-03-22 |  | 2021-04-05 | 2021-04-05 | 2021-04-05 | 10 | 2021-05-05 | 32 | 2021-05-24 | 13 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-04-15 | 8 | [13 empty] | 2021-05-28 | 2021-05-28 | 0 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 |  | 2021-05-28 | 0
120687551 | 532 | PGE | 94534 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-03-24 |  |  | 2021-04-07 | 2021-04-07 | 10 | 2021-04-07 | 10 | 2021-04-20 | 9 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-07 | 0 | [13 empty] | 2021-04-20 | 2021-04-21 | 1 | [15 empty] | 2021-04-20 | 2021-04-21 | 1 | 2021-04-21 |  | 2021-04-21 | 0
120687584 | 533 | PGE | 95762 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-03-24 |  |  | 2021-04-07 | 2021-04-07 | 10 | 2021-04-07 | 10 | 2021-04-09 | 2 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-05-11 | 24 |  |  |  |  | 2021-03-24 | 2021-04-07 | 2021-03-24 | 2021-04-15 | 16 |  |  |  |  | 2021-05-11 | 2021-05-21 | 8 | [15 empty] | 2021-05-11 | 2021-05-12 | 1 | 2021-05-21 |  | 2021-05-21 | 0
120691460 | 534 | PGE | 95682 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 42.497 |  | 2021-03-25 |  | 2021-04-08 | 2021-04-08 | 2021-04-08 | 10 | 2021-04-15 | 15 | 2021-04-16 | 1 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | 2021-05-10 | 22 |  |  |  |  | 2021-03-25 | 2021-04-19 | 2021-03-25 | 2021-04-21 | 19 |  |  |  |  | 2021-05-10 | 2021-05-17 | 5 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-17 |  | 2021-05-17 | 0
120469866 | 535 | PGE | 95065 | NEM | NEM Paired Storage | Commercial | OTHR, Solar PV, Storage | 30.246 |  | 2021-01-27 |  | 2021-02-10 | 2021-02-10 | 2021-02-10 | 10 | 2021-04-06 | 48 | 2021-04-08 | 2 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | 2021-11-05 | 148 | [13 empty] | 2021-11-05 | 2021-11-08 | 1 | [15 empty] | 2021-11-05 | 2021-11-08 | 1 | 2021-11-08 |  | 2021-11-08 | 0
120714964 | 537 | PGE | 94920 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.08 |  | 2021-03-30 |  | 2021-10-11 | 2021-04-12 | 2021-04-12 | 9 | 2021-04-12 | 9 | 2021-04-20 | 6 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-04-20 | 6 | [13 empty] | 2021-10-22 | 2021-10-22 | 0 | [15 empty] | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 |  | 2021-10-22 | 0
120566958 | 538 | PGE | 95618 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 56.873 |  | 2021-02-23 |  |  | 2021-03-06 | 2021-03-06 | 8 | 2021-03-06 | 8 | 2021-03-18 | 8 | [15 empty] | 2021-03-06 | 2021-03-06 | 0 | 2021-03-06 | 2021-04-01 | 18
120491075 | 540 | PGE | 94550 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31 |  | 2021-02-02 |  | 2021-02-16 | 2021-02-16 | 2021-02-16 | 9 | 2021-03-17 | 30 | 2021-03-25 | 6 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-04-09 | 17 | [13 empty] | 2021-08-31 | 2021-08-31 | 0 | [15 empty] | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 |  | 2021-08-31 | 0
120423593 | 541 | PGE | 93901 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 51.699 |  | 2021-01-12 |  | 2021-01-23 | 2021-01-23 | 2021-01-23 | 7 | 2021-03-03 | 34 | 2021-03-23 | 14 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | 2021-11-03 | 158 |  |  |  |  | 2021-01-12 | 2021-03-03 | 2021-01-12 | 2021-03-05 | 36 |  |  |  |  | 2021-12-07 | 2021-12-16 | 7 | [15 empty] | 2021-12-07 | 2021-12-07 | 0 | 2021-12-16 |  | 2021-12-20 | 2
120477907 | 542 | PGE | 94583 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1447 |  | 2021-01-29 | 2021-02-02 |  | 2021-02-02 | 2021-02-02 | 2 | 2021-02-10 | 8 | 2021-04-08 | 40 | 2021-04-14 | 2021-06-22 | 48 | [12 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-09-22 | 64 |  |  |  |  | 2021-01-29 | 2021-12-27 | 2021-01-29
120651432 | 543 | PGE | 94027 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 96.54 |  | 2021-03-17 |  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 10 | 2021-05-14 | 42 | 2021-06-02 | 12 | [15 empty] | 2021-06-02 | 2021-06-09 | 5 | 2021-06-09 | 2021-06-25 | 12 |  |  |  |  | 2021-03-17 | 2021-03-31 | 2021-03-17 | 2021-04-13 | 19 |  |  |  |  | 2021-07-15 | 2021-07-15 | 0 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 |  | 2021-07-16 | 1
120680807 | 545 | PGE | 95120 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 37.345 |  | 2021-03-23 |  |  | 2021-04-06 | 2021-04-06 | 10 | 2021-04-06 | 10 | 2021-04-09 | 3 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-04-07 | 1 |  |  |  |  | 2021-03-23 | 2021-04-06 | 2021-03-23 | 2021-04-14 | 16 |  |  |  |  | 2021-04-23 | 2021-04-28 | 3 | [15 empty] | 2021-04-23 | 2021-04-23 | 0 | 2021-04-28 |  | 2021-04-28 | 0
120639238 | 546 | PGE | 95476 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 |  | 2021-03-12 |  |  | 2021-03-26 | 2021-03-26 | 10 | 2021-03-26 | 10 | 2021-03-29 | 1 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-07 | 8 | [13 empty] | 2021-09-13 | 2021-09-20 | 5 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-20 |  | 2021-09-20 | 0
120679364 | 547 | PGE | 95470 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-03-23 |  | 2021-04-06 | 2021-04-06 | 2021-04-06 | 10 | 2021-04-07 | 11 | 2021-04-09 | 2 | [15 empty] | 2021-04-06 | 2021-04-06 |  | 2021-04-06 | 2021-04-06 | 1 | [13 empty] | 2021-04-09 | 2021-04-09 | 0 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 |  | 2021-04-10 | 0
120664327 | 548 | PGE | 95492 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 |  | 2021-03-19 |  | 2021-04-02 | 2021-04-02 | 2021-04-02 | 10 | 2021-04-08 | 14 | 2021-04-09 | 1 | [15 empty] | 2021-04-02 | 2021-04-02 | 0 | 2021-04-02 | 2021-04-08 | 4 | [13 empty] | 2021-04-09 | 2021-04-09 | 0 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 |  | 2021-04-10 | 0
120611966 | 550 | PGE | 94547 | Non-NEM | NEMFC | Commercial | FUCE | 262.5 |  | 2021-03-08 |  |  | 2021-03-11 | 2021-03-11 | 3 | 2021-03-11 | 3 | 2021-04-16 | 26 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | 2021-04-05 | 17 |  |  |  |  | 2021-03-08 | 2021-05-13 | 2021-03-08 | 2021-05-27 | 58 |  |  |  |  | 2021-12-21 | 2021-12-23 | 2 | [15 empty] | 2021-12-21 | 2021-12-21 | 0 | 2021-12-23 |  | 2021-12-24 | 1
120722019 | 551 | PGE | 95448 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 59.575 |  | 2021-03-31 |  |  | 2021-04-16 | 2021-04-16 | 12 | 2021-04-16 | 12 | 2021-05-13 | 19 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13
120454664 | 552 | PGE | 94305 | NEM | NEMMT | IA in Progress | Solar PV, Storage | 31.34 |  | 2021-01-21 |  | 2021-02-04 | 2021-02-04 | 2021-02-04 | 10 | 2021-05-21 | 85 | 2021-06-02 | 7 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-06-03 | 8
120507668 | 553 | PGE | 95667 | NEM | NEMMT | Withdrawn | Solar PV, Storage | 894.727 |  | 2021-02-08 |  | 2021-07-13 | 2021-02-22 | 2021-02-22 | 9 | [29 empty] | 2021-02-08 |  | 2021-02-08 | [9 empty] | 2021-03-29 | 2021-07-16 | 77 |  |  |  | 2021-11-03 | 2021-11-03 | 0
120540680 | 554 | PGE | 94080 | Non-NEM | NEMFC | IA in Progress | FUCE | 300 |  | 2021-02-17 |  | 2021-04-12 | 2021-03-02 | 2021-03-02 | 9 | 2021-05-13 | 61 | 2021-06-28 | 31 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28
120647383 | 556 | PGE | 94590 | NEM | NEMMT | IA in Progress | ENGN, FUCE | 900 |  | 2021-03-16 |  | 2021-03-30 | 2021-03-30 | 2021-03-30 | 10 | 2021-07-23 | 91 | [5 empty] | 2021-07-23 | 2021-08-13 | 15 | 2021-08-13 |  |  |  | 2021-11-24 |  |  |  |  | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24
120421365 | 557 | PGE | 93450 | NEM | NEMMT | Study in Progress | Solar PV, Turbine | 18500 |  | 2021-01-12 | 2021-01-13 |  | 2021-01-12 | 2021-01-12 | 0 | 2021-02-03 | 15 | [5 empty] | 2021-02-03 | 2021-03-03 | 19 | 2021-03-03 | 2021-03-18 | 11 | 2021-05-20 |  |  | 2021-03-18 | 2021-04-07 | 14 | [10 empty] | 2021-01-12 |  | 2021-01-12
120237635 | 558 | PGE | 93251 | NEM | NEMMT | Study in Progress | Solar PV, Turbine | 106359.791 |  | 2020-12-29 |  | 2021-01-19 | 2021-01-04 | 2021-01-04 | 3 | 2021-02-10 | 29 | [5 empty] | 2021-02-10 | 2021-03-22 | 27 | 2021-03-22 | 2021-04-12 | 15 | 2021-06-09 |  |  | 2021-04-12 | 2021-05-03 | 15
120480244 | 559 | PGE | 95625 | NEM | NEMMT | Implementation | ENGN, Solar PV, Storage | 4744 |  | 2021-01-29 | 2021-02-01 |  | 2021-02-01 | 2021-02-01 | 1 | 2021-02-17 | 12 | [5 empty] | 2021-02-17 | 2021-03-15 | 18 | 2021-03-15 | 2021-03-17 | 2 | 2021-03-29 | 2021-08-31 | 109 | 2021-03-17 | 2021-03-17 | 0 | 2021-10-27 | 2021-10-27 | 0 | 2021-10-27 | 2021-10-27 | 18 |  |  |  |  | 2021-01-29 |  | 2021-01-29 | [9 empty] | 2021-11-11 |  | 42 | 10/19/2021 | 2022-01-07 | 59
120507711 | 560 | PGE | 94533 | NEM | NEMMT | Implementation | FUCE, Solar PV, WIND | 6689.431 |  | 2021-02-08 |  |  | 2021-02-22 | 2021-02-22 | 9 | 2021-02-22 | 9 | [5 empty] | 2021-02-22 | 2021-04-30 | 49 | 2021-04-30 | 2021-04-30 | 0 | 2021-06-15 | 2021-09-24 | 71 | 2021-04-30 | 2021-05-06 | 4 | 2021-10-14 | 2021-10-19 | 3 | 2021-10-19 | 2021-11-08 | 14 | [9 empty] | 2021-08-10 | 2021-08-24 | 2021-11-05 | 10
120526554 | 561 | PGE | 94583 | NEM | NEMMT | Study in Progress | FUCE, Solar PV, Storage | 2992.749 |  | 2021-02-11 | 2021-02-19 |  | 2021-02-16 | 2021-02-16 | 2 | 2021-03-03 | 13 | [5 empty] | 2021-03-03 | 2021-06-07 | 67 | 2021-06-07 | 2021-07-14 | 26 | 2021-08-23 |  |  | 2021-07-14 | 2021-07-14 | 0 | [10 empty] | 2021-02-11 |  | 2021-02-11
120487290 | 562 | PGE | 95403 | NEM | NEMMT | Implementation | FUCE, Solar PV | 1350 |  | 2021-02-01 |  | 2021-02-17 | 2021-02-17 | 2021-02-17 | 11 | 2021-03-27 | 38 | [5 empty] | 2021-03-27 | 2021-04-23 | 19 | 2021-04-23 |  |  | 2021-04-23 | 2021-07-12 | 54 |  |  |  | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-12-02 | 99 | [5 empty] | 2021-11-30 | 2021-11-30 | 2021-12-15 | 11 | [10 empty] | 2021-12-09
120508906 | 563 | PGE | 94080 | NEM | NEMMT | IA in Progress | FUCE, Solar PV | 769 |  | 2021-02-09 |  | 2021-02-22 | 2021-02-22 | 2021-02-22 | 8 | 2021-03-29 | 33 | 2021-07-07 | 70 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | [7 empty] | 2021-09-16 | 2021-09-16 | 2021-09-22 | 4
120454060 | 564 | PGE | 93280 | NEM | NEMMT | Implementation | FUCE, Solar PV | 249.5 |  | 2021-01-21 |  | 2021-02-04 | 2021-02-04 | 2021-02-04 | 10 | 2021-02-12 | 16 | 2021-03-05 | 14 | 2021-03-05 | 2021-04-02 | 20 | 2021-04-02 | 2021-05-07 | 25 | 2021-05-07 | 2021-05-24 | 11 |  | 2021-08-06 |  | 2021-05-24 |  |  | 2021-10-18 | 2021-10-21 | 3 | 2021-10-21 | 2021-12-01 | 26 |  | 2021-08-31 | 2021-10-06 | 25 | 2021-01-21 |  | 2021-01-21 |  |  | 2021-06-17 | [6 empty] | 2021-05-05 | 2021-05-05 | 0 |  |  |  | 2021-05-05 | 2021-05-05 | 0
120607849 | 565 | PGE | 95033 | NEM | NEMMT | Commercial | Solar PV, Storage | 30.104 |  | 2021-03-05 |  |  | 2021-03-17 | 2021-03-17 | 8 | 2021-03-17 | 8 | 2021-03-22 | 3 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-04-19 | 23 | [13 empty] | 2021-04-19 | 2021-04-23 | 4 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-23 |  | 2021-04-23 | 0
120512635 | 566 | PGE | 95449 | Non-NEM | Non-Export | Commercial | Storage | 140 |  | 2021-02-09 | 2021-02-11 |  | 2021-02-11 | 2021-02-11 | 2 | 2021-03-03 | 15 | 2021-04-20 | 34 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-08-09 | 77 | [5 empty] | 2021-03-04 | 2021-03-04 | 2021-03-04 | 0 |  |  |  |  | 2021-12-15 | 2021-12-22 | 5 | [15 empty] | 2021-12-15 | 2021-12-15 | 0 | 2021-12-22 |  | 2021-12-24 | 2 | 2021-12-01 | 17 | 0
120525065 | 567 | PGE | 95449 | Non-NEM | Non-Export | Commercial | Storage | 140 |  | 2021-02-10 | 2021-02-11 |  | 2021-02-11 | 2021-02-11 | 1 | 2021-03-03 | 14 | 2021-05-19 | 55 | [15 empty] | 2021-05-19 | 2021-05-19 | 0 | 2021-05-19 | 2021-08-16 | 61 |  |  |  |  | 2021-02-10 | 2021-03-04 | 2021-02-10 | 2021-03-05 | 16 |  |  |  |  | 2021-12-15 | 2021-12-22 | 5 | [15 empty] | 2021-12-15 | 2021-12-15 | 0 | 2021-12-22 |  | 2021-12-24 | 2 | 2021-12-15 | 7 | 0
120425938 | 568 | PGE | 96080 | Non-NEM | Non-Export | Commercial | Storage | 350 |  | 2021-01-13 | 2021-01-14 |  | 2021-01-14 | 2021-01-14 | 1 | 2021-02-03 | 14 | 2021-05-27 | 80 | [15 empty] | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-08-10 | 51 | [13 empty] | 2021-12-21 | 2021-12-30 | 7 | [15 empty] | 2021-12-21 | 2021-12-24 | 3 | 2021-12-30 |  | 2021-12-31 | 1 | 2021-12-20 | 9 | 0
120434596 | 569 | PGE | 95945 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-01-15 | 2021-01-19 |  | 2021-01-19 | 2021-01-19 | 1 | 2021-02-03 | 12 | 2021-06-10 | 89 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-08-30 | 56 | [5 empty] | 2021-07-09 | 2021-07-09 | 2021-08-06 | 20
120511644 | 570 | PGE | 95726 | Non-NEM | Non-Export | Implementation | Storage | 350 |  | 2021-02-09 | 2021-02-11 |  | 2021-02-11 | 2021-02-11 | 2 | 2021-03-03 | 15 | 2021-04-19 | 33 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-06-07 | 34
120512428 | 571 | PGE | 95709 | Non-NEM | Non-Export | Implementation | Storage | 350 |  | 2021-02-09 | 2021-02-11 |  | 2021-02-11 | 2021-02-11 | 2 | 2021-03-03 | 15 | 2021-06-23 | 79 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-09-30 | 69
120568376 | 572 | PGE | 95449 | Non-NEM | Non-Export | Commercial | Storage | 140 |  | 2021-02-23 | 2021-02-24 |  | 2021-02-24 | 2021-02-24 | 1 | 2021-03-10 | 11 | 2021-04-15 | 26 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-08-09 | 80 |  |  |  |  | 2021-02-23 | 2021-04-25 | 2021-02-23 | 2021-05-21 | 63 |  |  |  |  | 2021-12-08 | 2021-12-22 | 10 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-22 |  | 2021-12-22 | 0
120565908 | 573 | PGE | 95606 | Non-NEM | Non-Export | Implementation | ENGN, Solar PV | 21944.2 |  | 2021-02-22 | 2021-03-04 |  | 2021-02-23 | 2021-02-23 | 1 | 2021-03-17 | 17 | 2021-04-15 | 21 | 2021-05-05 | 2021-06-04 | 21 | [12 empty] | 2021-06-04 | 2021-06-23 | 13 | 2021-06-23 | 2021-08-19 | 40
120674707 | 574 | PGE | 95134 | Non-NEM | Non-Export | Withdrawn | Storage | 3000 |  | 2021-03-22 | 2021-03-24 |  | 2021-03-23 | 2021-03-23 | 1 | 2021-03-31 | 7
120508661 | 575 | PGE | 94560 | Non-NEM | Non-Export | Withdrawn | Storage – EV | 153.6 |  | 2021-02-08 | 2021-02-09 |  | 2021-02-09 | 2021-02-09 | 1 | 2021-02-24 | 11 | 2021-03-01 | 3
120557855 | 576 | PGE | 94566 | Non-NEM | Non-Export | Implementation | Storage | 1287 |  | 2021-02-20 | 2021-02-22 |  | 2021-02-22 | 2021-02-22 | 0 | 2021-03-03 | 7 | 2021-03-24 | 15 | 2021-04-07 | 2021-05-05 | 20 | [12 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-06-22 | 33 |  |  |  |  | 2021-02-20 |  | 2021-02-20 | [12 empty] | 2021-08-11
120256198 | 577 | PGE | 95501 | Non-NEM | Non-Export | Implementation | Storage | 980 |  | 2021-01-04 | 2021-01-05 |  | 2021-01-05 | 2021-01-05 | 1 | 2021-02-03 | 21 | 2021-07-20 | 116 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-08-16 | 135 |  |  |  |  | 2021-01-04 |  | 2021-01-04
120424269 | 578 | PGE | 95304 | Non-NEM | Non-Export | Commercial | ENGN, Solar PV | 766.6 |  | 2021-01-12 | 2021-01-14 |  | 2021-01-14 | 2021-01-14 | 2 | 2021-01-27 | 10 | 2021-03-01 | 22 | [15 empty] | 2021-03-19 | 2021-03-22 | 1 | 2021-03-22 | 2021-06-24 | 67 | [13 empty] | 2021-10-21 | 2021-11-01 | 7 | 2021-08-05 |  | 111 | [12 empty] | 2021-10-21 | 2021-10-22 | 1 | 2021-11-01 |  | 2021-11-01 | 0
120557752 | 579 | PGE | 93657 | Non-NEM | Non-Export | Implementation | Storage | 1287 |  | 2021-02-20 | 2021-02-22 |  | 2021-02-22 | 2021-02-22 | 0 | 2021-03-03 | 7 | 2021-03-24 | 15 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-06-22 | 63 |  |  |  |  | 2021-02-20 |  | 2021-02-20
120582870 | 580 | PGE | 95540 | Non-NEM | Non-Export | Withdrawn | Storage | 140 |  | 2021-02-26 | 2021-03-01 |  | 2021-03-01 | 2021-03-01 | 1 | 2021-03-24 | 18 | [17 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26
120600202 | 581 | PGE | 95623 | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2021-03-03 | 2021-03-05 |  | 2021-03-05 | 2021-03-05 | 2 | 2021-03-24 | 15 | 2021-05-07 | 32 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-07-02 | 69
120552924 | 582 | PGE | 94063 | Non-NEM | Non-Export | Commercial | Storage | 715 |  | 2021-02-18 | 2021-02-19 |  | 2021-02-19 | 2021-02-19 | 1 | 2021-03-03 | 9 | 2021-04-13 | 29 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-05-04 | 15 | [28 empty] | 2021-09-24 | 2021-10-04 | 6 |  |  |  | 2021-10-21 |  | 2021-10-21 | 1 | 2021-10-21 | 0 | 0
120541648 | 583 | PGE | 95709 | Non-NEM | Non-Export | Implementation | Storage | 420 |  | 2021-02-17 | 2021-02-18 |  | 2021-02-18 | 2021-02-18 | 1 | 2021-03-10 | 15 | 2021-04-14 | 25 | [15 empty] | 2021-04-14 | 2021-04-14 | 0 | 2021-04-14 | 2021-07-13 | 62 |  |  |  |  | 2021-02-17 | 2021-04-15 | 2021-02-17 | 2021-05-07 | 57
120258785 | 584 | PGE | 95521 | Non-NEM | Non-Export | Withdrawn | Storage | 70 |  | 2021-01-05 | 2021-01-06 |  | 2021-01-06 | 2021-01-06 | 1 | 2021-01-27 | 15 | 2021-03-09 | 28 | [15 empty] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | [6 empty] | 2021-01-05 | 2021-01-29 | 2021-01-05 | 2021-02-05 | 22
120433979 | 585 | PGE | 95969 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-01-15 | 2021-01-19 |  | 2021-01-19 | 2021-01-19 | 1 | 2021-02-03 | 12 | 2021-03-11 | 25 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | 2021-06-02 | 58 |  |  |  |  | 2021-01-15 | 2021-02-06 | 2021-01-15 | 2021-02-09 | 16
120526907 | 586 | PGE | 95223 | Non-NEM | Non-Export | IA in Progress | Storage | 210 |  | 2021-02-11 | 2021-02-16 |  | 2021-02-16 | 2021-02-16 | 2 | 2021-03-03 | 13 | 2021-06-23 | 79 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | [6 empty] | 2021-02-11 | 2021-03-04 | 2021-02-11 | 2021-03-16 | 22
120715337 | 587 | PGE | 93660 | Non-NEM | RESBCT | Implementation | Solar PV | 3500 |  | 2021-03-30 | 2021-03-31 |  | 2021-03-30 | 2021-03-30 | 0 | 2021-04-21 | 16 | [5 empty] | 2021-04-21 | 2021-05-11 | 14 | 2021-05-11 | 2021-05-11 | 0 | 2021-05-19 | 2021-10-20 | 107 | 2021-05-11 | 2021-05-12 | 1 | 2021-10-25 | 2021-10-25 | 0 | 2021-10-25 | 2021-11-15 | 14 |  | 2021-09-03 | 2021-09-16 | 8
120537443 | 588 | PGE | 93250 | Non-NEM | RESBCT | Implementation | Solar PV | 2341.786 |  | 2021-02-16 | 2021-02-19 |  | 2021-02-17 | 2021-02-17 | 1 | 2021-02-24 | 6 | [5 empty] | 2021-03-03 | 2021-03-24 | 15 | 2021-03-24 | [8 empty] | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 | 2021-09-28 | 19 |  |  |  |  | 2021-02-16 |  | 2021-02-16 | [12 empty] | 2021-10-05 | 2021-12-28 | 61
120612553 | 589 | PGE | 95765 | Non-NEM | RESBCT | IA in Progress | Solar PV | 2782.651 |  | 2021-03-08 | 2021-03-11 |  | 2021-03-09 | 2021-03-09 | 1 | 2021-03-24 | 12 | 2021-04-13 | 14 | 2021-04-28 | 2021-07-01 | 45 | 2021-07-30 | 2021-08-26 | 19 | 2021-08-26 | 2021-08-26 | 0 | 2021-08-30 | 2021-11-15 | 53 | 2021-08-26 | 2021-08-26 | 0 | 2021-12-13 | 2021-12-14 | 1 | 2021-12-14 | [6 empty] | 2021-03-08 |  | 2021-03-08
120684293 | 590 | PGE | 93241 | NEM | VNEM | Commercial | Solar PV | 38.28 |  | 2021-03-24 |  | 2021-04-07 | 2021-04-05 | 2021-04-05 | 8 | 2021-04-29 | 26 | 2021-05-11 | 8 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2021-08-31 | 78 |  |  |  |  | 2021-03-24 | 2021-05-03 | 2021-03-24 | 2021-05-25 | 44 |  | 2021-05-11 | 2021-05-11 | 0 | 2021-09-09 | 2021-09-20 | 7 | [15 empty] | 2021-09-09 | 2021-09-10 | 1 | 2021-09-20 |  | 2021-10-05 | 11
120458566 | 591 | PGE | 94965 | NEM | VNEM | Study in Progress | Solar PV | 30.26 |  | 2021-01-22 |  | 2021-02-05 | 2021-02-05 | 2021-02-05 | 10
120583633 | 592 | PGE | 95912 | NEM | VNEM | Application Review in Progress | Solar PV | 31.024 |  | 2021-02-27 |  | 2021-03-10 | 2021-03-10 | 2021-03-10 | 7
120643625 | 593 | PGE | 94621 | NEM | VNEM | Commercial | Solar PV | 86.4 |  | 2021-03-15 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 6 | 2021-06-16 | 66 | 2021-09-03 | 56 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-20 | 10 | [5 empty] | 2021-06-17 | 2021-06-17 | 2021-07-02 | 11 |  |  |  |  | 2021-09-24 | 2021-09-30 | 4 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-30 |  | 2021-10-04 | 2
120461526 | 594 | PGE | 93234 | NEM | VNEM | Commercial | Solar PV | 38.78 |  | 2021-01-25 |  | 2021-02-08 | 2021-02-08 | 2021-02-08 | 10 | 2021-03-12 | 33 | 2021-03-24 | 8 | [15 empty] | 2021-03-24 | 2021-04-14 | 15 | 2021-04-14 | 2021-09-16 | 108 |  |  |  |  | 2021-01-25 |  | 2021-01-25 |  |  | 2021-08-06 | 2021-08-12 | 2021-08-18 | 4 | 2021-10-16 | 2021-10-28 | 8 | [15 empty] | 2021-10-16 | 2021-10-18 | 0 | 2021-10-28 |  | 2021-11-02 | 3
120585023 | 595 | PGE | 93455 | NEM | VNEM | Commercial | Solar PV | 217.549 |  | 2021-03-01 |  | 2021-03-10 | 2021-03-10 | 2021-03-10 | 7 | 2021-03-18 | 13 | 2021-04-29 | 30 | [15 empty] | 2021-04-29 | 2021-05-14 | 11 | 2021-05-14 | 2021-07-12 | 39 |  |  |  |  | 2021-03-01 | 2021-07-01 | 2021-03-01 | 2021-07-02 | 88 |  | 2021-07-02 | 2021-07-02 | 0 | 2021-08-20 | 2021-09-01 | 8 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-09-01 |  | 2021-09-02 | 1
120637757 | 596 | PGE | 95035 | NEM | VNEM | Commercial | Solar PV | 35.595 |  | 2021-03-12 |  | 2021-03-22 | 2021-03-22 | 2021-03-22 | 6 | 2021-06-23 | 72 | 2021-07-13 | 13 | [15 empty] | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13 | 2021-07-23 | 8 |  |  |  |  | 2021-03-12 | 2021-04-01 | 2021-03-12 | 2021-04-01 | 14 |  |  |  |  | 2021-09-02 | 2021-09-10 | 5 | [15 empty] | 2021-09-02 | 2021-09-02 | 0 | 2021-09-10 |  | 2021-09-15 | 3
120450062 | 597 | PGE | 94030 | NEM | VNEM | Commercial | Solar PV | 150 |  | 2021-01-20 |  | 2021-02-03 | 2021-02-03 | 2021-02-03 | 10 | 2021-03-05 | 31 | 2021-03-25 | 14 | [15 empty] | 2021-03-25 | 2021-04-15 | 15 | 2021-04-15 | 2021-06-15 | 42 | [5 empty] | 2021-03-05 | 2021-03-05 | 2021-03-08 | 1 |  | 2021-03-11 | 2021-03-11 | 0 | 2021-08-20 | 2021-08-31 | 7 | [15 empty] | 2021-08-20 | 2021-08-23 | 1 | 2021-08-31 |  | 2021-09-16 | 11
120552007 | 598 | PGE | 93927 | NEM | VNEMMASH | IA in Progress | Solar PV | 30.402 |  | 2021-02-18 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 11 | 2021-03-16 | 18 | 2021-03-16 | 0 | [15 empty] | 2021-03-16 | 2021-04-06 | 15 | 2021-04-06 | [6 empty] | 2021-02-18 | 2021-03-09 | 2021-02-18 | 2021-03-12 | 16
120582557 | 599 | PGE | 96007 | NEM | VNEMMASH | IA in Progress | Solar PV | 52.493 |  | 2021-02-26 |  | 2021-03-10 | 2021-03-10 | 2021-03-10 | 8 | 2021-03-16 | 12 | 2021-05-28 | 53 | [15 empty] | 2021-05-28 | 2021-06-08 | 6 | 2021-06-08 | [6 empty] | 2021-02-26 | 2021-03-16 | 2021-02-26 | 2021-03-23 | 17
120541015 | 600 | PGE | 93637 | NEM | VNEMMASH | Application Accepted | Solar PV | 43.53 |  | 2021-02-17 |  | 2021-03-10 | 2021-03-05 | 2021-03-05 | 12 | 2021-03-10 | 15 | 2021-04-02 | 17 | [15 empty] | 2021-04-02 | 2021-06-28 | 60 | 2021-06-28 | [6 empty] | 2021-02-17 | 2021-05-13 | 2021-02-17 | 2021-05-27 | 71
120582748 | 601 | PGE | 93434 | NEM | VNEMMASH | Implementation | Solar PV | 39.976 |  | 2021-02-26 |  | 2021-03-12 | 2021-03-11 | 2021-03-11 | 9 | 2021-05-10 | 51 | 2021-07-02 | 38 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-11-08 | 89 |  |  |  |  | 2021-02-26 | 2021-05-11 | 2021-02-26 | 2021-05-26 | 63 | 2021-12-03
120582841 | 602 | PGE | 93434 | NEM | VNEMMASH | Implementation | Solar PV | 39.976 |  | 2021-02-26 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 10 | 2021-05-10 | 51 | 2021-07-02 | 38 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-11-08 | 89 |  |  |  |  | 2021-02-26 | 2021-05-11 | 2021-02-26 | 2021-05-26 | 63 | 2021-12-03 | [6 empty] | 2021-11-18 |  | 38
120582785 | 603 | PGE | 93434 | NEM | VNEMMASH | Implementation | Solar PV | 39.976 |  | 2021-02-26 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 10 | 2021-05-10 | 51 | 2021-07-28 | 55 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | 2021-07-29 | 1 |  |  |  |  | 2021-02-26 | 2021-05-11 | 2021-02-26 | 2021-05-26 | 63 | 2021-12-03 | [6 empty] | 2021-12-15 |  | 21
120582789 | 605 | PGE | 93434 | NEM | VNEMMASH | Implementation | Solar PV | 39.976 |  | 2021-02-26 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 10 | 2021-05-10 | 51 | 2021-07-28 | 55 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | 2021-07-29 | 1 |  |  |  |  | 2021-02-26 | 2021-05-11 | 2021-02-26 | 2021-05-26 | 63 | 2021-12-03 | [6 empty] | 2021-12-15 |  | 21
120582229 | 606 | PGE | 93458 | NEM | VNEMMASH | Implementation | Solar PV | 39.976 |  | 2021-02-26 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 10 | 2021-03-31 | 23 | 2021-04-21 | 15 | [15 empty] | 2021-04-21 | 2021-05-26 | 25 | 2021-05-26 | 2021-06-10 | 10 |  |  |  |  | 2021-02-26 | 2021-05-11 | 2021-02-26 | 2021-05-26 | 63 | [7 empty] | 2021-12-07 |  | 27
120582228 | 607 | PGE | 93458 | NEM | VNEMMASH | Implementation | Solar PV | 39.976 |  | 2021-02-26 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 10 | 2021-03-31 | 23 | 2021-04-21 | 15 | [15 empty] | 2021-04-21 | 2021-05-26 | 25 | 2021-05-26 | 2021-06-10 | 10 |  |  |  |  | 2021-02-26 | 2021-05-11 | 2021-02-26 | 2021-05-26 | 63
120574050 | 608 | PGE | 93401 | NEM | VNEMMASH | Withdrawn | Solar PV | 42.168 |  | 2021-02-24 |  | 2021-03-09 | 2021-03-09 | 2021-03-09 | 9 | 2021-03-11 | 11 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-04-16 | 15 | 2021-04-16 | [6 empty] | 2021-02-24 | 2021-03-11 | 2021-02-24 | 2021-03-16 | 14
120574061 | 609 | PGE | 93401 | NEM | VNEMMASH | Withdrawn | Solar PV | 34.179 |  | 2021-02-24 |  | 2021-03-09 | 2021-03-09 | 2021-03-09 | 9 | 2021-03-11 | 11 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-04-16 | 15 | 2021-04-16 | [6 empty] | 2021-02-24 | 2021-03-11 | 2021-02-24 | 2021-03-16 | 14
120574052 | 610 | PGE | 93401 | NEM | VNEMMASH | Withdrawn | Solar PV | 34.179 |  | 2021-02-24 |  | 2021-03-09 | 2021-03-09 | 2021-03-09 | 9 | 2021-03-11 | 11 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-04-16 | 15 | 2021-04-16 | [6 empty] | 2021-02-24 | 2021-03-11 | 2021-02-24 | 2021-03-16 | 14
120573126 | 611 | PGE | 96021 | NEM | VNEMMASH | IA in Progress | Solar PV | 34.121 |  | 2021-02-24 |  | 2021-03-09 | 2021-03-09 | 2021-03-09 | 9 | 2021-03-15 | 13 | 2021-04-02 | 14 | [15 empty] | 2021-04-02 | 2021-04-08 | 4 | 2021-04-08 | [6 empty] | 2021-02-24 | 2021-07-27 | 2021-02-24 | 2021-07-28 | 108
120582524 | 612 | PGE | 96007 | NEM | VNEMMASH | IA in Progress | Solar PV | 37.983 |  | 2021-02-26 |  | 2021-03-10 | 2021-03-10 | 2021-03-10 | 8 | 2021-03-16 | 12 | 2021-03-26 | 8 | [15 empty] | 2021-03-26 | 2021-04-16 | 15 | 2021-04-16 | [6 empty] | 2021-02-26 | 2021-04-30 | 2021-02-26 | 2021-05-06 | 49
120593034 | 613 | PGE | 96080 | NEM | VNEMMASH | IA in Progress | Solar PV | 43.53 |  | 2021-03-02 |  | 2021-03-09 | 2021-03-09 | 2021-03-09 | 5 | 2021-03-17 | 11 | 2021-03-31 | 10 | [15 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | [6 empty] | 2021-03-02 | 2021-03-25 | 2021-03-02 | 2021-03-31 | 21
120593054 | 614 | PGE | 96080 | NEM | VNEMMASH | IA in Progress | Solar PV | 37.983 |  | 2021-03-02 |  | 2021-03-09 | 2021-03-09 | 2021-03-09 | 5 | 2021-03-16 | 10 | 2021-04-01 | 12 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | [6 empty] | 2021-03-02 | 2021-03-25 | 2021-03-02 | 2021-03-31 | 21
120540999 | 615 | PGE | 95422 | NEM | VNEMMASH | IA in Progress | Solar PV | 30.402 |  | 2021-02-17 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 12 | 2021-03-15 | 18 | 2021-03-24 | 7 | [15 empty] | 2021-03-24 | 2021-04-14 | 15 | 2021-04-14 | [6 empty] | 2021-02-17 | 2021-05-13 | 2021-02-17 | 2021-05-27 | 71
120540965 | 616 | PGE | 95422 | NEM | VNEMMASH | IA in Progress | Solar PV | 63.72 |  | 2021-02-17 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 12 | 2021-03-15 | 18 | 2021-03-24 | 7 | [15 empty] | 2021-03-24 | 2021-04-14 | 15 | 2021-04-14 | [6 empty] | 2021-02-17 | 2021-03-05 | 2021-02-17 | 2021-03-11 | 16 |  | 2021-03-24 | 2021-04-07 | 10
120491352 | 617 | PGE | 94043 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 68.358 |  | 2021-02-02 |  | 2021-02-17 | 2021-02-17 | 2021-02-17 | 10 | 2021-02-22 | 13 | 2021-03-16 | 16 | [15 empty] | 2021-03-16 | 2021-04-21 | 26 | 2021-04-21 | [6 empty] | 2021-02-02 | 2021-02-22 | 2021-02-02 | 2021-02-24 | 15 |  | 2021-04-20 | 2021-04-21 | 1
120474307 | 618 | PGE | 95012 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 75.636 |  | 2021-01-28 |  | 2021-02-11 | 2021-02-11 | 2021-02-11 | 10 | 2021-03-16 | 32 | 2021-05-05 | 36 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | [6 empty] | 2021-01-28 | 2021-03-16 | 2021-01-28 | 2021-03-18 | 34 |  | 2021-04-21 | 2021-04-21 | 0
120424174 | 619 | PGE | 95401 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 60.446 |  | 2021-01-12 |  | 2021-01-27 | 2021-01-27 | 2021-01-27 | 10 | 2021-03-16 | 43 | 2021-03-28 | 8 | [15 empty] | 2021-05-14 | 2021-05-18 | 2 | 2021-05-18 | [6 empty] | 2021-01-12 | 2021-03-16 | 2021-01-12 | 2021-03-23 | 48
120591196 | 620 | PGE | 95037 | NEM | VNEMSOMAH | Implementation | Solar PV | 95.363 |  | 2021-03-02 |  | 2021-03-15 | 2021-03-15 | 2021-03-15 | 9 | 2021-03-17 | 11 | 2021-04-14 | 20 | [15 empty] | 2021-04-14 | 2021-04-14 | 0 | 2021-04-14 | 2021-05-26 | 30 | [5 empty] | 2021-03-26 | 2021-03-26 | 2021-04-12 | 11 |  | 2021-04-14 | 2021-04-27 | 9
120715555 | 621 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 64.705 |  | 2021-03-30 |  | 2021-04-08 | 2021-04-08 | 2021-04-08 | 7 | 2021-04-16 | 13 | 2021-05-07 | 15 | [15 empty] | 2021-05-07 | 2021-05-07 | 0 | 2021-05-07 | [6 empty] | 2021-03-30 | 2021-05-07 | 2021-03-30 | 2021-05-25 | 40
120491715 | 622 | PGE | 95112 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 41.246 |  | 2021-02-02 |  | 2021-02-17 | 2021-02-17 | 2021-02-17 | 10 | [29 empty] | 2021-02-02 |  | 2021-02-02
120510373 | 623 | PGE | 95116 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 65.629 |  | 2021-02-09 |  | 2021-02-23 | 2021-02-23 | 2021-02-23 | 9 | [29 empty] | 2021-02-09 |  | 2021-02-09
120528720 | 624 | PGE | 95210 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 58.04 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 |  | 2021-02-11
120528824 | 625 | PGE | 95210 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 |  | 2021-02-11
120528539 | 626 | PGE | 95210 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 43.53 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 |  | 2021-02-11
120528951 | 627 | PGE | 95210 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 |  | 2021-02-11
120527343 | 628 | PGE | 95210 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 |  | 2021-02-11
120527994 | 629 | PGE | 95210 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 |  | 2021-02-11
120528823 | 630 | PGE | 95210 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 |  | 2021-02-11
120527751 | 631 | PGE | 95210 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 |  | 2021-02-11
120528507 | 632 | PGE | 95210 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 |  | 2021-02-11
120528891 | 633 | PGE | 95210 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 39.172 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 |  | 2021-02-11
120527807 | 634 | PGE | 95210 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 38.052 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11 |  | 2021-02-11
120535043 | 635 | PGE | 93721 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 34.867 |  | 2021-02-15 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 13 | [29 empty] | 2021-02-15 |  | 2021-02-15
120534668 | 636 | PGE | 93721 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 34.8 |  | 2021-02-15 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 13 | [29 empty] | 2021-02-15 |  | 2021-02-15
120535026 | 637 | PGE | 93721 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 34.281 |  | 2021-02-15 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 13 | [29 empty] | 2021-02-15 |  | 2021-02-15
120534319 | 638 | PGE | 93721 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 34.22 |  | 2021-02-14 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 13 | [29 empty] | 2021-02-14 |  | 2021-02-14
120534364 | 639 | PGE | 93721 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 33.93 |  | 2021-02-14 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 13 | [29 empty] | 2021-02-14 |  | 2021-02-14
120534317 | 640 | PGE | 93721 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 33.35 |  | 2021-02-14 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 13 | [29 empty] | 2021-02-14 |  | 2021-02-14
120257223 | 641 | PGE | 94509 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 46.766 |  | 2021-01-04 |  |  | 2021-01-12 | 2021-01-12 | 6 | 2021-01-12 | 6 | [5 empty] | 2021-01-12 | 2021-01-23 | 7 | 2021-01-23 | [18 empty] | 2021-01-04 |  | 2021-01-04
120508677 | 642 | PGE | 95112 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 65.584 |  | 2021-02-08 |  | 2021-02-23 | 2021-02-23 | 2021-02-23 | 10 | 2021-03-30 | 35 | [5 empty] | 2021-03-30 | 2021-06-08 | 49 | 2021-06-08 | 2021-06-18 | 8 | 2021-06-18 | 2021-09-14 | 60 | 2021-06-18 | 2021-06-18 | 0 | 2021-09-14 | 2021-09-14 | 0 | 2021-09-14 | [6 empty] | 2021-02-08 |  | 2021-02-08
120491626 | 643 | PGE | 95112 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 43.2 |  | 2021-02-02 |  | 2021-02-12 | 2021-02-12 | 2021-02-12 | 8 | 2021-04-02 | 42 | [5 empty] | 2021-04-02 | 2021-06-18 | 54 | 2021-06-18 | 2021-06-18 | 0 | 2021-06-18 | 2021-09-17 | 63 | 2021-06-18 | 2021-06-18 | 0 | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | 2021-10-05 | 12 |  |  |  |  | 2021-02-02 | 2021-05-13 | 2021-02-02 | 2021-05-27 | 81
120537787 | 644 | PGE | 95111 | NEM | VNEMSOMAH | Implementation | Solar PV | 115.42 |  | 2021-02-16 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 13 | 2021-04-05 | 34 | 2021-04-26 | 15 | [15 empty] | 2021-04-26 | 2021-05-14 | 14 | 2021-05-14 | 2021-08-04 | 56 |  |  |  |  | 2021-02-16 | 2021-06-24 | 2021-02-16 | 2021-07-08 | 100 |  | 2021-07-08 | 2021-07-08 | 0
120638882 | 645 | PGE | 95492 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 68.358 |  | 2021-03-12 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 7 | 2021-04-13 | 22 | 2021-05-04 | 15 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | [6 empty] | 2021-03-12 | 2021-06-08 | 2021-03-12 | 2021-06-11 | 64 |  | 2021-06-25 | 2021-07-04 | 5
120639172 | 646 | PGE | 94025 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 95.363 |  | 2021-03-12 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 10 | 2021-04-13 | 22 | 2021-05-04 | 15 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | [6 empty] | 2021-03-12 | 2021-04-21 | 2021-03-12 | 2021-05-07 | 40 |  | 2021-05-04 | 2021-05-04 | 0
120539885 | 647 | PGE | 93930 | NEM | VNEMSOMAH | Application Accepted | Solar PV | 69.12 |  | 2021-02-17 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 12 | 2021-03-05 | 12 | 2021-03-25 | 14 | [25 empty] | 2021-02-17 | 2021-03-05 | 2021-02-17 | 2021-03-11 | 16
120638417 | 648 | PGE | 94952 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.179 |  | 2021-03-12 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 7 | 2021-03-26 | 10 | 2021-04-01 | 4 | [15 empty] | 2021-04-01 | 2021-04-22 | 15 | 2021-04-22 | [6 empty] | 2021-03-12 | 2021-05-25 | 2021-03-12 | 2021-06-15 | 66
120581731 | 649 | PGE | 95112 | NEM | VNEMSOMAH | Implementation | Solar PV | 86.4 |  | 2021-02-26 |  | 2021-03-10 | 2021-03-10 | 2021-03-10 | 8 | 2021-03-16 | 12 | 2021-04-05 | 14 | [15 empty] | 2021-04-05 | 2021-04-26 | 15 | 2021-04-26 | 2021-07-27 | 64 | [5 empty] | 2021-04-26 | 2021-04-26 | 2021-05-03 | 5 |  | 2021-04-26 | 2021-04-26 | 0
120424191 | 650 | PGE | 95401 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 61.783 |  | 2021-01-12 |  | 2021-01-27 | 2021-01-27 | 2021-01-27 | 10 | 2021-03-16 | 43 | 2021-03-28 | 8 | [15 empty] | 2021-05-14 | 2021-05-18 | 2 | 2021-05-18 | [6 empty] | 2021-01-12 | 2021-03-16 | 2021-01-12 | 2021-04-05 | 57
120460773 | 651 | PGE | 94118 | NEM | VNEMSOMAH | Implementation | Solar PV | 100 |  | 2021-01-25 |  | 2021-02-08 | 2021-02-08 | 2021-02-08 | 10 | 2021-04-07 | 51 | 2021-04-28 | 15 | [15 empty] | 2021-04-28 | 2021-05-13 | 11 | 2021-05-13 | 2021-12-28 | 157 |  |  |  |  | 2021-01-25 | 2021-04-07 | 2021-01-25 | 2021-04-07 | 51 | 2021-07-09
120638418 | 652 | PGE | 94952 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 52.868 |  | 2021-03-12 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 7 | 2021-03-26 | 10 | 2021-04-09 | 10 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | [6 empty] | 2021-03-12 | 2021-06-18 | 2021-03-12 | 2021-07-09 | 83 |  | 2021-07-04 | 2021-07-04 | 0
120528116 | 653 | PGE | 94086 | NEM | VNEMSOMAH | Commercial | Solar PV | 100.91 |  | 2021-02-11 |  |  | 2021-02-24 | 2021-02-24 | 8 | 2021-02-24 | 8 | 2021-03-16 | 14 | [15 empty] | 2021-03-16 | 2021-04-06 | 15 | 2021-04-06 | 2021-09-21 | 117 | [5 empty] | 2021-02-24 | 2021-02-24 | 2021-02-25 | 1 |  | 2021-03-04 | 2021-03-12 | 6 | 2021-10-08 | 2021-10-13 | 3 | [15 empty] | 2021-10-08 | 2021-10-08 | 0 | 2021-10-13 |  | 2021-10-19 | 4
120528189 | 654 | PGE | 94086 | NEM | VNEMSOMAH | Commercial | Solar PV | 100.91 |  | 2021-02-11 |  |  | 2021-02-26 | 2021-02-26 | 10 | 2021-02-26 | 10 | 2021-03-17 | 13 | [15 empty] | 2021-03-17 | 2021-04-06 | 14 | 2021-04-06 | 2021-09-21 | 117 | [5 empty] | 2021-02-26 | 2021-02-26 | 2021-03-01 | 1 |  | 2021-03-04 | 2021-03-12 | 6 | 2021-10-08 | 2021-10-13 | 3 | [15 empty] | 2021-10-08 | 2021-10-08 | 0 | 2021-10-13 |  | 2021-10-19 | 4
120528270 | 655 | PGE | 94086 | NEM | VNEMSOMAH | Commercial | Solar PV | 72.22 |  | 2021-02-11 |  |  | 2021-02-26 | 2021-02-26 | 10 | 2021-02-26 | 10 | 2021-03-17 | 13 | [15 empty] | 2021-03-17 | 2021-04-06 | 14 | 2021-04-06 | 2021-09-21 | 117 | [5 empty] | 2021-03-09 | 2021-03-09 | 2021-03-10 | 1 |  | 2021-03-12 | 2021-03-12 | 0 | 2021-10-08 | 2021-10-13 | 3 | [15 empty] | 2021-10-08 | 2021-10-08 | 0 | 2021-10-13 |  | 2021-10-19 | 4
120531980 | 656 | PGE | 94040 | NEM | VNEMSOMAH | Implementation | Solar PV | 115.42 |  | 2021-02-12 |  | 2021-03-03 | 2021-03-03 | 2021-03-03 | 12 | 2021-03-05 | 14 | 2021-04-12 | 26 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-07-27 | 74 |  |  |  |  | 2021-02-12 | 2021-03-05 | 2021-02-12 | 2021-03-10 | 17 |  | 2021-03-24 | 2021-04-07 | 10
120601849 | 657 | PGE | 95130 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 111.038 |  | 2021-03-04 |  |  | 2021-03-15 | 2021-03-15 | 7 | 2021-03-15 | 7 | 2021-04-12 | 20 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-09-09 | 105 |  |  |  |  | 2021-03-04 | 2021-03-24 | 2021-03-04 | 2021-04-05 | 22 |  | 2021-04-12 | 2021-04-12 | 0
120506337 | 659 | PGE | 95476 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-02-08 | 2021-02-09 |  | 2021-02-08 | 2021-02-08 | 0 | 2021-03-03 | 16 | 2021-04-06 | 24 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-04-30 | 18 | [13 empty] | 2021-11-19 | 2021-12-02 | 7 | [15 empty] | 2021-11-19 | 2021-11-19 | 0 | 2021-12-02 |  | 2021-12-02 | 0
120538796 | 660 | PGE | 93950 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-02-17 | 2021-02-18 |  | 2021-02-17 | 2021-02-17 | 0 | 2021-03-03 | 10 | 2021-04-20 | 34 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-04-23 | 3 | [13 empty] | 2021-11-16 | 2021-11-30 | 8 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-30 |  | 2021-11-30 | 0
120538819 | 661 | PGE | 94403 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-02-17 | 2021-02-18 |  | 2021-02-18 | 2021-02-18 | 1 | 2021-03-03 | 10 | 2021-04-19 | 33 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-04-20 | 1
120539333 | 662 | PGE | 93960 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-02-17 | 2021-02-18 |  | 2021-02-18 | 2021-02-18 | 1 | 2021-03-03 | 10 | 2021-04-23 | 37 | [15 empty] | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | 2021-04-27 | 2 | [13 empty] | 2021-09-13 | 2021-09-24 | 9 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-24 |  | 2021-09-24 | 0
120539500 | 663 | PGE | 93644 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-02-17 | 2021-02-18 |  | 2021-02-18 | 2021-02-18 | 1 | 2021-03-03 | 10 | 2021-04-13 | 29 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-04-23 | 8 | [13 empty] | 2021-11-10 | 2021-12-02 | 13 | [15 empty] | 2021-11-10 | 2021-11-15 | 2 | 2021-12-02 |  | 2021-12-03 | 1
120542018 | 664 | PGE | 94952 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-02-17 | 2021-02-18 |  | 2021-02-18 | 2021-02-18 | 1 | 2021-03-03 | 10 | 2021-04-07 | 25 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-25 | 12 | [13 empty] | 2021-09-08 | 2021-09-16 | 6 | [15 empty] | 2021-09-08 | 2021-09-09 | 1 | 2021-09-16 |  | 2021-09-16 | 0
120553724 | 665 | PGE | 93722 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-02-18 | 2021-02-19 |  | 2021-02-19 | 2021-02-19 | 1 | 2021-03-03 | 9 | 2021-03-25 | 16 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-03-31 | 4 | [13 empty] | 2021-12-07 | 2021-12-16 | 7 | [15 empty] | 2021-12-07 | 2021-12-08 | 1 | 2021-12-16 |  | 2021-12-17 | 1
120565433 | 666 | PGE | 94720 | Non-NEM | Make Before Break | Implementation | ENGN | 4562 |  | 2021-02-22 | 2021-02-24 |  | 2021-02-23 | 2021-02-23 | 1 | 2021-03-30 | 26 | 2021-06-11 | 52 | [15 empty] | 2021-06-24 | 2021-09-10 | 54 | 2021-09-10 | 2021-09-27 | 11 | [19 empty] | 2021-10-04 | [14 empty] | 2021-09-28 | 2021-09-30 |  | 3 |  |  | 155
120581877 | 667 | PGE | 93458 | NEM | VNEMMASH | Implementation | Solar PV | 37.598 |  | 2021-02-26 |  | 2021-03-11 | 2021-03-11 | 2021-03-11 | 9 | 2021-05-11 | 52 | 2021-06-16 | 25 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | 2021-09-14 | 62 |  |  |  |  | 2021-02-26 | 2021-05-11 | 2021-02-26 | 2021-05-26 | 63
120593158 | 668 | PGE | 95404 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 54.65 |  | 2021-03-02 |  | 2021-06-01 | 2021-03-09 | 2021-03-09 | 5 | 2021-06-04 | 67 | 2021-06-04 | 0 | [34 empty] | 2021-06-04 | 2021-06-04 | 0 | [15 empty] | 2021-06-04 |  |  | 2021-06-04 |  | 2021-06-04 | 0
120659937 | 669 | PGE | 93710 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-03-11 | 2021-03-19 |  | 2021-03-19 | 2021-03-19 | 6 | 2021-03-31 | 14 | 2021-04-26 | 18 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-04-28 | 2 | [13 empty] | 2021-11-24 | [17 empty] | 2021-11-24 | 2021-11-29 | 1
120662541 | 670 | PGE | 95111 | Non-NEM | Make Before Break | Study in Progress | ENGN, Turbine | 30358.8 |  | 2021-03-19 | 2021-03-22 |  | 2021-03-19 | 2021-03-19 | 0 | 2021-03-31 | 8 | 2021-04-30 | 22 | 2021-08-02 | 2021-08-17 | 11 | 2021-09-09 | 2021-10-07 | 20 | 2021-10-07 | 2021-10-19 | 8 | 2021-10-29 |  |  | 2021-10-19 | 2021-10-19 | 0
120664959 | 671 | PGE | 93453 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 32.641 |  | 2021-03-19 |  | 2021-04-05 | 2021-03-24 | 2021-03-24 | 3 | 2021-04-07 | 13 | 2021-04-23 | 12 | [34 empty] | 2021-05-14 | 2021-06-08 | 16 | 2021-05-03 | 2021-08-09 | 68 |  |  |  | 2021-10-18 | 2021-12-17 | 41 | [6 empty] | 2021-05-14 | 2021-06-08 | 16 | 2021-06-08 | 2021-06-08 |  | 0 |  |  | 56
120672708 | 672 | PGE | 95337 | NEM | EXPNEM | Commercial | Solar PV | 30.402 |  | 2021-03-22 |  | 2021-04-05 | 2021-04-05 | 2021-04-05 | 10 | 2021-07-07 | 75 | 2021-07-21 | 10 | [15 empty] | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | 2021-07-26 | 3 | [13 empty] | 2021-08-23 | 2021-08-27 | 4 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-27 |  | 2021-08-31 | 2
120676644 | 673 | PGE | 94040 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-03-23 | 2021-03-24 |  | 2021-03-23 | 2021-03-23 | 0 | 2021-04-07 | 11 | 2021-06-23 | 54 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-07-14 | 14
120678216 | 674 | PGE | 95076 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.5 |  | 2021-03-23 |  | 2021-04-06 | 2021-04-06 | 2021-04-06 | 10 | 2021-05-05 | 31 | 2021-05-24 | 13 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-05-18 | 9 | [13 empty] | 2021-05-24 | 2021-05-24 | 0 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24 |  | 2021-05-25 | 1
120688511 | 675 | PGE | 95030 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.355 |  | 2021-03-25 |  | 2021-05-04 | 2021-04-02 | 2021-04-02 | 6 | [19 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04
120690329 | 676 | PGE | 93311 | Non-NEM | RESBCT | Implementation | Solar PV | 4500 |  | 2021-03-25 | 2021-03-26 |  | 2021-03-26 | 2021-03-26 | 1 | 2021-03-31 | 4 | [5 empty] | 2021-03-31 | 2021-04-28 | 20 | 2021-04-28 | 2021-04-28 | 0 | 2021-05-06 | 2021-09-17 | 93 | 2021-04-28 | 2021-04-29 | 1 | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | 2021-10-12 | 17 |  | 2021-08-24 | 2021-09-16 | 16
120691583 | 677 | PGE | 93446 | NEM | EXPNEM | IA in Progress | Solar PV | 114.141 |  | 2021-03-25 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 1 | 2021-05-03 | 27 | 2021-05-11 | 6 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11
120702459 | 678 | PGE | 94612 | NEM | EXPNEM | Commercial | Solar PV | 60.318 |  | 2021-03-27 |  | 2021-04-07 | 2021-04-07 | 2021-04-07 | 7 | 2021-07-12 | 73 | 2021-07-14 | 2 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-27 | 9 |  |  |  |  | 2021-03-27 | 2021-09-13 | 2021-03-27 | 2021-09-13 | 117 |  |  |  |  | 2021-11-02 | 2021-11-17 | 10 | [15 empty] | 2021-11-02 | 2021-11-02 | 0 | 2021-11-17 |  | 2021-11-22 | 3
120709097 | 679 | PGE | 93308 | NEM | EXPNEM | Commercial | Solar PV | 40.979 |  | 2021-03-29 |  | 2021-04-28 | 2021-04-06 | 2021-04-06 | 6 | 2021-05-03 | 25 | 2021-05-18 | 11 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | 2021-05-25 | 5 | [13 empty] | 2021-06-02 | 2021-06-10 | 6 | [15 empty] | 2021-06-02 | 2021-06-03 | 1 | 2021-06-10 |  | 2021-06-17 | 5
120709130 | 680 | PGE | 93309 | NEM | EXPNEM | Commercial | Solar PV | 57.927 |  | 2021-03-29 |  | 2021-04-26 | 2021-04-12 | 2021-04-12 | 10 | 2021-06-05 | 48 | 2021-06-23 | 12 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-07-19 | 17 |  |  |  |  | 2021-03-29 | 2021-06-05 | 2021-03-29 | 2021-06-16 | 56 |  |  |  |  | 2021-12-09 | 2021-12-17 | 6 | [15 empty] | 2021-12-09 | 2021-12-09 | 0 | 2021-12-17 |  | 2021-12-29 | 8
120722334 | 681 | PGE | 95448 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.612 |  | 2021-03-31 |  |  | 2021-04-14 | 2021-04-14 | 10 | 2021-04-14 | 10 | 2021-06-11 | 41 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19
120723303 | 682 | PGE | 95404 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 44.948 |  | 2021-04-01 |  | 2021-04-21 | 2021-04-15 | 2021-04-15 | 10 | 2021-04-15 | 10 | 2021-04-21 | 4 | [15 empty] | 2021-04-01 | 2021-04-01 |  | 2021-04-01 | 2021-04-01 | 1 |  |  |  |  | 2021-04-01 |  | 2021-04-01 | [6 empty] | 2021-04-29 | 2021-05-05 | 4 | [15 empty] | 2021-04-29 | 2021-04-29 | 0 | 2021-05-05 |  | 2021-05-05 | 0
120726657 | 683 | PGE | 95674 | NEM | EXPNEM | Implementation | Solar PV | 166.6 |  | 2021-04-01 |  | 2021-05-20 | 2021-04-05 | 2021-04-05 | 2 | 2021-05-21 | 36 | 2021-06-08 | 11 | 2021-06-08 | 2021-07-06 | 19 | 2021-07-06 | 2021-07-20 | 10 | 2021-07-20 |  |  |  | 2021-10-11 |  |  |  |  | 2021-10-11 | 2021-10-11 | 0 | 2021-10-11 | 2021-10-14 | 3 |  |  |  |  | 2021-04-01 | 2021-08-13 | 2021-04-01 | 2021-08-27 | 104 | [7 empty] | 2021-11-05 | 2022-01-07 | 41
120727153 | 684 | PGE | 93610 | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-04-01 |  |  | 2021-04-13 | 2021-04-13 | 8 | 2021-04-23 | 16 | 2021-05-11 | 12 | 2021-05-11 | 2021-06-01 | 14 | [12 empty] | 2021-06-01 | 2021-06-02 | 1 | 2021-06-02 | 2021-06-03 | 1 |  |  |  |  | 2021-04-01 | 2021-04-23 | 2021-04-01 | 2021-05-07 | 26
120727154 | 685 | PGE | 95945 | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2021-04-01 | 2021-04-05 |  | 2021-04-02 | 2021-04-02 | 1 | 2021-04-21 | 14 | 2021-06-11 | 36 | [15 empty] | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-09-13 | 64 |  |  |  |  | 2021-04-01 |  | 2021-04-01
120727269 | 686 | PGE | 95340 | NEM | EXPNEM | Implementation | Solar PV | 420 |  | 2021-04-01 |  |  | 2021-04-15 | 2021-04-15 | 10 | 2021-04-22 | 15 | 2021-05-11 | 13 | 2021-05-11 | 2021-06-03 | 16 | [12 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-11 | 6 | [16 empty] | 2021-11-05 | 2021-11-17 | 7
120727935 | 687 | PGE | 95035 | NEM | EXPNEM | IA in Progress | Solar PV | 47.27 |  | 2021-04-01 |  | 2021-04-02 | 2021-04-02 | 2021-04-02 | 1 | 2021-04-07 | 4 | 2021-04-26 | 13 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-06-01 | 25
120728241 | 688 | PGE | 95762 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 310.231 |  | 2021-04-01 |  | 2021-04-13 | 2021-04-13 | 2021-04-13 | 8 | 2021-10-29 | 148 | 2021-11-22 | 15 | 2021-11-22 | [24 empty] | 2021-04-01 |  | 2021-04-01 |  |  | 2021-10-14
120728327 | 689 | PGE | 95726 | Non-NEM | Non-Export | Implementation | Storage | 715 |  | 2021-03-25 | 2021-04-05 |  |  | 2021-04-05 | 7 | 2021-04-14 | 14 | 2021-05-20 | 26 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2021-07-21 | 42 |  |  |  |  | 2021-04-01 | 2021-06-09 | 2021-04-01 | 2021-07-09 | 69
120733969 | 690 | PGE | 93631 | NEM | EXPNEM | Implementation | Solar PV | 34.179 |  | 2021-04-02 |  | 2021-06-29 | 2021-04-14 | 2021-04-14 | 8 | 2021-07-19 | 74 | 2021-07-23 | 4 | [15 empty] | 2021-07-23 | 2021-07-23 | 0 | 2021-07-23 | 2021-08-06 | 10 |  |  |  |  | 2021-04-02 | 2021-07-22 | 2021-04-02 | 2021-08-06 | 88 | [7 empty] | 2021-09-17 | 2021-11-09 | 37 |  |  |  | 2021-11-10 | 2021-12-17 | 24
120734424 | 691 | PGE | 95317 | NEM | EXPNEM | Implementation | Solar PV | 38.78 |  | 2021-04-02 |  | 2021-05-25 | 2021-04-14 | 2021-04-14 | 8 | 2021-06-03 | 43 | 2021-06-21 | 12 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-07-13 | 15 |  |  |  |  | 2021-04-02 | 2021-06-17 | 2021-04-02 | 2021-07-02 | 64 |  |  |  |  | 2021-09-13 | 2021-09-21 | 6 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-21
120734966 | 692 | PGE | 93923 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 43.04 |  | 2021-04-02 |  |  | 2021-04-14 | 2021-04-14 | 8 | 2021-04-14 | 8 | 2021-04-20 | 4 | [15 empty] | 2021-04-14 | 2021-04-14 |  | 2021-04-14 | 2021-04-20 | 5 | [13 empty] | 2021-04-22 | 2021-04-22 | 0 | [15 empty] | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 |  | 2021-04-23 | 1
120735262 | 693 | PGE | 93280 | NEM | EXPNEM | Withdrawn | Solar PV | 1560 |  | 2021-04-02 | 2021-04-05 |  | 2021-04-02 | 2021-04-02 | 0 | 2021-04-14 | 8 | 2021-05-20 | 26 | [25 empty] | 2021-04-02 |  | 2021-04-02
120735552 | 694 | PGE | 95126 | NEM | VNEMSOMAH | Implementation | Solar PV | 50.396 |  | 2021-04-02 |  | 2021-04-08 | 2021-04-08 | 2021-04-08 | 4 | 2021-04-16 | 10 | 2021-05-21 | 25 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-07-27 | 45 |  |  |  |  | 2021-04-02 | 2021-06-14 | 2021-04-02 | 2021-06-24 | 58
120737106 | 695 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 33.614 |  | 2021-04-02 |  |  | 2021-04-13 | 2021-04-13 | 7 | 2021-04-13 | 7 | 2021-05-06 | 17 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 | [6 empty] | 2021-04-02 | 2021-05-12 | 2021-04-02 | 2021-05-26 | 38
120737194 | 696 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.179 |  | 2021-04-02 |  |  | 2021-04-13 | 2021-04-13 | 7 | 2021-04-13 | 7 | 2021-05-06 | 17 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 | [6 empty] | 2021-04-02 | 2021-05-12 | 2021-04-02 | 2021-05-26 | 38
120737196 | 697 | PGE | 94928 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 38.018 |  | 2021-04-02 |  |  | 2021-04-13 | 2021-04-13 | 7 | 2021-04-13 | 7 | 2021-07-16 | 66 | [15 empty] | 2021-07-16 | 2021-08-27 | 30 | 2021-08-27 | [6 empty] | 2021-04-02 | 2021-07-07 | 2021-04-02 | 2021-07-19 | 74
120737197 | 698 | PGE | 94928 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 30.402 |  | 2021-04-02 |  |  | 2021-04-13 | 2021-04-13 | 7 | 2021-04-13 | 7 | 2021-05-06 | 17 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 | [6 empty] | 2021-04-02 | 2021-07-07 | 2021-04-02 | 2021-07-19 | 74
120737359 | 699 | PGE | 93618 | NEM | EXPNEM | IA in Progress | Solar PV | 31.804 |  | 2021-04-02 |  | 2021-04-05 | 2021-04-05 | 2021-04-05 | 1 | 2021-04-05 | 1 | 2021-04-09 | 4 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | 2021-04-12 | 1 | [5 empty] | 2021-07-07 | 2021-07-07 | 2021-07-08 | 1 |  |  |  |  | 2021-08-20 | 2021-08-27 | 5 | 2021-06-15 | 2021-10-25 | 92 |  |  |  | 2021-11-30 | 0 | 32 | [6 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-27 | 2021-10-07 |  | 28 |  |  | 131
120737583 | 700 | PGE | 93446 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-04-02 |  | 2021-04-28 | 2021-04-14 | 2021-04-14 | 8 | 2021-05-10 | 26 | 2021-06-28 | 34 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-06-29 | 1 | [13 empty] | 2021-09-10 | 2021-09-23 | 9 | [15 empty] | 2021-09-10 | 2021-09-12 | 0 | 2021-09-23 |  | 2021-09-23 | 0
120738200 | 701 | PGE | 93309 | NEM | EXPNEM | Commercial | Solar PV | 101.728 |  | 2021-04-02 |  | 2021-05-04 | 2021-04-12 | 2021-04-12 | 6 | 2021-05-11 | 27 | 2021-06-25 | 32 | [15 empty] | 2021-07-13 | 2021-07-20 | 5 | 2021-07-20 | 2021-08-18 | 21 |  |  |  |  | 2021-04-02 |  | 2021-04-02 |  |  | 2021-08-27 |  |  |  | 2021-11-08 | 2021-11-16 | 5 | [15 empty] | 2021-11-08 | 2021-11-09 | 1 | 2021-11-16 |  | 2021-11-17 | 1
120738210 | 702 | PGE | 93309 | NEM | EXPNEM | Commercial | Solar PV | 178.024 |  | 2021-04-02 |  | 2021-05-06 | 2021-04-05 | 2021-04-05 | 1 | 2021-05-06 | 24 | 2021-06-30 | 38 | [15 empty] | 2021-06-30 | 2021-07-06 | 3 | 2021-07-06 | 2021-07-16 | 8 | [13 empty] | 2021-12-20 | 2021-12-28 | 6 | [15 empty] | 2021-12-20 | 2021-12-21 | 1 | 2021-12-28 |  | 2021-12-30 | 2
120741508 | 703 | PGE | 95476 | NEM | VNEM | Commercial | Solar PV | 34.639 |  | 2021-04-05 |  | 2021-04-14 | 2021-04-14 | 2021-04-14 | 7 | 2021-05-07 | 24 | 2021-06-09 | 22 | [15 empty] | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | 2021-06-14 | 3 | [5 empty] | 2021-06-17 | 2021-06-17 | 2021-06-17 | 0 |  | 2021-06-16 | 2021-06-16 | 0 | 2021-07-29 | 2021-08-03 | 3 | [15 empty] | 2021-07-29 | 2021-07-29 | 0 | 2021-08-03 |  | 2021-08-10 | 5
120742000 | 704 | PGE | 94608 | NEM | VNEM | Commercial | Solar PV | 54.828 |  | 2021-04-05 |  | 2021-04-14 | 2021-04-14 | 2021-04-14 | 7 | 2021-05-25 | 36 | 2021-06-11 | 12 | [15 empty] | 2021-06-11 | 2021-07-29 | 33 | 2021-07-29 | 2021-07-30 | 1 | [5 empty] | 2021-06-04 | 2021-06-04 | 2021-06-04 | 0 |  | 2021-06-04 | 2021-06-11 | 5 | 2021-08-03 | 2021-08-10 | 5 | [15 empty] | 2021-08-03 | 2021-08-03 | 0 | 2021-08-10 |  | 2021-08-12 | 2
120742847 | 705 | PGE | 94566 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 36.461 |  | 2021-04-05 |  |  | 2021-04-15 | 2021-04-15 | 8 | 2021-04-15 | 8 | 2021-04-19 | 2 | [15 empty] | 2021-04-05 | 2021-04-05 |  | 2021-04-05 | 2021-04-05 | 1 |  |  |  |  | 2021-04-05 | 2021-06-07 | 2021-04-05 | 2021-06-14 | 49
120743046 | 706 | PGE | 94515 | Non-NEM | Non-Export | Implementation | Storage | 429 |  | 2021-04-05 | 2021-04-19 |  | 2021-04-19 | 2021-04-19 | 10 | 2021-05-12 | 27 | 2021-08-23 | 71 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23 | 2021-08-30 | 5 | [5 empty] | 2021-06-14 | 2021-06-14 | 2021-07-09 | 18
120745137 | 707 | PGE | 96022 | NEM | EXPNEM | IA in Progress | Solar PV | 123.798 |  | 2021-04-05 |  | 2021-04-29 | 2021-04-16 | 2021-04-16 | 9 | 2021-05-10 | 25 | 2021-06-01 | 15 | [15 empty] | 2021-06-01 | 2021-06-01 | 0 | 2021-06-01
120745382 | 708 | PGE | 95360 | NEM | EXPNEM | Study in Progress | Solar PV | 1875 |  | 2021-04-05 | 2021-04-09 |  | 2021-04-06 | 2021-04-06 | 1 | 2021-05-12 | 27 | 2021-06-11 | 21 | 2021-07-06 | 2021-08-03 | 20 | 2021-09-03 | 2021-10-04 | 20 | 2021-10-04 |  | 1 | 2021-10-13 |  |  |  | 2021-10-04 | 7 | [10 empty] | 2021-04-05 |  | 2021-04-05
120746949 | 709 | PGE | 95448 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 32.178 |  | 2021-04-05 |  | 2021-04-15 | 2021-04-15 | 2021-04-15 | 8 | 2021-04-23 | 14 | 2021-04-27 | 2
120748479 | 710 | PGE | 95205 | NEM | EXPNEM | Commercial | Solar PV | 133.2 |  | 2021-04-06 |  | 2021-04-13 | 2021-04-08 | 2021-04-08 | 2 | 2021-04-14 | 6 | 2021-04-28 | 10 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-06-30 | 44 | [13 empty] | 2021-07-15 | 2021-07-22 | 5 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-22 |  | 2021-07-29 | 5
120748631 | 711 | PGE | 95762 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.341 |  | 2021-04-06 |  |  | 2021-04-20 | 2021-04-20 | 10 | 2021-04-20 | 10 | 2021-05-11 | 15 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-04-20 | 0 |  |  |  |  | 2021-04-06 | 2021-05-11 | 2021-04-06 | 2021-05-25 | 35 |  |  |  |  | 2021-05-28 | 2021-05-28 | 0 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 |  | 2021-05-28 | 0
120749173 | 712 | PGE | 95037 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.54 |  | 2021-04-06 |  | 2021-04-09 | 2021-04-08 | 2021-04-08 | 2 | 2021-06-08 | 44 | 2021-07-07 | 20 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | 2021-10-21 | 75 |  |  |  |  | 2021-04-06 | 2021-04-08 | 2021-04-06 | 2021-04-15 | 7 |  |  |  |  | 2021-10-21 | 2021-10-26 | 3 | [15 empty] | 2021-10-21 | 2021-10-22 | 1 | 2021-10-26 |  | 2021-10-27 | 1
120749736 | 713 | PGE | 95501 | Non-NEM | Non-Export | IA in Progress | Storage | 420 |  | 2021-04-06 | 2021-04-09 |  | 2021-04-08 | 2021-04-08 | 2 | 2021-05-12 | 26 | 2021-10-12 | 106 | [15 empty] | 2021-10-12 | 2021-10-12 | 0 | 2021-10-12 | [7 empty] | 2021-12-09 | 2021-12-09
120751228 | 714 | PGE | 95112 | Non-NEM | NEMFC | IA in Progress | FUCE | 525 |  | 2021-04-06 |  | 2021-04-20 | 2021-04-20 | 2021-04-20 | 10 | 2021-06-09 | 45 | 2021-10-21 | 94 | [15 empty] | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21 | 2021-12-17 | 38 | [16 empty] | 2020-01-14 | 2021-01-22 | 257 |  |  |  | 2021-10-19 | 0 | 59
120753059 | 715 | PGE | 94920 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 43.732 |  | 2021-04-06 |  |  | 2021-04-20 | 2021-04-20 | 10 | 2021-04-20 | 10 | 2021-05-06 | 12 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-05-05 | 11 | [13 empty] | 2021-12-13 | 2021-12-14 | 1 | [15 empty] | 2021-12-13 | 2021-12-14 | 1 | 2021-12-14 |  | 2021-12-14 | 0
120753598 | 716 | PGE | 95112 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 66.513 |  | 2021-04-06 |  |  | 2021-04-20 | 2021-04-20 | 10 | 2021-04-22 | 12 | 2021-05-27 | 25 | [15 empty] | 2021-05-27 | 2021-05-28 | 1 | 2021-05-28 | [6 empty] | 2021-04-06 |  | 2021-04-06 |  |  | 2021-06-11 | 2021-06-25 | 2021-06-25 | 10
120754663 | 717 | PGE | 95035 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.119 |  | 2021-04-07 |  |  | 2021-04-20 | 2021-04-20 | 9 | 2021-04-20 | 9 | 2021-05-06 | 12 | [15 empty] | 2021-04-07 | 2021-04-07 |  | 2021-04-07 | 2021-04-07 | 1 |  |  |  |  | 2021-04-07 |  | 2021-04-07 | [6 empty] | 2021-05-18 | 2021-05-18 | 0 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 |  | 2021-05-18 | 0
120755133 | 718 | PGE | 95138 | NEM | EXPNEM | Study in Progress | Solar PV | 912.4 |  | 2021-04-07 |  | 2021-11-30 | 2021-04-21 | 2021-04-21 | 10 | 2021-12-02 | 165 | [27 empty] | 2021-04-07 | 2021-05-05 | 2021-04-07 | 2021-05-25 | 34 | 2021-05-25
120756037 | 719 | PGE | 94583 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 72.22 |  | 2021-04-07 |  |  | 2021-04-13 | 2021-04-13 | 4 | 2021-04-14 | 5 | 2021-08-04 | 78 | [15 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | [6 empty] | 2021-04-07 | 2021-07-15 | 2021-04-07 | 2021-07-19 | 71 | 2021-04-29 | 2021-08-02 | 2021-08-04 | 65
120756234 | 720 | PGE | 94583 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 72.22 |  | 2021-04-07 |  |  | 2021-04-13 | 2021-04-13 | 4 | 2021-04-14 | 5 | 2021-08-04 | 78 | [15 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | [6 empty] | 2021-04-07 |  | 2021-04-07 |  |  | 2021-04-29 | 2021-05-13 | 2021-05-13 | 10
120756624 | 721 | PGE | 95602 | NEM | SNEM | Application Review in Progress | Solar PV | 6570 |  | 2021-04-07 |  | 2021-04-14 | 2021-04-14 | 2021-04-14 | 5
120759039 | 722 | PGE | 93311 | NEM | EXPNEM | Commercial | Solar PV | 72.55 |  | 2021-04-07 |  | 2021-04-08 | 2021-04-08 | 2021-04-08 | 1 | 2021-04-16 | 7 | 2021-04-27 | 7 | [15 empty] | 2021-04-27 | 2021-04-30 | 3 | 2021-04-30 | 2021-08-16 | 74 |  |  |  |  | 2021-04-07 | 2021-04-08 | 2021-04-07 | 2021-04-15 | 6 |  |  |  |  | 2021-09-16 | 2021-09-22 | 4 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-22 |  | 2021-09-27 | 3
120760228 | 723 | PGE | 94720 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 564.698 |  | 2021-04-07 |  | 2021-04-25 | 2021-04-22 | 2021-04-22 | 11 | 2021-06-17 | 50 | 2021-07-08 | 14 | 2021-07-27 | 2021-08-25 | 21 | [12 empty] | 2021-09-01 | 2021-09-16 | 10 | 2021-09-16 | [6 empty] | 2021-04-07 |  | 2021-04-07
120764579 | 724 | PGE | 95501 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 1930 |  | 2021-04-08 | 2021-04-14 |  | 2021-04-14 | 2021-04-14 | 4 | 2021-04-28 | 14 | [5 empty] | 2021-07-02 | 2021-07-28 | 17 | 2021-07-28 |  |  |  | 2021-10-18
120764598 | 725 | PGE | 95330 | NEM | EXPNEM | Commercial | Solar PV | 224.463 |  | 2021-04-08 |  |  | 2021-04-09 | 2021-04-09 | 1 | 2021-04-08 | 0 | 2021-04-29 | 15 | [15 empty] | 2021-04-29 | 2021-05-03 | 2 | 2021-05-03 | 2021-08-23 | 78 |  |  |  |  | 2021-04-08 | 2021-04-22 | 2021-04-08 | 2021-05-07 | 21 |  |  |  |  | 2021-08-24 | 2021-09-01 | 6 | 2021-08-05 |  | 111 |  |  |  | 2021-09-04 | 2021-09-04 | 0 | [6 empty] | 2021-08-24 | 2021-08-25 | 1 | 2021-09-01 |  | 2021-09-09 | 5
120765792 | 727 | PGE | 95603 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 43.2 |  | 2021-04-08 |  | 2021-04-17 | 2021-04-17 | 2021-04-17 | 6 | 2021-11-18 | 156 | 2021-12-10 | 14 | [15 empty] | 2021-12-10 | 2021-12-31 | 15 | 2021-12-31
120766845 | 728 | PGE | 93311 | NEM | EXPNEM | Application Review in Progress | Solar PV | 528.528 |  | 2021-04-08 |  |  | 2021-04-22 | 2021-04-22 | 10
120767244 | 729 | PGE | 95030 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 125.563 |  | 2021-04-08 |  | 2021-04-16 | 2021-04-16 | 2021-04-16 | 6 | 2021-07-20 | 71 | 2021-08-10 | 15 | [15 empty] | 2021-04-16 | 2021-04-16 |  | 2021-04-16 | 2021-05-13 | 20 | [13 empty] | 2021-08-10 | 2021-08-12 | 2 | [15 empty] | 2021-08-10 | 2021-08-11 | 1 | 2021-08-12 |  | 2021-08-12 | 0
120769789 | 730 | PGE | 94801 | NEM | EXPNEM | Commercial | Solar PV | 91.863 |  | 2021-04-09 |  | 2021-04-12 | 2021-04-12 | 2021-04-12 | 1 | 2021-04-13 | 2 | 2021-04-28 | 11 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-04-29 | 1 | [13 empty] | 2021-05-03 | 2021-05-11 | 6 | [15 empty] | 2021-05-03 | 2021-05-04 | 1 | 2021-05-11 |  | 2021-05-14 | 3
120770341 | 731 | PGE | 94597 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.52 |  | 2021-04-09 |  |  | 2021-04-22 | 2021-04-22 | 9 | 2021-04-22 | 9 | 2021-04-26 | 2 | [15 empty] | 2021-04-09 | 2021-04-09 |  | 2021-04-09 | 2021-04-09 | 1 | [13 empty] | 2021-04-26 | 2021-04-26 | 0 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 |  | 2021-04-26 | 0
120770571 | 732 | PGE | 95776 | NEM | EXPNEM | IA in Progress | Solar PV | 39.739 |  | 2021-04-09 |  | 2021-04-15 | 2021-04-12 | 2021-04-12 | 1 | 2021-05-11 | 22 | 2021-05-24 | 9 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24
120771011 | 733 | PGE | 94506 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 |  | 2021-04-09 |  |  | 2021-04-13 | 2021-04-13 | 2 | 2021-04-13 | 2 | 2021-04-14 | 1 | [15 empty] | 2021-04-09 | 2021-04-09 |  | 2021-04-09 | 2021-04-09 | 1 | [13 empty] | 2021-06-01 | 2021-06-03 | 2 | [15 empty] | 2021-06-01 | 2021-06-01 | 0 | 2021-06-03 |  | 2021-06-03 | 0
120772377 | 734 | PGE | 94565 | NEM | EXPNEM | Commercial | Solar PV | 36.83 |  | 2021-04-09 |  | 2021-06-30 | 2021-04-12 | 2021-04-12 | 1 | 2021-07-01 | 58 | 2021-07-27 | 17 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-08-20 | 18 |  |  |  |  | 2021-04-12 | 2021-08-09 | 2021-04-12 | 2021-08-18 | 90 |  |  |  |  | 2021-08-27 | 2021-09-02 | 4 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-09-02 |  | 2021-09-13 | 6
120772942 | 735 | PGE | 95969 | Non-NEM | Non-Export | Withdrawn | Storage | 490 |  | 2021-04-09 | 2021-04-14 |  | 2021-04-14 | 2021-04-14 | 3 | 2021-04-21 | 8 | 2021-06-15 | 38 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-15 | [6 empty] | 2021-04-09 |  | 2021-04-09
120773604 | 736 | PGE | 94027 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 32.678 |  | 2021-04-09 |  | 2021-04-22 | 2021-04-22 | 2021-04-22 | 9 | 2021-05-05 | 18 | 2021-05-18 | 9 | [15 empty] | 2021-04-22 | 2021-04-22 |  | 2021-04-22 | 2021-04-27 | 4
120774008 | 737 | PGE | 94022 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 36.403 |  | 2021-04-09 |  | 2021-04-22 | 2021-04-22 | 2021-04-22 | 9 | 2021-05-05 | 18 | 2021-05-17 | 8 | [15 empty] | 2021-04-22 | 2021-04-22 |  | 2021-04-22 | 2021-04-23 | 2
120774032 | 738 | PGE | 95030 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.007 |  | 2021-04-09 |  | 2021-04-13 | 2021-04-13 | 2021-04-13 | 2 | 2021-08-20 | 93 | 2021-08-25 | 3 | [15 empty] | 2021-05-13 | 2021-05-13 |  | 2021-05-13 | 2021-05-13 | 1 | [13 empty] | 2021-08-25 | 2021-08-25 | 0 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 |  | 2021-08-25 | 0
120792184 | 739 | PGE | 93434 | NEM | VNEM | Commercial | Solar PV | 46.946 |  | 2021-04-11 |  | 2021-04-15 | 2021-04-15 | 2021-04-15 | 3 | 2021-07-01 | 57 | 2021-08-06 | 25 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | 2021-08-09 | 1 | [5 empty] | 2021-07-07 | 2021-07-07 | 2021-07-19 | 8 |  | 2021-08-02 | 2021-08-06 | 4 | 2021-09-25 | 2021-10-06 | 7 | [15 empty] | 2021-09-25 | 2021-09-27 | 0 | 2021-10-06 |  | 2021-10-12 | 4
120794139 | 740 | PGE | 94952 | NEM | EXPNEM | Commercial | Solar PV | 193.173 |  | 2021-04-12 |  | 2021-04-21 | 2021-04-12 | 2021-04-12 | 0 | 2021-04-26 | 10 | 2021-05-12 | 12 | [15 empty] | 2021-05-12 | 2021-05-12 | 0 | 2021-05-12 | 2021-05-17 | 3 |  |  |  |  | 2021-04-12 | 2021-04-26 | 2021-04-12 | 2021-05-10 | 20 |  |  |  |  | 2021-05-19 | 2021-06-16 | 19 | [15 empty] | 2021-05-19 | 2021-06-09 | 14 | 2021-06-16 |  | 2021-06-23 | 5
120794825 | 741 | PGE | 94062 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.48 |  | 2021-04-12 |  | 2021-04-16 | 2021-04-16 | 2021-04-16 | 4 | 2021-04-22 | 8 | 2021-05-05 | 9 | [15 empty] | 2021-04-12 | 2021-04-12 |  | 2021-04-12 | 2021-04-12 | 1 | [13 empty] | 2021-05-05 | 2021-05-05 | 0 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 |  | 2021-05-05 | 0
120795295 | 742 | PGE | 94608 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-04-12 |  | 2021-05-18 | 2021-05-05 | 2021-05-05 | 17 | 2021-06-10 | 42 | 2021-06-16 | 4 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | 2021-07-02 | 12 | [5 empty] | 2021-07-08 | 2021-07-08 | 2021-07-19 | 7 |  |  |  |  | 2021-10-28 | 2021-11-04 | 5 | 2021-07-20 | 2021-11-07 | 78 | [12 empty] | 2021-10-28 | 2021-10-29 | 1 | 2021-11-04 |  | 2021-11-10 | 4
120796075 | 743 | PGE | 93244 | NEM | EXPNEM | Implementation | Solar PV | 125 |  | 2021-04-12 |  | 2021-04-23 | 2021-04-23 | 2021-04-23 | 9 | 2021-06-10 | 42 | [17 empty] | 2021-07-02 | 2021-07-19 | 10 | 2021-07-19 | 2021-07-19 | 0 |  |  |  |  | 2021-04-12 | 2021-06-07 | 2021-04-12 | 2021-06-16 | 46 |  |  |  |  | 2021-08-02 | 2021-08-12 | 8 | 2021-07-16 | 2021-11-29 | 92 |  |  |  | 2022-01-03 | 0 | 9 | [6 empty] | 2021-08-02 | 2021-08-02 | 0 | 2021-08-12 | 2021-08-16 |  | 2 |  |  | 88
120799551 | 744 | PGE | 95963 | NEM | EXPNEM | Commercial | Solar PV | 43.875 |  | 2021-04-12 |  | 2021-05-24 | 2021-04-28 | 2021-04-28 | 12 | 2021-05-24 | 30 | 2021-06-08 | 10 | [15 empty] | 2021-06-08 | 2021-06-28 | 14 | 2021-06-28 | 2021-08-13 | 33 |  |  |  |  | 2021-04-12 | 2021-06-28 | 2021-04-12 | 2021-07-15 | 66 | 2021-08-06 |  |  |  | 2021-09-03 | 2021-09-20 | 10 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-20 |  | 2021-09-20 | 0
120803445 | 745 | PGE | 93206 | NEM | EXPNEM | IA in Progress | Solar PV | 900 |  | 2021-04-13 |  |  | 2021-04-28 | 2021-04-28 | 11 | 2021-04-29 | 12 | [5 empty] | 2021-04-29 | 2021-06-04 | 25 | 2021-06-04 |  |  |  | 2021-09-01 |  |  |  |  | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01
120803549 | 746 | PGE | 95648 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.559 |  | 2021-04-13 |  |  | 2021-04-26 | 2021-04-26 | 9 | 2021-04-26 | 9 | 2021-05-11 | 11 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-05-24 | 20 | [13 empty] | 2021-05-25 | 2021-05-26 | 1 | [15 empty] | 2021-05-25 | 2021-05-26 | 1 | 2021-05-26 |  | 2021-05-26 | 0
120804361 | 747 | PGE | 93266 | NEM | EXPNEM | Implementation | Solar PV | 300 |  | 2021-04-13 |  | 2021-04-26 | 2021-04-19 | 2021-04-19 | 4 | 2021-05-20 | 27 | 2021-06-09 | 13 | 2021-06-09 | 2021-07-07 | 19 | [12 empty] | 2021-07-07 | 2021-07-12 | 3 | 2021-07-12 | 2021-07-12 | 0 |  |  |  |  | 2021-04-13 | 2021-04-26 | 2021-04-13 | 2021-05-10 | 19
120806392 | 748 | PGE | 94062 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 37.8 |  | 2021-04-13 |  |  | 2021-04-14 | 2021-04-14 | 1 | 2021-04-14 | 1 | 2021-04-30 | 12 | [15 empty] | 2021-04-23 | 2021-04-23 |  | 2021-04-23 | 2021-04-30 | 6 | [13 empty] | 2021-06-01 | 2021-06-01 | 0 | [15 empty] | 2021-06-01 | 2021-06-01 | 0 | 2021-06-01 |  | 2021-06-01 | 0
120807556 | 749 | PGE | 93656 | NEM | EXPNEM | Commercial | Solar PV | 165.405 |  | 2021-04-13 |  | 2021-04-28 | 2021-04-28 | 2021-04-28 | 11 | 2021-05-21 | 28 | 2021-06-04 | 9 | [15 empty] | 2021-06-04 | 2021-06-04 | 0 | 2021-06-04 | 2021-06-07 | 1 |  |  |  |  | 2021-04-13 | 2021-05-24 | 2021-04-13 | 2021-06-03 | 36 |  |  |  |  | 2021-07-30 | 2021-08-09 | 6 | [15 empty] | 2021-07-30 | 2021-08-02 | 1 | 2021-08-09 |  | 2021-08-09 | 0
120807656 | 750 | PGE | 95545 | NEM | EXPNEM | IA in Progress | Solar PV | 31.024 |  | 2021-04-13 |  | 2021-05-06 | 2021-04-15 | 2021-04-15 | 2 | 2021-05-06 | 17 | 2021-07-09 | 44 | [15 empty] | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09 | [6 empty] | 2021-04-13 | 2021-06-02 | 2021-04-13 | 2021-06-15 | 44
120807659 | 751 | PGE | 95545 | NEM | EXPNEM | IA in Progress | Solar PV | 31.024 |  | 2021-04-13 |  | 2021-04-28 | 2021-04-15 | 2021-04-15 | 2 | 2021-04-28 | 11 | 2021-05-13 | 11 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13 | [6 empty] | 2021-04-13 | 2021-07-20 | 2021-04-13 | 2021-07-29 | 75
120808104 | 752 | PGE | 95341 | NEM | EXPNEM | Commercial | Solar PV | 40.1 |  | 2021-04-13 |  | 2021-04-14 | 2021-04-14 | 2021-04-14 | 1 | 2021-04-29 | 12 | 2021-05-12 | 9 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13 | 2021-05-24 | 7 | [5 empty] | 2021-08-09 | 2021-08-09 | 2021-08-18 | 7 | 2021-09-27 |  |  |  | 2021-10-20 | 2021-10-28 | 6 | [15 empty] | 2021-10-20 | 2021-10-21 | 1 | 2021-10-28 |  | 2021-10-28 | 0
120808780 | 753 | PGE | 95640 | NEM | EXPNEM | Commercial | Solar PV | 36 |  | 2021-04-13 |  |  | 2021-04-14 | 2021-04-14 | 1 | 2021-04-14 | 1 | 2021-04-28 | 10 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-05-03 | 3 | [13 empty] | 2021-07-23 | 2021-07-29 | 4 | [15 empty] | 2021-07-23 | 2021-07-23 | 0 | 2021-07-29 |  | 2021-08-10 | 8
120808879 | 754 | PGE | 95746 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.36 |  | 2021-04-13 |  |  | 2021-04-26 | 2021-04-26 | 9 | 2021-04-26 | 9 | 2021-05-11 | 11 | [15 empty] | 2021-04-13 | 2021-04-13 |  | 2021-04-13 | 2021-04-13 | 1 | [13 empty] | 2021-05-11 | 2021-05-12 | 1 | [15 empty] | 2021-05-11 | 2021-05-12 | 1 | 2021-05-12 |  | 2021-05-12 | 0
120809109 | 755 | PGE | 94539 | NEM | EXPNEM | Commercial | Solar PV | 52.33 |  | 2021-04-13 |  | 2021-04-21 | 2021-04-14 | 2021-04-14 | 1 | 2021-04-23 | 8 | 2021-04-26 | 1 | [15 empty] | 2021-04-26 | 2021-05-12 | 12 | 2021-05-12 | 2021-05-14 | 2 |  |  |  |  | 2021-04-13 | 2021-04-26 | 2021-04-13 | 2021-05-10 | 19 |  |  |  |  | 2021-08-05 | 2021-08-18 | 9 | [15 empty] | 2021-08-05 | 2021-08-18 | 9 | 2021-08-18 |  | 2021-08-23 | 3
120809175 | 756 | PGE | 95669 | NEM | EXPNEM | Implementation | Solar PV | 200 |  | 2021-04-13 |  | 2021-04-14 | 2021-04-14 | 2021-04-14 | 1 | 2021-04-19 | 4 | 2021-05-04 | 11 | 2021-05-04 | 2021-06-01 | 19 | 2021-06-10 | 2021-07-08 | 19 | 2021-07-08 | 2021-07-14 | 4 |  | 2021-10-06 |  | 2021-07-14 |  |  | 2021-10-06 | 2021-10-06 | 0 | 2021-10-06 | 2021-11-19 | 31 |  |  |  |  | 2021-04-13 | 2021-04-28 | 2021-04-13 | 2021-05-10 | 19
120809811 | 757 | PGE | 95476 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 69.278 |  | 2021-04-13 |  | 2021-04-20 | 2021-04-20 | 2021-04-20 | 5 | 2021-04-30 | 13 | 2021-06-16 | 32 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | [6 empty] | 2021-04-13 |  | 2021-04-13
120812770 | 758 | PGE | 95236 | NEM | EXPNEM | IA in Progress | Solar PV | 31.024 |  | 2021-04-14 |  | 2021-05-18 | 2021-04-23 | 2021-04-23 | 7 | 2021-05-25 | 29 | [17 empty] | 2021-07-22 | 2021-08-24 | 23 | 2021-08-24 | [6 empty] | 2021-04-14 | 2021-06-14 | 2021-04-14 | 2021-06-18 | 46
120812930 | 759 | PGE | 93907 | NEM | EXPNEM | Implementation | Solar PV | 300 |  | 2021-04-14 |  | 2021-04-29 | 2021-04-27 | 2021-04-27 | 9 | 2021-06-08 | 38 | [5 empty] | 2021-06-08 | 2021-07-06 | 19 | 2021-07-06 |  |  |  | 2021-11-09 |  |  |  |  | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | 2021-12-07 | 17
120814029 | 760 | PGE | 95304 | NEM | EXPNEM | Application Review in Progress | Solar PV | 37.858 |  | 2021-04-14 |  | 2021-04-26 | 2021-04-26 | 2021-04-26 | 8
120814896 | 761 | PGE | 95448 | NEM | EXPNEM | Implementation | Solar PV | 33.504 |  | 2021-04-14 |  | 2021-05-24 | 2021-04-26 | 2021-04-26 | 8 | 2021-06-10 | 40 | 2021-07-07 | 18 | [15 empty] | 2021-07-07 | 2021-07-16 | 7 | 2021-07-16 | 2021-07-16 | 0 |  |  |  |  | 2021-04-14 |  | 2021-04-14 |  |  | 2021-06-17
120815794 | 762 | PGE | 93726 | NEM | EXPNEM | Commercial | Solar PV | 215.661 |  | 2021-04-14 |  | 2021-04-15 | 2021-04-15 | 2021-04-15 | 1 | 2021-05-13 | 21 | 2021-05-28 | 11 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | 2021-07-12 | 29 |  |  |  |  | 2021-04-14 | 2021-06-11 | 2021-04-14 | 2021-06-17 | 45 |  |  |  |  | 2021-11-19 | 2021-12-02 | 7 | [15 empty] | 2021-11-19 | 2021-11-23 | 2 | 2021-12-02 |  | 2021-12-09 | 5
120816189 | 763 | PGE | 93286 | NEM | EXPNEM | IA in Progress | Solar PV | 375 |  | 2021-04-14 |  | 2021-06-23 | 2021-04-27 | 2021-04-27 | 9 | 2021-08-31 | 97 | 2021-10-06 | 25 | 2021-10-06 | 2021-11-02 | 19 | [12 empty] | 2021-11-02 | 2021-11-03 | 1 | 2021-11-03 | [6 empty] | 2021-04-14 |  | 2021-04-14 |  |  | 2021-09-08
120816701 | 764 | PGE | 93230 | NEM | EXPNEM | Withdrawn | Solar PV | 2760 |  | 2021-04-14 | 2021-04-16 |  | 2021-04-16 | 2021-04-16 | 2 | 2021-04-21 | 5 | 2021-06-16 | 39 | [25 empty] | 2021-04-14 |  | 2021-04-14
120816753 | 765 | PGE | 95501 | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2021-04-14 | 2021-04-16 |  | 2021-04-16 | 2021-04-16 | 2 | 2021-05-12 | 20 | 2021-07-15 | 44 | [15 empty] | 2021-07-15 | 2021-07-16 | 1 | 2021-07-16 | 2021-10-14 | 63 |  |  |  |  | 2021-04-14 |  | 2021-04-14
120822175 | 766 | PGE | 93307 | NEM | EXPNEM | Application Review in Progress | Solar PV | 272.254 |  | 2021-04-15 |  | 2021-05-19 | 2021-04-28 | 2021-04-28 | 9
120822307 | 767 | PGE | 93446 | NEM | EXPNEM | Commercial | Solar PV | 300 |  | 2021-04-15 |  | 2021-05-20 | 2021-04-28 | 2021-04-28 | 9 | 2021-06-04 | 35 | 2021-06-14 | 6 | [15 empty] | 2021-06-14 | 2021-07-01 | 13 | 2021-07-01 | 2021-12-03 | 106 | [13 empty] | 2021-12-03 | 2021-12-20 | 11 | [15 empty] | 2021-12-03 | 2021-12-06 | 1 | 2021-12-20 |  | 2021-12-20 | 0
120822482 | 768 | PGE | 95955 | NEM | EXPNEM | IA in Progress | Solar PV | 88.18 |  | 2021-04-15 |  | 2021-04-20 | 2021-04-16 | 2021-04-16 | 1 | 2021-04-28 | 9 | 2021-05-19 | 15 | 2021-05-19 | 2021-07-09 | 35 | [12 empty] | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09 | 2021-11-12 | 88 | [13 empty] | 2021-12-27 | [17 empty] | 2021-12-27 | 2021-12-28 | 1
120823102 | 769 | PGE | 94583 | NEM | EXPNEM | Withdrawn | Solar PV | 240 |  | 2021-04-15 |  | 2021-04-16 | 2021-04-16 | 2021-04-16 | 1 | 2021-05-04 | 13 | 2021-06-28 | 38 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | [6 empty] | 2021-04-15 | 2021-05-19 | 2021-04-15 | 2021-05-28 | 31
120823257 | 770 | PGE | 94583 | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-04-15 |  | 2021-04-16 | 2021-04-16 | 2021-04-16 | 1 | 2021-05-04 | 13 | 2021-07-08 | 45 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [6 empty] | 2021-04-15 | 2021-05-17 | 2021-04-15 | 2021-05-18 | 23
120823543 | 771 | PGE | 95215 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2043.114 |  | 2021-04-15 | 2021-04-20 |  | 2021-04-20 | 2021-04-20 | 3 | 2021-05-05 | 14 | 2021-07-31 | 60 | 2021-08-30 | 2021-10-13 | 31 | 2021-11-08 | 2021-12-08 | 19 | 2021-12-08 | 2021-12-08 | 0 |  |  |  | 2021-12-08 | 2021-12-08 | 0 | [10 empty] | 2021-04-15 |  | 2021-04-15 |  |  | 2021-07-21 | 2021-07-22 |  | 1
120823637 | 772 | PGE | 93638 | Non-NEM | Non-Export | IA in Progress | ENGN | 4500 |  | 2021-04-15 | 2021-04-16 |  | 2021-04-16 | 2021-04-16 | 1 | 2021-04-21 | 4 | 2021-05-24 | 23 | 2021-07-16 | 2021-08-17 | 22 | [12 empty] | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26
120825142 | 773 | PGE | 94558 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-04-16 | 2021-04-16 |  | 2021-04-16 | 2021-04-16 | 0 | 2021-04-28 | 8 | 2021-07-02 | 46 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-10-07 | 67 | [13 empty] | 2021-11-12 | 2021-11-18 | 4 | [15 empty] | 2021-11-12 | 2021-11-12 | 0 | 2021-11-18 |  | 2021-11-19 | 1
120826645 | 774 | PGE | 94598 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-04-16 |  | 2021-04-27 | 2021-04-27 | 2021-04-27 | 7 | 2021-05-07 | 15 | 2021-05-10 | 1 | [15 empty] | 2021-04-27 | 2021-04-27 |  | 2021-04-27 | 2021-05-07 | 9 | [13 empty] | 2021-05-10 | 2021-05-10 | 0 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 |  | 2021-05-10 | 0
120827781 | 775 | PGE | 93660 | NEM | EXPNEM | Commercial | Solar PV | 62.5 |  | 2021-04-16 |  | 2021-04-19 | 2021-04-19 | 2021-04-19 | 1 | 2021-05-21 | 25 | 2021-06-05 | 9 | [15 empty] | 2021-06-05 | 2021-06-05 | 0 | 2021-06-05 | 2021-06-11 | 4 |  |  |  |  | 2021-04-16 | 2021-05-27 | 2021-04-16 | 2021-06-15 | 41 |  |  |  |  | 2021-11-03 | 2021-11-12 | 6 | [15 empty] | 2021-11-03 | 2021-11-03 | 0 | 2021-11-12 |  | 2021-11-19 | 5
120828526 | 776 | PGE | 95206 | NEM | EXPNEM | Application Review in Progress | Solar PV | 379.1 |  | 2021-04-16 |  | 2021-04-29 | 2021-04-29 | 2021-04-29 | 9
120828870 | 777 | PGE | 95677 | NEM | EXPNEM | Commercial | Solar PV | 98.987 |  | 2021-04-16 |  | 2021-04-19 | 2021-04-19 | 2021-04-19 | 1 | 2021-04-22 | 4 | 2021-05-04 | 8 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | 2021-07-01 | 41 |  |  |  |  | 2021-04-16 | 2021-07-16 | 2021-04-16 | 2021-07-23 | 68 |  |  |  |  | 2021-07-12 | 2021-07-22 | 8 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-22 |  | 2021-07-29 | 5
120828873 | 778 | PGE | 95348 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-04-16 |  | 2021-06-14 | 2021-04-19 | 2021-04-19 | 1 | 2021-06-16 | 42 | 2021-07-01 | 11 | [15 empty] | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01 | 2021-10-28 | 83 |  |  |  |  | 2021-04-16 | 2021-06-16 | 2021-04-16 | 2021-06-24 | 48 |  |  |  |  | 2021-10-29 | 2021-11-01 | 1 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-11-01 |  | 2021-11-03 | 2
120830341 | 779 | PGE | 95677 | NEM | VNEMSOMAH | Implementation | Solar PV | 86.4 |  | 2021-04-16 |  | 2021-05-04 | 2021-04-30 | 2021-04-30 | 10 | 2021-06-11 | 39 | 2021-07-02 | 15 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-11-22 | 98 | [5 empty] | 2021-06-28 | 2021-06-28 | 2021-07-15 | 12 |  | 2021-07-19 | 2021-07-19 | 0
120830947 | 780 | PGE | 93245 | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-04-16 |  | 2021-05-12 | 2021-04-30 | 2021-04-30 | 10 | 2021-07-15 | 62 | 2021-09-08 | 38 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | [6 empty] | 2021-04-16 | 2021-06-19 | 2021-04-16 | 2021-07-02 | 54
120831810 | 781 | PGE | 93631 | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2021-04-16 |  |  | 2021-04-19 | 2021-04-19 | 1 | 2021-04-19 | 1 | 2021-04-23 | 4 | [15 empty] | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | [6 empty] | 2021-04-16 | 2021-04-21 | 2021-04-16 | 2021-05-07 | 15
120842473 | 782 | PGE | 95206 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2012.104 |  | 2021-04-19 | 2021-04-21 |  | 2021-04-19 | 2021-04-19 | 0 | 2021-05-05 | 12 | 2021-08-03 | 62 | 2021-08-30 | 2021-10-13 | 31 | 2021-11-08 | 2021-12-08 | 19 | 2021-12-08 | [18 empty] | 2021-04-19 |  | 2021-04-19 |  |  | 2021-07-22 | 2021-07-22 |  | 0
120842663 | 783 | PGE | 93638 | NEM | EXPNEM | Commercial | Solar PV | 170 |  | 2021-04-19 |  | 2021-04-19 | 2021-04-19 | 2021-04-19 | 0 | 2021-06-10 | 37 | 2021-06-29 | 13 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | 2021-08-19 | 36 |  |  |  |  | 2021-04-19 | 2021-08-19 | 2021-04-19 | 2021-09-07 | 98 |  |  |  |  | 2021-12-06 | 2021-12-16 | 8 | 2021-09-30 | 2021-09-30 | 0 | [12 empty] | 2021-12-06 | 2021-12-07 | 1 | 2021-12-16 |  | 2021-12-21 | 3
120844725 | 784 | PGE | 93638 | NEM | EXPNEM | IA in Progress | Solar PV | 196 |  | 2021-04-19 |  | 2021-04-19 | 2021-04-19 | 2021-04-19 | 0 | 2021-06-10 | 37 | 2021-06-29 | 13 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | 2021-08-25 | 40 |  |  |  |  | 2021-04-19 | 2021-08-04 | 2021-04-19 | 2021-08-05 | 76 | [7 empty] | 2021-11-15 | 2021-11-15 | 0
120847643 | 785 | PGE | 94928 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-04-19 | 2021-04-21 |  | 2021-04-21 | 2021-04-21 | 2 | 2021-05-05 | 12 | 2021-07-06 | 42 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-09-20 | 53 | [13 empty] | 2021-10-20 | 2021-11-04 | 11 | [15 empty] | 2021-10-20 | 2021-10-20 | 0 | 2021-11-04 |  | 2021-11-04 | 0
120851262 | 786 | PGE | 95242 | Non-NEM | NEMFC | Implementation | FUCE | 1470 |  | 2021-04-20 |  | 2021-05-04 | 2021-05-04 | 2021-05-04 | 10 | 2021-05-06 | 12 | 2021-07-27 | 56 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-10-22 | 62 | [19 empty] | 2021-12-09
120854663 | 787 | PGE | 95020 | NEM | EXPNEM | IA in Progress | Solar PV | 300 |  | 2021-04-20 |  | 2021-05-04 | 2021-05-04 | 2021-05-04 | 10 | 2021-05-14 | 18 | 2021-08-09 | 59 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-07-13 | 28 | [5 empty] | 2021-06-17 | 2021-06-17 | 2021-07-02 | 11 |  |  |  |  | 2021-11-05 |  |  | 2021-09-01 | 2022-01-04 | 84 | [12 empty] | 2021-11-05 | 2021-11-05 | 0
120854836 | 788 | PGE | 93631 | NEM | EXPNEM | Commercial | Solar PV | 240 |  | 2021-04-20 |  | 2021-04-21 | 2021-04-21 | 2021-04-21 | 1 | 2021-04-28 | 6 | 2021-05-10 | 8 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2021-11-12 | 130 |  |  |  |  | 2021-04-20 | 2021-04-21 | 2021-04-20 | 2021-05-07 | 13 |  |  |  |  | 2021-11-23 | 2021-12-03 | 6 | [15 empty] | 2021-11-23 | 2021-11-24 | 1 | 2021-12-03 |  | 2021-12-09 | 4
120855236 | 789 | PGE | 93618 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-04-20 |  | 2021-04-21 | 2021-04-21 | 2021-04-21 | 1 | 2021-04-27 | 5 | 2021-05-10 | 9 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | [6 empty] | 2021-04-20 | 2021-04-27 | 2021-04-20 | 2021-05-10 | 14
120855661 | 790 | PGE | 93618 | NEM | EXPNEM | IA in Progress | Solar PV | 117.475 |  | 2021-04-20 |  | 2021-04-21 | 2021-04-21 | 2021-04-21 | 1 | 2021-04-28 | 6 | 2021-05-12 | 10 | [15 empty] | 2021-05-12 | 2021-05-12 | 0 | 2021-05-12 | 2021-06-11 | 21 | [16 empty] | 2021-07-16 | 2021-12-08 | 99 |  |  |  | 2022-01-13 | 0 | 1
120855807 | 792 | PGE | 93673 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-04-20 |  | 2021-04-21 | 2021-04-21 | 2021-04-21 | 1 | 2021-04-28 | 6 | 2021-05-11 | 9 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2021-11-24 | 137 |  |  |  |  | 2021-04-20 | 2021-04-21 | 2021-04-20 | 2021-05-07 | 13 |  |  |  |  | 2021-11-26 | 2021-12-06 | 5 | [15 empty] | 2021-11-26 | 2021-11-29 | 0 | 2021-12-06 |  | 2021-12-10 | 4
120855838 | 793 | PGE | 93662 | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2021-04-20 |  | 2021-04-21 | 2021-04-21 | 2021-04-21 | 1 | 2021-04-28 | 6 | 2021-05-11 | 9 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | [6 empty] | 2021-04-20 | 2021-04-21 | 2021-04-20 | 2021-05-07 | 13
120856990 | 794 | PGE | 95050 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 279.436 |  | 2021-04-21 |  | 2021-05-06 | 2021-05-06 | 2021-05-06 | 11 | 2021-06-15 | 38 | 2021-07-28 | 30 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | 2021-08-09 | 8 | [9 empty] | 2021-07-08 | 2021-07-21 | 2021-07-28 | 9
120859634 | 795 | PGE | 94040 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.564 |  | 2021-04-21 |  | 2021-04-26 | 2021-04-26 | 2021-04-26 | 3 | 2021-05-20 | 21 | 2021-05-24 | 2 | [15 empty] | 2021-05-20 | 2021-05-20 |  | 2021-05-20 | 2021-05-20 | 1 | [13 empty] | 2021-09-09 | 2021-09-09 | 0 | [15 empty] | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 |  | 2021-09-09 | 0
120860814 | 796 | PGE | 94087 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-04-21 |  | 2021-04-29 | 2021-04-29 | 2021-04-29 | 6 | 2021-05-04 | 9 | 2021-05-25 | 15 | [15 empty] | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-06-14 | 13 | [13 empty] | 2021-06-14 | 2021-06-23 | 7 | [15 empty] | 2021-06-14 | 2021-06-15 | 1 | 2021-06-23 |  | 2021-06-24 | 1
120860895 | 797 | PGE | 95963 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-04-21 |  | 2021-06-15 | 2021-04-22 | 2021-04-22 | 1 | 2021-06-18 | 41 | 2021-07-08 | 13 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-15 | 5 |  |  |  |  | 2021-04-21 | 2021-05-17 | 2021-04-21 | 2021-05-18 | 19 |  |  |  |  | 2021-07-15 | 2021-07-20 | 3 | [15 empty] | 2021-07-15 | 2021-07-16 | 1 | 2021-07-20 |  | 2021-07-27 | 5
120862032 | 798 | PGE | 93420 | NEM | EXPNEM | Study in Progress | Solar PV | 61.513 |  | 2021-04-21 |  | 2021-11-16 | 2021-05-04 | 2021-05-04 | 9
120863035 | 799 | PGE | 95687 | Non-NEM | NEMFC | Implementation | FUCE | 262.5 |  | 2021-04-22 |  |  | 2021-05-06 | 2021-05-06 | 10 | 2021-05-06 | 10 | 2021-05-27 | 15 | [15 empty] | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-10-11 | 94 |  |  |  |  | 2021-04-22 |  | 2021-04-22
120863572 | 800 | PGE | 94538 | NEM | EXPNEM | Implementation | Solar PV | 89.246 |  | 2021-04-22 |  | 2021-05-14 | 2021-05-04 | 2021-05-04 | 8 | 2021-05-17 | 17 | 2021-06-28 | 29 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-07-12 | 9 |  |  |  |  | 2021-04-22 | 2021-08-24 | 2021-04-22 | 2021-09-08 | 96 | 2021-07-29 |  |  |  | 2021-09-10 | 2021-09-21 | 7 | [15 empty] | 2021-09-10 | 2021-09-13 | 1 | 2021-09-21
120864448 | 801 | PGE | 93420 | Non-NEM | Non-Export | Withdrawn | Storage | 420 |  | 2021-04-22 | 2021-04-23 |  | 2021-04-23 | 2021-04-23 | 1 | 2021-05-19 | 19 | 2021-06-18 | 21 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-18 | 2021-06-23 | 3 |  |  |  |  | 2021-04-22 |  | 2021-04-22
120864514 | 802 | PGE | 95441 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 36.12 |  | 2021-04-22 |  | 2021-04-27 | 2021-04-27 | 2021-04-27 | 3 | 2021-04-27 | 3 | 2021-04-28 | 1 | [15 empty] | 2021-04-22 | 2021-04-22 |  | 2021-04-22 | 2021-04-27 | 4 | [13 empty] | 2021-04-28 | 2021-05-05 | 5 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-05-05 |  | 2021-05-06 | 1
120865154 | 803 | PGE | 95404 | NEM | EXPNEM | IA in Progress | Solar PV | 326.971 |  | 2021-04-22 |  | 2021-04-23 | 2021-04-23 | 2021-04-23 | 1 | 2021-04-30 | 6 | 2021-05-19 | 13 | [15 empty] | 2021-05-19 | 2021-05-19 | 0 | 2021-05-19 | 2021-05-25 | 4 |  |  |  |  | 2021-04-22 | 2021-04-23 | 2021-04-22 | 2021-05-07 | 11
120866578 | 804 | PGE | 95688 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.38 |  | 2021-04-22 |  | 2021-04-30 | 2021-04-30 | 2021-04-30 | 6 | 2021-05-05 | 9 | 2021-05-14 | 7 | [15 empty] | 2021-04-30 | 2021-04-30 |  | 2021-04-30 | 2021-05-14 | 11 | [13 empty] | 2021-05-14 | 2021-05-14 | 0 | [15 empty] | 2021-05-14 | 2021-05-14 | 0 | 2021-05-14 |  | 2021-05-17 | 1
120866974 | 805 | PGE | 93454 | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-04-22 |  | 2021-05-20 | 2021-04-23 | 2021-04-23 | 1 | 2021-05-03 | 7 | 2021-05-21 | 14 | [15 empty] | 2021-05-21 | 2021-06-16 | 17 | 2021-06-16
120866976 | 806 | PGE | 95320 | NEM | EXPNEM | Commercial | Solar PV | 86 |  | 2021-04-22 |  |  | 2021-05-04 | 2021-05-04 | 8 | 2021-05-04 | 8 | 2021-05-26 | 16 | [15 empty] | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 | 2021-08-24 | 62 |  |  |  |  | 2021-05-26 | 2021-08-25 | 2021-05-26 | 2021-09-08 | 72 |  |  |  |  | 2021-10-13 | 2021-10-19 | 4 | [15 empty] | 2021-10-13 | 2021-10-14 | 1 | 2021-10-19 |  | 2021-10-19 | 0
120867210 | 807 | PGE | 94574 | NEM | EXPNEM | Commercial | Solar PV | 116.6 |  | 2021-04-22 |  | 2021-04-28 | 2021-04-26 | 2021-04-26 | 2 | 2021-06-02 | 28 | 2021-06-21 | 13 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-23 | 2 | [13 empty] | 2021-07-17 | 2021-07-28 | 7 | [15 empty] | 2021-07-17 | 2021-07-19 | 0 | 2021-07-28 |  | 2021-10-27 | 64
120869339 | 809 | PGE | 95602 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 38.019 |  | 2021-04-22 |  | 2021-05-03 | 2021-05-03 | 2021-05-03 | 7 | 2021-05-03 | 7 | 2021-05-05 | 2 | [15 empty] | 2021-05-03 | 2021-05-03 |  | 2021-05-03 | 2021-05-03 | 1 | [13 empty] | 2021-05-05 | 2021-05-05 | 0 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 |  | 2021-05-10 | 3
120869498 | 810 | PGE | 95565 | Non-NEM | Non-Export | Implementation | Storage | 572 |  | 2021-04-22 | 2021-04-23 |  | 2021-04-23 | 2021-04-23 | 1 | 2021-05-19 | 19 | 2021-09-10 | 79 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | 2021-12-16 | 66 |  |  |  |  | 2021-04-22 | 2021-06-04 | 2021-04-22 | 2021-06-16 | 38
120872340 | 811 | PGE | 95076 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 35.116 |  | 2021-04-23 |  | 2021-05-05 | 2021-05-05 | 2021-05-05 | 8 | 2021-06-22 | 41 | 2021-06-23 | 1 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-06-22 | 33
120872738 | 812 | PGE | 94560 | NEM | EXPNEM | IA in Progress | Solar PV | 908.3 |  | 2021-04-23 |  | 2021-04-29 | 2021-04-29 | 2021-04-29 | 4 | 2021-04-30 | 5 | 2021-05-17 | 11 | 2021-07-07 | 2021-08-05 | 21 | [12 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05
120873403 | 813 | PGE | 93637 | NEM | EXPNEM | Commercial | Solar PV | 240 |  | 2021-04-23 |  | 2021-05-04 | 2021-05-04 | 2021-05-04 | 7 | 2021-05-17 | 16 | 2021-06-01 | 10 | [15 empty] | 2021-06-01 | 2021-06-10 | 7 | 2021-06-10 | 2021-08-18 | 48 |  |  |  |  | 2021-04-23 | 2021-06-10 | 2021-04-23 | 2021-06-17 | 38 |  |  |  |  | 2021-11-24 | 2021-12-02 | 4 | 2021-09-28 | 2021-09-28 | 0 | [12 empty] | 2021-11-24 | 2021-11-24 | 0 | 2021-12-02 |  | 2021-12-03 | 1
120873418 | 814 | PGE | 93637 | NEM | EXPNEM | Commercial | Solar PV | 240 |  | 2021-04-23 |  | 2021-05-04 | 2021-05-04 | 2021-05-04 | 7 | 2021-05-21 | 20 | 2021-06-02 | 7 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-08-25 | 59 |  |  |  |  | 2021-04-23 | 2021-06-10 | 2021-04-23 | 2021-06-17 | 38 |  |  |  |  | 2021-12-03 | 2021-12-14 | 7 | 2021-09-28 | 2021-09-28 | 0 | [12 empty] | 2021-12-03 | 2021-12-06 | 1 | 2021-12-14 |  | 2021-12-14 | 0
120873425 | 815 | PGE | 93638 | NEM | EXPNEM | Implementation | Solar PV | 320 |  | 2021-04-23 |  | 2021-05-05 | 2021-05-04 | 2021-05-04 | 7 | 2021-06-08 | 31 | 2021-06-23 | 11 | [15 empty] | 2021-08-03 | 2021-08-03 | 0 | 2021-08-03 | 2021-08-18 | 11 |  |  |  |  | 2021-04-23 | 2021-08-03 | 2021-04-23 | 2021-08-13 | 78 | [7 empty] | 2021-11-10 | 2021-11-10 | 0
120874705 | 816 | PGE | 95206 | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-04-23 |  | 2021-04-26 | 2021-04-26 | 2021-04-26 | 1 | 2021-04-29 | 4 | 2021-05-20 | 15 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2021-05-24 | 2 |  |  |  |  | 2021-04-23 | 2021-04-26 | 2021-04-23 | 2021-05-10 | 11 |  |  |  |  | 2021-12-23 | 2021-12-30 | 5 | 2021-08-23 | 2021-09-09 | 12 | [12 empty] | 2021-12-23 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-31 |  | 1 |  |  | 174
120875063 | 817 | PGE | 96080 | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2021-04-23 | 2021-04-27 |  | 2021-04-27 | 2021-04-27 | 2 | 2021-05-19 | 18 | 2021-06-17 | 20 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-08-11 | 38 |  |  |  |  | 2021-04-23 |  | 2021-04-23
120875131 | 818 | PGE | 96080 | NEM | EXPNEM | Implementation | Solar PV | 375 |  | 2021-04-23 |  | 2021-05-05 | 2021-05-05 | 2021-05-05 | 8 | 2021-05-21 | 20 | 2021-06-28 | 25 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-09-24 | 62 |  |  |  |  | 2021-04-23 | 2021-05-21 | 2021-04-23 | 2021-06-03 | 28
120875952 | 819 | PGE | 94605 | NEM | EXPNEM | Commercial | Solar PV | 300 |  | 2021-04-23 |  | 2021-04-26 | 2021-04-26 | 2021-04-26 | 1 | 2021-06-05 | 29 | 2021-06-16 | 7 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | 2021-10-12 | 82 | [13 empty] | 2021-11-17 | 2021-11-29 | 6 | [15 empty] | 2021-11-17 | 2021-11-17 | 0 | 2021-11-29 |  | 2021-12-02 | 3
120876292 | 820 | PGE | 95125 | NEM | EXPNEM | Commercial | Solar PV | 30.45 |  | 2021-04-23 |  | 2021-05-17 | 2021-05-04 | 2021-05-04 | 7 | 2021-05-18 | 17 | 2021-06-03 | 11 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-16 | 9 |  |  |  |  | 2021-04-23 | 2021-05-17 | 2021-04-23 | 2021-05-28 | 25 |  |  |  |  | 2021-08-18 | 2021-08-25 | 5 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-25 |  | 2021-08-30 | 3
120876297 | 821 | PGE | 94024 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 38.23 |  | 2021-04-23 |  | 2021-05-05 | 2021-05-05 | 2021-05-05 | 8 | 2021-05-20 | 19 | 2021-05-24 | 2 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-05-25 | 14 | [13 empty] | 2021-08-13 | 2021-08-23 | 6 | [15 empty] | 2021-08-13 | 2021-08-13 | 0 | 2021-08-23 |  | 2021-08-23 | 0
120876541 | 822 | PGE | 93637 | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2021-04-23 |  | 2021-06-03 | 2021-05-05 | 2021-05-05 | 8 | 2021-06-02 | 27 | 2021-06-17 | 11 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-06-29 | 8 |  |  |  |  | 2021-04-23 | 2021-06-04 | 2021-04-23 | 2021-06-15 | 36
120876608 | 823 | PGE | 94062 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 52.72 |  | 2021-04-23 |  | 2021-05-05 | 2021-05-05 | 2021-05-05 | 8 | 2021-05-26 | 23 | 2021-06-03 | 5 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-07-14 | 48 | [13 empty] | 2021-07-30 | 2021-08-04 | 3 | [15 empty] | 2021-07-30 | 2021-07-30 | 0 | 2021-08-04 |  | 2021-08-05 | 1
120876757 | 824 | PGE | 93451 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 1804.932 |  | 2021-04-23 | 2021-04-27 |  | 2021-04-27 | 2021-04-27 | 2 | 2021-06-09 | 32 | 2021-10-18 | 91 | 2021-11-03 | 2021-12-30 | 38 | [22 empty] | 2021-04-23 |  | 2021-04-23
120876784 | 825 | PGE | 93637 | NEM | NEMMT | IA in Progress | Solar PV, Storage | 478 |  | 2021-04-23 |  | 2021-05-10 | 2021-05-10 | 2021-05-10 | 11 | 2021-06-15 | 36 | 2021-07-07 | 15 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | [11 empty] | 2021-09-22 | 2021-10-01 | 2021-10-15 | 7
120876852 | 826 | PGE | 95472 | NEM | EXPNEM | Commercial | Solar PV | 30.45 |  | 2021-04-23 |  | 2021-05-13 | 2021-04-28 | 2021-04-28 | 3 | 2021-05-24 | 21 | 2021-06-10 | 12 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-06-21 | 7 |  |  |  |  | 2021-04-23 | 2021-05-13 | 2021-04-23 | 2021-05-26 | 23 |  |  |  |  | 2021-12-06 | 2021-12-23 | 13 | 2021-08-16 | 2021-11-22 | 68 |  |  |  | 2021-11-24 | 2021-12-27 | 20 | [6 empty] | 2021-12-06 | 2021-12-07 | 1 | 2021-12-23 | 2021-12-23 | 2021-12-29 | 0 |  |  | 168
120876953 | 827 | PGE | 95616 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-04-23 | 2021-04-26 |  | 2021-04-26 | 2021-04-26 | 1 | 2021-05-12 | 13 | 2021-07-12 | 41 | [15 empty] | 2021-07-12 | 2021-07-30 | 14 | 2021-07-30 | 2021-08-11 | 8
120877425 | 828 | PGE | 93614 | NEM | EXPNEM | Commercial | Solar PV | 69.457 |  | 2021-04-23 |  | 2021-05-05 | 2021-05-05 | 2021-05-05 | 8 | 2021-06-08 | 31 | 2021-06-22 | 10 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-06-29 | 5 | [13 empty] | 2021-10-07 | 2021-10-14 | 5 | [15 empty] | 2021-10-07 | 2021-10-08 | 1 | 2021-10-14 |  | 2021-10-14 | 0
120881225 | 829 | PGE | 95423 | NEM | EXPNEM | Application Accepted | Solar PV | 32.505 |  | 2021-04-25 |  | 2021-05-06 | 2021-05-06 | 2021-05-06 | 8 | 2021-05-21 | 19 | 2021-06-09 | 12 | [25 empty] | 2021-04-25 |  | 2021-04-25
120881315 | 830 | PGE | 95116 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-04-25 | 2021-04-26 |  | 2021-04-26 | 2021-04-26 | 0 | 2021-05-12 | 12 | 2021-07-02 | 36 | [15 empty] | 2021-07-02 | 2021-07-23 | 14 | 2021-07-23 | 2021-08-11 | 13
120883454 | 831 | PGE | 94612 | NEM | EXPNEM | IA in Progress | Solar PV | 41.566 |  | 2021-04-26 |  | 2021-08-03 | 2021-04-27 | 2021-04-27 | 1 | 2021-08-09 | 73 | 2021-08-25 | 12 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | 2021-09-07 | 8 |  |  |  |  | 2021-05-07 | 2021-08-25 | 2021-05-07 | 2021-09-08 | 85
120884810 | 832 | PGE | 94558 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 58.082 |  | 2021-04-26 |  | 2021-05-12 | 2021-05-07 | 2021-05-07 | 9 | 2021-05-13 | 13 | 2021-05-17 | 2 | [15 empty] | 2021-05-17 | 2021-05-17 | 0 | 2021-05-17 | 2021-11-02 | 118 | [5 empty] | 2021-05-17 | 2021-05-17 | 2021-05-28 | 9 |  |  |  |  | 2021-11-23 |  |  | 2021-12-17 |  | 19 | [12 empty] | 2021-11-23 | 2021-11-23 | 0
120885848 | 833 | PGE | 93622 | NEM | EXPNEM | Commercial | Solar PV | 30.165 |  | 2021-04-26 |  | 2021-04-27 | 2021-04-27 | 2021-04-27 | 1 | 2021-05-05 | 7 | 2021-05-21 | 12 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-08-31 | 70 | [13 empty] | 2021-10-06 | 2021-10-14 | 6 | [15 empty] | 2021-10-06 | 2021-10-06 | 0 | 2021-10-14 |  | 2021-10-21 | 5
120885849 | 834 | PGE | 93637 | NEM | EXPNEM | Implementation | Solar PV | 530 |  | 2021-04-26 |  | 2021-05-07 | 2021-05-07 | 2021-05-07 | 9 | 2021-06-08 | 30 | 2021-06-24 | 12 | [15 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-24 | 2021-08-17 | 37 | [5 empty] | 2021-08-17 | 2021-08-17 | 2021-08-31 | 10
120886344 | 835 | PGE | 93638 | NEM | EXPNEM | Commercial | Solar PV | 520 |  | 2021-04-26 |  | 2021-05-10 | 2021-05-10 | 2021-05-10 | 10 | 2021-05-18 | 16 | 2021-06-07 | 13 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-08-25 | 56 | [5 empty] | 2021-06-09 | 2021-06-09 | 2021-06-17 | 6 |  |  |  |  | 2021-12-06 | 2021-12-16 | 8 | [15 empty] | 2021-12-06 | 2021-12-07 | 1 | 2021-12-16 |  | 2021-12-17 | 1
120887117 | 836 | PGE | 94720 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 2119.8 |  | 2021-04-26 | 2021-04-29 |  | 2021-04-29 | 2021-04-29 | 3 | 2021-05-26 | 22 | 2021-07-01 | 25 | 2021-07-22 | 2021-08-25 | 24 | [12 empty] | 2021-09-15 | [9 empty] | 2021-04-26 |  | 2021-04-26
120887228 | 837 | PGE | 93662 | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2021-04-26 |  |  | 2021-04-27 | 2021-04-27 | 1 | 2021-04-27 | 1 | 2021-05-10 | 9 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | [6 empty] | 2021-04-26 | 2021-05-06 | 2021-04-26 | 2021-05-25 | 21
120887293 | 838 | PGE | 94024 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 40.591 |  | 2021-04-26 |  |  | 2021-05-07 | 2021-05-07 | 9 | 2021-05-07 | 9 | 2021-05-24 | 11 | [15 empty] | 2021-05-07 | 2021-05-07 | 0 | 2021-05-07 | 2021-05-11 | 2 | [13 empty] | 2021-08-17 | 2021-08-24 | 5 | [15 empty] | 2021-08-17 | 2021-08-17 | 0 | 2021-08-24 |  | 2021-08-25 | 1
120887432 | 839 | PGE | 93618 | NEM | EXPNEM | Commercial | Solar PV | 58.738 |  | 2021-04-26 |  |  | 2021-04-27 | 2021-04-27 | 1 | 2021-04-27 | 1 | 2021-05-10 | 9 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2021-12-01 | 141 |  |  |  |  | 2021-04-26 | 2021-05-06 | 2021-04-26 | 2021-05-25 | 21 |  |  |  |  | 2021-12-14 | 2021-12-22 | 6 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-22 |  | 2021-12-27 | 3
120887512 | 840 | PGE | 93242 | NEM | EXPNEM | IA in Progress | Solar PV | 46.99 |  | 2021-04-26 |  |  | 2021-04-27 | 2021-04-27 | 1 | 2021-04-27 | 1 | 2021-05-10 | 9 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | [6 empty] | 2021-04-26 | 2021-05-10 | 2021-04-26 | 2021-05-26 | 22
120888831 | 841 | PGE | 95946 | NEM | EXPNEM | Implementation | Solar PV | 34.179 |  | 2021-04-27 |  | 2021-05-07 | 2021-04-28 | 2021-04-28 | 1 | 2021-05-18 | 15 | 2021-06-09 | 15 | 2021-06-09 | 2021-07-08 | 20 | 2021-07-21 | 2021-08-18 | 20 | 2021-08-18 |  |  |  | 2021-11-10 |  |  |  |  | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | 2021-12-16 | 23 |  |  |  |  | 2021-04-27 |  | 2021-04-27 |  |  | 2021-05-25
120889138 | 842 | PGE | 94538 | NEM | EXPNEM | Commercial | Solar PV | 65.188 |  | 2021-04-27 |  | 2021-06-15 | 2021-04-28 | 2021-04-28 | 1 | 2021-06-17 | 36 | 2021-07-09 | 15 | [15 empty] | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12 | 2021-09-21 | 50 | [13 empty] | 2021-10-05 | 2021-10-13 | 6 | [15 empty] | 2021-10-05 | 2021-10-06 | 1 | 2021-10-13 |  | 2021-10-19 | 4
120889784 | 843 | PGE | 93637 | NEM | EXPNEM | Implementation | Solar PV | 192 |  | 2021-04-27 |  | 2021-05-03 | 2021-05-03 | 2021-05-03 | 4 | 2021-05-10 | 9 | 2021-06-03 | 17 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-08-25 | 58 |  |  |  |  | 2021-04-27 |  | 2021-04-27
120890108 | 844 | PGE | 94583 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-04-27 |  |  | 2021-05-03 | 2021-05-03 | 4 | 2021-05-03 | 4 | 2021-05-20 | 13 | [34 empty] | 2021-05-21 | 2021-05-21 | 0 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 |  | 2021-05-21 | 0
120890366 | 845 | PGE | 93637 | NEM | EXPNEM | Implementation | Solar PV | 410.518 |  | 2021-04-27 |  | 2021-05-03 | 2021-05-03 | 2021-05-03 | 4 | 2021-06-16 | 35 | 2021-06-28 | 8 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-08-16 | 34 |  |  |  |  | 2021-04-27 | 2021-08-16 | 2021-04-27 | 2021-08-27 | 86
120890711 | 846 | PGE | 95926 | NEM | EXPNEM | Withdrawn | Solar PV | 177.127 |  | 2021-04-27 |  | 2021-05-11 | 2021-05-11 | 2021-05-11 | 10
120890756 | 847 | PGE | 95422 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 206.6 |  | 2021-04-27 |  |  | 2021-05-10 | 2021-05-10 | 9 | 2021-05-10 | 9 | 2021-08-16 | 68 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | 2021-10-11 | 39 |  |  |  |  | 2021-04-27 |  | 2021-04-27
120891405 | 848 | PGE | 93647 | NEM | EXPNEM | Application Review in Progress | Solar PV | 206.358 |  | 2021-04-27 |  | 2021-05-10 | 2021-05-10 | 2021-05-10 | 9 | [29 empty] | 2021-04-27 |  | 2021-04-27
120891861 | 849 | PGE | 93673 | NEM | EXPNEM | Commercial | Solar PV | 36 |  | 2021-04-27 |  |  | 2021-04-28 | 2021-04-28 | 1 | 2021-04-28 | 1 | 2021-05-11 | 9 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2021-10-12 | 107 |  |  |  |  | 2021-04-27 | 2021-05-06 | 2021-04-27 | 2021-05-25 | 20 |  |  |  |  | 2021-10-19 | 2021-10-27 | 6 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-27 |  | 2021-11-01 | 3
120892017 | 850 | PGE | 93618 | NEM | EXPNEM | Commercial | Solar PV | 36 |  | 2021-04-27 |  | 2021-04-29 | 2021-04-29 | 2021-04-29 | 2 | 2021-04-29 | 2 | 2021-05-11 | 8 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2021-12-02 | 141 |  |  |  |  | 2021-04-27 | 2021-04-29 | 2021-04-27 | 2021-05-10 | 9 |  |  |  |  | 2021-12-03 | 2021-12-10 | 5 | [15 empty] | 2021-12-03 | 2021-12-06 | 1 | 2021-12-10 |  | 2021-12-17 | 5
120893156 | 851 | PGE | 93311 | NEM | EXPNEM | IA in Progress | Solar PV | 240 |  | 2021-04-27 |  |  | 2021-05-03 | 2021-05-03 | 4 | 2021-05-03 | 4 | 2021-05-20 | 13 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20
120894133 | 852 | PGE | 95205 | NEM | EXPNEM | Implementation | Solar PV | 56.869 |  | 2021-04-28 |  | 2021-05-10 | 2021-05-03 | 2021-05-03 | 3 | 2021-05-19 | 15 | 2021-06-02 | 9 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-08-02 | 42
120896852 | 853 | PGE | 95667 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-04-28 | 2021-05-03 |  | 2021-04-28 | 2021-04-28 | 0 | 2021-05-26 | 20 | 2021-06-30 | 24 | [15 empty] | 2021-06-30 | 2021-07-20 | 13 | 2021-07-20 | 2021-08-30 | 29 |  |  |  |  | 2021-04-28 | 2021-06-18 | 2021-04-28 | 2021-06-21 | 37
120897331 | 854 | PGE | 95687 | Non-NEM | NEMFC | IA in Progress | FUCE | 262.5 |  | 2021-04-28 |  | 2021-05-12 | 2021-05-12 | 2021-05-12 | 10 | 2021-07-09 | 50 | 2021-09-02 | 39 | [15 empty] | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02 | 2021-10-27 | 38 |  |  |  |  | 2021-04-28 | 2021-07-09 | 2021-04-28 | 2021-07-19 | 56
120897465 | 855 | PGE | 95133 | NEM | EXPNEM | Implementation | Solar PV | 34.082 |  | 2021-04-28 |  | 2021-05-03 | 2021-05-03 | 2021-05-03 | 3 | 2021-05-20 | 16 | 2021-06-10 | 14 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-06-17 | 5 |  |  |  |  | 2021-04-28 |  | 2021-04-28 |  |  | 2021-08-26
120897470 | 856 | PGE | 93422 | Non-NEM | Non-Export | Study in Progress | Storage | 929.5 |  | 2021-04-28 | 2021-05-03 |  | 2021-05-03 | 2021-05-03 | 3 | 2021-05-26 | 20 | 2021-06-17 | 15 | 2021-07-23 | 2021-08-20 | 20 | 2021-09-03 | 2021-09-27 | 15 | 2021-09-27 |  |  |  | 2021-11-15 |  |  |  |  | 2021-12-14 | 2021-12-15 | 1 | 2021-12-15 | [6 empty] | 2021-04-28 | 2021-05-27 | 2021-04-28 | 2021-05-27 | 21
120897509 | 857 | PGE | 93908 | NEM | NEM Paired Storage | Study in Progress | ENGN, Solar PV, Storage | 3443.5 |  | 2021-04-28 |  | 2021-08-10 | 2021-05-06 | 2021-05-06 | 6 | 2021-08-23 | 81 | 2021-09-13 | 14 | 2021-09-23 | 2021-11-30 | 45 | 2021-12-16
120897689 | 858 | PGE | 94561 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-04-28 |  | 2021-05-21 | 2021-04-29 | 2021-04-29 | 1 | 2021-05-28 | 22 | 2021-06-02 | 2 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-06-08 | 4 | [13 empty] | 2021-07-15 | 2021-07-29 | 10 | [15 empty] | 2021-07-15 | 2021-07-21 | 4 | 2021-07-29 |  | 2021-08-04 | 4
120897974 | 859 | PGE | 93906 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2071.458 |  | 2021-04-28 | 2021-05-03 |  | 2021-05-03 | 2021-05-03 | 3 | 2021-05-26 | 20 | 2021-12-10 | 136
120897990 | 860 | PGE | 95361 | NEM | EXPNEM | Commercial | Solar PV | 53.84 |  | 2021-04-28 |  | 2021-04-29 | 2021-04-29 | 2021-04-29 | 1 | 2021-05-06 | 6 | 2021-05-25 | 13 | [15 empty] | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-05-27 | 2 | [5 empty] | 2021-06-02 | 2021-06-02 | 2021-06-15 | 9 |  |  |  |  | 2021-08-06 | 2021-08-20 | 10 | [15 empty] | 2021-08-06 | 2021-08-20 | 10 | 2021-08-20 |  | 2021-08-27 | 5
120899666 | 861 | PGE | 95032 | NEM | EXPNEM | Commercial | Solar PV | 31.024 |  | 2021-04-29 |  | 2021-05-11 | 2021-04-29 | 2021-04-29 | 0 | 2021-06-08 | 27 | 2021-06-29 | 15 | [34 empty] | 2021-06-29 | 2021-07-15 | 11 | [15 empty] | 2021-06-29 | 2021-07-22 | 16 | 2021-07-15 |  | 2021-07-20 | 3
120900572 | 862 | PGE | 93263 | NEM | EXPNEM | Implementation | Solar PV | 600 |  | 2021-04-29 |  |  | 2021-05-11 | 2021-05-11 | 8 | 2021-05-13 | 10 | [5 empty] | 2021-05-13 | 2021-06-11 | 20 | 2021-06-11 |  |  |  | 2021-09-03 |  |  |  |  | 2021-09-03 | 2021-09-03 |  | 2021-09-03 | 2021-09-20 | 12 | 10 | [8 empty] | 2021-10-08 | [6 empty] | 2021-11-11 |  | 42
120900752 | 863 | PGE | 95119 | NEM | EXPNEM | Application Review in Progress | Solar PV | 45.653 |  | 2021-04-29 |  | 2021-05-10 | 2021-05-10 | 2021-05-10 | 7
120904132 | 864 | PGE | 95334 | NEM | EXPNEM | Commercial | Solar PV | 187.5 |  | 2021-04-29 |  | 2021-05-10 | 2021-04-29 | 2021-04-29 | 0 | 2021-05-12 | 9 | 2021-05-28 | 12 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | 2021-06-09 | 7 |  |  |  |  | 2021-04-29 | 2021-05-10 | 2021-04-29 | 2021-05-26 | 19 |  |  |  |  | 2021-09-01 | 2021-09-09 | 5 | [15 empty] | 2021-09-01 | 2021-09-02 | 1 | 2021-09-09 |  | 2021-09-16 | 5
120904630 | 865 | PGE | 95688 | NEM | EXPNEM | IA in Progress | Solar PV | 180 |  | 2021-04-29 |  | 2021-05-10 | 2021-05-10 | 2021-05-10 | 7 | 2021-08-02 | 65 | 2021-08-18 | 12 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | [6 empty] | 2021-04-29 | 2021-11-02 | 2021-04-29 | 2021-11-30 | 147
120905190 | 866 | PGE | 93666 | NEM | EXPNEM | IA in Progress | Solar PV | 58.738 |  | 2021-04-29 |  |  | 2021-04-30 | 2021-04-30 | 1 | 2021-04-30 | 1 | 2021-05-11 | 7 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11
120905379 | 867 | PGE | 93622 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 37.5 |  | 2021-04-29 |  | 2021-05-12 | 2021-05-12 | 2021-05-12 | 9 | 2021-05-18 | 13 | 2021-06-03 | 11 | [15 empty] | 2021-06-03 | 2021-06-09 | 4 | 2021-06-09 | 2021-06-11 | 2 |  |  |  |  | 2021-04-29 | 2021-06-04 | 2021-04-29 | 2021-06-16 | 33 |  |  |  |  | 2021-09-13 | 2021-09-21 | 6 | 2022-01-10 |  | 4 | [12 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-21 | 2021-09-22 |  | 1 |  |  | 101
120908082 | 868 | PGE | 93637 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-04-30 |  | 2021-05-06 | 2021-04-30 | 2021-04-30 | 0 | 2021-05-06 | 4 | 2021-05-24 | 12 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24 | 2021-06-01 | 5 |  |  |  |  | 2021-04-30 | 2021-05-06 | 2021-04-30 | 2021-05-25 | 17 |  |  |  |  | 2021-06-21 | 2021-06-29 | 6 | [15 empty] | 2021-06-21 | 2021-06-22 | 1 | 2021-06-29 |  | 2021-07-07 | 5
120908889 | 869 | PGE | 95912 | NEM | EXPNEM | Implementation | Solar PV | 156 |  | 2021-04-30 |  |  | 2021-05-04 | 2021-05-04 | 2 | 2021-05-05 | 3 | 2021-05-19 | 10 | 2021-05-19 | 2021-06-23 | 24 | 2021-06-23 | 2021-07-16 | 16 | 2021-07-16 |  |  |  | 2021-09-23 |  |  |  |  | 2021-09-23 | 2021-09-23 |  | 2021-09-23 | 2021-11-19 | 42 | 40 |  |  |  | 2021-04-30 | 2021-05-18 | 2021-04-30 | 2021-05-25 | 17
120910554 | 870 | PGE | 95688 | NEM | EXPNEM | Study in Progress | Solar PV | 540 |  | 2021-04-30 |  | 2021-07-20 | 2021-05-03 | 2021-05-03 | 1 | 2021-08-02 | 64 | 2021-08-18 | 12 | 2021-08-18 | 2021-09-28 | 28 | 2021-09-28 | 2021-10-20 | 16 | 2021-10-20 | [18 empty] | 2021-04-30 |  | 2021-04-30
120918853 | 871 | PGE | 94110 | Non-NEM | Non-Export | Commercial | Solar PV | 65.7 |  | 2021-05-02 | 2021-05-04 |  | 2021-05-04 | 2021-05-04 | 1 | 2021-05-12 | 7 | 2021-05-13 | 1 | [15 empty] | 2021-05-13 | 2021-05-24 | 7 | 2021-05-24 | 2021-06-29 | 25 | [13 empty] | 2021-07-20 | 2021-07-22 | 2 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-22 |  | 2021-07-22 | 0
120920307 | 872 | PGE | 94028 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 40 |  | 2021-05-03 |  | 2021-05-24 | 2021-05-11 | 2021-05-11 | 6 | 2021-06-17 | 32 | 2021-06-18 | 1 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24 | [11 empty] | 2021-07-08
120924554 | 873 | PGE | 93206 | NEM | EXPNEM | Commercial | Solar PV | 132 |  | 2021-05-03 |  | 2021-05-06 | 2021-07-08 | 2021-05-06 | 3 | 2021-07-08 | 46 | 2021-07-28 | 14 | [15 empty] | 2021-10-11 | 2021-10-29 | 14 | 2021-10-29 | 2021-10-29 | 0 | [13 empty] | 2021-12-09 | 2021-12-21 | 8 | [15 empty] | 2021-12-09 | 2021-12-10 | 1 | 2021-12-21 |  | 2021-12-21 | 0
120924866 | 874 | PGE | 95937 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-05-03 |  |  | 2021-05-04 | 2021-05-04 | 1 | 2021-05-04 | 1 | 2021-05-20 | 12 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2021-05-24 | 2 |  |  |  |  | 2021-05-03 | 2021-05-14 | 2021-05-03 | 2021-05-28 | 19 |  |  |  |  | 2021-09-29 | 2021-10-06 | 5 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-10-06 |  | 2021-10-13 | 5
120927287 | 875 | PGE | 96035 | NEM | EXPNEM | IA in Progress | Solar PV | 95.8 |  | 2021-05-04 |  | 2021-05-13 | 2021-05-13 | 2021-05-13 | 7 | 2021-05-21 | 13 | 2021-06-07 | 10 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [6 empty] | 2021-05-04 | 2021-05-21 | 2021-05-04 | 2021-06-03 | 21
120929506 | 876 | PGE | 95236 | NEM | EXPNEM | Commercial | Solar PV | 140.742 |  | 2021-05-04 |  |  | 2021-05-14 | 2021-05-14 | 8 | 2021-05-14 | 8 | 2021-06-02 | 12 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-06-24 | 16 |  |  |  |  | 2021-05-04 | 2021-05-18 | 2021-05-04 | 2021-05-28 | 18 |  |  |  |  | 2021-07-12 | 2021-07-19 | 5 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-19 |  | 2021-07-19 | 0
120929636 | 877 | PGE | 95519 | Non-NEM | Non-Export | Withdrawn | Storage | 140 |  | 2021-05-04 | 2021-05-04 |  | 2021-05-04 | 2021-05-04 | 0 | 2021-05-26 | 16 | 2021-06-21 | 17 | 2021-07-16 | 2021-08-19 | 24 | [12 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | [6 empty] | 2021-05-04 | 2021-05-28 | 2021-05-04 | 2021-06-15 | 29 | [19 empty] | 2021-08-25
120929967 | 878 | PGE | 95677 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-05-04 |  |  | 2021-05-12 | 2021-05-12 | 6 | 2021-05-12 | 6 | 2021-05-13 | 1 | [34 empty] | 2021-06-08 | 2021-08-02 | 38 | [15 empty] | 2021-06-08 | 2021-07-23 | 32 | 2021-08-02 |  | 2021-08-03 | 1
120930410 | 879 | PGE | 93612 | NEM | EXPNEM | Commercial | Solar PV | 118.695 |  | 2021-05-04 |  | 2021-05-10 | 2021-05-05 | 2021-05-05 | 1 | 2021-05-12 | 6 | 2021-05-19 | 5 | [15 empty] | 2021-05-19 | 2021-05-19 | 0 | 2021-05-19 | 2021-06-23 | 24 | [13 empty] | 2021-08-18 | 2021-09-16 | 20 | [15 empty] | 2021-08-18 | 2021-09-14 | 18 | 2021-09-16 |  | 2021-09-23 | 5
120931208 | 880 | PGE | 95667 | Non-NEM | Non-Export | IA in Progress | Storage | 420 |  | 2021-05-04 | 2021-05-04 |  | 2021-05-04 | 2021-05-04 | 0 | 2021-05-26 | 16 | 2021-07-20 | 37 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20
120931541 | 881 | PGE | 93609 | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-05-04 |  | 2021-05-10 | 2021-05-10 | 2021-05-10 | 4 | 2021-05-10 | 4 | 2021-06-09 | 21 | [15 empty] | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | [6 empty] | 2021-05-04 |  | 2021-05-04 |  |  | 2021-05-17
120932439 | 882 | PGE | 95035 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 247.184 |  | 2021-05-04 |  | 2021-05-18 | 2021-05-18 | 2021-05-18 | 10 | 2021-07-19 | 52 | 2021-08-09 | 15 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-10-19 | 50 | [9 empty] | 2021-08-02 | 2021-08-09 | 2021-08-09 | 5 |  |  |  | 2021-12-17 | 2021-12-20 | 1
120932558 | 883 | PGE | 95035 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 185 |  | 2021-05-04 |  | 2021-05-18 | 2021-05-18 | 2021-05-18 | 10 | 2021-07-19 | 52 | 2021-08-16 | 20 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | 2021-10-19 | 45 | [9 empty] | 2021-07-19 | 2021-08-16 | 2021-08-16 | 20 |  |  |  | 2021-12-17 | 2021-12-20 | 1
120932622 | 884 | PGE | 94545 | NEM | EXPNEM | Commercial | Solar PV | 440 |  | 2021-05-04 |  | 2021-05-05 | 2021-05-05 | 2021-05-05 | 1 | 2021-05-07 | 3 | 2021-07-12 | 44 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-09-10 | 43 | [13 empty] | 2021-09-27 | 2021-10-05 | 6 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-10-05 |  | 2021-10-11 | 4
120933067 | 885 | PGE | 94404 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 49.179 |  | 2021-05-04 |  |  | 2021-05-12 | 2021-05-12 | 6 | 2021-05-20 | 12 | 2021-05-20 | 0 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2021-05-21 | 1 | [13 empty] | 2021-12-16 | 2021-12-16 | 0 | [15 empty] | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16 |  | 2021-12-16 | 0
120935441 | 886 | PGE | 93901 | NEM | NEMMT | IA in Progress | FUCE, Solar PV | 800 |  | 2021-05-05 |  | 2021-05-19 | 2021-05-19 | 2021-05-19 | 10 | 2021-09-13 | 90 | 2021-11-04 | 38 | 2021-11-04 | 2021-12-27 | 34 | [12 empty] | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27 | [6 empty] | 2021-05-05 | 2021-09-13 | 2021-05-05 | 2021-09-20 | 95 | 2021-11-01 | 2021-12-27 | 2021-12-27 | 37
120935902 | 887 | PGE | 93638 | NEM | EXPNEM | Implementation | Solar PV | 300 |  | 2021-05-05 |  | 2021-05-14 | 2021-05-14 | 2021-05-14 | 7 | 2021-05-14 | 7 | 2021-06-09 | 17 | [15 empty] | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | 2021-07-01 | 16 |  |  |  |  | 2021-05-05 |  | 2021-05-05 |  |  | 2021-05-17
120939133 | 888 | PGE | 93609 | NEM | EXPNEM | Implementation | Solar PV | 45.45 |  | 2021-05-05 |  | 2021-05-14 | 2021-05-14 | 2021-05-14 | 7 | 2021-10-06 | 107 | 2021-10-11 | 3 | [15 empty] | 2021-10-11 | 2021-10-11 | 0 | 2021-10-11 | 2021-10-20 | 7 |  |  |  |  | 2021-07-07 | 2021-10-06 | 2021-07-07 | 2021-10-07 | 65
120942016 | 889 | PGE | 95215 | NEM | EXPNEM | Study in Progress | Solar PV | 954.853 |  | 2021-05-06 |  | 2021-11-03 | 2021-05-11 | 2021-05-11 | 3 | 2021-11-03 | 126 | 2021-11-24 | 14 | 2021-11-24 | 2021-12-22 | 18 | 2021-12-23 | [21 empty] | 2021-05-06 | 2021-12-23 | 2021-05-06 |  |  | 2021-12-09
120942653 | 890 | PGE | 93249 | NEM | EXPNEM | IA in Progress | Solar PV | 86.4 |  | 2021-05-06 |  | 2021-05-10 | 2021-05-10 | 2021-05-10 | 2 | 2021-06-15 | 27 | 2021-06-29 | 10 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | [6 empty] | 2021-05-06 | 2021-06-15 | 2021-05-06 | 2021-06-24 | 34
120946002 | 891 | PGE | 93710 | Non-NEM | Non-Export | IA in Progress | Storage | 210 |  | 2021-05-06 | 2021-05-07 |  | 2021-05-07 | 2021-05-07 | 1 | 2021-05-26 | 14 | 2021-07-27 | 42 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-08-25 | 21
120948228 | 892 | PGE | 94544 | Non-NEM | NEMFC | Implementation | FUCE | 1050 |  | 2021-05-07 |  |  | 2021-05-14 | 2021-05-14 | 5 | 2021-05-14 | 5 | 2021-08-13 | 63 | 2021-08-13 | 2021-09-02 | 14 | [12 empty] | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02 | 2021-12-08 | 65 |  |  |  |  | 2021-05-07 |  | 2021-05-07 | [6 empty] | 2021-12-31 | [5 empty] | 2021-06-29 | [11 empty] | 2021-12-31 | 2021-12-31 | 0
120949009 | 893 | PGE | 95954 | Non-NEM | Non-Export | Withdrawn | Storage | 490 |  | 2021-05-07 | 2021-05-07 |  | 2021-05-07 | 2021-05-07 | 0 | 2021-05-26 | 13 | 2021-06-25 | 21 | [15 empty] | 2021-06-25 | 2021-06-28 | 1 | 2021-06-28 | [6 empty] | 2021-05-07 | 2021-05-27 | 2021-05-07 | 2021-05-27 | 14
120949049 | 894 | PGE | 95476 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.23 |  | 2021-05-07 |  |  | 2021-05-12 | 2021-05-12 | 3 | 2021-05-12 | 3 | 2021-05-13 | 1 | [15 empty] | 2021-08-13 | 2021-08-13 |  | 2021-08-13 | 2021-09-15 | 24 | [13 empty] | 2021-09-16 | 2021-09-16 | 0 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 |  | 2021-09-16 | 0
120949585 | 895 | PGE | 93280 | NEM | VNEMMASH | Withdrawn | Solar PV | 114.8 |  | 2021-05-07 |  | 2021-05-14 | 2021-05-14 | 2021-05-14 | 5 | [29 empty] | 2021-05-07 |  | 2021-05-07
120949681 | 896 | PGE | 95928 | NEM | SNEM | Commercial | ENGN, Solar PV | 39.477 |  | 2021-05-07 |  | 2021-08-05 | 2021-05-21 | 2021-05-21 | 10 | 2021-06-16 | 27 | 2021-06-29 | 9 | [25 empty] | 2021-05-07 | 2021-06-16 | 2021-05-07 | 2021-06-28 | 35 |  |  |  |  | 2021-10-14 | 2021-10-18 | 2 | [15 empty] | 2021-10-14 | 2021-10-14 | 0 | 2021-10-18 |  | 2021-10-20 | 2
120950094 | 897 | PGE | 93243 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1187.5 |  | 2021-05-07 | 2021-05-10 |  | 2021-05-10 | 2021-05-10 | 1 | 2021-05-19 | 8 | 2021-06-30 | 29 | 2021-07-20 | 2021-08-27 | 28 | [12 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-11-29 | 62 |  |  |  |  | 2021-05-07 | 2021-06-01 | 2021-05-07 | 2021-06-15 | 26
120951103 | 898 | PGE | 95206 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 61.126 |  | 2021-05-07 |  | 2021-05-14 | 2021-05-14 | 2021-05-14 | 5 | 2021-06-23 | 32 | 2021-07-15 | 15 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | [6 empty] | 2021-05-07 | 2021-09-16 | 2021-05-07 | 2021-09-20 | 93 |  | 2021-09-25
120951527 | 899 | PGE | 94563 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-05-07 |  | 2021-05-20 | 2021-05-12 | 2021-05-12 | 3 | 2021-05-26 | 13 | 2021-06-09 | 9 | [25 empty] | 2021-05-07 | 2021-05-20 | 2021-05-07 | 2021-05-28 | 15 | [25 empty] | 2021-05-26 |  | 2021-06-09 | 11
121004429 | 900 | PGE | 95227 | NEM | EXPNEM | Withdrawn | Solar PV | 31.078 |  | 2021-05-10 |  | 2021-05-13 | 2021-05-13 | 2021-05-13 | 3
121007066 | 901 | PGE | 95215 | NEM | EXPNEM | Commercial | Solar PV | 75.105 |  | 2021-05-10 |  | 2021-10-20 | 2021-05-10 | 2021-05-10 | 0 | 2021-10-27 | 119 | 2021-10-27 | 1 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-09-02 | 62 |  |  |  |  | 2021-05-10 | 2021-10-20 | 2021-05-10 | 2021-10-21 | 115 |  |  |  |  | 2021-10-27 | 2021-11-04 | 6 | [15 empty] | 2021-10-27 | 2021-10-28 | 1 | 2021-11-04 |  | 2021-11-09 | 3
121008816 | 902 | PGE | 95912 | NEM | EXPNEM | Study in Progress | Solar PV | 120 |  | 2021-05-10 |  | 2021-05-28 | 2021-05-10 | 2021-05-10 | 0 | 2021-06-04 | 18 | 2021-06-17 | 9 | 2021-06-17 | 2021-07-22 | 24 | 2021-06-04 | 2021-09-01 | 62 | 2021-09-01 | [18 empty] | 2021-05-10 | 2021-05-28 | 2021-05-10 | 2021-06-15 | 25
121011229 | 903 | PGE | 95949 | NEM | SNEM | Application Review in Progress | Solar PV | 1603.8 |  | 2021-05-10 |  | 2021-05-18 | 2021-05-18 | 2021-05-18 | 6
121130249 | 904 | PGE | 95682 | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-05-10 |  | 2021-05-17 | 2021-05-13 | 2021-05-13 | 3 | 2021-05-20 | 8 | 2021-07-12 | 35 | [15 empty] | 2021-07-12 | 2021-07-15 | 3 | 2021-07-15 | 2021-07-16 | 1 |  |  |  |  | 2021-05-10 | 2021-06-10 | 2021-05-10 | 2021-06-17 | 27 |  |  |  |  | 2021-12-06 | 2021-12-17 | 9 | 2021-08-19 | 2021-10-11 | 36 | [12 empty] | 2021-12-06 | 2021-12-07 | 1 | 2021-12-17 | 2021-12-21 |  | 2 |  |  | 155
121138825 | 905 | PGE | 95682 | NEM | EXPNEM | Implementation | Solar PV | 171.802 |  | 2021-05-10 |  | 2021-05-12 | 2021-05-12 | 2021-05-12 | 2 | 2021-05-17 | 5 | 2021-06-09 | 16 | 2021-06-09 | 2021-07-08 | 20 | 2021-05-17 | 2021-08-17 | 64 | 2021-08-17 |  |  |  | 2021-11-10 |  |  |  |  | 2021-11-10 | 2021-11-10 |  | 2021-11-10 | 2021-11-12 | 3 | 1 |  |  |  | 2021-05-10 | 2021-05-12 | 2021-05-10 | 2021-05-26 | 12
121187860 | 906 | PGE | 93311 | NEM | EXPNEM | Commercial | Solar PV | 32.76 |  | 2021-05-11 |  | 2021-07-10 | 2021-05-14 | 2021-05-14 | 3 | 2021-07-16 | 46 | 2021-07-22 | 4 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | 2021-08-19 | 20 | [13 empty] | 2021-08-19 | [17 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-06-30 |  | 2021-09-07 | 50
121188855 | 907 | PGE | 94582 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 224.234 |  | 2021-05-11 |  | 2021-05-14 | 2021-05-14 | 2021-05-14 | 3
121189607 | 908 | PGE | 95134 | NEM | NEMMT | Withdrawn | FUCE, Storage | 306.488 |  | 2021-05-11 | 2021-05-17 |  |  | 2021-05-17 | 4 | 2021-06-15 | 24
121190299 | 909 | PGE | 95240 | NEM | EXPNEM | Implementation | Solar PV | 51.478 |  | 2021-05-11 |  | 2021-06-30 | 2021-05-18 | 2021-05-18 | 5 | 2021-06-28 | 33 | 2021-08-06 | 28 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | 2021-08-17 | 7 | [13 empty] | 2021-08-20 | 2021-08-27 | 5 | 2021-10-12 |  | 64 | [12 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-27 | 2021-08-30 |  | 1 |  |  | 77
121190694 | 910 | PGE | 93721 | NEM | EXPNEM | IA in Progress | Solar PV | 39.976 |  | 2021-05-11 |  | 2021-05-14 | 2021-05-14 | 2021-05-14 | 3 | 2021-05-14 | 3 | 2021-07-20 | 45 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-12-16 | 103 |  |  |  |  | 2021-05-11 | 2021-12-27 | 2021-05-11
121191139 | 911 | PGE | 93313 | NEM | NEM Paired Storage | IA in Progress | ENGN, Solar PV, Storage | 6080 |  | 2021-05-11 | 2021-05-13 |  | 2021-05-13 | 2021-05-13 | 2 | 2021-05-26 | 11 | [5 empty] | 2021-05-26 | 2021-06-25 | 21 | 2021-06-25 | 2021-07-12 | 10 | 2021-07-26 | 2021-11-08 | 74 | 2021-07-12 | 2021-07-12 | 0 | [10 empty] | 2021-05-11 |  | 2021-05-11
121191864 | 912 | PGE | 93306 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2360 |  | 2021-05-11 | 2021-05-13 |  | 2021-05-13 | 2021-05-13 | 2 | 2021-05-26 | 11 | [5 empty] | 2021-05-26 | 2021-08-23 | 61 | 2021-08-23 | 2021-08-23 | 0 | 2021-09-02 | 2021-12-29 | 80 | 2021-08-23 | 2021-08-23 | 0 | [10 empty] | 2021-05-11 |  | 2021-05-11
121317816 | 913 | PGE | 93612 | NEM | EXPNEM | Implementation | Solar PV | 99.9 |  | 2021-05-12 |  |  | 2021-05-19 | 2021-05-19 | 5 | 2021-05-20 | 6 | 2021-05-25 | 3 | [15 empty] | 2021-06-04 | 2021-06-04 | 0 | 2021-06-04 | 2021-06-07 | 1 |  |  |  |  | 2021-05-12 | 2021-05-20 | 2021-05-12 | 2021-05-28 | 12
121318427 | 914 | PGE | 94563 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 57.054 |  | 2021-05-12 |  | 2021-05-21 | 2021-05-21 | 2021-05-21 | 7 | 2021-06-17 | 25 | 2021-06-30 | 9 | [15 empty] | 2021-06-30 | 2021-07-21 | 14 | 2021-07-21 | 2021-10-19 | 63
121318645 | 915 | PGE | 95060 | NEM | VNEMSOMAH | Implementation | Solar PV | 30.159 |  | 2021-05-12 |  | 2021-05-26 | 2021-05-26 | 2021-05-26 | 10 | 2021-06-08 | 18 | 2021-06-24 | 12 | [15 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-24 | 2021-07-07 | 8 |  |  |  |  | 2021-05-12 | 2021-06-11 | 2021-05-12 | 2021-06-15 | 23
121319468 | 916 | PGE | 95124 | NEM | EXPNEM | Commercial | Solar PV | 125 |  | 2021-05-12 |  | 2021-05-25 | 2021-05-14 | 2021-05-14 | 2 | 2021-05-25 | 9 | 2021-06-10 | 11 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-06-14 | 2 | [13 empty] | 2021-09-02 | 2021-09-14 | 7 | [15 empty] | 2021-09-02 | 2021-09-03 | 1 | 2021-09-14 |  | 2021-09-21 | 5
121321905 | 917 | PGE | 94010 | NEM | EXPNEM | Implementation | Solar PV | 199.172 |  | 2021-05-12 |  | 2021-05-24 | 2021-05-24 | 2021-05-24 | 8 | 2021-06-07 | 17 | 2021-06-16 | 7 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | 2021-07-06 | 13 |  |  |  |  | 2021-05-12 | 2021-06-07 | 2021-05-12 | 2021-06-16 | 24 | [7 empty] | 2019-12-19 | 2020-05-15 | 102 |  |  |  | 2021-11-12 | 2021-12-06 | 14
121322442 | 918 | PGE | 94574 | NEM | EXPNEM | IA in Progress | Solar PV | 180 |  | 2021-05-12 |  | 2021-05-17 | 2021-05-17 | 2021-05-17 | 3 | 2021-05-17 | 3 | 2021-09-23 | 90 | [15 empty] | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | [6 empty] | 2021-05-12 |  | 2021-05-12
121322443 | 919 | PGE | 93311 | NEM | EXPNEM | Study in Progress | Solar PV | 900 |  | 2021-05-12 | 2021-05-18 |  | 2021-05-17 | 2021-05-17 | 3 | 2021-06-23 | 29 | [5 empty] | 2021-07-05 | 2021-08-10 | 25 | 2021-08-10 |  | 1 | 2021-09-30 | 2021-12-28 | 60 |  | 2021-08-10 | 4
121322455 | 920 | PGE | 95453 | Non-NEM | Non-Export | IA in Progress | Storage | 420 |  | 2021-05-12 | 2021-05-13 |  | 2021-05-13 | 2021-05-13 | 1 | 2021-06-02 | 14 | 2021-09-09 | 69 | [15 empty] | 2021-09-09 | 2021-12-30 | 77 | 2021-12-30
121323269 | 921 | PGE | 93434 | NEM | VNEM | Commercial | Solar PV, Storage | 54.717 |  | 2021-05-12 |  | 2021-06-09 | 2021-05-27 | 2021-05-27 | 11 | 2021-07-01 | 35 | 2021-08-06 | 25 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | 2021-08-09 | 1 | [5 empty] | 2021-08-04 | 2021-08-04 | 2021-08-06 | 2 |  | 2021-08-06 | 2021-08-06 | 0 | 2021-09-25 | 2021-10-06 | 7 | [15 empty] | 2021-09-25 | 2021-09-27 | 0 | 2021-10-06 |  | 2021-10-12 | 4
121323768 | 922 | PGE | 94063 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 425 |  | 2021-05-13 |  | 2021-05-27 | 2021-05-27 | 2021-05-27 | 10 | 2021-11-29 | 136 | [32 empty] | 2021-12-14
121324169 | 923 | PGE | 95037 | NEM | EXPNEM | Commercial | Solar PV | 247.518 |  | 2021-05-13 |  | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2 | 2021-05-17 | 2 | 2021-08-21 | 67 | [15 empty] | 2021-08-21 | 2021-08-21 | 0 | 2021-08-21 | 2021-08-24 | 1 |  |  |  |  | 2021-05-13 | 2021-05-19 | 2021-05-13 | 2021-05-28 | 11 |  |  |  |  | 2021-09-01 | 2021-09-09 | 5 | [15 empty] | 2021-09-01 | 2021-09-01 | 0 | 2021-09-09 |  | 2021-09-21 | 8
121324261 | 924 | PGE | 94063 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 516.6 |  | 2021-05-13 |  | 2021-05-27 | 2021-05-27 | 2021-05-27 | 10 | 2021-06-19 | 25 | 2021-07-12 | 14 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [11 empty] | 2021-06-29 | 2021-07-12 | 2021-07-12 | 8
121325067 | 925 | PGE | 94577 | NEM | EXPNEM | Withdrawn | Solar PV | 66.6 |  | 2021-05-13 |  | 2021-10-27 | 2021-05-13 | 2021-05-13 | 0 | 2021-10-28 | 117
121325832 | 926 | PGE | 93301 | NEM | EXPNEM | IA in Progress | Solar PV | 1212 |  | 2021-05-13 | 2021-05-27 |  | 2021-05-26 | 2021-05-26 | 9 | 2021-06-09 | 18 | [5 empty] | 2021-06-14 | 2021-07-12 | 19 | 2021-07-12 | 2021-07-12 | 0 | 2021-08-03 | 2021-10-28 | 61 | 2021-07-12 | 2021-07-12 | 0 | 2021-11-01 | 2021-11-02 | 1 | 2021-11-02 | [6 empty] | 2021-05-13 |  | 2021-05-13
121326648 | 928 | PGE | 95521 | NEM | VNEM | Implementation | Solar PV | 98.938 |  | 2021-05-13 |  | 2021-05-27 | 2021-05-27 | 2021-05-27 | 10 | 2021-10-04 | 99 | 2021-10-25 | 15 | [15 empty] | 2021-10-25 | 2021-10-25 | 0 | 2021-10-25 | 2021-11-05 | 9 | [9 empty] | 2021-10-14 | 2021-10-25 | 2021-10-25 | 7
121327892 | 929 | PGE | 93725 | NEM | EXPNEM | Commercial | Solar PV | 644.705 |  | 2021-05-13 |  | 2021-05-18 | 2021-05-18 | 2021-05-18 | 3 | 2021-05-21 | 6 | 2021-06-04 | 9 | 2021-06-04 | 2021-07-02 | 20 | [12 empty] | 2021-07-02 | 2021-07-06 | 1 | 2021-07-06 | 2021-07-13 | 5 |  |  |  |  | 2021-05-13 | 2021-10-14 | 2021-05-13 | 2021-10-27 | 116 |  |  |  |  | 2021-12-10 | 2021-12-20 | 6 | [15 empty] | 2021-12-10 | 2021-12-10 | 0 | 2021-12-20 |  | 2021-12-23 | 3
121328758 | 930 | PGE | 95977 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 50.23 |  | 2021-05-13 |  | 2021-05-18 | 2021-05-18 | 2021-05-18 | 3 | 2021-05-27 | 10 | 2021-06-01 | 2 | [34 empty] | 2021-06-01 | 2021-06-01 | 0 | [15 empty] | 2021-06-01 |  |  | 2021-06-01 |  | 2021-06-01 | 0
121329814 | 931 | PGE | 95361 | NEM | EXPNEM | Commercial | Solar PV | 72 |  | 2021-05-13 |  | 2021-05-27 | 2021-05-27 | 2021-05-27 | 10 | 2021-09-01 | 77 | 2021-09-15 | 9 | [15 empty] | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | 2021-09-16 | 1 | [13 empty] | 2021-09-20 | 2021-09-28 | 6 | [15 empty] | 2021-09-20 | 2021-09-21 | 1 | 2021-09-28 |  | 2021-09-28 | 0
121333375 | 932 | PGE | 95422 | NEM | EXPNEM | IA in Progress | Solar PV | 641.076 |  | 2021-05-14 |  |  | 2021-05-18 | 2021-05-18 | 2 | 2021-05-18 | 2 | 2021-08-19 | 65 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-09-14 | 17 |  |  |  |  | 2021-05-14 | 2021-11-10 | 2021-05-14 | 2021-12-01 | 137
121333652 | 933 | PGE | 95228 | Non-NEM | Non-Export | Withdrawn | Solar PV | 44.66 |  | 2021-05-14 | 2021-05-20 |  | 2021-05-17 | 2021-05-17 | 1 | 2021-06-02 | 12
121333662 | 934 | PGE | 93301 | Non-NEM | Non-Export | IA in Progress | Storage | 985 |  | 2021-05-14 | 2021-05-17 |  | 2021-05-17 | 2021-05-17 | 1 | 2021-05-26 | 8 | 2021-08-02 | 46 | 2021-08-18 | 2021-09-17 | 21 | [12 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | 2021-12-17 | 62
121334398 | 935 | PGE | 93703 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 4411.742 |  | 2021-05-14 | 2021-05-17 |  | 2021-05-17 | 2021-05-17 | 1 | 2021-05-26 | 8 | [5 empty] | 2021-06-14 | 2021-07-27 | 30 | 2021-07-27 | 2021-08-02 | 4 | 2021-08-17 | 2021-11-02 | 54 | 2021-08-02 | 2021-08-16 | 10 | 2021-12-29 | [6 empty] | 2021-12-08 | 2021-12-29 | 15
121334909 | 936 | PGE | 93673 | NEM | EXPNEM | Implementation | Solar PV | 865.259 |  | 2021-05-14 |  | 2021-05-28 | 2021-05-28 | 2021-05-28 | 10 | 2021-06-14 | 20 | 2021-07-01 | 13 | 2021-07-01 | 2021-07-30 | 20 | [12 empty] | 2021-07-30 | 2021-07-30 | 0 | 2021-07-30 | 2021-08-27 | 20 | [5 empty] | 2021-07-23 | 2021-07-23 | 2021-08-05 | 9 | 2021-07-09 | [6 empty] | 2021-11-17 |  | 39
121335540 | 937 | PGE | 93314 | NEM | EXPNEM | Commercial | Solar PV | 250 |  | 2021-05-14 |  | 2021-05-24 | 2021-05-24 | 2021-05-24 | 6 | 2021-05-28 | 10 | 2021-06-07 | 5 | [15 empty] | 2021-06-07 | 2021-06-16 | 7 | 2021-06-16 | 2021-10-08 | 80 |  |  |  |  | 2021-05-14 | 2021-05-28 | 2021-05-14 | 2021-06-15 | 21 |  |  |  |  | 2021-11-02 | 2021-11-10 | 6 | [15 empty] | 2021-11-02 | 2021-11-03 | 1 | 2021-11-10 |  | 2021-11-10 | 0
121336530 | 938 | PGE | 95692 | NEM | EXPNEM | Implementation | Solar PV | 480 |  | 2021-05-14 |  | 2021-06-29 | 2021-06-14 | 2021-06-14 | 20 | 2021-07-09 | 38 | 2021-07-26 | 11 | 2021-07-26 | 2021-08-30 | 25 | 2021-08-31 | 2021-09-21 | 14 | 2021-09-21 |  |  |  | 2021-12-20 |  |  |  |  | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-23 | 4 | 3 |  |  |  |  | 2021-07-09 | 2021-07-09 | 2021-07-19 | 6
121345569 | 939 | PGE | 94027 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 40.75 |  | 2021-05-17 |  | 2021-05-26 | 2021-05-19 | 2021-05-19 | 2 | 2021-09-27 | 92 | 2021-09-28 | 1 | [34 empty] | 2021-11-23 | 2021-11-23 | 0 | [15 empty] | 2021-11-23 |  |  | 2021-11-23 |  | 2021-11-23 | 0
121346000 | 940 | PGE | 95060 | NEM | NEMMT | IA in Progress | ENGN, Solar PV, Storage | 985 |  | 2021-05-17 |  |  | 2021-05-24 | 2021-05-24 | 5 | 2021-05-24 | 5 | [5 empty] | 2021-05-24 | 2021-06-15 | 15 | 2021-06-15 | 2021-07-01 | 12 | 2021-08-04 | 2021-12-16 | 92 | 2021-07-01 | 2021-07-01 | 0 | 2021-12-17 | 2021-12-17 | 0 | 2021-12-17
121347262 | 941 | PGE | 94515 | NEM | EXPNEM | IA in Progress | Solar PV | 151.403 |  | 2021-05-17 |  | 2021-06-10 | 2021-05-20 | 2021-05-20 | 3 | 2021-06-22 | 25 | 2021-07-12 | 13 | 2021-07-12 | 2021-08-11 | 22 | [12 empty] | 2021-08-11 | 2021-08-11 | 0 | 2021-08-11 | 2021-09-16 | 25 |  |  |  |  | 2021-05-17 | 2021-06-05 | 2021-05-17 | 2021-06-16 | 21 |  |  |  |  | 2021-12-14 | 2021-12-22 | 6 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-22
121347821 | 942 | PGE | 93648 | NEM | EXPNEM | IA in Progress | Solar PV | 75 |  | 2021-05-17 |  |  | 2021-05-18 | 2021-05-18 | 1 | 2021-05-18 | 1 | 2021-06-15 | 19 | [15 empty] | 2021-06-15 | 2021-06-17 | 2 | 2021-06-17 | 2021-06-17 | 0 |  |  |  |  | 2021-05-17 | 2021-05-18 | 2021-05-17 | 2021-05-28 | 9
121351959 | 943 | PGE | 95691 | NEM | EXPNEM | Withdrawn | Solar PV | 50 |  | 2021-05-18 |  | 2021-06-10 | 2021-05-20 | 2021-05-20 | 2
121351984 | 944 | PGE | 95348 | NEM | EXPNEM | Commercial | Solar PV | 47.351 |  | 2021-05-18 |  | 2021-05-18 | 2021-05-18 | 2021-05-18 | 0 | 2021-06-05 | 12 | 2021-06-21 | 10 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-25 | 4 | [13 empty] | 2021-09-10 | 2021-09-20 | 6 | [15 empty] | 2021-09-10 | 2021-09-12 | 0 | 2021-09-20 |  | 2021-09-27 | 5
121351986 | 945 | PGE | 95019 | NEM | VNEMSOMAH | Implementation | Solar PV | 64.643 |  | 2021-05-18 |  | 2021-05-25 | 2021-05-25 | 2021-05-25 | 5 | 2021-06-29 | 29 | 2021-08-05 | 26 | [15 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | 2021-09-30 | 39 |  |  |  |  | 2021-05-18 | 2021-06-04 | 2021-05-18 | 2021-06-16 | 20 |  | 2021-06-29 | 2021-06-29 | 0
121352161 | 946 | PGE | 95019 | NEM | VNEMSOMAH | Implementation | Solar PV | 53.25 |  | 2021-05-18 |  | 2021-05-25 | 2021-05-25 | 2021-05-25 | 5 | 2021-06-30 | 30 | 2021-07-22 | 15 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | 2021-09-30 | 49 |  |  |  |  | 2021-05-18 | 2021-06-04 | 2021-05-18 | 2021-06-16 | 20 |  | 2021-06-30 | 2021-06-30 | 0
121352351 | 947 | PGE | 95019 | NEM | VNEMSOMAH | Implementation | Solar PV | 41.375 |  | 2021-05-18 |  | 2021-06-02 | 2021-06-02 | 2021-06-02 | 10 | 2021-06-30 | 30 | 2021-08-05 | 25 | [15 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | 2021-09-30 | 39 |  |  |  |  | 2021-05-18 |  | 2021-05-18 |  |  | 2021-07-23
121352364 | 948 | PGE | 95019 | NEM | VNEMSOMAH | Implementation | Solar PV | 55.628 |  | 2021-05-18 |  | 2021-06-02 | 2021-06-02 | 2021-06-02 | 10 | 2021-06-30 | 30 | 2021-08-12 | 30 | [15 empty] | 2021-08-12 | 2021-08-12 | 0 | 2021-08-12 | 2021-09-30 | 34 |  |  |  |  | 2021-05-18 |  | 2021-05-18 |  |  | 2021-07-23 | 2021-08-12 | 2021-08-12 | 14
121352451 | 949 | PGE | 95019 | NEM | VNEMSOMAH | Implementation | Solar PV | 70.798 |  | 2021-05-18 |  | 2021-06-01 | 2021-06-01 | 2021-06-01 | 9 | 2021-06-29 | 29 | 2021-07-21 | 15 | [15 empty] | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | 2021-09-30 | 50 |  |  |  |  | 2021-05-18 |  | 2021-05-18
121352460 | 950 | PGE | 95019 | NEM | VNEMSOMAH | Implementation | Solar PV | 54.229 |  | 2021-05-18 |  | 2021-06-02 | 2021-06-02 | 2021-06-02 | 10 | 2021-06-29 | 29 | 2021-08-05 | 26 | [15 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | 2021-09-30 | 39 |  |  |  |  | 2021-05-18 |  | 2021-05-18 |  |  | 2021-07-19
121353897 | 951 | PGE | 93637 | NEM | EXPNEM | Commercial | Solar PV | 74.573 |  | 2021-05-18 |  | 2021-06-02 | 2021-06-02 | 2021-06-02 | 10 | 2021-06-28 | 28 | [17 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-08-09 | 10 |  |  |  |  | 2021-05-18 |  | 2021-05-18 |  |  | 2021-06-16 |  |  |  | 2021-07-19 | 2021-07-26 | 5 | [15 empty] | 2021-07-19 | 2021-07-19 | 0 | 2021-07-26 |  | 2021-08-09 | 10
121354209 | 952 | PGE | 95205 | NEM | EXPNEM | IA in Progress | Solar PV | 261.34 |  | 2021-05-18 |  | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2 | 2021-05-26 | 6 | 2021-06-07 | 7 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [6 empty] | 2021-11-04 | 2021-12-01 | 2021-11-04 | 2021-12-15 | 26
121354483 | 953 | PGE | 94611 | NEM | EXPNEM | Study in Progress | Solar PV | 99.9 |  | 2021-05-18 |  | 2021-07-30 | 2021-05-20 | 2021-05-20 | 2 | 2021-08-04 | 54
121355803 | 954 | PGE | 95453 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 630 |  | 2021-05-18 |  |  | 2021-06-02 | 2021-06-02 | 10 | 2021-06-02 | 10 | 2021-07-13 | 28 | 2021-07-30 | 2021-09-07 | 26 | [12 empty] | 2021-06-29 | 2021-06-29 |  | 2021-06-29 | 2021-06-30 | 2 |  |  |  |  | 2021-05-18 | 2021-06-09 | 2021-05-18 | 2021-06-09 | 15 | [10 empty] | 2021-12-21
121360523 | 955 | PGE | 93242 | NEM | EXPNEM | Commercial | Solar PV | 53.289 |  | 2021-05-19 |  | 2021-06-17 | 2021-06-17 | 2021-06-17 | 20 | 2021-06-18 | 21 | 2021-07-01 | 9 | [15 empty] | 2021-07-01 | 2021-07-07 | 3 | 2021-07-07 | 2021-07-07 | 0 |  |  |  |  | 2021-05-19 | 2021-05-27 | 2021-05-19 | 2021-06-07 | 12 |  |  |  |  | 2021-11-12 | 2021-11-23 | 7 | [15 empty] | 2021-11-12 | 2021-11-15 | 1 | 2021-11-23 |  | 2021-11-29 | 2
121361569 | 956 | PGE | 94901 | NEM | EXPNEM | Commercial | Solar PV | 37.306 |  | 2021-05-19 |  | 2021-05-20 | 2021-05-20 | 2021-05-20 | 1 | 2021-06-03 | 10 | 2021-06-21 | 12 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-09-16 | 61 | [5 empty] | 2021-09-30 | 2021-09-30 | 2021-10-13 | 9 |  |  |  |  | 2021-10-25 | 2021-11-05 | 9 | [15 empty] | 2021-10-25 | 2021-10-25 | 0 | 2021-11-05 |  | 2021-11-15 | 5
121361989 | 957 | PGE | 95236 | NEM | EXPNEM | Commercial | Solar PV | 31.024 |  | 2021-05-19 |  | 2021-06-24 | 2021-05-27 | 2021-05-27 | 6 | 2021-06-25 | 26 | 2021-07-12 | 10 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-07-12 | 0 | [13 empty] | 2021-10-29 | 2021-11-08 | 6 | [15 empty] | 2021-10-29 | 2021-11-01 | 1 | 2021-11-08 |  | 2021-11-09 | 1
121363542 | 958 | PGE | 93249 | NEM | EXPNEM | Commercial | Solar PV | 80.637 |  | 2021-05-19 |  | 2021-05-27 | 2021-05-21 | 2021-05-21 | 2 | 2021-06-05 | 11 | 2021-06-23 | 12 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-07-08 | 10 | [5 empty] | 2021-07-30 | 2021-07-30 | 2021-08-13 | 10 |  |  |  |  | 2021-08-10 | 2021-08-13 | 3 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-13 |  | 2021-08-23 | 6
121363583 | 959 | PGE | 95691 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-05-19 |  | 2021-06-10 | 2021-06-04 | 2021-06-04 | 11 | 2021-06-21 | 22 | 2021-07-12 | 14 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-07-15 | 3 |  |  |  |  | 2021-05-19 | 2021-07-12 | 2021-05-19 | 2021-07-19 | 41 |  |  |  |  | 2021-10-13 | 2021-10-19 | 4 | [15 empty] | 2021-10-13 | 2021-10-13 | 0 | 2021-10-19 |  | 2021-11-08 | 14
121364335 | 960 | PGE | 94513 | Non-NEM | Non-Export | Implementation | Storage | 929.5 |  | 2021-05-19 | 2021-05-20 |  | 2021-05-20 | 2021-05-20 | 1 | 2021-06-23 | 24 | 2021-07-26 | 22 | 2021-08-02 | 2021-08-27 | 19 | [12 empty] | 2021-08-27 | 2021-09-01 | 3 | 2021-09-01 | 2021-11-24 | 58
121365736 | 961 | PGE | 95973 | NEM | EXPNEM | IA in Progress | Solar PV | 74.731 |  | 2021-05-20 |  | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2 | 2021-06-01 | 7 | 2021-06-15 | 10 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-15 | [6 empty] | 2021-05-20 | 2021-06-01 | 2021-05-20 | 2021-06-15 | 17
121366170 | 962 | PGE | 94954 | NEM | EXPNEM | IA in Progress | Solar PV | 248.292 |  | 2021-05-20 |  | 2021-06-03 | 2021-06-03 | 2021-06-03 | 9 | 2021-07-21 | 42 | 2021-08-04 | 10 | [15 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | [6 empty] | 2021-05-20 |  | 2021-05-20
121367566 | 963 | PGE | 95060 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-05-20 |  | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2 | 2021-06-15 | 17 | 2021-07-01 | 12 | [15 empty] | 2021-07-01 | 2021-07-02 | 1 | 2021-07-02 | 2021-12-30 | 124 |  |  |  |  | 2021-05-20 | 2021-11-15 | 2021-05-20 | 2021-11-17 | 125 |  |  |  |  | 2021-12-31 | [17 empty] | 2021-12-31
121367736 | 964 | PGE | 94576 | NEM | EXPNEM | Commercial | Solar PV | 54.72 |  | 2021-05-20 |  | 2021-06-15 | 2021-05-24 | 2021-05-24 | 2 | 2021-06-17 | 19 | 2021-07-22 | 24 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | 2021-10-15 | 60 |  |  |  |  | 2021-05-20 | 2021-06-04 | 2021-05-20 | 2021-06-07 | 11 |  |  |  |  | 2021-10-20 | 2021-10-27 | 5 | [15 empty] | 2021-10-20 | 2021-10-20 | 0 | 2021-10-27 |  | 2021-11-01 | 3
121368174 | 965 | PGE | 94621 | Non-NEM | Non-Export | IA in Progress | Storage | 630 |  | 2021-05-20 | 2021-05-20 |  | 2021-05-20 | 2021-05-20 | 0 | 2021-06-16 | 18 | 2021-10-26 | 92 | [15 empty] | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26
121368484 | 966 | PGE | 95126 | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2021-05-20 |  | 2021-08-26 | 2021-05-20 | 2021-05-20 | 0 | 2021-10-07 | 97 | 2021-10-19 | 8 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-10-29 | 8 | [5 empty] | 2021-10-07 | 2021-10-07 | 2021-10-19 | 8
121368559 | 967 | PGE | 93619 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-05-20 |  | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2 | 2021-06-03 | 9 | 2021-06-17 | 10 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-06-17 | 0 |  |  |  |  | 2021-05-20 | 2021-06-03 | 2021-05-20 | 2021-06-15 | 17 |  |  |  |  | 2021-09-16 | 2021-09-24 | 6 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-24 |  | 2021-10-01 | 5
121368827 | 968 | PGE | 95035 | NEM | EXPNEM | IA in Progress | Solar PV | 57.42 |  | 2021-05-20 |  | 2021-06-01 | 2021-05-24 | 2021-05-24 | 2 | 2021-06-05 | 10 | 2021-07-21 | 31 | [15 empty] | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21
121369425 | 969 | PGE | 94022 | NEM | EXPNEM | Application Review in Progress | Solar PV | 73.552 |  | 2021-05-20 |  | 2021-06-03 | 2021-05-27 | 2021-05-27 | 5
121369594 | 970 | PGE | 93245 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-05-20 |  | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2 | 2021-06-01 | 7 | 2021-06-17 | 12 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-12-14 | 123 |  |  |  |  | 2021-05-20 | 2021-06-05 | 2021-05-20 | 2021-06-16 | 18 |  |  |  |  | 2021-12-15 | [17 empty] | 2021-12-15 | 2021-12-15 | 0
121369966 | 971 | PGE | 93618 | NEM | NEMMT | Application Accepted | Solar PV | 250 |  | 2021-05-20 |  | 2021-06-05 | 2021-06-05 | 2021-06-05 | 10 | 2021-07-06 | 31 | 2021-07-27 | 15 | 2021-07-27 | 2021-08-24 | 20 | [12 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | 2021-09-17 | 17 |  |  |  |  | 2021-05-20 |  | 2021-05-20 |  |  | 2021-07-14 | 2021-07-27 | 2021-07-27 | 9 | 2021-09-17 | [17 empty] | 2021-09-17 | 2021-09-17 | 0
121370658 | 972 | PGE | 95126 | NEM | EXPNEM | Implementation | Solar PV | 162.5 |  | 2021-05-20 |  |  | 2021-06-01 | 2021-06-01 | 7 | 2021-06-01 | 7 | 2021-07-12 | 28 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-10-29 | 78 | [5 empty] | 2021-06-24 | 2021-06-24 | 2021-07-13 | 12
121370748 | 973 | PGE | 95126 | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2021-05-20 |  | 2021-06-01 | 2021-06-01 | 2021-06-01 | 7 | 2021-06-01 | 7 | 2021-08-09 | 48 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-10-29 | 58 | [5 empty] | 2021-11-18 | 2021-11-18 | 2021-12-15 | 17
121373181 | 974 | PGE | 94558 | NEM | EXPNEM | Commercial | Solar PV | 59.519 |  | 2021-05-21 |  | 2021-06-11 | 2021-05-25 | 2021-05-25 | 2 | 2021-06-22 | 21 | 2021-07-08 | 11 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-16 | 6 |  |  |  |  | 2021-05-21 | 2021-05-25 | 2021-05-21 | 2021-06-07 | 10 |  |  |  |  | 2021-11-01 | 2021-11-05 | 4 | [15 empty] | 2021-11-01 | 2021-11-01 | 0 | 2021-11-05 |  | 2021-11-12 | 4
121373517 | 975 | PGE | 94704 | NEM | EXPNEM | IA in Progress | Solar PV | 36.511 |  | 2021-05-21 |  | 2021-06-03 | 2021-06-03 | 2021-06-03 | 8 | 2021-07-09 | 33 |  |  | 2021-08-09 | 2021-09-01 | 17 | [12 empty] | 2021-09-01 | 2021-09-02 | 1 | 2021-09-02 | [11 empty] | 2021-07-23
121373784 | 976 | PGE | 94558 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-05-21 |  | 2021-08-05 | 2021-06-02 | 2021-06-02 | 7 | 2021-06-29 | 26 | 2021-08-20 | 37 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-20 | 2021-08-30 | 6 |  |  |  |  | 2021-05-21 | 2021-08-05 | 2021-05-21 | 2021-08-13 | 58 |  |  |  |  | 2021-10-28 | 2021-11-04 | 5 | [15 empty] | 2021-10-28 | 2021-10-28 | 0 | 2021-11-04 |  | 2021-11-04 | 0
121374252 | 977 | PGE | 93654 | NEM | NEMMT | Implementation | Solar PV | 659.212 |  | 2021-05-21 |  | 2021-08-12 | 2021-06-02 | 2021-06-02 | 7 | 2021-08-20 | 63 | 2021-09-03 | 10 | 2021-09-03 | 2021-10-01 | 19 | [12 empty] | 2021-10-01 | 2021-10-13 | 8 | 2021-10-13 | [6 empty] | 2021-08-12 | 2021-09-30 | 2021-08-12 | 2021-10-06 | 38 | 2021-08-24 | 2021-10-06 | 2021-10-13 | 30
121374355 | 978 | PGE | 93307 | NEM | EXPNEM | Withdrawn | Solar PV | 150 |  | 2021-05-21 |  | 2021-06-15 | 2021-06-03 | 2021-06-03 | 8 | 2021-06-17 | 18 | 2021-07-02 | 11 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | [6 empty] | 2021-05-21 |  | 2021-05-21 |  |  | 2021-07-01
121374357 | 979 | PGE | 95127 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.408 |  | 2021-05-21 |  | 2021-05-24 | 2021-05-24 | 2021-05-24 | 1 | 2021-06-07 | 10 | 2021-06-09 | 2 | [34 empty] | 2021-06-10 | 2021-06-10 | 0 | [15 empty] | 2021-06-10 |  |  | 2021-06-10 |  | 2021-06-10 | 0
121374869 | 980 | PGE | 93245 | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-05-21 |  |  | 2021-05-28 | 2021-05-28 | 5 | 2021-05-28 | 5 | 2021-06-15 | 11 | 2021-06-15 | 2021-07-14 | 20 | [12 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-10-01 | 56 |  |  |  |  | 2021-05-21 | 2021-05-28 | 2021-05-21 | 2021-06-15 | 16 |  |  |  |  | 2021-10-01 | 2021-10-08 | 5 | [15 empty] | 2021-10-01 | 2021-10-01 | 0 | 2021-10-08 |  | 2021-10-15 | 5
121375280 | 981 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 90.925 |  | 2021-05-21 |  | 2021-06-01 | 2021-06-01 | 2021-06-01 | 6 | 2021-06-07 | 10 | 2021-06-21 | 10 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-30 | 7 |  |  |  |  | 2021-05-21 | 2021-06-01 | 2021-05-21 | 2021-06-15 | 16 |  |  |  |  | 2021-11-29 | 2021-12-09 | 8 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-12-09 |  | 2021-12-16 | 5
121375380 | 982 | PGE | 94558 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.305 |  | 2021-05-21 |  | 2021-06-03 | 2021-05-25 | 2021-05-25 | 2 | 2021-06-08 | 11 | 2021-06-08 | 0 | [25 empty] | 2021-05-21 |  | 2021-05-21 | [6 empty] | 2021-07-14 | 2021-07-14 | 0 | [15 empty] | 2021-06-28 | 2021-07-01 | 2 | 2021-07-14 |  | 2021-07-14 | 0
121375492 | 983 | PGE | 94103 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-05-21 |  | 2021-07-07 | 2021-06-04 | 2021-06-04 | 9 | 2021-07-14 | 36 | 2021-07-14 | 0 | [15 empty] | 2021-07-14 | 2021-07-21 | 5 | 2021-07-21 | 2021-07-21 | 0 | [13 empty] | 2021-07-29 | 2021-08-05 | 5 | [15 empty] | 2021-07-29 | 2021-07-29 | 0 | 2021-08-05 |  | 2021-08-13 | 6
121375499 | 984 | PGE | 93609 | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-05-21 |  | 2021-06-11 | 2021-06-04 | 2021-06-04 | 9 | 2021-06-15 | 16 | 2021-07-01 | 12 | 2021-07-01 | 2021-07-30 | 20 | [12 empty] | 2021-07-30 | 2021-07-30 | 0 | 2021-07-30 | [6 empty] | 2021-05-21 |  | 2021-05-21 |  |  | 2021-07-09
121375882 | 985 | PGE | 95205 | NEM | EXPNEM | IA in Progress | Solar PV | 37.598 |  | 2021-05-21 |  | 2021-06-07 | 2021-06-07 | 2021-06-07 | 10 | 2021-07-06 | 30 | 2021-07-22 | 12 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | [6 empty] | 2021-05-21 |  | 2021-05-21
121376015 | 986 | PGE | 94923 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 |  | 2021-05-21 |  | 2021-05-25 | 2021-05-25 | 2021-05-25 | 2 | 2021-05-28 | 5 | 2021-06-02 | 2 | [15 empty] | 2021-05-21 | 2021-05-21 |  | 2021-05-21 | 2021-06-15 | 18 | [13 empty] | 2021-06-15 | 2021-06-15 | 0 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-15 |  | 2021-06-15 | 0
121376016 | 987 | PGE | 95928 | NEM | EXPNEM | IA in Progress | Solar PV, WIND | 86.681 |  | 2021-05-21 |  | 2021-06-14 | 2021-06-05 | 2021-06-05 | 9 | 2021-07-09 | 33 | 2021-07-27 | 12 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27
121376996 | 988 | PGE | 95928 | NEM | VNEMMASH | Application Review in Progress | Solar PV | 72.55 |  | 2021-05-21 |  | 2021-06-07 | 2021-06-07 | 2021-06-07 | 10 | [29 empty] | 2021-05-21 |  | 2021-05-21
121377065 | 989 | PGE | 93455 | NEM | EXPNEM | IA in Progress | Solar PV | 63.892 |  | 2021-05-21 |  | 2021-06-01 | 2021-06-01 | 2021-06-01 | 6 | 2021-06-15 | 16 | 2021-06-23 | 6 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23
121377177 | 990 | PGE | 93446 | NEM | EXPNEM | IA in Progress | Solar PV | 72.22 |  | 2021-05-21 |  | 2021-06-15 | 2021-06-01 | 2021-06-01 | 6 | 2021-06-16 | 17 | 2021-07-01 | 11 | [15 empty] | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01
121377178 | 991 | PGE | 95928 | NEM | VNEMMASH | Application Review in Progress | Solar PV | 72.55 |  | 2021-05-21 |  | 2021-06-04 | 2021-06-04 | 2021-06-04 | 9 | [29 empty] | 2021-05-21 |  | 2021-05-21
121377182 | 992 | PGE | 94586 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.752 |  | 2021-05-21 |  |  | 2021-06-02 | 2021-06-02 | 7 | 2021-06-02 | 7 | 2021-07-12 | 27 | [15 empty] | 2021-05-21 | 2021-05-21 |  | 2021-05-21 | 2021-05-21 | 1 | [13 empty] | 2021-10-19 | 2021-10-29 | 8 | [15 empty] | 2021-10-19 | 2021-10-20 | 1 | 2021-10-29 |  | 2021-10-29 | 0
121377527 | 993 | PGE | 94112 | Non-NEM | Continuous Uncompensated Export | IA in Progress | Solar PV | 271.284 |  | 2021-05-21 | 2021-05-24 |  | 2021-05-24 | 2021-05-24 | 1 | 2021-06-02 | 7 | 2021-07-14 | 29 | [15 empty] | 2021-07-14 | 2021-07-28 | 10 | 2021-07-28
121377656 | 994 | PGE | 95928 | NEM | VNEMMASH | Application Review in Progress | Solar PV | 72.55 |  | 2021-05-21 |  | 2021-06-04 | 2021-06-04 | 2021-06-04 | 9 | [29 empty] | 2021-05-21 |  | 2021-05-21
121377796 | 995 | PGE | 94580 | NEM | NEMMT | Implementation | ENGN, Solar PV, Storage | 1792 |  | 2021-05-21 |  |  | 2021-05-28 | 2021-05-28 | 5 | 2021-06-03 | 8 | 2021-07-23 | 35 | [15 empty] | 2021-07-29 | 2021-08-05 | 5 | 2021-08-05 | 2021-08-16 | 7 |  |  |  |  | 2021-05-21 |  | 2021-05-21 | [9 empty] | 2021-12-29 |  | 12
121387357 | 996 | PGE | 93314 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-05-24 |  | 2021-06-09 | 2021-05-25 | 2021-05-25 | 1 | 2021-06-09 | 11 | 2021-06-10 | 1 | [34 empty] | 2021-06-10 | 2021-06-10 | 0 | [15 empty] | 2021-06-10 |  |  | 2021-06-10 |  | 2021-06-10 | 0
121388233 | 997 | PGE | 93280 | NEM | EXPNEM | Implementation | Solar PV | 470 |  | 2021-05-24 |  |  | 2021-06-07 | 2021-06-07 | 9 | [7 empty] | 2021-06-08 | 2021-07-01 | 17 | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01 | 2021-09-27 | 60 | 2021-07-01 | 2021-07-01 | 0 | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-11-01 | 25 |  |  |  |  | 2021-05-24 |  | 2021-05-24 |  |  | 2021-06-17 | [6 empty] | 2021-12-14 |  | 22
121388478 | 998 | PGE | 93619 | NEM | EXPNEM | Implementation | Solar PV | 34.8 |  | 2021-05-24 |  | 2021-06-07 | 2021-06-07 | 2021-06-07 | 9 | 2021-08-04 | 50 | 2021-09-24 | 36 | [15 empty] | 2021-10-08 | 2021-10-08 | 0 | 2021-10-08 | 2021-10-12 | 2 | [9 empty] | 2021-10-01 | 2021-11-02 | 2021-11-02 | 22
121389094 | 999 | PGE | 95605 | NEM | EXPNEM | Commercial | Solar PV | 249.258 |  | 2021-05-24 |  | 2021-06-03 | 2021-06-03 | 2021-06-03 | 7 | 2021-07-15 | 36 | 2021-08-10 | 18 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-10 | 2021-09-07 | 19 |  |  |  |  | 2021-05-24 | 2021-06-03 | 2021-05-24 | 2021-06-15 | 15 |  |  |  |  | 2021-10-14 | 2021-10-21 | 5 | [15 empty] | 2021-10-14 | 2021-10-14 | 0 | 2021-10-21 |  | 2021-10-28 | 5
121389545 | 1000 | PGE | 95973 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-05-24 |  | 2021-06-07 | 2021-06-04 | 2021-06-04 | 8 | 2021-06-09 | 11 | 2021-06-15 | 4 | 2021-06-15 | 2021-07-14 | 20 | 2021-07-14 | 2021-08-09 | 18 | 2021-08-09 |  |  |  | 2021-11-24 |  |  |  |  | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | [6 empty] | 2021-05-24 | 2021-06-09 | 2021-05-24 | 2021-06-17 | 17
121389688 | 1001 | PGE | 93313 | NEM | EXPNEM | IA in Progress | Solar PV | 90.477 |  | 2021-05-24 |  | 2021-06-11 | 2021-06-02 | 2021-06-02 | 6 | 2021-11-03 | 114 | 2021-11-19 | 11 | [15 empty] | 2021-11-19 | 2021-11-19 | 0 | 2021-11-19 | 2021-12-16 | 17 |  |  |  |  | 2021-05-24 | 2021-06-02 | 2021-05-24 | 2021-06-15 | 15
121389970 | 1002 | PGE | 95946 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-05-24 |  | 2021-06-08 | 2021-06-08 | 2021-06-08 | 10 | 2021-06-18 | 18 | 2021-07-08 | 13 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-09-09 | 44 | [13 empty] | 2021-09-17 | 2021-09-27 | 6 | [15 empty] | 2021-09-17 | 2021-09-20 | 1 | 2021-09-27 |  | 2021-10-01 | 4
121390538 | 1003 | PGE | 95046 | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-05-24 |  | 2021-06-04 | 2021-06-04 | 2021-06-04 | 8 | 2021-07-26 | 43 | 2021-08-19 | 18 | [15 empty] | 2021-08-19 | 2021-08-20 | 1 | 2021-08-20 | 2021-09-13 | 15 |  |  |  |  | 2021-05-24 | 2021-07-26 | 2021-05-24 | 2021-08-05 | 51 |  |  |  |  | 2021-11-19 | 2021-11-30 | 5 | [15 empty] | 2021-11-19 | 2021-11-21 | 0 | 2021-11-30 |  | 2021-11-30 | 0
121391420 | 1004 | PGE | 95928 | NEM | EXPNEM | Commercial | Solar PV | 40.269 |  | 2021-05-24 |  | 2021-06-02 | 2021-06-02 | 2021-06-02 | 6 | 2021-07-12 | 33 | 2021-07-26 | 10 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-08-04 | 7 | [13 empty] | 2021-08-09 | 2021-08-13 | 4 | [15 empty] | 2021-08-09 | 2021-08-10 | 1 | 2021-08-13 |  | 2021-08-19 | 4
121391712 | 1005 | PGE | 93280 | NEM | EXPNEM | Study in Progress | Solar PV | 1560 |  | 2021-05-24 | 2021-05-26 |  | 2021-05-25 | 2021-05-25 | 1 | 2021-06-02 | 6 | 2021-07-26 | 37 | 2021-08-12 | 2021-09-10 | 20 | 2021-10-19 | 2021-11-12 | 17 | 2021-11-12 |  | 1 | 2021-11-23 |  |  |  | 2021-11-12 | 1 | [10 empty] | 2021-05-24 |  | 2021-05-24 |  |  | 2021-08-06
121393152 | 1006 | PGE | 93722 | NEM | EXPNEM | Implementation | Solar PV | 221.358 |  | 2021-05-25 |  | 2021-06-08 | 2021-06-08 | 2021-06-08 | 9 | 2021-06-15 | 14 | 2021-07-02 | 13 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-07-08 | 3 |  |  |  |  | 2021-05-25 | 2021-08-13 | 2021-05-25 | 2021-08-27 | 66 | 2021-08-06 |  |  |  | 2021-09-13 | 2021-09-16 | 3 | 2021-10-21 |  | 57 | [12 empty] | 2021-09-13 | 2021-09-14 | 1 | 2021-09-16 | 2021-09-17 |  | 1 |  |  | 80
121393713 | 1007 | PGE | 95340 | NEM | EXPNEM | Commercial | Solar PV | 213.803 |  | 2021-05-25 |  | 2021-06-08 | 2021-06-08 | 2021-06-08 | 9 | 2021-06-15 | 14 | 2021-07-06 | 14 | [15 empty] | 2021-08-25 | 2021-08-30 | 3 | 2021-08-30 | 2021-08-31 | 1 |  |  |  |  | 2021-05-25 |  | 2021-05-25 |  |  | 2021-07-09 |  |  |  | 2021-12-08 | 2021-12-20 | 8 | [15 empty] | 2021-12-08 | 2021-12-09 | 1 | 2021-12-20 |  | 2021-12-20 | 0
121396920 | 1008 | PGE | 93242 | NEM | EXPNEM | IA in Progress | Solar PV | 85.259 |  | 2021-05-25 |  | 2021-06-04 | 2021-06-04 | 2021-06-04 | 7 | 2021-06-09 | 10 | 2021-06-21 | 8 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-24 | 3 |  |  |  |  | 2021-05-25 | 2021-06-09 | 2021-05-25 | 2021-06-17 | 16
121397037 | 1009 | PGE | 93706 | NEM | EXPNEM | Implementation | Solar PV | 60 |  | 2021-05-25 |  | 2021-06-09 | 2021-06-08 | 2021-06-08 | 9 | 2021-06-09 | 10 | 2021-06-18 | 7 | [15 empty] | 2021-06-18 | 2021-06-25 | 5 | 2021-06-25 | 2021-06-28 | 1 |  |  |  |  | 2021-05-25 | 2021-06-16 | 2021-05-25 | 2021-06-24 | 21 |  |  |  |  | 2021-12-29 | [17 empty] | 2021-12-29 | 2021-12-30 | 1
121397387 | 1010 | PGE | 95376 | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-05-25 |  |  | 2021-06-08 | 2021-06-08 | 9 | 2021-06-08 | 9 | 2021-06-23 | 11 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-11-08 | 96
121397581 | 1011 | PGE | 93648 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 30.402 |  | 2021-05-25 |  |  | 2021-06-11 | 2021-06-11 | 12 | 2021-06-25 | 22 | 2021-07-19 | 15 | [15 empty] | 2021-07-19 | 2021-07-19 | 0 | 2021-07-19 | [6 empty] | 2021-05-25 |  | 2021-05-25
121397640 | 1012 | PGE | 93648 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.179 |  | 2021-05-25 |  |  | 2021-06-11 | 2021-06-11 | 12 | 2021-06-25 | 22 | 2021-07-19 | 15 | [15 empty] | 2021-07-19 | 2021-07-19 | 0 | 2021-07-19 | [6 empty] | 2021-05-25 |  | 2021-05-25
121398219 | 1013 | PGE | 94560 | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-05-26 | 2021-05-27 |  | 2021-05-27 | 2021-05-27 | 1 | 2021-06-09 | 9 | 2021-07-28 | 34 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | 2021-10-22 | 61 | [13 empty] | 2021-11-30 | 2021-12-08 | 6 | [15 empty] | 2021-11-30 | 2021-11-30 | 0 | 2021-12-08 |  | 2021-12-09 | 1
121398274 | 1014 | PGE | 94538 | NEM | NEMMT | Application Accepted | Solar PV, Storage | 56.26 |  | 2021-05-25 | 2021-05-27 |  | 2021-05-26 | 2021-05-26 | 1 | 2021-06-16 | 15
121401104 | 1015 | PGE | 95330 | NEM | EXPNEM | Withdrawn | Solar PV | 1466.6 |  | 2021-05-26 |  | 2021-06-04 | 2021-06-04 | 2021-06-04 | 6 | 2021-08-04 | 48 | 2021-09-08 | 24 | 2021-09-24 | 2021-10-25 | 21 | [22 empty] | 2021-08-10 | 2021-09-29 | 2021-08-10 | 2021-10-18 | 48
121401939 | 1016 | PGE | 95936 | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2021-05-26 | 2021-05-28 |  | 2021-05-27 | 2021-05-27 | 1 | 2021-06-23 | 19 | 2021-07-15 | 15 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-08-06 | 16
121402560 | 1017 | PGE | 95004 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 750 |  | 2021-05-26 |  | 2021-06-09 | 2021-06-09 | 2021-06-09 | 9 | 2021-08-18 | 58 | 2021-10-11 | 37 | [15 empty] | 2021-10-11 | 2021-10-11 | 0 | 2021-10-11 | [11 empty] | 2021-09-10 | 2021-09-10 | 2021-10-11 | 0
121403282 | 1018 | PGE | 95482 | NEM | VNEMMASH | Implementation | Solar PV | 41.246 |  | 2021-05-26 |  | 2021-06-10 | 2021-06-10 | 2021-06-10 | 10 | 2021-08-02 | 46 | 2021-08-23 | 15 | [15 empty] | 2021-08-23 | 2021-09-14 | 15 | 2021-09-14 | 2021-09-16 | 2 | [5 empty] | 2021-08-05 | 2021-08-05 | 2021-08-13 | 6
121403301 | 1019 | PGE | 95482 | NEM | VNEMMASH | Implementation | Solar PV | 36.905 |  | 2021-05-26 |  | 2021-06-10 | 2021-06-10 | 2021-06-10 | 10 | 2021-08-02 | 46 | 2021-08-23 | 15 | [15 empty] | 2021-08-23 | 2021-09-14 | 15 | 2021-09-14 | 2021-09-16 | 2 | [5 empty] | 2021-09-24 | 2021-09-24 | 2021-10-15 | 15
121403307 | 1020 | PGE | 95482 | NEM | VNEMMASH | Implementation | Solar PV | 55.756 |  | 2021-05-26 |  | 2021-06-10 | 2021-06-10 | 2021-06-10 | 10 | 2021-08-02 | 46 | 2021-08-23 | 15 | [15 empty] | 2021-08-23 | 2021-09-14 | 15 | 2021-09-14 | 2021-09-16 | 2 | [5 empty] | 2021-08-05 | 2021-08-05 | 2021-08-13 | 6
121403923 | 1021 | PGE | 93721 | NEM | EXPNEM | Application Review in Progress | Solar PV | 32.125 |  | 2021-05-26 |  | 2021-06-11 | 2021-06-04 | 2021-06-04 | 6
121403946 | 1022 | PGE | 95540 | Non-NEM | Non-Export | IA in Progress | Storage | 630 |  | 2021-05-26 | 2021-05-28 |  | 2021-05-27 | 2021-05-27 | 1 | 2021-06-30 | 24 | 2021-09-17 | 55 | [15 empty] | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | [6 empty] | 2021-05-26 |  | 2021-05-26
121407586 | 1023 | PGE | 93408 | Non-NEM | Non-Export | Implementation | ENGN, Storage | 290 |  | 2021-05-27 | 2021-05-28 |  | 2021-05-27 | 2021-05-27 | 0 | 2021-06-23 | 18 | 2021-08-10 | 33 | [15 empty] | 2021-08-10 | 2021-08-25 | 11 | 2021-08-25 | 2021-11-23 | 62 |  |  |  |  | 2021-05-27 | 2021-07-01 | 2021-05-27 | 2021-07-07 | 27
121416495 | 1024 | PGE | 94611 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.395 |  | 2021-05-27 |  | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2 | 2021-06-04 | 5 | 2021-06-08 | 2 | [34 empty] | 2021-06-08 | 2021-06-08 | 0 | [15 empty] | 2021-06-08 |  |  | 2021-06-08 |  | 2021-06-08 | 0
121416566 | 1025 | PGE | 95959 | NEM | VNEMMASH | IA in Progress | Solar PV | 37.758 |  | 2021-05-27 |  | 2021-06-11 | 2021-06-11 | 2021-06-11 | 10 | 2021-08-19 | 58 | 2021-09-08 | 13 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | [6 empty] | 2021-05-27 |  | 2021-05-27
121416960 | 1026 | PGE | 95032 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.232 |  | 2021-05-27 |  | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2 | 2021-07-13 | 31 | 2021-07-15 | 2 | [34 empty] | 2021-07-16 | 2021-07-16 | 0 | [15 empty] | 2021-07-16 |  |  | 2021-07-16 |  | 2021-07-16 | 0
121417422 | 1027 | PGE | 95330 | NEM | EXPNEM | Commercial | Solar PV | 32.401 |  | 2021-05-27 |  | 2021-10-11 | 2021-06-07 | 2021-06-07 | 6 | 2021-10-18 | 99 | 2021-10-21 | 3 | [15 empty] | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21 | 2021-12-06 | 29 |  |  |  |  | 2021-05-27 | 2021-10-21 | 2021-05-27 | 2021-11-03 | 111 |  |  |  |  | 2021-12-08 | 2021-12-17 | 7 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-17 |  | 2021-12-23 | 4
121424947 | 1028 | PGE | 95045 | NEM | EXPNEM | Implementation | Solar PV | 35.187 |  | 2021-05-28 |  | 2021-06-14 | 2021-06-14 | 2021-06-14 | 10 | 2021-06-17 | 13 | 2021-07-07 | 13 | [15 empty] | 2021-07-07 | 2021-07-26 | 13 | 2021-07-26 | 2021-08-13 | 14 |  |  |  |  | 2021-05-28 | 2021-06-17 | 2021-05-28 | 2021-07-02 | 24
121425609 | 1029 | PGE | 95020 | NEM | EXPNEM | Commercial | Solar PV | 90 |  | 2021-05-28 |  | 2021-06-16 | 2021-06-08 | 2021-06-08 | 6 | 2021-07-02 | 24 | 2021-07-21 | 12 | [15 empty] | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | 2021-08-18 | 20 | [13 empty] | 2021-08-27 | 2021-09-07 | 6 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-09-07 |  | 2021-09-13 | 4
121426881 | 1030 | PGE | 95422 | NEM | EXPNEM | Implementation | Solar PV | 98.329 |  | 2021-05-28 |  | 2021-06-23 | 2021-06-23 | 2021-06-23 | 17 | 2021-08-18 | 56 | 2021-09-29 | 29 | [15 empty] | 2021-09-29 | 2021-10-19 | 14 | 2021-10-19 | 2021-12-10 | 35 |  |  |  |  | 2021-05-28 |  | 2021-05-28 |  |  | 2021-09-08
121427426 | 1031 | PGE | 95959 | NEM | VNEMMASH | IA in Progress | Solar PV | 36.54 |  | 2021-05-28 |  | 2021-06-11 | 2021-06-11 | 2021-06-11 | 9 | 2021-08-19 | 57 | 2021-09-08 | 13 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | [6 empty] | 2021-05-28 |  | 2021-05-28
121428122 | 1032 | PGE | 95943 | NEM | EXPNEM | IA in Progress | Solar PV | 35.172 |  | 2021-05-28 |  | 2021-10-14 | 2021-06-09 | 2021-06-09 | 7 | 2021-10-28 | 106 | 2021-11-09 | 8 | [15 empty] | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | [6 empty] | 2021-05-28 | 2021-10-05 | 2021-05-28 | 2021-10-18 | 98
121428277 | 1033 | PGE | 95650 | NEM | EXPNEM | Study in Progress | Solar PV | 66.6 |  | 2021-05-28 |  | 2021-07-08 | 2021-06-09 | 2021-06-09 | 7 | 2021-07-02 | 24 | 2021-08-30 | 40 | 2021-08-30 | 2021-10-04 | 24 | 2021-10-04 | 2021-10-27 | 17 | 2021-10-27
121428473 | 1034 | PGE | 95018 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 36.796 |  | 2021-05-28 |  |  | 2021-06-02 | 2021-06-02 | 2 | 2021-06-02 | 2 | 2021-06-07 | 3 | [55 empty] | 2021-06-07 |  | 2021-06-07 | 1
121432290 | 1035 | PGE | 94517 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-05-30 |  | 2021-06-02 | 2021-06-02 | 2021-06-02 | 1 | 2021-07-12 | 28 | 2021-07-13 | 1 | [34 empty] | 2021-07-14 | 2021-07-14 | 0 | [15 empty] | 2021-07-14 |  |  | 2021-07-14 |  | 2021-07-14 | 0
121435809 | 1036 | PGE | 93401 | NEM | EXPNEM | Implementation | Solar PV | 34.179 |  | 2021-06-01 |  | 2021-06-15 | 2021-06-15 | 2021-06-15 | 10 | 2021-08-02 | 43 | 2021-11-02 | 65 | [15 empty] | 2021-11-02 | 2021-11-15 | 8 | 2021-11-15 | 2021-11-15 | 0 |  |  |  |  | 2021-06-01 |  | 2021-06-01 |  |  | 2021-09-02
121435858 | 1037 | PGE | 93401 | NEM | EXPNEM | Implementation | Solar PV | 34.179 |  | 2021-06-01 |  | 2021-06-15 | 2021-06-15 | 2021-06-15 | 10 | 2021-08-25 | 60 | 2021-09-07 | 8 | [15 empty] | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-12-31 | 80 |  |  |  |  | 2021-06-01 | 2021-08-25 | 2021-06-01 | 2021-09-08 | 69
121435881 | 1038 | PGE | 93401 | NEM | EXPNEM | Implementation | Solar PV | 42.472 |  | 2021-06-01 |  | 2021-06-09 | 2021-06-09 | 2021-06-09 | 6 | 2021-08-12 | 51 | 2021-08-25 | 9 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | 2021-11-15 | 56 |  |  |  |  | 2021-06-01 | 2021-08-23 | 2021-06-01 | 2021-09-07 | 68
121438450 | 1039 | PGE | 93706 | NEM | EXPNEM | IA in Progress | Solar PV | 696 |  | 2021-06-01 |  | 2021-07-15 | 2021-06-15 | 2021-06-15 | 10 | 2021-07-26 | 38 | 2021-08-11 | 12 | 2021-08-11 | 2021-09-05 | 17 | [12 empty] | 2021-09-05 | 2021-09-05 | 0 | 2021-09-05 | 2021-10-20 | 31 | [16 empty] | 2021-11-15 |  | 41
121438653 | 1040 | PGE | 95553 | NEM | EXPNEM | Commercial | Solar PV | 226.751 |  | 2021-06-01 |  | 2021-07-06 | 2021-06-14 | 2021-06-14 | 9 | 2021-06-30 | 21 | 2021-08-06 | 26 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | 2021-08-16 | 6 |  |  |  |  | 2021-06-01 |  | 2021-06-01 | [6 empty] | 2021-12-10 | 2021-12-22 | 8 | [15 empty] | 2021-12-10 | 2021-12-10 | 0 | 2021-12-22 |  | 2021-12-22 | 0
121439361 | 1041 | PGE | 93204 | NEM | EXPNEM | Commercial | Solar PV | 36.186 |  | 2021-06-01 |  | 2021-06-14 | 2021-06-09 | 2021-06-09 | 6 | 2021-06-28 | 19 | 2021-07-08 | 7 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-08-16 | 27 |  |  |  |  | 2021-06-01 | 2021-07-08 | 2021-06-01 | 2021-07-19 | 33 |  |  |  |  | 2021-09-17 | 2021-09-23 | 4 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-23 |  | 2021-09-30 | 5
121439497 | 1043 | PGE | 94507 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.657 |  | 2021-06-01 |  | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2 | 2021-06-15 | 10 | 2021-06-16 | 1 | [34 empty] | 2021-06-16 | 2021-06-16 | 0 | [15 empty] | 2021-06-16 |  |  | 2021-06-16 |  | 2021-06-16 | 0
121445323 | 1044 | PGE | 93725 | NEM | EXPNEM | Implementation | Solar PV | 75.777 |  | 2021-06-02 |  | 2021-06-15 | 2021-06-14 | 2021-06-14 | 8 | 2021-06-14 | 8 | 2021-07-02 | 14 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-07-02 | 0 |  |  |  |  | 2021-06-02 |  | 2021-06-02 |  |  | 2021-07-09
121445490 | 1045 | PGE | 95632 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-06-02 |  | 2021-06-14 | 2021-06-14 | 2021-06-14 | 8 | 2021-06-16 | 10 | 2021-06-28 | 8 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-07-26 | 19 |  |  |  |  | 2021-06-02 | 2021-06-16 | 2021-06-02 | 2021-06-28 | 18 |  |  |  |  | 2021-07-26 | 2021-08-03 | 6 | [15 empty] | 2021-07-26 | 2021-07-27 | 1 | 2021-08-03 |  | 2021-08-04 | 1
121445573 | 1046 | PGE | 93706 | NEM | EXPNEM | Commercial | Solar PV | 229.645 |  | 2021-06-02 |  |  | 2021-06-09 | 2021-06-09 | 5 | 2021-06-09 | 5 | 2021-06-24 | 11 | 2021-06-24 | 2021-07-06 | 7 | [12 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-07-08 | 2 | [13 empty] | 2021-11-05 | 2021-11-12 | 4 | [15 empty] | 2021-11-05 | 2021-11-05 | 0 | 2021-11-12 |  | 2021-11-19 | 5
121446288 | 1047 | PGE | 94578 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 56.965 |  | 2021-06-02 |  |  | 2021-06-11 | 2021-06-11 | 7 | 2021-06-11 | 7 | 2021-07-02 | 15 | [15 empty] | 2021-07-02 | 2021-07-26 | 15 | 2021-07-26 | [6 empty] | 2021-06-02 | 2021-09-21 | 2021-06-02 | 2021-09-23 | 79 |  | 2021-08-19 | 2021-08-19 | 0
121446467 | 1048 | PGE | 95301 | NEM | EXPNEM | IA in Progress | Solar PV | 72.547 |  | 2021-06-02 |  | 2021-08-23 | 2021-06-09 | 2021-06-09 | 5 | 2021-08-25 | 59 | 2021-09-16 | 15 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | 2021-10-07 | 15 |  |  |  |  | 2021-06-02 | 2021-08-25 | 2021-06-02 | 2021-09-08 | 68 | [7 empty] | 2021-11-16 |  | 40
121447252 | 1049 | PGE | 94519 | Non-NEM | Non-Export | Withdrawn | Solar PV | 50 |  | 2021-06-02 |  |  | 2021-06-02 | 2021-06-02 | 0
121447549 | 1050 | PGE | 93212 | Non-NEM | RESBCT | Implementation | Solar PV | 3125 |  | 2021-06-02 | 2021-06-04 |  | 2021-06-04 | 2021-06-04 | 2 | 2021-06-16 | 10 | [5 empty] | 2021-06-16 | 2021-07-12 | 17 | 2021-07-12 | 2021-07-12 | 0 | 2021-07-22 | 2021-10-05 | 52 | 2021-07-12 | 2021-07-12 | 0 | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-11-15 | 18
121448017 | 1051 | PGE | 93907 | NEM | EXPNEM | Commercial | Solar PV | 60.868 |  | 2021-06-02 |  | 2021-06-18 | 2021-06-10 | 2021-06-10 | 6 | 2021-06-22 | 14 | 2021-07-14 | 15 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-22 | 6 | [13 empty] | 2021-07-31 | 2021-08-10 | 6 | [15 empty] | 2021-07-31 | 2021-08-02 | 0 | 2021-08-10 |  | 2021-08-13 | 3
121449425 | 1052 | PGE | 95060 | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.3 |  | 2021-06-02 |  | 2021-06-12 | 2021-06-10 | 2021-06-10 | 6
121449590 | 1053 | PGE | 95060 | NEM | EXPNEM | Application Review in Progress | Solar PV | 40.002 |  | 2021-06-02 |  | 2021-06-15 | 2021-06-10 | 2021-06-10 | 6
121449970 | 1054 | PGE | 95210 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 277.81 |  | 2021-06-03 |  | 2021-06-17 | 2021-06-17 | 2021-06-17 | 10 | 2021-10-19 | 96 | 2021-11-09 | 15 | [15 empty] | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | [6 empty] | 2021-06-03 | 2021-11-16 | 2021-06-03 | 2021-12-15 | 134
121450747 | 1055 | PGE | 94601 | NEM | EXPNEM | IA in Progress | Solar PV | 168.227 |  | 2021-06-03 |  | 2021-08-02 | 2021-06-15 | 2021-06-15 | 8 | 2021-10-15 | 94 | 2021-10-20 | 3 | [15 empty] | 2021-10-20 | 2021-10-20 | 0 | 2021-10-20 | 2021-12-22 | 42 |  |  |  |  | 2021-07-14 | 2021-10-14 | 2021-07-14 | 2021-10-27 | 74 | [7 empty] | 2022-01-11 |  | 3
121451502 | 1056 | PGE | 94924 | NEM | EXPNEM | IA in Progress | Solar PV | 57.177 |  | 2021-06-03 |  | 2021-06-17 | 2021-06-17 | 2021-06-17 | 10 | 2021-07-09 | 25 | 2021-07-26 | 11 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26
121452520 | 1057 | PGE | 95503 | NEM | EXPNEM | Commercial | Solar PV | 38.78 |  | 2021-06-03 |  | 2021-06-11 | 2021-06-11 | 2021-06-11 | 6 | 2021-06-15 | 8 | 2021-07-06 | 14 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-07-14 | 6 | [13 empty] | 2021-10-12 | 2021-10-18 | 4 | [15 empty] | 2021-10-12 | 2021-10-12 | 0 | 2021-10-18 |  | 2021-10-25 | 5
121452981 | 1058 | PGE | 93710 | NEM | EXPNEM | IA in Progress | ENGN, Solar PV | 437.796 |  | 2021-06-03 |  | 2021-06-17 | 2021-06-17 | 2021-06-17 | 10 | 2021-08-06 | 45 | 2021-08-23 | 11 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23
121453077 | 1059 | PGE | 95070 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.29 |  | 2021-06-03 |  | 2021-06-16 | 2021-06-07 | 2021-06-07 | 2 | 2021-08-27 | 60 | 2021-08-31 | 2 | [34 empty] | 2021-08-31 | 2021-08-31 | 0 | [15 empty] | 2021-08-31 |  |  | 2021-08-31 |  | 2021-08-31 | 0
121453943 | 1060 | PGE | 93446 | NEM | EXPNEM | Commercial | Solar PV | 35.005 |  | 2021-06-03 |  | 2021-06-11 | 2021-06-11 | 2021-06-11 | 6 | 2021-06-16 | 9 | 2021-07-08 | 15 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-09 | 1 | [13 empty] | 2021-07-26 | 2021-08-04 | 7 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-08-04 |  | 2021-08-11 | 5
121454801 | 1061 | PGE | 95659 | NEM | EXPNEM | Study in Progress | Solar PV | 634.724 |  | 2021-06-03 |  | 2021-10-26 | 2021-06-11 | 2021-06-11 | 6 | 2021-11-10 | 112 | 2021-12-03 | 14 | 2021-12-03
121454804 | 1062 | PGE | 95037 | NEM | EXPNEM | Study in Progress | Solar PV | 312.5 |  | 2021-06-03 |  | 2021-10-19 | 2021-06-11 | 2021-06-11 | 6 | 2021-11-01 | 105 | 2021-12-22 | 34 | 2021-12-22 | [24 empty] | 2021-06-03 |  | 2021-06-03
121460523 | 1063 | PGE | 95361 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 54.494 |  | 2021-06-03 |  | 2021-06-14 | 2021-06-08 | 2021-06-08 | 3 | 2021-06-16 | 9 | 2021-07-02 | 12 | [15 empty] | 2021-08-11 | 2021-08-11 | 0 | 2021-08-11 | 2021-08-11 | 0 | [13 empty] | 2021-08-11 | [17 empty] | 2021-08-11 | 2021-08-12 | 1
121464511 | 1064 | PGE | 94710 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-06-03 |  |  | 2021-06-11 | 2021-06-11 | 6 | 2021-06-11 | 6 | 2021-06-17 | 4 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-07-16 | 20 | [13 empty] | 2021-07-28 | 2021-08-05 | 6 | [15 empty] | 2021-07-28 | 2021-08-05 | 6 | 2021-08-05 |  | 2021-08-11 | 4
121466224 | 1065 | PGE | 93401 | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2021-06-04 | 2021-06-04 |  | 2021-06-04 | 2021-06-04 | 0 | 2021-06-30 | 18 | 2021-08-25 | 39 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | 2021-09-29 | 24 |  |  |  |  | 2021-06-04 | 2021-09-07 | 2021-06-04 | 2021-09-10 | 68
121466710 | 1066 | PGE | 93311 | NEM | EXPNEM | Withdrawn | ENGN | 1000 |  | 2021-06-04 |  |  | 2021-06-22 | 2021-06-22 | 12 | 2021-06-22 | 12 | 2021-07-09 | 12
121467447 | 1067 | PGE | 93711 | NEM | EXPNEM | IA in Progress | Solar PV | 44.37 |  | 2021-06-04 |  | 2021-08-13 | 2021-06-12 | 2021-06-12 | 5 | 2021-08-18 | 52 | 2021-09-08 | 14 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-09-08 | 0 | [5 empty] | 2021-12-29 | 2021-12-29 | [6 empty] | 2021-12-29 | [17 empty] | 2021-12-29 | 2021-12-30 | 1
121467479 | 1068 | PGE | 93245 | NEM | EXPNEM | Implementation | Solar PV | 266.145 |  | 2021-06-04 |  | 2021-07-08 | 2021-06-15 | 2021-06-15 | 7 | 2021-07-08 | 23 | 2021-08-10 | 23 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-10 | 2021-08-26 | 12
121467889 | 1069 | PGE | 96013 | Non-NEM | Non-Export | IA in Progress | Storage | 140 |  | 2021-06-04 | 2021-06-04 |  | 2021-06-04 | 2021-06-04 | 0 | 2021-06-30 | 18 | 2021-07-20 | 13 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | [6 empty] | 2021-06-04 | 2021-06-30 | 2021-06-04 | 2021-07-14 | 27 | [19 empty] | 2021-07-26
121469162 | 1070 | PGE | 95603 | NEM | VNEM | IA in Progress | Solar PV | 48.363 |  | 2021-06-04 |  | 2021-07-21 | 2021-06-18 | 2021-06-18 | 10 | 2021-12-13 | 131 | 2021-12-29 | 12 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29
121469331 | 1071 | PGE | 95603 | NEM | VNEM | IA in Progress | Solar PV | 57.71 |  | 2021-06-04 |  | 2021-07-21 | 2021-06-18 | 2021-06-18 | 10 | 2021-12-13 | 131 | 2021-12-29 | 12 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29
121469365 | 1072 | PGE | 95603 | NEM | VNEM | IA in Progress | Solar PV | 52.163 |  | 2021-06-04 |  | 2021-07-21 | 2021-06-18 | 2021-06-18 | 10 | 2021-12-13 | 131 | 2021-12-29 | 12 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29
121469768 | 1073 | PGE | 95446 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 32.436 |  | 2021-06-04 |  | 2021-06-18 | 2021-06-18 | 2021-06-18 | 10 | 2021-06-25 | 15 | 2021-07-19 | 15 | [15 empty] | 2021-07-19 | 2021-07-19 | 0 | 2021-07-19 | [7 empty] | 2021-07-21 | 2021-07-21 | 2021-08-03 | 9
121469908 | 1074 | PGE | 95446 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 52.163 |  | 2021-06-04 |  | 2021-06-18 | 2021-06-18 | 2021-06-18 | 10 | 2021-06-25 | 15 | 2021-07-19 | 15 | [15 empty] | 2021-07-19 | 2021-07-19 | 0 | 2021-07-19 | [7 empty] | 2021-07-21 | 2021-07-21 | 2021-08-03 | 9
121470469 | 1075 | PGE | 94954 | NEM | EXPNEM | Commercial | Solar PV | 31.791 |  | 2021-06-04 |  | 2021-06-12 | 2021-06-12 | 2021-06-12 | 5 | 2021-06-16 | 8 | 2021-07-06 | 13 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-07-21 | 11 | [13 empty] | 2021-10-11 | 2021-10-18 | 5 | [15 empty] | 2021-10-11 | 2021-10-12 | 1 | 2021-10-18 |  | 2021-10-25 | 5
121478443 | 1076 | PGE | 94062 | NEM | SNEM Paired Storage | Implementation | Solar PV, Storage | 42.725 |  | 2021-06-06 |  | 2021-08-11 | 2021-06-09 | 2021-06-09 | 2 | 2021-08-21 | 54 | 2021-08-23 | 0 | [34 empty] | 2021-08-23 | [17 empty] | 2021-08-23 | 2021-10-15 | 38
121479895 | 1077 | PGE | 94954 | NEM | EXPNEM | Implementation | Solar PV | 38.78 |  | 2021-06-07 |  | 2021-09-03 | 2021-06-10 | 2021-06-10 | 3 | 2021-09-03 | 63 | 2021-09-21 | 11 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | 2021-12-07 | 52 | [16 empty] | 2021-12-29 |  | 12
121484017 | 1078 | PGE | 95126 | NEM | EXPNEM | Implementation | Solar PV | 162.5 |  | 2021-06-07 |  | 2021-06-17 | 2021-06-16 | 2021-06-16 | 7 | 2021-06-16 | 7 | 2021-10-19 | 87 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-10-29 | 8 |  |  |  |  | 2021-06-07 | 2021-10-13 | 2021-06-07 | 2021-10-22 | 97
121484291 | 1079 | PGE | 95695 | NEM | EXPNEM | IA in Progress | Solar PV | 55.575 |  | 2021-06-07 |  | 2021-06-12 | 2021-06-12 | 2021-06-12 | 4 | 2021-06-16 | 7 | 2021-07-07 | 14 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | 2021-08-04 | 20 |  |  |  |  | 2021-06-07 | 2021-06-12 | 2021-06-07 | 2021-06-18 | 9 |  |  |  |  | 2021-08-26 | 2021-09-01 | 4 | 2021-09-17 |  | 81 | [12 empty] | 2021-08-26 | 2021-08-27 | 1 | 2021-09-01
121485338 | 1080 | PGE | 94519 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-06-07 |  | 2021-08-18 | 2021-06-12 | 2021-06-12 | 4 | 2021-08-30 | 59 | 2021-09-21 | 15 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | 2021-09-24 | 3 | [13 empty] | 2021-11-11 | 2021-11-17 | 3 | [15 empty] | 2021-11-11 | 2021-11-11 | 0 | 2021-11-17 |  | 2021-12-06 | 11
121485419 | 1081 | PGE | 95123 | NEM | EXPNEM | IA in Progress | Solar PV | 98.286 |  | 2021-06-07 |  | 2021-07-19 | 2021-06-12 | 2021-06-12 | 4 | 2021-09-23 | 76 | 2021-10-08 | 11 | [15 empty] | 2021-10-08 | 2021-10-08 | 0 | 2021-10-08 | [7 empty] | 2021-10-08 | 2021-10-08 | 2021-10-21 | 9
121485540 | 1082 | PGE | 95123 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-06-07 |  | 2021-06-12 | 2021-06-12 | 2021-06-12 | 4 | 2021-07-19 | 29 | 2021-08-04 | 12 | [15 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | 2021-08-30 | 18 | [5 empty] | 2021-11-19 | 2021-11-19 | 2021-12-13 | 14
121486366 | 1083 | PGE | 94517 | NEM | EXPNEM | Application Review in Progress | Solar PV | 900 |  | 2021-06-07 |  | 2021-07-28 | 2021-06-12 | 2021-06-12 | 4
121488398 | 1084 | PGE | 95695 | NEM | EXPNEM | IA in Progress | Solar PV | 58.63 |  | 2021-06-08 |  | 2021-08-03 | 2021-06-12 | 2021-06-12 | 3 | 2021-08-05 | 41 | 2021-08-24 | 13 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | 2021-08-31 | 5 |  |  |  |  | 2021-06-08 | 2021-07-14 | 2021-06-08 | 2021-07-28 | 35
121490216 | 1085 | PGE | 93704 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-06-08 |  |  | 2021-06-15 | 2021-06-15 | 5 | 2021-06-15 | 5 | 2021-06-18 | 3 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-18 | 2021-06-22 | 2 |  |  |  |  | 2021-06-08 | 2021-09-01 | 2021-06-08 | 2021-09-10 | 66 |  |  |  |  | 2021-12-02 | 2021-12-09 | 5 | [15 empty] | 2021-12-02 | 2021-12-02 | 0 | 2021-12-09 |  | 2021-12-16 | 5
121490383 | 1086 | PGE | 93710 | NEM | EXPNEM | IA in Progress | Solar PV | 38.138 |  | 2021-06-08 |  | 2021-07-01 | 2021-07-01 | 2021-07-01 | 17 | 2021-08-03 | 39 | 2021-08-13 | 8 | [15 empty] | 2021-08-13 | 2021-08-13 | 0 | 2021-08-13 | 2021-11-08 | 60 | [9 empty] | 2021-08-13 | 2021-11-18 | 2021-11-18 | 67
121490418 | 1087 | PGE | 94574 | NEM | EXPNEM | IA in Progress | Solar PV | 133.3 |  | 2021-06-08 |  |  | 2021-06-15 | 2021-06-15 | 5 | 2021-06-15 | 5 | 2021-07-27 | 29 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-08-06 | 8
121492025 | 1088 | PGE | 95692 | NEM | EXPNEM | Implementation | Solar PV | 66.6 |  | 2021-06-08 |  | 2021-06-24 | 2021-06-16 | 2021-06-16 | 6 | 2021-06-22 | 10 | 2021-07-12 | 13 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-07-20 | 6 |  |  |  |  | 2021-06-08 |  | 2021-06-08 | [9 empty] | 2021-08-18 | 2022-01-10 | 98
121492733 | 1089 | PGE | 93307 | NEM | EXPNEM | Implementation | Solar PV | 540 |  | 2021-06-08 |  | 2021-06-18 | 2021-06-18 | 2021-06-18 | 8 | 2021-06-22 | 10 | 2021-06-29 | 5 | 2021-06-29 | 2021-07-27 | 19 | [12 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-08-01 | 3 | [16 empty] | 2021-10-21 |  | 57
121496977 | 1090 | PGE | 95376 | NEM | EXPNEM | Withdrawn | Solar PV | 1200 |  | 2021-06-09 | 2021-06-09 |  | 2021-06-09 | 2021-06-09 | 0 | 2021-08-04 | 39 | 2021-10-14 | 50 | [25 empty] | 2021-06-09 |  | 2021-06-09
121497134 | 1091 | PGE | 94539 | NEM | EXPNEM | Commercial | Solar PV | 86.4 |  | 2021-06-09 |  | 2021-06-21 | 2021-06-15 | 2021-06-15 | 4 | 2021-06-28 | 13 | 2021-07-15 | 12 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-07-16 | 1 | [13 empty] | 2021-10-15 | 2021-10-18 | 1 | [15 empty] | 2021-10-15 | 2021-10-15 | 0 | 2021-10-18 |  | 2021-10-26 | 6
121498671 | 1092 | PGE | 93955 | NEM | EXPNEM | Commercial | Solar PV | 57.71 |  | 2021-06-09 |  | 2021-07-17 | 2021-06-16 | 2021-06-16 | 5 | 2021-07-27 | 33 | 2021-08-31 | 25 | [15 empty] | 2021-08-31 | 2021-09-02 | 2 | 2021-09-02 | 2021-09-06 | 1 | [13 empty] | 2021-09-16 | 2021-09-21 | 3 | 2021-11-08 |  | 45 | [12 empty] | 2021-09-16 | 2021-09-17 | 1 | 2021-09-21 |  | 2021-10-22 | 23
121499088 | 1093 | PGE | 93950 | NEM | EXPNEM | Commercial | Solar PV | 34.179 |  | 2021-06-09 |  | 2021-07-30 | 2021-06-16 | 2021-06-16 | 5 | 2021-08-04 | 39 | 2021-08-19 | 11 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-08-24 | 3 | [13 empty] | 2021-09-30 | 2021-10-05 | 3 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-10-05 |  | 2021-10-12 | 5
121499589 | 1094 | PGE | 93656 | NEM | EXPNEM | Withdrawn | Solar PV | 1680 |  | 2021-06-09 | 2021-06-10 |  | 2021-06-10 | 2021-06-10 | 1 | 2021-06-16 | 5 | 2021-07-26 | 27 | 2021-08-12 | 2021-09-09 | 19 | [23 empty] | 2021-07-08 | 2021-07-08 | 2021-07-21 | 9
121512563 | 1095 | PGE | 93618 | NEM | EXPNEM | Implementation | Solar PV | 830 |  | 2021-06-10 |  | 2021-06-23 | 2021-06-23 | 2021-06-23 | 9 | 2021-07-22 | 29 | 2021-08-05 | 10 | [15 empty] | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02 | 2021-11-29 | 58 |  |  |  |  | 2021-06-10 |  | 2021-06-10 |  |  | 2021-07-23 | [6 empty] | 2021-11-01 |  | 50
121513248 | 1096 | PGE | 94928 | NEM | NEMMT | Application Review in Progress | ENGN, Solar PV | 625 |  | 2021-06-10 |  | 2021-06-24 | 2021-06-24 | 2021-06-24 | 10
121513322 | 1097 | PGE | 94945 | NEM | NEMMT | Application Review in Progress | ENGN, Solar PV | 625 |  | 2021-06-10 |  | 2021-06-24 | 2021-06-24 | 2021-06-24 | 10
121514479 | 1098 | PGE | 95602 | NEM | EXPNEM | Implementation | Solar PV | 60 |  | 2021-06-10 |  | 2021-06-16 | 2021-06-16 | 2021-06-16 | 4 | 2021-06-29 | 13 | 2021-07-13 | 9 | [15 empty] | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13 | 2021-07-26 | 9
121514782 | 1099 | PGE | 93313 | NEM | EXPNEM | IA in Progress | Solar PV | 136 |  | 2021-06-10 |  | 2021-06-16 | 2021-06-16 | 2021-06-16 | 4 | 2021-06-18 | 6 | 2021-06-29 | 7 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | [6 empty] | 2021-06-10 | 2021-06-23 | 2021-06-10 | 2021-07-09 | 20
121516061 | 1100 | PGE | 95603 | NEM | EXPNEM | Implementation | Solar PV | 43.964 |  | 2021-06-10 |  | 2021-09-09 | 2021-06-16 | 2021-06-16 | 4 | 2021-09-09 | 63 | 2021-09-15 | 4 | [15 empty] | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | 2021-10-12 | 19 |  |  |  |  | 2021-06-10 | 2021-09-09 | 2021-06-10 | 2021-09-10 | 64
121516212 | 1101 | PGE | 94952 | NEM | NEMMT | IA in Progress | Solar PV, Storage | 8248.335 |  | 2021-06-10 | 2021-06-14 |  | 2021-06-14 | 2021-06-14 | 2 | 2021-06-23 | 9 | [5 empty] | 2021-07-15 | 2021-08-02 | 12 | 2021-08-02 | 2021-08-02 | 0 | 2021-08-16 | 2021-12-10 | 80 | 2021-08-02 | 2021-08-03 | 1 | 2021-12-16 | [6 empty] | 2021-12-16 | 2021-11-29 | -13 | 2021-06-10 | 2021-07-08 | 2021-06-10 | 2021-07-08 | 19
121518919 | 1102 | PGE | 93612 | NEM | VNEM | IA in Progress | Solar PV | 520.277 |  | 2021-06-11 |  | 2021-06-21 | 2021-06-21 | 2021-06-21 | 6 | 2021-07-09 | 19 | 2021-07-30 | 15 | [15 empty] | 2021-07-30 | 2021-08-20 | 15 | 2021-08-20 | [6 empty] | 2021-06-11 |  | 2021-06-11
121519464 | 1103 | PGE | 94010 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 30.75 |  | 2021-06-11 |  | 2021-10-19 | 2021-06-14 | 2021-06-14 | 1 | 2021-10-21 | 92 | 2021-10-25 | 2
121520439 | 1104 | PGE | 93612 | NEM | VNEM | Implementation | Solar PV | 49.035 |  | 2021-06-11 |  | 2021-06-21 | 2021-06-21 | 2021-06-21 | 6 | 2021-08-09 | 40 | 2021-08-30 | 15 | [15 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-09-02 | 3 | [9 empty] | 2021-09-10
121522353 | 1105 | PGE | 93638 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 76.036 |  | 2021-06-11 |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 10 | 2021-06-30 | 13 | 2021-07-22 | 15 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | [6 empty] | 2021-06-11 | 2021-07-07 | 2021-06-11 | 2021-07-08 | 18 |  | 2021-07-22 | 2021-07-22 | 0
121522371 | 1106 | PGE | 93638 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 76.036 |  | 2021-06-11 |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 10 | 2021-06-30 | 13 | 2021-07-22 | 15 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | [6 empty] | 2021-06-11 | 2021-07-07 | 2021-06-11 | 2021-07-08 | 18 |  | 2021-07-22 | 2021-07-22 | 0
121522401 | 1107 | PGE | 94551 | NEM | EXPNEM | Commercial | Solar PV | 75.4 |  | 2021-06-11 |  | 2021-06-23 | 2021-06-17 | 2021-06-17 | 4 | 2021-07-12 | 20 | 2021-07-21 | 7 | [15 empty] | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | 2021-08-24 | 24 |  |  |  |  | 2021-08-24 | 2021-09-01 | 2021-08-24 | 2021-09-10 | 12 |  |  |  |  | 2021-10-19 | 2021-10-27 | 6 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-27 |  | 2021-11-01 | 3
121522570 | 1108 | PGE | 93638 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 76.006 |  | 2021-06-11 |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 10 | 2021-06-30 | 13 | 2021-07-22 | 15 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | [6 empty] | 2021-06-11 | 2021-07-07 | 2021-06-11 | 2021-07-08 | 18 |  | 2021-07-22 | 2021-07-22 | 0
121522878 | 1109 | PGE | 93420 | NEM | VNEM | Commercial | Solar PV | 200 |  | 2021-06-11 |  | 2021-06-21 | 2021-06-21 | 2021-06-21 | 6 | 2021-07-26 | 30 | 2021-08-13 | 14 | [15 empty] | 2021-08-13 | 2021-08-13 | 0 | 2021-08-13 | 2021-10-07 | 38 | [9 empty] | 2021-08-30 | 2021-10-07 | 2021-10-11 | 27 | 2021-12-23 | 2021-12-30 | 5 | [15 empty] | 2021-12-23 | 2021-12-27 | 2 | 2021-12-30 |  | 2021-12-31 | 1
121523121 | 1110 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 64.643 |  | 2021-06-11 |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 10 | 2021-06-30 | 13 | 2021-07-22 | 15 | [15 empty] | 2021-07-22 | 2021-08-03 | 8 | 2021-08-03 | [6 empty] | 2021-06-11 | 2021-07-21 | 2021-06-11 | 2021-08-03 | 36 |  | 2021-08-03 | 2021-08-03 | 0
121523477 | 1111 | PGE | 93635 | NEM | EXPNEM | Implementation | Solar PV | 162.5 |  | 2021-06-11 |  | 2021-08-11 | 2021-06-22 | 2021-06-22 | 7 | 2021-08-23 | 50 | 2021-09-02 | 8 | [15 empty] | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02 | 2021-09-09 | 4 |  |  |  |  | 2021-06-11 | 2021-08-23 | 2021-06-11 | 2021-09-07 | 60 | [7 empty] | 2021-11-08 |  | 45
121523561 | 1112 | PGE | 93455 | NEM | EXPNEM | Withdrawn | Solar PV | 500 |  | 2021-06-11 |  | 2021-06-21 | 2021-06-21 | 2021-06-21 | 6 | 2021-07-08 | 18 | 2021-07-22 | 10 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22
121523563 | 1113 | PGE | 94804 | NEM | EXPNEM | IA in Progress | Solar PV | 400 |  | 2021-06-11 |  |  | 2021-06-17 | 2021-06-17 | 4 | 2021-06-17 | 4 | 2021-07-09 | 15 | [15 empty] | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12
121523564 | 1114 | PGE | 94804 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-06-11 |  | 2021-06-17 | 2021-06-17 | 2021-06-17 | 4 | 2021-06-18 | 5 | 2021-07-21 | 22 | [15 empty] | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21
121527967 | 1115 | PGE | 94582 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.15 |  | 2021-06-13 |  | 2021-06-15 | 2021-06-15 | 2021-06-15 | 1 | 2021-07-14 | 21 | 2021-07-20 | 4 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-15 | 2021-07-14 | 20 | [13 empty] | 2021-07-20 | 2021-07-20 | 0 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 |  | 2021-07-20 | 0
121530817 | 1116 | PGE | 94549 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.232 |  | 2021-06-14 |  | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2 | 2021-07-01 | 13 | 2021-07-06 | 2 | [15 empty] | 2021-06-14 | 2021-06-14 |  | 2021-06-14 | 2021-06-14 | 1 | [13 empty] | 2021-07-06 | 2021-07-06 | 0 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 |  | 2021-07-06 | 0
121531728 | 1117 | PGE | 95126 | NEM | EXPNEM | IA in Progress | Solar PV | 75.463 |  | 2021-06-14 |  |  | 2021-06-17 | 2021-06-17 | 3 | 2021-06-17 | 3 | 2021-07-09 | 15 | [15 empty] | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12 | 2021-11-04 | 82 |  |  |  |  | 2021-06-14 | 2021-06-23 | 2021-06-14 | 2021-07-09 | 18
121531833 | 1118 | PGE | 95126 | NEM | EXPNEM | Implementation | Solar PV | 145.8 |  | 2021-06-14 |  | 2021-06-24 | 2021-06-22 | 2021-06-22 | 6 | 2021-06-22 | 6 | 2021-10-26 | 88 | [15 empty] | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26 | 2021-11-02 | 5 |  |  |  |  | 2021-06-14 | 2021-10-13 | 2021-06-14 | 2021-10-22 | 92
121532817 | 1119 | PGE | 94027 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 40.75 |  | 2021-06-14 |  | 2021-08-05 | 2021-06-16 | 2021-06-16 | 2 | 2021-08-17 | 45 | 2021-08-19 | 2 | [34 empty] | 2021-08-19 | 2021-08-24 | 3 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-24 |  | 2021-08-25 | 1
121533362 | 1120 | PGE | 95062 | NEM | EXPNEM | Commercial | Solar PV | 109.873 |  | 2021-06-14 |  | 2021-06-17 | 2021-06-17 | 2021-06-17 | 3 | 2021-07-07 | 16 | 2021-08-25 | 35 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | 2021-08-25 | 0 |  |  |  |  | 2021-06-14 | 2021-07-17 | 2021-06-14 | 2021-07-28 | 31 |  |  |  |  | 2021-11-29 | 2021-12-07 | 6 | [15 empty] | 2021-11-29 | 2021-11-30 | 1 | 2021-12-07 |  | 2021-12-14 | 5
121535307 | 1121 | PGE | 94556 | NEM | EXPNEM | Withdrawn | Solar PV | 80.24 |  | 2021-06-14 |  |  | 2021-06-17 | 2021-06-17 | 3 | 2021-06-17 | 3 | 2021-07-20 | 22 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-08-18 | 21 |  |  |  |  | 2021-06-14 | 2021-06-29 | 2021-06-14 | 2021-07-12 | 19
121535352 | 1122 | PGE | 94556 | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-06-14 |  | 2021-08-02 | 2021-06-18 | 2021-06-18 | 4 | 2021-08-02 | 34 | 2021-08-16 | 10 | [15 empty] | 2021-08-16 | 2021-08-17 | 1 | 2021-08-17 | 2021-08-18 | 1 |  |  |  |  | 2021-06-14 | 2021-09-30 | 2021-06-14 | 2021-10-15 | 87
121535461 | 1123 | PGE | 94556 | NEM | EXPNEM | IA in Progress | Solar PV | 90.067 |  | 2021-06-14 |  | 2021-06-17 | 2021-06-17 | 2021-06-17 | 3 | 2021-06-21 | 5 | 2021-08-16 | 39 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | 2021-08-18 | 2 |  |  |  |  | 2021-06-14 | 2021-06-29 | 2021-06-14 | 2021-07-12 | 19
121535968 | 1124 | PGE | 94513 | NEM | EXPNEM | IA in Progress | Solar PV | 34.921 |  | 2021-06-14 |  | 2021-06-22 | 2021-06-22 | 2021-06-22 | 6 | 2021-06-23 | 7 | 2021-08-06 | 31 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06
121538801 | 1125 | PGE | 93446 | NEM | VNEM | Application Review in Progress | Solar PV | 82.82 |  | 2021-06-15 |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 8 | [29 empty] | 2021-06-15 |  | 2021-06-15 |  |  | 2021-07-09
121539277 | 1126 | PGE | 95993 | NEM | EXPNEM | IA in Progress | Solar PV | 320.808 |  | 2021-06-15 |  | 2021-06-17 | 2021-06-17 | 2021-06-17 | 2 | 2021-06-17 | 2 | 2021-07-20 | 22 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-07-20 | 0 |  |  |  |  | 2021-06-15 | 2021-08-13 | 2021-06-15 | 2021-08-13 | 42 |  |  |  |  | 2021-12-23 | [17 empty] | 2021-12-23 | 2021-12-23 | 0
121540929 | 1127 | PGE | 95304 | NEM | EXPNEM | Withdrawn | Solar PV | 133.2 |  | 2021-06-15 |  | 2021-06-18 | 2021-06-18 | 2021-06-18 | 3 | [29 empty] | 2021-06-15 |  | 2021-06-15
121540966 | 1128 | PGE | 95336 | NEM | EXPNEM | Study in Progress | Solar PV | 533.3 |  | 2021-06-15 |  | 2021-11-15 | 2021-06-18 | 2021-06-18 | 3 | 2021-11-18 | 109 | 2021-12-06 | 10 | 2021-12-06 | [24 empty] | 2021-06-15 |  | 2021-06-15
121541035 | 1129 | PGE | 95304 | NEM | EXPNEM | Withdrawn | Solar PV | 66.6 |  | 2021-06-15 |  | 2021-06-18 | 2021-06-18 | 2021-06-18 | 3 | [29 empty] | 2021-06-15 |  | 2021-06-15
121541287 | 1131 | PGE | 94903 | NEM | EXPNEM | IA in Progress | Solar PV | 420 |  | 2021-06-15 |  | 2021-06-23 | 2021-06-23 | 2021-06-23 | 6 | 2021-07-01 | 12 | 2021-08-26 | 39 | 2021-08-26 | 2021-09-22 | 18 | 2021-09-22 | 2021-10-14 | 16 | 2021-10-14 |  |  |  | 2021-12-31 |  |  |  |  | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31
121541983 | 1132 | PGE | 93637 | NEM | NEMMT | IA in Progress | ENGN, Solar PV | 1192 |  | 2021-06-15 | 2021-06-22 |  | 2021-06-21 | 2021-06-21 | 4 | 2021-07-07 | 15 | [5 empty] | 2021-07-12 | 2021-08-09 | 20 | 2021-08-09 | 2021-08-09 | 0 | 2021-08-19 | 2021-11-17 | 62 | 2021-08-09 | 2021-08-09 | 0 | 2021-12-06 | 2021-12-07 | 1 | 2021-12-07 | [6 empty] | 2021-06-15 |  | 2021-06-15
121542109 | 1133 | PGE | 94577 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-06-15 |  | 2021-06-18 | 2021-06-18 | 2021-06-18 | 3 | 2021-06-22 | 5 | 2021-07-12 | 13 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-08-02 | 15 |  |  |  |  | 2021-06-15 | 2021-06-22 | 2021-06-15 | 2021-07-09 | 17 |  |  |  |  | 2021-11-29 | 2021-11-29 | 0 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 |  | 2021-12-03 | 4
121542355 | 1134 | PGE | 93652 | NEM | EXPNEM | Implementation | Solar PV | 228.528 |  | 2021-06-15 |  | 2021-07-06 | 2021-06-23 | 2021-06-23 | 6 | 2021-06-30 | 11 | 2021-08-06 | 26 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | 2021-08-27 | 15 |  |  |  |  | 2021-06-15 | 2021-08-02 | 2021-06-15 | 2021-08-13 | 42
121542722 | 1135 | PGE | 94010 | NEM | EXPNEM | Commercial | Solar PV | 58.04 |  | 2021-06-15 |  | 2021-06-18 | 2021-06-18 | 2021-06-18 | 3 | 2021-08-02 | 33 | 2021-08-09 | 5 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-16 | 5 | [13 empty] | 2021-09-10 | 2021-09-15 | 3 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-15 |  | 2021-09-22 | 5
121545717 | 1136 | PGE | 95603 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-06-16 |  | 2021-06-21 | 2021-06-21 | 2021-06-21 | 3 | 2021-06-29 | 9 | 2021-07-14 | 10 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-11-03 | 79 | [13 empty] | 2021-11-18 | 2021-11-30 | 6 | [15 empty] | 2021-11-18 | 2021-11-18 | 0 | 2021-11-30 |  | 2021-12-02 | 2
121546397 | 1137 | PGE | 93307 | NEM | EXPNEM | Application Submitted | Solar PV | 31.32 |  | 2021-06-16 |  | 2021-12-06 | 2021-06-30 | 2021-06-30 | 10
121547049 | 1138 | PGE | 94539 | NEM | EXPNEM | Withdrawn | Solar PV | 57.71 |  | 2021-06-16 |  | 2021-06-21 | 2021-06-21 | 2021-06-21 | 3 | 2021-06-30 | 10 | [5 empty] | 2021-06-30 | 2021-07-27 | 18 | 2021-07-27
121547611 | 1139 | PGE | 94538 | NEM | EXPNEM | IA in Progress | Solar PV | 700 |  | 2021-06-16 |  | 2021-10-04 | 2021-06-24 | 2021-06-24 | 6 | 2021-10-13 | 83 | 2021-12-17 | 44 | [15 empty] | 2021-12-17 | 2021-12-17 | 0 | 2021-12-17 | [6 empty] | 2021-06-16 | 2021-10-13 | 2021-06-16 | 2021-10-15 | 85
121548564 | 1140 | PGE | 95340 | NEM | EXPNEM | Implementation | Solar PV | 120 |  | 2021-06-16 |  | 2021-06-28 | 2021-06-28 | 2021-06-28 | 8 | 2021-07-08 | 15 | 2021-07-26 | 12 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-08-16 | 15 | [16 empty] | 2021-10-22 |  | 56
121548990 | 1141 | PGE | 94571 | NEM | EXPNEM | Study in Progress | Solar PV | 31.024 |  | 2021-06-16 |  | 2021-07-06 | 2021-06-22 | 2021-06-22 | 4 | 2021-12-06 | 118 | [27 empty] | 2021-07-17 |  | 2021-07-17
121550219 | 1142 | PGE | 95694 | NEM | EXPNEM | Study in Progress | Solar PV | 720 |  | 2021-06-16 |  | 2021-09-10 | 2021-06-22 | 2021-06-22 | 4 | 2021-09-13 | 61 | 2021-10-04 | 15 | 2021-10-04 | 2021-11-04 | 23 | 2021-11-15 | 2021-12-21 | 24 | 2021-12-21
121550762 | 1143 | PGE | 93402 | NEM | VNEM | Study in Progress | Solar PV | 200 |  | 2021-06-16 |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 7 | 2021-08-12 | 40 | 2021-09-01 | 14 | [30 empty] | 2021-07-09
121551327 | 1144 | PGE | 94538 | Non-NEM | Non-Export | Withdrawn | Storage | 145 |  | 2021-06-17 | 2021-06-17 |  | 2021-06-17 | 2021-06-17 | 0
121552131 | 1145 | PGE | 95062 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 166.032 |  | 2021-06-17 |  | 2021-07-01 | 2021-07-01 | 2021-07-01 | 10 | 2021-07-30 | 30 | 2021-09-10 | 29 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | 2021-11-15 | 45 |  |  |  |  | 2021-06-17 | 2021-10-01 | 2021-06-17 | 2021-10-11 | 80 |  | 2021-10-25 | 2021-11-02 | 6
121552919 | 1146 | PGE | 93449 | NEM | VNEM | IA in Progress | Solar PV | 300 |  | 2021-06-17 |  | 2021-07-01 | 2021-07-01 | 2021-07-01 | 10 | 2021-08-05 | 34 | 2021-09-09 | 24 | [15 empty] | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 | [6 empty] | 2021-06-17 | 2021-12-17 | 2021-06-17 | 2021-12-27 | 132
121553602 | 1147 | PGE | 95251 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 41.099 |  | 2021-06-17 |  | 2021-06-24 | 2021-06-21 | 2021-06-21 | 2 | 2021-06-30 | 9 | 2021-07-07 | 4 | [25 empty] | 2021-06-17 |  | 2021-06-17 | [9 empty] | 2021-11-18 |  | 38
121554184 | 1148 | PGE | 93249 | NEM | EXPNEM | IA in Progress | Solar PV | 3000 |  | 2021-06-17 | 2021-06-18 |  | 2021-06-17 | 2021-06-17 | 0 | 2021-06-30 | 9 | [5 empty] | 2021-07-19 | 2021-08-18 | 22 | 2021-08-18 | 2021-08-18 | 0 | 2021-08-26 | 2021-11-23 | 61 | 2021-08-18 | 2021-08-18 | 0 | 2021-12-17 | 2021-12-20 | 1 | 2021-12-20
121556095 | 1149 | PGE | 95691 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-06-17 |  |  | 2021-06-22 | 2021-06-22 | 3 | 2021-06-22 | 3 | 2021-07-12 | 13 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-08-19 | 28 | [13 empty] | 2021-11-22 | 2021-12-02 | 6 | [15 empty] | 2021-11-22 | 2021-11-23 | 1 | 2021-12-02 |  | 2021-12-08 | 4
121561972 | 1150 | PGE | 93311 | NEM | EXPNEM | IA in Progress | Solar PV | 480.146 |  | 2021-06-18 |  | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2 | 2021-06-30 | 8 | 2021-07-12 | 7 | 2021-07-12 | 2021-08-09 | 20 | [12 empty] | 2021-08-09 | 2021-08-20 | 9 | 2021-08-20 | 2021-09-08 | 12
121562533 | 1151 | PGE | 95301 | NEM | EXPNEM | Study in Progress | Solar PV | 971.537 |  | 2021-06-18 |  | 2021-08-10 | 2021-06-30 | 2021-06-30 | 8 | 2021-08-12 | 38 | 2021-09-17 | 25 | 2021-09-17 | 2021-10-22 | 25 | 2021-10-28 | 2021-11-30 | 20 | 2021-11-30 | [18 empty] | 2021-06-18 | 2021-08-10 | 2021-06-18 | 2021-08-19 | 43
121562722 | 1152 | PGE | 94580 | NEM | EXPNEM | IA in Progress | Solar PV | 40.32 |  | 2021-06-18 |  | 2021-09-09 | 2021-07-02 | 2021-07-02 | 10 | 2021-09-10 | 58 | 2021-09-13 | 1 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13
121563112 | 1153 | PGE | 94010 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 48.618 |  | 2021-06-22 |  | 2021-09-29 | 2021-06-22 | 2021-06-22 | 0 | 2021-10-07 | 75 | 2021-10-11 | 2
121563554 | 1154 | PGE | 93612 | NEM | VNEM | IA in Progress | Solar PV | 576.251 |  | 2021-06-18 |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 5 | 2021-08-03 | 31 | 2021-08-25 | 16 | 2021-08-25 | 2021-09-16 | 15 | [12 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16
121563715 | 1155 | PGE | 93612 | NEM | VNEM | IA in Progress | Solar PV | 520.008 |  | 2021-06-18 |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 5 | 2021-09-16 | 62 | 2021-09-22 | 4 | [15 empty] | 2021-09-22 | 2021-09-22 | 0 | 2021-09-22
121564326 | 1156 | PGE | 94062 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.065 |  | 2021-06-18 |  | 2021-10-20 | 2021-06-22 | 2021-06-22 | 2
121564714 | 1157 | PGE | 95374 | NEM | EXPNEM | Commercial | Solar PV | 62.5 |  | 2021-06-18 |  | 2021-07-06 | 2021-06-28 | 2021-06-28 | 6 | 2021-07-01 | 9 | 2021-08-16 | 31 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | 2021-10-19 | 45 |  |  |  |  | 2021-06-18 | 2021-08-25 | 2021-06-18 | 2021-08-25 | 47 |  |  |  |  | 2021-11-01 | 2021-11-09 | 6 | [15 empty] | 2021-11-01 | 2021-11-01 | 0 | 2021-11-09 |  | 2021-11-10 | 1
121564945 | 1158 | PGE | 93722 | NEM | EXPNEM | Withdrawn | Solar PV | 42.054 |  | 2021-06-18 |  | 2021-06-24 | 2021-06-24 | 2021-06-24 | 4
121565488 | 1159 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 103.603 |  | 2021-06-18 |  | 2021-06-30 | 2021-06-30 | 2021-06-30 | 8 | 2021-07-07 | 12 | 2021-07-23 | 12 | [15 empty] | 2021-07-28 | 2021-07-29 | 1 | 2021-07-29 | 2021-08-11 | 9 | [13 empty] | 2021-12-13 | 2021-12-21 | 6 | [15 empty] | 2021-12-13 | 2021-12-14 | 1 | 2021-12-21 |  | 2021-12-24 | 3
121565493 | 1160 | PGE | 93654 | NEM | EXPNEM | Commercial | Solar PV | 34.179 |  | 2021-06-18 |  | 2021-06-28 | 2021-06-28 | 2021-06-28 | 6 | 2021-07-01 | 9 | 2021-07-08 | 4 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-08 | 0 | [13 empty] | 2021-10-04 | 2021-10-04 | 0 | [15 empty] | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04 |  | 2021-10-05 | 1
121571764 | 1161 | PGE | 94022 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-06-20 |  | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2 | 2021-07-02 | 9 | 2021-07-22 | 13 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | 2021-11-03 | 73 |  |  |  |  | 2021-06-20 | 2021-07-22 | 2021-06-20 | 2021-07-30 | 28
121573132 | 1162 | PGE | 94957 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.486 |  | 2021-06-21 |  |  | 2021-06-23 | 2021-06-23 | 2 | 2021-06-23 | 2 | 2021-06-23 | 0 | [34 empty] | 2021-06-25 | 2021-06-25 | 0 | [15 empty] | 2021-06-25 |  |  | 2021-06-25 |  | 2021-06-25 | 0
121574245 | 1163 | PGE | 94040 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.173 |  | 2021-06-21 |  |  | 2021-06-24 | 2021-06-24 | 3 | 2021-06-24 | 3 | 2021-06-25 | 1 | [34 empty] | 2021-06-29 | 2021-06-29 | 0 | [15 empty] | 2021-06-29 |  |  | 2021-06-29 |  | 2021-06-29 | 0
121574417 | 1164 | PGE | 95688 | NEM | EXPNEM | Commercial | Solar PV | 52.163 |  | 2021-06-21 |  | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2 | 2021-07-07 | 11 | 2021-07-20 | 9 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-10-19 | 64 |  |  |  |  | 2021-06-21 | 2021-08-11 | 2021-06-21 | 2021-08-13 | 38 |  |  |  |  | 2021-10-25 | 2021-11-01 | 5 | [15 empty] | 2021-10-25 | 2021-10-26 | 1 | 2021-11-01 |  | 2021-11-03 | 2
121575399 | 1165 | PGE | 95694 | NEM | EXPNEM | IA in Progress | Solar PV | 336 |  | 2021-06-21 |  | 2021-07-22 | 2021-06-29 | 2021-06-29 | 6 | 2021-07-13 | 15 | 2021-08-27 | 33 | [15 empty] | 2021-08-25 | 2021-08-27 | 2 | 2021-08-27 | [6 empty] | 2021-06-21 |  | 2021-06-21 |  |  | 2021-08-13
121575848 | 1166 | PGE | 93401 | NEM | VNEM | Application Review in Progress | Solar PV | 49.692 |  | 2021-06-21 |  | 2021-07-06 | 2021-07-06 | 2021-07-06 | 10
121576035 | 1167 | PGE | 95030 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 42.01 |  | 2021-06-21 |  | 2021-08-12 | 2021-06-24 | 2021-06-24 | 3 | 2021-08-12 | 37 | 2021-08-18 | 4 | [34 empty] | 2021-08-18 | 2021-08-23 | 3 | [15 empty] | 2021-08-18 | 2021-08-19 | 1 | 2021-08-23 |  | 2021-08-25 | 2
121576380 | 1168 | PGE | 95377 | NEM | EXPNEM | IA in Progress | Solar PV | 428.274 |  | 2021-06-21 |  | 2021-06-24 | 2021-06-24 | 2021-06-24 | 3 | 2021-08-16 | 39 | 2021-09-07 | 15 | 2021-09-07 | 2021-10-05 | 20 | 2021-10-08 | 2021-11-01 | 16 | 2021-11-01 | [8 empty] | 2021-11-01 | 2021-11-10 | 7 | 2021-11-10 | [6 empty] | 2021-06-21 | 2021-08-16 | 2021-06-21 | 2021-08-27 | 48
121578259 | 1169 | PGE | 95207 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 163.772 |  | 2021-06-22 |  | 2021-07-30 | 2021-06-24 | 2021-06-24 | 2 | 2021-09-17 | 61 | 2021-11-08 | 36 | [15 empty] | 2021-11-08 | 2021-11-08 | 0 | 2021-11-08 | 2021-11-17 | 6 |  |  |  |  | 2021-06-22 | 2021-11-05 | 2021-06-22 | 2021-11-19 | 105 | [7 empty] | 2021-09-27 | 2021-12-03 | 46 |  |  |  | 2021-12-03 | 2021-12-03 | 0
121580385 | 1170 | PGE | 94565 | NEM | EXPNEM | IA in Progress | Solar PV | 293.899 |  | 2021-06-22 |  |  | 2021-06-25 | 2021-06-25 | 3 | 2021-06-25 | 3 | 2021-07-15 | 13 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | [6 empty] | 2021-06-22 | 2021-07-31 | 2021-06-22 | 2021-08-13 | 37
121581280 | 1171 | PGE | 94024 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.47 |  | 2021-06-22 |  | 2021-09-08 | 2021-06-25 | 2021-06-25 | 3 | 2021-09-22 | 64 | 2021-09-24 | 2 | [34 empty] | 2021-09-27 | 2021-09-28 | 1 | [15 empty] | 2021-09-27 | 2021-09-28 | 1 | 2021-09-28 |  | 2021-09-29 | 1
121582005 | 1172 | PGE | 95439 | NEM | EXPNEM | Implementation | Solar PV | 37.2 |  | 2021-06-22 |  | 2021-07-13 | 2021-06-29 | 2021-06-29 | 5 | 2021-07-09 | 12 | 2021-08-06 | 20 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | 2021-08-26 | 14
121582010 | 1173 | PGE | 95965 | Non-NEM | Continuous Uncompensated Export | IA in Progress | ENGN, Micro Turbine | 130 |  | 2021-06-22 | 2021-06-23 |  | 2021-06-22 | 2021-06-22 | 0 | 2021-07-07 | 10 | 2021-09-21 | 53 | [15 empty] | 2021-10-25 | 2021-10-27 | 2 | 2021-10-27
121582372 | 1174 | PGE | 94028 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 30.12 |  | 2021-06-22 |  | 2021-08-27 | 2021-06-28 | 2021-06-28 | 4
121582507 | 1175 | PGE | 95490 | Non-NEM | Non-Export | IA in Progress | ENGN, Storage | 830 |  | 2021-06-22 | 2021-06-23 |  | 2021-06-23 | 2021-06-23 | 1 | 2021-07-14 | 15 | 2021-11-15 | 86 | [15 empty] | 2021-11-15 | 2021-11-17 | 2 | 2021-11-17 | [6 empty] | 2021-06-22 |  | 2021-06-22
121583458 | 1176 | PGE | 93402 | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-06-22 |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 3 | 2021-08-13 | 37 | 2021-10-08 | 39 | [15 empty] | 2021-10-08 | 2021-10-08 | 0 | 2021-10-08
121586069 | 1177 | PGE | 93308 | NEM | EXPNEM | Commercial | Solar PV | 47.431 |  | 2021-06-23 |  | 2021-06-28 | 2021-06-28 | 2021-06-28 | 3 | 2021-07-07 | 9 | 2021-07-22 | 11 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | 2021-08-05 | 10 | [13 empty] | 2021-08-05 | 2021-08-12 | 5 | [15 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-12 |  | 2021-08-18 | 4
121586392 | 1178 | PGE | 95336 | Non-NEM | Non-Export | Withdrawn | Solar PV | 420 |  | 2021-06-23 | 2021-06-23 |  | 2021-06-23 | 2021-06-23 | 0 | 2021-06-30 | 5
121586625 | 1180 | PGE | 95620 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-06-23 |  | 2021-06-28 | 2021-06-28 | 2021-06-28 | 3 | 2021-07-14 | 14 | 2021-07-20 | 4 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-10-15 | 62 |  |  |  |  | 2021-06-23 | 2021-07-14 | 2021-06-23 | 2021-07-15 | 15 |  |  |  |  | 2021-11-01 | 2021-11-04 | 3 | [15 empty] | 2021-11-01 | 2021-11-01 | 0 | 2021-11-04 |  | 2021-11-10 | 4
121587043 | 1181 | PGE | 93206 | NEM | EXPNEM | Application Accepted | Solar PV | 62.5 |  | 2021-06-23 |  | 2021-07-09 | 2021-07-01 | 2021-07-01 | 6 | 2021-07-14 | 14 | 2021-07-26 | 8 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | [6 empty] | 2021-06-23 |  | 2021-06-23
121590274 | 1183 | PGE | 95376 | NEM | EXPNEM | Commercial | Solar PV | 129.6 |  | 2021-06-23 |  | 2021-06-29 | 2021-06-29 | 2021-06-29 | 4 | 2021-07-08 | 10 | 2021-08-18 | 29 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | 2021-09-07 | 13 | [13 empty] | 2021-12-15 | 2021-12-23 | 6 | [15 empty] | 2021-12-15 | 2021-12-15 | 0 | 2021-12-23 |  | 2021-12-28 | 3
121593172 | 1184 | PGE | 95603 | NEM | EXPNEM | IA in Progress | Solar PV | 36 |  | 2021-06-24 |  | 2021-07-31 | 2021-06-30 | 2021-06-30 | 4 | 2021-08-04 | 28 | 2021-08-19 | 11 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-09-07 | 12
121593388 | 1185 | PGE | 95360 | NEM | EXPNEM | Implementation | Solar PV | 500 |  | 2021-06-24 |  | 2021-07-09 | 2021-07-07 | 2021-07-07 | 8 | 2021-07-15 | 14 | 2021-08-12 | 20 | [15 empty] | 2021-08-23 | 2021-09-10 | 13 | 2021-09-10 | 2021-09-10 | 0 |  |  |  |  | 2021-06-24 |  | 2021-06-24 |  |  | 2021-08-05 | [6 empty] | 2021-09-24 |  | 76
121593561 | 1186 | PGE | 96007 | Non-NEM | Non-Export | Implementation | ENGN, Storage | 170 |  | 2021-06-24 | 2021-06-24 |  | 2021-06-24 | 2021-06-24 | 0 | 2021-07-21 | 18 | 2021-09-17 | 41 | [15 empty] | 2021-09-17 | 2021-10-05 | 12 | 2021-10-05 | 2021-10-14 | 7 |  |  |  |  | 2021-06-24 |  | 2021-06-24
121595368 | 1187 | PGE | 95070 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.195 |  | 2021-06-24 |  | 2021-07-07 | 2021-06-30 | 2021-06-30 | 4 | 2021-09-13 | 55 | 2021-09-14 | 1 | [34 empty] | 2021-09-14 | 2021-09-14 | 0 | [15 empty] | 2021-09-14 |  |  | 2021-09-14 |  | 2021-09-14 | 0
121599869 | 1188 | PGE | 94062 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 35.12 |  | 2021-06-25 |  | 2021-10-26 | 2021-07-08 | 2021-07-08 | 8 | 2021-10-29 | 88 | 2021-11-03 | 3
121600524 | 1189 | PGE | 93291 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 423.302 |  | 2021-06-17 | 2021-06-29 |  | 2021-06-28 | 2021-06-28 | 7 | 2021-07-21 | 23 | [5 empty] | 2021-09-08 | 2021-10-05 | 19 | 2021-10-05 | 2021-12-10 | 45 |  |  |  | 2021-12-10 | 2021-12-10 | 0 | [10 empty] | 2021-06-25 |  | 2021-06-25
121600650 | 1190 | PGE | 93245 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-06-25 |  | 2021-07-15 | 2021-06-30 | 2021-06-30 | 3 | 2021-07-19 | 15 | 2021-07-23 | 4 | [15 empty] | 2021-07-23 | 2021-07-23 | 0 | 2021-07-23 | 2021-08-26 | 24 |  |  |  |  | 2021-06-25 | 2021-11-04 | 2021-06-25 | 2021-11-19 | 102 |  |  |  |  | 2021-12-07 | 2021-12-16 | 7 | [15 empty] | 2021-12-07 | 2021-12-08 | 1 | 2021-12-16 |  | 2021-12-17 | 1
121601978 | 1191 | PGE | 95497 | NEM | EXPNEM | IA in Progress | Solar PV | 38.018 |  | 2021-06-25 |  | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2 | 2021-11-12 | 97 | 2021-11-29 | 9 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2021-12-10 | 9
121602291 | 1192 | PGE | 95746 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.464 |  | 2021-06-25 |  | 2021-07-07 | 2021-07-07 | 2021-07-07 | 7 | 2021-07-09 | 9 | 2021-07-12 | 1 | [15 empty] | 2021-06-25 | 2021-07-07 | 7 | 2021-07-07 | 2021-07-13 | 4 |  |  |  |  | 2021-06-25 |  | 2021-06-25 | [6 empty] | 2021-07-13 | 2021-07-13 | 0 | [15 empty] | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13 |  | 2021-07-13 | 0
121602477 | 1193 | PGE | 93635 | NEM | EXPNEM | IA in Progress | Solar PV | 395.854 |  | 2021-06-25 |  | 2021-07-22 | 2021-06-30 | 2021-06-30 | 3 | 2021-07-26 | 20 | 2021-08-09 | 10 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-23 | 10 |  |  |  |  | 2021-06-25 | 2021-07-26 | 2021-06-25 | 2021-08-05 | 28 | [7 empty] | 2021-10-21 | 2022-01-04 | 49
121602847 | 1194 | PGE | 95501 | Non-NEM | Non-Export | Study in Progress | Storage | 490 |  | 2021-06-25 | 2021-06-30 |  | 2021-06-25 | 2021-06-25 | 0 | 2021-07-21 | 17 | 2021-12-03 | 93 | 2021-12-22 | [24 empty] | 2021-06-25 |  | 2021-06-25
121604471 | 1195 | PGE | 95124 | NEM | EXPNEM | Implementation | Solar PV | 56.324 |  | 2021-06-25 |  |  | 2021-07-02 | 2021-07-02 | 5 | 2021-07-02 | 5 | 2021-07-20 | 11 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-07-26 | 4
121604580 | 1196 | PGE | 93458 | NEM | EXPNEM | Commercial | Solar PV | 45.384 |  | 2021-06-25 |  | 2021-07-02 | 2021-07-02 | 2021-07-02 | 5 | 2021-07-15 | 13 | 2021-07-27 | 8 | [15 empty] | 2021-07-27 | 2021-07-30 | 3 | 2021-07-30 | 2021-08-06 | 5 |  |  |  |  | 2021-06-25 |  | 2021-06-25 |  |  | 2021-07-23 |  |  |  | 2021-11-29 | 2021-12-14 | 11 | [15 empty] | 2021-11-29 | 2021-11-30 | 1 | 2021-12-14 |  | 2021-12-15 | 1
121621808 | 1197 | PGE | 93615 | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-06-28 |  | 2021-07-01 | 2021-06-30 | 2021-06-30 | 2 | 2021-07-01 | 3 | 2021-07-07 | 3 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | 2021-10-06 | 64 |  |  |  |  | 2021-06-28 | 2021-07-27 | 2021-06-28 | 2021-08-06 | 28 | [7 empty] | 2021-07-26 | 2021-12-12 | 96
121621925 | 1198 | PGE | 94556 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-06-28 |  |  | 2021-07-07 | 2021-07-07 | 6 | 2021-07-07 | 6 | 2021-07-07 | 0 | [34 empty] | 2021-07-08 | 2021-07-08 | 0 | [15 empty] | 2021-07-08 |  |  | 2021-07-08 |  | 2021-07-08 | 0
121622681 | 1199 | PGE | 95492 | NEM | EXPNEM | IA in Progress | Solar PV | 139.826 |  | 2021-06-28 |  | 2021-10-22 | 2021-07-12 | 2021-07-12 | 9 | 2021-11-02 | 89 | 2021-11-26 | 15 | [15 empty] | 2021-11-26 | 2021-11-26 | 0 | 2021-11-26 | 2021-11-30 | 1 |  |  |  |  | 2021-06-28 | 2021-10-18 | 2021-06-28 | 2021-10-19 | 79
121624051 | 1200 | PGE | 94558 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-06-28 |  | 2021-07-02 | 2021-06-30 | 2021-06-30 | 2 | 2021-08-05 | 27 | 2021-08-20 | 11 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-20 | 2021-08-30 | 6 |  |  |  |  | 2021-06-28 | 2021-08-05 | 2021-06-28 | 2021-08-13 | 33 |  |  |  |  | 2021-10-28 | 2021-11-04 | 5 | [15 empty] | 2021-10-28 | 2021-10-28 | 0 | 2021-11-04 |  | 2021-11-04 | 0
121624263 | 1201 | PGE | 95422 | NEM | EXPNEM | IA in Progress | Solar PV | 145.153 |  | 2021-06-28 |  | 2021-07-16 | 2021-06-30 | 2021-06-30 | 2 | 2021-07-22 | 17 | 2021-08-12 | 15 | [15 empty] | 2021-08-12 | 2021-08-12 | 0 | 2021-08-12 | 2021-08-18 | 4 |  |  |  |  | 2021-06-28 | 2021-07-01 | 2021-06-28 | 2021-07-13 | 10
121624979 | 1202 | PGE | 95492 | NEM | EXPNEM | IA in Progress | Solar PV | 627.287 |  | 2021-06-28 |  |  | 2021-07-13 | 2021-07-13 | 10 | 2021-07-13 | 10 | 2021-08-31 | 35 | [15 empty] | 2021-08-31 | 2021-09-03 | 3 | 2021-09-03 | 2021-10-15 | 29 |  |  |  |  | 2021-06-28 |  | 2021-06-28 | [9 empty] | 2021-11-17 |  | 39
121630100 | 1204 | PGE | 95215 | NEM | EXPNEM | Study in Progress | Solar PV | 72.441 |  | 2021-06-29 |  | 2021-07-12 | 2021-07-01 | 2021-07-01 | 2 | 2021-07-15 | 11 | 2021-09-02 | 35 | 2021-09-02 | 2021-10-01 | 20 | 2021-11-08 | 2021-12-06 | 17 | 2021-12-06 | [18 empty] | 2021-06-29 | 2021-08-20 | 2021-06-29 | 2021-09-07 | 48
121630227 | 1205 | PGE | 95695 | NEM | EXPNEM | Commercial | Solar PV | 52.163 |  | 2021-06-29 |  |  | 2021-07-06 | 2021-07-06 | 4 | 2021-07-06 | 4 | 2021-07-20 | 10 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-10-22 | 67 |  |  |  |  | 2021-06-29 | 2021-07-12 | 2021-06-29 | 2021-07-23 | 17 |  |  |  |  | 2021-11-05 | 2021-11-12 | 4 | [15 empty] | 2021-11-05 | 2021-11-05 | 0 | 2021-11-12 |  | 2021-11-19 | 5
121630590 | 1206 | PGE | 95219 | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-06-29 |  |  | 2021-07-09 | 2021-07-09 | 7 | 2021-07-12 | 8 | 2021-08-05 | 18 | [15 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | 2021-08-06 | 1 | [13 empty] | 2021-12-28 | [17 empty] | 2021-12-28 | 2021-12-28 | 0
121632075 | 1207 | PGE | 94551 | NEM | EXPNEM | IA in Progress | Solar PV | 126.998 |  | 2021-06-29 |  | 2021-07-06 | 2021-07-06 | 2021-07-06 | 4 | 2021-07-13 | 9 | 2021-08-10 | 20 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-10 | [6 empty] | 2021-06-29 | 2021-07-13 | 2021-06-29 | 2021-07-19 | 13
121632387 | 1208 | PGE | 94520 | NEM | EXPNEM | Implementation | Solar PV | 600 |  | 2021-06-29 |  | 2021-07-12 | 2021-07-12 | 2021-07-12 | 8 | 2021-07-15 | 11 | 2021-07-27 | 8 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-11-04 | 71 |  |  |  |  | 2021-06-29 | 2021-07-15 | 2021-06-29 | 2021-07-19 | 13 |  |  |  |  | 2021-11-04 | 2021-11-16 | 7 | 2021-09-21 | 2021-09-21 | 0 | [12 empty] | 2021-11-04 | 2021-11-05 | 1 | 2021-11-16 | 2021-11-18 |  | 2 |  |  | 99
121632404 | 1209 | PGE | 95407 | NEM | EXPNEM | Withdrawn | Solar PV | 57.443 |  | 2021-06-29 |  | 2021-07-07 | 2021-07-07 | 2021-07-07 | 5
121632751 | 1210 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-06-29 |  |  | 2021-07-14 | 2021-07-14 | 10 | 2021-07-14 | 10 | 2021-07-30 | 12 | [15 empty] | 2021-07-30 | 2021-08-02 | 1 | 2021-08-02 | 2021-08-02 | 0 |  |  |  |  | 2021-06-29 |  | 2021-06-29 |  |  | 2021-07-28 |  |  |  | 2021-12-14 | 2021-12-22 | 6 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-22 |  | 2021-12-22 | 0
121633079 | 1211 | PGE | 93610 | NEM | EXPNEM | Implementation | Solar PV | 500 |  | 2021-06-29 |  | 2021-08-03 | 2021-07-14 | 2021-07-14 | 10 | 2021-09-17 | 56 | 2021-10-08 | 15 | [15 empty] | 2021-10-08 | 2021-10-08 | 0 | 2021-10-08 | 2021-10-13 | 3 | [5 empty] | 2021-12-23 | 2021-12-23 | [9 empty] | 2021-11-04 |  | 47
121633205 | 1212 | PGE | 93722 | NEM | EXPNEM | Commercial | Solar PV | 31.909 |  | 2021-06-29 |  | 2021-07-07 | 2021-07-07 | 2021-07-07 | 5 | 2021-07-15 | 11 | 2021-07-20 | 3 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-09-07 | 34 | [13 empty] | 2021-09-24 | 2021-09-30 | 4 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-30 |  | 2021-10-07 | 5
121633368 | 1213 | PGE | 95126 | NEM | EXPNEM | IA in Progress | Solar PV | 30.23 |  | 2021-06-29 |  | 2021-10-29 | 2021-07-07 | 2021-07-07 | 5 | 2021-11-15 | 96 | 2021-12-02 | 11 | [15 empty] | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02
121634030 | 1214 | PGE | 94558 | NEM | EXPNEM | Commercial | Solar PV | 129.827 |  | 2021-06-29 |  | 2021-07-29 | 2021-07-13 | 2021-07-13 | 9 | 2021-07-30 | 22 | 2021-08-19 | 14 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-09-07 | 12 | [13 empty] | 2021-10-01 | 2021-10-07 | 4 | [15 empty] | 2021-10-01 | 2021-10-01 | 0 | 2021-10-07 |  | 2021-10-14 | 5
121636937 | 1215 | PGE | 95361 | NEM | EXPNEM | Withdrawn | Solar PV | 38.78 |  | 2021-06-30 |  | 2021-08-13 | 2021-07-14 | 2021-07-14 | 9 | 2021-08-21 | 36 | 2021-09-08 | 11 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-10-20 | 30 |  |  |  |  | 2021-06-30 | 2021-09-09 | 2021-06-30 | 2021-09-10 | 50
121639356 | 1216 | PGE | 95030 | NEM | EXPNEM | Study in Progress | Solar PV | 549.991 |  | 2021-06-30 |  | 2021-07-29 | 2021-07-08 | 2021-07-08 | 5 | 2021-08-03 | 23 | 2021-09-08 | 25 | 2021-09-08 | 2021-09-27 | 13 | 2021-10-04 | 2021-11-03 | 22 | 2021-11-03 | 2021-11-10 | 5 |  |  |  | 2021-11-10 | [12 empty] | 2021-06-30 | 2021-07-17 | 2021-06-30 | 2021-07-28 | 19
121640615 | 1217 | PGE | 95422 | NEM | EXPNEM | IA in Progress | Solar PV | 131.105 |  | 2021-06-30 |  | 2021-07-08 | 2021-07-08 | 2021-07-08 | 5 | 2021-08-18 | 34 | 2021-09-03 | 12 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-11-05 | 44 |  |  |  |  | 2021-06-30 | 2021-11-09 | 2021-06-30 | 2021-11-24 | 102
121640894 | 1218 | PGE | 95070 | NEM | EXPNEM | IA in Progress | Solar PV | 240 |  | 2021-06-30 |  | 2021-07-08 | 2021-07-08 | 2021-07-08 | 5 | 2021-07-13 | 8 | 2021-07-29 | 12 | [15 empty] | 2021-07-29 | 2021-07-29 | 0 | 2021-07-29 | 2021-08-11 | 9 |  |  |  |  | 2021-06-30 | 2021-07-27 | 2021-06-30 | 2021-08-06 | 26
121641275 | 1219 | PGE | 95401 | NEM | EXPNEM | Withdrawn | Solar PV | 381.322 |  | 2021-06-30 |  | 2021-08-10 | 2021-07-09 | 2021-07-09 | 6 | 2021-08-16 | 32 | 2021-09-03 | 14 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | [7 empty] | 2021-08-16 | 2021-08-16 | 2021-08-27 | 9
120637986 | 1220 | PGE | 95131 | NEM | SNEM | Study in Progress | Solar PV | 33.3 |  | 2021-03-12 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 7 | 2021-06-16 | 67 | 2021-07-23 | 26 | [25 empty] | 2021-03-12 |  | 2021-03-12
120673324 | 1221 | PGE | 95614 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 34.2 |  | 2021-03-22 |  |  | 2021-04-05 | 2021-04-05 | 10 | 2021-04-07 | 12 | 2021-04-09 | 2 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05
120771059 | 1222 | PGE | 93446 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-04-09 |  | 2021-08-31 | 2021-04-22 | 2021-04-22 | 9 | 2021-10-15 | 132 | 2021-11-21 | 24 | [15 empty] | 2021-11-21 | 2021-11-21 | 0 | 2021-11-21 | [6 empty] | 2021-08-26 |  | 2021-08-26
121513316 | 1223 | PGE | 93401 | NEM | NEMMT | Application Review in Progress | ENGN, Solar PV | 625 |  | 2021-06-10 |  | 2021-06-23 | 2021-06-23 | 2021-06-23 | 9
121522845 | 1224 | PGE | 93308 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-06-11 |  | 2021-08-12 | 2021-07-16 | 2021-07-16 | 24 | 2021-08-17 | 46 | 2021-08-20 | 3 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-20 | 2021-08-23 | 1 | [13 empty] | 2021-08-23 | 2021-08-30 | 5 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-30 |  | 2021-09-07 | 5
121578810 | 1225 | PGE | 93636 | NEM | EXPNEM | Withdrawn | Solar PV | 36.133 |  | 2021-06-22 |  | 2021-07-07 | 2021-07-07 | 2021-07-07 | 10 | [29 empty] | 2021-06-22 |  | 2021-06-22
121626896 | 1226 | PGE | 93635 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-06-28 | 2021-06-29 |  | 2021-06-29 | 2021-06-29 | 1 | 2021-07-28 | 21 | 2021-09-02 | 26 | [15 empty] | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02 | 2021-09-08 | 3
121642659 | 1227 | PGE | 93249 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-06-30 | 2021-07-01 |  | 2021-07-01 | 2021-07-01 | 1 | 2021-07-28 | 19 | 2021-08-26 | 21 | [15 empty] | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | 2021-09-05 | 6
121645055 | 1228 | PGE | 94560 | Non-NEM | Non-Export | IA in Progress | Storage | 96 |  | 2021-07-01 |  |  | 2021-07-07 | 2021-07-07 | 3 | 2021-07-07 | 3 | 2021-08-03 | 19 | 2021-08-12 | 2021-10-07 | 39 | [12 empty] | 2021-12-06 | 2021-12-07 | 1 | 2021-12-07
121645132 | 1229 | PGE | 93230 | NEM | EXPNEM | Commercial | Solar PV | 37.006 |  | 2021-07-01 |  | 2021-07-14 | 2021-07-14 | 2021-07-14 | 8 | 2021-07-22 | 14 | 2021-08-09 | 12 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-11 | 2 |  |  |  |  | 2021-07-01 | 2021-07-22 | 2021-07-01 | 2021-07-29 | 19 |  |  |  |  | 2021-08-13 | 2021-08-27 | 10 | [15 empty] | 2021-08-13 | 2021-08-16 | 1 | 2021-08-27 |  | 2021-08-27 | 0
121645475 | 1230 | PGE | 93652 | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-07-01 |  | 2021-07-15 | 2021-07-15 | 2021-07-15 | 9 | 2021-07-21 | 13 | 2021-08-09 | 13 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | [6 empty] | 2021-07-01 | 2021-07-21 | 2021-07-01 | 2021-07-29 | 19
121645590 | 1231 | PGE | 95619 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 36.387 |  | 2021-07-01 |  | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2 | 2021-07-09 | 5 | 2021-07-13 | 2 | [15 empty] | 2021-07-01 | 2021-07-01 |  | 2021-07-01 | 2021-07-01 | 1 |  |  |  |  | 2021-07-01 |  | 2021-07-01 | [9 empty] | 2021-08-16 |  | 104
121646778 | 1232 | PGE | 93727 | Non-NEM | Non-Export | IA in Progress | ENGN | 1429 |  | 2021-07-01 | 2021-07-16 |  | 2021-07-16 | 2021-07-16 | 10 | 2021-08-04 | 23 | 2021-10-22 | 56 | [15 empty] | 2021-11-15 | 2021-11-17 | 2 | 2021-11-17
121649129 | 1233 | PGE | 95602 | NEM | SNEM | Application Submitted | Solar PV | 52.2 |  | 2021-07-01 |  | 2021-07-16 | 2021-07-16 | 2021-07-16 | 10
121649217 | 1234 | PGE | 94960 | NEM | EXPNEM | Withdrawn | Solar PV | 76.547 |  | 2021-07-01 |  | 2021-07-26 | 2021-07-13 | 2021-07-13 | 7 | 2021-08-03 | 22 | 2021-08-23 | 14 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23
121654096 | 1235 | PGE | 94506 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-07-02 |  | 2021-07-14 | 2021-07-14 | 2021-07-14 | 7 | 2021-08-10 | 26 | 2021-08-10 | 0 | [25 empty] | 2021-07-02 | 2021-08-30 | 2021-07-02 | 2021-08-30 | 40 |  |  |  |  | 2021-08-30 | 2021-09-08 | 6 | [15 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-09-08 |  | 2021-09-09 | 1
121655443 | 1236 | PGE | 95112 | NEM | EXPNEM | IA in Progress | Solar PV | 192 |  | 2021-07-02 |  | 2021-07-13 | 2021-07-13 | 2021-07-13 | 6 | 2021-07-14 | 7 | 2021-09-07 | 38 | [15 empty] | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-09-08 | 1 |  |  |  |  | 2021-07-02 |  | 2021-07-02
121655489 | 1237 | PGE | 95648 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 998.26 |  | 2021-07-02 |  | 2021-07-19 | 2021-07-19 | 2021-07-19 | 10 | 2021-08-04 | 22 | 2021-09-08 | 24 | [15 empty] | 2021-09-08 | 2021-09-23 | 11 | 2021-09-23 | 2021-10-04 | 7 | [13 empty] | 2021-11-15 | [17 empty] | 2021-11-15 | 2021-11-16 | 1
121656755 | 1238 | PGE | 95667 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-07-02 |  | 2021-07-15 | 2021-07-15 | 2021-07-15 | 8 | 2021-07-30 | 19 | 2021-08-30 | 21 | [15 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-09-01 | 2 |  |  |  |  | 2021-07-02 | 2021-09-30 | 2021-07-02 | 2021-10-15 | 73 |  |  |  |  | 2021-10-19 | 2021-10-29 | 8 | [15 empty] | 2021-10-19 | 2021-10-20 | 1 | 2021-10-29 |  | 2021-10-29 | 0
121657104 | 1239 | PGE | 93313 | NEM | EXPNEM | Implementation | Solar PV | 816 |  | 2021-07-02 |  | 2021-07-16 | 2021-07-16 | 2021-07-16 | 9 | 2021-07-23 | 14 | 2021-08-09 | 11 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-23 | 10
121657804 | 1240 | PGE | 94027 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 306.642 |  | 2021-07-02 |  | 2021-07-19 | 2021-07-19 | 2021-07-19 | 10
121664116 | 1241 | PGE | 95969 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.4 |  | 2021-07-05 |  | 2021-07-27 | 2021-07-15 | 2021-07-15 | 7 | 2021-08-06 | 23 | 2021-08-10 | 2 | [34 empty] | 2021-08-10 | 2021-08-10 | 0 | [15 empty] | 2021-08-10 |  |  | 2021-08-10 |  | 2021-08-10 | 0
121664160 | 1242 | PGE | 93635 | NEM | EXPNEM | Withdrawn | Solar PV | 181.47 |  | 2021-07-05 |  | 2021-07-16 | 2021-07-16 | 2021-07-16 | 8 | 2021-07-22 | 12 | [27 empty] | 2021-07-05 | 2021-07-26 | 2021-07-05 | 2021-08-09 | 24
121664841 | 1243 | PGE | 95620 | NEM | EXPNEM | Application Review in Progress | Solar PV | 34.179 |  | 2021-07-05 |  | 2021-07-16 | 2021-07-16 | 2021-07-16 | 8 | [29 empty] | 2021-07-05 |  | 2021-07-05
121665205 | 1244 | PGE | 95230 | NEM | EXPNEM | Implementation | Solar PV | 375 |  | 2021-07-05 |  | 2021-07-19 | 2021-07-19 | 2021-07-19 | 9 | 2021-08-05 | 22 | 2021-08-18 | 9 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | 2021-09-07 | 13 |  |  |  |  | 2021-07-05 | 2021-08-06 | 2021-07-05 | 2021-08-18 | 31 | [7 empty] | 2021-10-22 | 2021-11-24 | 22
121667563 | 1245 | PGE | 95030 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.232 |  | 2021-07-06 |  |  | 2021-07-15 | 2021-07-15 | 7 | 2021-07-15 | 7 | 2021-07-19 | 2 | [34 empty] | 2021-07-20 | 2021-07-22 | 2 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-22 |  | 2021-07-26 | 2
121667574 | 1246 | PGE | 95423 | NEM | EXPNEM | Implementation | Solar PV | 30.373 |  | 2021-07-06 |  | 2021-10-04 | 2021-07-19 | 2021-07-19 | 9 | 2021-10-06 | 65 | 2021-10-21 | 11 | [15 empty] | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21 | 2021-11-04 | 10 |  |  |  |  | 2021-07-06 | 2021-10-06 | 2021-07-06 | 2021-10-19 | 74 | [7 empty] | 2021-12-01 |  | 31
121669113 | 1247 | PGE | 96022 | NEM | EXPNEM | Implementation | Solar PV | 51.589 |  | 2021-07-06 |  | 2021-08-11 | 2021-07-13 | 2021-07-13 | 5 | 2021-09-13 | 48 | 2021-10-04 | 15 | [15 empty] | 2021-10-04 | 2021-10-25 | 15 | 2021-10-25 | 2021-11-16 | 15 |  |  |  |  | 2021-07-06 | 2021-08-23 | 2021-07-06 | 2021-09-07 | 44 | [7 empty] | 2021-12-17 |  | 19
121669762 | 1248 | PGE | 93401 | Non-NEM | Non-Export | Implementation | Storage | 643.5 |  | 2021-07-06 | 2021-07-07 |  | 2021-07-07 | 2021-07-07 | 1 | 2021-07-28 | 16 | 2021-09-30 | 45 | [15 empty] | 2021-07-30 | 2021-07-30 | 0 | 2021-07-30 | 2021-10-27 | 62 |  |  |  |  | 2021-07-06 |  | 2021-07-06
121669763 | 1249 | PGE | 93635 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-07-06 |  | 2021-07-20 | 2021-07-20 | 2021-07-20 | 10 | 2021-09-20 | 53 | [17 empty] | 2021-09-24 | 2021-10-05 | 7 | 2021-10-05 | 2021-11-30 | 37 |  |  |  |  | 2021-07-06 | 2021-08-16 | 2021-07-06 | 2021-08-27 | 38 |  |  |  |  | 2021-12-02 | 2021-12-08 | 4 | [15 empty] | 2021-12-02 | 2021-12-03 | 1 | 2021-12-08 |  | 2021-12-09 | 1
121669924 | 1250 | PGE | 95123 | NEM | EXPNEM | Implementation | Solar PV | 86.4 |  | 2021-07-06 |  | 2021-07-20 | 2021-07-20 | 2021-07-20 | 10 | 2021-09-08 | 45 | 2021-09-29 | 15 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | 2021-10-28 | 21 |  |  |  |  | 2021-07-06 | 2021-12-22 | 2021-07-06
121669991 | 1251 | PGE | 95123 | NEM | EXPNEM | Implementation | Solar PV | 86.4 |  | 2021-07-06 |  | 2021-07-20 | 2021-07-20 | 2021-07-20 | 10 | 2021-09-25 | 57 | 2021-10-15 | 14 | [15 empty] | 2021-10-15 | 2021-10-15 | 0 | 2021-10-15 | 2021-10-28 | 9 |  |  |  |  | 2021-07-06 | 2021-12-22 | 2021-07-06
121670131 | 1252 | PGE | 95123 | NEM | EXPNEM | Implementation | Solar PV | 73.256 |  | 2021-07-06 |  | 2021-07-20 | 2021-07-20 | 2021-07-20 | 10 | 2021-09-25 | 57 | 2021-10-15 | 14 | [15 empty] | 2021-10-15 | 2021-10-15 | 0 | 2021-10-15 | 2021-10-28 | 9 |  |  |  |  | 2021-07-06 | 2021-12-23 | 2021-07-06
121670323 | 1253 | PGE | 95033 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.987 |  | 2021-07-06 |  | 2021-07-13 | 2021-07-13 | 2021-07-13 | 5 | 2021-07-22 | 12 | 2021-08-04 | 9 | [15 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | 2021-08-09 | 3 |  |  |  |  | 2021-07-06 |  | 2021-07-06 | [27 empty] | 2021-07-29 |  | 2021-08-09 | 8
121671009 | 1254 | PGE | 93630 | NEM | EXPNEM | Implementation | Solar PV | 180 |  | 2021-07-06 |  | 2021-07-14 | 2021-07-09 | 2021-07-09 | 3 | 2021-07-20 | 10 | 2021-08-02 | 9 | 2021-08-02 | 2021-08-30 | 20 | [12 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-10-21 | 37 |  |  |  |  | 2021-07-06 | 2021-07-20 | 2021-07-06 | 2021-07-28 | 16 | [7 empty] | 2021-11-15 |  | 41
121671470 | 1255 | PGE | 94303 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 48.827 |  | 2021-07-06 |  | 2021-07-19 | 2021-07-19 | 2021-07-19 | 9 | 2021-08-09 | 24 | 2021-08-27 | 14 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | [6 empty] | 2021-07-06 | 2021-09-17 | 2021-07-06 | 2021-10-01 | 62 |  | 2021-10-01 | 2021-10-15 | 10
121672569 | 1256 | PGE | 94806 | NEM | VNEM | IA in Progress | Solar PV | 35.67 |  | 2021-07-07 |  | 2021-07-21 | 2021-07-21 | 2021-07-21 | 10 | 2021-08-06 | 22 | 2021-08-27 | 15 | [15 empty] | 2021-08-27 | 2021-09-20 | 15 | 2021-09-20 | [6 empty] | 2021-07-07 | 2021-10-22 | 2021-07-07 | 2021-11-03 | 84 |  | 2021-11-04 | 2021-11-04 | 0
121672781 | 1257 | PGE | 94806 | NEM | VNEM | IA in Progress | Solar PV | 35.38 |  | 2021-07-07 |  | 2021-07-21 | 2021-07-21 | 2021-07-21 | 10 | 2021-08-06 | 22 | 2021-08-27 | 15 | [15 empty] | 2021-08-27 | 2021-09-20 | 15 | 2021-09-20 | [6 empty] | 2021-07-07 | 2021-10-22 | 2021-07-07 | 2021-11-03 | 84 |  | 2021-11-04 | 2021-11-04 | 0
121672913 | 1258 | PGE | 94806 | NEM | VNEM | IA in Progress | Solar PV | 35.67 |  | 2021-07-07 |  | 2021-07-21 | 2021-07-21 | 2021-07-21 | 10 | 2021-08-06 | 22 | 2021-08-27 | 15 | [15 empty] | 2021-08-27 | 2021-09-20 | 15 | 2021-09-20 | [6 empty] | 2021-07-07 | 2021-10-22 | 2021-07-07 | 2021-11-03 | 84 |  | 2021-11-04 | 2021-11-04 | 0
121672985 | 1259 | PGE | 94806 | NEM | VNEM | IA in Progress | Solar PV | 53.36 |  | 2021-07-07 |  | 2021-07-21 | 2021-07-21 | 2021-07-21 | 10 | 2021-08-06 | 22 | 2021-08-27 | 15 | [15 empty] | 2021-08-27 | 2021-09-20 | 15 | 2021-09-20 | [6 empty] | 2021-07-07 | 2021-10-22 | 2021-07-07 | 2021-11-03 | 84 |  | 2021-11-04 | 2021-11-04 | 0
121674078 | 1260 | PGE | 95401 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 63.292 |  | 2021-07-07 |  | 2021-07-13 | 2021-07-13 | 2021-07-13 | 4 | 2021-07-26 | 13 | 2021-08-16 | 15 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | [6 empty] | 2021-07-07 |  | 2021-07-07 |  |  | 2021-08-06
121674165 | 1261 | PGE | 95401 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 62.872 |  | 2021-07-07 |  | 2021-07-13 | 2021-07-13 | 2021-07-13 | 4 | 2021-07-26 | 13 | 2021-08-16 | 15 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | [6 empty] | 2021-07-07 |  | 2021-07-07 |  |  | 2021-08-06
121675223 | 1262 | PGE | 93230 | NEM | EXPNEM | Implementation | Solar PV | 120 |  | 2021-07-07 |  | 2021-08-05 | 2021-07-13 | 2021-07-13 | 4 | 2021-08-05 | 21 | [17 empty] | 2021-08-17 | 2021-08-17 | 0 | 2021-08-17 | 2021-11-03 | 55 |  |  |  |  | 2021-07-07 |  | 2021-07-07 |  |  | 2021-07-23
121676464 | 1263 | PGE | 95926 | NEM | EXPNEM | IA in Progress | Solar PV | 83.3 |  | 2021-07-07 |  | 2021-08-05 | 2021-07-13 | 2021-07-13 | 4 | 2021-08-09 | 23 | [5 empty] | 2021-08-09 | 2021-09-17 | 28 | 2021-09-17 |  |  |  | 2021-11-23
121677360 | 1264 | PGE | 93646 | NEM | EXPNEM | Implementation | Solar PV | 139.15 |  | 2021-07-07 |  | 2021-07-27 | 2021-07-19 | 2021-07-19 | 8 | 2021-10-11 | 67 | 2021-10-21 | 8 | [15 empty] | 2021-10-21 | 2021-10-25 | 2 | 2021-10-25 | 2021-10-27 | 2 | [5 empty] | 2021-11-08 | 2021-11-08 | 2021-11-09 | 1 | 2021-10-14 | [6 empty] | 2021-11-15 |  | 41
121677853 | 1265 | PGE | 95457 | NEM | EXPNEM | Implementation | Solar PV | 434.952 |  | 2021-07-07 |  | 2021-07-13 | 2021-07-13 | 2021-07-13 | 4 | 2021-07-21 | 10 | 2021-08-25 | 25 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | 2021-09-08 | 9 |  |  |  |  | 2021-07-07 | 2021-07-21 | 2021-07-07 | 2021-07-29 | 16
121677966 | 1266 | PGE | 94062 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.545 |  | 2021-07-07 |  | 2021-08-10 | 2021-07-16 | 2021-07-16 | 7
121678341 | 1267 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 37.598 |  | 2021-07-07 |  | 2021-07-20 | 2021-07-20 | 2021-07-20 | 9 | 2021-08-02 | 18 | 2021-08-23 | 15 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23 | [6 empty] | 2021-07-07 | 2021-07-28 | 2021-07-07 | 2021-08-13 | 27
121678407 | 1268 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 63.182 |  | 2021-07-07 |  | 2021-07-20 | 2021-07-20 | 2021-07-20 | 9 | 2021-08-02 | 18 | 2021-11-05 | 68 | [15 empty] | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05 | [6 empty] | 2021-07-07 | 2021-09-08 | 2021-07-07 | 2021-09-10 | 46 |  | 2021-09-24 | 2021-09-24 | 0
121678996 | 1269 | PGE | 95008 | NEM | VNEMSOMAH | Implementation | Solar PV | 75.43 |  | 2021-07-07 |  | 2021-07-16 | 2021-07-16 | 2021-07-16 | 7 | 2021-07-26 | 13 | 2021-09-13 | 34 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-12-13 | 62 |  |  |  |  | 2021-07-07 |  | 2021-07-07 |  |  | 2021-08-06
121678998 | 1270 | PGE | 95008 | NEM | VNEMSOMAH | Implementation | Solar PV | 66.259 |  | 2021-07-07 |  | 2021-07-16 | 2021-07-16 | 2021-07-16 | 7 | 2021-07-26 | 13 | 2021-08-16 | 15 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | 2021-12-13 | 81 |  |  |  |  | 2021-07-07 |  | 2021-07-07 |  |  | 2021-08-06
121679712 | 1271 | PGE | 94115 | Non-NEM | Continuous Uncompensated Export | Commercial | ENGN, Solar PV | 66.6 |  | 2021-07-07 | 2021-07-08 |  | 2021-07-08 | 2021-07-08 | 1 | 2021-07-14 | 5 | 2021-09-27 | 52 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-26 | 21 | [13 empty] | 2021-10-29 | 2021-11-03 | 3 | [15 empty] | 2021-10-29 | 2021-10-30 | 0 | 2021-11-03 |  | 2021-11-03 | 0
121679736 | 1272 | PGE | 94028 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 38.27 |  | 2021-07-07 |  | 2021-09-13 | 2021-07-16 | 2021-07-16 | 7
121681799 | 1273 | PGE | 95642 | Non-NEM | Non-Export | Study in Progress | ENGN | 170 |  | 2021-07-08 | 2021-07-08 |  | 2021-07-08 | 2021-07-08 | 0 | 2021-07-21 | 9 | 2021-08-25 | 25 | 2021-09-30 | 2021-11-03 | 24 | [22 empty] | 2021-08-04 | 2021-08-06 | 2021-08-04 | 2021-08-06 | 2
121684141 | 1274 | PGE | 95376 | NEM | EXPNEM | Commercial | Solar PV | 43.53 |  | 2021-07-08 |  | 2021-07-13 | 2021-07-13 | 2021-07-13 | 3 | 2021-07-26 | 12 | 2021-08-11 | 12 | [15 empty] | 2021-08-11 | 2021-08-11 | 0 | 2021-08-11 | 2021-08-20 | 7 | [13 empty] | 2021-09-10 | 2021-09-20 | 6 | [15 empty] | 2021-09-10 | 2021-09-12 | 0 | 2021-09-20 |  | 2021-10-19 | 21
121684217 | 1275 | PGE | 95035 | NEM | VNEM | Commercial | Solar PV | 33.39 |  | 2021-07-08 |  | 2021-07-15 | 2021-07-15 | 2021-07-15 | 5 | 2021-08-24 | 33 | 2021-09-13 | 13 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-09-17 | 4 |  |  |  |  | 2021-07-08 |  | 2021-07-08 |  |  | 2021-08-06 | 2021-08-24 | 2021-08-25 | 12 | 2021-12-03 | 2021-12-09 | 4 | [15 empty] | 2021-12-03 | 2021-12-06 | 1 | 2021-12-09 |  | 2021-12-10 | 1
121684550 | 1276 | PGE | 95035 | NEM | VNEM | Implementation | Solar PV | 32.445 |  | 2021-07-08 |  | 2021-07-15 | 2021-07-15 | 2021-07-15 | 5 | 2021-08-24 | 33 | 2021-09-15 | 15 | [15 empty] | 2021-09-15 | 2021-10-06 | 15 | 2021-10-06 | 2021-10-14 | 6 |  |  |  |  | 2021-07-08 |  | 2021-07-08 |  |  | 2021-08-06 | 2021-10-19 | 2021-10-19 | 51 | 2021-12-03 | [17 empty] | 2021-12-03 | 2021-12-06 | 1
121687252 | 1277 | PGE | 94566 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-07-09 |  |  | 2021-07-17 | 2021-07-17 | 5 | 2021-07-17 | 5 | 2021-07-20 | 1 | [25 empty] | 2021-07-09 | 2021-08-20 | 2021-07-09 | 2021-08-20 | 30 |  |  |  |  | 2021-08-20 | 2021-08-27 | 5 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-27 |  | 2021-08-31 | 2
121690217 | 1278 | PGE | 93242 | NEM | EXPNEM | Withdrawn | Solar PV | 1560 |  | 2021-07-09 | 2021-07-09 |  | 2021-07-09 | 2021-07-09 | 0 | 2021-07-21 | 8 | 2021-08-13 | 17 | [25 empty] | 2021-07-09 | 2021-07-30 | 2021-07-09
121693828 | 1279 | PGE | 94588 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 850 |  | 2021-07-09 |  | 2021-09-16 | 2021-07-19 | 2021-07-19 | 6 | 2021-09-24 | 54 | 2021-11-29 | 43 | 2021-12-06 | [24 empty] | 2021-07-09 |  | 2021-07-09 |  |  | 2021-09-07
121709667 | 1280 | PGE | 93923 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 37.957 |  | 2021-07-11 |  |  | 2021-07-19 | 2021-07-19 | 5 | 2021-07-19 | 5 | 2021-07-19 | 0 | [34 empty] | 2021-07-19 | 2021-07-19 | 0 | [15 empty] | 2021-07-19 |  |  | 2021-07-19 |  | 2021-07-19 | 0
121712221 | 1281 | PGE | 94027 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-07-12 |  |  | 2021-07-19 | 2021-07-19 | 5 | 2021-07-19 | 5 | 2021-07-21 | 2 | [25 empty] | 2021-07-12 | 2021-10-19 | 2021-07-12 | 2021-10-19 | 70 |  |  |  |  | 2021-10-19 | 2021-10-19 | 0 | [15 empty] | 2021-10-19 |  |  | 2021-10-19 |  | 2021-10-19 | 0
121713542 | 1282 | PGE | 95123 | NEM | EXPNEM | Implementation | Solar PV | 52.163 |  | 2021-07-12 |  | 2021-07-26 | 2021-07-26 | 2021-07-26 | 10 | 2021-09-08 | 41 | 2021-09-29 | 15 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | 2021-10-28 | 21 |  |  |  |  | 2021-07-12 | 2021-12-09 | 2021-07-12 | 2021-12-15 | 108 | 2021-12-09 | 2021-12-10 | 2021-12-10 | 1
121713944 | 1283 | PGE | 94804 | NEM | EXPNEM | IA in Progress | Solar PV | 814.048 |  | 2021-07-12 |  | 2021-08-03 | 2021-07-14 | 2021-07-14 | 2 | 2021-08-06 | 19 | 2021-08-25 | 13 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | [6 empty] | 2021-07-12 |  | 2021-07-12
121714055 | 1284 | PGE | 94014 | NEM | EXPNEM | Commercial | Solar PV | 34.179 |  | 2021-07-12 |  | 2021-07-26 | 2021-07-15 | 2021-07-15 | 3 | 2021-08-02 | 15 | 2021-08-09 | 5 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-10 | 1 | [13 empty] | 2021-08-18 | 2021-08-24 | 4 | [15 empty] | 2021-08-18 | 2021-08-19 | 1 | 2021-08-24 |  | 2021-08-27 | 3
121714415 | 1285 | PGE | 95322 | NEM | EXPNEM | IA in Progress | Solar PV | 240 |  | 2021-07-12 |  | 2021-07-29 | 2021-07-22 | 2021-07-22 | 8 | 2021-10-25 | 74 | 2021-11-09 | 11 | [15 empty] | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09
121715895 | 1286 | PGE | 95501 | Non-NEM | Non-Export | Withdrawn | Storage | 350 |  | 2021-07-12 | 2021-07-13 |  | 2021-07-13 | 2021-07-13 | 1 | 2021-07-28 | 12 | 2021-08-18 | 15 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | [6 empty] | 2021-07-12 |  | 2021-07-12
121716126 | 1287 | PGE | 95501 | Non-NEM | Non-Export | Withdrawn | Storage | 560 |  | 2021-07-12 | 2021-07-13 |  | 2021-07-13 | 2021-07-13 | 1 | 2021-07-28 | 12 | 2021-08-23 | 18 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23
121716351 | 1288 | PGE | 95762 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.964 |  | 2021-07-12 |  | 2021-10-18 | 2021-07-20 | 2021-07-20 | 6 | 2021-10-26 | 75 | 2021-10-27 | 1 | [34 empty] | 2021-10-27 | 2021-10-27 | 0 | [15 empty] | 2021-10-27 |  |  | 2021-10-27 |  | 2021-10-27 | 0
121716853 | 1289 | PGE | 93620 | NEM | EXPNEM | Study in Progress | Solar PV | 975 |  | 2021-07-12 |  | 2021-07-23 | 2021-07-19 | 2021-07-19 | 5 | 2021-07-30 | 14 | 2021-08-17 | 12 | 2021-08-17 | 2021-09-22 | 25 | 2021-09-22 | 2021-10-13 | 15 | 2021-10-13 | 2021-10-22 | 7 |  |  |  | 2021-10-22 | [12 empty] | 2021-07-12 | 2021-07-30 | 2021-07-12 | 2021-08-13 | 24
121716964 | 1290 | PGE | 95240 | NEM | EXPNEM | Application Review in Progress | Solar PV | 636 |  | 2021-07-12 |  | 2021-08-20 | 2021-07-26 | 2021-07-26 | 10
121717092 | 1291 | PGE | 94549 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-07-12 |  | 2021-07-20 | 2021-07-20 | 2021-07-20 | 6 | 2021-08-04 | 17 | 2021-08-04 | 0 | [34 empty] | 2021-08-04 | 2021-08-04 | 0 | [15 empty] | 2021-08-04 |  |  | 2021-08-04 |  | 2021-08-04 | 0
121717607 | 1292 | PGE | 95337 | NEM | EXPNEM | Study in Progress | Solar PV | 96.768 |  | 2021-07-12 |  | 2021-07-19 | 2021-07-19 | 2021-07-19 | 5 | 2021-07-22 | 8 | 2021-08-10 | 13 | 2021-08-10 | 2021-09-07 | 19 | 2021-09-08 | 2021-10-05 | 19 | 2021-10-05 | [18 empty] | 2021-07-12 | 2021-07-26 | 2021-07-12 | 2021-08-09 | 20
121718040 | 1293 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 46.536 |  | 2021-07-12 |  | 2021-07-26 | 2021-07-15 | 2021-07-15 | 3 | 2021-07-31 | 14 | 2021-08-09 | 5 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-09-08 | 21 | [13 empty] | 2021-10-21 | 2021-10-28 | 5 | [15 empty] | 2021-10-21 | 2021-10-21 | 0 | 2021-10-28 |  | 2021-11-03 | 4
121719754 | 1294 | PGE | 95691 | NEM | EXPNEM | IA in Progress | Solar PV | 105.56 |  | 2021-07-13 |  | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2 | 2021-07-23 | 8 | 2021-08-10 | 12 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-10 | 2021-08-18 | 6 |  |  |  |  | 2021-07-13 | 2021-07-15 | 2021-07-13 | 2021-07-28 | 11
121721397 | 1295 | PGE | 94027 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 35.08 |  | 2021-07-13 |  | 2021-10-07 | 2021-07-27 | 2021-07-27 | 10 | 2021-10-13 | 65 | 2021-10-15 | 2 | [15 empty] | 2021-07-13 | 2021-07-13 |  | 2021-07-13 | 2021-07-16 | 4
121722288 | 1296 | PGE | 95407 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 115.42 |  | 2021-07-13 |  | 2021-07-27 | 2021-07-27 | 2021-07-27 | 10 | 2021-08-05 | 17 | 2021-08-26 | 15 | [15 empty] | 2021-08-26 | 2021-09-16 | 14 | 2021-09-16 | [6 empty] | 2021-07-13 | 2021-08-17 | 2021-07-13 | 2021-08-25 | 31 |  | 2021-08-26 | 2021-09-16 | 14
121722546 | 1297 | PGE | 93262 | NEM | EXPNEM | Implementation | Solar PV | 300 |  | 2021-07-13 |  |  | 2021-07-20 | 2021-07-20 | 5 | 2021-07-20 | 5 | 2021-08-16 | 19 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | 2021-08-17 | 1 |  |  |  |  | 2021-07-13 | 2021-07-30 | 2021-07-13 | 2021-08-13 | 23 | [7 empty] | 2021-09-08 | 2022-01-04 | 80 |  |  |  | 2022-01-04 | 0 | 8
121725874 | 1298 | PGE | 94062 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 45.116 |  | 2021-07-14 |  |  | 2021-07-21 | 2021-07-21 | 5 | 2021-07-21 | 5 | 2021-07-22 | 1 | [25 empty] | 2021-07-14 |  | 2021-07-14 | [6 empty] | 2021-07-22 | 2021-07-22 | 0 | [15 empty] | 2021-07-22 |  |  | 2021-07-22 |  | 2021-07-22 | 0
121726540 | 1299 | PGE | 95231 | NEM | EXPNEM | Application Review in Progress | Solar PV | 35.09 |  | 2021-07-14 |  | 2021-07-16 | 2021-07-16 | 2021-07-16 | 2 | [29 empty] | 2021-07-14 |  | 2021-07-14
121726607 | 1300 | PGE | 94608 | NEM | EXPNEM | IA in Progress | Solar PV | 51.939 |  | 2021-07-14 |  | 2021-07-30 | 2021-07-20 | 2021-07-20 | 4 | 2021-08-04 | 15 | 2021-10-05 | 43 | [15 empty] | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | 2021-10-07 | 2 |  |  |  |  | 2021-07-14 | 2021-10-05 | 2021-07-14 | 2021-10-18 | 67 | [7 empty] | 2021-12-10 | 2021-12-10 | 0 |  |  |  | 2021-12-27 | 0 | 14
121727091 | 1301 | PGE | 95913 | NEM | EXPNEM | Commercial | Solar PV | 34.29 |  | 2021-07-14 |  | 2021-07-20 | 2021-07-20 | 2021-07-20 | 4 | 2021-07-20 | 4 | 2021-08-09 | 14 | [15 empty] | 2021-08-09 | 2021-08-16 | 5 | 2021-08-16 | 2021-08-16 | 0 |  |  |  |  | 2021-07-14 |  | 2021-07-14 |  |  | 2021-08-06 |  |  |  | 2021-08-09 | 2021-08-16 | 5 | [15 empty] | 2021-08-09 | 2021-08-10 | 1 | 2021-08-16 |  | 2021-08-16 | 0
121729951 | 1302 | PGE | 93635 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-07-14 |  | 2021-07-23 | 2021-07-23 | 2021-07-23 | 7 | 2021-08-31 | 34 | 2021-09-15 | 10 | [15 empty] | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | 2021-09-15 | 0 |  |  |  |  | 2021-07-14 | 2021-08-31 | 2021-07-14 | 2021-09-10 | 41 |  |  |  |  | 2021-09-28 | 2021-10-05 | 5 | [15 empty] | 2021-09-28 | 2021-09-28 | 0 | 2021-10-05 |  | 2021-10-05 | 0
121730121 | 1303 | PGE | 95501 | Non-NEM | Non-Export | Implementation | Storage | 420 |  | 2021-07-14 | 2021-07-14 |  | 2021-07-14 | 2021-07-14 | 0 | 2021-08-11 | 20 | 2021-10-08 | 41 | [15 empty] | 2021-10-08 | 2021-10-08 | 0 | 2021-10-08 | 2021-10-27 | 13 |  |  |  |  | 2021-07-14 |  | 2021-07-14
121731246 | 1304 | PGE | 94028 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.66 |  | 2021-07-14 |  | 2021-09-16 | 2021-07-22 | 2021-07-22 | 6 | 2021-09-27 | 52 | 2021-09-28 | 1 | [34 empty] | 2021-09-28 | 2021-09-28 | 0 | [15 empty] | 2021-09-28 |  |  | 2021-09-28 |  | 2021-09-28 | 0
121731507 | 1305 | PGE | 95322 | NEM | EXPNEM | Implementation | Solar PV | 437.5 |  | 2021-07-14 |  | 2021-07-26 | 2021-07-26 | 2021-07-26 | 8 | 2021-08-10 | 19 | 2021-08-31 | 15 | [15 empty] | 2021-08-31 | 2021-09-22 | 15 | 2021-09-22 | 2021-12-17 | 59 |  |  |  |  | 2021-07-14 | 2021-12-22 | 2021-07-14 |  |  | 2021-08-13
121734791 | 1306 | PGE | 94585 | NEM | EXPNEM | Commercial | Solar PV | 56.472 |  | 2021-07-15 |  | 2021-11-29 | 2021-07-26 | 2021-07-26 | 7 | 2021-11-30 | 94 | 2021-12-13 | 9 | [15 empty] | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13 | 2021-12-13 | 0 |  |  |  |  | 2021-07-15 |  | 2021-07-15 | [6 empty] | 2021-12-14 | 2021-12-22 | 6 | [15 empty] | 2021-12-14 | 2021-12-15 | 1 | 2021-12-22 |  | 2021-12-28 | 4
121735402 | 1307 | PGE | 93635 | NEM | EXPNEM | Withdrawn | Solar PV | 33.3 |  | 2021-07-15 |  | 2021-07-27 | 2021-07-27 | 2021-07-27 | 8 | 2021-07-27 | 8 | 2021-08-17 | 15 | [15 empty] | 2021-08-17 | 2021-08-17 | 0 | 2021-08-17
121735517 | 1308 | PGE | 95125 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.309 |  | 2021-07-15 |  | 2021-07-22 | 2021-07-22 | 2021-07-22 | 5 | 2021-08-04 | 14 | 2021-08-06 | 2 | [34 empty] | 2021-08-06 | 2021-08-06 | 0 | [15 empty] | 2021-08-06 |  |  | 2021-08-06 |  | 2021-08-06 | 0
121735711 | 1309 | PGE | 93706 | NEM | EXPNEM | IA in Progress | Solar PV | 666.6 |  | 2021-07-15 |  | 2021-07-28 | 2021-07-28 | 2021-07-28 | 9 | 2021-08-12 | 20 | 2021-08-27 | 11 | 2021-08-27 | 2021-09-23 | 18 | 2021-09-23 | 2021-10-04 | 7 | 2021-10-04 |  |  |  | 2021-12-03 |  |  |  |  | 2021-12-03 | 2021-12-03 | 0 | 2021-12-03 | [6 empty] | 2021-07-15 | 2021-07-30 | 2021-07-15 | 2021-08-13 | 21
121736634 | 1310 | PGE | 96080 | NEM | EXPNEM | IA in Progress | Solar PV | 129.767 |  | 2021-07-15 |  | 2021-08-05 | 2021-08-03 | 2021-08-03 | 13 | 2021-08-20 | 26 | 2021-09-08 | 12 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-09-09 | 1 |  |  |  |  | 2021-07-15 | 2021-09-23 | 2021-07-15 | 2021-10-06 | 58 |  |  |  |  | 2021-11-18 | 2021-12-02 | 8 | 2021-10-20 |  | 58 | [12 empty] | 2021-11-18 | 2021-11-19 | 1 | 2021-12-02 | 2021-12-03 |  | 1 |  |  | 97
121737090 | 1311 | PGE | 95685 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 42.775 |  | 2021-07-15 |  | 2021-09-29 | 2021-07-23 | 2021-07-23 | 6 | 2021-10-08 | 60 | 2021-10-12 | 2
121738475 | 1312 | PGE | 95322 | NEM | EXPNEM | Commercial | Solar PV | 125 |  | 2021-07-15 |  | 2021-08-10 | 2021-07-28 | 2021-07-28 | 9 | 2021-08-12 | 20 | 2021-08-27 | 11 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-08-30 | 1 |  |  |  |  | 2021-07-15 | 2021-08-30 | 2021-07-15 | 2021-09-10 | 40 |  |  |  |  | 2021-09-21 | 2021-09-30 | 7 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-30 |  | 2021-09-30 | 0
121742796 | 1313 | PGE | 93637 | NEM | EXPNEM | Study in Progress | FUCE | 999.5 |  | 2021-07-16 |  |  | 2021-07-26 | 2021-07-26 | 6 | 2021-07-26 | 6 | 2021-08-16 | 15 | 2021-08-16 | 2021-09-20 | 24 | 2021-09-23 | 2021-10-19 | 18 | 2021-10-19 | 2021-10-19 | 0 |  |  |  | 2021-10-19 | [12 empty] | 2021-07-16 |  | 2021-07-16
121743503 | 1314 | PGE | 95648 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 32.47 |  | 2021-07-16 |  | 2021-07-26 | 2021-07-26 | 2021-07-26 | 6 | 2021-08-12 | 19 | 2021-08-13 | 1 | [34 empty] | 2021-08-16 | 2021-08-16 | 0 | [15 empty] | 2021-08-16 |  |  | 2021-08-16 |  | 2021-08-16 | 0
121743843 | 1315 | PGE | 95965 | NEM | EXPNEM | IA in Progress | Solar PV | 300 |  | 2021-07-16 |  | 2021-08-09 | 2021-07-26 | 2021-07-26 | 6 | 2021-08-16 | 21 | 2021-09-01 | 12 | [15 empty] | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01
121743878 | 1316 | PGE | 95476 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-07-16 |  | 2021-07-26 | 2021-07-26 | 2021-07-26 | 6 | 2021-08-04 | 13 | 2021-08-18 | 10 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | 2021-08-20 | 2 |  |  |  |  | 2021-07-16 | 2021-08-02 | 2021-07-16 | 2021-08-13 | 20 |  |  |  |  | 2021-08-20 | 2021-08-26 | 4 | [15 empty] | 2021-08-20 | 2021-08-23 | 1 | 2021-08-26 |  | 2021-08-30 | 2
121743879 | 1317 | PGE | 95020 | NEM | EXPNEM | IA in Progress | Solar PV | 33.24 |  | 2021-07-16 |  | 2021-11-04 | 2021-07-26 | 2021-07-26 | 6 | 2021-11-08 | 80 | 2021-12-22 | 29 | [15 empty] | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22 | 2021-12-27 | 3 |  |  |  |  | 2021-07-16 |  | 2021-07-16
121746096 | 1318 | PGE | 93242 | NEM | EXPNEM | Implementation | Solar PV | 170 |  | 2021-07-16 |  | 2021-07-30 | 2021-07-29 | 2021-07-29 | 9 | 2021-08-05 | 14 | 2021-08-20 | 11 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-20 | 2021-09-17 | 19 |  |  |  |  | 2021-07-16 | 2021-08-05 | 2021-07-16 | 2021-08-13 | 20 | [7 empty] | 2021-10-04 |  | 70
121746802 | 1319 | PGE | 94080 | NEM | EXPNEM | Implementation | Solar PV | 125.259 |  | 2021-07-16 |  |  | 2021-07-29 | 2021-07-29 | 9 | 2021-07-29 | 9 | 2021-08-09 | 7 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-11-05 | 63 |  |  |  |  | 2021-07-16 | 2021-08-23 | 2021-07-16 | 2021-08-23 | 26
121752722 | 1320 | PGE | 95020 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.022 |  | 2021-07-19 |  |  | 2021-07-27 | 2021-07-27 | 6 | 2021-07-27 | 6 | 2021-07-28 | 1 | [25 empty] | 2021-07-19 | 2021-11-27 | 2021-07-19 | 2021-11-27 | 90 |  |  |  |  | 2021-11-27 | 2021-11-27 | 0 | [15 empty] | 2021-11-27 |  |  | 2021-11-27 |  | 2021-11-27 | 0
121754384 | 1321 | PGE | 93307 | NEM | EXPNEM | Study in Progress | Solar PV | 1240.07 |  | 2021-07-19 | 2021-07-26 |  | 2021-07-26 | 2021-07-26 | 5 | 2021-08-04 | 12 | 2021-09-14 | 28 | 2021-10-01 | 2021-11-05 | 25 | 2021-12-03 | [21 empty] | 2021-07-19 | 2021-08-20 | 2021-07-19 | 2021-09-07 | 35
121754976 | 1322 | PGE | 95336 | NEM | EXPNEM | Study in Progress | Solar PV | 420 |  | 2021-07-19 |  | 2021-09-13 | 2021-07-26 | 2021-07-26 | 5 | 2021-10-21 | 67 | 2021-11-18 | 19 | 2021-11-18 | 2021-12-17 | 19 | 2021-12-28
121757817 | 1323 | PGE | 93230 | NEM | EXPNEM | Study in Progress | Solar PV | 3950 |  | 2021-07-19 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 8 | 2021-09-16 | 42 | [5 empty] | 2021-09-16 | 2021-10-21 | 25 | 2021-10-21 | 2021-10-22 | 1 | 2021-11-15 |  |  | 2021-10-22 | 2021-10-27 | 3
121760674 | 1324 | PGE | 93280 | NEM | VNEM | Implementation | Solar PV | 64.86 |  | 2021-07-20 |  | 2021-09-24 | 2021-07-20 | 2021-07-20 | 0 | 2021-11-02 | 74 | 2021-11-05 | 3 | [15 empty] | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05 | 2021-12-14 | 24 |  |  |  |  | 2021-11-01 |  | 2021-11-01 | [9 empty] | 2021-12-22 |  | 16
121761647 | 1325 | PGE | 94904 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.6 |  | 2021-07-20 |  | 2021-07-29 | 2021-07-29 | 2021-07-29 | 7
121761800 | 1326 | PGE | 94404 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.375 |  | 2021-07-20 |  | 2021-08-12 | 2021-07-29 | 2021-07-29 | 7 | [29 empty] | 2021-07-20 |  | 2021-07-20
121762277 | 1327 | PGE | 93263 | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-07-20 |  | 2021-07-26 | 2021-07-26 | 2021-07-26 | 4 | 2021-09-03 | 33 | 2021-09-30 | 18 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | 2021-12-16 | 52 |  |  |  |  | 2021-07-20 | 2021-08-21 | 2021-07-20 | 2021-08-27 | 28 | [7 empty] | 2021-11-02 |  | 49
121763000 | 1328 | PGE | 94558 | NEM | EXPNEM | IA in Progress | Solar PV | 43.31 |  | 2021-07-20 |  | 2021-07-27 | 2021-07-27 | 2021-07-27 | 5 | 2021-09-29 | 50 | 2021-11-01 | 23 | [15 empty] | 2021-11-01 | 2021-11-01 | 0 | 2021-11-01 | 2021-11-25 | 16 | [5 empty] | 2021-12-21 | 2021-12-21 | [9 empty] | 2021-12-17 |  | 19
121764162 | 1329 | PGE | 95111 | NEM | EXPNEM | Application Review in Progress | Solar PV | 167.863 |  | 2021-07-20 |  | 2021-10-02 | 2021-07-28 | 2021-07-28 | 6 | [29 empty] | 2021-07-20 |  | 2021-07-20
121765603 | 1330 | PGE | 94558 | NEM | EXPNEM | Commercial | Solar PV | 32.095 |  | 2021-07-20 |  | 2021-08-03 | 2021-08-03 | 2021-08-03 | 10 | 2021-08-16 | 19 | 2021-09-03 | 14 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-07 | 1 |  |  |  |  | 2021-07-20 | 2021-08-23 | 2021-07-20 | 2021-09-07 | 34 |  |  |  |  | 2021-09-20 | 2021-09-28 | 6 | [15 empty] | 2021-09-20 | 2021-09-20 | 0 | 2021-09-28 |  | 2021-10-05 | 5
121767242 | 1331 | PGE | 94111 | NEM | EXPNEM | IA in Progress | Solar PV | 94.059 |  | 2021-07-21 |  | 2021-11-11 | 2021-07-28 | 2021-07-28 | 5 | 2021-11-17 | 83 | 2021-12-01 | 8 | [15 empty] | 2021-12-01 | 2021-12-01 | 0 | 2021-12-01
121770110 | 1332 | PGE | 94513 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-07-21 |  | 2021-07-30 | 2021-07-30 | 2021-07-30 | 7 | 2021-08-13 | 17 | 2021-08-13 | 0 | [34 empty] | 2021-08-13 | 2021-08-13 | 0 | [15 empty] | 2021-08-13 |  |  | 2021-08-13 |  | 2021-08-13 | 0
121770192 | 1333 | PGE | 95122 | NEM | EXPNEM | IA in Progress | Solar PV | 144.967 |  | 2021-07-21 |  | 2021-07-28 | 2021-07-28 | 2021-07-28 | 5 | 2021-10-02 | 51 | 2021-11-23 | 35 | [15 empty] | 2021-11-23 | 2021-11-23 | 0 | 2021-11-23 | [6 empty] | 2021-07-21 | 2021-10-06 | 2021-07-21 | 2021-10-21 | 65
121770675 | 1334 | PGE | 93301 | NEM | EXPNEM | Application Review in Progress | Solar PV | 402.52 |  | 2021-07-21 |  | 2021-07-28 | 2021-07-28 | 2021-07-28 | 5 | [29 empty] | 2021-07-21 |  | 2021-07-21
121771508 | 1335 | PGE | 95125 | NEM | EXPNEM | Commercial | Solar PV | 58.623 |  | 2021-07-21 |  | 2021-08-11 | 2021-07-29 | 2021-07-29 | 6 | 2021-08-26 | 26 | 2021-09-09 | 9 | [15 empty] | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 | 2021-09-09 | 0 | [9 empty] | 2021-10-01 | 2021-10-06 | 2021-10-06 | 3 | 2021-12-13 | 2021-12-21 | 6 | [15 empty] | 2021-12-13 | 2021-12-14 | 1 | 2021-12-21 |  | 2021-12-21 | 0
121776517 | 1336 | PGE | 95401 | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 |  | 2021-07-22 |  | 2021-08-02 | 2021-08-02 | 2021-08-02 | 7 | [29 empty] | 2021-07-22 |  | 2021-07-22
121778028 | 1337 | PGE | 94534 | NEM | EXPNEM | IA in Progress | ENGN, Solar PV | 227.661 |  | 2021-07-22 |  | 2021-08-17 | 2021-07-29 | 2021-07-29 | 5 | 2021-11-03 | 73 | 2021-11-19 | 11 | [15 empty] | 2021-11-19 | 2021-11-19 | 0 | 2021-11-19
121778329 | 1338 | PGE | 94404 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.204 |  | 2021-07-22 |  | 2021-07-31 | 2021-07-22 | 2021-07-22 | 0 | 2021-08-12 | 15 | 2021-09-07 | 17 | [34 empty] | 2021-09-07 | 2021-09-07 | 0 | [15 empty] | 2021-09-07 |  |  | 2021-09-07 |  | 2021-09-07 | 0
121780249 | 1339 | PGE | 94560 | NEM | EXPNEM | Withdrawn | Solar PV | 1000 |  | 2021-07-22 |  | 2021-08-03 | 2021-07-30 | 2021-07-30 | 6 | 2021-08-11 | 14 | 2021-09-09 | 20 | 2021-09-14 | 2021-10-12 | 20 | [12 empty] | 2021-10-12 | 2021-10-12 | 0 | 2021-10-12 | 2021-10-19 | 5 |  |  |  |  | 2021-07-22 | 2021-07-30 | 2021-07-22 | 2021-08-09 | 12
121780388 | 1340 | PGE | 95334 | NEM | EXPNEM | Commercial | Solar PV | 32.269 |  | 2021-07-22 |  | 2021-09-13 | 2021-07-23 | 2021-07-23 | 1 | 2021-09-24 | 45 | 2021-10-07 | 9 | [15 empty] | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-10-22 | 11 |  |  |  |  | 2021-07-22 | 2021-09-24 | 2021-07-22 | 2021-09-28 | 47 |  |  |  |  | 2021-10-27 | 2021-11-04 | 6 | [15 empty] | 2021-10-27 | 2021-10-28 | 1 | 2021-11-04 |  | 2021-11-04 | 0
121784437 | 1341 | PGE | 93711 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-07-23 |  | 2021-08-02 | 2021-08-02 | 2021-08-02 | 6 | 2021-08-20 | 20 | 2021-08-26 | 4 | [25 empty] | 2021-07-23 | 2021-09-13 | 2021-07-23 | 2021-09-13 | 35 |  |  |  |  | 2021-09-13 | 2021-09-13 | 0 | [15 empty] | 2021-09-13 |  |  | 2021-09-13 |  | 2021-09-13 | 0
121784570 | 1342 | PGE | 95521 | Non-NEM | Non-Export | Implementation | Storage | 280 |  | 2021-07-23 | 2021-07-23 |  | 2021-07-23 | 2021-07-23 | 0 | 2021-08-11 | 13 | 2021-09-08 | 19 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-09-10 | 2 |  |  |  |  | 2021-07-23 |  | 2021-07-23 | [9 empty] | 2021-10-19 |  | 59
121785644 | 1343 | PGE | 93648 | NEM | EXPNEM | IA in Progress | Solar PV | 956.275 |  | 2021-07-23 |  | 2021-08-19 | 2021-08-05 | 2021-08-05 | 9 | 2021-09-14 | 36 | 2021-09-24 | 8 | 2021-09-24 | 2021-10-22 | 20 | [12 empty] | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | [6 empty] | 2021-07-23 | 2021-12-03 | 2021-07-23 | 2021-12-16 | 100 | 2021-10-01
121786065 | 1344 | PGE | 95668 | NEM | EXPNEM | Commercial | Solar PV | 35.139 |  | 2021-07-23 |  | 2021-08-05 | 2021-08-03 | 2021-08-03 | 7 | 2021-09-13 | 35 | 2021-09-15 | 2 | [15 empty] | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | 2021-10-06 | 15 |  |  |  |  | 2021-07-23 | 2021-09-15 | 2021-07-23 | 2021-09-22 | 42 |  |  |  |  | 2021-11-15 | 2021-11-18 | 3 | [15 empty] | 2021-11-15 | 2021-11-15 | 0 | 2021-11-18 |  | 2021-11-18 | 0
121786105 | 1345 | PGE | 93426 | Non-NEM | Non-Export | IA in Progress | Storage | 929.5 |  | 2021-07-23 | 2021-07-23 |  | 2021-07-23 | 2021-07-23 | 0 | 2021-08-11 | 13 | 2021-10-19 | 48 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | [6 empty] | 2021-07-23 | 2021-08-13 | 2021-07-23 | 2021-08-27 | 25
121786333 | 1346 | PGE | 94608 | NEM | EXPNEM | IA in Progress | Solar PV | 91.69 |  | 2021-07-23 |  | 2021-08-18 | 2021-08-02 | 2021-08-02 | 6 | 2021-08-21 | 20 | 2021-09-29 | 26 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | 2021-12-01 | 42 |  |  |  |  | 2021-07-23 | 2021-08-18 | 2021-07-23 | 2021-09-07 | 31 |  |  |  |  | 2021-12-29 | [17 empty] | 2021-12-29 | 2021-12-29 | 0
121786720 | 1347 | PGE | 94558 | NEM | EXPNEM | Withdrawn | Solar PV | 600 |  | 2021-07-23 |  | 2021-11-08 | 2021-08-03 | 2021-08-03 | 7 | [29 empty] | 2021-07-23 | 2021-08-03 | 2021-07-23 | 2021-08-04 | 8
121787477 | 1348 | PGE | 94030 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 45.226 |  | 2021-07-23 |  | 2021-08-03 | 2021-08-03 | 2021-08-03 | 7 | 2021-08-16 | 16 | 2021-08-16 | 0 | [34 empty] | 2021-08-16 | 2021-08-16 | 0 | [15 empty] | 2021-08-16 |  |  | 2021-08-16 |  | 2021-08-16 | 0
121787561 | 1349 | PGE | 93309 | NEM | VNEM | Application Review in Progress | Solar PV | 100 |  | 2021-07-23 |  | 2021-07-26 | 2021-07-26 | 2021-07-26 | 1
121789750 | 1350 | PGE | 94028 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 37.95 |  | 2021-07-24 |  |  | 2021-08-03 | 2021-08-03 | 6 | 2021-08-03 | 6 | 2021-08-05 | 2 | [34 empty] | 2021-08-05 | 2021-08-05 | 0 | [15 empty] | 2021-08-05 |  |  | 2021-08-05 |  | 2021-08-05 | 0
121795009 | 1351 | PGE | 94503 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.428 |  | 2021-07-26 |  |  | 2021-08-03 | 2021-08-03 | 6 | 2021-08-03 | 6 | 2021-08-05 | 2 | [34 empty] | 2021-08-05 | 2021-08-05 | 0 | [15 empty] | 2021-08-05 |  |  | 2021-08-05 |  | 2021-08-05 | 0
121795306 | 1352 | PGE | 95403 | NEM | EXPNEM | Commercial | Solar PV | 41.882 |  | 2021-07-26 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 7 | 2021-08-18 | 17 | 2021-09-08 | 14 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-09-13 | 3 | [13 empty] | 2021-10-26 | 2021-11-03 | 6 | [15 empty] | 2021-10-26 | 2021-10-27 | 1 | 2021-11-03 |  | 2021-11-04 | 1
121797033 | 1353 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 32.858 |  | 2021-07-26 |  |  | 2021-08-04 | 2021-08-04 | 7 | 2021-08-04 | 7 | 2021-08-17 | 9 | [15 empty] | 2021-08-17 | 2021-08-18 | 1 | 2021-08-18 | 2021-09-17 | 21 |  |  |  |  | 2021-07-26 | 2021-08-05 | 2021-07-26 | 2021-08-17 | 16 |  |  |  |  | 2021-11-04 | 2021-11-14 | 5 | [15 empty] | 2021-11-04 | 2021-11-04 | 0 | 2021-11-14 |  | 2021-11-15 | 0
121797187 | 1354 | PGE | 95403 | NEM | EXPNEM | Commercial | Solar PV | 62.5 |  | 2021-07-26 |  | 2021-08-03 | 2021-08-03 | 2021-08-03 | 6 | 2021-09-01 | 27 | 2021-09-22 | 14 | [15 empty] | 2021-09-22 | 2021-09-22 | 0 | 2021-09-22 | 2021-09-24 | 2 | [13 empty] | 2021-11-02 | 2021-11-10 | 6 | [15 empty] | 2021-11-02 | 2021-11-02 | 0 | 2021-11-10 |  | 2021-11-18 | 5
121798062 | 1355 | PGE | 95932 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-07-26 |  | 2021-08-10 | 2021-08-03 | 2021-08-03 | 6 | 2021-08-13 | 14 | 2021-08-31 | 12 | [15 empty] | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 | 2021-12-29 | 82 | [13 empty] | 2021-12-30 | [17 empty] | 2021-12-30 | 2021-12-31 | 1
121798064 | 1356 | PGE | 93622 | NEM | EXPNEM | Study in Progress | Solar PV | 816 |  | 2021-07-26 |  | 2021-08-09 | 2021-08-09 | 2021-08-09 | 10 | 2021-09-08 | 31 | 2021-09-29 | 15 | 2021-09-29 | 2021-11-03 | 25 | 2021-09-08 | 2021-12-06 | 60 | 2021-12-06 | [23 empty] | 2021-09-10
121799926 | 1357 | PGE | 93610 | NEM | EXPNEM | Implementation | Solar PV | 33.249 |  | 2021-07-26 |  | 2021-08-18 | 2021-08-04 | 2021-08-04 | 7 | 2021-08-24 | 21 | 2021-11-10 | 55 | [15 empty] | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | 2021-12-02 | 13 |  |  |  |  | 2021-07-26 | 2021-08-24 | 2021-07-26 | 2021-09-08 | 31 |  |  |  |  | 2021-12-28 | [17 empty] | 2021-12-28 | 2021-12-28 | 0
121800454 | 1358 | PGE | 95203 | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 |  | 2021-07-26 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 7 | 2021-08-06 | 9 | 2021-08-19 | 9 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19
121800511 | 1359 | PGE | 95442 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.199 |  | 2021-07-26 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 7
121801686 | 1360 | PGE | 94025 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 225 |  | 2021-07-27 |  |  | 2021-08-03 | 2021-08-03 | 5 | 2021-08-03 | 5
121801958 | 1361 | PGE | 94040 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 40.1 |  | 2021-07-27 |  | 2021-08-02 | 2021-08-02 | 2021-08-02 | 4
121802035 | 1362 | PGE | 94022 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 48.766 |  | 2021-07-27 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 6
121802186 | 1363 | PGE | 95677 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2581.081 |  | 2021-07-27 | 2021-07-27 |  | 2021-07-27 | 2021-07-27 | 0 | 2021-08-25 | 21 | [5 empty] | 2021-08-25 | 2021-09-23 | 20 | 2021-09-23 | 2021-09-23 | 0 | 2021-09-30 |  |  | 2021-09-23 | 2021-09-24 | 1
121802407 | 1364 | PGE | 95060 | NEM | EXPNEM | Commercial | Solar PV | 71.669 |  | 2021-07-27 |  | 2021-08-02 | 2021-08-02 | 2021-08-02 | 4 | 2021-08-24 | 20 | 2021-09-08 | 10 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-11-19 | 51 | [13 empty] | 2021-11-23 | 2021-12-07 | 8 | [15 empty] | 2021-11-23 | 2021-11-23 | 0 | 2021-12-07 |  | 2021-12-13 | 4
121802615 | 1365 | PGE | 93301 | NEM | EXPNEM | Withdrawn | Solar PV | 34.9 |  | 2021-07-27 |  | 2021-08-09 | 2021-08-09 | 2021-08-09 | 9 | 2021-09-28 | 44
121803652 | 1366 | PGE | 94806 | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-07-27 | 2021-07-27 |  | 2021-07-27 | 2021-07-27 | 0 | 2021-08-11 | 11 | 2021-09-08 | 19 | [15 empty] | 2021-09-08 | 2021-09-23 | 11 | 2021-09-23 | 2021-10-18 | 17
121804584 | 1367 | PGE | 93301 | NEM | EXPNEM | Withdrawn | Solar PV | 39.045 |  | 2021-07-27 |  | 2021-08-09 | 2021-08-09 | 2021-08-09 | 9 | 2021-09-13 | 33 | 2021-09-30 | 13 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | 2021-11-15 | 31
121805167 | 1368 | PGE | 94539 | NEM | EXPNEM | Commercial | Solar PV | 57.71 |  | 2021-07-27 |  | 2021-08-03 | 2021-08-03 | 2021-08-03 | 5 | 2021-08-05 | 7 | 2021-08-17 | 8 | [15 empty] | 2021-08-17 | 2021-08-17 | 0 | 2021-08-17 | 2021-08-17 | 0 | [13 empty] | 2021-08-20 | 2021-08-31 | 7 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-31 |  | 2021-09-07 | 4
121805355 | 1369 | PGE | 93635 | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-07-27 |  |  | 2021-08-09 | 2021-08-09 | 9 | 2021-08-09 | 9 | [17 empty] | 2021-09-10 | 2021-09-17 | 5 | 2021-09-17 | 2021-09-17 | 0 |  |  |  |  | 2021-07-27 |  | 2021-07-27 |  |  | 2021-08-13 | [6 empty] | 2021-11-08 |  | 45
121806780 | 1370 | PGE | 95991 | NEM | NEMMT | IA in Progress | ENGN, Solar PV | 359.2 |  | 2021-07-28 |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 10 | 2021-10-09 | 51 | 2021-10-29 | 14 | 2021-10-29 | 2021-12-08 | 25 | [12 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | [7 empty] | 2021-10-09 | 2021-10-09 | 2021-10-21 | 8
121807295 | 1371 | PGE | 95461 | NEM | EXPNEM | Study in Progress | Solar PV | 172.8 |  | 2021-07-28 |  |  | 2021-08-03 | 2021-08-03 | 4 | 2021-08-03 | 4 | 2021-08-20 | 13 | 2021-08-20 | 2021-09-27 | 25 | 2021-10-04 | 2021-10-26 | 16 | 2021-10-26
121807833 | 1372 | PGE | 95912 | NEM | EXPNEM | Withdrawn | Solar PV | 60.6 |  | 2021-07-28 |  | 2021-08-03 | 2021-08-03 | 2021-08-03 | 4
121808444 | 1373 | PGE | 94010 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.49 |  | 2021-07-28 |  | 2021-11-12 | 2021-08-05 | 2021-08-05 | 6
121808551 | 1374 | PGE | 93646 | NEM | EXPNEM | Implementation | Solar PV | 50 |  | 2021-07-28 |  |  | 2021-08-09 | 2021-08-09 | 8 | 2021-08-09 | 8 | 2021-09-17 | 28 | [15 empty] | 2021-09-17 | 2021-10-06 | 13 | 2021-10-06 | 2021-10-06 | 0 |  |  |  |  | 2021-07-28 |  | 2021-07-28 |  |  | 2021-08-13 | [6 empty] | 2021-11-01 | 2021-11-30 | 18
121808625 | 1375 | PGE | 94010 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 43.625 |  | 2021-07-28 |  | 2021-09-13 | 2021-08-05 | 2021-08-05 | 6 | 2021-09-24 | 41
121808969 | 1376 | PGE | 93646 | NEM | EXPNEM | Implementation | Solar PV | 30.354 |  | 2021-07-28 |  |  | 2021-08-09 | 2021-08-09 | 8 | 2021-08-09 | 8 | 2021-08-23 | 10 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23 | 2021-09-22 | 21 |  |  |  |  | 2021-07-28 |  | 2021-07-28 |  |  | 2021-08-13 | [6 empty] | 2021-09-17 | 2021-11-29 | 48
121809226 | 1377 | PGE | 94010 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-07-28 |  | 2021-08-05 | 2021-08-05 | 2021-08-05 | 6 | 2021-08-19 | 16 | 2021-08-22 | 1 | [34 empty] | 2021-08-22 | 2021-08-22 | 0 | [15 empty] | 2021-08-22 |  |  | 2021-08-22 |  | 2021-08-22 | 0
121812895 | 1378 | PGE | 94085 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 125.956 |  | 2021-07-29 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 4 | [29 empty] | 2021-07-29 |  | 2021-07-29
121813359 | 1379 | PGE | 94035 | Non-NEM | Non-Export | Study in Progress | Solar PV | 3891.183 |  | 2021-07-29 | 2021-07-30 |  | 2021-07-30 | 2021-07-30 | 1 | 2021-09-01 | 24 | [5 empty] | 2021-09-01 | 2021-09-30 | 20 | 2021-09-30 | 2021-09-30 | 0 | 2021-10-04 |  |  | 2021-09-30 | 2021-09-30 | 0
121814219 | 1380 | PGE | 94526 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-07-29 |  |  | 2021-08-06 | 2021-08-06 | 6 | 2021-08-06 | 6 | 2021-08-09 | 1 | [34 empty] | 2021-08-09 | 2021-08-09 | 0 | [15 empty] | 2021-08-09 |  |  | 2021-08-09 |  | 2021-08-09 | 0
121814237 | 1381 | PGE | 95970 | NEM | EXPNEM | Study in Progress | Solar PV | 244.488 |  | 2021-07-29 |  | 2021-08-30 | 2021-08-05 | 2021-08-05 | 5 | 2021-09-07 | 27 | 2021-09-27 | 14 | 2021-09-27 | 2021-10-22 | 19 | 2021-10-26 | 2021-11-18 | 16 | 2021-11-18
121814318 | 1382 | PGE | 93635 | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-07-29 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 4 | 2021-08-11 | 9 | 2021-08-27 | 12 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-09-02 | 4 |  |  |  |  | 2021-07-29 | 2021-08-11 | 2021-07-29 | 2021-09-07 | 27 | [7 empty] | 2021-11-08 |  | 45
121814594 | 1383 | PGE | 94561 | NEM | EXPNEM | Withdrawn | Solar PV | 35.487 |  | 2021-07-29 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 4 | 2021-08-09 | 7
121814940 | 1384 | PGE | 93301 | NEM | EXPNEM | Implementation | Solar PV | 407.612 |  | 2021-07-29 |  | 2021-08-18 | 2021-08-04 | 2021-08-04 | 4 | 2021-10-20 | 58 | 2021-10-27 | 5 | [15 empty] | 2021-10-27 | 2021-10-27 | 0 | 2021-10-27 | 2021-11-11 | 10 |  |  |  |  | 2021-07-29 |  | 2021-07-29
121815160 | 1385 | PGE | 94574 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-07-29 |  | 2021-08-06 | 2021-08-06 | 2021-08-06 | 6 | 2021-08-20 | 16 | 2021-09-01 | 8 | [34 empty] | 2021-09-01 | 2021-09-01 | 0 | [15 empty] | 2021-09-01 |  |  | 2021-09-01 |  | 2021-09-01 | 0
121815216 | 1386 | PGE | 93203 | NEM | EXPNEM | Implementation | Solar PV | 489.177 |  | 2021-07-29 |  | 2021-08-17 | 2021-08-05 | 2021-08-05 | 5 | 2021-10-20 | 58 | 2021-11-02 | 9 | [15 empty] | 2021-11-02 | 2021-11-02 | 0 | 2021-11-02 | 2021-11-15 | 8 |  |  |  |  | 2021-07-29 |  | 2021-07-29
121819927 | 1387 | PGE | 95955 | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-07-30 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 3 | 2021-08-06 | 5 | 2021-08-25 | 13 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | [6 empty] | 2021-07-30 | 2021-11-18 | 2021-07-30 | 2021-12-08 | 89
121820120 | 1388 | PGE | 95322 | NEM | EXPNEM | IA in Progress | Solar PV | 312.5 |  | 2021-07-30 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 3 | 2021-08-18 | 13 | 2021-09-03 | 12 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-10-07 | 23 |  |  |  |  | 2021-07-30 | 2021-12-20 | 2021-07-30
121820644 | 1389 | PGE | 94609 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.97 |  | 2021-07-30 |  |  | 2021-08-07 | 2021-08-07 | 5 | 2021-08-07 | 5 | 2021-08-07 | 0 | [34 empty] | 2021-08-07 | 2021-08-07 | 0 | [15 empty] | 2021-08-07 |  |  | 2021-08-07 |  | 2021-08-07 | 0
121821877 | 1390 | PGE | 93309 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-07-30 |  | 2021-08-07 | 2021-08-07 | 2021-08-07 | 5 | 2021-08-24 | 17 | 2021-08-26 | 2 | [34 empty] | 2021-08-26 | 2021-08-26 | 0 | [15 empty] | 2021-08-26 |  |  | 2021-08-26 |  | 2021-08-26 | 0
121822650 | 1391 | PGE | 93422 | NEM | NEMMT | Study in Progress | ENGN, Solar PV | 1264.8 |  | 2021-07-30 | 2021-08-03 |  | 2021-08-03 | 2021-08-03 | 2 | 2021-08-18 | 13 | 2021-09-16 | 20 | 2021-09-30 | 2021-12-10 | 48
121826722 | 1392 | PGE | 95407 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-08-01 |  | 2021-08-21 | 2021-08-11 | 2021-08-11 | 7 | 2021-08-24 | 16 | 2021-09-15 | 15 | [15 empty] | 2021-09-15 | 2021-09-16 | 1 | 2021-09-16 | 2021-11-15 | 41 | [13 empty] | 2021-11-23 | 2021-12-02 | 5 | [15 empty] | 2021-11-23 | 2021-11-23 | 0 | 2021-12-02 |  | 2021-12-09 | 5
121829677 | 1393 | PGE | 94506 | NEM | EXPNEM | IA in Progress | Solar PV | 41.094 |  | 2021-08-02 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 2 | 2021-08-09 | 5 | 2021-08-30 | 15 | [15 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-09-02 | 3
121829885 | 1394 | PGE | 95650 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 35.116 |  | 2021-08-02 |  |  | 2021-08-09 | 2021-08-09 | 5 | 2021-08-09 | 5 | 2021-08-11 | 2
121830404 | 1395 | PGE | 95207 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100 |  | 2021-08-02 |  | 2021-08-06 | 2021-08-04 | 2021-08-04 | 2 | 2021-08-09 | 5 | 2021-09-10 | 23 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | [6 empty] | 2021-08-02 | 2021-10-08 | 2021-08-02 | 2021-10-15 | 53 |  | 2021-10-18 | 2021-10-18 | 0 |  |  |  | 2021-09-08 |  | 88
121833129 | 1396 | PGE | 93905 | NEM | EXPNEM | Commercial | Solar PV | 140.252 |  | 2021-08-02 |  | 2021-08-09 | 2021-08-04 | 2021-08-04 | 2 | 2021-08-13 | 9 | 2021-08-31 | 12 | [15 empty] | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 | 2021-10-29 | 42 |  |  |  |  | 2021-08-02 | 2021-08-18 | 2021-08-02 | 2021-09-07 | 25 |  |  |  |  | 2021-11-03 | 2021-11-12 | 6 | [15 empty] | 2021-11-03 | 2021-11-04 | 1 | 2021-11-12 |  | 2021-11-15 | 1
121833135 | 1397 | PGE | 93401 | NEM | EXPNEM | IA in Progress | Solar PV | 101.57 |  | 2021-08-02 |  | 2021-08-05 | 2021-08-05 | 2021-08-05 | 3 | 2021-08-11 | 7 | 2021-08-27 | 12 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-09-10 | 9 |  |  |  |  | 2021-08-02 | 2021-10-12 | 2021-08-02 | 2021-10-15 | 53 |  |  |  |  | 2021-12-13 | [17 empty] | 2021-12-13 | 2021-12-13 | 0
121833539 | 1398 | PGE | 94578 | NEM | EXPNEM | IA in Progress | Solar PV | 733.3 |  | 2021-08-02 |  | 2021-08-18 | 2021-08-04 | 2021-08-04 | 2 | 2021-08-28 | 19 | 2021-09-08 | 6 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | [6 empty] | 2021-08-02 |  | 2021-08-02
121833944 | 1399 | PGE | 95765 | NEM | EXPNEM | Study in Progress | Solar PV | 500 |  | 2021-08-02 |  | 2021-11-22 | 2021-08-11 | 2021-08-11 | 7 | 2021-12-21 | 97 | [27 empty] | 2021-08-02 | 2021-11-22 | 2021-08-02 | 2021-12-15 | 93
121838661 | 1400 | PGE | 94558 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-08-03 |  |  | 2021-08-05 | 2021-08-05 | 2 | 2021-08-05 | 2 | 2021-08-24 | 13 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | 2021-12-20 | 80 |  |  |  |  | 2021-08-03 | 2021-08-05 | 2021-08-03 | 2021-08-13 | 8 |  |  |  |  | 2021-12-23 | 2021-12-30 | 5 | [15 empty] | 2021-12-23 | 2021-12-23 | 0 | 2021-12-30 |  | 2021-12-31 | 1
121839530 | 1401 | PGE | 95943 | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 |  | 2021-08-03 |  | 2021-11-19 | 2021-08-16 | 2021-08-16 | 9
121839668 | 1402 | PGE | 95317 | NEM | EXPNEM | IA in Progress | Solar PV | 840 |  | 2021-08-03 |  | 2021-08-17 | 2021-08-17 | 2021-08-17 | 10 | 2021-09-08 | 25 | 2021-09-29 | 15 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | [6 empty] | 2021-08-03 |  | 2021-08-03 |  |  | 2021-09-10
121841040 | 1403 | PGE | 93907 | NEM | EXPNEM | IA in Progress | Solar PV | 125 |  | 2021-08-04 |  | 2021-08-06 | 2021-08-06 | 2021-08-06 | 2 | 2021-08-16 | 8 | 2021-10-12 | 40 | [15 empty] | 2021-10-12 | 2021-10-12 | 0 | 2021-10-12 | 2021-10-12 | 0 |  |  |  |  | 2021-08-04 | 2021-10-05 | 2021-08-04 | 2021-10-18 | 52
121841534 | 1404 | PGE | 93955 | NEM | EXPNEM | Implementation | Solar PV | 34.179 |  | 2021-08-04 |  |  | 2021-08-10 | 2021-08-10 | 4 | 2021-08-26 | 16 | 2021-09-24 | 20 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | 2021-10-04 | 6 | [13 empty] | 2021-12-14 | 2021-12-23 | 7 | [15 empty] | 2021-12-14 | 2021-12-15 | 1 | 2021-12-23 | 2021-12-23 |  | 0 |  |  | 97
121842236 | 1405 | PGE | 93710 | Non-NEM | Non-Export | IA in Progress | Solar PV | 3500 |  | 2021-08-04 | 2021-08-10 |  | 2021-08-04 | 2021-08-04 | 0 | 2021-09-01 | 20 | 2021-09-23 | 15 | 2021-10-28 | 2021-11-30 | 20 | [12 empty] | 2021-11-30 | 2021-11-30 | 0 | 2021-11-30 | [6 empty] | 2021-08-04 | 2021-10-28 | 2021-08-04 | 2021-11-05 | 66
121843079 | 1406 | PGE | 94041 | NEM | EXPNEM | IA in Progress | Solar PV | 81.967 |  | 2021-08-04 |  | 2021-08-10 | 2021-08-10 | 2021-08-10 | 4 | 2021-08-27 | 17 | 2021-10-11 | 30 | [15 empty] | 2021-10-11 | 2021-10-11 | 0 | 2021-10-11 | 2021-11-16 | 25 |  |  |  |  | 2021-08-04 | 2021-09-27 | 2021-08-04 | 2021-10-06 | 44 |  |  |  |  | 2021-12-30 | [17 empty] | 2021-12-30 | 2021-12-30 | 0
121843105 | 1407 | PGE | 95060 | NEM | EXPNEM | Commercial | Solar PV | 48.973 |  | 2021-08-04 |  | 2021-08-16 | 2021-08-10 | 2021-08-10 | 4 | 2021-08-24 | 14 | 2021-09-08 | 10 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-09-09 | 1 | [13 empty] | 2021-10-01 | 2021-11-03 | 23 | [15 empty] | 2021-10-01 | 2021-10-04 | 1 | 2021-11-03 |  | 2021-11-08 | 3
121844567 | 1408 | PGE | 93727 | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 |  | 2021-08-04 |  | 2021-08-24 | 2021-08-17 | 2021-08-17 | 9
121844627 | 1409 | PGE | 93638 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 38.4 |  | 2021-08-04 |  | 2021-08-30 | 2021-08-06 | 2021-08-06 | 2 | 2021-08-31 | 19 | 2021-09-17 | 12 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | [6 empty] | 2021-08-04 | 2021-10-13 | 2021-08-04 | 2021-10-22 | 56
121844678 | 1410 | PGE | 93230 | NEM | EXPNEM | Implementation | Solar PV | 125 |  | 2021-08-04 |  | 2021-08-17 | 2021-08-17 | 2021-08-17 | 9 | 2021-09-30 | 40 | 2021-10-19 | 13 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-10-29 | 8 |  |  |  |  | 2021-08-04 | 2021-09-30 | 2021-08-04 | 2021-10-14 | 50
121844989 | 1411 | PGE | 95317 | NEM | EXPNEM | Implementation | Solar PV | 120 |  | 2021-08-04 |  | 2021-08-10 | 2021-08-10 | 2021-08-10 | 4 | 2021-08-11 | 5 | 2021-08-31 | 14 | [15 empty] | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 | 2021-09-09 | 6 |  |  |  |  | 2021-08-04 | 2021-08-11 | 2021-08-04 | 2021-08-24 | 14
121845137 | 1412 | PGE | 93224 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 26331.652 |  | 2021-08-04 | 2021-08-10 |  | 2021-08-04 | 2021-08-04 | 0 | 2021-09-09 | 25 | [5 empty] | 2021-09-09
121845177 | 1413 | PGE | 95334 | NEM | EXPNEM | IA in Progress | Solar PV | 551.02 |  | 2021-08-04 |  | 2021-08-24 | 2021-08-11 | 2021-08-11 | 5 | 2021-09-17 | 31 | 2021-10-30 | 30 | [15 empty] | 2021-10-30 | 2021-10-29 | 0 | 2021-10-29 | [6 empty] | 2021-08-04 | 2021-10-05 | 2021-08-04 | 2021-10-18 | 52
121845210 | 1414 | PGE | 93907 | NEM | EXPNEM | IA in Progress | Solar PV | 225 |  | 2021-08-04 |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 5 | 2021-08-18 | 10 | 2021-10-12 | 38 | [15 empty] | 2021-10-12 | 2021-10-12 | 0 | 2021-10-12 | 2021-10-18 | 4 |  |  |  |  | 2021-08-04 | 2021-09-29 | 2021-08-04 | 2021-10-15 | 51
121848289 | 1415 | PGE | 95932 | NEM | EXPNEM | Application Accepted | Solar PV | 199.295 |  | 2021-08-05 |  | 2021-10-21 | 2021-08-11 | 2021-08-11 | 4 | 2021-11-03 | 63 | 2021-11-03 | 1 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | [6 empty] | 2021-08-05 | 2021-09-17 | 2021-08-05 | 2021-09-22 | 33
121848703 | 1416 | PGE | 93230 | NEM | EXPNEM | Implementation | Solar PV | 150 |  | 2021-08-05 |  | 2021-08-16 | 2021-08-16 | 2021-08-16 | 7 | 2021-09-30 | 39 | 2021-10-15 | 11 | [15 empty] | 2021-10-15 | 2021-10-15 | 0 | 2021-10-15 | 2021-10-29 | 10 |  |  |  |  | 2021-08-05 | 2021-09-30 | 2021-08-05 | 2021-10-15 | 50
121848713 | 1417 | PGE | 95932 | NEM | EXPNEM | IA in Progress | Solar PV | 200 |  | 2021-08-05 |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 4 | 2021-08-18 | 9 | 2021-09-23 | 25 | [15 empty] | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | [6 empty] | 2021-08-05 | 2021-10-18 | 2021-08-05 | 2021-11-01 | 61
121848826 | 1418 | PGE | 95932 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-08-05 |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 4 | 2021-08-19 | 10 | 2021-10-06 | 33 | [15 empty] | 2021-10-06 | 2021-10-06 | 0 | 2021-10-06 | 2021-10-19 | 9 |  |  |  |  | 2021-08-05 | 2021-08-11 | 2021-08-05 | 2021-08-24 | 13
121850773 | 1419 | PGE | 94574 | NEM | EXPNEM | Study in Progress | Solar PV | 41.47 |  | 2021-08-05 |  | 2021-08-21 | 2021-08-11 | 2021-08-11 | 4 | [41 empty] | 2021-08-05 | 2021-11-16 | 71
121850835 | 1420 | PGE | 93654 | NEM | EXPNEM | IA in Progress | Solar PV | 778.129 |  | 2021-08-05 |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 4 | 2021-08-16 | 7 | 2021-09-03 | 14 | 2021-09-03 | 2021-10-04 | 20 | [12 empty] | 2021-10-04 | 2021-10-05 | 1 | 2021-10-05 | 2021-10-13 | 6 |  |  |  |  | 2021-08-05 |  | 2021-08-05
121851470 | 1421 | PGE | 94704 | NEM | EXPNEM | IA in Progress | Solar PV | 204 |  | 2021-08-05 |  | 2021-08-19 | 2021-08-19 | 2021-08-19 | 10 | 2021-09-13 | 26 | 2021-11-09 | 41 | 2021-11-09 | 2021-12-07 | 17 | [12 empty] | 2021-12-07 | 2021-12-07 | 0 | 2021-12-07 | [6 empty] | 2021-08-05 |  | 2021-08-05 |  |  | 2021-10-14
121851471 | 1422 | PGE | 94589 | NEM | EXPNEM | Study in Progress | Solar PV | 532 |  | 2021-08-05 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 9 | 2021-11-17 | 72 | [27 empty] | 2021-08-05 |  | 2021-08-05 |  |  | 2021-12-14
121853279 | 1423 | PGE | 93380 | Non-NEM | RESBCT | Withdrawn | Solar PV | 4000 |  | 2021-08-06 | 2021-08-10 |  | 2021-08-06 | 2021-08-06 | 0
121854731 | 1424 | PGE | 95203 | NEM | EXPNEM | Commercial | Solar PV | 60 |  | 2021-08-06 |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 3 | 2021-09-03 | 20 | 2021-09-27 | 15 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-12 | 11 | [13 empty] | 2021-10-15 | 2021-10-22 | 5 | [15 empty] | 2021-10-15 | 2021-10-15 | 0 | 2021-10-22 |  | 2021-10-28 | 4
121854971 | 1425 | PGE | 93637 | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-08-06 |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 3 | 2021-08-16 | 6 | 2021-09-03 | 14 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-10 | 4 | [13 empty] | 2021-12-27 | [17 empty] | 2021-12-27 | 2021-12-27 | 0
121855212 | 1426 | PGE | 93654 | NEM | VNEMMASH | IA in Progress | Solar PV | 47.1 |  | 2021-08-06 |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 3 | 2021-09-13 | 25 | 2021-09-16 | 3 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | [6 empty] | 2021-08-06 | 2021-10-28 | 2021-08-06 | 2021-11-05 | 64 |  | 2021-11-05 | 2021-11-05 | 0
121856930 | 1427 | PGE | 94506 | NEM | EXPNEM | Withdrawn | Solar PV | 250 |  | 2021-08-06 |  |  | 2021-08-13 | 2021-08-13 | 5 | 2021-08-24 | 12 | 2021-09-03 | 8 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-07 | 1 |  |  |  |  | 2021-08-06 | 2021-08-24 | 2021-08-06 | 2021-09-07 | 21
121857244 | 1428 | PGE | 95618 | NEM | EXPNEM | Commercial | Solar PV | 81.587 |  | 2021-08-06 |  | 2021-08-20 | 2021-08-11 | 2021-08-11 | 3 | 2021-08-27 | 15 | 2021-09-20 | 15 | [15 empty] | 2021-09-20 | 2021-09-20 | 0 | 2021-09-20 | 2021-09-21 | 1 | [13 empty] | 2021-10-11 | 2021-10-13 | 2 | [15 empty] | 2021-10-11 | 2021-10-11 | 0 | 2021-10-13 |  | 2021-10-19 | 4
121857379 | 1429 | PGE | 95607 | NEM | EXPNEM | Application Review in Progress | Solar PV | 31.337 |  | 2021-08-06 |  | 2021-08-12 | 2021-08-12 | 2021-08-12 | 4
121863035 | 1430 | PGE | 95482 | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 500.5 |  | 2021-08-09 |  | 2021-08-20 | 2021-08-20 | 2021-08-20 | 9 | 2021-09-10 | 23 | 2021-10-27 | 33 | [15 empty] | 2021-11-08 | 2021-11-10 | 2 | 2021-11-10 | 2021-11-17 | 4
121863112 | 1431 | PGE | 94022 | NEM | EXPNEM | Application Review in Progress | Solar PV | 152.592 |  | 2021-08-09 |  | 2021-11-10 | 2021-08-12 | 2021-08-12 | 3 | [29 empty] | 2021-08-09 | 2021-11-09 | 2021-08-09 | 2021-11-29 | 76
121863116 | 1432 | PGE | 93446 | NEM | EXPNEM | Commercial | Solar PV | 37.658 |  | 2021-08-09 |  | 2021-08-17 | 2021-08-17 | 2021-08-17 | 6 | 2021-08-23 | 10 | 2021-09-07 | 10 | [15 empty] | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-09-09 | 2 |  |  |  |  | 2021-08-09 |  | 2021-08-09 | [6 empty] | 2021-10-22 | 2021-11-01 | 6 | [15 empty] | 2021-10-22 | 2021-10-22 | 0 | 2021-11-01 |  | 2021-11-01 | 0
121864229 | 1433 | PGE | 94583 | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-08-09 |  | 2021-08-12 | 2021-08-12 | 2021-08-12 | 3 | 2021-08-17 | 6 | 2021-10-05 | 34 | [15 empty] | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | [6 empty] | 2021-08-09 | 2021-08-12 | 2021-08-09 | 2021-08-24 | 11
121864242 | 1434 | PGE | 94022 | NEM | EXPNEM | Application Review in Progress | Solar PV | 221.897 |  | 2021-08-09 |  | 2021-11-10 | 2021-08-12 | 2021-08-12 | 3 | [29 empty] | 2021-08-09 | 2021-11-10 | 2021-08-09 | 2021-12-01 | 78
121865289 | 1435 | PGE | 95667 | Non-NEM | Non-Export | IA in Progress | Storage | 210 |  | 2021-08-09 | 2021-08-10 |  | 2021-08-09 | 2021-08-09 | 0 | 2021-09-08 | 21 | 2021-09-29 | 15 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | 2021-12-28 | 61
121865340 | 1436 | PGE | 94089 | NEM | EXPNEM | Study in Progress | Solar PV | 235.573 |  | 2021-08-09 |  | 2021-11-23 | 2021-08-12 | 2021-08-12 | 3 | 2021-12-08 | 83 | 2021-12-28 | 14 | 2021-12-28
121865417 | 1437 | PGE | 94949 | NEM | EXPNEM | IA in Progress | Solar PV | 199.8 |  | 2021-08-09 |  | 2021-08-19 | 2021-08-12 | 2021-08-12 | 3 | 2021-08-25 | 12 | 2021-09-16 | 15 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | 2021-09-21 | 3 |  |  |  |  | 2021-08-09 | 2021-08-12 | 2021-08-09 | 2021-08-24 | 11
121866144 | 1438 | PGE | 93610 | NEM | EXPNEM | Implementation | Solar PV | 220 |  | 2021-08-09 |  | 2021-08-23 | 2021-08-23 | 2021-08-23 | 10 | 2021-09-15 | 26 | 2021-10-06 | 15 | [15 empty] | 2021-10-06 | 2021-10-06 | 0 | 2021-10-06 | 2021-10-21 | 11 |  |  |  |  | 2021-12-27 | 2021-12-27 | 2021-12-27
121866731 | 1439 | PGE | 94597 | NEM | EXPNEM | Commercial | Solar PV | 31.062 |  | 2021-08-09 |  | 2021-08-20 | 2021-08-20 | 2021-08-20 | 9 | 2021-08-25 | 12 | 2021-08-30 | 3 | [34 empty] | 2021-08-31 | 2021-09-08 | 5 | [15 empty] | 2021-08-31 | 2021-09-01 | 1 | 2021-09-08 |  | 2021-09-08 | 0
121877548 | 1440 | PGE | 94526 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-08-10 |  | 2021-09-15 | 2021-08-10 | 2021-08-10 | 0 | 2021-09-24 | 32 | 2021-09-27 | 1 | [34 empty] | 2021-09-27 | 2021-09-27 | 0 | [15 empty] | 2021-09-27 |  |  | 2021-09-27 |  | 2021-09-27 | 0
121878137 | 1441 | PGE | 93720 | NEM | EXPNEM | Implementation | Solar PV | 720.8 |  | 2021-08-10 |  | 2021-08-20 | 2021-08-20 | 2021-08-20 | 8 | 2021-08-23 | 9 | 2021-09-01 | 7 | [15 empty] | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01 | 2021-09-15 | 9 |  |  |  |  | 2021-08-10 | 2021-08-23 | 2021-08-10 | 2021-09-07 | 19
121880085 | 1442 | PGE | 93380 | Non-NEM | RESBCT | Withdrawn | Solar PV | 4000 |  | 2021-08-10 | 2021-08-11 |  | 2021-08-11 | 2021-08-11 | 1
121880104 | 1443 | PGE | 95961 | NEM | EXPNEM | Study in Progress | Solar PV | 132 |  | 2021-08-10 |  |  | 2021-08-13 | 2021-08-13 | 3 | 2021-08-13 | 3 | 2021-09-03 | 15 | 2021-09-03 | 2021-10-07 | 23 | 2021-10-12 | 2021-11-09 | 20 | 2021-11-09 | [18 empty] | 2021-08-10 |  | 2021-08-10
121880753 | 1444 | PGE | 95935 | NEM | EXPNEM | Study in Progress | Solar PV | 86.909 |  | 2021-08-10 |  | 2021-08-20 | 2021-08-16 | 2021-08-16 | 4 | 2021-08-24 | 10 | 2021-09-10 | 12 | 2021-09-10 | 2021-10-09 | 20 | 2021-11-09 | 2021-12-07 | 17 | 2021-12-07
121881100 | 1445 | PGE | 95901 | NEM | EXPNEM | IA in Progress | Solar PV | 36 |  | 2021-08-10 |  | 2021-08-16 | 2021-08-16 | 2021-08-16 | 4 | 2021-08-20 | 8 | 2021-09-08 | 12 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08
121882442 | 1446 | PGE | 95453 | NEM | VNEM | IA in Progress | Solar PV | 52.161 |  | 2021-08-10 |  | 2021-08-24 | 2021-08-24 | 2021-08-24 | 10 | 2021-09-29 | 35 | 2021-10-20 | 15 | [15 empty] | 2021-10-20 | 2021-11-10 | 15 | 2021-11-10 | 2021-11-16 | 3 |  |  |  |  | 2021-08-10 | 2021-11-10 | 2021-08-10 | 2021-12-15 | 87 |  | 2021-12-29 | 2021-12-30 | 1
121882491 | 1447 | PGE | 95453 | NEM | VNEM | IA in Progress | Solar PV | 46.2 |  | 2021-08-10 |  | 2021-08-24 | 2021-08-24 | 2021-08-24 | 10 | 2021-09-29 | 35 | 2021-10-20 | 15 | [15 empty] | 2021-10-20 | 2021-11-10 | 15 | 2021-11-10 | 2021-11-16 | 3 |  |  |  |  | 2021-08-10 | 2021-11-10 | 2021-08-10 | 2021-12-15 | 87 |  | 2021-12-29 | 2021-12-30 | 1
121882510 | 1448 | PGE | 95453 | NEM | VNEM | IA in Progress | Solar PV | 54.292 |  | 2021-08-10 |  | 2021-08-24 | 2021-08-24 | 2021-08-24 | 10 | 2021-09-29 | 35 | 2021-11-12 | 31 | [15 empty] | 2021-11-12 | 2021-11-12 | 0 | 2021-11-12 | [6 empty] | 2021-08-10 | 2021-11-10 | 2021-08-10 | 2021-12-15 | 87 |  | 2021-12-29 | 2021-12-30 | 1
121882517 | 1449 | PGE | 95453 | NEM | VNEM | IA in Progress | Solar PV | 54.292 |  | 2021-08-10 |  | 2021-08-24 | 2021-08-24 | 2021-08-24 | 10 | 2021-09-29 | 35 | 2021-10-20 | 15 | [15 empty] | 2021-10-20 | 2021-11-10 | 15 | 2021-11-10 | 2021-11-16 | 3 |  |  |  |  | 2021-08-10 | 2021-11-10 | 2021-08-10 | 2021-12-15 | 87 |  | 2021-12-29 | 2021-12-30 | 1
121883905 | 1450 | PGE | 93309 | NEM | EXPNEM | Implementation | Solar PV | 215.388 |  | 2021-08-11 |  | 2021-08-23 | 2021-08-23 | 2021-08-23 | 8 | 2021-08-25 | 10 | 2021-09-10 | 11 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | 2021-09-17 | 5
121884706 | 1451 | PGE | 93905 | NEM | EXPNEM | Commercial | Solar PV | 86.4 |  | 2021-08-11 |  | 2021-09-03 | 2021-08-16 | 2021-08-16 | 3 | 2021-09-29 | 34 | 2021-10-27 | 20 | [15 empty] | 2021-10-27 | 2021-10-27 | 0 | 2021-10-27 | 2021-12-15 | 32 | [13 empty] | 2021-12-21 | 2021-12-28 | 5 | [15 empty] | 2021-12-21 | 2021-12-21 | 0 | 2021-12-28 |  | 2021-12-30 | 2
121885645 | 1452 | PGE | 95525 | Non-NEM | Non-Export | IA in Progress | Storage | 350 |  | 2021-08-11 | 2021-08-12 |  | 2021-08-12 | 2021-08-12 | 1 | 2021-09-01 | 15 | 2021-11-15 | 51 | [15 empty] | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | [6 empty] | 2021-08-11 |  | 2021-08-11
121887284 | 1453 | PGE | 95970 | NEM | EXPNEM | Study in Progress | Solar PV | 133.2 |  | 2021-08-11 |  | 2021-08-16 | 2021-08-16 | 2021-08-16 | 3 | 2021-08-23 | 8 | 2021-09-10 | 13 | 2021-09-10 | 2021-10-14 | 24 | 2021-10-19 | 2021-11-17 | 20 | 2021-11-17 | [18 empty] | 2021-08-11 | 2021-09-10 | 2021-08-11 | 2021-09-10 | 21
121889840 | 1454 | PGE | 94549 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.262 |  | 2021-08-12 |  | 2021-08-24 | 2021-08-24 | 2021-08-24 | 8 | 2021-10-15 | 45 | 2021-11-04 | 14 | [34 empty] | 2021-11-04 | 2021-11-04 | 0 | [15 empty] | 2021-11-04 | 2021-11-04 | 0 | 2021-11-04 |  | 2021-11-12 | 5
121890400 | 1455 | PGE | 95776 | NEM | EXPNEM | IA in Progress | Solar PV | 89.91 |  | 2021-08-12 |  |  | 2021-08-20 | 2021-08-20 | 6 | 2021-08-20 | 6 | 2021-09-08 | 12 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-10-01 | 17
121891044 | 1456 | PGE | 95912 | NEM | EXPNEM | Withdrawn | Solar PV | 125 |  | 2021-08-12 |  | 2021-08-25 | 2021-08-25 | 2021-08-25 | 9
121893860 | 1457 | PGE | 95762 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.988 |  | 2021-08-12 |  | 2021-08-25 | 2021-08-25 | 2021-08-25 | 9 | 2021-09-13 | 21 | 2021-09-14 | 1 | [34 empty] | 2021-09-14 | 2021-09-14 | 0 | [15 empty] | 2021-09-14 |  |  | 2021-09-14 |  | 2021-09-14 | 0
121896330 | 1458 | PGE | 94507 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.191 |  | 2021-08-13 |  | 2021-09-27 | 2021-08-25 | 2021-08-25 | 8
121896536 | 1459 | PGE | 94559 | NEM | EXPNEM | Application Review in Progress | Solar PV | 39.737 |  | 2021-08-13 |  | 2021-08-27 | 2021-08-27 | 2021-08-27 | 10
121896609 | 1460 | PGE | 95340 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 42.725 |  | 2021-08-13 |  | 2021-08-17 | 2021-08-17 | 2021-08-17 | 2 | 2021-09-13 | 20 | 2021-09-14 | 1 | [15 empty] | 2021-08-13 | 2021-08-13 |  | 2021-08-13 | 2021-08-13 | 1 | [13 empty] | 2021-09-14 | 2021-09-14 | 0 | [15 empty] | 2021-09-14 |  |  | 2021-09-14 |  | 2021-09-14 | 0
121897072 | 1461 | PGE | 95134 | NEM | EXPNEM | IA in Progress | Solar PV | 60.834 |  | 2021-08-13 |  | 2021-08-24 | 2021-08-23 | 2021-08-23 | 6 | 2021-08-27 | 10 | 2021-09-17 | 14 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17
121897494 | 1462 | PGE | 93401 | NEM | EXPNEM | IA in Progress | Solar PV | 200 |  | 2021-08-13 |  | 2021-12-08 | 2021-08-23 | 2021-08-23 | 6 | 2021-12-09 | 80 | 2021-12-27 | 12 | [15 empty] | 2021-12-27 | 2021-12-28 | 1 | 2021-12-28 | [6 empty] | 2021-08-13 |  | 2021-08-13
121897872 | 1463 | PGE | 95616 | NEM | EXPNEM | Commercial | Solar PV | 38.253 |  | 2021-08-13 |  | 2021-08-23 | 2021-08-23 | 2021-08-23 | 6 | 2021-08-24 | 7 | 2021-09-09 | 11 | [15 empty] | 2021-09-09 | 2021-09-13 | 2 | 2021-09-13 | 2021-09-14 | 1 | [13 empty] | 2021-11-04 | 2021-11-10 | 4 | [15 empty] | 2021-11-04 | 2021-11-04 | 0 | 2021-11-10 |  | 2021-11-12 | 1
121898308 | 1464 | PGE | 94062 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 39.176 |  | 2021-08-13 |  | 2021-09-13 | 2021-08-25 | 2021-08-25 | 8 | 2021-09-24 | 29 | 2021-09-28 | 2 | [34 empty] | 2021-12-10 | [17 empty] | 2021-12-10 | 2021-12-10 | 0
121899208 | 1465 | PGE | 94402 | NEM | EXPNEM | Commercial | Solar PV | 78.283 |  | 2021-08-13 |  | 2021-11-24 | 2021-08-24 | 2021-08-24 | 7 | 2021-09-20 | 25 | 2021-10-05 | 11 | [15 empty] | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | 2021-11-10 | 26 | [13 empty] | 2021-12-01 | 2021-12-09 | 6 | [15 empty] | 2021-12-01 | 2021-12-02 | 1 | 2021-12-09 |  | 2021-12-16 | 5
121899639 | 1466 | PGE | 94110 | NEM | EXPNEM | Study in Progress | Solar PV | 43.2 |  | 2021-08-13 |  | 2021-09-07 | 2021-08-23 | 2021-08-23 | 6 | 2021-09-17 | 24
121902629 | 1467 | PGE | 93455 | NEM | EXPNEM | Implementation | Solar PV | 500 |  | 2021-08-14 |  |  | 2021-08-19 | 2021-08-19 | 3 | 2021-08-23 | 5 | 2021-11-16 | 59 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-19 | 3 | [13 empty] | 2021-12-22 | 2021-12-29 | 5 | [15 empty] | 2021-12-22 | 2021-12-23 | 1 | 2021-12-29 | 2021-12-30 |  | 1 |  |  | 94
121906537 | 1468 | PGE | 95407 | NEM | EXPNEM | IA in Progress | Solar PV | 328.367 |  | 2021-08-16 |  | 2021-08-25 | 2021-08-25 | 2021-08-25 | 7 | 2021-10-11 | 39 | 2021-12-08 | 39 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | 2021-12-09 | 1 |  |  |  |  | 2021-08-16 | 2021-10-11 | 2021-08-16 | 2021-10-21 | 47
121907680 | 1469 | PGE | 95321 | Non-NEM | Non-Export | Study in Progress | Storage | 210 |  | 2021-08-16 | 2021-08-23 |  | 2021-08-17 | 2021-08-17 | 1 | 2021-09-08 | 16 | 2021-10-11 | 23 | 2021-10-29 | 2021-12-20 | 33
121907797 | 1470 | PGE | 95945 | NEM | EXPNEM | Commercial | Solar PV | 32.88 |  | 2021-08-16 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2 | 2021-10-20 | 46 | 2021-11-03 | 10 | [15 empty] | 2021-11-03 | 2021-11-03 | 0 | 2021-11-03 | 2021-11-23 | 13 | [13 empty] | 2021-11-23 | 2021-12-02 | 5 | [15 empty] | 2021-11-23 | 2021-11-23 | 0 | 2021-12-02 |  | 2021-12-02 | 0
121908590 | 1472 | PGE | 93728 | NEM | EXPNEM | IA in Progress | Solar PV | 55.889 |  | 2021-08-16 |  |  | 2021-08-25 | 2021-08-25 | 7 | 2021-08-25 | 7 | 2021-09-03 | 7 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03
121908771 | 1473 | PGE | 94523 | NEM | EXPNEM | Implementation | Solar PV | 66.6 |  | 2021-08-16 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 10 | 2021-09-07 | 15 | 2021-09-21 | 10 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | 2021-09-23 | 2 |  |  |  |  | 2021-08-16 | 2021-09-07 | 2021-08-16 | 2021-09-10 | 18
121910998 | 1474 | PGE | 95376 | NEM | EXPNEM | Commercial | Solar PV | 45.452 |  | 2021-08-17 |  | 2021-08-25 | 2021-08-25 | 2021-08-25 | 6 | 2021-09-16 | 21 | 2021-10-05 | 13 | [15 empty] | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | 2021-10-08 | 3 | [13 empty] | 2021-12-06 | 2021-12-16 | 8 | [15 empty] | 2021-12-06 | 2021-12-07 | 1 | 2021-12-16 |  | 2021-12-21 | 3
121911636 | 1475 | PGE | 94574 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-08-17 |  | 2021-08-25 | 2021-08-25 | 2021-08-25 | 6 | 2021-09-22 | 25 | 2021-10-22 | 22 | [15 empty] | 2021-10-22 | 2021-10-25 | 1 | 2021-10-25 | 2021-12-03 | 26 |  |  |  |  | 2021-08-17 | 2021-09-08 | 2021-08-17 | 2021-09-10 | 17
121911825 | 1476 | PGE | 95616 | NEM | EXPNEM | Implementation | Solar PV | 33.884 |  | 2021-08-17 |  |  | 2021-08-25 | 2021-08-25 | 6 | 2021-08-25 | 6 | 2021-09-17 | 16 | [15 empty] | 2021-09-17 | 2021-09-23 | 4 | 2021-09-23 | 2021-09-23 | 0 | [9 empty] | 2021-10-22 |  |  |  | 2021-11-01 | [17 empty] | 2021-11-01 | 2021-11-01 | 0
121912383 | 1477 | PGE | 95674 | NEM | EXPNEM | IA in Progress | Solar PV | 53.184 |  | 2021-08-17 |  | 2021-08-25 | 2021-08-25 | 2021-08-25 | 6 | 2021-09-06 | 13 | 2021-10-14 | 27 | [15 empty] | 2021-10-14 | 2021-10-14 | 0 | 2021-10-14 | [6 empty] | 2021-08-17 | 2021-11-01 | 2021-08-17 | 2021-11-18 | 65
121912801 | 1478 | PGE | 95501 | Non-NEM | Non-Export | IA in Progress | Storage | 420 |  | 2021-08-17 | 2021-08-23 |  | 2021-08-18 | 2021-08-18 | 1 | 2021-09-08 | 15 | 2021-12-10 | 64 | [25 empty] | 2021-08-17 |  | 2021-08-17
121912981 | 1479 | PGE | 93654 | NEM | EXPNEM | IA in Progress | Solar PV | 126.15 |  | 2021-08-17 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 10 | 2021-09-20 | 23 | 2021-12-29 | 69 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29
121912982 | 1480 | PGE | 93263 | NEM | EXPNEM | Implementation | Solar PV | 120 |  | 2021-08-17 |  | 2021-08-23 | 2021-08-23 | 2021-08-23 | 4 | 2021-09-10 | 17 | 2021-09-21 | 7 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | 2021-09-29 | 6 |  |  |  |  | 2021-08-17 | 2021-09-10 | 2021-08-17 | 2021-09-14 | 19
121913957 | 1481 | PGE | 94544 | NEM | NEMMT | IA in Progress | Solar PV, Storage | 55.9 |  | 2021-08-17 |  |  | 2021-08-25 | 2021-08-25 | 6 | 2021-08-25 | 6 | 2021-10-05 | 28 | [15 empty] | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05
121917117 | 1482 | PGE | 93313 | NEM | EXPNEM | Commercial | Solar PV | 44.04 |  | 2021-08-18 |  | 2021-08-24 | 2021-08-24 | 2021-08-24 | 4 | 2021-08-25 | 5 | 2021-09-10 | 11 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | 2021-11-24 | 52 | [13 empty] | 2021-11-24 | 2021-12-07 | 7 | [15 empty] | 2021-11-24 | 2021-11-29 | 1 | 2021-12-07 |  | 2021-12-07 | 0
121918190 | 1483 | PGE | 94903 | Non-NEM | NEMFC | Application Review in Progress | FUCE, Storage | 892.5 |  | 2021-08-18 |  | 2021-09-01 | 2021-09-01 | 2021-09-01 | 10 | [29 empty] | 2021-08-18 |  | 2021-08-18
121919734 | 1484 | PGE | 94027 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 32.01 |  | 2021-08-19 |  | 2021-09-24 | 2021-08-30 | 2021-08-30 | 7 | 2021-10-07 | 34 | 2021-10-11 | 2
121919795 | 1485 | PGE | 95688 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 12240 |  | 2021-08-19 |  | 2021-12-29 | 2021-08-25 | 2021-08-25 | 4
121919833 | 1486 | PGE | 95060 | NEM | EXPNEM | IA in Progress | Solar PV | 40.252 |  | 2021-08-19 |  | 2021-08-27 | 2021-08-27 | 2021-08-27 | 6 | 2021-09-01 | 9 | 2021-09-08 | 4 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08
121919898 | 1487 | PGE | 93280 | NEM | EXPNEM | Withdrawn | Solar PV | 840 |  | 2021-08-19 |  | 2021-08-30 | 2021-08-31 | 2021-08-30 | 7 | 2021-08-31 | 8 | 2021-09-20 | 13 | [15 empty] | 2021-09-20 | [9 empty] | 2021-08-19 |  | 2021-08-19 |  |  | 2021-09-08
121920019 | 1488 | PGE | 95926 | NEM | EXPNEM | IA in Progress | Solar PV | 133.3 |  | 2021-08-19 |  | 2021-08-27 | 2021-08-27 | 2021-08-27 | 6 | 2021-09-01 | 9 | 2021-09-17 | 11 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | [6 empty] | 2021-08-19 | 2021-08-27 | 2021-08-19 | 2021-09-09 | 14
121920077 | 1489 | PGE | 93266 | NEM | EXPNEM | Implementation | Solar PV | 385.259 |  | 2021-08-19 |  |  | 2021-08-24 | 2021-08-24 | 3 | 2021-08-24 | 3 | 2021-09-08 | 10 | 2021-09-10 | 2021-10-05 | 17 | [12 empty] | 2021-09-08 | 2021-09-27 | 13 | 2021-09-27 | 2021-10-05 | 6
121920255 | 1490 | PGE | 93635 | NEM | EXPNEM | Implementation | Solar PV | 181.47 |  | 2021-08-19 |  | 2021-09-27 | 2021-08-25 | 2021-08-25 | 4 | 2021-09-28 | 27 | 2021-10-25 | 19 | [15 empty] | 2021-10-25 | 2021-10-25 | 0 | 2021-10-25 | 2021-10-26 | 1 |  |  |  |  | 2021-08-19 | 2021-10-06 | 2021-08-19 | 2021-10-19 | 42 | [7 empty] | 2021-12-17 |  | 19
121920711 | 1491 | PGE | 93727 | NEM | EXPNEM | IA in Progress | Solar PV | 219.518 |  | 2021-08-19 |  | 2021-08-27 | 2021-08-27 | 2021-08-27 | 6 | 2021-10-09 | 35 | 2021-10-27 | 12 | [15 empty] | 2021-10-27 | 2021-10-27 | 0 | 2021-10-27 | [6 empty] | 2021-08-19 | 2021-10-27 | 2021-08-19 | 2021-11-05 | 55
121921002 | 1492 | PGE | 93250 | NEM | EXPNEM | Implementation | Solar PV | 290 |  | 2021-08-19 |  | 2021-08-25 | 2021-08-25 | 2021-08-25 | 4 | 2021-08-30 | 7 | 2021-09-15 | 11 | [15 empty] | 2021-12-10 | 2021-12-10 | 0 | 2021-12-10 | 2021-12-15 | 3 |  |  |  |  | 2021-08-19 | 2021-08-30 | 2021-08-19 | 2021-09-08 | 13
121921070 | 1493 | PGE | 93427 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.887 |  | 2021-08-19 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 8 | 2021-09-16 | 19 | 2021-09-16 | 0 | [34 empty] | 2021-09-16 | 2021-09-16 | 0 | [15 empty] | 2021-09-16 |  |  | 2021-09-16 |  | 2021-09-16 | 0
121921172 | 1494 | PGE | 93703 | NEM | EXPNEM | IA in Progress | Solar PV | 146 |  | 2021-08-19 |  | 2021-08-27 | 2021-08-27 | 2021-08-27 | 6 | 2021-09-01 | 9 | 2021-09-21 | 13 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [6 empty] | 2021-08-19 | 2021-10-26 | 2021-08-19 | 2021-11-04 | 54
121921294 | 1495 | PGE | 93263 | NEM | EXPNEM | Implementation | Solar PV | 246.28 |  | 2021-08-19 |  | 2021-09-08 | 2021-08-24 | 2021-08-24 | 3 | 2021-09-22 | 23 | 2021-10-07 | 11 | [15 empty] | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-12-14 | 45 |  |  |  |  | 2021-08-19 | 2021-09-22 | 2021-08-19 | 2021-09-23 | 24
121921651 | 1496 | PGE | 94952 | NEM | EXPNEM | IA in Progress | Solar PV | 30.159 |  | 2021-08-19 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 7 | 2021-11-08 | 56 | 2021-11-24 | 11 | [15 empty] | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 2021-11-30 | 2 |  |  |  |  | 2021-08-19 | 2021-11-24 | 2021-08-19 | 2021-12-13 | 78
121921653 | 1497 | PGE | 93725 | NEM | EXPNEM | Implementation | Solar PV | 53.289 |  | 2021-08-19 |  | 2021-09-02 | 2021-09-02 | 2021-09-02 | 10 | 2021-11-10 | 58 | 2021-11-18 | 5 | [15 empty] | 2021-11-18 | 2021-11-18 | 0 | 2021-11-18 | 2021-11-18 | 0 |  |  |  |  | 2021-08-19 | 2021-11-10 | 2021-08-19 | 2021-12-06 | 73
121921754 | 1498 | PGE | 94024 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.99 |  | 2021-08-19 |  | 2021-09-02 | 2021-09-02 | 2021-09-02 | 10
121922382 | 1499 | PGE | 95076 | NEM | EXPNEM | Implementation | Solar PV | 133.2 |  | 2021-08-19 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 8 | 2021-10-04 | 31 | 2021-10-19 | 11 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-12-20 | 41 |  |  |  |  | 2021-08-19 | 2021-10-04 | 2021-08-19 | 2021-10-18 | 41
121922835 | 1500 | PGE | 95695 | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-08-20 |  | 2021-10-22 | 2021-08-28 | 2021-08-28 | 5 | 2021-10-27 | 47 | 2021-11-09 | 9 | [15 empty] | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | 2021-12-27 | 31
121923917 | 1501 | PGE | 93420 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.131 |  | 2021-08-20 |  | 2021-12-17 | 2021-09-01 | 2021-09-01 | 8
121924602 | 1502 | PGE | 93401 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 44.178 |  | 2021-08-20 |  | 2021-10-13 | 2021-09-01 | 2021-09-01 | 8 | 2021-10-22 | 44 | 2021-10-25 | 1 | [34 empty] | 2021-10-25 | 2021-10-25 | 0 | [15 empty] | 2021-10-25 |  |  | 2021-10-25 |  | 2021-10-25 | 0
121925307 | 1503 | PGE | 94533 | Non-NEM | Non-Export | IA in Progress | Storage | 8999.16 |  | 2021-08-20 | 2021-08-24 |  | 2021-08-20 | 2021-08-20 | 0 | 2021-09-09 | 13 | 2021-12-01 | 56 | [15 empty] | 2021-12-01 | 2021-12-01 | 0 | 2021-12-01 | [6 empty] | 2021-09-10 |  | 2021-09-10
121925470 | 1504 | PGE | 95709 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.375 |  | 2021-08-20 |  |  | 2021-09-01 | 2021-09-01 | 8 | 2021-09-01 | 8 | 2021-09-07 | 3 | [34 empty] | 2021-09-07 | 2021-09-07 | 0 | [15 empty] | 2021-09-07 |  |  | 2021-09-07 |  | 2021-09-07 | 0
121925724 | 1505 | PGE | 93635 | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-08-20 |  |  | 2021-08-26 | 2021-08-26 | 4 | 2021-08-30 | 6 | 2021-09-13 | 9 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-09-13 | 0 |  |  |  |  | 2021-08-20 | 2021-08-30 | 2021-08-20 | 2021-09-09 | 13 |  |  |  |  | 2021-09-30 | 2021-10-07 | 5 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-10-07 |  | 2021-10-07 | 0
121925788 | 1506 | PGE | 95691 | NEM | EXPNEM | IA in Progress | Solar PV | 36 |  | 2021-08-20 |  | 2021-08-28 | 2021-08-28 | 2021-08-28 | 5 | 2021-09-09 | 13 | 2021-09-23 | 10 | [15 empty] | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | 2021-11-22 | 41 |  |  |  |  | 2021-08-20 | 2021-09-09 | 2021-08-20 | 2021-09-09 | 13 |  |  |  |  | 2021-12-28 | [17 empty] | 2021-12-28 | 2021-12-28 | 0
121927450 | 1507 | PGE | 93630 | NEM | VNEM | Commercial | Solar PV | 39.976 |  | 2021-08-20 |  | 2021-08-30 | 2021-08-25 | 2021-08-25 | 3 | 2021-09-01 | 8 | 2021-09-13 | 7 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-09-14 | 1 |  |  |  |  | 2021-08-20 | 2021-09-13 | 2021-08-20 | 2021-09-14 | 16 |  | 2021-09-13 | 2021-09-13 | 0 | 2021-10-25 | 2021-10-29 | 4 | [15 empty] | 2021-10-25 | 2021-10-25 | 0 | 2021-10-29 |  | 2021-11-01 | 1
121927966 | 1508 | PGE | 93620 | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-08-20 |  | 2021-08-31 | 2021-08-27 | 2021-08-27 | 5 | 2021-09-01 | 8 | 2021-09-16 | 10 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | 2021-09-28 | 8 |  |  |  |  | 2021-08-20 | 2021-09-01 | 2021-08-20 | 2021-09-10 | 14
121928646 | 1509 | PGE | 95334 | NEM | EXPNEM | Study in Progress | Solar PV | 276 |  | 2021-08-20 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 7 | 2021-10-06 | 32 | 2021-10-27 | 15 | 2021-10-27 | 2021-12-15 | 32 | 2021-12-15 | [21 empty] | 2021-08-20 | 2021-11-17 | 2021-08-20 | 2021-12-14 | 78
121933957 | 1510 | PGE | 94544 | NEM | EXPNEM | Application Review in Progress | Solar PV | 312.82 |  | 2021-08-21 |  | 2021-09-24 | 2021-08-28 | 2021-08-28 | 5 | [29 empty] | 2021-08-21 | 2021-08-28 | 2021-08-21 | 2021-09-09 | 12
121938018 | 1511 | PGE | 95472 | NEM | EXPNEM | Commercial | Solar PV | 50.209 |  | 2021-08-22 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 6 | 2021-09-20 | 19 | 2021-10-11 | 15 | [15 empty] | 2021-10-11 | 2021-10-11 | 0 | 2021-10-11 | 2021-10-15 | 4 | [5 empty] | 2021-10-27 | 2021-10-27 | 2021-11-05 | 7 |  |  |  |  | 2021-11-15 | 2021-11-18 | 3 | [15 empty] | 2021-11-15 | 2021-11-15 | 0 | 2021-11-18 |  | 2021-11-19 | 1
121938754 | 1512 | PGE | 95448 | NEM | EXPNEM | IA in Progress | Solar PV | 30.159 |  | 2021-08-23 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 5 | 2021-09-03 | 9 | 2021-09-27 | 15 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-14 | 13
121940803 | 1513 | PGE | 96056 | NEM | EXPNEM | IA in Progress | Solar PV | 115.456 |  | 2021-08-23 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 5 | 2021-10-05 | 30 | 2021-10-20 | 11 | [15 empty] | 2021-10-20 | 2021-10-20 | 0 | 2021-10-20 | 2021-12-15 | 37 |  |  |  |  | 2021-08-23 | 2021-10-14 | 2021-08-23 | 2021-10-27 | 46 |  |  |  |  | 2021-12-16 | [17 empty] | 2021-12-16 | 2021-12-17 | 1
121940872 | 1514 | PGE | 95334 | NEM | EXPNEM | Study in Progress | Solar PV | 840 |  | 2021-08-23 |  | 2021-09-03 | 2021-08-31 | 2021-08-31 | 6 | 2021-09-10 | 13 | 2021-09-27 | 11 | 2021-09-27 | 2021-10-29 | 24 | 2021-10-29 | 2021-11-30 | 19 | 2021-11-30
121941031 | 1515 | PGE | 93463 | NEM | EXPNEM | Implementation | Solar PV | 40.252 |  | 2021-08-23 |  |  | 2021-08-31 | 2021-08-31 | 6 | 2021-09-01 | 7 | 2021-09-14 | 8 | [15 empty] | 2021-09-14 | 2021-09-14 | 0 | 2021-09-14 | 2021-09-20 | 4 |  |  |  |  | 2021-08-23 | 2021-09-01 | 2021-08-23 | 2021-09-10 | 13 | [7 empty] | 2021-10-05 | 2022-01-12 | 67
121942807 | 1517 | PGE | 95361 | NEM | EXPNEM | Commercial | Solar PV | 44.494 |  | 2021-08-23 |  | 2021-09-13 | 2021-09-02 | 2021-09-02 | 8 | 2021-09-13 | 14 | 2021-09-27 | 10 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-01 | 4 | [13 empty] | 2021-10-21 | 2021-11-02 | 8 | [15 empty] | 2021-10-21 | 2021-10-22 | 1 | 2021-11-02 |  | 2021-11-02 | 0
121945252 | 1518 | PGE | 93702 | NEM | EXPNEM | IA in Progress | Solar PV | 288 |  | 2021-08-24 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 4 | 2021-09-22 | 20 | 2021-10-05 | 9 | [15 empty] | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | [6 empty] | 2021-08-24 |  | 2021-08-24
121945535 | 1519 | PGE | 94027 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 78.035 |  | 2021-08-24 |  | 2021-09-30 | 2021-09-07 | 2021-09-07 | 9 | 2021-10-18 | 38 | 2021-10-21 | 3
121947813 | 1520 | PGE | 93704 | NEM | EXPNEM | IA in Progress | Solar PV | 145.057 |  | 2021-08-24 |  | 2021-09-16 | 2021-08-30 | 2021-08-30 | 4 | 2021-09-20 | 18 | 2021-10-07 | 13 | [15 empty] | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | [6 empty] | 2021-08-24 | 2021-09-16 | 2021-08-24 | 2021-09-20 | 18
121951394 | 1521 | PGE | 95222 | NEM | SNEM | Application Submitted | Solar PV | 7392 |  | 2021-08-24 |  | 2021-09-01 | 2021-09-01 | 2021-09-01 | 6
121951566 | 1522 | PGE | 93726 | NEM | EXPNEM | IA in Progress | Solar PV | 240 |  | 2021-08-24 |  |  | 2021-08-30 | 2021-08-30 | 4 | 2021-08-30 | 4 | 2021-09-21 | 15 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [6 empty] | 2021-08-24 |  | 2021-08-24
121951689 | 1523 | PGE | 93721 | NEM | EXPNEM | IA in Progress | Solar PV | 192 |  | 2021-08-24 |  |  | 2021-08-30 | 2021-08-30 | 4 | 2021-08-30 | 4 | 2021-09-21 | 15 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [6 empty] | 2021-08-24 |  | 2021-08-24
121951736 | 1524 | PGE | 93722 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-08-24 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 4 | 2021-09-08 | 10 | 2021-09-22 | 10 | [15 empty] | 2021-09-22 | 2021-09-22 | 0 | 2021-09-22 | [6 empty] | 2021-08-24 | 2021-10-26 | 2021-08-24 | 2021-11-04 | 51
121952207 | 1525 | PGE | 95020 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.009 |  | 2021-08-25 |  | 2021-09-20 | 2021-09-07 | 2021-09-07 | 8 | 2021-09-29 | 24 | 2021-10-04 | 3 | [34 empty] | 2021-10-07 | 2021-10-07 | 0 | [15 empty] | 2021-10-07 |  |  | 2021-10-07 |  | 2021-10-07 | 0
121952503 | 1526 | PGE | 95965 | NEM | EXPNEM | Application Review in Progress | Solar PV | 241.512 |  | 2021-08-25 |  | 2021-09-08 | 2021-09-08 | 2021-09-08 | 9
121953249 | 1527 | PGE | 95215 | NEM | EXPNEM | IA in Progress | Solar PV | 57.873 |  | 2021-08-25 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 4 | 2021-09-07 | 8 | 2021-10-13 | 26 | [15 empty] | 2021-10-13 | 2021-10-13 | 0 | 2021-10-13 | 2021-11-05 | 17
121954360 | 1528 | PGE | 93631 | NEM | EXPNEM | Implementation | Solar PV | 150 |  | 2021-08-25 |  |  | 2021-09-09 | 2021-09-09 | 10 | 2021-09-10 | 11 | 2021-09-27 | 11 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-09-29 | 2 |  |  |  |  | 2021-08-25 | 2021-09-14 | 2021-08-25 | 2021-09-23 | 20
121954525 | 1529 | PGE | 95466 | NEM | EXPNEM | Application Review in Progress | Solar PV | 34.348 |  | 2021-08-25 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 4 | [29 empty] | 2021-08-25 |  | 2021-08-25
121954526 | 1530 | PGE | 95695 | NEM | EXPNEM | Implementation | Solar PV | 150 |  | 2021-08-25 |  | 2021-09-03 | 2021-09-03 | 2021-09-03 | 7 | 2021-09-10 | 11 | 2021-09-27 | 11 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-09-29 | 2 |  |  |  |  | 2021-08-25 |  | 2021-08-25
121954586 | 1531 | PGE | 93307 | NEM | EXPNEM | IA in Progress | Solar PV | 330 |  | 2021-08-25 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 4 | 2021-09-07 | 8 | 2021-09-27 | 14 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | [6 empty] | 2021-09-01 |  | 2021-09-01
121954755 | 1532 | PGE | 95466 | NEM | EXPNEM | Application Review in Progress | Solar PV | 104.35 |  | 2021-08-25 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 4 | [29 empty] | 2021-08-25 |  | 2021-08-25
121955755 | 1533 | PGE | 93380 | Non-NEM | RESBCT | Study in Progress | Solar PV | 5000 |  | 2021-08-25 | 2021-08-27 |  | 2021-08-25 | 2021-08-25 | 0 | 2021-09-08 | 9 | [5 empty] | 2021-09-08 | 2021-10-05 | 19 | 2021-10-05 | 2021-10-14 | 7 | 2021-12-03 |  |  | 2021-10-14 | 2021-10-14 | 0
121956158 | 1535 | PGE | 95203 | NEM | EXPNEM | Application Review in Progress | Solar PV | 89.406 |  | 2021-08-25 |  | 2021-09-01 | 2021-09-01 | 2021-09-01 | 5
121956220 | 1536 | PGE | 94533 | NEM | EXPNEM | Application Review in Progress | Solar PV | 58.447 |  | 2021-08-25 |  | 2021-09-01 | 2021-09-01 | 2021-09-01 | 5 | [29 empty] | 2021-08-25 |  | 2021-08-25
121956520 | 1537 | PGE | 93301 | NEM | EXPNEM | Application Review in Progress | Solar PV | 165.528 |  | 2021-08-25 |  | 2021-09-07 | 2021-11-03 | 2021-09-07 | 8
121956689 | 1538 | PGE | 94560 | NEM | EXPNEM | IA in Progress | Solar PV | 375 |  | 2021-08-25 |  | 2021-09-01 | 2021-09-01 | 2021-09-01 | 5 | 2021-09-15 | 14 | 2021-09-30 | 11 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | 2021-10-15 | 11 |  |  |  |  | 2021-08-25 | 2021-09-15 | 2021-08-25 | 2021-09-20 | 17 | [7 empty] | 2021-10-27 |  | 53
121957322 | 1539 | PGE | 93446 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.925 |  | 2021-08-25 |  | 2021-09-08 | 2021-09-08 | 2021-09-08 | 9 | 2021-09-22 | 19 | 2021-09-23 | 1 | [34 empty] | 2021-11-19 | 2021-11-19 | 0 | [15 empty] | 2021-11-19 |  |  | 2021-11-19 |  | 2021-11-19 | 0
121957681 | 1540 | PGE | 93706 | NEM | EXPNEM | IA in Progress | Solar PV | 206 |  | 2021-08-25 |  |  | 2021-09-02 | 2021-09-02 | 6 | 2021-09-02 | 6 | 2021-09-21 | 12 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [6 empty] | 2021-08-25 |  | 2021-08-25
121957683 | 1541 | PGE | 93702 | NEM | EXPNEM | IA in Progress | Solar PV | 231.357 |  | 2021-08-25 |  |  | 2021-09-02 | 2021-09-02 | 6 | 2021-09-02 | 6 | 2021-09-21 | 12 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [6 empty] | 2021-08-25 |  | 2021-08-25
121958032 | 1542 | PGE | 95361 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-08-25 |  | 2021-09-10 | 2021-09-02 | 2021-09-02 | 6 | 2021-09-10 | 11 | 2021-10-13 | 23 | [15 empty] | 2021-10-13 | 2021-10-13 | 0 | 2021-10-13 | [6 empty] | 2021-08-25 | 2021-09-10 | 2021-08-25 | 2021-09-14 | 13
121958482 | 1543 | PGE | 93901 | NEM | EXPNEM | Implementation | Solar PV | 200 |  | 2021-08-26 |  | 2021-09-07 | 2021-09-07 | 2021-09-07 | 7 | 2021-09-14 | 12 | 2021-10-04 | 14 | [15 empty] | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04 | 2021-12-28 | 58
121958836 | 1544 | PGE | 95969 | NEM | EXPNEM | IA in Progress | Solar PV | 200 |  | 2021-08-26 |  | 2021-10-18 | 2021-09-02 | 2021-09-02 | 5 | 2021-10-22 | 40 | 2021-11-08 | 11 | [15 empty] | 2021-11-08 | 2021-11-08 | 0 | 2021-11-08 | [6 empty] | 2021-08-26 | 2021-10-11 | 2021-08-26 | 2021-10-15 | 35
121959594 | 1545 | PGE | 93702 | NEM | EXPNEM | IA in Progress | Solar PV | 252 |  | 2021-08-26 |  |  | 2021-09-02 | 2021-09-02 | 5 | 2021-09-02 | 5 | 2021-09-21 | 12 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [6 empty] | 2021-08-26 |  | 2021-08-26
121959988 | 1546 | PGE | 93926 | NEM | EXPNEM | IA in Progress | Solar PV | 276 |  | 2021-08-26 |  | 2021-09-09 | 2021-09-09 | 2021-09-09 | 9 | 2021-09-14 | 12 | 2021-10-22 | 28 | [15 empty] | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22
121960026 | 1547 | PGE | 95060 | NEM | EXPNEM | IA in Progress | Solar PV | 45.572 |  | 2021-08-26 |  | 2021-10-19 | 2021-09-02 | 2021-09-02 | 5 | 2021-10-27 | 43 | 2021-11-18 | 15 | [15 empty] | 2021-11-18 | 2021-11-18 | 0 | 2021-11-18 | [6 empty] | 2021-08-26 | 2021-09-02 | 2021-08-26 | 2021-09-10 | 10
121960166 | 1548 | PGE | 93705 | NEM | EXPNEM | IA in Progress | Solar PV | 192 |  | 2021-08-26 |  |  | 2021-09-02 | 2021-09-02 | 5 | 2021-09-02 | 5 | 2021-09-22 | 13 | [15 empty] | 2021-09-22 | 2021-09-22 | 0 | 2021-09-22 | [6 empty] | 2021-08-26 | 2021-10-26 | 2021-08-26 | 2021-11-04 | 49
121961252 | 1549 | PGE | 93960 | NEM | EXPNEM | IA in Progress | Solar PV | 180 |  | 2021-08-26 |  | 2021-09-07 | 2021-09-07 | 2021-09-07 | 7 | 2021-09-14 | 12 | 2021-10-08 | 18 | [15 empty] | 2021-10-08 | 2021-10-08 | 0 | 2021-10-08
121961293 | 1550 | PGE | 95666 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 37.775 |  | 2021-08-26 |  | 2021-12-28 | 2021-09-07 | 2021-09-07 | 7
121962644 | 1551 | PGE | 95993 | Non-NEM | RESBCT | Study in Progress | Solar PV | 106.368 |  | 2021-08-26 | 2021-08-27 |  | 2021-08-27 | 2021-08-27 | 1 | 2021-09-15 | 13 | 2021-10-05 | 14 | 2021-10-18 | 2021-11-22 | 24 | 2021-12-17
121964094 | 1552 | PGE | 95616 | NEM | VNEM | Application Review in Progress | Solar PV | 116.08 |  | 2021-08-27 |  | 2021-09-13 | 2021-09-13 | 2021-09-13 | 10
121964097 | 1553 | PGE | 95120 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.2 |  | 2021-08-27 |  | 2021-09-08 | 2021-09-08 | 2021-09-08 | 7
121965334 | 1554 | PGE | 93446 | NEM | EXPNEM | Application Review in Progress | Solar PV | 88.2 |  | 2021-08-27 |  | 2021-10-13 | 2021-09-07 | 2021-09-07 | 6
121967150 | 1555 | PGE | 94566 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 3084.193 |  | 2021-08-27 | 2021-09-13 |  | 2021-09-13 | 2021-09-13 | 10 | 2021-10-06 | 27 | [5 empty] | 2021-10-08 | 2021-11-10 | 23 | 2021-11-10 | [18 empty] | 2021-08-27 | 2021-10-08 | 2021-08-27 | 2021-10-21 | 38
121967154 | 1556 | PGE | 95360 | NEM | EXPNEM | Study in Progress | Solar PV | 840 |  | 2021-08-27 |  |  | 2021-09-13 | 2021-09-13 | 10 | 2021-09-14 | 11 | 2021-10-13 | 21 | 2021-10-13 | 2021-11-24 | 29 | 2021-11-24 | 2021-12-17 | 15 | 2021-12-17 | [19 empty] | 2021-12-02 | 2021-12-02 | 2021-12-16 | 10
121967204 | 1557 | PGE | 93380 | Non-NEM | RESBCT | Study in Progress | Solar PV | 5000 |  | 2021-08-27 | 2021-08-30 |  | 2021-08-30 | 2021-08-30 | 1 | 2021-09-08 | 7 | [5 empty] | 2021-09-08 | 2021-10-05 | 19 | 2021-10-05 | 2021-10-14 | 7 | 2021-12-03 |  |  | 2021-10-14 | 2021-10-14 | 0
121967208 | 1558 | PGE | 93311 | Non-NEM | RESBCT | Study in Progress | Solar PV | 5000 |  | 2021-08-27 | 2021-08-30 |  | 2021-08-30 | 2021-08-30 | 1 | 2021-09-22 | 17 | [5 empty] | 2021-09-22 | 2021-10-20 | 20 | 2021-10-20 | 2021-10-25 | 3 | 2021-12-13 |  |  | 2021-10-25 | 2021-10-25 | 0
121967339 | 1559 | PGE | 93638 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 38.4 |  | 2021-08-27 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 1 | 2021-08-31 | 2 | 2021-09-17 | 12 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | [6 empty] | 2021-08-27 | 2021-10-13 | 2021-08-27 | 2021-10-22 | 39
121967411 | 1560 | PGE | 93638 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 38.4 |  | 2021-08-27 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 1 | 2021-08-31 | 2 | 2021-09-17 | 12 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | [6 empty] | 2021-08-27 | 2021-10-13 | 2021-08-27 | 2021-10-22 | 39
121967412 | 1561 | PGE | 93638 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 38.4 |  | 2021-08-27 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 1 | 2021-08-31 | 2 | 2021-09-17 | 12 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | [6 empty] | 2021-08-27 | 2021-10-13 | 2021-08-27 | 2021-10-22 | 39
121967529 | 1562 | PGE | 93307 | NEM | EXPNEM | Application Review in Progress | Solar PV | 54.292 |  | 2021-08-27 |  | 2021-09-02 | 2021-09-02 | 2021-09-02 | 4 | [29 empty] | 2021-08-27 |  | 2021-08-27
121971424 | 1563 | PGE | 95121 | NEM | EXPNEM | IA in Progress | Solar PV | 72.22 |  | 2021-08-30 |  | 2021-09-17 | 2021-09-07 | 2021-09-07 | 5 | 2021-10-05 | 25 | 2021-10-20 | 11 | [15 empty] | 2021-10-20 | 2021-10-21 | 1 | 2021-10-21
121971473 | 1564 | PGE | 94509 | NEM | EXPNEM | Implementation | Solar PV | 86.65 |  | 2021-08-30 |  | 2021-09-13 | 2021-09-22 | 2021-09-13 | 9 | 2021-09-22 | 16 | 2021-10-13 | 15 | [15 empty] | 2021-11-17 | 2021-12-06 | 11 | 2021-12-06 | 2021-12-06 | 0
121972635 | 1565 | PGE | 95472 | NEM | EXPNEM | Commercial | Solar PV | 34.179 |  | 2021-08-30 |  |  | 2021-09-07 | 2021-09-07 | 5 | 2021-09-07 | 5 | 2021-09-24 | 13 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | 2021-10-14 | 14 |  |  |  |  | 2021-08-30 | 2021-09-07 | 2021-08-30 | 2021-09-10 | 8 |  |  |  |  | 2021-11-21 | 2021-11-30 | 4 | [15 empty] | 2021-11-21 | 2021-11-21 | 0 | 2021-11-30 |  | 2021-12-03 | 3
121972858 | 1566 | PGE | 93926 | NEM | EXPNEM | Study in Progress | Solar PV | 390 |  | 2021-08-30 |  | 2021-09-02 | 2021-09-02 | 2021-09-02 | 3 | 2021-09-03 | 4 | 2021-09-21 | 11 | 2021-09-21 | 2021-11-24 | 45 | 2021-11-24 | 2021-12-20 | 16 | 2021-12-20
121974467 | 1567 | PGE | 94087 | NEM | EXPNEM | IA in Progress | Solar PV | 125 |  | 2021-08-30 |  | 2021-09-07 | 2021-09-07 | 2021-09-07 | 5 | 2021-09-21 | 15 | 2021-10-12 | 15 | [15 empty] | 2021-10-12 | 2021-10-12 | 0 | 2021-10-12 | 2021-11-02 | 15 |  |  |  |  | 2021-08-30 | 2021-09-07 | 2021-08-30 | 2021-09-10 | 8
121974755 | 1568 | PGE | 95003 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-08-30 |  |  | 2021-09-13 | 2021-09-13 | 9 | 2021-09-13 | 9 | 2021-09-13 | 0 | [34 empty] | 2021-09-13 | 2021-09-13 | 0 | [15 empty] | 2021-09-13 |  |  | 2021-09-13 |  | 2021-09-13 | 0
121974926 | 1569 | PGE | 93930 | NEM | EXPNEM | Implementation | Solar PV | 336 |  | 2021-08-30 |  |  | 2021-09-13 | 2021-09-13 | 9 | 2021-09-14 | 10 | 2021-11-03 | 36 | [15 empty] | 2021-11-03 | 2021-11-03 | 0 | 2021-11-03 | 2021-12-30 | 38
121975521 | 1570 | PGE | 93901 | NEM | EXPNEM | Implementation | Solar PV | 220 |  | 2021-08-31 |  |  | 2021-09-13 | 2021-09-13 | 8 | 2021-09-14 | 9 | 2021-09-30 | 12 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | 2021-12-15 | 51 |  |  |  |  | 2021-08-31 | 2021-09-14 | 2021-08-31 | 2021-09-21 | 14
121976292 | 1571 | PGE | 93314 | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-08-31 |  |  | 2021-09-13 | 2021-09-13 | 8 | 2021-09-13 | 8 | 2021-09-21 | 6 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | 2021-11-18 | 41 |  |  |  |  | 2021-08-31 | 2021-09-14 | 2021-08-31 | 2021-09-21 | 14 |  |  |  |  | 2021-12-20 | 2021-12-28 | 6 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-28 |  | 2021-12-29 | 1
121977365 | 1574 | PGE | 95030 | NEM | EXPNEM | Commercial | Solar PV | 34.9 |  | 2021-08-31 |  | 2021-11-22 | 2021-09-07 | 2021-09-07 | 4 | 2021-11-26 | 59 | 2021-12-06 | 5 | [15 empty] | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-22 | 12 | [13 empty] | 2021-12-22 | 2021-12-30 | 6 | [15 empty] | 2021-12-22 | 2021-12-23 | 1 | 2021-12-30 |  | 2021-12-31 | 1
121978170 | 1575 | PGE | 93242 | NEM | EXPNEM | Study in Progress | Solar PV | 1560 |  | 2021-08-31 | 2021-09-01 |  | 2021-09-01 | 2021-09-01 | 1 | 2021-10-21 | 36 | [5 empty] | 2021-10-21 | 2021-11-17 | 18 | 2021-11-17 | 2021-11-18 | 1 |  |  |  | 2021-11-18 | 2021-12-02 | 8 | [10 empty] | 2021-08-31 | 2021-10-12 | 2021-08-31 | 2021-10-22 | 37
121979772 | 1576 | PGE | 93908 | NEM | EXPNEM | Implementation | Solar PV | 136 |  | 2021-08-31 |  |  | 2021-09-13 | 2021-09-13 | 8 | 2021-09-14 | 9 | 2021-09-30 | 12 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | 2021-12-15 | 51 |  |  |  |  | 2021-08-31 | 2021-09-14 | 2021-08-31 | 2021-10-13 | 30
121985947 | 1577 | PGE | 94103 | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-09-01 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 9 | 2021-10-14 | 30 | 2021-10-20 | 4 | [15 empty] | 2021-10-20 | 2021-10-20 | 0 | 2021-10-20 | 2021-11-04 | 11 | [5 empty] | 2021-11-04 | 2021-11-04 | 2021-11-05 | 1 |  |  |  |  | 2021-11-10 | 2021-11-18 | 5 | [15 empty] | 2021-11-10 | 2021-11-12 | 1 | 2021-11-18 |  | 2021-11-24 | 4
121986313 | 1578 | PGE | 93703 | NEM | EXPNEM | IA in Progress | Solar PV | 82.146 |  | 2021-09-01 |  |  | 2021-09-16 | 2021-09-16 | 10 | 2021-09-27 | 17 | 2021-10-18 | 15 | [15 empty] | 2021-10-18 | 2021-10-18 | 0 | 2021-10-18
121986325 | 1579 | PGE | 93720 | NEM | EXPNEM | Implementation | Solar PV | 344.924 |  | 2021-09-01 |  |  | 2021-09-16 | 2021-09-16 | 10 | 2021-09-27 | 17 | 2021-10-18 | 15 | [15 empty] | 2021-10-18 | 2021-10-18 | 0 | 2021-10-18 | 2021-11-23 | 25
121986653 | 1580 | PGE | 95616 | NEM | EXPNEM | Commercial | Solar PV | 51.508 |  | 2021-09-01 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 9 | 2021-10-05 | 23 | 2021-10-20 | 11 | [15 empty] | 2021-10-20 | 2021-10-20 | 0 | 2021-10-20 | 2021-10-27 | 5 | [13 empty] | 2021-11-02 | 2021-11-09 | 5 | [15 empty] | 2021-11-02 | 2021-11-02 | 0 | 2021-11-09 |  | 2021-11-15 | 3
121986695 | 1581 | PGE | 95616 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-09-01 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 9 | 2021-09-17 | 11 | 2021-10-20 | 23 | [15 empty] | 2021-10-20 | 2021-10-20 | 0 | 2021-10-20 | 2021-10-26 | 4 | [13 empty] | 2021-11-02 | 2021-11-09 | 5 | [15 empty] | 2021-11-02 | 2021-11-02 | 0 | 2021-11-09 |  | 2021-11-23 | 9
121987918 | 1582 | PGE | 95020 | NEM | EXPNEM | IA in Progress | Solar PV | 75.278 |  | 2021-09-02 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 8 | 2021-10-12 | 27 | 2021-12-07 | 37 | [15 empty] | 2021-12-07 | 2021-12-07 | 0 | 2021-12-07
121988272 | 1583 | PGE | 93268 | NEM | EXPNEM | IA in Progress | Solar PV | 95.822 |  | 2021-09-02 |  | 2021-10-09 | 2021-09-09 | 2021-09-09 | 4 | 2021-10-12 | 27 | 2021-10-22 | 8 | [15 empty] | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | 2021-11-15 | 15 |  |  |  |  | 2021-09-02 | 2021-10-22 | 2021-09-02 | 2021-11-03 | 43
121988363 | 1584 | PGE | 94510 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.599 |  | 2021-09-02 |  | 2021-09-27 | 2021-09-15 | 2021-09-15 | 8 | 2021-10-08 | 25 | 2021-10-11 | 1 | [25 empty] | 2021-09-02 | 2021-10-18 | 2021-09-02 | 2021-10-18 | 31 |  |  |  |  | 2021-10-18 | 2021-10-18 | 0 | [15 empty] | 2021-10-18 |  |  | 2021-10-18 |  | 2021-10-18 | 0
121988538 | 1585 | PGE | 95258 | NEM | EXPNEM | Study in Progress | Solar PV | 270 |  | 2021-09-02 |  | 2021-09-17 | 2021-09-17 | 2021-09-17 | 10 | 2021-11-03 | 43
121988597 | 1586 | PGE | 95240 | NEM | EXPNEM | IA in Progress | Solar PV | 111.259 |  | 2021-09-02 |  |  | 2021-09-17 | 2021-09-17 | 10 | 2021-09-22 | 13 | 2021-10-13 | 15 | [15 empty] | 2021-10-13 | 2021-11-03 | 15 | 2021-11-03 | [7 empty] | 2021-11-12 | 2021-11-12 | 2021-12-06 | 14
121989661 | 1587 | PGE | 94591 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.028 |  | 2021-09-02 |  | 2021-09-30 | 2021-09-15 | 2021-09-15 | 8 | 2021-10-08 | 25 | 2021-10-11 | 1 | [34 empty] | 2021-10-11 | 2021-10-11 | 0 | [15 empty] | 2021-10-11 |  |  | 2021-10-11 |  | 2021-10-11 | 0
121989770 | 1588 | PGE | 93710 | NEM | EXPNEM | IA in Progress | Solar PV | 175 |  | 2021-09-02 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 8 | 2021-10-15 | 30 | 2021-10-29 | 10 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | 2021-11-01 | 1 | [5 empty] | 2021-10-29 | 2021-10-29 | 2021-11-18 | 13 |  |  |  |  | 2021-12-16 | [17 empty] | 2021-12-16 | 2021-12-17 | 1
121989866 | 1589 | PGE | 95341 | NEM | EXPNEM | IA in Progress | Solar PV | 840 |  | 2021-09-02 |  |  | 2021-09-16 | 2021-09-16 | 9 | 2021-09-27 | 16 | 2021-11-01 | 25 | [15 empty] | 2021-11-01 | 2021-11-01 | 0 | 2021-11-01
121990859 | 1590 | PGE | 93960 | NEM | EXPNEM | Study in Progress | Solar PV | 500 |  | 2021-09-02 |  |  | 2021-09-14 | 2021-09-14 | 7 | 2021-09-14 | 7 | [5 empty] | 2021-09-17 | 2021-10-11 | 16 | 2021-10-11
121991851 | 1591 | PGE | 95304 | NEM | EXPNEM | IA in Progress | Solar PV | 135.897 |  | 2021-09-02 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 8 | 2021-10-12 | 27 | 2021-10-26 | 10 | [15 empty] | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26 | 2021-11-05 | 8 |  |  |  |  | 2021-09-02 | 2021-11-10 | 2021-09-02 | 2021-12-01 | 60
121995079 | 1592 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 72.22 |  | 2021-09-03 |  | 2021-09-08 | 2021-09-08 | 2021-09-08 | 2 | 2021-09-15 | 7 | 2021-10-06 | 15 | [15 empty] | 2021-10-06 | 2021-10-27 | 15 | 2021-10-27 | [6 empty] | 2021-09-03 |  | 2021-09-03 |  |  | 2021-12-20
121997476 | 1593 | PGE | 93725 | NEM | EXPNEM | Application Accepted | Solar PV | 40.252 |  | 2021-09-03 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 7 | 2021-12-16 | 70
122009584 | 1594 | PGE | 94533 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100 |  | 2021-09-07 |  | 2021-09-08 | 2021-09-08 | 2021-09-08 | 1 | 2021-09-13 | 4 | 2021-10-01 | 14 | [15 empty] | 2021-10-01 | 2021-10-01 | 0 | 2021-10-01 | [6 empty] | 2021-09-07 | 2021-09-10 | 2021-09-07 | 2021-09-14 | 5 |  | 2021-09-17 | 2021-10-01 | 10
122009623 | 1595 | PGE | 93720 | NEM | EXPNEM | Implementation | Solar PV | 591.6 |  | 2021-09-07 |  | 2021-09-14 | 2021-09-14 | 2021-09-14 | 5 | 2021-09-16 | 7 | 2021-09-24 | 6 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | 2021-10-01 | 5 |  |  |  |  | 2021-09-07 | 2021-09-14 | 2021-09-07 | 2021-09-21 | 10
122009679 | 1596 | PGE | 94533 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100 |  | 2021-09-07 |  | 2021-09-08 | 2021-09-08 | 2021-09-08 | 1 | 2021-09-13 | 4 | 2021-10-01 | 14 | [15 empty] | 2021-10-01 | 2021-10-01 | 0 | 2021-10-01 | [6 empty] | 2021-09-07 | 2021-09-10 | 2021-09-07 | 2021-09-14 | 5 |  | 2021-09-17 | 2021-10-01 | 10
122009844 | 1597 | PGE | 93727 | NEM | EXPNEM | Implementation | Solar PV | 34.8 |  | 2021-09-07 |  |  | 2021-09-13 | 2021-09-13 | 4 | 2021-09-13 | 4 | 2021-09-29 | 12 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | 2021-10-27 | 20 | [5 empty] | 2021-09-29 | 2021-09-29 | 2021-10-14 | 11 |  |  |  |  | 2021-12-31 | [17 empty] | 2021-12-31
122009898 | 1598 | PGE | 94533 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100 |  | 2021-09-07 |  | 2021-09-08 | 2021-09-08 | 2021-09-08 | 1 | 2021-09-13 | 4 | 2021-10-01 | 14 | [15 empty] | 2021-10-01 | 2021-10-01 | 0 | 2021-10-01 | [6 empty] | 2021-09-07 | 2021-09-10 | 2021-09-07 | 2021-09-14 | 5 |  | 2021-09-17 | 2021-10-01 | 10
122009964 | 1599 | PGE | 95062 | NEM | EXPNEM | IA in Progress | Solar PV | 255.015 |  | 2021-09-07 |  | 2021-09-08 | 2021-09-08 | 2021-09-08 | 1 | 2021-09-13 | 4 | 2021-09-28 | 11 | [15 empty] | 2021-09-28 | 2021-09-28 | 0 | 2021-09-28 | [6 empty] | 2021-09-07 | 2021-09-13 | 2021-09-07 | 2021-09-20 | 9
122012455 | 1600 | PGE | 94533 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 43.2 |  | 2021-09-08 |  | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2 | 2021-09-13 | 3 | 2021-10-01 | 14 | [15 empty] | 2021-10-01 | 2021-10-01 | 0 | 2021-10-01 | [7 empty] | 2021-09-10 | 2021-09-10 | 2021-09-14 | 2
122012643 | 1601 | PGE | 95125 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 85.601 |  | 2021-09-08 |  | 2021-09-22 | 2021-09-22 | 2021-09-22 | 10 | 2021-10-04 | 18 | 2021-10-25 | 15 | [15 empty] | 2021-10-25 | 2021-11-16 | 15 | 2021-11-16 | [6 empty] | 2021-09-08 | 2021-11-15 | 2021-09-08 | 2021-12-15 | 67
122012720 | 1602 | PGE | 95125 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 41.349 |  | 2021-09-08 |  | 2021-09-22 | 2021-09-22 | 2021-09-22 | 10 | 2021-10-04 | 18 | 2021-10-25 | 15 | [15 empty] | 2021-10-25 | 2021-11-16 | 15 | 2021-11-16 | [6 empty] | 2021-09-08 | 2021-10-25 | 2021-09-08 | 2021-11-03 | 40 |  | 2021-11-16 | 2021-11-16 | 0
122012800 | 1603 | PGE | 94546 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 93.276 |  | 2021-09-08 |  | 2021-09-22 | 2021-09-22 | 2021-09-22 | 10 | 2021-10-04 | 18 | 2021-11-18 | 32 | [15 empty] | 2021-11-18 | 2021-11-18 | 0 | 2021-11-18 | [6 empty] | 2021-09-08 | 2021-11-24 | 2021-09-08 | 2021-11-29 | 55 |  | 2021-12-08 | 2021-12-08 | 0
122012802 | 1604 | PGE | 94546 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 61.126 |  | 2021-09-08 |  | 2021-09-22 | 2021-09-22 | 2021-09-22 | 10 | 2021-10-04 | 18 | 2021-11-18 | 32 | [15 empty] | 2021-11-18 | 2021-11-18 | 0 | 2021-11-18 | [6 empty] | 2021-09-08 | 2021-11-24 | 2021-09-08 | 2021-11-29 | 55 |  | 2021-12-08 | 2021-12-08 | 0
122014354 | 1605 | PGE | 93901 | NEM | EXPNEM | Implementation | Solar PV | 150 |  | 2021-09-08 |  |  | 2021-09-14 | 2021-09-14 | 4 | 2021-09-15 | 5 | 2021-11-05 | 37 | [15 empty] | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05 | 2021-12-15 | 25 |  |  |  |  | 2021-09-08 | 2021-09-15 | 2021-09-08 | 2021-09-22 | 10
122014809 | 1606 | PGE | 93308 | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2021-09-08 |  |  | 2021-09-20 | 2021-09-20 | 8 | 2021-09-20 | 8 | 2021-09-23 | 3 | [15 empty] | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | 2021-09-24 | 1 | [13 empty] | 2021-10-28 | [17 empty] | 2021-10-28 | 2021-10-28 | 0
122014821 | 1607 | PGE | 95120 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 40.163 |  | 2021-09-08 |  | 2021-11-26 | 2021-09-08 | 2021-09-08 | 0 | 2021-12-07 | 61 | 2021-12-13 | 4 | [34 empty] | 2021-12-13 | 2021-12-13 | 0 | [15 empty] | 2021-12-13 |  |  | 2021-12-13 |  | 2021-12-13 | 0
122015193 | 1608 | PGE | 95120 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.621 |  | 2021-09-08 |  |  | 2021-09-17 | 2021-09-17 | 7 | 2021-09-17 | 7 | 2021-09-19 | 0 | [34 empty] | 2021-09-19 | 2021-09-19 | 0 | [15 empty] | 2021-09-19 |  |  | 2021-09-19 |  | 2021-09-19 | 0
122016197 | 1609 | PGE | 95650 | NEM | EXPNEM | IA in Progress | Solar PV | 34.179 |  | 2021-09-08 |  | 2021-09-22 | 2021-09-22 | 2021-09-22 | 10 | 2021-11-16 | 48 | 2021-12-02 | 10 | [15 empty] | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02
122018296 | 1610 | PGE | 95492 | NEM | VNEM | Application Accepted | Solar PV | 1920 |  | 2021-09-09 |  | 2021-10-14 | 2021-09-13 | 2021-09-13 | 2 | 2021-12-10 | 63 | 2021-12-31 | 15
122018459 | 1611 | PGE | 94107 | Non-NEM | Non-Export | IA in Progress | ENGN | 60 |  | 2021-09-09 | 2021-09-10 |  | 2021-09-09 | 2021-09-09 | 0 | 2021-09-22 | 9 | 2021-10-05 | 9 | [15 empty] | 2021-10-22 | 2021-10-27 | 3 | 2021-10-27
122019694 | 1613 | PGE | 93611 | NEM | VNEMMASH | IA in Progress | Solar PV | 39.875 |  | 2021-09-09 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 4 | 2021-12-01 | 56 | 2021-12-08 | 5 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | 2021-12-14 | 4
122019747 | 1615 | PGE | 93611 | NEM | VNEMMASH | IA in Progress | Solar PV | 50.025 |  | 2021-09-09 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 4 | 2021-12-01 | 56 | 2021-12-08 | 5 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | 2021-12-14 | 4
122020546 | 1617 | PGE | 95667 | NEM | EXPNEM | Implementation | Solar PV | 178.024 |  | 2021-09-09 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 4 | 2021-10-04 | 17 | 2021-10-21 | 13 | [15 empty] | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21 | 2021-11-09 | 13 | [5 empty] | 2021-10-06 | 2021-10-06 | 2021-10-21 | 11 | [7 empty] | 2021-12-01 |  | 31
122020637 | 1618 | PGE | 95220 | NEM | EXPNEM | Study in Progress | Solar PV | 840 |  | 2021-09-09 |  | 2021-10-28 | 2021-09-13 | 2021-09-13 | 2 | 2021-11-23 | 52 | 2021-12-09 | 10 | 2021-12-09
122020675 | 1619 | PGE | 95540 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 630 |  | 2021-09-09 | 2021-09-10 |  | 2021-09-10 | 2021-09-10 | 1 | 2021-09-29 | 14 | 2021-11-16 | 33 | 2021-12-07 | [14 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | 2021-10-11 | 7
122021468 | 1620 | PGE | 94551 | NEM | EXPNEM | Withdrawn | Solar PV | 500 |  | 2021-09-09 |  |  | 2021-09-13 | 2021-09-13 | 2 | 2021-09-13 | 2 | 2021-09-29 | 12 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | [7 empty] | 2021-09-15 | 2021-09-15 | 2021-09-22 | 5
122034566 | 1621 | PGE | 95616 | NEM | EXPNEM | IA in Progress | Solar PV | 131.66 |  | 2021-09-10 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 3 | 2021-09-23 | 9 | 2021-10-07 | 10 | [15 empty] | 2021-10-07 | 2021-10-08 | 1 | 2021-10-08 | [6 empty] | 2021-09-10 | 2021-09-15 | 2021-09-10 | 2021-09-22 | 8
122034767 | 1622 | PGE | 95648 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-09-10 |  |  | 2021-09-24 | 2021-09-24 | 10 | 2021-09-24 | 10 | 2021-09-28 | 2 | [25 empty] | 2021-09-10 | 2021-11-03 | 2021-09-10 | 2021-11-03 | 38 |  |  |  |  | 2021-11-03 | 2021-11-03 | 0 | [15 empty] | 2021-11-03 |  |  | 2021-11-03 |  | 2021-11-03 | 0
122034784 | 1623 | PGE | 95202 | NEM | EXPNEM | Implementation | Solar PV | 82.454 |  | 2021-09-10 |  |  | 2021-09-15 | 2021-09-15 | 3 | 2021-09-15 | 3 | 2021-09-30 | 11 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | 2021-10-14 | 10 |  |  |  |  | 2021-09-10 | 2021-09-15 | 2021-09-10 | 2021-09-22 | 8
122035283 | 1624 | PGE | 93245 | NEM | EXPNEM | IA in Progress | Solar PV | 80 |  | 2021-09-10 | 2021-09-24 |  | 2021-09-15 | 2021-09-15 | 3 | 2021-09-29 | 13 | 2021-10-19 | 14 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | [6 empty] | 2021-09-10 | 2021-11-01 | 2021-09-10 | 2021-11-01 | 36
122036733 | 1625 | PGE | 95236 | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 |  | 2021-09-10 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 3
122037235 | 1626 | PGE | 95403 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.287 |  | 2021-09-10 |  | 2021-10-26 | 2021-09-24 | 2021-09-24 | 10 | 2021-11-02 | 37 | 2021-11-03 | 1 | [34 empty] | 2021-11-03 | 2021-11-03 | 0 | [15 empty] | 2021-11-03 |  |  | 2021-11-03 |  | 2021-11-03 | 0
122042960 | 1627 | PGE | 94024 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.63 |  | 2021-09-13 |  | 2021-10-21 | 2021-09-27 | 2021-09-27 | 10 | 2021-10-25 | 30 | 2021-10-27 | 2 | [34 empty] | 2021-10-27 | 2021-10-27 | 0 | [15 empty] | 2021-10-27 |  |  | 2021-10-27 |  | 2021-10-27 | 0
122043467 | 1628 | PGE | 95376 | NEM | EXPNEM | Withdrawn | Solar PV | 95.8 |  | 2021-09-13 |  | 2021-09-17 | 2021-09-17 | 2021-09-17 | 4 | [29 empty] | 2021-09-13 |  | 2021-09-13
122044521 | 1629 | PGE | 93908 | NEM | EXPNEM | Study in Progress | Solar PV | 39.596 |  | 2021-09-13 |  | 2021-09-27 | 2021-09-27 | 2021-09-27 | 10 | 2021-11-03 | 37
122048959 | 1630 | PGE | 93427 | NEM | EXPNEM | Study in Progress | Solar PV | 72 |  | 2021-09-14 |  | 2021-09-28 | 2021-09-28 | 2021-09-28 | 10 | 2021-12-17 | 65
122049507 | 1631 | PGE | 95658 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 32.668 |  | 2021-09-14 |  | 2021-09-27 | 2021-09-27 | 2021-09-27 | 9 | 2021-10-07 | 17 | 2021-10-11 | 2 | [34 empty] | 2021-10-11 | 2021-10-11 | 0 | [15 empty] | 2021-10-11 |  |  | 2021-10-11 |  | 2021-10-11 | 0
122049797 | 1632 | PGE | 93427 | NEM | EXPNEM | Study in Progress | Solar PV | 240 |  | 2021-09-14 |  | 2021-09-28 | 2021-09-28 | 2021-09-28 | 10 | 2021-10-05 | 15 | 2021-10-26 | 15 | [25 empty] | 2021-10-07 |  | 2021-10-07 |  |  | 2021-10-15
122050122 | 1633 | PGE | 94503 | NEM | NEM Paired Storage | Implementation | ENGN, Solar PV, Storage | 140 |  | 2021-09-14 |  | 2021-09-17 | 2021-09-17 | 2021-09-17 | 3 | 2021-09-17 | 3 | 2021-10-18 | 21 | [15 empty] | 2021-10-18 | 2021-10-18 | 0 | 2021-10-18 | 2021-11-19 | 23
122051314 | 1634 | PGE | 93612 | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-09-15 |  |  | 2021-09-20 | 2021-09-20 | 3 | 2021-09-20 | 3 | 2021-09-29 | 7 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | 2021-11-19 | 36 | [13 empty] | 2021-11-19 | 2021-11-30 | 5 | [15 empty] | 2021-11-19 | 2021-11-22 | 1 | 2021-11-30 |  | 2021-11-30 | 0
122051677 | 1635 | PGE | 94526 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-09-15 |  | 2021-10-18 | 2021-09-27 | 2021-09-27 | 8 | 2021-10-26 | 29 | 2021-10-28 | 2 | [34 empty] | 2021-10-28 | 2021-10-28 | 0 | [15 empty] | 2021-10-28 |  |  | 2021-10-28 |  | 2021-10-28 | 0
122052117 | 1636 | PGE | 94022 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.025 |  | 2021-09-15 |  | 2021-10-27 | 2021-09-15 | 2021-09-15 | 0 | 2021-12-03 | 54 | 2021-12-07 | 2 | [34 empty] | 2021-12-07 | 2021-12-08 | 1 | [15 empty] | 2021-12-07 | 2021-12-07 | 0 | 2021-12-08 |  | 2021-12-09 | 1
122052264 | 1637 | PGE | 94556 | NEM | EXPNEM | Implementation | Solar PV | 92.318 |  | 2021-09-15 |  |  | 2021-09-20 | 2021-09-20 | 3 | 2021-09-20 | 3 | 2021-10-06 | 12 | [15 empty] | 2021-10-06 | 2021-10-06 | 0 | 2021-10-06 | 2021-10-28 | 16 |  |  |  |  | 2021-09-15 | 2021-09-20 | 2021-09-15 | 2021-09-23 | 6
122055664 | 1638 | PGE | 93706 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-09-15 |  |  | 2021-09-17 | 2021-09-17 | 2 | 2021-09-17 | 2 | 2021-09-28 | 7 | [15 empty] | 2021-09-28 | 2021-09-28 | 0 | 2021-09-28
122057795 | 1639 | PGE | 95228 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-09-16 |  |  | 2021-09-23 | 2021-09-23 | 5 | 2021-09-23 | 5 | 2021-09-27 | 2 | [34 empty] | 2021-09-28 | 2021-09-28 | 0 | [15 empty] | 2021-09-28 |  |  | 2021-09-28 |  | 2021-09-28 | 0
122058430 | 1640 | PGE | 93610 | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-09-16 |  | 2021-09-30 | 2021-09-27 | 2021-09-27 | 7 | 2021-10-26 | 28 | 2021-11-15 | 13 | [15 empty] | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-16 | 1 |  |  |  |  | 2021-09-16 | 2021-12-07 | 2021-09-16 | 2021-12-16 | 62 |  |  |  |  | 2021-12-21 | 2021-12-29 | 6 | [15 empty] | 2021-12-21 | 2021-12-22 | 1 | 2021-12-29 |  | 2021-12-29 | 0
122058605 | 1641 | PGE | 95111 | NEM | VNEMSOMAH | Implementation | Solar PV | 185.821 |  | 2021-09-16 |  | 2021-09-23 | 2021-09-23 | 2021-09-23 | 5 | 2021-10-08 | 16 | 2021-11-30 | 34 | [15 empty] | 2021-11-30 | 2021-11-30 | 0 | 2021-11-30 | 2021-12-08 | 6 |  |  |  |  | 2021-09-16 |  | 2021-09-16 |  |  | 2021-11-17
122058966 | 1642 | PGE | 96007 | NEM | NEMMT | Application Review in Progress | FUCE, Solar PV | 500 |  | 2021-09-16 |  | 2021-09-29 | 2021-09-29 | 2021-09-29 | 9
122059026 | 1643 | PGE | 95929 | NEM | EXPNEM | IA in Progress | Solar PV | 1010.281 |  | 2021-09-16 |  | 2021-09-30 | 2021-09-30 | 2021-09-30 | 10 | 2021-11-03 | 34 | 2021-11-29 | 15 | [15 empty] | 2021-11-29 | 2021-11-30 | 1 | 2021-11-30 | [6 empty] | 2021-09-16 |  | 2021-09-16
122060253 | 1645 | PGE | 95033 | NEM | SNEM Paired Storage | IA in Progress | Solar PV, Storage | 35.2 |  | 2021-09-16 |  |  | 2021-09-17 | 2021-09-17 | 1 | 2021-09-17 | 1 | 2021-10-28 | 29 | [15 empty] | 2021-09-16 | 2021-09-16 |  | 2021-09-16 | 2021-09-17 | 2
122060257 | 1646 | PGE | 95035 | NEM | EXPNEM | Study in Progress | Solar PV | 166.5 |  | 2021-09-16 |  | 2021-09-30 | 2021-09-30 | 2021-09-30 | 10 | 2021-10-20 | 24
122060336 | 1647 | PGE | 94578 | NEM | VNEMMASH | Study in Progress | Solar PV | 43.2 |  | 2021-09-16 |  | 2021-09-30 | 2021-09-30 | 2021-09-30 | 10 | 2021-12-16 | 62
122064947 | 1648 | PGE | 93230 | NEM | EXPNEM | Study in Progress | Solar PV | 2125 |  | 2021-09-17 | 2021-09-21 |  | 2021-09-20 | 2021-09-20 | 1 | 2021-10-20 | 23 | [5 empty] | 2021-10-29 | 2021-11-29 | 18 | 2021-11-29 | 2021-11-30 | 1 |  |  |  | 2021-11-30 | [17 empty] | 2021-11-01
122065585 | 1649 | PGE | 94063 | NEM | EXPNEM | IA in Progress | Solar PV | 172.8 |  | 2021-09-17 |  |  | 2021-10-01 | 2021-10-01 | 10 | 2021-10-01 | 10 | 2021-10-13 | 8 | [15 empty] | 2021-10-13 | 2021-10-13 | 0 | 2021-10-13 | [6 empty] | 2021-09-17 | 2021-10-13 | 2021-09-17 | 2021-10-22 | 25
122065682 | 1650 | PGE | 94063 | NEM | EXPNEM | IA in Progress | Solar PV | 86.4 |  | 2021-09-17 |  |  | 2021-09-20 | 2021-09-20 | 1 | 2021-09-20 | 1 | 2021-09-22 | 2 | [15 empty] | 2021-09-22 | 2021-09-22 | 0 | 2021-09-22 | [6 empty] | 2021-09-17 | 2021-09-20 | 2021-09-17 | 2021-09-23 | 4
122066737 | 1651 | PGE | 95228 | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 60.02 |  | 2021-09-17 |  | 2021-09-27 | 2021-09-27 | 2021-09-27 | 6 | 2021-10-04 | 11 | 2021-10-22 | 14 | [15 empty] | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | 2021-10-23 | 0 |  |  |  |  | 2021-09-29 | 2021-10-04 | 2021-09-29 | 2021-10-18 | 13 |  |  |  |  | 2021-10-27 | 2021-11-02 | 4 | [15 empty] | 2021-10-27 | 2021-10-28 | 1 | 2021-11-02 |  | 2021-11-03 | 1
122067319 | 1652 | PGE | 95202 | NEM | EXPNEM | Application Review in Progress | Solar PV | 242 |  | 2021-09-17 |  | 2021-09-21 | 2021-09-20 | 2021-09-20 | 1 | [29 empty] | 2021-09-17 |  | 2021-09-17
122067663 | 1653 | PGE | 93308 | NEM | EXPNEM | Implementation | Solar PV | 166 |  | 2021-09-17 |  |  | 2021-09-29 | 2021-09-29 | 8 | 2021-09-29 | 8 | 2021-10-11 | 8 | [15 empty] | 2021-10-11 | 2021-10-26 | 11 | 2021-10-26 | 2021-10-26 | 0 |  |  |  |  | 2021-09-17 |  | 2021-09-17 |  |  | 2021-10-01
122067745 | 1654 | PGE | 93308 | NEM | EXPNEM | IA in Progress | Solar PV | 170 |  | 2021-09-17 |  |  | 2021-09-29 | 2021-09-29 | 8 | 2021-09-29 | 8 | 2021-10-11 | 8 | [15 empty] | 2021-10-11 | 2021-10-26 | 11 | 2021-10-26 | [6 empty] | 2021-09-17 |  | 2021-09-17 |  |  | 2021-10-01
122067925 | 1655 | PGE | 95336 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 3000 |  | 2021-09-17 | 2021-09-21 |  | 2021-09-20 | 2021-09-20 | 1 | 2021-11-10 | 38 | [5 empty] | 2021-11-10 | 2021-12-08 | 17 | 2021-12-08 | 2021-12-22 | 10 |  |  |  | 2021-12-22 | 2021-12-22 | 0
122071270 | 1656 | PGE | 93725 | NEM | EXPNEM | Implementation | Solar PV | 38.78 |  | 2021-09-20 |  | 2021-09-30 | 2021-10-05 | 2021-09-30 | 8 | 2021-10-05 | 11 | 2021-10-11 | 4 | [15 empty] | 2021-10-11 | 2021-10-26 | 11 | 2021-10-26 | 2021-10-26 | 0 |  |  |  |  | 2021-09-20 |  | 2021-09-20 |  |  | 2021-10-15
122077612 | 1657 | PGE | 93615 | NEM | EXPNEM | Commercial | Solar PV | 56.415 |  | 2021-09-21 |  |  | 2021-09-23 | 2021-09-23 | 2 | 2021-09-23 | 2 | 2021-10-05 | 8 | [15 empty] | 2021-10-05 | 2021-10-22 | 13 | 2021-10-22 | 2021-11-01 | 6 | [13 empty] | 2021-11-01 | 2021-11-09 | 6 | [15 empty] | 2021-11-01 | 2021-11-01 | 0 | 2021-11-09 |  | 2021-11-09 | 0
122077732 | 1658 | PGE | 93624 | NEM | EXPNEM | Study in Progress | Solar PV | 1680 |  | 2021-09-21 | 2021-09-23 |  | 2021-09-23 | 2021-09-23 | 2 | 2021-10-06 | 11 | [5 empty] | 2021-11-04 | 2021-11-30 | 15 | 2021-11-30 | 2021-12-08 | 6 | 2021-12-20 |  |  | 2021-12-08 | 2021-12-10 | 2 | [10 empty] | 2021-09-21 |  | 2021-09-21
122078973 | 1659 | PGE | 94598 | NEM | EXPNEM | Implementation | Solar PV | 150 |  | 2021-09-21 |  | 2021-10-12 | 2021-10-02 | 2021-10-02 | 8 | 2021-10-02 | 8 | 2021-11-15 | 29 | [15 empty] | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-18 | 3 |  |  |  |  | 2021-09-21 | 2021-10-26 | 2021-09-21 | 2021-10-26 | 25 | [7 empty] | 2021-12-14 | 2021-12-14 | 0
122079425 | 1660 | PGE | 94109 | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-09-21 |  | 2021-10-05 | 2021-10-05 | 2021-10-05 | 10 | 2021-12-16 | 59 | 2021-12-31 | 11 | [15 empty] | 2021-12-31
122081092 | 1661 | PGE | 93727 | NEM | EXPNEM | IA in Progress | Solar PV | 111 |  | 2021-09-21 |  | 2021-10-05 | 2021-10-05 | 2021-10-05 | 10 | 2021-12-01 | 48 | 2021-12-22 | 15 | [15 empty] | 2021-12-22
122082488 | 1662 | PGE | 93436 | NEM | EXPNEM | IA in Progress | Solar PV | 75 |  | 2021-09-22 |  | 2021-09-22 | 2021-09-22 | 2021-09-22 | 0 | 2021-10-22 | 22 | 2021-11-02 | 7 | [15 empty] | 2021-11-02 | 2021-11-02 | 0 | 2021-11-02 | [6 empty] | 2021-10-22 | 2021-10-22 | 2021-10-22 | 2021-11-03 | 8
122084597 | 1664 | PGE | 95401 | NEM | EXPNEM | Implementation | Solar PV | 46.4 |  | 2021-09-22 |  | 2021-10-06 | 2021-10-06 | 2021-10-06 | 10 | 2021-12-01 | 47 | 2021-12-22 | 15 | [15 empty] | 2021-12-22 | 2021-12-27 | 3 | 2021-12-27 | 2021-12-30 | 3 | [5 empty] | 2021-12-02 | 2021-12-02 | 2021-12-16 | 10
122084895 | 1665 | PGE | 95379 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 59.313 |  | 2021-09-22 |  | 2021-09-30 | 2021-09-30 | 2021-09-30 | 6 | 2021-10-08 | 12 | 2021-10-29 | 15 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | [6 empty] | 2021-09-22 |  | 2021-09-22 |  |  | 2021-10-15
122085093 | 1666 | PGE | 95379 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 35.9 |  | 2021-09-22 |  | 2021-09-30 | 2021-09-30 | 2021-09-30 | 6 | 2021-10-08 | 12 | 2021-10-29 | 15 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | [6 empty] | 2021-09-22 |  | 2021-09-22 |  |  | 2021-10-15
122085156 | 1667 | PGE | 94019 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 37.832 |  | 2021-09-22 |  | 2021-09-27 | 2021-09-27 | 2021-09-27 | 3 | 2021-10-05 | 9 | 2021-10-22 | 13 | [15 empty] | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | [6 empty] | 2021-09-22 | 2021-10-04 | 2021-09-22 | 2021-10-08 | 12
122085420 | 1668 | PGE | 93308 | NEM | EXPNEM | Implementation | Solar PV | 352.056 |  | 2021-09-22 |  | 2021-09-24 | 2021-09-24 | 2021-09-24 | 2 | 2021-09-28 | 4 | 2021-10-11 | 9 | [15 empty] | 2021-10-11 | 2021-10-26 | 11 | 2021-10-26 | 2021-10-26 | 0 |  |  |  |  | 2021-09-22 | 2021-09-28 | 2021-09-22 | 2021-10-07 | 11
122085443 | 1669 | PGE | 94019 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 37.832 |  | 2021-09-22 |  | 2021-09-27 | 2021-09-27 | 2021-09-27 | 3 | 2021-10-05 | 9 | 2021-10-22 | 13 | [15 empty] | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | [6 empty] | 2021-09-22 | 2021-10-04 | 2021-09-22 | 2021-10-08 | 12
122085445 | 1670 | PGE | 94019 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 37.832 |  | 2021-09-22 |  | 2021-09-27 | 2021-09-27 | 2021-09-27 | 3 | 2021-10-05 | 9 | 2021-11-19 | 32 | [15 empty] | 2021-11-19 | 2021-11-19 | 0 | 2021-11-19 | [6 empty] | 2021-09-22 | 2021-10-04 | 2021-09-22 | 2021-10-08 | 12
122086155 | 1671 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 116.058 |  | 2021-09-22 |  | 2021-09-24 | 2021-09-24 | 2021-09-24 | 2 | 2021-10-12 | 14 | 2021-10-15 | 3 | [15 empty] | 2021-10-15 | 2021-10-15 | 0 | 2021-10-15 | 2021-10-20 | 3 | [13 empty] | 2021-12-17 | 2021-12-17 | 0 | [15 empty] | 2021-12-17 | 2021-12-17 | 0 | 2021-12-17 |  | 2021-12-17 | 0
122088345 | 1672 | PGE | 94506 | NEM | VNEM | Application Review in Progress | Solar PV | 250 |  | 2021-09-23 |  | 2021-10-06 | 2021-10-06 | 2021-10-06 | 9 | [29 empty] | 2021-09-23 |  | 2021-09-23
122089083 | 1673 | PGE | 95620 | NEM | EXPNEM | Study in Progress | Solar PV | 658.3 |  | 2021-09-23 |  | 2021-10-06 | 2021-10-06 | 2021-10-06 | 9 | 2021-10-20 | 19 | 2021-11-10 | 15 | 2021-11-10 | 2021-12-20 | 25 | 2021-12-20
122089561 | 1674 | PGE | 95215 | NEM | EXPNEM | Study in Progress | Solar PV | 32.87 |  | 2021-09-23 |  |  | 2021-10-05 | 2021-10-05 | 8 | 2021-10-05 | 8 | 2021-10-22 | 13 | 2021-10-15 | 2021-11-10 | 18 | 2021-11-10 | 2021-12-07 | 16 | 2021-12-07 | [23 empty] | 2021-10-15
122091387 | 1675 | PGE | 95360 | NEM | EXPNEM | Implementation | Solar PV | 140.115 |  | 2021-09-23 |  |  | 2021-09-28 | 2021-09-28 | 3 | 2021-09-28 | 3 | 2021-10-15 | 13 | [15 empty] | 2021-11-01 | 2021-11-10 | 7 | 2021-11-10 | 2021-11-10 | 0 |  |  |  |  | 2021-09-23 |  | 2021-09-23 |  |  | 2021-10-14 | [6 empty] | 2021-11-17 |  | 39
122092226 | 1676 | PGE | 95519 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 420 |  | 2021-09-23 | 2021-09-24 |  | 2021-09-24 | 2021-09-24 | 1 | 2021-10-13 | 14 | 2021-11-16 | 23 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | [6 empty] | 2021-09-23 | 2021-12-21 | 2021-09-23
122096792 | 1677 | PGE | 93280 | NEM | EXPNEM | Implementation | Solar PV | 240 |  | 2021-09-24 |  |  | 2021-10-08 | 2021-10-08 | 10 | 2021-10-08 | 10 | 2021-10-29 | 15 | [15 empty] | 2021-10-29 | 2021-11-22 | 15 | 2021-11-22 | 2021-11-30 | 4
122098587 | 1678 | PGE | 95320 | NEM | EXPNEM | IA in Progress | Solar PV | 88.928 |  | 2021-09-24 |  | 2021-10-13 | 2021-09-28 | 2021-09-28 | 2 | 2021-10-19 | 17 | 2021-11-05 | 13 | [15 empty] | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05 | [6 empty] | 2021-09-24 | 2021-11-12 | 2021-09-24 | 2021-12-01 | 45
122098768 | 1679 | PGE | 95076 | NEM | EXPNEM | Implementation | Solar PV | 31.024 |  | 2021-09-24 |  | 2021-10-07 | 2021-10-07 | 2021-10-07 | 9 | 2021-11-01 | 26 | 2021-11-23 | 15 | [15 empty] | 2021-11-23 | 2021-11-23 | 0 | 2021-11-23 | 2021-12-01 | 4
122099156 | 1680 | PGE | 94402 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 36.423 |  | 2021-09-25 |  | 2021-12-01 | 2021-10-01 | 2021-10-01 | 4
122103113 | 1682 | PGE | 94538 | Non-NEM | Inadvertent Export | Application Accepted | Storage | 140.65 |  | 2021-09-26 | 2021-09-27 |  | 2021-09-27 | 2021-09-27 | 0 | 2021-11-03 | 27
122103987 | 1683 | PGE | 94904 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.15 |  | 2021-09-27 |  | 2021-10-01 | 2021-10-01 | 2021-10-01 | 4
122105342 | 1684 | PGE | 94563 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 30.232 |  | 2021-09-27 |  | 2021-10-08 | 2021-10-01 | 2021-10-01 | 4 | 2021-10-14 | 13 | 2021-10-14 | 0 | [25 empty] | 2021-09-27 | 2021-11-02 | 2021-09-27 | 2021-11-02 | 26 |  |  |  |  | 2021-11-02 | [17 empty] | 2021-11-02 | 2021-11-02 | 0
122105909 | 1685 | PGE | 95988 | NEM | EXPNEM | Application Review in Progress | Solar PV | 550 |  | 2021-09-27 |  | 2021-10-11 | 2021-10-11 | 2021-10-11 | 10 | [29 empty] | 2021-09-27 |  | 2021-09-27
122106679 | 1686 | PGE | 94558 | NEM | EXPNEM | IA in Progress | Solar PV | 51.694 |  | 2021-09-27 |  | 2021-09-28 | 2021-09-28 | 2021-09-28 | 1 | 2021-10-01 | 4 | 2021-10-15 | 10 | [15 empty] | 2021-10-15 | 2021-10-15 | 0 | 2021-10-15
122107197 | 1687 | PGE | 93706 | NEM | EXPNEM | Implementation | Solar PV | 244.589 |  | 2021-09-27 |  | 2021-10-27 | 2021-10-02 | 2021-10-02 | 4 | 2021-10-26 | 21 | 2021-11-05 | 8 | [15 empty] | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05 | 2021-11-09 | 2 |  |  |  |  | 2021-09-27 |  | 2021-09-27 | [9 empty] | 2021-12-07 |  | 27
122107411 | 1688 | PGE | 93609 | NEM | EXPNEM | Implementation | Solar PV | 146.753 |  | 2021-09-27 |  |  | 2021-09-30 | 2021-09-30 | 3 | 2021-10-15 | 14 | 2021-10-26 | 7 | [15 empty] | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26 | 2021-10-29 | 3 |  |  |  |  | 2021-10-20 |  | 2021-10-20
122109151 | 1689 | PGE | 94605 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 30.15 |  | 2021-09-28 |  |  | 2021-10-12 | 2021-10-12 | 10 | 2021-10-12 | 10 | 2021-11-19 | 27
122109295 | 1690 | PGE | 95691 | NEM | VNEM | Implementation | Solar PV | 40.372 |  | 2021-09-28 |  | 2021-09-29 | 2021-09-29 | 2021-09-29 | 1 | 2021-11-23 | 39 | 2021-12-14 | 13 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2021-12-20 | 4 | [5 empty] | 2021-12-22 | 2021-12-22
122109296 | 1691 | PGE | 95691 | NEM | VNEM | Implementation | Solar PV | 40.372 |  | 2021-09-28 |  | 2021-09-29 | 2021-09-29 | 2021-09-29 | 1 | 2021-11-23 | 39 | 2021-12-14 | 13 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2021-12-20 | 4 | [5 empty] | 2021-12-22 | 2021-12-22
122109642 | 1692 | PGE | 95370 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 429 |  | 2021-09-28 |  | 2021-10-12 | 2021-10-12 | 2021-10-12 | 10 | 2021-11-17 | 35 | 2021-12-20 | 21 | 2021-12-20
122112221 | 1693 | PGE | 95365 | NEM | EXPNEM | Implementation | Solar PV | 187.5 |  | 2021-09-28 |  | 2021-10-11 | 2021-10-11 | 2021-10-11 | 9 | 2021-10-15 | 13 | 2021-12-08 | 35 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | 2021-12-27 | 13 |  |  |  |  | 2021-09-28 | 2021-10-15 | 2021-09-28 | 2021-11-01 | 24
122113003 | 1694 | PGE | 95912 | NEM | EXPNEM | Commercial | Solar PV | 54.77 |  | 2021-09-28 |  | 2021-10-06 | 2021-10-06 | 2021-10-06 | 6 | 2021-10-11 | 9 | 2021-10-25 | 10 | [15 empty] | 2021-10-25 | 2021-10-25 | 0 | 2021-10-25 | 2021-11-24 | 21 | [13 empty] | 2021-11-29 | 2021-12-08 | 7 | [15 empty] | 2021-11-29 | 2021-11-30 | 1 | 2021-12-08 |  | 2021-12-08 | 0
122113186 | 1695 | PGE | 95128 | NEM | EXPNEM | Implementation | Solar PV | 904.446 |  | 2021-09-28 |  |  | 2021-10-08 | 2021-10-08 | 8 | 2021-10-08 | 8 | 2021-11-16 | 26 | [15 empty] | 2021-11-16 | 2021-12-02 | 10 | 2021-12-02 | 2021-12-02 | 0 |  |  |  |  | 2021-09-28 |  | 2021-09-28
122113265 | 1696 | PGE | 94549 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.08 |  | 2021-09-28 |  | 2021-10-01 | 2021-10-01 | 2021-10-01 | 3
122115847 | 1697 | PGE | 94558 | NEM | EXPNEM | IA in Progress | Solar PV | 133.2 |  | 2021-09-28 |  | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2 | 2021-10-04 | 4 | 2021-10-19 | 11 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19
122117671 | 1698 | PGE | 94558 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.204 |  | 2021-09-29 |  | 2021-09-30 | 2021-09-30 | 2021-09-30 | 1 | 2021-10-28 | 21 | 2021-11-01 | 2 | [26 empty] | 2021-11-02 | 2021-11-02 | 2021-11-02 | 0 |  |  |  |  | 2021-11-02 | 2021-11-02 | 0 | [15 empty] | 2021-11-02 |  |  | 2021-11-02 |  | 2021-11-03 | 1
122118348 | 1699 | PGE | 96021 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 49.411 |  | 2021-09-29 |  | 2021-10-13 | 2021-10-13 | 2021-10-13 | 10 | 2021-10-19 | 14 | 2021-11-09 | 15 | [15 empty] | 2021-11-09 | 2021-12-03 | 15 | 2021-12-03 | [6 empty] | 2021-09-29 | 2021-11-02 | 2021-09-29 | 2021-12-15 | 52 |  | 2021-12-29 | 2021-12-29 | 0
122118512 | 1700 | PGE | 96021 | NEM | VNEMSOMAH | Withdrawn | Solar PV | 45.634 |  | 2021-09-29 |  | 2021-10-13 | 2021-10-13 | 2021-10-13 | 10 | 2021-10-19 | 14 | 2021-11-09 | 15 | [15 empty] | 2021-11-09 | [9 empty] | 2021-09-29 | 2021-11-02 | 2021-09-29
122119191 | 1701 | PGE | 95327 | NEM | EXPNEM | Commercial | Solar PV | 39.46 |  | 2021-09-29 |  | 2021-10-11 | 2021-10-11 | 2021-10-11 | 8 | 2021-10-20 | 15 | 2021-11-03 | 10 | [15 empty] | 2021-11-03 | 2021-11-03 | 0 | 2021-11-03 | 2021-11-05 | 2 | [13 empty] | 2021-11-23 | 2021-11-30 | 3 | [15 empty] | 2021-11-23 | 2021-11-23 | 0 | 2021-11-30 |  | 2021-12-06 | 4
122121898 | 1702 | PGE | 93727 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 1331.879 |  | 2021-09-29 |  | 2021-10-13 | 2021-10-13 | 2021-10-13 | 10
122123584 | 1703 | PGE | 94952 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 342 |  | 2021-09-29 |  | 2021-10-13 | 2021-10-13 | 2021-10-13 | 10 | 2021-11-08 | 28 | [27 empty] | 2021-09-29 |  | 2021-09-29
122124912 | 1704 | PGE | 94513 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 117.6 |  | 2021-09-30 |  | 2021-10-11 | 2021-10-11 | 2021-10-11 | 7
122125202 | 1705 | PGE | 94025 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.775 |  | 2021-09-30 |  | 2021-12-03 | 2021-10-07 | 2021-10-07 | 5
122125257 | 1706 | PGE | 95301 | NEM | NEM Paired Storage | Study in Progress | ENGN, Solar PV, Storage | 9516.518 |  | 2021-09-30 | 2021-10-04 |  | 2021-09-30 | 2021-09-30 | 0 | 2021-10-20 | 14 | [27 empty] | 2021-09-30 |  | 2021-09-30
122126846 | 1707 | PGE | 93446 | NEM | EXPNEM | IA in Progress | Solar PV | 35.5 |  | 2021-09-30 |  | 2021-10-06 | 2021-10-06 | 2021-10-06 | 4 | 2021-11-15 | 31 | 2021-12-02 | 11 | [15 empty] | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02
122127005 | 1708 | PGE | 95019 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.49 |  | 2021-09-30 |  | 2021-10-14 | 2021-10-14 | 2021-10-14 | 10 | 2021-10-19 | 13 | 2021-12-03 | 30 | [15 empty] | 2021-12-03 | 2021-12-03 | 0 | 2021-12-03 | [6 empty] | 2021-09-30 | 2021-11-02 | 2021-09-30 | 2021-12-15 | 51 |  | 2021-12-29
122128598 | 1709 | PGE | 94586 | Non-NEM | Continuous Uncompensated Export | IA in Progress | Solar PV | 57.71 |  | 2021-09-30 | 2021-10-01 |  | 2021-10-01 | 2021-10-01 | 1 | 2021-10-06 | 4 | 2021-11-19 | 31 | [15 empty] | 2021-11-19 | 2021-12-14 | 15 | 2021-12-14
122129592 | 1710 | PGE | 94027 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 72.405 |  | 2021-09-30 |  | 2021-10-19 | 2021-10-04 | 2021-10-04 | 2
122129742 | 1711 | PGE | 94566 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 32.781 |  | 2021-09-30 |  | 2021-10-04 | 2021-10-04 | 2021-10-04 | 2 | 2021-10-20 | 14 | 2021-10-23 | 2 | [25 empty] | 2021-09-30 | 2021-11-11 | 2021-09-30 | 2021-11-11 | 29 |  |  |  |  | 2021-11-11 | 2021-11-22 | 6 | [15 empty] | 2021-11-11 | 2021-11-11 | 0 | 2021-11-22 |  | 2021-11-24 | 2
122130114 | 1712 | PGE | 93727 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 3065.042 |  | 2021-09-30 | 2021-10-04 |  | 2021-10-04 | 2021-10-04 | 2
122130667 | 1713 | PGE | 95035 | NEM | EXPNEM | Application Accepted | ENGN, Solar PV | 482 |  | 2021-09-30 | 2021-10-04 |  | 2021-10-04 | 2021-10-04 | 2 | 2021-10-20 | 14 | [27 empty] | 2021-09-30 | 2021-11-22 | 2021-09-30 | 2021-12-07 | 45 | 2021-12-07
120467593 | 1714 | PGE | 94904 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-01-27 |  |  | 2021-02-08 | 2021-02-08 | 8 | 2021-02-08 | 8 | 2021-02-09 | 1 | [55 empty] | 2021-02-08 |  | 2021-03-10 | 23
120535961 | 1715 | PGE | 94062 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-02-16 |  |  | 2021-02-25 | 2021-02-25 | 7 | 2021-02-25 | 7 | 2021-03-03 | 4 | [55 empty] | 2021-02-25 |  | 2021-03-08 | 8
120575690 | 1716 | PGE | 95070 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-02-25 |  |  | 2021-03-08 | 2021-03-08 | 7 | 2021-03-08 | 7 | 2021-03-11 | 3 | [55 empty] | 2021-03-08 |  | 2021-04-09 | 25
120600005 | 1717 | PGE | 94563 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-03-03 | 2021-03-16 |  | 2021-03-16 | 2021-03-16 | 9 | 2021-04-01 | 21 | 2021-04-07 | 4 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-07 | 0 | [34 empty] | 2021-03-16 |  | 2021-04-13 | 21
120635484 | 1718 | PGE | 94044 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-03-11 |  |  | 2021-03-25 | 2021-03-25 | 10 | 2021-03-25 | 10 | 2021-04-07 | 9 | [15 empty] | 2021-03-11 | 2021-03-11 |  | 2021-03-11 | 2021-05-05 | 40 | [34 empty] | 2021-05-01 |  | 2021-05-06 | 4
120644894 | 1719 | PGE | 94941 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-03-15 |  |  | 2021-03-30 | 2021-03-30 | 11 | 2021-04-09 | 19 | 2021-04-14 | 3 | [15 empty] | 2021-04-09 | 2021-04-09 |  | 2021-04-09 | 2021-05-14 | 26 | [34 empty] | 2021-05-12 |  | 2021-06-07 | 19
120654831 | 1720 | PGE | 95448 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-03-17 |  |  | 2021-03-31 | 2021-03-31 | 10 | 2021-05-07 | 37 | 2021-05-14 | 5 | [15 empty] | 2021-03-17 | 2021-03-17 |  | 2021-03-17 | 2021-07-22 | 92 | [34 empty] | 2021-06-24 |  | 2021-07-22 | 21
120826983 | 1721 | PGE | 94526 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-04-16 |  |  | 2021-04-30 | 2021-04-30 | 10 | 2021-04-30 | 10 | 2021-05-04 | 2 | [15 empty] | 2021-04-16 | 2021-04-16 |  | 2021-04-16 | 2021-05-04 | 13 | [34 empty] | 2021-05-04 |  | 2021-05-12 | 7
120882338 | 1722 | PGE | 94941 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-04-26 |  |  | 2021-05-10 | 2021-05-10 | 10 | 2021-05-25 | 21 | 2021-06-02 | 5 | [15 empty] | 2021-04-26 | 2021-04-26 |  | 2021-04-26 | 2021-06-02 | 28 | [34 empty] | 2021-06-02 |  | 2021-06-04 | 3
120885594 | 1723 | PGE | 95713 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-04-26 | 2021-05-10 |  | 2021-05-10 | 2021-05-10 | 10 | 2021-05-24 | 20 | 2021-06-01 | 5 | [15 empty] | 2021-06-01 | 2021-06-01 | 0 | 2021-06-01 | 2021-06-01 | 0 | [34 empty] | 2021-05-10 |  | 2021-06-01 | 17
121355006 | 1724 | PGE | 94803 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-05-18 |  |  | 2021-05-25 | 2021-05-25 | 5 | 2021-05-25 | 5 | 2021-09-13 | 76 | [15 empty] | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-09-03 | 71 | [34 empty] | 2021-08-26 |  | 2021-09-13 | 13
121443452 | 1725 | PGE | 94563 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-06-02 |  |  | 2021-06-16 | 2021-06-16 | 10 | 2021-06-16 | 10 | 2021-06-30 | 10 | [15 empty] | 2021-06-02 | 2021-06-02 |  | 2021-06-02 | 2021-06-30 | 21 | [34 empty] | 2021-06-30 |  | 2021-06-30 | 1
121592973 | 1726 | PGE | 95667 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-06-24 |  |  | 2021-07-09 | 2021-07-09 | 10 | 2021-07-09 | 10 | 2021-07-23 | 10 | [15 empty] | 2021-07-23 | 2021-07-28 | 3 | 2021-07-28 | 2021-07-28 | 0 | [34 empty] | 2021-07-09 |  | 2021-07-28 | 14
121807258 | 1727 | PGE | 94025 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-07-28 |  |  | 2021-08-03 | 2021-08-03 | 4 | 2021-08-12 | 11 | 2021-08-13 | 1 | [15 empty] | 2021-08-13 | 2021-08-13 | 0 | 2021-08-13 | 2021-10-05 | 36 | [34 empty] | 2021-10-06 |  | 2021-10-06 | 1
121891950 | 1728 | PGE | 95949 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-08-12 |  |  | 2021-08-24 | 2021-08-24 | 8 | 2021-08-24 | 8 | 2021-09-08 | 10 | [15 empty] | 2021-08-12 | 2021-08-12 |  | 2021-08-12 | 2021-09-22 | 30 | [34 empty] | 2021-09-22 |  | 2021-09-22 | 1
121955970 | 1729 | PGE | 95018 | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-08-25 |  |  | 2021-09-09 | 2021-09-09 | 10 | 2021-09-09 | 10 | 2021-09-10 | 1 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | 2021-09-10 | 0 | [34 empty] | 2021-09-09 |  | 2021-09-16 | 6
122079395 | 1730 | PGE | 95229 | Non-NEM | Inadvertent Export | Commercial | Storage | 5 |  | 2021-09-21 | 2021-10-05 |  | 2021-10-05 | 2021-10-05 | 10 | 2021-10-19 | 20 | 2021-10-26 | 5 | [55 empty] | 2021-10-19 |  | 2021-11-02 | 11
120633074 | 1731 | PGE | 94536 | Non-NEM | Non-Export | IA in Progress | Storage | 5 |  | 2021-03-11 |  |  | 2021-03-25 | 2021-03-25 | 10 | 2021-03-25 | 10 | 2021-04-14 | 14
120661827 | 1732 | PGE | 94941 | Non-NEM | Non-Export | IA in Progress | Storage | 5 |  | 2021-03-19 |  |  | 2021-04-01 | 2021-04-01 | 9 | 2021-04-01 | 9 | 2021-04-07 | 4
120794130 | 1733 | PGE | 95006 | Non-NEM | Non-Export | IA in Progress | Storage | 5 |  | 2021-04-12 |  |  | 2021-04-17 | 2021-04-17 | 4 | 2021-04-17 | 4 | 2021-04-19 | 0 | [15 empty] | 2021-04-12 | 2021-04-12 |  | 2021-04-12 | 2021-04-12 | 1
120744638 | 1734 | PGE | 94970 | Non-NEM | Non-Export | Study in Progress | Storage | 5 |  | 2021-04-05 | 2021-04-19 |  | 2021-04-19 | 2021-04-19 | 10 | 2021-05-20 | 33 | 2021-06-03 | 9 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-06-03 | 32
121912129 | 1735 | PGE | 94558 | Non-NEM | Non-Export | Study in Progress | Storage | 5.5 |  | 2021-08-17 | 2021-08-31 |  | 2021-08-31 | 2021-08-31 | 10 | 2021-09-15 | 20
120497288 | 1736 | PGE | 95018 | Non-NEM | Non-Export | Application Accepted | Storage | 10 |  | 2021-02-03 |  |  | 2021-02-16 | 2021-02-16 | 8 | 2021-02-16 | 8 | 2021-02-16 | 0
120672243 | 1737 | PGE | 93644 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-03-22 |  |  | 2021-04-05 | 2021-04-05 | 10 | 2021-12-08 | 181 | 2021-12-23 | 11 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08
120741010 | 1738 | PGE | 95959 | Non-NEM | Non-Export | Application Accepted | Storage | 10 |  | 2021-04-04 |  |  | 2021-04-14 | 2021-04-14 | 7 | 2021-04-14 | 7 | 2021-04-25 | 7 | [15 empty] | 2021-04-25 | 2021-04-25 | 0 | 2021-04-25 | 2021-06-29 | 45
120594813 | 1739 | PGE | 95070 | Non-NEM | Non-Export | Application Review in Progress | Storage | 10 |  | 2021-03-03 | 2021-03-17 |  | 2021-03-17 | 2021-03-17 | 10
120400357 | 1740 | PGE | 96021 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-07 |  |  | 2021-01-12 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-26 | 9 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-03-11 | 40 | [34 empty] | 2021-10-13 |  | 2021-10-20 | 6
120401555 | 1741 | PGE | 95650 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-07 |  |  | 2021-01-12 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-14 | 2 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-02-12 | 22 | [34 empty] | 2021-07-30 |  | 2021-08-11 | 9
120435015 | 1742 | PGE | 94010 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-15 | 2021-01-26 |  | 2021-01-26 | 2021-01-26 | 6 | 2021-01-29 | 9 | 2021-02-01 | 1 | [15 empty] | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 2021-08-07 | 135 | [34 empty] | 2021-08-13 |  | 2021-08-13 | 1
120451197 | 1743 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-20 |  |  | 2021-01-26 | 2021-01-26 | 4 | 2021-01-26 | 4 | 2021-01-26 | 0 | [55 empty] | 2021-01-26 |  | 2021-02-09 | 11
120452364 | 1744 | PGE | 94549 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-21 |  |  | 2021-01-26 | 2021-01-26 | 3 | 2021-01-26 | 3 | 2021-01-28 | 2 | [55 empty] | 2021-01-26 |  | 2021-02-09 | 11
120461884 | 1745 | PGE | 95633 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-25 |  |  | 2021-02-05 | 2021-02-05 | 9 | 2021-02-05 | 9 | 2021-02-12 | 5 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | 2021-03-30 | 36 | [34 empty] | 2021-05-05 |  | 2021-05-05 | 1
120461885 | 1746 | PGE | 94028 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-25 |  |  | 2021-02-08 | 2021-02-08 | 10 | 2021-02-08 | 10 | 2021-02-12 | 4 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-04-13 | 45 | [34 empty] | 2021-07-12 |  | 2021-07-12 | 1
120462283 | 1747 | PGE | 94903 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-25 | 2021-02-03 |  | 2021-02-03 | 2021-02-03 | 7 | 2021-03-01 | 24 | 2021-03-03 | 2 | [55 empty] | 2021-02-03 |  | 2021-03-10 | 26
120462480 | 1748 | PGE | 95006 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-25 |  |  | 2021-02-03 | 2021-02-03 | 7 | 2021-02-03 | 7 | 2021-02-04 | 1 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-02-11 | 6 | [34 empty] | 2021-07-30 |  | 2021-07-30 | 1
120462603 | 1749 | PGE | 94939 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-25 |  |  | 2021-02-03 | 2021-02-03 | 7 | 2021-02-03 | 7 | 2021-02-05 | 2 | [55 empty] | 2021-02-03 |  | 2021-02-11 | 7
120464496 | 1750 | PGE | 93420 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-26 |  |  | 2021-02-03 | 2021-02-03 | 6 | 2021-02-03 | 6 | 2021-02-04 | 1 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-02-03 | 0 | [34 empty] | 2021-02-03 |  | 2021-04-06 | 45
120466021 | 1751 | PGE | 95667 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-26 |  |  | 2021-02-08 | 2021-02-08 | 9 | 2021-02-08 | 9 | 2021-02-08 | 0 | [55 empty] | 2021-02-08 |  | 2021-03-03 | 18
120486478 | 1752 | PGE | 94062 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-01 |  |  | 2021-02-08 | 2021-02-08 | 5 | 2021-02-08 | 5 | 2021-02-12 | 4 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-03-25 | 32 | [34 empty] | 2021-05-28 |  | 2021-05-28 | 1
120486725 | 1753 | PGE | 95726 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-01 |  |  | 2021-02-13 | 2021-02-13 | 9 | 2021-02-13 | 9 | 2021-02-23 | 5 | [15 empty] | 2021-02-13 | 2021-02-13 | 0 | 2021-02-13 | 2021-04-02 | 33 | [34 empty] | 2021-04-11 |  | 2021-04-11 | 0
120490162 | 1754 | PGE | 93460 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-02 |  |  | 2021-02-13 | 2021-02-13 | 8 | 2021-02-13 | 8 | 2021-02-24 | 6 | [55 empty] | 2021-06-02 |  | 2021-06-03 | 2
120492171 | 1755 | PGE | 94901 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-02 |  |  | 2021-02-16 | 2021-02-16 | 9 | 2021-02-16 | 9 | 2021-02-16 | 0 | [15 empty] | 2021-02-16 | 2021-02-16 | 0 | 2021-02-16 | 2021-03-17 | 21 | [34 empty] | 2021-10-11 |  | 2021-10-20 | 8
120496874 | 1756 | PGE | 94028 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-03 |  |  | 2021-02-16 | 2021-02-16 | 8 | 2021-02-16 | 8 | 2021-02-18 | 2 | [55 empty] | 2021-02-16 |  | 2021-02-23 | 6
120501286 | 1757 | PGE | 95667 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-04 |  |  | 2021-02-18 | 2021-02-18 | 9 | 2021-02-18 | 9 | 2021-03-10 | 14 | [15 empty] | 2021-02-18 | 2021-02-18 |  | 2021-02-18 | 2021-03-07 | 12 | [13 empty] | 2021-04-01 | 2021-04-01 | 0 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 |  | 2021-04-01 | 0
120503211 | 1758 | PGE | 95762 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-05 |  |  | 2021-02-22 | 2021-02-22 | 10 | 2021-02-22 | 10 | 2021-02-25 | 3 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-06-24 | 87 | [34 empty] | 2021-07-08 |  | 2021-07-08 | 1
120503916 | 1759 | PGE | 95070 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-05 |  |  | 2021-02-22 | 2021-02-22 | 10 | 2021-02-22 | 10 | 2021-03-02 | 6 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-02 | 6 | [34 empty] | 2021-03-02 |  | 2021-03-12 | 9
120524726 | 1760 | PGE | 93420 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-10 |  |  | 2021-02-22 | 2021-02-22 | 7 | 2021-02-22 | 7 | 2021-02-22 | 0 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-01 | 5 | [5 empty] | 2021-03-17 | 2021-03-17 | 2021-03-24 | 5 | [25 empty] | 2021-02-22 |  | 2021-04-06 | 32
120530915 | 1761 | PGE | 95425 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-12 |  |  | 2021-02-23 | 2021-02-23 | 6 | 2021-02-23 | 6 | 2021-04-05 | 29 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-05-27 | 67 | [34 empty] | 2021-08-20 |  | 2021-09-08 | 14
120534279 | 1762 | PGE | 95728 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-14 |  |  | 2021-02-23 | 2021-02-23 | 5 | 2021-02-23 | 5 | 2021-02-23 | 0 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-05-26 | 66 | [34 empty] | 2021-08-24 |  | 2021-08-24 | 1
120540812 | 1763 | PGE | 95248 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-17 |  |  | 2021-02-25 | 2021-02-25 | 6 | 2021-02-25 | 6 | 2021-03-03 | 4 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-18 | 15 | [34 empty] | 2021-08-03 |  | 2021-08-09 | 5
120552024 | 1764 | PGE | 95945 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-18 |  |  | 2021-02-25 | 2021-02-25 | 5 | 2021-02-25 | 5 | 2021-03-16 | 13 | [25 empty] | 2021-02-18 | 2021-03-17 | 2021-02-18 | 2021-03-24 | 24 | [25 empty] | 2021-02-25 |  | 2021-03-25 | 21
120558070 | 1765 | PGE | 95521 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-21 | 2021-02-25 |  | 2021-02-25 | 2021-02-25 | 3 | 2021-02-26 | 4 | 2021-03-01 | 1 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-17 | 12 | [34 empty] | 2021-02-25 |  | 2021-03-30 | 24
120565306 | 1766 | PGE | 95603 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-22 |  |  | 2021-03-03 | 2021-03-03 | 7 | 2021-03-03 | 7 | 2021-03-08 | 3 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-03 | 0 | [34 empty] | 2021-03-09 |  | 2021-03-10 | 2
120575609 | 1767 | PGE | 95975 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-25 |  |  | 2021-03-08 | 2021-03-08 | 7 | 2021-03-08 | 7 | 2021-03-09 | 1 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-04-19 | 30 | [34 empty] | 2021-06-22 |  | 2021-07-09 | 14
120580616 | 1768 | PGE | 95120 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-26 |  |  | 2021-03-09 | 2021-03-09 | 7 | 2021-03-09 | 7 | 2021-03-22 | 9 | [15 empty] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | 2021-03-30 | 15 | [34 empty] | 2021-09-29 |  | 2021-09-29 | 1
120581185 | 1769 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-26 |  |  | 2021-03-09 | 2021-03-09 | 7 | 2021-03-09 | 7 | 2021-03-11 | 2 | [55 empty] | 2021-03-09 |  | 2021-03-17 | 7
120599769 | 1770 | PGE | 93420 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-03 | 2021-03-15 |  | 2021-03-12 | 2021-03-12 | 7 | 2021-03-17 | 10 | 2021-03-23 | 4 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-18 | 1 | [34 empty] | 2021-08-24 |  | 2021-08-24 | 1
120600141 | 1771 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-03 |  |  | 2021-03-15 | 2021-03-15 | 8 | 2021-03-15 | 8 | 2021-03-17 | 2 | [15 empty] | 2021-03-03 | 2021-03-03 |  | 2021-03-03 | 2021-03-03 | 1 | [34 empty] | 2021-04-07 |  | 2021-04-07 | 1
120602655 | 1772 | PGE | 94553 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-04 |  |  | 2021-03-17 | 2021-03-17 | 9 | 2021-03-17 | 9 | 2021-03-23 | 4 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-24 | 5 | [36 empty] | 2021-04-07
120606001 | 1773 | PGE | 95667 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-05 |  |  | 2021-03-22 | 2021-03-22 | 11 | 2021-07-08 | 87 | 2021-07-28 | 14 | [15 empty] | 2021-07-08 | 2021-07-08 |  | 2021-07-08 | 2021-07-26 | 13 | [34 empty] | 2021-07-08 |  | 2021-07-28 | 15
120611909 | 1774 | PGE | 94941 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-08 |  |  | 2021-03-22 | 2021-03-22 | 10 | 2021-03-22 | 10 | 2021-03-29 | 5 | [15 empty] | 2021-03-29 | 2021-04-01 | 3 | 2021-04-01 | 2021-04-13 | 8 | [34 empty] | 2021-04-29 |  | 2021-04-29 | 1
120628659 | 1775 | PGE | 94549 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-10 |  |  | 2021-03-24 | 2021-03-24 | 10 | 2021-03-24 | 10 | 2021-04-01 | 6 | [15 empty] | 2021-03-10 | 2021-03-10 |  | 2021-03-10 | 2021-03-25 | 12 | [34 empty] | 2021-03-25 |  | 2021-04-07 | 10
120628690 | 1776 | PGE | 95685 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-10 |  |  | 2021-03-24 | 2021-03-24 | 10 | 2021-03-24 | 10 | 2021-04-01 | 6 | [15 empty] | 2021-03-10 | 2021-03-10 |  | 2021-03-10 | 2021-03-25 | 12 | [34 empty] | 2021-03-10 |  | 2021-05-04 | 40
120633085 | 1777 | PGE | 95018 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-11 |  |  | 2021-03-25 | 2021-03-25 | 10 | 2021-03-25 | 10 | 2021-04-01 | 5 | [15 empty] | 2021-03-11 | 2021-03-11 |  | 2021-03-11 | 2021-03-11 | 1 | [34 empty] | 2021-04-07 |  | 2021-05-05 | 21
120635500 | 1778 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-11 |  |  | 2021-03-25 | 2021-03-25 | 10 | 2021-03-25 | 10 | 2021-04-06 | 8 | [15 empty] | 2021-03-11 | 2021-03-11 |  | 2021-03-11 | 2021-03-11 | 1 | [34 empty] | 2021-05-05 |  | 2021-05-05 | 1
120635575 | 1779 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-11 |  |  | 2021-03-25 | 2021-03-25 | 10 | 2021-03-25 | 10 | 2021-04-06 | 8 | [15 empty] | 2021-03-11 | 2021-03-11 |  | 2021-03-11 | 2021-03-11 | 1 | [34 empty] | 2021-05-05 |  | 2021-05-05 | 1
120654562 | 1780 | PGE | 94402 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-17 |  |  | 2021-03-31 | 2021-03-31 | 10 | 2021-03-31 | 10 | 2021-04-07 | 5 | [15 empty] | 2021-03-17 | 2021-03-17 |  | 2021-03-17 | 2021-03-17 | 1 | [34 empty] | 2021-05-06 |  | 2021-05-06 | 1
120685662 | 1781 | PGE | 93401 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-24 |  |  | 2021-04-07 | 2021-04-07 | 10 | 2021-04-07 | 10 | 2021-04-09 | 2 | [15 empty] | 2021-03-24 | 2021-03-24 |  | 2021-03-24 | 2021-07-06 | 75 | [34 empty] | 2021-03-24 |  | 2021-07-06 | 75
120689723 | 1782 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-25 |  |  | 2021-04-08 | 2021-04-08 | 10 | 2021-04-08 | 10 | 2021-04-16 | 6 | [15 empty] | 2021-03-25 | 2021-03-25 |  | 2021-03-25 | 2021-03-25 | 1 | [34 empty] | 2021-05-07 |  | 2021-05-07 | 1
120696381 | 1783 | PGE | 93420 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-26 |  |  | 2021-04-02 | 2021-04-02 | 5 | 2021-04-02 | 5 | 2021-04-09 | 5 | [15 empty] | 2021-03-26 | 2021-03-26 |  | 2021-03-26 | 2021-04-02 | 6 | [34 empty] | 2021-04-09 |  | 2021-04-15 | 5
120704109 | 1784 | PGE | 95501 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-28 |  |  | 2021-04-09 | 2021-04-09 | 9 | 2021-04-29 | 23 | 2021-05-05 | 4 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-06-29 | 38 | [34 empty] | 2021-09-06 |  | 2021-09-09 | 4
120726826 | 1785 | PGE | 95614 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-01 |  |  | 2021-04-14 | 2021-04-14 | 9 | 2021-04-14 | 9 | 2021-04-20 | 4 | [15 empty] | 2021-04-14 | 2021-04-14 | 0 | 2021-04-14 | 2021-05-03 | 13 | [34 empty] | 2021-04-14 |  | 2021-06-02 | 36
120742775 | 1786 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-05 |  |  | 2021-04-16 | 2021-04-16 | 9 | 2021-04-16 | 9 | 2021-04-21 | 3 | [55 empty] | 2021-04-16 |  | 2021-04-29 | 10
120750931 | 1787 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-06 | 2021-04-17 |  | 2021-04-17 | 2021-04-17 | 8 | 2021-05-03 | 19 | 2021-05-03 | 0 | [55 empty] | 2021-05-03 |  | 2021-05-11 | 7
120823253 | 1788 | PGE | 95959 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-15 |  |  | 2021-04-29 | 2021-04-29 | 10 | 2021-05-12 | 19 | 2021-05-12 | 0 | [15 empty] | 2021-04-15 | 2021-04-15 |  | 2021-04-15 | 2021-05-12 | 20 | [34 empty] | 2021-05-12 |  | 2021-05-12 | 1
120841745 | 1789 | PGE | 93446 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-19 |  |  | 2021-05-03 | 2021-05-03 | 10 | 2021-05-07 | 14 | 2021-06-04 | 19 | [15 empty] | 2021-04-19 | 2021-04-19 |  | 2021-04-19 | 2021-06-04 | 35 | [34 empty] | 2021-10-19 |  | 2021-10-27 | 7
120863835 | 1790 | PGE | 95065 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-22 |  |  | 2021-05-06 | 2021-05-06 | 10 | 2021-05-12 | 14 | 2021-05-12 | 0 | [15 empty] | 2021-04-22 | 2021-04-22 |  | 2021-04-22 | 2021-05-12 | 15 | [34 empty] | 2021-05-12 |  | 2021-05-12 | 1
120882323 | 1791 | PGE | 94708 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-26 |  |  | 2021-05-10 | 2021-05-10 | 10 | 2021-05-25 | 21 | 2021-06-16 | 15 | [15 empty] | 2021-04-26 | 2021-04-26 |  | 2021-04-26 | 2021-06-16 | 38 | [34 empty] | 2021-06-16 |  | 2021-06-16 | 1
120891705 | 1792 | PGE | 94552 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-27 |  |  | 2021-05-11 | 2021-05-11 | 10 | 2021-05-18 | 15 | 2021-05-26 | 6 | [15 empty] | 2021-04-27 | 2021-04-27 |  | 2021-04-27 | 2021-05-26 | 22 | [34 empty] | 2021-05-26 |  | 2021-05-28 | 3
120893493 | 1793 | PGE | 95667 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-28 |  |  | 2021-05-12 | 2021-05-12 | 10 | 2021-05-12 | 10 | 2021-05-20 | 6 | [55 empty] | 2021-05-12 |  | 2021-05-20 | 7
120910166 | 1794 | PGE | 95959 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-30 |  |  | 2021-05-14 | 2021-05-14 | 10 | 2021-05-14 | 10 | 2021-05-18 | 2 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | 2021-06-22 | 24 | [34 empty] | 2021-06-22 |  | 2021-06-23 | 2
121030318 | 1795 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-10 |  |  | 2021-05-24 | 2021-05-24 | 10 | 2021-05-24 | 10 | 2021-06-09 | 11 | [15 empty] | 2021-05-10 | 2021-05-10 |  | 2021-05-10 | 2021-06-09 | 23 | [34 empty] | 2021-06-28 |  | 2021-06-30 | 3
121334719 | 1796 | PGE | 95003 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-14 | 2021-05-25 |  | 2021-05-25 | 2021-05-25 | 7 | 2021-06-03 | 13 | 2021-06-08 | 3 | [15 empty] | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-06-08 | 0 | [34 empty] | 2021-06-08 |  | 2021-06-08 | 1
121334767 | 1797 | PGE | 95004 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-14 | 2021-05-25 |  | 2021-05-25 | 2021-05-25 | 7 | 2021-06-03 | 13 | 2021-06-07 | 2 | [15 empty] | 2021-05-14 | 2021-05-14 |  | 2021-05-14 | 2021-05-14 | 1 | [34 empty] | 2021-05-25 |  | 2021-06-07 | 10
121351089 | 1798 | PGE | 95065 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-18 |  |  | 2021-05-28 | 2021-05-28 | 8 | 2021-05-28 | 8 | 2021-06-02 | 2 | [15 empty] | 2021-05-18 | 2021-05-18 | 11 | 2021-05-18 | 2021-06-01 | 11 | [34 empty] | 2021-05-18 |  | 2021-06-17 | 23
121364798 | 1799 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-20 | 2021-06-01 |  | 2021-06-01 | 2021-06-01 | 7 | 2021-06-15 | 17 | 2021-06-24 | 7 | [15 empty] | 2021-06-24 | 2021-06-25 | 1 | 2021-06-25 | 2021-06-25 | 0 | [34 empty] | 2021-06-25 |  | 2021-06-25 | 1
121391379 | 1800 | PGE | 95688 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-24 |  |  | 2021-06-04 | 2021-06-04 | 8 | 2021-07-30 | 47 | 2021-08-11 | 8 | [15 empty] | 2021-07-30 | 2021-07-30 | 0 | 2021-07-30 | 2021-08-11 | 8 | [34 empty] | 2021-08-12 |  | 2021-08-12 | 1
121396580 | 1801 | PGE | 95120 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-25 |  |  | 2021-06-01 | 2021-06-01 | 4 | 2021-06-01 | 4 | 2021-06-11 | 8 | [15 empty] | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-09-21 | 70 | [13 empty] | 2021-09-21 | 2021-09-29 | 6 | [15 empty] | 2021-09-21 | 2021-09-29 | 6 | 2021-09-29 |  | 2021-09-29 | 0
121534459 | 1802 | PGE | 95066 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-06-14 |  |  | 2021-06-25 | 2021-06-25 | 9 | 2021-06-25 | 9 | 2021-06-30 | 3 | [55 empty] | 2021-06-30 |  | 2021-07-28 | 21
121547656 | 1803 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-06-16 | 2021-06-21 |  | 2021-06-21 | 2021-06-21 | 3 | 2021-06-22 | 4 | 2021-06-23 | 1 | [55 empty] | 2021-07-09 |  | 2021-07-09 | 1
121555775 | 1804 | PGE | 95060 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-06-17 |  |  | 2021-06-21 | 2021-06-21 | 2 | 2021-06-21 | 2 | 2021-06-23 | 2 | [55 empty] | 2021-06-29 |  | 2021-06-29 | 1
121596606 | 1805 | PGE | 95709 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-06-24 | 2021-06-29 |  | 2021-06-29 | 2021-06-29 | 3 | 2021-07-12 | 11 | 2021-07-14 | 2 | [15 empty] | 2021-07-14 | 2021-07-14 |  | 2021-07-14 | 2021-06-29 | 1 | [34 empty] | 2021-07-14 |  | 2021-07-14 | 1
121646889 | 1806 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-01 | 2021-07-06 |  | 2021-07-06 | 2021-07-06 | 2 | 2021-07-07 | 3 | 2021-07-08 | 1 | [15 empty] | 2021-07-08 | 2021-07-13 | 3 | 2021-07-13 | 2021-07-13 | 0 | [34 empty] | 2021-07-06 |  | 2021-07-14 | 7
121647350 | 1807 | PGE | 93637 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-01 |  |  | 2021-07-06 | 2021-07-06 | 2 | 2021-07-06 | 2 | 2021-07-26 | 14 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-07-28 | 2 | [34 empty] | 2021-09-27 |  | 2021-09-27 | 1
121683273 | 1808 | PGE | 94605 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-08 |  |  | 2021-07-13 | 2021-07-13 | 3 | 2021-07-13 | 3 | 2021-07-20 | 5 | [15 empty] | 2021-07-08 | 2021-07-08 |  | 2021-07-08 | 2021-07-08 | 1 | [34 empty] | 2021-07-20 |  | 2021-07-20 | 1
121718626 | 1809 | PGE | 95503 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-13 |  |  | 2021-07-15 | 2021-07-15 | 2 | 2021-07-15 | 2 | 2021-08-02 | 12 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-10-29 | 75 | [34 empty] | 2021-10-29 |  | 2021-10-29 | 1
121764759 | 1810 | PGE | 95709 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-20 | 2021-07-30 |  | 2021-07-30 | 2021-07-30 | 8 | 2021-07-30 | 8 | 2021-08-13 | 10 | [15 empty] | 2021-08-13 | 2021-08-13 | 0 | 2021-08-13 | 2021-08-13 | 0 | [34 empty] | 2021-07-30 |  | 2021-08-13 | 11
121798139 | 1811 | PGE | 93637 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-26 | 2021-08-04 |  | 2021-08-04 | 2021-08-04 | 7 | 2021-08-19 | 18 | 2021-09-07 | 12 | [15 empty] | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-09-29 | 16 | [34 empty] | 2021-10-27 |  | 2021-10-28 | 2
121799751 | 1812 | PGE | 93637 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-26 | 2021-08-02 |  | 2021-07-29 | 2021-07-29 | 3 | 2021-08-23 | 20 | 2021-09-13 | 14 | [15 empty] | 2021-09-13 | 2021-09-29 | 12 | 2021-09-29 | 2021-09-29 | 0 | [34 empty] | 2021-11-04 |  | 2021-11-04 | 1
121807533 | 1813 | PGE | 93446 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-28 |  |  | 2021-08-03 | 2021-08-03 | 4 | 2021-08-03 | 4 | 2021-08-04 | 1 | [15 empty] | 2021-07-28 | 2021-07-28 |  | 2021-07-28 | 2021-08-05 | 7 | [34 empty] | 2021-07-28 |  | 2021-08-23 | 19
121820795 | 1814 | PGE | 95005 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-30 |  |  | 2021-08-03 | 2021-08-03 | 2 | 2021-08-03 | 2 | 2021-08-04 | 1 | [15 empty] | 2021-07-30 | 2021-07-30 |  | 2021-07-30 | 2021-07-30 | 1 | [34 empty] | 2021-07-30 |  | 2021-09-28 | 43
121844198 | 1815 | PGE | 93465 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-04 | 2021-08-13 |  | 2021-08-13 | 2021-08-13 | 7 | 2021-08-17 | 9 | 2021-08-18 | 1 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | 2021-08-19 | 1 | [34 empty] | 2021-08-19 |  | 2021-08-19 | 1
121847518 | 1816 | PGE | 94951 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-05 |  |  | 2021-08-10 | 2021-08-10 | 3 | 2021-08-10 | 3 | 2021-08-31 | 15 | [15 empty] | 2021-08-05 | 2021-08-05 |  | 2021-08-05 | 2021-08-05 | 1 | [34 empty] | 2021-08-17 |  | 2021-08-31 | 11
121864231 | 1817 | PGE | 94611 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-09 |  |  | 2021-08-12 | 2021-08-12 | 3 | 2021-08-12 | 3 | 2021-08-17 | 3 | [15 empty] | 2021-08-09 | 2021-08-09 |  | 2021-08-09 | 2021-08-09 | 1 | [34 empty] | 2021-08-09 |  | 2021-08-17 | 7
121916429 | 1818 | PGE | 95409 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-18 | 2021-09-01 |  | 2021-09-01 | 2021-09-01 | 10 | 2021-09-16 | 20 | 2021-10-20 | 24 | [15 empty] | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01 | 2021-10-04 | 22 | [34 empty] | 2021-09-01 |  | 2021-10-20 | 36
121918126 | 1819 | PGE | 95409 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-18 |  |  | 2021-08-24 | 2021-08-24 | 4 | 2021-08-24 | 4 | 2021-11-08 | 53 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | 2021-09-24 | 22 | [34 empty] | 2021-08-24 |  | 2021-11-08 | 55
121923652 | 1820 | PGE | 94028 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-20 | 2021-08-24 |  | 2021-08-24 | 2021-08-24 | 2 | 2021-08-24 | 2 | 2021-09-13 | 13 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-09-13 | 0 | [34 empty] | 2021-08-24 |  | 2021-09-21 | 21
121926388 | 1821 | PGE | 95476 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-20 |  |  | 2021-09-03 | 2021-09-03 | 10 | 2021-09-03 | 10 | 2021-09-27 | 15 | [15 empty] | 2021-08-20 | 2021-08-20 |  | 2021-08-20 | 2021-08-20 | 1 | [34 empty] | 2021-09-03 |  | 2021-09-27 | 16
121944227 | 1822 | PGE | 95033 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-24 |  |  | 2021-09-08 | 2021-09-08 | 10 | 2021-09-08 | 10 | 2021-09-13 | 3 | [15 empty] | 2021-08-24 | 2021-08-24 |  | 2021-08-24 | 2021-08-24 | 1 | [34 empty] | 2021-10-18 |  | 2021-10-18 | 1
121960215 | 1823 | PGE | 94611 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-26 |  |  | 2021-08-30 | 2021-08-30 | 2 | 2021-08-30 | 2 | 2021-09-03 | 4 | [15 empty] | 2021-08-26 | 2021-08-26 |  | 2021-08-26 | 2021-08-26 | 1 | [34 empty] | 2021-08-30 |  | 2021-09-14 | 12
122012276 | 1824 | PGE | 95033 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-08 |  |  | 2021-10-15 | 2021-10-15 | 27 | 2021-10-15 | 27 | 2021-10-18 | 1 | [15 empty] | 2021-09-07 | 2021-09-07 |  | 2021-09-07 | 2021-09-08 | 2 | [34 empty] | 2021-10-15 |  | 2021-10-22 | 6
122044618 | 1825 | PGE | 94038 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-13 |  |  | 2021-10-15 | 2021-10-15 | 24 | 2021-10-15 | 24 | 2021-10-26 | 7 | [15 empty] | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26 | 2021-10-26 | 0 | [34 empty] | 2021-10-15 |  | 2021-10-26 | 8
122049051 | 1826 | PGE | 95076 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-14 | 2021-10-15 |  | 2021-10-15 | 2021-10-15 | 23 | 2021-10-20 | 26 | 2021-11-01 | 8 | [55 empty] | 2021-10-15 |  | 2021-11-10 | 19
122057147 | 1827 | PGE | 95570 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-16 | 2021-09-28 |  | 2021-09-28 | 2021-09-28 | 8 | 2021-10-08 | 16 | 2021-10-14 | 4 | [15 empty] | 2021-10-14 | 2021-10-14 | 0 | 2021-10-14 | 2021-10-14 | 0 | [34 empty] | 2021-10-25 |  | 2021-11-15 | 16
122063879 | 1828 | PGE | 95370 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-17 | 2021-09-21 |  | 2021-09-21 | 2021-09-21 | 2 | 2021-09-22 | 3 | 2021-10-07 | 11 | [15 empty] | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-10-11 | 2 | [34 empty] | 2021-09-21 |  | 2021-10-12 | 16
122071072 | 1829 | PGE | 95018 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-19 |  |  | 2021-10-15 | 2021-10-15 | 19 | 2021-10-15 | 19 | 2021-10-19 | 2 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-10-19 | 0 | [34 empty] | 2021-10-15 |  | 2021-10-28 | 10
122137265 | 1830 | PGE | 95014 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-10-01 | 2021-10-04 |  | 2021-10-04 | 2021-10-04 | 1 | 2021-10-08 | 5 | 2021-10-08 | 0 | [55 empty] | 2021-10-04 |  | 2021-10-08 | 5
120241570 | 1831 | PGE | 95033 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2020-12-30 |  |  | 2021-01-08 | 2021-01-08 | 6 | 2021-01-08 | 6 | 2021-01-11 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-01-20 | 7
120241718 | 1832 | PGE | 95030 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2020-12-30 |  |  | 2021-01-08 | 2021-01-08 | 6 | 2021-01-08 | 6 | 2021-01-11 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-01-20 | 7
120399509 | 1833 | PGE | 94611 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-07 |  |  | 2021-01-12 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-19 | 4 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-11-23 | 219 | [34 empty] | 2021-12-01 |  | 2021-12-16 | 12
120420080 | 1834 | PGE | 93446 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-01-11 |  |  | 2021-01-22 | 2021-01-22 | 8 | 2021-01-22 | 8 | 2021-02-01 | 6 | [15 empty] | 2021-01-22 | 2021-01-22 | 0 | 2021-01-22 | 2021-02-01 | 6
120426398 | 1835 | PGE | 94586 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-01-13 |  |  | 2021-01-25 | 2021-01-25 | 7 | 2021-01-25 | 7 | 2021-01-25 | 0 | [15 empty] | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | 2021-02-11 | 13
120435060 | 1836 | PGE | 94611 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-01-15 |  |  | 2021-01-25 | 2021-01-25 | 5 | 2021-01-25 | 5 | [17 empty] | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25
120486650 | 1837 | PGE | 94605 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-02-01 |  |  | 2021-02-10 | 2021-02-10 | 7 | 2021-02-10 | 7 | 2021-02-24 | 9 | [15 empty] | 2021-02-10 | 2021-02-10 | 0 | 2021-02-10 | 2021-11-11 | 191
120502415 | 1838 | PGE | 95667 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-02-05 |  |  | 2021-02-22 | 2021-02-22 | 10 | 2021-02-22 | 10 | 2021-04-09 | 34 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-04-23 | 44
120529429 | 1839 | PGE | 95971 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-02-12 |  |  | 2021-02-22 | 2021-02-22 | 5 | 2021-02-22 | 5 | 2021-03-03 | 7 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-05-25 | 66
120599715 | 1840 | PGE | 93465 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-03-03 | 2021-03-15 |  | 2021-03-15 | 2021-03-15 | 8 | 2021-03-17 | 10 | 2021-03-23 | 4 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-18 | 1
120659935 | 1841 | PGE | 94960 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-03-18 |  |  | 2021-04-01 | 2021-04-01 | 10 | 2021-04-01 | 10 | 2021-04-07 | 4
120692826 | 1842 | PGE | 93454 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-03-25 |  |  | 2021-03-29 | 2021-03-29 | 2 | 2021-04-15 | 15 | 2021-04-25 | 6 | [15 empty] | 2021-04-25 | 2021-04-25 | 0 | 2021-04-25 | 2021-08-02 | 68
120702643 | 1843 | PGE | 96061 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-03-28 |  |  | 2021-04-09 | 2021-04-09 | 9 | 2021-05-12 | 32 | 2021-06-09 | 19 | [15 empty] | 2021-04-09 | 2021-04-09 |  | 2021-04-09 | 2021-06-15 | 48
120751731 | 1844 | PGE | 95667 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-04-06 |  |  | 2021-04-13 | 2021-04-13 | 5 | 2021-04-13 | 5 | 2021-04-13 | 0 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13
120866313 | 1845 | PGE | 93420 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-04-22 |  |  | 2021-05-06 | 2021-05-06 | 10 | 2021-05-17 | 17 | 2021-06-08 | 15 | [15 empty] | 2021-04-22 | 2021-04-22 |  | 2021-04-22 | 2021-06-08 | 34
120875910 | 1846 | PGE | 94062 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-04-23 |  |  | 2021-05-07 | 2021-05-07 | 10 | 2021-05-12 | 13 | 2021-07-02 | 36 | [15 empty] | 2021-04-23 | 2021-04-23 |  | 2021-04-23 | 2021-07-02 | 51
120915563 | 1847 | PGE | 94929 | Non-NEM | Non-Export | Application Accepted | Storage | 10 |  | 2021-05-02 |  |  | 2021-05-14 | 2021-05-14 | 9 | 2021-05-14 | 9 | 2021-05-17 | 1 | [15 empty] | 2021-05-17 | 2021-05-17 | 0 | 2021-05-17
121397483 | 1848 | PGE | 95503 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-05-25 | 2021-06-01 |  | 2021-06-01 | 2021-06-01 | 4 | 2021-06-28 | 23 | 2021-07-15 | 12 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-07-20 | 3
121435140 | 1849 | PGE | 95327 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-06-01 |  |  | 2021-06-14 | 2021-06-14 | 9 | 2021-06-14 | 9 | 2021-06-30 | 12 | [15 empty] | 2021-06-30 | 2021-06-30 | 0 | 2021-06-30 | 2021-07-27 | 18 | [34 empty] | 2021-12-10 |  | 2021-12-10 | 1
121446017 | 1850 | PGE | 94037 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-06-02 |  |  | 2021-06-16 | 2021-06-16 | 10 | 2021-06-16 | 10 | 2021-06-23 | 5 | [15 empty] | 2021-06-16 | 2021-06-16 |  | 2021-06-16 | 2021-10-05 | 80
121523763 | 1851 | PGE | 95503 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-06-12 |  |  | 2021-06-24 | 2021-06-24 | 8 | 2021-06-24 | 8 | 2021-07-16 | 15 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-16 | 2021-07-20 | 2
121544402 | 1852 | PGE | 95553 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-06-16 |  |  | 2021-06-29 | 2021-06-29 | 9 | 2021-06-29 | 9 | 2021-07-20 | 14 | [15 empty] | 2021-07-20 | 2021-07-22 | 2 | 2021-07-22 | 2021-07-27 | 3
121621784 | 1853 | PGE | 95633 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-06-28 |  |  | 2021-07-02 | 2021-07-02 | 4 | 2021-07-02 | 4 | 2021-07-16 | 9 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-16
121718164 | 1854 | PGE | 94611 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-07-12 |  |  | 2021-07-26 | 2021-07-26 | 10 | 2021-07-26 | 10 | 2021-08-03 | 6 | [15 empty] | 2021-07-26 | 2021-07-26 |  | 2021-07-26 | 2021-09-08 | 33
121718642 | 1855 | PGE | 95033 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-07-12 |  |  | 2021-07-27 | 2021-07-27 | 11 | 2021-07-27 | 11 | 2021-07-30 | 3 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-07-30 | 3
121770500 | 1856 | PGE | 96022 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-07-21 |  |  | 2021-07-26 | 2021-07-26 | 3 | 2021-07-26 | 3 | 2021-08-09 | 10 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26
121882833 | 1857 | PGE | 95634 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-08-10 | 2021-08-17 |  | 2021-08-17 | 2021-08-17 | 5 | 2021-09-09 | 21 | 2021-09-13 | 2 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-09-14 | 1
121882882 | 1858 | PGE | 95503 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-08-10 | 2021-08-13 |  | 2021-08-13 | 2021-08-13 | 3 | 2021-09-28 | 34 | 2021-09-29 | 1 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29
121956334 | 1859 | PGE | 95333 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-08-25 | 2021-08-27 |  | 2021-08-27 | 2021-08-27 | 2 | 2021-09-14 | 13 | 2021-09-29 | 11 | [15 empty] | 2021-09-10 | 2021-09-10 |  | 2021-09-10 | 2021-09-19 | 6
121956548 | 1860 | PGE | 93670 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-08-25 |  |  | 2021-09-07 | 2021-09-07 | 8 | 2021-09-07 | 8 | 2021-09-14 | 5 | [15 empty] | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-09-29 | 16
121988775 | 1861 | PGE | 95573 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-09-02 |  |  | 2021-09-03 | 2021-09-03 | 1 | 2021-09-03 | 1 | 2021-09-27 | 15 | [15 empty] | 2021-09-27 | 2021-09-30 | 3 | 2021-09-30 | 2021-10-12 | 8
121988822 | 1862 | PGE | 95464 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-09-02 | 2021-09-15 |  | 2021-09-15 | 2021-09-15 | 8 | 2021-09-16 | 9 | 2021-09-24 | 6 | [15 empty] | 2021-09-01 | 2021-09-01 |  | 2021-09-01 | 2021-09-02 | 2
121996270 | 1863 | PGE | 95452 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-09-03 | 2021-09-15 |  | 2021-09-15 | 2021-09-15 | 7 | 2021-09-16 | 8 | 2021-09-24 | 6 | [15 empty] | 2021-09-01 | 2021-09-01 |  | 2021-09-01 | 2021-09-03 | 3
122004126 | 1864 | PGE | 95453 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-09-06 | 2021-09-13 |  | 2021-09-13 | 2021-09-13 | 4 | 2021-09-15 | 6 | 2021-09-24 | 7 | [15 empty] | 2021-09-01 | 2021-09-01 |  | 2021-09-01 | 2021-09-06 | 4
122012317 | 1865 | PGE | 95425 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-08 |  |  | 2021-09-22 | 2021-09-22 | 10 | 2021-09-22 | 10 | 2021-10-05 | 9 | [15 empty] | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | 2021-10-05 | 0
122033879 | 1866 | PGE | 94549 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-10 |  |  | 2021-09-24 | 2021-09-24 | 10 | 2021-09-24 | 10 | 2021-10-13 | 13 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | 2021-10-13 | 13
122057160 | 1867 | PGE | 94611 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-09-16 | 2021-09-16 |  | 2021-09-16 | 2021-09-16 | 0 | 2021-09-23 | 5 | 2021-10-13 | 14 | [15 empty] | 2021-09-16 | 2021-09-16 |  | 2021-09-16 | 2021-09-27 | 8 |  |  |  |  | 2021-09-16 | 2021-09-27 | 2021-09-16 | 2021-10-12 | 18
122065208 | 1868 | PGE | 93608 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-17 | 2021-09-20 |  | 2021-09-20 | 2021-09-20 | 1 | 2021-09-29 | 8 | 2021-10-04 | 3 | [15 empty] | 2021-09-15 | 2021-09-15 |  | 2021-09-15 | 2021-09-17 | 3
122071209 | 1869 | PGE | 93667 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-20 |  |  | 2021-10-04 | 2021-10-04 | 10 | 2021-10-04 | 10 | 2021-10-07 | 3 | [15 empty] | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-10-07 | 0 | [34 empty] | 2021-11-17 |  | 2021-12-13 | 19
122075833 | 1870 | PGE | 95524 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-21 | 2021-10-04 |  | 2021-10-04 | 2021-10-04 | 9 | 2021-10-11 | 14 | 2021-10-14 | 3 | [15 empty] | 2021-10-14 | 2021-10-14 | 0 | 2021-10-14 | 2021-10-14 | 0
122076307 | 1871 | PGE | 95503 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-21 |  |  | 2021-10-05 | 2021-10-05 | 10 | 2021-10-05 | 10 | 2021-10-26 | 15 | [15 empty] | 2021-09-20 | 2021-09-20 |  | 2021-09-20 | 2021-10-05 | 12
122078975 | 1872 | PGE | 95570 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-21 |  |  | 2021-10-05 | 2021-10-05 | 10 | 2021-10-05 | 10 | 2021-10-12 | 5 | [15 empty] | 2021-09-21 | 2021-09-21 |  | 2021-09-21 | 2021-09-21 | 1
122087525 | 1873 | PGE | 94556 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-23 |  |  | 2021-10-07 | 2021-10-07 | 10 | 2021-10-07 | 10 | 2021-10-13 | 4 | [15 empty] | 2021-10-13 | 2021-10-13 | 0 | 2021-10-13 | 2021-10-13 | 0 | [34 empty] | 2021-10-26 |  | 2021-12-13 | 35
122106714 | 1874 | PGE | 93608 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-27 | 2021-10-08 |  | 2021-10-08 | 2021-10-08 | 9 | 2021-10-26 | 21 | 2021-10-29 | 3 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | 2021-10-29 | 0 | [34 empty] | 2021-12-09 |  | 2021-12-09 | 1
122113215 | 1875 | PGE | 93608 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-28 | 2021-10-04 |  | 2021-10-04 | 2021-10-04 | 4 | 2021-10-14 | 12 | 2021-10-18 | 2 | [15 empty] | 2021-09-21 | 2021-09-21 |  | 2021-09-21 | 2021-09-28 | 6 | [34 empty] | 2021-12-15 |  | 2021-12-15 | 1
122125963 | 1876 | PGE | 93608 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-30 | 2021-10-12 |  | 2021-10-12 | 2021-10-12 | 8 | 2021-10-26 | 18 | 2021-10-29 | 3 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | 2021-10-29 | 0 | [34 empty] | 2021-12-21 |  | 2021-12-21 | 1
121590538 | 1877 | PGE | 95501 | Non-NEM | Non-Export | Implementation | Storage | 10 |  | 2021-06-24 |  |  | 2021-07-08 | 2021-07-08 | 9 | 2021-07-08 | 9 | 2021-07-23 | 11 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-09-25 | 55
121975538 | 1878 | PGE | 93292 | Non-NEM | Non-Export | Implementation | Storage | 10 |  | 2021-08-31 |  |  | 2021-09-03 | 2021-09-03 | 3 | 2021-09-03 | 3 | 2021-09-15 | 7 | [15 empty] | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | 2021-10-06 | 15
122057013 | 1879 | PGE | 94578 | Non-NEM | Non-Export | Implementation | Storage | 10 |  | 2021-09-16 |  |  | 2021-09-21 | 2021-09-21 | 3 | 2021-09-21 | 3 | 2021-09-23 | 2 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | 2021-09-29 | 6
122068418 | 1880 | PGE | 95503 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-09-18 | [5 empty] | 2021-09-21 | 1 | 2021-09-28 | 5 | [15 empty] | 2021-09-17 | 2021-09-17 |  | 2021-09-17 | 2021-09-18 | 1
122083071 | 1881 | PGE | 95549 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-09-22 |  |  | 2021-09-24 | 2021-09-24 | 2 | 2021-09-24 | 2 | 2021-09-28 | 2 | [15 empty] | 2021-09-21 | 2021-09-21 |  | 2021-09-21 | 2021-09-22 | 2
120401954 | 1882 | PGE | 95006 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-01-07 |  |  | 2021-01-15 | 2021-01-15 | 6 | 2021-01-15 | 6 | 2021-01-15 | 0
120724474 | 1883 | PGE | 93953 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-04-01 |  |  | 2021-04-13 | 2021-04-13 | 8 | 2021-04-13 | 8 | 2021-04-16 | 3
121397437 | 1884 | PGE | 95713 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-05-25 | 2021-05-28 |  | 2021-05-28 | 2021-05-28 | 3 | 2021-06-03 | 6 | 2021-06-07 | 2 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28
122064147 | 1885 | PGE | 95033 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-09-17 |  |  | 2021-10-01 | 2021-10-01 | 10 | 2021-10-01 | 10
122071608 | 1886 | PGE | 95672 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-09-20 |  |  | 2021-10-04 | 2021-10-04 | 10 | 2021-10-04 | 10
122074460 | 1887 | PGE | 95503 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-09-20 |  |  | 2021-09-23 | 2021-09-23 | 3 | 2021-09-23 | 3 | 2021-09-28 | 3
122093171 | 1888 | PGE | 95503 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-09-23 |  |  | 2021-10-06 | 2021-10-06 | 9 | 2021-10-06 | 9 | 2021-10-27 | 15
122117764 | 1889 | PGE | 93670 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-09-29 | 2021-10-13 |  | 2021-10-13 | 2021-10-13 | 10 | 2021-10-25 | 18 | 2021-10-25 | 0 | [15 empty] | 2021-08-30 | 2021-08-30 |  | 2021-08-30 | 2021-09-29 | 23
122117866 | 1890 | PGE | 95521 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-29 |  |  | 2021-10-13 | 2021-10-13 | 10 | 2021-10-13 | 10 | 2021-12-14 | 41 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2021-12-14 | 0
122118524 | 1891 | PGE | 95519 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-29 |  |  | 2021-10-13 | 2021-10-13 | 10 | 2021-10-13 | 10 | 2021-11-03 | 15 | [34 empty] | 2021-12-14 | 2021-12-14 | 0 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 |  | 2021-12-14 | 0
122118548 | 1892 | PGE | 93608 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-09-29 | 2021-10-01 |  | 2021-10-01 | 2021-10-01 | 2 | 2021-10-15 | 12 | 2021-10-18 | 1
120567793 | 1893 | PGE | 95407 | Non-NEM | Non-Export | Study in Progress | Solar PV | 11.52 |  | 2021-02-23 |  |  | 2021-03-09 | 2021-03-09 | 10 | 2021-03-09 | 10
120722944 | 1894 | PGE | 95684 | Non-NEM | Non-Export | Application Accepted | Storage | 15 |  | 2021-04-01 |  |  | 2021-04-15 | 2021-04-15 | 10 | 2021-04-15 | 10 | 2021-04-20 | 3
120741171 | 1895 | PGE | 95667 | Non-NEM | Non-Export | Implementation | Storage | 15 |  | 2021-04-05 |  |  | 2021-04-14 | 2021-04-14 | 7 | 2021-04-14 | 7 | 2021-04-25 | 7 | [15 empty] | 2021-04-25 | 2021-04-25 | 0 | 2021-04-25 | 2021-12-23 | 167
120911794 | 1896 | PGE | 95762 | Non-NEM | Non-Export | Application Accepted | Storage | 15 |  | 2021-05-01 |  |  | 2021-05-14 | 2021-05-14 | 9 | 2021-05-14 | 9 | 2021-05-18 | 2 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18
121192277 | 1897 | PGE | 95667 | Non-NEM | Non-Export | Application Accepted | Storage | 15 |  | 2021-05-12 |  |  | 2021-05-26 | 2021-05-26 | 10 | 2021-07-01 | 35 | 2021-07-15 | 9 | [15 empty] | 2021-07-01 | 2021-07-01 |  | 2021-07-01 | 2021-07-16 | 12
121259243 | 1898 | PGE | 95667 | Non-NEM | Non-Export | Application Accepted | Storage | 15 |  | 2021-05-12 |  |  | 2021-05-26 | 2021-05-26 | 10 | 2021-07-06 | 37 | 2021-07-15 | 7 | [15 empty] | 2021-06-30 | 2021-06-30 |  | 2021-06-30 | 2021-07-16 | 13
121686349 | 1899 | PGE | 95667 | Non-NEM | Non-Export | Application Accepted | Storage | 15 |  | 2021-07-09 | 2021-07-13 |  | 2021-07-13 | 2021-07-13 | 2 | 2021-07-16 | 5 | 2021-07-19 | 1 | [15 empty] | 2021-07-19 | 2021-08-02 | 10 | 2021-08-02 | 2021-10-30 | 63
122081974 | 1900 | PGE | 95667 | Non-NEM | Inadvertent Export | Application Accepted | Storage | 15 |  | 2021-09-21 | 2021-10-04 |  | 2021-10-04 | 2021-10-04 | 9 | 2021-10-21 | 22 | 2021-10-27 | 4 | [15 empty] | 2021-10-27 | 2021-10-27 |  | 2021-10-27 | 2021-10-27 | 1
120713177 | 1901 | PGE | 95125 | Non-NEM | Non-Export | Application Review in Progress | Storage | 15 |  | 2021-03-30 | 2021-04-08 |  | 2021-04-08 | 2021-04-08 | 7
120402072 | 1902 | PGE | 95409 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-07 |  |  | 2021-01-20 | 2021-01-20 | 8 | 2021-01-20 | 8 | 2021-01-21 | 1 | [55 empty] | 2021-01-21 |  | 2021-01-29 | 7
120404457 | 1903 | PGE | 95667 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-08 |  |  | 2021-01-21 | 2021-01-21 | 8 | 2021-01-21 | 8 | 2021-01-22 | 1 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-04-12 | 56 | [34 empty] | 2021-04-12 |  | 2021-04-12 | 1
120404481 | 1904 | PGE | 95549 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-08 |  |  | 2021-01-21 | 2021-01-21 | 8 | 2021-01-21 | 8 | 2021-01-22 | 1 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-07-01 | 113 | [34 empty] | 2021-10-18 |  | 2021-10-18 | 1
120404482 | 1905 | PGE | 94020 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-08 |  |  | 2021-01-21 | 2021-01-21 | 8 | 2021-01-21 | 8 | 2021-01-21 | 0 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-07-01 | 113 | [34 empty] | 2021-08-26 |  | 2021-08-26 | 1
120468624 | 1906 | PGE | 94066 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-27 |  |  | 2021-02-08 | 2021-02-08 | 8 | 2021-03-12 | 31 | 2021-03-26 | 10 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-20 | 17 | [34 empty] | 2021-04-20 |  | 2021-05-02 | 9
120478504 | 1907 | PGE | 94611 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-29 |  |  | 2021-02-10 | 2021-02-10 | 8 | 2021-02-10 | 8 | 2021-02-18 | 5 | [15 empty] | 2021-02-10 | 2021-02-10 | 0 | 2021-02-10 | 2021-02-12 | 2 | [34 empty] | 2021-02-10 |  | 2021-02-23 | 10
120487354 | 1908 | PGE | 95650 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-02-01 |  |  | 2021-02-13 | 2021-02-13 | 9 | 2021-02-13 | 9 | 2021-03-08 | 14 | [15 empty] | 2021-02-13 | 2021-02-13 | 0 | 2021-02-13 | 2021-08-06 | 121 | [34 empty] | 2021-08-10 |  | 2021-08-10 | 1
120498453 | 1909 | PGE | 95682 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-02-03 |  |  | 2021-02-13 | 2021-02-13 | 7 | 2021-02-13 | 7 | 2021-02-23 | 5 | [15 empty] | 2021-02-13 | 2021-02-13 | 0 | 2021-02-13 | 2021-08-03 | 118 | [34 empty] | 2021-08-03 |  | 2021-08-03 | 1
120516130 | 1910 | PGE | 95682 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-02-10 |  |  | 2021-02-22 | 2021-02-22 | 7 | 2021-02-22 | 7 | 2021-02-23 | 1 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-05-25 | 66 | [34 empty] | 2021-10-07 |  | 2021-10-07 | 1
120579815 | 1911 | PGE | 95945 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-02-26 |  |  | 2021-03-01 | 2021-03-01 | 1 | 2021-03-01 | 1 | 2021-03-18 | 13 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-08-30 | 128 | [34 empty] | 2021-08-30 |  | 2021-09-02 | 4
120581948 | 1912 | PGE | 93953 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-02-26 |  |  | 2021-03-09 | 2021-03-09 | 7 | 2021-03-09 | 7 | 2021-03-10 | 1 | [55 empty] | 2021-03-09 |  | 2021-04-12 | 25
120646083 | 1913 | PGE | 95975 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-03-15 |  |  | 2021-03-29 | 2021-03-29 | 10 | 2021-03-29 | 10 | 2021-03-30 | 1 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-04-21 | 17 | [34 empty] | 2021-04-27 |  | 2021-04-27 | 1
120646101 | 1914 | PGE | 95650 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-03-16 | 2021-03-30 |  | 2021-03-30 | 2021-03-30 | 10 | 2021-04-14 | 21 | 2021-04-19 | 3 | [15 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-05-05 | 26 | [34 empty] | 2021-05-05 |  | 2021-05-06 | 2
120737645 | 1915 | PGE | 94062 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-04-02 |  |  | 2021-04-14 | 2021-04-14 | 8 | 2021-04-14 | 8 | 2021-04-28 | 10 | [15 empty] | 2021-04-14 | 2021-04-14 |  | 2021-04-14 | 2021-04-28 | 11 | [34 empty] | 2021-08-06 |  | 2021-08-06 | 1
120991190 | 1916 | PGE | 95223 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-05-10 |  |  | 2021-05-24 | 2021-05-24 | 10 | 2021-06-07 | 19 | 2021-06-07 | 0 | [15 empty] | 2021-05-10 | 2021-05-10 |  | 2021-05-10 | 2021-06-07 | 21 | [34 empty] | 2021-06-02 |  | 2021-06-07 | 4
121530920 | 1917 | PGE | 94708 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-06-14 | 2021-06-17 |  | 2021-06-17 | 2021-06-17 | 3 | 2021-06-17 | 3 | 2021-06-22 | 3 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-06-22 | 0 | [34 empty] | 2021-06-17 |  | 2021-06-25 | 7
121712104 | 1918 | PGE | 95685 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-07-12 |  |  | 2021-07-15 | 2021-07-15 | 3 | 2021-07-15 | 3 | 2021-08-02 | 12 | [15 empty] | 2021-07-12 | 2021-07-12 |  | 2021-07-12 | 2021-07-12 | 1 | [34 empty] | 2021-07-15 |  | 2021-08-02 | 13
121883351 | 1919 | PGE | 94951 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-08-11 | 2021-08-13 |  | 2021-08-13 | 2021-08-13 | 2 | 2021-08-25 | 10 | 2021-08-26 | 1 | [15 empty] | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | 2021-10-13 | 33 | [13 empty] | 2021-10-13 | 2021-10-20 | 5 | [15 empty] | 2021-10-13 | 2021-10-13 | 0 | 2021-10-20 |  | 2021-10-20 | 0
121957503 | 1920 | PGE | 95959 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-08-25 |  |  | 2021-08-30 | 2021-08-30 | 3 | 2021-08-30 | 3 | 2021-09-07 | 5 | [15 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-09-27 | 19 | [34 empty] | 2021-08-30 |  | 2021-09-28 | 22
122106530 | 1921 | PGE | 95044 | Non-NEM | Inadvertent Export | Commercial | Storage | 15 |  | 2021-09-27 |  |  | 2021-10-11 | 2021-10-11 | 10 | 2021-10-11 | 10 | 2021-10-13 | 2 | [15 empty] | 2021-10-13 | 2021-10-13 | 0 | 2021-10-13 | 2021-10-13 | 0 | [34 empty] | 2021-10-11 |  | 2021-10-15 | 5
120237645 | 1922 | PGE | 95664 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2020-12-29 |  |  | 2021-01-08 | 2021-01-08 | 7 | 2021-01-08 | 7 | 2021-01-11 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-01-28 | 13
120242942 | 1923 | PGE | 95442 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2020-12-30 |  |  | 2021-01-11 | 2021-01-11 | 7 | 2021-01-11 | 7 | 2021-01-13 | 2 | [15 empty] | 2021-01-11 | 2021-01-11 | 0 | 2021-01-11
120248239 | 1924 | PGE | 93401 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-01-01 |  |  | 2021-01-11 | 2021-01-11 | 5 | 2021-01-11 | 5 | 2021-01-11 | 0 | [15 empty] | 2021-01-11 | 2021-01-11 | 0 | 2021-01-11
120248272 | 1925 | PGE | 95658 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-01-01 |  |  | 2021-01-11 | 2021-01-11 | 5 | 2021-01-11 | 5 | 2021-01-11 | 0 | [15 empty] | 2021-01-11 | 2021-01-11 | 0 | 2021-01-11
120408118 | 1926 | PGE | 95651 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-01-08 |  |  | 2021-01-22 | 2021-01-22 | 9 | 2021-01-22 | 9 | 2021-01-25 | 1 | [15 empty] | 2021-01-22 | 2021-01-22 | 0 | 2021-01-22 | 2021-12-01 | 216
120427968 | 1927 | PGE | 95682 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-01-14 | 2021-01-25 |  | 2021-01-25 | 2021-01-25 | 6 | 2021-03-16 | 41 | 2021-03-17 | 1 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17
120435040 | 1928 | PGE | 95549 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-01-15 | 2021-01-26 |  | 2021-01-19 | 2021-01-19 | 1 | 2021-01-29 | 9 | 2021-02-01 | 1 | [15 empty] | 2021-01-29 | 2021-01-29 | 0 | 2021-01-29
120435063 | 1929 | PGE | 95521 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-01-15 | 2021-01-26 |  | 2021-01-26 | 2021-01-26 | 6 | 2021-02-05 | 14 | 2021-02-08 | 1 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05
120435064 | 1930 | PGE | 95603 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-01-16 | 2021-01-26 |  | 2021-01-26 | 2021-01-26 | 5 | 2021-02-05 | 13 | 2021-02-08 | 1 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05
120508898 | 1931 | PGE | 95762 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-08 |  |  | 2021-02-19 | 2021-02-19 | 8 | 2021-02-19 | 8 | 2021-02-22 | 1 | [15 empty] | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | 2021-05-25 | 67
120525872 | 1932 | PGE | 95633 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-10 |  |  | 2021-02-22 | 2021-02-22 | 7 | 2021-02-22 | 7 | 2021-02-23 | 1 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-05-25 | 66
120525983 | 1933 | PGE | 95713 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-10 |  |  | 2021-02-22 | 2021-02-22 | 7 | 2021-02-22 | 7 | 2021-02-23 | 1 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22
120529582 | 1934 | PGE | 95682 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-12 |  |  | 2021-02-23 | 2021-02-23 | 6 | 2021-02-23 | 6 | 2021-02-23 | 0 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-05-26 | 66
120553729 | 1935 | PGE | 95470 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-18 |  |  | 2021-02-25 | 2021-02-25 | 5 | 2021-02-25 | 5 | 2021-02-26 | 1 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25
120571947 | 1936 | PGE | 95651 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-24 |  |  | 2021-03-01 | 2021-03-01 | 3 | 2021-03-01 | 3 | 2021-03-02 | 1 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01
120571948 | 1937 | PGE | 95762 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-24 |  |  | 2021-03-01 | 2021-03-01 | 3 | 2021-03-01 | 3 | 2021-03-02 | 1 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-10-06 | 154
120604675 | 1938 | PGE | 95682 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-03-04 |  |  | 2021-03-09 | 2021-03-09 | 3 | 2021-03-09 | 3 | 2021-03-11 | 2 | [15 empty] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | 2021-09-27 | 141
120645879 | 1939 | PGE | 95667 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-03-16 | 2021-03-30 |  | 2021-03-30 | 2021-03-30 | 10 | 2021-06-25 | 72 | 2021-07-15 | 13 | [15 empty] | 2021-06-25 | 2021-06-25 | 0 | 2021-06-25 | 2021-07-28 | 22
120646103 | 1940 | PGE | 95658 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-03-16 | 2021-03-30 |  | 2021-03-30 | 2021-03-30 | 10 | 2021-05-25 | 50 | 2021-05-28 | 3 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28
120655619 | 1941 | PGE | 95070 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-03-17 |  |  | 2021-03-31 | 2021-03-31 | 10 | 2021-03-31 | 10 | 2021-04-06 | 4 | [15 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | 2021-07-07 | 68
120656073 | 1942 | PGE | 94062 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-03-18 |  |  | 2021-04-01 | 2021-04-01 | 10 | 2021-04-01 | 10 | 2021-04-07 | 4 | [55 empty] | 2021-12-21 |  | 2021-12-22 | 2
120689171 | 1943 | PGE | 95472 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-03-25 |  |  | 2021-04-08 | 2021-04-08 | 10 | 2021-04-08 | 10 | 2021-04-14 | 4 | [15 empty] | 2021-04-08 | 2021-04-08 |  | 2021-04-08 | 2021-07-28 | 80
120702618 | 1944 | PGE | 95762 | Non-NEM | Non-Export | Application Accepted | Storage | 15 |  | 2021-03-28 |  |  | 2021-04-08 | 2021-04-08 | 8 | 2021-04-08 | 8 | 2021-04-25 | 11 | [15 empty] | 2021-04-25 | 2021-04-25 | 0 | 2021-04-25 | 2021-07-28 | 65
120727280 | 1945 | PGE | 96003 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-04-01 |  |  | 2021-04-15 | 2021-04-15 | 10 | 2021-04-15 | 10 | 2021-04-22 | 5 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-11-01 | 139
120774248 | 1946 | PGE | 95728 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-04-10 |  |  | 2021-04-17 | 2021-04-17 | 5 | 2021-04-17 | 5 | 2021-04-21 | 2 | [15 empty] | 2021-04-17 | 2021-04-17 | 0 | 2021-04-17
120803932 | 1947 | PGE | 94062 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-04-13 |  |  | 2021-04-17 | 2021-04-17 | 3 | 2021-04-17 | 3 | [17 empty] | 2021-04-13 | 2021-04-13 |  | 2021-04-13 | 2021-04-17 | 4
121559450 | 1948 | PGE | 95476 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-06-18 |  |  | 2021-06-22 | 2021-06-22 | 2 | 2021-06-22 | 2 | 2021-09-01 | 50 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22
121674166 | 1949 | PGE | 94022 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-07-07 |  |  | 2021-07-12 | 2021-07-12 | 3 | 2021-07-12 | 3 | 2021-07-14 | 2 | [15 empty] | 2021-07-07 | 2021-07-07 |  | 2021-07-07 | 2021-07-07 | 1
121680318 | 1950 | PGE | 95682 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-07-08 |  |  | 2021-07-13 | 2021-07-13 | 3 | 2021-07-13 | 3 | 2021-07-20 | 5 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-23 | 7
121710191 | 1951 | PGE | 95070 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-07-11 |  |  | 2021-07-15 | 2021-07-15 | 3 | 2021-07-15 | 3 | 2021-07-29 | 10 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-07-26 | 7
121718165 | 1952 | PGE | 95672 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-07-12 |  |  | 2021-07-15 | 2021-07-15 | 3 | 2021-07-15 | 3 | 2021-07-20 | 3 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-07-19 | 2
121725579 | 1953 | PGE | 95667 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-07-14 |  |  | 2021-07-28 | 2021-07-28 | 10 | 2021-07-28 | 10 | 2021-08-17 | 14 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28
121882811 | 1954 | PGE | 95651 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-08-10 |  |  | 2021-08-16 | 2021-08-16 | 4 | 2021-08-16 | 4 | 2021-09-07 | 15 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16
121986883 | 1955 | PGE | 95667 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-09-01 |  |  | 2021-09-03 | 2021-09-03 | 2 | 2021-09-03 | 2 | 2021-09-08 | 2 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-29 | 17
121986947 | 1956 | PGE | 95472 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-09-01 |  |  | 2021-09-03 | 2021-09-03 | 2 | 2021-09-03 | 2 | 2021-09-22 | 12 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-23 | 13
121987068 | 1957 | PGE | 95033 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-09-02 |  |  | 2021-09-17 | 2021-09-17 | 10 | 2021-09-17 | 10 | 2021-10-07 | 14 | [15 empty] | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-10-30 | 16
121987673 | 1958 | PGE | 95667 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-09-01 | 2021-09-10 |  | 2021-09-10 | 2021-09-10 | 6 | 2021-09-30 | 20 | 2021-10-19 | 13 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-12-09 | 34
121991506 | 1959 | PGE | 93925 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 15 |  | 2021-09-02 | 2021-09-16 |  | 2021-09-16 | 2021-09-16 | 9 | 2021-09-23 | 14 | 2021-09-27 | 2 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | 2021-12-16 | 62
121330213 | 1960 | PGE | 95006 | Non-NEM | Non-Export | Implementation | Storage | 15 |  | 2021-05-14 | 2021-06-23 |  | 2021-05-26 | 2021-05-26 | 8 | 2021-07-23 | 48 | 2021-07-26 | 1 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-11-04 | 72
121399829 | 1961 | PGE | 94043 | Non-NEM | Non-Export | Implementation | Storage | 15 |  | 2021-05-26 |  |  | 2021-06-02 | 2021-06-02 | 4 | 2021-06-02 | 4 | 2021-06-11 | 7 | [15 empty] | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-10-20 | 91
121986988 | 1962 | PGE | 95682 | Non-NEM | Non-Export | Implementation | Storage | 15 |  | 2021-09-01 |  |  | 2021-09-07 | 2021-09-07 | 3 | 2021-09-07 | 3 | 2021-09-07 | 0 | [15 empty] | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-09-27 | 14
121990988 | 1963 | PGE | 95404 | Non-NEM | Non-Export | Study in Progress | Storage | 15 |  | 2021-09-02 | 2021-09-17 |  | 2021-09-17 | 2021-09-17 | 10 | 2021-10-01 | 20 | 2021-10-22 | 15 | [15 empty] | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22
121731990 | 1964 | PGE | 94122 | Non-NEM | Non-Export | IA in Progress | Solar PV | 15.048 |  | 2021-07-14 | 2021-07-20 |  | 2021-07-20 | 2021-07-20 | 4 | 2021-07-27 | 9 | 2021-08-10 | 10 | [15 empty] | 2021-08-10 | 2021-08-11 | 1 | 2021-08-11
120712224 | 1965 | PGE | 94061 | Non-NEM | Non-Export | Study in Progress | Storage | 17.68 |  | 2021-03-30 |  |  | 2021-04-07 | 2021-04-07 | 6 | 2021-04-07 | 6 | 2021-04-09 | 2
120692688 | 1966 | PGE | 93405 | Non-NEM | Non-Export | Application Accepted | Storage | 20 |  | 2021-03-25 |  |  | 2021-03-29 | 2021-03-29 | 2 | 2021-04-12 | 12 | 2021-04-19 | 5 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-04-23 | 4
120406929 | 1967 | PGE | 93614 | Non-NEM | Non-Export | Commercial | Storage | 20 |  | 2021-01-08 |  |  | 2021-01-22 | 2021-01-22 | 9 | 2021-01-22 | 9 | 2021-02-10 | 13 | [15 empty] | 2021-01-22 | 2021-01-22 | 0 | 2021-01-22 | 2021-03-10 | 32 | [34 empty] | 2021-07-21 |  | 2021-08-04 | 11
120887180 | 1968 | PGE | 95070 | Non-NEM | Non-Export | Commercial | Storage | 20 |  | 2021-04-26 |  |  | 2021-05-10 | 2021-05-10 | 10 | 2021-05-26 | 22 | 2021-05-26 | 0 | [15 empty] | 2021-05-10 | 2021-05-10 |  | 2021-05-10 | 2021-05-21 | 10 | [34 empty] | 2021-10-29 |  | 2021-10-29 | 1
121996639 | 1969 | PGE | 94062 | Non-NEM | Non-Export | IA in Progress | Storage | 20 |  | 2021-09-03 |  |  | 2021-09-20 | 2021-09-20 | 10 | 2021-09-20 | 10 | 2021-10-06 | 12 | [15 empty] | 2021-10-06 | 2021-10-06 | 0 | 2021-10-06 | 2021-10-06 | 0
120532272 | 1970 | PGE | 95014 | Non-NEM | Break Before Make | Commercial | ENGN | 21 |  | 2021-02-12 |  |  | 2021-02-18 | 2021-02-18 | 3 | 2021-02-18 | 3 | 2021-03-01 | 7
120474560 | 1971 | PGE | 95030 | Non-NEM | Break Before Make | Commercial | ENGN | 22 |  | 2021-01-28 | 2021-02-03 |  | 2021-02-03 | 2021-02-03 | 4 | 2021-02-10 | 9 | 2021-03-01 | 12
120793050 | 1972 | PGE | 94103 | Non-NEM | Non-Export | Commercial | Solar PV | 22.831 |  | 2021-04-12 | 2021-04-26 |  | 2021-04-26 | 2021-04-26 | 10 | 2021-05-17 | 25 | 2021-07-09 | 37 | [15 empty] | 2021-07-23 | 2021-07-23 | 0 | 2021-07-23 | 2021-07-30 | 5 | [13 empty] | 2021-09-08 | 2021-09-15 | 5 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-15 |  | 2021-09-16 | 1
120639171 | 1973 | PGE | 93940 | Non-NEM | Break Before Make | Commercial | ENGN | 24 |  | 2021-03-12 | 2021-03-24 |  | 2021-03-24 | 2021-03-24 | 8 | 2021-03-26 | 10
120680004 | 1974 | PGE | 94904 | Non-NEM | Non-Export | Commercial | Storage | 25 |  | 2021-03-23 |  |  | 2021-04-06 | 2021-04-06 | 10 | 2021-04-06 | 10 | 2021-04-14 | 6 | [15 empty] | 2021-03-23 | 2021-03-23 |  | 2021-03-23 | 2021-05-18 | 41 | [34 empty] | 2021-05-27 |  | 2021-06-10 | 11
121865297 | 1975 | PGE | 94028 | Non-NEM | Non-Export | Commercial | Storage | 25 |  | 2021-08-09 | 2021-08-17 |  | 2021-08-17 | 2021-08-17 | 6 | 2021-08-17 | 6 | 2021-08-18 | 1 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | 2021-08-19 | 1 | [34 empty] | 2021-08-17 |  | 2021-08-24 | 6
120399733 | 1976 | PGE | 95033 | Non-NEM | Non-Export | Study in Progress | Storage | 25 |  | 2021-01-07 | 2021-01-12 |  | 2021-01-12 | 2021-01-12 | 3 | 2021-01-21 | 9 | 2021-01-22 | 1 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-01-29 | 12
122084815 | 1977 | PGE | 95446 | Non-NEM | Non-Export | IA in Progress | Storage | 28.95 |  | 2021-09-22 |  |  | 2021-10-06 | 2021-10-06 | 10 | 2021-10-06 | 10
120604395 | 1978 | PGE | 94565 | Non-NEM | Continuous Uncompensated Export | Application Accepted | ENGN, Turbine |  |  | 2021-03-04 | 2021-03-08 |  | 2021-03-08 | 2021-03-08 | 2 | 2021-04-07 | 24 | [27 empty] | 2021-03-04 |  | 2021-03-04
120889200 | 1979 | PGE | 96088 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-27 |  |  | 2021-05-11 | 2021-05-11 | 10 | 2021-05-14 | 13 | 2021-06-07 | 15 | [15 empty] | 2021-04-27 | 2021-04-27 |  | 2021-04-27 | 2021-06-18 | 39 | [34 empty] | 2021-06-18 |  | 2021-06-18 | 1
120406951 | 1980 | PGE | 94710 | Non-NEM | Non-Export | Implementation | ENGN |  |  | 2021-01-08 | 2021-01-11 |  | 2021-01-11 | 2021-01-11 | 1 | 2021-01-21 | 8 | 2021-02-11 | 15 | 2021-03-09 | 2021-04-06 | 20 | [12 empty] | 2021-05-18 | 2021-06-09 | 15 | 2021-06-09 | 2021-06-18 | 7 | [16 empty] | 2021-08-10 |  | 108
120807839 | 1981 | PGE | 95603 | Non-NEM | Continuous Uncompensated Export | Implementation | Solar PV | 96 |  | 2021-04-13 |  |  | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 0 | [17 empty] | 2021-04-13 | 2021-04-13 |  | 2021-04-13 | 2021-04-13 | 1
120772379 | 1982 | PGE | 94089 | Non-NEM | Make Before Break | Study in Progress | ENGN |  |  | 2021-04-09 | 2021-04-14 |  | 2021-04-14 | 2021-04-14 | 3 | 2021-04-28 | 13 | 2021-05-21 | 17 | [25 empty] | 2021-04-09 |  | 2021-04-09
120241717 | 1983 | PGE | 95445 | Non-NEM | Non-Export | Withdrawn | Storage | 10 |  | 2020-12-30 |  |  | 2021-01-08 | 2021-01-08 | 6 | 2021-01-08 | 6 | 2021-01-20 | 7 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-02-08 | 20
120461775 | 1984 | PGE | 93422 | Non-NEM | Non-Export | Withdrawn | Storage | 10 |  | 2021-01-25 |  |  | 2021-02-08 | 2021-02-08 | 10
120531666 | 1985 | PGE | 93405 | Non-NEM | Non-Export | Withdrawn | Storage | 20 |  | 2021-02-12 |  |  | 2021-02-23 | 2021-02-23 | 6 | 2021-02-23 | 6 | 2021-02-24 | 1 | [26 empty] | 2021-02-24 | 2021-02-24 | 2021-02-25 | 1
120578776 | 1986 | PGE | 95667 | Non-NEM | Non-Export | Withdrawn | Storage | 15 |  | 2021-02-26 |  |  | 2021-03-01 | 2021-03-01 | 1 | 2021-03-01 | 1 | 2021-03-02 | 1 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01
120602199 | 1987 | PGE | 96022 | Non-NEM | Non-Export | Withdrawn | Storage | 25 |  | 2021-03-04 |  |  | 2021-03-16 | 2021-03-16 | 8 | 2021-03-16 | 8 | 2021-03-23 | 5 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16
120615167 | 1988 | PGE | 95014 | Non-NEM | Non-Export | Withdrawn | Storage | 20 |  | 2021-03-09 |  |  | 2021-03-24 | 2021-03-24 | 11 | 2021-03-24 | 11 | 2021-04-06 | 9 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22
120640341 | 1989 | PGE | 93654 | NEM | EXPNEM | Withdrawn | Solar PV | 41.76 |  | 2021-03-12 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 10 | 2021-05-25 | 52 | 2021-06-10 | 11 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | [7 empty] | 2021-07-22 | 2021-07-22 | 2021-07-30 | 6
120663000 | 1990 | PGE | 93638 | Non-NEM | Non-Export | Withdrawn | ENGN |  |  | 2021-03-19 | 2021-03-19 |  | 2021-03-19 | 2021-03-19 | 0 | [29 empty] | 2021-03-19 |  | 2021-03-19
120680100 | 1991 | PGE | 95321 | Non-NEM | Non-Export | Withdrawn | Storage | 15 |  | 2021-03-23 |  |  | 2021-04-06 | 2021-04-06 | 10 | 2021-04-06 | 10 | 2021-04-22 | 12
120708164 | 1992 | PGE | 95014 | NEM | NEMMT | Implementation | FUCE, OTHR, Solar PV, Storage | 2400 |  | 2021-03-29 | 2021-03-31 |  | 2021-03-30 | 2021-03-30 | 1 | 2021-04-16 | 14 | 2021-05-07 | 15 | 2021-05-28 | 2021-07-08 | 27 | [12 empty] | 2021-07-08 | 2021-07-12 | 2 | 2021-07-12 | 2021-10-13 | 66
120750640 | 1993 | PGE | 95033 | Non-NEM | Non-Export | Withdrawn | Storage | 10 |  | 2021-04-06 | 2021-04-17 |  | 2021-04-17 | 2021-04-17 | 8
121358837 | 1994 | PGE | 95682 | Non-NEM | Non-Export | Withdrawn | Storage | 10 |  | 2021-05-19 |  |  | 2021-05-26 | 2021-05-26 | 5 | 2021-05-26 | 5 | 2021-05-27 | 1 | [15 empty] | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26
121548186 | 1995 | PGE | 93637 | Non-NEM | Non-Export | Withdrawn | Storage | 10 |  | 2021-06-16 | 2021-06-22 |  | 2021-06-22 | 2021-06-22 | 4
121549771 | 1996 | PGE | 93637 | Non-NEM | Non-Export | Withdrawn | Storage | 10 |  | 2021-06-16 | 2021-06-22 |  | 2021-06-22 | 2021-06-22 | 4
121549898 | 1997 | PGE | 93637 | Non-NEM | Non-Export | Withdrawn | Storage | 10 |  | 2021-06-16 | 2021-06-22 |  | 2021-06-22 | 2021-06-22 | 4
121579817 | 1998 | PGE | 94806 | Non-NEM | Non-Export | Withdrawn | Storage | 5 |  | 2021-06-22 |  |  | 2021-07-05 | 2021-07-05 | 8 | 2021-07-05 | 8 | 2021-07-09 | 3 | [15 empty] | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09
121669613 | 1999 | PGE | 95135 | Non-NEM | Non-Export | Withdrawn | Solar PV, Storage | 15 |  | 2021-07-06 | 2021-07-08 |  | 2021-07-08 | 2021-07-08 | 2
121918169 | 2000 | PGE | 93637 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 36.423 |  | 2021-08-18 |  | 2021-12-16 | 2021-08-30 | 2021-08-30 | 8 | 2021-12-22 | 86 | 2021-12-27 | 3 | [34 empty] | 2021-12-27 | 2021-12-27 | 0 | [15 empty] | 2021-12-27 |  |  | 2021-12-27 |  | 2021-12-27 | 0
121951368 | 2001 | PGE | 95667 | Non-NEM | Non-Export | Withdrawn | Storage | 15 |  | 2021-08-24 | 2021-08-27 |  | 2021-08-27 | 2021-08-27 | 3
121954195 | 2002 | PGE | 95123 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.35 |  | 2021-08-25 |  | 2021-12-29 | 2021-09-08 | 2021-09-08 | 9
121968964 | 2003 | PGE | 96104 | Non-NEM | RESBCT | Withdrawn | Solar PV | 0.222 |  | 2021-08-28
121969648 | 2004 | PGE | 94580 | Non-NEM | Non-Export | Withdrawn | Solar PV, Storage, WIND | 14.28 |  | 2021-08-28
122020818 | 2005 | PGE | 95219 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 36.373 |  | 2021-09-09 |  | 2021-09-21 | 2021-09-21 | 2021-09-21 | 8 | 2021-10-22 | 31 | 2021-12-06 | 28 | [34 empty] | 2021-12-06 | 2021-12-06 | 0 | [15 empty] | 2021-12-06 |  |  | 2021-12-06 |  | 2021-12-06 | 0
122034786 | 2006 | PGE | 94028 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.823 |  | 2021-09-10 |  | 2021-11-22 | 2021-09-24 | 2021-09-24 | 10
122051088 | 2007 | PGE | 95573 | Non-NEM | Inadvertent Export | Withdrawn | Storage | 10 |  | 2021-09-15 |  |  | 2021-09-27 | 2021-09-27 | 8 | 2021-09-27 | 8 | 2021-10-14 | 13 | [15 empty] | 2021-09-14 | 2021-09-14 |  | 2021-09-14 | 2021-09-15 | 2
122052523 | 2008 | PGE | 95602 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.232 |  | 2021-09-15 |  | 2021-10-11 | 2021-09-15 | 2021-09-15 | 0 | 2021-10-15 | 22 | 2021-10-18 | 1 | [34 empty] | 2021-10-18 | 2021-10-18 | 0 | [15 empty] | 2021-10-18 |  |  | 2021-10-18 |  | 2021-10-18 | 0
122082268 | 2009 | PGE | 94803 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.423 |  | 2021-09-22 |  | 2021-09-28 | 2021-09-28 | 2021-09-28 | 4 | 2021-10-26 | 24 | 2021-11-29 | 21 | [34 empty] | 2021-11-29 | 2021-11-29 | 0 | [15 empty] | 2021-11-29 |  |  | 2021-11-29 |  | 2021-11-29 | 0
122085965 | 2010 | PGE | 93446 | NEM | EXPNEM | Implementation | Solar PV | 30.015 |  | 2021-09-22 |  | 2021-10-06 | 2021-10-06 | 2021-10-06 | 10 | 2021-11-22 | 42 | 2021-12-15 | 15 | [15 empty] | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 2021-12-15 | 0
122086745 | 2011 | PGE | 94563 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.236 |  | 2021-09-22 |  | 2021-10-06 | 2021-10-06 | 2021-10-06 | 10
122130500 | 2012 | PGE | 94503 | Non-NEM | Break Before Make | Application Review in Progress | ENGN | 72 |  | 2021-09-30 | 2021-10-05 |  | 2021-10-05 | 2021-10-05 | 3
122134314 | 2013 | PGE | 93243 | NEM | EXPNEM | Study in Progress | Solar PV | 1250 |  | 2021-10-01 | 2021-10-04 |  | 2021-10-04 | 2021-10-04 | 1 | 2021-10-13 | 8
122134505 | 2014 | PGE | 95066 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 52.768 |  | 2021-10-01 |  | 2021-10-14 | 2021-10-14 | 2021-10-14 | 9 | 2021-10-22 | 15 | [27 empty] | 2021-10-01 |  | 2021-10-01 |  |  | 2021-10-24
122134922 | 2015 | PGE | 95066 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 32.78 |  | 2021-10-01 |  | 2021-10-14 | 2021-10-14 | 2021-10-14 | 9 | 2021-10-22 | 15 | [27 empty] | 2021-10-01 |  | 2021-10-01 |  |  | 2021-11-01
122135478 | 2016 | PGE | 95376 | NEM | EXPNEM | Study in Progress | Solar PV | 95.8 |  | 2021-10-01 |  | 2021-10-13 | 2021-10-13 | 2021-10-13 | 8 | 2021-12-10 | 47 | 2021-12-29 | 13 | 2021-12-29 | [24 empty] | 2021-10-01 | 2021-12-10 | 2021-10-01
122135614 | 2017 | PGE | 94801 | NEM | EXPNEM | Study in Progress | Solar PV | 2640 |  | 2021-10-01 | 2021-10-04 |  | 2021-10-01 | 2021-10-01 | 0 | 2021-10-27 | 18
122135704 | 2018 | PGE | 93660 | Non-NEM | RESBCT | Withdrawn | Solar PV | 988.418 |  | 2021-10-01 | 2021-10-04 |  | 2021-10-04 | 2021-10-04 | 1 | 2021-10-13 | 8 | 2021-11-01 | 13
122135820 | 2019 | PGE | 94401 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 62.643 |  | 2021-10-01 |  | 2021-10-19 | 2021-10-12 | 2021-10-12 | 7 | 2021-11-04 | 24 | 2021-11-17 | 8 | [15 empty] | 2021-11-17 | 2021-11-29 | 6 | 2021-11-29
122136308 | 2020 | PGE | 95953 | NEM | VNEMMASH | IA in Progress | Solar PV | 35.454 |  | 2021-10-01 |  | 2021-10-04 | 2021-10-04 | 2021-10-04 | 1 | 2021-10-25 | 16 | 2021-11-10 | 12 | [15 empty] | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | [6 empty] | 2021-10-01 | 2021-12-13 | 2021-10-01 | 2021-12-16 | 51
122136321 | 2021 | PGE | 95953 | NEM | VNEMMASH | IA in Progress | Solar PV | 38.018 |  | 2021-10-01 |  | 2021-10-04 | 2021-10-04 | 2021-10-04 | 1 | 2021-10-25 | 16 | 2021-11-10 | 12 | [15 empty] | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | [6 empty] | 2021-10-01 | 2021-11-18 | 2021-10-01 | 2021-11-29 | 38
122136964 | 2022 | PGE | 94403 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-10-01 |  | 2021-11-04 | 2021-10-12 | 2021-10-12 | 7 | 2021-11-08 | 26 | 2021-11-16 | 5 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | [6 empty] | 2021-12-08 | 2021-12-10 | 2021-12-08 | 2021-12-29 | 15
122137005 | 2023 | PGE | 95032 | NEM | SNEM Paired Storage | Commercial | OTHR, Solar PV, Storage | 33.662 |  | 2021-10-01 |  | 2021-10-05 | 2021-10-01 | 2021-10-01 | 0 | 2021-10-21 | 14 | 2021-10-25 | 2 | [25 empty] | 2021-10-01 |  | 2021-10-01 | [6 empty] | 2021-11-18 | 2021-11-18 | 0 | [15 empty] | 2021-11-18 |  |  | 2021-11-18 |  | 2021-11-18 | 0
122137345 | 2024 | PGE | 95205 | NEM | EXPNEM | Implementation | Solar PV | 97.071 |  | 2021-10-01 |  |  | 2021-10-07 | 2021-10-07 | 4 | 2021-10-07 | 4 | 2021-11-19 | 30 | [15 empty] | 2021-11-19 | 2021-11-29 | 4 | 2021-11-29 | 2021-11-30 | 1
122140104 | 2025 | PGE | 93710 | NEM | EXPNEM | IA in Progress | Solar PV | 312 |  | 2021-10-02 |  |  | 2021-10-13 | 2021-10-13 | 7 | 2021-10-13 | 7 | 2021-11-01 | 13 | [15 empty] | 2021-11-01 | 2021-11-01 | 0 | 2021-11-01 | [6 empty] | 2021-10-02 |  | 2021-10-02
122140397 | 2026 | PGE | 93703 | NEM | EXPNEM | IA in Progress | Solar PV | 192 |  | 2021-10-02 |  | 2021-10-04 | 2021-10-04 | 2021-10-04 | 0 | 2021-10-05 | 1 | 2021-10-19 | 10 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | [6 empty] | 2021-10-02 |  | 2021-10-02
122140409 | 2027 | PGE | 93725 | NEM | EXPNEM | Study in Progress | Solar PV | 312 |  | 2021-10-02 |  |  | 2021-10-15 | 2021-10-15 | 9 | 2021-10-15 | 9 | 2021-10-25 | 6 | [25 empty] | 2021-10-02 |  | 2021-10-02
122140455 | 2028 | PGE | 93701 | NEM | EXPNEM | IA in Progress | Solar PV | 180 |  | 2021-10-02 |  |  | 2021-10-11 | 2021-10-11 | 5 | 2021-10-11 | 5 | 2021-10-20 | 7 | [15 empty] | 2021-10-20 | 2021-10-20 | 0 | 2021-10-20 | [6 empty] | 2021-10-02 |  | 2021-10-02
122140472 | 2029 | PGE | 93704 | NEM | EXPNEM | IA in Progress | Solar PV | 195.759 |  | 2021-10-02 |  |  | 2021-10-15 | 2021-10-15 | 9 | 2021-10-15 | 9 | 2021-11-04 | 14 | [15 empty] | 2021-11-04 | 2021-11-30 | 15 | 2021-11-30 | [6 empty] | 2021-10-02 |  | 2021-10-02
122143207 | 2030 | PGE | 95076 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 66.959 |  | 2021-10-04 |  | 2021-10-06 | 2021-10-06 | 2021-10-06 | 2 | 2021-10-08 | 4 | 2021-11-23 | 31 | [15 empty] | 2021-11-23 | 2021-11-23 | 0 | 2021-11-23 | [6 empty] | 2021-10-04 | 2021-11-01 | 2021-10-04 | 2021-11-23 | 35 |  | 2021-11-23 | 2021-11-23 | 0
122143420 | 2031 | PGE | 95912 | NEM | EXPNEM | Implementation | Solar PV | 125 |  | 2021-10-04 |  | 2021-10-11 | 2021-10-11 | 2021-10-11 | 5 | 2021-10-12 | 6 | 2021-11-30 | 32 | [15 empty] | 2021-11-30 | 2021-12-01 | 1 | 2021-12-01 | 2021-12-02 | 1 |  |  |  |  | 2021-12-01 | 2021-12-02 | 2021-12-01 | 2021-12-02 | 1
122144546 | 2032 | PGE | 94954 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 786.5 |  | 2021-10-04 |  | 2021-10-17 | 2021-10-17 | 2021-10-17 | 9 | 2021-11-05 | 24 | 2021-12-22 | 30 | 2021-12-22
122144589 | 2033 | PGE | 94589 | NEM | VNEMSOMAH | Implementation | Solar PV | 100.91 |  | 2021-10-04 |  | 2021-10-06 | 2021-10-06 | 2021-10-06 | 2 | 2021-10-08 | 4 | 2021-11-10 | 23 | [15 empty] | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | 2021-12-02 | 13 |  |  |  |  | 2021-10-04 | 2021-10-25 | 2021-10-04 | 2021-11-03 | 22 |  | 2021-11-05 | 2021-11-10 | 3
122144594 | 2034 | PGE | 94589 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 103.993 |  | 2021-10-04 |  | 2021-10-06 | 2021-10-06 | 2021-10-06 | 2 | 2021-10-08 | 4 | 2021-11-10 | 23 | [15 empty] | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | [6 empty] | 2021-10-04 | 2021-10-25 | 2021-10-04 | 2021-11-03 | 22 |  | 2021-11-05 | 2021-11-10 | 3
122144942 | 2035 | PGE | 93446 | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-10-04 |  | 2021-10-15 | 2021-10-15 | 2021-10-15 | 9 | 2021-10-28 | 18 | 2021-11-19 | 15 | [15 empty] | 2021-11-19 | 2021-11-19 | 0 | 2021-11-19 | 2021-12-29 | 26 |  |  |  |  | 2021-10-04 |  | 2021-10-04 | [6 empty] | 2021-12-31 | [17 empty] | 2021-12-31
122145024 | 2036 | PGE | 94517 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-10-04 |  |  | 2021-10-07 | 2021-10-07 | 3 | 2021-10-07 | 3 | 2021-10-13 | 4 | [15 empty] | 2021-09-29 | 2021-09-29 |  | 2021-09-29 | 2021-10-05 | 5
122145948 | 2037 | PGE | 95948 | NEM | EXPNEM | IA in Progress | Solar PV | 214.508 |  | 2021-10-04 |  | 2021-10-06 | 2021-10-06 | 2021-10-06 | 2 | 2021-10-14 | 8 | 2021-10-28 | 10 | [15 empty] | 2021-10-28 | 2021-10-28 | 0 | 2021-10-28 | [7 empty] | 2021-10-14 | 2021-10-14 | 2021-10-27 | 9
122146209 | 2038 | PGE | 93243 | NEM | EXPNEM | Application Review in Progress | Solar PV | 875 |  | 2021-10-04 |  |  | 2021-10-18 | 2021-10-18 | 10
122146971 | 2039 | PGE | 95503 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-10-05 |  |  | 2021-10-08 | 2021-10-08 | 3 | 2021-10-08 | 3 | 2021-10-14 | 4 | [15 empty] | 2021-10-04 | 2021-10-04 |  | 2021-10-04 | 2021-10-05 | 2
122147302 | 2040 | PGE | 93402 | NEM | VNEM | Implementation | Solar PV | 200 |  | 2021-10-05 |  | 2021-10-15 | 2021-10-15 | 2021-10-15 | 8 | 2021-10-20 | 11 | 2021-12-13 | 35 | [15 empty] | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13 | 2021-12-15 | 2 | [10 empty] | 2021-12-16 | 2021-12-16 | 0
122147527 | 2041 | PGE | 95959 | NEM | EXPNEM | Study in Progress | Solar PV | 137.349 |  | 2021-10-05 |  | 2021-10-14 | 2021-10-12 | 2021-10-12 | 5 | 2021-10-27 | 16 | 2021-11-10 | 10 | 2021-11-10
122149023 | 2042 | PGE | 94903 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 37.598 |  | 2021-10-05 |  |  | 2021-10-19 | 2021-10-19 | 10 | 2021-10-21 | 12 | 2021-11-12 | 15 | [15 empty] | 2021-11-12 | 2021-11-12 | 0 | 2021-11-12 | [6 empty] | 2021-10-05 | 2021-11-12 | 2021-10-05 | 2021-12-15 | 48
122149234 | 2043 | PGE | 95117 | NEM | EXPNEM | Withdrawn | Solar PV | 34.65 |  | 2021-10-05 |  | 2021-10-13 | 2021-10-13 | 2021-10-13 | 6
122149306 | 2044 | PGE | 95361 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.163 |  | 2021-10-05 |  | 2021-11-23 | 2021-10-05 | 2021-10-05 | 0
122149556 | 2045 | PGE | 94571 | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-10-05 |  |  | 2021-10-12 | 2021-10-12 | 5 | 2021-10-12 | 5 | 2021-10-28 | 12 | [15 empty] | 2021-10-28 | 2021-11-01 | 2 | 2021-11-01 | 2021-11-05 | 4 | [13 empty] | 2021-11-05 | 2021-11-16 | 6 | [15 empty] | 2021-11-05 | 2021-11-05 | 0 | 2021-11-16
122149632 | 2046 | PGE | 94571 | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.3 |  | 2021-10-05 |  | 2021-10-13 | 2021-10-13 | 2021-10-13 | 6
122149955 | 2047 | PGE | 94558 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 159.12 |  | 2021-10-05 |  | 2021-10-08 | 2021-10-08 | 2021-10-08 | 3
122151178 | 2048 | PGE | 94903 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 37.598 |  | 2021-10-05 |  |  | 2021-10-19 | 2021-10-19 | 10 | 2021-10-21 | 12 | 2021-11-12 | 15 | [15 empty] | 2021-11-12 | 2021-11-12 | 0 | 2021-11-12 | [6 empty] | 2021-10-05 | 2021-11-12 | 2021-10-05 | 2021-12-15 | 48
122151409 | 2049 | PGE | 93701 | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-10-05 |  |  | 2021-10-12 | 2021-10-12 | 5 | 2021-10-12 | 5 | 2021-10-22 | 8 | [15 empty] | 2021-10-22 | 2021-10-25 | 1 | 2021-10-25 | [6 empty] | 2021-10-05 |  | 2021-10-05
122151732 | 2050 | PGE | 93727 | NEM | EXPNEM | IA in Progress | Solar PV | 216 |  | 2021-10-05 |  |  | 2021-10-12 | 2021-10-12 | 5 | 2021-10-12 | 5 | 2021-10-25 | 9 | [15 empty] | 2021-10-25 | 2021-10-25 | 0 | 2021-10-25 | [6 empty] | 2021-10-05 |  | 2021-10-05
122151912 | 2051 | PGE | 94804 | NEM | EXPNEM | Commercial | Solar PV | 86.4 |  | 2021-10-05 |  |  | 2021-10-07 | 2021-10-07 | 2 | 2021-10-07 | 2 | 2021-10-14 | 5 | [15 empty] | 2021-10-14 | 2021-10-14 | 0 | 2021-10-14 | 2021-10-15 | 1 | [13 empty] | 2021-10-25 | 2021-11-03 | 7 | [15 empty] | 2021-10-25 | 2021-10-25 | 0 | 2021-11-03 |  | 2021-11-03 | 0
122151929 | 2052 | PGE | 95240 | NEM | EXPNEM | Application Accepted | Solar PV | 600 |  | 2021-10-05 |  | 2021-10-17 | 2021-10-17 | 2021-10-17 | 8 | 2021-11-04 | 22 | [27 empty] | 2021-10-05 | 2021-11-03 | 2021-10-05 | 2021-11-29 | 36
122152216 | 2053 | PGE | 93711 | NEM | EXPNEM | Application Accepted | Solar PV | 255.598 |  | 2021-10-05 |  |  | 2021-10-07 | 2021-10-07 | 2 | 2021-10-07 | 2 | 2021-10-20 | 9 | [25 empty] | 2021-10-05 |  | 2021-10-05 |  |  | 2021-10-18
122152224 | 2054 | PGE | 95361 | NEM | EXPNEM | IA in Progress | Solar PV | 1392.353 |  | 2021-10-05 | 2021-10-08 |  | 2021-10-05 | 2021-10-05 | 0 | 2021-10-20 | 11 | 2021-11-16 | 18 | [15 empty] | 2021-11-29 | 2021-12-02 | 3 | 2021-12-02
122153620 | 2055 | PGE | 95212 | NEM | EXPNEM | Study in Progress | Solar PV | 98.083 |  | 2021-10-06 |  | 2021-12-08 | 2021-10-11 | 2021-10-11 | 3 | 2021-12-09 | 43 | 2021-12-23 | 10 | 2021-12-23 | [24 empty] | 2021-10-06 |  | 2021-10-06 | [9 empty] | 2021-09-23 |  | 77
122154145 | 2056 | PGE | 94945 | NEM | EXPNEM | IA in Progress | Solar PV | 36 |  | 2021-10-06 |  |  | 2021-10-07 | 2021-10-07 | 1 | 2021-10-07 | 1 | 2021-10-21 | 10 | [15 empty] | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21
122154225 | 2057 | PGE | 95070 | NEM | EXPNEM | Application Review in Progress | Solar PV | 36.149 |  | 2021-10-06 |  | 2021-10-07 | 2021-10-07 | 2021-10-07 | 1
122154971 | 2058 | PGE | 93705 | NEM | EXPNEM | IA in Progress | Solar PV | 180 |  | 2021-10-06 |  |  | 2021-10-18 | 2021-10-18 | 8 | 2021-10-18 | 8 | 2021-11-01 | 10 | [15 empty] | 2021-11-01 | 2021-11-01 | 0 | 2021-11-01 | [6 empty] | 2021-10-06 |  | 2021-10-06
122155439 | 2059 | PGE | 95415 | NEM | EXPNEM | Application Review in Progress | Solar PV | 36 |  | 2021-10-06 |  | 2021-10-18 | 2021-10-18 | 2021-10-18 | 8 | [29 empty] | 2021-10-06 |  | 2021-10-06
122155566 | 2060 | PGE | 94563 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 34.963 |  | 2021-10-06 |  | 2021-10-06 | 2021-10-06 | 2021-10-06 | 0 | 2021-11-18 | 30 | 2021-11-22 | 2 | [25 empty] | 2021-10-06 |  | 2021-10-06
122157182 | 2061 | PGE | 95212 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.45 |  | 2021-10-06 |  | 2021-11-30 | 2021-10-08 | 2021-10-08 | 2
122157522 | 2062 | PGE | 93309 | NEM | EXPNEM | Study in Progress | Solar PV | 1200 |  | 2021-10-06 | 2021-10-08 |  | 2021-10-08 | 2021-10-08 | 2 | 2021-10-13 | 5 | [5 empty] | 2021-10-19 | 2021-11-15 | 18 | 2021-11-15 |  | 1 | 2021-11-23 |  |  |  | 2021-11-15 | 1 | [15 empty] | 2021-12-01
122157567 | 2063 | PGE | 95377 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 280 |  | 2021-10-06 | 2021-10-07 |  | 2021-10-07 | 2021-10-07 | 1 | 2021-11-03 | 20 | 2021-11-24 | 14 | 2021-12-17 | [24 empty] | 2021-10-06 | 2021-11-09 | 2021-10-06 | 2021-11-09 | 24
122157944 | 2064 | PGE | 93401 | NEM | VNEM | Application Review in Progress | Solar PV | 42.586 |  | 2021-10-06 |  | 2021-10-20 | 2021-10-20 | 2021-10-20 | 10
122159148 | 2065 | PGE | 93644 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 36.223 |  | 2021-10-07 |  | 2021-10-08 | 2021-10-08 | 2021-10-08 | 1 | 2021-12-01 | 36 | 2021-12-03 | 2 | [34 empty] | 2021-12-03 | 2021-12-03 | 0 | [15 empty] | 2021-12-03 |  |  | 2021-12-03 |  | 2021-12-03 | 0
122159858 | 2066 | PGE | 95020 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.393 |  | 2021-10-07 |  | 2021-12-08 | 2021-10-08 | 2021-10-08 | 1 | 2021-12-14 | 45 | 2021-12-20 | 4 | [34 empty] | 2021-12-20 | 2021-12-20 | 0 | [15 empty] | 2021-12-20 |  |  | 2021-12-20 |  | 2021-12-20 | 0
122160070 | 2067 | PGE | 95521 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-10-07 |  |  | 2021-10-21 | 2021-10-21 | 10 | 2021-10-21 | 10 | 2021-11-05 | 11 | [15 empty] | 2021-10-06 | 2021-10-06 |  | 2021-10-06 | 2021-10-21 | 12
122160268 | 2068 | PGE | 95037 | NEM | EXPNEM | Application Review in Progress | Solar PV | 259.89 |  | 2021-10-07 |  | 2021-10-15 | 2021-10-15 | 2021-10-15 | 6
122160594 | 2069 | PGE | 95991 | NEM | EXPNEM | Study in Progress | Solar PV | 364.492 |  | 2021-10-07 |  | 2021-10-14 | 2021-10-14 | 2021-10-14 | 5 | 2021-10-26 | 13 | 2021-11-15 | 13 | 2021-11-15 | [24 empty] | 2021-10-07 | 2021-10-26 | 2021-10-07 | 2021-11-04 | 20
122160727 | 2070 | PGE | 93637 | NEM | EXPNEM | Study in Progress | Solar PV | 4954.17 |  | 2021-10-07 | 2021-10-08 |  | 2021-10-08 | 2021-10-08 | 1 | 2021-10-13 | 4 | [5 empty] | 2021-10-18 | 2021-11-16 | 20 | 2021-11-16 | 2021-11-30 | 8 |  |  |  | 2021-11-30 | 2021-12-17 | 13
122162128 | 2071 | PGE | 94503 | Non-NEM | Break Before Make | Application Review in Progress | ENGN |  |  | 2021-10-07 | 2021-10-12 |  | 2021-10-12 | 2021-10-12 | 3
122162214 | 2072 | PGE | 95501 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 10 |  | 2021-10-07 | 2021-10-20 |  | 2021-10-20 | 2021-10-20 | 9
122163322 | 2073 | PGE | 95338 | NEM | EXPNEM | Implementation | Solar PV | 62.5 |  | 2021-10-07 |  | 2021-10-15 | 2021-10-11 | 2021-10-11 | 2 | 2021-10-27 | 14 | 2021-11-10 | 10 | [15 empty] | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | 2021-11-16 | 3
122163762 | 2074 | PGE | 93727 | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.2 |  | 2021-10-07 |  | 2021-10-18 | 2021-10-18 | 2021-10-18 | 7
122164274 | 2075 | PGE | 93309 | NEM | EXPNEM | Commercial | Solar PV | 33.128 |  | 2021-10-07 |  | 2021-10-15 | 2021-10-15 | 2021-10-15 | 6 | 2021-10-25 | 12 | 2021-10-27 | 2 | [15 empty] | 2021-10-27 | 2021-10-27 | 0 | 2021-10-27 | 2021-11-19 | 16 | [13 empty] | 2021-12-16 | 2021-12-28 | 8 | [15 empty] | 2021-12-16 | 2021-12-17 | 1 | 2021-12-28 |  | 2021-12-29 | 1
122164314 | 2076 | PGE | 93309 | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-10-07 |  | 2021-10-15 | 2021-10-15 | 2021-10-15 | 6 | 2021-10-19 | 8 | 2021-10-21 | 2 | [15 empty] | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21 | 2021-11-19 | 20 | [13 empty] | 2021-12-16 | 2021-12-28 | 8 | [15 empty] | 2021-12-16 | 2021-12-17 | 1 | 2021-12-28 |  | 2021-12-29 | 1
122167420 | 2077 | PGE | 94928 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 5750.204 |  | 2021-10-08 | 2021-10-08 |  | 2021-10-08 | 2021-10-08 | 0 | 2021-10-27 | 13 | [5 empty] | 2021-10-27 | 2021-11-23 | 18 | 2021-11-23 | 2021-11-23 | 0 | 2021-12-09 |  |  | 2021-11-23 | 2021-11-23 | 0 | [15 empty] | 2021-11-29 | 2021-11-29 | 2021-11-29 | 0
122167561 | 2078 | PGE | 94612 | NEM | EXPNEM | Withdrawn | Solar PV | 37.196 |  | 2021-10-08 |  | 2021-10-14 | 2021-10-14 | 2021-10-14 | 4 | 2021-10-27 | 13 | 2021-11-15 | 12
122167654 | 2079 | PGE | 94562 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 53.892 |  | 2021-10-08 |  |  | 2021-10-22 | 2021-10-22 | 10 | 2021-10-22 | 10 | 2021-11-12 | 14
122168119 | 2080 | PGE | 94930 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 30.402 |  | 2021-10-08 |  | 2021-10-18 | 2021-10-18 | 2021-10-18 | 6 | 2021-11-02 | 17 | 2021-11-24 | 15 | [15 empty] | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | [6 empty] | 2021-10-08 |  | 2021-10-08 |  |  | 2021-12-13
122168980 | 2081 | PGE | 94558 | NEM | EXPNEM | Commercial | Solar PV | 34.179 |  | 2021-10-08 |  |  | 2021-10-19 | 2021-10-19 | 7 | 2021-10-19 | 7 | 2021-10-26 | 5 | [15 empty] | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26 | 2021-10-29 | 3 | [13 empty] | 2021-11-17 | 2021-11-30 | 7 | [15 empty] | 2021-11-17 | 2021-11-17 | 0 | 2021-11-30 |  | 2021-12-01 | 1
122169001 | 2082 | PGE | 93656 | NEM | EXPNEM | Study in Progress | Solar PV | 2375 |  | 2021-10-08 | 2021-10-12 |  | 2021-10-12 | 2021-10-12 | 2 | 2021-10-20 | 8 | [5 empty] | 2021-11-17 | 2021-12-17 | 20 | 2021-12-17 | 2021-12-22 | 3 |  |  |  | 2021-12-22
122169461 | 2083 | PGE | 94949 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 45.15 |  | 2021-10-08 |  | 2021-10-15 | 2021-10-11 | 2021-10-11 | 1
122169547 | 2084 | PGE | 93245 | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-10-08 |  | 2021-12-02 | 2021-10-22 | 2021-10-22 | 10 | 2021-12-08 | 40 | 2021-12-28 | 14 | [15 empty] | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28 | [6 empty] | 2021-11-10 | 2021-11-17 | 2021-11-10 | 2021-12-06 | 15
122169773 | 2085 | PGE | 95035 | NEM | EXPNEM | Study in Progress | Solar PV | 180.797 |  | 2021-10-08 |  | 2021-10-18 | 2021-10-18 | 2021-10-18 | 6 | 2021-12-21 | 49
122169882 | 2086 | PGE | 95341 | NEM | EXPNEM | Study in Progress | Solar PV | 4125 |  | 2021-10-08 | 2021-10-12 |  | 2021-10-12 | 2021-10-12 | 2 | 2021-10-20 | 8 | [5 empty] | 2021-11-01 | 2021-11-30 | 18 | 2021-11-30 | 2021-12-07 | 5 | 2021-12-13 |  |  | 2021-12-07 | 2021-12-08 | 1
122171742 | 2087 | PGE | 93725 | NEM | EXPNEM | IA in Progress | Solar PV | 227.075 |  | 2021-10-09 |  |  | 2021-10-19 | 2021-10-19 | 6 | 2021-10-19 | 6 | 2021-11-01 | 9 | [15 empty] | 2021-11-01 | 2021-11-02 | 1 | 2021-11-02 | [6 empty] | 2021-10-09 |  | 2021-10-09
122184074 | 2088 | PGE | 93940 | NEM | EXPNEM | IA in Progress | Solar PV | 58.645 |  | 2021-10-11 |  | 2021-10-18 | 2021-10-18 | 2021-10-18 | 5 | 2021-11-02 | 16 | 2021-12-10 | 25 | [15 empty] | 2021-12-10 | 2021-12-10 | 0 | 2021-12-10
122185032 | 2089 | PGE | 93940 | NEM | EXPNEM | IA in Progress | Solar PV | 105.02 |  | 2021-10-11 |  | 2021-10-25 | 2021-10-25 | 2021-10-25 | 10 | 2021-11-05 | 19 | 2021-12-14 | 24 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14
122185245 | 2090 | PGE | 94603 | NEM | EXPNEM | Implementation | Solar PV | 91.26 |  | 2021-10-11 |  | 2021-10-14 | 2021-10-14 | 2021-10-14 | 3 | 2021-10-14 | 3 | 2021-10-18 | 2 | [15 empty] | 2021-10-18 | 2021-10-18 | 0 | 2021-10-18 | 2021-11-09 | 16
122185378 | 2091 | PGE | 94550 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 38.396 |  | 2021-10-11 |  | 2021-10-29 | 2021-10-21 | 2021-10-21 | 8
122185382 | 2092 | PGE | 95112 | NEM | EXPNEM | IA in Progress | Solar PV | 633.3 |  | 2021-10-11 |  | 2021-10-14 | 2021-10-14 | 2021-10-14 | 3 | 2021-11-05 | 19 | 2021-12-16 | 26 | [15 empty] | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16 | [7 empty] | 2021-12-16 | 2021-12-16
122186309 | 2093 | PGE | 94010 | NEM | EXPNEM | IA in Progress | Solar PV | 58.883 |  | 2021-10-11 |  | 2021-10-25 | 2021-10-25 | 2021-10-25 | 10 | 2021-11-10 | 22 | 2021-12-27 | 30 | [15 empty] | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27
122186321 | 2094 | PGE | 93940 | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-10-11 |  |  | 2021-10-14 | 2021-10-14 | 3 | 2021-10-14 | 3 | 2021-10-28 | 10 | [15 empty] | 2021-10-28 | 2021-11-01 | 2 | 2021-11-01 | [6 empty] | 2021-10-11 |  | 2021-10-11
122186458 | 2095 | PGE | 93940 | NEM | EXPNEM | IA in Progress | Solar PV | 40.354 |  | 2021-10-11 |  |  | 2021-10-14 | 2021-10-14 | 3 | 2021-10-14 | 3 | 2021-10-28 | 10 | [15 empty] | 2021-10-28 | 2021-11-01 | 2 | 2021-11-01
122186521 | 2096 | PGE | 93420 | NEM | EXPNEM | Application Accepted | Solar PV | 120.756 |  | 2021-10-11 |  | 2021-11-16 | 2021-10-13 | 2021-10-13 | 2 | 2021-12-07 | 38
122186529 | 2097 | PGE | 94025 | NEM | EXPNEM | IA in Progress | Solar PV | 170.14 |  | 2021-10-11 |  | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2 | 2021-10-21 | 8 | 2021-10-21 | 0 | [15 empty] | 2021-10-21 | 2021-10-22 | 1 | 2021-10-22 | [6 empty] | 2021-10-11 | 2021-11-09 | 2021-10-11 | 2021-12-06 | 37
122187180 | 2098 | PGE | 93206 | NEM | EXPNEM | Study in Progress | Solar PV | 150 |  | 2021-10-11 |  |  | 2021-10-25 | 2021-10-25 | 10 | 2021-11-04 | 18 | [5 empty] | 2021-11-04 | 2021-12-07 | 20 | 2021-12-07 | [18 empty] | 2021-10-11 |  | 2021-10-11
122187331 | 2099 | PGE | 94507 | NEM | EXPNEM | Implementation | Solar PV | 193.9 |  | 2021-10-11 |  | 2021-10-22 | 2021-10-22 | 2021-10-22 | 9 | 2021-11-01 | 15 | 2021-11-16 | 10 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-12-08 | 14 |  |  |  |  | 2021-10-11 | 2021-11-01 | 2021-10-11 | 2021-11-22 | 29
122188567 | 2100 | PGE | 94025 | NEM | EXPNEM | IA in Progress | Solar PV | 172.823 |  | 2021-10-12 |  | 2021-10-22 | 2021-11-15 | 2021-10-22 | 8 | 2021-11-19 | 27 | 2021-12-13 | 14 | [15 empty] | 2021-12-13 | 2021-12-28 | 11 | 2021-12-28 | [6 empty] | 2021-10-12 |  | 2021-10-12
122188950 | 2101 | PGE | 94947 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-10-12 | 2021-10-22 |  | 2021-10-22 | 2021-10-22 | 8 | 2021-10-25 | 9 | 2021-11-01 | 5 | [55 empty] | 2021-11-01 |  | 2021-11-01 | 1
122189184 | 2102 | PGE | 93940 | NEM | EXPNEM | IA in Progress | Solar PV | 37.75 |  | 2021-10-12 |  |  | 2021-10-13 | 2021-10-13 | 1 | 2021-10-13 | 1 | 2021-10-26 | 9 | [15 empty] | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26 | [6 empty] | 2021-10-12 |  | 2021-10-12
122189742 | 2103 | PGE | 95035 | NEM | VNEM | Implementation | Solar PV | 37.8 |  | 2021-10-12 |  | 2021-10-19 | 2021-10-19 | 2021-10-19 | 5 | 2021-10-22 | 8 | 2021-11-09 | 12 | [15 empty] | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | 2021-12-08 | 18 |  |  |  |  | 2021-10-12 |  | 2021-10-12 |  |  | 2021-11-01 | 2021-11-09 | 2021-12-09 | 6
122190165 | 2104 | PGE | 95060 | Non-NEM | Inadvertent Export | Application Accepted | Storage | 980 |  | 2021-10-12 | 2021-10-13 |  | 2021-10-13 | 2021-10-13 | 1 | 2021-12-15 | 43 | [28 empty] | 2021-12-17 | 2021-12-17
122190544 | 2105 | PGE | 95603 | NEM | EXPNEM | IA in Progress | Solar PV | 40.891 |  | 2021-10-12 |  | 2021-10-26 | 2021-10-26 | 2021-10-26 | 10 | 2021-10-26 | 10 | 2021-11-08 | 9 | [15 empty] | 2021-11-08 | 2021-11-08 | 0 | 2021-11-08
122190665 | 2106 | PGE | 93311 | NEM | EXPNEM | Study in Progress | ENGN | 1000 |  | 2021-10-12 |  |  | 2021-10-15 | 2021-10-15 | 3 | 2021-10-15 | 3 | 2021-10-31 | 10 | 2021-10-31 | 2021-11-30 | 18 | 2021-11-30 | 2021-12-29 | 21 | 2021-12-29
122190846 | 2107 | PGE | 93940 | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-10-12 |  |  | 2021-10-14 | 2021-10-14 | 2 | 2021-10-14 | 2 | 2021-10-28 | 10 | [15 empty] | 2021-10-28 | 2021-11-01 | 2 | 2021-11-01
122191437 | 2108 | PGE | 93705 | NEM | EXPNEM | IA in Progress | Solar PV | 230 |  | 2021-10-12 |  | 2021-10-26 | 2021-10-26 | 2021-10-26 | 10 | 2021-11-02 | 15 | 2021-11-09 | 5 | [15 empty] | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | [6 empty] | 2021-10-12 |  | 2021-10-12
122191504 | 2109 | PGE | 95304 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 704.8 |  | 2021-10-12 | 2021-10-13 |  | 2021-10-12 | 2021-10-12 | 0 | 2021-11-10 | 21 | 2021-12-31 | 34 | [25 empty] | 2021-10-12 | 2021-12-10 | 2021-10-12 | 2021-12-15 | 43 | 2021-12-15
122191709 | 2110 | PGE | 94558 | NEM | EXPNEM | Implementation | Solar PV | 31.868 |  | 2021-10-12 |  | 2021-11-15 | 2021-10-22 | 2021-10-22 | 8 | 2021-11-17 | 25 | 2021-12-06 | 11 | [15 empty] | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-08 | 2 | [13 empty] | 2021-12-22 | [17 empty] | 2021-12-22 | 2021-12-22 | 0
122191832 | 2111 | PGE | 93901 | NEM | EXPNEM | IA in Progress | Solar PV | 300 |  | 2021-10-12 |  |  | 2021-10-18 | 2021-10-18 | 4 | 2021-10-21 | 7 | 2021-10-28 | 5 | [15 empty] | 2021-10-28 | 2021-11-17 | 13 | 2021-11-17 | 2021-12-31 | 30
122191938 | 2112 | PGE | 95112 | NEM | EXPNEM | Application Review in Progress | Solar PV | 93.5 |  | 2021-10-12 |  | 2021-10-26 | 2021-10-26 | 2021-10-26 | 10 | [29 empty] | 2021-10-12 |  | 2021-10-12
122192117 | 2113 | PGE | 94710 | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 |  | 2021-10-12 |  | 2021-10-26 | 2021-10-26 | 2021-10-26 | 10
122192180 | 2114 | PGE | 93706 | NEM | EXPNEM | Commercial | Solar PV | 52.882 |  | 2021-10-12 |  | 2021-10-13 | 2021-10-13 | 2021-10-13 | 1 | 2021-10-15 | 3 | 2021-11-08 | 16 | [15 empty] | 2021-11-08 | 2021-11-08 | 0 | 2021-11-08 | 2021-11-19 | 8 | [13 empty] | 2021-12-15 | 2021-12-23 | 6 | [15 empty] | 2021-12-15 | 2021-12-16 | 1 | 2021-12-23 |  | 2021-12-24 | 1
122192182 | 2115 | PGE | 95503 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-10-12 | 2021-10-25 |  | 2021-10-25 | 2021-10-25 | 9 | 2021-11-15 | 23 | 2021-12-02 | 11
122192250 | 2116 | PGE | 94080 | NEM | EXPNEM | Implementation | Solar PV | 60 |  | 2021-10-12 |  | 2021-10-13 | 2021-10-13 | 2021-10-13 | 1 | 2021-11-01 | 14 | 2021-11-16 | 10 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-19 | 3 |  |  |  |  | 2021-10-12 | 2021-11-30 | 2021-10-12 | 2021-12-15 | 43
122192632 | 2117 | PGE | 93637 | NEM | EXPNEM | Implementation | Solar PV | 420 |  | 2021-10-12 |  |  | 2021-10-14 | 2021-10-14 | 2 | 2021-10-14 | 2 | 2021-10-29 | 11 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | 2021-11-29 | 18 |  |  |  |  | 2021-10-12 | 2021-10-14 | 2021-10-12 | 2021-10-27 | 11
122193209 | 2118 | PGE | 94583 | Non-NEM | Inadvertent Export | Application Accepted | Storage | 929.5 |  | 2021-10-13 | 2021-10-15 |  | 2021-10-13 | 2021-10-13 | 0 | 2021-11-24 | 29
122193232 | 2119 | PGE | 94563 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-10-12 |  |  | 2021-10-13 | 2021-10-13 | 1 | 2021-10-13 | 1 | 2021-10-14 | 1
122195463 | 2120 | PGE | 94133 | NEM | EXPNEM | IA in Progress | Solar PV | 72 |  | 2021-10-13 |  | 2021-10-15 | 2021-10-15 | 2021-10-15 | 2 | 2021-11-29 | 30 | 2021-12-13 | 10 | [15 empty] | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13 | [7 empty] | 2021-11-29 | 2021-11-29 | 2021-12-15 | 12
122199699 | 2121 | PGE | 94588 | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-10-13 |  | 2021-10-14 | 2021-10-14 | 2021-10-14 | 1 | 2021-10-26 | 9 | 2021-10-28 | 2 | [15 empty] | 2021-10-28 | 2021-10-28 | 0 | 2021-10-28
122199719 | 2122 | PGE | 94566 | NEM | EXPNEM | Study in Progress | Solar PV | 483.1 |  | 2021-10-13 |  | 2021-10-27 | 2021-10-27 | 2021-10-27 | 10 | 2021-12-13 | 40 | [28 empty] | 2021-12-31 | 2021-12-31
122199823 | 2123 | PGE | 93420 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-10-13 | 2021-10-27 |  | 2021-10-27 | 2021-10-27 | 10 | 2021-11-04 | 16 | 2021-11-18 | 9
122200004 | 2124 | PGE | 94566 | NEM | EXPNEM | Withdrawn | Solar PV | 400 |  | 2021-10-13 |  | 2021-10-26 | 2021-10-26 | 2021-10-26 | 9 | 2021-11-19 | 26 | [32 empty] | 2021-12-13
122200118 | 2125 | PGE | 94566 | NEM | EXPNEM | Withdrawn | Solar PV | 524.8 |  | 2021-10-13 |  |  | 2021-10-27 | 2021-10-27 | 10 | 2021-10-27 | 10
122206225 | 2126 | PGE | 95209 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2330 |  | 2021-10-14 | 2021-10-18 |  | 2021-10-14 | 2021-10-14 | 0 | 2021-11-17 | 23 | [5 empty] | 2021-12-03
122206852 | 2127 | PGE | 93640 | NEM | EXPNEM | IA in Progress | Solar PV | 840 |  | 2021-10-14 |  | 2021-10-14 | 2021-10-14 | 2021-10-14 | 0 | 2021-10-21 | 5 | 2021-12-23 | 42 | [15 empty] | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23 | [6 empty] | 2021-10-14 | 2021-10-15 | 2021-10-14 | 2021-10-27 | 9
122207612 | 2128 | PGE | 95409 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-10-14 | 2021-10-15 |  | 2021-10-15 | 2021-10-15 | 1 | [19 empty] | 2021-10-14 | 2021-10-14 |  | 2021-10-14 | 2021-10-14 | 1
122208006 | 2129 | PGE | 93720 | NEM | EXPNEM | IA in Progress | Solar PV | 312.5 |  | 2021-10-14 |  |  | 2021-10-18 | 2021-10-18 | 2 | 2021-10-18 | 2 | 2021-11-08 | 15 | [15 empty] | 2021-11-08 | 2021-12-02 | 15 | 2021-12-02 | [6 empty] | 2021-10-14 |  | 2021-10-14
122208568 | 2130 | PGE | 95901 | NEM | EXPNEM | Study in Progress | Solar PV | 480 |  | 2021-10-14 |  | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2 | 2021-11-05 | 16 | 2021-11-22 | 10 | 2021-11-22 | [24 empty] | 2021-10-14 | 2021-10-18 | 2021-10-14 | 2021-11-01 | 12
122210226 | 2131 | PGE | 94538 | NEM | EXPNEM | Application Review in Progress | Solar PV | 500 |  | 2021-10-14 |  | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2
122210450 | 2132 | PGE | 95337 | NEM | EXPNEM | Study in Progress | Solar PV | 200 |  | 2021-10-14 |  |  | 2021-10-28 | 2021-10-28 | 10 | 2021-10-28 | 10 | 2021-12-09 | 27 | 2021-12-09 | [24 empty] | 2021-10-14 |  | 2021-10-14
122210491 | 2133 | PGE | 95322 | Non-NEM | Inadvertent Export | Application Accepted | Storage | 929.5 |  | 2021-10-14 | 2021-10-15 |  | 2021-10-15 | 2021-10-15 | 1 | 2021-11-24 | 28
122211918 | 2134 | PGE | 94588 | NEM | EXPNEM | IA in Progress | Solar PV | 225 |  | 2021-10-15 |  | 2021-10-28 | 2021-10-28 | 2021-10-28 | 9 | 2021-11-16 | 21 | 2021-12-21 | 23 | [15 empty] | 2021-12-21 | 2021-12-21 | 0 | 2021-12-21
122213809 | 2135 | PGE | 93249 | Non-NEM | Non-Export | IA in Progress | Solar PV | 747.708 |  | 2021-10-15 | 2021-10-18 |  | 2021-10-18 | 2021-10-18 | 1 | 2021-10-27 | 8 | 2021-12-08 | 27 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | [7 empty] | 2021-11-04 | 2021-11-04 | 2021-12-03 | 18
122213892 | 2136 | PGE | 93654 | NEM | EXPNEM | Application Review in Progress | Solar PV | 44.593 |  | 2021-10-15 |  | 2021-10-22 | 2021-10-22 | 2021-10-22 | 5 | [29 empty] | 2021-10-15 |  | 2021-10-15
122214499 | 2137 | PGE | 93405 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-10-15 | 2021-10-26 |  | 2021-10-26 | 2021-10-26 | 7 | 2021-11-10 | 18 | 2021-11-16 | 3 | [15 empty] | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26
122220359 | 2138 | PGE | 94062 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 41.289 |  | 2021-10-18 |  | 2021-10-28 | 2021-10-18 | 2021-10-18 | 0 | 2021-11-05 | 14 | 2021-11-07 | 0
122220601 | 2139 | PGE | 95242 | NEM | EXPNEM | Study in Progress | Solar PV | 125 |  | 2021-10-18 |  | 2021-10-27 | 2021-10-27 | 2021-10-27 | 7 | 2021-11-12 | 18 | 2021-12-01 | 11 | 2021-12-01 | 2021-12-27 | 18 | 2021-12-27 | [21 empty] | 2021-10-18 | 2021-11-12 | 2021-10-18 | 2021-12-06 | 32
122221121 | 2140 | PGE | 95020 | NEM | EXPNEM | Implementation | Solar PV | 473.704 |  | 2021-10-18 |  |  | 2021-10-28 | 2021-10-28 | 8 | 2021-10-28 | 8 | 2021-11-12 | 10 | [15 empty] | 2021-11-12 | 2021-11-12 | 0 | 2021-11-12 | 2021-11-12 | 0
122221594 | 2141 | PGE | 93446 | NEM | EXPNEM | Implementation | Solar PV | 31.88 |  | 2021-10-18 |  | 2021-11-01 | 2021-11-01 | 2021-11-01 | 10 | 2021-12-01 | 29 | 2021-12-15 | 10 | [15 empty] | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 2021-12-21 | 4 | [5 empty] | 2021-12-21 | 2021-12-21
122222153 | 2142 | PGE | 95236 | NEM | EXPNEM | IA in Progress | Solar PV | 40.388 |  | 2021-10-18 |  |  | 2021-10-21 | 2021-10-21 | 3 | 2021-10-21 | 3 | 2021-11-24 | 23 | [15 empty] | 2021-11-24 | 2021-11-29 | 1 | 2021-11-29 | [6 empty] | 2021-10-18 | 2021-10-21 | 2021-10-18 | 2021-11-02 | 11
122222172 | 2143 | PGE | 94080 | Non-NEM | Inadvertent Export | Withdrawn | Solar PV | 215.378 |  | 2021-10-18 | 2021-10-18 |  | 2021-10-18 | 2021-10-18 | 0
122222503 | 2144 | PGE | 95991 | NEM | EXPNEM | IA in Progress | Solar PV | 133.2 |  | 2021-10-18 |  | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2 | 2021-11-04 | 13 | 2021-11-16 | 7 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16
122222534 | 2145 | PGE | 96007 | NEM | EXPNEM | Commercial | Solar PV | 32.436 |  | 2021-10-18 |  | 2021-10-21 | 2021-10-21 | 2021-10-21 | 3 | 2021-10-29 | 9 | 2021-11-12 | 9 | [15 empty] | 2021-11-12 | 2021-11-12 | 0 | 2021-11-12 | 2021-11-12 | 0 | [13 empty] | 2021-12-02 | 2021-12-06 | 2 | [15 empty] | 2021-12-02 | 2021-12-02 | 0 | 2021-12-06 |  | 2021-12-06 | 0
122223346 | 2146 | PGE | 94590 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 37.598 |  | 2021-10-18 |  | 2021-10-19 | 2021-10-19 | 2021-10-19 | 1 | 2021-12-31 | 51 | [27 empty] | 2021-10-18 | 2021-12-01 | 2021-10-18 | 2021-12-14 | 38
122224171 | 2147 | PGE | 94112 | NEM | EXPNEM | Study in Progress | Solar PV | 66.6 |  | 2021-10-18 |  | 2021-11-03 | 2021-10-27 | 2021-10-27 | 7 | 2021-12-23 | 45
122224190 | 2148 | PGE | 94587 | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2021-10-18 |  |  | 2021-10-19 | 2021-10-19 | 1 | 2021-10-19 | 1 | 2021-10-22 | 3 | [15 empty] | 2021-10-22 | 2021-10-27 | 3 | 2021-10-27 | 2021-10-29 | 2
122225538 | 2149 | PGE | 94061 | NEM | EXPNEM | Study in Progress | Solar PV | 33.3 |  | 2021-10-19 |  | 2021-11-02 | 2021-11-02 | 2021-11-02 | 10 | 2021-11-02 | 10 | 2021-11-19 | 12 | 2021-11-19 | 2021-12-20 | 19 | 2021-12-20 | [22 empty] | 2021-12-15 | 2021-12-15
122225609 | 2150 | PGE | 95205 | NEM | EXPNEM | Application Review in Progress | Solar PV | 133.2 |  | 2021-10-19 |  | 2021-11-02 | 2021-11-02 | 2021-11-02 | 10 | [29 empty] | 2021-10-19 |  | 2021-10-19
122225668 | 2151 | PGE | 95205 | NEM | EXPNEM | Application Review in Progress | Solar PV | 133.2 |  | 2021-10-19 |  | 2021-11-02 | 2021-11-02 | 2021-11-02 | 10 | [29 empty] | 2021-10-19 |  | 2021-10-19
122225940 | 2152 | PGE | 94536 | NEM | EXPNEM | Implementation | Solar PV | 106.314 |  | 2021-10-19 |  | 2021-10-22 | 2021-10-22 | 2021-10-22 | 3 | 2021-10-29 | 8 | 2021-12-15 | 30 | [15 empty] | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 2021-12-29 | 10
122227408 | 2153 | PGE | 95987 | NEM | EXPNEM | Application Accepted | Solar PV | 1486.251 |  | 2021-10-19 | 2021-10-25 |  | 2021-10-25 | 2021-10-25 | 4 | 2021-11-03 | 11 | [27 empty] | 2021-10-19 | 2021-12-20 | 2021-10-19
122227703 | 2154 | PGE | 94062 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 46.105 |  | 2021-10-19 |  | 2021-11-11 | 2021-10-21 | 2021-10-21 | 2
122227723 | 2155 | PGE | 95301 | Non-NEM | RESBCT | Study in Progress | Solar PV | 782.366 |  | 2021-10-19 | 2021-10-20 |  | 2021-10-19 | 2021-10-19 | 0 | 2021-11-17 | 20 | 2021-12-16 | 19
122229013 | 2156 | PGE | 93635 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 75.974 |  | 2021-10-19 |  | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2 | 2021-11-05 | 13 | 2021-11-29 | 13 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | [6 empty] | 2021-10-19 | 2021-11-16 | 2021-10-19 | 2021-12-03 | 30 |  | 2021-12-03 | 2021-12-03 | 0
122229016 | 2157 | PGE | 93635 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 75.974 |  | 2021-10-19 |  | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2 | 2021-11-05 | 13 | 2021-11-30 | 14 | [15 empty] | 2021-11-30 | 2021-11-30 | 0 | 2021-11-30 | [6 empty] | 2021-10-19 | 2021-12-03 | 2021-10-19 | 2021-12-15 | 38 |  | 2021-12-22 | 2021-12-22 | 0
122229255 | 2158 | PGE | 93245 | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-10-19 |  |  | 2021-10-21 | 2021-10-21 | 2 | 2021-10-21 | 2 | 2021-11-04 | 10 | [15 empty] | 2021-11-04 | 2021-11-29 | 14 | 2021-11-29 | [6 empty] | 2021-10-19 |  | 2021-10-19 |  |  | 2021-11-01
122230855 | 2159 | PGE | 93405 | Non-NEM | Inadvertent Export | Withdrawn | Storage | 10 |  | 2021-10-20 | [5 empty] | 2021-12-16 | 38 | 2021-12-27 | 7 | [15 empty] | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27 | 2021-12-27 | 0
122231419 | 2160 | PGE | 94597 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 40.163 |  | 2021-10-20 |  | 2021-11-22 | 2021-10-21 | 2021-10-21 | 1 | 2021-11-30 | 26 | 2021-12-02 | 2 | [34 empty] | 2021-12-02 | 2021-12-02 | 0 | [15 empty] | 2021-12-02 |  |  | 2021-12-02 |  | 2021-12-02 | 0
122232342 | 2161 | PGE | 94062 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 40 |  | 2021-10-20 |  | 2021-11-09 | 2021-10-26 | 2021-10-26 | 4
122232465 | 2162 | PGE | 95134 | Non-NEM | NEMFC | IA in Progress | FUCE | 200 |  | 2021-10-20 |  | 2021-11-02 | 2021-11-02 | 2021-11-02 | 9 | 2021-11-16 | 18 | 2021-12-09 | 15 | [15 empty] | 2021-12-09 | 2021-12-09 | 0 | 2021-12-09 | [7 empty] | 2021-11-16 | 2021-11-16 | 2021-11-16 | 0 |  | 2021-12-14 | 2021-12-14 | 0
122232722 | 2163 | PGE | 94404 | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2021-10-20 |  | 2021-10-27 | 2021-10-27 | 2021-10-27 | 5 | 2021-12-09 | 33
122233070 | 2164 | PGE | 94538 | NEM | VNEM | IA in Progress | Solar PV | 33.075 |  | 2021-10-20 |  |  | 2021-11-03 | 2021-11-03 | 10 | 2021-11-15 | 17 | 2021-12-08 | 15 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | [6 empty] | 2021-10-20 |  | 2021-10-20
122233915 | 2165 | PGE | 93648 | NEM | EXPNEM | Application Review in Progress | Solar PV | 173.477 |  | 2021-10-20 |  | 2021-10-21 | 2021-10-21 | 2021-10-21 | 1 | [29 empty] | 2021-10-20 |  | 2021-10-20
122235324 | 2166 | PGE | 94538 | NEM | VNEM | IA in Progress | Solar PV | 30.24 |  | 2021-10-20 |  | 2021-10-25 | 2021-10-25 | 2021-10-25 | 3 | 2021-10-27 | 5 | 2021-11-16 | 13 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | [6 empty] | 2021-10-20 | 2021-12-09 | 2021-10-20 | 2021-12-16 | 38 |  | 2021-12-20 | 2021-12-20 | 0
122235584 | 2167 | PGE | 95935 | NEM | EXPNEM | Commercial | Solar PV | 33.909 |  | 2021-10-20 |  | 2021-11-02 | 2021-11-02 | 2021-11-02 | 9 | 2021-11-08 | 13 | 2021-11-16 | 5 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-18 | 2 | [13 empty] | 2021-11-24 | 2021-12-01 | 3 | [15 empty] | 2021-11-24 | 2021-11-29 | 1 | 2021-12-01 |  | 2021-12-02 | 1
122239546 | 2168 | PGE | 93420 | NEM | EXPNEM | IA in Progress | Solar PV | 56.041 |  | 2021-10-21 |  | 2021-10-22 | 2021-10-22 | 2021-10-22 | 1 | 2021-10-25 | 2 | 2021-11-23 | 20 | [15 empty] | 2021-11-23 | 2021-11-23 | 0 | 2021-11-23 | [18 empty] | 2021-12-21 |  | 17
122240157 | 2169 | PGE | 93263 | NEM | EXPNEM | IA in Progress | Solar PV | 550 |  | 2021-10-21 |  |  | 2021-10-28 | 2021-10-28 | 5 | 2021-10-28 | 5 | 2021-11-29 | 19 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29
122240289 | 2170 | PGE | 93720 | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-10-21 |  |  | 2021-10-22 | 2021-10-22 | 1 | 2021-10-22 | 1 | 2021-10-28 | 4 | [15 empty] | 2021-10-28 | 2021-11-17 | 13 | 2021-11-17 | [6 empty] | 2021-10-21 |  | 2021-10-21 |  |  | 2021-11-01
122240356 | 2171 | PGE | 93446 | NEM | EXPNEM | Application Review in Progress | Solar PV | 533.3 |  | 2021-10-21 |  | 2021-10-22 | 2021-10-22 | 2021-10-22 | 1
122240372 | 2172 | PGE | 93212 | NEM | EXPNEM | Study in Progress | Solar PV | 2000 |  | 2021-10-21 | 2021-10-22 |  | 2021-10-22 | 2021-10-22 | 1 | 2021-11-03 | 9
122240568 | 2173 | PGE | 93727 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1488 |  | 2021-10-21 | 2021-10-27 |  | 2021-10-27 | 2021-10-27 | 4 | 2021-12-15 | 36
122241073 | 2174 | PGE | 95236 | NEM | EXPNEM | Study in Progress | Solar PV | 38.995 |  | 2021-10-21 |  | 2021-11-04 | 2021-10-29 | 2021-10-29 | 6 | 2021-11-23 | 22 | 2021-12-10 | 11 | 2021-12-10 | [24 empty] | 2021-10-21 | 2021-11-23 | 2021-10-21 | 2021-12-15 | 36
122241310 | 2175 | PGE | 93638 | NEM | EXPNEM | Application Review in Progress | Solar PV | 39.976 |  | 2021-10-21 |  | 2021-11-04 | 2021-11-04 | 2021-11-04 | 10 | [29 empty] | 2021-10-21 | 2021-11-04 | 2021-10-21 | 2021-12-03 | 28 | 2021-11-19
122243997 | 2176 | PGE | 94549 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-10-28 |  |  | 2021-10-28 | 2021-10-28 | 0 | 2021-10-28 | 0 | 2021-11-18 | 14 | [15 empty] | 2021-10-21 | 2021-10-21 |  | 2021-10-21 | 2021-10-22 | 2 | [34 empty] | 2021-10-28 |  | 2021-11-18 | 16
122245084 | 2177 | PGE | 95472 | NEM | EXPNEM | Study in Progress | Solar PV | 62.541 |  | 2021-10-22 |  |  | 2021-11-02 | 2021-11-02 | 7 | 2021-11-05 | 10 | 2021-11-29 | 13 | 2021-11-29 | 2021-12-27 | 20 | 2021-12-27 | [21 empty] | 2021-10-22 |  | 2021-10-22
122245209 | 2178 | PGE | 95969 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 490 |  | 2021-10-22 | 2021-10-26 |  | 2021-10-22 | 2021-10-22 | 0 | 2021-11-10 | 13 | 2021-12-20 | 25 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | [6 empty] | 2021-10-22 | 2021-11-22 | 2021-10-22 | 2021-12-07 | 29
122245421 | 2179 | PGE | 95320 | NEM | EXPNEM | Implementation | Solar PV | 360 |  | 2021-10-22 |  |  | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | 0 | 2021-11-30 | 24 | [15 empty] | 2021-11-30 | 2021-11-30 | 0 | 2021-11-30 | 2021-12-14 | 10 |  |  |  |  | 2021-10-22 | 2021-10-25 | 2021-10-22 | 2021-11-03 | 8
122245498 | 2180 | PGE | 95954 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 490 |  | 2021-10-22 | 2021-10-26 |  | 2021-10-22 | 2021-10-22 | 0 | 2021-11-10 | 13 | 2021-12-20 | 25 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | [6 empty] | 2021-10-22 | 2021-11-22 | 2021-10-22 | 2021-12-07 | 29
122245758 | 2181 | PGE | 95472 | NEM | EXPNEM | Study in Progress | Solar PV | 93.654 |  | 2021-10-22 |  | 2021-11-05 | 2021-11-05 | 2021-11-05 | 10 | 2021-11-30 | 24 | 2021-12-21 | 15 | 2021-12-21
122246869 | 2182 | PGE | 95304 | NEM | EXPNEM | Study in Progress | Solar PV | 720 |  | 2021-10-22 |  | 2021-11-03 | 2021-11-01 | 2021-11-01 | 6 | 2021-11-05 | 10 | 2021-12-01 | 15 | 2021-12-01
122247185 | 2183 | PGE | 94561 | NEM | EXPNEM | Implementation | Solar PV | 31.966 |  | 2021-10-22 |  |  | 2021-10-28 | 2021-10-28 | 4 | 2021-10-28 | 4 | 2021-11-15 | 11 | [15 empty] | 2021-11-12 | 2021-11-12 | 0 | 2021-11-12 | 2021-11-15 | 1
122247778 | 2184 | PGE | 95403 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.6 |  | 2021-10-22 |  | 2021-11-16 | 2021-10-28 | 2021-10-28 | 4
122250900 | 2185 | PGE | 94550 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 38.394 |  | 2021-10-24 |  | 2021-10-25 | 2021-10-25 | 2021-10-25 | 0
122251596 | 2186 | PGE | 95605 | NEM | EXPNEM | Application Review in Progress | Solar PV | 200 |  | 2021-10-24 |  | 2021-11-29 | 2021-11-01 | 2021-11-01 | 5
122252447 | 2187 | PGE | 94941 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-10-25 | 2021-11-30 |  | 2021-11-30 | 2021-11-30 | 23 | 2021-12-02 | 25 | 2021-12-16 | 10 | [15 empty] | 2021-10-25 | 2021-10-25 |  | 2021-10-25 | 2021-10-25 | 1 | [13 empty] | 2021-12-16 | 2021-12-17 | 1 | [15 empty] | 2021-12-16 | 2021-12-17 | 1 | 2021-12-17 |  | 2021-12-20 | 1
122255096 | 2188 | PGE | 95032 | NEM | EXPNEM | Commercial | Solar PV | 31.074 |  | 2021-10-25 |  | 2021-11-03 | 2021-11-03 | 2021-11-03 | 7 | 2021-11-12 | 13 | 2021-11-30 | 10 | [15 empty] | 2021-11-30 | 2021-11-30 | 0 | 2021-11-30 | 2021-12-01 | 1 | [13 empty] | 2021-12-01 | 2021-12-23 | 16 | [15 empty] | 2021-12-01 | 2021-12-03 | 2 | 2021-12-23 |  | 2021-12-24 | 1
122255392 | 2189 | PGE | 96080 | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-10-25 |  | 2021-12-01 | 2021-11-15 | 2021-11-15 | 14 | 2021-12-07 | 28 | 2021-12-28 | 15 | [15 empty] | 2021-12-28 | 2021-12-29 | 1 | 2021-12-29 | [6 empty] | 2021-10-25 | 2021-12-07 | 2021-10-25 | 2021-12-16 | 35
122256053 | 2190 | PGE | 95691 | NEM | VNEM | IA in Progress | Solar PV | 100.395 |  | 2021-10-25 |  | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2 | 2021-11-01 | 5 | 2021-11-19 | 13 | [15 empty] | 2021-11-19 | 2021-11-19 | 0 | 2021-11-19 | [7 empty] | 2021-11-16 | 2021-11-16 | 2021-11-29 | 7 |  | 2021-11-19 | 2021-11-19 | 0
122256451 | 2191 | PGE | 94568 | NEM | EXPNEM | IA in Progress | Solar PV | 99.9 |  | 2021-10-25 |  |  | 2021-10-27 | 2021-10-27 | 2 | 2021-10-27 | 2 | 2021-12-13 | 30 | [15 empty] | 2021-12-13 | 2021-12-24 | 9 | 2021-12-24 | 2021-12-24 | 0 |  |  |  |  | 2021-10-25 |  | 2021-10-25 |  |  | 2021-11-01
122257071 | 2192 | PGE | 95619 | Non-NEM | Break Before Make | Commercial | ENGN | 200 |  | 2021-10-26 | 2021-11-09 |  | 2021-11-09 | 2021-11-09 | 10 | 2021-12-21 | 37
122257365 | 2193 | PGE | 96003 | NEM | EXPNEM | Commercial | Solar PV | 33.174 |  | 2021-10-26 |  |  | 2021-11-03 | 2021-11-03 | 6 | 2021-11-03 | 6 | 2021-11-19 | 11 | [15 empty] | 2021-11-19 | 2021-11-29 | 4 | 2021-11-29 | 2021-11-30 | 1 |  |  |  |  | 2021-10-26 | 2021-11-03 | 2021-10-26 | 2021-11-29 | 21 |  |  |  |  | 2021-11-30 | 2021-12-07 | 5 | [15 empty] | 2021-11-30 | 2021-12-01 | 1 | 2021-12-07 |  | 2021-12-08 | 1
122257373 | 2194 | PGE | 93635 | NEM | EXPNEM | IA in Progress | Solar PV | 86 |  | 2021-10-26 |  |  | 2021-11-02 | 2021-11-02 | 5 | 2021-11-02 | 5 | 2021-11-19 | 12 | [15 empty] | 2021-11-19 | 2021-12-14 | 15 | 2021-12-14 | [6 empty] | 2021-10-26 |  | 2021-10-26 |  |  | 2021-12-08
122257456 | 2195 | PGE | 95138 | NEM | EXPNEM | IA in Progress | Solar PV | 516.525 |  | 2021-10-26 |  |  | 2021-10-27 | 2021-10-27 | 1 | 2021-10-27 | 1 | 2021-11-22 | 17 | [15 empty] | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22
122257674 | 2196 | PGE | 95138 | NEM | EXPNEM | Study in Progress | Solar PV | 139.03 |  | 2021-10-26 |  |  | 2021-11-03 | 2021-11-03 | 6 | 2021-11-03 | 6
122257741 | 2197 | PGE | 95667 | Non-NEM | Break Before Make | Commercial | ENGN | 150 |  | 2021-10-26 |  |  | 2021-11-09 | 2021-11-09 | 10
122257746 | 2198 | PGE | 95138 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-10-26 |  | 2021-11-01 | 2021-11-01 | 2021-11-01 | 4 | 2021-11-04 | 7 | 2021-11-19 | 10 | 2021-11-19 | 2021-12-24 | 23 | [12 empty] | 2021-12-24 | 2021-12-28 | 2 | 2021-12-28
122258151 | 2199 | PGE | 94538 | NEM | EXPNEM | Application Review in Progress | Solar PV | 162.5 |  | 2021-10-26 |  | 2021-11-03 | 2021-11-03 | 2021-11-03 | 6 | [29 empty] | 2021-10-26 |  | 2021-10-26
122258242 | 2200 | PGE | 94538 | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-10-26 |  |  | 2021-11-04 | 2021-11-04 | 7 | 2021-11-04 | 7 | 2021-12-31 | 38 | [15 empty] | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | [6 empty] | 2021-10-26 | 2021-11-23 | 2021-10-26 | 2021-12-09 | 29
122258379 | 2201 | PGE | 94066 | NEM | EXPNEM | IA in Progress | Solar PV | 81.005 |  | 2021-10-26 |  | 2021-11-03 | 2021-11-03 | 2021-11-03 | 6 | 2021-12-02 | 24 | 2021-12-16 | 10 | [15 empty] | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16 | [6 empty] | 2021-10-26 | 2021-11-03 | 2021-10-26 | 2021-11-30 | 22
122258716 | 2202 | PGE | 93263 | NEM | EXPNEM | IA in Progress | Solar PV | 95.8 |  | 2021-10-26 |  |  | 2021-11-03 | 2021-11-03 | 6 | 2021-11-03 | 6 | 2021-11-19 | 11 | [15 empty] | 2021-11-19 | 2021-11-24 | 3 | 2021-11-24 | [6 empty] | 2021-10-26 | 2021-11-03 | 2021-10-26 | 2021-11-29 | 21
122259295 | 2203 | PGE | 95304 | NEM | EXPNEM | Implementation | Solar PV | 96.096 |  | 2021-10-26 |  |  | 2021-11-05 | 2021-11-05 | 8 | 2021-11-05 | 8 | 2021-11-22 | 10 | [15 empty] | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22 | 2021-11-29 | 3 |  |  |  |  | 2021-10-26 | 2021-11-05 | 2021-10-26 | 2021-11-29 | 21
122259400 | 2204 | PGE | 95304 | NEM | EXPNEM | Implementation | Solar PV | 62.5 |  | 2021-10-26 |  |  | 2021-11-05 | 2021-11-05 | 8 | 2021-11-05 | 8 | 2021-11-22 | 10 | [15 empty] | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22 | 2021-11-29 | 3 |  |  |  |  | 2021-10-26 | 2021-11-05 | 2021-10-26 | 2021-11-29 | 21
122259924 | 2205 | PGE | 95436 | NEM | EXPNEM | Study in Progress | Solar PV | 49.549 |  | 2021-10-26 |  | 2021-11-03 | 2021-11-03 | 2021-11-03 | 6 | 2021-11-29 | 21 | 2021-12-15 | 12 | 2021-12-15 | [24 empty] | 2021-10-26 | 2021-11-29 | 2021-10-26 | 2021-12-15 | 33
122259995 | 2206 | PGE | 95451 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 41.387 |  | 2021-10-26 |  |  | 2021-10-29 | 2021-10-29 | 3 | 2021-10-29 | 3 | 2021-11-03 | 3 | [37 empty] | 2021-12-29 |  | 12
122260210 | 2207 | PGE | 93727 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 3146.5 |  | 2021-10-26 | 2021-10-27 |  | 2021-10-27 | 2021-10-27 | 1 | 2021-12-15 | 33
122260218 | 2208 | PGE | 95472 | NEM | EXPNEM | Study in Progress | Solar PV | 161.008 |  | 2021-10-26 |  | 2021-11-03 | 2021-11-03 | 2021-11-03 | 6 | 2021-11-04 | 7 | [27 empty] | 2021-10-26 | 2021-12-01 | 2021-10-26 | 2021-12-01 | 23
122260279 | 2209 | PGE | 93640 | NEM | EXPNEM | Application Accepted | Solar PV | 907.612 |  | 2021-10-26 |  | 2021-12-31 | 2021-11-05 | 2021-11-05 | 8 | 2021-12-27 | 41 | [27 empty] | 2021-10-26 |  | 2021-10-26
122261060 | 2210 | PGE | 94062 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 33.012 |  | 2021-10-26 |  | 2021-11-05 | 2021-11-05 | 2021-11-05 | 8 | 2021-11-12 | 12 | [17 empty] | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05 | 2021-11-12 | 4 |  |  |  |  | 2021-10-26 | 2021-11-12 | 2021-10-26 | 2021-11-29 | 21
122261978 | 2211 | PGE | 94706 | NEM | EXPNEM | IA in Progress | Solar PV | 100.425 |  | 2021-10-27 |  | 2021-11-08 | 2021-11-08 | 2021-11-08 | 8 | 2021-11-12 | 11 | 2021-11-17 | 3 | [15 empty] | 2021-11-17 | 2021-11-17 | 0 | 2021-11-17 | [6 empty] | 2021-10-27 | 2021-11-12 | 2021-10-27 | 2021-12-06 | 25
122262063 | 2212 | PGE | 94526 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.375 |  | 2021-10-27 |  |  | 2021-10-29 | 2021-10-29 | 2 | 2021-10-29 | 2 | 2021-11-02 | 2 | [34 empty] | 2021-11-23 | 2021-11-23 | 0 | [15 empty] | 2021-11-23 |  |  | 2021-11-23 |  | 2021-11-23 | 0
122262199 | 2213 | PGE | 94566 | NEM | EXPNEM | Withdrawn | Solar PV | 495.7 |  | 2021-10-27 |  | 2021-11-05 | 2021-11-05 | 2021-11-05 | 7
122262245 | 2214 | PGE | 95912 | NEM | EXPNEM | Study in Progress | Solar PV | 60.708 |  | 2021-10-27 |  | 2021-12-07 | 2021-10-29 | 2021-10-29 | 2 | 2021-12-17 | 34 | [28 empty] | 2021-12-17 | 2021-12-17
122262346 | 2215 | PGE | 94560 | NEM | EXPNEM | IA in Progress | Solar PV | 987.5 |  | 2021-10-27 | 2021-10-29 |  | 2021-10-29 | 2021-10-29 | 2 | 2021-11-10 | 10 | 2021-12-20 | 25 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | [6 empty] | 2021-10-27 | 2021-11-15 | 2021-10-27 | 2021-12-02 | 23
122263240 | 2216 | PGE | 93638 | NEM | VNEM | Study in Progress | Solar PV | 61.78 |  | 2021-10-27 |  | 2021-11-15 | 2021-11-10 | 2021-11-10 | 10 | [29 empty] | 2021-10-27 |  | 2021-10-27
122263421 | 2217 | PGE | 94043 | NEM | EXPNEM | IA in Progress | Solar PV | 226.969 |  | 2021-10-27 |  |  | 2021-11-02 | 2021-11-02 | 4 | 2021-11-02 | 4 | 2021-11-19 | 12 | [15 empty] | 2021-11-19 | 2021-11-30 | 5 | 2021-11-30 | [6 empty] | 2021-10-27 |  | 2021-10-27 |  |  | 2021-12-14
122263611 | 2218 | PGE | 93242 | NEM | EXPNEM | Implementation | Solar PV | 95.947 |  | 2021-10-27 |  | 2021-11-03 | 2021-11-03 | 2021-11-03 | 5 | 2021-12-13 | 30 | 2021-12-27 | 10 | [15 empty] | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27 | 2021-12-27 | 0 |  |  |  |  | 2021-10-27 | 2021-12-27 | 2021-10-27
122265254 | 2219 | PGE | 95037 | NEM | EXPNEM | IA in Progress | Solar PV | 266.6 |  | 2021-10-27 |  | 2021-11-04 | 2021-10-29 | 2021-10-29 | 2 | 2021-11-08 | 8 | 2021-12-22 | 29 | [15 empty] | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22 | [7 empty] | 2021-11-08 | 2021-11-08 | 2021-11-30 | 13
122265562 | 2220 | PGE | 95361 | NEM | EXPNEM | IA in Progress | Solar PV | 96.475 |  | 2021-10-27 |  |  | 2021-10-29 | 2021-10-29 | 2 | 2021-10-29 | 2 | 2021-11-18 | 13 | [15 empty] | 2021-12-07 | 2021-12-24 | 13 | 2021-12-24 | [6 empty] | 2021-10-27 |  | 2021-10-27 |  |  | 2021-12-14
122265751 | 2221 | PGE | 94801 | NEM | EXPNEM | Application Review in Progress | Solar PV | 800 |  | 2021-10-27 |  | 2021-11-18 | 2021-11-04 | 2021-11-04 | 6 | [29 empty] | 2021-10-27 |  | 2021-10-27
122265758 | 2222 | PGE | 95206 | NEM | EXPNEM | Implementation | Solar PV | 46.265 |  | 2021-10-27 |  |  | 2021-10-29 | 2021-10-29 | 2 | 2021-10-29 | 2 | 2021-11-12 | 9 | [15 empty] | 2021-11-12 | 2021-11-15 | 1 | 2021-11-15 | 2021-12-30 | 31 |  |  |  |  | 2021-10-27 |  | 2021-10-27 |  |  | 2021-12-14
122266609 | 2223 | PGE | 93955 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 168.78 |  | 2021-10-28 |  | 2021-10-29 | 2021-10-29 | 2021-10-29 | 1 | 2021-11-17 | 13 | [33 empty] | 2021-11-17 | 2021-11-17 | 0
122267338 | 2224 | PGE | 94080 | NEM | EXPNEM | IA in Progress | Solar PV | 120.364 |  | 2021-10-28 |  | 2021-11-12 | 2021-11-12 | 2021-11-12 | 10 | 2021-12-07 | 25 | 2021-12-17 | 8 | [15 empty] | 2021-12-17 | 2021-12-17 | 0 | 2021-12-17
122268182 | 2225 | PGE | 95448 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.5 |  | 2021-10-28 |  | 2021-11-03 | 2021-11-03 | 2021-11-03 | 4 | 2021-11-17 | 13 | 2021-11-17 | 0 | [34 empty] | 2021-11-17 | 2021-11-17 | 0 | [15 empty] | 2021-11-17 |  |  | 2021-11-17 |  | 2021-11-17 | 0
122268996 | 2226 | PGE | 93432 | NEM | EXPNEM | IA in Progress | Solar PV | 30.763 |  | 2021-10-28 |  | 2021-11-12 | 2021-11-12 | 2021-11-12 | 10 | 2021-11-12 | 10 | 2021-12-02 | 12 | [15 empty] | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02
122269543 | 2227 | PGE | 93301 | NEM | EXPNEM | Study in Progress | Solar PV | 34.8 |  | 2021-10-28 |  | 2021-12-08 | 2021-11-01 | 2021-11-01 | 2 | 2021-12-13 | 29
122269689 | 2228 | PGE | 93239 | Non-NEM | Inadvertent Export | Withdrawn | Solar PV | 33 |  | 2021-10-28 | 2021-11-03 |  | 2021-10-29 | 2021-10-29 | 1
122271054 | 2229 | PGE | 94027 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 36.168 |  | 2021-10-28 |  | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2 | 2021-11-04 | 5 | 2021-11-05 | 1
122271445 | 2230 | PGE | 95521 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 15 |  | 2021-10-28 | 2021-11-12 |  | 2021-11-12 | 2021-11-12 | 10 | 2021-11-19 | 15 | 2021-11-29 | 4 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29
122273152 | 2231 | PGE | 93908 | NEM | EXPNEM | IA in Progress | Solar PV | 410.518 |  | 2021-10-29 |  | 2021-11-05 | 2021-11-05 | 2021-11-05 | 5 | 2021-11-09 | 7 | 2021-12-30 | 34 | [15 empty] | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | [6 empty] | 2021-10-29 |  | 2021-10-29
122273446 | 2232 | PGE | 95205 | NEM | EXPNEM | Study in Progress | Solar PV | 780 |  | 2021-10-29 |  |  | 2021-11-02 | 2021-11-02 | 2 | 2021-11-02 | 2 | 2021-11-18 | 11 | [25 empty] | 2021-10-29 |  | 2021-10-29 |  |  | 2021-12-01
122274220 | 2233 | PGE | 95627 | NEM | EXPNEM | Study in Progress | Solar PV | 180 |  | 2021-10-29 |  | 2021-11-15 | 2021-11-15 | 2021-11-15 | 10 | 2021-12-07 | 24 | 2021-12-28 | 15 | 2021-12-28 | [24 empty] | 2021-10-29 |  | 2021-10-29
122274775 | 2234 | PGE | 94801 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100 |  | 2021-10-29 |  | 2021-11-04 | 2021-11-04 | 2021-11-04 | 4 | 2021-11-29 | 18 | 2021-12-16 | 13 | [15 empty] | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16
122275248 | 2235 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100.91 |  | 2021-10-29 |  | 2021-11-15 | 2021-11-15 | 2021-11-15 | 10 | 2021-11-29 | 18 | 2021-12-20 | 15 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | [6 empty] | 2021-10-29 | 2021-12-01 | 2021-10-29 | 2021-12-15 | 30 |  | 2021-12-20 | 2021-12-20 | 0
122275509 | 2236 | PGE | 95337 | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-10-29 |  |  | 2021-11-01 | 2021-11-01 | 1 | 2021-11-01 | 1 | 2021-12-23 | 35 | [15 empty] | 2021-12-23
122275611 | 2237 | PGE | 95361 | NEM | NEMMT | Application Review in Progress | ENGN, Solar PV | 875 |  | 2021-10-29 |  | 2021-11-15 | 2021-11-15 | 2021-11-15 | 10
122275616 | 2238 | PGE | 95337 | NEM | EXPNEM | Application Review in Progress | Solar PV | 698.573 |  | 2021-10-29 |  | 2021-11-15 | 2021-11-15 | 2021-11-15 | 10
122276275 | 2239 | PGE | 93662 | NEM | EXPNEM | IA in Progress | Solar PV | 354.723 |  | 2021-10-29 |  | 2021-11-10 | 2021-11-10 | 2021-11-10 | 8 | 2021-11-29 | 18 | 2021-12-27 | 20 | [15 empty] | 2021-12-27 | 2021-12-28 | 1 | 2021-12-28 | [6 empty] | 2021-10-29 | 2021-11-10 | 2021-10-29 | 2021-11-29 | 18
122277430 | 2240 | PGE | 94062 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 48.625 |  | 2021-10-29 |  | 2021-11-08 | 2021-11-03 | 2021-11-03 | 3 | 2021-12-13 | 28 | 2021-12-15 | 2 | [34 empty] | 2021-12-15 | 2021-12-15 | 0 | [15 empty] | 2021-12-15 |  |  | 2021-12-15 |  | 2021-12-15 | 0
122280139 | 2241 | PGE | 94030 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.423 |  | 2021-11-01 |  | 2021-11-05 | 2021-11-05 | 2021-11-05 | 4
122280784 | 2242 | PGE | 95321 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 34.3 |  | 2021-11-01 |  |  | 2021-11-03 | 2021-11-03 | 2 | 2021-11-03 | 2 | 2021-11-08 | 3
122280876 | 2243 | PGE | 95422 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 357.5 |  | 2021-11-08 |  | 2021-11-22 | 2021-11-22 | 2021-11-22 | 9 | 2021-12-24 | 31 | [17 empty] | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22
122280945 | 2244 | PGE | 93923 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-11-01 |  |  | 2021-11-04 | 2021-11-04 | 3 | 2021-11-04 | 3 | [17 empty] | 2021-11-04 | 2021-11-04 | 0 | 2021-11-04
122280987 | 2245 | PGE | 93230 | NEM | EXPNEM | IA in Progress | Solar PV | 299.834 |  | 2021-11-01 |  |  | 2021-11-12 | 2021-11-12 | 8 | 2021-11-16 | 10 | 2021-12-02 | 10 | [15 empty] | 2021-12-02 | 2021-12-06 | 2 | 2021-12-06 | [6 empty] | 2021-11-01 |  | 2021-11-01
122283864 | 2246 | PGE | 94538 | NEM | NEMMT | Application Review in Progress | ENGN, Solar PV | 601.568 |  | 2021-11-01 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 10
122284822 | 2247 | PGE | 93204 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 730 |  | 2021-11-01 |  | 2021-12-14 | 2021-11-02 | 2021-11-02 | 1
122284827 | 2248 | PGE | 93711 | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 |  | 2021-11-01 |  | 2021-11-08 | 2021-11-08 | 2021-11-08 | 5
122286721 | 2249 | PGE | 93420 | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-11-02 | 2021-11-02 |  | 2021-11-02 | 2021-11-02 | 0 | 2021-11-03 | 1 | 2021-11-09 | 4 | [15 empty] | 2021-11-02 | 2021-11-02 |  | 2021-11-02 | 2021-11-02 | 1
122288350 | 2250 | PGE | 94520 | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 |  | 2021-11-02 |  | 2021-11-05 | 2021-11-05 | 2021-11-05 | 3
122288352 | 2251 | PGE | 94585 | NEM | EXPNEM | Study in Progress | Solar PV | 44.98 |  | 2021-11-02 |  | 2021-11-19 | 2021-11-08 | 2021-11-08 | 4 | 2021-12-24 | 35
122289045 | 2252 | PGE | 94611 | Non-NEM | Non-Export | Study in Progress | ENGN, Solar PV | 4.85 |  | 2021-11-02 |  |  | 2021-11-15 | 2021-11-15 | 8 | 2021-11-15 | 8
122289470 | 2253 | PGE | 93610 | NEM | EXPNEM | Study in Progress | Solar PV | 840 |  | 2021-11-02 |  |  | 2021-11-17 | 2021-11-17 | 10 | 2021-11-17 | 10 | 2021-12-29 | 28 | 2021-12-29 | [25 empty] | 2021-12-01 | 2021-12-01 | 2021-12-15 | 10
122289738 | 2254 | PGE | 95340 | NEM | EXPNEM | Study in Progress | Solar PV | 456 |  | 2021-11-02 |  |  | 2021-11-12 | 2021-11-12 | 7 | 2021-11-23 | 14 | 2021-12-08 | 9 | 2021-12-08
122289768 | 2255 | PGE | 93726 | NEM | EXPNEM | Application Review in Progress | Solar PV | 75 |  | 2021-11-02 |  | 2021-11-04 | 2021-11-04 | 2021-11-04 | 2 | [29 empty] | 2021-11-02 | 2021-11-19 | 2021-11-02 | 2021-12-15 | 28
122289959 | 2256 | PGE | 94621 | NEM | EXPNEM | IA in Progress | Solar PV | 86.881 |  | 2021-11-02 |  | 2021-11-03 | 2021-11-03 | 2021-11-03 | 1 | 2021-11-10 | 6 | 2021-11-16 | 3 | [15 empty] | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16
122290078 | 2257 | PGE | 94551 | NEM | EXPNEM | Application Review in Progress | Solar PV | 41.502 |  | 2021-11-02 |  | 2021-11-04 | 2021-11-04 | 2021-11-04 | 2
122290582 | 2258 | PGE | 93610 | NEM | EXPNEM | Study in Progress | Solar PV | 840 |  | 2021-11-02 |  | 2021-12-07 | 2021-11-15 | 2021-11-15 | 8 | 2021-12-13 | 26
122290881 | 2259 | PGE | 95682 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-10-15 |  |  | 2021-11-02 | 2021-11-02 | 12 | 2021-11-02 | 12 | 2021-11-08 | 4 | [15 empty] | 2021-10-15 | 2021-10-15 |  | 2021-10-15 | 2021-10-15 | 1 | [34 empty] | 2021-11-02 |  | 2021-12-13 | 30
122291305 | 2260 | PGE | 95901 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 260 |  | 2021-11-02 |  | 2021-11-17 | 2021-11-17 | 2021-11-17 | 10
122291660 | 2261 | PGE | 93420 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-02 | 2021-11-18 |  | 2021-11-18 | 2021-11-18 | 11 | 2021-11-23 | 14 | 2021-12-13 | 12 | [15 empty] | 2021-11-02 | 2021-11-02 |  | 2021-11-02 | 2021-11-02 | 1
122291720 | 2262 | PGE | 94539 | NEM | EXPNEM | IA in Progress | Solar PV | 205.581 |  | 2021-11-02 |  | 2021-11-09 | 2021-11-04 | 2021-11-04 | 2 | 2021-11-09 | 5 | 2021-11-24 | 10 | [15 empty] | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24
122291793 | 2263 | PGE | 93422 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-11-02 | 2021-11-17 |  | 2021-11-17 | 2021-11-17 | 10 | 2021-12-02 | 19 | 2021-12-21 | 13 | [15 empty] | 2021-11-02 | 2021-11-02 |  | 2021-11-02 | 2021-12-02 | 23
122291821 | 2264 | PGE | 95681 | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 |  | 2021-11-02 |  |  | 2021-11-04 | 2021-11-04 | 2 | 2021-11-04 | 2 | 2021-11-18 | 9 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29
122292070 | 2265 | PGE | 95338 | NEM | EXPNEM | Implementation | Solar PV | 49.771 |  | 2021-11-02 |  |  | 2021-11-04 | 2021-11-04 | 2 | 2021-11-04 | 2 | 2021-11-19 | 10 | [15 empty] | 2021-11-19 | 2021-11-30 | 5 | 2021-11-30 | 2021-12-06 | 4 |  |  |  |  | 2021-11-02 |  | 2021-11-02 |  |  | 2021-11-30
122292077 | 2266 | PGE | 93420 | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-11-02 | 2021-11-17 |  | 2021-11-17 | 2021-11-17 | 10 | 2021-12-02 | 19 | 2021-12-20 | 12 | [15 empty] | 2021-11-02 | 2021-11-02 |  | 2021-11-02 | 2021-11-02 | 1 | [13 empty] | 2021-12-20 | 2021-12-21 | 1 | [15 empty] | 2021-12-20 | 2021-12-21 | 1 | 2021-12-21 |  | 2021-12-23 | 2
122292177 | 2267 | PGE | 94565 | NEM | EXPNEM | IA in Progress | Solar PV | 52.163 |  | 2021-11-02 |  | 2021-11-04 | 2021-11-04 | 2021-11-04 | 2 | 2021-11-29 | 16 | 2021-12-28 | 21 | [15 empty] | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28
122292335 | 2268 | PGE | 95338 | NEM | EXPNEM | IA in Progress | Solar PV | 49.916 |  | 2021-11-02 |  |  | 2021-11-04 | 2021-11-04 | 2 | 2021-11-04 | 2 | 2021-12-02 | 17 | [15 empty] | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02 | [6 empty] | 2021-11-02 | 2021-12-14 | 2021-11-02 | 2021-12-14 | 27
122292513 | 2269 | PGE | 95110 | NEM | EXPNEM | IA in Progress | Solar PV | 33.983 |  | 2021-11-02 |  | 2021-11-04 | 2021-11-04 | 2021-11-04 | 2 | 2021-12-09 | 24 | 2021-12-28 | 13 | [15 empty] | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28
122292559 | 2270 | PGE | 95338 | NEM | EXPNEM | IA in Progress | Solar PV | 119.778 |  | 2021-11-02 |  |  | 2021-11-04 | 2021-11-04 | 2 | 2021-11-04 | 2 | 2021-12-21 | 30 | [15 empty] | 2021-12-21 | 2021-12-21 | 0 | 2021-12-21 | [6 empty] | 2021-11-02 | 2021-11-04 | 2021-11-02 | 2021-11-19 | 12
122307104 | 2271 | PGE | 95762 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.204 |  | 2021-11-03 |  | 2021-12-06 | 2021-11-05 | 2021-11-05 | 2 | 2021-12-15 | 27 | 2021-12-16 | 1 | [34 empty] | 2021-12-16 | 2021-12-16 | 0 | [15 empty] | 2021-12-16 |  |  | 2021-12-16 |  | 2021-12-16 | 0
122307132 | 2272 | PGE | 95018 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-05 |  |  | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05 | 0 | 2021-11-19 | 9 | [15 empty] | 2021-11-02 | 2021-11-02 |  | 2021-11-02 | 2021-11-03 | 2 | [34 empty] | 2021-11-05 |  | 2021-11-19 | 11
122307360 | 2273 | PGE | 93722 | NEM | EXPNEM | Study in Progress | Solar PV | 724.754 |  | 2021-11-03 |  | 2021-11-17 | 2021-11-17 | 2021-11-17 | 9 | 2021-12-28 | 36
122308262 | 2274 | PGE | 94544 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-03 | 2021-11-18 |  | 2021-11-18 | 2021-11-18 | 10 | 2021-11-19 | 11 | 2021-12-02 | 7 | [55 empty] | 2021-11-18 |  | 2021-12-02 | 11
122308325 | 2275 | PGE | 95912 | NEM | EXPNEM | IA in Progress | Solar PV | 250.103 |  | 2021-11-03 |  |  | 2021-11-18 | 2021-11-18 | 10 | 2021-11-18 | 10 | 2021-12-13 | 15 | [15 empty] | 2021-12-13 | 2021-12-29 | 12 | 2021-12-29 | [6 empty] | 2021-11-03 | 2021-11-18 | 2021-11-03 | 2021-12-15 | 27
122309088 | 2276 | PGE | 93420 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-11-03 |  |  | 2021-11-04 | 2021-11-04 | 1 | 2021-11-04 | 1 | 2021-11-10 | 4 | [15 empty] | 2021-11-03 | 2021-11-03 |  | 2021-11-03 | 2021-11-08 | 4
122309106 | 2277 | PGE | 95066 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-03 | 2021-11-18 |  | 2021-11-18 | 2021-11-18 | 10 | 2021-11-23 | 13 | 2021-12-16 | 15 | [55 empty] | 2021-11-23 |  | 2021-12-16 | 18
122309577 | 2278 | PGE | 93422 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-11-03 | 2021-11-04 |  | 2021-11-04 | 2021-11-04 | 1 | 2021-11-08 | 3 | 2021-11-10 | 2 | [15 empty] | 2021-11-03 | 2021-11-03 |  | 2021-11-03 | 2021-11-08 | 4
122309635 | 2279 | PGE | 94704 | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-11-03 |  | 2021-11-05 | 2021-11-05 | 2021-11-05 | 2 | 2021-12-07 | 21 | 2021-12-22 | 11 | [15 empty] | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22
122309993 | 2280 | PGE | 93636 | NEM | EXPNEM | Implementation | Solar PV | 30.33 |  | 2021-11-03 |  | 2021-11-08 | 2021-11-08 | 2021-11-08 | 3 | 2021-12-01 | 17 | 2021-12-10 | 7 | [15 empty] | 2021-12-10 | 2021-12-10 | 0 | 2021-12-10 | 2021-12-15 | 3 |  |  |  |  | 2021-11-04 | 2021-11-08 | 2021-11-04 | 2021-12-06 | 19
122310094 | 2281 | PGE | 93280 | NEM | EXPNEM | Implementation | Solar PV | 840 |  | 2021-11-03 |  |  | 2021-11-18 | 2021-11-18 | 10 | 2021-11-22 | 12 | 2021-12-02 | 6 | [15 empty] | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02 | 2021-12-03 | 1
122310438 | 2282 | PGE | 95912 | NEM | EXPNEM | Study in Progress | Solar PV | 250.103 |  | 2021-11-03 |  | 2021-11-10 | 2021-11-10 | 2021-11-10 | 5 | 2021-12-17 | 29 | [27 empty] | 2021-11-03 | 2021-12-17 | 2021-11-03
122310712 | 2283 | PGE | 95932 | NEM | EXPNEM | Study in Progress | Solar PV | 110.933 |  | 2021-11-03 |  | 2021-11-09 | 2021-11-05 | 2021-11-05 | 2 | 2021-12-27 | 35 | [27 empty] | 2021-11-03 | 2021-12-27 | 2021-11-03
122310837 | 2284 | PGE | 94577 | NEM | EXPNEM | IA in Progress | Solar PV | 37.913 |  | 2021-11-03 |  | 2021-11-08 | 2021-11-04 | 2021-11-04 | 1 | 2021-11-09 | 4 | 2021-11-29 | 11 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29
122312816 | 2285 | PGE | 94607 | NEM | EXPNEM | Implementation | Solar PV | 500 |  | 2021-11-03 |  | 2021-11-05 | 2021-11-05 | 2021-11-05 | 2 | 2021-11-09 | 4 | 2021-11-10 | 1 | [15 empty] | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | 2021-12-31 | 34 | [5 empty] | 2021-12-14 | 2021-12-14
122312879 | 2286 | PGE | 95361 | NEM | EXPNEM | Study in Progress | Solar PV | 160.303 |  | 2021-11-03 |  | 2021-11-15 | 2021-11-15 | 2021-11-15 | 7 | 2021-12-02 | 18 | 2021-12-30 | 20 | 2021-12-30
122313972 | 2287 | PGE | 94558 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 30.35 |  | 2021-11-04 |  | 2021-11-09 | 2021-11-09 | 2021-11-09 | 3 | 2021-12-21 | 30 | 2021-12-28 | 5
122314127 | 2288 | PGE | 94404 | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 |  | 2021-11-04 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 7 | 2021-11-29 | 14 | 2021-12-14 | 11 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | [6 empty] | 2021-11-04 | 2021-12-07 | 2021-11-04 | 2021-12-15 | 26 | 2021-12-15
122318512 | 2289 | PGE | 93647 | NEM | EXPNEM | Withdrawn | Solar PV | 44.95 |  | 2021-11-04 | [34 empty] | 2021-11-04 |  | 2021-11-04
122318741 | 2290 | PGE | 93612 | NEM | EXPNEM | IA in Progress | Solar PV | 244.589 |  | 2021-11-04 |  | 2021-11-05 | 2021-11-05 | 2021-11-05 | 1 | 2021-11-08 | 2 | 2021-11-15 | 4 | [15 empty] | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | [6 empty] | 2021-11-04 |  | 2021-11-04
122319511 | 2291 | PGE | 94066 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 3799.4 |  | 2021-11-04 | 2021-11-04 |  | 2021-11-04 | 2021-11-04 | 0 | 2021-12-29 | 36
122319580 | 2292 | PGE | 93313 | NEM | EXPNEM | IA in Progress | Solar PV | 701.428 |  | 2021-11-04 |  | 2021-11-09 | 2021-11-05 | 2021-11-05 | 1 | 2021-11-10 | 4 | 2021-11-29 | 10 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29
122319919 | 2293 | PGE | 93230 | NEM | EXPNEM | Study in Progress | Solar PV | 4125 |  | 2021-11-04 | 2021-11-04 |  | 2021-11-04 | 2021-11-04 | 0 | 2021-12-01 | 16 | [5 empty] | 2021-12-24 | [33 empty] | 2020-01-13 | 2020-05-08 | 82 |  |  |  | 2021-09-30 | 2021-11-23 | 37
122320434 | 2294 | PGE | 93940 | NEM | EXPNEM | IA in Progress | Solar PV | 55.33 |  | 2021-11-04 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 7 | 2021-11-19 | 10 | 2021-12-31 | 28 | [15 empty] | 2021-12-31
122321435 | 2295 | PGE | 93721 | NEM | VNEM | Application Review in Progress | Solar PV | 54.951 |  | 2021-11-04 |  | 2021-11-08 | 2021-11-08 | 2021-11-08 | 2
122321450 | 2296 | PGE | 95334 | NEM | EXPNEM | Application Review in Progress | Solar PV | 180.93 |  | 2021-11-04 |  | 2021-12-15 | 2021-11-16 | 2021-11-16 | 7
122321986 | 2297 | PGE | 95138 | NEM | EXPNEM | Implementation | Solar PV | 133.3 |  | 2021-11-04 |  |  | 2021-11-08 | 2021-11-08 | 2 | 2021-11-08 | 2 | 2021-11-24 | 11 | [15 empty] | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 2021-12-02 | 4 |  |  |  |  | 2021-11-04 | 2021-11-08 | 2021-11-04 | 2021-12-02 | 17
122322362 | 2298 | PGE | 95131 | NEM | EXPNEM | IA in Progress | Solar PV | 633.3 |  | 2021-11-04 |  | 2021-11-19 | 2021-11-19 | 2021-11-19 | 10 | 2021-11-19 | 10 | 2021-12-31 | 28 | [15 empty] | 2021-12-31 | [9 empty] | 2021-11-04 | 2021-11-19 | 2021-11-04 | 2021-12-15 | 26
122322535 | 2299 | PGE | 95409 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-11-04 | 2021-11-15 |  | 2021-11-15 | 2021-11-15 | 6 | 2021-11-23 | 12 | 2021-12-03 | 6
122322701 | 2300 | PGE | 95912 | NEM | EXPNEM | Study in Progress | Solar PV | 342.883 |  | 2021-11-04 |  | 2021-11-10 | 2021-11-09 | 2021-11-09 | 3 | 2021-12-27 | 34
122322709 | 2301 | PGE | 95932 | NEM | EXPNEM | Application Review in Progress | Solar PV | 121.018 |  | 2021-11-04 |  | 2021-11-09 | 2021-11-09 | 2021-11-09 | 3 | [29 empty] | 2021-11-04 |  | 2021-11-04
122322882 | 2302 | PGE | 95912 | NEM | EXPNEM | Application Review in Progress | Solar PV | 114.967 |  | 2021-11-04 |  | 2021-11-08 | 2021-11-08 | 2021-11-08 | 2
122323100 | 2303 | PGE | 95540 | NEM | EXPNEM | IA in Progress | Solar PV | 58.99 |  | 2021-11-04 |  |  | 2021-11-16 | 2021-11-16 | 7 | 2021-11-16 | 7 | 2021-12-09 | 15 | [15 empty] | 2021-12-09 | 2021-12-30 | 15 | 2021-12-30 | [6 empty] | 2021-11-04 | 2021-11-16 | 2021-11-04 | 2021-12-14 | 25
122324626 | 2304 | PGE | 95726 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-11-05 |  |  | 2021-11-09 | 2021-11-09 | 2 | 2021-11-09 | 2 | 2021-11-16 | 4 | [15 empty] | 2021-11-05 | 2021-11-05 |  | 2021-11-05 | 2021-11-05 | 1
122325400 | 2305 | PGE | 95449 | NEM | EXPNEM | Application Review in Progress | Solar PV | 103.102 |  | 2021-11-05 |  | 2021-11-19 | 2021-11-19 | 2021-11-19 | 9
122325599 | 2306 | PGE | 95403 | NEM | EXPNEM | Implementation | Solar PV | 172.8 |  | 2021-11-05 |  |  | 2021-11-10 | 2021-11-10 | 3 | 2021-11-10 | 3 | 2021-11-29 | 10 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2021-12-07 | 6 |  |  |  |  | 2021-11-05 | 2021-11-10 | 2021-11-05 | 2021-12-06 | 18
122326379 | 2307 | PGE | 93654 | NEM | EXPNEM | Application Review in Progress | Solar PV | 30.16 |  | 2021-11-05 |  | 2021-11-09 | 2021-11-09 | 2021-11-09 | 2 | [29 empty] | 2021-11-05 |  | 2021-11-05
122326746 | 2308 | PGE | 95065 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-05 | 2021-11-15 |  | 2021-11-15 | 2021-11-15 | 5 | 2021-11-15 | 5 | 2021-11-16 | 1 | [15 empty] | 2021-11-05 | 2021-11-05 |  | 2021-11-05 | 2021-11-05 | 1 | [34 empty] | 2021-11-15 |  | 2021-11-29 | 11
122327000 | 2309 | PGE | 93230 | NEM | EXPNEM | IA in Progress | Solar PV | 147.168 |  | 2021-11-05 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 6 | 2021-12-02 | 16 | 2021-12-17 | 11 | [15 empty] | 2021-12-17 | 2021-12-17 | 0 | 2021-12-17 | [6 empty] | 2021-11-05 | 2021-12-17 | 2021-11-05
122327050 | 2310 | PGE | 95003 | Non-NEM | Inadvertent Export | Commercial | Storage | 5 |  | 2021-11-05 |  |  | 2021-11-08 | 2021-11-08 | 1 | 2021-11-08 | 1 | 2021-11-16 | 5 | [15 empty] | 2021-11-05 | 2021-11-05 |  | 2021-11-05 | 2021-11-05 | 1 | [34 empty] | 2021-11-05 |  | 2021-11-16 | 8
122327638 | 2311 | PGE | 95425 | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-11-05 | 2021-11-17 |  | 2021-11-17 | 2021-11-17 | 7 | 2021-11-24 | 12 | 2021-12-03 | 5 | [55 empty] | 2021-12-03 |  | 2021-12-03 | 1
122328497 | 2312 | PGE | 95376 | NEM | EXPNEM | Application Accepted | Solar PV | 1100 |  | 2021-11-05 | 2021-11-09 |  | 2021-11-09 | 2021-11-09 | 2 | 2021-11-24 | 12 | [27 empty] | 2021-11-05 | 2021-12-28 | 2021-11-05
122328528 | 2313 | PGE | 95521 | NEM | VNEMMASH | Study in Progress | Solar PV | 189.835 |  | 2021-11-05 |  | 2021-11-15 | 2021-11-15 | 2021-11-15 | 5 | 2021-12-15 | 25
122328825 | 2314 | PGE | 93625 | NEM | EXPNEM | Study in Progress | Solar PV | 856.526 |  | 2021-11-05 |  | 2021-11-10 | 2021-11-10 | 2021-11-10 | 3 | 2021-11-12 | 4 | 2021-12-03 | 13 | 2021-12-14 | [24 empty] | 2021-11-11 | 2021-11-11 | 2021-11-11 | 2021-12-13 | 19 | [7 empty] | 2021-08-18 |  | 102
122328992 | 2315 | PGE | 93625 | NEM | EXPNEM | Study in Progress | Solar PV | 813.333 |  | 2021-11-05 |  | 2021-11-10 | 2021-11-10 | 2021-11-10 | 3 | 2021-11-12 | 4 | 2021-12-03 | 13 | 2021-12-14 | [24 empty] | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-12-13 | 19
122329405 | 2316 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 66.601 |  | 2021-11-05 |  | 2021-11-09 | 2021-11-09 | 2021-11-09 | 2 | 2021-11-22 | 10 | 2021-12-14 | 14 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | [6 empty] | 2021-11-05 |  | 2021-11-05
122329435 | 2317 | PGE | 95407 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 36.619 |  | 2021-11-05 |  | 2021-11-09 | 2021-11-09 | 2021-11-09 | 2 | 2021-11-22 | 10 | 2021-12-14 | 14 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | [6 empty] | 2021-11-05 |  | 2021-11-05
122329470 | 2318 | PGE | 95422 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-11-05 |  |  | 2021-11-09 | 2021-11-09 | 2 | 2021-11-09 | 2 | 2021-11-12 | 2
122331236 | 2319 | PGE | 93460 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-11-06 | 2021-11-15 |  | 2021-11-15 | 2021-11-15 | 4 | 2021-11-18 | 7 | 2021-11-29 | 5 | [15 empty] | 2021-11-04 | 2021-11-04 |  | 2021-11-04 | 2021-11-06 | 2
122331974 | 2320 | PGE | 94574 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.15 |  | 2021-11-06 |  | 2021-11-11 | 2021-11-11 | 2021-11-11 | 3
122332160 | 2321 | PGE | 93453 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-07 |  |  | 2021-11-19 | 2021-11-19 | 8 | 2021-11-19 | 8 | 2021-11-23 | 2 | [15 empty] | 2021-11-23 | 2021-11-23 | 0 | 2021-11-23 | 2021-11-23 | 0
122335113 | 2322 | PGE | 93647 | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-11-08 |  | 2021-11-09 | 2021-11-09 | 2021-11-09 | 1 | 2021-11-16 | 5 | 2021-11-29 | 7 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2021-12-01 | 2 |  |  |  |  | 2021-11-08 | 2021-11-16 | 2021-11-08 | 2021-12-13 | 22
122335170 | 2323 | PGE | 95521 | Non-NEM | Inadvertent Export | Commercial | Storage | 5 |  | 2021-11-08 |  |  | 2021-11-19 | 2021-11-19 | 8 | 2021-11-19 | 8 | 2021-12-01 | 6 | [15 empty] | 2021-12-01 | 2021-12-01 | 0 | 2021-12-01 | 2021-12-01 | 0 | [34 empty] | 2021-11-19 |  | 2021-12-27 | 27
122335390 | 2324 | PGE | 95020 | NEM | EXPNEM | Implementation | Solar PV | 264 |  | 2021-11-08 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 5 | 2021-11-29 | 12 | 2021-12-13 | 10 | [15 empty] | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13 | 2021-12-14 | 1 |  |  |  |  | 2021-11-08 | 2021-11-16 | 2021-11-08 | 2021-12-13 | 22
122336217 | 2325 | PGE | 93420 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-11-08 | 2021-11-19 |  | 2021-11-19 | 2021-11-19 | 8 | 2021-11-22 | 9 | 2021-12-03 | 7
122336410 | 2326 | PGE | 93465 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-11-08 | 2021-11-19 |  | 2021-11-19 | 2021-11-19 | 8 | 2021-11-22 | 9 | 2021-12-03 | 7
122336891 | 2327 | PGE | 95138 | NEM | EXPNEM | IA in Progress | Solar PV | 260 |  | 2021-11-08 |  |  | 2021-11-10 | 2021-11-10 | 2 | 2021-11-10 | 2 | 2021-11-29 | 10 | [15 empty] | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29
122337263 | 2328 | PGE | 93933 | NEM | EXPNEM | IA in Progress | Solar PV | 601.224 |  | 2021-11-08 |  |  | 2021-11-16 | 2021-11-16 | 5 | 2021-11-16 | 5 | 2021-12-14 | 18 | [15 empty] | 2021-12-14 | 2021-12-16 | 2 | 2021-12-16 | [6 empty] | 2021-11-08 | 2021-11-29 | 2021-11-08 | 2021-12-15 | 24
122338518 | 2329 | PGE | 93204 | NEM | EXPNEM | Implementation | Solar PV | 62.5 |  | 2021-11-08 |  |  | 2021-11-10 | 2021-11-10 | 2 | 2021-11-10 | 2 | 2021-11-15 | 2 | [15 empty] | 2021-11-15 | 2021-12-07 | 14 | 2021-12-07 | 2021-12-08 | 1
122338543 | 2330 | PGE | 94558 | NEM | EXPNEM | Application Review in Progress | Solar PV | 652.994 |  | 2021-11-08 |  | 2021-11-09 | 2021-11-09 | 2021-11-09 | 1 | [29 empty] | 2021-11-08 |  | 2021-11-08
122340008 | 2331 | PGE | 93201 | NEM | EXPNEM | Study in Progress | Solar PV | 800 |  | 2021-11-09 |  | 2021-11-23 | 2021-11-22 | 2021-11-22 | 8 | 2021-12-07 | 17 | 2021-12-24 | 13 | 2021-12-24
122340355 | 2332 | PGE | 94114 | NEM | VNEM | Application Review in Progress | Solar PV | 52.163 |  | 2021-11-09 |  | 2021-11-24 | 2021-11-24 | 2021-11-24 | 10
122340749 | 2333 | PGE | 93901 | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.2 |  | 2021-11-09 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 4
122340767 | 2334 | PGE | 93426 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-11-09 | 2021-11-23 |  | 2021-11-23 | 2021-11-23 | 9 | 2021-11-23 | 9 | 2021-12-14 | 13
122340837 | 2335 | PGE | 93307 | NEM | EXPNEM | Implementation | Solar PV | 230.852 |  | 2021-11-09 |  |  | 2021-11-15 | 2021-11-15 | 3 | 2021-11-15 | 3 | 2021-11-29 | 8 | [15 empty] | 2021-11-29 | 2021-12-01 | 2 | 2021-12-01 | 2021-12-01 | 0
122341273 | 2336 | PGE | 93901 | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.2 |  | 2021-11-09 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 4
122341395 | 2337 | PGE | 95616 | NEM | EXPNEM | IA in Progress | Solar PV | 50.092 |  | 2021-11-09 |  | 2021-11-10 | 2021-11-10 | 2021-11-10 | 1 | 2021-11-12 | 2 | 2021-11-30 | 10 | [15 empty] | 2021-11-30 | 2021-11-30 | 0 | 2021-11-30
122341708 | 2338 | PGE | 95131 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 241.12 |  | 2021-11-09 |  | 2021-11-10 | 2021-11-10 | 2021-11-10 | 1 | [29 empty] | 2021-11-09 |  | 2021-11-09
122342053 | 2339 | PGE | 94585 | NEM | EXPNEM | Study in Progress | Solar PV | 200 |  | 2021-11-09 |  | 2021-11-19 | 2021-11-19 | 2021-11-19 | 7 | 2021-12-23 | 29 | [39 empty] | 2020-11-02 | 2021-06-09 | 149
122343117 | 2340 | PGE | 94565 | NEM | VNEM | Application Review in Progress | Solar PV | 86.4 |  | 2021-11-09 |  | 2021-11-17 | 2021-11-17 | 2021-11-17 | 5
122343432 | 2341 | PGE | 95616 | NEM | EXPNEM | Study in Progress | Solar PV | 146.17 |  | 2021-11-09 |  | 2021-11-23 | 2021-11-23 | 2021-11-23 | 9 | 2021-12-21 | 27
122343595 | 2342 | PGE | 95126 | NEM | EXPNEM | Application Review in Progress | Solar PV | 30.236 |  | 2021-11-09 |  | 2021-11-30 | 2021-11-19 | 2021-11-19 | 7
122343728 | 2343 | PGE | 93446 | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.3 |  | 2021-11-09 |  | 2021-12-09 | 2021-11-19 | 2021-11-19 | 7
122343859 | 2344 | PGE | 93401 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-09 | 2021-11-10 |  | 2021-11-10 | 2021-11-10 | 1 | 2021-11-10 | 1 | 2021-11-16 | 3 | [15 empty] | 2021-11-08 | 2021-11-08 |  | 2021-11-08 | 2021-11-08 | 1
122344267 | 2345 | PGE | 93203 | NEM | EXPNEM | Study in Progress | Solar PV | 900 |  | 2021-11-09 |  | 2021-11-15 | 2021-11-15 | 2021-11-15 | 3 | 2021-11-16 | 4 | 2021-12-29 | 29
122344944 | 2346 | PGE | 94089 | NEM | EXPNEM | IA in Progress | Solar PV | 233.2 |  | 2021-11-09 |  | 2021-11-15 | 2021-11-15 | 2021-11-15 | 3 | 2021-11-15 | 3 | 2021-11-30 | 9 | [15 empty] | 2021-11-30 | 2021-11-30 | 0 | 2021-11-30
122345193 | 2347 | PGE | 94510 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.111 |  | 2021-11-09 |  | 2021-12-03 | 2021-11-15 | 2021-11-15 | 3 | 2021-12-13 | 21 | 2021-12-20 | 5 | [34 empty] | 2021-12-20 | 2021-12-20 | 0 | [15 empty] | 2021-12-20 |  |  | 2021-12-20 |  | 2021-12-20 | 0
122346045 | 2348 | PGE | 95338 | NEM | EXPNEM | Study in Progress | Solar PV | 57.874 |  | 2021-11-09 |  | 2021-11-17 | 2021-11-16 | 2021-11-16 | 4 | 2021-11-29 | 11
122346070 | 2349 | PGE | 94577 | NEM | EXPNEM | Application Accepted | Solar PV | 1270 |  | 2021-11-09 | 2021-11-15 |  | 2021-11-15 | 2021-11-15 | 3 | 2021-12-01 | 13
122357831 | 2350 | PGE | 93212 | NEM | EXPNEM | Study in Progress | Solar PV | 801.632 |  | 2021-11-10 |  | 2021-12-06 | 2021-11-23 | 2021-11-23 | 8 | 2021-12-07 | 16 | 2021-12-24 | 13 | 2021-12-24
122357935 | 2351 | PGE | 94952 | NEM | EXPNEM | Study in Progress | Solar PV | 43.2 |  | 2021-11-10 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 3 | 2021-12-01 | 12 | 2021-12-15 | 10 | 2021-12-29
122357937 | 2352 | PGE | 94541 | NEM | EXPNEM | Application Review in Progress | Solar PV | 127.195 |  | 2021-11-10 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 3
122358099 | 2353 | PGE | 93201 | NEM | EXPNEM | Study in Progress | Solar PV | 601.224 |  | 2021-11-10 |  |  | 2021-11-19 | 2021-11-19 | 6 | 2021-11-24 | 9 | 2021-12-13 | 11 | 2021-12-13
122358306 | 2354 | PGE | 94536 | NEM | EXPNEM | IA in Progress | Solar PV | 79.292 |  | 2021-11-10 |  | 2021-11-15 | 2021-11-15 | 2021-11-15 | 2 | 2021-11-17 | 4 | 2021-12-27 | 26 | [15 empty] | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27 | [6 empty] | 2021-11-17 |  | 2021-11-17
122358962 | 2355 | PGE | 95128 | NEM | EXPNEM | Application Review in Progress | Solar PV | 100.91 |  | 2021-11-10 |  | 2021-12-13 | 2021-11-15 | 2021-11-15 | 2
122359705 | 2356 | PGE | 93280 | NEM | EXPNEM | IA in Progress | Solar PV | 601.224 |  | 2021-11-10 |  | 2021-11-24 | 2021-11-24 | 2021-11-24 | 9 | 2021-11-29 | 10 | 2021-12-14 | 11 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14
122359708 | 2357 | PGE | 93908 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 2161.5 |  | 2021-11-10 | 2021-11-17 |  | 2021-11-17 | 2021-11-17 | 4 | 2021-12-08 | 17 | [27 empty] | 2021-11-10 |  | 2021-11-10
122359873 | 2358 | PGE | 93908 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 2661.5 |  | 2021-11-10 | 2021-11-17 |  | 2021-11-17 | 2021-11-17 | 4 | 2021-12-08 | 17 | [27 empty] | 2021-11-10 |  | 2021-11-10
122360286 | 2359 | PGE | 94612 | NEM | EXPNEM | IA in Progress | Solar PV | 59.764 |  | 2021-11-10 |  | 2021-11-15 | 2021-11-15 | 2021-11-15 | 2 | 2021-11-16 | 3 | 2021-12-02 | 10 | [15 empty] | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02
122360302 | 2360 | PGE | 94577 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 2631.072 |  | 2021-11-10 | 2021-11-15 |  | 2021-11-12 | 2021-11-12 | 1 | 2021-12-01 | 12
122361048 | 2361 | PGE | 95020 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1096.5 |  | 2021-11-10 | 2021-11-17 |  | 2021-11-17 | 2021-11-17 | 4 | 2021-12-01 | 12 | [27 empty] | 2021-12-08 | 2021-12-30 | 2021-12-08
122361076 | 2362 | PGE | 93401 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-11-10 |  |  | 2021-11-15 | 2021-11-15 | 2 | 2021-11-15 | 2 | 2021-11-16 | 1 | [15 empty] | 2021-11-10 | 2021-11-10 |  | 2021-11-10 | 2021-11-10 | 1
122361163 | 2363 | PGE | 94612 | NEM | EXPNEM | IA in Progress | Solar PV | 50.529 |  | 2021-11-10 |  | 2021-11-15 | 2021-11-15 | 2021-11-15 | 2 | 2021-11-16 | 3 | 2021-12-02 | 10 | [15 empty] | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02
122361718 | 2364 | PGE | 94065 | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-11-10 |  | 2021-11-15 | 2021-11-15 | 2021-11-15 | 2 | 2021-11-17 | 4 | 2021-11-18 | 1 | [15 empty] | 2021-11-18 | 2021-12-10 | 14 | 2021-12-10
122361726 | 2365 | PGE | 95442 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-10 | 2021-11-15 |  | 2021-11-15 | 2021-11-15 | 2 | 2021-11-17 | 4 | 2021-12-09 | 14 | [15 empty] | 2021-11-10 | 2021-11-10 |  | 2021-11-10 | 2021-11-10 | 1
122362387 | 2366 | PGE | 95404 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.705 |  | 2021-11-10 |  | 2021-11-17 | 2021-11-17 | 2021-11-17 | 4 | 2021-11-20 | 6 | 2021-11-21 | 0 | [25 empty] | 2021-11-10 | 2021-12-01 | 2021-11-10 | 2021-12-01 | 12 |  |  |  |  | 2021-12-02 | 2021-12-02 | 0 | [15 empty] | 2021-12-02 |  |  | 2021-12-02 |  | 2021-12-02 | 0
122362390 | 2367 | PGE | 93401 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 69.472 |  | 2021-11-10 |  | 2021-11-29 | 2021-11-29 | 2021-11-29 | 10 | 2021-12-07 | 16 | [27 empty] | 2021-11-10 |  | 2021-11-10
122362498 | 2368 | PGE | 94558 | NEM | EXPNEM | Implementation | Solar PV | 72 |  | 2021-11-10 |  | 2021-11-23 | 2021-11-23 | 2021-11-23 | 8 | 2021-12-02 | 13 | 2021-12-16 | 10 | [15 empty] | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16 | 2021-12-20 | 2 |  |  |  |  | 2021-11-10 | 2021-12-02 | 2021-11-10 | 2021-12-16 | 23
122362889 | 2369 | PGE | 95452 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-11-10 |  |  | 2021-11-17 | 2021-11-17 | 4 | 2021-11-17 | 4 | 2021-11-17 | 0 | [34 empty] | 2021-11-17 | 2021-11-17 | 0 | [15 empty] | 2021-11-17 |  |  | 2021-11-17 |  | 2021-11-17 | 0
122363757 | 2370 | PGE | 94549 | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-11-11 | 2021-11-29 |  | 2021-11-29 | 2021-11-29 | 9 | 2021-12-16 | 22
122363913 | 2371 | PGE | 93446 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-11-11 |  |  | 2021-11-15 | 2021-11-15 | 1 | 2021-11-15 | 1 | 2021-11-18 | 3 | [15 empty] | 2021-11-10 | 2021-11-10 |  | 2021-11-10 | 2021-11-11 | 2
122364112 | 2372 | PGE | 93453 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-11-11 | 2021-11-15 |  | 2021-11-15 | 2021-11-15 | 1 | 2021-11-18 | 4 | 2021-11-29 | 5 | [15 empty] | 2021-11-11 | 2021-11-11 |  | 2021-11-11 | 2021-11-11 | 1
122365068 | 2373 | PGE | 95497 | NEM | EXPNEM | Application Review in Progress | Solar PV | 86.4 |  | 2021-11-11 |  | 2021-11-29 | 2021-11-23 | 2021-11-23 | 7 | [29 empty] | 2021-11-11 |  | 2021-11-11
122365086 | 2374 | PGE | 93420 | Non-NEM | Inadvertent Export | Implementation | Solar PV, Storage | 10 |  | 2021-11-11 |  |  | 2021-11-15 | 2021-11-15 | 1 | 2021-11-15 | 1 | [17 empty] | 2021-11-11 | 2021-11-11 |  | 2021-11-11 | 2021-11-11 | 1
122365233 | 2375 | PGE | 93454 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-11-11 |  |  | 2021-11-15 | 2021-11-15 | 1 | 2021-11-15 | 1 | 2021-11-16 | 1 | [15 empty] | 2021-11-11 | 2021-11-11 |  | 2021-11-11 | 2021-11-11 | 1
122365287 | 2376 | PGE | 96092 | NEM | EXPNEM | Application Review in Progress | Solar PV | 772.134 |  | 2021-11-11 |  | 2021-11-12 | 2021-11-12 | 2021-11-12 | 0
122365291 | 2377 | PGE | 96092 | NEM | EXPNEM | Withdrawn | Solar PV | 1654.572 |  | 2021-11-11 | 2021-11-15 |  | 2021-11-12 | 2021-11-12 | 0
122365323 | 2378 | PGE | 96092 | NEM | EXPNEM | Study in Progress | Solar PV | 527.483 |  | 2021-11-11 |  |  | 2021-11-12 | 2021-11-12 | 0 | 2021-11-12 | 0 | 2021-12-07 | 15 | 2021-12-07
122365326 | 2379 | PGE | 93710 | NEM | EXPNEM | Application Accepted | Solar PV | 33.3 |  | 2021-11-11 |  | 2021-11-22 | 2021-11-22 | 2021-11-22 | 6 | 2021-12-24 | 28 | [27 empty] | 2021-11-11 | 2021-12-30 | 2021-11-11
122365398 | 2380 | PGE | 93710 | NEM | EXPNEM | Implementation | Solar PV | 30.003 |  | 2021-11-11 |  | 2021-11-15 | 2021-11-15 | 2021-11-15 | 1 | 2021-11-30 | 10 | 2021-12-14 | 10 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2021-12-16 | 2 |  |  |  |  | 2021-11-11 | 2021-11-30 | 2021-11-11 | 2021-12-15 | 21
122365856 | 2381 | PGE | 93241 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 30.402 |  | 2021-11-11 |  | 2021-11-29 | 2021-11-29 | 2021-11-29 | 9 | 2021-12-09 | 17 | 2021-12-30 | 15 | [15 empty] | 2021-12-30 | [9 empty] | 2021-11-11 |  | 2021-11-11
122365857 | 2382 | PGE | 93241 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 63.182 |  | 2021-11-11 |  | 2021-11-29 | 2021-11-29 | 2021-11-29 | 9 | 2021-12-09 | 17 | 2021-12-30 | 15 | [15 empty] | 2021-12-30 | [9 empty] | 2021-11-11 |  | 2021-11-11
122366121 | 2383 | PGE | 95497 | NEM | EXPNEM | Application Review in Progress | Solar PV | 37.598 |  | 2021-11-11 |  | 2021-11-22 | 2021-11-15 | 2021-11-15 | 1 | [29 empty] | 2021-11-11 |  | 2021-11-11
122367375 | 2384 | PGE | 93460 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-11-12 |  |  | 2021-11-15 | 2021-11-15 | 1 | 2021-11-15 | 1 | 2021-12-27 | 28 | [15 empty] | 2021-11-10 | 2021-11-10 |  | 2021-11-10 | 2021-11-11 | 2
122368682 | 2385 | PGE | 95202 | NEM | EXPNEM | Study in Progress | Solar PV | 280 |  | 2021-11-12 |  | 2021-11-15 | 2021-11-15 | 2021-11-15 | 1 | 2021-12-24 | 28 | [27 empty] | 2021-11-12 | 2021-12-24 | 2021-11-12
122369006 | 2386 | PGE | 93242 | NEM | EXPNEM | Implementation | Solar PV | 150 |  | 2021-11-12 |  | 2021-12-03 | 2021-11-29 | 2021-11-29 | 9 | 2021-12-02 | 12 | 2021-12-22 | 14 | [15 empty] | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22 | 2021-12-27 | 3 |  |  |  |  | 2021-11-12 | 2021-12-07 | 2021-11-12 | 2021-12-16 | 22
122369244 | 2387 | PGE | 95602 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1192.682 |  | 2021-11-12 |  | 2021-11-15 | 2021-11-15 | 2021-11-15 | 1
122369295 | 2388 | PGE | 95602 | NEM | EXPNEM | Application Review in Progress | Solar PV | 203.456 |  | 2021-11-12 |  | 2021-11-15 | 2021-11-15 | 2021-11-15 | 1
122370185 | 2389 | PGE | 96092 | NEM | EXPNEM | Withdrawn | Solar PV | 1145.473 |  | 2021-11-12 | 2021-11-15 |  | 2021-11-15 | 2021-11-15 | 1
122370653 | 2390 | PGE | 94945 | NEM | EXPNEM | Application Review in Progress | Solar PV | 384.928 |  | 2021-11-12 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2
122371024 | 2391 | PGE | 94945 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1135.29 |  | 2021-11-12 |  | 2021-11-30 | 2021-11-30 | 2021-11-30 | 10
122371574 | 2392 | PGE | 95993 | NEM | EXPNEM | Application Review in Progress | Solar PV | 31.724 |  | 2021-11-12 |  | 2021-11-29 | 2021-11-29 | 2021-11-29 | 9 | [29 empty] | 2021-11-12 |  | 2021-11-12 |  |  | 2021-12-14
122371948 | 2393 | PGE | 95385 | NEM | EXPNEM | Study in Progress | Solar PV | 316.555 |  | 2021-11-12 |  | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2 | 2021-11-22 | 6
122373708 | 2394 | PGE | 95464 | NEM | EXPNEM | Study in Progress | Solar PV | 464.599 |  | 2021-11-13 |  |  | 2021-11-17 | 2021-11-17 | 2 | 2021-11-17 | 2 | 2021-12-06 | 11 | 2021-12-06
122374080 | 2395 | PGE | 93427 | NEM | EXPNEM | Application Accepted | Solar PV | 33.3 |  | 2021-11-13 |  |  | 2021-11-30 | 2021-11-30 | 9 | 2021-11-30 | 9 | [27 empty] | 2021-11-13 |  | 2021-11-13
122374317 | 2396 | PGE | 95404 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 31.068 |  | 2021-11-14 |  | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2 | 2021-11-24 | 7 | 2021-11-24 | 0
122374465 | 2397 | PGE | 95030 | NEM | EXPNEM | Study in Progress | Solar PV | 32.453 |  | 2021-11-15 |  |  | 2021-12-01 | 2021-12-01 | 10 | 2021-12-01 | 10 | 2021-12-22 | 15 | 2021-12-22
122374758 | 2398 | PGE | 93401 | NEM | NEMMT | Application Review in Progress | Solar PV, Storage | 884.284 |  | 2021-11-15 |  | 2021-12-01 | 2021-12-01 | 2021-12-01 | 10 | [29 empty] | 2021-11-15 |  | 2021-11-15
122375509 | 2399 | PGE | 95682 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-15 | 2021-11-18 |  | 2021-11-18 | 2021-11-18 | 3 | 2021-11-22 | 5 | 2021-12-06 | 8 | [15 empty] | 2021-11-15 | 2021-11-15 |  | 2021-11-15 | 2021-11-18 | 4 | [34 empty] | 2021-11-18 |  | 2021-12-06 | 13
122376485 | 2400 | PGE | 95361 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.179 |  | 2021-11-15 |  | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2 | 2021-11-29 | 8 | 2021-12-20 | 15 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | [6 empty] | 2021-11-15 | 2021-11-17 | 2021-11-15 | 2021-12-15 | 20
122377656 | 2401 | PGE | 95762 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 15 |  | 2021-11-15 |  |  | 2021-12-01 | 2021-12-01 | 10 | 2021-12-01 | 10 | 2021-12-09 | 6
122377980 | 2402 | PGE | 93706 | NEM | EXPNEM | Study in Progress | Solar PV | 40.252 |  | 2021-11-15 |  | 2021-11-23 | 2021-11-23 | 2021-11-23 | 6 | 2021-12-28 | 29 | [28 empty] | 2021-12-28 | 2021-12-28
122378014 | 2403 | PGE | 94954 | NEM | EXPNEM | Implementation | Solar PV | 62.5 |  | 2021-11-15 |  |  | 2021-11-29 | 2021-11-29 | 8 | 2021-11-29 | 8 | 2021-12-15 | 12 | [15 empty] | 2021-12-15 | 2021-12-27 | 8 | 2021-12-27 | 2021-12-27 | 0 | [9 empty] | 2021-12-14
122378231 | 2404 | PGE | 93631 | NEM | EXPNEM | Implementation | Solar PV | 38.956 |  | 2021-11-15 |  | 2021-11-19 | 2021-11-17 | 2021-11-17 | 2 | 2021-11-30 | 9 | 2021-12-06 | 4 | [15 empty] | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-15 | 7 |  |  |  |  | 2021-11-15 | 2021-11-30 | 2021-11-15 | 2021-12-15 | 20
122378365 | 2405 | PGE | 94568 | NEM | EXPNEM | Study in Progress | Solar PV | 50 |  | 2021-11-15 |  |  | 2021-11-29 | 2021-11-29 | 8 | 2021-11-29 | 8
122379318 | 2406 | PGE | 94080 | NEM | NEMMT | Application Review in Progress | Solar PV, Storage | 789.853 |  | 2021-11-16 |  | 2021-12-02 | 2021-12-02 | 2021-12-02 | 10
122379325 | 2407 | PGE | 95695 | NEM | EXPNEM | Withdrawn | TRBS | 6250 |  | 2021-11-10 | 2021-11-19 |  | 2021-11-16 | 2021-11-16 | 3
122380080 | 2408 | PGE | 94901 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-16 | 2021-11-19 |  | 2021-11-19 | 2021-11-19 | 3 | 2021-12-01 | 9 | 2021-12-03 | 2 | [15 empty] | 2021-11-16 | 2021-11-16 |  | 2021-11-16 | 2021-11-16 | 1
122381009 | 2409 | PGE | 96056 | NEM | EXPNEM | Study in Progress | Solar PV | 40.252 |  | 2021-11-16 |  | 2021-11-17 | 2021-11-17 | 2021-11-17 | 1 | 2021-12-21 | 23
122381642 | 2410 | PGE | 95446 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-16 |  |  | 2021-11-22 | 2021-11-22 | 4 | 2021-11-22 | 4 | 2021-12-03 | 7 | [15 empty] | 2021-11-16 | 2021-11-16 |  | 2021-11-16 | 2021-11-16 | 1 | [34 empty] | 2021-12-03 |  | 2021-12-03 | 1
122383113 | 2411 | PGE | 95913 | NEM | EXPNEM | Study in Progress | Solar PV | 361.092 |  | 2021-11-16 |  | 2021-12-01 | 2021-12-01 | 2021-12-01 | 9 | 2021-12-14 | 18
122383161 | 2412 | PGE | 94707 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.987 |  | 2021-11-16 |  |  | 2021-11-16 | 2021-11-16 | 0 | 2021-11-19 | 3 | 2021-11-20 | 0 | [34 empty] | 2021-11-20 | 2021-11-20 | 0 | [15 empty] | 2021-11-20 |  |  | 2021-11-20 |  | 2021-11-20 | 0
122384366 | 2413 | PGE | 93454 | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2021-11-16 |  | 2021-11-24 | 2021-11-24 | 2021-11-24 | 6 | 2021-11-30 | 8
122384841 | 2414 | PGE | 95376 | NEM | EXPNEM | Application Accepted | Solar PV | 1200 |  | 2021-11-17 | 2021-11-19 |  | 2021-11-19 | 2021-11-19 | 2 | 2021-12-08 | 13 | 2021-12-29 | 15 | [25 empty] | 2021-11-17 | 2021-12-20 | 2021-11-17
122384855 | 2415 | PGE | 95695 | NEM | EXPNEM | Application Review in Progress | Solar PV | 57.217 |  | 2021-11-09 |  | 2021-12-21 | 2021-11-19 | 2021-11-19 | 7 | [29 empty] | 2021-12-14 |  | 2021-12-14
122384943 | 2416 | PGE | 94404 | NEM | EXPNEM | Application Review in Progress | Solar PV | 95.827 |  | 2021-11-17 |  | 2021-11-29 | 2021-11-23 | 2021-11-23 | 4 | [29 empty] | 2021-11-17 |  | 2021-11-17
122385070 | 2417 | PGE | 94404 | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 |  | 2021-11-17 |  | 2021-11-29 | 2021-11-23 | 2021-11-23 | 4 | [29 empty] | 2021-11-17 |  | 2021-11-17
122385077 | 2418 | PGE | 94402 | NEM | EXPNEM | Application Review in Progress | Solar PV | 62.5 |  | 2021-11-17 |  | 2021-11-19 | 2021-11-19 | 2021-11-19 | 2
122385088 | 2419 | PGE | 94404 | NEM | EXPNEM | Application Review in Progress | Solar PV | 80.639 |  | 2021-11-17 |  | 2021-12-03 | 2021-11-30 | 2021-11-30 | 7 | [29 empty] | 2021-11-17 |  | 2021-11-17
122385154 | 2420 | PGE | 94401 | NEM | EXPNEM | IA in Progress | Solar PV | 63.081 |  | 2021-11-17 |  | 2021-11-18 | 2021-11-18 | 2021-11-18 | 1 | 2021-11-22 | 3 | 2021-12-08 | 10 | [15 empty] | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08
122385534 | 2421 | PGE | 93727 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-11-17 |  |  | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 7 | 2021-12-14 | 10 | [15 empty] | 2021-12-14 | 2021-12-16 | 2 | 2021-12-16 | [6 empty] | 2021-11-17 |  | 2021-11-17
122385635 | 2422 | PGE | 93405 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-11-17 |  | 2021-12-07 | 2021-11-19 | 2021-11-19 | 2 | 2021-12-14 | 17 | 2021-12-29 | 11 | [15 empty] | 2021-11-17 | 2021-11-17 |  | 2021-11-17 | 2021-12-16 | 22
122385679 | 2423 | PGE | 95076 | NEM | EXPNEM | IA in Progress | Solar PV | 60.9 |  | 2021-11-17 |  | 2021-12-03 | 2021-12-03 | 2021-12-03 | 10 | 2021-12-07 | 12 | 2021-12-23 | 12 | [15 empty] | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23 | [6 empty] | 2021-11-17 | 2021-12-07 | 2021-11-17 | 2021-12-16 | 19
122385969 | 2424 | PGE | 93703 | NEM | EXPNEM | IA in Progress | Solar PV | 83.3 |  | 2021-11-17 |  |  | 2021-12-03 | 2021-12-03 | 10 | 2021-12-03 | 10 | 2021-12-23 | 14 | [15 empty] | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23 | [6 empty] | 2021-11-17 | 2021-12-07 | 2021-11-17 | 2021-12-16 | 19
122386283 | 2425 | PGE | 93206 | NEM | EXPNEM | Study in Progress | Solar PV | 501.02 |  | 2021-11-17 |  | 2021-11-29 | 2021-11-29 | 2021-11-29 | 6 | 2021-12-15 | 18 | [5 empty] | 2021-12-15
122386479 | 2426 | PGE | 95032 | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 |  | 2021-11-17 |  | 2021-12-02 | 2021-12-02 | 2021-12-02 | 9 | [29 empty] | 2021-11-17 |  | 2021-11-17
122386859 | 2427 | PGE | 94526 | Non-NEM | Inadvertent Export | Commercial | Storage | 5 |  | 2021-11-17 | 2021-12-02 |  | 2021-12-02 | 2021-12-02 | 9 | 2021-12-15 | 18 | 2021-12-23 | 6 | [55 empty] | 2021-12-02 |  | 2021-12-23 | 16
122386862 | 2428 | PGE | 94610 | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 500.5 |  | 2021-11-17 |  |  | 2021-11-29 | 2021-11-29 | 6 | 2021-11-29 | 6 | 2021-12-20 | 15 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20
122387714 | 2429 | PGE | 94545 | NEM | EXPNEM | Application Review in Progress | Solar PV | 48.875 |  | 2021-11-17 |  | 2021-11-18 | 2021-11-18 | 2021-11-18 | 1
122388686 | 2430 | PGE | 93203 | NEM | EXPNEM | Application Review in Progress | Solar PV | 993.487 |  | 2021-11-17 |  | 2021-12-02 | 2021-12-02 | 2021-12-02 | 9
122388803 | 2431 | PGE | 93230 | NEM | EXPNEM | Implementation | Solar PV | 47.677 |  | 2021-11-17 |  | 2021-11-19 | 2021-11-19 | 2021-11-19 | 2 | 2021-11-24 | 5 | 2021-12-14 | 12 | [15 empty] | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2021-12-28 | 10 |  |  |  |  | 2021-11-17 |  | 2021-11-17
122389193 | 2432 | PGE | 93940 | NEM | EXPNEM | Study in Progress | Solar PV | 57.71 |  | 2021-11-17 |  | 2021-12-03 | 2021-12-03 | 2021-12-03 | 10 | 2021-12-07 | 12 | [27 empty] | 2021-11-17 | 2021-12-07 | 2021-11-17 | 2021-12-16 | 19
122389524 | 2433 | PGE | 94574 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 30.08 |  | 2021-11-17 |  | 2021-11-22 | 2021-11-22 | 2021-11-22 | 3 | 2021-11-24 | 5 | 2021-11-29 | 1
122389823 | 2434 | PGE | 95619 | NEM | NEM Paired Storage | Application Accepted | ENGN, Solar PV, Storage | 865.4 |  | 2021-11-17 |  |  | 2021-11-18 | 2021-11-18 | 1 | 2021-11-18 | 1 | 2021-12-09 | 13
122389982 | 2435 | PGE | 95023 | NEM | EXPNEM | Withdrawn | Solar PV | 875 |  | 2021-11-18 |  | 2021-11-22 | 2021-11-22 | 2021-11-22 | 2
122390487 | 2436 | PGE | 94558 | NEM | EXPNEM | Application Review in Progress | Solar PV | 68.768 |  | 2021-11-18 |  | 2021-11-22 | 2021-11-22 | 2021-11-22 | 2
122390785 | 2437 | PGE | 95746 | NEM | EXPNEM | Study in Progress | Solar PV | 37.599 |  | 2021-11-18 |  |  | 2021-11-29 | 2021-11-29 | 5 | 2021-11-29 | 5
122391477 | 2438 | PGE | 95403 | NEM | EXPNEM | Implementation | Solar PV | 300 |  | 2021-11-18 |  | 2021-11-30 | 2021-11-30 | 2021-11-30 | 6 | 2021-11-30 | 6 | 2021-12-15 | 11 | [15 empty] | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 2021-12-16 | 1
122391766 | 2439 | PGE | 94403 | NEM | EXPNEM | IA in Progress | Solar PV | 86.4 |  | 2021-11-18 |  | 2021-11-19 | 2021-11-19 | 2021-11-19 | 1 | 2021-11-19 | 1 | 2021-12-29 | 26 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29
122391940 | 2440 | PGE | 93266 | NEM | EXPNEM | Study in Progress | Solar PV | 840 |  | 2021-11-18 |  |  | 2021-11-29 | 2021-11-29 | 5 | 2021-11-29 | 5 | 2021-12-14 | 11 | 2021-12-14 | [24 empty] | 2021-11-18 |  | 2021-11-18 |  |  | 2021-12-14
122392070 | 2441 | PGE | 95003 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-18 | 2021-11-19 |  | 2021-11-19 | 2021-11-19 | 1 | 2021-12-01 | 7 | 2021-12-15 | 10 | [15 empty] | 2021-11-18 | 2021-11-18 |  | 2021-11-18 | 2021-11-18 | 1 | [34 empty] | 2021-11-19 |  | 2021-12-15 | 19
122392165 | 2442 | PGE | 93458 | NEM | VNEMMASH | Application Review in Progress | Solar PV | 39.976 |  | 2021-11-18 |  | 2021-11-19 | 2021-11-19 | 2021-11-19 | 1
122392688 | 2443 | PGE | 93908 | NEM | EXPNEM | IA in Progress | Solar PV | 360 |  | 2021-11-18 |  |  | 2021-11-22 | 2021-11-22 | 2 | 2021-11-29 | 5 | 2021-12-01 | 2 | [15 empty] | 2021-12-01 | 2021-12-01 | 0 | 2021-12-01 | [6 empty] | 2021-11-18 | 2021-11-29 | 2021-11-18 | 2021-12-15 | 17
122392748 | 2444 | PGE | 95131 | Non-NEM | NEMFC | Application Review in Progress | FUCE | 1100 |  | 2021-11-18 |  | 2021-12-31 | 2021-12-03 | 2021-12-03 | 9
122393193 | 2445 | PGE | 94010 | NEM | EXPNEM | Study in Progress | Solar PV | 31.9 |  | 2021-11-18 |  | 2021-11-24 | 2021-11-24 | 2021-11-24 | 4 | 2021-12-13 | 15
122393533 | 2446 | PGE | 93654 | NEM | EXPNEM | IA in Progress | Solar PV | 71.79 |  | 2021-11-18 |  | 2021-12-06 | 2021-11-22 | 2021-11-22 | 2 | 2021-12-06 | 10 | 2021-12-16 | 8 | [15 empty] | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16 | [6 empty] | 2021-11-18 |  | 2021-11-18
122393668 | 2447 | PGE | 94608 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 864.427 |  | 2021-11-18 |  | 2021-12-04 | 2021-12-04 | 2021-12-04 | 9 | [29 empty] | 2021-11-18 |  | 2021-11-18
122393895 | 2448 | PGE | 93420 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 32.61 |  | 2021-11-18 |  | 2021-12-02 | 2021-11-22 | 2021-11-22 | 2 | 2021-12-09 | 13
122393897 | 2449 | PGE | 93624 | NEM | EXPNEM | Application Accepted | Solar PV | 1907.237 |  | 2021-11-18 | 2021-11-19 |  | 2021-11-19 | 2021-11-19 | 1 | 2021-12-08 | 12 | 2021-12-27 | 13 | [26 empty] | 2021-12-09 | 2021-12-09
122393898 | 2450 | PGE | 93239 | NEM | EXPNEM | IA in Progress | Solar PV | 31.664 |  | 2021-11-18 |  | 2021-12-02 | 2021-11-22 | 2021-11-22 | 2 | 2021-12-02 | 8 | 2021-12-15 | 9 | [15 empty] | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15
122393962 | 2451 | PGE | 93725 | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 1600 |  | 2021-11-18 | 2021-11-19 |  | 2021-11-19 | 2021-11-19 | 1
122394079 | 2452 | PGE | 93624 | NEM | EXPNEM | Study in Progress | Solar PV | 625 |  | 2021-11-18 |  |  | 2021-11-30 | 2021-11-30 | 6 | 2021-11-30 | 6 | 2021-12-15 | 11 | 2021-12-15
122398151 | 2453 | PGE | 95570 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-11-19 |  |  | 2021-11-24 | 2021-11-24 | 3 | 2021-11-24 | 3 | 2021-12-03 | 5 | [15 empty] | 2021-11-19 | 2021-11-19 |  | 2021-11-19 | 2021-11-19 | 1
122398987 | 2454 | PGE | 95210 | NEM | EXPNEM | Application Review in Progress | Solar PV | 31.139 |  | 2021-11-19 |  | 2021-11-29 | 2021-11-29 | 2021-11-29 | 4
122399109 | 2455 | PGE | 94806 | NEM | EXPNEM | Application Review in Progress | Solar PV | 81.757 |  | 2021-11-19 |  | 2021-12-14 | 2021-12-02 | 2021-12-02 | 7
122399580 | 2456 | PGE | 94941 | Non-NEM | Non-Export | Implementation | Storage | 10 |  | 2021-11-19 |  |  | 2021-11-24 | 2021-11-24 | 3 | 2021-11-24 | 3 | [17 empty] | 2021-11-19 | 2021-11-19 |  | 2021-11-19 | 2021-11-19 | 1
122399798 | 2457 | PGE | 93725 | NEM | EXPNEM | Application Review in Progress | Solar PV | 187.5 |  | 2021-11-19 |  | 2021-12-17 | 2021-11-22 | 2021-11-22 | 1 | [29 empty] | 2021-11-19 |  | 2021-11-19
122400023 | 2458 | PGE | 95963 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 36.448 |  | 2021-11-19 |  | 2021-11-29 | 2021-11-29 | 2021-11-29 | 4 | 2021-12-01 | 6 | 2021-12-20 | 13 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | [6 empty] | 2021-11-19 | 2021-12-14 | 2021-11-19 | 2021-12-14 | 15
122400034 | 2459 | PGE | 95963 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 38.018 |  | 2021-11-19 |  | 2021-11-29 | 2021-11-29 | 2021-11-29 | 4 | 2021-12-01 | 6 | 2021-12-20 | 13 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | [6 empty] | 2021-11-19 | 2021-12-14 | 2021-11-19 | 2021-12-14 | 15
122400094 | 2460 | PGE | 93720 | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-11-19 |  |  | 2021-11-30 | 2021-11-30 | 5 | 2021-11-30 | 5 | 2021-12-07 | 5 | [15 empty] | 2021-12-07 | 2021-12-07 | 0 | 2021-12-07 | 2021-12-08 | 1 |  |  |  |  | 2021-11-19 |  | 2021-11-19
122400162 | 2461 | PGE | 93306 | NEM | EXPNEM | Implementation | Solar PV | 72.22 |  | 2021-11-19 |  | 2021-11-29 | 2021-11-29 | 2021-11-29 | 4 | 2021-12-02 | 7 | 2021-12-16 | 10 | [15 empty] | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16 | 2021-12-30 | 10
122401791 | 2462 | PGE | 94566 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 31.375 |  | 2021-11-20 |  |  | 2021-11-24 | 2021-11-24 | 2 | 2021-11-24 | 2
122404218 | 2463 | PGE | 93204 | Non-NEM | Non-Export | Application Review in Progress | Storage | 929.5 |  | 2021-11-22 | 2021-11-22 |  | 2021-11-22 | 2021-11-22 | 0
122404242 | 2464 | PGE | 93206 | Non-NEM | Non-Export | Application Accepted | Storage | 858 |  | 2021-11-22 | 2021-11-22 |  | 2021-11-22 | 2021-11-22 | 0 | 2021-12-08 | 10
122404283 | 2465 | PGE | 93204 | Non-NEM | Non-Export | Application Review in Progress | Storage | 929.5 |  | 2021-11-22 | 2021-11-22 |  | 2021-11-22 | 2021-11-22 | 0
122404688 | 2466 | PGE | 95556 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-11-22 |  |  | 2021-11-23 | 2021-11-23 | 1 | 2021-11-23 | 1 | 2021-11-29 | 2
122405253 | 2467 | PGE | 94533 | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-11-22 |  | 2021-11-30 | 2021-11-30 | 2021-11-30 | 4 | 2021-12-02 | 6 | 2021-12-17 | 11 | [15 empty] | 2021-12-17 | 2021-12-17 | 0 | 2021-12-17 | [6 empty] | 2021-11-22 | 2021-12-02 | 2021-11-22 | 2021-12-16 | 16
122406427 | 2468 | PGE | 94549 | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-11-22 |  |  | 2021-11-23 | 2021-11-23 | 1 | 2021-11-23 | 1 | 2021-12-13 | 12 | [15 empty] | 2021-11-22 | 2021-11-22 |  | 2021-11-22 | 2021-11-22 | 1 | [34 empty] | 2021-11-22 |  | 2021-12-13 | 16
122406605 | 2469 | PGE | 93311 | NEM | EXPNEM | Study in Progress | Solar PV | 751.224 |  | 2021-11-22 |  |  | 2021-11-29 | 2021-11-29 | 3 | 2021-12-01 | 5 | [5 empty] | 2021-12-01 | 2021-12-29 | 20 | 2021-12-29
122407082 | 2470 | PGE | 93204 | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-11-22 |  |  | 2021-12-08 | 2021-12-08 | 10 | 2021-12-08 | 10 | 2021-12-30 | 16 | [15 empty] | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30
122407083 | 2471 | PGE | 94901 | Non-NEM | Non-Export | Application Review in Progress | Storage | 7.68 |  | 2021-11-22 | 2021-12-08 |  | 2021-12-08 | 2021-12-08 | 10
122407198 | 2472 | PGE | 93460 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 25 |  | 2021-11-22 |  |  | 2021-11-24 | 2021-11-24 | 2 | 2021-11-24 | 2 | 2021-12-10 | 10 | [15 empty] | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24
122407432 | 2473 | PGE | 94945 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 649.409 |  | 2021-11-22 |  | 2021-12-08 | 2021-12-08 | 2021-12-08 | 10
122407462 | 2474 | PGE | 94945 | NEM | EXPNEM | IA in Progress | Solar PV | 276.132 |  | 2021-11-22 |  |  | 2021-11-23 | 2021-11-23 | 1 | 2021-11-23 | 1 | 2021-12-10 | 11 | [15 empty] | 2021-12-10 | 2021-12-10 | 0 | 2021-12-10
122407544 | 2475 | PGE | 93720 | NEM | EXPNEM | Application Review in Progress | Solar PV | 50 |  | 2021-11-22 |  | 2021-12-21 | 2021-12-03 | 2021-12-03 | 7
122407864 | 2476 | PGE | 93308 | NEM | EXPNEM | IA in Progress | Solar PV | 54.81 |  | 2021-11-22 |  | 2021-12-08 | 2021-12-08 | 2021-12-08 | 10 | 2021-12-13 | 13 | 2021-12-27 | 10 | [15 empty] | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27
122408008 | 2477 | PGE | 93420 | Non-NEM | Inadvertent Export | Implementation | Storage | 25 |  | 2021-11-23 |  |  | 2021-11-24 | 2021-11-24 | 1 | 2021-11-24 | 1 | 2021-12-10 | 10 | [15 empty] | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 2021-11-29 | 1
122408093 | 2478 | PGE | 93420 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-23 |  |  | 2021-11-24 | 2021-11-24 | 1 | 2021-11-24 | 1 | 2021-12-13 | 11 | [15 empty] | 2021-11-22 | 2021-11-22 |  | 2021-11-22 | 2021-11-22 | 1
122408100 | 2479 | PGE | 93426 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-23 |  |  | 2021-11-24 | 2021-11-24 | 1 | 2021-11-24 | 1 | 2021-12-13 | 11 | [15 empty] | 2021-11-22 | 2021-11-22 |  | 2021-11-22 | 2021-11-22 | 1
122408176 | 2480 | PGE | 93280 | NEM | EXPNEM | Application Review in Progress | Solar PV | 601.224 |  | 2021-11-23 |  | 2021-12-09 | 2021-12-09 | 2021-12-09 | 10 | [29 empty] | 2021-11-23 |  | 2021-11-23
122408186 | 2481 | PGE | 93422 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-23 |  |  | 2021-11-24 | 2021-11-24 | 1 | 2021-11-24 | 1 | 2021-12-13 | 11 | [15 empty] | 2021-11-23 | 2021-11-23 |  | 2021-11-23 | 2021-11-23 | 1
122408404 | 2482 | PGE | 93924 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-11-23 |  |  | 2021-11-24 | 2021-11-24 | 1 | 2021-11-24 | 1 | 2021-11-30 | 2
122408815 | 2483 | PGE | 96002 | NEM | EXPNEM | Application Review in Progress | Solar PV | 50 |  | 2021-11-23 |  | 2021-12-02 | 2021-12-02 | 2021-12-02 | 5
122408934 | 2484 | PGE | 93612 | NEM | EXPNEM | IA in Progress | Solar PV | 53.626 |  | 2021-11-23 |  |  | 2021-11-29 | 2021-11-29 | 2 | 2021-11-29 | 2 | 2021-12-06 | 5 | [15 empty] | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | [6 empty] | 2021-11-23 | 2021-11-29 | 2021-11-23 | 2021-12-15 | 14
122408959 | 2485 | PGE | 96002 | NEM | EXPNEM | Application Review in Progress | Solar PV | 50 |  | 2021-11-23 |  | 2021-12-06 | 2021-12-06 | 2021-12-06 | 7
122409262 | 2486 | PGE | 93619 | NEM | EXPNEM | Application Review in Progress | Solar PV | 48.51 |  | 2021-11-23 |  | 2021-12-06 | 2021-12-06 | 2021-12-06 | 7
122409338 | 2487 | PGE | 93460 | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-11-23 | 2021-11-29 |  | 2021-11-29 | 2021-11-29 | 2 | 2021-12-31 | 26 | [17 empty] | 2021-11-19 | 2021-11-19 |  | 2021-11-19 | 2021-11-23 | 3
122409453 | 2488 | PGE | 94550 | NEM | EXPNEM | Study in Progress | Solar PV | 155.565 |  | 2021-11-23 |  | 2021-12-09 | 2021-12-09 | 2021-12-09 | 10 | 2021-12-15 | 14
122409913 | 2489 | PGE | 93662 | NEM | EXPNEM | Application Review in Progress | Solar PV | 443.735 |  | 2021-11-23 |  | 2021-12-08 | 2021-12-06 | 2021-12-06 | 7 | [29 empty] | 2021-11-23 | 2021-12-06 | 2021-11-23 | 2021-12-16 | 15
122409987 | 2490 | PGE | 94538 | NEM | EXPNEM | Application Review in Progress | Solar PV | 402.52 |  | 2021-11-23 |  | 2021-12-09 | 2021-12-09 | 2021-12-09 | 10
122411834 | 2491 | PGE | 95320 | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 |  | 2021-11-23 |  | 2021-11-24 | 2021-11-24 | 2021-11-24 | 1 | [29 empty] | 2021-11-23 |  | 2021-11-23
122412588 | 2492 | PGE | 93405 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-24 | 2021-11-24 |  | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 0 | 2021-12-13 | 11 | [15 empty] | 2021-11-13 | 2021-11-13 |  | 2021-11-13 | 2021-11-13 | 0
122412624 | 2493 | PGE | 94534 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.163 |  | 2021-11-24 |  | 2021-12-07 | 2021-11-24 | 2021-11-24 | 0
122413844 | 2494 | PGE | 93654 | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-11-24 |  |  | 2021-12-10 | 2021-12-10 | 10 | 2021-12-10 | 10 | 2021-12-22 | 8 | [15 empty] | 2021-12-22 | [9 empty] | 2021-11-24 |  | 2021-11-24
122413897 | 2495 | PGE | 93610 | NEM | EXPNEM | Application Review in Progress | Solar PV | 760 |  | 2021-11-24 |  | 2021-12-13 | 2021-11-29 | 2021-11-29 | 1
122414001 | 2496 | PGE | 94901 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.163 |  | 2021-11-24 |  | 2021-11-29 | 2021-11-24 | 2021-11-24 | 0
122414203 | 2497 | PGE | 94710 | NEM | EXPNEM | Application Review in Progress | Solar PV | 34.627 |  | 2021-11-24 |  | 2021-12-01 | 2021-12-01 | 2021-12-01 | 3
122414877 | 2498 | PGE | 94957 | NEM | EXPNEM | Study in Progress | Solar PV | 73.4 |  | 2021-11-24 |  |  | 2021-12-10 | 2021-12-10 | 10 | 2021-12-10 | 10
122415136 | 2499 | PGE | 94533 | NEM | VNEM | IA in Progress | Solar PV | 38.629 |  | 2021-11-24 |  | 2021-11-30 | 2021-11-30 | 2021-11-30 | 2 | 2021-12-10 | 10 | 2021-12-31 | 15 | [15 empty] | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31
122415138 | 2500 | PGE | 94533 | NEM | VNEM | IA in Progress | Solar PV | 33.75 |  | 2021-11-24 |  | 2021-11-30 | 2021-11-30 | 2021-11-30 | 2 | 2021-12-10 | 10 | 2021-12-31 | 15 | [15 empty] | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31
122417042 | 2501 | PGE | 93422 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-11-24 |  |  | 2021-11-30 | 2021-11-30 | 2 | 2021-11-30 | 2 | 2021-12-20 | 14 | [15 empty] | 2021-11-24 | 2021-11-24 |  | 2021-11-24 | 2021-11-24 | 1
122418625 | 2502 | PGE | 94404 | NEM | EXPNEM | IA in Progress | Solar PV | 164.41 |  | 2021-11-26 |  |  | 2021-12-06 | 2021-12-06 | 5 | 2021-12-06 | 5 | 2021-12-27 | 15 | [15 empty] | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27
122418626 | 2503 | PGE | 94403 | NEM | EXPNEM | Study in Progress | Solar PV | 99.9 |  | 2021-11-26 |  | 2021-11-29 | 2021-11-29 | 2021-11-29 | 0 | 2021-12-01 | 2 | 2021-12-22 | 15 | 2021-12-22
122418632 | 2504 | PGE | 94403 | NEM | EXPNEM | Study in Progress | Solar PV | 312.5 |  | 2021-11-26 |  | 2021-12-10 | 2021-12-10 | 2021-12-10 | 9 | 2021-12-16 | 13
122418634 | 2505 | PGE | 94404 | NEM | EXPNEM | IA in Progress | Solar PV | 248.79 |  | 2021-11-26 |  | 2021-12-10 | 2021-12-10 | 2021-12-10 | 9 | 2021-12-14 | 11 | 2021-12-29 | 11 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29
122418716 | 2506 | PGE | 94404 | NEM | EXPNEM | IA in Progress | Solar PV | 200 |  | 2021-11-26 |  |  | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 0 | 2021-12-13 | 10 | [15 empty] | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
122418756 | 2507 | PGE | 94403 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-11-26 |  |  | 2021-12-06 | 2021-12-06 | 5 | 2021-12-06 | 5 | 2021-12-23 | 13 | [15 empty] | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23
122418760 | 2508 | PGE | 94404 | NEM | EXPNEM | Study in Progress | Solar PV | 150 |  | 2021-11-26 |  | 2021-12-10 | 2021-12-10 | 2021-12-10 | 9 | 2021-12-16 | 13
122418762 | 2509 | PGE | 94403 | NEM | EXPNEM | Study in Progress | Solar PV | 230.087 |  | 2021-11-26 |  | 2021-12-10 | 2021-12-10 | 2021-12-10 | 9 | 2021-12-14 | 11
122418764 | 2510 | PGE | 94404 | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-11-26 |  | 2021-11-30 | 2021-11-30 | 2021-11-30 | 1 | 2021-12-02 | 3 | 2021-12-03 | 1 | [15 empty] | 2021-12-03 | 2021-12-06 | 1 | 2021-12-06
122418823 | 2511 | PGE | 94402 | NEM | EXPNEM | Study in Progress | Solar PV | 99.9 |  | 2021-11-26 |  | 2021-12-14 | 2021-12-01 | 2021-12-01 | 2 | 2021-12-03 | 4 | 2021-12-14 | 7 | 2021-12-14
122418873 | 2512 | PGE | 93453 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-27 |  |  | 2021-12-09 | 2021-12-09 | 8 | 2021-12-09 | 8 | 2021-12-29 | 14 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 2021-12-29 | 0
122419192 | 2513 | PGE | 94566 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-11-27 |  |  | 2021-12-01 | 2021-12-01 | 2 | 2021-12-01 | 2 | 2021-12-28 | 19 | [34 empty] | 2021-12-28 | 2021-12-28 | 0 | [15 empty] | 2021-12-28 |  |  | 2021-12-28 |  | 2021-12-28 | 0
122419403 | 2514 | PGE | 95135 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 32.158 |  | 2021-11-27 |  |  | 2021-11-27 | 2021-11-27 | 0 | 2021-11-30 | 1 | 2021-12-20 | 14 | [34 empty] | 2021-12-20 | 2021-12-20 | 0 | [15 empty] | 2021-12-20 |  |  | 2021-12-20 |  | 2021-12-20 | 0
122420366 | 2515 | PGE | 93308 | Non-NEM | Non-Export | Study in Progress | Solar PV | 1246.18 |  | 2021-11-23 | 2021-12-01 |  |  | 2021-12-01 | 4 | 2021-12-15 | 14
122420537 | 2516 | PGE | 93654 | NEM | NEMMT | Withdrawn | ENGN, Solar PV, Storage | 4123.1 |  | 2021-11-29 | 2021-12-08 |  | 2021-12-08 | 2021-12-08 | 7 | [29 empty] | 2021-11-29 |  | 2021-11-29
122420611 | 2517 | PGE | 93420 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-11-29 | 2021-12-08 |  | 2021-12-08 | 2021-12-08 | 7 | 2021-12-17 | 14
122421226 | 2518 | PGE | 93234 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 37.926 |  | 2021-11-29 |  | 2021-12-03 | 2021-12-03 | 2021-12-03 | 4 | 2021-12-10 | 9 | 2021-12-31 | 15 | [15 empty] | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | [6 empty] | 2021-11-29 |  | 2021-11-29
122421301 | 2519 | PGE | 94558 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 31.97 |  | 2021-11-29 |  | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2 | 2021-12-08 | 7
122421473 | 2520 | PGE | 93234 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 45.542 |  | 2021-11-29 |  | 2021-12-03 | 2021-12-03 | 2021-12-03 | 4 | 2021-12-10 | 9 | 2021-12-31 | 15 | [15 empty] | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | [6 empty] | 2021-11-29 |  | 2021-11-29 |  |  | 2021-12-15 | 2021-12-29 |  | 10
122421726 | 2521 | PGE | 93309 | NEM | VNEM | Study in Progress | Solar PV | 300 |  | 2021-11-29 |  | 2021-12-14 | 2021-12-02 | 2021-12-02 | 3 | 2021-12-17 | 14
122421728 | 2522 | PGE | 93619 | NEM | EXPNEM | IA in Progress | Solar PV | 36 |  | 2021-11-29 |  | 2021-12-02 | 2021-12-02 | 2021-12-02 | 3 | 2021-12-06 | 5 | 2021-12-30 | 18 | [15 empty] | 2021-12-30
122422040 | 2523 | PGE | 93722 | NEM | EXPNEM | Application Accepted | Solar PV | 1060.096 |  | 2021-11-29 | 2021-12-02 |  | 2021-12-01 | 2021-12-01 | 2 | 2021-12-15 | 12 | [27 empty] | 2021-11-29 |  | 2021-11-29
122422630 | 2524 | PGE | 95920 | NEM | EXPNEM | Application Review in Progress | Solar PV | 63.994 |  | 2021-11-29 |  | 2021-11-29 | 2021-11-29 | 2021-11-29 | 0
122423461 | 2525 | PGE | 93308 | NEM | EXPNEM | Application Accepted | Solar PV | 996.944 |  | 2021-11-29 | 2021-12-02 |  | 2021-12-01 | 2021-12-01 | 2 | 2021-12-15 | 12 | [27 empty] | 2021-11-29 |  | 2021-11-29
122423677 | 2526 | PGE | 93314 | NEM | EXPNEM | Study in Progress | Solar PV | 701.428 |  | 2021-11-29 |  |  | 2021-12-13 | 2021-12-13 | 10 | 2021-12-27 | 20 | [5 empty] | 2021-12-27
122423849 | 2527 | PGE | 93307 | NEM | EXPNEM | Study in Progress | Solar PV | 60 |  | 2021-11-29 |  | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2 | 2021-12-01 | 2 | [5 empty] | 2021-12-01 | 2021-12-29 | 20 | 2021-12-29 | [18 empty] | 2021-11-29 |  | 2021-11-29 |  |  | 2021-12-14
122423912 | 2528 | PGE | 93711 | NEM | EXPNEM | Implementation | Solar PV | 40.6 |  | 2021-11-29 |  | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2 | 2021-12-02 | 3 | 2021-12-15 | 9 | [15 empty] | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 2021-12-20 | 3 |  |  |  |  | 2021-11-29 | 2021-12-02 | 2021-11-29 | 2021-12-16 | 13
122424487 | 2529 | PGE | 95695 | NEM | EXPNEM | Application Review in Progress | TRBS | 5000 |  | 2021-11-30 | 2021-12-01 |  | 2021-12-01 | 2021-12-01 | 1
122424808 | 2530 | PGE | 95128 | NEM | EXPNEM | Implementation | Solar PV | 300 |  | 2021-11-30 |  |  | 2021-12-07 | 2021-12-07 | 5 | 2021-12-07 | 5 | 2021-12-21 | 10 | [15 empty] | 2021-12-21 | 2021-12-21 | 0 | 2021-12-21 | 2021-12-24 | 3
122424831 | 2531 | PGE | 93422 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-30 |  |  | 2021-12-01 | 2021-12-01 | 1 | 2021-12-01 | 1 | 2021-12-20 | 13 | [15 empty] | 2021-11-23 | 2021-11-23 |  | 2021-11-23 | 2021-11-23 | 1
122425387 | 2532 | PGE | 95138 | NEM | EXPNEM | IA in Progress | Solar PV | 420 |  | 2021-11-30 |  |  | 2021-12-07 | 2021-12-07 | 5 | 2021-12-07 | 5 | 2021-12-22 | 11 | [15 empty] | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22
122425730 | 2533 | PGE | 93609 | NEM | EXPNEM | Study in Progress | Solar PV | 45.45 |  | 2021-11-30 |  |  | 2021-12-06 | 2021-12-06 | 4 | 2021-12-06 | 4
122426248 | 2534 | PGE | 95123 | NEM | VNEM | Application Review in Progress | Solar PV | 200 |  | 2021-11-30 |  | 2021-12-13 | 2021-12-13 | 2021-12-13 | 9
122426427 | 2535 | PGE | 94556 | Non-NEM | Non-Export | Study in Progress | Solar PV, Storage | 10 |  | 2021-11-30 |  |  | 2021-12-07 | 2021-12-07 | 5 | 2021-12-07 | 5
122426646 | 2536 | PGE | 93311 | NEM | EXPNEM | Application Review in Progress | Solar PV | 187.17 |  | 2021-11-30 |  | 2021-12-01 | 2021-12-01 | 2021-12-01 | 1
122426780 | 2537 | PGE | 93311 | NEM | EXPNEM | Implementation | Solar PV | 100.107 |  | 2021-11-30 |  |  | 2021-12-01 | 2021-12-01 | 1 | 2021-12-01 | 1 | 2021-12-15 | 10 | [15 empty] | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 2021-12-23 | 6 | [5 empty] | 2021-12-21 | 2021-12-21
122427042 | 2538 | PGE | 94022 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.16 |  | 2021-11-30 |  | 2021-12-09 | 2021-12-02 | 2021-12-02 | 2
122427571 | 2539 | PGE | 93610 | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-11-30 |  |  | 2021-12-02 | 2021-12-02 | 2 | 2021-12-02 | 2 | 2021-12-20 | 12 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | 2021-12-27 | 5 |  |  |  |  | 2021-11-30 | 2021-12-03 | 2021-11-30 | 2021-12-16 | 12
122428356 | 2540 | PGE | 95540 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-11-30 |  |  | 2021-12-10 | 2021-12-10 | 8 | 2021-12-10 | 8 | 2021-12-13 | 1 | [15 empty] | 2021-11-30 | 2021-11-30 |  | 2021-11-30 | 2021-11-30 | 1
122428694 | 2541 | PGE | 94070 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.913 |  | 2021-11-30 |  | 2021-12-17 | 2021-12-02 | 2021-12-02 | 2
122429666 | 2542 | PGE | 93460 | NEM | EXPNEM | Study in Progress | Solar PV | 39.027 |  | 2021-12-01 |  | 2021-12-07 | 2021-12-07 | 2021-12-07 | 4 | 2021-12-15 | 10 | [27 empty] | 2021-12-01 |  | 2021-12-01 |  |  | 2021-12-15
122429895 | 2543 | PGE | 95249 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 44.173 |  | 2021-12-01 |  | 2021-12-15 | 2021-12-15 | 2021-12-15 | 10 | 2021-12-27 | 18 | [27 empty] | 2021-12-01 |  | 2021-12-01
122429963 | 2544 | PGE | 95249 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 35.22 |  | 2021-12-01 |  | 2021-12-15 | 2021-12-15 | 2021-12-15 | 10 | 2021-12-27 | 18 | [27 empty] | 2021-12-01 |  | 2021-12-01
122430264 | 2545 | PGE | 95320 | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 |  | 2021-12-01 |  | 2021-12-15 | 2021-12-15 | 2021-12-15 | 10 | [29 empty] | 2021-12-01 |  | 2021-12-01 |  |  | 2021-12-15
122430318 | 2546 | PGE | 93420 | Non-NEM | Non-Export | Application Accepted | ENGN, Storage | 1530 |  | 2021-12-01 | 2021-12-02 |  | 2021-12-02 | 2021-12-02 | 1 | 2021-12-15 | 10 | [27 empty] | 2021-12-01 |  | 2021-12-01
122430762 | 2547 | PGE | 93711 | NEM | EXPNEM | Application Review in Progress | Solar PV | 81.78 |  | 2021-12-01 |  | 2021-12-07 | 2021-12-03 | 2021-12-03 | 2
122431149 | 2548 | PGE | 95037 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 53.188 |  | 2021-12-01 |  | 2021-12-15 | 2021-12-15 | 2021-12-15 | 10 | 2021-12-27 | 18 | [27 empty] | 2021-12-01 |  | 2021-12-01
122431177 | 2549 | PGE | 95365 | NEM | EXPNEM | Application Review in Progress | Solar PV | 133.2 |  | 2021-12-01 |  | 2021-12-15 | 2021-12-03 | 2021-12-03 | 2 | [29 empty] | 2021-12-01 |  | 2021-12-01
122431320 | 2550 | PGE | 95037 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 34.179 |  | 2021-12-01 |  | 2021-12-15 | 2021-12-15 | 2021-12-15 | 10 | 2021-12-27 | 18 | [27 empty] | 2021-12-01 |  | 2021-12-01
122431381 | 2551 | PGE | 93611 | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.2 |  | 2021-12-01 |  | 2021-12-06 | 2021-12-06 | 2021-12-06 | 3 | [29 empty] | 2021-12-01 |  | 2021-12-01
122432133 | 2552 | PGE | 94027 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.131 |  | 2021-12-01 |  | 2021-12-29 | 2021-12-01 | 2021-12-01 | 0
122432178 | 2553 | PGE | 95642 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-12-01 | 2021-12-10 |  | 2021-12-10 | 2021-12-10 | 7 | 2021-12-10 | 7 | 2021-12-29 | 13 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29
122432402 | 2554 | PGE | 94526 | Non-NEM | Inadvertent Export | Commercial | Storage | 5 |  | 2021-12-01 |  |  | 2021-12-07 | 2021-12-07 | 4 | 2021-12-07 | 4 | 2021-12-21 | 10 | [15 empty] | 2021-12-01 | 2021-12-01 |  | 2021-12-01 | 2021-12-01 | 1 | [34 empty] | 2021-12-01 |  | 2021-12-21 | 15
122436825 | 2555 | PGE | 95668 | NEM | EXPNEM | Study in Progress | Solar PV | 66.6 |  | 2021-12-02 |  | 2021-12-03 | 2021-12-03 | 2021-12-03 | 1 | 2021-12-15 | 9 | 2021-12-29 | 10 | 2021-12-29 | [24 empty] | 2021-12-14 | 2021-12-15 | 2021-12-14
122436929 | 2556 | PGE | 94551 | NEM | EXPNEM | IA in Progress | Solar PV | 471.432 |  | 2021-12-02 |  |  | 2021-12-16 | 2021-12-16 | 10 | 2021-12-16 | 10 | 2021-12-31 | 11 | [15 empty] | 2021-12-31 | [9 empty] | 2021-12-02 | 2021-12-16 | 2021-12-02
122437076 | 2557 | PGE | 93245 | NEM | EXPNEM | Application Review in Progress | Solar PV | 44.006 |  | 2021-12-02 |  | 2021-12-17 | 2021-12-03 | 2021-12-03 | 1 | [29 empty] | 2021-12-02 |  | 2021-12-02
122437987 | 2558 | PGE | 95932 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 58.705 |  | 2021-12-02 |  | 2021-12-14 | 2021-12-14 | 2021-12-14 | 8 | [29 empty] | 2021-12-02 |  | 2021-12-02 |  |  | 2021-12-14
122438015 | 2559 | PGE | 95932 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 59.281 |  | 2021-12-02 |  | 2021-12-14 | 2021-12-14 | 2021-12-14 | 8 | [29 empty] | 2021-12-02 |  | 2021-12-02 |  |  | 2021-12-14
122438038 | 2560 | PGE | 95932 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 70.44 |  | 2021-12-02 |  | 2021-12-14 | 2021-12-14 | 2021-12-14 | 8 | [29 empty] | 2021-12-02 |  | 2021-12-02 |  |  | 2021-12-15
122438360 | 2561 | PGE | 95682 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 643.5 |  | 2021-12-02 | 2021-12-09 |  | 2021-12-09 | 2021-12-09 | 5 | 2021-12-29 | 19
122438529 | 2562 | PGE | 93311 | NEM | EXPNEM | Study in Progress | Solar PV | 400.816 |  | 2021-12-02 |  |  | 2021-12-07 | 2021-12-07 | 3 | 2021-12-07 | 3 | [27 empty] | 2021-12-02 |  | 2021-12-02 |  |  | 2021-12-15
122438576 | 2563 | PGE | 95131 | NEM | EXPNEM | IA in Progress | Solar PV | 476.175 |  | 2021-12-02 |  |  | 2021-12-06 | 2021-12-06 | 2 | 2021-12-06 | 2 | 2021-12-20 | 10 | [15 empty] | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | [6 empty] | 2021-12-02 |  | 2021-12-02
122438919 | 2564 | PGE | 93436 | NEM | EXPNEM | Study in Progress | Solar PV | 200.408 |  | 2021-12-02 |  |  | 2021-12-08 | 2021-12-08 | 4 | 2021-12-08 | 4 | [5 empty] | 2021-12-08 | [21 empty] | 2021-12-02 |  | 2021-12-02 |  |  | 2021-12-15
122438938 | 2565 | PGE | 95519 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 10 |  | 2021-12-02 | 2021-12-06 |  | 2021-12-06 | 2021-12-06 | 2
122439011 | 2566 | PGE | 93662 | NEM | VNEMSOMAH | IA in Progress | Solar PV | 31.381 |  | 2021-12-02 |  | 2021-12-07 | 2021-12-07 | 2021-12-07 | 3 | 2021-12-10 | 6 | 2021-12-31 | 15 | [15 empty] | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | [6 empty] | 2021-12-02 | 2021-12-23 | 2021-12-02 | 2021-12-27 | 17
122439161 | 2567 | PGE | 95569 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 15 |  | 2021-12-02 |  |  | 2021-12-16 | 2021-12-16 | 10 | 2021-12-16 | 10 | 2021-12-24 | 6 | [15 empty] | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16
122442441 | 2568 | PGE | 93940 | NEM | EXPNEM | Study in Progress | Solar PV | 43.78 |  | 2021-12-03 |  |  | 2021-12-17 | 2021-12-17 | 10 | 2021-12-17 | 10
122442449 | 2569 | PGE | 95677 | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 |  | 2021-12-03 |  | 2021-12-17 | 2021-12-17 | 2021-12-17 | 10
122442458 | 2570 | PGE | 95945 | NEM | VNEM | Application Review in Progress | Solar PV | 46.32 |  | 2021-12-03 |  | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2
122442689 | 2571 | PGE | 95134 | NEM | EXPNEM | IA in Progress | Solar PV | 467.322 |  | 2021-12-03 |  |  | 2021-12-07 | 2021-12-07 | 2 | 2021-12-07 | 2 | 2021-12-23 | 12 | [15 empty] | 2021-12-23 | [9 empty] | 2021-12-03 |  | 2021-12-03
122443031 | 2572 | PGE | 95963 | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2021-12-03 |  | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2 | 2021-12-10 | 5 | 2021-12-29 | 13 | 2021-12-29
122443211 | 2573 | PGE | 95963 | NEM | EXPNEM | Study in Progress | Solar PV | 241.711 |  | 2021-12-03 |  | 2021-12-10 | 2021-12-07 | 2021-12-07 | 2 | 2021-12-13 | 6 | 2021-12-29 | 12 | 2021-12-29
122443347 | 2574 | PGE | 94611 | Non-NEM | Non-Export | Study in Progress | HYDR | 29.84 |  | 2021-12-03 |  |  | 2021-12-07 | 2021-12-07 | 2 | 2021-12-07 | 2
122443437 | 2575 | PGE | 94063 | NEM | EXPNEM | Study in Progress | Solar PV | 299.7 |  | 2021-12-03 |  | 2021-12-06 | 2021-12-06 | 2021-12-06 | 1 | 2021-12-22 | 13
122443619 | 2576 | PGE | 95963 | NEM | EXPNEM | Study in Progress | Solar PV | 491.397 |  | 2021-12-03 |  | 2021-12-10 | 2021-12-07 | 2021-12-07 | 2 | 2021-12-13 | 6 | 2021-12-29 | 12 | 2021-12-29 | [24 empty] | 2021-12-03 | 2021-12-13 | 2021-12-03 | 2021-12-29 | 18
122443649 | 2577 | PGE | 95037 | NEM | EXPNEM | Withdrawn | Solar PV | 360 |  | 2021-12-03 |  |  | 2021-12-10 | 2021-12-10 | 5 | 2021-12-10 | 5
122443747 | 2578 | PGE | 95963 | NEM | EXPNEM | Study in Progress | Solar PV | 693.907 |  | 2021-12-03 |  | 2021-12-10 | 2021-12-07 | 2021-12-07 | 2 | 2021-12-15 | 8 | 2021-12-29 | 10 | 2021-12-29 | [24 empty] | 2021-12-03 | 2021-12-15 | 2021-12-03
122443886 | 2579 | PGE | 94403 | NEM | EXPNEM | Application Review in Progress | Solar PV | 703.235 |  | 2021-12-03 |  | 2021-12-13 | 2021-12-13 | 2021-12-13 | 6
122443937 | 2580 | PGE | 95521 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 10 |  | 2021-12-03 | 2021-12-06 |  | 2021-12-06 | 2021-12-06 | 1
122444072 | 2581 | PGE | 95963 | NEM | EXPNEM | Application Review in Progress | Solar PV | 72.622 |  | 2021-12-03 |  | 2021-12-17 | 2021-12-17 | 2021-12-17 | 10
122444142 | 2582 | PGE | 94530 | NEM | EXPNEM | Study in Progress | Solar PV | 149.464 |  | 2021-12-03 |  |  | 2021-12-06 | 2021-12-06 | 1 | 2021-12-06 | 1 | [28 empty] | 2021-12-17 | 2021-12-17
122444202 | 2583 | PGE | 95688 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 36.423 |  | 2021-12-03 |  | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2
122444448 | 2584 | PGE | 95521 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-12-03 |  |  | 2021-12-16 | 2021-12-16 | 9 | 2021-12-16 | 9
122444622 | 2585 | PGE | 93420 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-12-04 |  |  | 2021-12-14 | 2021-12-14 | 6 | 2021-12-14 | 6 | 2021-12-30 | 12
122445477 | 2586 | PGE | 94611 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-12-04 | 2021-12-17 |  | 2021-12-17 | 2021-12-17 | 9 | 2021-12-27 | 15 | [17 empty] | 2021-12-03 | 2021-12-03 |  | 2021-12-03 | 2021-12-04 | 1
122445478 | 2587 | PGE | 95626 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 31.423 |  | 2021-12-04 |  |  | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 0 | 2021-12-29 | 17
122445805 | 2588 | PGE | 93422 | Non-NEM | Inadvertent Export | Withdrawn | Solar PV, Storage | 10 |  | 2021-12-04 | 2021-12-07 |  | 2021-12-07 | 2021-12-07 | 1
122445812 | 2589 | PGE | 93426 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-12-04 |  |  | 2021-12-17 | 2021-12-17 | 9 | 2021-12-17 | 9 | 2021-12-27 | 6 | [15 empty] | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27 | 2021-12-27 | 0
122446314 | 2590 | PGE | 95973 | NEM | EXPNEM | Study in Progress | Solar PV | 187.5 |  | 2021-12-05 |  |  | 2021-12-10 | 2021-12-10 | 4 | 2021-12-10 | 4 | 2021-12-29 | 13 | 2021-12-29 | [24 empty] | 2021-12-17 |  | 2021-12-17
122446357 | 2591 | PGE | 95973 | NEM | EXPNEM | Study in Progress | Solar PV | 187.5 |  | 2021-12-05 |  |  | 2021-12-10 | 2021-12-10 | 4 | 2021-12-10 | 4 | 2021-12-29 | 13 | 2021-12-29 | [24 empty] | 2021-12-17 |  | 2021-12-17
122446562 | 2592 | PGE | 94565 | Non-NEM | Non-Export | Withdrawn | Solar PV, Storage | 5.76 |  | 2021-12-05 | 2021-12-17 |  | 2021-12-17 | 2021-12-17 | 9
122447430 | 2593 | PGE | 93933 | NEM | EXPNEM | Study in Progress | Solar PV | 75 |  | 2021-12-06 |  | 2021-12-20 | 2021-12-20 | 2021-12-20 | 10 | 2021-12-27 | 15
122447589 | 2594 | PGE | 94403 | NEM | EXPNEM | Study in Progress | Solar PV | 124.395 |  | 2021-12-06 |  |  | 2021-12-20 | 2021-12-20 | 10 | 2021-12-20 | 10
122447594 | 2595 | PGE | 94403 | NEM | EXPNEM | Study in Progress | Solar PV | 150 |  | 2021-12-06 |  |  | 2021-12-20 | 2021-12-20 | 10 | 2021-12-20 | 10
122447652 | 2596 | PGE | 94402 | NEM | EXPNEM | Study in Progress | Solar PV | 199.8 |  | 2021-12-06 |  |  | 2021-12-20 | 2021-12-20 | 10 | 2021-12-20 | 10
122447742 | 2597 | PGE | 94403 | NEM | EXPNEM | Study in Progress | Solar PV | 120.046 |  | 2021-12-06 |  |  | 2021-12-10 | 2021-12-10 | 4 | 2021-12-10 | 4 | 2021-12-28 | 12 | 2021-12-20
122447774 | 2598 | PGE | 93933 | NEM | EXPNEM | Application Accepted | Solar PV | 115.42 |  | 2021-12-06 |  | 2021-12-07 | 2021-12-06 | 2021-12-06 | 0 | 2021-12-07 | 1 | [27 empty] | 2021-12-06 |  | 2021-12-06
122447830 | 2599 | PGE | 94401 | NEM | EXPNEM | Study in Progress | Solar PV | 166.5 |  | 2021-12-06 |  |  | 2021-12-10 | 2021-12-10 | 4 | 2021-12-10 | 4
122447852 | 2600 | PGE | 95134 | NEM | EXPNEM | Study in Progress | Solar PV | 626 |  | 2021-12-06 |  |  | 2021-12-20 | 2021-12-20 | 10 | 2021-12-20 | 10 | [27 empty] | 2021-12-06 |  | 2021-12-06
122447854 | 2601 | PGE | 95023 | NEM | EXPNEM | Study in Progress | Solar PV | 437.5 |  | 2021-12-06 |  |  | 2021-12-07 | 2021-12-07 | 1 | 2021-12-07 | 1 | 2021-12-22 | 11 | 2021-12-22 | [24 empty] | 2021-12-06 | 2021-12-07 | 2021-12-06 | 2021-12-16 | 8
122447890 | 2602 | PGE | 94402 | NEM | EXPNEM | IA in Progress | Solar PV | 150 |  | 2021-12-06 |  |  | 2021-12-10 | 2021-12-10 | 4 | 2021-12-10 | 4 | 2021-12-21 | 7 | [15 empty] | 2021-12-21
122447961 | 2603 | PGE | 94401 | NEM | EXPNEM | Study in Progress | Solar PV | 187.5 |  | 2021-12-06 |  |  | 2021-12-08 | 2021-12-08 | 2 | 2021-12-09 | 3
122448335 | 2604 | PGE | 93204 | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 |  | 2021-12-06 |  | 2021-12-07 | 2021-12-07 | 2021-12-07 | 1
122448639 | 2605 | PGE | 93446 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-12-06 |  |  | 2021-12-07 | 2021-12-07 | 1 | 2021-12-07 | 1 | 2021-12-23 | 12 | [15 empty] | 2021-12-06 | 2021-12-06 |  | 2021-12-06 | 2021-12-06 | 1
122448921 | 2606 | PGE | 93307 | NEM | EXPNEM | IA in Progress | Solar PV | 75.259 |  | 2021-12-06 |  | 2021-12-07 | 2021-12-07 | 2021-12-07 | 1 | 2021-12-15 | 7 | 2021-12-29 | 10 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29
122448974 | 2607 | PGE | 93637 | NEM | EXPNEM | IA in Progress | Solar PV | 39.899 |  | 2021-12-06 |  |  | 2021-12-08 | 2021-12-08 | 2 | 2021-12-08 | 2 | 2021-12-23 | 11 | [15 empty] | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23
122449098 | 2608 | PGE | 95685 | NEM | VNEM | Study in Progress | Solar PV | 45.661 |  | 2021-12-06 |  | 2021-12-07 | 2021-12-07 | 2021-12-07 | 1 | 2021-12-31 | 19
122449348 | 2609 | PGE | 93704 | NEM | EXPNEM | IA in Progress | Solar PV | 179.156 |  | 2021-12-06 |  | 2021-12-08 | 2021-12-08 | 2021-12-08 | 2 | 2021-12-20 | 10 | 2021-12-29 | 7 | [15 empty] | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | [6 empty] | 2021-12-06 | 2021-12-20 | 2021-12-06
122449399 | 2610 | PGE | 95065 | NEM | EXPNEM | Study in Progress | Solar PV | 63.722 |  | 2021-12-06 |  |  | 2021-12-08 | 2021-12-08 | 2 | 2021-12-08 | 2
122449427 | 2611 | PGE | 93960 | NEM | EXPNEM | Study in Progress | Solar PV | 801.632 |  | 2021-12-06 |  |  | 2021-12-08 | 2021-12-08 | 2 | 2021-12-08 | 2 | [5 empty] | 2021-12-15
122449600 | 2612 | PGE | 95073 | NEM | EXPNEM | Study in Progress | Solar PV | 64.88 |  | 2021-12-06 |  |  | 2021-12-08 | 2021-12-08 | 2 | 2021-12-08 | 2
122449792 | 2613 | PGE | 94568 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 687.611 |  | 2021-12-06 |  | 2021-12-16 | 2021-12-16 | 2021-12-16 | 8 | [29 empty] | 2021-12-06 |  | 2021-12-06
122449844 | 2614 | PGE | 93660 | Non-NEM | RESBCT | Study in Progress | Solar PV | 988.418 |  | 2021-12-06 | 2021-12-10 |  | 2021-12-06 | 2021-12-06 | 0 | 2021-12-22 | 12 | [5 empty] | 2021-12-22
122449967 | 2615 | PGE | 93638 | NEM | EXPNEM | Application Review in Progress | Solar PV | 166.5 |  | 2021-12-06 |  | 2021-12-10 | 2021-12-10 | 2021-12-10 | 4
122450247 | 2616 | PGE | 93622 | NEM | EXPNEM | Application Review in Progress | Solar PV | 972.915 |  | 2021-12-06 | 2021-12-07 |  | 2021-12-07 | 2021-12-07 | 1 | [29 empty] | 2021-12-06 |  | 2021-12-06
122450295 | 2617 | PGE | 95133 | NEM | EXPNEM | IA in Progress | Solar PV | 126.414 |  | 2021-12-06 |  | 2021-12-08 | 2021-12-08 | 2021-12-08 | 2 | 2021-12-08 | 2 | 2021-12-24 | 12 | [15 empty] | 2021-12-24 | 2021-12-24 | 0 | 2021-12-24
122450330 | 2618 | PGE | 95033 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.729 |  | 2021-12-06 |  | 2021-12-08 | 2021-12-08 | 2021-12-08 | 2
122452405 | 2619 | PGE | 95376 | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 |  | 2021-12-07 |  | 2021-12-21 | 2021-12-21 | 2021-12-21 | 10
122452774 | 2620 | PGE | 95361 | NEM | EXPNEM | Application Accepted | Solar PV | 245.198 |  | 2021-12-07 |  | 2021-12-13 | 2021-12-10 | 2021-12-10 | 3 | 2021-12-10 | 3
122452790 | 2621 | PGE | 94609 | NEM | EXPNEM | Application Review in Progress | Solar PV | 44.884 |  | 2021-12-07 |  | 2021-12-20 | 2021-12-20 | 2021-12-20 | 9
122453032 | 2622 | PGE | 95361 | NEM | EXPNEM | Application Review in Progress | Solar PV | 83.3 |  | 2021-12-07 |  | 2021-12-10 | 2021-12-10 | 2021-12-10 | 3
122453152 | 2623 | PGE | 95134 | NEM | EXPNEM | Application Review in Progress | Solar PV | 540 |  | 2021-12-07 |  | 2021-12-20 | 2021-12-20 | 2021-12-20 | 9 | [29 empty] | 2021-12-07 |  | 2021-12-07
122453230 | 2624 | PGE | 95361 | NEM | EXPNEM | Application Accepted | Solar PV | 33.3 |  | 2021-12-07 |  | 2021-12-13 | 2021-12-10 | 2021-12-10 | 3 | 2021-12-10 | 3
122453342 | 2625 | PGE | 95134 | NEM | EXPNEM | Study in Progress | Solar PV | 852 |  | 2021-12-07 |  |  | 2021-12-21 | 2021-12-21 | 10 | 2021-12-21 | 10 | [27 empty] | 2021-12-07 |  | 2021-12-07
122453649 | 2626 | PGE | 94574 | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.857 |  | 2021-12-07 |  |  | 2021-12-07 | 2021-12-07 | 0 | 2021-12-09 | 2 | 2021-12-09 | 0 | [34 empty] | 2021-12-16 | 2021-12-16 | 0 | [15 empty] | 2021-12-16 |  |  | 2021-12-16 |  | 2021-12-16 | 0
122453826 | 2627 | PGE | 93610 | NEM | EXPNEM | Study in Progress | Solar PV | 660 |  | 2021-12-07 |  |  | 2021-12-10 | 2021-12-10 | 3 | 2021-12-13 | 4
122454118 | 2628 | PGE | 95926 | NEM | EXPNEM | Application Review in Progress | Solar PV | 875 |  | 2021-12-07 |  | 2021-12-27 | 2021-12-08 | 2021-12-08 | 1 | [29 empty] | 2021-12-07 |  | 2021-12-07
122454355 | 2629 | PGE | 93420 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-12-07 |  |  | 2021-12-08 | 2021-12-08 | 1 | 2021-12-08 | 1 | 2021-12-24 | 12
122454852 | 2630 | PGE | 95073 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 40.175 |  | 2021-12-08 |  | 2021-12-09 | 2021-12-09 | 2021-12-09 | 1
122455078 | 2631 | PGE | 93304 | NEM | EXPNEM | Study in Progress | Solar PV | 150 |  | 2021-12-08 |  |  | 2021-12-22 | 2021-12-22 | 10 | 2021-12-22 | 10
122455092 | 2632 | PGE | 95695 | NEM | EXPNEM | Study in Progress | Solar PV | 31.92 |  | 2021-12-08 |  |  | 2021-12-14 | 2021-12-14 | 4 | 2021-12-14 | 4 | [27 empty] | 2021-12-08 |  | 2021-12-08 |  |  | 2021-12-15
122455318 | 2633 | PGE | 93401 | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2021-12-08 |  |  | 2021-12-09 | 2021-12-09 | 1 | 2021-12-09 | 1
122455481 | 2634 | PGE | 93280 | NEM | EXPNEM | Study in Progress | Solar PV | 501.02 |  | 2021-12-08 |  |  | 2021-12-14 | 2021-12-14 | 4 | 2021-12-16 | 6
122455535 | 2635 | PGE | 93304 | NEM | EXPNEM | Application Review in Progress | Solar PV | 73.553 |  | 2021-12-08 |  | 2021-12-08 | 2021-12-08 | 2021-12-08 | 0
122455701 | 2636 | PGE | 93405 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-12-08 |  |  | 2021-12-14 | 2021-12-14 | 4 | 2021-12-14 | 4 | 2021-12-29 | 11
122455818 | 2637 | PGE | 93638 | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2021-12-08 |  |  | 2021-12-09 | 2021-12-09 | 1 | 2021-12-10 | 2 | 2021-12-23 | 9 | 2021-12-23 | [24 empty] | 2021-12-10 | 2021-12-13 | 2021-12-10
122455972 | 2638 | PGE | 95928 | NEM | EXPNEM | Application Review in Progress | Solar PV | 261 |  | 2021-12-08 |  | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2
122456058 | 2639 | PGE | 95492 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 36.3 |  | 2021-12-08 |  | 2021-12-28 | 2021-12-09 | 2021-12-09 | 1
122456319 | 2640 | PGE | 95338 | NEM | EXPNEM | Study in Progress | Solar PV | 36 |  | 2021-12-08 |  |  | 2021-12-21 | 2021-12-21 | 9 | 2021-12-21 | 9 | [27 empty] | 2021-12-08 | 2021-12-21 | 2021-12-08
122456331 | 2641 | PGE | 93654 | NEM | NEMMT | Study in Progress | ENGN, Solar PV, Storage | 2744.5 |  | 2021-12-08 | 2021-12-09 |  | 2021-12-09 | 2021-12-09 | 1 | 2021-12-29 | 15 | [5 empty] | 2021-12-29 | [21 empty] | 2021-12-08 |  | 2021-12-08
122456400 | 2642 | PGE | 94103 | Non-NEM | Inadvertent Export | Application Review in Progress | Solar PV | 130.635 |  | 2021-12-08 | 2021-12-21 |  | 2021-12-21 | 2021-12-21 | 9
122456505 | 2643 | PGE | 94530 | NEM | EXPNEM | Study in Progress | Solar PV | 53.35 |  | 2021-12-08 |  |  | 2021-12-22 | 2021-12-22 | 10 | 2021-12-22 | 10 | [27 empty] | 2021-12-08 |  | 2021-12-08
122456508 | 2644 | PGE | 94539 | NEM | EXPNEM | Study in Progress | Solar PV | 49.692 |  | 2021-12-08 |  |  | 2021-12-22 | 2021-12-22 | 10 | 2021-12-22 | 10
122456625 | 2645 | PGE | 94598 | Non-NEM | Non-Export | Application Review in Progress | Storage | 7.68 |  | 2021-12-08 | 2021-12-09 |  | 2021-12-09 | 2021-12-09 | 1
122456683 | 2646 | PGE | 94577 | NEM | EXPNEM | Study in Progress | Solar PV | 39.832 |  | 2021-12-08 |  |  | 2021-12-13 | 2021-12-13 | 3 | 2021-12-13 | 3
122456703 | 2647 | PGE | 95320 | NEM | EXPNEM | Study in Progress | Solar PV | 840 |  | 2021-12-08 |  |  | 2021-12-13 | 2021-12-13 | 3 | 2021-12-13 | 3
122456753 | 2648 | PGE | 94559 | NEM | EXPNEM | Study in Progress | Solar PV | 360 |  | 2021-12-08 |  |  | 2021-12-13 | 2021-12-13 | 3 | 2021-12-13 | 3 | [27 empty] | 2021-12-08 |  | 2021-12-08 |  |  | 2021-12-15
122456927 | 2649 | PGE | 93401 | NEM | VNEM | Application Review in Progress | Solar PV | 68.13 |  | 2021-12-08 |  | 2021-12-13 | 2021-12-10 | 2021-12-10 | 2
122456934 | 2650 | PGE | 95242 | NEM | EXPNEM | Application Review in Progress | Solar PV | 333 |  | 2021-12-08 |  | 2021-12-22 | 2021-12-22 | 2021-12-22 | 10
122457180 | 2651 | PGE | 95215 | NEM | EXPNEM | Application Review in Progress | Solar PV | 576 |  | 2021-12-08 |  | 2021-12-15 | 2021-12-15 | 2021-12-15 | 5
122457537 | 2652 | PGE | 95215 | NEM | EXPNEM | Application Review in Progress | Solar PV | 360 |  | 2021-12-08 |  | 2021-12-14 | 2021-12-14 | 2021-12-14 | 4
122457539 | 2653 | PGE | 93301 | NEM | EXPNEM | IA in Progress | Solar PV | 185.259 |  | 2021-12-08 |  |  | 2021-12-10 | 2021-12-10 | 2 | 2021-12-10 | 2 | 2021-12-20 | 6 | [15 empty] | 2021-12-20
122458016 | 2654 | PGE | 94124 | Non-NEM | Continuous Uncompensated Export | Application Review in Progress | Solar PV | 26.59 |  | 2021-12-08 | 2021-12-22 |  | 2021-12-22 | 2021-12-22 | 10
122458042 | 2655 | PGE | 95476 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 31.743 |  | 2021-12-08 |  |  | 2021-12-09 | 2021-12-09 | 1 | 2021-12-09 | 1 | 2021-12-09 | 0 | [25 empty] | 2021-12-08 |  | 2021-12-08
122458061 | 2656 | PGE | 95482 | NEM | EXPNEM | Application Review in Progress | Solar PV | 655.386 |  | 2021-12-08 |  | 2021-12-22 | 2021-12-22 | 2021-12-22 | 10
122458063 | 2657 | PGE | 95076 | NEM | EXPNEM | Withdrawn | Solar PV | 625 |  | 2021-12-08
122458072 | 2658 | PGE | 94515 | NEM | EXPNEM | Application Review in Progress | Solar PV | 127.882 |  | 2021-12-08 |  | 2021-12-20 | 2021-12-20 | 2021-12-20 | 8 | [29 empty] | 2021-12-08 |  | 2021-12-08
122458109 | 2659 | PGE | 95926 | NEM | EXPNEM | Application Review in Progress | Solar PV | 875 |  | 2021-12-08 |  | 2021-12-21 | 2021-12-21 | 2021-12-21 | 9 | [29 empty] | 2021-12-08 | 2021-12-21 | 2021-12-08
122458132 | 2660 | PGE | 95482 | NEM | EXPNEM | Application Review in Progress | Solar PV | 346.047 |  | 2021-12-08 |  | 2021-12-22 | 2021-12-22 | 2021-12-22 | 10
122458155 | 2661 | PGE | 95973 | NEM | EXPNEM | Study in Progress | Solar PV | 875 |  | 2021-12-08 |  |  | 2021-12-21 | 2021-12-21 | 9 | 2021-12-21 | 9 | [27 empty] | 2021-12-08 |  | 2021-12-08
122458174 | 2662 | PGE | 96080 | NEM | EXPNEM | Application Review in Progress | Solar PV | 437.5 |  | 2021-12-08 |  | 2021-12-21 | 2021-12-21 | 2021-12-21 | 9 | [29 empty] | 2021-12-08 | 2021-12-21 | 2021-12-08
122458192 | 2663 | PGE | 95938 | NEM | EXPNEM | Application Review in Progress | Solar PV | 500 |  | 2021-12-08 |  | 2021-12-22 | 2021-12-22 | 2021-12-22 | 10 | [29 empty] | 2021-12-08 | 2021-12-22 | 2021-12-08
122458202 | 2664 | PGE | 94087 | NEM | EXPNEM | Study in Progress | Solar PV | 157.519 |  | 2021-12-08 |  | 2021-12-22 | 2021-12-22 | 2021-12-22 | 10 | 2021-12-28 | 14
122459247 | 2665 | PGE | 93280 | NEM | EXPNEM | Study in Progress | Solar PV | 150 |  | 2021-12-09 |  | 2021-12-13 | 2021-12-13 | 2021-12-13 | 2 | 2021-12-14 | 3 | [5 empty] | 2021-12-14 | [21 empty] | 2021-12-09 | 2021-12-14 | 2021-12-09
122459681 | 2666 | PGE | 95758 | Non-NEM | RESBCT | Withdrawn | Solar PV | 5000 |  | 2021-12-09
122459689 | 2667 | PGE | 94087 | NEM | EXPNEM | IA in Progress | Solar PV | 211.572 |  | 2021-12-09 |  |  | 2021-12-15 | 2021-12-15 | 4 | 2021-12-15 | 4 | 2021-12-29 | 10 | [15 empty] | 2021-12-29
122459754 | 2668 | PGE | 93401 | NEM | EXPNEM | Study in Progress | Solar PV | 101.249 |  | 2021-12-09 |  |  | 2021-12-15 | 2021-12-15 | 4 | 2021-12-15 | 4
122459824 | 2669 | PGE | 95962 | Non-NEM | RESBCT | IA in Progress | HYDR | 1275 |  | 2021-12-02 |  |  | 2021-12-03 | 2021-12-03 | 1 | 2021-12-07 | 3 | [17 empty] | 2021-12-07 | 2021-12-10 | 3 | 2021-12-10
122459978 | 2670 | PGE | 95076 | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 |  | 2021-12-09 |  | 2021-12-14 | 2021-12-13 | 2021-12-13 | 2
122460351 | 2671 | PGE | 95060 | NEM | EXPNEM | Study in Progress | Solar PV | 43.2 |  | 2021-12-09 |  | 2021-12-14 | 2021-12-14 | 2021-12-14 | 3 | 2021-12-20 | 7
122460452 | 2672 | PGE | 95207 | NEM | VNEM | Study in Progress | Solar PV | 300 |  | 2021-12-09 |  | 2021-12-13 | 2021-12-13 | 2021-12-13 | 2 | 2021-12-31 | 16
122460636 | 2673 | PGE | 93725 | NEM | EXPNEM | Application Accepted | Solar PV | 1500 |  | 2021-12-09 | 2021-12-13 |  | 2021-12-13 | 2021-12-13 | 2 | 2021-12-22 | 9
122460817 | 2674 | PGE | 95688 | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-12-09 |  | 2021-12-13 | 2021-12-13 | 2021-12-13 | 2 | 2021-12-15 | 4 | 2021-12-30 | 11 | [15 empty] | 2021-12-30
122460882 | 2675 | PGE | 94062 | NEM | EXPNEM | Application Review in Progress | Solar PV | 517.216 |  | 2021-12-09 |  | 2021-12-14 | 2021-12-14 | 2021-12-14 | 3
122461042 | 2676 | PGE | 95119 | NEM | EXPNEM | IA in Progress | Solar PV | 83.3 |  | 2021-12-09 |  |  | 2021-12-15 | 2021-12-15 | 4 | 2021-12-15 | 4 | 2021-12-30 | 11 | [15 empty] | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30
122461054 | 2677 | PGE | 95688 | NEM | EXPNEM | Study in Progress | Solar PV | 120 |  | 2021-12-09 |  |  | 2021-12-23 | 2021-12-23 | 10 | 2021-12-23 | 10
122461188 | 2678 | PGE | 95687 | NEM | EXPNEM | Study in Progress | Solar PV | 170 |  | 2021-12-09 |  |  | 2021-12-23 | 2021-12-23 | 10 | 2021-12-23 | 10
122461471 | 2679 | PGE | 93706 | NEM | EXPNEM | IA in Progress | Solar PV | 57.687 |  | 2021-12-09 |  | 2021-12-14 | 2021-12-13 | 2021-12-13 | 2 | 2021-12-16 | 5 | 2021-12-22 | 4 | [15 empty] | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22
122461563 | 2680 | PGE | 95112 | NEM | EXPNEM | Application Review in Progress | Solar PV | 75 |  | 2021-12-09 |  | 2021-12-15 | 2021-12-15 | 2021-12-15 | 4 | [29 empty] | 2021-12-09 |  | 2021-12-09
122461885 | 2681 | PGE | 94063 | NEM | EXPNEM | Application Review in Progress | Solar PV | 322.016 |  | 2021-12-09 |  | 2021-12-17 | 2021-12-17 | 2021-12-17 | 6
122462120 | 2682 | PGE | 95688 | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2021-12-09 |  |  | 2021-12-13 | 2021-12-13 | 2 | 2021-12-15 | 4 | 2021-12-30 | 11 | [15 empty] | 2021-12-30
122462129 | 2683 | PGE | 95688 | NEM | EXPNEM | IA in Progress | Solar PV | 96 |  | 2021-12-09 |  | 2021-12-10 | 2021-12-10 | 2021-12-10 | 1 | 2021-12-13 | 2 | 2021-12-29 | 12 | [15 empty] | 2021-12-29
122462191 | 2684 | PGE | 95688 | NEM | EXPNEM | Study in Progress | Solar PV | 156 |  | 2021-12-09 |  |  | 2021-12-23 | 2021-12-23 | 10 | 2021-12-23 | 10
122462263 | 2685 | PGE | 95687 | NEM | EXPNEM | Study in Progress | Solar PV | 120 |  | 2021-12-09 |  |  | 2021-12-23 | 2021-12-23 | 10 | 2021-12-23 | 10
122462557 | 2686 | PGE | 95131 | NEM | EXPNEM | IA in Progress | Solar PV | 133.2 |  | 2021-12-09 |  |  | 2021-12-15 | 2021-12-15 | 4 | 2021-12-15 | 4 | 2021-12-31 | 12 | [15 empty] | 2021-12-31 | [9 empty] | 2021-12-09 |  | 2021-12-09
122473448 | 2687 | PGE | 96092 | NEM | EXPNEM | Application Review in Progress | Solar PV | 250 |  | 2021-12-10 |  | 2021-12-24 | 2021-12-24 | 2021-12-24 | 10 | [29 empty] | 2021-12-10 | 2021-12-24 | 2021-12-10
122473497 | 2688 | PGE | 96092 | NEM | EXPNEM | Study in Progress | Solar PV | 62.5 |  | 2021-12-10 |  |  | 2021-12-24 | 2021-12-24 | 10 | 2021-12-24 | 10 | [27 empty] | 2021-12-10 | 2021-12-27 | 2021-12-10
122473508 | 2689 | PGE | 96092 | NEM | EXPNEM | Application Review in Progress | Solar PV | 125 |  | 2021-12-10 |  |  | 2021-12-24 | 2021-12-24 | 10 | [29 empty] | 2021-12-10 | 2021-12-24 | 2021-12-10
122473513 | 2690 | PGE | 95901 | NEM | EXPNEM | Application Review in Progress | Solar PV | 437.5 |  | 2021-12-10 |  |  | 2021-12-24 | 2021-12-24 | 10 | [29 empty] | 2021-12-10 | 2021-12-24 | 2021-12-10
122473515 | 2691 | PGE | 96080 | NEM | EXPNEM | Application Review in Progress | Solar PV | 375 |  | 2021-12-10 |  |  | 2021-12-24 | 2021-12-24 | 10 | [29 empty] | 2021-12-10 | 2021-12-24 | 2021-12-10
122473944 | 2692 | PGE | 95695 | NEM | EXPNEM | Application Review in Progress | Solar PV | 562.5 |  | 2021-12-10 |  | 2021-12-21 | 2021-12-14 | 2021-12-14 | 2 | [29 empty] | 2021-12-10 |  | 2021-12-10
122473980 | 2693 | PGE | 95973 | NEM | EXPNEM | Study in Progress | Solar PV | 312.5 |  | 2021-12-10 |  |  | 2021-12-17 | 2021-12-17 | 5 | 2021-12-27 | 11 | [27 empty] | 2021-12-10 | 2021-12-27 | 2021-12-10
122474038 | 2694 | PGE | 95076 | NEM | EXPNEM | Application Review in Progress | Solar PV | 1124.507 |  | 2021-12-10 | 2021-12-15 |  | 2021-12-15 | 2021-12-15 | 3
122474322 | 2695 | PGE | 93455 | NEM | EXPNEM | Study in Progress | Solar PV | 47.337 |  | 2021-12-10 |  |  | 2021-12-15 | 2021-12-15 | 3 | 2021-12-15 | 3
122474833 | 2696 | PGE | 95525 | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-12-10 |  |  | 2021-12-14 | 2021-12-14 | 2 | 2021-12-14 | 2 | 2021-12-22 | 6 | [15 empty] | 2021-12-03 | 2021-12-03 |  | 2021-12-03 | 2021-12-10 | 6
122474988 | 2697 | PGE | 95917 | NEM | EXPNEM | Study in Progress | Solar PV | 51.829 |  | 2021-12-10 |  |  | 2021-12-24 | 2021-12-24 | 10 | 2021-12-24 | 10
122475218 | 2698 | PGE | 93206 | NEM | EXPNEM | Application Review in Progress | Solar PV | 60 |  | 2021-12-10 |  | 2021-12-20 | 2021-12-20 | 2021-12-20 | 6
122475585 | 2699 | PGE | 95917 | NEM | EXPNEM | Study in Progress | Solar PV | 31.102 |  | 2021-12-10 |  |  | 2021-12-24 | 2021-12-24 | 10 | 2021-12-24 | 10
122475772 | 2700 | PGE | 93308 | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2021-12-10 |  | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2 | 2021-12-27 | 11 | [27 empty] | 2021-12-27 | 2021-12-27 | 2021-12-27
122475824 | 2701 | PGE | 95320 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 514.6 |  | 2021-12-10 |  | 2021-12-22 | 2021-12-22 | 2021-12-22 | 8 | [29 empty] | 2021-12-10 |  | 2021-12-10
122475895 | 2702 | PGE | 93706 | NEM | EXPNEM | Application Review in Progress | Solar PV | 209.791 |  | 2021-12-10 |  | 2021-12-21 | 2021-12-21 | 2021-12-21 | 7
122476741 | 2703 | PGE | 94402 | NEM | EXPNEM | Application Review in Progress | Solar PV | 364.601 |  | 2021-12-10 |  | 2021-12-22 | 2021-12-22 | 2021-12-22 | 8
122478327 | 2704 | PGE | 95117 | Non-NEM | Non-Export | Study in Progress | Solar PV | 34.65 |  | 2021-12-11 | 2021-12-11 |  | 2021-12-11 | 2021-12-11 | 0 | 2021-12-15 | 2
122480168 | 2705 | PGE | 94546 | NEM | EXPNEM | Application Review in Progress | Solar PV | 50.682 |  | 2021-12-12 |  | 2021-12-16 | 2021-12-16 | 2021-12-16 | 3
122480278 | 2706 | PGE | 94303 | NEM | EXPNEM | Application Review in Progress | Solar PV | 36.762 |  | 2021-12-12 |  | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2
122480553 | 2707 | PGE | 94806 | NEM | EXPNEM | Application Review in Progress | Solar PV | 61.746 |  | 2021-12-12 |  | 2021-12-16 | 2021-12-16 | 2021-12-16 | 3
122480586 | 2708 | PGE | 94014 | NEM | EXPNEM | Application Review in Progress | Solar PV | 32.479 |  | 2021-12-12 |  | 2021-12-14 | 2021-12-14 | 2021-12-14 | 1
122480657 | 2709 | PGE | 94103 | NEM | EXPNEM | Application Review in Progress | Solar PV | 88.515 |  | 2021-12-12 |  | 2021-12-14 | 2021-12-14 | 2021-12-14 | 1
122480658 | 2710 | PGE | 94704 | NEM | EXPNEM | Application Review in Progress | Solar PV | 92.441 |  | 2021-12-12 |  | 2021-12-14 | 2021-12-14 | 2021-12-14 | 1
122480660 | 2711 | PGE | 95123 | NEM | EXPNEM | Application Review in Progress | Solar PV | 39.261 |  | 2021-12-12 |  | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2
122480702 | 2712 | PGE | 94118 | NEM | EXPNEM | Application Review in Progress | Solar PV | 88.515 |  | 2021-12-12 |  | 2021-12-14 | 2021-12-14 | 2021-12-14 | 1
122480703 | 2713 | PGE | 94520 | NEM | EXPNEM | Application Review in Progress | Solar PV | 45.328 |  | 2021-12-12 |  | 2021-12-14 | 2021-12-14 | 2021-12-14 | 1
122481053 | 2714 | PGE | 95076 | NEM | EXPNEM | Study in Progress | Solar PV | 125 |  | 2021-12-13 |  | 2021-12-14 | 2021-12-14 | 2021-12-14 | 1 | 2021-12-22 | 7
122481170 | 2715 | PGE | 95012 | NEM | EXPNEM | Study in Progress | Solar PV | 241.512 |  | 2021-12-13 |  | 2021-12-20 | 2021-12-14 | 2021-12-14 | 1 | 2021-12-22 | 7
122481193 | 2716 | PGE | 94960 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.232 |  | 2021-12-13 |  | 2021-12-22 | 2021-12-13 | 2021-12-13 | 0
122481299 | 2717 | PGE | 95062 | NEM | EXPNEM | Application Review in Progress | Solar PV | 30.023 |  | 2021-12-13 |  | 2021-12-21 | 2021-12-21 | 2021-12-21 | 6
122481300 | 2718 | PGE | 93455 | NEM | EXPNEM | Application Review in Progress | Solar PV | 179.1 |  | 2021-12-13 |  | 2021-12-27 | 2021-12-27 | 2021-12-27 | 10
122481536 | 2719 | PGE | 93422 | NEM | EXPNEM | Study in Progress | Micro Turbine, Solar PV | 66.6 |  | 2021-12-13 |  | 2021-12-13 | 2021-12-13 | 2021-12-13 | 0 | 2021-12-15 | 2 | [27 empty] | 2021-12-13 | 2021-12-15 | 2021-12-13
122481674 | 2720 | PGE | 93420 | Non-NEM | Break Before Make | Application Review in Progress | Storage | 10 |  | 2021-12-13 | 2021-12-27 |  | 2021-12-27 | 2021-12-27 | 10
122481691 | 2721 | PGE | 94566 | NEM | EXPNEM | Study in Progress | Solar PV | 53.35 |  | 2021-12-13 |  |  | 2021-12-27 | 2021-12-27 | 10 | 2021-12-27 | 10
122481964 | 2722 | PGE | 95333 | NEM | EXPNEM | Application Review in Progress | Solar PV | 437.5 |  | 2021-12-13 |  | 2021-12-27 | 2021-12-27 | 2021-12-27 | 10
122482229 | 2723 | PGE | 93245 | NEM | EXPNEM | Study in Progress | Solar PV | 240 |  | 2021-12-13 |  |  | 2021-12-15 | 2021-12-15 | 2 | 2021-12-28 | 11 | [27 empty] | 2021-12-13 |  | 2021-12-13
122482274 | 2724 | PGE | 93725 | NEM | EXPNEM | Study in Progress | Solar PV | 183.441 |  | 2021-12-13 |  | 2021-12-14 | 2021-12-14 | 2021-12-14 | 1 | 2021-12-16 | 3 | 2021-12-29 | 9 | 2021-12-29 | [24 empty] | 2021-12-13 |  | 2021-12-13
122482419 | 2725 | PGE | 93706 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.163 |  | 2021-12-13 |  | 2021-12-23 | 2021-12-13 | 2021-12-13 | 0
122482861 | 2726 | PGE | 94545 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 2655.2 |  | 2021-12-13 | 2021-12-16 |  | 2021-12-16 | 2021-12-16 | 3
122482862 | 2727 | PGE | 93635 | NEM | EXPNEM | IA in Progress | Solar PV | 41.031 |  | 2021-12-13 |  |  | 2021-12-16 | 2021-12-16 | 3 | 2021-12-16 | 3 | 2021-12-31 | 11 | [15 empty] | 2021-12-31
122482913 | 2728 | PGE | 93660 | NEM | EXPNEM | Study in Progress | Solar PV | 36 |  | 2021-12-13 |  |  | 2021-12-16 | 2021-12-16 | 3 | 2021-12-16 | 3 | [27 empty] | 2021-12-13 |  | 2021-12-13
122483006 | 2729 | PGE | 93637 | NEM | EXPNEM | Study in Progress | Solar PV | 240 |  | 2021-12-13 |  |  | 2021-12-15 | 2021-12-15 | 2 | 2021-12-17 | 4 | [5 empty] | 2021-12-17 | [21 empty] | 2021-12-13 | 2021-12-17 | 2021-12-13
122483483 | 2730 | PGE | 94585 | NEM | NEMMT | Application Review in Progress | ENGN, Solar PV, WIND | 1200 |  | 2021-12-13 | 2021-12-17 |  | 2021-12-16 | 2021-12-16 | 3
122483891 | 2731 | PGE | 94510 | NEM | EXPNEM | Application Review in Progress | Solar PV | 125 |  | 2021-12-13 |  | 2021-12-27 | 2021-12-27 | 2021-12-27 | 10
122484082 | 2732 | PGE | 94590 | NEM | EXPNEM | Study in Progress | Solar PV | 58.634 |  | 2021-12-13 |  |  | 2021-12-27 | 2021-12-27 | 10 | 2021-12-27 | 10
122484097 | 2733 | PGE | 95472 | NEM | VNEMSOMAH | Study in Progress | Solar PV | 49.411 |  | 2021-12-13 |  | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2 | 2021-12-31 | 14 | [27 empty] | 2021-12-13 | 2021-12-17 | 2021-12-13 | 2021-12-17 | 4
122484497 | 2734 | PGE | 95076 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 491.512 |  | 2021-12-14 |  | 2021-12-28 | 2021-12-28 | 2021-12-28 | 10
122484682 | 2735 | PGE | 93307 | NEM | EXPNEM | Application Review in Progress | Solar PV | 38.78 |  | 2021-12-14
122485208 | 2736 | PGE | 93401 | NEM | EXPNEM | Study in Progress | Solar PV | 200.518 |  | 2021-12-14 |  |  | 2021-12-21 | 2021-12-21 | 5 | 2021-12-21 | 5
122485321 | 2737 | PGE | 95407 | NEM | EXPNEM | Study in Progress | Solar PV | 85.556 |  | 2021-12-14 |  |  | 2021-12-21 | 2021-12-21 | 5 | 2021-12-21 | 5
122485848 | 2738 | PGE | 95912 | NEM | EXPNEM | Study in Progress | Solar PV | 66.6 |  | 2021-12-14 |  |  | 2021-12-16 | 2021-12-16 | 2 | 2021-12-16 | 2 | [27 empty] | 2021-12-14 | 2021-12-16 | 2021-12-14
122485880 | 2739 | PGE | 93660 | NEM | EXPNEM | Application Review in Progress | Solar PV | 145.672 |  | 2021-12-14 |  | 2021-12-28 | 2021-12-28 | 2021-12-28 | 10 | [29 empty] | 2021-12-14 |  | 2021-12-14
122486082 | 2740 | PGE | 95066 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 10 |  | 2021-12-14 | 2021-12-23 |  | 2021-12-23 | 2021-12-23 | 7 | [29 empty] | 2021-12-14 |  | 2021-12-14
122486138 | 2741 | PGE | 93620 | NEM | EXPNEM | Study in Progress | Solar PV | 62.5 |  | 2021-12-14 |  | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2 | 2021-12-16 | 2 | [27 empty] | 2021-12-14 |  | 2021-12-14
122486374 | 2742 | PGE | 93420 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-12-14 |  |  | 2021-12-28 | 2021-12-28 | 10 | 2021-12-28 | 10
122487225 | 2743 | PGE | 95687 | NEM | EXPNEM | Study in Progress | Solar PV | 360 |  | 2021-12-14 |  |  | 2021-12-16 | 2021-12-16 | 2 | 2021-12-16 | 2
122487321 | 2744 | PGE | 95203 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 66.256 |  | 2021-12-14 |  | 2021-12-17 | 2021-12-17 | 2021-12-17 | 3
122487345 | 2745 | PGE | 93624 | NEM | EXPNEM | Study in Progress | Solar PV | 38.956 |  | 2021-12-14 |  |  | 2021-12-28 | 2021-12-28 | 10 | 2021-12-28 | 10
122487353 | 2746 | PGE | 95203 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 30.913 |  | 2021-12-14 |  | 2021-12-17 | 2021-12-17 | 2021-12-17 | 3
122487757 | 2747 | PGE | 93727 | NEM | EXPNEM | Application Review in Progress | Solar PV | 908.176 |  | 2021-12-14 |  | 2021-12-21 | 2021-12-21 | 2021-12-21 | 5
122487857 | 2748 | PGE | 93905 | NEM | EXPNEM | Application Review in Progress | Solar PV | 40.384 |  | 2021-12-14 |  | 2021-12-28 | 2021-12-28 | 2021-12-28 | 10
122488679 | 2749 | PGE | 94028 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.741 |  | 2021-12-15 |  | 2021-12-29 | 2021-12-29 | 2021-12-29 | 10
122488892 | 2750 | PGE | 95926 | NEM | EXPNEM | Study in Progress | Solar PV | 50 |  | 2021-12-15 |  |  | 2021-12-22 | 2021-12-22 | 5 | 2021-12-28 | 9 | [27 empty] | 2021-12-15 | 2021-12-28 | 2021-12-15
122489139 | 2751 | PGE | 95333 | NEM | EXPNEM | Application Review in Progress | Solar PV | 220 |  | 2021-12-15 |  | 2021-12-29 | 2021-12-29 | 2021-12-29 | 10 | [29 empty] | 2021-12-15 |  | 2021-12-15
122489449 | 2752 | PGE | 94602 | NEM | EXPNEM | Study in Progress | Solar PV | 57.71 |  | 2021-12-15 |  |  | 2021-12-29 | 2021-12-29 | 10 | 2021-12-29 | 10
122489713 | 2753 | PGE | 93280 | NEM | EXPNEM | Application Review in Progress | Solar PV | 360 |  | 2021-12-15 |  |  | 2021-12-29 | 2021-12-29 | 10 | [29 empty] | 2021-12-15 | 2021-12-29 | 2021-12-15
122489740 | 2754 | PGE | 95687 | NEM | EXPNEM | Study in Progress | Solar PV | 120 |  | 2021-12-15 |  | 2021-12-20 | 2021-12-20 | 2021-12-20 | 3 | 2021-12-20 | 3
122489917 | 2755 | PGE | 95482 | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 |  | 2021-12-15 |  | 2021-12-23 | 2021-12-21 | 2021-12-21 | 4
122489919 | 2756 | PGE | 93901 | NEM | EXPNEM | Application Review in Progress | Solar PV | 113.288 |  | 2021-12-15 |  | 2021-12-17 | 2021-12-17 | 2021-12-17 | 2 | [29 empty] | 2021-12-15 |  | 2021-12-15
122490280 | 2757 | PGE | 94124 | NEM | EXPNEM | Application Review in Progress | Solar PV | 83.3 |  | 2021-12-15 |  | 2021-12-20 | 2021-12-20 | 2021-12-20 | 3
122490564 | 2758 | PGE | 94928 | NEM | EXPNEM | Application Review in Progress | Solar PV | 95.8 |  | 2021-12-15 |  | 2021-12-29 | 2021-12-29 | 2021-12-29 | 10
122491444 | 2759 | PGE | 93635 | NEM | EXPNEM | Application Review in Progress | Solar PV | 62.5 |  | 2021-12-15 |  | 2021-12-27 | 2021-12-27 | 2021-12-27 | 8 | [29 empty] | 2021-12-15 |  | 2021-12-15
122491737 | 2760 | PGE | 93631 | NEM | EXPNEM | Application Review in Progress | Solar PV | 125 |  | 2021-12-15 |  | 2021-12-28 | 2021-12-28 | 2021-12-28 | 9
122492059 | 2761 | PGE | 95603 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 33.122 |  | 2021-12-15 |  |  | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 0
122492385 | 2762 | PGE | 94945 | NEM | EXPNEM | Study in Progress | Solar PV | 500 |  | 2021-12-15 |  |  | 2021-12-20 | 2021-12-20 | 3 | 2021-12-20 | 3 | [27 empty] | 2021-12-15 | 2021-12-20 | 2021-12-15
122492406 | 2763 | PGE | 95407 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 35.22 |  | 2021-12-15 |  | 2021-12-23 | 2021-12-23 | 2021-12-23 | 6 | [29 empty] | 2021-12-15 |  | 2021-12-15
122492542 | 2764 | PGE | 95407 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 38.018 |  | 2021-12-15 |  | 2021-12-23 | 2021-12-23 | 2021-12-23 | 6 | [29 empty] | 2021-12-15 |  | 2021-12-15
122492548 | 2765 | PGE | 94066 | NEM | EXPNEM | Study in Progress | Solar PV | 501.275 |  | 2021-12-15 |  | 2021-12-21 | 2021-12-17 | 2021-12-17 | 2 | 2021-12-28 | 9
122492556 | 2766 | PGE | 94403 | NEM | EXPNEM | Application Review in Progress | Solar PV | 341.891 |  | 2021-12-15 |  | 2021-12-29 | 2021-12-29 | 2021-12-29 | 10
122493833 | 2767 | PGE | 95949 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.963 |  | 2021-12-16 |  | 2021-12-30 | 2021-12-16 | 2021-12-16 | 0
122493926 | 2768 | PGE | 94549 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-12-16 |  |  | 2021-12-30 | 2021-12-30 | 10 | 2021-12-30 | 10
122494328 | 2769 | PGE | 93312 | NEM | EXPNEM | Study in Progress | Solar PV | 300.612 |  | 2021-12-16 |  |  | 2021-12-29 | 2021-12-29 | 9 | 2021-12-29 | 9
122494566 | 2770 | PGE | 95341 | NEM | EXPNEM | Application Review in Progress | Solar PV | 801.632 |  | 2021-12-16 |  | 2021-12-30 | 2021-12-30 | 2021-12-30 | 10
122494604 | 2771 | PGE | 95687 | NEM | EXPNEM | Application Review in Progress | Solar PV | 120 |  | 2021-12-16 |  | 2021-12-29 | 2021-12-29 | 2021-12-29 | 9
122494922 | 2772 | PGE | 93618 | NEM | EXPNEM | Application Review in Progress | Solar PV | 32.87 |  | 2021-12-16 |  | 2021-12-29 | 2021-12-29 | 2021-12-29 | 9
122495134 | 2773 | PGE | 94520 | NEM | EXPNEM | Application Review in Progress | Solar PV | 45.212 |  | 2021-12-16 |  | 2021-12-17 | 2021-12-17 | 2021-12-17 | 1
122495385 | 2774 | PGE | 93245 | NEM | EXPNEM | Application Review in Progress | Solar PV | 113.937 |  | 2021-12-16 |  | 2021-12-30 | 2021-12-30 | 2021-12-30 | 10 | [29 empty] | 2021-12-16 | 2021-12-30 | 2021-12-16
122495546 | 2775 | PGE | 93446 | NEM | EXPNEM | Application Review in Progress | Solar PV | 120.756 |  | 2021-12-16 |  | 2021-12-30 | 2021-12-30 | 2021-12-30 | 10
122495749 | 2776 | PGE | 94538 | NEM | VNEM | Study in Progress | Solar PV | 33.075 |  | 2021-12-16 |  | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2 | 2021-12-31 | 11 | [17 empty] | 2021-12-16 | 2021-12-16 |  | 2021-12-16 | 2021-12-16 | 1 |  |  |  |  | 2021-12-16 | 2021-12-21 | 2021-12-16 | 2021-12-23 | 5
122496088 | 2777 | PGE | 95966 | NEM | EXPNEM | Study in Progress | Solar PV | 3691.6 |  | 2021-12-16 | 2021-12-22 |  | 2021-12-21 | 2021-12-21 | 3 | 2021-12-29 | 9 | [5 empty] | 2021-12-29
122496256 | 2778 | PGE | 96092 | NEM | EXPNEM | Application Review in Progress | Solar PV | 1654.572 |  | 2021-12-16 | 2021-12-22 |  | 2021-12-22 | 2021-12-22 | 4
122496571 | 2779 | PGE | 93245 | NEM | EXPNEM | Application Review in Progress | Solar PV | 180 |  | 2021-12-16 |  | 2021-12-22 | 2021-12-22 | 2021-12-22 | 4 | [29 empty] | 2021-12-16 |  | 2021-12-16
122496585 | 2780 | PGE | 93636 | NEM | EXPNEM | Application Review in Progress | Solar PV | 200 |  | 2021-12-16 |  | 2021-12-21 | 2021-12-21 | 2021-12-21 | 3 | [29 empty] | 2021-12-16 |  | 2021-12-16
122496695 | 2781 | PGE | 95687 | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2021-12-16 |  | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2 | 2021-12-27 | 7
122498451 | 2782 | PGE | 95003 | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 |  | 2021-12-17 |  | 2021-12-31 | 2021-12-31 | 2021-12-31 | 10
122499115 | 2783 | PGE | 93234 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 56.935 |  | 2021-12-17 |  | 2021-12-23 | 2021-12-23 | 2021-12-23 | 4 | [29 empty] | 2021-12-17 |  | 2021-12-17 |  |  | 2021-12-31
122499141 | 2784 | PGE | 94903 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-12-17 |  |  | 2021-12-27 | 2021-12-27 | 6 | 2021-12-27 | 6 | [17 empty] | 2021-12-17 | 2021-12-17 |  | 2021-12-17 | 2021-12-27 | 7
122499322 | 2785 | PGE | 93306 | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 33.741 |  | 2021-12-17 |  |  | 2021-12-31 | 2021-12-31 | 10 | 2021-12-31 | 10
122499720 | 2786 | PGE | 95387 | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 |  | 2021-12-17 |  | 2021-12-27 | 2021-12-20 | 2021-12-20 | 1 | [29 empty] | 2021-12-17 |  | 2021-12-17
122500595 | 2787 | PGE | 94513 | NEM | EXPNEM | Study in Progress | Solar PV | 43.2 |  | 2021-12-17 |  |  | 2021-12-30 | 2021-12-30 | 9 | 2021-12-30 | 9
122500726 | 2788 | PGE | 94010 | NEM | EXPNEM | Study in Progress | Solar PV | 32.614 |  | 2021-12-17 |  |  | 2021-12-23 | 2021-12-23 | 4 | 2021-12-29 | 8
122502772 | 2789 | PGE | 95765 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.35 |  | 2021-12-18
122502789 | 2790 | PGE | 94563 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.35 |  | 2021-12-18
122502958 | 2791 | PGE | 95765 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.163 |  | 2021-12-18
122502997 | 2792 | PGE | 95128 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2830 |  | 2021-12-18 |  |  | 2021-12-21 | 2021-12-21 | 1 | 2021-12-21 | 1 | [5 empty] | 2021-12-21
122503044 | 2793 | PGE | 95138 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 2724 |  | 2021-12-18 | 2021-12-23 |  | 2021-12-23 | 2021-12-23 | 3 | [29 empty] | 2021-12-18 |  | 2021-12-18
122503047 | 2794 | PGE | 95035 | NEM | NEMMT | Application Review in Progress | FUCE, Solar PV, Storage | 1144 |  | 2021-12-18 |  | 2021-12-29 | 2021-12-29 | 2021-12-29 | 7 | [29 empty] | 2021-12-18 |  | 2021-12-18
122503055 | 2795 | PGE | 95112 | NEM | NEM Paired Storage | Application Review in Progress | FUCE, Solar PV, Storage | 2525.5 |  | 2021-12-18 | 2021-12-24 |  | 2021-12-22 | 2021-12-22 | 2 | [29 empty] | 2021-12-18 |  | 2021-12-18
122503266 | 2796 | PGE | 95046 | NEM | EXPNEM | Study in Progress | Solar PV | 564 |  | 2021-12-18 |  |  | 2021-12-23 | 2021-12-23 | 3 | 2021-12-23 | 3
122503268 | 2797 | PGE | 95111 | NEM | EXPNEM | Application Review in Progress | Solar PV | 160 |  | 2021-12-18 |  | 2021-12-30 | 2021-12-30 | 2021-12-30 | 8
122503274 | 2798 | PGE | 95037 | NEM | EXPNEM | Application Review in Progress | Solar PV | 913.625 |  | 2021-12-18 |  | 2021-12-23 | 2021-12-23 | 2021-12-23 | 3
122504818 | 2799 | PGE | 95993 | NEM | EXPNEM | Application Review in Progress | Solar PV | 34.179 |  | 2021-12-20 | [34 empty] | 2021-12-20 |  | 2021-12-20
122505105 | 2800 | PGE | 93301 | NEM | EXPNEM | Application Review in Progress | Solar PV | 57.71 |  | 2021-12-20
122505316 | 2801 | PGE | 93638 | NEM | EXPNEM | Application Review in Progress | Solar PV | 62.431 |  | 2021-12-20 |  | 2021-12-24 | 2021-12-24 | 2021-12-24 | 4 | [29 empty] | 2021-12-27 |  | 2021-12-27
122505443 | 2802 | PGE | 95317 | NEM | EXPNEM | Application Review in Progress | Solar PV | 59.964 |  | 2021-12-20 | [34 empty] | 2021-12-20 |  | 2021-12-20
122505677 | 2803 | PGE | 95336 | NEM | EXPNEM | Application Review in Progress | Solar PV | 93.238 |  | 2021-12-20 | [34 empty] | 2021-12-20 |  | 2021-12-20
122505750 | 2804 | PGE | 95688 | NEM | EXPNEM | Study in Progress | Solar PV | 330.617 |  | 2021-12-20 |  |  | 2021-12-24 | 2021-12-24 | 4 | 2021-12-30 | 8
122506039 | 2805 | PGE | 93308 | NEM | EXPNEM | Application Review in Progress | Solar PV | 300 |  | 2021-12-20 |  | 2021-12-24 | 2021-12-24 | 2021-12-24 | 4
122506106 | 2806 | PGE | 93960 | NEM | EXPNEM | Study in Progress | Solar PV | 96 |  | 2021-12-20 |  |  | 2021-12-24 | 2021-12-24 | 4 | 2021-12-30 | 8 | [27 empty] | 2021-12-20 |  | 2021-12-20
122506340 | 2807 | PGE | 95688 | NEM | EXPNEM | Application Review in Progress | Solar PV | 120 |  | 2021-12-20
122506381 | 2808 | PGE | 94920 | NEM | EXPNEM | Application Review in Progress | Solar PV | 101.964 |  | 2021-12-20
122507267 | 2809 | PGE | 95340 | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2021-12-21 |  |  | 2021-12-27 | 2021-12-27 | 4 | 2021-12-30 | 7
122507412 | 2810 | PGE | 93657 | NEM | EXPNEM | Application Review in Progress | Solar PV | 35.045 |  | 2021-12-21 |  |  | 2021-12-28 | 2021-12-28 | 5 | [29 empty] | 2021-12-21 |  | 2021-12-21
122507459 | 2811 | PGE | 93722 | NEM | EXPNEM | Application Review in Progress | Solar PV | 32.698 |  | 2021-12-21
122507673 | 2812 | PGE | 95409 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.423 |  | 2021-12-21
122507889 | 2813 | PGE | 96080 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 38.018 |  | 2021-12-21 |  | 2021-12-31 | 2021-12-31 | 2021-12-31 | 8 | [29 empty] | 2021-12-21 |  | 2021-12-21
122508200 | 2814 | PGE | 96080 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 60.804 |  | 2021-12-21 |  | 2021-12-31 | 2021-12-31 | 2021-12-31 | 8 | [29 empty] | 2021-12-21 |  | 2021-12-21
122508348 | 2815 | PGE | 93454 | NEM | EXPNEM | Application Review in Progress | Solar PV | 133.3 |  | 2021-12-21
122508788 | 2816 | PGE | 95033 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 10 |  | 2021-12-21
122509911 | 2817 | PGE | 95136 | NEM | EXPNEM | Application Review in Progress | Solar PV | 292.76 |  | 2021-12-21
122510037 | 2818 | PGE | 93654 | NEM | EXPNEM | Application Review in Progress | Solar PV | 848.589 |  | 2021-12-21
122510102 | 2819 | PGE | 95403 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 41.643 |  | 2021-12-21 |  | 2021-12-23 | 2021-12-23 | 2021-12-23 | 2 | [29 empty] | 2021-12-21 | 2021-12-31 | 2021-12-21
122510189 | 2820 | PGE | 95403 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 37.926 |  | 2021-12-21 | [34 empty] | 2021-12-21 |  | 2021-12-21
122510235 | 2821 | PGE | 95403 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 37.926 |  | 2021-12-21 | [34 empty] | 2021-12-21 |  | 2021-12-21
122510240 | 2822 | PGE | 95403 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 37.926 |  | 2021-12-21 |  | 2021-12-23 | 2021-12-23 | 2021-12-23 | 2 | [29 empty] | 2021-12-21 | 2021-12-31 | 2021-12-21
122510340 | 2823 | PGE | 95403 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 53.188 |  | 2021-12-21 | [34 empty] | 2021-12-21 |  | 2021-12-21
122510350 | 2824 | PGE | 95403 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 53.188 |  | 2021-12-21 | [34 empty] | 2021-12-21 |  | 2021-12-21
122510929 | 2825 | PGE | 93230 | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.3 |  | 2021-12-22
122511146 | 2826 | PGE | 93230 | NEM | EXPNEM | Application Review in Progress | Solar PV | 387.4 |  | 2021-12-22
122511481 | 2827 | PGE | 95687 | NEM | EXPNEM | Application Review in Progress | Solar PV | 600 |  | 2021-12-22 |  |  | 2021-12-29 | 2021-12-29 | 5
122511518 | 2828 | PGE | 93930 | NEM | EXPNEM | Application Review in Progress | Solar PV | 109.731 |  | 2021-12-22 |  | 2021-12-28 | 2021-12-27 | 2021-12-27 | 3 | [29 empty] | 2021-12-28 |  | 2021-12-28
122511610 | 2829 | PGE | 95687 | NEM | EXPNEM | Application Review in Progress | Solar PV | 60 |  | 2021-12-22
122511628 | 2830 | PGE | 95304 | NEM | EXPNEM | Application Review in Progress | Solar PV | 580.504 |  | 2021-12-22 |  | 2021-12-24 | 2021-12-24 | 2021-12-24 | 2 | [29 empty] | 2021-12-22 |  | 2021-12-22
122511691 | 2831 | PGE | 94553 | NEM | EXPNEM | Study in Progress | Solar PV | 62.5 |  | 2021-12-22 |  |  | 2021-12-27 | 2021-12-27 | 3 | 2021-12-27 | 3
122511918 | 2832 | PGE | 95006 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.963 |  | 2021-12-22
122512103 | 2833 | PGE | 94560 | Non-NEM | Continuous Uncompensated Export | Application Accepted | Solar PV | 133.2 |  | 2021-12-22 | 2021-12-22 |  | 2021-12-22 | 2021-12-22 | 0 | 2021-12-29 | 5
122512644 | 2834 | PGE | 95334 | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.3 |  | 2021-12-22 |  | 2021-12-27 | 2021-12-27 | 2021-12-27 | 3 | [29 empty] | 2021-12-22 |  | 2021-12-22
122512792 | 2835 | PGE | 93646 | NEM | EXPNEM | Application Review in Progress | Solar PV | 400.816 |  | 2021-12-22
122512847 | 2836 | PGE | 95334 | NEM | EXPNEM | Study in Progress | Solar PV | 33.3 |  | 2021-12-22 |  | 2021-12-27 | 2021-12-27 | 2021-12-27 | 3 | 2021-12-30 | 6 | [27 empty] | 2021-12-22 | 2021-12-30 | 2021-12-22
122512973 | 2837 | PGE | 94565 | NEM | EXPNEM | Application Review in Progress | Solar PV | 101.728 |  | 2021-12-22
122514366 | 2838 | PGE | 95020 | NEM | EXPNEM | Application Review in Progress | Solar PV | 1872 |  | 2021-12-23 | 2021-12-27 |  | 2021-12-27 | 2021-12-27 | 2
122514438 | 2839 | PGE | 95987 | NEM | EXPNEM | Application Review in Progress | Solar PV | 47.351 |  | 2021-12-23 | [34 empty] | 2021-12-23 |  | 2021-12-23
122514586 | 2840 | PGE | 95120 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.423 |  | 2021-12-23
122514649 | 2841 | PGE | 93432 | NEM | EXPNEM | Application Review in Progress | Solar PV | 30.402 |  | 2021-12-23 |  | 2021-12-24 | 2021-12-24 | 2021-12-24 | 1 | [29 empty] | 2021-12-23 |  | 2021-12-23
122514675 | 2842 | PGE | 93280 | NEM | EXPNEM | Study in Progress | Solar PV | 58.133 |  | 2021-12-23 |  | 2021-12-28 | 2021-12-27 | 2021-12-27 | 2 | 2021-12-29 | 4 | [27 empty] | 2021-12-28 | 2021-12-29 | 2021-12-28
122514788 | 2843 | PGE | 93721 | NEM | EXPNEM | Application Review in Progress | Solar PV | 133.2 |  | 2021-12-23 |  | 2021-12-24 | 2021-12-24 | 2021-12-24 | 1
122514852 | 2844 | PGE | 95367 | NEM | EXPNEM | Study in Progress | Solar PV | 60 |  | 2021-12-23 |  |  | 2021-12-27 | 2021-12-27 | 2 | 2021-12-27 | 2
122514976 | 2845 | PGE | 95205 | NEM | EXPNEM | Application Review in Progress | Solar PV | 612.5 |  | 2021-12-23
122515057 | 2846 | PGE | 94028 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.963 |  | 2021-12-23
122515152 | 2847 | PGE | 95020 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.963 |  | 2021-12-23
122515513 | 2848 | PGE | 94550 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.963 |  | 2021-12-23 | [34 empty] | 2021-12-23 |  | 2021-12-23
122515533 | 2849 | PGE | 95070 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 41.853 |  | 2021-12-23
122515723 | 2850 | PGE | 94957 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.163 |  | 2021-12-23
122516525 | 2851 | PGE | 93601 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.35 |  | 2021-12-23
122517953 | 2852 | PGE | 94022 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 40.35 |  | 2021-12-24
122517977 | 2853 | PGE | 94551 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.423 |  | 2021-12-24 | [34 empty] | 2021-12-24 |  | 2021-12-24
122518112 | 2854 | PGE | 94549 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 40.163 |  | 2021-12-24
122518195 | 2855 | PGE | 94582 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.423 |  | 2021-12-24
122518209 | 2856 | PGE | 94506 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.423 |  | 2021-12-24
122520288 | 2857 | PGE | 95926 | NEM | EXPNEM | Application Review in Progress | Solar PV | 72.419 |  | 2021-12-27 |  | 2021-12-28 | 2021-12-28 | 2021-12-28 | 1 | [29 empty] | 2021-12-27 |  | 2021-12-27
122520775 | 2858 | PGE | 95126 | NEM | EXPNEM | Application Review in Progress | Solar PV | 289.504 |  | 2021-12-27
122521653 | 2859 | PGE | 95762 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.928 |  | 2021-12-28 |  | 2021-12-29 | 2021-12-29 | 2021-12-29 | 1
122521759 | 2860 | PGE | 94708 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 5 |  | 2021-12-28
122521904 | 2861 | PGE | 96021 | NEM | EXPNEM | Application Review in Progress | Solar PV | 39.352 |  | 2021-12-28 |  |  | 2021-12-31 | 2021-12-31 | 3 | [29 empty] | 2021-12-28 |  | 2021-12-28
122522126 | 2862 | PGE | 93314 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.163 |  | 2021-12-28
122522307 | 2863 | PGE | 94089 | NEM | EXPNEM | Application Review in Progress | Solar PV | 129.6 |  | 2021-12-28
122522450 | 2864 | PGE | 95032 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.641 |  | 2021-12-28 | [34 empty] | 2021-12-28 |  | 2021-12-28
122522610 | 2865 | PGE | 94089 | NEM | EXPNEM | Application Review in Progress | Solar PV | 259.215 |  | 2021-12-28
122522670 | 2866 | PGE | 94559 | NEM | EXPNEM | Application Review in Progress | Solar PV | 90.377 |  | 2021-12-28
122522780 | 2867 | PGE | 93427 | NEM | EXPNEM | Application Review in Progress | Solar PV | 115.42 |  | 2021-12-28
122522872 | 2868 | PGE | 95448 | NEM | EXPNEM | Application Review in Progress | Solar PV | 42.381 |  | 2021-12-28
122523083 | 2869 | PGE | 93427 | NEM | EXPNEM | Application Review in Progress | Solar PV | 249.754 |  | 2021-12-28
122523440 | 2870 | PGE | 94929 | NEM | EXPNEM | Application Review in Progress | Solar PV | 59.33 |  | 2021-12-28
122523855 | 2871 | PGE | 94533 | NEM | EXPNEM | Application Review in Progress | Solar PV | 180 |  | 2021-12-28 |  |  | 2021-12-31 | 2021-12-31 | 3 | [29 empty] | 2021-12-28 |  | 2021-12-28
122523880 | 2872 | PGE | 93427 | NEM | EXPNEM | Application Review in Progress | Solar PV | 245.373 |  | 2021-12-28
122524037 | 2873 | PGE | 95367 | NEM | EXPNEM | Application Review in Progress | Solar PV | 60 |  | 2021-12-28
122524531 | 2874 | PGE | 95367 | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 |  | 2021-12-28
122524585 | 2875 | PGE | 95536 | Non-NEM | Inadvertent Export | Study in Progress | Storage | 15 |  | 2021-12-29 |  |  | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 0
122524890 | 2876 | PGE | 93245 | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 |  | 2021-12-29 | [34 empty] | 2021-12-29 |  | 2021-12-29
122524943 | 2877 | PGE | 94602 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.163 |  | 2021-12-29
122525007 | 2878 | PGE | 94022 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 45.525 |  | 2021-12-29
122525020 | 2879 | PGE | 95360 | NEM | EXPNEM | Application Review in Progress | Solar PV | 120 |  | 2021-12-29 | [34 empty] | 2021-12-29 |  | 2021-12-29
122525071 | 2880 | PGE | 95928 | NEM | EXPNEM | Application Review in Progress | Solar PV | 294.086 |  | 2021-12-29 |  | 2021-12-30 | 2021-12-30 | 2021-12-30 | 1 | [29 empty] | 2021-12-29 |  | 2021-12-29
122525363 | 2881 | PGE | 95204 | NEM | EXPNEM | Application Review in Progress | Solar PV | 46.11 |  | 2021-12-29
122525670 | 2882 | PGE | 93308 | NEM | EXPNEM | Application Review in Progress | Solar PV | 60 |  | 2021-12-29
122526655 | 2883 | PGE | 94526 | NEM | EXPNEM | Application Review in Progress | Solar PV | 45.572 |  | 2021-12-29 |  | 2021-12-31 | 2021-12-31 | 2021-12-31 | 2 | [29 empty] | 2021-12-29 |  | 2021-12-29
122527780 | 2884 | PGE | 95476 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 15 |  | 2021-12-30
122527874 | 2885 | PGE | 93455 | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 |  | 2021-12-30
122528339 | 2886 | PGE | 95928 | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 |  | 2021-12-30 | [34 empty] | 2021-12-30 |  | 2021-12-30
122528508 | 2887 | PGE | 95694 | NEM | EXPNEM | Application Review in Progress | Solar PV | 111.278 |  | 2021-12-30
122528820 | 2888 | PGE | 95073 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 68.358 |  | 2021-12-30 | [34 empty] | 2021-12-30 |  | 2021-12-30
122530376 | 2889 | PGE | 95695 | NEM | EXPNEM | Application Review in Progress | Solar PV | 187.5 |  | 2021-12-30 | [34 empty] | 2021-12-30 |  | 2021-12-30
122530575 | 2890 | PGE | 93640 | NEM | EXPNEM | Application Review in Progress | Solar PV | 987.5 |  | 2021-12-30 | 2021-12-31 |  | 2021-12-31 | 2021-12-31 | 1 | [29 empty] | 2021-12-30 |  | 2021-12-30
122530703 | 2891 | PGE | 93640 | NEM | EXPNEM | Application Review in Progress | Solar PV | 987.5 |  | 2021-12-30 | 2021-12-31 |  | 2021-12-31 | 2021-12-31 | 1 | [29 empty] | 2021-12-30 |  | 2021-12-30
122530714 | 2892 | PGE | 95212 | NEM | EXPNEM | Application Review in Progress | Solar PV | 195.956 |  | 2021-12-30
122530741 | 2893 | PGE | 94019 | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.423 |  | 2021-12-30
122530763 | 2894 | PGE | 93640 | NEM | EXPNEM | Application Review in Progress | Solar PV | 750 |  | 2021-12-30 | 2021-12-31 |  | 2021-12-31 | 2021-12-31 | 1 | [29 empty] | 2021-12-30 |  | 2021-12-30
122530766 | 2895 | PGE | 95612 | NEM | EXPNEM | Application Review in Progress | Solar PV | 36.312 |  | 2021-12-30
122531266 | 2896 | PGE | 93308 | NEM | EXPNEM | Application Review in Progress | Solar PV | 83.702 |  | 2021-12-30
122531474 | 2897 | PGE | 93308 | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.3 |  | 2021-12-30
122533579 | 2898 | PGE | 95612 | NEM | EXPNEM | Application Review in Progress | Solar PV | 36.312 |  | 2021-12-31 | [34 empty] | 2021-12-31 |  | 2021-12-31
122533771 | 2899 | PGE | 96080 | NEM | EXPNEM | Application Review in Progress | Solar PV | 32.011 |  | 2021-12-31 | [34 empty] | 2021-12-31 |  | 2021-12-31
122533857 | 2900 | PGE | 95938 | NEM | EXPNEM | Study in Progress | Solar PV | 33.3 |  | 2021-12-31 |  |  | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | 0
122533974 | 2901 | PGE | 95973 | NEM | EXPNEM | Study in Progress | Solar PV | 62.5 |  | 2021-12-31 |  |  | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | 0
122533977 | 2902 | PGE | 94596 | Non-NEM | Non-Export | Application Review in Progress | Solar PV | 185.192 |  | 2021-12-31
122534211 | 2903 | PGE | 95963 | NEM | EXPNEM | Study in Progress | Solar PV | 30.639 |  | 2021-12-31 |  |  | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | 0 | [27 empty] | 2021-12-31 | 2021-12-31 | 2021-12-31
122534395 | 2904 | PGE | 94503 | NEM | EXPNEM | Application Review in Progress | Solar PV | 430.57 |  | 2021-12-31 | [34 empty] | 2021-12-31 |  | 2021-12-31
122534536 | 2905 | PGE | 95932 | NEM | EXPNEM | Application Review in Progress | Solar PV | 50 |  | 2021-12-31 | [34 empty] | 2021-12-31 |  | 2021-12-31
122534571 | 2906 | PGE | 94503 | NEM | EXPNEM | Application Review in Progress | Solar PV | 660 |  | 2021-12-31 | [34 empty] | 2021-12-31 |  | 2021-12-31
122534699 | 2907 | PGE | 95938 | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.3 |  | 2021-12-31 | [34 empty] | 2021-12-31 |  | 2021-12-31
122534774 | 2908 | PGE | 94574 | NEM | NEMMT | Application Review in Progress | FUCE, Solar PV, Storage | 1727.2 |  | 2021-12-31 | [34 empty] | 2021-12-31 |  | 2021-12-31
122535223 | 2909 | PGE | 93446 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1387.2 |  | 2021-12-31 | [34 empty] | 2021-12-31 |  | 2021-12-31
122535312 | 2910 | PGE | 93446 | NEM | EXPNEM | Application Review in Progress | Solar PV | 389.006 |  | 2021-12-31 | [34 empty] | 2021-12-31 |  | 2021-12-31
122488152 | 2911 | PGE | 94545 | NEM | SNEM | Application Review in Progress | Solar PV | 69.6 |  | 2021-12-24 |  | 2021-12-28 | 2021-12-28 | 2021-12-28 | 2
122514999 | 2912 | PGE | 93608 | Non-NEM | Non-Export | Application Review in Progress | Storage | 10 |  | 2021-12-28
122252186 | 2913 | PGE | 94538 | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1798.9 |  | 2021-10-19 | 2021-10-28 |  | 2021-10-27 | 2021-10-27 | 6 | 2021-12-15 | 38
122455602 | 2914 | PGE | 93249 | NEM | NEMMT | Application Review in Progress | FUCE, Solar PV | 28650 |  | 2021-12-02 | 2021-12-10 |  | 2021-12-02 | 2021-12-02 | 0
122459390 | 2915 | PGE | 93306 | NEM | VNEM | Application Review in Progress | Solar PV | 134.823 |  | 2021-12-17 |  | 2021-12-31 | 2021-12-31 | 2021-12-31 | 10
122460296 | 2916 | PGE | 95334 | NEM | EXPNEM | Application Review in Progress | Solar PV | 187.5 |  | 2021-12-23
122460601 | 2917 | PGE | 93422 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-12-16 |  |  | 2021-12-24 | 2021-12-24 | 6 | 2021-12-24 | 6 | 2021-12-27 | 1 | [15 empty] | 2021-12-16 | 2021-12-16 |  | 2021-12-16 | 2021-12-24 | 7
122461167 | 2918 | PGE | 95441 | NEM | EXPNEM | Study in Progress | Solar PV | 56.906 |  | 2021-12-14 |  |  | 2021-12-23 | 2021-12-23 | 7 | 2021-12-23 | 7
122461346 | 2919 | PGE | 93960 | NEM | NEMMT | Application Review in Progress | Solar PV, Storage, WIND | 3198.65 |  | 2021-12-22 | 2021-12-22 |  | 2021-12-22 | 2021-12-22 | 0 | [29 empty] | 2021-12-22 |  | 2021-12-22
122461731 | 2920 | PGE | 95112 | NEM | EXPNEM | Study in Progress | Solar PV | 66.6 |  | 2021-12-15 |  | 2021-12-21 | 2021-12-21 | 2021-12-21 | 4
122461737 | 2921 | PGE | 93656 | NEM | NEMMT | Application Review in Progress | Solar PV, Storage | 138.166 |  | 2021-12-10 |  | 2021-12-20 | 2021-12-13 | 2021-12-13 | 1
122462041 | 2922 | PGE | 95472 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 37.632 |  | 2021-12-28 | [34 empty] | 2021-12-28 |  | 2021-12-28
122462225 | 2923 | PGE | 94704 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 538.367 |  | 2021-12-22
122471908 | 2924 | PGE | 93637 | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.3 |  | 2021-12-13 |  | 2021-12-27 | 2021-12-27 | 2021-12-27 | 10
122473450 | 2925 | PGE | 93446 | NEM | EXPNEM | Study in Progress | Solar PV | 53.35 |  | 2021-12-13 |  |  | 2021-12-27 | 2021-12-27 | 10 | 2021-12-27 | 10
122475090 | 2926 | PGE | 93923 | Non-NEM | Non-Export | Study in Progress | Storage | 3.84 |  | 2021-12-16 |  |  | 2021-12-30 | 2021-12-30 | 10 | 2021-12-30 | 10
122475873 | 2927 | PGE | 95334 | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.3 |  | 2021-12-20 |  | 2021-12-31 | 2021-12-31 | 2021-12-31 | 9 | [29 empty] | 2021-12-20 |  | 2021-12-20
122476324 | 2928 | PGE | 95726 | NEM | EXPNEM | Application Review in Progress | Solar PV | 98.329 |  | 2021-12-12 |  | 2021-12-24 | 2021-12-24 | 2021-12-24 | 9 | [29 empty] | 2021-12-12 | 2021-12-24 | 2021-12-12
122476375 | 2929 | PGE | 94401 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 241.771 |  | 2021-12-27 |  | 2021-12-30 | 2021-12-30 | 2021-12-30 | 3
122476517 | 2930 | PGE | 94568 | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 122.27 |  | 2021-12-14 |  | 2021-12-21 | 2021-12-21 | 2021-12-21 | 5
122476573 | 2931 | PGE | 94568 | NEM | NEMMT | Application Review in Progress | Solar PV, Storage | 157.05 |  | 2021-12-14 |  | 2021-12-28 | 2021-12-28 | 2021-12-28 | 10
122480663 | 2932 | PGE | 95453 | NEM | EXPNEM | Application Accepted | Solar PV | 330 |  | 2021-12-14 |  | 2021-12-31 | 2021-12-17 | 2021-12-17 | 3 | 2021-12-27 | 9 | [27 empty] | 2021-12-14 |  | 2021-12-14
122480666 | 2933 | PGE | 95453 | NEM | EXPNEM | Application Review in Progress | Solar PV | 132 |  | 2021-12-14 |  | 2021-12-27 | 2021-12-27 | 2021-12-27 | 9 | [29 empty] | 2021-12-14 | 2021-12-27 | 2021-12-14
122481029 | 2934 | PGE | 94507 | Non-NEM | Non-Export | IA in Progress | Storage | 7.68 |  | 2021-12-14 | 2021-12-14 |  | 2021-12-14 | 2021-12-14 | 0 | 2021-12-16 | 2 | 2021-12-21 | 3 | [15 empty] | 2021-12-15 | 2021-12-15 |  | 2021-12-15 | 2021-12-15 | 1
122481072 | 2935 | PGE | 95963 | NEM | EXPNEM | Study in Progress | Solar PV | 79.763 |  | 2021-12-16 |  |  | 2021-12-20 | 2021-12-20 | 2 | 2021-12-20 | 2
122481591 | 2936 | PGE | 95060 | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 |  | 2021-12-18 |  | 2021-12-30 | 2021-12-23 | 2021-12-23 | 3 | [29 empty] | 2021-12-27 |  | 2021-12-27
122481722 | 2937 | PGE | 93446 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-12-14 |  |  | 2021-12-24 | 2021-12-24 | 8 | 2021-12-24 | 8 | 2021-12-27 | 1 | [15 empty] | 2021-12-13 | 2021-12-13 |  | 2021-12-13 | 2021-12-24 | 10
122482156 | 2938 | PGE | 95037 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1150 |  | 2021-12-20
122483056 | 2939 | PGE | 93654 | NEM | EXPNEM | Study in Progress | Solar PV | 47.332 |  | 2021-12-14 |  | 2021-12-15 | 2021-12-15 | 2021-12-15 | 1 | 2021-12-17 | 3 | 2021-12-29 | 8
122483373 | 2940 | PGE | 93630 | NEM | EXPNEM | Study in Progress | Solar PV | 642.832 |  | 2021-12-16 |  |  | 2021-12-17 | 2021-12-17 | 1 | 2021-12-17 | 1 | [27 empty] | 2021-12-16 | 2021-12-17 | 2021-12-16
122483561 | 2941 | PGE | 93311 | NEM | VNEM | Application Review in Progress | Solar PV | 61.222 |  | 2021-12-14 |  | 2021-12-27 | 2021-12-27 | 2021-12-27 | 9
122483669 | 2942 | PGE | 94547 | NEM | NEMMT | Study in Progress | FUCE, Solar PV | 300 |  | 2021-12-20 |  |  | 2021-12-29 | 2021-12-29 | 7 | 2021-12-29 | 7
122483914 | 2943 | PGE | 95688 | NEM | EXPNEM | Study in Progress | Solar PV | 510 |  | 2021-12-14 |  |  | 2021-12-16 | 2021-12-16 | 2 | 2021-12-27 | 9
122483973 | 2944 | PGE | 94538 | NEM | EXPNEM | Application Review in Progress | Solar PV | 300.221 |  | 2021-12-14 |  | 2021-12-28 | 2021-12-28 | 2021-12-28 | 10 | [29 empty] | 2021-12-14 | 2021-12-27 | 2021-12-14
122485609 | 2945 | PGE | 95076 | NEM | EXPNEM | Application Review in Progress | Solar PV | 191.062 |  | 2021-12-30
122486570 | 2946 | PGE | 95460 | NEM | EXPNEM | Application Review in Progress | Solar PV | 183.3 |  | 2021-12-27 |  | 2021-12-28 | 2021-12-28 | 2021-12-28 | 1
122487017 | 2947 | PGE | 94010 | NEM | EXPNEM | Application Review in Progress | Solar PV | 341.891 |  | 2021-12-15 |  | 2021-12-23 | 2021-12-20 | 2021-12-20 | 3
122487338 | 2948 | PGE | 94534 | NEM | EXPNEM | Study in Progress | Solar PV | 175.486 |  | 2021-12-28 |  |  | 2021-12-29 | 2021-12-29 | 1 | 2021-12-29 | 1 | [27 empty] | 2021-12-28 |  | 2021-12-28
122487443 | 2949 | PGE | 94534 | NEM | EXPNEM | Study in Progress | Solar PV | 312 |  | 2021-12-28 |  |  | 2021-12-29 | 2021-12-29 | 1 | 2021-12-29 | 1 | [27 empty] | 2021-12-28 |  | 2021-12-28
122487481 | 2950 | PGE | 94080 | NEM | EXPNEM | Study in Progress | Solar PV | 215.378 |  | 2021-12-15 |  | 2021-12-29 | 2021-12-29 | 2021-12-29 | 10
122488863 | 2951 | PGE | 95060 | NEM | VNEM | Application Review in Progress | Solar PV | 130.48 |  | 2021-12-27
122488932 | 2952 | PGE | 93905 | NEM | EXPNEM | Study in Progress | Solar PV | 36.54 |  | 2021-12-18 |  | 2021-12-30 | 2021-12-30 | 2021-12-30 | 8 | 2021-12-30 | 8
122488947 | 2953 | PGE | 93455 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 51.356 |  | 2021-12-17 |  | 2021-12-20 | 2021-12-20 | 2021-12-20 | 1
122489571 | 2954 | PGE | 94558 | NEM | EXPNEM | Application Review in Progress | Solar PV | 50 |  | 2021-12-28 | [34 empty] | 2021-12-28 |  | 2021-12-28
122492038 | 2955 | PGE | 93640 | NEM | EXPNEM | Application Review in Progress | Solar PV | 315000 |  | 2021-12-22 | 2021-12-28 |  | 2021-12-28 | 2021-12-28 | 4
122492532 | 2956 | PGE | 93636 | NEM | EXPNEM | Application Review in Progress | Solar PV | 250 |  | 2021-12-30
122494179 | 2957 | PGE | 93638 | NEM | EXPNEM | Application Review in Progress | Solar PV | 187.5 |  | 2021-12-20
122495095 | 2958 | PGE | 93210 | NEM | EXPNEM | Application Review in Progress | Solar PV | 862.5 |  | 2021-12-21
122495708 | 2959 | PGE | 93455 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 242.006 |  | 2021-12-29
122495956 | 2960 | PGE | 95023 | NEM | EXPNEM | Study in Progress | Solar PV | 400.816 |  | 2021-12-20 |  |  | 2021-12-30 | 2021-12-30 | 8 | 2021-12-30 | 8 | [27 empty] | 2021-12-20 |  | 2021-12-20
122495996 | 2961 | PGE | 96092 | NEM | EXPNEM | Application Review in Progress | Solar PV | 1145.473 |  | 2021-12-20 | 2021-12-22 |  | 2021-12-22 | 2021-12-22 | 2
122496533 | 2962 | PGE | 94030 | NEM | EXPNEM | Application Review in Progress | Solar PV | 280.756 |  | 2021-12-27
122499376 | 2963 | PGE | 93263 | NEM | EXPNEM | Application Review in Progress | Solar PV | 687.5 |  | 2021-12-20 | [34 empty] | 2021-12-20 |  | 2021-12-20
122499808 | 2964 | PGE | 93280 | NEM | EXPNEM | Application Review in Progress | Solar PV | 250 |  | 2021-12-20 | [34 empty] | 2021-12-20 |  | 2021-12-20
122499848 | 2965 | PGE | 93280 | NEM | EXPNEM | Application Review in Progress | Solar PV | 375 |  | 2021-12-20 |  | 2021-12-27 | 2021-12-21 | 2021-12-21 | 1 | [29 empty] | 2021-12-20 |  | 2021-12-20
122499972 | 2966 | PGE | 93280 | NEM | EXPNEM | Study in Progress | Solar PV | 875 |  | 2021-12-20 |  |  | 2021-12-21 | 2021-12-21 | 1 | 2021-12-27 | 5 | [27 empty] | 2021-12-20 | 2021-12-27 | 2021-12-20
122500037 | 2967 | PGE | 93250 | NEM | EXPNEM | Application Review in Progress | Solar PV | 562.5 |  | 2021-12-20 |  | 2021-12-28 | 2021-12-21 | 2021-12-21 | 1 | [29 empty] | 2021-12-20 |  | 2021-12-20
122500158 | 2968 | PGE | 93263 | NEM | EXPNEM | Study in Progress | Solar PV | 125 |  | 2021-12-20 |  |  | 2021-12-21 | 2021-12-21 | 1 | 2021-12-27 | 5 | [27 empty] | 2021-12-20 | 2021-12-27 | 2021-12-20
122500206 | 2969 | PGE | 93250 | NEM | EXPNEM | Study in Progress | Solar PV | 187.5 |  | 2021-12-20 |  |  | 2021-12-21 | 2021-12-21 | 1 | 2021-12-27 | 5 | [27 empty] | 2021-12-20 | 2021-12-27 | 2021-12-20
122500237 | 2970 | PGE | 93250 | NEM | EXPNEM | Application Review in Progress | Solar PV | 375 |  | 2021-12-20 |  | 2021-12-27 | 2021-12-21 | 2021-12-21 | 1 | [29 empty] | 2021-12-20 |  | 2021-12-20
122500246 | 2971 | PGE | 93420 | Non-NEM | Inadvertent Export | IA in Progress | Storage | 5 |  | 2021-12-20 |  |  | 2021-12-21 | 2021-12-21 | 1 | 2021-12-21 | 1 | 2021-12-27 | 4 | [15 empty] | 2021-12-17 | 2021-12-17 |  | 2021-12-17 | 2021-12-17 | 1
122500319 | 2972 | PGE | 95988 | NEM | EXPNEM | Application Review in Progress | Solar PV | 74.59 |  | 2021-12-20 |  | 2021-12-31 | 2021-12-31 | 2021-12-31 | 9 | [29 empty] | 2021-12-20 |  | 2021-12-20
122500430 | 2973 | PGE | 93280 | NEM | EXPNEM | Application Review in Progress | Solar PV | 875 |  | 2021-12-20 |  | 2021-12-27 | 2021-12-21 | 2021-12-21 | 1 | [29 empty] | 2021-12-20 |  | 2021-12-20
122500442 | 2974 | PGE | 94533 | NEM | EXPNEM | Application Review in Progress | Solar PV | 120 |  | 2021-12-28 | [34 empty] | 2021-12-28 |  | 2021-12-28
122500562 | 2975 | PGE | 93250 | NEM | EXPNEM | Application Review in Progress | Solar PV | 437.5 |  | 2021-12-20 |  | 2021-12-28 | 2021-12-21 | 2021-12-21 | 1 | [29 empty] | 2021-12-20 |  | 2021-12-20
122501143 | 2976 | PGE | 95037 | NEM | EXPNEM | Application Review in Progress | Solar PV | 145.259 |  | 2021-12-18 |  | 2021-12-23 | 2021-12-23 | 2021-12-23 | 3 | [29 empty] | 2021-12-18 |  | 2021-12-18
122501177 | 2977 | PGE | 95119 | NEM | EXPNEM | Application Review in Progress | Solar PV | 120 |  | 2021-12-18 |  | 2021-12-23 | 2021-12-23 | 2021-12-23 | 3 | [29 empty] | 2021-12-18 |  | 2021-12-18
122501601 | 2978 | PGE | 95125 | NEM | EXPNEM | Application Review in Progress | Solar PV | 276 |  | 2021-12-18 |  | 2021-12-30 | 2021-12-30 | 2021-12-30 | 8 | [29 empty] | 2021-12-18 |  | 2021-12-18
122503040 | 2979 | PGE | 94019 | NEM | EXPNEM | Application Review in Progress | Solar PV | 296.468 |  | 2021-12-20 | [34 empty] | 2021-12-20 |  | 2021-12-20
122503872 | 2980 | PGE | 95570 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 10 |  | 2021-12-21
122504181 | 2981 | PGE | 93908 | NEM | EXPNEM | Application Review in Progress | Solar PV | 241.512 |  | 2021-12-21
122504989 | 2982 | PGE | 95060 | NEM | EXPNEM | Application Review in Progress | Solar PV | 31.186 |  | 2021-12-22
122505108 | 2983 | PGE | 93314 | NEM | EXPNEM | Application Review in Progress | Solar PV | 115.42 |  | 2021-12-21
122505437 | 2984 | PGE | 94536 | NEM | VNEM | Application Review in Progress | Solar PV | 400 |  | 2021-12-23 |  | 2021-12-24 | 2021-12-24 | 2021-12-24 | 1
122505586 | 2985 | PGE | 96080 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 42.978 |  | 2021-12-21 |  | 2021-12-31 | 2021-12-31 | 2021-12-31 | 8 | [29 empty] | 2021-12-21 |  | 2021-12-21
122507236 | 2986 | PGE | 95134 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1387.5 |  | 2021-12-29 | 2021-12-30 |  | 2021-12-30 | 2021-12-30 | 1 | [29 empty] | 2021-12-29 |  | 2021-12-29
122507279 | 2987 | PGE | 95409 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 10 |  | 2021-12-22
122507553 | 2988 | PGE | 93245 | NEM | EXPNEM | Application Review in Progress | Solar PV | 205.259 |  | 2021-12-28 | [34 empty] | 2021-12-28 |  | 2021-12-28
122509819 | 2989 | PGE | 95330 | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 2539.1 |  | 2021-12-22 | 2021-12-27 |  | 2021-12-23 | 2021-12-23 | 1
122510002 | 2990 | PGE | 95695 | NEM | EXPNEM | Application Review in Progress | Solar PV | 50 |  | 2021-12-23 |  | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2
122510154 | 2991 | PGE | 95407 | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 41.795 |  | 2021-12-23 |  | 2021-12-24 | 2021-12-24 | 2021-12-24 | 1 | [29 empty] | 2021-12-23 |  | 2021-12-23
122514436 | 2992 | PGE | 95401 | NEM | EXPNEM | Study in Progress | Solar PV | 349.55 |  | 2021-12-27 |  |  | 2021-12-28 | 2021-12-28 | 1 | 2021-12-28 | 1 | [27 empty] | 2021-12-27 | 2021-12-28 | 2021-12-27
122515692 | 2993 | PGE | 93608 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 10 |  | 2021-12-28
122519915 | 2994 | PGE | 93722 | NEM | VNEM | Application Review in Progress | Solar PV | 186.204 |  | 2021-12-30 | [34 empty] | 2021-12-30 |  | 2021-12-30
122520009 | 2995 | PGE | 95330 | NEM | EXPNEM | Application Review in Progress | Solar PV | 588.87 |  | 2021-12-29 | [34 empty] | 2021-12-29 |  | 2021-12-29
122520724 | 2996 | PGE | 95131 | NEM | EXPNEM | Application Review in Progress | Solar PV | 869.259 |  | 2021-12-30
122520728 | 2997 | PGE | 95134 | NEM | EXPNEM | Application Review in Progress | Solar PV | 454.226 |  | 2021-12-30
122521669 | 2998 | PGE | 94558 | NEM | VNEM | Application Review in Progress | Solar PV | 278.108 |  | 2021-12-29
122523436 | 2999 | PGE | 93608 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 10 |  | 2021-12-30
122523777 | 3000 | PGE | 94085 | NEM | EXPNEM | Application Review in Progress | Solar PV | 40.252 |  | 2021-12-29
122524526 | 3001 | PGE | 93711 | NEM | VNEM | Application Review in Progress | Solar PV | 182.942 |  | 2021-12-29
122525379 | 3002 | PGE | 94533 | NEM | EXPNEM | Application Review in Progress | Solar PV | 276 |  | 2021-12-31 | [34 empty] | 2021-12-31 |  | 2021-12-31
122526401 | 3003 | PGE | 93422 | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 10 |  | 2021-12-31
122528792 | 3004 | PGE | 93618 | NEM | EXPNEM | Application Review in Progress | Solar PV | 275 |  | 2021-12-31

## Q3 nonNEM less than 30 kW
Notification No | Key | Zip Code | Utility | NEM Type | Project Type | Project Status | Technology Type | Size Total Proposed Gen | Cost Envelope Requested? | Application Received | Provide: 1st Written Notice/Invoice | Provide: NEM Deficiency Notice | Application Review | Provide: 1st Written Notice/Invoice | Cycle Time A (Business Days to Acknowledge Interconnection Request Submission) | Application Deemed Complete | Cycle Time B (Business Days to Deem Complete) | Conduct: Initial Review (IR) | Cycle Time C (Time from Interconnection Request Deemed Complete to Completion of Initial Review & Provision of Results) | Conduct: Supplemental Review (SR) | Conduct: Supplemental Review (SR) | Cycle Time D (Time from Supplemental Review Start Date to Completion of Supplemental Review) | Conduct: Screens Q and R | Conduct: Screens Q and R | Cycle Time E (Time from Electrical Interdependence Test Start Date to its Completion) | Scoping Meeting Date | Scoping Meeting Date | Cycle Time F (Time from Electrical Interdependence Test Completion to EIT Results Scoping Meeting Held) | DSA Agreement Executed by PG&E | Conduct: SIS | Cycle Time H (Time from System Impact Study Start Date to its Completion Date) | Scoping Meeting Date | Tendered DSA Agreement | Cycle Time G (Time from Study Scoping Meeting Until Study Agreement Provided) | Tender Draft IA | Tender Draft IA | Cycle Time I (Time to Provide Draft Generator Interconnection Agreement Applicable Milestone) | Tender Draft IA | IA Negotiations/Customer Signature | Cycle Time J(a) (Time from Draft Generator Interconnection Agreement Provided to Date Generator Interconnection Agreement Executed) | Cycle Time J(b) (Time from Final Study Report Date for Detailed Study to Date Generator Interconnection Agreement Executed) | Receive Customer Changes | Determine Material Modifications | Cycle Time M (Time from Request to Consider Modification to Determination Whether Modification is Material (F.3.b.v)) | Variance Request Received (Typ. From Cust) | Conduct: Variance Request Review | Variance Request Received (Typ. From Cust) | Conduct: Variance Request Review | Cycle Time N (Time for Responding to Line-Side Taps Variance Requests (for utilities that require a variance request)) | Conduct: Meter Review | Tender: Meter Invoice | Tender: Meter Invoice | Cycle Time O (Design and Invoice of Net Generation Output Meter) | Move to FMO | FMO - PASS | Cycle Time P (Installation of Net Generation Output Meter) | SP&D Design Start | SP&D Design End | Cycle Time Q(a) (Time from Customer Agreement to Proceed to Final Design and Issuance of Invoice SP&D) | Tender EA Invoice | IT Design End | Cycle Time Q(b) (Time from Customer Agreement to Proceed to Final Design and Issuance of Invoice Telemetry) | SP&D Construction Start | SP&D Construction Finish | Cycle Time R(a) (Time from Customer Payment of Invoice and Completion of Customer Work to Completion of Upgrade Construction SP&D) | PG&E Construction Start IT | PG&E Construction Complete IT | Cycle Time R(b) (Time from Customer Payment of Invoice and Completion of Customer Work to Completion of Upgrade Construction Telemetry) | PPI Authorization Letter | PPI Completion | Cycle Time S (Time for Scheduling of Commissioning Test) | FMO - PASS (Move to FMO) | FMO Schedule Inspection FMO Order | Cycle Time S(b) (This is for Projects that do not require PPI) | FMO - PASS | Permission to Operate - Conditional (COD) | Permission to Operate - Final (COD) | Cycle Time K(a) (Time from when the customer notifies the utility it has completed all of its obligations under the agreements (F.5.b) including commissioning tests, to when the utility provides the customer Permission to Operate - FMO Inspection: Task 7390 AFD FMO - PASS to Task 7502 AFD Permission to Parallel - Conditional or 7503 AFD Permission to Operate - Final (COD)) | Conduct Pre Paralell Inspection (PPI) | Cycle Time K(b) (This Cycle Time is for Projects that require PPI) | Cycle Time L (Total Time from Submission of Interconnection Request to Permission to Operate (Not in Rule 21, tracked for informational purposes))
120467593 | 1714 | 94904 | PGE | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-01-27 |  |  | 2021-02-08 | 2021-02-08 | 8 | 2021-02-08 | 8 | 2021-02-09 | 1 | [27 empty] | 0 | [29 empty] | 2021-03-10
120535961 | 1715 | 94062 | PGE | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-02-16 |  |  | 2021-02-25 | 2021-02-25 | 7 | 2021-02-25 | 7 | 2021-03-03 | 4 | [27 empty] | 0 | [29 empty] | 2021-03-08
120575690 | 1716 | 95070 | PGE | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-02-25 |  |  | 2021-03-08 | 2021-03-08 | 7 | 2021-03-08 | 7 | 2021-03-11 | 3 | [27 empty] | 0 | [29 empty] | 2021-04-09
120600005 | 1717 | 94563 | PGE | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-03-03 | 2021-03-16 |  | 2021-03-16 | 2021-03-16 | 9 | 2021-04-01 | 21 | 2021-04-07 | 4 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-07 | 0 | [6 empty] | 0 | [29 empty] | 2021-04-13
120635484 | 1718 | 94044 | PGE | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-03-11 |  |  | 2021-03-25 | 2021-03-25 | 10 | 2021-03-25 | 10 | 2021-04-07 | 9 | [19 empty] | 2021-05-05 | [7 empty] | 0 | [29 empty] | 2021-05-06
120644894 | 1719 | 94941 | PGE | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-03-15 |  |  | 2021-03-30 | 2021-03-30 | 11 | 2021-04-09 | 19 | 2021-04-14 | 3 | [19 empty] | 2021-05-14 | [7 empty] | 0 | [29 empty] | 2021-06-07
120654831 | 1720 | 95448 | PGE | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-03-17 |  |  | 2021-03-31 | 2021-03-31 | 10 | 05/07/2021 |  | 2021-05-14 | 6 | [19 empty] | 2021-07-22 | [7 empty] | 0 | [29 empty] | 2021-07-22
120826983 | 1721 | 94526 | PGE | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-04-16 |  |  | 2021-04-30 | 2021-04-30 | 10 | 2021-04-30 | 18 | 2021-05-04 | 3 | [19 empty] | 2021-05-04 | [7 empty] | 0 | [29 empty] | 2021-05-12
120882338 | 1722 | 94941 | PGE | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-04-26 |  |  | 2021-05-10 | 2021-05-10 | 10 | 2021-05-25 | 21 | 2021-06-02 | 5 | [19 empty] | 2021-06-02 | [7 empty] | 0 | [29 empty] | 2021-06-04
120885594 | 1723 | 95713 | PGE | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-04-26 | 2021-05-10 |  | 2021-05-10 | 2021-05-10 | 10 | 2021-05-24 | 20 | 2021-06-01 | 5 | [15 empty] | 2021-06-01 | 2021-06-01 | 0 | 2021-06-01 | 2021-06-01 | 0 | [6 empty] | 0 | [29 empty] | 2021-06-01
121355006 | 1724 | 94803 | PGE | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-05-18 |  |  | 2021-05-25 | 2021-05-25 | 5 | 2021-05-25 | 5 | 2021-09-13 | 76 | [15 empty] | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-09-03 | 71 | [6 empty] | 0 | [29 empty] | 2021-09-13
121443452 | 1725 | 94563 | PGE | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-06-02 |  |  | 2021-06-16 | 2021-06-16 | 10 | 2021-06-16 | 10 | 2021-06-30 | 10 | [19 empty] | 2021-06-30 | [7 empty] | 0 | [29 empty] | 2021-06-30
121592973 | 1726 | 95667 | PGE | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-06-24 |  |  | 2021-07-09 | 2021-07-09 | 10 | 2021-07-09 | 10 | 2021-07-23 | 10 | [15 empty] | 2021-07-23 | 2021-07-28 | 3 | 2021-07-28 | 2021-07-28 | 0 | [6 empty] | 0 | [29 empty] | 2021-07-28
121807258 | 1727 | 94025 | PGE | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-07-28 |  |  | 2021-08-03 | 2021-08-03 | 4 | 2021-08-12 | 11 | 2021-08-13 | 1 | [15 empty] | 2021-08-13 | 2021-08-13 | 0 | 2021-08-13 | 2021-10-05 | 36 | [6 empty] | 0 | [29 empty] | 2021-10-06
121891950 | 1728 | 95949 | PGE | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-08-12 |  |  | 2021-08-24 | 2021-08-24 | 8 | 2021-08-24 | 8 | 2021-09-08 | 10 | [19 empty] | 2021-09-22 | [7 empty] | 0 | [29 empty] | 2021-09-22
121955970 | 1729 | 95018 | PGE | Non-NEM | Non-Export | Commercial | Storage | 5 |  | 2021-08-25 |  |  | 2021-09-09 | 2021-09-09 | 10 | 2021-09-09 | 10 | 2021-09-10 | 1 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | 2021-09-10 | 0 | [6 empty] | 0 | [29 empty] | 2021-09-16
122079395 | 1730 | 95229 | PGE | Non-NEM | Inadvertent Export | Commercial | Storage | 5 |  | 2021-09-21 | 2021-10-05 |  | 2021-10-05 | 2021-10-05 | 10 | 2021-10-19 | 20 | 2021-10-26 | 5 | [27 empty] | 0 | [29 empty] | 2021-11-02
120633074 | 1731 | 94536 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 5 |  | 2021-03-11 |  |  | 2021-03-25 | 2021-03-25 | 10 | 2021-03-25 | 10 | 2021-04-14 | 14 | [27 empty] | 0
120661827 | 1732 | 94941 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 5 |  | 2021-03-19 |  |  | 2021-04-01 | 2021-04-01 | 9 | 2021-04-01 | 9 | 2021-04-07 | 4 | [27 empty] | 0
120794130 | 1733 | 95006 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 5 |  | 2021-04-12 |  |  | 2021-04-17 | 2021-04-17 | 4 | 2021-04-17 | 4 | 2021-04-19 | 0 | [19 empty] | 2021-04-12 | [7 empty] | 0
120744638 | 1734 | 94970 | PGE | Non-NEM | Non-Export | Study in Progress | Storage | 5 |  | 2021-04-05 | 2021-04-19 |  | 2021-04-19 | 2021-04-19 | 10 | 2021-05-20 | 33 | 2021-06-03 | 9 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-06-03 | 32 | [6 empty] | 0
121912129 | 1735 | 94558 | PGE | Non-NEM | Non-Export | Study in Progress | Storage | 5.5 |  | 2021-08-17 | 2021-08-31 |  | 2021-08-31 | 2021-08-31 | 10 | 2021-09-15 | 20 | [29 empty] | 0
120497288 | 1736 | 95018 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 10 |  | 2021-02-03 |  |  | 2021-02-16 | 2021-02-16 | 8 | 2021-02-16 | 8 | 2021-02-16 | 0 | [27 empty] | 0
120672243 | 1737 | 93644 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 10 |  | 2021-03-22 |  |  | 2021-04-05 | 2021-04-05 | 10 | 2021-12-08 | 181 | [29 empty] | 0
120741010 | 1738 | 95959 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 10 |  | 2021-04-04 |  |  | 2021-04-14 | 2021-04-14 | 7 | 2021-04-14 | 27 | 2021-04-25 | 8 | [15 empty] | 2021-04-25 | 2021-04-25 | 0 | 2021-04-25 | 2021-06-29 | 45 | [6 empty] | 0
120594813 | 1739 | 95070 | PGE | Non-NEM | Non-Export | Application Review in Progress | Storage | 10 |  | 2021-03-03 | 2021-03-17 |  | 2021-03-17 | 2021-03-17 | 10 | [31 empty] | 0
120400357 | 1740 | 96021 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-07 |  |  | 2021-01-12 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-26 | 9 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-03-11 | 40 | [6 empty] | 0 | [29 empty] | 2021-10-20
120401555 | 1741 | 95650 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-07 |  |  | 2021-01-12 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-14 | 2 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-02-12 | 22 | [6 empty] | 0 | [29 empty] | 2021-08-11
120435015 | 1742 | 94010 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-15 | 2021-01-26 |  | 2021-01-26 | 2021-01-26 | 6 | 2021-01-29 | 9 | 2021-02-01 | 1 | [15 empty] | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 2021-08-07 | 135 | [6 empty] | 0 | [29 empty] | 2021-08-13
120451197 | 1743 | 95033 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-20 |  |  | 2021-01-26 | 2021-01-26 | 4 | 2021-01-26 | 4 | 2021-01-26 | 0 | [27 empty] | 0 | [29 empty] | 2021-02-09
120452364 | 1744 | 94549 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-21 |  |  | 2021-01-26 | 2021-01-26 | 3 | 2021-01-26 | 3 | 2021-01-28 | 2 | [27 empty] | 0 | [29 empty] | 2021-02-09
120461884 | 1745 | 95633 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-25 |  |  | 2021-02-05 | 2021-02-05 | 9 | 2021-02-05 | 9 | 2021-02-12 | 5 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | 2021-03-30 | 36 | [6 empty] | 0 | [29 empty] | 2021-05-05
120461885 | 1746 | 94028 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-25 |  |  | 2021-02-08 | 2021-02-08 | 10 | 2021-02-08 | 10 | 2021-02-12 | 4 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-04-13 | 45 | [6 empty] | 0 | [29 empty] | 2021-07-12
120462283 | 1747 | 94903 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-25 | 2021-02-03 |  | 2021-02-03 | 2021-02-03 | 7 | 2021-03-01 | 24 | 2021-03-03 | 2 | [27 empty] | 0 | [29 empty] | 2021-03-10
120462480 | 1748 | 95006 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-25 |  |  | 2021-02-03 | 2021-02-03 | 7 | 2021-02-03 | 7 | 2021-02-04 | 1 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-02-11 | 6 | [6 empty] | 0 | [29 empty] | 2021-07-30
120462603 | 1749 | 94939 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-25 |  |  | 2021-02-03 | 2021-02-03 | 7 | 2021-02-03 | 7 | 2021-02-05 | 2 | [27 empty] | 0 | [29 empty] | 2021-02-11
120464496 | 1750 | 93420 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-26 |  |  | 2021-02-03 | 2021-02-03 | 6 | 2021-02-03 | 6 | 2021-02-04 | 1 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-02-03 | 0 | [6 empty] | 0 | [29 empty] | 2021-04-06
120466021 | 1751 | 95667 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-01-26 |  |  | 2021-02-08 | 2021-02-08 | 9 | 2021-02-08 | 9 | 2021-02-08 | 0 | [27 empty] | 0 | [29 empty] | 2021-03-03
120486478 | 1752 | 94062 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-01 |  |  | 2021-02-08 | 2021-02-08 | 5 | 2021-02-08 | 5 | 2021-02-12 | 4 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-03-25 | 32 | [6 empty] | 0 | [29 empty] | 2021-05-28
120486725 | 1753 | 95726 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-01 |  |  | 2021-02-13 | 2021-02-13 | 9 | 2021-02-13 | 9 | 2021-02-23 | 5 | [15 empty] | 2021-02-13 | 2021-02-13 | 0 | 2021-02-13 | 2021-04-02 | 33 | [6 empty] | 0 | [29 empty] | 2021-04-11
120490162 | 1754 | 93460 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-02 |  |  | 2021-02-13 | 2021-02-13 | 8 | 2021-02-13 | 8 | 2021-02-24 | 6 | [27 empty] | 0 | [29 empty] | 2021-06-03
120492171 | 1755 | 94901 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-02 |  |  | 2021-02-16 | 2021-02-16 | 9 | 2021-02-16 | 9 | 2021-02-16 | 0 | [15 empty] | 2021-02-16 | 2021-02-16 | 0 | 2021-02-16 | 2021-03-17 | 21 | [6 empty] | 0 | [29 empty] | 2021-10-20
120496874 | 1756 | 94028 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-03 |  |  | 2021-02-16 | 2021-02-16 | 8 | 2021-02-16 | 8 | 2021-02-18 | 2 | [27 empty] | 0 | [29 empty] | 2021-02-23
120501286 | 1757 | 95667 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-04 |  |  | 2021-02-18 | 2021-02-18 | 9 | 2021-02-18 | 9 | 2021-03-10 | 14 | [19 empty] | 2021-03-07 | [7 empty] | 0 | [6 empty] | 2021-04-01 | 2021-04-01 | 0 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 |  | 2021-04-01 | 0
120503211 | 1758 | 95762 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-05 |  |  | 2021-02-22 | 2021-02-22 | 10 | 2021-02-22 | 10 | 2021-02-25 | 3 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-06-24 | 87 | [6 empty] | 0 | [29 empty] | 2021-07-08
120503916 | 1759 | 95070 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-05 |  |  | 2021-02-22 | 2021-02-22 | 10 | 2021-02-22 | 10 | 2021-03-02 | 6 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-02 | 6 | [6 empty] | 0 | [29 empty] | 2021-03-12
120524726 | 1760 | 93420 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-10 |  |  | 2021-02-22 | 2021-02-22 | 7 | 2021-02-22 | 7 | 2021-02-22 | 0 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-01 | 5 | [5 empty] | 2021-03-17 | 2021-03-17 | 2021-03-24 | 5 | [27 empty] | 2021-04-06
120530915 | 1761 | 95425 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-12 |  |  | 2021-02-23 | 2021-02-23 | 6 | 2021-02-23 | 6 | 2021-04-05 | 29 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-05-27 | 67 | [6 empty] | 0 | [29 empty] | 2021-09-08
120534279 | 1762 | 95728 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-14 |  |  | 2021-02-23 | 2021-02-23 | 5 | 2021-02-23 | 5 | 2021-02-23 | 0 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-05-26 | 66 | [6 empty] | 0 | [29 empty] | 2021-08-24
120540812 | 1763 | 95248 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-17 |  |  | 2021-02-25 | 2021-02-25 | 6 | 2021-02-25 | 6 | 2021-03-03 | 4 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-18 | 15 | [6 empty] | 0 | [29 empty] | 2021-08-09
120552024 | 1764 | 95945 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-18 |  |  | 2021-02-25 | 2021-02-25 | 5 | 2021-02-25 | 5 | 2021-03-16 | 13 | [25 empty] | 2021-02-18 | 2021-03-17 | 2021-02-18 | 2021-03-24 | 24 | [27 empty] | 2021-03-25
120558070 | 1765 | 95521 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-21 | 2021-02-25 |  | 2021-02-25 | 2021-02-25 | 3 | 2021-02-26 | 4 | 2021-03-01 | 1 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-17 | 12 | [6 empty] | 0 | [29 empty] | 2021-03-30
120565306 | 1766 | 95603 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-22 |  |  | 2021-03-03 | 2021-03-03 | 7 | 2021-03-03 | 7 | 2021-03-08 | 3 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-03 | 0 | [6 empty] | 0 | [29 empty] | 2021-03-10
120575609 | 1767 | 95975 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-25 |  |  | 2021-03-08 | 2021-03-08 | 7 | 2021-03-08 | 7 | 2021-03-09 | 1 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-04-19 | 30 | [6 empty] | 0 | [29 empty] | 2021-07-09
120580616 | 1768 | 95120 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-26 |  |  | 2021-03-09 | 2021-03-09 | 7 | 2021-03-09 | 7 | 2021-03-22 | 9 | [15 empty] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | 2021-03-30 | 15 | [6 empty] | 0 | [29 empty] | 2021-09-29
120581185 | 1769 | 95033 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-02-26 |  |  | 2021-03-09 | 2021-03-09 | 7 | 2021-03-09 | 7 | 2021-03-11 | 2 | [27 empty] | 0 | [29 empty] | 2021-03-17
120599769 | 1770 | 93420 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-03 | 2021-03-15 |  | 2021-03-12 | 2021-03-12 | 7 | 2021-03-17 | 10 | 2021-03-23 | 4 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-18 | 1 | [6 empty] | 0 | [29 empty] | 2021-08-24
120600141 | 1771 | 95033 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-03 |  |  | 2021-03-15 | 2021-03-15 | 8 | 2021-03-15 | 8 | 2021-03-17 | 2 | [19 empty] | 2021-03-03 | [7 empty] | 0 | [29 empty] | 2021-04-07
120602655 | 1772 | 94553 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-04 |  |  | 2021-03-17 | 2021-03-17 | 9 | 2021-03-17 | 9 | 2021-03-23 | 4 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-24 | 5 | [6 empty] | 0 | [29 empty] | 2021-04-07
120606001 | 1773 | 95667 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-05 |  |  | 2021-03-22 | 2021-03-22 | 11 | 2021-07-08 | 87 | 2021-07-28 | 14 | [19 empty] | 2021-07-26 | [7 empty] | 0 | [29 empty] | 2021-07-28
120611909 | 1774 | 94941 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-08 |  |  | 2021-03-22 | 2021-03-22 | 10 | 2021-03-22 | 10 | 2021-03-29 | 5 | [15 empty] | 2021-03-29 | 2021-04-01 | 3 | 2021-04-01 | 2021-04-13 | 8 | [6 empty] | 0 | [29 empty] | 2021-04-29
120628659 | 1775 | 94549 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-10 |  |  | 2021-03-24 | 2021-03-24 | 10 | 2021-03-24 | 10 | 2021-04-01 | 6 | [19 empty] | 2021-03-25 | [7 empty] | 0 | [29 empty] | 2021-04-07
120628690 | 1776 | 95685 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-10 |  |  | 2021-03-24 | 2021-03-24 | 10 | 2021-03-24 | 10 | 2021-04-01 | 6 | [19 empty] | 2021-03-25 | [7 empty] | 0 | [29 empty] | 2021-05-04
120633085 | 1777 | 95018 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-11 |  |  | 2021-03-25 | 2021-03-25 | 10 | 2021-03-25 | 10 | 2021-04-01 | 5 | [19 empty] | 2021-03-11 | [7 empty] | 0 | [29 empty] | 2021-05-05
120635500 | 1778 | 95033 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-11 |  |  | 2021-03-25 | 2021-03-25 | 10 | 2021-03-25 | 10 | 2021-04-06 | 8 | [19 empty] | 2021-03-11 | [7 empty] | 0 | [29 empty] | 2021-05-05
120635575 | 1779 | 95033 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-11 |  |  | 2021-03-25 | 2021-03-25 | 10 | 2021-03-25 | 10 | 2021-04-06 | 8 | [19 empty] | 2021-03-11 | [7 empty] | 0 | [29 empty] | 2021-05-05
120654562 | 1780 | 94402 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-17 |  |  | 2021-03-31 | 2021-03-31 | 10 | 2021-03-31 | 10 | 2021-04-07 | 5 | [19 empty] | 2021-03-17 | [7 empty] | 0 | [29 empty] | 2021-05-06
120685662 | 1781 | 93401 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-24 |  |  | 2021-04-07 | 2021-04-07 | 10 | 2021-04-07 | 10 | 2021-04-09 | 2 | [19 empty] | 2021-07-06 | [7 empty] | 0 | [29 empty] | 2021-07-06
120689723 | 1782 | 95033 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-25 |  |  | 2021-04-08 | 2021-04-08 | 10 | 2021-04-08 | 10 | 2021-04-16 | 6 | [19 empty] | 2021-03-25 | [7 empty] | 0 | [29 empty] | 2021-05-07
120696381 | 1783 | 93420 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-26 |  |  | 2021-04-02 | 2021-04-02 | 5 | 2021-04-02 | 5 | 2021-04-09 | 5 | [19 empty] | 2021-04-02 | [7 empty] | 0 | [29 empty] | 2021-04-15
120704109 | 1784 | 95501 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-03-28 |  |  | 2021-04-09 | 2021-04-09 | 9 | 2021-04-29 | 32 | 2021-05-05 | 5 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-06-29 | 38 | [6 empty] | 0 | [29 empty] | 2021-09-09
120726826 | 1785 | 95614 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-01 |  |  | 2021-04-14 | 2021-04-14 | 9 | 2021-04-14 | 9 | 2021-04-20 | 4 | [15 empty] | 2021-04-14 | 2021-04-14 | 0 | 2021-04-14 | 2021-05-03 | 13 | [6 empty] | 0 | [29 empty] | 2021-06-02
120742775 | 1786 | 95033 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-05 |  |  | 2021-04-16 | 2021-04-16 | 9 | 2021-04-16 | 9 | 2021-04-21 | 3 | [27 empty] | 0 | [29 empty] | 2021-04-29
120750931 | 1787 | 95033 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-06 | 2021-04-17 |  | 2021-04-17 | 2021-04-17 | 8 | 2021-05-03 | 19 | 2021-05-03 | 0 | [27 empty] | 0 | [29 empty] | 2021-05-11
120823253 | 1788 | 95959 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-15 |  |  | 2021-04-29 | 2021-04-29 | 10 | 2021-05-12 | 19 | 2021-05-12 | 0 | [19 empty] | 2021-05-12 | [7 empty] | 0 | [29 empty] | 2021-05-12
120841745 | 1789 | 93446 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-19 |  |  | 2021-05-03 | 2021-05-03 | 10 | 05/07/2021 | 134 | 2021-06-04 | 21 | [19 empty] | 2021-06-04 | [7 empty] | 0 | [29 empty] | 2021-10-27
120863835 | 1790 | 95065 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-22 |  |  | 2021-05-06 | 2021-05-06 | 10 | 2021-05-12 | 14 | 2021-05-12 | 0 | [19 empty] | 2021-05-12 | [7 empty] | 0 | [29 empty] | 2021-05-12
120882323 | 1791 | 94708 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-26 |  |  | 2021-05-10 | 2021-05-10 | 10 | 2021-05-25 | 21 | 2021-06-16 | 15 | [19 empty] | 2021-06-16 | [7 empty] | 0 | [29 empty] | 2021-06-16
120891705 | 1792 | 94552 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-27 |  |  | 2021-05-11 | 2021-05-11 | 10 | 2021-05-18 | 15 | 2021-05-26 | 6 | [19 empty] | 2021-05-26 | [7 empty] | 0 | [29 empty] | 2021-05-28
120893493 | 1793 | 95667 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-28 |  |  | 2021-05-12 | 2021-05-12 | 10 | 2021-05-12 | 10 | 2021-05-20 | 6 | [27 empty] | 0 | [29 empty] | 2021-05-20
120910166 | 1794 | 95959 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-04-30 |  |  | 2021-05-14 | 2021-05-14 | 10 | 2021-05-14 | 14 | 2021-05-18 | 3 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | 2021-06-22 | 24 | [6 empty] | 0 | [29 empty] | 2021-06-23
121030318 | 1795 | 95033 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-10 |  |  | 2021-05-24 | 2021-05-24 | 10 | 2021-05-24 | 34 | 2021-06-09 | 13 | [19 empty] | 2021-06-09 | [7 empty] | 0 | [29 empty] | 2021-06-30
121334719 | 1796 | 95003 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-14 | 2021-05-25 |  | 2021-05-25 | 2021-05-25 | 7 | 2021-06-03 | 13 | 2021-06-08 | 3 | [15 empty] | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-06-08 | 0 | [6 empty] | 0 | [29 empty] | 2021-06-08
121334767 | 1797 | 95004 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-14 | 2021-05-25 |  | 2021-05-25 | 2021-05-25 | 7 | 2021-06-03 | 13 | 2021-06-07 | 2 | [19 empty] | 2021-05-14 | [7 empty] | 0 | [29 empty] | 2021-06-07
121351089 | 1798 | 95065 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-18 |  |  | 2021-05-28 | 2021-05-28 | 8 | 2021-05-28 | 8 | 2021-06-02 | 2 | [15 empty] | 2021-06-02 | 2021-06-17 | 11 | 2021-06-17 | 2021-06-01 | -12 | [6 empty] | 0 | [29 empty] | 2021-06-17
121364798 | 1799 | 95033 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-20 | 2021-06-01 |  | 2021-06-01 | 2021-06-01 | 7 | 2021-06-15 | 17 | 2021-06-24 | 7 | [15 empty] | 2021-06-24 | 2021-06-25 | 1 | 2021-06-25 | 2021-06-25 | 0 | [6 empty] | 0 | [29 empty] | 2021-06-25
121391379 | 1800 | 95688 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-24 |  |  | 2021-06-04 | 2021-06-04 | 8 | 2021-07-30 | 47 | 2021-08-11 | 8 | [15 empty] | 2021-07-30 | 2021-07-30 | 0 | 2021-07-30 | 2021-08-11 | 8 | [6 empty] | 0 | [29 empty] | 2021-08-12
121396580 | 1801 | 95120 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-05-25 |  |  | 2021-06-01 | 2021-06-01 | 4 | 2021-06-01 | 4 | 2021-06-11 | 8 | [15 empty] | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-09-21 | 70 | [6 empty] | 0 | [6 empty] | 2021-09-21 | 2021-09-29 | 6 | [15 empty] | 2021-09-21 | 2021-09-29 | 6 | 2021-09-29 |  | 2021-09-29 | 0
121534459 | 1802 | 95066 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-06-14 |  |  | 2021-06-25 | 2021-06-25 | 9 | 2021-06-25 | 9 | 2021-06-30 | 3 | [27 empty] | 0 | [29 empty] | 2021-07-28
121547656 | 1803 | 95033 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-06-16 | 2021-06-21 |  | 2021-06-21 | 2021-06-21 | 3 | 2021-06-22 | 4 | 2021-06-23 | 1 | [27 empty] | 0 | [29 empty] | 2021-07-09
121555775 | 1804 | 95060 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-06-17 |  |  | 2021-06-21 | 2021-06-21 | 2 | 2021-06-21 | 2 | 2021-06-23 | 2 | [27 empty] | 0 | [29 empty] | 2021-06-29
121596606 | 1805 | 95709 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-06-24 | 2021-06-29 |  | 2021-06-29 | 2021-06-29 | 3 | 2021-07-12 | 11 | 2021-07-14 | 2 | [19 empty] | 2021-06-29 | [7 empty] | 0 | [29 empty] | 2021-07-14
121646889 | 1806 | 95033 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-01 | 2021-07-06 |  | 2021-07-06 | 2021-07-06 | 2 | 2021-07-07 | 3 | 2021-07-08 | 1 | [15 empty] | 2021-07-08 | 2021-07-13 | 3 | 2021-07-13 | 2021-07-13 | 0 | [6 empty] | 0 | [29 empty] | 2021-07-14
121647350 | 1807 | 93637 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-01 |  |  | 2021-07-06 | 2021-07-06 | 2 | 2021-07-06 | 2 | 2021-07-26 | 14 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-07-28 | 2 | [6 empty] | 0 | [29 empty] | 2021-09-27
121683273 | 1808 | 94605 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-08 |  |  | 2021-07-13 | 2021-07-13 | 3 | 2021-07-13 | 3 | 2021-07-20 | 5 | [19 empty] | 2021-07-08 | [7 empty] | 0 | [29 empty] | 2021-07-20
121718626 | 1809 | 95503 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-13 |  |  | 2021-07-15 | 2021-07-15 | 2 | 2021-07-15 | 2 | 2021-08-02 | 12 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-10-29 | 75 | [6 empty] | 0 | [29 empty] | 2021-10-29
121764759 | 1810 | 95709 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-20 | 2021-07-30 |  | 2021-07-30 | 2021-07-30 | 8 | 2021-07-30 | 8 | 2021-08-13 | 10 | [15 empty] | 2021-08-13 | 2021-08-13 | 0 | 2021-08-13 | 2021-08-13 | 0 | [6 empty] | 0 | [29 empty] | 2021-08-13
121798139 | 1811 | 93637 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-26 | 2021-08-04 |  | 2021-08-04 | 2021-08-04 | 7 | 2021-08-19 | 18 | 2021-09-07 | 12 | [15 empty] | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-09-29 | 16 | [6 empty] | 0 | [29 empty] | 2021-10-28
121799751 | 1812 | 93637 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-26 | 2021-08-02 |  | 2021-07-29 | 2021-07-29 | 3 | 2021-08-23 | 20 | 2021-09-13 | 14 | [15 empty] | 2021-09-13 | 2021-09-29 | 12 | 2021-09-29 | 2021-09-29 | 0 | [6 empty] | 0 | [29 empty] | 2021-11-04
121807533 | 1813 | 93446 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-28 |  |  | 2021-08-03 | 2021-08-03 | 4 | 2021-08-03 | 4 | 2021-08-04 | 1 | [19 empty] | 2021-08-05 | [7 empty] | 0 | [29 empty] | 2021-08-23
121820795 | 1814 | 95005 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-07-30 |  |  | 2021-08-03 | 2021-08-03 | 2 | 2021-08-03 | 2 | 2021-08-04 | 1 | [19 empty] | 2021-07-30 | [7 empty] | 0 | [29 empty] | 2021-09-28
121844198 | 1815 | 93465 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-04 | 2021-08-13 |  | 2021-08-13 | 2021-08-13 | 7 | 2021-08-17 | 9 | 2021-08-18 | 1 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | 2021-08-19 | 1 | [6 empty] | 0 | [29 empty] | 2021-08-19
121847518 | 1816 | 94951 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-05 |  |  | 2021-08-10 | 2021-08-10 | 3 | 2021-08-10 | 3 | 2021-08-31 | 15 | [19 empty] | 2021-08-05 | [7 empty] | 0 | [29 empty] | 2021-08-31
121864231 | 1817 | 94611 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-09 |  |  | 2021-08-12 | 2021-08-12 | 3 | 2021-08-12 | 3 | 2021-08-17 | 3 | [19 empty] | 2021-08-09 | [7 empty] | 0 | [29 empty] | 2021-08-17
121916429 | 1818 | 95409 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-18 | 2021-09-01 |  | 2021-09-01 | 2021-09-01 | 10 | 2021-09-16 | 20 | 2021-10-20 | 24 | [15 empty] | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01 | 2021-10-04 | 22 | [6 empty] | 0 | [29 empty] | 2021-10-20
121918126 | 1819 | 95409 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-18 |  |  | 2021-08-24 | 2021-08-24 | 4 | 2021-08-24 | 4 | 2021-11-08 | 53 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | 2021-09-24 | 22 | [6 empty] | 0 | [29 empty] | 2021-11-08
121923652 | 1820 | 94028 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-20 | 2021-08-24 |  | 2021-08-24 | 2021-08-24 | 2 | 2021-08-24 | 2 | 2021-09-13 | 13 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-09-13 | 0 | [6 empty] | 0 | [29 empty] | 2021-09-21
121926388 | 1821 | 95476 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-20 |  |  | 2021-09-03 | 2021-09-03 | 10 | 2021-09-03 | 10 | 2021-09-27 | 15 | [19 empty] | 2021-08-20 | [7 empty] | 0 | [29 empty] | 2021-09-27
121944227 | 1822 | 95033 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-24 |  |  | 2021-09-08 | 2021-09-08 | 10 | 2021-09-08 | 10 | 2021-09-13 | 3 | [19 empty] | 2021-08-24 | [7 empty] | 0 | [29 empty] | 2021-10-18
121960215 | 1823 | 94611 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-08-26 |  |  | 2021-08-30 | 2021-08-30 | 2 | 2021-08-30 | 2 | 2021-09-03 | 4 | [19 empty] | 2021-08-26 | [7 empty] | 0 | [29 empty] | 2021-09-14
122012276 | 1824 | 95033 | PGE | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-08 |  |  | 2021-10-15 | 2021-10-15 | 27 | 2021-10-15 | 27 | 2021-10-18 | 1 | [19 empty] | 2021-09-08 | [7 empty] | 0 | [29 empty] | 2021-10-22
122044618 | 1825 | 94038 | PGE | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-13 |  |  | 2021-10-15 | 2021-10-15 | 24 | 2021-10-15 | 24 | 2021-10-26 | 7 | [15 empty] | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26 | 2021-10-26 | 0 | [6 empty] | 0 | [29 empty] | 2021-10-26
122049051 | 1826 | 95076 | PGE | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-14 | 2021-10-15 |  | 2021-10-15 | 2021-10-15 | 23 | 2021-10-20 | 26 | 2021-11-01 | 8 | [27 empty] | 0 | [29 empty] | 2021-11-10
122057147 | 1827 | 95570 | PGE | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-16 | 2021-09-28 |  | 2021-09-28 | 2021-09-28 | 8 | 2021-10-08 | 16 | 2021-10-14 | 4 | [15 empty] | 2021-10-14 | 2021-10-14 | 0 | 2021-10-14 | 2021-10-14 | 0 | [6 empty] | 0 | [29 empty] | 2021-11-15
122063879 | 1828 | 95370 | PGE | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-17 | 2021-09-21 |  | 2021-09-21 | 2021-09-21 | 2 | 2021-09-22 | 3 | 2021-10-07 | 11 | [15 empty] | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-10-11 | 2 | [6 empty] | 0 | [29 empty] | 2021-10-12
122071072 | 1829 | 95018 | PGE | Non-NEM | Inadvertent Export | Commercial | Storage | 10 |  | 2021-09-19 |  |  | 2021-10-15 | 2021-10-15 | 19 | 2021-10-15 | 19 | 2021-10-19 | 2 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-10-19 | 0 | [6 empty] | 0 | [29 empty] | 2021-10-28
122137265 | 1830 | 95014 | PGE | Non-NEM | Non-Export | Commercial | Storage | 10 |  | 2021-10-01 | 2021-10-04 |  | 2021-10-04 | 2021-10-04 | 1 | 2021-10-08 | 5 | 2021-10-08 | 0 | [27 empty] | 0 | [29 empty] | 2021-10-08
120241570 | 1831 | 95033 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2020-12-30 |  |  | 2021-01-08 | 2021-01-08 | 6 | 2021-01-08 | 6 | 2021-01-11 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-01-20 | 7 | [6 empty] | 0
120241718 | 1832 | 95030 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2020-12-30 |  |  | 2021-01-08 | 2021-01-08 | 6 | 2021-01-08 | 6 | 2021-01-11 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-01-20 | 7 | [6 empty] | 0
120399509 | 1833 | 94611 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-01-07 |  |  | 2021-01-12 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-19 | 4 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-11-23 | 219 | [6 empty] | 0
120420080 | 1834 | 93446 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-01-11 |  |  | 2021-01-22 | 2021-01-22 | 8 | 2021-01-22 | 8 | 2021-02-01 | 6 | [15 empty] | 2021-01-22 | 2021-01-22 | 0 | 2021-01-22 | 2021-02-01 | 6 | [6 empty] | 0
120426398 | 1835 | 94586 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-01-13 |  |  | 2021-01-25 | 2021-01-25 | 7 | 2021-01-25 | 7 | 2021-01-25 | 0 | [15 empty] | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | 2021-02-11 | 13 | [6 empty] | 0
120435060 | 1836 | 94611 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-01-15 |  |  | 2021-01-25 | 2021-01-25 | 5 | 2021-01-25 | 5 | [17 empty] | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | [8 empty] | 0
120486650 | 1837 | 94605 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-02-01 |  |  | 2021-02-10 | 2021-02-10 | 7 | 2021-02-10 | 7 | 2021-02-24 | 9 | [15 empty] | 2021-02-10 | 2021-02-10 | 0 | 2021-02-10 | 2021-11-11 | 191 | [6 empty] | 0
120502415 | 1838 | 95667 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-02-05 |  |  | 2021-02-22 | 2021-02-22 | 10 | 2021-02-22 | 10 | 2021-04-09 | 34 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-04-23 | 44 | [6 empty] | 0
120529429 | 1839 | 95971 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-02-12 |  |  | 2021-02-22 | 2021-02-22 | 5 | 2021-02-22 | 5 | 2021-03-03 | 7 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-05-25 | 66 | [6 empty] | 0
120599715 | 1840 | 93465 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-03-03 | 2021-03-15 |  | 2021-03-15 | 2021-03-15 | 8 | 2021-03-17 | 10 | 2021-03-23 | 4 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-18 | 1 | [6 empty] | 0
120659935 | 1841 | 94960 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-03-18 |  |  | 2021-04-01 | 2021-04-01 | 10 | 2021-04-01 | 10 | 2021-04-07 | 4 | [27 empty] | 0
120692826 | 1842 | 93454 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-03-25 |  |  | 2021-03-29 | 2021-03-29 | 2 | 2021-04-15 | 15 | 2021-04-25 | 6 | [15 empty] | 2021-04-25 | 2021-04-25 | 0 | 2021-04-25 | 2021-08-02 | 68 | [6 empty] | 0
120702643 | 1843 | 96061 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-03-28 |  |  | 2021-04-09 | 2021-04-09 | 9 | 2021-05-12 | 32 | 2021-06-09 | 19 | [19 empty] | 2021-06-15 | [7 empty] | 0
120751731 | 1844 | 95667 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-04-06 |  |  | 2021-04-13 | 2021-04-13 | 5 | 2021-04-13 | 5 | 2021-04-13 | 0 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | [8 empty] | 0
120866313 | 1845 | 93420 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-04-22 |  |  | 2021-05-06 | 2021-05-06 | 10 | 2021-05-17 | 17 | 2021-06-08 | 15 | [19 empty] | 2021-06-08 | [7 empty] | 0
120875910 | 1846 | 94062 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-04-23 |  |  | 2021-05-07 | 2021-05-07 | 10 | 2021-05-12 | 13 | 2021-07-02 | 36 | [19 empty] | 2021-07-02 | [7 empty] | 0
120915563 | 1847 | 94929 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-05-02 |  |  | 2021-05-14 | 2021-05-14 | 9 | 2021-05-14 |  | 2021-05-17 | 2 | [15 empty] | 2021-05-17 | 2021-05-17 | 0 | 2021-05-17 | [8 empty] | 0
121397483 | 1848 | 95503 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-05-25 | 2021-06-01 |  | 2021-06-01 | 2021-06-01 | 4 | 2021-06-28 | 23 | 2021-07-15 | 12 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-07-20 | 3 | [6 empty] | 0
121435140 | 1849 | 95327 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-06-01 |  |  | 2021-06-14 | 2021-06-14 | 9 | 2021-06-14 | 9 | 2021-06-30 | 12 | [15 empty] | 2021-06-30 | 2021-06-30 | 0 | 2021-06-30 | 2021-07-27 | 18 | [6 empty] | 0
121446017 | 1850 | 94037 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-06-02 |  |  | 2021-06-16 | 2021-06-16 | 10 | 2021-06-16 | 10 | 2021-06-23 | 5 | [15 empty] | 2021-06-16 | 2021-06-16 | 1 | 2021-06-16 | 2021-10-05 | 77 | [6 empty] | 0
121523763 | 1851 | 95503 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-06-12 |  |  | 2021-06-24 | 2021-06-24 | 8 | 2021-06-24 | 8 | 2021-07-16 | 15 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-16 | 2021-07-20 | 2 | [6 empty] | 0
121544402 | 1852 | 95553 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-06-16 |  |  | 2021-06-29 | 2021-06-29 | 9 | 2021-06-29 | 9 | 2021-07-20 | 14 | [15 empty] | 2021-07-20 | 2021-07-22 | 2 | 2021-07-22 | 2021-07-27 | 3 | [6 empty] | 0
121621784 | 1853 | 95633 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-06-28 |  |  | 2021-07-02 | 2021-07-02 | 4 | 2021-07-02 | 4 | 2021-07-16 | 9 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-16 | [8 empty] | 0
121718164 | 1854 | 94611 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-07-12 |  |  | 2021-07-26 | 2021-07-26 | 10 | 2021-07-26 | 10 | 2021-08-03 | 6 | [19 empty] | 2021-09-08 | [7 empty] | 0
121718642 | 1855 | 95033 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-07-12 |  |  | 2021-07-27 | 2021-07-27 | 11 | 2021-07-27 | 11 | 2021-07-30 | 3 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-07-30 | 3 | [6 empty] | 0
121770500 | 1856 | 96022 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-07-21 |  |  | 2021-07-26 | 2021-07-26 | 3 | 2021-07-26 | 3 | 2021-08-09 | 10 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | [8 empty] | 0
121882833 | 1857 | 95634 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-08-10 | 2021-08-17 |  | 2021-08-17 | 2021-08-17 | 5 | 2021-09-09 | 21 | 2021-09-13 | 2 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-09-14 | 1 | [6 empty] | 0
121882882 | 1858 | 95503 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-08-10 | 2021-08-13 |  | 2021-08-13 | 2021-08-13 | 3 | 2021-09-28 | 34 | 2021-09-29 | 1 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | [8 empty] | 0
121956334 | 1859 | 95333 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-08-25 | 2021-08-27 |  | 2021-08-27 | 2021-08-27 | 2 | 2021-09-14 | 13 | 2021-09-29 | 11 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | [8 empty] | 0
121956548 | 1860 | 93670 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-08-25 |  |  | 2021-09-07 | 2021-09-07 | 8 | 2021-09-07 | 8 | 2021-09-14 | 5 | [15 empty] | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-09-29 | 16 | [6 empty] | 0
121988775 | 1861 | 95573 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-09-02 |  |  | 2021-09-03 | 2021-09-03 | 1 | 2021-09-03 | 1 | 2021-09-27 | 15 | [15 empty] | 2021-09-27 | 2021-09-30 | 3 | 2021-09-30 | 2021-10-12 | 8 | [6 empty] | 0
121988822 | 1862 | 95464 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-09-02 | 2021-09-15 |  | 2021-09-15 | 2021-09-15 | 8 | 2021-09-16 | 9 | 2021-09-24 | 6 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | [8 empty] | 0
121996270 | 1863 | 95452 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-09-03 | 2021-09-15 |  | 2021-09-15 | 2021-09-15 | 7 | 2021-09-16 | 8 | 2021-09-24 | 6 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | [8 empty] | 0
122004126 | 1864 | 95453 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-09-06 | 2021-09-13 |  | 2021-09-13 | 2021-09-13 | 4 | 2021-09-15 | 6 | 2021-09-24 | 7 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | [8 empty] | 0
122012317 | 1865 | 95425 | PGE | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-08 |  |  | 2021-09-22 | 2021-09-22 | 10 | 2021-09-22 | 10 | 2021-10-05 | 9 | [15 empty] | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | 2021-10-05 | 0 | [6 empty] | 0
122033879 | 1866 | 94549 | PGE | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-10 |  |  | 2021-09-24 | 2021-09-24 | 10 | 2021-09-24 | 10 | 2021-10-13 | 13 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | 2021-10-13 | 13 | [6 empty] | 0
122057160 | 1867 | 94611 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 10 |  | 2021-09-16 | 2021-09-16 |  | 2021-09-16 | 2021-09-16 | 0 | 2021-09-23 | 5 | 2021-10-13 | 14 | [19 empty] | 2021-09-27 | [5 empty] | 2021-09-16 | 2021-09-27 | 2021-09-16 | 2021-10-12 | 18
122065208 | 1868 | 93608 | PGE | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-17 | 2021-09-20 |  | 2021-09-20 | 2021-09-20 | 1 | 2021-09-29 | 8 | 2021-10-04 | 3 | [15 empty] | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04 | [8 empty] | 0
122071209 | 1869 | 93667 | PGE | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-20 |  |  | 2021-10-04 | 2021-10-04 | 10 | 2021-10-04 | 10 | 2021-10-07 | 3 | [15 empty] | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-10-07 | 0 | [6 empty] | 0
122075833 | 1870 | 95524 | PGE | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-21 | 2021-10-04 |  | 2021-10-04 | 2021-10-04 | 9 | 2021-10-11 | 14 | 2021-10-14 | 3 | [15 empty] | 2021-10-14 | 2021-10-14 | 0 | 2021-10-14 | 2021-10-14 | 0 | [6 empty] | 0
122076307 | 1871 | 95503 | PGE | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-21 |  |  | 2021-10-05 | 2021-10-05 | 10 | 2021-10-05 | 10 | 2021-10-26 | 15 | [19 empty] | 2021-10-05 | [7 empty] | 0
122078975 | 1872 | 95570 | PGE | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-21 |  |  | 2021-10-05 | 2021-10-05 | 10 | 2021-10-05 | 10 | 2021-10-12 | 5 | [19 empty] | 2021-09-21 | [7 empty] | 0
122087525 | 1873 | 94556 | PGE | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-23 |  |  | 2021-10-07 | 2021-10-07 | 10 | 2021-10-07 | 10 | 2021-10-13 | 4 | [15 empty] | 2021-10-13 | 2021-10-13 | 0 | 2021-10-13 | 2021-10-13 | 0 | [6 empty] | 0
122106714 | 1874 | 93608 | PGE | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-27 | 2021-10-08 |  | 2021-10-08 | 2021-10-08 | 9 | 2021-10-26 | 21 | 2021-10-29 | 3 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | 2021-10-29 | 0 | [6 empty] | 0
122113215 | 1875 | 93608 | PGE | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-28 | 2021-10-04 |  | 2021-10-04 | 2021-10-04 | 4 | 2021-10-14 | 12 | 2021-10-18 | 2 | [19 empty] | 2021-09-28 | [7 empty] | 0
122125963 | 1876 | 93608 | PGE | Non-NEM | Inadvertent Export | IA in Progress | Storage | 10 |  | 2021-09-30 | 2021-10-12 |  | 2021-10-12 | 2021-10-12 | 8 | 2021-10-26 | 18 | 2021-10-29 | 3 | [15 empty] | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | 2021-10-29 | 0 | [6 empty] | 0
121590538 | 1877 | 95501 | PGE | Non-NEM | Non-Export | Implementation | Storage | 10 |  | 2021-06-24 |  |  | 2021-07-08 | 2021-07-08 | 9 | 2021-07-08 | 9 | 2021-07-23 | 11 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-09-25 | 55 | [6 empty] | 0
121975538 | 1878 | 93292 | PGE | Non-NEM | Non-Export | Implementation | Storage | 10 |  | 2021-08-31 |  |  | 2021-09-03 | 2021-09-03 | 3 | 2021-09-03 | 3 | 2021-09-15 | 7 | [15 empty] | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | 2021-10-06 | 15 | [6 empty] | 0
122057013 | 1879 | 94578 | PGE | Non-NEM | Non-Export | Implementation | Storage | 10 |  | 2021-09-16 |  |  | 2021-09-21 | 2021-09-21 | 3 | 2021-09-21 | 3 | 2021-09-23 | 2 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | 2021-09-29 | 6 | [6 empty] | 0
122068418 | 1880 | 95503 | PGE | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-09-18 |  |  |  | 0 |  | 2021-09-21 | 1 | 2021-09-28 | 5 | [19 empty] | 2021-09-18 | [7 empty] | 0
122083071 | 1881 | 95549 | PGE | Non-NEM | Inadvertent Export | Implementation | Storage | 10 |  | 2021-09-22 |  |  | 2021-09-24 | 2021-09-24 | 2 | 2021-09-24 | 2 | 2021-09-28 | 2 | [19 empty] | 2021-09-22 | [7 empty] | 0
120401954 | 1882 | 95006 | PGE | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-01-07 |  |  | 2021-01-15 | 2021-01-15 | 6 | 2021-01-15 | 6 | 2021-01-15 | 0 | [27 empty] | 0
120724474 | 1883 | 93953 | PGE | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-04-01 |  |  | 2021-04-13 | 2021-04-13 | 8 | 2021-04-13 | 8 | 2021-04-16 | 3 | [27 empty] | 0
121397437 | 1884 | 95713 | PGE | Non-NEM | Non-Export | Study in Progress | Storage | 10 |  | 2021-05-25 | 2021-05-28 |  | 2021-05-28 | 2021-05-28 | 3 | 2021-06-03 | 6 | 2021-06-07 | 2 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | [8 empty] | 0
122064147 | 1885 | 95033 | PGE | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-09-17 |  |  | 2021-10-01 | 2021-10-01 | 10 | 2021-10-01 | 10 | [29 empty] | 0
122071608 | 1886 | 95672 | PGE | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-09-20 |  |  | 2021-10-04 | 2021-10-04 | 10 | 2021-10-04 | 10 | [29 empty] | 0
122074460 | 1887 | 95503 | PGE | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-09-20 |  |  | 2021-09-23 | 2021-09-23 | 3 | 2021-09-23 | 3 | 2021-09-28 | 3 | [27 empty] | 0
122093171 | 1888 | 95503 | PGE | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-09-23 |  |  | 2021-10-06 | 2021-10-06 | 9 | 2021-10-06 | 9 | 2021-10-27 | 15 | [27 empty] | 0
122117764 | 1889 | 93670 | PGE | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-09-29 | 2021-10-13 |  | 2021-10-13 | 2021-10-13 | 10 | 2021-10-25 | 18 | 2021-10-25 | 0 | [19 empty] | 2021-09-29 | [7 empty] | 0
122117866 | 1890 | 95521 | PGE | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-09-29 |  |  | 2021-10-13 | 2021-10-13 | 10 | 2021-10-13 | 10 | [29 empty] | 0
122118524 | 1891 | 95519 | PGE | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-09-29 |  |  | 2021-10-13 | 2021-10-13 | 10 | 2021-10-13 | 10 | 2021-11-03 | 15 | [27 empty] | 0
122118548 | 1892 | 93608 | PGE | Non-NEM | Inadvertent Export | Study in Progress | Storage | 10 |  | 2021-09-29 | 2021-10-01 |  | 2021-10-01 | 2021-10-01 | 2 | 2021-10-15 | 12 | 2021-10-18 | 1 | [27 empty] | 0
120567793 | 1893 | 95407 | PGE | Non-NEM | Non-Export | Study in Progress | Solar PV | 11.52 |  | 2021-02-23 |  |  | 2021-03-09 | 2021-03-09 | 10 | 2021-03-09 | 10 | [29 empty] | 0
120722944 | 1894 | 95684 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 15 |  | 2021-04-01 |  |  | 2021-04-15 | 2021-04-15 | 10 | 2021-04-15 | 30 | 2021-04-20 | 4 | [27 empty] | 0
120741171 | 1895 | 95667 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 15 |  | 2021-04-05 |  |  | 2021-04-14 | 2021-04-14 | 7 | 2021-04-14 | 27 | 2021-04-25 | 8 | [15 empty] | 2021-04-25 | 2021-04-25 | 0 | 2021-04-25 | [8 empty] | 0
120911794 | 1896 | 95762 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 15 |  | 2021-05-01 |  |  | 2021-05-14 | 2021-05-14 | 9 | 2021-05-14 | 23 | 2021-05-18 | 3 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | [8 empty] | 0
121192277 | 1897 | 95667 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 15 |  | 2021-05-12 |  |  | 2021-05-26 | 2021-05-26 | 10 | 2021-07-01 | 35 | 2021-07-15 | 9 | [19 empty] | 2021-07-16 | [7 empty] | 0
121259243 | 1898 | 95667 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 15 |  | 2021-05-12 |  |  | 2021-05-26 | 2021-05-26 | 10 | 2021-07-06 | 37 | 2021-07-15 | 7 | [19 empty] | 2021-07-16 | [7 empty] | 0
121686349 | 1899 | 95667 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 15 |  | 2021-07-09 | 2021-07-13 |  | 2021-07-13 | 2021-07-13 | 2 | 2021-07-16 | 5 | 2021-07-19 | 1 | [15 empty] | 2021-07-19 | 2021-08-02 | 10 | 2021-08-02 | 2021-10-30 | 63 | [6 empty] | 0
122081974 | 1900 | 95667 | PGE | Non-NEM | Inadvertent Export | Application Accepted | Storage | 15 |  | 2021-09-21 | 2021-10-04 |  | 2021-10-04 | 2021-10-04 | 9 | 2021-10-21 | 22 | 2021-10-27 | 4 | [19 empty] | 2021-10-27 | [7 empty] | 0
120713177 | 1901 | 95125 | PGE | Non-NEM | Non-Export | Application Review in Progress | Storage | 15 |  | 2021-03-30 | 2021-04-08 |  | 2021-04-08 | 2021-04-08 | 7 | [31 empty] | 0
120402072 | 1902 | 95409 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-07 |  |  | 2021-01-20 | 2021-01-20 | 8 | 2021-01-20 | 8 | 2021-01-21 | 1 | [27 empty] | 0 | [29 empty] | 2021-01-29
120404457 | 1903 | 95667 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-08 |  |  | 2021-01-21 | 2021-01-21 | 8 | 2021-01-21 | 8 | 2021-01-22 | 1 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-04-12 | 56 | [6 empty] | 0 | [29 empty] | 2021-04-12
120404481 | 1904 | 95549 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-08 |  |  | 2021-01-21 | 2021-01-21 | 8 | 2021-01-21 | 8 | 2021-01-22 | 1 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-07-01 | 113 | [6 empty] | 0 | [29 empty] | 2021-10-18
120404482 | 1905 | 94020 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-08 |  |  | 2021-01-21 | 2021-01-21 | 8 | 2021-01-21 | 8 | 2021-01-21 | 0 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-07-01 | 113 | [6 empty] | 0 | [29 empty] | 2021-08-26
120468624 | 1906 | 94066 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-27 |  |  | 2021-02-08 | 2021-02-08 | 8 | 2021-03-12 | 31 | 2021-03-26 | 10 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-20 | 17 | [6 empty] | 0 | [29 empty] | 2021-05-02
120478504 | 1907 | 94611 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-01-29 |  |  | 2021-02-10 | 2021-02-10 | 8 | 2021-02-10 | 8 | 2021-02-18 | 5 | [15 empty] | 2021-02-10 | 2021-02-10 | 0 | 2021-02-10 | 2021-02-12 | 2 | [6 empty] | 0 | [29 empty] | 2021-02-23
120487354 | 1908 | 95650 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-02-01 |  |  | 2021-02-13 | 2021-02-13 | 9 | 2021-02-13 | 9 | 2021-03-08 | 14 | [15 empty] | 2021-02-13 | 2021-02-13 | 0 | 2021-02-13 | 2021-08-06 | 121 | [6 empty] | 0 | [29 empty] | 2021-08-10
120498453 | 1909 | 95682 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-02-03 |  |  | 2021-02-13 | 2021-02-13 | 7 | 2021-02-13 | 7 | 2021-02-23 | 5 | [15 empty] | 2021-02-13 | 2021-02-13 | 0 | 2021-02-13 | 2021-08-03 | 118 | [6 empty] | 0 | [29 empty] | 2021-08-03
120516130 | 1910 | 95682 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-02-10 |  |  | 2021-02-22 | 2021-02-22 | 7 | 2021-02-22 | 7 | 2021-02-23 | 1 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-05-25 | 66 | [6 empty] | 0 | [29 empty] | 2021-10-07
120579815 | 1911 | 95945 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-02-26 |  |  | 2021-03-01 | 2021-03-01 | 1 | 2021-03-01 | 1 | 2021-03-18 | 13 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-08-30 | 128 | [6 empty] | 0 | [29 empty] | 2021-09-02
120581948 | 1912 | 93953 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-02-26 |  |  | 2021-03-09 | 2021-03-09 | 7 | 2021-03-09 | 7 | 2021-03-10 | 1 | [27 empty] | 0 | [29 empty] | 2021-04-12
120646083 | 1913 | 95975 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-03-15 |  |  | 2021-03-29 | 2021-03-29 | 10 | 2021-03-29 | 10 | 2021-03-30 | 1 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-04-21 | 17 | [6 empty] | 0 | [29 empty] | 2021-04-27
120646101 | 1914 | 95650 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-03-16 | 2021-03-30 |  | 2021-03-30 | 2021-03-30 | 10 | 2021-04-14 | 21 | 2021-04-19 | 3 | [15 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-05-05 | 26 | [6 empty] | 0 | [29 empty] | 2021-05-06
120737645 | 1915 | 94062 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-04-02 |  |  | 2021-04-14 | 2021-04-14 | 8 | 2021-04-14 | 22 | 2021-04-28 | 11 | [19 empty] | 2021-04-28 | [7 empty] | 0 | [29 empty] | 2021-08-06
120991190 | 1916 | 95223 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-05-10 |  |  | 2021-05-24 | 2021-05-24 | 10 | 2021-06-07 | 19 | 2021-06-07 | 0 | [19 empty] | 2021-06-07 | [7 empty] | 0 | [29 empty] | 2021-06-07
121530920 | 1917 | 94708 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-06-14 | 2021-06-17 |  | 2021-06-17 | 2021-06-17 | 3 | 2021-06-17 | 3 | 2021-06-22 | 3 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-06-22 | 0 | [6 empty] | 0 | [29 empty] | 2021-06-25
121712104 | 1918 | 95685 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-07-12 |  |  | 2021-07-15 | 2021-07-15 | 3 | 2021-07-15 | 3 | 2021-08-02 | 12 | [19 empty] | 2021-07-12 | [7 empty] | 0 | [29 empty] | 2021-08-02
121883351 | 1919 | 94951 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-08-11 | 2021-08-13 |  | 2021-08-13 | 2021-08-13 | 2 | 2021-08-25 | 10 | 2021-08-26 | 1 | [15 empty] | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | 2021-10-13 | 33 | [6 empty] | 0 | [6 empty] | 2021-10-13 | 2021-10-20 | 5 | [15 empty] | 2021-10-13 | 2021-10-13 | 0 | 2021-10-20 |  | 2021-10-20 | 0
121957503 | 1920 | 95959 | PGE | Non-NEM | Non-Export | Commercial | Storage | 15 |  | 2021-08-25 |  |  | 2021-08-30 | 2021-08-30 | 3 | 2021-08-30 | 3 | 2021-09-07 | 5 | [15 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-09-27 | 19 | [6 empty] | 0 | [29 empty] | 2021-09-28
122106530 | 1921 | 95044 | PGE | Non-NEM | Inadvertent Export | Commercial | Storage | 15 |  | 2021-09-27 |  |  | 2021-10-11 | 2021-10-11 | 10 | 2021-10-11 | 10 | 2021-10-13 | 2 | [15 empty] | 2021-10-13 | 2021-10-13 | 0 | 2021-10-13 | 2021-10-13 | 0 | [6 empty] | 0 | [29 empty] | 2021-10-15
120237645 | 1922 | 95664 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2020-12-29 |  |  | 2021-01-08 | 2021-01-08 | 7 | 2021-01-08 | 7 | 2021-01-11 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-01-28 | 13 | [6 empty] | 0
120242942 | 1923 | 95442 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2020-12-30 |  |  | 2021-01-11 | 2021-01-11 | 7 | 2021-01-11 | 7 | 2021-01-13 | 2 | [15 empty] | 2021-01-11 | 2021-01-11 | 0 | 2021-01-11 | [8 empty] | 0
120248239 | 1924 | 93401 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-01-01 |  |  | 2021-01-11 | 2021-01-11 | 5 | 2021-01-11 | 5 | 2021-01-11 | 0 | [15 empty] | 2021-01-11 | 2021-01-11 | 0 | 2021-01-11 | [8 empty] | 0
120248272 | 1925 | 95658 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-01-01 |  |  | 2021-01-11 | 2021-01-11 | 5 | 2021-01-11 | 5 | 2021-01-11 | 0 | [15 empty] | 2021-01-11 | 2021-01-11 | 0 | 2021-01-11 | [8 empty] | 0
120408118 | 1926 | 95651 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-01-08 |  |  | 2021-01-22 | 2021-01-22 | 9 | 2021-01-22 | 9 | 2021-01-25 | 1 | [15 empty] | 2021-01-22 | 2021-01-22 | 0 | 2021-01-22 | 2021-12-01 | 216 | [6 empty] | 0
120427968 | 1927 | 95682 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-01-14 | 2021-01-25 |  | 2021-01-25 | 2021-01-25 | 6 | 2021-03-16 | 41 | 2021-03-17 | 1 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | [8 empty] | 0
120435040 | 1928 | 95549 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-01-15 | 2021-01-26 |  | 2021-01-19 | 2021-01-19 | 1 | 2021-01-29 | 9 | 2021-02-01 | 1 | [15 empty] | 2021-01-29 | 2021-01-29 | 0 | 2021-01-29 | [8 empty] | 0
120435063 | 1929 | 95521 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-01-15 | 2021-01-26 |  | 2021-01-26 | 2021-01-26 | 6 | 2021-02-05 | 14 | 2021-02-08 | 1 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | [8 empty] | 0
120435064 | 1930 | 95603 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-01-16 | 2021-01-26 |  | 2021-01-26 | 2021-01-26 | 5 | 2021-02-05 | 13 | 2021-02-08 | 1 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | [8 empty] | 0
120508898 | 1931 | 95762 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-08 |  |  | 2021-02-19 | 2021-02-19 | 8 | 2021-02-19 | 8 | 2021-02-22 | 1 | [15 empty] | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | 2021-05-25 | 67 | [6 empty] | 0
120525872 | 1932 | 95633 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-10 |  |  | 2021-02-22 | 2021-02-22 | 7 | 2021-02-22 | 7 | 2021-02-23 | 1 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-05-25 | 66 | [6 empty] | 0
120525983 | 1933 | 95713 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-10 |  |  | 2021-02-22 | 2021-02-22 | 7 | 2021-02-22 | 7 | 2021-02-23 | 1 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | [8 empty] | 0
120529582 | 1934 | 95682 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-12 |  |  | 2021-02-23 | 2021-02-23 | 6 | 2021-02-23 | 6 | 2021-02-23 | 0 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-05-26 | 66 | [6 empty] | 0
120553729 | 1935 | 95470 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-18 |  |  | 2021-02-25 | 2021-02-25 | 5 | 2021-02-25 | 5 | 2021-02-26 | 1 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | [8 empty] | 0
120571947 | 1936 | 95651 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-24 |  |  | 2021-03-01 | 2021-03-01 | 3 | 2021-03-01 | 3 | 2021-03-02 | 1 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | [8 empty] | 0
120571948 | 1937 | 95762 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-02-24 |  |  | 2021-03-01 | 2021-03-01 | 3 | 2021-03-01 | 3 | 2021-03-02 | 1 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-10-06 | 154 | [6 empty] | 0
120604675 | 1938 | 95682 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-03-04 |  |  | 2021-03-09 | 2021-03-09 | 3 | 2021-03-09 | 3 | 2021-03-11 | 2 | [15 empty] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | 2021-09-27 | 141 | [6 empty] | 0
120645879 | 1939 | 95667 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-03-16 | 2021-03-30 |  | 2021-03-30 | 2021-03-30 | 10 | 2021-06-25 | 72 | 2021-07-15 | 13 | [15 empty] | 2021-06-25 | 2021-06-25 | 0 | 2021-06-25 | 2021-07-28 | 22 | [6 empty] | 0
120646103 | 1940 | 95658 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-03-16 | 2021-03-30 |  | 2021-03-30 | 2021-03-30 | 10 | 2021-05-25 | 50 | 2021-05-28 | 3 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | [8 empty] | 0
120655619 | 1941 | 95070 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-03-17 |  |  | 2021-03-31 | 2021-03-31 | 10 | 2021-03-31 | 10 | 2021-04-06 | 4 | [15 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | 2021-07-07 | 68 | [6 empty] | 0
120656073 | 1942 | 94062 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-03-18 |  |  | 2021-04-01 | 2021-04-01 | 10 | 2021-04-01 | 10 | 2021-04-07 | 4 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | 2021-07-16 | 74 | [6 empty] | 0
120689171 | 1943 | 95472 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-03-25 |  |  | 2021-04-08 | 2021-04-08 | 10 | 2021-04-08 | 10 | 2021-04-14 | 4 | [19 empty] | 2021-07-28 | [7 empty] | 0
120702618 | 1944 | 95762 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-03-28 |  |  | 2021-04-08 | 2021-04-08 | 8 | 04/08/2021 |  | 2021-04-25 | 12 | [15 empty] | 2021-04-25 | 2021-04-25 | 0 | 2021-04-25 | 2021-07-28 | 65 | [6 empty] | 0
120727280 | 1945 | 96003 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-04-01 |  |  | 2021-04-15 | 2021-04-15 | 10 | 2021-04-15 | 10 | 2021-04-22 | 5 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-11-01 | 139 | [6 empty] | 0
120774248 | 1946 | 95728 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-04-10 |  |  | 2021-04-17 | 2021-04-17 | 5 | 2021-04-17 | 5 | 2021-04-21 | 2 | [15 empty] | 2021-04-17 | 2021-04-17 | 0 | 2021-04-17 | [8 empty] | 0
120803932 | 1947 | 94062 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-04-13 |  |  | 2021-04-17 | 2021-04-17 | 3 | 2021-04-17 | 3 | [21 empty] | 2021-04-17 | [7 empty] | 0
121559450 | 1948 | 95476 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-06-18 |  |  | 2021-06-22 | 2021-06-22 | 2 | 2021-06-22 | 2 | 2021-09-01 | 50 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | [8 empty] | 0
121674166 | 1949 | 94022 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-07-07 |  |  | 2021-07-12 | 2021-07-12 | 3 | 2021-07-12 | 3 | 2021-07-14 | 2 | [19 empty] | 2021-07-07 | [7 empty] | 0
121680318 | 1950 | 95682 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-07-08 |  |  | 2021-07-13 | 2021-07-13 | 3 | 2021-07-13 | 3 | 2021-07-20 | 5 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-23 | 7 | [6 empty] | 0
121710191 | 1951 | 95070 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-07-11 |  |  | 2021-07-15 | 2021-07-15 | 3 | 2021-07-15 | 3 | 2021-07-29 | 10 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-07-26 | 7 | [6 empty] | 0
121718165 | 1952 | 95672 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-07-12 |  |  | 2021-07-15 | 2021-07-15 | 3 | 2021-07-15 | 3 | 2021-07-20 | 3 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-07-19 | 2 | [6 empty] | 0
121725579 | 1953 | 95667 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-07-14 |  |  | 2021-07-28 | 2021-07-28 | 10 | 2021-07-28 | 10 | 2021-08-17 | 14 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | [8 empty] | 0
121882811 | 1954 | 95651 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-08-10 |  |  | 2021-08-16 | 2021-08-16 | 4 | 2021-08-16 | 4 | 2021-09-07 | 15 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | [8 empty] | 0
121986883 | 1955 | 95667 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-09-01 |  |  | 2021-09-03 | 2021-09-03 | 2 | 2021-09-03 | 2 | 2021-09-08 | 2 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-29 | 17 | [6 empty] | 0
121986947 | 1956 | 95472 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-09-01 |  |  | 2021-09-03 | 2021-09-03 | 2 | 2021-09-03 | 2 | 2021-09-22 | 12 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-23 | 13 | [6 empty] | 0
121987068 | 1957 | 95033 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-09-02 |  |  | 2021-09-17 | 2021-09-17 | 10 | 2021-09-17 | 10 | 2021-10-07 | 14 | [15 empty] | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-10-30 | 16 | [6 empty] | 0
121987673 | 1958 | 95667 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 15 |  | 2021-09-01 | 2021-09-10 |  | 2021-09-10 | 2021-09-10 | 6 | 2021-09-30 | 20 | 2021-10-19 | 13 | [15 empty] | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | [8 empty] | 0
121991506 | 1959 | 93925 | PGE | Non-NEM | Inadvertent Export | IA in Progress | Storage | 15 |  | 2021-09-02 | 2021-09-16 |  | 2021-09-16 | 2021-09-16 | 9 | 2021-09-23 | 14 | 2021-09-27 | 2 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | [8 empty] | 0
121330213 | 1960 | 95006 | PGE | Non-NEM | Non-Export | Implementation | Storage | 15 |  | 2021-05-14 | 2021-06-23 |  | 2021-05-26 | 2021-05-26 | 8 | 2021-07-23 | 48 | 2021-07-26 | 1 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-11-04 | 72 | [6 empty] | 0
121399829 | 1961 | 94043 | PGE | Non-NEM | Non-Export | Implementation | Storage | 15 |  | 2021-05-26 |  |  | 2021-06-02 | 2021-06-02 | 4 | 2021-06-02 | 4 | 2021-06-11 | 7 | [15 empty] | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-10-20 | 91 | [6 empty] | 0
121986988 | 1962 | 95682 | PGE | Non-NEM | Non-Export | Implementation | Storage | 15 |  | 2021-09-01 |  |  | 2021-09-07 | 2021-09-07 | 3 | 2021-09-07 | 3 | 2021-09-07 | 0 | [15 empty] | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-09-27 | 14 | [6 empty] | 0
121990988 | 1963 | 95404 | PGE | Non-NEM | Non-Export | Study in Progress | Storage | 15 |  | 2021-09-02 | 2021-09-17 |  | 2021-09-17 | 2021-09-17 | 10 | 2021-10-01 | 20 | 2021-10-22 | 15 | [15 empty] | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | [8 empty] | 0
121731990 | 1964 | 94122 | PGE | Non-NEM | Non-Export | IA in Progress | Solar PV | 15.048 |  | 2021-07-14 | 2021-07-20 |  | 2021-07-20 | 2021-07-20 | 4 | 2021-07-27 | 9 | 2021-08-10 | 10 | [15 empty] | 2021-08-10 | 2021-08-11 | 1 | 2021-08-11 | [8 empty] | 0
120712224 | 1965 | 94061 | PGE | Non-NEM | Non-Export | Study in Progress | Storage | 17.68 |  | 2021-03-30 |  |  | 2021-04-07 | 2021-04-07 | 6 | 2021-04-07 | 6 | 2021-04-09 | 2 | [27 empty] | 0
120692688 | 1966 | 93405 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 20 |  | 2021-03-25 |  |  | 2021-03-29 | 2021-03-29 | 2 | 2021-04-12 | 12 | 2021-04-19 | 5 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-04-23 | 4 | [6 empty] | 0
120406929 | 1967 | 93614 | PGE | Non-NEM | Non-Export | Commercial | Storage | 20 |  | 2021-01-08 |  |  | 2021-01-22 | 2021-01-22 | 9 | 2021-01-22 | 9 | 2021-02-10 | 13 | [15 empty] | 2021-01-22 | 2021-01-22 | 0 | 2021-01-22 | 2021-03-10 | 32 | [6 empty] | 0 | [29 empty] | 2021-08-04
120887180 | 1968 | 95070 | PGE | Non-NEM | Non-Export | Commercial | Storage | 20 |  | 2021-04-26 |  |  | 2021-05-10 | 2021-05-10 | 10 | 2021-05-26 | 22 | 2021-05-26 | 0 | [19 empty] | 2021-05-21 | [7 empty] | 0 | [29 empty] | 2021-10-29
121996639 | 1969 | 94062 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 20 |  | 2021-09-03 |  |  | 2021-09-20 | 2021-09-20 | 10 | 2021-09-20 | 10 | 2021-10-06 | 12 | [15 empty] | 2021-10-06 | 2021-10-06 | 0 | 2021-10-06 | 2021-10-06 | 0 | [6 empty] | 0
120532272 | 1970 | 95014 | PGE | Non-NEM | Break Before Make | Commercial | ENGN | 21 |  | 2021-02-12 |  |  | 2021-02-18 | 2021-02-18 | 3 | 2021-02-18 | 3 | 2021-03-01 | 7 | [27 empty] | 0
120474560 | 1971 | 95030 | PGE | Non-NEM | Break Before Make | Commercial | ENGN | 22 |  | 2021-01-28 | 2021-02-03 |  | 2021-02-03 | 2021-02-03 | 4 | 2021-02-10 | 9 | 2021-03-01 | 12 | [27 empty] | 0
120793050 | 1972 | 94103 | PGE | Non-NEM | Non-Export | Commercial | Solar PV | 22.831 |  | 2021-04-12 | 2021-04-26 |  | 2021-04-26 | 2021-04-26 | 10 | 2021-05-17 | 25 | 2021-07-09 | 37 | [15 empty] | 2021-07-23 | 2021-07-23 | 0 | 2021-07-23 | 2021-07-30 | 5 | [6 empty] | 0 | [6 empty] | 2021-09-08 | 2021-09-15 | 5 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-15 |  | 2021-09-16 | 1
120639171 | 1973 | 93940 | PGE | Non-NEM | Break Before Make | Commercial | ENGN | 24 |  | 2021-03-12 | 2021-03-24 |  | 2021-03-24 | 2021-03-24 | 8 | 2021-03-26 | 10 | [29 empty] | 0
120680004 | 1974 | 94904 | PGE | Non-NEM | Non-Export | Commercial | Storage | 25 |  | 2021-03-23 |  |  | 2021-04-06 | 2021-04-06 | 10 | 2021-04-06 | 10 | 2021-04-14 | 6 | [19 empty] | 2021-05-18 | [7 empty] | 0 | [29 empty] | 2021-06-10
121865297 | 1975 | 94028 | PGE | Non-NEM | Non-Export | Commercial | Storage | 25 |  | 2021-08-09 | 2021-08-17 |  | 2021-08-17 | 2021-08-17 | 6 | 2021-08-17 | 6 | 2021-08-18 | 1 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | 2021-08-19 | 1 | [6 empty] | 0 | [29 empty] | 2021-08-24
120399733 | 1976 | 95033 | PGE | Non-NEM | Non-Export | Study in Progress | Storage | 25 |  | 2021-01-07 | 2021-01-12 |  | 2021-01-12 | 2021-01-12 | 3 | 2021-01-21 | 9 | 2021-01-22 | 1 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-01-29 | 12 | [6 empty] | 0
122084815 | 1977 | 95446 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 28.95 |  | 2021-09-22 |  |  | 2021-10-06 | 2021-10-06 | 10 | 2021-10-06 | 10 | [29 empty] | 0
120604395 | 1978 | 94565 | PGE | Non-NEM | Continuous Uncompensated Export | Application Accepted | ENGN, Turbine |  |  | 2021-03-04 | 2021-03-08 |  | 2021-03-08 | 2021-03-08 | 2 | 2021-04-07 | 24 | [27 empty] | 2021-03-04 |  | 2021-03-04
120889200 | 1979 | 96088 | PGE | Non-NEM | Non-Export | Commercial | Storage |  |  | 2021-04-27 |  |  | 2021-05-11 | 2021-05-11 | 10 | 2021-05-14 | 36 | 2021-06-07 | 17 | [19 empty] | 2021-06-18 | [7 empty] | 0 | [29 empty] | 2021-06-18
120406951 | 1980 | 94710 | PGE | Non-NEM | Non-Export | Implementation | ENGN |  |  | 2021-01-08 | 2021-01-11 |  | 2021-01-11 | 2021-01-11 | 1 | 2021-01-21 | 8 | 2021-02-11 | 15 | 2021-03-09 | 2021-04-06 | 20 | [12 empty] | 2021-05-18 | 2021-06-09 | 15 | 2021-06-09 | 2021-06-18 | 7 | [6 empty] | 0
120807839 | 1981 | 95603 | PGE | Non-NEM | Continuous Uncompensated Export | Implementation | Solar PV |  |  | 2021-04-13 |  |  | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 0 | [21 empty] | 2021-04-13 | [7 empty] | 0
120772379 | 1982 | 94089 | PGE | Non-NEM | Make Before Break | Study in Progress | ENGN |  |  | 2021-04-09 | 2021-04-14 |  | 2021-04-14 | 2021-04-14 | 3 | 2021-04-28 | 13 | 2021-05-21 | 17 | [25 empty] | 2021-04-09 |  | 2021-04-09

## Q3 19 Timelines Report
19 Timelines Report
Notification No | Key | Zip Code | Utility | NEM Type | Project Type | Project Status | Technology Type | Size Total Proposed Gen | Cost Envelope Requested? | Application Received | Provide: 1st Written Notice/Invoice | Provide: NEM Deficiency Notice | Application Review | Provide: 1st Written Notice/Invoice | Cycle Time A (Business Days to Acknowledge Interconnection Request Submission) | Application Deemed Complete | Cycle Time B (Business Days to Deem Complete) | Conduct: Initial Review (IR) | Cycle Time C (Time from Interconnection Request Deemed Complete to Completion of Initial Review & Provision of Results) | Conduct: Supplemental Review (SR) | Conduct: Supplemental Review (SR) | Cycle Time D (Time from Supplemental Review Start Date to Completion of Supplemental Review) | Conduct: Screens Q and R | Conduct: Screens Q and R | Cycle Time E (Time from Electrical Interdependence Test Start Date to its Completion) | Scoping Meeting Date | Scoping Meeting Date | Cycle Time F (Time from Electrical Interdependence Test Completion to EIT Results Scoping Meeting Held) | DSA Agreement Executed by PG&E | Conduct: SIS | Cycle Time H (Time from System Impact Study Start Date to its Completion Date) | Scoping Meeting Date | Tendered DSA Agreement | Cycle Time G (Time from Study Scoping Meeting Until Study Agreement Provided) | Tender Draft IA | Tender Draft IA | Cycle Time I (Time to Provide Draft Generator Interconnection Agreement Applicable Milestone) | Tender Draft IA | IA Negotiations/Customer Signature | Cycle Time J(a) (Time from Draft Generator Interconnection Agreement Provided to Date Generator Interconnection Agreement Executed) | Cycle Time J(b) (Time from Final Study Report Date for Detailed Study to Date Generator Interconnection Agreement Executed) | Receive Customer Changes | Determine Material Modifications | Cycle Time M (Time from Request to Consider Modification to Determination Whether Modification is Material (F.3.b.v)) | Variance Request Received (Typ. From Cust) | Conduct: Variance Request Review | Variance Request Received (Typ. From Cust) | Conduct: Variance Request Review | Cycle Time N (Time for Responding to Line-Side Taps Variance Requests (for utilities that require a variance request)) | Conduct: Meter Review | Tender: Meter Invoice | Tender: Meter Invoice | Cycle Time O (Design and Invoice of Net Generation Output Meter) | Move to FMO | FMO - PASS | Cycle Time P (Installation of Net Generation Output Meter) | SP&D Design Start | SP&D Design End | Cycle Time Q(a) (Time from Customer Agreement to Proceed to Final Design and Issuance of Invoice SP&D) | Tender EA Invoice | IT Design End | Cycle Time Q(b) (Time from Customer Agreement to Proceed to Final Design and Issuance of Invoice Telemetry) | SP&D Construction Start | SP&D Construction Finish | Cycle Time R(a) (Time from Customer Payment of Invoice and Completion of Customer Work to Completion of Upgrade Construction SP&D) | PG&E Construction Start IT | PG&E Construction Complete IT | Cycle Time R(b) (Time from Customer Payment of Invoice and Completion of Customer Work to Completion of Upgrade Construction Telemetry) | PPI Authorization Letter | PPI Completion | Cycle Time S (Time for Scheduling of Commissioning Test) | FMO - PASS (Move to FMO) | FMO Schedule Inspection FMO Order | Cycle Time S(b) (This is for Projects that do not require PPI) | FMO - PASS | Permission to Operate - Conditional (COD) | Permission to Operate - Final (COD) | Cycle Time K(a) (Time from when the customer notifies the utility it has completed all of its obligations under the agreements (F.5.b) including commissioning tests, to when the utility provides the customer Permission to Operate - FMO Inspection: Task 7390 AFD FMO - PASS to Task 7502 AFD Permission to Parallel - Conditional or 7503 AFD Permission to Operate - Final (COD)) | Conduct Pre Paralell Inspection (PPI) | Cycle Time K(b) (This Cycle Time is for Projects that require PPI) | Cycle Time L (Total Time from Submission of Interconnection Request to Permission to Operate (Not in Rule 21, tracked for informational purposes))
120237417 | 1 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 111.324 |  | 2020-12-29 |  | 2021-01-27 | 2020-12-29 | 2020-12-29 | 0 | 2021-01-28 | 20 | [27 empty] | 2020-12-29
120237481 | 2 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 32.89 |  | 2020-12-29 |  |  | 2020-12-29 | 2020-12-29 | 0 | 2020-12-29 | 0 | 2021-01-19 | 13 | [15 empty] | 2021-01-19 | 2021-01-19 | 0 | 2021-01-19 | 2021-01-25 | 4 | [12 empty] | 2021-08-25 | [17 empty] | 2021-08-25 | 2021-08-26 | 1
120237636 | 3 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 94.943 |  | 2020-12-29 |  | 2020-12-29 | 2020-12-29 | 2020-12-29 | 0 | 2020-12-30 | 1 | 2021-01-11 | 7 | [15 empty] | 2021-01-11 | 2021-01-11 | 0 | 2021-01-11 | 2021-01-14 | 3 |  |  |  |  | 2020-12-29 | 2021-01-05 | 2021-01-19 | 13 | [7 empty] | 2021-03-02 | 2021-04-27 | 40 |  |  |  | 2021-08-16 |  |  | 2021-08-16
120237659 | 4 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 43.2 |  | 2020-12-29 |  | 2021-01-11 | 2021-01-11 | 2021-01-11 | 8 | 2021-02-11 | 30 | 2021-02-26 | 10 | [15 empty] | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26
120239187 | 5 | PGE | NEM | VNEMMASH | Implementation | Solar PV | 113.676 |  | 2020-12-29 |  | 2021-01-13 | 2021-01-13 | 2021-01-13 | 10 | 2021-03-31 | 63 | 2021-04-05 | 3 | [15 empty] | 2021-04-05 | 2021-04-23 | 14 | 2021-04-23 | 2021-05-20 | 19 |  |  |  |  | 2020-12-29 | 2021-04-29 | 2021-04-29 | 84
120239245 | 6 | PGE | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 57.325 |  | 2020-12-29 |  | 2021-02-16 | 2021-01-05 | 2021-01-05 | 4 | 2021-01-05 | 4 | 2021-01-07 | 2 | [15 empty] | 2021-01-05 | 2021-01-05 | 0 | 2021-01-05 | 2021-02-17 | 29 | [9 empty] | 2021-01-12 | 2021-01-12 | 0
120239248 | 7 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 207.052 |  | 2020-12-29 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 9 | 2021-01-22 | 16 | 2021-02-17 | 17 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-05-11 | 83 |  |  |  |  | 2020-12-29 | [7 empty] | 2021-09-20 | 2021-09-27 | 5 | [15 empty] | 2021-09-20 | 2021-09-20 | 0 | 2021-09-27 | 2021-09-28 |  | 1 |  |  | 189 |  | 189
120239758 | 8 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 1320 |  | 2020-12-29 | 2021-01-04 |  | 2020-12-31 | 2020-12-31 | 2 | 2021-01-13 | 10 | [5 empty] | 2021-01-13 | 2021-02-05 | 16 | 2021-02-05
120240818 | 9 | PGE | Non-NEM | Non-Export | Implementation | Storage | 357.5 |  | 2020-12-30 | 2020-12-31 |  | 2020-12-31 | 2020-12-31 | 1 | 2021-01-27 | 18 | 2021-05-12 | 74 | [15 empty] | 2021-02-01 | 2021-02-01 | 0 | 2021-02-01 | 2021-05-25 | 80 |  |  |  |  | 2020-12-30
120241984 | 10 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 420 |  | 2020-12-30 |  | 2021-01-28 | 2021-01-28 | 2021-01-28 | 19 | 2021-04-08 | 68 | [17 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | [6 empty] | 2020-12-30
120242187 | 11 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 480 |  | 2020-12-30 |  | 2021-01-11 | 2021-01-11 | 2021-01-11 | 7 | 2021-01-28 | 19 | 2021-04-29 | 64 | [15 empty] | 2021-04-29 | 2021-04-29 | 0 | 2021-04-29 | [6 empty] | 2020-12-30
120242240 | 12 | PGE | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2020-12-30 |  |  | 2021-01-13 | 2021-01-13 | 9 | 2021-01-13 | 9 | 2021-02-03 | 14 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-06-28 | 101 |  |  |  |  | 2020-12-30 | 2021-01-13 | 2021-01-27 | 18 |  |  |  |  | 2021-07-06 | 2021-07-13 | 5 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-13 |  | 2021-07-14 | 1
120242384 | 13 | PGE | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2020-12-30 | 2020-12-31 |  | 2020-12-31 | 2020-12-31 | 1 | 2021-01-27 | 18 | 2021-03-02 | 23 | [15 empty] | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | 2021-06-28 | 83 |  |  |  |  | 2020-12-30 | 2021-01-28 | 2021-02-05 | 25
120242433 | 14 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 125 |  | 2020-12-30 |  | 2020-12-31 | 2020-12-31 | 2020-12-31 | 1 | 2021-01-05 | 3 | 2021-01-11 | 4
120242519 | 15 | PGE | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2020-12-30 | 2020-12-31 |  | 2020-12-31 | 2020-12-31 | 1 | 2021-01-27 | 18 | 2021-07-28 | 127 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | 2021-08-17 | 14 |  |  |  |  | 2020-12-30 | 2021-04-06 | 2021-04-14 | 72
120242688 | 16 | PGE | NEM | EXPNEM | Commercial | Solar PV | 90.079 |  | 2020-12-30 |  | 2021-02-05 | 2020-12-31 | 2020-12-31 | 1 | 2021-03-30 | 61 | 2021-05-04 | 25 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | 2021-07-26 | 57 | [12 empty] | 2021-07-31 | 2021-08-05 | 3 | [15 empty] | 2021-07-31 | 2021-08-02 | 0 | 2021-08-05 |  | 2021-08-11 | 4
120243147 | 17 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.454 |  | 2020-12-31 |  |  | 2021-01-07 | 2021-01-07 | 4 | 2021-01-07 | 4 | 2021-01-28 | 14 | [15 empty] | 2021-01-07 | 2021-01-07 | 0 | 2021-01-07 | 2021-02-16 | 26 | [12 empty] | 2021-02-16 | 2021-02-17 | 1 | [15 empty] | 2021-02-16 | 2021-02-17 | 1 | 2021-02-17 |  | 2021-02-17 | 0
120244060 | 19 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 58.04 |  | 2020-12-31 |  |  | 2021-01-14 | 2021-01-14 | 9 | 2021-01-14 | 9 | 2021-02-11 | 19 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11
120253137 | 20 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-01-04 |  | 2021-01-05 | 2021-01-05 | 2021-01-05 | 1 | 2021-01-11 | 5 | 2021-01-21 | 7 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-06-03 | 93 |  |  |  |  | 2021-01-04 | 2021-09-24 | 2021-09-28 | 186
120254145 | 21 | PGE | NEM | EXPNEM | Implementation | Solar PV | 131.497 |  | 2021-01-04 |  |  | 2021-01-14 | 2021-01-14 | 8 | 2021-01-14 | 8 | 2021-02-04 | 14 | [15 empty] | 2021-02-04 | 2021-02-04 | 0 | 2021-02-04 | 2021-03-21 | 30 |  |  |  |  | 2021-01-04 | 2021-03-01 | 2021-03-01 | 38 |  |  |  |  | 2021-07-20 | 2021-07-29 | 7 | 2021-06-14 | [14 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-29 | 2021-07-29 |  | 0 |  |  | 144 |  | 144
120254901 | 22 | PGE | NEM | EXPNEM | Implementation | Solar PV | 700 |  | 2021-01-04 |  |  | 2021-01-15 | 2021-01-15 | 9 | 2021-01-15 | 9 | 2021-02-04 | 13 | [15 empty] | 2021-02-04 | 2021-02-04 | 0 | 2021-02-04 | 2021-02-05 | 1 | [5 empty] | 2021-02-04 | 2021-02-09 | 3
120256497 | 23 | PGE | NEM | EXPNEM | Commercial | Solar PV | 99.9 |  | 2021-01-04 |  | 2021-01-14 | 2021-01-07 | 2021-01-07 | 3 | 2021-01-15 | 9 | 2021-02-02 | 11 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-02 | 0 | [12 empty] | 2021-02-03 | 2021-02-09 | 4 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-09 |  | 2021-02-10 | 1
120257019 | 24 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 52.49 |  | 2021-01-04 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
120257082 | 25 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 61.773 |  | 2021-01-04 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
120257085 | 26 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 65.263 |  | 2021-01-04 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
120257087 | 27 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.444 |  | 2021-01-04 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
120257095 | 28 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 63.867 |  | 2021-01-04 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
120257143 | 29 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 62.122 |  | 2021-01-04 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
120257146 | 30 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 41.88 |  | 2021-01-04 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
120257149 | 31 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 63.169 |  | 2021-01-04 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
120257217 | 32 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 57.585 |  | 2021-01-04 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
120257840 | 33 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 |  | 2021-01-05 |  | 2021-02-17 | 2021-01-08 | 2021-01-08 | 3 | 2021-01-08 | 3 | 2021-01-11 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-02-17 | 26 | [12 empty] | 2021-02-17 | 2021-02-17 | 0 | [15 empty] | 2021-02-17 | 2021-02-17 | 0 | 2021-02-17 |  | 2021-02-17 | 0
120258147 | 34 | PGE | NEM | EXPNEM | Commercial | Solar PV | 62.5 |  | 2021-01-05 |  | 2021-01-06 | 2021-01-06 | 2021-01-06 | 1 | 2021-01-19 | 9 | 2021-02-18 | 21 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-05-26 | 69 |  |  |  |  | 2021-01-05 | 2021-01-06 | 2021-01-20 | 10 |  |  |  |  | 2021-07-16 | 2021-07-20 | 2 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-20 |  | 2021-07-26 | 4
120258656 | 35 | PGE | NEM | EXPNEM | Commercial | Solar PV | 85.573 |  | 2021-01-05 |  | 2021-01-06 | 2021-01-06 | 2021-01-06 | 1 | 2021-01-07 | 2 | 2021-01-08 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-03-10 | 41 |  |  |  |  | 2021-01-05 | [7 empty] | 2021-03-12 | 2021-04-21 | 28 | [15 empty] | 2021-03-12 | 2021-04-21 | 28 | 2021-04-21 |  | 2021-04-23 | 2
120258859 | 36 | PGE | NEM | EXPNEM | Commercial | Solar PV | 53.808 |  | 2021-01-05 |  | 2021-01-06 | 2021-01-06 | 2021-01-06 | 1 | 2021-01-06 | 1 | 2021-01-21 | 10 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-04-09 | 55 | [12 empty] | 2021-04-12 | 2021-04-19 | 5 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-19 |  | 2021-04-27 | 6
120258980 | 37 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-01-05 |  | 2021-01-20 | 2021-01-20 | 2021-01-20 | 10 | 2021-01-28 | 16 | 2021-02-02 | 3 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-04 | 2 | [12 empty] | 2021-02-08 | 2021-02-08 | 0 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 |  | 2021-02-10 | 2
120260346 | 38 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.886 |  | 2021-01-05 |  | 2021-01-06 | 2021-01-06 | 2021-01-06 | 1 | 2021-01-27 | 15 | 2021-02-11 | 11 | [15 empty] | 2021-02-11 | 2021-02-16 | 2 | 2021-02-16 | 2021-02-23 | 5 |  |  |  |  | 2021-01-05 | 2021-08-09 | 2021-08-18 | 157 |  |  |  |  | 2021-09-17 | 2021-09-30 | 9 | 2021-03-17 | 2021-06-03 | 55 |  |  |  | 2021-06-03 | 2021-07-14 | 28 | 2021-06-03 | 2021-07-14 | 28 |  |  |  | 2021-09-17 | 2021-09-20 | 1 | 2021-09-30
120260620 | 39 | PGE | NEM | EXPNEM | Commercial | Solar PV | 83.3 |  | 2021-01-05 |  | 2021-02-02 | 2021-01-19 | 2021-01-19 | 9 | 2021-01-19 | 9 | 2021-02-02 | 10 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-06-28 | 102 |  |  |  |  | 2021-01-05 | 2021-01-19 | 2021-01-28 | 16 |  |  |  |  | 2021-07-06 | 2021-07-13 | 5 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-13 |  | 2021-07-13 | 0
120260704 | 40 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-01-05 |  | 2021-01-12 | 2021-01-06 | 2021-01-06 | 1 | 2021-01-13 | 6 | 2021-02-02 | 13 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-02 | 0 |  |  |  |  | 2021-01-05 | 2021-01-06 | 2021-01-20 | 10
120261107 | 41 | PGE | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-01-05 |  |  | 2021-01-19 | 2021-01-19 | 9 | 2021-01-19 | 9 | 2021-02-08 | 14 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-03-01 | 14 | [12 empty] | 2021-03-23 | 2021-04-01 | 7 | [15 empty] | 2021-03-23 | 2021-03-24 | 1 | 2021-04-01 |  | 2021-04-01 | 0
120261917 | 42 | PGE | NEM | VNEMMASH | Implementation | Solar PV | 433.597 |  | 2021-01-05 |  | 2021-07-26 | 2021-01-12 | 2021-01-12 | 5 | 2021-01-12 | 5 | 2021-02-19 | 26 |  |  |  | 2021-03-02 | 2021-04-23 | 38 | 2021-04-23 |  |  | 2021-04-23 | 2021-07-16 | 58 | [7 empty] | 2021-07-27 | N/A | 7 |  |  |  |  | 2021-08-18 | 2021-08-18 | 0 |  | 2021-08-18 | 2021-08-18 | 0 |  |  |  | 2021-09-08
120262031 | 43 | PGE | NEM | VNEMMASH | Implementation | Solar PV | 530 |  | 2021-01-05 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 5 | 2021-01-12 | 5 | 2021-02-24 | 29 | [15 empty] | 2021-02-24 | 2021-02-24 | 0 | 2021-02-24 | 2021-05-05 | 50 | [8 empty] | 2021-06-17 | 2021-08-18 | 2021-08-18 | 43
120262567 | 44 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 2600.5 |  | 2021-01-06 | 2021-01-07 |  | 2021-01-07 | 2021-01-07 | 1 | 2021-01-27 | 14 | [5 empty] | 2021-01-27 | 2021-03-04 | 25 | 2021-03-04 | 2021-03-04 | 0 | 2021-03-25 | 2021-06-21 | 61 | 2021-03-04 | 2021-03-08 | 2 | 2021-07-29 | 2021-07-29 | 0 | 2021-07-29 | 2021-08-18 | 14 |  | 2021-07-15
120300339 | 46 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 493.369 |  | 2021-01-06 |  | 2021-02-22 | 2021-01-07 | 2021-01-07 | 1 | 2021-02-23 | 32 | 2021-03-09 | 10 | [15 empty] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09
120331569 | 47 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 1625 |  | 2021-01-06 | 2021-01-07 |  | 2021-01-07 | 2021-01-07 | 1 | 2021-01-20 | 9 | 2021-03-02 | 28 | 2021-03-08 | 2021-04-01 | 18 | 2021-05-03 | 2021-05-12 | 7 | 2021-05-12 | 2021-05-13 | 1 | 2021-05-21 | 2021-08-10 | 55 | 2021-05-13 | 2021-05-13 | 0 | 2021-08-19 | 2021-08-27 | 6 | 2021-08-27 |  |  |  | 2021-08-19 | 2021-08-26 | 5
120342553 | 48 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 52.675 |  | 2021-01-06 |  |  | 2021-01-19 | 2021-01-19 | 8 | 2021-01-19 | 8 | 2021-02-08 | 14 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08
120400544 | 50 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 53.35 |  | 2021-01-07 |  |  | 2021-01-08 | 2021-01-08 | 1 | 2021-01-08 | 1 | 2021-01-26 | 11 | [15 empty] | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 2021-01-29 | 3 |  |  |  |  | 2021-01-07 | 2021-02-02 | 2021-02-08 | 21
120400551 | 51 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-01-07 |  |  | 2021-01-08 | 2021-01-08 | 1 | 2021-01-08 | 1 | 2021-02-08 | 20 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-02-12 | 4 |  |  |  |  | 2021-01-07 | 2021-02-04 | 2021-02-09 | 22
120400883 | 52 | PGE | NEM | EXPNEM | Implementation | Solar PV | 112.682 |  | 2021-01-07 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-28 | 11 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23 | 2021-08-23 | 0 |  |  |  |  | 2021-01-07 |  |  |  | 2021-09-08
120400937 | 53 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 168.87 |  | 2021-01-07 |  | 2021-01-08 | 2021-01-08 | 2021-01-08 | 1 | 2021-01-11 | 2 | 2021-02-20 | 27 | [15 empty] | 2021-02-20 | 2021-02-20 | 0 | 2021-02-20 | 2021-08-18 | 125 |  |  |  |  | 2021-01-07 | 2021-03-02 | 2021-03-03 | 37 |  |  |  |  | 2021-08-21 | [17 empty] | 2021-08-21 | 2021-08-23 | 0
120401435 | 54 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.741 |  | 2021-01-07 |  |  | 2021-01-12 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-03-09 | 38 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-03-10 | 39 | [12 empty] | 2021-03-10 | 2021-03-10 | 0 | [15 empty] | 2021-03-10 | 2021-03-10 | 0 | 2021-03-10 |  | 2021-03-13 | 2
120401572 | 55 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 41.331 |  | 2021-01-07 |  |  | 2021-01-12 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-14 | 2 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-05-17 | 87 |  |  |  |  | 2021-01-07 | 2021-05-17 | 2021-05-17 | 90 |  |  |  |  | 2021-05-20 | 2021-05-21 | 1 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-21 |  | 2021-05-21 | 0
120402483 | 56 | PGE | NEM | EXPNEM | Commercial | Solar PV | 62.5 |  | 2021-01-07 |  |  | 2021-01-21 | 2021-01-21 | 9 | 2021-01-21 | 9 | 2021-03-10 | 33 | [15 empty] | 2021-03-10 | 2021-03-10 | 0 | 2021-03-10 | 2021-06-28 | 77 |  |  |  |  | 2021-01-07 | 2021-01-21 | 2021-02-02 | 17 |  |  |  |  | 2021-07-14 | 2021-07-20 | 4 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-20 |  | 2021-07-22 | 2
120403977 | 57 | PGE | NEM | EXPNEM | Implementation | Solar PV | 54.229 |  | 2021-01-07 |  |  | 2021-01-21 | 2021-01-21 | 9 | 2021-01-21 | 9 | 2021-02-10 | 14 | [15 empty] | 2021-02-10 | 2021-02-10 | 0 | 2021-02-10 | 2021-03-03 | 14 |  |  |  |  | 2021-01-07 | 2021-05-19 | 2021-05-28 | 99 | [7 empty] | 2021-06-22
120405542 | 59 | PGE | NEM | EXPNEM | Implementation | Solar PV | 82.656 |  | 2021-01-08 |  |  | 2021-01-22 | 2021-01-22 | 9 | 2021-01-22 | 9 | 2021-03-03 | 27 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-06-15 | 73 | [5 empty] | 2021-03-12 | 2021-03-15 | 1
120405864 | 60 | PGE | NEM | EXPNEM | Commercial | Solar PV | 60 |  | 2021-01-08 |  |  | 2021-01-22 | 2021-01-22 | 9 | 2021-01-22 | 9 | 2021-02-11 | 14 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-22 | 6 |  |  |  |  | 2021-01-08 | 2021-01-22 | 2021-02-02 | 16 |  |  |  |  | 2021-05-01 | 2021-05-10 | 5 | [15 empty] | 2021-05-01 | 2021-05-03 | 0 | 2021-05-10 |  | 2021-05-10 | 0
120406220 | 61 | PGE | NEM | EXPNEM | Commercial | Solar PV | 83.3 |  | 2021-01-08 |  |  | 2021-01-23 | 2021-01-23 | 9 | 2021-01-23 | 9 | 2021-02-06 | 10 | [15 empty] | 2021-02-06 | 2021-02-06 | 0 | 2021-02-06 | 2021-06-02 | 80 |  |  |  |  | 2021-01-08 | 2021-01-23 | 2021-02-02 | 16 |  |  |  |  | 2021-07-20 | 2021-07-27 | 5 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-27 |  | 2021-07-29 | 2
120406395 | 62 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-01-08 |  | 2021-01-16 | 2021-01-16 | 2021-01-16 | 5 | 2021-02-24 | 31 | 2021-03-15 | 13 | [15 empty] | 2021-02-24 | 2021-02-24 | 0 | 2021-02-24 | 2021-03-10 | 10 | [12 empty] | 2021-03-15 | 2021-03-15 | 0 | [15 empty] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 |  | 2021-03-22 | 5
120406633 | 63 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 350 |  | 2021-01-08 | 2021-01-11 |  | 2021-01-11 | 2021-01-11 | 1 | 2021-02-03 | 17 | 2021-04-30 | 61 | [15 empty] | 2021-04-30 | 2021-04-30 | 0 | 2021-04-30 | 2021-05-06 | 4 |  |  |  |  | 2021-01-08 | 2021-03-26 | 2021-04-12 | 64
120406850 | 64 | PGE | NEM | EXPNEM | Commercial | Solar PV | 62.5 |  | 2021-01-08 |  |  | 2021-01-23 | 2021-01-23 | 9 | 2021-01-23 | 9 | 2021-02-09 | 11 | [15 empty] | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | 2021-07-06 | 102 |  |  |  |  | 2021-01-08 | 2021-01-23 | 2021-02-02 | 16 |  |  |  |  | 2021-07-06 | 2021-07-14 | 6 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-14 |  | 2021-07-14 | 0
120407430 | 65 | PGE | NEM | VNEMSOMAH | Application Accepted | Solar PV | 74.404 |  | 2021-01-08 |  | 2021-01-14 | 2021-01-14 | 2021-01-14 | 4 | 2021-01-18 | 5 | 2021-04-06 | 54 | [25 empty] | 2021-01-08 |  |  |  | 2021-01-19
120407821 | 66 | PGE | NEM | VNEMSOMAH | Withdrawn | Solar PV | 172.8 |  | 2021-01-08 |  | 2021-01-25 | 2021-01-22 | 2021-01-22 | 9 | 2021-06-25 | 117 | [5 empty] | 2021-06-25 | 2021-07-26 | 20 | 2021-07-26 | [18 empty] | 2021-01-08 | 2021-09-13
120407845 | 67 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 37.68 |  | 2021-01-08 |  | 2021-01-14 | 2021-01-14 | 2021-01-14 | 4 | 2021-01-21 | 8 | 2021-01-25 | 2 | [15 empty] | 2021-01-14 | 2021-01-14 | 0 | 2021-01-14
120407891 | 68 | PGE | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2021-01-08 | 2021-01-12 |  | 2021-01-11 | 2021-01-11 | 1 | 2021-02-03 | 17 | 2021-03-30 | 38 | [15 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-04-12 | 9 |  |  |  |  | 2021-01-08
120407969 | 69 | PGE | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-01-08 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2 | 2021-01-12 | 2 | 2021-02-25 | 30 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-26 | 21 |  |  |  |  | 2021-01-08 |  |  |  | 2021-02-05 | 2021-03-25 | 2021-03-25 | 33 | 2021-05-24 | 2021-06-02 | 6 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-06-02 |  | 2021-06-04 | 2
120407972 | 70 | PGE | NEM | NEM Paired Storage | IA in Progress | ENGN, Solar PV, Storage | 924.893 |  | 2021-01-08 |  | 2021-03-30 | 2021-01-20 | 2021-01-20 | 7 | 2021-03-31 | 56 | 2021-05-10 | 28 | [15 empty] | 2021-05-10 | 2021-05-11 | 1 | 2021-05-11 | [6 empty] | 2021-01-08
120408129 | 71 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 30.399 |  | 2021-01-09 |  |  | 2021-01-16 | 2021-01-16 | 5 | 2021-01-16 | 5 | 2021-02-04 | 12 | [15 empty] | 2021-01-16 | 2021-01-16 | 0 | 2021-01-16 | 2021-02-16 | 19
120408133 | 72 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 |  | 2021-01-08 |  |  | 2021-01-14 | 2021-01-14 | 4 | 2021-01-14 | 4 | 2021-02-03 | 13 | [15 empty] | 2021-01-14 | 2021-01-14 | 0 | 2021-01-14 | 2021-02-03 | 13 | [12 empty] | 2021-02-03 | 2021-02-09 | 4 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-09 |  | 2021-02-09 | 0
120408782 | 73 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 150 |  | 2021-01-09 |  |  | 2021-01-11 | 2021-01-11 | 0 | 2021-01-13 | 2 | 2021-03-15 | 41 | [15 empty] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | 2021-07-28 | 95 | [5 empty] | 2021-02-23 | 2021-02-23 | 0
120416915 | 74 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 62.048 |  | 2021-01-10 |  | 2021-01-25 | 2021-01-25 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
120416916 | 75 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.292 |  | 2021-01-10 |  | 2021-01-25 | 2021-01-25 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
120416928 | 76 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 38.78 |  | 2021-01-10 |  | 2021-01-25 | 2021-01-25 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
120416929 | 77 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.292 |  | 2021-01-10 |  | 2021-01-25 | 2021-01-25 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
120416934 | 79 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 62.048 |  | 2021-01-10 |  | 2021-01-25 | 2021-01-25 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
120416970 | 80 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 42.054 |  | 2021-01-10 |  | 2021-01-25 | 2021-01-25 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
120416971 | 81 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 35.045 |  | 2021-01-10 |  | 2021-01-25 | 2021-01-25 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
120416981 | 82 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.292 |  | 2021-01-10 |  | 2021-01-25 | 2021-01-25 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
120418460 | 83 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 32.032 |  | 2021-01-11 |  |  | 2021-01-12 | 2021-01-12 | 1 | 2021-01-12 | 1 | 2021-01-27 | 10 | [15 empty] | 2021-01-27 | 2021-01-27 | 0 | 2021-01-27 | [6 empty] | 2021-01-11 | 2021-01-12 | 2021-01-26 | 10
120418596 | 84 | PGE | NEM | EXPNEM | Implementation | Solar PV | 66.6 |  | 2021-01-11 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 1 | 2021-01-19 | 5 | 2021-02-03 | 11 | 2021-02-03 | 2021-03-18 | 30 | 2021-03-23 | 2021-03-25 | 2 | 2021-03-25 |  |  | 2021-03-25 | 2021-06-22 | 62 |  |  |  | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-06-23 | 1 |  |  |  |  | 2021-01-11 | 2021-01-12 | 2021-01-26 | 10
120418631 | 85 | PGE | NEM | EXPNEM | Implementation | Solar PV | 40.1 |  | 2021-01-11 |  |  | 2021-01-26 | 2021-01-26 | 10 | 2021-01-26 | 10 | 2021-02-18 | 16 | [15 empty] | 2021-02-16 | 2021-02-16 | 0 | 2021-02-16 | 2021-02-22 | 4 |  |  |  |  | 2021-01-11 | 2021-01-26 | 2021-02-03 | 16
120418656 | 86 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 37.099 |  | 2021-01-11 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 1 | 2021-03-30 | 54 | 2021-08-09 | 92 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-09-13 | 24 |  |  |  |  | 2021-01-11 | 2021-02-01 | 2021-02-05 | 18 |  |  |  |  | 2021-09-13 | [17 empty] | 2021-09-13 | 2021-09-13 | 0
120418864 | 87 | PGE | NEM | EXPNEM | Implementation | Solar PV | 91.918 |  | 2021-01-11 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 1 | 2021-01-19 | 5 | 2021-02-03 | 11 | 2021-02-03 | 2021-03-18 | 30 | 2021-03-24 | 2021-03-25 | 1 | 2021-03-25 | [8 empty] | 2021-09-15 | 2021-09-21 | 4 | 2021-09-21 | 2021-09-23 | 2 |  |  |  |  | 2021-01-11 | 2021-01-27 | 2021-02-02 | 15
120418897 | 88 | PGE | NEM | EXPNEM | Implementation | Solar PV | 55.708 |  | 2021-01-11 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 1 | 2021-01-19 | 5 | 2021-02-02 | 10 | 2021-02-02 | 2021-03-19 | 32 | 2021-03-24 | 2021-03-25 | 1 | 2021-03-25 | [8 empty] | 2021-09-15 | 2021-09-21 | 4 | 2021-09-21 | 2021-09-23 | 2 |  |  |  |  | 2021-01-11 | 2021-01-27 | 2021-02-02 | 15
120418953 | 89 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.409 |  | 2021-01-11 |  |  | 2021-01-16 | 2021-01-16 | 4 | 2021-01-16 | 4 | 2021-02-01 | 9 | [15 empty] | 2021-01-16 | 2021-01-16 | 0 | 2021-01-16 | 2021-01-19 | 0 | [12 empty] | 2021-02-01 | 2021-02-01 | 0 | [15 empty] | 2021-02-01 | 2021-02-01 | 0 | 2021-02-01 |  | 2021-02-01 | 0
120419667 | 90 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.714 |  | 2021-01-11 |  | 2021-02-01 | 2021-01-19 | 2021-01-19 | 5 | 2021-02-05 | 18 | 2021-02-22 | 10 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | 2021-02-08 | 1 | [12 empty] | 2021-02-22 | 2021-03-03 | 7 | [15 empty] | 2021-02-22 | 2021-02-23 | 1 | 2021-03-03 |  | 2021-03-06 | 2
120419685 | 91 | PGE | Non-NEM | Non-Export | Implementation | Storage | 280 |  | 2021-01-11 | 2021-01-12 |  | 2021-01-12 | 2021-01-12 | 1 | 2021-02-03 | 16 | 2021-03-01 | 17 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-05-27 | 63 |  |  |  |  | 2021-01-11
120419880 | 92 | PGE | NEM | NEMMT | IA in Progress | Solar PV | 663.66 |  | 2021-01-11 |  | 2021-01-26 | 2021-01-26 | 2021-01-26 | 10 | 2021-02-19 | 27 | 2021-03-11 | 14 | 2021-03-11 | 2021-04-08 | 20 | 2021-04-08 | 2021-05-11 | 23 | 2021-05-11 |  |  |  | 2021-08-05 |  |  |  |  | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | [6 empty] | 2021-01-11 | 2021-01-26 | 2021-02-03 | 16 | 2021-06-17
120419988 | 93 | PGE | NEM | EXPNEM | Commercial | Solar PV | 95.8 |  | 2021-01-11 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 1 | 2021-01-13 | 2 | 2021-01-29 | 11 | [15 empty] | 2021-01-29 | 2021-02-14 | 10 | 2021-02-14 | 2021-02-18 | 2 | [12 empty] | 2021-05-07 | 2021-05-18 | 7 | [15 empty] | 2021-05-07 | 2021-05-10 | 1 | 2021-05-18 |  | 2021-05-21 | 3
120536314 | 94 | PGE | NEM | EXPNEM | Implementation | Solar PV | 3858.508 |  | 2021-02-16 | 2021-02-18 |  | 2021-02-17 | 2021-02-17 | 1 | 2021-03-03 | 11 | [5 empty] | 2021-03-04 | 2021-04-07 | 24 | 2021-04-07 | 2021-04-07 | 0 | 2021-05-03 | 2021-07-12 | 48 | 2021-04-07 | 2021-04-08 | 1 | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13 | 2021-08-16 | 24 |  |  |  |  | 2021-02-16 | 2021-03-04
120484500 | 95 | PGE | NEM | EXPNEM | Implementation | Solar PV | 520 |  | 2021-02-01 |  | 2021-02-12 | 2021-02-12 | 2021-02-12 | 9 | 2021-02-25 | 17 | 2021-03-03 | 4 | 2021-03-03 | 2021-03-31 | 20 | [12 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | 2021-06-04 | 46
120472984 | 96 | PGE | NEM | EXPNEM | Commercial | Solar PV | 31.404 |  | 2021-01-28 |  | 2021-01-28 | 2021-01-28 | 2021-01-28 | 0 | 2021-02-04 | 5 | 2021-02-11 | 5 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-11 | 0 | [12 empty] | 2021-08-23 | 2021-09-02 | 8 | [15 empty] | 2021-08-23 | 2021-08-24 | 1 | 2021-09-02 |  | 2021-09-13 | 6
120454806 | 97 | PGE | NEM | EXPNEM | Commercial | Solar PV | 200 |  | 2021-01-21 |  |  | 2021-01-22 | 2021-01-22 | 1 | 2021-01-22 | 1 | 2021-02-12 | 15 | [15 empty] | 2021-02-12 | 2021-02-12 | 0 | 2021-02-12 | 2021-02-17 | 2 | [12 empty] | 2021-06-02 | 2021-06-10 | 6 | [15 empty] | 2021-06-02 | 2021-06-03 | 1 | 2021-06-10 |  | 2021-06-17 | 5
120470690 | 98 | PGE | NEM | EXPNEM | Commercial | Solar PV | 250 |  | 2021-01-27 |  | 2021-01-28 | 2021-01-28 | 2021-01-28 | 1 | 2021-01-29 | 2 | 2021-02-14 | 10 | [15 empty] | 2021-02-14 | 2021-02-14 | 0 | 2021-02-14 | 2021-02-18 | 2 | [12 empty] | 2021-08-10 | 2021-08-17 | 5 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-17 |  | 2021-08-24 | 5
120527951 | 99 | PGE | NEM | EXPNEM | Commercial | Solar PV | 127.683 |  | 2021-02-11 |  | 2021-02-12 | 2021-02-12 | 2021-02-12 | 1 | 2021-02-16 | 2 | 2021-02-20 | 3 | [15 empty] | 2021-02-20 | 2021-02-20 | 0 | 2021-02-20 | 2021-02-24 | 2 |  |  |  |  | 2021-02-11 | [7 empty] | 2021-08-05 | 2021-08-11 | 4 | [15 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-11 |  | 2021-08-18 | 5
120430502 | 100 | PGE | NEM | EXPNEM | IA in Progress | Solar PV, Storage | 94.803 |  | 2021-01-14 |  | 2021-01-19 | 2021-01-15 | 2021-01-15 | 1 | 2021-02-18 | 23 | 2021-03-01 | 7 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-03 | 2
120496964 | 101 | PGE | NEM | EXPNEM | Commercial | Solar PV | 33.06 |  | 2021-02-03 |  |  | 2021-02-04 | 2021-02-04 | 1 | 2021-02-04 | 1 | 2021-02-18 | 9 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-05-26 | 69 | [12 empty] | 2021-07-22 | 2021-07-22 | 0 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 |  | 2021-07-28 | 4
120528102 | 102 | PGE | NEM | EXPNEM | Commercial | Solar PV | 63.135 |  | 2021-02-11 |  | 2021-02-12 | 2021-02-12 | 2021-02-12 | 1 | 2021-02-16 | 2 | 2021-03-03 | 11 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-08 | 3 | [12 empty] | 2021-05-12 | 2021-05-19 | 5 | [15 empty] | 2021-05-12 | 2021-05-13 | 1 | 2021-05-19 |  | 2021-05-26 | 5
120551262 | 103 | PGE | NEM | EXPNEM | Implementation | Solar PV | 770 |  | 2021-02-18 |  |  | 2021-02-23 | 2021-02-23 | 3 | 2021-02-23 | 3 | 2021-03-01 | 4 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-11 | 8 | [15 empty] | 2021-05-18 | 2021-08-16 | 62 |  |  |  | 2021-08-16 |  |  | 2021-08-16
120500354 | 104 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 31.062 |  | 2021-02-04 |  | 2021-03-01 | 2021-02-16 | 2021-02-16 | 7 | 2021-02-16 | 7 | 2021-03-12 | 18 | [15 empty] | 2021-03-12 | 2021-03-12 | 0 | 2021-03-12 | 2021-03-12 | 0 | [12 empty] | 2021-07-27 | [17 empty] | 2021-07-27 | 2021-07-27 | 0
120475610 | 105 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 316.555 |  | 2021-01-28 |  | 2021-04-26 | 2021-02-03 | 2021-02-03 | 4 | 2021-02-17 | 15 | 2021-03-08 | 14 | [15 empty] | 2021-03-08 | 2021-03-17 | 7 | 2021-03-17 | 2021-03-18 | 1 |  |  |  |  | 2021-01-28
120580995 | 106 | PGE | NEM | EXPNEM | Commercial | Solar PV | 103.592 |  | 2021-02-26 |  | 2021-03-01 | 2021-03-01 | 2021-03-01 | 1 | 2021-03-04 | 4 | 2021-03-23 | 13 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | 2021-03-24 | 1 |  |  |  |  | 2021-02-26 | 2021-05-17 | 2021-05-28 | 65 |  |  |  |  | 2021-08-13 | 2021-08-20 | 5 | [15 empty] | 2021-08-13 | 2021-08-13 | 0 | 2021-08-20 |  | 2021-08-27 | 5
120531895 | 107 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 40.733 |  | 2021-02-12 |  |  | 2021-02-16 | 2021-02-16 | 1 | 2021-02-16 | 1 | 2021-03-02 | 10 | [15 empty] | 2021-03-02 | 2021-03-03 | 1 | 2021-03-03 | 2021-03-26 | 17 | [15 empty] | 2021-07-06
120582494 | 108 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 260.887 |  | 2021-02-26 |  | 2021-03-02 | 2021-03-02 | 2021-03-02 | 2 | 2021-03-09 | 7 | 2021-03-29 | 14 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-03-29 | 0 |  |  |  |  | 2021-02-26
120430750 | 109 | PGE | NEM | EXPNEM | IA in Progress | Solar PV, Storage | 94.803 |  | 2021-01-14 |  | 2021-02-01 | 2021-01-15 | 2021-01-15 | 1 | 2021-02-01 | 11 | 2021-02-11 | 8 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-16 | 2 |  |  |  |  | 2021-01-14 | 2021-01-15 | 2021-01-28 | 9 |  |  |  |  | 2021-09-21 | 2021-09-29 | 6 | [15 empty] | 2021-09-21 | 2021-09-22 | 1 | 2021-09-29
120464628 | 110 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 86.965 |  | 2021-01-26 |  | 2021-01-28 | 2021-01-26 | 2021-01-26 | 0 | 2021-01-28 | 2 | 2021-08-18 | 141 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-02 | 8 |  |  |  |  | 2021-01-26 | 2021-01-26 | 2021-02-03 | 6 |  |  |  |  | 2021-08-21 | 2021-08-30 | 5 | [15 empty] | 2021-08-21 | 2021-08-23 | 0 | 2021-08-30 | 2021-09-07 |  | 5 |  |  | 156 |  | 156
120449765 | 111 | PGE | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-01-20 |  | 2021-02-01 | 2021-01-28 | 2021-01-28 | 6 | 2021-01-29 | 7 | 2021-01-29 | 0 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-01 | 4 |  |  |  |  | 2021-01-20 | 2021-01-29 | 2021-02-05 | 12 |  |  |  |  | 2021-07-19 | 2021-07-23 | 4 | [15 empty] | 2021-07-19 | 2021-07-19 | 0 | 2021-07-23 |  | 2021-07-23 | 0
120428509 | 112 | PGE | NEM | EXPNEM | Commercial | Solar PV | 69.6 |  | 2021-01-14 |  |  | 2021-01-28 | 2021-01-28 | 9 | 2021-01-28 | 9 | 2021-02-18 | 14 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-23 | 23 |  |  |  |  | 2021-01-14 | 2021-01-28 | 2021-02-05 | 15 |  |  |  |  | 2021-05-11 | 2021-05-19 | 6 | [15 empty] | 2021-05-11 | 2021-05-12 | 1 | 2021-05-19 |  | 2021-05-19 | 0
120475331 | 113 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 167.045 |  | 2021-01-28 |  | 2021-01-29 | 2021-01-29 | 2021-01-29 | 1 | 2021-02-01 | 2 | 2021-03-15 | 29 | [15 empty] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | 2021-03-25 | 8 |  |  |  |  | 2021-01-28 | 2021-02-01 | 2021-02-05 | 6
120496624 | 114 | PGE | NEM | EXPNEM | Commercial | Solar PV | 185.596 |  | 2021-02-03 |  | 2021-02-08 | 2021-02-04 | 2021-02-04 | 1 | 2021-02-10 | 5 | 2021-02-25 | 10 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-03 | 4 |  |  |  |  | 2021-02-03 | 2021-02-04 | 2021-02-09 | 4 |  |  |  |  | 2021-05-11 | 2021-05-20 | 7 | [15 empty] | 2021-05-11 | 2021-05-12 | 1 | 2021-05-20 |  | 2021-05-27 | 5
120475330 | 115 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 65 |  | 2021-01-28 |  | 2021-03-01 | 2021-02-08 | 2021-02-08 | 7 | 2021-02-08 | 7 | 2021-03-03 | 16 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-04 | 1 |  |  |  |  | 2021-01-28 | 2021-02-08 | 2021-02-09 | 8 | [7 empty] | 2021-07-01
120475372 | 116 | PGE | NEM | EXPNEM | Implementation | Solar PV | 66.6 |  | 2021-01-28 |  | 2021-04-13 | 2021-02-05 | 2021-02-05 | 6 | 2021-02-10 | 9 | 2021-02-17 | 4 | [15 empty] | 2021-02-17 | 2021-02-17 | 0 | 2021-02-17 | 2021-03-16 | 19 |  |  |  |  | 2021-01-28 | 2021-02-05 | 2021-02-09 | 8
120496259 | 117 | PGE | NEM | EXPNEM | Commercial | Solar PV | 48.582 |  | 2021-02-03 |  | 2021-02-10 | 2021-02-04 | 2021-02-04 | 1 | 2021-02-14 | 7 | 2021-03-05 | 13 | [15 empty] | 2021-03-05 | 2021-03-05 | 0 | 2021-03-05 | 2021-03-09 | 2 |  |  |  |  | 2021-02-03 | 2021-02-14 | 2021-02-16 | 8 |  |  |  |  | 2021-05-06 | 2021-05-17 | 7 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-17 |  | 2021-05-20 | 3
120464575 | 118 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 147.625 |  | 2021-01-26 |  |  | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 0 | 2021-02-11 | 12 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-22 | 6 |  |  |  |  | 2021-01-26 | 2021-02-26 | 2021-03-01 | 23
120462488 | 119 | PGE | NEM | EXPNEM | Commercial | Solar PV | 175 |  | 2021-01-25 |  | 2021-01-26 | 2021-01-26 | 2021-01-26 | 1 | 2021-01-28 | 3 | 2021-02-12 | 11 | [15 empty] | 2021-02-12 | 2021-02-12 | 0 | 2021-02-12 | 2021-02-17 | 2 |  |  |  |  | 2021-01-25 | 2021-03-10 | 2021-03-12 | 33 |  |  |  |  | 2021-05-24 | 2021-06-03 | 7 | [15 empty] | 2021-05-24 | 2021-05-26 | 2 | 2021-06-03 |  | 2021-06-09 | 4
120474841 | 120 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 32.77 |  | 2021-01-28 |  | 2021-01-29 | 2021-01-29 | 2021-01-29 | 1 | 2021-02-04 | 5 | 2021-03-04 | 19 | [15 empty] | 2021-03-04 | 2021-03-04 | 0 | 2021-03-04 | 2021-03-11 | 5 |  |  |  |  | 2021-01-29 | 2021-03-15 | 2021-03-17 | 32
120479842 | 121 | PGE | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-01-29 |  | 2021-02-09 | 2021-02-09 | 2021-02-09 | 7 | 2021-02-10 | 8 | 2021-03-02 | 13 | [15 empty] | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | 2021-03-05 | 3 |  |  |  |  | 2021-01-29 | 2021-04-14 | 2021-04-29 | 63 |  |  |  |  | 2021-05-07 | 2021-05-07 | 0 | [15 empty] | 2021-05-07 | 2021-05-07 | 0 | 2021-05-07 |  | 2021-05-07 | 0
120435037 | 122 | PGE | NEM | EXPNEM | Commercial | Solar PV | 47.82 |  | 2021-01-15 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 1 | 2021-01-28 | 8 | 2021-02-02 | 3 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-18 | 11 | [12 empty] | 2021-02-22 | 2021-02-26 | 4 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-26 |  | 2021-03-03 | 3
120428756 | 123 | PGE | NEM | EXPNEM | Commercial | Solar PV | 56.866 |  | 2021-01-14 |  | 2021-01-15 | 2021-01-15 | 2021-01-15 | 1 | 2021-01-29 | 10 | 2021-02-11 | 9 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-03-11 | 19 |  |  |  |  | 2021-01-14 | 2021-01-15 | 2021-01-28 | 9 |  |  |  |  | 2021-03-15 | 2021-03-24 | 7 | [15 empty] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-24 |  | 2021-03-25 | 1
120493496 | 124 | PGE | NEM | EXPNEM | Commercial | Solar PV | 31.024 |  | 2021-02-02 |  |  | 2021-02-03 | 2021-02-03 | 1 | 2021-02-03 | 1 | 2021-02-26 | 16 | [15 empty] | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-03-15 | 11 | [12 empty] | 2021-03-18 | 2021-03-24 | 4 | [15 empty] | 2021-03-18 | 2021-03-19 | 1 | 2021-03-24 |  | 2021-03-25 | 1
120426374 | 125 | PGE | NEM | EXPNEM | Commercial | Solar PV | 68.358 |  | 2021-01-13 |  |  | 2021-01-28 | 2021-01-28 | 10 | 2021-01-28 | 10 | 2021-02-18 | 14 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-10 | 14 | [12 empty] | 2021-03-13 | 2021-03-25 | 8 | [15 empty] | 2021-03-13 | 2021-03-15 | 0 | 2021-03-25 |  | 2021-03-25 | 0
120529039 | 126 | PGE | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-02-11 |  | 2021-02-25 | 2021-02-16 | 2021-02-16 | 2 | 2021-03-09 | 17 | 2021-03-24 | 11 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-03-26 | 2 |  |  |  |  | 2021-02-17 | [7 empty] | 2021-03-29 | 2021-04-02 | 4 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-04-02 |  | 2021-04-05 | 1
120443085 | 128 | PGE | NEM | EXPNEM | Commercial | Solar PV | 70.479 |  | 2021-01-18 |  | 2021-03-04 | 2021-01-20 | 2021-01-20 | 1 | 2021-03-09 | 34 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-03-31 | 3 |  |  |  |  | 2021-03-02 | 2021-03-09 | 2021-03-12 | 8 |  |  |  |  | 2021-04-02 | 2021-04-12 | 6 | [15 empty] | 2021-04-02 | 2021-04-05 | 1 | 2021-04-12 |  | 2021-04-19 | 5
120430305 | 131 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 33.05 |  | 2021-01-14 |  |  | 2021-01-25 | 2021-01-25 | 6 | 2021-01-25 | 6 | 2021-02-04 | 8 | [15 empty] | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | 2021-02-04 | 8
120527785 | 134 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 40.356 |  | 2021-02-11 |  | 2021-02-22 | 2021-02-22 | 2021-02-22 | 6 | 2021-03-11 | 19 | 2021-03-17 | 4 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-02-26 | 4 | [12 empty] | 2021-08-19 | 2021-08-19 | 0 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 |  | 2021-08-19 | 0
120473401 | 135 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 34.2 |  | 2021-01-28 |  | 2021-02-10 | 2021-02-10 | 2021-02-10 | 9 | 2021-03-17 | 33 | 2021-03-25 | 6 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-21 | 2 | [15 empty] | 2021-06-30
120681589 | 136 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.356 |  | 2021-03-23 |  |  | 2021-04-06 | 2021-04-06 | 10 | 2021-04-06 | 10 | 2021-04-07 | 1 | [19 empty] | 2021-03-23 | N/A | [9 empty] | 2021-04-29 | 2021-04-29 | 0 | 2021-07-19 | 2021-07-27 | 6 | [15 empty] | 2021-07-19 | 2021-07-20 | 1 | 2021-07-27 |  | 2021-07-27 | 0
120499344 | 139 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 |  | 2021-02-04 |  | 2021-02-10 | 2021-02-10 | 2021-02-10 | 4 | 2021-04-14 | 48 | 2021-04-23 | 7 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-29 | 24 | [12 empty] | 2021-04-23 | 2021-04-24 | 0 | [15 empty] | 2021-04-23 | 2021-04-24 | 0 | 2021-04-24 |  | 2021-04-27 | 1
120711215 | 140 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.8 |  | 2021-03-30 |  | 2021-04-09 | 2021-04-09 | 2021-04-09 | 8 | 2021-05-21 | 38 | 2021-05-26 | 3 | [15 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-03-30 | 0 | [12 empty] | 2021-05-26 | 2021-05-26 | 0 | [15 empty] | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 |  | 2021-05-27 | 1
120527063 | 141 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 53.626 |  | 2021-02-11 |  | 2021-02-22 | 2021-02-22 | 2021-02-22 | 6 | 2021-03-11 | 19 | 2021-03-22 | 7 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-01 | 5 | [5 empty] | 2021-04-22 | 2021-05-07 | 11 | [7 empty] | 2021-06-10 | 2021-09-13 | 65 |  |  |  | 2021-10-06
120503943 | 144 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 39.988 |  | 2021-02-05 |  | 2021-02-21 | 2021-02-21 | 2021-02-21 | 9 | 2021-03-16 | 26 | 2021-03-24 | 6 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-16 | 0 |  |  |  |  | 2021-05-19 | 2021-05-19 | 2021-05-28 | 7 |  |  |  |  | 2021-06-15 | 2021-06-25 | 8 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-25 |  | 2021-06-28 | 1
120432706 | 145 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 39.857 |  | 2021-01-15 |  |  | 2021-01-25 | 2021-01-25 | 5 | 2021-01-25 | 5 | 2021-01-26 | 1 | [15 empty] | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | 2021-01-28 | 3 | [12 empty] | 2021-01-28 | 2021-01-28 | 0 | [15 empty] | 2021-01-28 | 2021-01-28 | 0 | 2021-01-28 |  | 2021-01-30 | 1
120237723 | 146 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2020-12-29 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 9 | 2021-01-28 | 20 | 2021-02-02 | 3 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-03 | 1 | [12 empty] | 2021-02-11 | 2021-02-11 | 0 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 |  | 2021-02-17 | 3
120454746 | 147 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 |  | 2021-01-21 |  |  | 2021-02-03 | 2021-02-03 | 9 | 2021-02-03 | 9 | 2021-02-09 | 4 | [15 empty] | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | 2021-02-09 | 0 | [12 empty] | 2021-02-12 | 2021-02-12 | 0 | [15 empty] | 2021-02-12 | 2021-02-12 | 0 | 2021-02-12 |  | 2021-02-17 | 2
120434709 | 148 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-01-15 |  |  | 2021-01-28 | 2021-01-28 | 8 | 2021-01-28 | 8 | 2021-02-08 | 7 | [15 empty] | 2021-01-28 | 2021-01-28 | 0 | 2021-01-28 | 2021-02-08 | 7 | [12 empty] | 2021-02-08 | 2021-02-16 | 5 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-16 |  | 2021-02-17 | 1
120528378 | 150 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-02-11 |  |  | 2021-02-23 | 2021-02-23 | 7 | 2021-02-23 | 7 | 2021-02-26 | 3 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-02-23 | 0 | [12 empty] | 2021-02-26 | 2021-02-28 | 0 | [15 empty] | 2021-02-26 | 2021-02-28 | 0 | 2021-02-28 |  | 2021-03-06 | 5
120537974 | 152 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 |  | 2021-02-16 |  |  | 2021-03-01 | 2021-03-01 | 9 | 2021-03-01 | 9 | 2021-03-02 | 1 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-03 | 2 | [12 empty] | 2021-03-04 | 2021-03-04 | 0 | [15 empty] | 2021-03-04 | 2021-03-04 | 0 | 2021-03-04 |  | 2021-03-06 | 1
120506167 | 153 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 |  | 2021-02-08 |  |  | 2021-02-23 | 2021-02-23 | 10 | 2021-02-23 | 10 | 2021-03-03 | 6 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-02 | 5 | [12 empty] | 2021-03-08 | 2021-03-08 | 0 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 |  | 2021-03-11 | 3
120506404 | 154 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 |  | 2021-02-08 |  |  | 2021-02-23 | 2021-02-23 | 10 | 2021-02-23 | 10 | 2021-03-03 | 6 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-03 | 6 | [12 empty] | 2021-03-08 | 2021-03-08 | 0 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 |  | 2021-03-11 | 3
120552170 | 155 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-02-18 |  |  | 2021-03-03 | 2021-03-03 | 9 | 2021-03-03 | 9 | 2021-03-04 | 1 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-08 | 3 |  |  |  |  | 2021-02-18 | 2021-03-03 | 2021-03-03 | 9 |  |  |  |  | 2021-03-08 | 2021-03-08 | 0 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 |  | 2021-03-13 | 4
120529057 | 157 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.92 |  | 2021-02-11 |  | 2021-02-24 | 2021-02-23 | 2021-02-23 | 7 | 2021-02-25 | 9 | 2021-03-09 | 8 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-02 | 3 | [12 empty] | 2021-03-09 | 2021-03-10 | 1 | [15 empty] | 2021-03-09 | 2021-03-10 | 1 | 2021-03-10 |  | 2021-03-13 | 2
120529081 | 159 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-02-11 |  |  | 2021-02-23 | 2021-02-23 | 7 | 2021-02-23 | 7 | 2021-02-25 | 2 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-08 | 9 | [12 empty] | 2021-03-11 | 2021-03-11 | 0 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 |  | 2021-03-13 | 1
120462758 | 161 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.337 |  | 2021-01-25 |  |  | 2021-02-08 | 2021-02-08 | 10 | 2021-02-08 | 10 | 2021-02-26 | 13 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-03-02 | 15 | [12 empty] | 2021-03-17 | 2021-03-17 | 0 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 |  | 2021-03-19 | 2
120508284 | 162 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.741 |  | 2021-02-08 |  |  | 2021-02-23 | 2021-02-23 | 10 | 2021-02-23 | 10 | 2021-03-01 | 4 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-02 | 5 | [12 empty] | 2021-03-17 | 2021-03-17 | 0 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 |  | 2021-03-19 | 2
120569248 | 163 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-02-23 |  |  | 2021-03-06 | 2021-03-06 | 8 | 2021-03-06 | 8 | 2021-03-08 | 0 | [15 empty] | 2021-03-06 | 2021-03-06 | 0 | 2021-03-06 | 2021-03-23 | 11 | [12 empty] | 2021-03-23 | 2021-03-23 | 0 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 |  | 2021-03-27 | 3
120506268 | 165 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.646 |  | 2021-02-08 |  | 2021-02-16 | 2021-02-16 | 2021-02-16 | 5 | 2021-03-02 | 15 | 2021-03-06 | 3 | [15 empty] | 2021-03-06 | 2021-03-06 | 0 | 2021-03-06 | 2021-03-10 | 2 | [12 empty] | 2021-03-24 | 2021-03-25 | 1 | [15 empty] | 2021-03-24 | 2021-03-25 | 1 | 2021-03-25 |  | 2021-03-30 | 3
120428651 | 166 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.393 |  | 2021-01-14 |  | 2021-01-23 | 2021-01-23 | 2021-01-23 | 5 | 2021-02-25 | 28 | 2021-03-16 | 13 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-16 | 0 | [12 empty] | 2021-03-29 | 2021-03-29 | 0 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 |  | 2021-03-30 | 1
120586339 | 167 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.75 |  | 2021-03-01 |  |  | 2021-03-13 | 2021-03-13 | 9 | 2021-03-13 | 9 | 2021-03-16 | 1 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-29 | 10 | [12 empty] | 2021-03-29 | 2021-03-29 | 0 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 |  | 2021-04-03 | 4
120587077 | 168 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 |  | 2021-03-01 |  | 2021-03-29 | 2021-03-13 | 2021-03-13 | 9 | 2021-03-13 | 9 | 2021-03-23 | 6 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-29 | 10 | [12 empty] | 2021-03-29 | 2021-03-29 | 0 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 |  | 2021-04-03 | 4
120591285 | 170 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 46.533 |  | 2021-03-02 |  | 2021-03-31 | 2021-03-13 | 2021-03-13 | 8 | 2021-03-13 | 8 | 2021-03-24 | 7 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-31 | 12 | [12 empty] | 2021-03-31 | 2021-03-31 | 0 | [15 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 |  | 2021-04-03 | 2
120587295 | 171 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-03-01 |  |  | 2021-03-13 | 2021-03-13 | 9 | 2021-03-13 | 9 | 2021-03-23 | 6 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-29 | 10 | [12 empty] | 2021-03-31 | 2021-04-01 | 1 | [15 empty] | 2021-03-31 | 2021-04-01 | 1 | 2021-04-01 |  | 2021-04-03 | 1
120642909 | 173 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.36 |  | 2021-03-15 |  |  | 2021-03-27 | 2021-03-27 | 9 | 2021-03-27 | 9 | 2021-04-03 | 5 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | 2021-03-30 | 1 | [12 empty] | 2021-04-03 | 2021-04-05 | 0 | [15 empty] | 2021-04-03 | 2021-04-05 | 0 | 2021-04-05 |  | 2021-04-10 | 4
120665466 | 176 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 |  | 2021-03-19 |  |  | 2021-04-02 | 2021-04-02 | 10 | 2021-04-02 | 10 | 2021-04-08 | 4 | [19 empty] | 2021-03-19 | N/A | [12 empty] | 2021-04-08 | 2021-04-08 | 0 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 |  | 2021-04-10 | 1
120686618 | 177 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.699 |  | 2021-03-24 |  |  | 2021-04-07 | 2021-04-07 | 10 | 2021-04-07 | 10 | 2021-04-09 | 2 | [19 empty] | 2021-03-24 | N/A | [12 empty] | 2021-04-09 | 2021-04-09 | 0 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 |  | 2021-04-10 | 0
120506283 | 178 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-02-08 |  | 2021-02-16 | 2021-02-16 | 2021-02-16 | 5 | 2021-03-17 | 26 | 2021-03-22 | 3 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-03-24 | 2 | [12 empty] | 2021-04-12 | 2021-04-12 | 0 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 |  | 2021-04-13 | 1
120525535 | 179 | PGE | NEM | NEMMT | IA in Progress | FUCE, Storage | 1470 |  | 2021-02-10 |  | 2021-03-07 | 2021-02-22 | 2021-02-22 | 7 | 2021-03-21 | 26 | 2021-04-08 | 13 | 2021-04-08 | 2021-05-06 | 20 | [12 empty] | 2021-05-20 | 2021-06-04 | 10 | 2021-06-04 | [7 empty] | 2021-03-21 | 2021-03-25 | 3
120454393 | 180 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-01-21 | 2021-01-25 |  | 2021-01-25 | 2021-01-25 | 2 | 2021-03-03 | 28 | 2021-03-22 | 13 | [15 empty] | 2021-03-22 | 2021-03-23 | 1 | 2021-03-23 | 2021-07-09 | 76 |  |  |  |  | 2021-01-21 | 2021-03-23 | 2021-04-02 | 50
120632092 | 181 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 46.538 |  | 2021-03-10 |  |  | 2021-03-24 | 2021-03-24 | 10 | 2021-03-24 | 10 | 2021-04-12 | 13 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-03-30 | 4 | [8 empty] | 2021-03-24 | 2021-03-24 | 2021-03-24 | 0 | 2021-06-07 | 2021-06-15 | 6 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-15 |  | 2021-06-15 | 0
120555694 | 182 | PGE | Non-NEM | Continuous Uncompensated Export | Withdrawn | Solar PV | 625 |  | 2021-02-19 | 2021-02-22 |  | 2021-02-22 | 2021-02-22 | 1 | 2021-02-24 | 3 | 2021-03-15 | 13 | [15 empty] | 2021-03-15 | 2021-03-31 | 12 | 2021-03-31 | [10 empty] | 2021-03-31
120659150 | 184 | PGE | NEM | EXPNEM | Implementation | Solar PV | 795.8 |  | 2021-03-18 |  | 2021-04-01 | 2021-04-01 | 2021-04-01 | 10 | 2021-05-28 | 51 | 2021-07-29 | 42 | [15 empty] | 2021-07-29 | 2021-07-29 | 0 | 2021-07-29 | 2021-09-07 | 27 |  |  |  |  | 2021-03-18 | 2021-06-04 | 2021-06-16 | 63
120659151 | 185 | PGE | NEM | EXPNEM | Implementation | Solar PV | 333.3 |  | 2021-03-18 |  | 2021-04-01 | 2021-04-01 | 2021-04-01 | 10 | 2021-05-06 | 35 | 2021-07-09 | 44 | [15 empty] | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09 | 2021-09-07 | 41 |  |  |  |  | 2021-03-18 | 2021-06-04 | 2021-06-16 | 63
120673552 | 186 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 69.804 |  | 2021-03-22 |  | 2021-06-11 | 2021-04-01 | 2021-04-01 | 8 | 2021-09-07 | 118
120693209 | 187 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 98.136 |  | 2021-03-25 |  | 2021-09-29 | 2021-04-05 | 2021-04-05 | 7
120708558 | 188 | PGE | NEM | EXPNEM | Implementation | Solar PV | 240 |  | 2021-03-29 |  | 2021-05-14 | 2021-04-06 | 2021-04-06 | 6 | 2021-05-10 | 30 | 2021-07-16 | 47 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-16 | 2021-08-12 | 19 |  |  |  |  | 2021-03-29 | 2021-08-03 | 2021-08-13 | 97
120698495 | 189 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 830 |  | 2021-03-26 |  | 2021-07-21 | 2021-04-07 | 2021-04-07 | 8 | 2021-08-04 | 91 | 2021-08-24 | 14 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24
120717219 | 190 | PGE | NEM | EXPNEM | Commercial | Solar PV | 36.913 |  | 2021-03-31 |  | 2021-07-09 | 2021-04-07 | 2021-04-07 | 5 | 2021-07-07 | 68 | 2021-07-26 | 13 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-07-27 | 1 |  |  |  |  | 2021-03-31 | 2021-07-12 | 2021-07-23 | 80 |  |  |  |  | 2021-07-27 | 2021-08-02 | 4 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-08-02 |  | 2021-08-02 | 0
120720930 | 191 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 150.795 |  | 2021-03-31 |  | 2021-04-12 | 2021-04-12 | 2021-04-12 | 8
120433597 | 192 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 150 |  | 2021-01-15 |  | 2021-07-13 | 2021-01-19 | 2021-01-19 | 1 | 2021-07-29 | 135 | 2021-09-07 | 27 | [15 empty] | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 | 2021-09-15 | 4 | [5 empty] | 2021-08-09 | 2021-08-19 | 8 |  |  |  |  | 2021-09-30 | [17 empty] | 2021-09-30
120445426 | 193 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 35.713 |  | 2021-01-19 |  | 2021-01-20 | 2021-01-20 | 2021-01-20 | 1
120458867 | 194 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 343.39 |  | 2021-01-22 |  | 2021-05-11 | 2021-01-25 | 2021-01-25 | 1 | [29 empty] | 2021-01-22
120460496 | 195 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 86.4 |  | 2021-01-24 |  | 2021-07-17 | 2021-01-26 | 2021-01-26 | 1 | 2021-07-23 | 126 | [27 empty] | 2021-01-24
120446515 | 196 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 32.88 |  | 2021-01-19 |  | 2021-02-09 | 2021-01-26 | 2021-01-26 | 5 | 2021-02-19 | 22 | 2021-05-04 | 52 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | 2021-06-17 | 31
120468691 | 197 | PGE | NEM | EXPNEM | Implementation | Solar PV | 43.128 |  | 2021-01-27 |  | 2021-04-15 | 2021-01-27 | 2021-01-27 | 0 | 2021-04-19 | 57 | 2021-04-27 | 6 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-09-01 | 3 |  |  |  |  | 2021-01-27 | 2021-05-14 | 2021-05-28 | 86 |  |  |  |  | 2021-09-23 | 2021-09-30 | 5 | [15 empty] | 2021-09-23 | 2021-09-24 | 1 | 2021-09-30
120475484 | 199 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 52.78 |  | 2021-01-28 |  | 2021-01-29 | 2021-01-29 | 2021-01-29 | 1
120433179 | 200 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 62.5 |  | 2021-01-15 |  | 2021-02-02 | 2021-02-01 | 2021-02-01 | 10
120496525 | 201 | PGE | NEM | EXPNEM | Commercial | Solar PV | 30.277 |  | 2021-02-03 |  | 2021-02-04 | 2021-02-04 | 2021-02-04 | 1 | 2021-06-03 | 84 | 2021-06-18 | 11 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-18 | 2021-06-21 | 1 | [12 empty] | 2021-07-12 | 2021-07-12 | 0 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 |  | 2021-07-12 | 0
120500796 | 202 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 299.7 |  | 2021-02-04 |  | 2021-02-05 | 2021-02-05 | 2021-02-05 | 1 | [29 empty] | 2021-02-04
120503280 | 203 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 44.198 |  | 2021-02-05 |  | 2021-02-08 | 2021-02-08 | 2021-02-08 | 1
120474956 | 204 | PGE | NEM | EXPNEM | Implementation | Solar PV | 37.009 |  | 2021-01-28 |  | 2021-04-14 | 2021-02-09 | 2021-02-09 | 8 | 2021-04-21 | 58 | 2021-04-26 | 3 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-05-14 | 14 |  |  |  |  | 2021-05-19 | 2021-05-19 | 2021-05-28 | 7 |  |  |  |  | 2021-06-24 | 2021-06-30 | 4 | 2021-06-30 | [14 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-30 | 2021-07-07 |  | 4 |  |  | 111 |  | 111
120511110 | 205 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 114.365 |  | 2021-02-09 |  | 2021-08-09 | 2021-02-10 | 2021-02-10 | 1 | 2021-08-13 | 130 | 2021-08-24 | 7 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24
120486196 | 206 | PGE | NEM | EXPNEM | Implementation | Solar PV | 36.312 |  | 2021-02-01 |  | 2021-02-11 | 2021-02-10 | 2021-02-10 | 7 | 2021-08-17 | 138 | 2021-08-30 | 9 | [15 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-09-01 | 2 |  |  |  |  | 2021-02-01 | 2021-08-17 | 2021-09-02 | 150
120536259 | 207 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 36 |  | 2021-02-16 |  | 2021-06-05 | 2021-02-17 | 2021-02-17 | 1 | 2021-06-09 | 80 | 2021-06-17 | 6 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | [6 empty] | 2021-02-16 | 2021-06-05 | 2021-06-16 | 85
120500854 | 208 | PGE | NEM | EXPNEM | Commercial | Solar PV | 187.5 |  | 2021-02-04 |  | 2021-04-16 | 2021-02-17 | 2021-02-17 | 8 | 2021-04-21 | 53 | 2021-05-27 | 26 | [15 empty] | 2021-05-27 | 2021-06-09 | 8 | 2021-06-09 | 2021-06-09 | 0 |  |  |  |  | 2021-02-04 | 2021-04-20 | 2021-05-07 | 65 |  |  |  |  | 2021-06-10 | 2021-06-17 | 5 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-17 |  | 2021-06-17 | 0
120534633 | 209 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 341.862 |  | 2021-02-15 |  | 2021-04-16 | 2021-02-18 | 2021-02-18 | 2 | 2021-04-30 | 53 | 2021-05-16 | 10 | 2021-05-16 | 2021-06-14 | 19 | [12 empty] | 2021-06-14 | 2021-06-14 | 0 | 2021-06-14 | 2021-08-30 | 54 |  |  |  |  | 2021-02-15 | 2021-04-30 | 2021-05-10 | 59
120570852 | 210 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 38.779 |  | 2021-02-23 |  | 2021-08-21 | 2021-02-24 | 2021-02-24 | 1 | [29 empty] | 2021-08-18
120572497 | 211 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2021-02-24 |  | 2021-03-31 | 2021-02-25 | 2021-02-25 | 1 | 2021-06-10 | 75 | 2021-06-17 | 5 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17
120531156 | 212 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 395.208 |  | 2021-02-12 |  | 2021-03-04 | 2021-02-27 | 2021-02-27 | 9 | [29 empty] | 2021-02-12
120534902 | 213 | PGE | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-02-15 |  | 2021-03-01 | 2021-03-01 | 2021-03-01 | 9 | 2021-05-03 | 54 | 2021-05-24 | 15 | [15 empty] | 2021-05-24 | 2021-06-10 | 12 | 2021-06-10 | 2021-06-25 | 11 | [5 empty] | 2021-05-24 | 2021-06-03 | 7 | 2021-08-13 |  |  |  | 2021-08-31 | 2021-09-01 | 1 | [15 empty] | 2021-08-31 | 2021-09-01 | 1 | 2021-09-01 |  | 2021-09-02 | 1
120537256 | 214 | PGE | NEM | EXPNEM | Implementation | Solar PV | 240 |  | 2021-02-16 |  | 2021-03-02 | 2021-03-02 | 2021-03-02 | 10 | 2021-05-04 | 55 | [5 empty] | 2021-05-04 | 2021-06-16 | 30 | 2021-06-16 |  |  |  | 2021-08-31 |  |  |  |  | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 | 2021-09-07 | 4 |  |  |  |  | 2021-02-16
120587464 | 215 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 268.003 |  | 2021-03-01 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 3 | 2021-05-11 | 51 | 2021-06-16 | 25 | [15 empty] | 2021-06-16 | 2021-06-17 | 1 | 2021-06-17 | 2021-06-17 | 0
120574009 | 216 | PGE | NEM | EXPNEM | Study in Progress | ENGN, OTHR | 39.894 |  | 2021-02-24 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 7 | 2021-04-21 | 40 | [27 empty] | 2021-04-20 | 2021-04-21 | 2021-05-07 | 13
120605545 | 217 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 60.455 |  | 2021-03-05 |  | 2021-03-08 | 2021-03-08 | 2021-03-08 | 1
120569058 | 218 | PGE | NEM | EXPNEM | Implementation | Solar PV | 336 |  | 2021-02-23 |  | 2021-04-30 | 2021-03-08 | 2021-03-08 | 9 | 2021-05-12 | 56 | 2021-05-25 | 9 | [15 empty] | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-07-06 | 28 | [8 empty] | 2021-06-16 | [6 empty] | 2021-09-01 | 2021-09-13 | 7 |  |  |  | 2021-09-22 |  |  | 2021-09-22
120568229 | 219 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 50.848 |  | 2021-02-23 |  | 2021-03-09 | 2021-03-09 | 2021-03-09 | 10 | 2021-04-27 | 45 | 2021-05-24 | 19 | 2021-05-24 | 2021-06-28 | 24 | 2021-06-28 | 2021-07-22 | 17 | 2021-07-22 | 2021-08-04 | 9 |  |  |  | 2021-08-04 | [12 empty] | 2021-02-23
120567150 | 220 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 540 |  | 2021-02-23 |  | 2021-04-27 | 2021-03-09 | 2021-03-09 | 10 | 2021-05-03 | 49 | 2021-05-20 | 13 | 2021-05-24 | 2021-06-30 | 26 | 2021-07-12 | 2021-08-09 | 20 | 2021-08-09
120612481 | 221 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 65.56 |  | 2021-03-08 |  | 2021-03-10 | 2021-03-10 | 2021-03-10 | 2 | [29 empty] | 2021-03-08
120608662 | 222 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 47.56 |  | 2021-03-05 |  | 2021-05-20 | 2021-03-10 | 2021-03-10 | 3 | 2021-06-09 | 67 | 2021-06-17 | 6 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17
120618014 | 224 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-03-09 |  | 2021-03-29 | 2021-03-11 | 2021-03-11 | 2 | 2021-04-15 | 27 | 2021-09-14 | 105 | [15 empty] | 2021-09-14 | 2021-09-14 | 0 | 2021-09-14
120628386 | 225 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 323.042 |  | 2021-03-10 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 2 | [29 empty] | 2021-03-10
120581661 | 226 | PGE | NEM | EXPNEM | Commercial | Solar PV | 84.418 |  | 2021-02-26 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 10 | 2021-05-07 | 50 | 2021-07-14 | 46 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-16 | 2 | [5 empty] | 2021-07-02 | 2021-07-12 | 5 |  |  |  |  | 2021-07-16 | 2021-07-22 | 4 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-22 |  | 2021-07-22 | 0
120586983 | 227 | PGE | NEM | EXPNEM | Implementation | Solar PV | 460 |  | 2021-03-01 |  | 2021-03-13 | 2021-03-13 | 2021-03-13 | 9 | 2021-05-06 | 48 | 2021-06-07 | 21 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-06-08 | 1 |  |  |  |  | 2021-03-01
120636153 | 228 | PGE | NEM | EXPNEM | Commercial | Solar PV | 33.411 |  | 2021-03-11 |  | 2021-05-17 | 2021-03-15 | 2021-03-15 | 2 | 2021-05-19 | 49 | 2021-06-07 | 12 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-06-11 | 4 | [12 empty] | 2021-07-15 | 2021-07-20 | 3 | [15 empty] | 2021-07-15 | 2021-07-16 | 1 | 2021-07-20 |  | 2021-07-27 | 5
120637984 | 229 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 92.316 |  | 2021-03-12 |  | 2021-03-24 | 2021-03-16 | 2021-03-16 | 2 | [29 empty] | 2021-03-12
120599986 | 230 | PGE | NEM | EXPNEM | Implementation | Solar PV | 287.5 |  | 2021-03-03 |  | 2021-03-17 | 2021-03-17 | 2021-03-17 | 10 | 2021-04-20 | 34 | 2021-05-10 | 14 | [15 empty] | 2021-05-10 | 2021-05-17 | 5 | 2021-05-17 | 2021-05-17 | 0 |  |  |  |  | 2021-03-03 | 2021-04-20 | 2021-05-05 | 45 |  |  |  |  | 2021-09-10 | 2021-09-21 | 7 | 2021-07-26 | 2021-08-31 | 26 |  |  |  | 2021-09-13 |  |  | 2021-09-13 | [5 empty] | 2021-09-10 | 2021-09-12 | 0 | 2021-09-21
120640163 | 232 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.2 |  | 2021-03-12 |  | 2021-03-17 | 2021-03-17 | 2021-03-17 | 3 | [29 empty] | 2021-03-12
120638036 | 233 | PGE | NEM | EXPNEM | Commercial | Solar PV | 42.802 |  | 2021-03-12 |  | 2021-07-14 | 2021-03-17 | 2021-03-17 | 3 | 2021-07-20 | 90 | 2021-08-02 | 9 | [15 empty] | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | 2021-08-12 | 8 | [12 empty] | 2021-08-19 | 2021-08-26 | 5 | [15 empty] | 2021-08-19 | 2021-08-20 | 1 | 2021-08-26 |  | 2021-09-10 | 10
120637987 | 234 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 55.546 |  | 2021-03-12 |  | 2021-04-16 | 2021-03-17 | 2021-03-17 | 3 | [29 empty] | 2021-03-12
120651436 | 235 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 548.77 |  | 2021-03-17 |  | 2021-03-18 | 2021-03-18 | 2021-03-18 | 1 | 2021-04-15 | 21 | 2021-06-04 | 35 | [15 empty] | 2021-06-04 | 2021-06-04 | 0 | 2021-06-04 | 2021-06-18 | 10 |  |  |  |  | 2021-03-17
120642515 | 236 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 531.086 |  | 2021-03-14 |  | 2021-05-26 | 2021-03-18 | 2021-03-18 | 3 | 2021-06-03 | 57 | 2021-07-09 | 25 | [15 empty] | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12
120651457 | 237 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 500 |  | 2021-03-17 |  | 2021-03-18 | 2021-03-18 | 2021-03-18 | 1 | [29 empty] | 2021-03-17
120603645 | 238 | PGE | NEM | EXPNEM | Implementation | Solar PV | 335.644 |  | 2021-03-04 |  | 2021-03-18 | 2021-03-18 | 2021-03-18 | 10 | 2021-05-03 | 42 | 2021-06-21 | 34 | 2021-06-21 | 2021-08-09 | 34 | [12 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-24 | 11 |  |  |  |  | 2021-03-04
120651376 | 239 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 136.1 |  | 2021-03-17 |  | 2021-03-18 | 2021-03-18 | 2021-03-18 | 1 | [29 empty] | 2021-03-17
120608844 | 240 | PGE | NEM | EXPNEM | Implementation | Solar PV | 299.7 |  | 2021-03-05 |  | 2021-03-19 | 2021-03-19 | 2021-03-19 | 10 | 2021-06-16 | 72 | 2021-07-26 | 27 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-07-27 | 1 |  |  |  |  | 2021-03-05 | 2021-04-11 | 2021-05-03 | 41
120608539 | 241 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 187.5 |  | 2021-03-05 |  | 2021-03-19 | 2021-03-19 | 2021-03-19 | 10 | 2021-08-12 | 112 | 2021-09-02 | 15 | [15 empty] | 2021-09-02 | 2021-09-03 | 1 | 2021-09-03 | [6 empty] | 2021-03-05 | 2021-08-12 | 2021-08-24 | 120
120651931 | 243 | PGE | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-03-17 |  | 2021-03-25 | 2021-03-19 | 2021-03-19 | 2 | 2021-05-13 | 41 | 2021-06-03 | 14 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-14 | 7 | [5 empty] | 2021-06-24 | 2021-07-09 | 10 |  |  |  |  | 2021-08-09 | 2021-08-12 | 3 | 2021-09-29 | 2021-10-01 | 2 | [12 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-12 |  | 2021-08-19 | 5
120653625 | 244 | PGE | NEM | EXPNEM | Commercial | Solar PV | 33.128 |  | 2021-03-17 |  | 2021-04-13 | 2021-03-19 | 2021-03-19 | 2 | 2021-04-20 | 24 | 2021-07-06 | 53 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-07-27 | 15 | [12 empty] | 2021-08-04 | 2021-08-12 | 6 | [15 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-12 |  | 2021-08-16 | 2
120654327 | 245 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 351.986 |  | 2021-03-17 |  | 2021-04-14 | 2021-03-19 | 2021-03-19 | 2 | 2021-05-05 | 35 | 2021-07-02 | 41 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | [6 empty] | 2021-04-12
120660151 | 246 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 396.286 |  | 2021-03-18 |  | 2021-04-20 | 2021-03-22 | 2021-03-22 | 2 | 2021-04-27 | 28 | 2021-05-20 | 17 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | [6 empty] | 2021-03-18 | 2021-07-12 | 2021-07-23 | 89
120658536 | 247 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 780 |  | 2021-03-18 |  | 2021-04-14 | 2021-03-22 | 2021-03-22 | 2 | 2021-04-16 | 21 | 2021-05-12 | 18 | 2021-05-12 | 2021-06-01 | 13 | [12 empty] | 2021-06-01 | 2021-06-01 | 0 | 2021-06-01 | [6 empty] | 2021-03-18 | 2021-04-14 | 2021-05-07 | 36
120617479 | 248 | PGE | NEM | EXPNEM | Implementation | Solar PV | 150 |  | 2021-03-09 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 10 | 2021-06-21 | 73 | 2021-07-07 | 11 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | 2021-07-09 | 2 |  |  |  |  | 2021-03-09 | 2021-06-21 | 2021-07-08 | 85 | [7 empty] | 2021-09-30
120668012 | 249 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 43.78 |  | 2021-03-20 |  | 2021-07-14 | 2021-03-23 | 2021-03-23 | 1 | 2021-07-21 | 85
120673323 | 250 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 200 |  | 2021-03-22 |  | 2021-03-24 | 2021-03-24 | 2021-03-24 | 2 | 2021-05-05 | 32 | 2021-07-09 | 45 | [15 empty] | 2021-07-09 | 2021-07-10 | 0 | 2021-07-10 | 2021-08-19 | 28 | [5 empty] | 2021-09-21 | 2021-09-23 | 2
120677457 | 251 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 181.876 |  | 2021-03-23 |  | 2021-03-24 | 2021-03-24 | 2021-03-24 | 1 | 2021-06-07 | 53 | 2021-07-30 | 38 | [15 empty] | 2021-07-30 | 2021-07-30 | 0 | 2021-07-30 | 2021-08-19 | 14 |  |  |  |  | 2021-07-16 | 2021-08-21 | 2021-09-07 | 36
120677481 | 252 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 83.3 |  | 2021-03-23 |  | 2021-05-03 | 2021-03-24 | 2021-03-24 | 1 | 2021-05-18 | 40 | 2021-06-07 | 13 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-06-11 | 4 | [5 empty] | 2021-06-18 | 2021-07-02 | 10 |  |  |  |  | 2021-09-30 | [17 empty] | 2021-09-30 | 2021-09-30 | 0
120674435 | 253 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 183.3 |  | 2021-03-22 |  | 2021-03-31 | 2021-03-24 | 2021-03-24 | 2 | 2021-05-03 | 30 | 2021-06-01 | 20 | [15 empty] | 2021-06-01 | 2021-06-07 | 4 | 2021-06-07 | 2021-07-21 | 31 |  |  |  |  | 2021-03-22 | 2021-09-22 | 2021-09-22 | 129 | [7 empty] | 2021-07-20
120640079 | 254 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 168 |  | 2021-03-12 |  | 2021-03-25 | 2021-03-25 | 2021-03-25 | 9
120681063 | 255 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 46.08 |  | 2021-03-23 |  | 2021-09-17 | 2021-03-25 | 2021-03-25 | 2 | [29 empty] | 2021-03-23
120680849 | 256 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 323.852 |  | 2021-03-23 |  | 2021-03-30 | 2021-03-25 | 2021-03-25 | 2 | 2021-04-20 | 20 | 2021-06-30 | 50 | [15 empty] | 2021-06-30 | 2021-07-07 | 4 | 2021-07-07 | 2021-07-08 | 1
120685714 | 257 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 121.259 |  | 2021-03-24 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2 | 2021-04-28 | 25 | 2021-05-11 | 9 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | [6 empty] | 2021-03-24 | 2021-07-15 | 2021-07-19 | 81
120645642 | 259 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 86.4 |  | 2021-03-15 |  | 2021-03-29 | 2021-03-29 | 2021-03-29 | 10 | 2021-05-07 | 39 | 2021-05-18 | 7 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | [6 empty] | 2021-03-15
120677981 | 260 | PGE | NEM | EXPNEM | Commercial | Solar PV | 47.304 |  | 2021-03-23 |  | 2021-05-13 | 2021-03-29 | 2021-03-29 | 4 | 2021-05-14 | 38 | 2021-06-02 | 12 | [15 empty] | 2021-06-02 | 2021-06-07 | 3 | 2021-06-07 | 2021-06-08 | 1 | [8 empty] | 2021-06-17 |  |  |  | 2021-06-18 | 2021-06-29 | 7 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-29 |  | 2021-06-30 | 1
120653330 | 262 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 506.226 |  | 2021-03-17 |  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 10 | [29 empty] | 2021-03-17
120652016 | 263 | PGE | NEM | EXPNEM | Implementation | Solar PV | 516 |  | 2021-03-17 |  | 2021-04-01 | 2021-03-31 | 2021-03-31 | 10 | 2021-05-27 | 51 | 2021-06-17 | 14 | 2021-06-17 | 2021-07-16 | 20 | [12 empty] | 2021-07-16 | 2021-08-19 | 24 | 2021-08-19 | 2021-08-27 | 6 |  |  |  |  | 2021-05-04 | 2021-05-10 | 2021-05-26 | 16
120713658 | 266 | PGE | NEM | EXPNEM | Commercial | Solar PV | 114.669 |  | 2021-03-30 |  | 2021-04-14 | 2021-03-31 | 2021-03-31 | 1 | 2021-04-22 | 17 | 2021-06-18 | 40 | [15 empty] | 2021-06-18 | 2021-06-21 | 1 | 2021-06-21 | 2021-08-12 | 37 | [5 empty] | 2021-05-27 | 2021-06-07 | 6 |  |  |  |  | 2021-09-03 | 2021-09-15 | 7 | [15 empty] | 2021-09-03 | 2021-09-07 | 1 | 2021-09-15 |  | 2021-09-24 | 7
120419686 | 267 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 124.183 |  | 2021-01-11 |  | 2021-01-26 | 2021-01-14 | 2021-01-14 | 3 | 2021-01-28 | 12
120420143 | 268 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 92.482 |  | 2021-01-11 |  | 2021-01-27 | 2021-01-14 | 2021-01-14 | 3 | 2021-01-28 | 12
120420187 | 269 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 88.073 |  | 2021-01-11 |  | 2021-01-26 | 2021-01-20 | 2021-01-20 | 6 | 2021-01-28 | 12
120529179 | 270 | PGE | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-02-11 |  | 2021-02-12 | 2021-02-12 | 2021-02-12 | 1 | 2021-02-16 | 2 | 2021-05-11 | 60 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2021-05-20 | 7 | [12 empty] | 2021-08-18 | 2021-08-26 | 6 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-26 |  | 2021-08-30 | 2
120465673 | 271 | PGE | NEM | EXPNEM | Implementation | Solar PV | 875 |  | 2021-01-26 |  | 2021-02-08 | 2021-02-08 | 2021-02-08 | 9 | 2021-02-19 | 17 | [5 empty] | 2021-02-08 | 2021-03-10 | 21 | 2021-03-10 |  |  | 2021-03-10 | 2021-06-10 | 65 |  |  |  | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-08-20 | 50 |  |  |  |  | 2021-01-26 | 2021-09-14 | 2021-09-21 | 166 | 2021-02-10
120582876 | 272 | PGE | NEM | EXPNEM | Implementation | Solar PV | 900 |  | 2021-02-26 |  | 2021-03-02 | 2021-03-02 | 2021-03-02 | 2 | 2021-03-09 | 7 | [5 empty] | 2021-03-09 | 2021-04-02 | 18 | 2021-04-02 |  |  | 2021-04-02 | 2021-06-08 | 46 |  |  |  | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-07-12 | 23
120602200 | 273 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 65.59 |  | 2021-03-04 |  | 2021-03-10 | 2021-03-08 | 2021-03-08 | 2 | 2021-03-12 | 6 | 2021-04-30 | 35 | [15 empty] | 2021-04-30 | 2021-05-03 | 1 | 2021-05-03
120617291 | 274 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 360.183 |  | 2021-03-09 |  | 2021-03-11 | 2021-03-11 | 2021-03-11 | 2 | 2021-03-15 | 4 | 2021-04-23 | 29 | [15 empty] | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | 2021-05-11 | 12 |  |  |  |  | 2021-03-09 | 2021-07-30 | 2021-08-13 | 111
120477924 | 275 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 587.5 |  | 2021-01-29 |  | 2021-01-29 | 2021-01-29 | 2021-01-29 | 0 | 2021-03-18 | 33 | 2021-05-18 | 43 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | 2021-09-23 | 89 |  |  |  |  | 2021-01-29
120566066 | 276 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-02-22 |  | 2021-03-22 | 2021-02-24 | 2021-02-24 | 2 | 2021-03-24 | 22 | 2021-04-28 | 25 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28
120593233 | 277 | PGE | Non-NEM | Break Before Make | Commercial | ENGN | 3500 |  | 2021-03-02 | 2021-03-15 |  | 2021-03-05 | 2021-03-05 | 3 | 2021-03-24 | 16 | [5 empty] | 2021-03-24 | 2021-04-20 | 19 | 2021-04-20
120653009 | 278 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 37.186 |  | 2021-03-17 |  | 2021-03-19 | 2021-03-19 | 2021-03-19 | 2 | 2021-03-24 | 5 | 2021-05-24 | 43 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24
120552303 | 279 | PGE | NEM | EXPNEM | Implementation | Solar PV | 480 |  | 2021-02-18 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 10 | 2021-03-26 | 26 | 2021-04-15 | 14 | 2021-04-15 | 2021-05-20 | 25 | 2021-06-03 | 2021-06-28 | 17 | 2021-06-28 |  |  |  | 2021-07-26 |  |  |  |  | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-08-19 | 18
120553257 | 280 | PGE | NEM | EXPNEM | Implementation | Solar PV | 85.358 |  | 2021-02-18 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 10 | 2021-03-26 | 26 | 2021-04-16 | 15 | [15 empty] | 2021-04-16 | 2021-04-23 | 5 | 2021-04-23 | 2021-06-02 | 27
120685085 | 281 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 348 |  | 2021-03-24 |  |  | 2021-03-26 | 2021-03-26 | 2 | 2021-03-26 | 2 | 2021-06-19 | 59 | [15 empty] | 2021-06-19 | 2021-06-19 | 0 | 2021-06-19 | [6 empty] | 2021-03-24 | 2021-07-15 | 2021-07-15 | 79
120639109 | 282 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 125 |  | 2021-03-12 |  |  | 2021-03-26 | 2021-03-26 | 10 | 2021-03-26 | 10 | 2021-06-16 | 57 | 2021-06-24 | 2021-07-21 | 18 | 2021-07-21 | 2021-08-18 | 20 | 2021-08-18
120498232 | 283 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 687.5 |  | 2021-02-03 |  | 2021-02-04 | 2021-02-04 | 2021-02-04 | 1 | 2021-03-27 | 36 | 2021-05-18 | 36 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | 2021-09-23 | 89 |  |  |  |  | 2021-02-03
120498193 | 284 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 337.5 |  | 2021-02-03 |  | 2021-02-04 | 2021-02-04 | 2021-02-04 | 1 | 2021-03-27 | 36 | 2021-04-16 | 14 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | 2021-09-23 | 111 |  |  |  |  | 2021-02-03
120653902 | 285 | PGE | NEM | EXPNEM | Commercial | Solar PV | 37.598 |  | 2021-03-17 |  | 2021-03-25 | 2021-03-19 | 2021-03-19 | 2 | 2021-03-29 | 8 | 2021-04-22 | 18 | [15 empty] | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 | 2021-04-26 | 2 | [12 empty] | 2021-06-12 | 2021-06-18 | 4 | [15 empty] | 2021-06-12 | 2021-06-14 | 0 | 2021-06-18 |  | 2021-06-25 | 5
120640481 | 287 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-03-12 |  | 2021-03-17 | 2021-03-17 | 2021-03-17 | 3 | 2021-03-30 | 12 | 2021-05-10 | 29 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | [6 empty] | 2021-03-12
120707801 | 288 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 110 |  | 2021-03-29 |  |  | 2021-03-30 | 2021-03-30 | 1 | 2021-03-30 | 1 | 2021-04-16 | 13 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | [6 empty] | 2021-03-29 | 2021-05-11 | 2021-05-26 | 42
120709190 | 289 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 43.2 |  | 2021-03-29 |  |  | 2021-03-30 | 2021-03-30 | 1 | 2021-03-30 | 1 | [28 empty] | 2021-04-12 | 2021-04-29 | 13
120686200 | 290 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 236.419 |  | 2021-03-24 |  | 2021-03-30 | 2021-03-30 | 2021-03-30 | 4 | 2021-03-30 | 4 | 2021-04-16 | 13 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | [6 empty] | 2021-03-24
120553000 | 291 | PGE | NEM | EXPNEM | Commercial | Solar PV | 52.108 |  | 2021-02-18 |  | 2021-03-30 | 2021-02-19 | 2021-02-19 | 1 | 2021-03-31 | 29 | 2021-04-16 | 12 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | 2021-07-02 | 54 | [12 empty] | 2021-07-13 | 2021-07-21 | 6 | [15 empty] | 2021-07-13 | 2021-07-13 | 0 | 2021-07-21 |  | 2021-07-28 | 5
120636357 | 292 | PGE | NEM | EXPNEM | Implementation | Solar PV | 1250 |  | 2021-03-11 | 2021-03-15 | 2021-03-31 | 2021-03-12 | 2021-03-12 | 1 | 2021-03-31 | 14 | [5 empty] | 2021-03-31 | 2021-04-14 | 10 | 2021-04-14 | 2021-04-19 | 3 | 2021-04-21 | 2021-06-23 | 44 | 2021-04-19 | 2021-04-19 | 0 | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12 | 2021-09-08 | 41 |  |  |  |  | 2021-03-11
120640522 | 293 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 1125 |  | 2021-03-12 | 2021-03-15 |  | 2021-03-15 | 2021-03-15 | 1 | 2021-03-31 | 13 | 2021-04-16 | 12 | [25 empty] | 2021-03-12
120651424 | 294 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 275 |  | 2021-03-17 |  | 2021-04-15 | 2021-03-31 | 2021-03-31 | 10 | 2021-03-31 | 10 | 2021-04-16 | 12 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21
120651437 | 295 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 500 |  | 2021-03-17 |  | 2021-03-18 | 2021-03-18 | 2021-03-18 | 1 | 2021-04-01 | 11 | 2021-04-19 | 12 | 2021-04-19 | 2021-05-26 | 27 | 2021-06-24 | 2021-07-23 | 20 | 2021-07-23 | [18 empty] | 2021-03-17
120708334 | 296 | PGE | NEM | EXPNEM | Implementation | Solar PV | 1937.5 |  | 2021-03-29 | 2021-03-31 |  | 2021-03-31 | 2021-03-31 | 2 | 2021-04-07 | 7 | 2021-05-28 | 37 | 2021-06-09 | 2021-07-08 | 20 | [12 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-12 | 2 |  |  |  |  | 2021-03-29 | 2021-04-21 | 2021-05-07 | 29
120687625 | 297 | PGE | NEM | EXPNEM | Implementation | Solar PV | 445.259 |  | 2021-03-24 |  |  | 2021-04-05 | 2021-04-05 | 8 | 2021-04-07 | 10 | 2021-04-27 | 14 | [15 empty] | 2021-04-27 | 2021-04-27 | 0 | 2021-04-27 | 2021-05-14 | 13 |  |  |  |  | 2021-03-24 | 2021-05-14 | 2021-05-28 | 47 | [7 empty] | 2021-06-08
120698999 | 298 | PGE | NEM | EXPNEM | Implementation | Solar PV | 492.045 |  | 2021-03-26 |  |  | 2021-04-06 | 2021-04-06 | 7 | 2021-04-07 | 8 | 2021-04-20 | 9 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-05-19 | 21 |  |  |  |  | 2021-03-26 | [10 empty] | 2021-06-08 | 2021-10-04 | 82
120634278 | 299 | PGE | NEM | EXPNEM | Commercial | Solar PV | 35.045 |  | 2021-03-11 |  | 2021-03-15 | 2021-03-15 | 2021-03-15 | 2 | 2021-04-08 | 20 | 2021-04-22 | 10 | [15 empty] | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 | 2021-05-05 | 9 |  |  |  |  | 2021-03-11 | 2021-04-12 | 2021-04-29 | 35 |  |  |  |  | 2021-06-18 | 2021-06-24 | 4 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-24 |  | 2021-07-01 | 5
120704197 | 301 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 114.285 |  | 2021-03-28 |  | 2021-03-30 | 2021-03-30 | 2021-03-30 | 1 | 2021-04-09 | 9 | 2021-04-21 | 8 | [15 empty] | 2021-04-21 | 2021-04-21 | 0 | 2021-04-21 | [6 empty] | 2021-03-28 | 2021-04-09 | 2021-04-16 | 14
120528893 | 302 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 114.667 |  | 2021-02-11 |  | 2021-03-31 | 2021-03-01 | 2021-03-01 | 11 | 2021-04-11 | 40 | 2021-05-07 | 19 | [15 empty] | 2021-05-07 | 2021-05-07 | 0 | 2021-05-07 | 2021-05-07 | 0 |  |  |  |  | 2021-02-11 |  |  |  | 2021-05-04 | 2021-05-20 | 2021-05-20 | 12
120691918 | 304 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 200 |  | 2021-03-25 |  | 2021-04-09 | 2021-03-26 | 2021-03-26 | 1 | 2021-04-13 | 13 | 2021-05-03 | 14 | [15 empty] | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03
120434315 | 305 | PGE | NEM | EXPNEM | Commercial | Solar PV | 368.528 |  | 2021-01-15 |  | 2021-01-19 | 2021-01-19 | 2021-01-19 | 1 | 2021-03-12 | 38 | 2021-06-03 | 58 | [15 empty] | 2021-06-03 | 2021-06-14 | 7 | 2021-06-14 | 2021-08-09 | 39 | [12 empty] | 2021-08-12 | 2021-08-18 | 4 | [15 empty] | 2021-08-12 | 2021-08-12 | 0 | 2021-08-18 |  | 2021-08-19 | 1
120536517 | 306 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100.548 |  | 2021-02-16 |  | 2021-02-17 | 2021-02-17 | 2021-02-17 | 1 | 2021-03-08 | 14 | 2021-03-22 | 10 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-07-06 | 49 |  |  |  |  | 2021-02-16 | 2021-05-18 | 2021-05-28 | 73
120618122 | 307 | PGE | NEM | EXPNEM | Commercial | Solar PV | 36.513 |  | 2021-03-09 |  |  | 2021-03-23 | 2021-03-23 | 10 | 2021-03-23 | 10 | 2021-04-09 | 13 | [15 empty] | 2021-04-09 | 2021-06-28 | 55 | 2021-06-28 | 2021-07-19 | 14 | [12 empty] | 2021-08-10 | 2021-08-17 | 5 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-17 |  | 2021-08-18 | 1
120603169 | 308 | PGE | NEM | EXPNEM | Implementation | Solar PV | 1700 |  | 2021-03-04 | 2021-03-08 |  | 2021-03-08 | 2021-03-08 | 2 | 2021-03-24 | 14 | 2021-04-12 | 13 | 2021-05-10 | 2021-06-08 | 20 | [12 empty] | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-08-24 | 54 |  |  |  |  | 2021-04-06 | 2021-06-09 | 2021-07-09 | 66
120567198 | 309 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 216 |  | 2021-02-23 |  | 2021-02-24 | 2021-02-24 | 2021-02-24 | 1 | 2021-02-25 | 2 | 2021-03-18 | 15 | 2021-03-18 | 2021-04-29 | 30 | [12 empty] | 2021-04-29 | 2021-04-29 | 0 | 2021-04-29 | [6 empty] | 2021-02-23
120464204 | 310 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 62.5 |  | 2021-01-26 |  | 2021-02-05 | 2021-01-26 | 2021-01-26 | 0 | 2021-02-02 | 5 | 2021-03-19 | 32 | 2021-03-19 | 2021-04-16 | 20 | 2021-04-16 | 2021-06-29 | 51 | 2021-06-29 | 2021-07-19 | 13 |  |  |  | 2021-07-19 | [12 empty] | 2020-02-04 | 2021-08-18 | 2021-09-09 | 404
120587079 | 311 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 160 |  | 2021-03-01 |  |  | 2021-03-02 | 2021-03-02 | 1 | 2021-03-02 | 1 | 2021-03-19 | 13 | 2021-03-19 | 2021-05-06 | 34 | 2021-07-09 | 2021-08-05 | 19 | 2021-08-05 | [18 empty] | 2021-03-01
120555916 | 312 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 167.38 |  | 2021-02-19 |  | 2021-03-04 | 2021-02-22 | 2021-02-22 | 1 | 2021-03-09 | 12 | 2021-03-31 | 16 | 2021-03-31 | 2021-04-29 | 21 | 2021-05-05 | 2021-07-02 | 41 | 2021-07-02 |  |  |  | 2021-09-28 |  |  |  |  | 2021-09-28 | 2021-09-28 | 0 | 2021-09-28
120574886 | 313 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 828.528 |  | 2021-02-24 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 7 | 2021-03-16 | 14 | 2021-04-02 | 13 | 2021-04-02 | 2021-04-16 | 10 | [12 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16
120528364 | 314 | PGE | NEM | EXPNEM | Commercial | Solar PV | 133.2 |  | 2021-02-11 |  | 2021-02-24 | 2021-02-24 | 2021-02-24 | 8 | 2021-03-12 | 20 | 2021-03-26 | 10 | [15 empty] | 2021-03-26 | 2021-04-29 | 24 | 2021-04-29 | 2021-06-30 | 43 |  |  |  |  | 2021-02-11 | 2021-06-30 | 2021-07-12 | 104 |  |  |  |  | 2021-08-23 | 2021-09-01 | 7 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-09-01 |  | 2021-09-02 | 1
120421368 | 315 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.461 |  | 2021-01-12 |  | 2021-01-15 | 2021-01-13 | 2021-01-13 | 1 | 2021-01-19 | 4 | 2021-02-02 | 10 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02
120433880 | 316 | PGE | NEM | EXPNEM | Commercial | Solar PV | 132 |  | 2021-01-15 |  |  | 2021-01-19 | 2021-01-19 | 1 | 2021-01-19 | 1 | 2021-02-03 | 11 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-07-02 | 105 | [12 empty] | 2021-07-12 | 2021-07-20 | 6 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-20 |  | 2021-07-27 | 5
120420030 | 317 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 146.8 |  | 2021-01-11 |  | 2021-01-26 | 2021-01-20 | 2021-01-20 | 6 | 2021-01-28 | 12 | 2021-02-05 | 6 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05
120419882 | 318 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 153.25 |  | 2021-01-11 |  | 2021-02-02 | 2021-01-14 | 2021-01-14 | 3 | 2021-02-02 | 15 | 2021-02-05 | 3 | [15 empty] | 2021-02-05 | 2021-02-08 | 1 | 2021-02-08
120430865 | 320 | PGE | NEM | EXPNEM | Implementation | Solar PV | 71.771 |  | 2021-01-14 |  |  | 2021-01-29 | 2021-01-29 | 10 | 2021-01-29 | 10 | 2021-02-19 | 14 | [15 empty] | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | 2021-05-20 | 64 | [5 empty] | 2021-05-01 | 2021-05-10 | 5
120457754 | 321 | PGE | NEM | EXPNEM | Implementation | Solar PV | 30.159 |  | 2021-01-22 |  | 2021-02-19 | 2021-01-30 | 2021-01-30 | 5 | 2021-01-30 | 5 | 2021-02-19 | 13 | [15 empty] | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | 2021-08-25 | 131
120434090 | 322 | PGE | NEM | EXPNEM | Commercial | Solar PV | 125 |  | 2021-01-15 |  |  | 2021-02-01 | 2021-02-01 | 10 | 2021-02-01 | 12 | 2021-02-22 | 16 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-08-09 | 118 |  |  |  |  | 2021-01-15 | 2021-07-20 | 2021-07-29 | 135 |  |  |  |  | 2021-08-27 | 2021-09-02 | 4 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-09-02 |  | 2021-09-07 | 2
120497739 | 323 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 85.795 |  | 2021-02-03 |  | 2021-02-17 | 2021-02-17 | 2021-02-17 | 9 | 2021-02-23 | 13 | 2021-03-01 | 4 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01
120528538 | 324 | PGE | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-02-11 |  | 2021-02-17 | 2021-02-12 | 2021-02-12 | 1 | 2021-02-18 | 4 | 2021-03-02 | 8 | [15 empty] | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | 2021-08-24 | 123 |  |  |  |  | 2021-02-11 | 2021-07-15 | 2021-07-15 | 107 |  |  |  |  | 2021-09-08 | 2021-09-14 | 4 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-14 |  | 2021-09-29 | 11
120464733 | 325 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 72.381 |  | 2021-01-26 |  |  | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 0 | 2021-03-03 | 25 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-05-24 | 58 |  |  |  |  | 2021-01-26 | 2021-04-27 | 2021-05-10 | 73
120424651 | 326 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 84.718 |  | 2021-01-13 |  | 2021-02-13 | 2021-01-28 | 2021-01-28 | 10 | 2021-02-13 | 21 | 2021-03-07 | 14 | [15 empty] | 2021-03-07 | 2021-03-07 | 0 | 2021-03-07 | [6 empty] | 2021-01-13
120434647 | 327 | PGE | NEM | EXPNEM | Implementation | Solar PV | 540 |  | 2021-01-15 |  | 2021-01-24 | 2021-01-24 | 2021-01-24 | 4 | 2021-01-24 | 4 | 2021-03-08 | 29 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-04-16 | 29 |  |  |  |  | 2021-01-15 | 2021-04-15 | 2021-05-05 | 76
120565258 | 328 | PGE | NEM | EXPNEM | Commercial | Solar PV | 90.375 |  | 2021-02-22 |  | 2021-02-23 | 2021-02-23 | 2021-02-23 | 1 | 2021-02-26 | 4 | 2021-03-08 | 6 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-07-12 | 88 |  |  |  |  | 2021-02-22 | 2021-04-14 | 2021-05-07 | 54 |  |  |  |  | 2021-07-16 | 2021-07-23 | 5 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-23 |  | 2021-07-29 | 4
120565772 | 329 | PGE | NEM | EXPNEM | Commercial | Solar PV | 46.382 |  | 2021-02-22 |  | 2021-02-24 | 2021-02-24 | 2021-02-24 | 2 | 2021-02-26 | 4 | 2021-03-08 | 6 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-05-18 | 51 | [12 empty] | 2021-05-26 | 2021-06-03 | 5 | [15 empty] | 2021-05-26 | 2021-05-26 | 0 | 2021-06-03 |  | 2021-06-10 | 5
120501148 | 330 | PGE | NEM | EXPNEM | Implementation | Solar PV | 187.5 |  | 2021-02-04 |  | 2021-02-18 | 2021-02-16 | 2021-02-16 | 7 | 2021-02-16 | 7 | 2021-02-19 | 3 | [15 empty] | 2021-02-19 | 2021-03-09 | 12 | 2021-03-09 | 2021-05-07 | 43 |  |  |  |  | 2021-02-04 | 2021-08-26 | 2021-09-08 | 150
120572856 | 331 | PGE | NEM | EXPNEM | Commercial | Solar PV | 43.741 |  | 2021-02-24 |  | 2021-02-25 | 2021-02-25 | 2021-02-25 | 1 | 2021-03-01 | 3 | 2021-03-18 | 13 | [15 empty] | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18 | 2021-04-20 | 23 | [12 empty] | 2021-04-27 | 2021-05-06 | 7 | [15 empty] | 2021-04-27 | 2021-04-29 | 2 | 2021-05-06 |  | 2021-05-07 | 1
120512571 | 332 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 463.916 |  | 2021-02-09 |  | 2021-02-10 | 2021-02-10 | 2021-02-10 | 1 | 2021-03-02 | 14 | 2021-03-19 | 13 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | [6 empty] | 2021-02-09
120543065 | 333 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 32.109 |  | 2021-02-18 |  | 2021-02-19 | 2021-02-19 | 2021-02-19 | 1 | 2021-03-02 | 8 | 2021-03-19 | 13 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19
120536258 | 334 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 166.5 |  | 2021-02-16 |  |  | 2021-03-02 | 2021-03-02 | 10 | 2021-03-02 | 10 | 2021-03-19 | 13 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19
120578478 | 335 | PGE | NEM | EXPNEM | Commercial | Solar PV | 54.148 |  | 2021-02-25 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 1 | 2021-03-03 | 4 | 2021-03-22 | 13 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-04-24 | 24 |  |  |  |  | 2021-02-25 | [7 empty] | 2021-04-27 | 2021-06-03 | 26 | [15 empty] | 2021-04-27 | 2021-04-27 | 0 | 2021-06-03 |  | 2021-06-08 | 3
120592230 | 336 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 136 |  | 2021-03-02 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2 | 2021-03-04 | 2 | 2021-03-22 | 12 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-06-03 | 52
120591296 | 337 | PGE | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-02 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2 | 2021-03-10 | 6 | 2021-03-24 | 10 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-04-21 | 20 | [12 empty] | 2021-08-17 | 2021-08-24 | 5 | [15 empty] | 2021-08-17 | 2021-08-17 | 0 | 2021-08-24 |  | 2021-08-30 | 4
120582604 | 338 | PGE | NEM | EXPNEM | Commercial | Solar PV | 65.159 |  | 2021-02-26 |  | 2021-03-05 | 2021-03-02 | 2021-03-02 | 2 | 2021-03-12 | 10 | 2021-03-24 | 8 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-04-26 | 23 | [12 empty] | 2021-04-28 | 2021-05-11 | 9 | [15 empty] | 2021-04-28 | 2021-04-29 | 1 | 2021-05-11 |  | 2021-05-18 | 5
120491801 | 339 | PGE | NEM | EXPNEM | Implementation | Solar PV | 45.6 |  | 2021-02-02 |  | 2021-02-16 | 2021-02-11 | 2021-02-11 | 7 | 2021-02-11 | 7 | 2021-03-25 | 29 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-06-16 | 58 | [12 empty] | 2021-08-16 | 2021-08-27 | 9 | [15 empty] | 2021-08-16 | 2021-08-17 | 1 | 2021-08-27 | 2021-08-30 |  | 1 |  |  | 146 |  | 146
120591959 | 340 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 74.396 |  | 2021-03-02 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2 | 2021-03-08 | 4 | 2021-03-25 | 13 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-06-21 | 61
120478306 | 341 | PGE | NEM | EXPNEM | Implementation | Solar PV | 480 |  | 2021-01-29 |  |  | 2021-02-12 | 2021-02-12 | 10 | 2021-02-24 | 17 | 2021-02-26 | 2 | 2021-02-26 | 2021-03-25 | 19 | [12 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-04-15 | 15 | [15 empty] | 2021-06-08 | 2021-06-18 | 8
120591298 | 342 | PGE | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-02 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2 | 2021-03-09 | 5 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-08-19 | 102 | [12 empty] | 2021-08-21 | 2021-09-01 | 7 | [15 empty] | 2021-08-21 | 2021-08-24 | 1 | 2021-09-01 |  | 2021-09-09 | 5
120591365 | 343 | PGE | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-02 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2 | 2021-03-09 | 5 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-21 | 18 | [12 empty] | 2021-08-23 | 2021-09-01 | 7 | [15 empty] | 2021-08-23 | 2021-08-24 | 1 | 2021-09-01 |  | 2021-09-16 | 10
120591483 | 344 | PGE | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-02 |  | 2021-03-09 | 2021-03-04 | 2021-03-04 | 2 | 2021-03-09 | 5 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-21 | 18 | [12 empty] | 2021-08-23 | 2021-09-01 | 7 | [15 empty] | 2021-08-23 | 2021-08-24 | 1 | 2021-09-01 |  | 2021-09-16 | 10
120591299 | 345 | PGE | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-02 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2 | 2021-03-11 | 7 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-21 | 18 | [12 empty] | 2021-08-24 | 2021-09-01 | 6 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-09-01 |  | 2021-09-16 | 10
120617311 | 346 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 38.78 |  | 2021-03-09 |  |  | 2021-03-11 | 2021-03-11 | 2 | 2021-03-11 | 2 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-07-22 | 82 |  |  |  |  | 2021-03-09 | 2021-07-30 | 2021-08-09 | 107
120591488 | 347 | PGE | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-02 |  | 2021-03-09 | 2021-03-04 | 2021-03-04 | 2 | 2021-03-12 | 8 | 2021-03-26 | 10 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-08-19 | 102 | [12 empty] | 2021-08-24 | 2021-09-01 | 6 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-09-01 |  | 2021-09-09 | 5
120537095 | 348 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 420 |  | 2021-02-16 |  | 2021-02-17 | 2021-02-17 | 2021-02-17 | 1 | 2021-03-11 | 17 | 2021-03-27 | 11 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | 2021-04-29 | 23 | [15 empty] | 2021-07-30
120463096 | 349 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 56.965 |  | 2021-01-25 |  | 2021-01-26 | 2021-01-26 | 2021-01-26 | 1 | 2021-03-01 | 24 | 2021-03-29 | 20 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | [6 empty] | 2021-01-25
120586926 | 350 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 75.259 |  | 2021-03-01 |  | 2021-03-02 | 2021-03-02 | 2021-03-02 | 1 | 2021-03-12 | 9 | 2021-03-29 | 11 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | [6 empty] | 2021-03-01
120534361 | 351 | PGE | NEM | EXPNEM | Implementation | Solar PV | 230 |  | 2021-02-14 |  | 2021-03-01 | 2021-03-01 | 2021-03-01 | 9 | 2021-03-15 | 19 | 2021-03-29 | 10 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-06-22 | 60 | [15 empty] | 2021-07-20
120637856 | 352 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 590 |  | 2021-03-12 |  |  | 2021-03-16 | 2021-03-16 | 2 | 2021-03-16 | 2 | 2021-03-30 | 10 | 2021-06-17 | 2021-07-16 | 20 | [12 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | [6 empty] | 2021-03-12 | 2021-04-09 | 2021-04-16 | 25
120572666 | 353 | PGE | NEM | EXPNEM | Commercial | Solar PV | 61.126 |  | 2021-02-24 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 2 | 2021-03-17 | 15 | 2021-03-30 | 9 | [15 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-04-20 | 15 |  |  |  |  | 2021-03-12 | 2021-06-28 | 2021-07-01 | 78 |  |  |  |  | 2021-07-06 | 2021-07-08 | 2 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-08 |  | 2021-07-09 | 1
120538175 | 354 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 650.576 |  | 2021-02-16 |  | 2021-02-17 | 2021-02-17 | 2021-02-17 | 1 | 2021-03-16 | 20 | 2021-03-31 | 11 | [15 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | 2021-04-15 | 11 |  |  |  |  | 2021-02-16 | 2021-07-06 | 2021-07-19 | 107 |  |  |  |  | 2021-09-23 | 2021-09-29 | 4 | [15 empty] | 2021-09-23 | 2021-09-23 | 0 | 2021-09-29
120535220 | 355 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-02-15 |  | 2021-03-11 | 2021-02-16 | 2021-02-16 | 0 | 2021-03-18 | 22 | 2021-04-01 | 10 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01
120614007 | 356 | PGE | NEM | EXPNEM | Commercial | Solar PV | 30.159 |  | 2021-03-08 |  | 2021-03-23 | 2021-03-10 | 2021-03-10 | 2 | 2021-03-24 | 12 | 2021-04-01 | 6 | [15 empty] | 2021-04-01 | 2021-04-02 | 1 | 2021-04-02 | 2021-04-15 | 9 | [12 empty] | 2021-04-19 | 2021-04-27 | 6 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-27 |  | 2021-04-30 | 3
120575034 | 357 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 66.6 |  | 2021-02-24 |  | 2021-03-11 | 2021-02-26 | 2021-02-26 | 2 | 2021-03-18 | 16 | 2021-04-02 | 11 | [15 empty] | 2021-04-02 | 2021-04-02 | 0 | 2021-04-02
120567542 | 358 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 156 |  | 2021-02-23 |  |  | 2021-02-24 | 2021-02-24 | 1 | 2021-02-24 | 1 | 2021-04-05 | 28 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | [6 empty] | 2021-02-23
120612829 | 359 | PGE | NEM | EXPNEM | Commercial | Solar PV | 32.907 |  | 2021-03-08 |  | 2021-03-10 | 2021-03-10 | 2021-03-10 | 2 | 2021-03-17 | 7 | 2021-04-05 | 13 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-05-14 | 29 | [12 empty] | 2021-06-07 | 2021-06-16 | 7 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-16 |  | 2021-06-23 | 5
120630314 | 360 | PGE | NEM | EXPNEM | Commercial | Solar PV | 86.4 |  | 2021-03-10 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 2 | 2021-03-17 | 5 | 2021-04-05 | 13 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-07-15 | 71 |  |  |  |  | 2021-03-10 | 2021-05-25 | 2021-06-07 | 62 |  |  |  |  | 2021-07-20 | 2021-07-28 | 6 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-28 |  | 2021-08-11 | 10
120677938 | 361 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-03-23 |  |  | 2021-03-25 | 2021-03-25 | 2 | 2021-03-25 | 2 | 2021-04-05 | 7 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05
120658640 | 362 | PGE | NEM | EXPNEM | Commercial | Solar PV | 48.857 |  | 2021-03-18 |  | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2 | 2021-03-26 | 6 | 2021-04-05 | 6 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-07-22 | 76 | [12 empty] | 2021-08-17 | 2021-08-19 | 2 | [15 empty] | 2021-08-17 | 2021-08-17 | 0 | 2021-08-19 |  | 2021-08-23 | 2
120692850 | 363 | PGE | NEM | EXPNEM | Commercial | Solar PV | 466.6 |  | 2021-03-25 |  | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2 | 2021-03-31 | 4 | 2021-04-05 | 3 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-05-19 | 32 | [12 empty] | 2021-05-21 | 2021-05-26 | 3 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-26 |  | 2021-06-02 | 4
120602101 | 364 | PGE | NEM | EXPNEM | Commercial | Solar PV | 75.885 |  | 2021-03-04 |  | 2021-03-16 | 2021-03-05 | 2021-03-05 | 1 | 2021-03-19 | 11 | 2021-04-06 | 12 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-04-29 | 17 | [12 empty] | 2021-05-04 | 2021-05-13 | 7 | [15 empty] | 2021-05-04 | 2021-05-05 | 1 | 2021-05-13 |  | 2021-05-19 | 4
120651491 | 365 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.5 |  | 2021-03-17 |  | 2021-03-19 | 2021-03-19 | 2021-03-19 | 2 | 2021-03-23 | 4 | 2021-04-06 | 10 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06
120696257 | 366 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 35.852 |  | 2021-03-26 |  |  | 2021-03-29 | 2021-03-29 | 1 | 2021-03-29 | 1 | 2021-04-06 | 6 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-05-07 | 23
120639801 | 367 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-03-12 |  | 2021-03-17 | 2021-03-17 | 2021-03-17 | 3 | 2021-03-19 | 5 | 2021-04-07 | 13 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-21 | 10
120644805 | 368 | PGE | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-03-15 |  | 2021-03-18 | 2021-03-18 | 2021-03-18 | 3 | 2021-03-23 | 6 | 2021-04-07 | 11 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-16 | 7 |  |  |  |  | 2021-03-15 | [7 empty] | 2021-06-18 | 2021-06-30 | 8 | [15 empty] | 2021-06-18 | 2021-06-21 | 1 | 2021-06-30 |  | 2021-07-16 | 11
120633666 | 369 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 765.9 |  | 2021-03-11 |  | 2021-03-15 | 2021-03-15 | 2021-03-15 | 2 | 2021-03-24 | 9 | 2021-04-08 | 11 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | [6 empty] | 2021-03-11
120657788 | 370 | PGE | NEM | EXPNEM | Commercial | Solar PV | 55.067 |  | 2021-03-18 |  | 2021-04-02 | 2021-03-22 | 2021-03-22 | 2 | 2021-04-02 | 11 | 2021-04-08 | 4 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | 2021-04-13 | 3 | [12 empty] | 2021-04-15 | 2021-04-22 | 5 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-22 |  | 2021-04-29 | 5
120494223 | 371 | PGE | NEM | EXPNEM | Implementation | Solar PV | 969.737 |  | 2021-02-02 |  | 2021-03-10 | 2021-02-17 | 2021-02-17 | 10 | 2021-03-09 | 24 | 2021-03-23 | 10 | 2021-03-23 | 2021-04-09 | 13 | [12 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | 2021-04-28 | 13 | [8 empty] | 2021-05-25 | [6 empty] | 2021-06-22
120592266 | 372 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 89.259 |  | 2021-03-02 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2 | 2021-03-08 | 4 | 2021-04-12 | 25 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12
120647081 | 373 | PGE | NEM | EXPNEM | Implementation | Solar PV | 43.2 |  | 2021-03-16 |  |  | 2021-03-30 | 2021-03-30 | 10 | 2021-03-30 | 10 | 2021-04-12 | 9 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-09-16 | 110 | [12 empty] | 2021-09-17 | [17 empty] | 2021-09-17 | 2021-09-17 | 0
120611784 | 374 | PGE | NEM | EXPNEM | Commercial | Solar PV | 89.207 |  | 2021-03-08 |  | 2021-03-23 | 2021-03-10 | 2021-03-10 | 2 | 2021-03-26 | 14 | 2021-04-13 | 12 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-07-19 | 67 | [12 empty] | 2021-08-27 | 2021-09-02 | 4 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-09-02 |  | 2021-09-13 | 6
120466057 | 375 | PGE | NEM | EXPNEM | Implementation | Solar PV | 648.528 |  | 2021-01-26 |  | 2021-02-12 | 2021-02-09 | 2021-02-09 | 10 | 2021-03-01 | 23 | 2021-03-11 | 8 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | 2021-04-01 | 15 | [8 empty] | 2021-05-25 | [6 empty] | 2021-06-17 | 2021-08-11 | 38 |  |  |  | 2021-08-13 |  |  | 2021-08-13
120456663 | 376 | PGE | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-01-22 |  | 2021-03-15 | 2021-02-26 | 2021-02-26 | 24 | 2021-03-15 | 35 | 2021-04-01 | 13 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | 2021-04-02 | 1 | [12 empty] | 2021-05-20 | 2021-05-27 | 5 | [15 empty] | 2021-05-20 | 2021-05-21 | 1 | 2021-05-27 |  | 2021-05-27 | 0
120442992 | 377 | PGE | NEM | EXPNEM | Commercial | Solar PV | 95.8 |  | 2021-01-18 |  | 2021-03-16 | 2021-01-25 | 2021-01-25 | 4 | 2021-01-25 | 4 | 2021-02-11 | 13 | [15 empty] | 2021-02-19 | 2021-03-19 | 20 | 2021-03-19 | 2021-04-13 | 17 |  |  |  |  | 2021-01-18 | 2021-07-14 | 2021-07-27 | 132 |  |  |  |  | 2021-09-07 | 2021-09-15 | 6 | [15 empty] | 2021-09-07 | 2021-09-08 | 1 | 2021-09-15 |  | 2021-09-15 | 0
120431263 | 378 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 85.387 |  | 2021-01-14 |  | 2021-05-11 | 2021-01-15 | 2021-01-15 | 1 | 2021-01-19 | 4 | 2021-02-01 | 10 | [15 empty] | 2021-02-01 | 2021-02-01 | 0 | 2021-02-01 | 2021-05-11 | 70 |  |  |  |  | 2021-01-14 | 2021-05-11 | 2021-05-26 | 92
120427579 | 379 | PGE | NEM | EXPNEM | Implementation | Solar PV | 490 |  | 2021-01-13 |  |  | 2021-01-20 | 2021-01-20 | 4 | 2021-01-20 | 4 | 2021-02-03 | 10 | 2021-02-03 | 2021-03-17 | 29 | 2021-03-17 | 2021-03-23 | 4 | 2021-03-23 | [8 empty] | 2021-08-16 | 2021-08-18 | 2 | 2021-08-18 | 2021-08-19 | 1 |  |  |  |  | 2021-01-13 | 2021-01-20 | 2021-02-01 | 12 | [7 empty] | 2021-09-20
120433871 | 380 | PGE | NEM | EXPNEM | Implementation | Solar PV | 720 |  | 2021-01-15 |  |  | 2021-01-21 | 2021-01-21 | 3 | 2021-01-21 | 3 | [5 empty] | 2021-01-21 | 2021-02-25 | 24 | 2021-02-25 | [8 empty] | 2021-08-16 | 2021-08-18 | 2 | 2021-08-18 | 2021-08-19 | 1 |  |  |  |  | 2021-01-15 | 2021-01-21 | 2021-02-02 | 11
120446345 | 381 | PGE | NEM | EXPNEM | Commercial | Solar PV | 44.337 |  | 2021-01-19 |  | 2021-01-28 | 2021-01-28 | 2021-01-28 | 7 | 2021-01-28 | 7 | 2021-03-22 | 36 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-05-19 | 42 |  |  |  |  | 2021-01-19 | 2021-01-28 | 2021-02-05 | 13 |  |  |  |  | 2021-09-07 | 2021-09-16 | 7 | [15 empty] | 2021-09-07 | 2021-09-08 | 1 | 2021-09-16 |  | 2021-09-16 | 0
120487150 | 382 | PGE | NEM | EXPNEM | Commercial | Solar PV | 41.968 |  | 2021-02-01 |  | 2021-07-29 | 2021-02-02 | 2021-02-02 | 1 | 2021-02-10 | 7 | 2021-03-22 | 27 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-04-19 | 20 |  |  |  |  | 2021-02-01 | 2021-02-02 | 2021-02-08 | 5 |  |  |  |  | 2021-08-03 | 2021-08-27 | 18 | [15 empty] | 2021-08-03 | 2021-08-03 | 0 | 2021-08-27 |  | 2021-09-09 | 8
120452601 | 383 | PGE | NEM | EXPNEM | Withdrawn | Solar PV, Storage | 33.54 |  | 2021-01-21 |  | 2021-02-08 | 2021-02-04 | 2021-02-04 | 10 | [29 empty] | 2021-01-21 | 2021-02-04 | 2021-02-09 | 13
120495661 | 384 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 400 |  | 2021-02-03 |  | 2021-02-11 | 2021-02-03 | 2021-02-03 | 0 | 2021-02-22 | 12 | 2021-03-03 | 7 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | [6 empty] | 2021-02-03 | 2021-02-03 | 2021-02-09 | 4 | [7 empty] | 2021-06-16
120423690 | 385 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 41.219 |  | 2021-01-12 |  | 2021-01-13 | 2021-01-13 | 2021-01-13 | 1 | 2021-02-04 | 16 | 2021-03-24 | 33 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | [6 empty] | 2021-01-12 | 2021-02-05 | 2021-02-09 | 19
120473793 | 386 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-01-28 |  |  | 2021-01-29 | 2021-01-29 | 1 | 2021-01-29 | 1 | 2021-02-11 | 9 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-05-12 | 63 |  |  |  |  | 2021-01-28 | 2021-02-11 | 2021-02-11 | 10 |  |  |  |  | 2021-06-19 | 2021-07-14 | 16 | 2021-10-05 | 2021-10-05 | 0 | [12 empty] | 2021-06-19 | 2021-07-09 | 13 | 2021-07-14 | 2021-07-21 |  | 5 |  |  | 121 |  | 121
120453709 | 387 | PGE | NEM | EXPNEM | Implementation | Solar PV | 38.78 |  | 2021-01-21 |  | 2021-03-15 | 2021-01-29 | 2021-01-29 | 6 | 2021-02-12 | 16 | 2021-02-26 | 9 | [15 empty] | 2021-02-26 | 2021-03-16 | 12 | 2021-03-16 | 2021-04-09 | 18 |  |  |  |  | 2021-01-21 | 2021-02-10 | 2021-02-11 | 15 |  |  |  |  | 2021-05-17 | 2021-05-24 | 5 | 2021-05-18 | 2021-08-19 | 65 | [12 empty] | 2021-05-17 | 2021-05-17 | 0 | 2021-05-24 | 2021-06-17 |  | 17 |  |  | 103 |  | 103
120500120 | 388 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 200 |  | 2021-02-04 |  | 2021-02-11 | 2021-02-05 | 2021-02-05 | 1 | 2021-02-12 | 6 | 2021-02-22 | 5 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-05-05 | 52 |  |  |  |  | 2021-02-04 | 2021-02-12 | 2021-02-16 | 7
120493163 | 389 | PGE | NEM | EXPNEM | Commercial | Solar PV | 49.794 |  | 2021-02-02 |  | 2021-02-16 | 2021-02-11 | 2021-02-11 | 7 | 2021-02-11 | 7 | 2021-02-26 | 10 | [15 empty] | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-05-18 | 57 |  |  |  |  | 2021-02-02 | 2021-02-11 | 2021-02-16 | 9 |  |  |  |  | 2021-06-15 | 2021-06-24 | 7 | [15 empty] | 2021-06-15 | 2021-06-16 | 1 | 2021-06-24 |  | 2021-06-24 | 0
120524106 | 390 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 94.844 |  | 2021-02-10 |  |  | 2021-02-23 | 2021-02-23 | 8 | 2021-02-23 | 8 | 2021-03-11 | 12 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | [6 empty] | 2021-02-10 | 2021-02-23 | 2021-02-23 | 8
120553203 | 391 | PGE | NEM | EXPNEM | Commercial | Solar PV | 172.8 |  | 2021-02-18 |  | 2021-02-19 | 2021-02-19 | 2021-02-19 | 1 | 2021-02-25 | 5 | 2021-04-15 | 35 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-26 | 7 |  |  |  |  | 2021-02-18 | 2021-02-25 | 2021-02-25 | 5 |  |  |  |  | 2021-06-22 | 2021-06-29 | 5 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-29 |  | 2021-06-30 | 1
120511284 | 392 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 46.625 |  | 2021-02-09 |  | 2021-02-19 | 2021-02-10 | 2021-02-10 | 1 | 2021-02-25 | 11 | 2021-03-11 | 10 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | [6 empty] | 2021-02-09 | 2021-02-25 | 2021-02-25 | 11
120566926 | 393 | PGE | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-02-23 |  | 2021-02-24 | 2021-02-24 | 2021-02-24 | 1 | 2021-02-26 | 3 | 2021-03-26 | 20 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-08-13 | 98 |  |  |  |  | 2021-02-23 | 2021-02-26 | 2021-03-01 | 4 |  |  |  |  | 2021-08-13 | 2021-08-25 | 8 | [15 empty] | 2021-08-13 | 2021-08-16 | 1 | 2021-08-25 |  | 2021-09-07 | 8
120493168 | 394 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 104.7 |  | 2021-02-02 |  | 2021-02-24 | 2021-02-03 | 2021-02-03 | 1 | 2021-03-01 | 18 | 2021-03-17 | 12 | 2021-03-17 | 2021-04-14 | 20 | 2021-05-06 | 2021-06-10 | 24 | 2021-06-10 | 2021-06-25 | 11 |  |  |  | 2021-06-25 | [12 empty] | 2021-02-02 | 2021-06-11 | 2021-07-09 | 110
120424390 | 395 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 625 |  | 2021-01-13 |  | 2021-01-14 | 2021-01-14 | 2021-01-14 | 1 | 2021-01-20 | 4 | 2021-02-02 | 9 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | [6 empty] | 2021-01-13 | 2021-03-01 | 2021-03-02 | 32
120424357 | 396 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 183.3 |  | 2021-01-13 |  | 2021-01-14 | 2021-01-14 | 2021-01-14 | 1 | 2021-01-20 | 4 | 2021-02-02 | 9 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | [6 empty] | 2021-01-13 | 2021-03-01 | 2021-03-02 | 32
120425293 | 397 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 125 |  | 2021-01-13 |  | 2021-01-21 | 2021-01-21 | 2021-01-21 | 5 | 2021-02-25 | 29 | 2021-04-28 | 44 | 2021-04-28 | 2021-05-26 | 20 | 2021-06-28 | 2021-07-23 | 18 | 2021-07-23 | 2021-08-06 | 10 |  |  |  | 2021-08-06 | [13 empty] | 2021-02-25 | 2021-03-04 | 5
120506502 | 398 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 154.954 |  | 2021-02-08 |  | 2021-02-16 | 2021-02-08 | 2021-02-08 | 0 | 2021-03-08 | 19 | 2021-05-10 | 45 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2021-05-11 | 1 |  |  |  |  | 2021-02-08 | 2021-03-04 | 2021-03-04 | 17
120552377 | 399 | PGE | NEM | EXPNEM | Commercial | Solar PV | 125 |  | 2021-02-18 |  | 2021-03-04 | 2021-03-04 | 2021-03-04 | 10 | 2021-03-23 | 23 | 2021-03-30 | 5 | [15 empty] | 2021-05-14 | 2021-05-14 | 0 | 2021-05-14 | 2021-06-01 | 11 |  |  |  |  | 2021-02-18 | 2021-03-04 | 2021-03-05 | 11 |  |  |  |  | 2021-06-22 | 2021-06-29 | 5 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-29 |  | 2021-06-30 | 1
120556358 | 400 | PGE | NEM | EXPNEM | Commercial | Solar PV | 247.461 |  | 2021-02-19 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 10 | 2021-03-23 | 22 | 2021-03-30 | 5 | [15 empty] | 2021-03-30 | 2021-05-03 | 24 | 2021-05-03 | 2021-05-27 | 18 |  |  |  |  | 2021-02-19 | 2021-03-05 | 2021-03-05 | 10 |  |  |  |  | 2021-06-22 | 2021-06-29 | 5 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-29 |  | 2021-06-30 | 1
120552451 | 401 | PGE | NEM | EXPNEM | Implementation | Solar PV | 53.611 |  | 2021-02-18 |  | 2021-03-23 | 2021-03-04 | 2021-03-04 | 10 | 2021-03-04 | 10 | 2021-03-23 | 13 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | 2021-04-05 | 9 |  |  |  |  | 2021-02-18 | 2021-03-04 | 2021-03-05 | 11 | [7 empty] | 2021-07-02
120453909 | 402 | PGE | NEM | EXPNEM | Commercial | Solar PV | 45.572 |  | 2021-01-21 |  | 2021-02-22 | 2021-01-22 | 2021-01-22 | 1 | 2021-03-01 | 26 | 2021-03-08 | 5 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-08-25 | 120 |  |  |  |  | 2021-01-21 | 2021-03-05 | 2021-03-08 | 31 |  |  |  |  | 2021-08-28 | 2021-09-07 | 5 | [15 empty] | 2021-08-28 | 2021-08-30 | 0 | 2021-09-07 |  | 2021-09-15 | 6
120564923 | 403 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 146.495 |  | 2021-02-22 |  | 2021-02-23 | 2021-02-23 | 2021-02-23 | 1 | 2021-03-03 | 7 | 2021-06-12 | 71 | [15 empty] | 2021-06-12 | 2021-06-12 | 0 | 2021-06-12 | 2021-06-18 | 4 |  |  |  |  | 2021-02-22 | 2021-04-12 | 2021-04-29 | 48 |  |  |  |  | 2021-06-11 | [17 empty] | 2021-06-11 | 2021-06-11 | 0
120568698 | 404 | PGE | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-02-23 |  | 2021-03-24 | 2021-03-09 | 2021-03-09 | 10 | 2021-03-09 | 10 | 2021-03-29 | 14 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-06-03 | 20 |  |  |  |  | 2021-02-23 | 2021-03-09 | 2021-03-12 | 13
120479413 | 405 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 666.6 |  | 2021-01-29 |  | 2021-02-01 | 2021-02-01 | 2021-02-01 | 1 | 2021-03-10 | 27 | 2021-04-13 | 24 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | [6 empty] | 2021-01-29 | 2021-04-13 | 2021-05-07 | 69
120474874 | 406 | PGE | NEM | EXPNEM | Implementation | Solar PV | 437.5 |  | 2021-01-28 |  | 2021-02-10 | 2021-02-10 | 2021-02-10 | 9 | 2021-02-22 | 16 | 2021-03-05 | 9 | [15 empty] | 2021-03-05 | 2021-03-05 | 0 | 2021-03-05 | 2021-04-05 | 21 |  |  |  |  | 2021-01-28 | 2021-04-13 | 2021-05-07 | 70
120540245 | 407 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 36 |  | 2021-02-17 |  | 2021-02-25 | 2021-02-18 | 2021-02-18 | 1 | 2021-03-01 | 8 | 2021-03-19 | 14 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-04-09 | 15 |  |  |  |  | 2021-02-17 | 2021-03-10 | 2021-03-12 | 17
120527051 | 408 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 125 |  | 2021-02-11 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 20 | 2021-03-26 | 30 | 2021-04-16 | 15 | 2021-04-16 | 2021-06-25 | 49 | 2021-07-02 | 2021-07-22 | 13 | 2021-07-22 | [18 empty] | 2021-02-11 | 2021-03-12 | 2021-03-15 | 21
120479428 | 409 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-01-29 |  | 2021-02-01 | 2021-02-01 | 2021-02-01 | 1 | 2021-03-09 | 26 | 2021-03-27 | 13 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | [6 empty] | 2021-01-29 | 2021-03-11 | 2021-03-15 | 30
120479518 | 410 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 633.3 |  | 2021-01-29 |  | 2021-03-09 | 2021-02-01 | 2021-02-01 | 1 | 2021-03-09 | 26 | 2021-04-13 | 25 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | [6 empty] | 2021-01-29 | 2021-03-11 | 2021-03-15 | 30
120479524 | 412 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 766.6 |  | 2021-01-29 |  | 2021-03-10 | 2021-02-01 | 2021-02-01 | 1 | 2021-03-16 | 31 | 2021-07-08 | 80 | [15 empty] | 2021-07-08 | 2021-07-09 | 1 | 2021-07-09 | [6 empty] | 2021-01-29 | 2021-03-16 | 2021-03-18 | 33
120597727 | 413 | PGE | NEM | EXPNEM | Implementation | Solar PV | 34.8 |  | 2021-03-03 |  | 2021-03-18 | 2021-03-17 | 2021-03-17 | 10 | 2021-05-26 | 60 | 2021-06-10 | 10 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-08-02 | 36 |  |  |  |  | 2021-03-03 | 2021-03-18 | 2021-03-24 | 15
120598627 | 414 | PGE | NEM | EXPNEM | Implementation | Solar PV | 43.421 |  | 2021-03-03 |  | 2021-03-18 | 2021-03-17 | 2021-03-17 | 10 | 2021-05-10 | 48 | 2021-08-16 | 68 | [15 empty] | 2021-08-16 | 2021-08-25 | 7 | 2021-08-25 | 2021-09-01 | 5 |  |  |  |  | 2021-03-03 | 2021-03-18 | 2021-03-25 | 16 |  |  |  |  | 2021-09-09 | [17 empty] | 2021-09-09 | 2021-09-09 | 0
120603535 | 415 | PGE | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-03-04 |  | 2021-03-18 | 2021-03-18 | 2021-03-18 | 10 | 2021-04-24 | 36 | 2021-05-10 | 10 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2021-05-10 | 0 |  |  |  |  | 2021-03-04 | 2021-03-18 | 2021-03-25 | 15 |  |  |  |  | 2021-06-23 | 2021-06-28 | 3 | [15 empty] | 2021-06-23 | 2021-06-24 | 1 | 2021-06-28 |  | 2021-06-29 | 1
120604327 | 416 | PGE | NEM | EXPNEM | Commercial | Solar PV | 31.024 |  | 2021-03-04 |  | 2021-03-18 | 2021-03-18 | 2021-03-18 | 10 | 2021-05-03 | 42 | 2021-06-03 | 22 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-23 | 14 |  |  |  |  | 2021-03-04 | 2021-04-19 | 2021-05-07 | 46 |  |  |  |  | 2021-06-30 | 2021-07-12 | 7 | [15 empty] | 2021-06-30 | 2021-07-01 | 1 | 2021-07-12 |  | 2021-07-13 | 1
120608031 | 417 | PGE | NEM | EXPNEM | Commercial | Solar PV | 120 |  | 2021-03-05 |  | 2021-03-19 | 2021-03-19 | 2021-03-19 | 10 | 2021-05-24 | 56 | 2021-06-29 | 25 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | 2021-08-04 | 25 |  |  |  |  | 2021-03-05 | 2021-03-19 | 2021-03-25 | 14 |  |  |  |  | 2021-09-13 | 2021-09-20 | 5 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-20 |  | 2021-09-21 | 1
120633938 | 418 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 375 |  | 2021-03-11 |  | 2021-03-15 | 2021-03-15 | 2021-03-15 | 2 | 2021-03-18 | 5 | 2021-05-20 | 45 | [15 empty] | 2021-05-20 | 2021-06-08 | 12 | 2021-06-08 | [6 empty] | 2021-03-11 | 2021-03-18 | 2021-03-25 | 10
120479525 | 419 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 800 |  | 2021-01-29 |  | 2021-03-22 | 2021-02-01 | 2021-02-01 | 1 | 2021-03-25 | 38 | 2021-06-07 | 51 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [6 empty] | 2021-01-29 | 2021-03-22 | 2021-03-25 | 38
120606029 | 420 | PGE | NEM | EXPNEM | Commercial | Solar PV | 78.716 |  | 2021-03-05 |  |  | 2021-03-19 | 2021-03-19 | 10 | 2021-03-19 | 10 | 2021-04-05 | 11 | [15 empty] | 2021-06-25 | 2021-06-25 | 0 | 2021-06-25 | 2021-06-29 | 2 |  |  |  |  | 2021-03-05 | 2021-03-19 | 2021-03-25 | 14 |  |  |  |  | 2021-06-30 | 2021-07-12 | 7 | [15 empty] | 2021-06-30 | 2021-07-01 | 1 | 2021-07-12 |  | 2021-07-13 | 1
120472149 | 421 | PGE | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-01-27 |  | 2021-01-28 | 2021-01-28 | 2021-01-28 | 1 | 2021-02-03 | 5 | 2021-02-20 | 11 | [15 empty] | 2021-02-20 | 2021-02-20 | 0 | 2021-02-20 | 2021-08-24 | 129 |  |  |  |  | 2021-01-27 | 2021-06-02 | 2021-06-15 | 97 |  |  |  |  | 2021-08-27 | 2021-09-07 | 6 | [15 empty] | 2021-08-27 | 2021-08-30 | 1 | 2021-09-07 |  | 2021-09-14 | 5
120637799 | 422 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 78.723 |  | 2021-03-12 |  | 2021-03-16 | 2021-03-16 | 2021-03-16 | 2 | 2021-03-23 | 7 | 2021-04-07 | 11 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-08-10 | 87 |  |  |  |  | 2021-03-12 | 2021-03-23 | 2021-03-25 | 9
120559227 | 423 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-02-22 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 4 | 2021-03-11 | 13 | 2021-03-27 | 11 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | 2021-04-20 | 16 |  |  |  |  | 2021-02-22 | 2021-03-27 | 2021-03-29 | 25
120627586 | 424 | PGE | NEM | EXPNEM | Commercial | Solar PV | 250 |  | 2021-03-10 |  |  | 2021-03-24 | 2021-03-24 | 10 | 2021-03-24 | 10 | 2021-04-13 | 14 | [15 empty] | 2021-04-13 | 2021-05-18 | 25 | 2021-05-18 | 2021-06-08 | 14 |  |  |  |  | 2021-03-10 | 2021-03-24 | 2021-03-31 | 15 |  |  |  |  | 2021-07-30 | 2021-08-10 | 7 | [15 empty] | 2021-07-30 | 2021-08-02 | 1 | 2021-08-10 |  | 2021-08-11 | 1
120617304 | 425 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-03-09 |  | 2021-03-10 | 2021-03-10 | 2021-03-10 | 1 | 2021-03-16 | 5 | 2021-04-02 | 13 | [15 empty] | 2021-04-02 | 2021-04-02 | 0 | 2021-04-02 | 2021-04-05 | 1 |  |  |  |  | 2021-03-09 | 2021-04-12 | 2021-04-29 | 37
120617176 | 426 | PGE | NEM | EXPNEM | Implementation | Solar PV | 420 |  | 2021-03-09 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 10 | 2021-07-02 | 82 | 2021-07-20 | 11 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-07-23 | 3 |  |  |  |  | 2021-03-09 | 2021-06-14 | 2021-06-18 | 72
120511265 | 427 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 96 |  | 2021-02-09 |  | 2021-02-10 | 2021-02-10 | 2021-02-10 | 1 | 2021-03-24 | 30 | 2021-04-06 | 9 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | [6 empty] | 2021-02-09 | 2021-03-24 | 2021-04-02 | 37
120664033 | 428 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-03-19 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 2 | 2021-03-29 | 6 | 2021-04-06 | 6 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | [6 empty] | 2021-03-19 | 2021-04-29 | 2021-05-10 | 36
120664104 | 429 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 400 |  | 2021-03-19 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 2 | 2021-03-30 | 7 | 2021-04-06 | 5 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | [6 empty] | 2021-03-19 | 2021-04-23 | 2021-05-07 | 35
120635852 | 430 | PGE | NEM | EXPNEM | Commercial | Solar PV | 237.128 |  | 2021-03-11 |  | 2021-03-25 | 2021-03-25 | 2021-03-25 | 10 | 2021-05-24 | 52 | 2021-06-28 | 24 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-07-09 | 8 |  |  |  |  | 2021-03-11 | 2021-03-25 | 2021-04-05 | 17 |  |  |  |  | 2021-08-18 | 2021-08-25 | 5 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-25 |  | 2021-08-26 | 1
120637807 | 431 | PGE | NEM | EXPNEM | Commercial | Solar PV | 37.529 |  | 2021-03-12 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 10 | 2021-05-25 | 52 | 2021-06-08 | 9 | [15 empty] | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-06-14 | 4 |  |  |  |  | 2021-03-12 | 2021-03-26 | 2021-04-05 | 16 |  |  |  |  | 2021-08-05 | 2021-08-12 | 5 | [15 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-12 |  | 2021-08-13 | 1
120680002 | 432 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 97.072 |  | 2021-03-23 |  | 2021-03-25 | 2021-03-25 | 2021-03-25 | 2 | 2021-04-14 | 16 | 2021-05-04 | 14 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | [6 empty] | 2021-03-23 | 2021-03-25 | 2021-04-05 | 9
120565427 | 433 | PGE | NEM | EXPNEM | Commercial | Solar PV | 38.528 |  | 2021-02-22 |  | 2021-02-23 | 2021-02-23 | 2021-02-23 | 1 | 2021-03-25 | 23 | 2021-04-05 | 7 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-05-10 | 25 |  |  |  |  | 2021-02-22 | 2021-06-08 | 2021-06-17 | 82 |  |  |  |  | 2021-07-02 | 2021-07-23 | 14 | [15 empty] | 2021-07-02 | 2021-07-15 | 8 | 2021-07-23 |  | 2021-08-04 | 8
120680695 | 434 | PGE | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-03-23 |  |  | 2021-03-25 | 2021-03-25 | 2 | 2021-03-25 | 2 | 2021-04-06 | 8 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-05-19 | 31 |  |  |  |  | 2021-03-23 | 2021-03-25 | 2021-04-05 | 9 |  |  |  |  | 2021-08-03 | 2021-08-10 | 5 | [15 empty] | 2021-08-03 | 2021-08-03 | 0 | 2021-08-10 |  | 2021-08-13 | 3
120680223 | 435 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 142.054 |  | 2021-03-23 |  |  | 2021-03-25 | 2021-03-25 | 2 | 2021-03-25 | 2 | 2021-04-06 | 8 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-05-19 | 31 |  |  |  |  | 2021-03-23 | 2021-03-25 | 2021-04-05 | 9
120637819 | 436 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 52.163 |  | 2021-03-12 |  | 2021-03-24 | 2021-03-16 | 2021-03-16 | 2 | 2021-03-25 | 9 | 2021-04-12 | 12 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-08-10 | 84 |  |  |  |  | 2021-03-12 | 2021-03-25 | 2021-04-05 | 16
120536909 | 437 | PGE | NEM | EXPNEM | Implementation | Solar PV | 720 |  | 2021-02-16 |  | 2021-03-02 | 2021-03-02 | 2021-03-02 | 10 | 2021-05-10 | 59 | 2021-06-01 | 15 | 2021-06-01 | 2021-06-21 | 14 | [12 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-07-20 | 20 |  |  |  |  | 2021-02-16 | 2021-03-26 | 2021-04-12 | 39
120572565 | 439 | PGE | NEM | EXPNEM | Implementation | Solar PV | 85.259 |  | 2021-02-24 |  | 2021-03-10 | 2021-03-10 | 2021-03-10 | 10 | 2021-03-27 | 22 | 2021-04-16 | 14 | [15 empty] | 2021-04-16 | 2021-06-02 | 32 | 2021-06-02 | 2021-06-07 | 3 |  |  |  |  | 2021-02-24 | 2021-03-27 | 2021-04-12 | 33
120672611 | 440 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 40.153 |  | 2021-03-22 |  | 2021-03-24 | 2021-03-24 | 2021-03-24 | 2 | 2021-03-30 | 6 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-08-19 | 88 |  |  |  |  | 2021-03-22 | 2021-03-30 | 2021-04-12 | 15
120704078 | 441 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 220 |  | 2021-03-28 |  | 2021-03-29 | 2021-03-29 | 2021-03-29 | 0 | 2021-03-30 | 1 | 2021-04-16 | 13 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | [6 empty] | 2021-03-28 | 2021-03-29 | 2021-04-12 | 10
120704108 | 442 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-03-28 |  |  | 2021-03-30 | 2021-03-30 | 1 | 2021-03-30 | 1 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | [6 empty] | 2021-03-28 | 2021-03-30 | 2021-04-12 | 10
120535166 | 443 | PGE | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-02-15 |  |  | 2021-02-26 | 2021-02-26 | 8 | 2021-02-26 | 8 | 2021-03-15 | 11 | [15 empty] | 2021-03-15 | 2021-06-01 | 55 | 2021-06-01 | 2021-07-07 | 25 |  |  |  |  | 2021-02-15 | 2021-05-04 | 2021-05-18 | 65 |  |  |  |  | 2021-08-12 | 2021-08-19 | 5 | [15 empty] | 2021-08-12 | 2021-08-12 | 0 | 2021-08-19 |  | 2021-08-20 | 1
120658751 | 444 | PGE | NEM | EXPNEM | Implementation | Solar PV | 46.625 |  | 2021-03-18 |  | 2021-04-01 | 2021-04-01 | 2021-04-01 | 10 | 2021-06-30 | 73 | 2021-07-16 | 11 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-16 | 2021-07-20 | 2 |  |  |  |  | 2021-03-18 | 2021-04-01 | 2021-04-13 | 18
120654669 | 445 | PGE | NEM | EXPNEM | Implementation | Solar PV | 120 |  | 2021-03-17 |  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 10 | 2021-05-03 | 33 | [5 empty] | 2021-05-03 | 2021-05-25 | 16 | 2021-05-25 |  |  |  | 2021-08-19 |  |  |  |  | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-09-03 | 11 |  |  |  |  | 2021-03-17 | 2021-03-31 | 2021-04-13 | 19
120686513 | 446 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.536 |  | 2021-03-24 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2 | 2021-03-30 | 4 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-29 | 10 |  |  |  |  | 2021-03-24 | 2021-03-30 | 2021-04-13 | 14
120686439 | 447 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 59.764 |  | 2021-03-24 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2 | 2021-03-30 | 4 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | [6 empty] | 2021-03-24 | 2021-04-21 | 2021-05-07 | 32
120686397 | 448 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-03-24 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2 | 2021-03-30 | 4 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-29 | 10 |  |  |  |  | 2021-03-24 | 2021-04-21 | 2021-05-07 | 32
120654840 | 449 | PGE | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2021-03-17 |  |  | 2021-03-30 | 2021-03-30 | 9 | 2021-03-30 | 9 | 2021-04-19 | 14 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-04-28 | 7 |  |  |  |  | 2021-03-17 | 2021-03-30 | 2021-04-13 | 19 | [7 empty] | 2021-06-01
120690266 | 450 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-03-25 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 1 | 2021-03-31 | 4 | 2021-05-21 | 37 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-07-14 | 36 |  |  |  |  | 2021-03-25 | 2021-04-21 | 2021-05-07 | 31
120714464 | 451 | PGE | NEM | EXPNEM | Commercial | Solar PV | 76.296 |  | 2021-03-30 |  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 1 | 2021-04-01 | 2 | 2021-06-02 | 43 | [15 empty] | 2021-06-02 | 2021-06-03 | 1 | 2021-06-03 | 2021-06-09 | 4 |  |  |  |  | 2021-03-30 | 2021-04-21 | 2021-05-07 | 28 |  |  |  |  | 2021-08-19 | 2021-08-26 | 5 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-26 |  | 2021-08-30 | 2
120689917 | 452 | PGE | NEM | EXPNEM | Implementation | Solar PV | 93.552 |  | 2021-03-25 |  | 2021-04-01 | 2021-04-01 | 2021-04-01 | 5 | 2021-04-05 | 7 | 2021-06-21 | 54 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-07-07 | 11 |  |  |  |  | 2021-03-25 | 2021-04-01 | 2021-04-13 | 13
120242513 | 453 | PGE | NEM | EXPNEM | Commercial | Solar PV | 48.72 |  | 2020-12-30 |  | 2021-02-09 | 2021-01-06 | 2021-01-06 | 4 | 2021-03-12 | 49 | 2021-04-05 | 16 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-05-21 | 34 | [5 empty] | 2021-04-01 | 2021-04-13 | 8 |  |  |  |  | 2021-08-20 | 2021-08-24 | 2 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-24 |  | 2021-08-27 | 3
120664216 | 454 | PGE | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-03-19 |  | 2021-04-02 | 2021-04-02 | 2021-04-02 | 10 | 2021-05-25 | 47 | 2021-06-03 | 6 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-10 | 5 |  |  |  |  | 2021-03-19 | 2021-04-02 | 2021-04-14 | 18 |  |  |  |  | 2021-06-22 | 2021-06-29 | 5 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-29 |  | 2021-06-30 | 1
120602903 | 455 | PGE | NEM | EXPNEM | Implementation | Solar PV | 300 |  | 2021-03-04 |  | 2021-03-17 | 2021-03-17 | 2021-03-17 | 9 | 2021-05-24 | 57 | 2021-06-08 | 10 | [15 empty] | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-07-07 | 20 |  |  |  |  | 2021-03-04 | 2021-04-05 | 2021-04-14 | 29
120680099 | 456 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 125 |  | 2021-03-23 |  |  | 2021-04-06 | 2021-04-06 | 10 | 2021-04-20 | 20 | 2021-06-22 | 44 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | [6 empty] | 2021-03-23 | 2021-04-06 | 2021-04-14 | 16
120554661 | 457 | PGE | NEM | EXPNEM | Implementation | Solar PV | 43.593 |  | 2021-02-19 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 10 | 2021-03-22 | 21 | 2021-05-10 | 35 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2021-06-01 | 15 |  |  |  |  | 2021-02-19 | 2021-04-04 | 2021-04-14 | 38
120597306 | 458 | PGE | NEM | EXPNEM | Study in Progress | Solar PV, Storage | 1628 |  | 2021-03-03 | 2021-03-05 |  | 2021-03-05 | 2021-03-05 | 2 | 2021-03-31 | 20 | 2021-06-04 | 46 | 2021-06-15 | 2021-07-12 | 18 | [22 empty] | 2021-03-03 | 2021-04-02 | 2021-04-14 | 30
120652722 | 459 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 68.44 |  | 2021-03-17 |  | 2021-03-19 | 2021-03-19 | 2021-03-19 | 2 | 2021-04-02 | 12 | 2021-05-03 | 21 | [15 empty] | 2021-05-03 | 2021-05-04 | 1 | 2021-05-04 | 2021-06-16 | 30 |  |  |  |  | 2021-03-17 | 2021-04-02 | 2021-04-14 | 20
120695606 | 460 | PGE | NEM | EXPNEM | Implementation | Solar PV | 110 |  | 2021-03-26 |  |  | 2021-04-06 | 2021-04-06 | 7 | 2021-04-07 | 8 | 2021-05-13 | 26 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13 | 2021-05-17 | 2 | [5 empty] | 2021-04-06 | 2021-04-14 | 6
120431279 | 461 | PGE | NEM | EXPNEM | Commercial | Solar PV | 150 |  | 2021-01-14 |  | 2021-01-15 | 2021-01-15 | 2021-01-15 | 1 | 2021-01-19 | 2 | 2021-01-26 | 5 | [15 empty] | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 2021-04-06 | 49 |  |  |  |  | 2021-01-14 | 2021-01-15 | 2021-01-28 | 9 |  |  |  |  | 2021-04-09 | 2021-04-15 | 4 | [15 empty] | 2021-04-09 | 2021-04-12 | 1 | 2021-04-15 |  | 2021-04-19 | 2
120617738 | 462 | PGE | NEM | EXPNEM | Commercial | Solar PV | 258.2 |  | 2021-03-09 |  | 2021-03-11 | 2021-03-11 | 2021-03-11 | 2 | 2021-03-17 | 6 | 2021-03-26 | 7 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-05 | 6 | [12 empty] | 2021-04-06 | 2021-04-13 | 5 | [15 empty] | 2021-04-06 | 2021-04-07 | 1 | 2021-04-13 |  | 2021-04-16 | 3
120693011 | 463 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.588 |  | 2021-03-25 |  |  | 2021-04-07 | 2021-04-07 | 9 | 2021-04-07 | 9 | 2021-04-12 | 3 | [19 empty] | 2021-03-25 | N/A | [9 empty] | 2021-04-07 | 2021-04-20 | 9
120656083 | 465 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 933.1 |  | 2021-03-18 |  | 2021-04-01 | 2021-04-01 | 2021-04-01 | 10 | 2021-06-22 | 67 | 2021-07-26 | 23 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | [6 empty] | 2021-03-18
120658306 | 466 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.135 |  | 2021-03-18 |  | 2021-04-01 | 2021-04-01 | 2021-04-01 | 10 | 2021-04-24 | 26 | 2021-05-03 | 5 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | 2021-04-09 | 6 | [5 empty] | 2021-05-03 | 2021-05-17 | 10 |  | 2021-05-03 | 2021-05-03 | 0 | 2021-06-26 | 2021-07-13 | 10 | [15 empty] | 2021-06-26 | 2021-06-28 | 0 | 2021-07-13 |  | 2021-07-14 | 1
120655618 | 467 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 571.5 |  | 2021-03-17 |  | 2021-04-02 | 2021-04-02 | 2021-04-02 | 12 | 2021-06-22 | 68 | 2021-07-08 | 11 | 2021-07-27 | 2021-08-09 | 9 | [22 empty] | 2021-03-17 | 2021-04-29 | 2021-05-10 | 38
120697311 | 468 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 |  | 2021-03-26 |  | 2021-04-09 | 2021-04-09 | 2021-04-09 | 10 | 2021-04-19 | 16 | 2021-05-06 | 13 | [19 empty] | 2021-03-26 | N/A | [12 empty] | 2021-05-06 | 2021-05-06 | 0 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 |  | 2021-05-07 | 1
120449506 | 469 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 32.424 |  | 2021-01-20 |  | 2021-02-03 | 2021-02-03 | 2021-02-03 | 10 | 2021-09-21 | 170 | 2021-09-30 | 7 | [19 empty] | 2021-09-06 | N/A | [12 empty] | 2021-09-30 | [17 empty] | 2021-09-30 | 2021-09-30 | 0
120500786 | 470 | PGE | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 87.158 |  | 2021-02-04 |  | 2021-02-05 | 2021-02-05 | 2021-02-05 | 1
120461351 | 471 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.016 |  | 2021-01-25 |  | 2021-02-08 | 2021-02-08 | 2021-02-08 | 10 | 2021-05-26 | 86 | 2021-06-02 | 4 | [19 empty] | 2021-05-14 | N/A | [12 empty] | 2021-06-02 | 2021-06-02 | 0 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 |  | 2021-06-02 | 0
120497290 | 473 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 46.393 |  | 2021-02-03 |  | 2021-02-18 | 2021-02-18 | 2021-02-18 | 10 | 2021-05-21 | 76 | 2021-05-26 | 3 | [19 empty] | 2021-05-23 | N/A | [12 empty] | 2021-06-07 | 2021-06-07 | 0 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 |  | 2021-06-07 | 0
120506291 | 474 | PGE | NEM | NEM Paired Storage | Application Review in Progress | ENGN, Solar PV, Storage | 2503 |  | 2021-02-08 |  | 2021-04-05 | 2021-02-22 | 2021-02-22 | 9
120506355 | 475 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.54 |  | 2021-02-08 |  | 2021-05-09 | 2021-02-23 | 2021-02-23 | 10
120529036 | 476 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 405.19 |  | 2021-02-11 |  | 2021-02-24 | 2021-02-24 | 2021-02-24 | 8 | [29 empty] | 2021-02-11 | 2021-05-07 | 2021-05-25 | 72
120529038 | 477 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 399.09 |  | 2021-02-11 |  | 2021-02-24 | 2021-02-24 | 2021-02-24 | 8 | [29 empty] | 2021-02-11 | 2021-05-07 | 2021-05-25 | 72
120538562 | 478 | PGE | NEM | EXPNEM | IA in Progress | Solar PV, Storage | 349.179 |  | 2021-02-16 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 8 | 2021-05-26 | 71 | 2021-06-30 | 24 | [15 empty] | 2021-06-30 | 2021-06-30 | 0 | 2021-06-30 | [6 empty] | 2021-02-16 | 2021-08-05 | 2021-08-13 | 126
120582937 | 480 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 41.393 |  | 2021-02-26 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 10 | 2021-04-23 | 40 | 2021-04-26 | 1 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-03-29 | 0 | [12 empty] | 2021-04-26 | 2021-04-26 | 0 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 |  | 2021-04-26 | 0
120603633 | 481 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1395.292 |  | 2021-03-04 |  | 2021-03-18 | 2021-03-17 | 2021-03-17 | 9
120645634 | 484 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 37.6 |  | 2021-03-15 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 9 | 2021-06-07 | 59 | 2021-06-15 | 6 | [19 empty] | 2021-04-30 | N/A | [12 empty] | 2021-06-15 | 2021-06-17 | 2 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-17 |  | 2021-06-17 | 0
120655749 | 485 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 871.4 |  | 2021-03-17 |  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 10 | 2021-06-22 | 68 | 2021-07-08 | 11 | 2021-07-27 | 2021-08-09 | 9 | [12 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | [6 empty] | 2021-03-17
120653359 | 486 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 341.598 |  | 2021-03-17 |  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 10 | 2021-06-04 | 56 | 2021-07-23 | 34 | [19 empty] | 2021-08-09 | N/A
120691162 | 487 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 39.195 |  | 2021-03-25 |  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 4 | 2021-06-17 | 59 | 2021-07-12 | 16 | [19 empty] | 2021-06-21 | N/A | [12 empty] | 2021-07-12 | 2021-07-12 | 0 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 |  | 2021-07-12 | 0
120498076 | 488 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1572 |  | 2021-02-03 | 2021-02-05 |  | 2021-02-05 | 2021-02-05 | 2 | 2021-02-10 | 5 | 2021-04-16 | 46 | 2021-04-23 | 2021-06-22 | 41 | [12 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-09-20 | 62 |  |  |  |  | 2021-02-03
120498261 | 489 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1872 |  | 2021-02-03 | 2021-02-05 |  | 2021-02-05 | 2021-02-05 | 2 | 2021-02-17 | 9 | 2021-04-20 | 44 | 2021-04-24 | 2021-06-24 | 42 | [12 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-24 | [6 empty] | 2021-02-03
120498260 | 490 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1542.8 |  | 2021-02-03 | 2021-02-05 |  | 2021-02-05 | 2021-02-05 | 2 | 2021-02-17 | 9 | 2021-04-20 | 44 | 2021-04-23 | 2021-06-23 | 42 | [12 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-09-21 | 62 |  |  |  |  | 2021-02-03
120477883 | 492 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1359.5 |  | 2021-01-29 |  | 2021-02-05 | 2021-02-05 | 2021-02-05 | 5 | 2021-04-07 | 47 | 2021-04-28 | 15 | 2021-05-10 | 2021-06-24 | 32 | [12 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-24 | 2021-09-21 | 61 |  |  |  |  | 2021-01-29
120477908 | 493 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1280.3 |  | 2021-01-29 |  | 2021-02-05 | 2021-02-05 | 2021-02-05 | 5 | 2021-04-07 | 47 | 2021-04-28 | 15 | 2021-06-02 | 2021-06-30 | 20 | [12 empty] | 2021-06-30 | 2021-06-30 | 0 | 2021-06-30 | [6 empty] | 2021-01-29
120498202 | 494 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1272 |  | 2021-02-03 |  | 2021-02-08 | 2021-02-08 | 2021-02-08 | 3 | 2021-04-07 | 44 | 2021-04-28 | 15 | 2021-05-07 | 2021-06-21 | 30 | [12 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-09-21 | 64 |  |  |  |  | 2021-02-03
120698794 | 495 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 |  | 2021-03-26 |  |  | 2021-04-07 | 2021-04-07 | 8 | 2021-04-07 | 8 | 2021-04-30 | 17 | [33 empty] | 2021-04-30 | 2021-04-30 | 0 | [15 empty] | 2021-04-30 | 2021-04-30 | 0 | 2021-04-30 |  | 2021-05-03 | 1
120477970 | 496 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1309.5 |  | 2021-01-29 |  | 2021-02-13 | 2021-02-13 | 2021-02-13 | 10 | 2021-04-09 | 49 | 2021-05-07 | 20 | 2021-05-28 | 2021-06-28 | 20 | [12 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | [6 empty] | 2021-01-29
120498209 | 497 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1405.3 |  | 2021-02-03 |  | 2021-02-16 | 2021-02-16 | 2021-02-16 | 8 | 2021-04-10 | 46 | 2021-05-07 | 19 | 2021-06-01 | 2021-06-29 | 20 | [12 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | [6 empty] | 2021-02-03
120719402 | 499 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.559 |  | 2021-03-31 |  |  | 2021-04-14 | 2021-04-14 | 10 | 2021-04-14 | 10 | 2021-04-22 | 6 | [15 empty] | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 | 2021-06-08 | 32 |  |  |  |  | 2021-03-31 | 2021-05-14 | 2021-06-03 | 45 |  |  |  |  | 2021-06-14 | 2021-06-08 | 0 | [15 empty] | 2021-06-14 | 2021-06-14 | 0 | 2021-06-08 |  | 2021-06-08 | 1
120498201 | 500 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 1547 |  | 2021-02-03 | 2021-02-05 |  | 2021-02-04 | 2021-02-04 | 1 | 2021-02-10 | 5 | 2021-04-08 | 40 | 2021-04-14 | 2021-06-22 | 48 | [12 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-09-20 | 62 |  |  |  |  | 2021-02-03
120702082 | 501 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 39.248 |  | 2021-03-27 |  |  | 2021-04-06 | 2021-04-06 | 6 | 2021-04-06 | 6 | 2021-04-08 | 2
120507290 | 502 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 647.732 |  | 2021-02-08 | 2021-02-10 |  | 2021-02-10 | 2021-02-10 | 2 | 2021-03-10 | 21 | 2021-03-31 | 15 | 2021-04-09 | 2021-05-03 | 16 | [12 empty] | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | 2021-07-30 | 62 |  |  |  |  | 2021-02-08
120690757 | 503 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 39.229 |  | 2021-03-25 |  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 4 | 2021-04-01 | 5 | 2021-04-21 | 14 | [15 empty] | 2021-03-31 | 2021-04-01 | 1 | 2021-04-01 | 2021-04-01 | 0
120401062 | 505 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 39.4 |  | 2021-01-07 |  | 2021-01-12 | 2021-01-12 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-15 | 3 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12
120525633 | 506 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.828 |  | 2021-02-10 |  |  | 2021-02-18 | 2021-02-18 | 5 | 2021-02-18 | 5 | 2021-02-22 | 2 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-05-11 | 58 | [12 empty] | 2021-05-13 | 2021-05-13 | 0 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13 |  | 2021-05-13 | 0
120496371 | 507 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.877 |  | 2021-02-03 |  | 2021-02-06 | 2021-02-06 | 2021-02-06 | 2 | 2021-02-19 | 11 | 2021-03-03 | 8 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-07-08 | 89 | [12 empty] | 2021-07-08 | 2021-07-08 | 0 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 |  | 2021-07-09 | 1
120506335 | 511 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 45.177 |  | 2021-02-08 |  | 2021-02-23 | 2021-02-23 | 2021-02-23 | 10 | 2021-03-16 | 25 | 2021-03-22 | 4 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-22 | 4 | [12 empty] | 2021-04-28 | 2021-04-28 | 0 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 |  | 2021-04-28 | 0
120511112 | 512 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.49 |  | 2021-02-09 |  | 2021-02-24 | 2021-02-24 | 2021-02-24 | 10 | 2021-03-16 | 24 | 2021-03-24 | 6 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-05-21 | 48 | [12 empty] | 2021-05-26 | 2021-05-26 | 0 | [15 empty] | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 |  | 2021-05-27 | 1
120606443 | 513 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.728 |  | 2021-03-05 |  |  | 2021-03-19 | 2021-03-19 | 10 | 2021-03-19 | 10 | 2021-03-22 | 1 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-06-07 | 55 | [12 empty] | 2021-06-09 | 2021-06-09 | 0 | [15 empty] | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 |  | 2021-06-09 | 0
120611965 | 514 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 36.39 |  | 2021-03-08 |  | 2021-03-19 | 2021-03-19 | 2021-03-19 | 9 | 2021-04-08 | 23 | 2021-04-09 | 1 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-05-06 | 34
120617582 | 515 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 31.997 |  | 2021-03-09 |  |  | 2021-03-20 | 2021-03-20 | 8 | 2021-03-20 | 8 | 2021-05-19 | 42 | [15 empty] | 2021-03-20 | 2021-03-20 | 0 | 2021-03-20
120636261 | 518 | PGE | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 30.08 |  | 2021-03-11 |  | 2021-03-24 | 2021-03-24 | 2021-03-24 | 9 | [19 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24
120638777 | 521 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 42.716 |  | 2021-03-12 |  |  | 2021-03-25 | 2021-03-25 | 9 | 2021-03-25 | 9 | 2021-03-29 | 2 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-04-20 | 18 | [12 empty] | 2021-04-20 | 2021-04-20 | 0 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 |  | 2021-04-20 | 0
120644111 | 523 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.715 |  | 2021-03-15 |  | 2021-04-20 | 2021-03-27 | 2021-03-27 | 9 | 2021-04-15 | 23 | 2021-04-20 | 3 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | 2021-04-16 | 14 | [12 empty] | 2021-07-19 | 2021-09-22 | 46 | [15 empty] | 2021-07-19 | 2021-07-20 | 1 | 2021-09-22 |  | 2021-09-22 | 0
120644697 | 524 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 38.545 |  | 2021-03-15 |  | 2021-03-29 | 2021-03-29 | 2021-03-29 | 10 | 2021-03-29 | 10 | 2021-04-15 | 13 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-04-21 | 17
120646380 | 526 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 |  | 2021-03-16 |  |  | 2021-03-29 | 2021-03-29 | 9 | 2021-03-29 | 9 | 2021-03-30 | 1 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-05-05 | 27 | [12 empty] | 2021-05-05 | 2021-05-05 | 0 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 |  | 2021-05-05 | 0
120675302 | 528 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 38.86 |  | 2021-03-22 |  | 2021-04-05 | 2021-04-05 | 2021-04-05 | 10 | 2021-05-05 | 32 | 2021-05-24 | 13 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-04-15 | 8 | [12 empty] | 2021-05-28 | 2021-05-28 | 0 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 |  | 2021-05-28 | 0
120687551 | 532 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-03-24 |  |  | 2021-04-07 | 2021-04-07 | 10 | 2021-04-07 | 10 | 2021-04-20 | 9 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-07 | 0 | [12 empty] | 2021-04-20 | 2021-04-21 | 1 | [15 empty] | 2021-04-20 | 2021-04-21 | 1 | 2021-04-21 |  | 2021-04-21 | 0
120687584 | 533 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-03-24 |  |  | 2021-04-07 | 2021-04-07 | 10 | 2021-04-07 | 10 | 2021-04-09 | 2 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-05-11 | 24 |  |  |  |  | 2021-03-24 | 2021-04-07 | 2021-04-15 | 16 |  |  |  |  | 2021-05-11 | 2021-05-21 | 8 | [15 empty] | 2021-05-11 | 2021-05-12 | 1 | 2021-05-21 |  | 2021-05-21 | 0
120691460 | 534 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 42.497 |  | 2021-03-25 |  | 2021-04-08 | 2021-04-08 | 2021-04-08 | 10 | 2021-04-15 | 15 | 2021-04-16 | 1 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | 2021-05-10 | 22 |  |  |  |  | 2021-03-25 | 2021-04-19 | 2021-04-21 | 19 |  |  |  |  | 2021-05-10 | 2021-05-17 | 5 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-17 |  | 2021-05-17 | 0
120469866 | 535 | PGE | NEM | NEM Paired Storage | IA in Progress | OTHR, Solar PV, Storage | 30.246 |  | 2021-01-27 |  | 2021-02-10 | 2021-02-10 | 2021-02-10 | 10 | 2021-04-06 | 48 | 2021-04-08 | 2 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08
120714964 | 537 | PGE | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 30.08 |  | 2021-03-30 |  |  | 2021-04-12 | 2021-04-12 | 9 | 2021-04-12 | 9 | 2021-04-20 | 6 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-04-20 | 6
120566958 | 538 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 56.873 |  | 2021-02-23 |  |  | 2021-03-06 | 2021-03-06 | 8 | 2021-03-06 | 8 | 2021-03-18 | 8 | [15 empty] | 2021-03-06 | 2021-03-06 | 0 | 2021-03-06 | 2021-04-01 | 18
120491075 | 540 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31 |  | 2021-02-02 |  | 2021-02-16 | 2021-02-16 | 2021-02-16 | 9 | 2021-03-17 | 30 | 2021-03-25 | 6 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-04-09 | 17 | [12 empty] | 2021-08-31 | 2021-08-31 | 0 | [15 empty] | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 |  | 2021-08-31 | 0
120423593 | 541 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 51.699 |  | 2021-01-12 |  | 2021-01-23 | 2021-01-23 | 2021-01-23 | 7 | 2021-03-03 | 34 | 2021-03-23 | 14 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | [6 empty] | 2021-01-12 | 2021-03-03 | 2021-03-05 | 36
120477907 | 542 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1447 |  | 2021-01-29 | 2021-02-02 |  | 2021-02-02 | 2021-02-02 | 2 | 2021-02-10 | 8 | 2021-04-08 | 40 | 2021-04-14 | 2021-06-22 | 48 | [12 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-09-22 | 64 |  |  |  |  | 2021-01-29 | 2021-03-19 | 2021-03-23 | 36
120651432 | 543 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 96.54 |  | 2021-03-17 |  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 10 | 2021-05-14 | 42 | 2021-06-02 | 12 | [15 empty] | 2021-06-02 | 2021-06-09 | 5 | 2021-06-09 | 2021-06-25 | 12 |  |  |  |  | 2021-03-17 | 2021-03-31 | 2021-04-13 | 19 |  |  |  |  | 2021-07-15 | 2021-07-15 | 0 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 |  | 2021-07-16 | 1
120680807 | 545 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 37.345 |  | 2021-03-23 |  |  | 2021-04-06 | 2021-04-06 | 10 | 2021-04-06 | 10 | 2021-04-09 | 3 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-04-07 | 1 |  |  |  |  | 2021-03-23 | 2021-04-06 | 2021-04-14 | 16 |  |  |  |  | 2021-04-23 | 2021-04-28 | 3 | [15 empty] | 2021-04-23 | 2021-04-23 | 0 | 2021-04-28 |  | 2021-04-28 | 0
120639238 | 546 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 |  | 2021-03-12 |  |  | 2021-03-26 | 2021-03-26 | 10 | 2021-03-26 | 10 | 2021-03-29 | 1 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-07 | 8 | [12 empty] | 2021-09-13 | 2021-09-20 | 5 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-20 |  | 2021-09-20 | 0
120679364 | 547 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-03-23 |  | 2021-04-06 | 2021-04-06 | 2021-04-06 | 10 | 2021-04-07 | 11 | 2021-04-09 | 2 | [19 empty] | 2021-04-06 | N/A | [12 empty] | 2021-04-09 | 2021-04-09 | 0 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 |  | 2021-04-10 | 0
120664327 | 548 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 |  | 2021-03-19 |  | 2021-04-02 | 2021-04-02 | 2021-04-02 | 10 | 2021-04-08 | 14 | 2021-04-09 | 1 | [15 empty] | 2021-04-02 | 2021-04-02 | 0 | 2021-04-02 | 2021-04-08 | 4 | [12 empty] | 2021-04-09 | 2021-04-09 | 0 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 |  | 2021-04-10 | 0
120611966 | 550 | PGE | Non-NEM | NEMFC | Implementation | FUCE | 262.5 |  | 2021-03-08 |  |  | 2021-03-11 | 2021-03-11 | 3 | 2021-03-11 | 3 | 2021-04-16 | 26 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | 2021-04-05 | 17 |  |  |  |  | 2021-03-08 | 2021-05-13 | 2021-05-27 | 58
120722019 | 551 | PGE | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 59.575 |  | 2021-03-31 |  |  | 2021-04-16 | 2021-04-16 | 12 | 2021-04-16 | 12 | 2021-05-13 | 19 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13
120454664 | 552 | PGE | NEM | NEMMT | IA in Progress | Solar PV, Storage | 31.34 |  | 2021-01-21 |  | 2021-02-04 | 2021-02-04 | 2021-02-04 | 10 | 2021-05-21 | 85 | 2021-06-02 | 7 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-06-03 | 8
120507668 | 553 | PGE | NEM | NEMMT | Application Review in Progress | Solar PV, Storage | 894.727 |  | 2021-02-08 |  | 2021-07-13 | 2021-02-22 | 2021-02-22 | 9 | [29 empty] | 2021-02-08
120540680 | 554 | PGE | Non-NEM | NEMFC | IA in Progress | FUCE | 300 |  | 2021-02-17 |  | 2021-04-12 | 2021-03-02 | 2021-03-02 | 9 | 2021-05-13 | 61 | 2021-06-28 | 31 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28
120647383 | 556 | PGE | NEM | NEMMT | Study in Progress | ENGN, FUCE | 900 |  | 2021-03-16 |  | 2021-03-30 | 2021-03-30 | 2021-03-30 | 10 | 2021-07-23 | 91 | [5 empty] | 2021-07-23 | 2021-08-13 | 15 | 2021-08-13
120421365 | 557 | PGE | NEM | NEMMT | Study in Progress | Solar PV, Turbine | 18500 |  | 2021-01-12 | 2021-01-13 |  | 2021-01-12 | 2021-01-12 | 0 | 2021-02-03 | 15 | [5 empty] | 2021-02-03 | 2021-03-03 | 19 | 2021-03-03 | 2021-03-18 | 11 | 2021-05-20 |  |  | 2021-03-18 | 2021-04-07 | 14 | [10 empty] | 2021-01-12
120237635 | 558 | PGE | NEM | NEMMT | Study in Progress | Solar PV, Turbine | 106359.791 |  | 2020-12-29 |  | 2021-01-19 | 2021-01-04 | 2021-01-04 | 3 | 2021-02-10 | 29 | [5 empty] | 2021-02-10 | 2021-03-22 | 27 | 2021-03-22 | 2021-04-12 | 15 | 2021-06-09 |  |  | 2021-04-12 | 2021-05-03 | 15
120480244 | 559 | PGE | NEM | NEMMT | Study in Progress | ENGN, Solar PV, Storage | 4585 |  | 2021-01-29 | 2021-02-01 |  | 2021-02-01 | 2021-02-01 | 1 | 2021-02-17 | 12 | [5 empty] | 2021-02-17 | 2021-03-15 | 18 | 2021-03-15 | 2021-03-17 | 2 | 2021-03-29 | 2021-08-31 | 109 | 2021-03-17 | 2021-03-17 | 0 | [10 empty] | 2021-01-29
120507711 | 560 | PGE | NEM | NEMMT | Study in Progress | FUCE, Solar PV, WIND | 6689.431 |  | 2021-02-08 |  |  | 2021-02-22 | 2021-02-22 | 9 | 2021-02-22 | 9 | [5 empty] | 2021-02-22 | 2021-04-30 | 49 | 2021-04-30 | 2021-04-30 | 0 | 2021-06-15 | 2021-09-24 | 71 | 2021-04-30 | 2021-05-06 | 4 | [14 empty] | 2021-08-10 | 2021-08-24 |  | 10
120526554 | 561 | PGE | NEM | NEMMT | Study in Progress | FUCE, Solar PV, Storage | 2992.749 |  | 2021-02-11 | 2021-02-19 |  | 2021-02-16 | 2021-02-16 | 2 | 2021-03-03 | 13 | [5 empty] | 2021-03-03 | 2021-06-07 | 67 | 2021-06-07 | 2021-07-14 | 26 | 2021-08-23 |  |  | 2021-07-14 | 2021-07-14 | 0 | [10 empty] | 2021-02-11
120487290 | 562 | PGE | NEM | NEMMT | IA in Progress | FUCE, Solar PV | 1350 |  | 2021-02-01 |  | 2021-02-17 | 2021-02-17 | 2021-02-17 | 11 | 2021-03-27 | 38 | [5 empty] | 2021-03-27 | 2021-04-23 | 19 | 2021-04-23 |  |  | 2021-04-23 | 2021-07-12 | 54 |  |  |  | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [7 empty] | 2021-07-19 | 2021-08-05 | 13
120508906 | 563 | PGE | NEM | NEMMT | IA in Progress | FUCE, Solar PV | 769 |  | 2021-02-09 |  | 2021-02-22 | 2021-02-22 | 2021-02-22 | 8 | 2021-03-29 | 33 | 2021-07-07 | 70 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | [7 empty] | 2021-09-16 | 2021-09-22 | 4
120454060 | 564 | PGE | NEM | NEMMT | Study in Progress | FUCE, Solar PV | 250 |  | 2021-01-21 |  | 2021-02-04 | 2021-02-04 | 2021-02-04 | 10 | 2021-02-12 | 16 | 2021-03-05 | 14 | 2021-03-05 | 2021-04-02 | 20 | 2021-04-02 | 2021-05-07 | 25 | 2021-05-07 | 2021-05-24 | 11 |  | 2021-08-06 |  | 2021-05-24 |  |  | 2021-08-06 | 2021-08-09 | 1 | 2021-08-09 |  |  |  | 2021-08-31 |  |  | 2021-01-21 |  |  |  | 2021-06-17
120607849 | 565 | PGE | NEM | NEMMT | Commercial | Solar PV, Storage | 30.104 |  | 2021-03-05 |  |  | 2021-03-17 | 2021-03-17 | 8 | 2021-03-17 | 8 | 2021-03-22 | 3 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-04-19 | 23 | [12 empty] | 2021-04-19 | 2021-04-23 | 4 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-23 |  | 2021-04-23 | 0
120512635 | 566 | PGE | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2021-02-09 | 2021-02-11 |  | 2021-02-11 | 2021-02-11 | 2 | 2021-03-03 | 15 | 2021-04-20 | 34 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-08-09 | 77 | [5 empty] | 2021-03-04 | 2021-03-04 | 0
120525065 | 567 | PGE | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2021-02-10 | 2021-02-11 |  | 2021-02-11 | 2021-02-11 | 1 | 2021-03-03 | 14 | 2021-05-19 | 55 | [15 empty] | 2021-05-19 | 2021-05-19 | 0 | 2021-05-19 | 2021-08-16 | 61 |  |  |  |  | 2021-02-10 | 2021-03-04 | 2021-03-05 | 16
120425938 | 568 | PGE | Non-NEM | Non-Export | Implementation | Storage | 350 |  | 2021-01-13 | 2021-01-14 |  | 2021-01-14 | 2021-01-14 | 1 | 2021-02-03 | 14 | 2021-05-27 | 80 | [15 empty] | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-08-10 | 51
120434596 | 569 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-01-15 | 2021-01-19 |  | 2021-01-19 | 2021-01-19 | 1 | 2021-02-03 | 12 | 2021-06-10 | 89 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-08-30 | 56 | [5 empty] | 2021-07-09 | 2021-08-06 | 20
120511644 | 570 | PGE | Non-NEM | Non-Export | Implementation | Storage | 350 |  | 2021-02-09 | 2021-02-11 |  | 2021-02-11 | 2021-02-11 | 2 | 2021-03-03 | 15 | 2021-04-19 | 33 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-06-07 | 34
120512428 | 571 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 350 |  | 2021-02-09 | 2021-02-11 |  | 2021-02-11 | 2021-02-11 | 2 | 2021-03-03 | 15 | 2021-06-23 | 79 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-09-30 | 69
120568376 | 572 | PGE | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2021-02-23 | 2021-02-24 |  | 2021-02-24 | 2021-02-24 | 1 | 2021-03-10 | 11 | 2021-04-15 | 26 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-08-09 | 80 |  |  |  |  | 2021-02-23 | 2021-04-25 | 2021-05-21 | 63
120565908 | 573 | PGE | Non-NEM | Non-Export | Implementation | ENGN, Solar PV | 21944.2 |  | 2021-02-22 | 2021-03-04 |  | 2021-02-23 | 2021-02-23 | 1 | 2021-03-17 | 17 | 2021-04-15 | 21 | 2021-05-05 | 2021-06-04 | 21 | [12 empty] | 2021-06-04 | 2021-06-23 | 13 | 2021-06-23 | 2021-08-19 | 40
120674707 | 574 | PGE | Non-NEM | Non-Export | Withdrawn | Storage | 3000 |  | 2021-03-22 | 2021-03-24 |  | 2021-03-23 | 2021-03-23 | 1 | 2021-03-31 | 7
120508661 | 575 | PGE | Non-NEM | Non-Export | Withdrawn | Storage – EV | 153.6 |  | 2021-02-08 | 2021-02-09 |  | 2021-02-09 | 2021-02-09 | 1 | 2021-02-24 | 11 | 2021-03-01 | 3
120557855 | 576 | PGE | Non-NEM | Non-Export | Implementation | Storage | 1287 |  | 2021-02-20 | 2021-02-22 |  | 2021-02-22 | 2021-02-22 | 0 | 2021-03-03 | 7 | 2021-03-24 | 15 | 2021-04-07 | 2021-05-05 | 20 | [12 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-06-22 | 33 |  |  |  |  | 2021-02-20 | [13 empty] | 2021-08-11
120256198 | 577 | PGE | Non-NEM | Non-Export | Implementation | Storage | 980 |  | 2021-01-04 | 2021-01-05 |  | 2021-01-05 | 2021-01-05 | 1 | 2021-02-03 | 21 | 2021-07-20 | 116 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-08-16 | 135 |  |  |  |  | 2021-01-04
120424269 | 578 | PGE | Non-NEM | Non-Export | Implementation | ENGN, Solar PV | 766.6 |  | 2021-01-12 | 2021-01-14 |  | 2021-01-14 | 2021-01-14 | 2 | 2021-01-27 | 10 | 2021-03-01 | 22 | [15 empty] | 2021-03-19 | 2021-03-22 | 1 | 2021-03-22 | 2021-06-24 | 67 | [15 empty] | 2021-08-05
120557752 | 579 | PGE | Non-NEM | Non-Export | Implementation | Storage | 1287 |  | 2021-02-20 | 2021-02-22 |  | 2021-02-22 | 2021-02-22 | 0 | 2021-03-03 | 7 | 2021-03-24 | 15 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-06-22 | 63 |  |  |  |  | 2021-02-20
120582870 | 580 | PGE | Non-NEM | Non-Export | Withdrawn | Storage | 140 |  | 2021-02-26 | 2021-03-01 |  | 2021-03-01 | 2021-03-01 | 1 | 2021-03-24 | 18 | [17 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26
120600202 | 581 | PGE | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2021-03-03 | 2021-03-05 |  | 2021-03-05 | 2021-03-05 | 2 | 2021-03-24 | 15 | 2021-05-07 | 32 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-07-02 | 69
120552924 | 582 | PGE | Non-NEM | Non-Export | Implementation | Storage | 715 |  | 2021-02-18 | 2021-02-19 |  | 2021-02-19 | 2021-02-19 | 1 | 2021-03-03 | 9 | 2021-04-13 | 29 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-05-04 | 15 | [27 empty] | 2021-09-24
120541648 | 583 | PGE | Non-NEM | Non-Export | Implementation | Storage | 420 |  | 2021-02-17 | 2021-02-18 |  | 2021-02-18 | 2021-02-18 | 1 | 2021-03-10 | 15 | 2021-04-14 | 25 | [15 empty] | 2021-04-14 | 2021-04-14 | 0 | 2021-04-14 | 2021-07-13 | 62 |  |  |  |  | 2021-02-17 | 2021-04-15 | 2021-05-07 | 57
120258785 | 584 | PGE | Non-NEM | Non-Export | Withdrawn | Storage | 70 |  | 2021-01-05 | 2021-01-06 |  | 2021-01-06 | 2021-01-06 | 1 | 2021-01-27 | 15 | 2021-03-09 | 28 | [15 empty] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | [6 empty] | 2021-01-05 | 2021-01-29 | 2021-02-05 | 22
120433979 | 585 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-01-15 | 2021-01-19 |  | 2021-01-19 | 2021-01-19 | 1 | 2021-02-03 | 12 | 2021-03-11 | 25 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | 2021-06-02 | 58 |  |  |  |  | 2021-01-15 | 2021-02-06 | 2021-02-09 | 16
120526907 | 586 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 210 |  | 2021-02-11 | 2021-02-16 |  | 2021-02-16 | 2021-02-16 | 2 | 2021-03-03 | 13 | 2021-06-23 | 79 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | [6 empty] | 2021-02-11 | 2021-03-04 | 2021-03-16 | 22
120715337 | 587 | PGE | Non-NEM | RESBCT | Study in Progress | Solar PV | 4000 |  | 2021-03-30 | 2021-03-31 |  | 2021-03-30 | 2021-03-30 | 0 | 2021-04-21 | 16 | [5 empty] | 2021-04-21 | 2021-05-11 | 14 | 2021-05-11 | 2021-05-11 | 0 | 2021-05-19 |  |  | 2021-05-11 | 2021-05-12 | 1 | [7 empty] | 2021-09-03 | 2021-09-16 | 8
120537443 | 588 | PGE | Non-NEM | RESBCT | Implementation | Solar PV | 2341.786 |  | 2021-02-16 | 2021-02-19 |  | 2021-02-17 | 2021-02-17 | 1 | 2021-02-24 | 6 | [5 empty] | 2021-03-03 | 2021-03-24 | 15 | 2021-03-24 | [8 empty] | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 | 2021-09-28 | 19 |  |  |  |  | 2021-02-16
120612553 | 589 | PGE | Non-NEM | RESBCT | Study in Progress | Solar PV | 2782.651 |  | 2021-03-08 | 2021-03-11 |  | 2021-03-09 | 2021-03-09 | 1 | 2021-03-24 | 12 | 2021-04-13 | 14 | 2021-04-28 | 2021-07-01 | 45 | 2021-07-30 | 2021-08-26 | 19 | 2021-08-26 | 2021-08-26 | 0 | 2021-08-30 |  |  | 2021-08-26 | 2021-08-26 | 0 | [10 empty] | 2021-03-08
120684293 | 590 | PGE | NEM | VNEM | Implementation | Solar PV | 38.28 |  | 2021-03-24 |  | 2021-04-07 | 2021-04-05 | 2021-04-05 | 8 | 2021-04-29 | 26 | 2021-05-11 | 8 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2021-08-31 | 78 |  |  |  |  | 2021-03-24 | 2021-05-03 | 2021-05-25 | 44 |  | 2021-05-11 | 2021-05-11 | 0 | 2021-09-09 | 2021-09-20 | 7 | [15 empty] | 2021-09-09 | 2021-09-10 | 1 | 2021-09-20
120458566 | 591 | PGE | NEM | VNEM | Study in Progress | Solar PV | 30.26 |  | 2021-01-22 |  | 2021-02-05 | 2021-02-05 | 2021-02-05 | 10
120583633 | 592 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 31.024 |  | 2021-02-27 |  | 2021-03-10 | 2021-03-10 | 2021-03-10 | 7
120643625 | 593 | PGE | NEM | VNEM | Implementation | Solar PV | 86.4 |  | 2021-03-15 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 6 | 2021-06-16 | 66 | 2021-09-03 | 56 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-20 | 10 | [5 empty] | 2021-06-17 | 2021-07-02 | 11 |  |  |  |  | 2021-09-24 | 2021-09-30 | 4 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-30
120461526 | 594 | PGE | NEM | VNEM | Implementation | Solar PV | 38.78 |  | 2021-01-25 |  | 2021-02-08 | 2021-02-08 | 2021-02-08 | 10 | 2021-03-12 | 33 | 2021-03-24 | 8 | [15 empty] | 2021-03-24 | 2021-04-14 | 15 | 2021-04-14 | 2021-09-16 | 108 |  |  |  |  | 2021-01-25 |  |  |  | 2021-08-06 | 2021-08-12 | 2021-08-18 | 4
120585023 | 595 | PGE | NEM | VNEM | Commercial | Solar PV | 217.549 |  | 2021-03-01 |  | 2021-03-10 | 2021-03-10 | 2021-03-10 | 7 | 2021-03-18 | 13 | 2021-04-29 | 30 | [15 empty] | 2021-04-29 | 2021-05-14 | 11 | 2021-05-14 | 2021-07-12 | 39 |  |  |  |  | 2021-03-01 | 2021-07-01 | 2021-07-02 | 88 |  | 2021-07-02 | 2021-07-02 | 0 | 2021-08-20 | 2021-09-01 | 8 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-09-01 |  | 2021-09-02 | 1
120637757 | 596 | PGE | NEM | VNEM | Commercial | Solar PV | 35.595 |  | 2021-03-12 |  | 2021-03-22 | 2021-03-22 | 2021-03-22 | 6 | 2021-06-23 | 72 | 2021-07-13 | 13 | [15 empty] | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13 | 2021-07-23 | 8 |  |  |  |  | 2021-03-12 | 2021-04-01 | 2021-04-01 | 14 |  |  |  |  | 2021-09-02 | 2021-09-10 | 5 | [15 empty] | 2021-09-02 | 2021-09-02 | 0 | 2021-09-10 |  | 2021-09-15 | 3
120450062 | 597 | PGE | NEM | VNEM | Commercial | Solar PV | 150 |  | 2021-01-20 |  | 2021-02-03 | 2021-02-03 | 2021-02-03 | 10 | 2021-03-05 | 31 | 2021-03-25 | 14 | [15 empty] | 2021-03-25 | 2021-04-15 | 15 | 2021-04-15 | 2021-06-15 | 42 | [5 empty] | 2021-03-05 | 2021-03-08 | 1 |  | 2021-03-11 | 2021-03-11 | 0 | 2021-08-20 | 2021-08-31 | 7 | [15 empty] | 2021-08-20 | 2021-08-23 | 1 | 2021-08-31 |  | 2021-09-16 | 11
120552007 | 598 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 30.402 |  | 2021-02-18 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 11 | 2021-03-16 | 18 | 2021-03-16 | 0 | [15 empty] | 2021-03-16 | 2021-04-06 | 15 | 2021-04-06 | [6 empty] | 2021-02-18 | 2021-03-09 | 2021-03-12 | 16
120582557 | 599 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 52.493 |  | 2021-02-26 |  | 2021-03-10 | 2021-03-10 | 2021-03-10 | 8 | 2021-03-16 | 12 | 2021-05-28 | 53 | [15 empty] | 2021-05-28 | 2021-06-08 | 6 | 2021-06-08 | [6 empty] | 2021-02-26 | 2021-03-16 | 2021-03-23 | 17
120541015 | 600 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 43.53 |  | 2021-02-17 |  | 2021-03-10 | 2021-03-05 | 2021-03-05 | 12 | 2021-03-10 | 16 | 2021-04-02 | 18 | [15 empty] | 2021-04-02 | 2021-06-28 | 60 | 2021-06-28 | [6 empty] | 2021-02-17 | 2021-05-13 | 2021-05-27 | 71
120582748 | 601 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 39.976 |  | 2021-02-26 |  | 2021-03-12 | 2021-03-11 | 2021-03-11 | 9 | 2021-05-10 | 51 | 2021-07-02 | 38 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | [6 empty] | 2021-02-26 | 2021-05-11 | 2021-05-26 | 63 | 2021-09-08
120582841 | 602 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 39.976 |  | 2021-02-26 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 10 | 2021-05-10 | 51 | 2021-07-02 | 38 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | [6 empty] | 2021-02-26 | 2021-05-11 | 2021-05-26 | 63 | 2021-09-08
120582785 | 603 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 39.976 |  | 2021-02-26 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 10 | 2021-05-10 | 51 | 2021-07-28 | 55 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | [6 empty] | 2021-02-26 | 2021-05-11 | 2021-05-26 | 63
120582789 | 605 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 39.976 |  | 2021-02-26 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 10 | 2021-05-10 | 51 | 2021-07-28 | 55 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | [6 empty] | 2021-02-26 | 2021-05-11 | 2021-05-26 | 63
120582229 | 606 | PGE | NEM | VNEMMASH | Implementation | Solar PV | 39.976 |  | 2021-02-26 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 10 | 2021-03-31 | 23 | 2021-04-21 | 15 | [15 empty] | 2021-04-21 | 2021-05-26 | 25 | 2021-05-26 | 2021-06-10 | 10 |  |  |  |  | 2021-02-26 | 2021-05-11 | 2021-05-26 | 63 | 2021-08-06
120582228 | 607 | PGE | NEM | VNEMMASH | Implementation | Solar PV | 39.976 |  | 2021-02-26 |  | 2021-03-12 | 2021-03-12 | 2021-03-12 | 10 | 2021-03-31 | 23 | 2021-04-21 | 15 | [15 empty] | 2021-04-21 | 2021-05-26 | 25 | 2021-05-26 | 2021-06-10 | 10 |  |  |  |  | 2021-02-26 | 2021-05-11 | 2021-05-26 | 63 | 2021-08-06
120574050 | 608 | PGE | NEM | VNEMMASH | Withdrawn | Solar PV | 42.168 |  | 2021-02-24 |  | 2021-03-09 | 2021-03-09 | 2021-03-09 | 9 | 2021-03-11 | 11 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-04-16 | 15 | 2021-04-16 | [6 empty] | 2021-02-24 | 2021-03-11 | 2021-03-16 | 14
120574061 | 609 | PGE | NEM | VNEMMASH | Withdrawn | Solar PV | 34.179 |  | 2021-02-24 |  | 2021-03-09 | 2021-03-09 | 2021-03-09 | 9 | 2021-03-11 | 11 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-04-16 | 15 | 2021-04-16 | [6 empty] | 2021-02-24 | 2021-03-11 | 2021-03-16 | 14
120574052 | 610 | PGE | NEM | VNEMMASH | Withdrawn | Solar PV | 34.179 |  | 2021-02-24 |  | 2021-03-09 | 2021-03-09 | 2021-03-09 | 9 | 2021-03-11 | 11 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-04-16 | 15 | 2021-04-16 | [6 empty] | 2021-02-24 | 2021-03-11 | 2021-03-16 | 14
120573126 | 611 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 34.121 |  | 2021-02-24 |  | 2021-03-09 | 2021-03-09 | 2021-03-09 | 9 | 2021-03-15 | 13 | 2021-04-02 | 14 | [15 empty] | 2021-04-02 | 2021-04-08 | 4 | 2021-04-08 | [6 empty] | 2021-02-24 | 2021-07-27 | 2021-07-28 | 108
120582524 | 612 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 37.983 |  | 2021-02-26 |  | 2021-03-10 | 2021-03-10 | 2021-03-10 | 8 | 2021-03-16 | 12 | 2021-03-26 | 8 | [15 empty] | 2021-03-26 | 2021-04-16 | 15 | 2021-04-16 | [6 empty] | 2021-02-26 | 2021-04-30 | 2021-05-06 | 49
120593034 | 613 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 43.53 |  | 2021-03-02 |  | 2021-03-09 | 2021-03-09 | 2021-03-09 | 5 | 2021-03-17 | 11 | 2021-03-31 | 10 | [15 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | [6 empty] | 2021-03-02 | 2021-03-25 | 2021-03-31 | 21
120593054 | 614 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 37.983 |  | 2021-03-02 |  | 2021-03-09 | 2021-03-09 | 2021-03-09 | 5 | 2021-03-16 | 10 | 2021-04-01 | 12 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | [6 empty] | 2021-03-02 | 2021-03-25 | 2021-03-31 | 21
120540999 | 615 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 30.402 |  | 2021-02-17 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 12 | 2021-03-15 | 18 | 2021-03-24 | 7 | [15 empty] | 2021-03-24 | 2021-04-14 | 15 | 2021-04-14 | [6 empty] | 2021-02-17 | 2021-05-13 | 2021-05-27 | 71
120540965 | 616 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 63.72 |  | 2021-02-17 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 12 | 2021-03-15 | 18 | 2021-03-24 | 7 | [15 empty] | 2021-03-24 | 2021-04-14 | 15 | 2021-04-14 | [6 empty] | 2021-02-17 | 2021-03-05 | 2021-03-11 | 16 |  | 2021-03-24 | 2021-04-07 | 10
120491352 | 617 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 68.358 |  | 2021-02-02 |  | 2021-02-17 | 2021-02-17 | 2021-02-17 | 10 | 2021-02-22 | 13 | 2021-03-16 | 16 | [15 empty] | 2021-03-16 | 2021-04-21 | 26 | 2021-04-21 | [6 empty] | 2021-02-02 | 2021-02-22 | 2021-02-24 | 15 |  | 2021-04-20 | 2021-04-21 | 1
120474307 | 618 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 75.636 |  | 2021-01-28 |  | 2021-02-11 | 2021-02-11 | 2021-02-11 | 10 | 2021-03-16 | 32 | 2021-05-05 | 36 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | [6 empty] | 2021-01-28 | 2021-03-16 | 2021-03-18 | 34 |  | 2021-04-21 | 2021-04-21 | 0
120424174 | 619 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 60.446 |  | 2021-01-12 |  | 2021-01-27 | 2021-01-27 | 2021-01-27 | 10 | 2021-03-16 | 43 | 2021-03-28 | 8 | [15 empty] | 2021-05-14 | 2021-05-18 | 2 | 2021-05-18 | [6 empty] | 2021-01-12 | 2021-03-16 | 2021-03-23 | 48 |  | 2021-03-24 | 2021-05-04 | 29
120591196 | 620 | PGE | NEM | VNEMSOMAH | Implementation | Solar PV | 95.363 |  | 2021-03-02 |  | 2021-03-15 | 2021-03-15 | 2021-03-15 | 9 | 2021-03-17 | 11 | 2021-04-14 | 20 | [15 empty] | 2021-04-14 | 2021-04-14 | 0 | 2021-04-14 | 2021-05-26 | 30 | [5 empty] | 2021-03-26 | 2021-04-12 | 11 |  | 2021-04-14 | 2021-04-27 | 9
120715555 | 621 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 64.705 |  | 2021-03-30 |  | 2021-04-08 | 2021-04-08 | 2021-04-08 | 7 | 2021-04-16 | 13 | 2021-05-07 | 15 | [15 empty] | 2021-05-07 | 2021-05-07 | 0 | 2021-05-07 | [6 empty] | 2021-03-30 | 2021-05-07 | 2021-05-25 | 40
120491715 | 622 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 41.246 |  | 2021-02-02 |  | 2021-02-17 | 2021-02-17 | 2021-02-17 | 10 | [29 empty] | 2021-02-02
120510373 | 623 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 65.629 |  | 2021-02-09 |  | 2021-02-23 | 2021-02-23 | 2021-02-23 | 9 | [29 empty] | 2021-02-09
120528720 | 624 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 58.04 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
120528824 | 625 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
120528539 | 626 | PGE | NEM | VNEMSOMAH | Withdrawn | Solar PV | 43.53 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
120528951 | 627 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
120527343 | 628 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
120527994 | 629 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
120528823 | 630 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
120527751 | 631 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
120528507 | 632 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
120528891 | 633 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 39.172 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
120527807 | 634 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 38.052 |  | 2021-02-11 |  | 2021-02-26 | 2021-02-26 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
120535043 | 635 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 34.867 |  | 2021-02-15 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 13 | [29 empty] | 2021-02-15
120534668 | 636 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 34.8 |  | 2021-02-15 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 13 | [29 empty] | 2021-02-15
120535026 | 637 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 34.281 |  | 2021-02-15 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 13 | [29 empty] | 2021-02-15
120534319 | 638 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 34.22 |  | 2021-02-14 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 13 | [29 empty] | 2021-02-14
120534364 | 639 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 33.93 |  | 2021-02-14 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 13 | [29 empty] | 2021-02-14
120534317 | 640 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 33.35 |  | 2021-02-14 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 13 | [29 empty] | 2021-02-14
120257223 | 641 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 46.766 |  | 2021-01-04 |  |  | 2021-01-12 | 2021-01-12 | 6 | 2021-01-12 | 6 | [5 empty] | 2021-01-12 | 2021-01-23 | 7 | 2021-01-23 | [18 empty] | 2021-01-04
120508677 | 642 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 65.584 |  | 2021-02-08 |  | 2021-02-23 | 2021-02-23 | 2021-02-23 | 10 | 2021-03-30 | 35 | [5 empty] | 2021-03-30 | 2021-06-08 | 49 | 2021-06-08 | 2021-06-18 | 8 | 2021-06-18 | 2021-09-14 | 60 | 2021-06-18 | 2021-06-18 | 0 | 2021-09-14 | 2021-09-14 | 0 | 2021-09-14 | [6 empty] | 2021-02-08
120491626 | 643 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 43.2 |  | 2021-02-02 |  | 2021-02-12 | 2021-02-12 | 2021-02-12 | 8 | 2021-04-02 | 42 | [5 empty] | 2021-04-02 | 2021-06-18 | 54 | 2021-06-18 | 2021-06-18 | 0 | 2021-06-18 | 2021-09-17 | 63 | 2021-06-18 | 2021-06-18 | 0 | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | [6 empty] | 2021-02-02 | 2021-05-13 | 2021-05-27 | 81
120537787 | 644 | PGE | NEM | VNEMSOMAH | Implementation | Solar PV | 115.42 |  | 2021-02-16 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 13 | 2021-04-05 | 34 | 2021-04-26 | 15 | [15 empty] | 2021-04-26 | 2021-05-14 | 14 | 2021-05-14 | 2021-08-04 | 56 |  |  |  |  | 2021-02-16 | 2021-06-24 | 2021-07-08 | 100 |  | 2021-07-08 | 2021-07-08 | 0
120638882 | 645 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 68.358 |  | 2021-03-12 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 7 | 2021-04-13 | 22 | 2021-05-04 | 15 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | [6 empty] | 2021-03-12 | 2021-06-08 | 2021-06-11 | 64 |  | 2021-06-25 | 2021-07-04 | 5
120639172 | 646 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 95.363 |  | 2021-03-12 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 10 | 2021-04-13 | 22 | 2021-05-04 | 15 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | [6 empty] | 2021-03-12 | 2021-04-21 | 2021-05-07 | 40 |  | 2021-05-04 | 2021-05-04 | 0
120539885 | 647 | PGE | NEM | VNEMSOMAH | Application Accepted | Solar PV | 69.12 |  | 2021-02-17 |  | 2021-03-05 | 2021-03-05 | 2021-03-05 | 12 | 2021-03-05 | 12 | 2021-03-25 | 14 | [25 empty] | 2021-02-17 | 2021-03-05 | 2021-03-11 | 16
120638417 | 648 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.179 |  | 2021-03-12 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 7 | 2021-03-26 | 10 | 2021-04-01 | 4 | [15 empty] | 2021-04-01 | 2021-04-22 | 15 | 2021-04-22 | [6 empty] | 2021-03-12 | 2021-05-25 | 2021-06-15 | 66
120581731 | 649 | PGE | NEM | VNEMSOMAH | Implementation | Solar PV | 86.4 |  | 2021-02-26 |  | 2021-03-10 | 2021-03-10 | 2021-03-10 | 8 | 2021-03-16 | 12 | 2021-04-05 | 14 | [15 empty] | 2021-04-05 | 2021-04-26 | 15 | 2021-04-26 | 2021-07-27 | 64 | [5 empty] | 2021-04-26 | 2021-05-03 | 5 |  | 2021-04-26 | 2021-04-26 | 0
120424191 | 650 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 61.783 |  | 2021-01-12 |  | 2021-01-27 | 2021-01-27 | 2021-01-27 | 10 | 2021-03-16 | 43 | 2021-03-28 | 8 | [15 empty] | 2021-05-14 | 2021-05-18 | 2 | 2021-05-18 | [6 empty] | 2021-01-12 | 2021-03-16 | 2021-04-05 | 57 |  | 2021-05-04 | 2021-05-04 | 0
120460773 | 651 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100 |  | 2021-01-25 |  | 2021-02-08 | 2021-02-08 | 2021-02-08 | 10 | 2021-04-07 | 51 | 2021-04-28 | 15 | [15 empty] | 2021-04-28 | 2021-05-13 | 11 | 2021-05-13 | [6 empty] | 2021-01-25 | 2021-04-07 | 2021-04-07 | 51 | 2021-07-09
120638418 | 652 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 52.868 |  | 2021-03-12 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 7 | 2021-03-26 | 10 | 2021-04-09 | 10 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | [6 empty] | 2021-03-12 | 2021-06-18 | 2021-07-09 | 83 |  | 2021-07-04 | 2021-07-04 | 0
120528116 | 653 | PGE | NEM | VNEMSOMAH | Implementation | Solar PV | 100.91 |  | 2021-02-11 |  |  | 2021-02-24 | 2021-02-24 | 8 | 2021-02-24 | 8 | 2021-03-16 | 14 | [15 empty] | 2021-03-16 | 2021-04-06 | 15 | 2021-04-06 | 2021-09-21 | 117 | [5 empty] | 2021-02-24 | 2021-02-25 | 1 |  | 2021-03-04 | 2021-03-12 | 6
120528189 | 654 | PGE | NEM | VNEMSOMAH | Implementation | Solar PV | 100.91 |  | 2021-02-11 |  |  | 2021-02-26 | 2021-02-26 | 10 | 2021-02-26 | 10 | 2021-03-17 | 13 | [15 empty] | 2021-03-17 | 2021-04-06 | 14 | 2021-04-06 | 2021-09-21 | 117 | [5 empty] | 2021-02-26 | 2021-03-01 | 1 |  | 2021-03-04 | 2021-03-12 | 6
120528270 | 655 | PGE | NEM | VNEMSOMAH | Implementation | Solar PV | 72.22 |  | 2021-02-11 |  |  | 2021-02-26 | 2021-02-26 | 10 | 2021-02-26 | 10 | 2021-03-17 | 13 | [15 empty] | 2021-03-17 | 2021-04-06 | 14 | 2021-04-06 | 2021-09-21 | 117 | [5 empty] | 2021-03-09 | 2021-03-10 | 1 |  | 2021-03-12 | 2021-03-12 | 0
120531980 | 656 | PGE | NEM | VNEMSOMAH | Implementation | Solar PV | 115.42 |  | 2021-02-12 |  | 2021-03-03 | 2021-03-03 | 2021-03-03 | 12 | 2021-03-05 | 14 | 2021-04-12 | 26 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-07-27 | 74 |  |  |  |  | 2021-02-12 | 2021-03-05 | 2021-03-10 | 17 |  | 2021-03-24 | 2021-04-07 | 10
120601849 | 657 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 111.038 |  | 2021-03-04 |  |  | 2021-03-15 | 2021-03-15 | 7 | 2021-03-15 | 7 | 2021-04-12 | 20 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | [6 empty] | 2021-03-04 | 2021-03-24 | 2021-04-05 | 22 |  | 2021-04-12 | 2021-04-12 | 0
120506337 | 659 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-02-08 | 2021-02-09 |  | 2021-02-08 | 2021-02-08 | 0 | 2021-03-03 | 16 | 2021-04-06 | 24 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-04-30 | 18
120538796 | 660 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-02-17 | 2021-02-18 |  | 2021-02-17 | 2021-02-17 | 0 | 2021-03-03 | 10 | 2021-04-20 | 34 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-04-23 | 3
120538819 | 661 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-02-17 | 2021-02-18 |  | 2021-02-18 | 2021-02-18 | 1 | 2021-03-03 | 10 | 2021-04-19 | 33 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-04-20 | 1
120539333 | 662 | PGE | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-02-17 | 2021-02-18 |  | 2021-02-18 | 2021-02-18 | 1 | 2021-03-03 | 10 | 2021-04-23 | 37 | [15 empty] | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | 2021-04-27 | 2 | [12 empty] | 2021-09-13 | 2021-09-24 | 9 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-24 |  | 2021-09-24 | 0
120539500 | 663 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-02-17 | 2021-02-18 |  | 2021-02-18 | 2021-02-18 | 1 | 2021-03-03 | 10 | 2021-04-13 | 29 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-04-23 | 8
120542018 | 664 | PGE | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-02-17 | 2021-02-18 |  | 2021-02-18 | 2021-02-18 | 1 | 2021-03-03 | 10 | 2021-04-07 | 25 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-25 | 12 | [12 empty] | 2021-09-08 | 2021-09-16 | 6 | [15 empty] | 2021-09-08 | 2021-09-09 | 1 | 2021-09-16 |  | 2021-09-16 | 0
120553724 | 665 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-02-18 | 2021-02-19 |  | 2021-02-19 | 2021-02-19 | 1 | 2021-03-03 | 9 | 2021-03-25 | 16 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-03-31 | 4
120565433 | 666 | PGE | Non-NEM | Make Before Break | Implementation | ENGN | 4562 |  | 2021-02-22 | 2021-02-24 |  | 2021-02-23 | 2021-02-23 | 1 | 2021-03-30 | 26 | 2021-06-11 | 52 | [15 empty] | 2021-06-24 | 2021-09-10 | 54 | 2021-09-10 | 2021-09-27 | 11 | [13 empty] | 9/27/2021 | [19 empty] | 9/27/2021 | 2021-09-30 |  | 4 | 9/27/21 | 3 | 155 | 3 | 155
120581877 | 667 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 37.598 |  | 2021-02-26 |  | 2021-03-11 | 2021-03-11 | 2021-03-11 | 9 | 2021-05-11 | 52 | 2021-06-16 | 25 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | [6 empty] | 2021-02-26 | 2021-05-11 | 2021-05-26 | 63
120593158 | 668 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 54.65 |  | 2021-03-02 |  | 2021-06-01 | 2021-03-09 | 2021-03-09 | 5 | 2021-06-04 | 67 | 2021-06-04 | 0 | [33 empty] | 2021-06-04 | 2021-06-04 | 0 | [15 empty] | 2021-06-04 |  |  | 2021-06-04 |  | 2021-06-04 | 0
120659937 | 669 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-03-11 | 2021-03-19 |  | 2021-03-19 | 2021-03-19 | 6 | 2021-03-31 | 14 | 2021-04-26 | 18 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-04-28 | 2
120662541 | 670 | PGE | Non-NEM | Make Before Break | Study in Progress | ENGN, Turbine | 30358.8 |  | 2021-03-19 | 2021-03-22 |  | 2021-03-19 | 2021-03-19 | 0 | 2021-03-31 | 8 | 2021-04-30 | 22 | 2021-08-02 | 2021-08-17 | 11 | 2021-09-09
120664959 | 671 | PGE | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 32.641 |  | 2021-03-19 |  | 2021-04-05 | 2021-03-24 | 2021-03-24 | 3 | 2021-04-07 | 13 | 2021-04-23 | 12 | [33 empty] | 2021-05-14 | 2021-06-08 | 16 | 2021-05-03 | 2021-08-09 | 68 | [12 empty] | 2021-05-14 | 2021-06-08 | 16 | 2021-06-08 | 2021-06-08 |  | 4 |  |  | 42 |  | 42
120672708 | 672 | PGE | NEM | EXPNEM | Commercial | Solar PV | 30.402 |  | 2021-03-22 |  | 2021-04-05 | 2021-04-05 | 2021-04-05 | 10 | 2021-07-07 | 75 | 2021-07-21 | 10 | [15 empty] | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | 2021-07-26 | 3 | [12 empty] | 2021-08-23 | 2021-08-27 | 4 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-27 |  | 2021-08-31 | 2
120676644 | 673 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-03-23 | 2021-03-24 |  | 2021-03-23 | 2021-03-23 | 0 | 2021-04-07 | 11 | 2021-06-23 | 54 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-07-14 | 14
120678216 | 674 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.5 |  | 2021-03-23 |  | 2021-04-06 | 2021-04-06 | 2021-04-06 | 10 | 2021-05-05 | 31 | 2021-05-24 | 13 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-05-18 | 9 | [12 empty] | 2021-05-24 | 2021-05-24 | 0 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24 |  | 2021-05-25 | 1
120688511 | 675 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.355 |  | 2021-03-25 |  | 2021-05-04 | 2021-04-02 | 2021-04-02 | 6 | [19 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04
120690329 | 676 | PGE | Non-NEM | RESBCT | IA in Progress | Solar PV | 4500 |  | 2021-03-25 | 2021-03-26 |  | 2021-03-26 | 2021-03-26 | 1 | 2021-03-31 | 4 | [5 empty] | 2021-03-31 | 2021-04-28 | 20 | 2021-04-28 | 2021-04-28 | 0 | 2021-05-06 | 2021-09-17 | 93 | 2021-04-28 | 2021-04-29 | 1 | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 |  |  |  | 2021-08-24 | 2021-09-16 | 16
120691583 | 677 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 114.141 |  | 2021-03-25 |  | 2021-03-26 | 2021-03-26 | 2021-03-26 | 1 | 2021-05-03 | 27 | 2021-05-11 | 6 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11
120702459 | 678 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 60.318 |  | 2021-03-27 |  | 2021-04-07 | 2021-04-07 | 2021-04-07 | 7 | 2021-07-12 | 73 | 2021-07-14 | 2 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-27 | 9 |  |  |  |  | 2021-03-27 | 2021-09-13 | 2021-09-13 | 117
120709097 | 679 | PGE | NEM | EXPNEM | Commercial | Solar PV | 40.979 |  | 2021-03-29 |  | 2021-04-28 | 2021-04-06 | 2021-04-06 | 6 | 2021-05-03 | 25 | 2021-05-18 | 11 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | 2021-05-25 | 5 | [12 empty] | 2021-06-02 | 2021-06-10 | 6 | [15 empty] | 2021-06-02 | 2021-06-03 | 1 | 2021-06-10 |  | 2021-06-17 | 5
120709130 | 680 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 57.927 |  | 2021-03-29 |  | 2021-04-26 | 2021-04-12 | 2021-04-12 | 10 | 2021-06-05 | 48 | 2021-06-23 | 12 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-07-19 | 17 |  |  |  |  | 2021-03-29 | 2021-06-05 | 2021-06-16 | 56
120722334 | 681 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.612 |  | 2021-03-31 |  |  | 2021-04-14 | 2021-04-14 | 10 | 2021-04-14 | 10 | 2021-06-11 | 41 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19
120723303 | 682 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 44.948 |  | 2021-04-01 |  | 2021-04-21 | 2021-04-15 | 2021-04-15 | 10 | 2021-04-15 | 11 | 2021-04-21 | 5 | [19 empty] | 2021-04-01 | N/A |  |  |  |  | 2021-04-01 | [7 empty] | 2021-04-29 | 2021-05-05 | 4 | [15 empty] | 2021-04-29 | 2021-04-29 | 0 | 2021-05-05 |  | 2021-05-05 | 0
120726657 | 683 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 166.6 |  | 2021-04-01 |  | 2021-05-20 | 2021-04-05 | 2021-04-05 | 2 | 2021-05-21 | 36 | 2021-06-08 | 11 | 2021-06-08 | 2021-07-06 | 19 | 2021-07-06 | 2021-07-20 | 10 | 2021-07-20 | [18 empty] | 2021-04-01 | 2021-08-13 | 2021-08-27 | 104
120727153 | 684 | PGE | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-04-01 |  |  | 2021-04-13 | 2021-04-13 | 8 | 2021-04-23 | 16 | 2021-05-11 | 12 | 2021-05-11 | 2021-06-01 | 14 | [12 empty] | 2021-06-01 | 2021-06-02 | 1 | 2021-06-02 | 2021-06-03 | 1 |  |  |  |  | 2021-04-01 | 2021-04-23 | 2021-05-07 | 26
120727154 | 685 | PGE | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2021-04-01 | 2021-04-05 |  | 2021-04-02 | 2021-04-02 | 1 | 2021-04-21 | 14 | 2021-06-11 | 36 | [15 empty] | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-09-13 | 64 |  |  |  |  | 2021-04-01
120727269 | 686 | PGE | NEM | EXPNEM | Implementation | Solar PV | 420 |  | 2021-04-01 |  |  | 2021-04-15 | 2021-04-15 | 10 | 2021-04-22 | 15 | 2021-05-11 | 13 | 2021-05-11 | 2021-06-03 | 16 | [12 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-11 | 6
120727935 | 687 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 47.27 |  | 2021-04-01 |  | 2021-04-02 | 2021-04-02 | 2021-04-02 | 1 | 2021-04-07 | 4 | 2021-04-26 | 13 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-06-01 | 25
120728241 | 688 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 310.231 |  | 2021-04-01 |  | 2021-04-13 | 2021-04-13 | 2021-04-13 | 8 | [29 empty] | 2021-04-01
120728327 | 689 | PGE | Non-NEM | Non-Export | Implementation | Storage | 715 |  | 2021-03-25 | 2021-04-05 |  |  | 2021-04-05 | 7 | 2021-04-14 | 14 | 2021-05-20 | 26 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2021-07-21 | 42 |  |  |  |  | 2021-04-01 | 2021-06-09 | 2021-07-09 | 69
120733969 | 690 | PGE | NEM | EXPNEM | Implementation | Solar PV | 34.179 |  | 2021-04-02 |  | 2021-06-29 | 2021-04-14 | 2021-04-14 | 8 | 2021-07-19 | 74 | 2021-07-23 | 4 | [15 empty] | 2021-07-23 | 2021-07-23 | 0 | 2021-07-23 | 2021-08-06 | 10 |  |  |  |  | 2021-04-02 | 2021-07-22 | 2021-08-06 | 88 | [7 empty] | 2021-09-17
120734424 | 691 | PGE | NEM | EXPNEM | Implementation | Solar PV | 38.78 |  | 2021-04-02 |  | 2021-05-25 | 2021-04-14 | 2021-04-14 | 8 | 2021-06-03 | 43 | 2021-06-21 | 12 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-07-13 | 15 |  |  |  |  | 2021-04-02 | 2021-06-17 | 2021-07-02 | 64 |  |  |  |  | 2021-09-13 | 2021-09-21 | 6 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-21
120734966 | 692 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 43.04 |  | 2021-04-02 |  |  | 2021-04-14 | 2021-04-14 | 8 | 2021-04-14 | 8 | 2021-04-20 | 4 | [19 empty] | 2021-04-20 | N/A | [12 empty] | 2021-04-22 | 2021-04-22 | 0 | [15 empty] | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 |  | 2021-04-23 | 1
120735262 | 693 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 1560 |  | 2021-04-02 | 2021-04-05 |  | 2021-04-02 | 2021-04-02 | 0 | 2021-04-14 | 8 | 2021-05-20 | 26 | [25 empty] | 2021-04-02
120735552 | 694 | PGE | NEM | VNEMSOMAH | Implementation | Solar PV | 50.396 |  | 2021-04-02 |  | 2021-04-08 | 2021-04-08 | 2021-04-08 | 4 | 2021-04-16 | 10 | 2021-05-21 | 25 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-07-27 | 45 |  |  |  |  | 2021-04-02 | 2021-06-14 | 2021-06-24 | 58
120737106 | 695 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 33.614 |  | 2021-04-02 |  |  | 2021-04-13 | 2021-04-13 | 7 | 2021-04-13 | 7 | 2021-05-06 | 17 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 | [6 empty] | 2021-04-02 | 2021-05-12 | 2021-05-26 | 38
120737194 | 696 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.179 |  | 2021-04-02 |  |  | 2021-04-13 | 2021-04-13 | 7 | 2021-04-13 | 7 | 2021-05-06 | 17 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 | [6 empty] | 2021-04-02 | 2021-05-12 | 2021-05-26 | 38
120737196 | 697 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 38.018 |  | 2021-04-02 |  |  | 2021-04-13 | 2021-04-13 | 7 | 2021-04-13 | 7 | 2021-07-16 | 66 | [15 empty] | 2021-07-16 | 2021-08-27 | 30 | 2021-08-27 | [6 empty] | 2021-04-02 | 2021-07-07 | 2021-07-19 | 74
120737197 | 698 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 30.402 |  | 2021-04-02 |  |  | 2021-04-13 | 2021-04-13 | 7 | 2021-04-13 | 7 | 2021-05-06 | 17 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 | [6 empty] | 2021-04-02 | 2021-07-07 | 2021-07-19 | 74
120737359 | 699 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.804 |  | 2021-04-02 |  | 2021-04-05 | 2021-04-05 | 2021-04-05 | 1 | 2021-04-05 | 1 | 2021-04-09 | 4 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | 2021-04-12 | 1 | [5 empty] | 2021-07-07 | 2021-07-08 | 1 |  |  |  |  | 2021-08-20 | 2021-08-27 | 5 | 2021-06-15 | [14 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-27
120737583 | 700 | PGE | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-04-02 |  | 2021-04-28 | 2021-04-14 | 2021-04-14 | 8 | 2021-05-10 | 26 | 2021-06-28 | 34 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-06-29 | 1 | [12 empty] | 2021-09-10 | 2021-09-23 | 9 | [15 empty] | 2021-09-10 | 2021-09-12 | 0 | 2021-09-23 |  | 2021-09-23 | 0
120738200 | 701 | PGE | NEM | EXPNEM | Implementation | Solar PV | 101.728 |  | 2021-04-02 |  | 2021-05-04 | 2021-04-12 | 2021-04-12 | 6 | 2021-05-11 | 27 | 2021-06-25 | 32 | [15 empty] | 2021-07-13 | 2021-07-20 | 5 | 2021-07-20 | 2021-08-18 | 21 |  |  |  |  | 2021-04-02 |  |  |  | 2021-08-27
120738210 | 702 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 178.024 |  | 2021-04-02 |  | 2021-05-06 | 2021-04-05 | 2021-04-05 | 1 | 2021-05-06 | 24 | 2021-06-30 | 38 | [15 empty] | 2021-06-30 | 2021-07-06 | 3 | 2021-07-06 | 2021-07-16 | 8
120741508 | 703 | PGE | NEM | VNEM | Commercial | Solar PV | 34.639 |  | 2021-04-05 |  | 2021-04-14 | 2021-04-14 | 2021-04-14 | 7 | 2021-05-07 | 24 | 2021-06-09 | 22 | [15 empty] | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | 2021-06-14 | 3 | [5 empty] | 2021-06-17 | 2021-06-17 | 0 |  | 2021-06-16 | 2021-06-16 | 0 | 2021-07-29 | 2021-08-03 | 3 | [15 empty] | 2021-07-29 | 2021-07-29 | 0 | 2021-08-03 |  | 2021-08-10 | 5
120742000 | 704 | PGE | NEM | VNEM | Commercial | Solar PV | 54.828 |  | 2021-04-05 |  | 2021-04-14 | 2021-04-14 | 2021-04-14 | 7 | 2021-05-25 | 36 | 2021-06-11 | 12 | [15 empty] | 2021-06-11 | 2021-07-29 | 33 | 2021-07-29 | 2021-07-30 | 1 | [5 empty] | 2021-06-04 | 2021-06-04 | 0 |  | 2021-06-04 | 2021-06-11 | 5 | 2021-08-03 | 2021-08-10 | 5 | [15 empty] | 2021-08-03 | 2021-08-03 | 0 | 2021-08-10 |  | 2021-08-12 | 2
120742847 | 705 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 36.461 |  | 2021-04-05 |  |  | 2021-04-15 | 2021-04-15 | 8 | 2021-04-15 | 8 | 2021-04-19 | 2 | [19 empty] | 2021-04-05 | N/A |  |  |  |  | 2021-04-05 | 2021-06-07 | 2021-06-14 | 49
120743046 | 706 | PGE | Non-NEM | Non-Export | Implementation | Storage | 429 |  | 2021-04-05 | 2021-04-19 |  | 2021-04-19 | 2021-04-19 | 10 | 2021-05-12 | 27 | 2021-08-23 | 71 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23 | 2021-08-30 | 5 | [5 empty] | 2021-06-14 | 2021-07-09 | 18
120745137 | 707 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 123.798 |  | 2021-04-05 |  | 2021-04-29 | 2021-04-16 | 2021-04-16 | 9 | 2021-05-10 | 25 | 2021-06-01 | 15 | [15 empty] | 2021-06-01 | 2021-06-01 | 0 | 2021-06-01
120745382 | 708 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 1875 |  | 2021-04-05 | 2021-04-09 |  | 2021-04-06 | 2021-04-06 | 1 | 2021-05-12 | 27 | 2021-06-11 | 21 | 2021-07-06 | 2021-08-03 | 20 | 2021-09-03 | [21 empty] | 2021-04-05
120746949 | 709 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 32.178 |  | 2021-04-05 |  | 2021-04-15 | 2021-04-15 | 2021-04-15 | 8 | 2021-04-23 | 14 | 2021-04-27 | 2
120748479 | 710 | PGE | NEM | EXPNEM | Commercial | Solar PV | 133.2 |  | 2021-04-06 |  | 2021-04-13 | 2021-04-08 | 2021-04-08 | 2 | 2021-04-14 | 6 | 2021-04-28 | 10 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-06-30 | 44 | [12 empty] | 2021-07-15 | 2021-07-22 | 5 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-22 |  | 2021-07-29 | 5
120748631 | 711 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.341 |  | 2021-04-06 |  |  | 2021-04-20 | 2021-04-20 | 10 | 2021-04-20 | 10 | 2021-05-11 | 15 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-04-20 | 0 |  |  |  |  | 2021-04-06 | 2021-05-11 | 2021-05-25 | 35 |  |  |  |  | 2021-05-28 | 2021-05-28 | 0 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 |  | 2021-05-28 | 0
120749173 | 712 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 33.54 |  | 2021-04-06 |  | 2021-04-09 | 2021-04-08 | 2021-04-08 | 2 | 2021-06-08 | 44 | 2021-07-07 | 20 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | [6 empty] | 2021-04-06 | 2021-04-08 | 2021-04-15 | 7
120749736 | 713 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 420 |  | 2021-04-06 | 2021-04-09 |  | 2021-04-08 | 2021-04-08 | 2 | 2021-05-12 | 26
120751228 | 714 | PGE | Non-NEM | NEMFC | Study in Progress | FUCE | 525 |  | 2021-04-06 |  | 2021-04-20 | 2021-04-20 | 2021-04-20 | 10 | 2021-06-09 | 45
120753059 | 715 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 43.732 |  | 2021-04-06 |  |  | 2021-04-20 | 2021-04-20 | 10 | 2021-04-20 | 10 | 2021-05-06 | 12 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-05-05 | 11
120753598 | 716 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 66.513 |  | 2021-04-06 |  |  | 2021-04-20 | 2021-04-20 | 10 | 2021-04-22 | 12 | 2021-05-27 | 25 | [15 empty] | 2021-05-27 | 2021-05-28 | 1 | 2021-05-28 | [6 empty] | 2021-04-06 |  |  |  | 2021-06-11 | 2021-06-25 | 2021-06-25 | 10
120754663 | 717 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.119 |  | 2021-04-07 |  |  | 2021-04-20 | 2021-04-20 | 9 | 2021-04-20 | 9 | 2021-05-06 | 12 | [19 empty] | 2021-04-07 | N/A |  |  |  |  | 2021-04-07 | [7 empty] | 2021-05-18 | 2021-05-18 | 0 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 |  | 2021-05-18 | 0
120755133 | 718 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 912.4 |  | 2021-04-07 |  | 2021-05-03 | 2021-04-21 | 2021-04-21 | 10 | [29 empty] | 2021-04-07 | 2021-05-05 | 2021-05-25 | 34 | 2021-05-25
120756037 | 719 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 72.22 |  | 2021-04-07 |  |  | 2021-04-13 | 2021-04-13 | 4 | 2021-04-14 | 5 | 2021-08-04 | 78 | [15 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | [6 empty] | 2021-04-07 | 2021-07-15 | 2021-07-19 | 71 | 2021-04-29 | 2021-08-02 | 2021-08-04 | 65
120756234 | 720 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 72.22 |  | 2021-04-07 |  |  | 2021-04-13 | 2021-04-13 | 4 | 2021-04-14 | 5 | 2021-08-04 | 78 | [15 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | [6 empty] | 2021-04-07 |  |  |  | 2021-04-29 | 2021-05-13 | 2021-05-13 | 10
120756624 | 721 | PGE | NEM | SNEM | Application Review in Progress | Solar PV | 6570 |  | 2021-04-07 |  | 2021-04-14 | 2021-04-14 | 2021-04-14 | 5
120759039 | 722 | PGE | NEM | EXPNEM | Commercial | Solar PV | 72.55 |  | 2021-04-07 |  | 2021-04-08 | 2021-04-08 | 2021-04-08 | 1 | 2021-04-16 | 7 | 2021-04-27 | 7 | [15 empty] | 2021-04-27 | 2021-04-30 | 3 | 2021-04-30 | 2021-08-16 | 74 |  |  |  |  | 2021-04-07 | 2021-04-08 | 2021-04-15 | 6 |  |  |  |  | 2021-09-16 | 2021-09-22 | 4 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-22 |  | 2021-09-27 | 3
120760228 | 723 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 564.698 |  | 2021-04-07 |  | 2021-04-25 | 2021-04-22 | 2021-04-22 | 11 | 2021-06-17 | 50 | 2021-07-08 | 14 | 2021-07-27 | 2021-08-25 | 21 | [12 empty] | 2021-09-01 | 2021-09-16 | 10 | 2021-09-16 | [6 empty] | 2021-04-07
120764579 | 724 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 1930 |  | 2021-04-08 | 2021-04-14 |  | 2021-04-14 | 2021-04-14 | 4 | 2021-04-28 | 14 | [5 empty] | 2021-07-02 | 2021-07-28 | 17 | 2021-07-28
120764598 | 725 | PGE | NEM | EXPNEM | Commercial | Solar PV | 224.463 |  | 2021-04-08 |  |  | 2021-04-09 | 2021-04-09 | 1 | 2021-04-08 | 0 | 2021-04-29 | 15 | [15 empty] | 2021-04-29 | 2021-05-03 | 2 | 2021-05-03 | 2021-08-23 | 78 |  |  |  |  | 2021-04-08 | 2021-04-22 | 2021-05-07 | 21 |  |  |  |  | 2021-08-24 | 2021-09-01 | 6 | [15 empty] | 2021-08-24 | 2021-08-25 | 1 | 2021-09-01 |  | 2021-09-09 | 5
120765792 | 727 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.2 |  | 2021-04-08 |  | 2021-04-17 | 2021-04-17 | 2021-04-17 | 6
120766845 | 728 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 528.528 |  | 2021-04-08 |  |  | 2021-04-22 | 2021-04-22 | 10
120767244 | 729 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 125.563 |  | 2021-04-08 |  | 2021-04-16 | 2021-04-16 | 2021-04-16 | 6 | 2021-07-20 | 71 | 2021-08-10 | 15 | [19 empty] | 2021-05-13 | N/A | [12 empty] | 2021-08-10 | 2021-08-12 | 2 | [15 empty] | 2021-08-10 | 2021-08-11 | 1 | 2021-08-12 |  | 2021-08-12 | 0
120769789 | 730 | PGE | NEM | EXPNEM | Commercial | Solar PV | 91.863 |  | 2021-04-09 |  | 2021-04-12 | 2021-04-12 | 2021-04-12 | 1 | 2021-04-13 | 2 | 2021-04-28 | 11 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-04-29 | 1 | [12 empty] | 2021-05-03 | 2021-05-11 | 6 | [15 empty] | 2021-05-03 | 2021-05-04 | 1 | 2021-05-11 |  | 2021-05-14 | 3
120770341 | 731 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.52 |  | 2021-04-09 |  |  | 2021-04-22 | 2021-04-22 | 9 | 2021-04-22 | 9 | 2021-04-26 | 2 | [19 empty] | 2021-04-09 | N/A | [12 empty] | 2021-04-26 | 2021-04-26 | 0 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 |  | 2021-04-26 | 0
120770571 | 732 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 39.739 |  | 2021-04-09 |  | 2021-04-15 | 2021-04-12 | 2021-04-12 | 1 | 2021-05-11 | 22 | 2021-05-24 | 9 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24
120771011 | 733 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 |  | 2021-04-09 |  |  | 2021-04-13 | 2021-04-13 | 2 | 2021-04-13 | 2 | 2021-04-14 | 1 | [19 empty] | 2021-04-09 | N/A | [12 empty] | 2021-06-01 | 2021-06-03 | 2 | [15 empty] | 2021-06-01 | 2021-06-01 | 0 | 2021-06-03 |  | 2021-06-03 | 0
120772377 | 734 | PGE | NEM | EXPNEM | Commercial | Solar PV | 36.83 |  | 2021-04-09 |  | 2021-06-30 | 2021-04-12 | 2021-04-12 | 1 | 2021-07-01 | 58 | 2021-07-27 | 17 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-08-20 | 18 |  |  |  |  | 2021-04-12 | 2021-08-09 | 2021-08-18 | 90 |  |  |  |  | 2021-08-27 | 2021-09-02 | 4 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-09-02 |  | 2021-09-13 | 6
120772942 | 735 | PGE | Non-NEM | Non-Export | Withdrawn | Storage | 490 |  | 2021-04-09 | 2021-04-14 |  | 2021-04-14 | 2021-04-14 | 3 | 2021-04-21 | 8 | 2021-06-15 | 38 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-15 | [6 empty] | 2021-04-09
120773604 | 736 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 32.678 |  | 2021-04-09 |  | 2021-04-22 | 2021-04-22 | 2021-04-22 | 9 | 2021-05-05 | 18 | 2021-05-18 | 9 | [19 empty] | 2021-04-27 | N/A
120774008 | 737 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 36.403 |  | 2021-04-09 |  | 2021-04-22 | 2021-04-22 | 2021-04-22 | 9 | 2021-05-05 | 18 | 2021-05-17 | 8 | [19 empty] | 2021-04-23 | N/A
120774032 | 738 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.007 |  | 2021-04-09 |  | 2021-04-13 | 2021-04-13 | 2021-04-13 | 2 | 2021-08-20 | 93 | 2021-08-25 | 3 | [19 empty] | 2021-05-13 | N/A | [12 empty] | 2021-08-25 | 2021-08-25 | 0 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 |  | 2021-08-25 | 0
120792184 | 739 | PGE | NEM | VNEM | Implementation | Solar PV | 46.946 |  | 2021-04-11 |  | 2021-04-15 | 2021-04-15 | 2021-04-15 | 3 | 2021-07-01 | 57 | 2021-08-06 | 25 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | 2021-08-09 | 1 | [5 empty] | 2021-07-07 | 2021-07-19 | 8 |  | 2021-08-02 | 2021-08-06 | 4 | 2021-09-25 | [17 empty] | 2021-09-25 | 2021-09-27 | 0
120794139 | 740 | PGE | NEM | EXPNEM | Commercial | Solar PV | 193.173 |  | 2021-04-12 |  | 2021-04-21 | 2021-04-12 | 2021-04-12 | 0 | 2021-04-26 | 10 | 2021-05-12 | 12 | [15 empty] | 2021-05-12 | 2021-05-12 | 0 | 2021-05-12 | 2021-05-17 | 3 |  |  |  |  | 2021-04-12 | 2021-04-26 | 2021-05-10 | 20 |  |  |  |  | 2021-05-19 | 2021-06-16 | 19 | [15 empty] | 2021-05-19 | 2021-06-09 | 14 | 2021-06-16 |  | 2021-06-23 | 5
120794825 | 741 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.48 |  | 2021-04-12 |  | 2021-04-16 | 2021-04-16 | 2021-04-16 | 4 | 2021-04-22 | 8 | 2021-05-05 | 9 | [19 empty] | 2021-04-12 | N/A | [12 empty] | 2021-05-05 | 2021-05-05 | 0 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 |  | 2021-05-05 | 0
120795295 | 742 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 |  | 2021-04-12 |  | 2021-05-18 | 2021-05-05 | 2021-05-05 | 17 | 2021-06-10 | 42 | 2021-06-16 | 4 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | 2021-07-02 | 12 | [5 empty] | 2021-07-08 | 2021-07-19 | 7 |  |  |  |  | 2021-08-20 |  |  | 2021-07-20 | [14 empty] | 2021-08-20 | 2021-08-20 | 0
120796075 | 743 | PGE | NEM | EXPNEM | Implementation | Solar PV | 125 |  | 2021-04-12 |  | 2021-04-23 | 2021-04-23 | 2021-04-23 | 9 | 2021-06-10 | 42 | [17 empty] | 2021-07-02 | 2021-07-19 | 10 | 2021-07-19 | 2021-07-19 | 0 |  |  |  |  | 2021-04-12 | 2021-06-07 | 2021-06-16 | 46 |  |  |  |  | 2021-08-02 | 2021-08-12 | 8 | 2021-07-16 | [14 empty] | 2021-08-02 | 2021-08-02 | 0 | 2021-08-12 | 2021-08-16 |  | 2 |  |  | 88 |  | 88
120799551 | 744 | PGE | NEM | EXPNEM | Commercial | Solar PV | 43.875 |  | 2021-04-12 |  | 2021-05-24 | 2021-04-28 | 2021-04-28 | 12 | 2021-05-24 | 30 | 2021-06-08 | 10 | [15 empty] | 2021-06-08 | 2021-06-28 | 14 | 2021-06-28 | 2021-08-13 | 33 |  |  |  |  | 2021-04-12 | 2021-06-28 | 2021-07-15 | 66 | 2021-08-06 |  |  |  | 2021-09-03 | 2021-09-20 | 10 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-20 |  | 2021-09-20 | 0
120803445 | 745 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 900 |  | 2021-04-13 |  |  | 2021-04-28 | 2021-04-28 | 11 | 2021-04-29 | 12 | [5 empty] | 2021-04-29 | 2021-06-04 | 25 | 2021-06-04 |  |  |  | 2021-09-01 |  |  |  |  | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01
120803549 | 746 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.559 |  | 2021-04-13 |  |  | 2021-04-26 | 2021-04-26 | 9 | 2021-04-26 | 9 | 2021-05-11 | 11 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-05-24 | 20 | [12 empty] | 2021-05-25 | 2021-05-26 | 1 | [15 empty] | 2021-05-25 | 2021-05-26 | 1 | 2021-05-26 |  | 2021-05-26 | 0
120804361 | 747 | PGE | NEM | EXPNEM | Implementation | Solar PV | 300 |  | 2021-04-13 |  | 2021-04-26 | 2021-04-19 | 2021-04-19 | 4 | 2021-05-20 | 27 | 2021-06-09 | 13 | 2021-06-09 | 2021-07-07 | 19 | [12 empty] | 2021-07-07 | 2021-07-12 | 3 | 2021-07-12 | 2021-07-12 | 0 |  |  |  |  | 2021-04-13 | 2021-04-26 | 2021-05-10 | 19
120806392 | 748 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 37.8 |  | 2021-04-13 |  |  | 2021-04-14 | 2021-04-14 | 1 | 2021-04-14 | 1 | 2021-04-30 | 12 | [19 empty] | 2021-04-30 | N/A | [12 empty] | 2021-06-01 | 2021-06-01 | 0 | [15 empty] | 2021-06-01 | 2021-06-01 | 0 | 2021-06-01 |  | 2021-06-01 | 0
120807556 | 749 | PGE | NEM | EXPNEM | Commercial | Solar PV | 165.405 |  | 2021-04-13 |  | 2021-04-28 | 2021-04-28 | 2021-04-28 | 11 | 2021-05-21 | 28 | 2021-06-04 | 9 | [15 empty] | 2021-06-04 | 2021-06-04 | 0 | 2021-06-04 | 2021-06-07 | 1 |  |  |  |  | 2021-04-13 | 2021-05-24 | 2021-06-03 | 36 |  |  |  |  | 2021-07-30 | 2021-08-09 | 6 | [15 empty] | 2021-07-30 | 2021-08-02 | 1 | 2021-08-09 |  | 2021-08-09 | 0
120807656 | 750 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.024 |  | 2021-04-13 |  | 2021-05-06 | 2021-04-15 | 2021-04-15 | 2 | 2021-05-06 | 17 | 2021-07-09 | 44 | [15 empty] | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09 | [6 empty] | 2021-04-13 | 2021-06-02 | 2021-06-15 | 44
120807659 | 751 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.024 |  | 2021-04-13 |  | 2021-04-28 | 2021-04-15 | 2021-04-15 | 2 | 2021-04-28 | 11 | 2021-05-13 | 11 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13 | [6 empty] | 2021-04-13 | 2021-07-20 | 2021-07-29 | 75
120808104 | 752 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 40.1 |  | 2021-04-13 |  | 2021-04-14 | 2021-04-14 | 2021-04-14 | 1 | 2021-04-29 | 12 | 2021-05-12 | 9 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13 | 2021-05-24 | 7 | [5 empty] | 2021-08-09 | 2021-08-18 | 7 | 2021-09-27 | [21 empty] | 6/5/2021 | 2021-06-07 | 0
120808780 | 753 | PGE | NEM | EXPNEM | Commercial | Solar PV | 36 |  | 2021-04-13 |  |  | 2021-04-14 | 2021-04-14 | 1 | 2021-04-14 | 1 | 2021-04-28 | 10 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-05-03 | 3 | [12 empty] | 2021-07-23 | 2021-07-29 | 4 | [15 empty] | 2021-07-23 | 2021-07-23 | 0 | 2021-07-29 |  | 2021-08-10 | 8
120808879 | 754 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.36 |  | 2021-04-13 |  |  | 2021-04-26 | 2021-04-26 | 9 | 2021-04-26 | 9 | 2021-05-11 | 11 | [19 empty] | 2021-04-13 | N/A | [12 empty] | 2021-05-11 | 2021-05-12 | 1 | [15 empty] | 2021-05-11 | 2021-05-12 | 1 | 2021-05-12 |  | 2021-05-12 | 0
120809109 | 755 | PGE | NEM | EXPNEM | Commercial | Solar PV | 52.33 |  | 2021-04-13 |  | 2021-04-21 | 2021-04-14 | 2021-04-14 | 1 | 2021-04-23 | 8 | 2021-04-26 | 1 | [15 empty] | 2021-04-26 | 2021-05-12 | 12 | 2021-05-12 | 2021-05-14 | 2 |  |  |  |  | 2021-04-13 | 2021-04-26 | 2021-05-10 | 19 |  |  |  |  | 2021-08-05 | 2021-08-18 | 9 | [15 empty] | 2021-08-05 | 2021-08-18 | 9 | 2021-08-18 |  | 2021-08-23 | 3
120809175 | 756 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 200 |  | 2021-04-13 |  | 2021-04-14 | 2021-04-14 | 2021-04-14 | 1 | 2021-04-19 | 4 | 2021-05-04 | 11 | 2021-05-04 | 2021-06-01 | 19 | 2021-06-10 | 2021-07-08 | 19 | 2021-07-08 | 2021-07-14 | 4 |  |  |  | 2021-07-14 | [12 empty] | 2021-04-13 | 2021-04-28 | 2021-05-10 | 19
120809811 | 757 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 69.278 |  | 2021-04-13 |  | 2021-04-20 | 2021-04-20 | 2021-04-20 | 5 | 2021-04-30 | 13 | 2021-06-16 | 32 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | [6 empty] | 2021-04-13
120812770 | 758 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.024 |  | 2021-04-14 |  | 2021-05-18 | 2021-04-23 | 2021-04-23 | 7 | 2021-05-25 | 29 | [17 empty] | 2021-07-22 | 2021-08-24 | 23 | 2021-08-24 | [6 empty] | 2021-04-14 | 2021-06-14 | 2021-06-18 | 46
120812930 | 759 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 300 |  | 2021-04-14 |  | 2021-04-29 | 2021-04-27 | 2021-04-27 | 9 | 2021-06-08 | 38 | [5 empty] | 2021-06-08 | 2021-07-06 | 19 | 2021-07-06
120814029 | 760 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 37.858 |  | 2021-04-14 |  | 2021-04-26 | 2021-04-26 | 2021-04-26 | 8
120814896 | 761 | PGE | NEM | EXPNEM | Implementation | Solar PV | 33.504 |  | 2021-04-14 |  | 2021-05-24 | 2021-04-26 | 2021-04-26 | 8 | 2021-06-10 | 40 | 2021-07-07 | 18 | [15 empty] | 2021-07-07 | 2021-07-16 | 7 | 2021-07-16 | 2021-07-16 | 0 |  |  |  |  | 2021-04-14 |  |  |  | 2021-06-17
120815794 | 762 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 215.661 |  | 2021-04-14 |  | 2021-04-15 | 2021-04-15 | 2021-04-15 | 1 | 2021-05-13 | 21 | 2021-05-28 | 11 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | 2021-07-12 | 29 |  |  |  |  | 2021-04-14 | 2021-06-11 | 2021-06-17 | 45
120816189 | 763 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 375 |  | 2021-04-14 |  | 2021-06-23 | 2021-04-27 | 2021-04-27 | 9 | 2021-08-31 | 97 | [27 empty] | 2021-04-14 |  |  |  | 2021-09-08
120816701 | 764 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 2760 |  | 2021-04-14 | 2021-04-16 |  | 2021-04-16 | 2021-04-16 | 2 | 2021-04-21 | 5 | 2021-06-16 | 39 | [25 empty] | 2021-04-14
120816753 | 765 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 140 |  | 2021-04-14 | 2021-04-16 |  | 2021-04-16 | 2021-04-16 | 2 | 2021-05-12 | 20 | 2021-07-15 | 44 | [15 empty] | 2021-07-15 | 2021-07-16 | 1 | 2021-07-16 | [6 empty] | 2021-04-14
120822175 | 766 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 272.254 |  | 2021-04-15 |  | 2021-05-19 | 2021-04-28 | 2021-04-28 | 9
120822307 | 767 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 300 |  | 2021-04-15 |  | 2021-05-20 | 2021-04-28 | 2021-04-28 | 9 | 2021-06-04 | 35 | 2021-06-14 | 6 | [15 empty] | 2021-06-14 | 2021-07-01 | 13 | 2021-07-01
120822482 | 768 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 88.18 |  | 2021-04-15 |  | 2021-04-20 | 2021-04-16 | 2021-04-16 | 1 | 2021-04-28 | 9 | 2021-05-19 | 15 | 2021-05-19 | 2021-07-09 | 35 | [12 empty] | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09
120823102 | 769 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 240 |  | 2021-04-15 |  | 2021-04-16 | 2021-04-16 | 2021-04-16 | 1 | 2021-05-04 | 13 | 2021-06-28 | 38 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | [6 empty] | 2021-04-15 | 2021-05-19 | 2021-05-28 | 31 | [7 empty] | 2021-07-20
120823257 | 770 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-04-15 |  | 2021-04-16 | 2021-04-16 | 2021-04-16 | 1 | 2021-05-04 | 13 | 2021-07-08 | 45 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [6 empty] | 2021-04-15 | 2021-05-17 | 2021-05-18 | 23
120823543 | 771 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2043.114 |  | 2021-04-15 | 2021-04-20 |  | 2021-04-20 | 2021-04-20 | 3 | 2021-05-05 | 14 | 2021-07-31 | 60 | 2021-08-30 | [24 empty] | 2021-04-15 |  |  |  | 2021-07-21 | 2021-07-22 |  | 1
120823637 | 772 | PGE | Non-NEM | Non-Export | IA in Progress | ENGN | 4500 |  | 2021-04-15 | 2021-04-16 |  | 2021-04-16 | 2021-04-16 | 1 | 2021-04-21 | 4 | 2021-05-24 | 23 | 2021-07-16 | 2021-08-17 | 22 | [12 empty] | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26
120825142 | 773 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 210 |  | 2021-04-16 | 2021-04-16 |  | 2021-04-16 | 2021-04-16 | 0 | 2021-04-28 | 8 | 2021-07-02 | 46 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02
120826645 | 774 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-04-16 |  | 2021-04-27 | 2021-04-27 | 2021-04-27 | 7 | 2021-05-07 | 15 | 2021-05-10 | 1 | [19 empty] | 2021-05-07 | N/A | [12 empty] | 2021-05-10 | 2021-05-10 | 0 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 |  | 2021-05-10 | 0
120827781 | 775 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-04-16 |  | 2021-04-19 | 2021-04-19 | 2021-04-19 | 1 | 2021-05-21 | 25 | 2021-06-05 | 9 | [15 empty] | 2021-06-05 | 2021-06-05 | 0 | 2021-06-05 | 2021-06-11 | 4 |  |  |  |  | 2021-04-16 | 2021-05-27 | 2021-06-15 | 41
120828526 | 776 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 379.1 |  | 2021-04-16 |  | 2021-04-29 | 2021-04-29 | 2021-04-29 | 9
120828870 | 777 | PGE | NEM | EXPNEM | Commercial | Solar PV | 98.987 |  | 2021-04-16 |  | 2021-04-19 | 2021-04-19 | 2021-04-19 | 1 | 2021-04-22 | 4 | 2021-05-04 | 8 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | 2021-07-01 | 41 |  |  |  |  | 2021-04-16 | 2021-07-16 | 2021-07-23 | 68 |  |  |  |  | 2021-07-12 | 2021-07-22 | 8 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-22 |  | 2021-07-29 | 5
120828873 | 778 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 49.565 |  | 2021-04-16 |  | 2021-06-14 | 2021-04-19 | 2021-04-19 | 1 | 2021-06-16 | 42 | 2021-07-01 | 11 | [15 empty] | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01 | 2021-08-18 | 33 |  |  |  |  | 2021-04-16 | 2021-06-16 | 2021-06-24 | 48
120830341 | 779 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 86.4 |  | 2021-04-16 |  | 2021-05-04 | 2021-04-30 | 2021-04-30 | 10 | 2021-06-11 | 39 | 2021-07-02 | 15 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | [7 empty] | 2021-06-28 | 2021-07-15 | 12 |  | 2021-07-19 | 2021-07-19 | 0
120830947 | 780 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-04-16 |  | 2021-05-12 | 2021-04-30 | 2021-04-30 | 10 | 2021-07-15 | 62 | 2021-09-08 | 38 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | [6 empty] | 2021-04-16 | 2021-06-19 | 2021-07-02 | 54
120831810 | 781 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2021-04-16 |  |  | 2021-04-19 | 2021-04-19 | 1 | 2021-04-19 | 1 | 2021-04-23 | 4 | [15 empty] | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | [6 empty] | 2021-04-16 | 2021-04-21 | 2021-05-07 | 15
120842473 | 782 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2012.104 |  | 2021-04-19 | 2021-04-21 |  | 2021-04-19 | 2021-04-19 | 0 | 2021-05-05 | 12 | 2021-08-03 | 62 | 2021-08-30 | [24 empty] | 2021-04-19 |  |  |  | 2021-07-22 | 2021-07-22 |  | 0
120842663 | 783 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 170 |  | 2021-04-19 |  | 2021-04-19 | 2021-04-19 | 2021-04-19 | 0 | 2021-06-10 | 37 | 2021-06-29 | 13 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | 2021-08-19 | 36 |  |  |  |  | 2021-04-19 | 2021-08-19 | 2021-09-07 | 98
120844725 | 784 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 196 |  | 2021-04-19 |  | 2021-04-19 | 2021-04-19 | 2021-04-19 | 0 | 2021-06-10 | 37 | 2021-06-29 | 13 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | 2021-08-25 | 40 |  |  |  |  | 2021-04-19 | 2021-08-04 | 2021-08-05 | 76
120847643 | 785 | PGE | Non-NEM | Non-Export | Commercial | Storage | 210 |  | 2021-04-19 | 2021-04-21 |  | 2021-04-21 | 2021-04-21 | 2 | 2021-05-05 | 12 | 2021-07-06 | 42 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-09-20 | 53
120851262 | 786 | PGE | Non-NEM | NEMFC | IA in Progress | FUCE | 1470 |  | 2021-04-20 |  | 2021-05-04 | 2021-05-04 | 2021-05-04 | 10 | 2021-05-06 | 12 | 2021-07-27 | 56 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27
120854663 | 787 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 300 |  | 2021-04-20 |  | 2021-05-04 | 2021-05-04 | 2021-05-04 | 10 | 2021-05-14 | 18 | 2021-08-09 | 59 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-07-13 | 28 | [5 empty] | 2021-06-17 | 2021-07-02 | 11 | [7 empty] | 2021-09-01
120854836 | 788 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 240 |  | 2021-04-20 |  | 2021-04-21 | 2021-04-21 | 2021-04-21 | 1 | 2021-04-28 | 6 | 2021-05-10 | 8 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | [6 empty] | 2021-04-20 | 2021-04-21 | 2021-05-07 | 13
120855236 | 789 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-04-20 |  | 2021-04-21 | 2021-04-21 | 2021-04-21 | 1 | 2021-04-27 | 5 | 2021-05-10 | 9 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | [6 empty] | 2021-04-20 | 2021-04-27 | 2021-05-10 | 14
120855661 | 790 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 117.475 |  | 2021-04-20 |  | 2021-04-21 | 2021-04-21 | 2021-04-21 | 1 | 2021-04-28 | 6 | 2021-05-12 | 10 | [15 empty] | 2021-05-12 | 2021-05-12 | 0 | 2021-05-12 | [17 empty] | 2021-07-16
120855801 | 791 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 91.917 |  | 2021-04-16 |  | 2021-04-21 | 2021-04-21 | 2021-04-21 | 3
120855807 | 792 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-04-20 |  | 2021-04-21 | 2021-04-21 | 2021-04-21 | 1 | 2021-04-28 | 6 | 2021-05-11 | 9 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | [6 empty] | 2021-04-20 | 2021-04-21 | 2021-05-07 | 13
120855838 | 793 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2021-04-20 |  | 2021-04-21 | 2021-04-21 | 2021-04-21 | 1 | 2021-04-28 | 6 | 2021-05-11 | 9 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | [6 empty] | 2021-04-20 | 2021-04-21 | 2021-05-07 | 13
120856990 | 794 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 279.436 |  | 2021-04-21 |  | 2021-05-06 | 2021-05-06 | 2021-05-06 | 11 | 2021-06-15 | 38 | 2021-07-28 | 30 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | 2021-08-09 | 8 | [8 empty] | 2021-07-08 | 2021-07-21 | 2021-07-28 | 9
120859634 | 795 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.564 |  | 2021-04-21 |  | 2021-04-26 | 2021-04-26 | 2021-04-26 | 3 | 2021-05-20 | 21 | 2021-05-24 | 2 | [19 empty] | 2021-05-20 | N/A | [12 empty] | 2021-09-09 | 2021-09-09 | 0 | [15 empty] | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 |  | 2021-09-09 | 0
120860814 | 796 | PGE | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-04-21 |  | 2021-04-29 | 2021-04-29 | 2021-04-29 | 6 | 2021-05-04 | 9 | 2021-05-25 | 15 | [15 empty] | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-06-14 | 13 | [12 empty] | 2021-06-14 | 2021-06-23 | 7 | [15 empty] | 2021-06-14 | 2021-06-15 | 1 | 2021-06-23 |  | 2021-06-24 | 1
120860895 | 797 | PGE | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-04-21 |  | 2021-06-15 | 2021-04-22 | 2021-04-22 | 1 | 2021-06-18 | 41 | 2021-07-08 | 13 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-15 | 5 |  |  |  |  | 2021-04-21 | 2021-05-17 | 2021-05-18 | 19 |  |  |  |  | 2021-07-15 | 2021-07-20 | 3 | [15 empty] | 2021-07-15 | 2021-07-16 | 1 | 2021-07-20 |  | 2021-07-27 | 5
120862032 | 798 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 61.513 |  | 2021-04-21 |  | 2021-09-22 | 2021-05-04 | 2021-05-04 | 9
120863035 | 799 | PGE | Non-NEM | NEMFC | IA in Progress | FUCE | 262.5 |  | 2021-04-22 |  |  | 2021-05-06 | 2021-05-06 | 10 | 2021-05-06 | 10 | 2021-05-27 | 15 | [15 empty] | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | [6 empty] | 2021-04-22
120863572 | 800 | PGE | NEM | EXPNEM | Commercial | Solar PV | 89.246 |  | 2021-04-22 |  | 2021-05-14 | 2021-05-04 | 2021-05-04 | 8 | 2021-05-17 | 17 | 2021-06-28 | 29 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-07-12 | 9 |  |  |  |  | 2021-04-22 | 2021-08-24 | 2021-09-08 | 96 | 2021-07-29 |  |  |  | 2021-09-10 | 2021-09-21 | 7 | [15 empty] | 2021-09-10 | 2021-09-13 | 1 | 2021-09-21 |  | 2021-09-22 | 1
120864448 | 801 | PGE | Non-NEM | Non-Export | Implementation | Storage | 420 |  | 2021-04-22 | 2021-04-23 |  | 2021-04-23 | 2021-04-23 | 1 | 2021-05-19 | 19 | 2021-06-18 | 21 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-18 | 2021-06-23 | 3 |  |  |  |  | 2021-04-22
120864514 | 802 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 36.12 |  | 2021-04-22 |  | 2021-04-27 | 2021-04-27 | 2021-04-27 | 3 | 2021-04-27 | 3 | 2021-04-28 | 1 | [19 empty] | 2021-04-27 | N/A | [12 empty] | 2021-04-28 | 2021-05-05 | 5 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-05-05 |  | 2021-05-06 | 1
120865154 | 803 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 326.971 |  | 2021-04-22 |  | 2021-04-23 | 2021-04-23 | 2021-04-23 | 1 | 2021-04-30 | 6 | 2021-05-19 | 13 | [15 empty] | 2021-05-19 | 2021-05-19 | 0 | 2021-05-19 | 2021-05-25 | 4 |  |  |  |  | 2021-04-22 | 2021-04-23 | 2021-05-07 | 11
120866578 | 804 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.38 |  | 2021-04-22 |  | 2021-04-30 | 2021-04-30 | 2021-04-30 | 6 | 2021-05-05 | 9 | 2021-05-14 | 7 | [19 empty] | 2021-05-14 | N/A | [12 empty] | 2021-05-14 | 2021-05-14 | 0 | [15 empty] | 2021-05-14 | 2021-05-14 | 0 | 2021-05-14 |  | 2021-05-17 | 1
120866974 | 805 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-04-22 |  | 2021-05-20 | 2021-04-23 | 2021-04-23 | 1 | 2021-05-03 | 7 | 2021-05-21 | 14 | [15 empty] | 2021-05-21 | 2021-06-16 | 17 | 2021-06-16
120866976 | 806 | PGE | NEM | EXPNEM | Implementation | Solar PV | 86 |  | 2021-04-22 |  |  | 2021-05-04 | 2021-05-04 | 8 | 2021-05-04 | 8 | 2021-05-26 | 16 | [15 empty] | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 | 2021-08-24 | 62 |  |  |  |  | 2021-05-26 | 2021-08-25 | 2021-09-08 | 72
120867210 | 807 | PGE | NEM | EXPNEM | Implementation | Solar PV | 116.6 |  | 2021-04-22 |  | 2021-04-28 | 2021-04-26 | 2021-04-26 | 2 | 2021-06-02 | 28 | 2021-06-21 | 13 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-23 | 2 | [12 empty] | 2021-07-17 | 2021-07-28 | 7 | [15 empty] | 2021-07-17 | 2021-07-19 | 0 | 2021-07-28
120869063 | 808 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-04-22 |  | 2021-04-26 | 2021-04-26 | 2021-04-26 | 2 | 2021-04-28 | 4 | 2021-06-16 | 34 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | 2021-06-22 | 4
120869339 | 809 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 38.019 |  | 2021-04-22 |  | 2021-05-03 | 2021-05-03 | 2021-05-03 | 7 | 2021-05-03 | 7 | 2021-05-05 | 2 | [19 empty] | 2021-05-03 | N/A | [12 empty] | 2021-05-05 | 2021-05-05 | 0 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 |  | 2021-05-10 | 3
120869498 | 810 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 572 |  | 2021-04-22 | 2021-04-23 |  | 2021-04-23 | 2021-04-23 | 1 | 2021-05-19 | 19 | 2021-09-10 | 79 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | [6 empty] | 2021-04-22 | 2021-06-04 | 2021-06-16 | 38
120872340 | 811 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 35.116 |  | 2021-04-23 |  | 2021-05-05 | 2021-05-05 | 2021-05-05 | 8 | 2021-06-22 | 41 | 2021-06-23 | 1 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-06-22 | 33
120872738 | 812 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 908.3 |  | 2021-04-23 |  | 2021-04-29 | 2021-04-29 | 2021-04-29 | 4 | 2021-04-30 | 5 | 2021-05-17 | 11 | 2021-07-07 | 2021-08-05 | 21 | [12 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05
120873403 | 813 | PGE | NEM | EXPNEM | Implementation | Solar PV | 240 |  | 2021-04-23 |  | 2021-05-04 | 2021-05-04 | 2021-05-04 | 7 | 2021-05-17 | 16 | 2021-06-01 | 10 | [15 empty] | 2021-06-01 | 2021-06-10 | 7 | 2021-06-10 | 2021-08-18 | 48 |  |  |  |  | 2021-04-23 | 2021-06-10 | 2021-06-17 | 38
120873418 | 814 | PGE | NEM | EXPNEM | Implementation | Solar PV | 240 |  | 2021-04-23 |  | 2021-05-04 | 2021-05-04 | 2021-05-04 | 7 | 2021-05-21 | 20 | 2021-06-02 | 7 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-08-25 | 59 |  |  |  |  | 2021-04-23 | 2021-06-10 | 2021-06-17 | 38
120873425 | 815 | PGE | NEM | EXPNEM | Implementation | Solar PV | 320 |  | 2021-04-23 |  | 2021-05-05 | 2021-05-04 | 2021-05-04 | 7 | 2021-06-08 | 31 | 2021-06-23 | 11 | [15 empty] | 2021-08-03 | 2021-08-03 | 0 | 2021-08-03 | 2021-08-18 | 11 |  |  |  |  | 2021-04-23 | 2021-08-03 | 2021-08-13 | 78
120874705 | 816 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-04-23 |  | 2021-04-26 | 2021-04-26 | 2021-04-26 | 1 | 2021-04-29 | 4 | 2021-05-20 | 15 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2021-05-24 | 2 |  |  |  |  | 2021-04-23 | 2021-04-26 | 2021-05-10 | 11 | [7 empty] | 2021-08-23 | 2021-09-09 | 12
120875063 | 817 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 140 |  | 2021-04-23 | 2021-04-27 |  | 2021-04-27 | 2021-04-27 | 2 | 2021-05-19 | 18 | 2021-06-17 | 20 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-08-11 | 38 |  |  |  |  | 2021-04-23
120875131 | 818 | PGE | NEM | EXPNEM | Implementation | Solar PV | 375 |  | 2021-04-23 |  | 2021-05-05 | 2021-05-05 | 2021-05-05 | 8 | 2021-05-21 | 20 | 2021-06-28 | 25 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-09-24 | 62 |  |  |  |  | 2021-04-23 | 2021-05-21 | 2021-06-03 | 28
120875952 | 819 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 300 |  | 2021-04-23 |  | 2021-04-26 | 2021-04-26 | 2021-04-26 | 1 | 2021-06-05 | 29 | 2021-06-16 | 7 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16
120876292 | 820 | PGE | NEM | EXPNEM | Commercial | Solar PV | 30.45 |  | 2021-04-23 |  | 2021-05-17 | 2021-05-04 | 2021-05-04 | 7 | 2021-05-18 | 17 | 2021-06-03 | 11 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-16 | 9 |  |  |  |  | 2021-04-23 | 2021-05-17 | 2021-05-28 | 25 |  |  |  |  | 2021-08-18 | 2021-08-25 | 5 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-25 |  | 2021-08-30 | 3
120876297 | 821 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 38.23 |  | 2021-04-23 |  | 2021-05-05 | 2021-05-05 | 2021-05-05 | 8 | 2021-05-20 | 19 | 2021-05-24 | 2 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-05-25 | 14 | [12 empty] | 2021-08-13 | 2021-08-23 | 6 | [15 empty] | 2021-08-13 | 2021-08-13 | 0 | 2021-08-23 |  | 2021-08-23 | 0
120876541 | 822 | PGE | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2021-04-23 |  | 2021-06-03 | 2021-05-05 | 2021-05-05 | 8 | 2021-06-02 | 27 | 2021-06-17 | 11 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-06-29 | 8 |  |  |  |  | 2021-04-23 | 2021-06-04 | 2021-06-15 | 36
120876608 | 823 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 52.72 |  | 2021-04-23 |  | 2021-05-05 | 2021-05-05 | 2021-05-05 | 8 | 2021-05-26 | 23 | 2021-06-03 | 5 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-07-14 | 48 | [12 empty] | 2021-07-30 | 2021-08-04 | 3 | [15 empty] | 2021-07-30 | 2021-07-30 | 0 | 2021-08-04 |  | 2021-08-05 | 1
120876757 | 824 | PGE | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1804.932 |  | 2021-04-23 | 2021-04-27 |  | 2021-04-27 | 2021-04-27 | 2 | 2021-06-09 | 32 | [27 empty] | 2021-04-23
120876784 | 825 | PGE | NEM | NEMMT | IA in Progress | Solar PV, Storage | 478 |  | 2021-04-23 |  | 2021-05-10 | 2021-05-10 | 2021-05-10 | 11 | 2021-06-15 | 36 | 2021-07-07 | 15 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | [10 empty] | 2021-09-22
120876852 | 826 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 30.45 |  | 2021-04-23 |  | 2021-05-13 | 2021-04-28 | 2021-04-28 | 3 | 2021-05-24 | 21 | 2021-06-10 | 12 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-06-21 | 7 |  |  |  |  | 2021-04-23 | 2021-05-13 | 2021-05-26 | 23 | [7 empty] | 2021-08-16
120876953 | 827 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-04-23 | 2021-04-26 |  | 2021-04-26 | 2021-04-26 | 1 | 2021-05-12 | 13 | 2021-07-12 | 41 | [15 empty] | 2021-07-12 | 2021-07-30 | 14 | 2021-07-30 | 2021-08-11 | 8
120877425 | 828 | PGE | NEM | EXPNEM | Implementation | Solar PV | 69.457 |  | 2021-04-23 |  | 2021-05-05 | 2021-05-05 | 2021-05-05 | 8 | 2021-06-08 | 31 | 2021-06-22 | 10 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-06-29 | 5
120881225 | 829 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 32.505 |  | 2021-04-25 |  | 2021-05-06 | 2021-05-06 | 2021-05-06 | 8 | 2021-05-21 | 19 | 2021-06-09 | 12 | [25 empty] | 2021-04-25
120881315 | 830 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-04-25 | 2021-04-26 |  | 2021-04-26 | 2021-04-26 | 0 | 2021-05-12 | 12 | 2021-07-02 | 36 | [15 empty] | 2021-07-02 | 2021-07-23 | 14 | 2021-07-23 | 2021-08-11 | 13
120883454 | 831 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 41.566 |  | 2021-04-26 |  | 2021-08-03 | 2021-04-27 | 2021-04-27 | 1 | 2021-08-09 | 73 | 2021-08-25 | 12 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | 2021-09-07 | 8 |  |  |  |  | 2021-05-07 | 2021-08-25 | 2021-09-08 | 85
120884810 | 832 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 58.082 |  | 2021-04-26 |  | 2021-05-12 | 2021-05-07 | 2021-05-07 | 9 | 2021-05-13 | 13 | 2021-05-17 | 2 | [15 empty] | 2021-05-17 | 2021-05-17 | 0 | 2021-05-17 | [7 empty] | 2021-05-17 | 2021-05-28 | 9
120885848 | 833 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 30.165 |  | 2021-04-26 |  | 2021-04-27 | 2021-04-27 | 2021-04-27 | 1 | 2021-05-05 | 7 | 2021-05-21 | 12 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-08-31 | 70
120885849 | 834 | PGE | NEM | EXPNEM | Implementation | Solar PV | 530 |  | 2021-04-26 |  | 2021-05-07 | 2021-05-07 | 2021-05-07 | 9 | 2021-06-08 | 30 | 2021-06-24 | 12 | [15 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-24 | 2021-08-17 | 37 | [5 empty] | 2021-08-17 | 2021-08-31 | 10
120886344 | 835 | PGE | NEM | EXPNEM | Implementation | Solar PV | 520 |  | 2021-04-26 |  | 2021-05-10 | 2021-05-10 | 2021-05-10 | 10 | 2021-05-18 | 16 | 2021-06-07 | 13 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-08-25 | 56 | [5 empty] | 2021-06-09 | 2021-06-17 | 6
120887117 | 836 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 2119.8 |  | 2021-04-26 | 2021-04-29 |  | 2021-04-29 | 2021-04-29 | 3 | 2021-05-26 | 22 | 2021-07-01 | 25 | 2021-07-22 | 2021-08-25 | 24 | [12 empty] | 2021-09-15 | [9 empty] | 2021-04-26
120887228 | 837 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2021-04-26 |  |  | 2021-04-27 | 2021-04-27 | 1 | 2021-04-27 | 1 | 2021-05-10 | 9 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | [6 empty] | 2021-04-26 | 2021-05-06 | 2021-05-25 | 21
120887293 | 838 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 40.591 |  | 2021-04-26 |  |  | 2021-05-07 | 2021-05-07 | 9 | 2021-05-07 | 9 | 2021-05-24 | 11 | [15 empty] | 2021-05-07 | 2021-05-07 | 0 | 2021-05-07 | 2021-05-11 | 2 | [12 empty] | 2021-08-17 | 2021-08-24 | 5 | [15 empty] | 2021-08-17 | 2021-08-17 | 0 | 2021-08-24 |  | 2021-08-25 | 1
120887432 | 839 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 58.738 |  | 2021-04-26 |  |  | 2021-04-27 | 2021-04-27 | 1 | 2021-04-27 | 1 | 2021-05-10 | 9 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | [6 empty] | 2021-04-26 | 2021-05-06 | 2021-05-25 | 21
120887512 | 840 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 46.99 |  | 2021-04-26 |  |  | 2021-04-27 | 2021-04-27 | 1 | 2021-04-27 | 1 | 2021-05-10 | 9 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | [6 empty] | 2021-04-26 | 2021-05-10 | 2021-05-26 | 22
120888831 | 841 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 34.179 |  | 2021-04-27 |  | 2021-05-07 | 2021-04-28 | 2021-04-28 | 1 | 2021-05-18 | 15 | 2021-06-09 | 15 | 2021-06-09 | 2021-07-08 | 20 | 2021-07-21 | 2021-08-18 | 20 | 2021-08-18 | [18 empty] | 2021-04-27 |  |  |  | 2021-05-25
120889138 | 842 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 65.188 |  | 2021-04-27 |  | 2021-06-15 | 2021-04-28 | 2021-04-28 | 1 | 2021-06-17 | 36 | 2021-07-09 | 15 | [15 empty] | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12
120889784 | 843 | PGE | NEM | EXPNEM | Implementation | Solar PV | 192 |  | 2021-04-27 |  | 2021-05-03 | 2021-05-03 | 2021-05-03 | 4 | 2021-05-10 | 9 | 2021-06-03 | 17 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-08-25 | 58 |  |  |  |  | 2021-04-27
120890108 | 844 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-04-27 |  |  | 2021-05-03 | 2021-05-03 | 4 | 2021-05-03 | 4 | 2021-05-20 | 13 | [33 empty] | 2021-05-21 | 2021-05-21 | 0 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 |  | 2021-05-21 | 0
120890366 | 845 | PGE | NEM | EXPNEM | Implementation | Solar PV | 410.518 |  | 2021-04-27 |  | 2021-05-03 | 2021-05-03 | 2021-05-03 | 4 | 2021-06-16 | 35 | 2021-06-28 | 8 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-08-16 | 34 |  |  |  |  | 2021-04-27 | 2021-08-16 | 2021-08-27 | 86
120890711 | 846 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 177.127 |  | 2021-04-27 |  | 2021-05-11 | 2021-05-11 | 2021-05-11 | 10
120890756 | 847 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 206.6 |  | 2021-04-27 |  |  | 2021-05-10 | 2021-05-10 | 9 | 2021-05-10 | 9 | 2021-08-16 | 68 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | [6 empty] | 2021-04-27
120891405 | 848 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 206.358 |  | 2021-04-27 |  | 2021-05-10 | 2021-05-10 | 2021-05-10 | 9 | [29 empty] | 2021-04-27
120891861 | 849 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 36 |  | 2021-04-27 |  |  | 2021-04-28 | 2021-04-28 | 1 | 2021-04-28 | 1 | 2021-05-11 | 9 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | [6 empty] | 2021-04-27 | 2021-05-06 | 2021-05-25 | 20
120892017 | 850 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 36 |  | 2021-04-27 |  | 2021-04-29 | 2021-04-29 | 2021-04-29 | 2 | 2021-04-29 | 2 | 2021-05-11 | 8 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | [6 empty] | 2021-04-27 | 2021-04-29 | 2021-05-10 | 9
120893156 | 851 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 240 |  | 2021-04-27 |  |  | 2021-05-03 | 2021-05-03 | 4 | 2021-05-03 | 4 | 2021-05-20 | 13 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20
120894133 | 852 | PGE | NEM | EXPNEM | Implementation | Solar PV | 56.869 |  | 2021-04-28 |  | 2021-05-10 | 2021-05-03 | 2021-05-03 | 3 | 2021-05-19 | 15 | 2021-06-02 | 9 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-08-02 | 42
120896852 | 853 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-04-28 | 2021-05-03 |  | 2021-04-28 | 2021-04-28 | 0 | 2021-05-26 | 20 | 2021-06-30 | 24 | [15 empty] | 2021-06-30 | 2021-07-20 | 13 | 2021-07-20 | 2021-08-30 | 29 |  |  |  |  | 2021-04-28 | 2021-06-18 | 2021-06-21 | 37
120897331 | 854 | PGE | Non-NEM | NEMFC | IA in Progress | FUCE | 262.5 |  | 2021-04-28 |  | 2021-05-12 | 2021-05-12 | 2021-05-12 | 10 | 2021-07-09 | 50 | 2021-09-02 | 39 | [15 empty] | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02 | [6 empty] | 2021-04-28 | 2021-07-09 | 2021-07-19 | 56
120897465 | 855 | PGE | NEM | EXPNEM | Implementation | Solar PV | 34.082 |  | 2021-04-28 |  | 2021-05-03 | 2021-05-03 | 2021-05-03 | 3 | 2021-05-20 | 16 | 2021-06-10 | 14 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-06-17 | 5 |  |  |  |  | 2021-04-28 |  |  |  | 2021-08-26
120897470 | 856 | PGE | Non-NEM | Non-Export | Study in Progress | Storage | 929.5 |  | 2021-04-28 | 2021-05-03 |  | 2021-05-03 | 2021-05-03 | 3 | 2021-05-26 | 20 | 2021-06-17 | 15 | 2021-07-23 | 2021-08-20 | 20 | 2021-09-03 | 2021-09-27 | 15 | 2021-09-27 | [18 empty] | 2021-04-28 | 2021-05-27 | 2021-05-27 | 21
120897509 | 857 | PGE | NEM | NEM Paired Storage | Study in Progress | ENGN, Solar PV, Storage | 3443.5 |  | 2021-04-28 |  | 2021-08-10 | 2021-05-06 | 2021-05-06 | 6 | 2021-08-23 | 81 | 2021-09-13 | 14 | 2021-09-23
120897689 | 858 | PGE | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-04-28 |  | 2021-05-21 | 2021-04-29 | 2021-04-29 | 1 | 2021-05-28 | 22 | 2021-06-02 | 2 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-06-08 | 4 | [12 empty] | 2021-07-15 | 2021-07-29 | 10 | [15 empty] | 2021-07-15 | 2021-07-21 | 4 | 2021-07-29 |  | 2021-08-04 | 4
120897974 | 859 | PGE | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 2071.458 |  | 2021-04-28 | 2021-05-03 |  | 2021-05-03 | 2021-05-03 | 3 | 2021-05-26 | 20
120897990 | 860 | PGE | NEM | EXPNEM | Commercial | Solar PV | 53.84 |  | 2021-04-28 |  | 2021-04-29 | 2021-04-29 | 2021-04-29 | 1 | 2021-05-06 | 6 | 2021-05-25 | 13 | [15 empty] | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-05-27 | 2 | [5 empty] | 2021-06-02 | 2021-06-15 | 9 |  |  |  |  | 2021-08-06 | 2021-08-20 | 10 | [15 empty] | 2021-08-06 | 2021-08-20 | 10 | 2021-08-20 |  | 2021-08-27 | 5
120899666 | 861 | PGE | NEM | EXPNEM | Commercial | Solar PV | 31.024 |  | 2021-04-29 |  | 2021-05-11 | 2021-04-29 | 2021-04-29 | 0 | 2021-06-08 | 27 | 2021-06-29 | 15 | [33 empty] | 2021-06-29 | 2021-07-15 | 11 | [15 empty] | 2021-06-29 | 2021-07-22 | 16 | 2021-07-15 |  | 2021-07-20 | 3
120900572 | 862 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-04-29 |  |  | 2021-05-11 | 2021-05-11 | 8 | 2021-05-13 | 10 | [5 empty] | 2021-05-13 | 2021-06-11 | 20 | 2021-06-11 |  |  |  | 2021-09-03
120900752 | 863 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 45.653 |  | 2021-04-29 |  | 2021-05-10 | 2021-05-10 | 2021-05-10 | 7
120904132 | 864 | PGE | NEM | EXPNEM | Commercial | Solar PV | 187.5 |  | 2021-04-29 |  | 2021-05-10 | 2021-04-29 | 2021-04-29 | 0 | 2021-05-12 | 9 | 2021-05-28 | 12 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | 2021-06-09 | 7 |  |  |  |  | 2021-04-29 | 2021-05-10 | 2021-05-26 | 19 |  |  |  |  | 2021-09-01 | 2021-09-09 | 5 | [15 empty] | 2021-09-01 | 2021-09-02 | 1 | 2021-09-09 |  | 2021-09-16 | 5
120904630 | 865 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 180 |  | 2021-04-29 |  | 2021-05-10 | 2021-05-10 | 2021-05-10 | 7 | 2021-08-02 | 65 | 2021-08-18 | 12 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | [6 empty] | 2021-04-29
120905190 | 866 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 58.738 |  | 2021-04-29 |  |  | 2021-04-30 | 2021-04-30 | 1 | 2021-04-30 | 1 | 2021-05-11 | 7 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11
120905379 | 867 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 37.5 |  | 2021-04-29 |  | 2021-05-12 | 2021-05-12 | 2021-05-12 | 9 | 2021-05-18 | 13 | 2021-06-03 | 11 | [15 empty] | 2021-06-03 | 2021-06-09 | 4 | 2021-06-09 | 2021-06-11 | 2 |  |  |  |  | 2021-04-29 | 2021-06-04 | 2021-06-16 | 33 |  |  |  |  | 2021-09-13 | 2021-09-21 | 6 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-21 | 2021-09-22 |  | 1 |  |  | 101 |  | 101
120908082 | 868 | PGE | NEM | EXPNEM | Commercial | Solar PV | 50 |  | 2021-04-30 |  | 2021-05-06 | 2021-04-30 | 2021-04-30 | 0 | 2021-05-06 | 4 | 2021-05-24 | 12 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24 | 2021-06-01 | 5 |  |  |  |  | 2021-04-30 | 2021-05-06 | 2021-05-25 | 17 |  |  |  |  | 2021-06-21 | 2021-06-29 | 6 | [15 empty] | 2021-06-21 | 2021-06-22 | 1 | 2021-06-29 |  | 2021-07-07 | 5
120908889 | 869 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 156 |  | 2021-04-30 |  |  | 2021-05-04 | 2021-05-04 | 2 | 2021-05-05 | 3 | 2021-05-19 | 10 | 2021-05-19 | 2021-06-23 | 24 | 2021-06-23 | 2021-07-16 | 16 | 2021-07-16 |  |  |  | 2021-09-23 | [14 empty] | 2021-04-30 | 2021-05-18 | 2021-05-25 | 17
120910554 | 870 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 540 |  | 2021-04-30 |  | 2021-07-20 | 2021-05-03 | 2021-05-03 | 1 | 2021-08-02 | 64 | 2021-08-18 | 12 | 2021-08-18 | 2021-09-28 | 28 | 2021-09-28 | [21 empty] | 2021-04-30
120918853 | 871 | PGE | Non-NEM | Non-Export | Commercial | Solar PV | 65.7 |  | 2021-05-02 | 2021-05-04 |  | 2021-05-04 | 2021-05-04 | 1 | 2021-05-12 | 7 | 2021-05-13 | 1 | [15 empty] | 2021-05-13 | 2021-05-24 | 7 | 2021-05-24 | 2021-06-29 | 25 | [12 empty] | 2021-07-20 | 2021-07-22 | 2 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-22 |  | 2021-07-22 | 0
120920307 | 872 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 40 |  | 2021-05-03 |  | 2021-05-24 | 2021-05-11 | 2021-05-11 | 6 | 2021-06-17 | 32 | 2021-06-18 | 1 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24 | [10 empty] | 2021-07-08
120924554 | 873 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 132 |  | 2021-05-03 |  | 2021-05-06 | 2021-07-08 | 2021-05-06 | 3 | 2021-07-08 | 46 | 2021-07-28 | 14
120924866 | 874 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-05-03 |  |  | 2021-05-04 | 2021-05-04 | 1 | 2021-05-04 | 1 | 2021-05-20 | 12 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2021-05-24 | 2 |  |  |  |  | 2021-05-03 | 2021-05-14 | 2021-05-28 | 19 |  |  |  |  | 2021-09-29 | [17 empty] | 2021-09-29 | 2021-09-29 | 0
120927287 | 875 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 95.8 |  | 2021-05-04 |  | 2021-05-13 | 2021-05-13 | 2021-05-13 | 7 | 2021-05-21 | 13 | 2021-06-07 | 10 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [6 empty] | 2021-05-04 | 2021-05-21 | 2021-06-03 | 21
120929506 | 876 | PGE | NEM | EXPNEM | Commercial | Solar PV | 140.742 |  | 2021-05-04 |  |  | 2021-05-14 | 2021-05-14 | 8 | 2021-05-14 | 8 | 2021-06-02 | 12 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-06-24 | 16 |  |  |  |  | 2021-05-04 | 2021-05-18 | 2021-05-28 | 18 |  |  |  |  | 2021-07-12 | 2021-07-19 | 5 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-19 |  | 2021-07-19 | 0
120929636 | 877 | PGE | Non-NEM | Non-Export | Withdrawn | Storage | 140 |  | 2021-05-04 | 2021-05-04 |  | 2021-05-04 | 2021-05-04 | 0 | 2021-05-26 | 16 | 2021-06-21 | 17 | 2021-07-16 | 2021-08-19 | 24 | [12 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | [6 empty] | 2021-05-04 | 2021-05-28 | 2021-06-15 | 29 | [19 empty] | 2021-08-25
120929967 | 878 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-05-04 |  |  | 2021-05-12 | 2021-05-12 | 6 | 2021-05-12 | 6 | 2021-05-13 | 1 | [33 empty] | 2021-06-08 | 2021-08-02 | 38 | [15 empty] | 2021-06-08 | 2021-07-23 | 32 | 2021-08-02 |  | 2021-08-03 | 1
120930410 | 879 | PGE | NEM | EXPNEM | Commercial | Solar PV | 118.695 |  | 2021-05-04 |  | 2021-05-10 | 2021-05-05 | 2021-05-05 | 1 | 2021-05-12 | 6 | 2021-05-19 | 5 | [15 empty] | 2021-05-19 | 2021-05-19 | 0 | 2021-05-19 | 2021-06-23 | 24 | [12 empty] | 2021-08-18 | 2021-09-16 | 20 | [15 empty] | 2021-08-18 | 2021-09-14 | 18 | 2021-09-16 |  | 2021-09-23 | 5
120931208 | 880 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 420 |  | 2021-05-04 | 2021-05-04 |  | 2021-05-04 | 2021-05-04 | 0 | 2021-05-26 | 16 | 2021-07-20 | 37 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20
120931541 | 881 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-05-04 |  | 2021-05-10 | 2021-05-10 | 2021-05-10 | 4 | 2021-05-10 | 4 | 2021-06-09 | 21 | [15 empty] | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | [6 empty] | 2021-05-04 |  |  |  | 2021-05-17
120932439 | 882 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 247.184 |  | 2021-05-04 |  | 2021-05-18 | 2021-05-18 | 2021-05-18 | 10 | 2021-07-19 | 52 | 2021-08-09 | 15 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | [10 empty] | 2021-08-02 | 2021-08-09 | 2021-08-09 | 5
120932558 | 883 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 185 |  | 2021-05-04 |  | 2021-05-18 | 2021-05-18 | 2021-05-18 | 10 | 2021-07-19 | 52 | 2021-08-16 | 20 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | [10 empty] | 2021-07-19 | 2021-08-16 | 2021-08-16 | 20
120932622 | 884 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 440 |  | 2021-05-04 |  | 2021-05-05 | 2021-05-05 | 2021-05-05 | 1 | 2021-05-07 | 3 | 2021-07-12 | 44 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-09-10 | 43 | [12 empty] | 2021-09-27 | [17 empty] | 2021-09-27 | 2021-09-27 | 0
120933067 | 885 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 49.179 |  | 2021-05-04 |  |  | 2021-05-12 | 2021-05-12 | 6 | 2021-05-20 | 12 | 2021-05-20 | 0 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2021-05-21 | 1
120935441 | 886 | PGE | NEM | NEMMT | Study in Progress | FUCE, Solar PV | 800 |  | 2021-05-05 |  | 2021-05-19 | 2021-05-19 | 2021-05-19 | 10 | 2021-09-13 | 90 | [27 empty] | 2021-05-05 | 2021-09-13 | 2021-09-20 | 95 | 2021-09-14
120935902 | 887 | PGE | NEM | EXPNEM | Implementation | Solar PV | 300 |  | 2021-05-05 |  | 2021-05-14 | 2021-05-14 | 2021-05-14 | 7 | 2021-05-14 | 7 | 2021-06-09 | 17 | [15 empty] | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | 2021-07-01 | 16 |  |  |  |  | 2021-05-05 |  |  |  | 2021-05-17
120939133 | 888 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 45.45 |  | 2021-05-05 |  | 2021-05-14 | 2021-05-14 | 2021-05-14 | 7
120942016 | 889 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 954.853 |  | 2021-05-06 |  |  | 2021-05-11 | 2021-05-11 | 3 | [29 empty] | 2021-05-06
120942653 | 890 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 86.4 |  | 2021-05-06 |  | 2021-05-10 | 2021-05-10 | 2021-05-10 | 2 | 2021-06-15 | 27 | 2021-06-29 | 10 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | [6 empty] | 2021-05-06 | 2021-06-15 | 2021-06-24 | 34
120946002 | 891 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 210 |  | 2021-05-06 | 2021-05-07 |  | 2021-05-07 | 2021-05-07 | 1 | 2021-05-26 | 14 | 2021-07-27 | 42 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-08-25 | 21
120948228 | 892 | PGE | Non-NEM | NEMFC | IA in Progress | FUCE | 2050 |  | 2021-05-07 |  |  | 2021-05-14 | 2021-05-14 | 5 | 2021-05-14 | 5 | 2021-08-13 | 63 | 2021-08-13 | 2021-09-02 | 14 | [12 empty] | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02 | [6 empty] | 2021-05-07 | [13 empty] | 2021-06-29
120949009 | 893 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 490 |  | 2021-05-07 | 2021-05-07 |  | 2021-05-07 | 2021-05-07 | 0 | 2021-05-26 | 13 | 2021-06-25 | 21 | [15 empty] | 2021-06-25 | 2021-06-28 | 1 | 2021-06-28 | [6 empty] | 2021-05-07 | 2021-05-27 | 2021-05-27 | 14
120949049 | 894 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.23 |  | 2021-05-07 |  |  | 2021-05-12 | 2021-05-12 | 3 | 2021-05-12 | 3 | 2021-05-13 | 1 | [19 empty] | 2021-09-15 | N/A | [12 empty] | 2021-09-16 | 2021-09-16 | 0 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 |  | 2021-09-16 | 0
120949585 | 895 | PGE | NEM | VNEMMASH | Withdrawn | Solar PV | 114.8 |  | 2021-05-07 |  | 2021-05-14 | 2021-05-14 | 2021-05-14 | 5 | [29 empty] | 2021-05-07
120949681 | 896 | PGE | NEM | SNEM | IA in Progress | ENGN, Solar PV | 39.477 |  | 2021-05-07 |  | 2021-08-05 | 2021-05-21 | 2021-05-21 | 10 | 2021-06-16 | 27 | 2021-06-29 | 9 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | [6 empty] | 2021-05-07 | 2021-06-16 | 2021-06-28 | 35
120950094 | 897 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1187.5 |  | 2021-05-07 | 2021-05-10 |  | 2021-05-10 | 2021-05-10 | 1 | 2021-05-19 | 8 | 2021-06-30 | 29 | 2021-07-20 | 2021-08-27 | 28 | [12 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | [6 empty] | 2021-05-07 | 2021-06-01 | 2021-06-15 | 26
120951103 | 898 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 61.126 |  | 2021-05-07 |  | 2021-05-14 | 2021-05-14 | 2021-05-14 | 5 | 2021-06-23 | 32 | 2021-07-15 | 15 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | [6 empty] | 2021-05-07 | 2021-09-16 | 2021-09-20 | 93 |  | 2021-09-25
120951527 | 899 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-05-07 |  | 2021-05-20 | 2021-05-12 | 2021-05-12 | 3 | 2021-05-26 | 13 | 2021-06-09 | 9 | [25 empty] | 2021-05-07 | 2021-05-20 | 2021-05-28 | 15 | [27 empty] | 2021-06-09
121004429 | 900 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 31.078 |  | 2021-05-10 |  | 2021-05-13 | 2021-05-13 | 2021-05-13 | 3
121007066 | 901 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 75.105 |  | 2021-05-10 |  | 2021-05-21 | 2021-05-10 | 2021-05-10 | 0 | 2021-05-27 | 13 | 2021-06-07 | 6 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-09-02 | 62 |  |  |  |  | 2021-05-10 | 2021-08-27 | 2021-09-09 | 85
121008816 | 902 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 120 |  | 2021-05-10 |  | 2021-05-28 | 2021-05-10 | 2021-05-10 | 0 | 2021-06-04 | 18 | 2021-06-17 | 9 | 2021-06-17 | 2021-07-22 | 24 | 2021-06-04 | 2021-09-01 | 62 | 2021-09-01 | [18 empty] | 2021-05-10 | 2021-05-28 | 2021-06-15 | 25
121011229 | 903 | PGE | NEM | SNEM | Application Review in Progress | Solar PV | 1603.8 |  | 2021-05-10 |  | 2021-05-18 | 2021-05-18 | 2021-05-18 | 6
121130249 | 904 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-05-10 |  | 2021-05-17 | 2021-05-13 | 2021-05-13 | 3 | 2021-05-20 | 8 | 2021-07-12 | 35 | [15 empty] | 2021-07-12 | 2021-07-15 | 3 | 2021-07-15 | 2021-07-16 | 1 |  |  |  |  | 2021-05-10 | 2021-06-10 | 2021-06-17 | 27 | [7 empty] | 2021-08-19 | 2021-10-11 | 36
121138825 | 905 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 171.802 |  | 2021-05-10 |  | 2021-05-12 | 2021-05-12 | 2021-05-12 | 2 | 2021-05-17 | 5 | 2021-06-09 | 16 | 2021-06-09 | 2021-07-08 | 20 | 2021-05-17 | 2021-08-17 | 64 | 2021-08-17 | [18 empty] | 2021-05-10 | 2021-05-12 | 2021-05-26 | 12
121187860 | 906 | PGE | NEM | EXPNEM | Commercial | Solar PV | 32.76 |  | 2021-05-11 |  | 2021-07-10 | 2021-05-14 | 2021-05-14 | 3 | 2021-07-16 | 46 | 2021-07-22 | 4 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | 2021-08-19 | 20 | [12 empty] | 2021-08-19 | [17 empty] | 2021-08-19 | 2021-08-19 | 0 |  |  | 2021-09-07
121188855 | 907 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 224.234 |  | 2021-05-11 |  | 2021-05-14 | 2021-05-14 | 2021-05-14 | 3
121189607 | 908 | PGE | NEM | NEMMT | Withdrawn | FUCE, Storage | 306.488 |  | 2021-05-11 | 2021-05-17 |  |  | 2021-05-17 | 4 | 2021-06-15 | 24
121190299 | 909 | PGE | NEM | EXPNEM | Implementation | Solar PV | 51.478 |  | 2021-05-11 |  | 2021-06-30 | 2021-05-18 | 2021-05-18 | 5 | 2021-06-28 | 33 | 2021-08-06 | 28 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | 2021-08-17 | 7 | [12 empty] | 2021-08-20 | 2021-08-27 | 5 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-27 | 2021-08-30 |  | 1 |  |  | 77 |  | 77
121190694 | 910 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 39.976 |  | 2021-05-11 |  | 2021-05-14 | 2021-05-14 | 2021-05-14 | 3 | 2021-05-14 | 3 | 2021-07-20 | 45 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | [6 empty] | 2021-05-11 | 2021-09-17 | 2021-09-22 | 93
121191139 | 911 | PGE | NEM | NEM Paired Storage | Study in Progress | ENGN, Solar PV, Storage | 6080 |  | 2021-05-11 | 2021-05-13 |  | 2021-05-13 | 2021-05-13 | 2 | 2021-05-26 | 11 | [5 empty] | 2021-05-26 | 2021-06-25 | 21 | 2021-06-25 | 2021-07-12 | 10 | 2021-07-26 |  |  | 2021-07-12 | 2021-07-12 | 0 | [10 empty] | 2021-05-11
121191864 | 912 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2360 |  | 2021-05-11 | 2021-05-13 |  | 2021-05-13 | 2021-05-13 | 2 | 2021-05-26 | 11 | [5 empty] | 2021-05-26 | 2021-08-23 | 61 | 2021-08-23 | 2021-08-23 | 0 | 2021-09-02 |  |  | 2021-08-23 | 2021-08-23 | 0 | [10 empty] | 2021-05-11
121317816 | 913 | PGE | NEM | EXPNEM | Implementation | Solar PV | 99.9 |  | 2021-05-12 |  |  | 2021-05-19 | 2021-05-19 | 5 | 2021-05-20 | 6 | 2021-05-25 | 3 | [15 empty] | 2021-06-04 | 2021-06-04 | 0 | 2021-06-04 | 2021-06-07 | 1 |  |  |  |  | 2021-05-12 | 2021-05-20 | 2021-05-28 | 12
121318427 | 914 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 57.054 |  | 2021-05-12 |  | 2021-05-21 | 2021-05-21 | 2021-05-21 | 7 | 2021-06-17 | 25 | 2021-06-30 | 9 | [15 empty] | 2021-06-30 | 2021-07-21 | 14 | 2021-07-21
121318645 | 915 | PGE | NEM | VNEMSOMAH | Implementation | Solar PV | 30.402 |  | 2021-05-12 |  | 2021-05-26 | 2021-05-26 | 2021-05-26 | 10 | 2021-06-08 | 18 | 2021-06-24 | 12 | [15 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-24 | 2021-07-07 | 8 |  |  |  |  | 2021-05-12 | 2021-06-11 | 2021-06-15 | 23
121319468 | 916 | PGE | NEM | EXPNEM | Commercial | Solar PV | 125 |  | 2021-05-12 |  | 2021-05-25 | 2021-05-14 | 2021-05-14 | 2 | 2021-05-25 | 9 | 2021-06-10 | 11 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-06-14 | 2 | [12 empty] | 2021-09-02 | 2021-09-14 | 7 | [15 empty] | 2021-09-02 | 2021-09-03 | 1 | 2021-09-14 |  | 2021-09-21 | 5
121321905 | 917 | PGE | NEM | EXPNEM | Implementation | Solar PV | 199.172 |  | 2021-05-12 |  | 2021-05-24 | 2021-05-24 | 2021-05-24 | 8 | 2021-06-07 | 17 | 2021-06-16 | 7 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | 2021-07-06 | 13 |  |  |  |  | 2021-05-12 | 2021-06-07 | 2021-06-16 | 24
121322442 | 918 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 180 |  | 2021-05-12 |  | 2021-05-17 | 2021-05-17 | 2021-05-17 | 3 | 2021-05-17 | 3 | 2021-09-23 | 90 | [15 empty] | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | [6 empty] | 2021-05-12
121322443 | 919 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 900 |  | 2021-05-12 | 2021-05-18 |  | 2021-05-17 | 2021-05-17 | 3 | 2021-06-23 | 29 | [5 empty] | 2021-07-05 | 2021-08-10 | 25 | 2021-08-10 | [5 empty] | 2021-08-10 | 2021-08-13 | 3
121322455 | 920 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 420 |  | 2021-05-12 | 2021-05-13 |  | 2021-05-13 | 2021-05-13 | 1 | 2021-06-02 | 14 | 2021-09-09 | 69
121323269 | 921 | PGE | NEM | VNEM | Implementation | Solar PV, Storage | 54.717 |  | 2021-05-12 |  | 2021-06-09 | 2021-05-27 | 2021-05-27 | 11 | 2021-07-01 | 35 | 2021-08-06 | 25 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | 2021-08-09 | 1 | [5 empty] | 2021-08-04 | 2021-08-06 | 2 |  | 2021-08-06 | 2021-08-06 | 0 | 2021-09-25 | [17 empty] | 2021-09-25 | 2021-09-27 | 0
121323768 | 922 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 353.075 |  | 2021-05-13 |  | 2021-05-27 | 2021-05-27 | 2021-05-27 | 10
121324169 | 923 | PGE | NEM | EXPNEM | Commercial | Solar PV | 247.518 |  | 2021-05-13 |  | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2 | 2021-05-17 | 2 | 2021-08-21 | 67 | [15 empty] | 2021-08-21 | 2021-08-21 | 0 | 2021-08-21 | 2021-08-24 | 1 |  |  |  |  | 2021-05-13 | 2021-05-19 | 2021-05-28 | 11 |  |  |  |  | 2021-09-01 | 2021-09-09 | 5 | [15 empty] | 2021-09-01 | 2021-09-01 | 0 | 2021-09-09 |  | 2021-09-21 | 8
121324261 | 924 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 516.6 |  | 2021-05-13 |  | 2021-05-27 | 2021-05-27 | 2021-05-27 | 10 | 2021-06-19 | 25 | 2021-07-12 | 14 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [10 empty] | 2021-06-29 | 2021-07-12 | 2021-07-12 | 8
121325067 | 925 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 19692.28 |  | 2021-05-13 |  | 2021-06-24 | 2021-05-13 | 2021-05-13 | 0 | 2021-06-18 | 25
121325832 | 926 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 1212 |  | 2021-05-13 | 2021-05-27 |  | 2021-05-26 | 2021-05-26 | 9 | 2021-06-09 | 18 | [5 empty] | 2021-06-14 | 2021-07-12 | 19 | 2021-07-12 | 2021-07-12 | 0 | 2021-08-03 |  |  | 2021-07-12 | 2021-07-12 | 0 | [10 empty] | 2021-05-13
121326648 | 928 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 98.938 |  | 2021-05-13 |  | 2021-05-27 | 2021-05-27 | 2021-05-27 | 10
121327892 | 929 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 644.705 |  | 2021-05-13 |  | 2021-05-18 | 2021-05-18 | 2021-05-18 | 3 | 2021-05-21 | 6 | 2021-06-04 | 9 | 2021-06-04 | 2021-07-02 | 20 | [12 empty] | 2021-07-02 | 2021-07-06 | 1 | 2021-07-06 | 2021-07-13 | 5 |  |  |  |  | 2021-05-13 | 2021-09-27
121328758 | 930 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 50.23 |  | 2021-05-13 |  | 2021-05-18 | 2021-05-18 | 2021-05-18 | 3 | 2021-05-27 | 10 | 2021-06-01 | 2 | [33 empty] | 2021-06-01 | 2021-06-01 | 0 | [15 empty] | 2021-06-01 |  |  | 2021-06-01 |  | 2021-06-01 | 0
121329814 | 931 | PGE | NEM | EXPNEM | Commercial | Solar PV | 72 |  | 2021-05-13 |  | 2021-05-27 | 2021-05-27 | 2021-05-27 | 10 | 2021-09-01 | 77 | 2021-09-15 | 9 | [15 empty] | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | 2021-09-16 | 1 | [12 empty] | 2021-09-20 | 2021-09-28 | 6 | [15 empty] | 2021-09-20 | 2021-09-21 | 1 | 2021-09-28 |  | 2021-09-28 | 0
121333375 | 932 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 641.076 |  | 2021-05-14 |  |  | 2021-05-18 | 2021-05-18 | 2 | 2021-05-18 | 2 | 2021-08-19 | 65 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-09-14 | 17 |  |  |  |  | 2021-05-14 | 2021-09-29
121333652 | 933 | PGE | Non-NEM | Non-Export | Withdrawn | Solar PV | 44.66 |  | 2021-05-14 | 2021-05-20 |  | 2021-05-17 | 2021-05-17 | 1 | 2021-06-02 | 12
121333662 | 934 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 985 |  | 2021-05-14 | 2021-05-17 |  | 2021-05-17 | 2021-05-17 | 1 | 2021-05-26 | 8 | 2021-08-02 | 46 | 2021-08-18 | 2021-09-17 | 21 | [12 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17
121334398 | 935 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 4252.742 |  | 2021-05-14 | 2021-05-17 |  | 2021-05-17 | 2021-05-17 | 1 | 2021-05-26 | 8 | [5 empty] | 2021-06-14 | 2021-07-27 | 30 | 2021-07-27 | 2021-08-02 | 4 | 2021-08-17 |  |  | 2021-08-02 | 2021-08-16 | 10
121334909 | 936 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 865.259 |  | 2021-05-14 |  | 2021-05-28 | 2021-05-28 | 2021-05-28 | 10 | 2021-06-14 | 20 | 2021-07-01 | 13 | 2021-07-01 | 2021-07-30 | 20 | [12 empty] | 2021-07-30 | 2021-07-30 | 0 | 2021-07-30 | [7 empty] | 2021-07-23 | 2021-08-05 | 9 | 2021-07-09
121335540 | 937 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-05-14 |  | 2021-05-24 | 2021-05-24 | 2021-05-24 | 6 | 2021-05-28 | 10 | 2021-06-07 | 5 | [15 empty] | 2021-06-07 | 2021-06-16 | 7 | 2021-06-16 | [6 empty] | 2021-05-14 | 2021-05-28 | 2021-06-15 | 21
121336530 | 938 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 480 |  | 2021-05-14 |  | 2021-06-29 | 2021-06-14 | 2021-06-14 | 20 | 2021-07-09 | 38 | 2021-07-26 | 11 | 2021-07-26 | 2021-08-30 | 25 | 2021-08-31 | 2021-09-21 | 14 | 2021-09-21 | [19 empty] | 2021-07-09 | 2021-07-19 | 6
121345569 | 939 | PGE | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 40.75 |  | 2021-05-17 |  | 2021-05-26 | 2021-05-19 | 2021-05-19 | 2 | 2021-09-27 | 92 | 2021-09-28 | 1
121346000 | 940 | PGE | NEM | NEMMT | Study in Progress | ENGN, Solar PV, Storage | 985 |  | 2021-05-17 |  |  | 2021-05-24 | 2021-05-24 | 5 | 2021-05-24 | 5 | [5 empty] | 2021-05-24 | 2021-06-15 | 15 | 2021-06-15 | 2021-07-01 | 12 | 2021-08-04 |  |  | 2021-07-01 | 2021-07-01 | 0
121347262 | 941 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 151.403 |  | 2021-05-17 |  | 2021-06-10 | 2021-05-20 | 2021-05-20 | 3 | 2021-06-22 | 25 | 2021-07-12 | 13 | 2021-07-12 | 2021-08-11 | 22 | [12 empty] | 2021-08-11 | 2021-08-11 | 0 | 2021-08-11 | 2021-09-16 | 25 |  |  |  |  | 2021-05-17 | 2021-06-05 | 2021-06-16 | 21
121347821 | 942 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 75 |  | 2021-05-17 |  |  | 2021-05-18 | 2021-05-18 | 1 | 2021-05-18 | 1 | 2021-06-15 | 19 | [15 empty] | 2021-06-15 | 2021-06-17 | 2 | 2021-06-17 | 2021-06-17 | 0 |  |  |  |  | 2021-05-17 | 2021-05-18 | 2021-05-28 | 9
121351959 | 943 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 50 |  | 2021-05-18 |  | 2021-06-10 | 2021-05-20 | 2021-05-20 | 2
121351984 | 944 | PGE | NEM | EXPNEM | Commercial | Solar PV | 47.351 |  | 2021-05-18 |  | 2021-05-18 | 2021-05-18 | 2021-05-18 | 0 | 2021-06-05 | 12 | 2021-06-21 | 10 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-25 | 4 | [12 empty] | 2021-09-10 | 2021-09-20 | 6 | [15 empty] | 2021-09-10 | 2021-09-12 | 0 | 2021-09-20 |  | 2021-09-27 | 5
121351986 | 945 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 64.643 |  | 2021-05-18 |  | 2021-05-25 | 2021-05-25 | 2021-05-25 | 5 | 2021-06-29 | 29 | 2021-08-05 | 26 | [15 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | [6 empty] | 2021-05-18 | 2021-06-04 | 2021-06-16 | 20 |  | 2021-06-29 | 2021-06-29 | 0
121352161 | 946 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 53.25 |  | 2021-05-18 |  | 2021-05-25 | 2021-05-25 | 2021-05-25 | 5 | 2021-06-30 | 30 | 2021-07-22 | 15 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | [6 empty] | 2021-05-18 | 2021-06-04 | 2021-06-16 | 20 |  | 2021-06-30 | 2021-06-30 | 0
121352351 | 947 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 41.375 |  | 2021-05-18 |  | 2021-06-02 | 2021-06-02 | 2021-06-02 | 10 | 2021-06-30 | 30 | 2021-08-05 | 25 | [15 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | [6 empty] | 2021-05-18 |  |  |  | 2021-07-23
121352364 | 948 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 55.628 |  | 2021-05-18 |  | 2021-06-02 | 2021-06-02 | 2021-06-02 | 10 | 2021-06-30 | 30 | 2021-08-12 | 30 | [15 empty] | 2021-08-12 | 2021-08-12 | 0 | 2021-08-12 | [6 empty] | 2021-05-18 |  |  |  | 2021-07-23 | 2021-08-12 | 2021-08-12 | 14
121352451 | 949 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 70.798 |  | 2021-05-18 |  | 2021-06-01 | 2021-06-01 | 2021-06-01 | 9 | 2021-06-29 | 29 | 2021-07-21 | 15 | [15 empty] | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | [6 empty] | 2021-05-18 |  |  |  | 2021-07-19
121352460 | 950 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 54.229 |  | 2021-05-18 |  | 2021-06-02 | 2021-06-02 | 2021-06-02 | 10 | 2021-06-29 | 29 | 2021-08-05 | 26 | [15 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | [6 empty] | 2021-05-18 |  |  |  | 2021-07-19
121353897 | 951 | PGE | NEM | EXPNEM | Commercial | Solar PV | 74.573 |  | 2021-05-18 |  | 2021-06-02 | 2021-06-02 | 2021-06-02 | 10 | 2021-06-28 | 28 | [17 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-08-09 | 10 |  |  |  |  | 2021-05-18 |  |  |  | 2021-06-16 |  |  |  | 2021-07-19 | 2021-07-26 | 5 | [15 empty] | 2021-07-19 | 2021-07-19 | 0 | 2021-07-26 |  | 2021-08-09 | 10
121354209 | 952 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 263.872 |  | 2021-05-18 |  | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2 | 2021-05-26 | 6 | 2021-06-07 | 7 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07
121354483 | 953 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 99.9 |  | 2021-05-18 |  | 2021-07-30 | 2021-05-20 | 2021-05-20 | 2 | 2021-08-04 | 54
121355803 | 954 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 630 |  | 2021-05-18 |  |  | 2021-06-02 | 2021-06-02 | 10 | 2021-06-02 | 10 | 2021-07-13 | 28 | 2021-07-30 | 2021-09-07 | 26 | [16 empty] | 2021-06-30 | N/A |  |  |  |  | 2021-05-18 | 2021-06-09 | 2021-06-09 | 15
121360523 | 955 | PGE | NEM | EXPNEM | Implementation | Solar PV | 53.289 |  | 2021-05-19 |  | 2021-06-17 | 2021-06-17 | 2021-06-17 | 20 | 2021-06-18 | 21 | 2021-07-01 | 9 | [15 empty] | 2021-07-01 | 2021-07-07 | 3 | 2021-07-07 | 2021-07-07 | 0 |  |  |  |  | 2021-05-19 | 2021-05-27 | 2021-06-07 | 12
121361569 | 956 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 37.306 |  | 2021-05-19 |  | 2021-05-20 | 2021-05-20 | 2021-05-20 | 1 | 2021-06-03 | 10 | 2021-06-21 | 12 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-09-16 | 61 | [5 empty] | 2021-09-30
121361989 | 957 | PGE | NEM | EXPNEM | Implementation | Solar PV | 31.024 |  | 2021-05-19 |  | 2021-06-24 | 2021-05-27 | 2021-05-27 | 6 | 2021-06-25 | 26 | 2021-07-12 | 10 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-07-12 | 0
121363542 | 958 | PGE | NEM | EXPNEM | Commercial | Solar PV | 80.637 |  | 2021-05-19 |  | 2021-05-27 | 2021-05-21 | 2021-05-21 | 2 | 2021-06-05 | 11 | 2021-06-23 | 12 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-07-08 | 10 | [5 empty] | 2021-07-30 | 2021-08-13 | 10 |  |  |  |  | 2021-08-10 | 2021-08-13 | 3 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-13 |  | 2021-08-23 | 6
121363583 | 959 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-05-19 |  | 2021-06-10 | 2021-06-04 | 2021-06-04 | 11 | 2021-06-21 | 22 | 2021-07-12 | 14 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-07-15 | 3 |  |  |  |  | 2021-05-19 | 2021-07-12 | 2021-07-19 | 41
121364335 | 960 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 929.5 |  | 2021-05-19 | 2021-05-20 |  | 2021-05-20 | 2021-05-20 | 1 | 2021-06-23 | 24 | 2021-07-26 | 22 | 2021-08-02 | 2021-08-27 | 19 | [12 empty] | 2021-08-27 | 2021-09-01 | 3 | 2021-09-01
121365736 | 961 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 74.731 |  | 2021-05-20 |  | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2 | 2021-06-01 | 7 | 2021-06-15 | 10 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-15 | [6 empty] | 2021-05-20 | 2021-06-01 | 2021-06-15 | 17
121366170 | 962 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 248.292 |  | 2021-05-20 |  | 2021-06-03 | 2021-06-03 | 2021-06-03 | 9 | 2021-07-21 | 42 | 2021-08-04 | 10 | [15 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | [6 empty] | 2021-05-20
121367566 | 963 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.53 |  | 2021-05-20 |  | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2 | 2021-06-15 | 17 | 2021-07-01 | 12 | [15 empty] | 2021-07-01 | 2021-07-02 | 1 | 2021-07-02 | [6 empty] | 2021-05-20 | 2021-06-15 | 2021-06-24 | 24
121367736 | 964 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 54.72 |  | 2021-05-20 |  | 2021-06-15 | 2021-05-24 | 2021-05-24 | 2 | 2021-06-17 | 19 | 2021-07-22 | 24 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | [6 empty] | 2021-05-20 | 2021-06-04 | 2021-06-07 | 11
121368174 | 965 | PGE | Non-NEM | Non-Export | Application Review in Progress | Storage | 508.95 |  | 2021-05-20 | 2021-05-20 |  | 2021-05-20 | 2021-05-20 | 0 | 2021-06-16 | 18
121368484 | 966 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 |  | 2021-05-20 |  | 2021-08-26 | 2021-05-20 | 2021-05-20 | 0
121368559 | 967 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-05-20 |  | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2 | 2021-06-03 | 9 | 2021-06-17 | 10 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-06-17 | 0 |  |  |  |  | 2021-05-20 | 2021-06-03 | 2021-06-15 | 17 |  |  |  |  | 2021-09-16 | 2021-09-24 | 6 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-24
121368827 | 968 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 57.42 |  | 2021-05-20 |  | 2021-06-01 | 2021-05-24 | 2021-05-24 | 2 | 2021-06-05 | 10 | 2021-07-21 | 31 | [15 empty] | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21
121369425 | 969 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 113.3 |  | 2021-05-20 |  | 2021-06-03 | 2021-05-27 | 2021-05-27 | 5
121369594 | 970 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-05-20 |  | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2 | 2021-06-01 | 7 | 2021-06-17 | 12 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-08-26 | 49 |  |  |  |  | 2021-05-20 | 2021-06-05 | 2021-06-16 | 18
121369966 | 971 | PGE | NEM | NEMMT | IA in Progress | Solar PV | 250 |  | 2021-05-20 |  | 2021-06-05 | 2021-06-05 | 2021-06-05 | 10 | 7/6/2021 | 34 | 2021-07-27 | 16 | 2021-07-27 | 2021-08-24 | 20 | [12 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | 2021-09-17 | 17 |  |  |  |  | 2021-05-20 |  |  |  | 2021-07-14 | 2021-07-27 | 2021-07-27 | 9 | 2021-09-17 | [17 empty] | 2021-09-17 | 2021-09-17 | 0
121370658 | 972 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 162.5 |  | 2021-05-20 |  |  | 2021-06-01 | 2021-06-01 | 7 | 2021-06-01 | 7 | 2021-07-12 | 28 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [7 empty] | 2021-06-24 | 2021-07-13 | 12
121370748 | 973 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 108.67 |  | 2021-05-20 |  | 2021-06-01 | 2021-06-01 | 2021-06-01 | 7 | 2021-06-01 | 7 | 2021-08-09 | 48 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09
121373181 | 974 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 59.519 |  | 2021-05-21 |  | 2021-06-11 | 2021-05-25 | 2021-05-25 | 2 | 2021-06-22 | 21 | 2021-07-08 | 11 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-16 | 6 |  |  |  |  | 2021-05-21 | 2021-05-25 | 2021-06-07 | 10
121373517 | 975 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 36.511 |  | 2021-05-21 |  | 2021-06-03 | 2021-06-03 | 2021-06-03 | 8 | 2021-07-09 | 33 |  |  | 2021-08-09 | 2021-09-01 | 17 | [12 empty] | 2021-09-01 | 2021-09-02 | 1 | 2021-09-02 | [10 empty] | 2021-07-23
121373784 | 976 | PGE | NEM | EXPNEM | Implementation | Solar PV | 100 |  | 2021-05-21 |  | 2021-08-05 | 2021-06-02 | 2021-06-02 | 7 | 2021-06-29 | 26 | 2021-08-20 | 37 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-20 | 2021-08-30 | 6 |  |  |  |  | 2021-05-21 | 2021-08-05 | 2021-08-13 | 58
121374252 | 977 | PGE | NEM | NEMMT | Study in Progress | Solar PV | 659.212 |  | 2021-05-21 |  | 2021-08-12 | 2021-06-02 | 2021-06-02 | 7 | 2021-08-20 | 63 | 2021-09-03 | 10 | 2021-09-03 | [24 empty] | 2021-08-12 | 2021-09-30 |  |  | 2021-08-24
121374355 | 978 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 150 |  | 2021-05-21 |  | 2021-06-15 | 2021-06-03 | 2021-06-03 | 8 | 2021-06-17 | 18 | 2021-07-02 | 11 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | [6 empty] | 2021-05-21 |  |  |  | 2021-07-01
121374357 | 979 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.408 |  | 2021-05-21 |  | 2021-05-24 | 2021-05-24 | 2021-05-24 | 1 | 2021-06-07 | 10 | 2021-06-09 | 2 | [33 empty] | 2021-06-10 | 2021-06-10 | 0 | [15 empty] | 2021-06-10 |  |  | 2021-06-10 |  | 2021-06-10 | 0
121374869 | 980 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 150 |  | 2021-05-21 |  |  | 2021-05-28 | 2021-05-28 | 5 | 2021-05-28 | 5 | 2021-06-15 | 11 | 2021-06-15 | 2021-07-14 | 20 | [12 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | [6 empty] | 2021-05-21 | 2021-05-28 | 2021-06-15 | 16
121375280 | 981 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 90.925 |  | 2021-05-21 |  | 2021-06-01 | 2021-06-01 | 2021-06-01 | 6 | 2021-06-07 | 10 | 2021-06-21 | 10 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-30 | 7 |  |  |  |  | 2021-05-21 | 2021-06-01 | 2021-06-15 | 16
121375380 | 982 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.305 |  | 2021-05-21 |  | 2021-06-03 | 2021-05-25 | 2021-05-25 | 2 | 2021-06-08 | 11 | 2021-06-08 | 0 | [25 empty] | 2021-05-21 | [7 empty] | 2021-07-14 | 2021-07-14 | 0 | [15 empty] | 2021-06-28 | 2021-07-01 | 3 | 2021-07-14 |  | 2021-07-14 | 0
121375492 | 983 | PGE | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-05-21 |  | 2021-07-07 | 2021-06-04 | 2021-06-04 | 9 | 2021-07-14 | 36 | 2021-07-14 | 0 | [15 empty] | 2021-07-14 | 2021-07-21 | 5 | 2021-07-21 | 2021-07-21 | 0 | [12 empty] | 2021-07-29 | 2021-08-05 | 5 | [15 empty] | 2021-07-29 | 2021-07-29 | 0 | 2021-08-05 |  | 2021-08-13 | 6
121375499 | 984 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-05-21 |  | 2021-06-11 | 2021-06-04 | 2021-06-04 | 9 | 2021-06-15 | 16 | 2021-07-01 | 12 | 2021-07-01 | 2021-07-30 | 20 | [12 empty] | 2021-07-30 | 2021-07-30 | 0 | 2021-07-30 | [6 empty] | 2021-05-21 |  |  |  | 2021-07-09
121375882 | 985 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 37.598 |  | 2021-05-21 |  | 2021-06-07 | 2021-06-07 | 2021-06-07 | 10 | 2021-07-06 | 30 | 2021-07-22 | 12 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | [6 empty] | 2021-05-21
121376015 | 986 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 |  | 2021-05-21 |  | 2021-05-25 | 2021-05-25 | 2021-05-25 | 2 | 2021-05-28 | 5 | 2021-06-02 | 2 | [19 empty] | 2021-06-15 | N/A | [12 empty] | 2021-06-15 | 2021-06-15 | 0 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-15 |  | 2021-06-15 | 0
121376016 | 987 | PGE | NEM | EXPNEM | IA in Progress | Solar PV, WIND | 86.681 |  | 2021-05-21 |  | 2021-06-14 | 2021-06-05 | 2021-06-05 | 9 | 2021-07-09 | 33 | 2021-07-27 | 12 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27
121376996 | 988 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 72.55 |  | 2021-05-21 |  | 2021-06-07 | 2021-06-07 | 2021-06-07 | 10 | [29 empty] | 2021-05-21
121377065 | 989 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 63.892 |  | 2021-05-21 |  | 2021-06-01 | 2021-06-01 | 2021-06-01 | 6 | 2021-06-15 | 16 | 2021-06-23 | 6 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23
121377177 | 990 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 72.22 |  | 2021-05-21 |  | 2021-06-15 | 2021-06-01 | 2021-06-01 | 6 | 2021-06-16 | 17 | 2021-07-01 | 11 | [15 empty] | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01
121377178 | 991 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 72.55 |  | 2021-05-21 |  | 2021-06-04 | 2021-06-04 | 2021-06-04 | 9 | [29 empty] | 2021-05-21
121377182 | 992 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 31.752 |  | 2021-05-21 |  |  | 2021-06-02 | 2021-06-02 | 7 | 2021-06-02 | 7 | 2021-07-12 | 27 | [19 empty] | 2021-05-21 | N/A | [12 empty] | 2021-09-16 | [17 empty] | 2021-09-16 | 2021-09-16 | 0
121377527 | 993 | PGE | Non-NEM | Continuous Uncompensated Export | IA in Progress | Solar PV | 271.284 |  | 2021-05-21 | 2021-05-24 |  | 2021-05-24 | 2021-05-24 | 1 | 2021-06-02 | 7 | 2021-07-14 | 29 | [15 empty] | 2021-07-14 | 2021-07-28 | 10 | 2021-07-28
121377656 | 994 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 72.55 |  | 2021-05-21 |  | 2021-06-04 | 2021-06-04 | 2021-06-04 | 9 | [29 empty] | 2021-05-21
121377796 | 995 | PGE | NEM | NEMMT | Implementation | ENGN, Solar PV, Storage | 1792 |  | 2021-05-21 |  |  | 2021-05-28 | 2021-05-28 | 5 | 2021-06-03 | 8 | 2021-07-23 | 35 | [15 empty] | 2021-07-29 | 2021-08-05 | 5 | 2021-08-05 | 2021-08-16 | 7 |  |  |  |  | 2021-05-21
121387357 | 996 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-05-24 |  | 2021-06-09 | 2021-05-25 | 2021-05-25 | 1 | 2021-06-09 | 11 | 2021-06-10 | 1 | [33 empty] | 2021-06-10 | 2021-06-10 | 0 | [15 empty] | 2021-06-10 |  |  | 2021-06-10 |  | 2021-06-10 | 0
121388233 | 997 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 470 |  | 2021-05-24 |  |  | 2021-06-07 | 2021-06-07 | 9 | [7 empty] | 2021-06-08 | 2021-07-01 | 17 | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01 | 2021-09-27 | 60 | 2021-07-01 | 2021-07-01 | 0 | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | [6 empty] | 2021-05-24 |  |  |  | 2021-06-17
121388478 | 998 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 34.8 |  | 2021-05-24 |  | 2021-06-07 | 2021-06-07 | 2021-06-07 | 9 | 2021-08-04 | 50 | 2021-09-24 | 36
121389094 | 999 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 249.258 |  | 2021-05-24 |  | 2021-06-03 | 2021-06-03 | 2021-06-03 | 7 | 2021-07-15 | 36 | 2021-08-10 | 18 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-10 | 2021-09-07 | 19 |  |  |  |  | 2021-05-24 | 2021-06-03 | 2021-06-15 | 15
121389545 | 1000 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2021-05-24 |  | 2021-06-07 | 2021-06-04 | 2021-06-04 | 8 | 2021-06-09 | 11 | 2021-06-15 | 4 | 2021-06-15 | 2021-07-14 | 20 | 2021-07-14 | 2021-08-09 | 18 | 2021-08-09 | [18 empty] | 2021-05-24 | 2021-06-09 | 2021-06-17 | 17
121389688 | 1001 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 90.477 |  | 2021-05-24 |  | 2021-06-11 | 2021-06-02 | 2021-06-02 | 6 | [29 empty] | 2021-05-24 | 2021-06-02 | 2021-06-15 | 15
121389970 | 1002 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-05-24 |  | 2021-06-08 | 2021-06-08 | 2021-06-08 | 10 | 2021-06-18 | 18 | 2021-07-08 | 13 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-09-09 | 44 | [12 empty] | 2021-09-17 | 2021-09-27 | 6 | [15 empty] | 2021-09-17 | 2021-09-20 | 1 | 2021-09-27
121390538 | 1003 | PGE | NEM | EXPNEM | Implementation | Solar PV | 150 |  | 2021-05-24 |  | 2021-06-04 | 2021-06-04 | 2021-06-04 | 8 | 2021-07-26 | 43 | 2021-08-19 | 18 | [15 empty] | 2021-08-19 | 2021-08-20 | 1 | 2021-08-20 | 2021-09-13 | 15 |  |  |  |  | 2021-05-24 | 2021-07-26 | 2021-08-05 | 51
121391420 | 1004 | PGE | NEM | EXPNEM | Commercial | Solar PV | 40.269 |  | 2021-05-24 |  | 2021-06-02 | 2021-06-02 | 2021-06-02 | 6 | 2021-07-12 | 33 | 2021-07-26 | 10 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-08-04 | 7 | [12 empty] | 2021-08-09 | 2021-08-13 | 4 | [15 empty] | 2021-08-09 | 2021-08-10 | 1 | 2021-08-13 |  | 2021-08-19 | 4
121391712 | 1005 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 1560 |  | 2021-05-24 | 2021-05-26 |  | 2021-05-25 | 2021-05-25 | 1 | 2021-06-02 | 6 | 2021-07-26 | 37 | 2021-08-12 | 2021-09-10 | 20 | [22 empty] | 2021-05-24 |  |  |  | 2021-08-06
121393152 | 1006 | PGE | NEM | EXPNEM | Implementation | Solar PV | 221.358 |  | 2021-05-25 |  | 2021-06-08 | 2021-06-08 | 2021-06-08 | 9 | 2021-06-15 | 14 | 2021-07-02 | 13 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-07-08 | 3 |  |  |  |  | 2021-05-25 | 2021-08-13 | 2021-08-27 | 66 | 2021-08-06 |  |  |  | 2021-09-13 | 2021-09-16 | 3 | [15 empty] | 2021-09-13 | 2021-09-14 | 1 | 2021-09-16 | 2021-09-17 |  | 1 |  |  | 80 |  | 80
121393713 | 1007 | PGE | NEM | EXPNEM | Implementation | Solar PV | 213.803 |  | 2021-05-25 |  | 2021-06-08 | 2021-06-08 | 2021-06-08 | 9 | 2021-06-15 | 14 | 2021-07-06 | 14 | [15 empty] | 2021-08-25 | 2021-08-30 | 3 | 2021-08-30 | 2021-08-31 | 1 |  |  |  |  | 2021-05-25 |  |  |  | 2021-07-09
121396920 | 1008 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 85.259 |  | 2021-05-25 |  | 2021-06-04 | 2021-06-04 | 2021-06-04 | 7 | 2021-06-09 | 10 | 2021-06-21 | 8 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-24 | 3 |  |  |  |  | 2021-05-25 | 2021-06-09 | 2021-06-17 | 16
121397037 | 1009 | PGE | NEM | EXPNEM | Implementation | Solar PV | 60 |  | 2021-05-25 |  | 2021-06-09 | 2021-06-08 | 2021-06-08 | 9 | 2021-06-09 | 10 | 2021-06-18 | 7 | [15 empty] | 2021-06-18 | 2021-06-25 | 5 | 2021-06-25 | 2021-06-28 | 1 |  |  |  |  | 2021-05-25 | 2021-06-16 | 2021-06-24 | 21
121397387 | 1010 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-05-25 |  |  | 2021-06-08 | 2021-06-08 | 9 | 2021-06-08 | 9 | 2021-06-23 | 11 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23
121397581 | 1011 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 30.402 |  | 2021-05-25 |  |  | 2021-06-11 | 2021-06-11 | 12 | 2021-06-25 | 22 | 2021-07-19 | 15 | [15 empty] | 2021-07-19 | 2021-07-19 | 0 | 2021-07-19 | [6 empty] | 2021-05-25
121397640 | 1012 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.179 |  | 2021-05-25 |  |  | 2021-06-11 | 2021-06-11 | 12 | 2021-06-25 | 22 | 2021-07-19 | 15 | [15 empty] | 2021-07-19 | 2021-07-19 | 0 | 2021-07-19 | [6 empty] | 2021-05-25
121398219 | 1013 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 210 |  | 2021-05-26 | 2021-05-27 |  | 2021-05-27 | 2021-05-27 | 1 | 2021-06-09 | 9 | 2021-07-28 | 34 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28
121398274 | 1014 | PGE | Non-NEM | Non-Export | Application Accepted | Solar PV, Storage | 114.26 |  | 2021-05-25 | 2021-05-27 |  | 2021-05-26 | 2021-05-26 | 1 | 2021-06-16 | 15
121401104 | 1015 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 1466.6 |  | 2021-05-26 |  | 2021-06-04 | 2021-06-04 | 2021-06-04 | 6 | 2021-08-04 | 48 | 2021-09-08 | 24 | 2021-09-24 | [24 empty] | 2021-08-10 | 2021-09-29
121401939 | 1016 | PGE | Non-NEM | Non-Export | Implementation | Storage | 140 |  | 2021-05-26 | 2021-05-28 |  | 2021-05-27 | 2021-05-27 | 1 | 2021-06-23 | 19 | 2021-07-15 | 15 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-08-06 | 16
121402560 | 1017 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 750 |  | 2021-05-26 |  | 2021-06-09 | 2021-06-09 | 2021-06-09 | 9 | 2021-08-18 | 58 | [31 empty] | 2021-09-10 | 2021-09-10 |  | 0
121403282 | 1018 | PGE | NEM | VNEMMASH | Implementation | Solar PV | 41.246 |  | 2021-05-26 |  | 2021-06-10 | 2021-06-10 | 2021-06-10 | 10 | 2021-08-02 | 46 | 2021-08-23 | 15 | [15 empty] | 2021-08-23 | 2021-09-14 | 15 | 2021-09-14 | 2021-09-16 | 2 | [5 empty] | 2021-08-05 | 2021-08-13 | 6
121403301 | 1019 | PGE | NEM | VNEMMASH | Implementation | Solar PV | 36.905 |  | 2021-05-26 |  | 2021-06-10 | 2021-06-10 | 2021-06-10 | 10 | 2021-08-02 | 46 | 2021-08-23 | 15 | [15 empty] | 2021-08-23 | 2021-09-14 | 15 | 2021-09-14 | 2021-09-16 | 2 | [5 empty] | 2021-09-24
121403307 | 1020 | PGE | NEM | VNEMMASH | Implementation | Solar PV | 55.756 |  | 2021-05-26 |  | 2021-06-10 | 2021-06-10 | 2021-06-10 | 10 | 2021-08-02 | 46 | 2021-08-23 | 15 | [15 empty] | 2021-08-23 | 2021-09-14 | 15 | 2021-09-14 | 2021-09-16 | 2 | [5 empty] | 2021-08-05 | 2021-08-13 | 6
121403923 | 1021 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 32.125 |  | 2021-05-26 |  | 2021-06-11 | 2021-06-04 | 2021-06-04 | 6
121403946 | 1022 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 630 |  | 2021-05-26 | 2021-05-28 |  | 2021-05-27 | 2021-05-27 | 1 | 2021-06-30 | 24 | 2021-09-17 | 55 | [15 empty] | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | [6 empty] | 2021-05-26
121407586 | 1023 | PGE | Non-NEM | Non-Export | IA in Progress | ENGN, Storage | 290 |  | 2021-05-27 | 2021-05-28 |  | 2021-05-27 | 2021-05-27 | 0 | 2021-06-23 | 18 | 2021-08-10 | 33 | [15 empty] | 2021-08-10 | 2021-08-25 | 11 | 2021-08-25 | [6 empty] | 2021-05-27 | 2021-07-01 | 2021-07-07 | 27
121416495 | 1024 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.395 |  | 2021-05-27 |  | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2 | 2021-06-04 | 5 | 2021-06-08 | 2 | [33 empty] | 2021-06-08 | 2021-06-08 | 0 | [15 empty] | 2021-06-08 |  |  | 2021-06-08 |  | 2021-06-08 | 0
121416566 | 1025 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 37.758 |  | 2021-05-27 |  | 2021-06-11 | 2021-06-11 | 2021-06-11 | 10 | 2021-08-19 | 58 | 2021-09-08 | 13 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | [6 empty] | 2021-05-27
121416960 | 1026 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.232 |  | 2021-05-27 |  | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2 | 2021-07-13 | 31 | 2021-07-15 | 2 | [33 empty] | 2021-07-16 | 2021-07-16 | 0 | [15 empty] | 2021-07-16 |  |  | 2021-07-16 |  | 2021-07-16 | 0
121417422 | 1027 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.2 |  | 2021-05-27 |  | 2021-06-07 | 2021-06-07 | 2021-06-07 | 6 | [29 empty] | 2021-05-27
121424947 | 1028 | PGE | NEM | EXPNEM | Implementation | Solar PV | 35.187 |  | 2021-05-28 |  | 2021-06-14 | 2021-06-14 | 2021-06-14 | 10 | 2021-06-17 | 13 | 2021-07-07 | 13 | [15 empty] | 2021-07-07 | 2021-07-26 | 13 | 2021-07-26 | 2021-08-13 | 14 |  |  |  |  | 2021-05-28 | 2021-06-17 | 2021-07-02 | 24
121425609 | 1029 | PGE | NEM | EXPNEM | Commercial | Solar PV | 90 |  | 2021-05-28 |  | 2021-06-16 | 2021-06-08 | 2021-06-08 | 6 | 2021-07-02 | 24 | 2021-07-21 | 12 | [15 empty] | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | 2021-08-18 | 20 | [12 empty] | 2021-08-27 | 2021-09-07 | 6 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-09-07 |  | 2021-09-13 | 4
121426881 | 1030 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 98.329 |  | 2021-05-28 |  | 2021-06-23 | 2021-06-23 | 2021-06-23 | 17 | 2021-08-18 | 56 | 2021-09-29 | 29 | [25 empty] | 2021-05-28 |  |  |  | 2021-09-08
121427426 | 1031 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 36.54 |  | 2021-05-28 |  | 2021-06-11 | 2021-06-11 | 2021-06-11 | 9 | 2021-08-19 | 57 | 2021-09-08 | 13 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | [6 empty] | 2021-05-28
121428122 | 1032 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 35.356 |  | 2021-05-28 |  | 2021-07-20 | 2021-06-09 | 2021-06-09 | 7 | [29 empty] | 2021-05-28 | 2021-07-20 | 2021-07-22 | 37
121428277 | 1033 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 66.6 |  | 2021-05-28 |  | 2021-07-08 | 2021-06-09 | 2021-06-09 | 7 | 2021-07-02 | 24 | 2021-08-30 | 40 | 2021-08-30
121428473 | 1034 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 36.796 |  | 2021-05-28 |  |  | 2021-06-02 | 2021-06-02 | 2 | 2021-06-02 | 2 | 2021-06-07 | 3 | [56 empty] | 2021-06-07
121432290 | 1035 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-05-30 |  | 2021-06-02 | 2021-06-02 | 2021-06-02 | 1 | 2021-07-12 | 28 | 2021-07-13 | 1 | [33 empty] | 2021-07-14 | 2021-07-14 | 0 | [15 empty] | 2021-07-14 |  |  | 2021-07-14 |  | 2021-07-14 | 0
121435809 | 1036 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 34.179 |  | 2021-06-01 |  | 2021-06-15 | 2021-06-15 | 2021-06-15 | 10 | 2021-08-02 | 43 | [27 empty] | 2021-06-01 |  |  |  | 2021-09-02
121435858 | 1037 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 34.179 |  | 2021-06-01 |  | 2021-06-15 | 2021-06-15 | 2021-06-15 | 10 | 2021-08-25 | 60 | 2021-09-07 | 8 | [15 empty] | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | [6 empty] | 2021-06-01 | 2021-08-25 | 2021-09-08 | 69
121435881 | 1038 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 42.472 |  | 2021-06-01 |  | 2021-06-09 | 2021-06-09 | 2021-06-09 | 6 | 2021-08-12 | 51 | 2021-08-25 | 9 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | [6 empty] | 2021-06-01 | 2021-08-23 | 2021-09-07 | 68
121438450 | 1039 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 696 |  | 2021-06-01 |  | 2021-07-15 | 2021-06-15 | 2021-06-15 | 10 | 2021-07-26 | 38 | 2021-08-11 | 12 | 2021-08-11 | 2021-09-05 | 17 | [12 empty] | 2021-09-05 | 2021-09-05 | 0 | 2021-09-05
121438653 | 1040 | PGE | NEM | EXPNEM | Implementation | Solar PV | 226.751 |  | 2021-06-01 |  | 2021-07-06 | 2021-06-14 | 2021-06-14 | 9 | 2021-06-30 | 21 | 2021-08-06 | 26 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | 2021-08-16 | 6 |  |  |  |  | 2021-06-01
121439361 | 1041 | PGE | NEM | EXPNEM | Commercial | Solar PV | 36.186 |  | 2021-06-01 |  | 2021-06-14 | 2021-06-09 | 2021-06-09 | 6 | 2021-06-28 | 19 | 2021-07-08 | 7 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-08-16 | 27 |  |  |  |  | 2021-06-01 | 2021-07-08 | 2021-07-19 | 33 |  |  |  |  | 2021-09-17 | 2021-09-23 | 4 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-23 |  | 2021-09-30 | 5
121439461 | 1042 | PGE | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 33.165 |  | 2021-06-01 |  | 2021-08-02 | 2021-06-03 | 2021-06-03 | 2 | 2021-08-16 | 53 | 2021-08-16 | 0
121439497 | 1043 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.657 |  | 2021-06-01 |  | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2 | 2021-06-15 | 10 | 2021-06-16 | 1 | [33 empty] | 2021-06-16 | 2021-06-16 | 0 | [15 empty] | 2021-06-16 |  |  | 2021-06-16 |  | 2021-06-16 | 0
121445323 | 1044 | PGE | NEM | EXPNEM | Implementation | Solar PV | 75.777 |  | 2021-06-02 |  | 2021-06-15 | 2021-06-14 | 2021-06-14 | 8 | 2021-06-14 | 8 | 2021-07-02 | 14 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-07-02 | 0 |  |  |  |  | 2021-06-02 |  |  |  | 2021-07-09
121445490 | 1045 | PGE | NEM | EXPNEM | Commercial | Solar PV | 33.3 |  | 2021-06-02 |  | 2021-06-14 | 2021-06-14 | 2021-06-14 | 8 | 2021-06-16 | 10 | 2021-06-28 | 8 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-07-26 | 19 |  |  |  |  | 2021-06-02 | 2021-06-16 | 2021-06-28 | 18 |  |  |  |  | 2021-07-26 | 2021-08-03 | 6 | [15 empty] | 2021-07-26 | 2021-07-27 | 1 | 2021-08-03 |  | 2021-08-04 | 1
121445573 | 1046 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 229.645 |  | 2021-06-02 |  |  | 2021-06-09 | 2021-06-09 | 5 | 2021-06-09 | 5 | 2021-06-24 | 11 | 2021-06-24 | 2021-07-06 | 7 | [12 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-07-08 | 2
121446288 | 1047 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 56.965 |  | 2021-06-02 |  |  | 2021-06-11 | 2021-06-11 | 7 | 2021-06-11 | 7 | 2021-07-02 | 15 | [15 empty] | 2021-07-02 | 2021-07-26 | 15 | 2021-07-26 | [6 empty] | 2021-06-02 | 2021-09-21 | 2021-09-23 | 79 |  | 2021-08-19 | 2021-08-19 | 0
121446467 | 1048 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 72.547 |  | 2021-06-02 |  | 2021-08-23 | 2021-06-09 | 2021-06-09 | 5 | 2021-08-25 | 59 | 2021-09-16 | 15 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | [6 empty] | 2021-06-02 | 2021-08-25 | 2021-09-08 | 68
121447252 | 1049 | PGE | Non-NEM | Non-Export | Withdrawn | Solar PV | 50 |  | 2021-06-02 |  |  | 2021-06-02 | 2021-06-02 | 0
121447549 | 1050 | PGE | Non-NEM | RESBCT | Study in Progress | Solar PV | 3111.7 |  | 2021-06-02 | 2021-06-04 |  | 2021-06-04 | 2021-06-04 | 2 | 2021-06-16 | 10 | [5 empty] | 2021-06-16 | 2021-07-12 | 17 | 2021-07-12 | 2021-07-12 | 0 | 2021-07-22 |  |  | 2021-07-12 | 2021-07-12 | 0
121448017 | 1051 | PGE | NEM | EXPNEM | Commercial | Solar PV | 60.868 |  | 2021-06-02 |  | 2021-06-18 | 2021-06-10 | 2021-06-10 | 6 | 2021-06-22 | 14 | 2021-07-14 | 15 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-22 | 6 | [12 empty] | 2021-07-31 | 2021-08-10 | 6 | [15 empty] | 2021-07-31 | 2021-08-02 | 0 | 2021-08-10 |  | 2021-08-13 | 3
121449425 | 1052 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.3 |  | 2021-06-02 |  | 2021-06-12 | 2021-06-10 | 2021-06-10 | 6
121449590 | 1053 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 40.002 |  | 2021-06-02 |  | 2021-06-15 | 2021-06-10 | 2021-06-10 | 6
121449970 | 1054 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 277.81 |  | 2021-06-03 |  | 2021-06-17 | 2021-06-17 | 2021-06-17 | 10 | [29 empty] | 2021-06-03
121450747 | 1055 | PGE | NEM | EXPNEM | Application Submitted | Solar PV | 168.227 |  | 2021-06-03 |  | 2021-08-02 | 2021-06-15 | 2021-06-15 | 8 | [29 empty] | 2021-07-14 | 2021-09-23 | 2021-09-28 | 53
121451502 | 1056 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 57.177 |  | 2021-06-03 |  | 2021-06-17 | 2021-06-17 | 2021-06-17 | 10 | 2021-07-09 | 25 | 2021-07-26 | 11 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26
121452520 | 1057 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 38.78 |  | 2021-06-03 |  | 2021-06-11 | 2021-06-11 | 2021-06-11 | 6 | 2021-06-15 | 8 | 2021-07-06 | 14 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-07-14 | 6 | [12 empty] | 2021-09-23 | [17 empty] | 2021-09-23 | 2021-09-23 | 0
121452981 | 1058 | PGE | NEM | EXPNEM | IA in Progress | ENGN, Solar PV | 437.796 |  | 2021-06-03 |  | 2021-06-17 | 2021-06-17 | 2021-06-17 | 10 | 2021-08-06 | 45 | 2021-08-23 | 11 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23
121453077 | 1059 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.29 |  | 2021-06-03 |  | 2021-06-16 | 2021-06-07 | 2021-06-07 | 2 | 2021-08-27 | 60 | 2021-08-31 | 2 | [33 empty] | 2021-08-31 | 2021-08-31 | 0 | [15 empty] | 2021-08-31 |  |  | 2021-08-31 |  | 2021-08-31 | 0
121453943 | 1060 | PGE | NEM | EXPNEM | Commercial | Solar PV | 35.005 |  | 2021-06-03 |  | 2021-06-11 | 2021-06-11 | 2021-06-11 | 6 | 2021-06-16 | 9 | 2021-07-08 | 15 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-09 | 1 | [12 empty] | 2021-07-26 | 2021-08-04 | 7 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-08-04 |  | 2021-08-11 | 5
121454801 | 1061 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 600 |  | 2021-06-03 |  | 2021-09-24 | 2021-06-11 | 2021-06-11 | 6
121454804 | 1062 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 312.5 |  | 2021-06-03 |  | 2021-09-02 | 2021-06-11 | 2021-06-11 | 6 | [29 empty] | 2021-06-03
121460523 | 1063 | PGE | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 54.494 |  | 2021-06-03 |  | 2021-06-14 | 2021-06-08 | 2021-06-08 | 3 | 2021-06-16 | 9 | 2021-07-02 | 12 | [15 empty] | 2021-08-11 | 2021-08-11 | 0 | 2021-08-11 | 2021-08-11 | 0 | [12 empty] | 2021-08-11 | [17 empty] | 2021-08-11 | 2021-08-12 | 1
121464511 | 1064 | PGE | NEM | EXPNEM | Commercial | Solar PV | 66.6 |  | 2021-06-03 |  |  | 2021-06-11 | 2021-06-11 | 6 | 2021-06-11 | 6 | 2021-06-17 | 4 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-07-16 | 20 | [12 empty] | 2021-07-28 | 2021-08-05 | 6 | [15 empty] | 2021-07-28 | 2021-08-05 | 6 | 2021-08-05 |  | 2021-08-11 | 4
121466224 | 1065 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 140 |  | 2021-06-04 | 2021-06-04 |  | 2021-06-04 | 2021-06-04 | 0 | 2021-06-30 | 18 | 2021-08-25 | 39 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | [6 empty] | 2021-06-04 | 2021-09-07 | 2021-09-10 | 68 | [19 empty] | 2021-08-25 | 2021-08-25 | 0
121466710 | 1066 | PGE | NEM | EXPNEM | Withdrawn | ENGN | 1000 |  | 2021-06-04 |  |  | 2021-06-22 | 2021-06-22 | 12 | 2021-06-22 | 12 | 2021-07-09 | 12
121467447 | 1067 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 44.37 |  | 2021-06-04 |  | 2021-08-13 | 2021-06-12 | 2021-06-12 | 5 | 2021-08-18 | 52 | 2021-09-08 | 14 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-09-08 | 0 | [12 empty] | 2021-09-22 | [17 empty] | 2021-09-22 | 2021-09-22 | 0
121467479 | 1068 | PGE | NEM | EXPNEM | Implementation | Solar PV | 266.145 |  | 2021-06-04 |  | 2021-07-08 | 2021-06-15 | 2021-06-15 | 7 | 2021-07-08 | 23 | 2021-08-10 | 23 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-10 | 2021-08-26 | 12
121467889 | 1069 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 140 |  | 2021-06-04 | 2021-06-04 |  | 2021-06-04 | 2021-06-04 | 0 | 2021-06-30 | 18 | 2021-07-20 | 13 | [15 empty] | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | [6 empty] | 2021-06-04 | 2021-06-30 | 2021-07-14 | 27 | [19 empty] | 2021-07-26
121469162 | 1070 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 48.363 |  | 2021-06-04 |  | 2021-07-21 | 2021-06-18 | 2021-06-18 | 10
121469331 | 1071 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 57.71 |  | 2021-06-04 |  | 2021-07-21 | 2021-06-18 | 2021-06-18 | 10
121469365 | 1072 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 52.163 |  | 2021-06-04 |  | 2021-07-21 | 2021-06-18 | 2021-06-18 | 10
121469768 | 1073 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 32.436 |  | 2021-06-04 |  | 2021-06-18 | 2021-06-18 | 2021-06-18 | 10 | 2021-06-25 | 15 | 2021-07-19 | 15 | [15 empty] | 2021-07-19 | 2021-07-19 | 0 | 2021-07-19 | [7 empty] | 2021-07-21 | 2021-08-03 | 9
121469908 | 1074 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 52.163 |  | 2021-06-04 |  | 2021-06-18 | 2021-06-18 | 2021-06-18 | 10 | 2021-06-25 | 15 | 2021-07-19 | 15 | [15 empty] | 2021-07-19 | 2021-07-19 | 0 | 2021-07-19 | [7 empty] | 2021-07-21 | 2021-08-03 | 9
121470469 | 1075 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.791 |  | 2021-06-04 |  | 2021-06-12 | 2021-06-12 | 2021-06-12 | 5 | 2021-06-16 | 8 | 2021-07-06 | 13 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-07-21 | 11
121478443 | 1076 | PGE | NEM | SNEM Paired Storage | Implementation | Solar PV, Storage | 42.725 |  | 2021-06-06 |  | 2021-08-11 | 2021-06-09 | 2021-06-09 | 2 | 2021-08-21 | 54 | 2021-08-23 | 0 | [33 empty] | 2021-08-23 | [17 empty] | 2021-08-23 | 2021-08-23 | 0
121479895 | 1077 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 38.78 |  | 2021-06-07 |  | 2021-09-03 | 2021-06-10 | 2021-06-10 | 3 | 2021-09-03 | 63 | 2021-09-21 | 11 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21
121484017 | 1078 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 162.5 |  | 2021-06-07 |  | 2021-06-17 | 2021-06-16 | 2021-06-16 | 7 | 2021-06-16 | 7 | [27 empty] | 2021-06-07
121484291 | 1079 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 55.575 |  | 2021-06-07 |  | 2021-06-12 | 2021-06-12 | 2021-06-12 | 4 | 2021-06-16 | 7 | 2021-07-07 | 14 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | 2021-08-04 | 20 |  |  |  |  | 2021-06-07 | 2021-06-12 | 2021-06-18 | 9 |  |  |  |  | 2021-08-26 | 2021-09-01 | 4 | 2021-09-17 | [14 empty] | 2021-08-26 | 2021-08-27 | 1 | 2021-09-01
121485338 | 1080 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-06-07 |  | 2021-08-18 | 2021-06-12 | 2021-06-12 | 4 | 2021-08-30 | 59 | 2021-09-21 | 15 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21
121485419 | 1081 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 98.286 |  | 2021-06-07 |  | 2021-07-19 | 2021-06-12 | 2021-06-12 | 4 | 2021-09-23 | 76
121485540 | 1082 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-06-07 |  | 2021-06-12 | 2021-06-12 | 2021-06-12 | 4 | 2021-07-19 | 29 | 2021-08-04 | 12 | [15 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | 2021-08-30 | 18
121486366 | 1083 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 900 |  | 2021-06-07 |  | 2021-07-28 | 2021-06-12 | 2021-06-12 | 4
121488398 | 1084 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 58.63 |  | 2021-06-08 |  | 2021-08-03 | 2021-06-12 | 2021-06-12 | 3 | 2021-08-05 | 41 | 2021-08-24 | 13 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | 2021-08-31 | 5 |  |  |  |  | 2021-06-08 | 2021-07-14 | 2021-07-28 | 35
121490216 | 1085 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-06-08 |  |  | 2021-06-15 | 2021-06-15 | 5 | 2021-06-15 | 5 | 2021-06-18 | 3 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-18 | 2021-06-22 | 2 |  |  |  |  | 2021-06-08 | 2021-09-01 | 2021-09-10 | 66
121490383 | 1086 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 38.138 |  | 2021-06-08 |  | 2021-07-01 | 2021-07-01 | 2021-07-01 | 17 | 2021-08-03 | 39 | 2021-08-13 | 8 | [15 empty] | 2021-08-13 | 2021-08-13 | 0 | 2021-08-13 | [10 empty] | 2021-08-13
121490418 | 1087 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 133.3 |  | 2021-06-08 |  |  | 2021-06-15 | 2021-06-15 | 5 | 2021-06-15 | 5 | 2021-07-27 | 29 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-08-06 | 8
121492025 | 1088 | PGE | NEM | EXPNEM | Implementation | Solar PV | 66.6 |  | 2021-06-08 |  | 2021-06-24 | 2021-06-16 | 2021-06-16 | 6 | 2021-06-22 | 10 | 2021-07-12 | 13 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-07-20 | 6 |  |  |  |  | 2021-06-08 | [10 empty] | 2021-08-18
121492733 | 1089 | PGE | NEM | EXPNEM | Implementation | Solar PV | 540 |  | 2021-06-08 |  | 2021-06-18 | 2021-06-18 | 2021-06-18 | 8 | 2021-06-22 | 10 | 2021-06-29 | 5 | 2021-06-29 | 2021-07-27 | 19 | [12 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-08-01 | 3
121496977 | 1090 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 1200 |  | 2021-06-09 | 2021-06-09 |  | 2021-06-09 | 2021-06-09 | 0 | 2021-08-04 | 39 | [27 empty] | 2021-06-09
121497134 | 1091 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 86.4 |  | 2021-06-09 |  | 2021-06-21 | 2021-06-15 | 2021-06-15 | 4 | 2021-06-28 | 13 | 2021-07-15 | 12 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-07-16 | 1 | [12 empty] | 2021-09-09 | [17 empty] | 2021-09-09 | 2021-09-10 | 1
121498671 | 1092 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 57.71 |  | 2021-06-09 |  | 2021-07-17 | 2021-06-16 | 2021-06-16 | 5 | 2021-07-27 | 33 | 2021-08-31 | 25 | [15 empty] | 2021-08-31 | 2021-09-02 | 2 | 2021-09-02 | 2021-09-06 | 1 | [12 empty] | 2021-09-16 | 2021-09-21 | 3 | [15 empty] | 2021-09-16 | 2021-09-17 | 1 | 2021-09-21
121499088 | 1093 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 34.179 |  | 2021-06-09 |  | 2021-07-30 | 2021-06-16 | 2021-06-16 | 5 | 2021-08-04 | 39 | 2021-08-19 | 11 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-08-24 | 3 | [12 empty] | 2021-09-30 | [17 empty] | 2021-09-30 | 2021-09-30 | 0
121499589 | 1094 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 1680 |  | 2021-06-09 | 2021-06-10 |  | 2021-06-10 | 2021-06-10 | 1 | 2021-06-16 | 5 | 2021-07-26 | 27 | 2021-08-12 | 2021-09-09 | 19 | [23 empty] | 2021-07-08 | 2021-07-21 | 9
121512563 | 1095 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 828.528 |  | 2021-06-10 |  | 2021-06-23 | 2021-06-23 | 2021-06-23 | 9 | 2021-07-22 | 29 | 2021-08-05 | 10 | [15 empty] | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02 | [6 empty] | 2021-06-10 |  |  |  | 2021-07-23
121513248 | 1096 | PGE | NEM | NEMMT | Application Review in Progress | ENGN, Solar PV | 625 |  | 2021-06-10 |  | 2021-06-24 | 2021-06-24 | 2021-06-24 | 10
121513322 | 1097 | PGE | NEM | NEMMT | Application Review in Progress | ENGN, Solar PV | 625 |  | 2021-06-10 |  | 2021-06-24 | 2021-06-24 | 2021-06-24 | 10
121514479 | 1098 | PGE | NEM | EXPNEM | Implementation | Solar PV | 60 |  | 2021-06-10 |  | 2021-06-16 | 2021-06-16 | 2021-06-16 | 4 | 2021-06-29 | 13 | 2021-07-13 | 9 | [15 empty] | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13 | 2021-07-26 | 9
121514782 | 1099 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 136 |  | 2021-06-10 |  | 2021-06-16 | 2021-06-16 | 2021-06-16 | 4 | 2021-06-18 | 6 | 2021-06-29 | 7 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | [6 empty] | 2021-06-10 | 2021-06-23 | 2021-07-09 | 20
121516061 | 1100 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 44.415 |  | 2021-06-10 |  | 2021-09-09 | 2021-06-16 | 2021-06-16 | 4 | 2021-09-09 | 63 | 2021-09-15 | 4 | [15 empty] | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | [6 empty] | 2021-06-10 | 2021-09-09 | 2021-09-10 | 64
121516212 | 1101 | PGE | NEM | NEMMT | Study in Progress | Solar PV, Storage | 8248.335 |  | 2021-06-10 | 2021-06-14 |  | 2021-06-14 | 2021-06-14 | 2 | 2021-06-23 | 9 | [5 empty] | 2021-07-15 | 2021-08-02 | 12 | 2021-08-02 | 2021-08-02 | 0 | 2021-08-16 |  |  | 2021-08-02 | 2021-08-03 | 1 | [10 empty] | 2021-06-10 | 2021-07-08 | 2021-07-08 | 19
121518919 | 1102 | PGE | NEM | VNEM | IA in Progress | Solar PV | 520.277 |  | 2021-06-11 |  | 2021-06-21 | 2021-06-21 | 2021-06-21 | 6 | 2021-07-09 | 19 | 2021-07-30 | 15 | [15 empty] | 2021-07-30 | 2021-08-20 | 15 | 2021-08-20 | [6 empty] | 2021-06-11
121519464 | 1103 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.75 |  | 2021-06-11 |  | 2021-09-27 | 2021-06-14 | 2021-06-14 | 1
121520439 | 1104 | PGE | NEM | VNEM | Implementation | Solar PV | 49.035 |  | 2021-06-11 |  | 2021-06-21 | 2021-06-21 | 2021-06-21 | 6 | 2021-08-09 | 40 | 2021-08-30 | 15 | [15 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-09-02 | 3 | [8 empty] | 2021-09-10 | 2021-09-13 |  | 1
121522353 | 1105 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 76.036 |  | 2021-06-11 |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 10 | 2021-06-30 | 13 | 2021-07-22 | 15 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | [6 empty] | 2021-06-11 | 2021-07-07 | 2021-07-08 | 18 |  | 2021-07-22 | 2021-07-22 | 0
121522371 | 1106 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 76.036 |  | 2021-06-11 |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 10 | 2021-06-30 | 13 | 2021-07-22 | 15 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | [6 empty] | 2021-06-11 | 2021-07-07 | 2021-07-08 | 18 |  | 2021-07-22 | 2021-07-22 | 0
121522401 | 1107 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 75.4 |  | 2021-06-11 |  | 2021-06-23 | 2021-06-17 | 2021-06-17 | 4 | 2021-07-12 | 20 | 2021-07-21 | 7 | [15 empty] | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | 2021-08-24 | 24 |  |  |  |  | 2021-08-24 | 2021-09-01 | 2021-09-10 | 12
121522570 | 1108 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 76.006 |  | 2021-06-11 |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 10 | 2021-06-30 | 13 | 2021-07-22 | 15 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | [6 empty] | 2021-06-11 | 2021-07-07 | 2021-07-08 | 18 |  | 2021-07-22 | 2021-07-22 | 0
121522878 | 1109 | PGE | NEM | VNEM | IA in Progress | Solar PV | 200 |  | 2021-06-11 |  | 2021-06-21 | 2021-06-21 | 2021-06-21 | 6 | 2021-07-26 | 30 | 2021-08-13 | 14 | [15 empty] | 2021-08-13 | 2021-08-13 | 0 | 2021-08-13 | [10 empty] | 2021-08-30
121523121 | 1110 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 64.643 |  | 2021-06-11 |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 10 | 2021-06-30 | 13 | 2021-07-22 | 15 | [15 empty] | 2021-07-22 | 2021-08-03 | 8 | 2021-08-03 | [6 empty] | 2021-06-11 | 2021-07-21 | 2021-08-03 | 36 |  | 2021-08-03 | 2021-08-03 | 0
121523477 | 1111 | PGE | NEM | EXPNEM | Implementation | Solar PV | 162.5 |  | 2021-06-11 |  | 2021-08-11 | 2021-06-22 | 2021-06-22 | 7 | 2021-08-23 | 50 | 2021-09-02 | 8 | [15 empty] | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02 | 2021-09-09 | 4 |  |  |  |  | 2021-06-11 | 2021-08-23 | 2021-09-07 | 60
121523561 | 1112 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 500 |  | 2021-06-11 |  | 2021-06-21 | 2021-06-21 | 2021-06-21 | 6 | 2021-07-08 | 18 | 2021-07-22 | 10 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22
121523563 | 1113 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 400 |  | 2021-06-11 |  |  | 2021-06-17 | 2021-06-17 | 4 | 2021-06-17 | 4 | 2021-07-09 | 15 | [15 empty] | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12
121523564 | 1114 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-06-11 |  | 2021-06-17 | 2021-06-17 | 2021-06-17 | 4 | 2021-06-18 | 5 | 2021-07-21 | 22 | [15 empty] | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21
121527967 | 1115 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.15 |  | 2021-06-13 |  | 2021-06-15 | 2021-06-15 | 2021-06-15 | 1 | 2021-07-14 | 21 | 2021-07-20 | 4 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-15 | 2021-07-14 | 20 | [12 empty] | 2021-07-20 | 2021-07-20 | 0 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 |  | 2021-07-20 | 0
121530817 | 1116 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.232 |  | 2021-06-14 |  | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2 | 2021-07-01 | 13 | 2021-07-06 | 2 | [19 empty] | 2021-06-14 | N/A | [12 empty] | 2021-07-06 | 2021-07-06 | 0 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 |  | 2021-07-06 | 0
121531728 | 1117 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 75.463 |  | 2021-06-14 |  |  | 2021-06-17 | 2021-06-17 | 3 | 2021-06-17 | 3 | 2021-07-09 | 15 | [15 empty] | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12 | [6 empty] | 2021-06-14 | 2021-06-23 | 2021-07-09 | 18
121531833 | 1118 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 145.8 |  | 2021-06-14 |  | 2021-06-24 | 2021-06-22 | 2021-06-22 | 6 | 2021-06-22 | 6 | [27 empty] | 2021-06-14
121532817 | 1119 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 40.75 |  | 2021-06-14 |  | 2021-08-05 | 2021-06-16 | 2021-06-16 | 2 | 2021-08-17 | 45 | 2021-08-19 | 2 | [33 empty] | 2021-08-19 | 2021-08-24 | 3 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-24 |  | 2021-08-25 | 1
121533362 | 1120 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 109.873 |  | 2021-06-14 |  | 2021-06-17 | 2021-06-17 | 2021-06-17 | 3 | 2021-07-07 | 16 | 2021-08-25 | 35 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | 2021-08-25 | 0 |  |  |  |  | 2021-06-14 | 2021-07-17 | 2021-07-28 | 31
121535307 | 1121 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 80.24 |  | 2021-06-14 |  |  | 2021-06-17 | 2021-06-17 | 3 | 2021-06-17 | 3 | 2021-07-20 | 22 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-08-18 | 21 |  |  |  |  | 2021-06-14 | 2021-06-29 | 2021-07-12 | 19
121535352 | 1122 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-06-14 |  | 2021-08-02 | 2021-06-18 | 2021-06-18 | 4 | 2021-08-02 | 34 | 2021-08-16 | 10 | [15 empty] | 2021-08-16 | 2021-08-17 | 1 | 2021-08-17 | 2021-08-18 | 1 |  |  |  |  | 2021-06-14 | 2021-09-30
121535461 | 1123 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 90.067 |  | 2021-06-14 |  | 2021-06-17 | 2021-06-17 | 2021-06-17 | 3 | 2021-06-21 | 5 | 2021-08-16 | 39 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | 2021-08-18 | 2 |  |  |  |  | 2021-06-14 | 2021-06-29 | 2021-07-12 | 19
121535968 | 1124 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 34.921 |  | 2021-06-14 |  | 2021-06-22 | 2021-06-22 | 2021-06-22 | 6 | 2021-06-23 | 7 | 2021-08-06 | 31 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06
121538801 | 1125 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 82.82 |  | 2021-06-15 |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 8 | [29 empty] | 2021-06-15 |  |  |  | 2021-07-09
121539277 | 1126 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 320.808 |  | 2021-06-15 |  | 2021-06-17 | 2021-06-17 | 2021-06-17 | 2 | 2021-06-17 | 2 | 2021-07-20 | 22 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-07-20 | 0 |  |  |  |  | 2021-06-15 | 2021-08-13 | 2021-08-13 | 42
121540929 | 1127 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 133.2 |  | 2021-06-15 |  | 2021-06-18 | 2021-06-18 | 2021-06-18 | 3 | [29 empty] | 2021-06-15
121540966 | 1128 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 541.315 |  | 2021-06-15 |  | 2021-06-18 | 2021-06-18 | 2021-06-18 | 3 | [29 empty] | 2021-06-15
121541035 | 1129 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 |  | 2021-06-15 |  | 2021-06-18 | 2021-06-18 | 2021-06-18 | 3 | [29 empty] | 2021-06-15
121541287 | 1131 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 420 |  | 2021-06-15 |  | 2021-06-23 | 2021-06-23 | 2021-06-23 | 6 | 2021-07-01 | 12 | 2021-08-26 | 39 | 2021-08-26 | 2021-09-22 | 18 | 2021-09-22
121541983 | 1132 | PGE | NEM | NEMMT | Study in Progress | ENGN, Solar PV | 1192 |  | 2021-06-15 | 2021-06-22 |  | 2021-06-21 | 2021-06-21 | 4 | 2021-07-07 | 15 | [5 empty] | 2021-07-12 | 2021-08-09 | 20 | 2021-08-09 | 2021-08-09 | 0 | 2021-08-19 |  |  | 2021-08-09 | 2021-08-09 | 0 | [10 empty] | 2021-06-15
121542109 | 1133 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 |  | 2021-06-15 |  | 2021-06-18 | 2021-06-18 | 2021-06-18 | 3 | 2021-06-22 | 5 | 2021-07-12 | 13 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-08-02 | 15 |  |  |  |  | 2021-06-15 | 2021-06-22 | 2021-07-09 | 17
121542355 | 1134 | PGE | NEM | EXPNEM | Implementation | Solar PV | 228.528 |  | 2021-06-15 |  | 2021-07-06 | 2021-06-23 | 2021-06-23 | 6 | 2021-06-30 | 11 | 2021-08-06 | 26 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | 2021-08-27 | 15 |  |  |  |  | 2021-06-15 | 2021-08-02 | 2021-08-13 | 42
121542722 | 1135 | PGE | NEM | EXPNEM | Commercial | Solar PV | 58.04 |  | 2021-06-15 |  | 2021-06-18 | 2021-06-18 | 2021-06-18 | 3 | 2021-08-02 | 33 | 2021-08-09 | 5 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-16 | 5 | [12 empty] | 2021-09-10 | 2021-09-15 | 3 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-15 |  | 2021-09-22 | 5
121545717 | 1136 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-06-16 |  | 2021-06-21 | 2021-06-21 | 2021-06-21 | 3 | 2021-06-29 | 9 | 2021-07-14 | 10 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14
121546397 | 1137 | PGE | NEM | EXPNEM | Application Submitted | Solar PV | 47.52 |  | 2021-06-16 |  | 2021-06-30 | 2021-06-30 | 2021-06-30 | 10
121547049 | 1138 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 57.71 |  | 2021-06-16 |  | 2021-06-21 | 2021-06-21 | 2021-06-21 | 3 | 2021-06-30 | 10 | [5 empty] | 2021-06-30 | 2021-07-27 | 18 | 2021-07-27
121547611 | 1139 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 700 |  | 2021-06-16 |  | 2021-06-24 | 2021-06-24 | 2021-06-24 | 6 | [29 empty] | 2021-06-16
121548564 | 1140 | PGE | NEM | EXPNEM | Implementation | Solar PV | 120 |  | 2021-06-16 |  | 2021-06-28 | 2021-06-28 | 2021-06-28 | 8 | 2021-07-08 | 15 | 2021-07-26 | 12 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-08-16 | 15
121548990 | 1141 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 31.024 |  | 2021-06-16 |  | 2021-07-06 | 2021-06-22 | 2021-06-22 | 4
121550219 | 1142 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 720 |  | 2021-06-16 |  | 2021-09-10 | 2021-06-22 | 2021-06-22 | 4 | 2021-09-13 | 61
121550762 | 1143 | PGE | NEM | VNEM | Study in Progress | Solar PV | 200 |  | 2021-06-16 |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 7 | 2021-08-12 | 40 | 2021-09-01 | 14 | [29 empty] | 2021-07-09
121551327 | 1144 | PGE | Non-NEM | Non-Export | Withdrawn | Storage | 145 |  | 2021-06-17 | 2021-06-17 |  | 2021-06-17 | 2021-06-17 | 0
121552131 | 1145 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 166.032 |  | 2021-06-17 |  | 2021-07-01 | 2021-07-01 | 2021-07-01 | 10 | 2021-07-30 | 30 | 2021-09-10 | 29 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | [6 empty] | 2021-06-17
121552919 | 1146 | PGE | NEM | VNEM | IA in Progress | Solar PV | 300 |  | 2021-06-17 |  | 2021-07-01 | 2021-07-01 | 2021-07-01 | 10 | 2021-08-05 | 34 | 2021-09-09 | 24 | [15 empty] | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 | [6 empty] | 2021-06-17
121553602 | 1147 | PGE | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 41.099 |  | 2021-06-17 |  | 2021-06-24 | 2021-06-21 | 2021-06-21 | 2 | 2021-06-30 | 9 | 2021-07-07 | 4 | [25 empty] | 2021-06-17
121554184 | 1148 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 3000 |  | 2021-06-17 | 2021-06-18 |  | 2021-06-17 | 2021-06-17 | 0 | 2021-06-30 | 9 | [5 empty] | 2021-07-19 | 2021-08-18 | 22 | 2021-08-18 | 2021-08-18 | 0 | 2021-08-26 |  |  | 2021-08-18 | 2021-08-18 | 0
121556095 | 1149 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-06-17 |  |  | 2021-06-22 | 2021-06-22 | 3 | 2021-06-22 | 3 | 2021-07-12 | 13 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-08-19 | 28
121561972 | 1150 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 480.146 |  | 2021-06-18 |  | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2 | 2021-06-30 | 8 | 2021-07-12 | 7 | 2021-07-12 | 2021-08-09 | 20 | [12 empty] | 2021-08-09 | 2021-08-20 | 9 | 2021-08-20 | 2021-09-08 | 12
121562533 | 1151 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 971.537 |  | 2021-06-18 |  | 2021-08-10 | 2021-06-30 | 2021-06-30 | 8 | 2021-08-12 | 38 | 2021-09-17 | 25 | 2021-09-17 | [24 empty] | 2021-06-18 | 2021-08-10 | 2021-08-19 | 43
121562722 | 1152 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 40.32 |  | 2021-06-18 |  | 2021-09-09 | 2021-07-02 | 2021-07-02 | 10 | 2021-09-10 | 58 | 2021-09-13 | 1 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13
121563112 | 1153 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 48.618 |  | 2021-06-22 |  | 2021-09-29 | 2021-06-22 | 2021-06-22 | 0
121563554 | 1154 | PGE | NEM | VNEM | IA in Progress | Solar PV | 576.251 |  | 2021-06-18 |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 5 | 2021-08-03 | 31 | 2021-08-25 | 16 | 2021-08-25 | 2021-09-16 | 15 | [12 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | [10 empty] | 2021-07-09
121563715 | 1155 | PGE | NEM | VNEM | IA in Progress | Solar PV | 520.008 |  | 2021-06-18 |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 5 | 2021-09-16 | 62 | 2021-09-22 | 4 | [15 empty] | 2021-09-22 | 2021-09-22 | 0 | 2021-09-22 | [10 empty] | 2021-07-09
121564326 | 1156 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.065 |  | 2021-06-18 |  | 2021-06-24 | 2021-06-22 | 2021-06-22 | 2
121564714 | 1157 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-06-18 |  | 2021-07-06 | 2021-06-28 | 2021-06-28 | 6 | 2021-07-01 | 9 | 2021-08-16 | 31 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | [6 empty] | 2021-06-18 | 2021-08-25 | 2021-08-25 | 47
121564945 | 1158 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 42.054 |  | 2021-06-18 |  | 2021-06-24 | 2021-06-24 | 2021-06-24 | 4
121565488 | 1159 | PGE | NEM | EXPNEM | Implementation | Solar PV | 103.603 |  | 2021-06-18 |  | 2021-06-30 | 2021-06-30 | 2021-06-30 | 8 | 2021-07-07 | 12 | 2021-07-23 | 12 | [15 empty] | 2021-07-28 | 2021-07-29 | 1 | 2021-07-29 | 2021-08-11 | 9
121565493 | 1160 | PGE | NEM | EXPNEM | Implementation | Solar PV | 34.179 |  | 2021-06-18 |  | 2021-06-28 | 2021-06-28 | 2021-06-28 | 6 | 2021-07-01 | 9 | 2021-07-08 | 4 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-08 | 0 | [12 empty] | 2021-09-27 | [17 empty] | 2021-09-27 | 2021-09-27 | 0
121571764 | 1161 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-06-20 |  | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2 | 2021-07-02 | 9 | 2021-07-22 | 13 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | [6 empty] | 2021-06-20 | 2021-07-22 | 2021-07-30 | 28
121573132 | 1162 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.486 |  | 2021-06-21 |  |  | 2021-06-23 | 2021-06-23 | 2 | 2021-06-23 | 2 | 2021-06-23 | 0 | [33 empty] | 2021-06-25 | 2021-06-25 | 0 | [15 empty] | 2021-06-25 |  |  | 2021-06-25 |  | 2021-06-25 | 0
121574245 | 1163 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.173 |  | 2021-06-21 |  |  | 2021-06-24 | 2021-06-24 | 3 | 2021-06-24 | 3 | 2021-06-25 | 1 | [33 empty] | 2021-06-29 | 2021-06-29 | 0 | [15 empty] | 2021-06-29 |  |  | 2021-06-29 |  | 2021-06-29 | 0
121574417 | 1164 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 52.163 |  | 2021-06-21 |  | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2 | 2021-07-07 | 11 | 2021-07-20 | 9 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | [6 empty] | 2021-06-21 | 2021-08-11 | 2021-08-13 | 38
121575399 | 1165 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 336 |  | 2021-06-21 |  | 2021-07-22 | 2021-06-29 | 2021-06-29 | 6 | 2021-07-13 | 15 | 2021-08-27 | 33 | [15 empty] | 2021-08-25 | 2021-08-27 | 2 | 2021-08-27 | [6 empty] | 2021-06-21 |  |  |  | 2021-08-13
121575848 | 1166 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 49.692 |  | 2021-06-21 |  | 2021-07-06 | 2021-07-06 | 2021-07-06 | 10
121576035 | 1167 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 42.01 |  | 2021-06-21 |  | 2021-08-12 | 2021-06-24 | 2021-06-24 | 3 | 2021-08-12 | 37 | 2021-08-18 | 4 | [33 empty] | 2021-08-18 | 2021-08-23 | 3 | [15 empty] | 2021-08-18 | 2021-08-19 | 1 | 2021-08-23 |  | 2021-08-25 | 2
121576380 | 1168 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 428.274 |  | 2021-06-21 |  | 2021-06-24 | 2021-06-24 | 2021-06-24 | 3 | 2021-08-16 | 39 | 2021-09-07 | 15 | 2021-09-07 | [24 empty] | 2021-06-21 | 2021-08-16 | 2021-08-27 | 48
121578259 | 1169 | PGE | NEM | EXPNEM | Study in Progress | Solar PV, Storage | 163.772 |  | 2021-06-22 |  | 2021-07-30 | 2021-06-24 | 2021-06-24 | 2 | 2021-09-17 | 61 | [27 empty] | 2021-06-22
121580385 | 1170 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 299.6 |  | 2021-06-22 |  |  | 2021-06-25 | 2021-06-25 | 3 | 2021-06-25 | 3 | 2021-07-15 | 13 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-07-26 | 7 |  |  |  |  | 2021-06-22 | 2021-07-31 | 2021-08-13 | 37
121581280 | 1171 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.47 |  | 2021-06-22 |  | 2021-09-08 | 2021-06-25 | 2021-06-25 | 3 | 2021-09-22 | 64 | 2021-09-24 | 2 | [33 empty] | 2021-09-27 | 2021-09-28 | 1 | [15 empty] | 2021-09-27 | 2021-09-28 | 1 | 2021-09-28 |  | 2021-09-29 | 1
121582005 | 1172 | PGE | NEM | EXPNEM | Implementation | Solar PV | 37.2 |  | 2021-06-22 |  | 2021-07-13 | 2021-06-29 | 2021-06-29 | 5 | 2021-07-09 | 12 | 2021-08-06 | 20 | [15 empty] | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | 2021-08-26 | 14
121582010 | 1173 | PGE | Non-NEM | Continuous Uncompensated Export | Application Accepted | ENGN, Micro Turbine | 130 |  | 2021-06-22 | 2021-06-23 |  | 2021-06-22 | 2021-06-22 | 0 | 2021-07-07 | 10 | 2021-09-21 | 53
121582372 | 1174 | PGE | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 30.12 |  | 2021-06-22 |  | 2021-08-27 | 2021-06-28 | 2021-06-28 | 4
121582507 | 1175 | PGE | Non-NEM | Non-Export | Application Accepted | ENGN, Storage | 830 |  | 2021-06-22 | 2021-06-23 |  | 2021-06-23 | 2021-06-23 | 1 | 2021-07-14 | 15 | [27 empty] | 2021-06-22
121583458 | 1176 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 600 |  | 2021-06-22 |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 3 | 2021-08-13 | 37
121586069 | 1177 | PGE | NEM | EXPNEM | Commercial | Solar PV | 47.431 |  | 2021-06-23 |  | 2021-06-28 | 2021-06-28 | 2021-06-28 | 3 | 2021-07-07 | 9 | 2021-07-22 | 11 | [15 empty] | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | 2021-08-05 | 10 | [12 empty] | 2021-08-05 | 2021-08-12 | 5 | [15 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-12 |  | 2021-08-18 | 4
121586392 | 1178 | PGE | Non-NEM | Non-Export | Withdrawn | Solar PV | 420 |  | 2021-06-23 | 2021-06-23 |  | 2021-06-23 | 2021-06-23 | 0 | 2021-06-30 | 5
121586625 | 1180 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-06-23 |  | 2021-06-28 | 2021-06-28 | 2021-06-28 | 3 | 2021-07-14 | 14 | 2021-07-20 | 4 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | [6 empty] | 2021-06-23 | 2021-07-14 | 2021-07-15 | 15
121587043 | 1181 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-06-23 |  | 2021-07-09 | 2021-07-01 | 2021-07-01 | 6 | 7/14/21 | 16 | 2021-07-26 | 9 | [15 empty] | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | [6 empty] | 2021-06-23
121590274 | 1183 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 129.6 |  | 2021-06-23 |  | 2021-06-29 | 2021-06-29 | 2021-06-29 | 4 | 2021-07-08 | 10 | 2021-08-18 | 29 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18
121593172 | 1184 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 36 |  | 2021-06-24 |  | 2021-07-31 | 2021-06-30 | 2021-06-30 | 4 | 2021-08-04 | 28 | 2021-08-19 | 11 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-09-07 | 12
121593388 | 1185 | PGE | NEM | EXPNEM | Implementation | Solar PV | 500 |  | 2021-06-24 |  | 2021-07-09 | 2021-07-07 | 2021-07-07 | 8 | 2021-07-15 | 14 | 2021-08-12 | 20 | [15 empty] | 2021-08-23 | 2021-09-10 | 13 | 2021-09-10 | 2021-09-10 | 0 |  |  |  |  | 2021-06-24 |  |  |  | 2021-08-05
121593561 | 1186 | PGE | Non-NEM | Non-Export | IA in Progress | ENGN, Storage | 170 |  | 2021-06-24 | 2021-06-24 |  | 2021-06-24 | 2021-06-24 | 0 | 2021-07-21 | 18 | 2021-09-17 | 41 | [15 empty] | 2021-09-17 | [9 empty] | 2021-06-24
121595368 | 1187 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.195 |  | 2021-06-24 |  | 2021-07-07 | 2021-06-30 | 2021-06-30 | 4 | 2021-09-13 | 55 | 2021-09-14 | 1 | [33 empty] | 2021-09-14 | 2021-09-14 | 0 | [15 empty] | 2021-09-14 |  |  | 2021-09-14 |  | 2021-09-14 | 0
121599869 | 1188 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.12 |  | 2021-06-25 |  | 2021-09-08 | 2021-07-08 | 2021-07-08 | 8
121600524 | 1189 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 423.302 |  | 2021-06-17 | 2021-06-29 |  | 2021-06-28 | 2021-06-28 | 7 | 2021-07-21 | 23 | [5 empty] | 2021-09-08 | [21 empty] | 2021-06-25
121600650 | 1190 | PGE | NEM | EXPNEM | Implementation | Solar PV | 66.6 |  | 2021-06-25 |  | 2021-07-15 | 2021-06-30 | 2021-06-30 | 3 | 2021-07-19 | 15 | 2021-07-23 | 4 | [15 empty] | 2021-07-23 | 2021-07-23 | 0 | 2021-07-23 | 2021-08-26 | 24 |  |  |  |  | 2021-06-25
121601978 | 1191 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 35.234 |  | 2021-06-25 |  | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2
121602291 | 1192 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.464 |  | 2021-06-25 |  | 2021-07-07 | 2021-07-07 | 2021-07-07 | 7 | 2021-07-09 | 9 | 2021-07-12 | 1 | [15 empty] | 2021-06-25 | 2021-07-07 | 7 | 2021-07-07 | 2021-07-13 | 4 |  |  |  |  | 2021-06-25 | [7 empty] | 2021-07-13 | 2021-07-13 | 0 | [15 empty] | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13 |  | 2021-07-13 | 0
121602477 | 1193 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 395.854 |  | 2021-06-25 |  | 2021-07-22 | 2021-06-30 | 2021-06-30 | 3 | 2021-07-26 | 20 | 2021-08-09 | 10 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-23 | 10 |  |  |  |  | 2021-06-25 | 2021-07-26 | 2021-08-05 | 28
121602847 | 1194 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 490 |  | 2021-06-25 | 2021-06-30 |  | 2021-06-25 | 2021-06-25 | 0 | 2021-07-21 | 17 | [27 empty] | 2021-06-25
121604471 | 1195 | PGE | NEM | EXPNEM | Implementation | Solar PV | 56.324 |  | 2021-06-25 |  |  | 2021-07-02 | 2021-07-02 | 5 | 2021-07-02 | 5 | 2021-07-20 | 11 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-07-26 | 4
121604580 | 1196 | PGE | NEM | EXPNEM | Implementation | Solar PV | 45.384 |  | 2021-06-25 |  | 2021-07-02 | 2021-07-02 | 2021-07-02 | 5 | 2021-07-15 | 13 | 2021-07-27 | 8 | [15 empty] | 2021-07-27 | 2021-07-30 | 3 | 2021-07-30 | 2021-08-06 | 5 |  |  |  |  | 2021-06-25 |  |  |  | 2021-07-23
121621808 | 1197 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 |  | 2021-06-28 |  | 2021-07-01 | 2021-06-30 | 2021-06-30 | 2 | 2021-07-01 | 3 | 2021-07-07 | 3 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | [6 empty] | 2021-06-28 | 2021-07-27 | 2021-08-06 | 28 | [7 empty] | 2021-07-26
121621925 | 1198 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-06-28 |  |  | 2021-07-07 | 2021-07-07 | 6 | 2021-07-07 | 6 | 2021-07-07 | 0 | [33 empty] | 2021-07-08 | 2021-07-08 | 0 | [15 empty] | 2021-07-08 |  |  | 2021-07-08 |  | 2021-07-08 | 0
121622681 | 1199 | PGE | NEM | EXPNEM | Application Submitted | Solar PV | 139.826 |  | 2021-06-28 |  | 2021-08-04 | 2021-07-12 | 2021-07-12 | 9 | [29 empty] | 2021-06-28
121624051 | 1200 | PGE | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-06-28 |  | 2021-07-02 | 2021-06-30 | 2021-06-30 | 2 | 2021-08-05 | 27 | 2021-08-20 | 11 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-20 | 2021-08-30 | 6 |  |  |  |  | 2021-06-28 | 2021-08-05 | 2021-08-13 | 33
121624263 | 1201 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 145.153 |  | 2021-06-28 |  | 2021-07-16 | 2021-06-30 | 2021-06-30 | 2 | 2021-07-22 | 17 | 2021-08-12 | 15 | [15 empty] | 2021-08-12 | 2021-08-12 | 0 | 2021-08-12 | 2021-08-18 | 4 |  |  |  |  | 2021-06-28 | 2021-07-01 | 2021-07-13 | 10
121624979 | 1202 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 627.287 |  | 2021-06-28 |  |  | 2021-07-13 | 2021-07-13 | 10 | 2021-07-13 | 10 | 2021-08-31 | 35 | [15 empty] | 2021-08-31 | 2021-09-03 | 3 | 2021-09-03 | [6 empty] | 2021-06-28
121630100 | 1204 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 72.441 |  | 2021-06-29 |  | 2021-07-12 | 2021-07-01 | 2021-07-01 | 2 | 2021-07-15 | 11 | 2021-09-02 | 35 | 2021-09-02 | [24 empty] | 2021-06-29 | 2021-08-20 | 2021-09-07 | 48
121630227 | 1205 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 52.163 |  | 2021-06-29 |  |  | 2021-07-06 | 2021-07-06 | 4 | 2021-07-06 | 4 | 2021-07-20 | 10 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | [6 empty] | 2021-06-29 | 2021-07-12 | 2021-07-23 | 17
121630590 | 1206 | PGE | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-06-29 |  |  | 2021-07-09 | 2021-07-09 | 7 | 2021-07-12 | 8 | 2021-08-05 | 18 | [15 empty] | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | 2021-08-06 | 1
121632075 | 1207 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 126.998 |  | 2021-06-29 |  | 2021-07-06 | 2021-07-06 | 2021-07-06 | 4 | 2021-07-13 | 9 | 2021-08-10 | 20 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-10 | [6 empty] | 2021-06-29 | 2021-07-13 | 2021-07-19 | 13
121632387 | 1208 | PGE | NEM | EXPNEM | Implementation | Solar PV | 600 |  | 2021-06-29 |  | 2021-07-12 | 2021-07-12 | 2021-07-12 | 8 | 2021-07-15 | 11 | 2021-07-27 | 8 | [15 empty] | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-08-26 | 22 |  |  |  |  | 2021-06-29 | 2021-07-15 | 2021-07-19 | 13
121632404 | 1209 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 57.443 |  | 2021-06-29 |  | 2021-07-07 | 2021-07-07 | 2021-07-07 | 5
121632751 | 1210 | PGE | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-06-29 |  |  | 2021-07-14 | 2021-07-14 | 10 | 2021-07-14 | 10 | 2021-07-30 | 12 | [15 empty] | 2021-07-30 | 2021-08-02 | 1 | 2021-08-02 | 2021-08-02 | 0 |  |  |  |  | 2021-06-29 |  |  |  | 2021-07-28
121633079 | 1211 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 500 |  | 2021-06-29 |  | 2021-08-03 | 2021-07-14 | 2021-07-14 | 10 | 2021-09-17 | 56 | [28 empty] | 2021-09-17
121633205 | 1212 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.909 |  | 2021-06-29 |  | 2021-07-07 | 2021-07-07 | 2021-07-07 | 5 | 2021-07-15 | 11 | 2021-07-20 | 3 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 | 2021-09-07 | 34 | [12 empty] | 2021-09-24 | 2021-09-30 | 4 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-30
121633368 | 1213 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 30.571 |  | 2021-06-29 |  | 2021-07-07 | 2021-07-07 | 2021-07-07 | 5
121634030 | 1214 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 129.827 |  | 2021-06-29 |  | 2021-07-29 | 2021-07-13 | 2021-07-13 | 9 | 2021-07-30 | 22 | 2021-08-19 | 14 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-09-07 | 12 | [12 empty] | 2021-09-23 | [17 empty] | 2021-09-23 | 2021-09-23 | 0
121636937 | 1215 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 38.78 |  | 2021-06-30 |  | 2021-08-13 | 2021-07-14 | 2021-07-14 | 9 | 2021-08-21 | 36 | 2021-09-08 | 11 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | [6 empty] | 2021-06-30 | 2021-09-09 | 2021-09-10 | 50
121639356 | 1216 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 549.991 |  | 2021-06-30 |  | 2021-07-29 | 2021-07-08 | 2021-07-08 | 5 | 2021-08-03 | 23 | 2021-09-08 | 25 | 2021-09-08 | 2021-09-27 | 13 | [22 empty] | 2021-06-30 | 2021-07-17 | 2021-07-28 | 19
121640615 | 1217 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 131.105 |  | 2021-06-30 |  | 2021-07-08 | 2021-07-08 | 2021-07-08 | 5 | 2021-08-18 | 34 | 2021-09-03 | 12 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | [6 empty] | 2021-06-30
121640894 | 1218 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 240 |  | 2021-06-30 |  | 2021-07-08 | 2021-07-08 | 2021-07-08 | 5 | 2021-07-13 | 8 | 2021-07-29 | 12 | [15 empty] | 2021-07-29 | 2021-07-29 | 0 | 2021-07-29 | 2021-08-11 | 9 |  |  |  |  | 2021-06-30 | 2021-07-27 | 2021-08-06 | 26
121641275 | 1219 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 372.261 |  | 2021-06-30 |  | 2021-08-10 | 2021-07-09 | 2021-07-09 | 6 | 2021-08-16 | 32 | 2021-09-03 | 14 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | [7 empty] | 2021-08-16 | 2021-08-27 | 9
120637986 | 1220 | PGE | NEM | SNEM | Study in Progress | Solar PV | 33.3 |  | 2021-03-12 |  | 2021-03-23 | 2021-03-23 | 2021-03-23 | 7 | 2021-06-16 | 67 | 2021-07-23 | 26 | [25 empty] | 2021-03-12
120673324 | 1221 | PGE | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 34.2 |  | 2021-03-22 |  |  | 2021-04-05 | 2021-04-05 | 10 | 2021-04-07 | 12 | 2021-04-09 | 2 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05
120771059 | 1222 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-04-09 |  | 2021-08-31 | 2021-04-22 | 2021-04-22 | 9 | [29 empty] | 2021-08-26
121513316 | 1223 | PGE | NEM | NEMMT | Application Review in Progress | ENGN, Solar PV | 625 |  | 2021-06-10 |  | 2021-06-23 | 2021-06-23 | 2021-06-23 | 9
121522845 | 1224 | PGE | NEM | EXPNEM | Commercial | Solar PV | 43.2 |  | 2021-06-11 |  | 2021-08-12 | 2021-07-16 | 2021-07-16 | 24 | 2021-08-17 | 46 | 2021-08-20 | 3 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-20 | 2021-08-23 | 1 | [12 empty] | 2021-08-23 | 2021-08-30 | 5 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-30 |  | 2021-09-07 | 5
121578810 | 1225 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 36.133 |  | 2021-06-22 |  | 2021-07-07 | 2021-07-07 | 2021-07-07 | 10 | [29 empty] | 2021-06-22
121626896 | 1226 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-06-28 | 2021-06-29 |  | 2021-06-29 | 2021-06-29 | 1 | 2021-07-28 | 21 | 2021-09-02 | 26 | [15 empty] | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02 | 2021-09-08 | 3
121642659 | 1227 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 |  | 2021-06-30 | 2021-07-01 |  | 2021-07-01 | 2021-07-01 | 1 | 2021-07-28 | 19 | 2021-08-26 | 21 | [15 empty] | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | 2021-09-05 | 6
121645055 | 1228 | PGE | NEM | NEM Paired Storage | Study in Progress | Storage | 96 |  | 2021-07-01 |  |  | 2021-07-07 | 2021-07-07 | 3 | 2021-07-07 | 3 | 2021-08-03 | 19 | 2021-08-12
121645132 | 1229 | PGE | NEM | EXPNEM | Commercial | Solar PV | 37.006 |  | 2021-07-01 |  | 2021-07-14 | 2021-07-14 | 2021-07-14 | 8 | 2021-07-22 | 14 | 2021-08-09 | 12 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-11 | 2 |  |  |  |  | 2021-07-01 | 2021-07-22 | 2021-07-29 | 19 |  |  |  |  | 2021-08-13 | 2021-08-27 | 10 | [15 empty] | 2021-08-13 | 2021-08-16 | 1 | 2021-08-27 |  | 2021-08-27 | 0
121645475 | 1230 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 250 |  | 2021-07-01 |  | 2021-07-15 | 2021-07-15 | 2021-07-15 | 9 | 2021-07-21 | 13 | 2021-08-09 | 13 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | [6 empty] | 2021-07-01 | 2021-07-21 | 2021-07-29 | 19
121645590 | 1231 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 36.387 |  | 2021-07-01 |  | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2 | 2021-07-09 | 5 | 2021-07-13 | 2 | [19 empty] | 2021-07-01 | N/A |  |  |  |  | 2021-07-01 | [10 empty] | 2021-08-16
121646778 | 1232 | PGE | Non-NEM | Non-Export | Application Accepted | ENGN | 1429 |  | 2021-07-01 | 2021-07-16 |  | 2021-07-16 | 2021-07-16 | 10 | 2021-08-04 | 23
121649129 | 1233 | PGE | NEM | SNEM | Application Submitted | Solar PV | 52.2 |  | 2021-07-01 |  | 2021-07-16 | 2021-07-16 | 2021-07-16 | 10
121649217 | 1234 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 76.547 |  | 2021-07-01 |  | 2021-07-26 | 2021-07-13 | 2021-07-13 | 7 | 2021-08-03 | 22 | 2021-08-23 | 14 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23
121654096 | 1235 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-07-02 |  | 2021-07-14 | 2021-07-14 | 2021-07-14 | 7 | 2021-08-10 | 26 | 2021-08-10 | 0 | [25 empty] | 2021-07-02 | 2021-08-30 | 2021-08-30 | 40 |  |  |  |  | 2021-08-30 | 2021-09-08 | 6 | [15 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-09-08 |  | 2021-09-09 | 1
121655443 | 1236 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 192 |  | 2021-07-02 |  | 2021-07-13 | 2021-07-13 | 2021-07-13 | 6 | 2021-07-14 | 7 | 2021-09-07 | 38 | [15 empty] | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-09-08 | 1 |  |  |  |  | 2021-07-02
121655489 | 1237 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 998.26 |  | 2021-07-02 |  | 2021-07-19 | 2021-07-19 | 2021-07-19 | 10 | 2021-08-04 | 22 | 2021-09-08 | 24 | [15 empty] | 2021-09-08 | 2021-09-23 | 11 | 2021-09-23
121656755 | 1238 | PGE | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-07-02 |  | 2021-07-15 | 2021-07-15 | 2021-07-15 | 8 | 2021-07-30 | 19 | 2021-08-30 | 21 | [15 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-09-01 | 2 |  |  |  |  | 2021-07-02 | 2021-09-30
121657104 | 1239 | PGE | NEM | EXPNEM | Implementation | Solar PV | 816 |  | 2021-07-02 |  | 2021-07-16 | 2021-07-16 | 2021-07-16 | 9 | 2021-07-23 | 14 | 2021-08-09 | 11 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-23 | 10
121657804 | 1240 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 306.642 |  | 2021-07-02 |  | 2021-07-19 | 2021-07-19 | 2021-07-19 | 10
121664116 | 1241 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.4 |  | 2021-07-05 |  | 2021-07-27 | 2021-07-15 | 2021-07-15 | 7 | 2021-08-06 | 23 | 2021-08-10 | 2 | [33 empty] | 2021-08-10 | 2021-08-10 | 0 | [15 empty] | 2021-08-10 |  |  | 2021-08-10 |  | 2021-08-10 | 0
121664160 | 1242 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 181.47 |  | 2021-07-05 |  | 2021-07-16 | 2021-07-16 | 2021-07-16 | 8 | 2021-07-22 | 12 | [27 empty] | 2021-07-05 | 2021-07-26 | 2021-08-09 | 24
121664841 | 1243 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 34.179 |  | 2021-07-05 |  | 2021-07-16 | 2021-07-16 | 2021-07-16 | 8 | [29 empty] | 2021-07-05
121665205 | 1244 | PGE | NEM | EXPNEM | Implementation | Solar PV | 375 |  | 2021-07-05 |  | 2021-07-19 | 2021-07-19 | 2021-07-19 | 9 | 2021-08-05 | 22 | 2021-08-18 | 9 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | 2021-09-07 | 13 |  |  |  |  | 2021-07-05 | 2021-08-06 | 2021-08-18 | 31
121667563 | 1245 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.232 |  | 2021-07-06 |  |  | 2021-07-15 | 2021-07-15 | 7 | 2021-07-15 | 7 | 2021-07-19 | 2 | [33 empty] | 2021-07-20 | 2021-07-22 | 2 | [15 empty] | 2021-07-20 | 2021-07-20 | 0 | 2021-07-22 |  | 2021-07-26 | 2
121667574 | 1246 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 30.373 |  | 2021-07-06 |  | 2021-07-19 | 2021-07-19 | 2021-07-19 | 9 | [29 empty] | 2021-07-06
121669113 | 1247 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 51.589 |  | 2021-07-06 |  | 2021-08-11 | 2021-07-13 | 2021-07-13 | 5 | 2021-09-13 | 48 | [27 empty] | 2021-07-06 | 2021-08-23 | 2021-09-07 | 44
121669762 | 1248 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 643.5 |  | 2021-07-06 | 2021-07-07 |  | 2021-07-07 | 2021-07-07 | 1 | 2021-07-28 | 16 | 2021-09-30 | 45 | [15 empty] | 2021-07-30 | 2021-07-30 | 0 | 2021-07-30 | [6 empty] | 2021-07-06
121669763 | 1249 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-07-06 |  | 2021-07-20 | 2021-07-20 | 2021-07-20 | 10 | [19 empty] | 2021-09-24 | [9 empty] | 2021-07-06 | 2021-08-16 | 2021-08-27 | 38
121669924 | 1250 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 86.4 |  | 2021-07-06 |  | 2021-07-20 | 2021-07-20 | 2021-07-20 | 10 | 2021-09-08 | 45 | 2021-09-29 | 15 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | [6 empty] | 2021-07-06 | 2021-09-25
121669991 | 1251 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 86.4 |  | 2021-07-06 |  | 2021-07-20 | 2021-07-20 | 2021-07-20 | 10 | 2021-09-25 | 57 | [27 empty] | 2021-07-06 | 2021-09-25
121670131 | 1252 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 73.256 |  | 2021-07-06 |  | 2021-07-20 | 2021-07-20 | 2021-07-20 | 10 | 2021-09-25 | 57 | [27 empty] | 2021-07-06 | 2021-09-25
121670323 | 1253 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.987 |  | 2021-07-06 |  | 2021-07-13 | 2021-07-13 | 2021-07-13 | 5 | 2021-07-22 | 12 | 2021-08-04 | 9 | [15 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | 2021-08-09 | 3 |  |  |  |  | 2021-07-06 | [30 empty] | 2021-08-09
121671009 | 1254 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 180 |  | 2021-07-06 |  | 2021-07-14 | 2021-07-09 | 2021-07-09 | 3 | 2021-07-20 | 10 | 2021-08-02 | 9 | 2021-08-02 | 2021-08-30 | 20 | [12 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | [6 empty] | 2021-07-06 | 2021-07-20 | 2021-07-28 | 16
121671470 | 1255 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 48.827 |  | 2021-07-06 |  | 2021-07-19 | 2021-07-19 | 2021-07-19 | 9 | 2021-08-09 | 24 | 2021-08-27 | 14 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | [6 empty] | 2021-07-06 | 2021-09-17
121672569 | 1256 | PGE | NEM | VNEM | IA in Progress | Solar PV | 35.67 |  | 2021-07-07 |  | 2021-07-21 | 2021-07-21 | 2021-07-21 | 10 | 2021-08-06 | 22 | 2021-08-27 | 15 | [15 empty] | 2021-08-27 | 2021-09-20 | 15 | 2021-09-20 | [6 empty] | 2021-07-07
121672781 | 1257 | PGE | NEM | VNEM | IA in Progress | Solar PV | 35.38 |  | 2021-07-07 |  | 2021-07-21 | 2021-07-21 | 2021-07-21 | 10 | 2021-08-06 | 22 | 2021-08-27 | 15 | [15 empty] | 2021-08-27 | 2021-09-20 | 15 | 2021-09-20 | [6 empty] | 2021-07-07
121672913 | 1258 | PGE | NEM | VNEM | IA in Progress | Solar PV | 35.67 |  | 2021-07-07 |  | 2021-07-21 | 2021-07-21 | 2021-07-21 | 10 | 2021-08-06 | 22 | 2021-08-27 | 15 | [15 empty] | 2021-08-27 | 2021-09-20 | 15 | 2021-09-20 | [6 empty] | 2021-07-07
121672985 | 1259 | PGE | NEM | VNEM | IA in Progress | Solar PV | 53.36 |  | 2021-07-07 |  | 2021-07-21 | 2021-07-21 | 2021-07-21 | 10 | 2021-08-06 | 22 | 2021-08-27 | 15 | [15 empty] | 2021-08-27 | 2021-09-20 | 15 | 2021-09-20 | [6 empty] | 2021-07-07
121674078 | 1260 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 63.292 |  | 2021-07-07 |  | 2021-07-13 | 2021-07-13 | 2021-07-13 | 4 | 2021-07-26 | 13 | 2021-08-16 | 15 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | [6 empty] | 2021-07-07 |  |  |  | 2021-08-06
121674165 | 1261 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 62.872 |  | 2021-07-07 |  | 2021-07-13 | 2021-07-13 | 2021-07-13 | 4 | 2021-07-26 | 13 | 2021-08-16 | 15 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | [6 empty] | 2021-07-07 |  |  |  | 2021-08-06
121675223 | 1262 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-07-07 |  | 2021-08-05 | 2021-07-13 | 2021-07-13 | 4 | 2021-08-05 | 21 | [17 empty] | 2021-08-17 | 2021-08-17 | 0 | 2021-08-17 | [6 empty] | 2021-07-07 |  |  |  | 2021-07-23
121676464 | 1263 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 83.3 |  | 2021-07-07 |  | 2021-08-05 | 2021-07-13 | 2021-07-13 | 4 | 2021-08-09 | 23 | [5 empty] | 2021-08-09 | 2021-09-17 | 28 | 2021-09-17
121677360 | 1264 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 139.15 |  | 2021-07-07 |  | 2021-07-27 | 2021-07-19 | 2021-07-19 | 8 | [30 empty] | 2021-07-23 | 2021-08-04 | 8
121677853 | 1265 | PGE | NEM | EXPNEM | Implementation | Solar PV | 434.952 |  | 2021-07-07 |  | 2021-07-13 | 2021-07-13 | 2021-07-13 | 4 | 2021-07-21 | 10 | 2021-08-25 | 25 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | 2021-09-08 | 9 |  |  |  |  | 2021-07-07 | 2021-07-21 | 2021-07-29 | 16
121677966 | 1266 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.545 |  | 2021-07-07 |  | 2021-08-10 | 2021-07-16 | 2021-07-16 | 7
121678341 | 1267 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 37.598 |  | 2021-07-07 |  | 2021-07-20 | 2021-07-20 | 2021-07-20 | 9 | 2021-08-02 | 18 | 2021-08-23 | 15 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23 | [6 empty] | 2021-07-07 | 2021-07-28 | 2021-08-13 | 27
121678407 | 1268 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 63.182 |  | 2021-07-07 |  | 2021-07-20 | 2021-07-20 | 2021-07-20 | 9 | 2021-08-02 | 18 | [27 empty] | 2021-07-07 | 2021-09-08 | 2021-09-10 | 46 |  | 2021-09-24 | 2021-09-24 | 0
121678996 | 1269 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 75.43 |  | 2021-07-07 |  | 2021-07-16 | 2021-07-16 | 2021-07-16 | 7 | 2021-07-26 | 13 | 2021-09-13 | 34 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | [6 empty] | 2021-07-07 |  |  |  | 2021-08-06
121678998 | 1270 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 66.259 |  | 2021-07-07 |  | 2021-07-16 | 2021-07-16 | 2021-07-16 | 7 | 2021-07-26 | 13 | 2021-08-16 | 15 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | [6 empty] | 2021-07-07 |  |  |  | 2021-08-06
121679712 | 1271 | PGE | Non-NEM | Continuous Uncompensated Export | IA in Progress | ENGN, Solar PV | 66.6 |  | 2021-07-07 | 2021-07-08 |  | 2021-07-08 | 2021-07-08 | 1 | 2021-07-14 | 5 | 2021-09-27 | 52 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27
121679736 | 1272 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 38.27 |  | 2021-07-07 |  | 2021-09-13 | 2021-07-16 | 2021-07-16 | 7
121681799 | 1273 | PGE | Non-NEM | Non-Export | Study in Progress | ENGN | 170 |  | 2021-07-08 | 2021-07-08 |  | 2021-07-08 | 2021-07-08 | 0 | 2021-07-21 | 9 | 2021-08-25 | 25 | 2021-09-30 | [24 empty] | 2021-08-04 | 2021-08-06 | 2021-08-06 | 2
121684141 | 1274 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.53 |  | 2021-07-08 |  | 2021-07-13 | 2021-07-13 | 2021-07-13 | 3 | 2021-07-26 | 12 | 2021-08-11 | 12 | [15 empty] | 2021-08-11 | 2021-08-11 | 0 | 2021-08-11 | 2021-08-20 | 7 | [12 empty] | 2021-09-10 | 2021-09-20 | 6 | [15 empty] | 2021-09-10 | 2021-09-12 | 0 | 2021-09-20
121684217 | 1275 | PGE | NEM | VNEM | IA in Progress | Solar PV | 33.39 |  | 2021-07-08 |  | 2021-07-15 | 2021-07-15 | 2021-07-15 | 5 | 2021-08-24 | 33 | 2021-09-13 | 13 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-09-17 | 4 |  |  |  |  | 2021-07-08 |  |  |  | 2021-08-06 | 2021-08-24 | 2021-08-25 | 12
121684550 | 1276 | PGE | NEM | VNEM | IA in Progress | Solar PV | 32.445 |  | 2021-07-08 |  | 2021-07-15 | 2021-07-15 | 2021-07-15 | 5 | 2021-08-24 | 33 | 2021-09-15 | 15 | [15 empty] | 2021-09-15 | [9 empty] | 2021-07-08 |  |  |  | 2021-08-06
121687252 | 1277 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.116 |  | 2021-07-09 |  |  | 2021-07-17 | 2021-07-17 | 5 | 2021-07-17 | 5 | 2021-07-20 | 1 | [25 empty] | 2021-07-09 | 2021-08-20 | 2021-08-20 | 30 |  |  |  |  | 2021-08-20 | 2021-08-27 | 5 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-27 |  | 2021-08-31 | 2
121690217 | 1278 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 1560 |  | 2021-07-09 | 2021-07-09 |  | 2021-07-09 | 2021-07-09 | 0 | 2021-07-21 | 8 | 2021-08-13 | 17 | [25 empty] | 2021-07-09 | 2021-07-30
121693828 | 1279 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 850 |  | 2021-07-09 |  | 2021-09-16 | 2021-07-19 | 2021-07-19 | 6 | 2021-09-24 | 54 | [27 empty] | 2021-07-09 |  |  |  | 2021-09-07
121709667 | 1280 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 37.957 |  | 2021-07-11 |  |  | 2021-07-19 | 2021-07-19 | 5 | 2021-07-19 | 5 | 2021-07-19 | 0 | [33 empty] | 2021-07-19 | 2021-07-19 | 0 | [15 empty] | 2021-07-19 |  |  | 2021-07-19 |  | 2021-07-19 | 0
121712221 | 1281 | PGE | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 35.116 |  | 2021-07-12 |  |  | 2021-07-19 | 2021-07-19 | 5 | 2021-07-19 | 5 | 2021-07-21 | 2 | [25 empty] | 2021-07-12
121713542 | 1282 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 52.163 |  | 2021-07-12 |  | 2021-07-26 | 2021-07-26 | 2021-07-26 | 10 | 2021-09-08 | 41 | 2021-09-29 | 15 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | [6 empty] | 2021-07-12
121713944 | 1283 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 814.048 |  | 2021-07-12 |  | 2021-08-03 | 2021-07-14 | 2021-07-14 | 2 | 2021-08-06 | 19 | 2021-08-25 | 13 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | [6 empty] | 2021-07-12
121714055 | 1284 | PGE | NEM | EXPNEM | Commercial | Solar PV | 34.179 |  | 2021-07-12 |  | 2021-07-26 | 2021-07-15 | 2021-07-15 | 3 | 2021-08-02 | 15 | 2021-08-09 | 5 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-10 | 1 | [12 empty] | 2021-08-18 | 2021-08-24 | 4 | [15 empty] | 2021-08-18 | 2021-08-19 | 1 | 2021-08-24 |  | 2021-08-27 | 3
121714415 | 1285 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 240 |  | 2021-07-12 |  | 2021-07-29 | 2021-07-22 | 2021-07-22 | 8
121715895 | 1286 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 350 |  | 2021-07-12 | 2021-07-13 |  | 2021-07-13 | 2021-07-13 | 1 | 2021-07-28 | 12 | 2021-08-18 | 15 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | [6 empty] | 2021-07-12
121716126 | 1287 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 560 |  | 2021-07-12 | 2021-07-13 |  | 2021-07-13 | 2021-07-13 | 1 | 2021-07-28 | 12 | 2021-08-23 | 18 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23
121716351 | 1288 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.964 |  | 2021-07-12 |  | 2021-08-04 | 2021-07-20 | 2021-07-20 | 6
121716853 | 1289 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 975 |  | 2021-07-12 |  | 2021-07-23 | 2021-07-19 | 2021-07-19 | 5 | 2021-07-30 | 14 | 2021-08-17 | 12 | 2021-08-17 | 2021-09-22 | 25 | 2021-09-22 | [21 empty] | 2021-07-12 | 2021-07-30 | 2021-08-13 | 24
121716964 | 1290 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 636 |  | 2021-07-12 |  | 2021-08-20 | 2021-07-26 | 2021-07-26 | 10
121717092 | 1291 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-07-12 |  | 2021-07-20 | 2021-07-20 | 2021-07-20 | 6 | 2021-08-04 | 17 | 2021-08-04 | 0 | [33 empty] | 2021-08-04 | 2021-08-04 | 0 | [15 empty] | 2021-08-04 |  |  | 2021-08-04 |  | 2021-08-04 | 0
121717607 | 1292 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 96.768 |  | 2021-07-12 |  | 2021-07-19 | 2021-07-19 | 2021-07-19 | 5 | 2021-07-22 | 8 | 2021-08-10 | 13 | 2021-08-10 | 2021-09-07 | 19 | 2021-09-08 | [21 empty] | 2021-07-12 | 2021-07-26 | 2021-08-09 | 20
121718040 | 1293 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 46.536 |  | 2021-07-12 |  | 2021-07-26 | 2021-07-15 | 2021-07-15 | 3 | 2021-07-31 | 14 | 2021-08-09 | 5 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-09-08 | 21
121719754 | 1294 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 105.56 |  | 2021-07-13 |  | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2 | 2021-07-23 | 8 | 2021-08-10 | 12 | [15 empty] | 2021-08-10 | 2021-08-10 | 0 | 2021-08-10 | 2021-08-18 | 6 |  |  |  |  | 2021-07-13 | 2021-07-15 | 2021-07-28 | 11
121721397 | 1295 | PGE | NEM | SNEM Paired Storage | IA in Progress | Solar PV, Storage | 35.08 |  | 2021-07-13 |  | 2021-09-24 | 2021-07-27 | 2021-07-27 | 10 | [23 empty] | 2021-07-16 | N/A
121722288 | 1296 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 115.42 |  | 2021-07-13 |  | 2021-07-27 | 2021-07-27 | 2021-07-27 | 10 | 2021-08-05 | 17 | 2021-08-26 | 15 | [15 empty] | 2021-08-26 | 2021-09-16 | 14 | 2021-09-16 | [6 empty] | 2021-07-13 | 2021-08-17 | 2021-08-25 | 31 |  | 2021-08-26 | 2021-09-16 | 14
121722546 | 1297 | PGE | NEM | EXPNEM | Implementation | Solar PV | 300 |  | 2021-07-13 |  |  | 2021-07-20 | 2021-07-20 | 5 | 2021-07-20 | 5 | 2021-08-16 | 19 | [15 empty] | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | 2021-08-17 | 1 |  |  |  |  | 2021-07-13 | 2021-07-30 | 2021-08-13 | 23 | [7 empty] | 2021-09-08
121725874 | 1298 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 45.116 |  | 2021-07-14 |  |  | 2021-07-21 | 2021-07-21 | 5 | 2021-07-21 | 5 | 2021-07-22 | 1 | [25 empty] | 2021-07-14 | [7 empty] | 2021-07-22 | 2021-07-22 | 0 | [15 empty] | 2021-07-22 |  |  | 2021-07-22 |  | 2021-07-22 | 0
121726540 | 1299 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 35.09 |  | 2021-07-14 |  | 2021-07-16 | 2021-07-16 | 2021-07-16 | 2 | [29 empty] | 2021-07-14
121726607 | 1300 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 51.939 |  | 2021-07-14 |  | 2021-07-30 | 2021-07-20 | 2021-07-20 | 4 | 2021-08-04 | 15 | [27 empty] | 2021-07-14 | 2021-09-23 | 2021-09-28 | 53
121727091 | 1301 | PGE | NEM | EXPNEM | Commercial | Solar PV | 34.29 |  | 2021-07-14 |  | 2021-07-20 | 2021-07-20 | 2021-07-20 | 4 | 2021-07-20 | 4 | 2021-08-09 | 14 | [15 empty] | 2021-08-09 | 2021-08-16 | 5 | 2021-08-16 | 2021-08-16 | 0 |  |  |  |  | 2021-07-14 |  |  |  | 2021-08-06 |  |  |  | 2021-08-09 | 2021-08-16 | 5 | [15 empty] | 2021-08-09 | 2021-08-10 | 1 | 2021-08-16 |  | 2021-08-16 | 0
121729951 | 1302 | PGE | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-07-14 |  | 2021-07-23 | 2021-07-23 | 2021-07-23 | 7 | 2021-08-31 | 34 | 2021-09-15 | 10 | [15 empty] | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | 2021-09-15 | 0 |  |  |  |  | 2021-07-14 | 2021-08-31 | 2021-09-10 | 41 |  |  |  |  | 2021-09-28 | [17 empty] | 2021-09-28 | 2021-09-28 | 0
121730121 | 1303 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 420 |  | 2021-07-14 | 2021-07-14 |  | 2021-07-14 | 2021-07-14 | 0 | 2021-08-11 | 20 | [27 empty] | 2021-07-14
121731246 | 1304 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.66 |  | 2021-07-14 |  | 2021-09-16 | 2021-07-22 | 2021-07-22 | 6 | 2021-09-27 | 52 | 2021-09-28 | 1 | [33 empty] | 2021-09-28 | 2021-09-28 | 0 | [15 empty] | 2021-09-28 |  |  | 2021-09-28 |  | 2021-09-28 | 0
121731507 | 1305 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 437.5 |  | 2021-07-14 |  | 2021-07-26 | 2021-07-26 | 2021-07-26 | 8 | 2021-08-10 | 19 | 2021-08-31 | 15 | [15 empty] | 2021-08-31 | 2021-09-22 | 15 | 2021-09-22 | [6 empty] | 2021-07-14 |  |  |  | 2021-08-13
121734791 | 1306 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 54.45 |  | 2021-07-15 |  | 2021-07-26 | 2021-07-26 | 2021-07-26 | 7 | [29 empty] | 2021-07-15
121735402 | 1307 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 33.3 |  | 2021-07-15 |  | 2021-07-27 | 2021-07-27 | 2021-07-27 | 8 | 2021-07-27 | 8 | 2021-08-17 | 15 | [15 empty] | 2021-08-17 | 2021-08-17 | 0 | 2021-08-17
121735517 | 1308 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.309 |  | 2021-07-15 |  | 2021-07-22 | 2021-07-22 | 2021-07-22 | 5 | 2021-08-04 | 14 | 2021-08-06 | 2 | [33 empty] | 2021-08-06 | 2021-08-06 | 0 | [15 empty] | 2021-08-06 |  |  | 2021-08-06 |  | 2021-08-06 | 0
121735711 | 1309 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 666.6 |  | 2021-07-15 |  | 2021-07-28 | 2021-07-28 | 2021-07-28 | 9 | 2021-08-12 | 20 | 2021-08-27 | 11 | 2021-08-27 | 2021-09-23 | 18 | 2021-09-23 | [21 empty] | 2021-07-15 | 2021-07-30 | 2021-08-13 | 21
121736634 | 1310 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 129.767 |  | 2021-07-15 |  | 2021-08-05 | 2021-08-03 | 2021-08-03 | 13 | 2021-08-20 | 26 | 2021-09-08 | 12 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-09-09 | 1 |  |  |  |  | 2021-07-15 | 2021-09-23
121737090 | 1311 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 42.775 |  | 2021-07-15 |  | 2021-09-29 | 2021-07-23 | 2021-07-23 | 6
121738475 | 1312 | PGE | NEM | EXPNEM | Commercial | Solar PV | 125 |  | 2021-07-15 |  | 2021-08-10 | 2021-07-28 | 2021-07-28 | 9 | 2021-08-12 | 20 | 2021-08-27 | 11 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-08-30 | 1 |  |  |  |  | 2021-07-15 | 2021-08-30 | 2021-09-10 | 40 |  |  |  |  | 2021-09-21 | 2021-09-30 | 7 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-30 |  | 2021-09-30 | 0
121742796 | 1313 | PGE | NEM | EXPNEM | Study in Progress | FUCE | 999.5 |  | 2021-07-16 |  |  | 2021-07-26 | 2021-07-26 | 6 | 2021-07-26 | 6 | 2021-08-16 | 15 | 2021-08-16 | 2021-09-20 | 24 | 2021-09-23 | [21 empty] | 2021-07-16
121743503 | 1314 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 32.47 |  | 2021-07-16 |  | 2021-07-26 | 2021-07-26 | 2021-07-26 | 6 | 2021-08-12 | 19 | 2021-08-13 | 1 | [33 empty] | 2021-08-16 | 2021-08-16 | 0 | [15 empty] | 2021-08-16 |  |  | 2021-08-16 |  | 2021-08-16 | 0
121743843 | 1315 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 300 |  | 2021-07-16 |  | 2021-08-09 | 2021-07-26 | 2021-07-26 | 6 | 2021-08-16 | 21 | 2021-09-01 | 12 | [15 empty] | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01
121743878 | 1316 | PGE | NEM | EXPNEM | Commercial | Solar PV | 100 |  | 2021-07-16 |  | 2021-07-26 | 2021-07-26 | 2021-07-26 | 6 | 2021-08-04 | 13 | 2021-08-18 | 10 | [15 empty] | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | 2021-08-20 | 2 |  |  |  |  | 2021-07-16 | 2021-08-02 | 2021-08-13 | 20 |  |  |  |  | 2021-08-20 | 2021-08-26 | 4 | [15 empty] | 2021-08-20 | 2021-08-23 | 1 | 2021-08-26 |  | 2021-08-30 | 2
121743879 | 1317 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 31.578 |  | 2021-07-16 |  | 2021-07-26 | 2021-07-26 | 2021-07-26 | 6 | [29 empty] | 2021-07-16
121746096 | 1318 | PGE | NEM | EXPNEM | Implementation | Solar PV | 170 |  | 2021-07-16 |  | 2021-07-30 | 2021-07-29 | 2021-07-29 | 9 | 2021-08-05 | 14 | 2021-08-20 | 11 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-20 | 2021-09-17 | 19 |  |  |  |  | 2021-07-16 | 2021-08-05 | 2021-08-13 | 20
121746802 | 1319 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 125.259 |  | 2021-07-16 |  |  | 2021-07-29 | 2021-07-29 | 9 | 2021-07-29 | 9 | 2021-08-09 | 7 | [15 empty] | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | [6 empty] | 2021-07-16 | 2021-08-23 | 2021-08-23 | 26
121752722 | 1320 | PGE | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 31.022 |  | 2021-07-19 |  |  | 2021-07-27 | 2021-07-27 | 6 | 2021-07-27 | 6 | 2021-07-28 | 1 | [25 empty] | 2021-07-19
121754384 | 1321 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 1240.07 |  | 2021-07-19 | 2021-07-26 |  | 2021-07-26 | 2021-07-26 | 5 | 2021-08-04 | 12 | 2021-09-14 | 28 | [25 empty] | 2021-07-19 | 2021-08-20 | 2021-09-07 | 35
121754976 | 1322 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 420 |  | 2021-07-19 |  | 2021-09-13 | 2021-07-26 | 2021-07-26 | 5
121757817 | 1323 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 3960 |  | 2021-07-19 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 8 | 2021-09-16 | 42 | [5 empty] | 2021-09-16
121760674 | 1324 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 64.86 |  | 2021-07-20 |  | 2021-09-24 | 2021-07-20 | 2021-07-20 | 0
121761647 | 1325 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.6 |  | 2021-07-20 |  | 2021-07-29 | 2021-07-29 | 2021-07-29 | 7
121761800 | 1326 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.375 |  | 2021-07-20 |  | 2021-08-12 | 2021-07-29 | 2021-07-29 | 7 | [29 empty] | 2021-07-20
121762277 | 1327 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 600 |  | 2021-07-20 |  | 2021-07-26 | 2021-07-26 | 2021-07-26 | 4 | 2021-09-03 | 33 | 2021-09-30 | 18 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | [6 empty] | 2021-07-20 | 2021-08-21 | 2021-08-27 | 28
121763000 | 1328 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 56.444 |  | 2021-07-20 |  | 2021-07-27 | 2021-07-27 | 2021-07-27 | 5 | 2021-09-29 | 50
121764162 | 1329 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 167.863 |  | 2021-07-20 |  | 2021-07-28 | 2021-07-28 | 2021-07-28 | 6 | [29 empty] | 2021-07-20
121765603 | 1330 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 32.095 |  | 2021-07-20 |  | 2021-08-03 | 2021-08-03 | 2021-08-03 | 10 | 2021-08-16 | 19 | 2021-09-03 | 14 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-07 | 1 |  |  |  |  | 2021-07-20 | 2021-08-23 | 2021-09-07 | 34 |  |  |  |  | 2021-09-20 | 2021-09-28 | 6 | [15 empty] | 2021-09-20 | 2021-09-20 | 0 | 2021-09-28
121767242 | 1331 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 95.738 |  | 2021-07-21 |  | 2021-08-20 | 2021-07-28 | 2021-07-28 | 5
121770110 | 1332 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-07-21 |  | 2021-07-30 | 2021-07-30 | 2021-07-30 | 7 | 2021-08-13 | 17 | 2021-08-13 | 0 | [33 empty] | 2021-08-13 | 2021-08-13 | 0 | [15 empty] | 2021-08-13 |  |  | 2021-08-13 |  | 2021-08-13 | 0
121770192 | 1333 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 144.967 |  | 2021-07-21 |  | 2021-07-28 | 2021-07-28 | 2021-07-28 | 5 | [29 empty] | 2021-07-21
121770675 | 1334 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 402.52 |  | 2021-07-21 |  | 2021-07-28 | 2021-07-28 | 2021-07-28 | 5 | [29 empty] | 2021-07-21
121771508 | 1335 | PGE | NEM | EXPNEM | Implementation | Solar PV | 58.623 |  | 2021-07-21 |  | 2021-08-11 | 2021-07-29 | 2021-07-29 | 6 | 2021-08-26 | 26 | 2021-09-09 | 9 | [15 empty] | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 | 2021-09-09 | 0
121776517 | 1336 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 |  | 2021-07-22 |  | 2021-08-02 | 2021-08-02 | 2021-08-02 | 7 | [29 empty] | 2021-07-22
121778028 | 1337 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 227.661 |  | 2021-07-22 |  | 2021-08-17 | 2021-07-29 | 2021-07-29 | 5
121778329 | 1338 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.204 |  | 2021-07-22 |  | 2021-07-31 | 2021-07-22 | 2021-07-22 | 0 | 2021-08-12 | 15 | 2021-09-07 | 17 | [33 empty] | 2021-09-07 | 2021-09-07 | 0 | [15 empty] | 2021-09-07 |  |  | 2021-09-07 |  | 2021-09-07 | 0
121780249 | 1339 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 1000 |  | 2021-07-22 |  | 2021-08-03 | 2021-07-30 | 2021-07-30 | 6 | 2021-08-11 | 14 | 2021-09-09 | 20 | 2021-09-14 | [24 empty] | 2021-07-22 | 2021-07-30 | 2021-08-09 | 12
121780388 | 1340 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 32.269 |  | 2021-07-22 |  | 2021-09-13 | 2021-07-23 | 2021-07-23 | 1 | 2021-09-24 | 45 | [27 empty] | 2021-07-22 | 2021-09-24 | 2021-09-28 | 47
121784437 | 1341 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-07-23 |  | 2021-08-02 | 2021-08-02 | 2021-08-02 | 6 | 2021-08-20 | 20 | 2021-08-26 | 4 | [25 empty] | 2021-07-23 | 2021-09-13 | 2021-09-13 | 35 |  |  |  |  | 2021-09-13 | 2021-09-13 | 0 | [15 empty] | 2021-09-13 |  |  | 2021-09-13 |  | 2021-09-13 | 0
121784570 | 1342 | PGE | Non-NEM | Non-Export | Implementation | Storage | 280 |  | 2021-07-23 | 2021-07-23 |  | 2021-07-23 | 2021-07-23 | 0 | 2021-08-11 | 13 | 2021-09-08 | 19 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-09-10 | 2 |  |  |  |  | 2021-07-23
121785644 | 1343 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 956.275 |  | 2021-07-23 |  | 2021-08-19 | 2021-08-05 | 2021-08-05 | 9 | 2021-09-14 | 36 | 2021-09-24 | 8 | 2021-09-24 | [24 empty] | 2021-07-23
121786065 | 1344 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 35.139 |  | 2021-07-23 |  | 2021-08-05 | 2021-08-03 | 2021-08-03 | 7 | 2021-09-13 | 35 | 2021-09-15 | 2 | [15 empty] | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | [6 empty] | 2021-07-23 | 2021-09-15 | 2021-09-22 | 42
121786105 | 1345 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 929.5 |  | 2021-07-23 | 2021-07-23 |  | 2021-07-23 | 2021-07-23 | 0 | 2021-08-11 | 13 | [27 empty] | 2021-07-23 | 2021-08-13 | 2021-08-27 | 25
121786333 | 1346 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 92.11 |  | 2021-07-23 |  | 2021-08-18 | 2021-08-02 | 2021-08-02 | 6 | 2021-08-21 | 20 | 2021-09-29 | 26 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | [6 empty] | 2021-07-23 | 2021-08-18 | 2021-09-07 | 31
121786720 | 1347 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 600 |  | 2021-07-23 |  | 2021-08-03 | 2021-08-03 | 2021-08-03 | 7 | [29 empty] | 2021-07-23 | 2021-08-03 | 2021-08-04 | 8
121787477 | 1348 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 45.226 |  | 2021-07-23 |  | 2021-08-03 | 2021-08-03 | 2021-08-03 | 7 | 2021-08-16 | 16 | 2021-08-16 | 0 | [33 empty] | 2021-08-16 | 2021-08-16 | 0 | [15 empty] | 2021-08-16 |  |  | 2021-08-16 |  | 2021-08-16 | 0
121787561 | 1349 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 100 |  | 2021-07-23 |  | 2021-07-26 | 2021-07-26 | 2021-07-26 | 1
121789750 | 1350 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 37.95 |  | 2021-07-24 |  |  | 2021-08-03 | 2021-08-03 | 6 | 2021-08-03 | 6 | 2021-08-05 | 2 | [33 empty] | 2021-08-05 | 2021-08-05 | 0 | [15 empty] | 2021-08-05 |  |  | 2021-08-05 |  | 2021-08-05 | 0
121795009 | 1351 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.428 |  | 2021-07-26 |  |  | 2021-08-03 | 2021-08-03 | 6 | 2021-08-03 | 6 | 2021-08-05 | 2 | [33 empty] | 2021-08-05 | 2021-08-05 | 0 | [15 empty] | 2021-08-05 |  |  | 2021-08-05 |  | 2021-08-05 | 0
121795306 | 1352 | PGE | NEM | EXPNEM | Implementation | Solar PV | 41.882 |  | 2021-07-26 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 7 | 2021-08-18 | 17 | 2021-09-08 | 14 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-09-13 | 3
121797033 | 1353 | PGE | NEM | EXPNEM | Implementation | Solar PV | 32.858 |  | 2021-07-26 |  |  | 2021-08-04 | 2021-08-04 | 7 | 2021-08-04 | 7 | 2021-08-17 | 9 | [15 empty] | 2021-08-17 | 2021-08-18 | 1 | 2021-08-18 | 2021-09-17 | 21 |  |  |  |  | 2021-07-26 | 2021-08-05 | 2021-08-17 | 16
121797187 | 1354 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 |  | 2021-07-26 |  | 2021-08-03 | 2021-08-03 | 2021-08-03 | 6 | 2021-09-01 | 27 | 2021-09-22 | 14 | [15 empty] | 2021-09-22 | 2021-09-22 | 0 | 2021-09-22
121798062 | 1355 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-07-26 |  | 2021-08-10 | 2021-08-03 | 2021-08-03 | 6 | 2021-08-13 | 14 | 2021-08-31 | 12 | [15 empty] | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31
121798064 | 1356 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 816 |  | 2021-07-26 |  | 2021-08-09 | 2021-08-09 | 2021-08-09 | 10 | 2021-09-08 | 31 | 2021-09-29 | 15 | 2021-09-29 | [28 empty] | 2021-09-10
121799926 | 1357 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 33.249 |  | 2021-07-26 |  | 2021-08-18 | 2021-08-04 | 2021-08-04 | 7 | 2021-08-24 | 21 | [27 empty] | 2021-07-26 | 2021-08-24 | 2021-09-08 | 31
121800454 | 1358 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 |  | 2021-07-26 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 7 | 2021-08-06 | 9 | 2021-08-19 | 9 | [15 empty] | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19
121800511 | 1359 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.199 |  | 2021-07-26 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 7
121801686 | 1360 | PGE | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 225 |  | 2021-07-27 |  |  | 2021-08-03 | 2021-08-03 | 5 | 2021-08-03 | 5
121801958 | 1361 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 40.1 |  | 2021-07-27 |  | 2021-08-02 | 2021-08-02 | 2021-08-02 | 4
121802035 | 1362 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 48.766 |  | 2021-07-27 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 6
121802186 | 1363 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2581.081 |  | 2021-07-27 | 2021-07-27 |  | 2021-07-27 | 2021-07-27 | 0 | 2021-08-25 | 21 | [5 empty] | 2021-08-25 | 2021-09-23 | 20 | 2021-09-23 | 2021-09-23 | 0 | 2021-09-30 |  |  | 2021-09-23 | 2021-09-24 | 1
121802407 | 1364 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 71.669 |  | 2021-07-27 |  | 2021-08-02 | 2021-08-02 | 2021-08-02 | 4 | 2021-08-24 | 20 | 2021-09-08 | 10 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08
121802615 | 1365 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 34.9 |  | 2021-07-27 |  | 2021-08-09 | 2021-08-09 | 2021-08-09 | 9 | 2021-09-28 | 44
121803652 | 1366 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 210 |  | 2021-07-27 | 2021-07-27 |  | 2021-07-27 | 2021-07-27 | 0 | 2021-08-11 | 11 | 2021-09-08 | 19 | [15 empty] | 2021-09-08 | 2021-09-23 | 11 | 2021-09-23
121804584 | 1367 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 39.046 |  | 2021-07-27 |  | 2021-08-09 | 2021-08-09 | 2021-08-09 | 9 | 2021-09-13 | 33 | 2021-09-30 | 13 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30
121805167 | 1368 | PGE | NEM | EXPNEM | Commercial | Solar PV | 57.71 |  | 2021-07-27 |  | 2021-08-03 | 2021-08-03 | 2021-08-03 | 5 | 2021-08-05 | 7 | 2021-08-17 | 8 | [15 empty] | 2021-08-17 | 2021-08-17 | 0 | 2021-08-17 | 2021-08-17 | 0 | [12 empty] | 2021-08-20 | 2021-08-31 | 7 | [15 empty] | 2021-08-20 | 2021-08-20 | 0 | 2021-08-31 |  | 2021-09-07 | 4
121805355 | 1369 | PGE | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-07-27 |  |  | 2021-08-09 | 2021-08-09 | 9 | 2021-08-09 | 9 | [17 empty] | 2021-09-10 | 2021-09-17 | 5 | 2021-09-17 | 2021-09-17 | 0 |  |  |  |  | 2021-07-27 |  |  |  | 2021-08-13
121806780 | 1370 | PGE | NEM | NEMMT | Application Review in Progress | ENGN, Solar PV | 359.2 |  | 2021-07-28 |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 10
121807295 | 1371 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 172.8 |  | 2021-07-28 |  |  | 2021-08-03 | 2021-08-03 | 4 | 2021-08-03 | 4 | 2021-08-20 | 13 | 2021-08-20 | 2021-09-27 | 25
121807833 | 1372 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 60.6 |  | 2021-07-28 |  | 2021-08-03 | 2021-08-03 | 2021-08-03 | 4
121808444 | 1373 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.49 |  | 2021-07-28 |  | 2021-08-05 | 2021-08-05 | 2021-08-05 | 6
121808551 | 1374 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-07-28 |  |  | 2021-08-09 | 2021-08-09 | 8 | 2021-08-09 | 8 | 2021-09-17 | 28 | [15 empty] | 2021-09-17 | [9 empty] | 2021-07-28 |  |  |  | 2021-08-13
121808625 | 1375 | PGE | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 43.625 |  | 2021-07-28 |  | 2021-09-13 | 2021-08-05 | 2021-08-05 | 6 | 2021-09-24 | 41
121808969 | 1376 | PGE | NEM | EXPNEM | Implementation | Solar PV | 30.354 |  | 2021-07-28 |  |  | 2021-08-09 | 2021-08-09 | 8 | 2021-08-09 | 8 | 2021-08-23 | 10 | [15 empty] | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23 | 2021-09-22 | 21 |  |  |  |  | 2021-07-28 |  |  |  | 2021-08-13 | [6 empty] | 2021-09-17
121809226 | 1377 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-07-28 |  | 2021-08-05 | 2021-08-05 | 2021-08-05 | 6 | 2021-08-19 | 16 | 2021-08-22 | 1 | [33 empty] | 2021-08-22 | 2021-08-22 | 0 | [15 empty] | 2021-08-22 |  |  | 2021-08-22 |  | 2021-08-22 | 0
121812895 | 1378 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 125.956 |  | 2021-07-29 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 4 | [29 empty] | 2021-07-29
121813359 | 1379 | PGE | Non-NEM | Non-Export | Study in Progress | Solar PV | 3891.183 |  | 2021-07-29 | 2021-07-30 |  | 2021-07-30 | 2021-07-30 | 1 | 2021-09-01 | 24 | [5 empty] | 2021-09-01 | 2021-09-30 | 20 | 2021-09-30 | 2021-09-30 | 0 |  |  |  | 2021-09-30 | 2021-09-30 | 0
121814219 | 1380 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-07-29 |  |  | 2021-08-06 | 2021-08-06 | 6 | 2021-08-06 | 6 | 2021-08-09 | 1 | [33 empty] | 2021-08-09 | 2021-08-09 | 0 | [15 empty] | 2021-08-09 |  |  | 2021-08-09 |  | 2021-08-09 | 0
121814237 | 1381 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 244.488 |  | 2021-07-29 |  | 2021-08-30 | 2021-08-05 | 2021-08-05 | 5 | 2021-09-07 | 27 | 2021-09-27 | 14 | 2021-09-27
121814318 | 1382 | PGE | NEM | EXPNEM | Implementation | Solar PV | 250 |  | 2021-07-29 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 4 | 2021-08-11 | 9 | 2021-08-27 | 12 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-09-02 | 4 |  |  |  |  | 2021-07-29 | 2021-08-11 | 2021-09-07 | 27
121814594 | 1383 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 35.487 |  | 2021-07-29 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 4 | 2021-08-09 | 7
121814940 | 1384 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 407.612 |  | 2021-07-29 |  | 2021-08-18 | 2021-08-04 | 2021-08-04 | 4 | [29 empty] | 2021-07-29
121815160 | 1385 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-07-29 |  | 2021-08-06 | 2021-08-06 | 2021-08-06 | 6 | 2021-08-20 | 16 | 2021-09-01 | 8 | [33 empty] | 2021-09-01 | 2021-09-01 | 0 | [15 empty] | 2021-09-01 |  |  | 2021-09-01 |  | 2021-09-01 | 0
121815216 | 1386 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 489.177 |  | 2021-07-29 |  | 2021-08-17 | 2021-08-05 | 2021-08-05 | 5 | [29 empty] | 2021-07-29
121819927 | 1387 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-07-30 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 3 | 2021-08-06 | 5 | 2021-08-25 | 13 | [15 empty] | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | [6 empty] | 2021-07-30
121820120 | 1388 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 312.5 |  | 2021-07-30 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 3 | 2021-08-18 | 13 | 2021-09-03 | 12 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | [6 empty] | 2021-07-30
121820644 | 1389 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.97 |  | 2021-07-30 |  |  | 2021-08-07 | 2021-08-07 | 5 | 2021-08-07 | 5 | 2021-08-07 | 0 | [33 empty] | 2021-08-07 | 2021-08-07 | 0 | [15 empty] | 2021-08-07 |  |  | 2021-08-07 |  | 2021-08-07 | 0
121821877 | 1390 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-07-30 |  | 2021-08-07 | 2021-08-07 | 2021-08-07 | 5 | 2021-08-24 | 17 | 2021-08-26 | 2 | [33 empty] | 2021-08-26 | 2021-08-26 | 0 | [15 empty] | 2021-08-26 |  |  | 2021-08-26 |  | 2021-08-26 | 0
121822650 | 1391 | PGE | NEM | NEMMT | Study in Progress | ENGN, Solar PV | 1264.8 |  | 2021-07-30 | 2021-08-03 |  | 2021-08-03 | 2021-08-03 | 2 | 2021-08-18 | 13 | 2021-09-16 | 20 | 2021-09-30
121826722 | 1392 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-08-01 |  | 2021-08-21 | 2021-08-11 | 2021-08-11 | 7 | 2021-08-24 | 16 | 2021-09-15 | 15 | [15 empty] | 2021-09-15 | 2021-09-16 | 1 | 2021-09-16
121829677 | 1393 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 41.094 |  | 2021-08-02 |  | 2021-08-04 | 2021-08-04 | 2021-08-04 | 2 | 2021-08-09 | 5 | 2021-08-30 | 15 | [15 empty] | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-09-02 | 3
121829885 | 1394 | PGE | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 35.116 |  | 2021-08-02 |  |  | 2021-08-09 | 2021-08-09 | 5 | 2021-08-09 | 5 | 2021-08-11 | 2
121830404 | 1395 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100 |  | 2021-08-02 |  | 2021-08-06 | 2021-08-04 | 2021-08-04 | 2 | 2021-08-09 | 5 | 2021-09-10 | 23 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | [6 empty] | 2021-08-02 | [10 empty] | 2021-09-08
121833129 | 1396 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 140.252 |  | 2021-08-02 |  | 2021-08-09 | 2021-08-04 | 2021-08-04 | 2 | 2021-08-13 | 9 | 2021-08-31 | 12 | [15 empty] | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 | [6 empty] | 2021-08-02 | 2021-08-18 | 2021-09-07 | 25
121833135 | 1397 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 101.57 |  | 2021-08-02 |  | 2021-08-05 | 2021-08-05 | 2021-08-05 | 3 | 2021-08-11 | 7 | 2021-08-27 | 12 | [15 empty] | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-09-10 | 9 |  |  |  |  | 2021-08-02
121833539 | 1398 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 733.3 |  | 2021-08-02 |  | 2021-08-18 | 2021-08-04 | 2021-08-04 | 2 | 2021-08-28 | 19 | 2021-09-08 | 6 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | [6 empty] | 2021-08-02
121833944 | 1399 | PGE | NEM | SNEM | Application Submitted | Solar PV | 400 |  | 2021-08-02 |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 7 | [29 empty] | 2021-08-02
121838661 | 1400 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 |  | 2021-08-03 |  |  | 2021-08-05 | 2021-08-05 | 2 | 2021-08-05 | 2 | 2021-08-24 | 13 | [15 empty] | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | [6 empty] | 2021-08-03 | 2021-08-05 | 2021-08-13 | 8
121839530 | 1401 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 |  | 2021-08-03 |  | 2021-08-16 | 2021-08-16 | 2021-08-16 | 9
121839668 | 1402 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 840 |  | 2021-08-03 |  | 2021-08-17 | 2021-08-17 | 2021-08-17 | 10 | 2021-09-08 | 25 | 2021-09-29 | 15 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | [6 empty] | 2021-08-03 |  |  |  | 2021-09-10
121841040 | 1403 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 125 |  | 2021-08-04 |  | 2021-08-06 | 2021-08-06 | 2021-08-06 | 2 | 2021-08-16 | 8 | [27 empty] | 2021-08-04 | 2021-08-31 | 2021-09-10 | 26
121841534 | 1404 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 34.179 |  | 2021-08-04 |  |  | 2021-08-10 | 2021-08-10 | 4 | 2021-08-26 | 16 | 2021-09-24 | 20 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24
121842236 | 1405 | PGE | Non-NEM | Non-Export | Application Accepted | Solar PV | 3500 |  | 2021-08-04 | 2021-08-10 |  | 2021-08-04 | 2021-08-04 | 0 | 2021-09-01 | 20 | 2021-09-23 | 15 | [25 empty] | 2021-08-04 | 2021-09-03 | 2021-09-10 | 26
121843079 | 1406 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 81.967 |  | 2021-08-04 |  | 2021-08-10 | 2021-08-10 | 2021-08-10 | 4 | 2021-08-27 | 17 | [27 empty] | 2021-08-04 | 2021-09-27
121843105 | 1407 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 48.973 |  | 2021-08-04 |  | 2021-08-16 | 2021-08-10 | 2021-08-10 | 4 | 2021-08-24 | 14 | 2021-09-08 | 10 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | 2021-09-09 | 1 | [12 empty] | 2021-09-23 | [17 empty] | 2021-09-23 | 2021-09-24 | 1
121844567 | 1408 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 |  | 2021-08-04 |  | 2021-08-24 | 2021-08-17 | 2021-08-17 | 9
121844627 | 1409 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 38.4 |  | 2021-08-04 |  | 2021-08-30 | 2021-08-06 | 2021-08-06 | 2 | 2021-08-31 | 19 | 2021-09-17 | 12 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | [6 empty] | 2021-08-04
121844678 | 1410 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 125 |  | 2021-08-04 |  | 2021-08-17 | 2021-08-17 | 2021-08-17 | 9 | 2021-09-30 | 40 | [27 empty] | 2021-08-04 | 2021-09-30
121844989 | 1411 | PGE | NEM | EXPNEM | Implementation | Solar PV | 120 |  | 2021-08-04 |  | 2021-08-10 | 2021-08-10 | 2021-08-10 | 4 | 2021-08-11 | 5 | 2021-08-31 | 14 | [15 empty] | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 | 2021-09-09 | 6 |  |  |  |  | 2021-08-04 | 2021-08-11 | 2021-08-24 | 14
121845137 | 1412 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 26331.652 |  | 2021-08-04 | 2021-08-10 |  | 2021-08-04 | 2021-08-04 | 0 | 2021-09-09 | 25 | [5 empty] | 2021-09-09
121845177 | 1413 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 550 |  | 2021-08-04 |  | 2021-08-24 | 2021-08-11 | 2021-08-11 | 5 | 2021-09-17 | 31 | [27 empty] | 2021-08-04
121845210 | 1414 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 225 |  | 2021-08-04 |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 5 | 2021-08-18 | 10 | [27 empty] | 2021-08-04 | 2021-09-29
121848289 | 1415 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 198.5 |  | 2021-08-05 |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 4 | 2021-08-19 | 10 | 2021-09-08 | 13 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | [6 empty] | 2021-08-05 | 2021-09-17 | 2021-09-22 | 33
121848703 | 1416 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 150 |  | 2021-08-05 |  | 2021-08-16 | 2021-08-16 | 2021-08-16 | 7 | 2021-09-30 | 39 | [27 empty] | 2021-08-05 | 2021-09-30
121848713 | 1417 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 200 |  | 2021-08-05 |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 4 | 2021-08-18 | 9 | 2021-09-23 | 25 | [15 empty] | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | [6 empty] | 2021-08-05 | 2021-09-03 | 2021-09-10 | 25
121848826 | 1418 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2021-08-05 |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 4 | 2021-08-19 | 10 | [27 empty] | 2021-08-05 | 2021-08-11 | 2021-08-24 | 13
121850773 | 1419 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 41.47 |  | 2021-08-05 |  | 2021-08-21 | 2021-08-11 | 2021-08-11 | 4
121850835 | 1420 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 778.129 |  | 2021-08-05 |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 4 | 2021-08-16 | 7 | 2021-09-03 | 14 | 2021-09-03 | [24 empty] | 2021-08-05
121851470 | 1421 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 204 |  | 2021-08-05 |  | 2021-08-19 | 2021-08-19 | 2021-08-19 | 10 | 2021-09-13 | 26 | [27 empty] | 2021-08-05 |  |  |  | 2021-08-27
121851471 | 1422 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 562 |  | 2021-08-05 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 9 | [29 empty] | 2021-08-05
121853279 | 1423 | PGE | Non-NEM | RESBCT | Withdrawn | Solar PV | 4000 |  | 2021-08-06 | 2021-08-10 |  | 2021-08-06 | 2021-08-06 | 0
121854731 | 1424 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 60 |  | 2021-08-06 |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 3 | 2021-09-03 | 20 | 2021-09-27 | 15 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27
121854971 | 1425 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-08-06 |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 3 | 2021-08-16 | 6 | 2021-09-03 | 14 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-10 | 4
121855212 | 1426 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 47.1 |  | 2021-08-06 |  | 2021-08-11 | 2021-08-11 | 2021-08-11 | 3 | 2021-09-13 | 25 | 2021-09-16 | 3 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | [6 empty] | 2021-08-06 | 2021-09-24
121856930 | 1427 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 250 |  | 2021-08-06 |  |  | 2021-08-13 | 2021-08-13 | 5 | 2021-08-24 | 12 | 2021-09-03 | 8 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-07 | 1 |  |  |  |  | 2021-08-06 | 2021-08-24 | 2021-09-07 | 21
121857244 | 1428 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 81.587 |  | 2021-08-06 |  | 2021-08-20 | 2021-08-11 | 2021-08-11 | 3 | 2021-08-27 | 15 | 2021-09-20 | 15 | [15 empty] | 2021-09-20 | 2021-09-20 | 0 | 2021-09-20
121857379 | 1429 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 31.337 |  | 2021-08-06 |  | 2021-08-12 | 2021-08-12 | 2021-08-12 | 4
121863035 | 1430 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 500.5 |  | 2021-08-09 |  | 2021-08-20 | 2021-08-20 | 2021-08-20 | 9 | 2021-09-10 | 23
121863112 | 1431 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 152.592 |  | 2021-08-09 |  | 2021-08-12 | 2021-08-12 | 2021-08-12 | 3 | [29 empty] | 2021-08-09
121863116 | 1432 | PGE | NEM | EXPNEM | Implementation | Solar PV | 37.612 |  | 2021-08-09 |  | 2021-08-17 | 2021-08-17 | 2021-08-17 | 6 | 2021-08-23 | 10 | 2021-09-07 | 10 | [15 empty] | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-09-09 | 2 |  |  |  |  | 2021-08-09
121864229 | 1433 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 600 |  | 2021-08-09 |  | 2021-08-12 | 2021-08-12 | 2021-08-12 | 3 | 2021-08-17 | 6 | [27 empty] | 2021-08-09 | 2021-08-12 | 2021-08-24 | 11
121864242 | 1434 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 221.897 |  | 2021-08-09 |  | 2021-08-12 | 2021-08-12 | 2021-08-12 | 3 | [29 empty] | 2021-08-09
121865289 | 1435 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 210 |  | 2021-08-09 | 2021-08-10 |  | 2021-08-09 | 2021-08-09 | 0 | 2021-09-08 | 21 | 2021-09-29 | 15 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29
121865340 | 1436 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 266.6 |  | 2021-08-09 |  | 2021-08-12 | 2021-08-12 | 2021-08-12 | 3
121865417 | 1437 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 199.8 |  | 2021-08-09 |  | 2021-08-19 | 2021-08-12 | 2021-08-12 | 3 | 2021-08-25 | 12 | 2021-09-16 | 15 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | [6 empty] | 2021-08-09 | 2021-08-12 | 2021-08-24 | 11
121866144 | 1438 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 220 |  | 2021-08-09 |  | 2021-08-23 | 2021-08-23 | 2021-08-23 | 10 | 2021-09-15 | 26
121866731 | 1439 | PGE | NEM | EXPNEM | Commercial | Solar PV | 31.062 |  | 2021-08-09 |  | 2021-08-20 | 2021-08-20 | 2021-08-20 | 9 | 2021-08-25 | 12 | 2021-08-30 | 3 | [33 empty] | 2021-08-31 | 2021-09-08 | 5 | [15 empty] | 2021-08-31 | 2021-09-01 | 1 | 2021-09-08 |  | 2021-09-08 | 0
121877548 | 1440 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-08-10 |  | 2021-09-15 | 2021-08-10 | 2021-08-10 | 0 | 2021-09-24 | 32 | 2021-09-27 | 1 | [33 empty] | 2021-09-27 | 2021-09-27 | 0 | [15 empty] | 2021-09-27 |  |  | 2021-09-27 |  | 2021-09-27 | 0
121878137 | 1441 | PGE | NEM | EXPNEM | Implementation | Solar PV | 720.8 |  | 2021-08-10 |  | 2021-08-20 | 2021-08-20 | 2021-08-20 | 8 | 2021-08-23 | 9 | 2021-09-01 | 7 | [15 empty] | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01 | 2021-09-15 | 9 |  |  |  |  | 2021-08-10 | 2021-08-23 | 2021-09-07 | 19
121880085 | 1442 | PGE | Non-NEM | RESBCT | Withdrawn | Solar PV | 4000 |  | 2021-08-10 | 2021-08-11 |  | 2021-08-11 | 2021-08-11 | 1
121880104 | 1443 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 132 |  | 2021-08-10 |  |  | 2021-08-13 | 2021-08-13 | 3 | 2021-08-13 | 3 | 2021-09-03 | 15 | 2021-09-03 | [24 empty] | 2021-08-10
121880753 | 1444 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 86.909 |  | 2021-08-10 |  | 2021-08-20 | 2021-08-16 | 2021-08-16 | 4 | 2021-08-24 | 10 | 2021-09-10 | 12 | 2021-09-10
121881100 | 1445 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 36 |  | 2021-08-10 |  | 2021-08-16 | 2021-08-16 | 2021-08-16 | 4 | 2021-08-20 | 8 | 2021-09-08 | 12 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08
121882442 | 1446 | PGE | NEM | VNEM | Study in Progress | Solar PV | 52.161 |  | 2021-08-10 |  | 2021-08-24 | 2021-08-24 | 2021-08-24 | 10 | 2021-09-29 | 35 | [27 empty] | 2021-08-10
121882491 | 1447 | PGE | NEM | VNEM | Study in Progress | Solar PV | 46.2 |  | 2021-08-10 |  | 2021-08-24 | 2021-08-24 | 2021-08-24 | 10 | 2021-09-29 | 35 | [27 empty] | 2021-08-10
121882510 | 1448 | PGE | NEM | VNEM | Study in Progress | Solar PV | 54.292 |  | 2021-08-10 |  | 2021-08-24 | 2021-08-24 | 2021-08-24 | 10 | 2021-09-29 | 35 | [27 empty] | 2021-08-10
121882517 | 1449 | PGE | NEM | VNEM | Study in Progress | Solar PV | 54.292 |  | 2021-08-10 |  | 2021-08-24 | 2021-08-24 | 2021-08-24 | 10 | 2021-09-29 | 35 | [27 empty] | 2021-08-10
121883905 | 1450 | PGE | NEM | EXPNEM | Implementation | Solar PV | 215.388 |  | 2021-08-11 |  | 2021-08-23 | 2021-08-23 | 2021-08-23 | 8 | 2021-08-25 | 10 | 2021-09-10 | 11 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | 2021-09-17 | 5
121884706 | 1451 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 86.4 |  | 2021-08-11 |  | 2021-09-03 | 2021-08-16 | 2021-08-16 | 3 | 2021-09-29 | 34
121885645 | 1452 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 350 |  | 2021-08-11 | 2021-08-12 |  | 2021-08-12 | 2021-08-12 | 1 | 2021-09-01 | 15 | [27 empty] | 2021-08-11
121887284 | 1453 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 133.2 |  | 2021-08-11 |  | 2021-08-16 | 2021-08-16 | 2021-08-16 | 3 | 2021-08-23 | 8 | 2021-09-10 | 13 | 2021-09-10 | [24 empty] | 2021-08-11 | 2021-09-10 | 2021-09-10 | 21
121889840 | 1454 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.262 |  | 2021-08-12 |  | 2021-08-24 | 2021-08-24 | 2021-08-24 | 8
121890400 | 1455 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 89.91 |  | 2021-08-12 |  |  | 2021-08-20 | 2021-08-20 | 6 | 2021-08-20 | 6 | 2021-09-08 | 12 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08
121891044 | 1456 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 125 |  | 2021-08-12 |  | 2021-08-25 | 2021-08-25 | 2021-08-25 | 9
121893860 | 1457 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.988 |  | 2021-08-12 |  | 2021-08-25 | 2021-08-25 | 2021-08-25 | 9 | 2021-09-13 | 21 | 2021-09-14 | 1 | [33 empty] | 2021-09-14 | 2021-09-14 | 0 | [15 empty] | 2021-09-14 |  |  | 2021-09-14 |  | 2021-09-14 | 0
121896330 | 1458 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.191 |  | 2021-08-13 |  | 2021-09-27 | 2021-08-25 | 2021-08-25 | 8
121896536 | 1459 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 39.737 |  | 2021-08-13 |  | 2021-08-27 | 2021-08-27 | 2021-08-27 | 10
121896609 | 1460 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 42.725 |  | 2021-08-13 |  | 2021-08-17 | 2021-08-17 | 2021-08-17 | 2 | 2021-09-13 | 20 | 2021-09-14 | 1 | [19 empty] | 2021-08-13 | N/A | [12 empty] | 2021-09-14 | 2021-09-14 | 0 | [15 empty] | 2021-09-14 |  |  | 2021-09-14 |  | 2021-09-14 | 0
121897072 | 1461 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 60.834 |  | 2021-08-13 |  | 2021-08-24 | 2021-08-23 | 2021-08-23 | 6 | 2021-08-27 | 10 | 2021-09-17 | 14 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17
121897494 | 1462 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 200 |  | 2021-08-13 |  | 2021-09-01 | 2021-08-23 | 2021-08-23 | 6 | [29 empty] | 2021-08-13
121897872 | 1463 | PGE | NEM | EXPNEM | Implementation | Solar PV | 38.253 |  | 2021-08-13 |  | 2021-08-23 | 2021-08-23 | 2021-08-23 | 6 | 2021-08-24 | 7 | 2021-09-09 | 11 | [15 empty] | 2021-09-09 | 2021-09-13 | 2 | 2021-09-13 | 2021-09-14 | 1
121898308 | 1464 | PGE | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 30.85 |  | 2021-08-13 |  | 2021-09-13 | 2021-08-25 | 2021-08-25 | 8 | 2021-09-24 | 29 | 2021-09-28 | 2
121899208 | 1465 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 78.283 |  | 2021-08-13 |  | 2021-08-25 | 2021-08-24 | 2021-08-24 | 7 | 2021-09-20 | 25
121899639 | 1466 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 43.2 |  | 2021-08-13 |  | 2021-09-07 | 2021-08-23 | 2021-08-23 | 6 | 2021-09-17 | 24
121902629 | 1467 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 500 |  | 2021-08-14 |  |  | 2021-08-19 | 2021-08-19 | 3 | 2021-08-23 | 5
121906537 | 1468 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 328.367 |  | 2021-08-16 |  | 2021-08-25 | 2021-08-25 | 2021-08-25 | 7 | [29 empty] | 2021-08-16
121907680 | 1469 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 210 |  | 2021-08-16 | 2021-08-23 |  | 2021-08-17 | 2021-08-17 | 1 | 2021-09-08 | 16
121907797 | 1470 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 32.88 |  | 2021-08-16 |  | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2
121908572 | 1471 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 4106 |  | 2021-08-16 |  | 2021-08-27 | 2021-08-27 | 2021-08-27 | 9
121908590 | 1472 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 55.889 |  | 2021-08-16 |  |  | 2021-08-25 | 2021-08-25 | 7 | 2021-08-25 | 7 | 2021-09-03 | 7 | [15 empty] | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03
121908771 | 1473 | PGE | NEM | EXPNEM | Implementation | Solar PV | 66.6 |  | 2021-08-16 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 10 | 2021-09-07 | 15 | 2021-09-21 | 10 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | 2021-09-23 | 2 |  |  |  |  | 2021-08-16 | 2021-09-07 | 2021-09-10 | 18
121910998 | 1474 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 45.452 |  | 2021-08-17 |  | 2021-08-25 | 2021-08-25 | 2021-08-25 | 6 | 2021-09-16 | 21
121911636 | 1475 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2021-08-17 |  | 2021-08-25 | 2021-08-25 | 2021-08-25 | 6 | 2021-09-22 | 25 | [27 empty] | 2021-08-17 | 2021-09-08 | 2021-09-10 | 17
121911825 | 1476 | PGE | NEM | EXPNEM | Implementation | Solar PV | 33.884 |  | 2021-08-17 |  |  | 2021-08-25 | 2021-08-25 | 6 | 2021-08-25 | 6 | 2021-09-17 | 16 | [15 empty] | 2021-09-17 | 2021-09-23 | 4 | 2021-09-23 | 2021-09-23 | 0
121912383 | 1477 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 55.488 |  | 2021-08-17 |  | 2021-08-25 | 2021-08-25 | 2021-08-25 | 6 | 2021-09-06 | 13 | [27 empty] | 2021-08-17
121912801 | 1478 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 210 |  | 2021-08-17 | 2021-08-23 |  | 2021-08-18 | 2021-08-18 | 1 | 2021-09-08 | 15 | [27 empty] | 2021-08-17
121912981 | 1479 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 126.15 |  | 2021-08-17 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 10 | 2021-09-20 | 23
121912982 | 1480 | PGE | NEM | EXPNEM | Implementation | Solar PV | 120 |  | 2021-08-17 |  | 2021-08-23 | 2021-08-23 | 2021-08-23 | 4 | 2021-09-10 | 17 | 2021-09-21 | 7 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | 2021-09-29 | 6 |  |  |  |  | 2021-08-17 | 2021-09-10 | 2021-09-14 | 19
121913957 | 1481 | PGE | NEM | NEMMT | Study in Progress | Solar PV, Storage | 55.9 |  | 2021-08-17 |  |  | 2021-08-25 | 2021-08-25 | 6 | 2021-08-25 | 6
121917117 | 1482 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 44.04 |  | 2021-08-18 |  | 2021-08-24 | 2021-08-24 | 2021-08-24 | 4 | 2021-08-25 | 5 | 2021-09-10 | 11 | [15 empty] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10
121918190 | 1483 | PGE | Non-NEM | NEMFC | Application Review in Progress | FUCE, Storage | 892.5 |  | 2021-08-18 |  | 2021-09-01 | 2021-09-01 | 2021-09-01 | 10 | [29 empty] | 2021-08-18
121919734 | 1484 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.01 |  | 2021-08-19 |  | 2021-09-24 | 2021-08-30 | 2021-08-30 | 7
121919795 | 1485 | PGE | NEM | SNEM | Application Review in Progress | Solar PV, Storage | 12240 |  | 2021-08-19 |  | 2021-08-25 | 2021-08-25 | 2021-08-25 | 4
121919833 | 1486 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 40.252 |  | 2021-08-19 |  | 2021-08-27 | 2021-08-27 | 2021-08-27 | 6 | 2021-09-01 | 9 | 2021-09-08 | 4 | [15 empty] | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08
121919898 | 1487 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 840 |  | 2021-08-19 |  | 2021-08-30 | 2021-08-31 | 2021-08-30 | 7 | 2021-08-31 | 8 | 2021-09-20 | 13 | [15 empty] | 2021-09-20 | [9 empty] | 2021-08-19 |  |  |  | 2021-09-08
121920019 | 1488 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 133.3 |  | 2021-08-19 |  | 2021-08-27 | 2021-08-27 | 2021-08-27 | 6 | 2021-09-01 | 9 | 2021-09-17 | 11 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | [6 empty] | 2021-08-19 | 2021-08-27 | 2021-09-09 | 14
121920077 | 1489 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 385.259 |  | 2021-08-19 |  |  | 2021-08-24 | 2021-08-24 | 3 | 2021-08-24 | 3 | 2021-09-08 | 10 | 2021-09-10 | [14 empty] | 2021-09-08 | 2021-09-27 | 13 | 2021-09-27
121920255 | 1490 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 181.47 |  | 2021-08-19 |  | 2021-09-27 | 2021-08-25 | 2021-08-25 | 4 | [29 empty] | 2021-08-19
121920711 | 1491 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 220 |  | 2021-08-19 |  | 2021-08-27 | 2021-08-27 | 2021-08-27 | 6 | [29 empty] | 2021-08-19
121921002 | 1492 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 290 |  | 2021-08-19 |  | 2021-08-25 | 2021-08-25 | 2021-08-25 | 4 | 2021-08-30 | 7 | 2021-09-15 | 11 | [15 empty] | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | [6 empty] | 2021-08-19 | 2021-08-30 | 2021-09-08 | 13
121921070 | 1493 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.887 |  | 2021-08-19 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 8 | 2021-09-16 | 19 | 2021-09-16 | 0 | [33 empty] | 2021-09-16 | 2021-09-16 | 0 | [15 empty] | 2021-09-16 |  |  | 2021-09-16 |  | 2021-09-16 | 0
121921172 | 1494 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 146 |  | 2021-08-19 |  | 2021-08-27 | 2021-08-27 | 2021-08-27 | 6 | 2021-09-01 | 9 | 2021-09-21 | 13 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [6 empty] | 2021-08-19
121921294 | 1495 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 246.28 |  | 2021-08-19 |  | 2021-09-08 | 2021-08-24 | 2021-08-24 | 3 | 2021-09-22 | 23 | [27 empty] | 2021-08-19 | 2021-09-22 | 2021-09-23 | 24
121921651 | 1496 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 30.159 |  | 2021-08-19 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 7 | [29 empty] | 2021-08-19
121921653 | 1497 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 53.289 |  | 2021-08-19 |  | 2021-09-02 | 2021-09-02 | 2021-09-02 | 10 | [29 empty] | 2021-08-19
121921754 | 1498 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.99 |  | 2021-08-19 |  | 2021-09-02 | 2021-09-02 | 2021-09-02 | 10
121922382 | 1499 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 133.2 |  | 2021-08-19 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 8 | [29 empty] | 2021-08-19
121922835 | 1500 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 50.518 |  | 2021-08-20 |  | 2021-09-09 | 2021-08-28 | 2021-08-28 | 5
121923917 | 1501 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.131 |  | 2021-08-20 |  | 2021-09-01 | 2021-09-01 | 2021-09-01 | 8
121924602 | 1502 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 44.178 |  | 2021-08-20 |  | 2021-09-27 | 2021-09-01 | 2021-09-01 | 8
121925307 | 1503 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 8999.16 |  | 2021-08-20 | 2021-08-24 |  | 2021-08-20 | 2021-08-20 | 0 | 2021-09-09 | 13 | [27 empty] | 2021-09-10
121925470 | 1504 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.375 |  | 2021-08-20 |  |  | 2021-09-01 | 2021-09-01 | 8 | 2021-09-01 | 8 | 2021-09-07 | 3 | [33 empty] | 2021-09-07 | 2021-09-07 | 0 | [15 empty] | 2021-09-07 |  |  | 2021-09-07 |  | 2021-09-07 | 0
121925724 | 1505 | PGE | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-08-20 |  |  | 2021-08-26 | 2021-08-26 | 4 | 2021-08-30 | 6 | 2021-09-13 | 9 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-09-13 | 0 |  |  |  |  | 2021-08-20 | 2021-08-30 | 2021-09-09 | 13 |  |  |  |  | 2021-09-30 | [17 empty] | 2021-09-30 | 2021-09-30 | 0
121925788 | 1506 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 35.558 |  | 2021-08-20 |  | 2021-08-28 | 2021-08-28 | 2021-08-28 | 5 | 2021-09-09 | 13 | 2021-09-23 | 10 | [15 empty] | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | [6 empty] | 2021-08-20 | 2021-09-09 | 2021-09-09 | 13
121927450 | 1507 | PGE | NEM | VNEM | Implementation | Solar PV | 39.976 |  | 2021-08-20 |  | 2021-08-30 | 2021-08-25 | 2021-08-25 | 3 | 2021-09-01 | 8 | 2021-09-13 | 7 | [15 empty] | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-09-14 | 1 |  |  |  |  | 2021-08-20 | 2021-09-13 | 2021-09-14 | 16 |  | 2021-09-13 | 2021-09-13 | 0
121927966 | 1508 | PGE | NEM | EXPNEM | Implementation | Solar PV | 33.3 |  | 2021-08-20 |  | 2021-08-31 | 2021-08-27 | 2021-08-27 | 5 | 2021-09-01 | 8 | 2021-09-16 | 10 | [15 empty] | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | 2021-09-28 | 8 |  |  |  |  | 2021-08-20 | 2021-09-01 | 2021-09-10 | 14
121928646 | 1509 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 276 |  | 2021-08-20 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 7 | [29 empty] | 2021-08-20
121933957 | 1510 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 312.82 |  | 2021-08-21 |  | 2021-09-24 | 2021-08-28 | 2021-08-28 | 5 | [29 empty] | 2021-08-21 | 2021-08-28 | 2021-09-09 | 12
121938018 | 1511 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 50.209 |  | 2021-08-22 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 6 | 2021-09-20 | 19
121938754 | 1512 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 30.159 |  | 2021-08-23 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 5 | 2021-09-03 | 9 | 2021-09-27 | 15 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27
121940803 | 1513 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 115.456 |  | 2021-08-23 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 5 | [29 empty] | 2021-08-23
121940872 | 1514 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 840 |  | 2021-08-23 |  | 2021-09-03 | 2021-08-31 | 2021-08-31 | 6 | 2021-09-10 | 13 | 2021-09-27 | 11 | 2021-09-27
121941031 | 1515 | PGE | NEM | EXPNEM | Implementation | Solar PV | 40.252 |  | 2021-08-23 |  |  | 2021-08-31 | 2021-08-31 | 6 | 2021-09-01 | 7 | 2021-09-14 | 8 | [15 empty] | 2021-09-14 | 2021-09-14 | 0 | 2021-09-14 | 2021-09-20 | 4 |  |  |  |  | 2021-08-23 | 2021-09-01 | 2021-09-10 | 13 | [7 empty] | 2021-10-05
121942766 | 1516 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 37.421 |  | 2021-08-23 |  | 2021-09-03 | 2021-09-03 | 2021-09-03 | 9
121942807 | 1517 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 44.494 |  | 2021-08-23 |  | 2021-09-13 | 2021-09-02 | 2021-09-02 | 8 | 2021-09-13 | 14 | 2021-09-27 | 10 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27
121945252 | 1518 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 288 |  | 2021-08-24 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 4 | 2021-09-22 | 20 | [27 empty] | 2021-08-24
121945535 | 1519 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 78.035 |  | 2021-08-24 |  | 2021-09-30 | 2021-09-07 | 2021-09-07 | 9
121947813 | 1520 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 145.057 |  | 2021-08-24 |  | 2021-09-16 | 2021-08-30 | 2021-08-30 | 4 | 2021-09-20 | 18 | [27 empty] | 2021-08-24 | 2021-09-16 | 2021-09-20 | 18
121951394 | 1521 | PGE | NEM | SNEM | Application Submitted | Solar PV | 7392 |  | 2021-08-24 |  | 2021-09-01 | 2021-09-01 | 2021-09-01 | 6
121951566 | 1522 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 240 |  | 2021-08-24 |  |  | 2021-08-30 | 2021-08-30 | 4 | 2021-08-30 | 4 | 2021-09-21 | 15 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [6 empty] | 2021-08-24
121951689 | 1523 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 192 |  | 2021-08-24 |  |  | 2021-08-30 | 2021-08-30 | 4 | 2021-08-30 | 4 | 2021-09-21 | 15 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [6 empty] | 2021-08-24
121951736 | 1524 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-08-24 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 4 | 2021-09-08 | 10 | 2021-09-22 | 10 | [15 empty] | 2021-09-22 | 2021-09-22 | 0 | 2021-09-22 | [6 empty] | 2021-08-24
121952207 | 1525 | PGE | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 34.009 |  | 2021-08-25 |  | 2021-09-20 | 2021-09-07 | 2021-09-07 | 8 | 2021-09-29 | 24
121952503 | 1526 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 241.512 |  | 2021-08-25 |  | 2021-09-08 | 2021-09-08 | 2021-09-08 | 9
121953249 | 1527 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 57.873 |  | 2021-08-25 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 4 | 2021-09-07 | 8
121954360 | 1528 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 150 |  | 2021-08-25 |  |  | 2021-09-09 | 2021-09-09 | 10 | 2021-09-10 | 11 | 2021-09-27 | 11 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | [6 empty] | 2021-08-25 | 2021-09-14 | 2021-09-23 | 20
121954525 | 1529 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 34.348 |  | 2021-08-25 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 4 | [29 empty] | 2021-08-25
121954526 | 1530 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 150 |  | 2021-08-25 |  | 2021-09-03 | 2021-09-03 | 2021-09-03 | 7 | 2021-09-10 | 11 | 2021-09-27 | 11 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | [6 empty] | 2021-08-25
121954586 | 1531 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 330 |  | 2021-08-25 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 4 | 2021-09-07 | 8 | 2021-09-27 | 14 | [15 empty] | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | [6 empty] | 2021-09-01
121954755 | 1532 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 104.35 |  | 2021-08-25 |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 4 | [29 empty] | 2021-08-25
121955755 | 1533 | PGE | Non-NEM | RESBCT | Study in Progress | Solar PV | 5000 |  | 2021-08-25 | 2021-08-27 |  | 2021-08-25 | 2021-08-25 | 0 | 2021-09-08 | 9 | [5 empty] | 2021-09-08
121955978 | 1534 | PGE | NEM | SNEM | Application Review in Progress | Solar PV, Storage | 37.69 |  | 2021-08-25 |  | 2021-09-07 | 2021-09-07 | 2021-09-07 | 8
121956158 | 1535 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 89.406 |  | 2021-08-25 |  | 2021-09-01 | 2021-09-01 | 2021-09-01 | 5
121956220 | 1536 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 58.447 |  | 2021-08-25 |  | 2021-09-01 | 2021-09-01 | 2021-09-01 | 5 | [29 empty] | 2021-08-25
121956520 | 1537 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 165.528 |  | 2021-08-25 |  | 2021-09-07 |  | 2021-09-07 | 8
121956689 | 1538 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 375 |  | 2021-08-25 |  | 2021-09-01 | 2021-09-01 | 2021-09-01 | 5 | 2021-09-15 | 14 | 2021-09-30 | 11 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | [6 empty] | 2021-08-25 | 2021-09-15 | 2021-09-20 | 17
121957322 | 1539 | PGE | NEM | SNEM Paired Storage | Implementation | Solar PV, Storage | 30.925 |  | 2021-08-25 |  | 2021-09-08 | 2021-09-08 | 2021-09-08 | 9 | 2021-09-22 | 19 | 2021-09-23 | 1 | [33 empty] | 2021-09-23 | 2021-09-23 | 0 | [15 empty] | 2021-09-23 |  |  | 2021-09-23
121957681 | 1540 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 206 |  | 2021-08-25 |  |  | 2021-09-02 | 2021-09-02 | 6 | 2021-09-02 | 6 | 2021-09-21 | 12 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [6 empty] | 2021-08-25
121957683 | 1541 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 231.357 |  | 2021-08-25 |  |  | 2021-09-02 | 2021-09-02 | 6 | 2021-09-02 | 6 | 2021-09-21 | 12 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [6 empty] | 2021-08-25
121958032 | 1542 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 100 |  | 2021-08-25 |  | 2021-09-10 | 2021-09-02 | 2021-09-02 | 6 | 2021-09-10 | 11 | [27 empty] | 2021-08-25 | 2021-09-10 | 2021-09-14 | 13
121958482 | 1543 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 200 |  | 2021-08-26 |  | 2021-09-07 | 2021-09-07 | 2021-09-07 | 7 | 2021-09-14 | 12
121958836 | 1544 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 200 |  | 2021-08-26 |  | 2021-09-02 | 2021-09-02 | 2021-09-02 | 5 | [29 empty] | 2021-08-26
121959594 | 1545 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 252 |  | 2021-08-26 |  |  | 2021-09-02 | 2021-09-02 | 5 | 2021-09-02 | 5 | 2021-09-21 | 12 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [6 empty] | 2021-08-26
121959988 | 1546 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 276 |  | 2021-08-26 |  | 2021-09-09 | 2021-09-09 | 2021-09-09 | 9 | 2021-09-14 | 12
121960026 | 1547 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 45.572 |  | 2021-08-26 |  | 2021-09-10 | 2021-09-02 | 2021-09-02 | 5 | [29 empty] | 2021-08-26 | 2021-09-02 | 2021-09-10 | 10
121960166 | 1548 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 192 |  | 2021-08-26 |  |  | 2021-09-02 | 2021-09-02 | 5 | 2021-09-02 | 5 | 2021-09-22 | 13 | [15 empty] | 2021-09-22 | 2021-09-22 | 0 | 2021-09-22 | [6 empty] | 2021-08-26
121961252 | 1549 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 180 |  | 2021-08-26 |  | 2021-09-07 | 2021-09-07 | 2021-09-07 | 7 | 2021-09-14 | 12
121961293 | 1550 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 37.775 |  | 2021-08-26 |  | 2021-09-07 | 2021-09-07 | 2021-09-07 | 7
121962644 | 1551 | PGE | Non-NEM | RESBCT | Application Accepted | Solar PV | 106.368 |  | 2021-08-26 | 2021-08-27 |  | 2021-08-27 | 2021-08-27 | 1 | 2021-09-15 | 13
121964094 | 1552 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 116.08 |  | 2021-08-27 |  | 2021-09-13 | 2021-09-13 | 2021-09-13 | 10
121964097 | 1553 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.2 |  | 2021-08-27 |  | 2021-09-08 | 2021-09-08 | 2021-09-08 | 7
121965334 | 1554 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 88.2 |  | 2021-08-27 |  | 2021-09-07 | 2021-09-07 | 2021-09-07 | 6
121967150 | 1555 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 3084.193 |  | 2021-08-27 | 2021-09-13 |  | 2021-09-13 | 2021-09-13 | 10 | [29 empty] | 2021-08-27
121967154 | 1556 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 840 |  | 2021-08-27 |  |  | 2021-09-13 | 2021-09-13 | 10 | 2021-09-14 | 11
121967204 | 1557 | PGE | Non-NEM | RESBCT | Study in Progress | Solar PV | 5000 |  | 2021-08-27 | 2021-08-30 |  | 2021-08-30 | 2021-08-30 | 1 | 2021-09-08 | 7 | [5 empty] | 2021-09-08
121967208 | 1558 | PGE | Non-NEM | RESBCT | Study in Progress | Solar PV | 5000 |  | 2021-08-27 | 2021-08-30 |  | 2021-08-30 | 2021-08-30 | 1 | 2021-09-22 | 17 | [5 empty] | 2021-09-22
121967339 | 1559 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 38.4 |  | 2021-08-27 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 1 | 2021-08-31 | 2 | 2021-09-17 | 12 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | [6 empty] | 2021-08-27
121967411 | 1560 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 38.4 |  | 2021-08-27 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 1 | 2021-08-31 | 2 | 2021-09-17 | 12 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | [6 empty] | 2021-08-27
121967412 | 1561 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 38.4 |  | 2021-08-27 |  | 2021-08-30 | 2021-08-30 | 2021-08-30 | 1 | 2021-08-31 | 2 | 2021-09-17 | 12 | [15 empty] | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | [6 empty] | 2021-08-27
121967529 | 1562 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 54.292 |  | 2021-08-27 |  | 2021-09-02 | 2021-09-02 | 2021-09-02 | 4 | [29 empty] | 2021-08-27
121971424 | 1563 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 72.22 |  | 2021-08-30 |  | 2021-09-17 | 2021-09-07 | 2021-09-07 | 5
121971473 | 1564 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 86.65 |  | 2021-08-30 |  | 2021-09-13 | 2021-09-22 | 2021-09-13 | 9 | 2021-09-22 | 16
121972635 | 1565 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 34.179 |  | 2021-08-30 |  |  | 2021-09-07 | 2021-09-07 | 5 | 2021-09-07 | 5 | 2021-09-24 | 13 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | [6 empty] | 2021-08-30 | 2021-09-07 | 2021-09-10 | 8
121972858 | 1566 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 390 |  | 2021-08-30 |  | 2021-09-02 | 2021-09-02 | 2021-09-02 | 3 | 2021-09-03 | 4 | 2021-09-21 | 11 | 2021-09-21
121974467 | 1567 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 125 |  | 2021-08-30 |  | 2021-09-07 | 2021-09-07 | 2021-09-07 | 5 | 2021-09-21 | 15 | [27 empty] | 2021-08-30 | 2021-09-07 | 2021-09-10 | 8
121974755 | 1568 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.963 |  | 2021-08-30 |  |  | 2021-09-13 | 2021-09-13 | 9 | 2021-09-13 | 9 | 2021-09-13 | 0 | [33 empty] | 2021-09-13 | 2021-09-13 | 0 | [15 empty] | 2021-09-13 |  |  | 2021-09-13 |  | 2021-09-13 | 0
121974926 | 1569 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 336 |  | 2021-08-30 |  |  | 2021-09-13 | 2021-09-13 | 9 | 2021-09-14 | 10
121975521 | 1570 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 220 |  | 2021-08-31 |  |  | 2021-09-13 | 2021-09-13 | 8 | 2021-09-14 | 9 | 2021-09-30 | 12 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | [6 empty] | 2021-08-31 | 2021-09-14 | 2021-09-21 | 14
121976292 | 1571 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 150 |  | 2021-08-31 |  |  | 2021-09-13 | 2021-09-13 | 8 | 2021-09-13 | 8 | 2021-09-21 | 6 | [15 empty] | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [6 empty] | 2021-08-31 | 2021-09-14 | 2021-09-21 | 14
121976650 | 1572 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 30.2 |  | 2021-08-31 |  |  | 2021-09-13 | 2021-09-13 | 8 | 2021-09-13 | 8
121977337 | 1573 | PGE | NEM | SNEM | Application Review in Progress | Solar PV | 34.83 |  | 2021-08-31 |  | 2021-09-20 | 2021-09-08 | 2021-09-08 | 5
121977365 | 1574 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 34.9 |  | 2021-08-31 |  | 2021-09-28 | 2021-09-07 | 2021-09-07 | 4
121978170 | 1575 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 1560 |  | 2021-08-31 | 2021-09-01 |  | 2021-09-01 | 2021-09-01 | 1 | 2021-09-08 | 5 | [27 empty] | 2021-08-31
121979772 | 1576 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 136 |  | 2021-08-31 |  |  | 2021-09-13 | 2021-09-13 | 8 | 2021-09-14 | 9 | 2021-09-30 | 12 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | [6 empty] | 2021-08-31 | 2021-09-14
121985947 | 1577 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 |  | 2021-09-01 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 9
121986313 | 1578 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 82.146 |  | 2021-09-01 |  |  | 2021-09-16 | 2021-09-16 | 10 | 2021-09-27 | 17
121986325 | 1579 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 344.924 |  | 2021-09-01 |  |  | 2021-09-16 | 2021-09-16 | 10 | 2021-09-27 | 17
121986653 | 1580 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 51.508 |  | 2021-09-01 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 9
121986695 | 1581 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.2 |  | 2021-09-01 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 9
121987918 | 1582 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 75.278 |  | 2021-09-02 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 8
121988272 | 1583 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 92.944 |  | 2021-09-02 |  | 2021-09-09 | 2021-09-09 | 2021-09-09 | 4 | [29 empty] | 2021-09-02
121988363 | 1584 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.599 |  | 2021-09-02 |  | 2021-09-27 | 2021-09-15 | 2021-09-15 | 8 | [29 empty] | 2021-09-02
121988538 | 1585 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 275.259 |  | 2021-09-02 |  | 2021-09-17 | 2021-09-17 | 2021-09-17 | 10
121988597 | 1586 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 111.259 |  | 2021-09-02 |  |  | 2021-09-17 | 2021-09-17 | 10 | 2021-09-22 | 13
121989661 | 1587 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.028 |  | 2021-09-02 |  | 2021-09-30 | 2021-09-15 | 2021-09-15 | 8
121989770 | 1588 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 175 |  | 2021-09-02 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 8
121989866 | 1589 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 840 |  | 2021-09-02 |  |  | 2021-09-16 | 2021-09-16 | 9 | 2021-09-27 | 16
121990859 | 1590 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 500 |  | 2021-09-02 |  |  | 2021-09-14 | 2021-09-14 | 7 | 2021-09-14 | 7 | [5 empty] | 2021-09-17
121991851 | 1591 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 135.91 |  | 2021-09-02 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 8 | [29 empty] | 2021-09-02
121995079 | 1592 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 72.22 |  | 2021-09-03 |  | 2021-09-08 | 2021-09-08 | 2021-09-08 | 2 | 2021-09-15 | 7 | [27 empty] | 2021-09-03
121997476 | 1593 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 40.252 |  | 2021-09-03 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 7
122009584 | 1594 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 100 |  | 2021-09-07 |  | 2021-09-08 | 2021-09-08 | 2021-09-08 | 1 | 2021-09-13 | 4 | [27 empty] | 2021-09-07 | 2021-09-10 | 2021-09-14 | 5 |  | 2021-09-17
122009623 | 1595 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 591.6 |  | 2021-09-07 |  | 2021-09-14 | 2021-09-14 | 2021-09-14 | 5 | 2021-09-16 | 7 | 2021-09-24 | 6 | [15 empty] | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | [6 empty] | 2021-09-07 | 2021-09-14 | 2021-09-21 | 10
122009679 | 1596 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 100 |  | 2021-09-07 |  | 2021-09-08 | 2021-09-08 | 2021-09-08 | 1 | 2021-09-13 | 4 | [27 empty] | 2021-09-07 | 2021-09-10 | 2021-09-14 | 5 |  | 2021-09-17
122009844 | 1597 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 34.8 |  | 2021-09-07 |  |  | 2021-09-13 | 2021-09-13 | 4 | 2021-09-13 | 4 | 2021-09-29 | 12 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | [7 empty] | 2021-09-29
122009898 | 1598 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 100 |  | 2021-09-07 |  | 2021-09-08 | 2021-09-08 | 2021-09-08 | 1 | 2021-09-13 | 4 | [27 empty] | 2021-09-07 | 2021-09-10 | 2021-09-14 | 5 |  | 2021-09-17
122009964 | 1599 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 276 |  | 2021-09-07 |  | 2021-09-08 | 2021-09-08 | 2021-09-08 | 1 | 2021-09-13 | 4 | 2021-09-28 | 11 | [15 empty] | 2021-09-28 | 2021-09-28 | 0 | 2021-09-28 | [6 empty] | 2021-09-07 | 2021-09-13 | 2021-09-20 | 9
122012455 | 1600 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 43.2 |  | 2021-09-08 |  | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2 | 2021-09-13 | 3 | [28 empty] | 2021-09-10 | 2021-09-14 | 2 |  | 2021-09-17
122012643 | 1601 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 85.601 |  | 2021-09-08 |  | 2021-09-22 | 2021-09-22 | 2021-09-22 | 10 | [29 empty] | 2021-09-08
122012720 | 1602 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.2 |  | 2021-09-08 |  | 2021-09-22 | 2021-09-22 | 2021-09-22 | 10 | [29 empty] | 2021-09-08
122012800 | 1603 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 93.276 |  | 2021-09-08 |  | 2021-09-22 | 2021-09-22 | 2021-09-22 | 10 | [29 empty] | 2021-09-08
122012802 | 1604 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 61.126 |  | 2021-09-08 |  | 2021-09-22 | 2021-09-22 | 2021-09-22 | 10 | [29 empty] | 2021-09-08
122014354 | 1605 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 150 |  | 2021-09-08 |  |  | 2021-09-14 | 2021-09-14 | 4 | 2021-09-15 | 5 | [27 empty] | 2021-09-08 | 2021-09-15 | 2021-09-22 | 10
122014809 | 1606 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100 |  | 2021-09-08 |  |  | 2021-09-20 | 2021-09-20 | 8 | 2021-09-20 | 8 | 2021-09-23 | 3 | [15 empty] | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23
122014821 | 1607 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 34.963 |  | 2021-09-08 |  | 2021-09-17 | 2021-09-08 | 2021-09-08 | 0 | 2021-09-30 | 16
122015193 | 1608 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.621 |  | 2021-09-08 |  |  | 2021-09-17 | 2021-09-17 | 7 | 2021-09-17 | 7 | 2021-09-19 | 0 | [33 empty] | 2021-09-19 | 2021-09-19 | 0 | [15 empty] | 2021-09-19 |  |  | 2021-09-19 |  | 2021-09-19 | 0
122016197 | 1609 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 34.179 |  | 2021-09-08 |  | 2021-09-22 | 2021-09-22 | 2021-09-22 | 10
122018296 | 1610 | PGE | NEM | VNEM | Application Accepted | Solar PV | 1920 |  | 2021-09-09 |  | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2 | 2021-09-22 | 9
122018459 | 1611 | PGE | Non-NEM | Non-Export | Application Accepted | ENGN | 60 |  | 2021-09-09 | 2021-09-10 |  | 2021-09-09 | 2021-09-09 | 0 | 2021-09-22 | 9
122019693 | 1612 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 160.225 |  | 2021-09-09 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 4
122019694 | 1613 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 160.225 |  | 2021-09-09 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 4
122019714 | 1614 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 160.225 |  | 2021-09-09 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 4
122019747 | 1615 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 160.225 |  | 2021-09-09 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 4
122019781 | 1616 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 160.225 |  | 2021-09-09 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 4
122020546 | 1617 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 178.024 |  | 2021-09-09 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 4
122020637 | 1618 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 840 |  | 2021-09-09 |  | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2
122020675 | 1619 | PGE | Non-NEM | Inadvertent Export | Application Accepted | Storage | 630 |  | 2021-09-09 | 2021-09-10 |  | 2021-09-10 | 2021-09-10 | 1 | 2021-09-29 | 14
122021468 | 1620 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 500 |  | 2021-09-09 |  |  | 2021-09-13 | 2021-09-13 | 2 | 2021-09-13 | 2 | 2021-09-29 | 12 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | [7 empty] | 2021-09-15 | 2021-09-22 | 5
122034566 | 1621 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 131.66 |  | 2021-09-10 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 3 | 2021-09-23 | 9 | [27 empty] | 2021-09-10 | 2021-09-15 | 2021-09-22 | 8
122034767 | 1622 | PGE | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 34.963 |  | 2021-09-10 |  |  | 2021-09-24 | 2021-09-24 | 10 | 2021-09-24 | 10 | 2021-09-28 | 2 | [25 empty] | 2021-09-10
122034784 | 1623 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 82.454 |  | 2021-09-10 |  |  | 2021-09-15 | 2021-09-15 | 3 | 2021-09-15 | 3 | 2021-09-30 | 11 | [15 empty] | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | [6 empty] | 2021-09-10 | 2021-09-15 | 2021-09-22 | 8
122035283 | 1624 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 80 |  | 2021-09-10 | 2021-09-24 |  | 2021-09-15 | 2021-09-15 | 3 | 2021-09-29 | 13 | [27 empty] | 2021-09-10 | 2021-09-29
122036733 | 1625 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 |  | 2021-09-10 |  | 2021-09-15 | 2021-09-15 | 2021-09-15 | 3
122037235 | 1626 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.287 |  | 2021-09-10 |  | 2021-09-24 | 2021-09-24 | 2021-09-24 | 10
122042960 | 1627 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.63 |  | 2021-09-13 |  | 2021-09-28 | 2021-09-27 | 2021-09-27 | 10
122043467 | 1628 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 95.8 |  | 2021-09-13 |  | 2021-09-17 | 2021-09-17 | 2021-09-17 | 4 | [29 empty] | 2021-09-13
122044521 | 1629 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 39.596 |  | 2021-09-13 |  | 2021-09-27 | 2021-09-27 | 2021-09-27 | 10
122048959 | 1630 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 72 |  | 2021-09-14 |  | 2021-09-28 | 2021-09-28 | 2021-09-28 | 10
122049507 | 1631 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.668 |  | 2021-09-14 |  | 2021-09-27 | 2021-09-27 | 2021-09-27 | 9
122049797 | 1632 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 240 |  | 2021-09-14 |  | 2021-09-28 | 2021-09-28 | 2021-09-28 | 10
122050122 | 1633 | PGE | NEM | NEM Paired Storage | Study in Progress | ENGN, Solar PV, Storage | 140 |  | 2021-09-14 |  | 2021-09-17 | 2021-09-17 | 2021-09-17 | 3 | 2021-09-17 | 3
122051314 | 1634 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 50 |  | 2021-09-15 |  |  | 2021-09-20 | 2021-09-20 | 3 | 2021-09-20 | 3 | 2021-09-29 | 7 | [15 empty] | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29
122051677 | 1635 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.116 |  | 2021-09-15 |  | 2021-09-27 | 2021-09-27 | 2021-09-27 | 8
122052117 | 1636 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.025 |  | 2021-09-15 |  | 2021-09-29 | 2021-09-15 | 2021-09-15 | 0
122052264 | 1637 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 92.318 |  | 2021-09-15 |  |  | 2021-09-20 | 2021-09-20 | 3 | 2021-09-20 | 3 | [27 empty] | 2021-09-15 | 2021-09-20 | 2021-09-23 | 6
122055664 | 1638 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 120 |  | 2021-09-15 |  |  | 2021-09-17 | 2021-09-17 | 2 | 2021-09-17 | 2 | 2021-09-28 | 7 | [15 empty] | 2021-09-28 | 2021-09-28 | 0 | 2021-09-28
122057795 | 1639 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.116 |  | 2021-09-16 |  |  | 2021-09-23 | 2021-09-23 | 5 | 2021-09-23 | 5 | 2021-09-27 | 2 | [33 empty] | 2021-09-28 | 2021-09-28 | 0 | [15 empty] | 2021-09-28 |  |  | 2021-09-28 |  | 2021-09-28 | 0
122058430 | 1640 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 |  | 2021-09-16 |  | 2021-09-30 | 2021-09-27 | 2021-09-27 | 7 | [29 empty] | 2021-09-16
122058605 | 1641 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 185.821 |  | 2021-09-16 |  | 2021-09-23 | 2021-09-23 | 2021-09-23 | 5 | [29 empty] | 2021-09-16
122058966 | 1642 | PGE | NEM | NEMMT | Application Review in Progress | FUCE, Solar PV | 500 |  | 2021-09-16 |  | 2021-09-29 | 2021-09-29 | 2021-09-29 | 9
122059026 | 1643 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 660.864 |  | 2021-09-16 |  | 2021-09-30 | 2021-09-30 | 2021-09-30 | 10 | [29 empty] | 2021-09-16
122059406 | 1644 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 48.55 |  | 2021-09-16 |  | 2021-09-24 | 2021-09-24 | 2021-09-24 | 6
122060253 | 1645 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 35.2 |  | 2021-09-16 |  |  | 2021-09-17 | 2021-09-17 | 1 | 2021-09-17 | 1 | [21 empty] | 2021-09-17 | N/A
122060257 | 1646 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 166.5 |  | 2021-09-16 |  | 2021-09-30 | 2021-09-30 | 2021-09-30 | 10
122060336 | 1647 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 43.2 |  | 2021-09-16 |  | 2021-09-30 | 2021-09-30 | 2021-09-30 | 10
122064947 | 1648 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 2125 |  | 2021-09-17 | 2021-09-21 |  | 2021-09-20 | 2021-09-20 | 1
122065585 | 1649 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 172.8 |  | 2021-09-17 |  |  |  | 0 | [30 empty] | 2021-09-17
122065682 | 1650 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 86.4 |  | 2021-09-17 |  |  | 2021-09-20 | 2021-09-20 | 1 | 2021-09-20 | 1 | 2021-09-22 | 2 | [15 empty] | 2021-09-22 | 2021-09-22 | 0 | 2021-09-22 | [6 empty] | 2021-09-17 | 2021-09-20 | 2021-09-23 | 4
122066737 | 1651 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 60.02 |  | 2021-09-17 |  | 2021-09-27 | 2021-09-27 | 2021-09-27 | 6
122067319 | 1652 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 242 |  | 2021-09-17 |  | 2021-09-21 | 2021-09-20 | 2021-09-20 | 1 | [29 empty] | 2021-09-17
122067663 | 1653 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 166 |  | 2021-09-17 |  |  | 2021-09-29 | 2021-09-29 | 8 | 2021-09-29 | 8 | [27 empty] | 2021-09-17
122067745 | 1654 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 170 |  | 2021-09-17 |  |  | 2021-09-29 | 2021-09-29 | 8 | 2021-09-29 | 8 | [27 empty] | 2021-09-17
122067925 | 1655 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 3000 |  | 2021-09-17 | 2021-09-21 |  | 2021-09-20 | 2021-09-20 | 1
122071270 | 1656 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 38.78 |  | 2021-09-20 |  | 2021-09-30 |  | 2021-09-30 | 8 | [29 empty] | 2021-09-20
122077612 | 1657 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 56.415 |  | 2021-09-21 |  |  | 2021-09-23 | 2021-09-23 | 2 | 2021-09-23 | 2
122077732 | 1658 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 1680 |  | 2021-09-21 | 2021-09-23 |  | 2021-09-23 | 2021-09-23 | 2 | [29 empty] | 2021-09-21
122078973 | 1659 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 |  | 2021-09-21 |  |  |  | 0 | [30 empty] | 2021-09-21
122079425 | 1660 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.3 |  | 2021-09-21 |  |  |  | 0
122081092 | 1661 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 111 |  | 2021-09-21 |  |  |  | 0
122082488 | 1662 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 75 |  | 2021-09-22 |  | 2021-09-22 | 2021-09-22 | 2021-09-22 | 0
122083667 | 1663 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.11 |  | 2021-09-22 |  | 2021-09-29 | 2021-09-29 | 2021-09-29 | 5
122084597 | 1664 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 46.4 |  | 2021-09-22 |  |  |  | 0
122084895 | 1665 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 59.313 |  | 2021-09-22 |  | 2021-09-30 | 2021-09-30 | 2021-09-30 | 6 | [29 empty] | 2021-09-22
122085093 | 1666 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 35.9 |  | 2021-09-22 |  | 2021-09-30 | 2021-09-30 | 2021-09-30 | 6 | [29 empty] | 2021-09-22
122085156 | 1667 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 37.832 |  | 2021-09-22 |  | 2021-09-27 | 2021-09-27 | 2021-09-27 | 3 | [29 empty] | 2021-09-22
122085420 | 1668 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 352.056 |  | 2021-09-22 |  | 2021-09-24 | 2021-09-24 | 2021-09-24 | 2 | 2021-09-28 | 4 | [27 empty] | 2021-09-22 | 2021-09-28
122085443 | 1669 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 37.832 |  | 2021-09-22 |  | 2021-09-27 | 2021-09-27 | 2021-09-27 | 3 | [29 empty] | 2021-09-22
122085445 | 1670 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 37.832 |  | 2021-09-22 |  | 2021-09-27 | 2021-09-27 | 2021-09-27 | 3 | [29 empty] | 2021-09-22
122086155 | 1671 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 116.058 |  | 2021-09-22 |  | 2021-09-24 | 2021-09-24 | 2021-09-24 | 2
122088345 | 1672 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 250 |  | 2021-09-23 |  |  |  | 0 | [30 empty] | 2021-09-23
122089083 | 1673 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 658.3 |  | 2021-09-23 |  |  |  | 0
122089561 | 1674 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 32.87 |  | 2021-09-23 |  |  |  | 0
122091387 | 1675 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 140.115 |  | 2021-09-23 |  |  | 2021-09-28 | 2021-09-28 | 3 | 2021-09-28 | 3 | [27 empty] | 2021-09-23
122092226 | 1676 | PGE | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 420 |  | 2021-09-23 | 2021-09-24 |  | 2021-09-24 | 2021-09-24 | 1 | [29 empty] | 2021-09-23
122096792 | 1677 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 240 |  | 2021-09-24 |  |  |  | 0
122098587 | 1678 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 |  | 2021-09-24 |  | 2021-09-28 | 2021-09-28 | 2021-09-28 | 2 | [29 empty] | 2021-09-24
122098768 | 1679 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 31.024 |  | 2021-09-24 |  |  |  | 0
122099156 | 1680 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.223 |  | 2021-09-25 |  |  |  | 0
122101660 | 1681 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.781 |  | 2021-09-26 |  |  |  | 0
122103113 | 1682 | PGE | Non-NEM | Inadvertent Export | Application Review in Progress | Storage | 140.65 |  | 2021-09-26 | 2021-09-27 |  | 2021-09-27 | 2021-09-27 | 0
122103987 | 1683 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.15 |  | 2021-09-27 |  |  |  | 0
122105342 | 1684 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.232 |  | 2021-09-27 |  |  |  | 0 | [30 empty] | 2021-09-27
122105909 | 1685 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 550 |  | 2021-09-27 |  |  |  | 0 | [30 empty] | 2021-09-27
122106679 | 1686 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 51.679 |  | 2021-09-27 |  | 2021-09-28 | 2021-09-28 | 2021-09-28 | 1
122107197 | 1687 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 244.589 |  | 2021-09-27 |  |  |  | 0 | [30 empty] | 2021-09-27
122107411 | 1688 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 146.753 |  | 2021-09-27 |  |  | 2021-09-30 | 2021-09-30 | 3
122109151 | 1689 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.15 |  | 2021-09-28 |  |  |  | 0
122109295 | 1690 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 40.372 |  | 2021-09-28 |  | 2021-09-29 | 2021-09-29 | 2021-09-29 | 1
122109296 | 1691 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 40.372 |  | 2021-09-28 |  | 2021-09-29 | 2021-09-29 | 2021-09-29 | 1
122109642 | 1692 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 429 |  | 2021-09-28 |  |  |  | 0
122112221 | 1693 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 187.5 |  | 2021-09-28 |  |  |  | 0 | [30 empty] | 2021-09-28
122113003 | 1694 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 54.77 |  | 2021-09-28 |  |  |  | 0
122113186 | 1695 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 904.446 |  | 2021-09-28 |  |  |  | 0 | [30 empty] | 2021-09-28
122113265 | 1696 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.08 |  | 2021-09-28 |  |  |  | 0
122115847 | 1697 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 133.2 |  | 2021-09-28 |  | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2
122117671 | 1698 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.204 |  | 2021-09-29 |  | 2021-09-30 | 2021-09-30 | 2021-09-30 | 1
122118348 | 1699 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 49.411 |  | 2021-09-29 |  |  |  | 0 | [30 empty] | 2021-09-29
122118512 | 1700 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 45.634 |  | 2021-09-29 |  |  |  | 0 | [30 empty] | 2021-09-29
122119191 | 1701 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 39.46 |  | 2021-09-29 |  |  |  | 0
122121898 | 1702 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1331.879 |  | 2021-09-29 |  |  |  | 0
122123584 | 1703 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 342 |  | 2021-09-29 |  |  |  | 0 | [30 empty] | 2021-09-29
122124912 | 1704 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 117.6 |  | 2021-09-30 |  |  |  | 0
122125202 | 1705 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.15 |  | 2021-09-30 |  |  |  | 0
122125257 | 1706 | PGE | NEM | NEM Paired Storage | Application Review in Progress | ENGN, Solar PV, Storage | 9154.6 |  | 2021-09-30 |  |  | 2021-09-30 | 2021-09-30 | 0 | [29 empty] | 2021-09-30
122126846 | 1707 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 35.5 |  | 2021-09-30 |  |  |  | 0
122127005 | 1708 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 34.49 |  | 2021-09-30 |  |  |  | 0 | [30 empty] | 2021-09-30
122128598 | 1709 | PGE | Non-NEM | Continuous Uncompensated Export | Application Review in Progress | Solar PV | 56.891 |  | 2021-09-30 |  |  |  | 0
122129592 | 1710 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 72.405 |  | 2021-09-30 |  |  |  | 0
122129742 | 1711 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.781 |  | 2021-09-30 |  |  |  | 0 | [30 empty] | 2021-09-30
122130114 | 1712 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 3065.042 |  | 2021-09-30 |  |  |  | 0
122130667 | 1713 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 1105.818 |  | 2021-09-30 |  |  |  | 0 | [30 empty] | 2021-09-30

## OP 22 CT Q2-2021
PG&E Interconnection Timeline Report | [7 empty] | Application Review: |  |  |  |  | Fast Track Initial Review: |  | Fast Track Supplemental Review: |  |  | Electrical Independence Test (EIT): |  |  | Scoping Meeting and Study Agreement: |  |  | System Impact Study (SIS): | [5 empty] | Draft Agreement: |  |  | Agreement Execution: |  |  |  | Material Modification: |  |  | Variance Request Review: |  |  | Net Generating Output Meter (NGOM): | [6 empty] | Minor Upgrades Design: | [5 empty] | Minor Upgrades Construction: | [5 empty] | Commissioning and In-Service:
Document Submission Frequency: Quarterly |  |  |  | Reporting Interval: 12/29/20 - 6/30/21 |  |  |  | ● 10 Business Days for initial application review [E.5.a.] (15 Business Days if Cost Envelope Option is selected [E.5.a.]) | [6 empty] | 20 Business Days [F.2.c.i.] |  |  | 20 Business Days [F.3.a.] |  |  | 5 Business Days [F.3.b.i.] |  |  | 60 Business Days [F.3.b.ii.] | [8 empty] | 90 Calendar Days [F.2.e.][F.3.2.ii.] |  |  |  | 10 Business Days [F.3.b.v] (20 Business Days if Cost Envelope Option is selected [F.3.b.v]) | [12 empty] | 60 Business Days (estimated timeline) | [5 empty] | 60 Business Days (estimated timeline) | [5 empty] | Mutually Agreeable Date with Customer
Proceeding Number: R.17-07-007; Decision Number: D.20-09-035; Ordering Paragraph (OP) Number from the Decision: 22 | [7 empty] | ● 10 Business Days for 1st deficiency cure review [E.5.b.i.] | [21 empty] | ● 15 Business Days for Fast Track [F.2.a] | [12 empty] | ● 20 Business Days to Design
[8 empty] | ● 5 Business Days for 2nd deficiency cure review [E.5.b.ii.] | [21 empty] | ● 30 Calendar Days for Detailed Study [F.3.e.i.] | [12 empty] | ● 20 Business Days to Install
Key | Utility | NEM Type | Project Type | Project Status | Technology Type | SizeTotal Proposed Gen | Cost Envelope Requested? | Application Received | Provide: 1st Written Notice/Invoice | Cycle Time A (Business Days to Acknowledge Interconnection Request Submission) | Application Deemed Complete | Cycle Time b (Business Days to Deem Complete) | Conduct: Initial Review (IR) | Cycle Time c (Time from Interconnection Request deemed complete to completion of initial review & provision of results) | Conduct: Supplemental Review (SR) | Conduct: Supplemental Review (SR) | Cycle Time d (Time from Supplemental Review start date to completion of Supplemental Review) | Conduct: Screens Q and R | Conduct: Screens Q and R | Cycle Time e (Time from Electrical Interdependence Test start date to its completion) | Scoping Meeting Date | Scoping Meeting Date | Cycle time f (Time from Electrical Interdependence Test completion to EIT results scoping meeting held) | DSA Agreement Executed by PG&E | Conduct: SIS | Cycle Time h (Time from System Impact Study start date to its completion date) | Scoping Meeting Date | Tendered DSA Agreement | Cycle Time g (Time from study scoping meeting until study agreement provided) | Tender Draft IA | Tender Draft IA | Cycle Time I (Time to provide Draft Generator Interconnection Agreement applicable milestone) | Tender Draft IA | IA Negotiations/Customer Signature | Cycle Time J(a) (Time from Draft Generator Interconnection Agreement provided to date Generator Interconnection Agreement Executed) | Cycle Time J(b) (Time from Final Study Report date for Detailed Study to date Generator Interconnection Agreement Executed) | Receive Customer Changes | Determine Material Modifications | Cycle Time M (Time from request to consider modification to determination whether modification is material (F.3.b.v)) | Variance Request Received (typ. From cust) | Conduct: Variance Request Review | Cycle Time N (Time for responding to line-side taps variance requests (for Utilities that require a variance request)) | Conduct: Meter Review | Tender: Meter Invoice | Tender: Meter Invoice | Cycle Time O (Design and invoice of net generation output meter) | Move to FMO | FMO - PASS | Cycle Time P (Installation of net generation output meter) | SP&D Design Start | SP&D Deisgn End | Cycle Time Q(a) Time from customer agreement to proceed to final design and issuance of invoice SP&D | Tender EA Invoice | IT Design End | Cycle Time Q(b)Time from customer agreement to proceed to final design and issuance of invoice Telemetry | SP&D Construction Start | SP&D Construction Finish | Cycle Time R(a) Time from customer payment of invoice and completion of customer work to completion of upgrade construction SP&D | PG&E Construction Start IT | PG&E Construction Complete IT | Cycle Time R(b)Time from customer payment of invoice and completion of customer work to completion of upgrade construction Telemetry | PPI Authorization Letter | PPI Completion | Cycle Time S (Time for scheduling of commissioning test) | FMO - PASS (Move to FMO) | FMO schedule Inspection FMO order | Cycle Time S(b) This is for projects that do not require PPI | FMO - PASS | Permission to Operate - Final (COD) | Permission to Operate - Conditional (COD) | Cycle time K(a)Time from when the customer notifies the utility it has completed all of its obligations under the agreements (F.5.b) including commissioning tests, to when the utility provides the customer Permission to Operate | Conduct Pre Paralell Inspection (PPI) | Cycle time K(b) This cycle time is for projects that require PPI | Cycle Time L (Total time from submission of Interconnection Request to Permission to Operate (Not in Rule 21, tracked for informational purposes))
1 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 111.324 | No | 2020-12-29 | 2020-12-29 | 0 | 2021-01-28 | 20 | [27 empty] | 2020-12-29
2 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 32.89 | No | 2020-12-29 | 2020-12-29 | 0 | 2020-12-29 | 0 | 2021-01-19 | 13 | [15 empty] | 2021-01-19 | 2021-01-19 | 0 | 2021-01-19 | 2021-01-25 | 4 | [11 empty] | 2021-03-23 | [17 empty] | 2021-03-23 | 2021-03-23 | 0
3 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 94.943 | No | 2020-12-29 | 2020-12-29 | 0 | 2020-12-30 | 1 | 2021-01-11 | 7 | [15 empty] | 2021-01-11 | 2021-01-11 | 0 | 2021-01-11 | 2021-01-14 | 3 |  |  |  |  | 2020-12-29 | 2021-01-19 | 13 | [7 empty] | 2021-03-02 | 2021-04-27 | 40
4 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 43.2 | No | 2020-12-29 | 2021-01-11 | 8 | 2021-02-11 | 30 | 2021-02-26 | 10 | [15 empty] | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26
5 | PGE | NEM | VNEMMASH | Implementation | Solar PV | 113.676 | No | 2020-12-29 | 2021-01-13 | 10 | 2021-03-31 | 63 | 2021-04-05 | 3 | [15 empty] | 2021-04-05 | 2021-04-23 | 14 | 2021-04-23 | 2021-05-20 | 19 |  |  |  |  | 2020-12-29 | 2021-04-29 | 84
6 | PGE | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 57.325 | No | 2020-12-29 | 2021-01-05 | 4 | 2021-01-05 | 4 | 2021-01-07 | 2 | [15 empty] | 2021-01-05 | 2021-01-05 | 0 | 2021-01-05 | 2021-02-17 | 29 | [8 empty] | 2021-01-12 | 2021-01-12 | 0
7 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 207.052 | No | 2020-12-29 | 2021-01-12 | 9 | 2021-01-22 | 16 | 2021-02-17 | 17 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-05-11 | 83 |  |  |  |  | 2020-12-29
8 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 1320 | No | 2020-12-29 | 2020-12-31 | 2 | 2021-01-13 | 10 | [5 empty] | 2021-01-13 | 2021-02-05 | 16 | 2021-02-05
9 | PGE | Non-NEM | Non-Export | Implementation | Storage | 357.5 | No | 2020-12-30 | 2020-12-31 | 1 | 2021-01-27 | 18 | 2021-05-12 | 74 | [15 empty] | 2021-02-01 | 2021-02-01 | 0 | 2021-02-01 | 2021-05-25 | 80 |  |  |  |  | 2020-12-30
10 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 420 | No | 2020-12-30 | 2021-01-28 | 19 | 2021-04-08 | 68 | [17 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | [6 empty] | 2020-12-30
11 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 480 | No | 2020-12-30 | 2021-01-11 | 7 | 2021-01-28 | 19 | 2021-04-29 | 64 | [15 empty] | 2021-04-29 | 2021-04-29 | 0 | 2021-04-29 | [6 empty] | 2020-12-30
12 | PGE | NEM | EXPNEM | Commercial | Solar PV | 33.3 | No | 2020-12-30 | 2021-01-13 | 9 | 2021-01-13 | 9 | 2021-02-03 | 14 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-06-28 | 101 |  |  |  |  | 2020-12-30 | 2021-01-27 | 18 |  |  |  |  | 2021-07-06 | 2021-07-13 | 5 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-13 | 2021-07-14 |  | 1
13 | PGE | Non-NEM | Non-Export | Implementation | Storage | 140 | No | 2020-12-30 | 2020-12-31 | 1 | 2021-01-27 | 18 | 2021-03-02 | 23 | [15 empty] | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | 2021-06-28 | 83 |  |  |  |  | 2020-12-30 | 2021-02-05 | 25
14 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 125 | No | 2020-12-30 | 2020-12-31 | 1 | 2021-01-05 | 3 | 2021-01-11 | 4
15 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 140 | No | 2020-12-30 | 2020-12-31 | 1 | 2021-01-27 | 18 | [27 empty] | 2020-12-30 | 2021-04-14 | 72
16 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 90.079 | No | 2020-12-30 | 2020-12-31 | 1 | 2021-03-30 | 61 | 2021-05-04 | 25 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04
17 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.454 | No | 2020-12-31 | 2021-01-07 | 4 | 2021-01-07 | 4 | 2021-01-28 | 14 | [15 empty] | 2021-01-07 | 2021-01-07 | 0 | 2021-01-07 | 2021-02-16 | 26 | [11 empty] | 2021-02-16 | 2021-02-17 | 1 | [15 empty] | 2021-02-16 | 2021-02-17 | 1 | 2021-02-17 | 2021-02-17 |  | 0
19 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 58.04 | No | 2020-12-31 | 2021-01-14 | 9 | 2021-01-14 | 9 | 2021-02-11 | 19 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11
20 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 120 | No | 2021-01-04 | 2021-01-05 | 1 | 2021-01-11 | 5 | 2021-01-21 | 7 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-06-03 | 93 |  |  |  |  | 2021-01-04
21 | PGE | NEM | EXPNEM | Implementation | Solar PV | 131.497 | No | 2021-01-04 | 2021-01-14 | 8 | 2021-01-14 | 8 | 2021-02-04 | 14 | [15 empty] | 2021-02-04 | 2021-02-04 | 0 | 2021-02-04 | 2021-03-21 | 30 |  |  |  |  | 2021-01-04 | 2021-03-01 | 38 | [7 empty] | 2021-06-14
22 | PGE | NEM | EXPNEM | Implementation | Solar PV | 700 | No | 2021-01-04 | 2021-01-15 | 9 | 2021-01-15 | 9 | 2021-02-04 | 13 | [15 empty] | 2021-02-04 | 2021-02-04 | 0 | 2021-02-04 | 2021-02-05 | 1 |  |  |  |  | 2021-02-04 | 2021-02-09 | 3
23 | PGE | NEM | EXPNEM | Commercial | Solar PV | 99.9 | No | 2021-01-04 | 2021-01-07 | 3 | 2021-01-15 | 9 | 2021-02-02 | 11 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-02 | 0 | [11 empty] | 2021-02-03 | 2021-02-09 | 4 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-09 | 2021-02-10 |  | 1
24 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 52.49 | No | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
25 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 61.773 | No | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
26 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 65.263 | No | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
27 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.444 | No | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
28 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 63.867 | No | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
29 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 62.122 | No | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
30 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 41.88 | No | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
31 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 63.169 | No | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
32 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 57.585 | No | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
33 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 | No | 2021-01-05 | 2021-01-08 | 3 | 2021-01-08 | 3 | 2021-01-11 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-02-17 | 26 | [11 empty] | 2021-02-17 | 2021-02-17 | 0 | [15 empty] | 2021-02-17 | 2021-02-17 | 0 | 2021-02-17 | 2021-02-17 |  | 0
34 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 | No | 2021-01-05 | 2021-01-06 | 1 | 2021-01-19 | 9 | 2021-02-18 | 21 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-05-26 | 69 |  |  |  |  | 2021-01-05 | 2021-01-20 | 10 |  |  |  |  | 2021-07-16 | [17 empty] | 2021-07-16 | 2021-07-16 | 0
35 | PGE | NEM | EXPNEM | Commercial | Solar PV | 85.573 | No | 2021-01-05 | 2021-01-06 | 1 | 2021-01-07 | 2 | 2021-01-08 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-03-10 | 41 |  |  |  |  | 2021-01-05 | [6 empty] | 2021-03-12 | 2021-04-21 | 28 | [15 empty] | 2021-03-12 | 2021-04-21 | 28 | 2021-04-21 | 2021-04-23 |  | 2
36 | PGE | NEM | EXPNEM | Commercial | Solar PV | 53.808 | No | 2021-01-05 | 2021-01-06 | 1 | 2021-01-06 | 1 | 2021-01-21 | 10 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-04-09 | 55 | [11 empty] | 2021-04-12 | 2021-04-19 | 5 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-19 | 2021-04-27 |  | 6
37 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 | No | 2021-01-05 | 2021-01-20 | 10 | 2021-01-28 | 16 | 2021-02-02 | 3 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-04 | 2 | [11 empty] | 2021-02-08 | 2021-02-08 | 0 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-02-10 |  | 2
38 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.886 | No | 2021-01-05 | 2021-01-06 | 1 | 2021-01-27 | 15 | 2021-02-11 | 11 | [15 empty] | 2021-02-11 | 2021-02-16 | 2 | 2021-02-16 | 2021-02-23 | 5 |  |  |  |  | 2021-01-05 | 2021-02-16 | 28 | [7 empty] | 2021-03-17 | 2021-06-03 | 55 |  |  |  | 2021-06-03
39 | PGE | NEM | EXPNEM | Commercial | Solar PV | 83.3 | No | 2021-01-05 | 2021-01-19 | 9 | 2021-01-19 | 9 | 2021-02-02 | 10 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-06-28 | 102 |  |  |  |  | 2021-01-05 | 2021-01-28 | 16 |  |  |  |  | 2021-07-06 | 2021-07-13 | 5 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-13 | 2021-07-13 |  | 0
40 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100 | No | 2021-01-05 | 2021-01-06 | 1 | 2021-01-13 | 6 | 2021-02-02 | 13 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-02 | 0 |  |  |  |  | 2021-01-05 | 2021-01-20 | 10
41 | PGE | NEM | EXPNEM | Commercial | Solar PV | 33.3 | No | 2021-01-05 | 2021-01-19 | 9 | 2021-01-19 | 9 | 2021-02-08 | 14 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-03-01 | 14 | [11 empty] | 2021-03-23 | 2021-04-01 | 7 | [15 empty] | 2021-03-23 | 2021-03-24 | 1 | 2021-04-01 | 2021-04-01 |  | 0
42 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 433.597 | No | 2021-01-05 | 2021-01-12 | 5 | 2021-01-12 | 5 | 2021-02-19 | 26 |  |  |  | 2021-03-02 | 2021-04-23 | 38 | 2021-04-23 |  |  | 4/23/2021 | 2021-07-16 | 58
43 | PGE | NEM | VNEMMASH | Implementation | Solar PV | 530 | No | 2021-01-05 | 2021-01-12 | 5 | 2021-01-12 | 5 | 2021-02-24 | 29 | [15 empty] | 2021-02-24 | 2021-02-24 | 0 | 2021-02-24 | 2021-05-05 | 50 | [7 empty] | 2021-06-17
44 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2600.5 | No | 2021-01-06 | 2021-01-07 | 1 | 2021-01-27 | 14 | [5 empty] | 2021-01-27 | 2021-03-04 | 25 | 2021-03-04 | 2021-03-04 | 0 | 2021-03-25 | 2021-06-21 | 61 | 2021-03-04 | 2021-03-08 | 2 | [7 empty] | 2021-07-15
46 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 493.369 | No | 2021-01-06 | 2021-01-07 | 1 | 2021-02-23 | 32 | 2021-03-09 | 10 | [15 empty] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09
47 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 1625 | No | 2021-01-06 | 2021-01-07 | 1 | 2021-01-20 | 9 | 2021-03-02 | 28 | 2021-03-08 | 2021-04-01 | 18 | 2021-05-03 | 2021-05-12 | 7 | 2021-05-12 | 2021-05-13 | 1 | 2021-05-21 |  |  | 2021-05-13 | 2021-05-13 | 0
48 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 52.675 | No | 2021-01-06 | 2021-01-19 | 8 | 2021-01-19 | 8 | 2021-02-08 | 14 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08
50 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 53.35 | No | 2021-01-07 | 2021-01-08 | 1 | 2021-01-08 | 1 | 2021-01-26 | 11 | [15 empty] | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 2021-01-29 | 3 |  |  |  |  | 2021-01-07 | 2021-02-08 | 21
51 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 | No | 2021-01-07 | 2021-01-08 | 1 | 2021-01-08 | 1 | 2021-02-08 | 20 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-02-12 | 4 |  |  |  |  | 2021-01-07 | 2021-02-09 | 22
52 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 112.682 | No | 2021-01-07 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-28 | 11 | [15 empty] | 2021-01-28 | [9 empty] | 2021-01-07
53 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 168.87 | No | 2021-01-07 | 2021-01-08 | 1 | 2021-01-11 | 2 | 2021-02-20 | 27 | [15 empty] | 2021-02-20 | 2021-02-20 | 0 | 2021-02-20 | [6 empty] | 2021-01-07 | 2021-03-03 | 37
54 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.741 | No | 2021-01-07 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-03-09 | 38 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-03-10 | 39 | [11 empty] | 2021-03-10 | 2021-03-10 | 0 | [15 empty] | 2021-03-10 | 2021-03-10 | 0 | 2021-03-10 | 2021-03-13 |  | 2
55 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 41.331 | No | 2021-01-07 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-14 | 2 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-05-17 | 87 |  |  |  |  | 2021-01-07 | 2021-05-17 | 90 |  |  |  |  | 2021-05-20 | 2021-05-21 | 1 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-21 | 2021-05-21 |  | 0
56 | PGE | NEM | EXPNEM | Implementation | Solar PV | 62.5 | No | 2021-01-07 | 2021-01-21 | 9 | 2021-01-21 | 9 | 2021-03-10 | 33 | [15 empty] | 2021-03-10 | 2021-03-10 | 0 | 2021-03-10 | 2021-06-28 | 77 |  |  |  |  | 2021-01-07 | 2021-02-02 | 17 |  |  |  |  | 2021-07-14 | [17 empty] | 2021-07-14 | 2021-07-14 | 0
57 | PGE | NEM | EXPNEM | Implementation | Solar PV | 54.229 | No | 2021-01-07 | 2021-01-21 | 9 | 2021-01-21 | 9 | 2021-02-10 | 14 | [15 empty] | 2021-02-10 | 2021-02-10 | 0 | 2021-02-10 | 2021-03-03 | 14 |  |  |  |  | 2021-01-07 | 2021-05-28 | 99 | [7 empty] | 2021-06-22
59 | PGE | NEM | EXPNEM | Implementation | Solar PV | 82.656 | No | 2021-01-08 | 2021-01-22 | 9 | 2021-01-22 | 9 | 2021-03-03 | 27 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-06-15 | 73 |  |  |  |  | 2021-03-12 | 2021-03-15 | 1
60 | PGE | NEM | EXPNEM | Commercial | Solar PV | 60 | No | 2021-01-08 | 2021-01-22 | 9 | 2021-01-22 | 9 | 2021-02-11 | 14 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-22 | 6 |  |  |  |  | 2021-01-08 | 2021-02-02 | 16 |  |  |  |  | 2021-05-01 | 2021-05-10 | 5 | [15 empty] | 2021-05-01 | 2021-05-03 | 0 | 2021-05-10 | 2021-05-10 |  | 0
61 | PGE | NEM | EXPNEM | Implementation | Solar PV | 83.3 | No | 2021-01-08 | 2021-01-23 | 9 | 2021-01-23 | 9 | 2021-02-06 | 10 | [15 empty] | 2021-02-06 | 2021-02-06 | 0 | 2021-02-06 | 2021-06-02 | 80 |  |  |  |  | 2021-01-08 | 2021-02-02 | 16
62 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 | No | 2021-01-08 | 2021-01-16 | 5 | 2021-02-24 | 31 | 2021-03-15 | 13 | [15 empty] | 2021-02-24 | 2021-02-24 | 0 | 2021-02-24 | 2021-03-10 | 10 | [11 empty] | 2021-03-15 | 2021-03-15 | 0 | [15 empty] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | 2021-03-22 |  | 5
63 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 350 | No | 2021-01-08 | 2021-01-11 | 1 | 2021-02-03 | 17 | 2021-04-30 | 61 | [15 empty] | 2021-04-30 | 2021-04-30 | 0 | 2021-04-30 | 2021-05-06 | 4 |  |  |  |  | 2021-01-08 | 2021-04-12 | 64
64 | PGE | NEM | EXPNEM | Commercial | Solar PV | 62.5 | No | 2021-01-08 | 2021-01-23 | 9 | 2021-01-23 | 9 | 2021-02-09 | 11 | [15 empty] | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | 2021-07-06 | 102 |  |  |  |  | 2021-01-08 | 2021-02-02 | 16 |  |  |  |  | 2021-07-06 | 2021-07-14 | 6 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-14 | 2021-07-14 |  | 0
65 | PGE | NEM | VNEMSOMAH | Application Accepted | Solar PV | 74.404 | No | 2021-01-08 | 2021-01-14 | 4 | 2021-01-18 | 5 | 2021-04-06 | 54 | [25 empty] | 2021-01-08 |  |  | 2021-01-19
66 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 172.8 | No | 2021-01-08 | 2021-01-22 | 9 | 2021-06-25 | 117 | [5 empty] | 2021-06-25 | [21 empty] | 2021-01-08
67 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 37.68 | No | 2021-01-08 | 2021-01-14 | 4 | 2021-01-21 | 8 | 2021-01-25 | 2 | [15 empty] | 2021-01-14 | 2021-01-14 | 0 | 2021-01-14
68 | PGE | Non-NEM | Non-Export | Implementation | Storage | 140 | No | 2021-01-08 | 2021-01-11 | 1 | 2021-02-03 | 17 | 2021-03-30 | 38 | [15 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-04-12 | 9 |  |  |  |  | 2021-01-08
69 | PGE | NEM | EXPNEM | Commercial | Solar PV | 33.3 | No | 2021-01-08 | 2021-01-12 | 2 | 2021-01-12 | 2 | 2021-02-25 | 30 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-26 | 21 |  |  |  |  | 2021-01-08 |  |  | 2021-02-05 | 2021-03-25 | 2021-03-25 | 33 | 2021-05-24 | 2021-06-02 | 6 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-06-02 | 2021-06-04 |  | 2
70 | PGE | NEM | NEM Paired Storage | IA in Progress | ENGN, Solar PV, Storage | 924.893 | No | 2021-01-08 | 2021-01-20 | 7 | 2021-03-31 | 56 | 2021-05-10 | 28 | [15 empty] | 2021-05-10 | 2021-05-11 | 1 | 2021-05-11 | [6 empty] | 2021-01-08
71 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 30.399 | No | 2021-01-09 | 2021-01-16 | 5 | 2021-01-16 | 5 | 2021-02-04 | 12 | [15 empty] | 2021-01-16 | 2021-01-16 | 0 | 2021-01-16 | 2021-02-16 | 19
72 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 | No | 2021-01-08 | 2021-01-14 | 4 | 2021-01-14 | 4 | 2021-02-03 | 13 | [15 empty] | 2021-01-14 | 2021-01-14 | 0 | 2021-01-14 | 2021-02-03 | 13 | [11 empty] | 2021-02-03 | 2021-02-09 | 4 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-09 | 2021-02-09 |  | 0
73 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 150 | No | 2021-01-09 | 2021-01-11 | 0 | 2021-01-13 | 2 | 2021-03-15 | 41 | [15 empty] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | [6 empty] | 2021-02-23 | 2021-02-23 | 0
74 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 62.048 | No | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
75 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.292 | No | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
76 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 38.78 | No | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
77 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.292 | No | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
79 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 62.048 | No | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
80 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 42.054 | No | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
81 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 35.045 | No | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
82 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.292 | No | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
83 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 32.032 | No | 2021-01-11 | 2021-01-12 | 1 | 2021-01-12 | 1 | 2021-01-27 | 10 | [15 empty] | 2021-01-27 | 2021-01-27 | 0 | 2021-01-27 | [6 empty] | 2021-01-11 | 2021-01-26 | 10
84 | PGE | NEM | EXPNEM | Implementation | Solar PV | 66.6 | No | 2021-01-11 | 2021-01-12 | 1 | 2021-01-19 | 5 | 2021-02-03 | 11 | 2021-02-03 | 2021-03-18 | 30 | 2021-03-23 | 2021-03-25 | 2 | 2021-03-25 |  |  | 3/25/2021 | 2021-06-22 | 62 |  |  |  | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-06-23 | 1 |  |  |  |  | 2021-01-11 | 2021-01-26 | 10
85 | PGE | NEM | EXPNEM | Implementation | Solar PV | 40.1 | No | 2021-01-11 | 2021-01-26 | 10 | 2021-01-26 | 10 | 2021-02-18 | 16 | [15 empty] | 2021-02-16 | 2021-02-16 | 0 | 2021-02-16 | 2021-02-22 | 4 |  |  |  |  | 2021-01-11 | 2021-02-03 | 16
86 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 37.099 | No | 2021-01-11 | 2021-01-12 | 1 | 2021-03-30 | 54 | [27 empty] | 2021-01-11 | 2021-02-05 | 18
87 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 91.918 | No | 2021-01-11 | 2021-01-12 | 1 | 2021-01-19 | 5 | 2021-02-03 | 11 | 2021-02-03 | 2021-03-18 | 30 | 2021-03-24 | 2021-03-25 | 1 | 2021-03-25 | [18 empty] | 2021-01-11 | 2021-02-02 | 15
88 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 55.708 | No | 2021-01-11 | 2021-01-12 | 1 | 2021-01-19 | 5 | 2021-02-02 | 10 | 2021-02-02 | 2021-03-19 | 32 | 2021-03-24 | 2021-03-25 | 1 | 2021-03-25 | [18 empty] | 2021-01-11 | 2021-02-02 | 15
89 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.409 | No | 2021-01-11 | 2021-01-16 | 4 | 2021-01-16 | 4 | 2021-02-01 | 9 | [15 empty] | 2021-01-16 | 2021-01-16 | 0 | 2021-01-16 | 2021-01-19 | 0 | [11 empty] | 2021-02-01 | 2021-02-01 | 0 | [15 empty] | 2021-02-01 | 2021-02-01 | 0 | 2021-02-01 | 2021-02-01 |  | 0
90 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.714 | No | 2021-01-11 | 2021-01-19 | 5 | 2021-02-05 | 18 | 2021-02-22 | 10 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | 2021-02-08 | 1 | [11 empty] | 2021-02-22 | 2021-03-03 | 7 | [15 empty] | 2021-02-22 | 2021-02-23 | 1 | 2021-03-03 | 2021-03-06 |  | 2
91 | PGE | Non-NEM | Non-Export | Implementation | Storage | 280 | No | 2021-01-11 | 2021-01-12 | 1 | 2021-02-03 | 16 | 2021-03-01 | 17 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-05-27 | 63 |  |  |  |  | 2021-01-11
92 | PGE | NEM | NEMMT | Study in Progress | Solar PV | 663.66 | No | 2021-01-11 | 2021-01-26 | 10 | 2021-02-19 | 27 | 2021-03-11 | 14 | 2021-03-11 | 2021-04-08 | 20 | 2021-04-08 | 2021-05-11 | 23 | 2021-05-11 | [18 empty] | 2021-01-11 | 2021-02-03 | 16 | 2021-06-17
93 | PGE | NEM | EXPNEM | Commercial | Solar PV | 95.8 | No | 2021-01-11 | 2021-01-12 | 1 | 2021-01-13 | 2 | 2021-01-29 | 11 | [15 empty] | 2021-01-29 | 2021-02-14 | 10 | 2021-02-14 | 2021-02-18 | 2 | [11 empty] | 2021-05-07 | 2021-05-18 | 7 | [15 empty] | 2021-05-07 | 2021-05-10 | 1 | 2021-05-18 | 2021-05-21 |  | 3
94 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 3858.508 | No | 2021-02-16 | 2021-02-17 | 1 | 2021-03-03 | 11 | [5 empty] | 2021-03-04 | 2021-04-07 | 24 | 2021-04-07 | 2021-04-07 | 0 | 2021-05-03 | 2021-07-12 | 48 | 2021-04-07 | 2021-04-08 | 1 | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13 | [6 empty] | 2021-02-16
95 | PGE | NEM | EXPNEM | Implementation | Solar PV | 520 | No | 2021-02-01 | 2021-02-12 | 9 | 2021-02-25 | 17 | 2021-03-03 | 4 | 2021-03-03 | 2021-03-31 | 20 | [12 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | 2021-06-04 | 46
96 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.404 | No | 2021-01-28 | 2021-01-28 | 0 | 2021-02-04 | 5 | 2021-02-11 | 5 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-11 | 0
97 | PGE | NEM | EXPNEM | Commercial | Solar PV | 200 | No | 2021-01-21 | 2021-01-22 | 1 | 2021-01-22 | 1 | 2021-02-12 | 15 | [15 empty] | 2021-02-12 | 2021-02-12 | 0 | 2021-02-12 | 2021-02-17 | 2 | [11 empty] | 2021-06-02 | 2021-06-10 | 6 | [15 empty] | 2021-06-02 | 2021-06-03 | 1 | 2021-06-10 | 2021-06-17 |  | 5
98 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 250 | No | 2021-01-27 | 2021-01-28 | 1 | 2021-01-29 | 2 | 2021-02-14 | 10 | [15 empty] | 2021-02-14 | 2021-02-14 | 0 | 2021-02-14 | 2021-02-18 | 2
99 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 127.683 | No | 2021-02-11 | 2021-02-12 | 1 | 2021-02-16 | 2 | 2021-02-20 | 3 | [15 empty] | 2021-02-20 | 2021-02-20 | 0 | 2021-02-20 | 2021-02-24 | 2 |  |  |  |  | 2021-02-11
100 | PGE | NEM | EXPNEM | IA in Progress | Solar PV, Storage | 94.803 | No | 2021-01-14 | 2021-01-15 | 1 | 2021-02-18 | 23 | 2021-03-01 | 7 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-03 | 2
101 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.06 | No | 2021-02-03 | 2021-02-04 | 1 | 2021-02-04 | 1 | 2021-02-18 | 9 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-05-26 | 69 | [11 empty] | 2021-06-08 | [17 empty] | 2021-06-08 | 2021-06-29 | 15
102 | PGE | NEM | EXPNEM | Commercial | Solar PV | 63.135 | No | 2021-02-11 | 2021-02-12 | 1 | 2021-02-16 | 2 | 2021-03-03 | 11 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-08 | 3 | [11 empty] | 2021-05-12 | 2021-05-19 | 5 | [15 empty] | 2021-05-12 | 2021-05-13 | 1 | 2021-05-19 | 2021-05-26 |  | 5
103 | PGE | NEM | EXPNEM | Implementation | Solar PV | 770 | No | 2021-02-18 | 2021-02-23 | 3 | 2021-02-23 | 3 | 2021-03-01 | 4 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-11 | 8 | [14 empty] | 2021-05-18
104 | PGE | NEM | EXPNEM | Implementation | Solar PV | 31.062 | No | 2021-02-04 | 2021-02-16 | 7 | 2021-02-16 | 7 | 2021-03-12 | 18 | [15 empty] | 2021-03-12 | 2021-03-12 | 0 | 2021-03-12 | 2021-03-12 | 0
105 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 316.555 | No | 2021-01-28 | 2021-02-03 | 4 | 2021-04-28 | 63 | 2021-03-08 | 37 | [15 empty] | 2021-03-08 | 2021-03-17 | 7 | 2021-03-17 | 2021-03-18 | 1 |  |  |  |  | 2021-01-28
106 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 103.592 | No | 2021-02-26 | 2021-03-01 | 1 | 2021-03-04 | 4 | 2021-03-23 | 13 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | 2021-03-24 | 1 |  |  |  |  | 2021-02-26 | 2021-05-28 | 65
107 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 40.733 | No | 2021-02-12 | 2021-02-16 | 1 | 2021-02-16 | 1 | 2021-03-02 | 10 | [15 empty] | 2021-03-02 | 2021-03-03 | 1 | 2021-03-03 | 2021-03-26 | 17
108 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 260.887 | No | 2021-02-26 | 2021-03-02 | 2 | 2021-03-09 | 7 | 2021-03-29 | 14 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-03-29 | 0 |  |  |  |  | 2021-02-26
109 | PGE | NEM | EXPNEM | IA in Progress | Solar PV, Storage | 94.803 | No | 2021-01-14 | 2021-01-15 | 1 | 2021-02-01 | 11 | 2021-02-11 | 8 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-16 | 2 |  |  |  |  | 2021-01-14 | 2021-01-28 | 9 |  |  |  |  | 2021-07-14 | [17 empty] | 2021-07-14 | 2021-07-15 | 1
110 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 86.965 | No | 2021-01-26 | 2021-01-26 | 0 | 2021-01-28 | 2 | 2021-02-18 | 14 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-02 | 8 |  |  |  |  | 2021-01-26 | 2021-02-03 | 6 | [7 empty] | 2021-05-18
111 | PGE | NEM | EXPNEM | Implementation | Solar PV | 150 | No | 2021-01-20 | 2021-01-28 | 6 | 2021-01-29 | 7 | 2021-01-29 | 0 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-01 | 4 |  |  |  |  | 2021-01-20 | 2021-02-05 | 12 |  |  |  |  | 2021-07-08 | [17 empty] | 2021-07-08 | 2021-07-08 | 0
112 | PGE | NEM | EXPNEM | Commercial | Solar PV | 69.6 | No | 2021-01-14 | 2021-01-28 | 9 | 2021-01-28 | 9 | 2021-02-18 | 14 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-23 | 23 |  |  |  |  | 2021-01-14 | 2021-02-05 | 15 |  |  |  |  | 2021-05-11 | 2021-05-19 | 6 | [15 empty] | 2021-05-11 | 2021-05-12 | 1 | 2021-05-19 | 2021-05-19 |  | 0
113 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 167.045 | No | 2021-01-28 | 2021-01-29 | 1 | 2021-02-01 | 2 | 2021-03-15 | 29 | [15 empty] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | 2021-03-25 | 8 |  |  |  |  | 2021-01-28 | 2021-02-05 | 6
114 | PGE | NEM | EXPNEM | Commercial | Solar PV | 185.596 | No | 2021-02-03 | 2021-02-04 | 1 | 2021-02-10 | 5 | 2021-02-25 | 10 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-03 | 4 |  |  |  |  | 2021-02-03 | 2021-02-09 | 4 |  |  |  |  | 2021-05-11 | 2021-05-20 | 7 | [15 empty] | 2021-05-11 | 2021-05-12 | 1 | 2021-05-20 | 2021-05-27 |  | 5
115 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 65 | No | 2021-01-28 | 2021-02-08 | 7 | 2021-02-08 | 7 | 2021-03-03 | 16 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-04 | 1 |  |  |  |  | 2021-01-28 | 2021-02-09 | 8
116 | PGE | NEM | EXPNEM | Implementation | Solar PV | 66.6 | No | 2021-01-28 | 2021-02-05 | 6 | 2021-02-10 | 9 | 2021-02-17 | 4 | [15 empty] | 2021-02-17 | 2021-02-17 | 0 | 2021-02-17 | 2021-03-16 | 19 |  |  |  |  | 2021-01-28 | 2021-02-09 | 8
117 | PGE | NEM | EXPNEM | Commercial | Solar PV | 48.582 | No | 2021-02-03 | 2021-02-04 | 1 | 2021-02-14 | 7 | 2021-03-05 | 13 | [15 empty] | 2021-03-05 | 2021-03-05 | 0 | 2021-03-05 | 2021-03-09 | 2 |  |  |  |  | 2021-02-03 | 2021-02-16 | 8 |  |  |  |  | 2021-05-06 | 2021-05-17 | 7 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-17 | 2021-05-20 |  | 3
118 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 147.625 | No | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 0 | 2021-02-11 | 12 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-22 | 6 |  |  |  |  | 2021-01-26 | 2021-03-01 | 23
119 | PGE | NEM | EXPNEM | Commercial | Solar PV | 175 | No | 2021-01-25 | 2021-01-26 | 1 | 2021-01-28 | 3 | 2021-02-12 | 11 | [15 empty] | 2021-02-12 | 2021-02-12 | 0 | 2021-02-12 | 2021-02-17 | 2 |  |  |  |  | 2021-01-25 | 2021-03-12 | 33 |  |  |  |  | 2021-05-24 | 2021-06-03 | 7 | [15 empty] | 2021-05-24 | 2021-05-26 | 2 | 2021-06-03 | 2021-06-09 |  | 4
120 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 32.77 | No | 2021-01-28 | 2021-01-29 | 1 | 2021-02-04 | 5 | 2021-03-04 | 19 | [15 empty] | 2021-03-04 | 2021-03-04 | 0 | 2021-03-04 | 2021-03-11 | 5 |  |  |  |  | 2021-01-29 | 2021-03-17 | 32
121 | PGE | NEM | EXPNEM | Commercial | Solar PV | 50 | No | 2021-01-29 | 2021-02-09 | 7 | 2021-02-10 | 8 | 2021-03-02 | 13 | [15 empty] | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | 2021-03-05 | 3 |  |  |  |  | 2021-01-29 | 2021-04-29 | 63 |  |  |  |  | 2021-05-07 | 2021-05-07 | 0 | [15 empty] | 2021-05-07 | 2021-05-07 | 0 | 2021-05-07 | 2021-05-07 |  | 0
122 | PGE | NEM | EXPNEM | Commercial | Solar PV | 47.82 | No | 2021-01-15 | 2021-01-19 | 1 | 2021-01-28 | 8 | 2021-02-02 | 3 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-18 | 11 | [11 empty] | 2021-02-22 | 2021-02-26 | 4 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-26 | 2021-03-03 |  | 3
123 | PGE | NEM | EXPNEM | Commercial | Solar PV | 56.866 | No | 2021-01-14 | 2021-01-15 | 1 | 2021-01-29 | 10 | 2021-02-11 | 9 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-03-11 | 19 |  |  |  |  | 2021-01-14 | 2021-01-28 | 9 |  |  |  |  | 2021-03-15 | 2021-03-24 | 7 | [15 empty] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-24 | 2021-03-25 |  | 1
124 | PGE | NEM | EXPNEM | Commercial | Solar PV | 31.024 | No | 2021-02-02 | 2021-02-03 | 1 | 2021-02-03 | 1 | 2021-02-26 | 16 | [15 empty] | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-03-15 | 11 | [11 empty] | 2021-03-18 | 2021-03-24 | 4 | [15 empty] | 2021-03-18 | 2021-03-19 | 1 | 2021-03-24 | 2021-03-25 |  | 1
125 | PGE | NEM | EXPNEM | Commercial | Solar PV | 68.358 | No | 2021-01-13 | 2021-01-28 | 10 | 2021-01-28 | 10 | 2021-02-18 | 14 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-10 | 14 | [11 empty] | 2021-03-13 | 2021-03-25 | 8 | [15 empty] | 2021-03-13 | 2021-03-15 | 0 | 2021-03-25 | 2021-03-25 |  | 0
126 | PGE | NEM | EXPNEM | Commercial | Solar PV | 33.3 | No | 2021-02-11 | 2021-02-16 | 2 | 2021-03-09 | 17 | 2021-03-24 | 11 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-03-26 | 2 |  |  |  |  | 2021-02-17 | [6 empty] | 2021-03-29 | 2021-04-02 | 4 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-04-02 | 2021-04-05 |  | 1
128 | PGE | NEM | EXPNEM | Commercial | Solar PV | 70.479 | No | 2021-01-18 | 2021-01-20 | 1 | 2021-03-09 | 34 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-03-31 | 3 |  |  |  |  | 2021-03-02 | 2021-03-12 | 8 |  |  |  |  | 2021-04-02 | 2021-04-12 | 6 | [15 empty] | 2021-04-02 | 2021-04-05 | 1 | 2021-04-12 | 2021-04-19 |  | 5
131 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 33.05 | No | 2021-01-14 | 2021-01-25 | 6 | 2021-01-25 | 6 | 2021-02-04 | 8 | [15 empty] | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | 2021-02-04 | 8
134 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 40.356 | No | 2021-02-11 | 2021-02-22 | 6 | 2021-03-11 | 19 | 2021-03-17 | 4 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-02-26 | 4
135 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 34.2 | No | 2021-01-28 | 2021-02-10 | 9 | 2021-03-17 | 33 | 2021-03-25 | 6 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-21 | 2 | [14 empty] | 2021-06-30
136 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 35.356 | No | 2021-03-23 | 2021-04-06 | 10 | 2021-04-06 | 10 | 2021-04-07 | 1 | [19 empty] | 2021-03-23 | N/A | [8 empty] | 2021-04-29 | 2021-04-29 | 0 | 2021-07-16 | [17 empty] | 2021-07-16 | 2021-07-16 | 0
139 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 | No | 2021-02-04 | 2021-02-10 | 4 | 2021-04-14 | 48 | 2021-04-23 | 7 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-29 | 24 | [11 empty] | 2021-04-23 | 2021-04-24 | 0 | [15 empty] | 2021-04-23 | 2021-04-24 | 0 | 2021-04-24 | 2021-04-27 |  | 1
140 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.8 | No | 2021-03-30 | 2021-04-09 | 8 | 2021-05-21 | 38 | 2021-05-26 | 3 | [15 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-03-30 | 0 | [11 empty] | 2021-05-26 | 2021-05-26 | 0 | [15 empty] | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 | 2021-05-27 |  | 1
141 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 53.626 | No | 2021-02-11 | 2021-02-22 | 6 | 2021-03-11 | 19 | 2021-03-22 | 7 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-01 | 5 |  |  |  |  | 2021-04-22 | 2021-05-07 | 11 | [7 empty] | 2021-06-10
144 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 39.988 | No | 2021-02-05 | 2021-02-21 | 9 | 2021-03-16 | 26 | 2021-03-24 | 6 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-16 | 0 |  |  |  |  | 2021-05-19 | 2021-05-28 | 7 |  |  |  |  | 2021-06-15 | 2021-06-25 | 8 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-25 | 2021-06-28 |  | 1
145 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 39.857 | No | 2021-01-15 | 2021-01-25 | 5 | 2021-01-25 | 5 | 2021-01-26 | 1 | [15 empty] | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | 2021-01-28 | 3 | [11 empty] | 2021-01-28 | 2021-01-28 | 0 | [15 empty] | 2021-01-28 | 2021-01-28 | 0 | 2021-01-28 | 2021-01-30 |  | 1
146 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 | No | 2020-12-29 | 2021-01-12 | 9 | 2021-01-28 | 20 | 2021-02-02 | 3 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-03 | 1 | [11 empty] | 2021-02-11 | 2021-02-11 | 0 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-17 |  | 3
147 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 | No | 2021-01-21 | 2021-02-03 | 9 | 2021-02-03 | 9 | 2021-02-09 | 4 | [15 empty] | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | 2021-02-09 | 0 | [11 empty] | 2021-02-12 | 2021-02-12 | 0 | [15 empty] | 2021-02-12 | 2021-02-12 | 0 | 2021-02-12 | 2021-02-17 |  | 2
148 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 | No | 2021-01-15 | 2021-01-28 | 8 | 2021-01-28 | 8 | 2021-02-08 | 7 | [15 empty] | 2021-01-28 | 2021-01-28 | 0 | 2021-01-28 | 2021-02-08 | 7 | [11 empty] | 2021-02-08 | 2021-02-16 | 5 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-16 | 2021-02-17 |  | 1
150 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 | No | 2021-02-11 | 2021-02-23 | 7 | 2021-02-23 | 7 | 2021-02-26 | 3 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-02-23 | 0 | [11 empty] | 2021-02-26 | 2021-02-28 | 0 | [15 empty] | 2021-02-26 | 2021-02-28 | 0 | 2021-02-28 | 2021-03-06 |  | 5
152 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 | No | 2021-02-16 | 2021-03-01 | 9 | 2021-03-01 | 9 | 2021-03-02 | 1 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-03 | 2 | [11 empty] | 2021-03-04 | 2021-03-04 | 0 | [15 empty] | 2021-03-04 | 2021-03-04 | 0 | 2021-03-04 | 2021-03-06 |  | 1
153 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 | No | 2021-02-08 | 2021-02-23 | 10 | 2021-02-23 | 10 | 2021-03-03 | 6 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-02 | 5 | [11 empty] | 2021-03-08 | 2021-03-08 | 0 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-03-11 |  | 3
154 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 | No | 2021-02-08 | 2021-02-23 | 10 | 2021-02-23 | 10 | 2021-03-03 | 6 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-03 | 6 | [11 empty] | 2021-03-08 | 2021-03-08 | 0 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-03-11 |  | 3
155 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 | No | 2021-02-18 | 2021-03-03 | 9 | 2021-03-03 | 9 | 2021-03-04 | 1 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-08 | 3 |  |  |  |  | 2021-02-18 | 2021-03-03 | 9 |  |  |  |  | 2021-03-08 | 2021-03-08 | 0 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-03-13 |  | 4
157 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.92 | No | 2021-02-11 | 2021-02-23 | 7 | 2021-02-25 | 9 | 2021-03-09 | 8 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-02 | 3 | [11 empty] | 2021-03-09 | 2021-03-10 | 1 | [15 empty] | 2021-03-09 | 2021-03-10 | 1 | 2021-03-10 | 2021-03-13 |  | 2
159 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 | No | 2021-02-11 | 2021-02-23 | 7 | 2021-02-23 | 7 | 2021-02-25 | 2 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-08 | 9 | [11 empty] | 2021-03-11 | 2021-03-11 | 0 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | 2021-03-13 |  | 1
161 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.337 | No | 2021-01-25 | 2021-02-08 | 10 | 2021-02-08 | 10 | 2021-02-26 | 13 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-03-02 | 15 | [11 empty] | 2021-03-17 | 2021-03-17 | 0 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-19 |  | 2
162 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.741 | No | 2021-02-08 | 2021-02-23 | 10 | 2021-02-23 | 10 | 2021-03-01 | 4 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-02 | 5 | [11 empty] | 2021-03-17 | 2021-03-17 | 0 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-19 |  | 2
163 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 | No | 2021-02-23 | 2021-03-06 | 8 | 2021-03-06 | 8 | 2021-03-08 | 0 | [15 empty] | 2021-03-06 | 2021-03-06 | 0 | 2021-03-06 | 2021-03-23 | 11 | [11 empty] | 2021-03-23 | 2021-03-23 | 0 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | 2021-03-27 |  | 3
165 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.646 | No | 2021-02-08 | 2021-02-16 | 5 | 2021-03-02 | 15 | 2021-03-06 | 3 | [15 empty] | 2021-03-06 | 2021-03-06 | 0 | 2021-03-06 | 2021-03-10 | 2 | [11 empty] | 2021-03-24 | 2021-03-25 | 1 | [15 empty] | 2021-03-24 | 2021-03-25 | 1 | 2021-03-25 | 2021-03-30 |  | 3
166 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.393 | No | 2021-01-14 | 2021-01-23 | 5 | 2021-02-25 | 28 | 2021-03-16 | 13 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-16 | 0 | [11 empty] | 2021-03-29 | 2021-03-29 | 0 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-03-30 |  | 1
167 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.75 | No | 2021-03-01 | 2021-03-13 | 9 | 2021-03-13 | 9 | 2021-03-16 | 1 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-29 | 10 | [11 empty] | 2021-03-29 | 2021-03-29 | 0 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-04-03 |  | 4
168 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 | No | 2021-03-01 | 2021-03-13 | 9 | 2021-03-13 | 9 | 2021-03-23 | 6 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-29 | 10 | [11 empty] | 2021-03-29 | 2021-03-29 | 0 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-04-03 |  | 4
170 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 46.533 | No | 2021-03-02 | 2021-03-13 | 8 | 2021-03-13 | 8 | 2021-03-24 | 7 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-31 | 12 | [11 empty] | 2021-03-31 | 2021-03-31 | 0 | [15 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | 2021-04-03 |  | 2
171 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 | No | 2021-03-01 | 2021-03-13 | 9 | 2021-03-13 | 9 | 2021-03-23 | 6 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-29 | 10 | [11 empty] | 2021-03-31 | 2021-04-01 | 1 | [15 empty] | 2021-03-31 | 2021-04-01 | 1 | 2021-04-01 | 2021-04-03 |  | 1
173 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.36 | No | 2021-03-15 | 2021-03-27 | 9 | 2021-03-27 | 9 | 2021-04-03 | 5 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | 2021-03-30 | 1 | [11 empty] | 2021-04-03 | 2021-04-05 | 0 | [15 empty] | 2021-04-03 | 2021-04-05 | 0 | 2021-04-05 | 2021-04-10 |  | 4
176 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 | No | 2021-03-19 | 2021-04-02 | 10 | 2021-04-02 | 10 | 2021-04-08 | 4 | [19 empty] | 2021-03-19 | N/A | [11 empty] | 2021-04-08 | 2021-04-08 | 0 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | 2021-04-10 |  | 1
177 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.699 | No | 2021-03-24 | 2021-04-07 | 10 | 2021-04-07 | 10 | 2021-04-09 | 2 | [19 empty] | 2021-03-24 | N/A | [11 empty] | 2021-04-09 | 2021-04-09 | 0 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | 2021-04-10 |  | 0
178 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 | No | 2021-02-08 | 2021-02-16 | 5 | 2021-03-17 | 26 | 2021-03-22 | 3 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-03-24 | 2 | [11 empty] | 2021-04-12 | 2021-04-12 | 0 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-04-13 |  | 1
179 | PGE | NEM | NEMMT | IA in Progress | FUCE, Storage | 1470 | No | 2021-02-10 | 2021-02-22 | 7 | 2021-03-21 | 26 | 2021-04-08 | 13 | 2021-04-08 | 2021-05-06 | 20 | [12 empty] | 2021-05-20 | 2021-06-04 | 10 | 2021-06-04 | [6 empty] | 2021-03-21 | 2021-03-25 | 3
180 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 210 | No | 2021-01-21 | 2021-01-25 | 2 | 2021-03-03 | 28 | 2021-03-22 | 13 | [15 empty] | 2021-03-22 | 2021-03-23 | 1 | 2021-03-23 | 2021-07-09 | 76 |  |  |  |  | 2021-01-21 | 2021-04-02 | 50
181 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 46.538 | No | 2021-03-10 | 2021-03-24 | 10 | 2021-03-24 | 10 | 2021-04-12 | 13 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-03-30 | 4 | [7 empty] | 2021-03-24 | 2021-03-24 | 2021-03-24 | 0 | 2021-06-07 | 2021-06-15 | 6 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-15 | 2021-06-15 |  | 0
182 | PGE | Non-NEM | Continuous Uncompensated Export | Withdrawn | Solar PV | 625 | No | 2021-02-19 | 2021-02-22 | 1 | 2021-02-24 | 3 | 2021-03-15 | 13 | [15 empty] | 2021-03-15 | 2021-03-31 | 12 | 2021-03-31 | [9 empty] | 2021-03-31
184 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 795.8 | No | 2021-03-18 | 2021-04-01 | 10 | 2021-05-28 | 51 | [27 empty] | 2021-03-18 | 2021-06-16 | 63
185 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 333.3 | No | 2021-03-18 | 2021-04-01 | 10 | 2021-05-06 | 35 | 2021-07-09 | 44 | [15 empty] | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09 | [6 empty] | 2021-03-18 | 2021-06-16 | 63
186 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 69.804 | No | 2021-03-22 | 2021-04-01 | 8
187 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 266.363 | No | 2021-03-25 | 2021-04-05 | 7
188 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 240 | No | 2021-03-29 | 2021-04-06 | 6 | 2021-05-10 | 30 | 2021-07-16 | 47 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-16 | [6 empty] | 2021-03-29
189 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 830 | No | 2021-03-26 | 2021-04-07 | 8
190 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 36.913 | No | 2021-03-31 | 2021-04-07 | 5 | 2021-07-07 | 68 | [27 empty] | 2021-03-31
191 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 150.795 | No | 2021-03-31 | 2021-04-12 | 8
192 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 | No | 2021-01-15 | 2021-01-19 | 1
193 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 35.713 | No | 2021-01-19 | 2021-01-20 | 1
194 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 343.39 | No | 2021-01-22 | 2021-01-25 | 1 | [29 empty] | 2021-01-22
195 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 86.4 | No | 2021-01-24 | 2021-01-26 | 1 | [29 empty] | 2021-01-24
196 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 32.88 | No | 2021-01-19 | 2021-01-26 | 5 | 2021-02-09 | 15 | 2021-05-04 | 59 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | 2021-06-17 | 31
197 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.128 | No | 2021-01-27 | 2021-01-27 | 0 | 2021-04-19 | 57 | 2021-04-27 | 6 | [15 empty] | 2021-04-27 | 2021-04-30 | 3 | 2021-04-30 | [6 empty] | 2021-01-27 | 2021-05-28 | 86
199 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 52.78 | No | 2021-01-28 | 2021-01-29 | 1
200 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 62.5 | No | 2021-01-15 | 2021-02-01 | 10
201 | PGE | NEM | EXPNEM | Commercial | Solar PV | 30.277 | No | 2021-02-03 | 2021-02-04 | 1 | 2021-06-03 | 84 | 2021-06-18 | 11 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-18 | 2021-06-21 | 1 | [11 empty] | 2021-07-12 | 2021-07-12 | 0 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-07-12 |  | 0
202 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 299.7 | No | 2021-02-04 | 2021-02-05 | 1 | [29 empty] | 2021-02-04
203 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 44.198 | No | 2021-02-05 | 2021-02-08 | 1
204 | PGE | NEM | EXPNEM | Implementation | Solar PV | 37.009 | No | 2021-01-28 | 2021-02-09 | 8 | 2021-04-21 | 58 | 2021-04-26 | 3 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-05-14 | 14 |  |  |  |  | 2021-05-19 | 2021-05-28 | 7 |  |  |  |  | 2021-06-24 | 2021-06-30 | 4 | 2021-06-30 | [14 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-30 |  | 2021-07-07 | 4 |  |  | 111
205 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 114.365 | No | 2021-02-09 | 2021-02-10 | 1
206 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 36.312 | No | 2021-02-01 | 2021-02-10 | 7 | [29 empty] | 2021-02-01
207 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 36 | No | 2021-02-16 | 2021-02-17 | 1 | 2021-06-09 | 80 | 2021-06-17 | 6 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | [6 empty] | 2021-02-16 | 2021-06-16 | 85
208 | PGE | NEM | EXPNEM | Commercial | Solar PV | 187.5 | No | 2021-02-04 | 2021-02-17 | 8 | 2021-04-21 | 53 | 2021-05-27 | 26 | [15 empty] | 2021-05-27 | 2021-06-09 | 8 | 2021-06-09 | 2021-06-09 | 0 |  |  |  |  | 2021-02-04 | 2021-05-07 | 65 |  |  |  |  | 2021-06-10 | 2021-06-17 | 5 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-17 | 2021-06-17 |  | 0
209 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 341.862 | No | 2021-02-15 | 2021-02-18 | 2 | 2021-04-30 | 53 | 2021-05-16 | 10 | 2021-05-16 | 2021-06-14 | 19 | [12 empty] | 2021-06-14 | 2021-06-14 | 0 | 2021-06-14 | [6 empty] | 2021-02-15 | 2021-05-10 | 59
210 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 50 | No | 2021-02-23 | 2021-02-24 | 1
211 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 38.392 | No | 2021-02-24 | 2021-02-25 | 1 | 2021-06-10 | 75 | 2021-06-17 | 5 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17
212 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 395.208 | No | 2021-02-12 | 2021-02-27 | 9 | [29 empty] | 2021-02-12
213 | PGE | NEM | EXPNEM | Implementation | Solar PV | 100 | No | 2021-02-15 | 2021-03-01 | 9 | 2021-05-03 | 54 | 2021-05-24 | 15 | [15 empty] | 2021-05-24 | 2021-06-10 | 12 | 2021-06-10 | 2021-06-25 | 11 |  |  |  |  | 2021-05-24 | 2021-06-03 | 7
214 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 240 | No | 2021-02-16 | 2021-03-02 | 10 | 2021-05-04 | 55 | [5 empty] | 2021-05-04 | 2021-06-16 | 30 | 2021-06-16 | [18 empty] | 2021-02-16
215 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 268.003 | No | 2021-03-01 | 2021-03-04 | 3 | 2021-05-11 | 51 | 2021-06-16 | 25 | [15 empty] | 2021-06-16 | 2021-06-17 | 1 | 2021-06-17 | 2021-06-17 | 0
216 | PGE | NEM | EXPNEM | Study in Progress | ENGN | 200 | No | 2021-02-24 | 2021-03-05 | 7 | 2021-04-21 | 40 | [27 empty] | 2021-04-20 | 2021-05-07 | 13
217 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 60.455 | No | 2021-03-05 | 2021-03-08 | 1
218 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 336 | No | 2021-02-23 | 2021-03-08 | 9 | 2021-05-12 | 56 | 2021-05-25 | 9 | [15 empty] | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-07-06 | 28 | [7 empty] | 2021-06-16
219 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 50.848 | No | 2021-02-23 | 2021-03-09 | 10 | 2021-04-27 | 45 | 2021-05-24 | 19 | 2021-05-24 | 2021-06-28 | 24 | 2021-06-28 | [21 empty] | 2021-02-23
220 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 540 | No | 2021-02-23 | 2021-03-09 | 10 | 2021-05-03 | 49 | 2021-05-20 | 13 | 2021-05-24 | 2021-06-30 | 26 | 2021-07-12
221 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 65.56 | No | 2021-03-08 | 2021-03-10 | 2 | [29 empty] | 2021-03-08
222 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 47.56 | No | 2021-03-05 | 2021-03-10 | 3 | 2021-06-09 | 67 | 2021-06-17 | 6 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17
224 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 50 | No | 2021-03-09 | 2021-03-11 | 2 | 2021-04-15 | 27
225 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 323.042 | No | 2021-03-10 | 2021-03-12 | 2 | [29 empty] | 2021-03-10
226 | PGE | NEM | EXPNEM | Implementation | Solar PV | 84.418 | No | 2021-02-26 | 2021-03-12 | 10 | 2021-05-07 | 50 | 2021-07-14 | 46 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-16 | 2 |  |  |  |  | 2021-07-02 | 2021-07-12 | 5 |  |  |  |  | 2021-07-16 | [17 empty] | 2021-07-16 | 2021-07-16 | 0
227 | PGE | NEM | EXPNEM | Implementation | Solar PV | 460 | No | 2021-03-01 | 2021-03-13 | 9 | 2021-05-06 | 48 | 2021-06-07 | 21 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-06-08 | 1 |  |  |  |  | 2021-03-01
228 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.411 | No | 2021-03-11 | 2021-03-15 | 2 | 2021-05-19 | 49 | 2021-06-07 | 12 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-06-11 | 4 | [11 empty] | 2021-07-15 | [17 empty] | 2021-07-15 | 2021-07-16 | 1
229 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 92.316 | No | 2021-03-12 | 2021-03-16 | 2 | [29 empty] | 2021-03-12
230 | PGE | NEM | EXPNEM | Implementation | Solar PV | 287.5 | No | 2021-03-03 | 2021-03-17 | 10 | 2021-04-20 | 34 | 2021-05-10 | 14 | [15 empty] | 2021-05-10 | 2021-05-17 | 5 | 2021-05-17 | 2021-05-17 | 0 |  |  |  |  | 2021-03-03 | 2021-05-05 | 45
232 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.2 | No | 2021-03-12 | 2021-03-17 | 3 | [29 empty] | 2021-03-12
233 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.041 | No | 2021-03-12 | 2021-03-17 | 3
234 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 55.546 | No | 2021-03-12 | 2021-03-17 | 3 | [29 empty] | 2021-03-12
235 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 548.77 | No | 2021-03-17 | 2021-03-18 | 1 | 2021-04-15 | 21 | 2021-06-04 | 35 | [15 empty] | 2021-06-04 | 2021-06-04 | 0 | 2021-06-04 | 2021-06-18 | 10 |  |  |  |  | 2021-03-17
236 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 531.086 | No | 2021-03-14 | 2021-03-18 | 3 | 2021-06-03 | 57 | 2021-07-09 | 25 | [15 empty] | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12
237 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 500 | No | 2021-03-17 | 2021-03-18 | 1 | [29 empty] | 2021-03-17
238 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 346.458 | No | 2021-03-04 | 2021-03-18 | 10 | 2021-05-03 | 42 | 2021-06-21 | 34 | 2021-06-21 | [24 empty] | 2021-03-04
239 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 136.1 | No | 2021-03-17 | 2021-03-18 | 1 | [29 empty] | 2021-03-17
240 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 299.7 | No | 2021-03-05 | 2021-03-19 | 10 | 2021-06-16 | 72 | [27 empty] | 2021-03-05 | 2021-05-03 | 41
241 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 187.5 | No | 2021-03-05 | 2021-03-19 | 10 | [29 empty] | 2021-03-05
243 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 | No | 2021-03-17 | 2021-03-19 | 2 | 2021-05-13 | 41 | 2021-06-03 | 14 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-14 | 7 |  |  |  |  | 2021-06-24 | 2021-07-09 | 10
244 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.128 | No | 2021-03-17 | 2021-03-19 | 2 | 2021-04-20 | 24 | 2021-07-06 | 53 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-07-09 | 3
245 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 351.986 | No | 2021-03-17 | 2021-03-19 | 2 | 2021-05-05 | 35 | 2021-07-02 | 41 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | [6 empty] | 2021-04-12
246 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 396.286 | No | 2021-03-18 | 2021-03-22 | 2 | 2021-04-27 | 28 | 2021-05-20 | 17 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | [6 empty] | 2021-03-18
247 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 780 | No | 2021-03-18 | 2021-03-22 | 2 | 2021-04-16 | 21 | 2021-05-12 | 18 | 2021-05-12 | 2021-06-01 | 13 | [12 empty] | 2021-06-01 | 2021-06-01 | 0 | 2021-06-01 | [6 empty] | 2021-03-18 | 2021-05-07 | 36
248 | PGE | NEM | EXPNEM | Implementation | Solar PV | 150 | No | 2021-03-09 | 2021-03-23 | 10 | 2021-06-21 | 73 | 2021-07-07 | 11 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | 2021-07-09 | 2 |  |  |  |  | 2021-03-09 | 2021-07-08 | 85
249 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.78 | No | 2021-03-20 | 2021-03-23 | 1 | [29 empty] | 2021-03-20
250 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 200 | No | 2021-03-22 | 2021-03-24 | 2 | 2021-05-05 | 32 | 2021-07-09 | 45 | [15 empty] | 2021-07-09 | 2021-07-10 | 0 | 2021-07-10
251 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 181.876 | No | 2021-03-23 | 2021-03-24 | 1 | 2021-06-07 | 53
252 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 83.3 | No | 2021-03-23 | 2021-03-24 | 1 | 2021-05-18 | 40 | 2021-06-07 | 13 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-06-11 | 4 |  |  |  |  | 2021-06-18 | 2021-07-02 | 10
253 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 183.3 | No | 2021-03-22 | 2021-03-24 | 2 | 2021-05-03 | 30 | 2021-06-01 | 20 | [15 empty] | 2021-06-01 | 2021-06-07 | 4 | 2021-06-07 | [6 empty] | 2021-03-22
254 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 168 | No | 2021-03-12 | 2021-03-25 | 9
255 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 46.08 | No | 2021-03-23 | 2021-03-25 | 2 | [29 empty] | 2021-03-23
256 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 323.852 | No | 2021-03-23 | 2021-03-25 | 2 | 2021-04-20 | 20 | 2021-06-30 | 50 | [15 empty] | 2021-06-30 | 2021-07-07 | 4 | 2021-07-07 | 2021-07-08 | 1
257 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 121.259 | No | 2021-03-24 | 2021-03-26 | 2 | 2021-04-28 | 25 | 2021-05-11 | 9 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | [6 empty] | 2021-03-24
259 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 86.4 | No | 2021-03-15 | 2021-03-29 | 10 | 2021-05-07 | 39 | 2021-05-18 | 7 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | [6 empty] | 2021-03-15
260 | PGE | NEM | EXPNEM | Commercial | Solar PV | 47.304 | No | 2021-03-23 | 2021-03-29 | 4 | 2021-05-14 | 38 | 2021-06-02 | 12 | [15 empty] | 2021-06-02 | 2021-06-07 | 3 | 2021-06-07 | 2021-06-08 | 1 | [7 empty] | 2021-06-17 |  |  |  | 2021-06-18 | 2021-06-29 | 7 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-29 | 2021-06-30 |  | 1
262 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 506.226 | No | 2021-03-17 | 2021-03-31 | 10 | [29 empty] | 2021-03-17
263 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 516 | No | 2021-03-17 | 2021-03-31 | 10 | 2021-05-27 | 51 | 2021-06-17 | 14 | 2021-06-17 | 2021-07-16 | 20 | [22 empty] | 2021-05-04 | 2021-05-26 | 16
266 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 115.724 | No | 2021-03-30 | 2021-03-31 | 1 | 2021-04-22 | 17 | 2021-06-18 | 40 | [15 empty] | 2021-06-18 | 2021-06-21 | 1 | 2021-06-21 | [6 empty] | 2021-05-27 | 2021-06-07 | 6
267 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 124.183 | No | 2021-01-11 | 2021-01-14 | 3 | 2021-01-28 | 12
268 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 92.482 | No | 2021-01-11 | 2021-01-14 | 3 | 2021-01-28 | 12
269 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 88.073 | No | 2021-01-11 | 2021-01-20 | 6 | 2021-01-28 | 12
270 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 | No | 2021-02-11 | 2021-02-12 | 1 | 2021-02-16 | 2 | 2021-05-11 | 60 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2021-05-20 | 7 | [11 empty] | 2021-06-23 | [17 empty] | 2021-06-23 | 2021-06-24 | 1
271 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 875 | No | 2021-01-26 | 2021-02-08 | 9 | 2021-02-19 | 17 | [5 empty] | 2021-02-08 | 2021-03-10 | 21 | 2021-03-10 |  |  | 3/10/2021 | 2021-06-10 | 65 |  |  |  | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | [6 empty] | 2021-01-26 |  |  | 2021-02-10
272 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 900 | No | 2021-02-26 | 2021-03-02 | 2 | 2021-03-09 | 7 | [5 empty] | 2021-03-09 | 2021-04-02 | 18 | 2021-04-02 |  |  | 4/2/2021 | 2021-06-08 | 46 |  |  |  | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-07-12 | 23
273 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 65.59 | No | 2021-03-04 | 2021-03-08 | 2 | 2021-03-12 | 6 | 2021-04-30 | 35 | [15 empty] | 2021-04-30 | 2021-05-03 | 1 | 2021-05-03
274 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 360.183 | No | 2021-03-09 | 2021-03-11 | 2 | 2021-03-15 | 4 | 2021-04-23 | 29 | [15 empty] | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | 2021-05-11 | 12 |  |  |  |  | 2021-03-09
275 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 587.5 | No | 2021-01-29 | 2021-01-29 | 0 | 2021-03-18 | 33 | 2021-05-18 | 43 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | [6 empty] | 2021-01-29
276 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 | No | 2021-02-22 | 2021-02-24 | 2 | 2021-03-24 | 22 | 2021-04-28 | 25 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28
277 | PGE | Non-NEM | Break Before Make | Commercial | ENGN | 3500 | No | 2021-03-02 | 2021-03-05 | 3 | 2021-03-24 | 16 | [5 empty] | 2021-03-24 | 2021-04-20 | 19 | 2021-04-20
278 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 37.186 | No | 2021-03-17 | 2021-03-19 | 2 | 2021-03-24 | 5 | 2021-05-24 | 43 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24
279 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 480 | No | 2021-02-18 | 2021-03-04 | 10 | 2021-03-26 | 26 | 2021-04-15 | 14 | 2021-04-15 | 2021-05-20 | 25 | 2021-06-03 | 2021-06-28 | 17 | 2021-06-28
280 | PGE | NEM | EXPNEM | Implementation | Solar PV | 85.358 | No | 2021-02-18 | 2021-03-04 | 10 | 2021-03-26 | 26 | 2021-04-16 | 15 | [15 empty] | 2021-04-16 | 2021-04-23 | 5 | 2021-04-23 | 2021-06-02 | 27
281 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 348 | No | 2021-03-24 | 2021-03-26 | 2 | 2021-03-26 | 2 | 2021-06-19 | 59 | [15 empty] | 2021-06-19 | 2021-06-19 | 0 | 2021-06-19 | [6 empty] | 2021-03-24 | 2021-07-15 | 79
282 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 125 | No | 2021-03-12 | 2021-03-26 | 10 | 2021-03-26 | 10 | 2021-06-16 | 57 | 2021-06-24
283 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 687.5 | No | 2021-02-03 | 2021-02-04 | 1 | 2021-03-27 | 36 | 2021-05-18 | 36 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | [6 empty] | 2021-02-03
284 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 337.5 | No | 2021-02-03 | 2021-02-04 | 1 | 2021-03-27 | 36 | 2021-04-16 | 14 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | [6 empty] | 2021-02-03
285 | PGE | NEM | EXPNEM | Commercial | Solar PV | 37.598 | No | 2021-03-17 | 2021-03-19 | 2 | 2021-03-29 | 8 | 2021-04-22 | 18 | [15 empty] | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 | 2021-04-26 | 2 | [11 empty] | 2021-06-12 | 2021-06-18 | 4 | [15 empty] | 2021-06-12 | 2021-06-14 | 0 | 2021-06-18 | 2021-06-25 |  | 5
286 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 50.209 | No | 2021-03-27 | 2021-03-29 | 0 | 2021-03-29 | 0 | 2021-05-10 | 30 | [15 empty] | 2021-05-10 | 2021-05-12 | 2 | 2021-05-12
287 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 600 | No | 2021-03-12 | 2021-03-17 | 3 | 2021-03-30 | 12 | 2021-05-10 | 29 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | [6 empty] | 2021-03-12
288 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 110 | No | 2021-03-29 | 2021-03-30 | 1 | 2021-03-30 | 1 | 2021-04-16 | 13 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | [6 empty] | 2021-03-29 | 2021-05-26 | 42
289 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 43.2 | No | 2021-03-29 | 2021-03-30 | 1 | 2021-03-30 | 1 | [27 empty] | 2021-04-12 | 2021-04-29 | 13
290 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 236.419 | No | 2021-03-24 | 2021-03-30 | 4 | 2021-03-30 | 4 | 2021-04-16 | 13 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | [6 empty] | 2021-03-24
291 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 52.108 | No | 2021-02-18 | 2021-02-19 | 1 | 2021-03-31 | 29 | 2021-04-16 | 12 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | 2021-07-02 | 54 | [11 empty] | 2021-07-13 | [17 empty] | 2021-07-13 | 2021-07-13 | 0
292 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 1250 | No | 2021-03-11 | 2021-03-12 | 1 | 2021-03-31 | 14 | [5 empty] | 2021-03-31 | 2021-04-14 | 10 | 2021-04-14 | 2021-04-19 | 3 | 2021-04-21 | 2021-06-23 | 44 | 2021-04-19 | 2021-04-19 | 0 | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12 | [6 empty] | 2021-03-11
293 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 1125 | No | 2021-03-12 | 2021-03-15 | 1 | 2021-03-31 | 13 | 2021-04-16 | 12 | [25 empty] | 2021-03-12
294 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 275 | No | 2021-03-17 | 2021-03-31 | 10 | 2021-03-31 | 10 | 2021-04-16 | 12 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21
295 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 500 | No | 2021-03-17 | 2021-03-18 | 1 | 2021-04-01 | 11 | 2021-04-19 | 12 | 2021-04-19 | 2021-05-26 | 27 | 2021-06-24 | [21 empty] | 2021-03-17
296 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 1937.5 | No | 2021-03-29 | 2021-03-31 | 2 | 2021-04-07 | 7 | 2021-05-28 | 37 | 2021-06-09 | 2021-07-08 | 20 | [12 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-12 | 2 |  |  |  |  | 2021-03-29 | 2021-05-07 | 29
297 | PGE | NEM | EXPNEM | Implementation | Solar PV | 445.259 | No | 2021-03-24 | 2021-04-05 | 8 | 2021-04-07 | 10 | 2021-04-27 | 14 | [15 empty] | 2021-04-27 | 2021-04-27 | 0 | 2021-04-27 | 2021-05-14 | 13 |  |  |  |  | 2021-03-24 | 2021-05-28 | 47 | [7 empty] | 2021-06-08
298 | PGE | NEM | EXPNEM | Implementation | Solar PV | 492.045 | No | 2021-03-26 | 2021-04-06 | 7 | 2021-04-07 | 8 | 2021-04-20 | 9 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-05-19 | 21 |  |  |  |  | 2021-03-26 | [9 empty] | 2021-06-08
299 | PGE | NEM | EXPNEM | Commercial | Solar PV | 35.045 | No | 2021-03-11 | 2021-03-15 | 2 | 2021-04-08 | 20 | 2021-04-22 | 10 | [15 empty] | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 | 2021-05-05 | 9 |  |  |  |  | 2021-03-11 | 2021-04-29 | 35 |  |  |  |  | 2021-06-18 | 2021-06-24 | 4 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-24 | 2021-07-01 |  | 5
301 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 114.285 | No | 2021-03-28 | 2021-03-30 | 1 | 2021-04-09 | 9 | 2021-04-21 | 8 | [15 empty] | 2021-04-21 | 2021-04-21 | 0 | 2021-04-21 | [6 empty] | 2021-03-28 | 2021-04-16 | 14
302 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 114.667 | No | 2021-02-11 | 2021-03-01 | 11 | 2021-04-11 | 40 | 2021-05-07 | 19 | [15 empty] | 2021-05-07 | 2021-05-07 | 0 | 2021-05-07 | 2021-05-07 | 0 |  |  |  |  | 2021-02-11 |  |  | 2021-05-04 | 2021-05-20 | 2021-05-20 | 12
303 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 372 | No | 2021-03-30 | 2021-04-09 | 8 | 2021-04-12 | 9 | 2021-05-19 | 27 | 2021-05-19 | [24 empty] | 2021-03-30
304 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 200 | No | 2021-03-25 | 2021-03-26 | 1 | 2021-04-13 | 13 | 2021-05-03 | 14 | [15 empty] | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03
305 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 368.528 | No | 2021-01-15 | 2021-01-19 | 1 | 2021-03-12 | 38 | 2021-06-03 | 58 | [15 empty] | 2021-06-03 | 2021-06-14 | 7 | 2021-06-14
306 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100.548 | No | 2021-02-16 | 2021-02-17 | 1 | 2021-03-08 | 14 | 2021-03-22 | 10 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-07-06 | 49 |  |  |  |  | 2021-02-16 | 2021-05-28 | 73
307 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 36.513 | No | 2021-03-09 | 2021-03-23 | 10 | 2021-03-23 | 10 | 2021-04-09 | 13 | [15 empty] | 2021-04-09 | 2021-06-28 | 55 | 2021-06-28
308 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 1700 | No | 2021-03-04 | 2021-03-08 | 2 | 2021-03-24 | 14 | 2021-04-12 | 13 | 2021-05-10 | 2021-06-08 | 20 | [12 empty] | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | [6 empty] | 2021-04-06 | 2021-07-09 | 66
309 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 230 | No | 2021-02-23 | 2021-02-24 | 1 | 2021-02-25 | 2 | 2021-03-18 | 15 | 2021-03-18 | 2021-04-29 | 30 | [12 empty] | 2021-04-29 | 2021-04-29 | 0 | 2021-04-29 | [6 empty] | 2021-02-23
310 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 62.5 | No | 2021-01-26 | 2021-01-26 | 0 | 2021-02-02 | 5 | 2021-03-19 | 32 | 2021-03-19 | 2021-04-16 | 20 | 2021-04-16 | 2021-06-29 | 51 | 2021-06-29 | [18 empty] | 2020-02-04
311 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 160 | No | 2021-03-01 | 2021-03-02 | 1 | 2021-03-02 | 1 | 2021-03-19 | 13 | 2021-03-19 | 2021-05-06 | 34 | 2021-07-09 | [21 empty] | 2021-03-01
312 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 167.38 | No | 2021-02-19 | 2021-02-22 | 1 | 2021-03-09 | 12 | 2021-03-31 | 16 | 2021-03-31 | 2021-04-29 | 21 | 2021-05-05 | 2021-07-02 | 41 | 2021-07-02
313 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 828.528 | No | 2021-02-24 | 2021-03-05 | 7 | 2021-03-16 | 14 | 2021-04-02 | 13 | 2021-04-02 | 2021-04-16 | 10 | [12 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16
314 | PGE | NEM | EXPNEM | Implementation | Solar PV | 133.2 | No | 2021-02-11 | 2021-02-24 | 8 | 2021-03-12 | 20 | 2021-03-26 | 10 | [15 empty] | 2021-03-26 | 2021-04-29 | 24 | 2021-04-29 | 2021-06-30 | 43 |  |  |  |  | 2021-02-11 | 2021-07-12 | 104
315 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.461 | No | 2021-01-12 | 2021-01-13 | 1 | 2021-01-19 | 4 | 2021-02-02 | 10 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02
316 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 132 | No | 2021-01-15 | 2021-01-19 | 1 | 2021-01-19 | 1 | 2021-02-03 | 11 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-07-02 | 105 | [11 empty] | 2021-07-12 | [17 empty] | 2021-07-12 | 2021-07-12 | 0
317 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 146.8 | No | 2021-01-11 | 2021-01-20 | 6 | 2021-01-28 | 12 | 2021-02-05 | 6 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05
318 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 153.25 | No | 2021-01-11 | 2021-01-14 | 3 | 2021-02-02 | 15 | 2021-02-05 | 3 | [15 empty] | 2021-02-05 | 2021-02-08 | 1 | 2021-02-08
320 | PGE | NEM | EXPNEM | Implementation | Solar PV | 71.771 | No | 2021-01-14 | 2021-01-29 | 10 | 2021-01-29 | 10 | 2021-02-19 | 14 | [15 empty] | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | 2021-05-20 | 64 |  |  |  |  | 2021-05-01 | 2021-05-10 | 5
321 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 30.159 | No | 2021-01-22 | 2021-01-30 | 5 | 2021-01-30 | 5 | 2021-02-19 | 13 | [15 empty] | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19
322 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 125 | No | 2021-01-15 | 2021-02-01 | 10 | 2021-02-01 | 10 | 2021-02-22 | 14 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | [6 empty] | 2021-01-15
323 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 85.795 | No | 2021-02-03 | 2021-02-17 | 9 | 2021-02-23 | 13 | 2021-03-01 | 4 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01
324 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 50 | No | 2021-02-11 | 2021-02-12 | 1 | 2021-02-18 | 4 | 2021-03-02 | 8 | [15 empty] | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | [6 empty] | 2021-02-11 | 2021-07-15 | 107
325 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 72.381 | No | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 0 | 2021-03-03 | 25 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-05-24 | 58 |  |  |  |  | 2021-01-26 | 2021-05-10 | 73
326 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 84.718 | No | 2021-01-13 | 2021-01-28 | 10 | 2021-02-13 | 21 | 2021-03-07 | 14 | [15 empty] | 2021-03-07 | 2021-03-07 | 0 | 2021-03-07 | [6 empty] | 2021-01-13
327 | PGE | NEM | EXPNEM | Implementation | Solar PV | 540 | No | 2021-01-15 | 2021-01-24 | 4 | 2021-01-24 | 4 | 2021-03-08 | 29 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-04-16 | 29 |  |  |  |  | 2021-01-15 | 2021-05-05 | 76
328 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 90.375 | No | 2021-02-22 | 2021-02-23 | 1 | 2021-02-26 | 4 | 2021-03-08 | 6 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-07-12 | 88 |  |  |  |  | 2021-02-22 | 2021-05-07 | 54 |  |  |  |  | 2021-07-16 | [17 empty] | 2021-07-16 | 2021-07-16 | 0
329 | PGE | NEM | EXPNEM | Commercial | Solar PV | 46.382 | No | 2021-02-22 | 2021-02-24 | 2 | 2021-02-26 | 4 | 2021-03-08 | 6 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-05-18 | 51 | [11 empty] | 2021-05-26 | 2021-06-03 | 5 | [15 empty] | 2021-05-26 | 2021-05-26 | 0 | 2021-06-03 | 2021-06-10 |  | 5
330 | PGE | NEM | EXPNEM | Implementation | Solar PV | 187.5 | No | 2021-02-04 | 2021-02-16 | 7 | 2021-02-16 | 7 | 2021-02-19 | 3 | [15 empty] | 2021-02-19 | 2021-03-09 | 12 | 2021-03-09 | 2021-05-07 | 43 |  |  |  |  | 2021-02-04
331 | PGE | NEM | EXPNEM | Commercial | Solar PV | 43.741 | No | 2021-02-24 | 2021-02-25 | 1 | 2021-03-01 | 3 | 2021-03-18 | 13 | [15 empty] | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18 | 2021-04-20 | 23 | [11 empty] | 2021-04-27 | 2021-05-06 | 7 | [15 empty] | 2021-04-27 | 2021-04-29 | 2 | 2021-05-06 | 2021-05-07 |  | 1
332 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 463.916 | No | 2021-02-09 | 2021-02-10 | 1 | 2021-03-02 | 14 | 2021-03-19 | 13 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | [6 empty] | 2021-02-09
333 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 32.109 | No | 2021-02-18 | 2021-02-19 | 1 | 2021-03-02 | 8 | 2021-03-19 | 13 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19
334 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 166.5 | No | 2021-02-16 | 2021-03-02 | 10 | 2021-03-02 | 10 | 2021-03-19 | 13 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19
335 | PGE | NEM | EXPNEM | Commercial | Solar PV | 54.148 | No | 2021-02-25 | 2021-02-26 | 1 | 2021-03-03 | 4 | 2021-03-22 | 13 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-04-24 | 24 |  |  |  |  | 2021-02-25 | [6 empty] | 2021-04-27 | 2021-06-03 | 26 | [15 empty] | 2021-04-27 | 2021-04-27 | 0 | 2021-06-03 | 2021-06-08 |  | 3
336 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 136 | No | 2021-03-02 | 2021-03-04 | 2 | 2021-03-04 | 2 | 2021-03-22 | 12 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-06-03 | 52
337 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 | No | 2021-03-02 | 2021-03-04 | 2 | 2021-03-10 | 6 | 2021-03-24 | 10 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-04-21 | 20
338 | PGE | NEM | EXPNEM | Commercial | Solar PV | 65.159 | No | 2021-02-26 | 2021-03-02 | 2 | 2021-03-12 | 10 | 2021-03-24 | 8 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-04-26 | 23 | [11 empty] | 2021-04-28 | 2021-05-11 | 9 | [15 empty] | 2021-04-28 | 2021-04-29 | 1 | 2021-05-11 | 2021-05-18 |  | 5
339 | PGE | NEM | EXPNEM | Implementation | Solar PV | 45.6 | No | 2021-02-02 | 2021-02-11 | 7 | 2021-02-11 | 7 | 2021-03-25 | 29 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-06-16 | 58
340 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 74.396 | No | 2021-03-02 | 2021-03-04 | 2 | 2021-03-08 | 4 | 2021-03-25 | 13 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-06-21 | 61
341 | PGE | NEM | EXPNEM | Implementation | Solar PV | 480 | No | 2021-01-29 | 2021-02-12 | 10 | 2021-02-24 | 17 | 2021-02-26 | 2 | 2021-02-26 | 2021-03-25 | 19 | [12 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-04-15 | 15 | [14 empty] | 2021-06-08 | 2021-06-18 | 8
342 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 | No | 2021-03-02 | 2021-03-04 | 2 | 2021-03-09 | 5 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26
343 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 | No | 2021-03-02 | 2021-03-04 | 2 | 2021-03-09 | 5 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-21 | 18
344 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 | No | 2021-03-02 | 2021-03-04 | 2 | 2021-03-09 | 5 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-21 | 18
345 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 | No | 2021-03-02 | 2021-03-04 | 2 | 2021-03-11 | 7 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-21 | 18
346 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 38.78 | No | 2021-03-09 | 2021-03-11 | 2 | 2021-03-11 | 2 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | [6 empty] | 2021-03-09
347 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 | No | 2021-03-02 | 2021-03-04 | 2 | 2021-03-12 | 8 | 2021-03-26 | 10 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-21 | 18
348 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 420 | No | 2021-02-16 | 2021-02-17 | 1 | 2021-03-11 | 17 | 2021-03-27 | 11 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | 2021-04-29 | 23
349 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 56.965 | No | 2021-01-25 | 2021-01-26 | 1 | 2021-03-01 | 24 | 2021-03-29 | 20 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | [6 empty] | 2021-01-25
350 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 75.259 | No | 2021-03-01 | 2021-03-02 | 1 | 2021-03-12 | 9 | 2021-03-29 | 11 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | [6 empty] | 2021-03-01
351 | PGE | NEM | EXPNEM | Implementation | Solar PV | 230 | No | 2021-02-14 | 2021-03-01 | 9 | 2021-03-15 | 19 | 2021-03-29 | 10 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-06-22 | 60
352 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 590 | No | 2021-03-12 | 2021-03-16 | 2 | 2021-03-16 | 2 | 2021-03-30 | 10 | 2021-06-17 | 2021-07-16 | 20 | [12 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | [6 empty] | 2021-03-12 | 2021-04-16 | 25
353 | PGE | NEM | EXPNEM | Commercial | Solar PV | 61.126 | No | 2021-02-24 | 2021-02-26 | 2 | 2021-03-17 | 15 | 2021-03-30 | 9 | [15 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-04-20 | 15 |  |  |  |  | 2021-03-12 | 2021-07-01 | 78 |  |  |  |  | 2021-07-06 | 2021-07-08 | 2 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-08 | 2021-07-09 |  | 1
354 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 650.576 | No | 2021-02-16 | 2021-02-17 | 1 | 2021-03-16 | 20 | 2021-03-31 | 11 | [15 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | 2021-04-15 | 11 |  |  |  |  | 2021-02-16
355 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100 | No | 2021-02-15 | 2021-02-16 | 0 | 2021-03-18 | 22 | 2021-04-01 | 10 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01
356 | PGE | NEM | EXPNEM | Commercial | Solar PV | 30.159 | No | 2021-03-08 | 2021-03-10 | 2 | 2021-03-24 | 12 | 2021-04-01 | 6 | [15 empty] | 2021-04-01 | 2021-04-02 | 1 | 2021-04-02 | 2021-04-15 | 9 | [11 empty] | 2021-04-19 | 2021-04-27 | 6 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-27 | 2021-04-30 |  | 3
357 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 66.6 | No | 2021-02-24 | 2021-02-26 | 2 | 2021-03-18 | 16 | 2021-04-02 | 11 | [15 empty] | 2021-04-02 | 2021-04-02 | 0 | 2021-04-02
358 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 170 | No | 2021-02-23 | 2021-02-24 | 1 | 2021-02-24 | 1 | 2021-04-05 | 28 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | [6 empty] | 2021-02-23
359 | PGE | NEM | EXPNEM | Commercial | Solar PV | 32.907 | No | 2021-03-08 | 2021-03-10 | 2 | 2021-03-17 | 7 | 2021-04-05 | 13 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-05-14 | 29 | [11 empty] | 2021-06-07 | 2021-06-16 | 7 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-16 | 2021-06-23 |  | 5
360 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 86.4 | No | 2021-03-10 | 2021-03-12 | 2 | 2021-03-17 | 5 | 2021-04-05 | 13 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | [6 empty] | 2021-03-10 | 2021-06-07 | 62
361 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 | No | 2021-03-23 | 2021-03-25 | 2 | 2021-03-25 | 2 | 2021-04-05 | 7 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05
362 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 49.123 | No | 2021-03-18 | 2021-03-22 | 2 | 2021-03-26 | 6 | 2021-04-05 | 6 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05
363 | PGE | NEM | EXPNEM | Commercial | Solar PV | 466.6 | No | 2021-03-25 | 2021-03-29 | 2 | 2021-03-31 | 4 | 2021-04-05 | 3 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-05-19 | 32 | [11 empty] | 2021-05-21 | 2021-05-26 | 3 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-26 | 2021-06-02 |  | 4
364 | PGE | NEM | EXPNEM | Commercial | Solar PV | 75.885 | No | 2021-03-04 | 2021-03-05 | 1 | 2021-03-19 | 11 | 2021-04-06 | 12 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-04-29 | 17 | [11 empty] | 2021-05-04 | 2021-05-13 | 7 | [15 empty] | 2021-05-04 | 2021-05-05 | 1 | 2021-05-13 | 2021-05-19 |  | 4
365 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.5 | No | 2021-03-17 | 2021-03-19 | 2 | 2021-03-23 | 4 | 2021-04-06 | 10 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06
366 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 35.852 | No | 2021-03-26 | 2021-03-29 | 1 | 2021-03-29 | 1 | 2021-04-06 | 6 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-05-07 | 23
367 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 | No | 2021-03-12 | 2021-03-17 | 3 | 2021-03-19 | 5 | 2021-04-07 | 13 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-21 | 10
368 | PGE | NEM | EXPNEM | Commercial | Solar PV | 50 | No | 2021-03-15 | 2021-03-18 | 3 | 2021-03-23 | 6 | 2021-04-07 | 11 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-16 | 7 |  |  |  |  | 2021-03-15 | [6 empty] | 2021-06-18 | 2021-06-30 | 8 | [15 empty] | 2021-06-18 | 2021-06-21 | 1 | 2021-06-30 | 2021-07-16 |  | 11
369 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 765.9 | No | 2021-03-11 | 2021-03-15 | 2 | 2021-03-24 | 9 | 2021-04-08 | 11 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | [6 empty] | 2021-03-11
370 | PGE | NEM | EXPNEM | Commercial | Solar PV | 55.067 | No | 2021-03-18 | 2021-03-22 | 2 | 2021-04-02 | 11 | 2021-04-08 | 4 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | 2021-04-13 | 3 | [11 empty] | 2021-04-15 | 2021-04-22 | 5 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-22 | 2021-04-29 |  | 5
371 | PGE | NEM | EXPNEM | Implementation | Solar PV | 969.737 | No | 2021-02-02 | 2021-02-17 | 10 | 2021-03-09 | 24 | 2021-03-23 | 10 | 2021-03-23 | 2021-04-09 | 13 | [12 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | 2021-04-28 | 13 | [7 empty] | 2021-05-25 | [6 empty] | 2021-06-22
372 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 89.259 | No | 2021-03-02 | 2021-03-04 | 2 | 2021-03-08 | 4 | 2021-04-12 | 25 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12
373 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 | No | 2021-03-16 | 2021-03-30 | 10 | 2021-03-30 | 10 | 2021-04-12 | 9 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12
374 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 89.207 | No | 2021-03-08 | 2021-03-10 | 2 | 2021-03-26 | 14 | 2021-04-13 | 12 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13
375 | PGE | NEM | EXPNEM | Implementation | Solar PV | 648.528 | No | 2021-01-26 | 2021-02-09 | 10 | 2021-03-01 | 23 | 2021-03-11 | 8 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | 2021-04-01 | 15 | [7 empty] | 2021-05-25 | [6 empty] | 2021-06-17
376 | PGE | NEM | EXPNEM | Commercial | Solar PV | 33.3 | No | 2021-01-22 | 2021-02-26 | 24 | 2021-03-15 | 35 | 2021-04-01 | 13 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | 2021-04-02 | 1 | [11 empty] | 2021-05-20 | 2021-05-27 | 5 | [15 empty] | 2021-05-20 | 2021-05-21 | 1 | 2021-05-27 | 2021-05-27 |  | 0
377 | PGE | NEM | EXPNEM | Implementation | Solar PV | 95.8 | No | 2021-01-18 | 2021-01-25 | 4 | 2021-01-25 | 4 | 2021-02-11 | 13 | [15 empty] | 2021-02-19 | 2021-03-19 | 20 | 2021-03-19 | 2021-04-13 | 17 |  |  |  |  | 2021-01-18
378 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 85.387 | No | 2021-01-14 | 2021-01-15 | 1 | 2021-05-25 | 91 | 2021-02-01 | 80 | [15 empty] | 2021-02-01 | 2021-02-01 | 0 | 2021-02-01 | 2021-05-11 | 70 |  |  |  |  | 2021-01-14 | 2021-05-26 | 92
379 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 490 | No | 2021-01-13 | 2021-01-20 | 4 | 2021-01-20 | 4 | 2021-02-03 | 10 | 2021-02-03 | 2021-03-17 | 29 | 2021-03-17 | 2021-03-23 | 4 | 2021-03-23 | [18 empty] | 2021-01-13 | 2021-02-01 | 12
380 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 720 | No | 2021-01-15 | 2021-01-21 | 3 | 2021-01-21 | 3 | [5 empty] | 2021-01-21 | 2021-02-25 | 24 | 2021-02-25 | [18 empty] | 2021-01-15 | 2021-02-02 | 11
381 | PGE | NEM | EXPNEM | Implementation | Solar PV | 44.337 | No | 2021-01-19 | 2021-01-28 | 7 | 2021-01-28 | 7 | 2021-03-22 | 36 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-05-19 | 42 |  |  |  |  | 2021-01-19 | 2021-02-05 | 13
382 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 41.968 | No | 2021-02-01 | 2021-02-02 | 1 | 2021-02-10 | 7 | 2021-03-22 | 27 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-04-19 | 20 |  |  |  |  | 2021-02-01 | 2021-02-08 | 5
383 | PGE | NEM | EXPNEM | Withdrawn | Solar PV, Storage | 33.54 | No | 2021-01-21 | 2021-02-04 | 10 | [29 empty] | 2021-01-21 | 2021-02-09 | 13
384 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 400 | No | 2021-02-03 | 2021-02-03 | 0 | 2021-02-22 | 12 | 2021-03-03 | 7 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | [6 empty] | 2021-02-03 | 2021-02-09 | 4 | [7 empty] | 2021-06-16
385 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 41.219 | No | 2021-01-12 | 2021-01-13 | 1 | 2021-02-04 | 16 | 2021-03-24 | 33 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | [6 empty] | 2021-01-12 | 2021-02-09 | 19
386 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 | No | 2021-01-28 | 2021-01-29 | 1 | 2021-01-29 | 1 | 2021-02-11 | 9 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-05-12 | 63 |  |  |  |  | 2021-01-28 | 2021-02-11 | 10 |  |  |  |  | 2021-06-19 | 2021-07-14 | 16 | [15 empty] | 2021-06-19 | 2021-07-09 | 13 | 2021-07-14
387 | PGE | NEM | EXPNEM | Implementation | Solar PV | 38.78 | No | 2021-01-21 | 2021-01-29 | 6 | 2021-02-12 | 16 | 2021-02-26 | 9 | [15 empty] | 2021-02-26 | 2021-03-16 | 12 | 2021-03-16 | 2021-04-09 | 18 |  |  |  |  | 2021-01-21 | 2021-02-11 | 15 |  |  |  |  | 2021-05-17 | 2021-05-24 | 5 | 2021-05-18 | [14 empty] | 2021-05-17 | 2021-05-17 | 0 | 2021-05-24 |  | 2021-06-17 | 17 |  |  | 103
388 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 200 | No | 2021-02-04 | 2021-02-05 | 1 | 2021-02-12 | 6 | 2021-02-22 | 5 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-05-05 | 52 |  |  |  |  | 2021-02-04 | 2021-02-16 | 7
389 | PGE | NEM | EXPNEM | Commercial | Solar PV | 49.794 | No | 2021-02-02 | 2021-02-11 | 7 | 2021-02-11 | 7 | 2021-02-26 | 10 | [15 empty] | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-05-18 | 57 |  |  |  |  | 2021-02-02 | 2021-02-16 | 9 |  |  |  |  | 2021-06-15 | 2021-06-24 | 7 | [15 empty] | 2021-06-15 | 2021-06-16 | 1 | 2021-06-24 | 2021-06-24 |  | 0
390 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 94.844 | No | 2021-02-10 | 2021-02-23 | 8 | 2021-02-23 | 8 | 2021-03-11 | 12 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | [6 empty] | 2021-02-10 | 2021-02-23 | 8
391 | PGE | NEM | EXPNEM | Commercial | Solar PV | 172.8 | No | 2021-02-18 | 2021-02-19 | 1 | 2021-02-25 | 5 | 2021-04-15 | 35 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-26 | 7 |  |  |  |  | 2021-02-18 | 2021-02-25 | 5 |  |  |  |  | 2021-06-22 | 2021-06-29 | 5 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-29 | 2021-06-30 |  | 1
392 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 46.625 | No | 2021-02-09 | 2021-02-10 | 1 | 2021-02-25 | 11 | 2021-03-11 | 10 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | [6 empty] | 2021-02-09 | 2021-02-25 | 11
393 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 150 | No | 2021-02-23 | 2021-02-24 | 1 | 2021-02-26 | 3 | 2021-03-26 | 20 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | [6 empty] | 2021-02-23 | 2021-03-01 | 4
394 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 104.7 | No | 2021-02-02 | 2021-02-03 | 1 | 2021-03-01 | 18 | 2021-03-17 | 12 | 2021-03-17 | 2021-04-14 | 20 | 2021-05-06 | 2021-06-10 | 24 | 2021-06-10 | 2021-06-25 | 11 |  |  |  | 2021-06-25 | [12 empty] | 2021-02-02 | 2021-07-09 | 110
395 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 625 | No | 2021-01-13 | 2021-01-14 | 1 | 2021-01-20 | 4 | 2021-02-02 | 9 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | [6 empty] | 2021-01-13 | 2021-03-02 | 32
396 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 183.3 | No | 2021-01-13 | 2021-01-14 | 1 | 2021-01-20 | 4 | 2021-02-02 | 9 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | [6 empty] | 2021-01-13 | 2021-03-02 | 32
397 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 125 | No | 2021-01-13 | 2021-01-21 | 5 | 2021-02-25 | 29 | 2021-04-28 | 44 | 2021-04-28 | 2021-05-26 | 20 | 2021-06-28 | [21 empty] | 2021-02-25 | 2021-03-04 | 5
398 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 154.954 | No | 2021-02-08 | 2021-02-08 | 0 | 2021-03-08 | 19 | 2021-05-10 | 45 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2021-05-11 | 1 |  |  |  |  | 2021-02-08 | 2021-03-04 | 17
399 | PGE | NEM | EXPNEM | Commercial | Solar PV | 125 | No | 2021-02-18 | 2021-03-04 | 10 | 2021-03-23 | 23 | 2021-03-30 | 5 | [15 empty] | 2021-05-14 | 2021-05-14 | 0 | 2021-05-14 | 2021-06-01 | 11 |  |  |  |  | 2021-02-18 | 2021-03-05 | 11 |  |  |  |  | 2021-06-22 | 2021-06-29 | 5 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-29 | 2021-06-30 |  | 1
400 | PGE | NEM | EXPNEM | Commercial | Solar PV | 247.461 | No | 2021-02-19 | 2021-03-05 | 10 | 2021-03-23 | 22 | 2021-03-30 | 5 | [15 empty] | 2021-03-30 | 2021-05-03 | 24 | 2021-05-03 | 2021-05-27 | 18 |  |  |  |  | 2021-02-19 | 2021-03-05 | 10 |  |  |  |  | 2021-06-22 | 2021-06-29 | 5 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-29 | 2021-06-30 |  | 1
401 | PGE | NEM | EXPNEM | Implementation | Solar PV | 53.611 | No | 2021-02-18 | 2021-03-04 | 10 | 2021-03-04 | 10 | 2021-03-23 | 13 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | 2021-04-05 | 9 |  |  |  |  | 2021-02-18 | 2021-03-05 | 11
402 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 45.572 | No | 2021-01-21 | 2021-01-22 | 1 | 2021-03-01 | 26 | 2021-03-08 | 5 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | [6 empty] | 2021-01-21 | 2021-03-08 | 31
403 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 146.495 | No | 2021-02-22 | 2021-02-23 | 1 | 2021-03-03 | 7 | 2021-06-12 | 71 | [15 empty] | 2021-06-12 | 2021-06-12 | 0 | 2021-06-12 | 2021-06-18 | 4 |  |  |  |  | 2021-02-22 | 2021-04-29 | 48 |  |  |  |  | 2021-06-11 | [17 empty] | 2021-06-11 | 2021-06-11 | 0
404 | PGE | NEM | EXPNEM | Implementation | Solar PV | 250 | No | 2021-02-23 | 2021-03-09 | 10 | 2021-03-09 | 10 | 2021-03-29 | 14 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-06-03 | 20 |  |  |  |  | 2021-02-23 | 2021-03-12 | 13
405 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 666.6 | No | 2021-01-29 | 2021-02-01 | 1 | 2021-03-10 | 27 | 2021-04-13 | 24 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | [6 empty] | 2021-01-29 | 2021-05-07 | 69
406 | PGE | NEM | EXPNEM | Implementation | Solar PV | 437.5 | No | 2021-01-28 | 2021-02-10 | 9 | 2021-02-22 | 16 | 2021-03-05 | 9 | [15 empty] | 2021-03-05 | 2021-03-05 | 0 | 2021-03-05 | 2021-04-05 | 21 |  |  |  |  | 2021-01-28 | 2021-05-07 | 70
407 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 36 | No | 2021-02-17 | 2021-02-18 | 1 | 2021-03-01 | 8 | 2021-03-19 | 14 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-04-09 | 15 |  |  |  |  | 2021-02-17 | 2021-03-12 | 17
408 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 125 | No | 2021-02-11 | 2021-03-12 | 20 | 2021-03-26 | 30 | 2021-04-16 | 15 | 2021-04-16 | 2021-06-25 | 49 | 2021-07-02 | [21 empty] | 2021-02-11 | 2021-03-15 | 21
409 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 600 | No | 2021-01-29 | 2021-02-01 | 1 | 2021-03-09 | 26 | 2021-03-27 | 13 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | [6 empty] | 2021-01-29 | 2021-03-15 | 30
410 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 633.3 | No | 2021-01-29 | 2021-02-01 | 1 | 2021-03-09 | 26 | 2021-04-13 | 25 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | [6 empty] | 2021-01-29 | 2021-03-15 | 30
412 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 766.6 | No | 2021-01-29 | 2021-02-01 | 1 | 2021-03-16 | 31 | 2021-07-08 | 80 | [15 empty] | 2021-07-08 | 2021-07-09 | 1 | 2021-07-09 | [6 empty] | 2021-01-29 | 2021-03-18 | 33
413 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 34.8 | No | 2021-03-03 | 2021-03-17 | 10 | 2021-05-26 | 60 | 2021-06-10 | 10 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | [6 empty] | 2021-03-03 | 2021-03-24 | 15
414 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 43.421 | No | 2021-03-03 | 2021-03-17 | 10 | 2021-05-10 | 48 | [27 empty] | 2021-03-03 | 2021-03-25 | 16
415 | PGE | NEM | EXPNEM | Commercial | Solar PV | 66.6 | No | 2021-03-04 | 2021-03-18 | 10 | 2021-04-24 | 36 | 2021-05-10 | 10 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2021-05-10 | 0 |  |  |  |  | 2021-03-04 | 2021-03-25 | 15 |  |  |  |  | 2021-06-23 | 2021-06-28 | 3 | [15 empty] | 2021-06-23 | 2021-06-24 | 1 | 2021-06-28 | 2021-06-29 |  | 1
416 | PGE | NEM | EXPNEM | Commercial | Solar PV | 31.024 | No | 2021-03-04 | 2021-03-18 | 10 | 2021-05-03 | 42 | 2021-06-03 | 22 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-23 | 14 |  |  |  |  | 2021-03-04 | 2021-05-07 | 46 |  |  |  |  | 2021-06-30 | 2021-07-12 | 7 | [15 empty] | 2021-06-30 | 2021-07-01 | 1 | 2021-07-12 | 2021-07-13 |  | 1
417 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 120 | No | 2021-03-05 | 2021-03-19 | 10 | 2021-05-24 | 56 | 2021-06-29 | 25 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | [6 empty] | 2021-03-05 | 2021-03-25 | 14
418 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 375 | No | 2021-03-11 | 2021-03-15 | 2 | 2021-03-18 | 5 | 2021-05-20 | 45 | [15 empty] | 2021-05-20 | 2021-06-08 | 12 | 2021-06-08 | [6 empty] | 2021-03-11 | 2021-03-25 | 10
419 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 800 | No | 2021-01-29 | 2021-02-01 | 1 | 2021-03-25 | 38 | 2021-06-07 | 51 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [6 empty] | 2021-01-29 | 2021-03-25 | 38
420 | PGE | NEM | EXPNEM | Commercial | Solar PV | 78.716 | No | 2021-03-05 | 2021-03-19 | 10 | 2021-03-19 | 10 | 2021-04-05 | 11 | [15 empty] | 2021-06-25 | 2021-06-25 | 0 | 2021-06-25 | 2021-06-29 | 2 |  |  |  |  | 2021-03-05 | 2021-03-25 | 14 |  |  |  |  | 2021-06-30 | 2021-07-12 | 7 | [15 empty] | 2021-06-30 | 2021-07-01 | 1 | 2021-07-12 | 2021-07-13 |  | 1
421 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 | No | 2021-01-27 | 2021-01-28 | 1 | 2021-02-03 | 5 | 2021-02-20 | 11 | [15 empty] | 2021-02-20 | 2021-02-20 | 0 | 2021-02-20 | [6 empty] | 2021-01-27 | 2021-06-15 | 97
422 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 78.723 | No | 2021-03-12 | 2021-03-16 | 2 | 2021-03-23 | 7 | 2021-04-07 | 11 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | [6 empty] | 2021-03-12 | 2021-03-25 | 9
423 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100 | No | 2021-02-22 | 2021-02-26 | 4 | 2021-03-11 | 13 | 2021-03-27 | 11 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | 2021-04-20 | 16 |  |  |  |  | 2021-02-22 | 2021-03-29 | 25
424 | PGE | NEM | EXPNEM | Implementation | Solar PV | 250 | No | 2021-03-10 | 2021-03-24 | 10 | 2021-03-24 | 10 | 2021-04-13 | 14 | [15 empty] | 2021-04-13 | 2021-05-18 | 25 | 2021-05-18 | 2021-06-08 | 14 |  |  |  |  | 2021-03-10 | 2021-03-31 | 15
425 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100 | No | 2021-03-09 | 2021-03-10 | 1 | 2021-03-16 | 5 | 2021-04-02 | 13 | [15 empty] | 2021-04-02 | 2021-04-02 | 0 | 2021-04-02 | 2021-04-05 | 1 |  |  |  |  | 2021-03-09 | 2021-04-29 | 37
426 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 420 | No | 2021-03-09 | 2021-03-23 | 10 | 2021-07-02 | 82 | [27 empty] | 2021-03-09 | 2021-06-18 | 72
427 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 96 | No | 2021-02-09 | 2021-02-10 | 1 | 2021-03-24 | 30 | 2021-04-06 | 9 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | [6 empty] | 2021-02-09 | 2021-04-02 | 37
428 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 600 | No | 2021-03-19 | 2021-03-23 | 2 | 2021-03-29 | 6 | 2021-04-06 | 6 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | [6 empty] | 2021-03-19 | 2021-05-10 | 36
429 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 400 | No | 2021-03-19 | 2021-03-23 | 2 | 2021-03-30 | 7 | 2021-04-06 | 5 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | [6 empty] | 2021-03-19 | 2021-05-07 | 35
430 | PGE | NEM | EXPNEM | Implementation | Solar PV | 237.128 | No | 2021-03-11 | 2021-03-25 | 10 | 2021-05-24 | 52 | 2021-06-28 | 24 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-07-09 | 8 |  |  |  |  | 2021-03-11 | 2021-04-05 | 17
431 | PGE | NEM | EXPNEM | Implementation | Solar PV | 37.529 | No | 2021-03-12 | 2021-03-26 | 10 | 2021-05-25 | 52 | 2021-06-08 | 9 | [15 empty] | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-06-14 | 4 |  |  |  |  | 2021-03-12 | 2021-04-05 | 16
432 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 97.072 | No | 2021-03-23 | 2021-03-25 | 2 | 2021-04-14 | 16 | 2021-05-04 | 14 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | [6 empty] | 2021-03-23 | 2021-04-05 | 9
433 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 38.528 | No | 2021-02-22 | 2021-02-23 | 1 | 2021-03-25 | 23 | 2021-04-05 | 7 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-05-10 | 25 |  |  |  |  | 2021-02-22 | 2021-06-17 | 82 |  |  |  |  | 2021-07-02 | [17 empty] | 2021-07-02 | 2021-07-15 | 8
434 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 150 | No | 2021-03-23 | 2021-03-25 | 2 | 2021-03-25 | 2 | 2021-04-06 | 8 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-05-19 | 31 |  |  |  |  | 2021-03-23 | 2021-04-05 | 9
435 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 142.054 | No | 2021-03-23 | 2021-03-25 | 2 | 2021-03-25 | 2 | 2021-04-06 | 8 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-05-19 | 31 |  |  |  |  | 2021-03-23 | 2021-04-05 | 9
436 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 52.163 | No | 2021-03-12 | 2021-03-16 | 2 | 2021-03-25 | 9 | 2021-04-12 | 12 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | [6 empty] | 2021-03-12 | 2021-04-05 | 16
437 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 720 | No | 2021-02-16 | 2021-03-02 | 10 | 2021-05-10 | 59 | 2021-06-01 | 15 | 2021-06-01 | 2021-06-21 | 14 | [12 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | [6 empty] | 2021-02-16 | 2021-04-12 | 39
439 | PGE | NEM | EXPNEM | Implementation | Solar PV | 85.259 | No | 2021-02-24 | 2021-03-10 | 10 | 2021-03-27 | 22 | 2021-04-16 | 14 | [15 empty] | 2021-04-16 | 2021-06-02 | 32 | 2021-06-02 | 2021-06-07 | 3 |  |  |  |  | 2021-02-24 | 2021-04-12 | 33
440 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 40.153 | No | 2021-03-22 | 2021-03-24 | 2 | 2021-03-30 | 6 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | [6 empty] | 2021-03-22 | 2021-04-12 | 15
441 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 220 | No | 2021-03-28 | 2021-03-29 | 0 | 2021-03-30 | 1 | 2021-04-16 | 13 | [15 empty] | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | [6 empty] | 2021-03-28 | 2021-04-12 | 10
442 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 250 | No | 2021-03-28 | 2021-03-30 | 1 | 2021-03-30 | 1 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | [6 empty] | 2021-03-28 | 2021-04-12 | 10
443 | PGE | NEM | EXPNEM | Implementation | Solar PV | 33.3 | No | 2021-02-15 | 2021-02-26 | 8 | 2021-02-26 | 8 | 2021-03-15 | 11 | [15 empty] | 2021-03-15 | 2021-06-01 | 55 | 2021-06-01 | 2021-07-07 | 25 |  |  |  |  | 2021-02-15 | 2021-05-18 | 65
444 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 46.625 | No | 2021-03-18 | 2021-04-01 | 10 | 2021-06-30 | 73 | 2021-07-16 | 11 | [15 empty] | 2021-07-16 | 2021-07-16 | 0 | 2021-07-16 | [6 empty] | 2021-03-18 | 2021-04-13 | 18
445 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 120 | No | 2021-03-17 | 2021-03-31 | 10 | 2021-05-03 | 33 | [5 empty] | 2021-05-03 | 2021-05-25 | 16 | 2021-05-25 | [18 empty] | 2021-03-17 | 2021-04-13 | 19
446 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.536 | No | 2021-03-24 | 2021-03-26 | 2 | 2021-03-30 | 4 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-29 | 10 |  |  |  |  | 2021-03-24 | 2021-04-13 | 14
447 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 64.427 | No | 2021-03-24 | 2021-03-26 | 2 | 2021-03-30 | 4 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-29 | 10 |  |  |  |  | 2021-03-24 | 2021-05-07 | 32
448 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 | No | 2021-03-24 | 2021-03-26 | 2 | 2021-03-30 | 4 | 2021-04-15 | 12 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-29 | 10 |  |  |  |  | 2021-03-24 | 2021-05-07 | 32
449 | PGE | NEM | EXPNEM | Implementation | Solar PV | 100 | No | 2021-03-17 | 2021-03-30 | 9 | 2021-03-30 | 9 | 2021-04-19 | 14 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-04-28 | 7 |  |  |  |  | 2021-03-17 | 2021-04-13 | 19 | [7 empty] | 2021-06-01
450 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 73.552 | No | 2021-03-25 | 2021-03-26 | 1 | 2021-03-31 | 4 | 2021-05-21 | 37 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-07-14 | 36 |  |  |  |  | 2021-03-25 | 2021-05-07 | 31
451 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 76.296 | No | 2021-03-30 | 2021-03-31 | 1 | 2021-04-01 | 2 | 2021-06-02 | 43 | [15 empty] | 2021-06-02 | 2021-06-03 | 1 | 2021-06-03 | 2021-06-09 | 4 |  |  |  |  | 2021-03-30 | 2021-05-07 | 28
452 | PGE | NEM | EXPNEM | Implementation | Solar PV | 93.552 | No | 2021-03-25 | 2021-04-01 | 5 | 2021-04-05 | 7 | 2021-06-21 | 54 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-07-07 | 11 |  |  |  |  | 2021-03-25 | 2021-04-13 | 13
453 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 48.72 | No | 2020-12-30 | 2021-01-06 | 4 | 2021-03-12 | 49 | 2021-04-05 | 16 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-05-21 | 34 |  |  |  |  | 2021-04-01 | 2021-04-13 | 8
454 | PGE | NEM | EXPNEM | Commercial | Solar PV | 50 | No | 2021-03-19 | 2021-04-02 | 10 | 2021-05-25 | 47 | 2021-06-03 | 6 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-10 | 5 |  |  |  |  | 2021-03-19 | 2021-04-14 | 18 |  |  |  |  | 2021-06-22 | 2021-06-29 | 5 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-29 | 2021-06-30 |  | 1
455 | PGE | NEM | EXPNEM | Implementation | Solar PV | 300 | No | 2021-03-04 | 2021-03-17 | 9 | 2021-05-24 | 57 | 2021-06-08 | 10 | [15 empty] | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-07-07 | 20 |  |  |  |  | 2021-03-04 | 2021-04-14 | 29
456 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 125 | No | 2021-03-23 | 2021-04-06 | 10 | 2021-04-20 | 20 | 2021-06-22 | 44 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | [6 empty] | 2021-03-23 | 2021-04-14 | 16
457 | PGE | NEM | EXPNEM | Implementation | Solar PV | 43.593 | No | 2021-02-19 | 2021-03-05 | 10 | 2021-03-22 | 21 | 2021-05-10 | 35 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2021-06-01 | 15 |  |  |  |  | 2021-02-19 | 2021-04-14 | 38
458 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 1100 | No | 2021-03-03 | 2021-03-05 | 2 | 2021-03-31 | 20 | 2021-06-04 | 46 | 2021-06-15 | 2021-07-12 | 18 | [22 empty] | 2021-03-03 | 2021-04-14 | 30
459 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 68.44 | No | 2021-03-17 | 2021-03-19 | 2 | 2021-04-02 | 12 | 2021-05-03 | 21 | [15 empty] | 2021-05-03 | 2021-05-04 | 1 | 2021-05-04 | 2021-06-16 | 30 |  |  |  |  | 2021-03-17 | 2021-04-14 | 20
460 | PGE | NEM | EXPNEM | Implementation | Solar PV | 110 | No | 2021-03-26 | 2021-04-06 | 7 | 2021-04-07 | 8 | 2021-05-13 | 26 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13 | 2021-05-17 | 2 |  |  |  |  | 2021-04-06 | 2021-04-14 | 6
461 | PGE | NEM | EXPNEM | Commercial | Solar PV | 150 | No | 2021-01-14 | 2021-01-15 | 1 | 2021-01-19 | 2 | 2021-01-26 | 5 | [15 empty] | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 2021-04-06 | 49 |  |  |  |  | 2021-01-14 | 2021-01-28 | 9 |  |  |  |  | 2021-04-09 | 2021-04-15 | 4 | [15 empty] | 2021-04-09 | 2021-04-12 | 1 | 2021-04-15 | 2021-04-19 |  | 2
462 | PGE | NEM | EXPNEM | Commercial | Solar PV | 258.2 | No | 2021-03-09 | 2021-03-11 | 2 | 2021-03-17 | 6 | 2021-03-26 | 7 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-05 | 6 | [11 empty] | 2021-04-06 | 2021-04-13 | 5 | [15 empty] | 2021-04-06 | 2021-04-07 | 1 | 2021-04-13 | 2021-04-16 |  | 3
463 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.588 | No | 2021-03-25 | 2021-04-07 | 9 | 2021-04-07 | 9 | 2021-04-12 | 3 | [19 empty] | 2021-03-25 | N/A | [8 empty] | 2021-04-07 | 2021-04-20 | 9
465 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 575.6 | No | 2021-03-18 | 2021-04-01 | 10 | 2021-06-22 | 67 | [27 empty] | 2021-03-18
466 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.135 | No | 2021-03-18 | 2021-04-01 | 10 | 2021-04-24 | 26 | 2021-05-03 | 5 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | 2021-04-09 | 6 |  |  |  |  | 2021-05-03 | 2021-05-17 | 10 |  | 2021-05-03 | 2021-05-03 | 0 | 2021-06-26 | 2021-07-13 | 10 | [15 empty] | 2021-06-26 | 2021-06-28 | 0 | 2021-07-13 | 2021-07-14 |  | 1
467 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 571.5 | No | 2021-03-17 | 2021-04-02 | 12 | 2021-06-22 | 68 | 2021-07-08 | 11 | [25 empty] | 2021-03-17 | 2021-05-10 | 38
468 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 | No | 2021-03-26 | 2021-04-09 | 10 | 2021-04-19 | 16 | 2021-05-06 | 13 | [19 empty] | 2021-03-26 | N/A | [11 empty] | 2021-05-06 | 2021-05-06 | 0 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 | 2021-05-07 |  | 1
469 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.424 | No | 2021-01-20 | 2021-02-03 | 10
470 | PGE | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 87.158 | No | 2021-02-04 | 2021-02-05 | 1
471 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.016 | No | 2021-01-25 | 2021-02-08 | 10 | 2021-05-26 | 86 | 2021-06-02 | 4 | [19 empty] | 2021-05-14 | N/A | [11 empty] | 2021-06-02 | 2021-06-02 | 0 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-06-02 |  | 0
473 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 46.393 | No | 2021-02-03 | 2021-02-18 | 10 | 2021-05-21 | 76 | 2021-05-26 | 3 | [19 empty] | 2021-05-23 | N/A | [11 empty] | 2021-06-07 | 2021-06-07 | 0 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-06-07 |  | 0
474 | PGE | NEM | NEM Paired Storage | Application Review in Progress | ENGN, Solar PV, Storage | 2503 | No | 2021-02-08 | 2021-02-22 | 9
475 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.54 | No | 2021-02-08 | 2021-02-23 | 10
476 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 409.842 | No | 2021-02-11 | 2021-02-24 | 8 | [29 empty] | 2021-02-11 | 2021-05-25 | 72
477 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 403.742 | No | 2021-02-11 | 2021-02-24 | 8 | [29 empty] | 2021-02-11 | 2021-05-25 | 72
478 | PGE | NEM | EXPNEM | IA in Progress | Solar PV, Storage | 349.179 | No | 2021-02-16 | 2021-02-26 | 8 | 2021-05-26 | 71 | 2021-06-30 | 24 | [15 empty] | 2021-06-30 | 2021-06-30 | 0 | 2021-06-30 | [6 empty] | 2021-02-16
480 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 41.393 | No | 2021-02-26 | 2021-03-12 | 10 | 2021-04-23 | 40 | 2021-04-26 | 1 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-03-29 | 0 | [11 empty] | 2021-04-26 | 2021-04-26 | 0 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-04-26 |  | 0
481 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1395.292 | No | 2021-03-04 | 2021-03-17 | 9
484 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 37.6 | No | 2021-03-15 | 2021-03-26 | 9 | 2021-06-07 | 59 | 2021-06-15 | 6 | [19 empty] | 2021-04-30 | N/A | [11 empty] | 2021-06-15 | 2021-06-17 | 2 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-17 | 2021-06-17 |  | 0
485 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 871.4 | No | 2021-03-17 | 2021-03-31 | 10 | 2021-06-22 | 68 | 2021-07-08 | 11 | [25 empty] | 2021-03-17
486 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 551.598 | No | 2021-03-17 | 2021-03-31 | 10 | 2021-06-04 | 56
487 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 39.195 | No | 2021-03-25 | 2021-03-31 | 4 | 2021-06-17 | 59 | 2021-07-12 | 16 | [19 empty] | 2021-06-21 | N/A | [11 empty] | 2021-07-12 | 2021-07-12 | 0 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-07-12 |  | 0
488 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1572 | No | 2021-02-03 | 2021-02-05 | 2 | 2021-02-10 | 5 | 2021-04-16 | 46 | 2021-04-23 | 2021-06-22 | 41 | [12 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | [6 empty] | 2021-02-03
489 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1872 | No | 2021-02-03 | 2021-02-05 | 2 | 2021-02-17 | 9 | 2021-04-20 | 44 | 2021-04-24 | 2021-06-24 | 42 | [12 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-24 | [6 empty] | 2021-02-03
490 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1542.8 | No | 2021-02-03 | 2021-02-05 | 2 | 2021-02-17 | 9 | 2021-04-20 | 44 | 2021-04-23 | 2021-06-23 | 42 | [12 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | [6 empty] | 2021-02-03
492 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1359.5 | No | 2021-01-29 | 2021-02-05 | 5 | 2021-04-07 | 47 | 2021-04-28 | 15 | 2021-05-10 | 2021-06-24 | 32 | [12 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-24 | [6 empty] | 2021-01-29
493 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1280.3 | No | 2021-01-29 | 2021-02-05 | 5 | 2021-04-07 | 47 | 2021-04-28 | 15 | 2021-06-02 | 2021-06-30 | 20 | [12 empty] | 2021-06-30 | 2021-06-30 | 0 | 2021-06-30 | [6 empty] | 2021-01-29
494 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1272 | No | 2021-02-03 | 2021-02-08 | 3 | 2021-04-07 | 44 | 2021-04-28 | 15 | 2021-05-07 | 2021-06-21 | 30 | [12 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | [6 empty] | 2021-02-03
495 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 | No | 2021-03-26 | 2021-04-07 | 8 | 2021-04-07 | 8 | 2021-04-30 | 17 | [32 empty] | 2021-04-30 | 2021-04-30 | 0 | [15 empty] | 2021-04-30 | 2021-04-30 | 0 | 2021-04-30 | 2021-05-03 |  | 1
496 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1309.5 | No | 2021-01-29 | 2021-02-13 | 10 | 2021-04-09 | 49 | 2021-05-07 | 20 | 2021-05-28 | 2021-06-28 | 20 | [12 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | [6 empty] | 2021-01-29
497 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1405.3 | No | 2021-02-03 | 2021-02-16 | 8 | 2021-04-10 | 46 | 2021-05-07 | 19 | 2021-06-01 | 2021-06-29 | 20 | [12 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | [6 empty] | 2021-02-03
499 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.559 | No | 2021-03-31 | 2021-04-14 | 10 | 2021-04-14 | 10 | 2021-04-22 | 6 | [15 empty] | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 | 2021-06-08 | 32 |  |  |  |  | 2021-03-31 | 2021-06-03 | 45 |  |  |  |  | 2021-06-14 | 2021-06-14 | 0 | [15 empty] | 2021-06-14 | 2021-06-14 | 0 | 2021-06-14 | 2021-06-08 |  | 4
500 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1547 | No | 2021-02-03 | 2021-02-04 | 1 | 2021-02-10 | 5 | 2021-04-08 | 40 | 2021-04-14 | 2021-06-22 | 48 | [12 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | [6 empty] | 2021-02-03
501 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 39.248 | No | 2021-03-27 | 2021-04-06 | 6 | 2021-04-06 | 6 | 2021-04-08 | 2
502 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 647.732 | No | 2021-02-08 | 2021-02-10 | 2 | 2021-03-10 | 21 | 2021-03-31 | 15 | 2021-04-09 | 2021-05-03 | 16 | [12 empty] | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | [6 empty] | 2021-02-08
503 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 39.229 | No | 2021-03-25 | 2021-03-31 | 4 | 2021-04-01 | 5 | 2021-04-21 | 14 | [15 empty] | 2021-03-31 | 2021-04-01 | 1 | 2021-04-01 | 2021-04-01 | 0
505 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 39.4 | No | 2021-01-07 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-15 | 3 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12
506 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.828 | No | 2021-02-10 | 2021-02-18 | 5 | 2021-02-18 | 5 | 2021-02-22 | 2 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-05-11 | 58 | [11 empty] | 2021-05-13 | 2021-05-13 | 0 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13 | 2021-05-13 |  | 0
507 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.877 | No | 2021-02-03 | 2021-02-06 | 2 | 2021-02-19 | 11 | 2021-03-03 | 8 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-07-08 | 89 | [11 empty] | 2021-07-08 | 2021-07-08 | 0 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-09 |  | 1
511 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 45.177 | No | 2021-02-08 | 2021-02-23 | 10 | 2021-03-16 | 25 | 2021-03-22 | 4 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-22 | 4 | [11 empty] | 2021-04-28 | 2021-04-28 | 0 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-04-28 |  | 0
512 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.49 | No | 2021-02-09 | 2021-02-24 | 10 | 2021-03-16 | 24 | 2021-03-24 | 6 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-05-21 | 48 | [11 empty] | 2021-05-26 | 2021-05-26 | 0 | [15 empty] | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 | 2021-05-27 |  | 1
513 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.728 | No | 2021-03-05 | 2021-03-19 | 10 | 2021-03-19 | 10 | 2021-03-22 | 1 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-06-07 | 55 | [11 empty] | 2021-06-09 | 2021-06-09 | 0 | [15 empty] | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | 2021-06-09 |  | 0
514 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 36.39 | No | 2021-03-08 | 2021-03-19 | 9 | 2021-04-08 | 23 | 2021-04-09 | 1 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-05-06 | 34
515 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 31.997 | No | 2021-03-09 | 2021-03-20 | 8 | 2021-03-20 | 8 | 2021-05-19 | 42 | [15 empty] | 2021-03-20 | 2021-03-20 | 0 | 2021-03-20
518 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.08 | No | 2021-03-11 | 2021-03-24 | 9 | [19 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24
521 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 42.716 | No | 2021-03-12 | 2021-03-25 | 9 | 2021-03-25 | 9 | 2021-03-29 | 2 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-04-20 | 18 | [11 empty] | 2021-04-20 | 2021-04-20 | 0 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-04-20 |  | 0
523 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 35.715 | No | 2021-03-15 | 2021-03-27 | 9 | 2021-04-15 | 23 | 2021-04-20 | 3 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | 2021-04-16 | 14 | [11 empty] | 2021-04-20 | [17 empty] | 2021-04-20 | 2021-04-21 | 1
524 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 38.545 | No | 2021-03-15 | 2021-03-29 | 10 | 2021-03-29 | 10 | 2021-04-15 | 13 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-04-21 | 17
526 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 | No | 2021-03-16 | 2021-03-29 | 9 | 2021-03-29 | 9 | 2021-03-30 | 1 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-05-05 | 27 | [11 empty] | 2021-05-05 | 2021-05-05 | 0 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-05-05 |  | 0
528 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 38.86 | No | 2021-03-22 | 2021-04-05 | 10 | 2021-05-05 | 32 | 2021-05-24 | 13 | [15 empty] | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-04-15 | 8 | [11 empty] | 2021-05-28 | 2021-05-28 | 0 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | 2021-05-28 |  | 0
532 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 | No | 2021-03-24 | 2021-04-07 | 10 | 2021-04-07 | 10 | 2021-04-20 | 9 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-07 | 0 | [11 empty] | 2021-04-20 | 2021-04-21 | 1 | [15 empty] | 2021-04-20 | 2021-04-21 | 1 | 2021-04-21 | 2021-04-21 |  | 0
533 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 | No | 2021-03-24 | 2021-04-07 | 10 | 2021-04-07 | 10 | 2021-04-09 | 2 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-05-11 | 24 |  |  |  |  | 2021-03-24 | 2021-04-15 | 16 |  |  |  |  | 2021-05-11 | 2021-05-21 | 8 | [15 empty] | 2021-05-11 | 2021-05-12 | 1 | 2021-05-21 | 2021-05-21 |  | 0
534 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 42.497 | No | 2021-03-25 | 2021-04-08 | 10 | 2021-04-15 | 15 | 2021-04-16 | 1 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | 2021-05-10 | 22 |  |  |  |  | 2021-03-25 | 2021-04-21 | 19 |  |  |  |  | 2021-05-10 | 2021-05-17 | 5 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-17 | 2021-05-17 |  | 0
535 | PGE | NEM | NEM Paired Storage | IA in Progress | OTHR, Solar PV, Storage | 30.246 | No | 2021-01-27 | 2021-02-10 | 10 | 2021-04-06 | 48 | 2021-04-08 | 2 | [15 empty] | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08
537 | PGE | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 30.08 | No | 2021-03-30 | 2021-04-12 | 9 | 2021-04-12 | 9 | 2021-04-20 | 6 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-04-20 | 6
538 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 56.873 | No | 2021-02-23 | 2021-03-06 | 8 | 2021-03-06 | 8 | 2021-03-18 | 8 | [15 empty] | 2021-03-06 | 2021-03-06 | 0 | 2021-03-06 | 2021-04-01 | 18
540 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 31 | No | 2021-02-02 | 2021-02-16 | 9 | 2021-03-17 | 30 | 2021-03-25 | 6 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-04-09 | 17
541 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 51.699 | No | 2021-01-12 | 2021-01-23 | 7 | 2021-03-03 | 34 | 2021-03-23 | 14 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | [6 empty] | 2021-01-12 | 2021-03-05 | 36
542 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 1451.1 | No | 2021-01-29 | 2021-02-02 | 2 | 2021-02-10 | 8 | 2021-04-08 | 40 | 2021-04-14 | 2021-06-22 | 48 | [12 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | [6 empty] | 2021-01-29 | 2021-03-23 | 36
543 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 96.54 | No | 2021-03-17 | 2021-03-31 | 10 | 2021-05-14 | 42 | 2021-06-02 | 12 | [15 empty] | 2021-06-02 | 2021-06-09 | 5 | 2021-06-09 | 2021-06-25 | 12 |  |  |  |  | 2021-03-17 | 2021-04-13 | 19 |  |  |  |  | 2021-07-15 | 2021-07-15 | 0 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-07-16 |  | 1
545 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 37.345 | No | 2021-03-23 | 2021-04-06 | 10 | 2021-04-06 | 10 | 2021-04-09 | 3 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-04-07 | 1 |  |  |  |  | 2021-03-23 | 2021-04-14 | 16 |  |  |  |  | 2021-04-23 | 2021-04-28 | 3 | [15 empty] | 2021-04-23 | 2021-04-23 | 0 | 2021-04-28 | 2021-04-28 |  | 0
546 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.36 | No | 2021-03-12 | 2021-03-26 | 10 | 2021-03-26 | 10 | 2021-03-29 | 1 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-04-07 | 8 | [11 empty] | 2021-04-13 | [17 empty] | 2021-04-13 | 2021-04-13 | 0
547 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 | No | 2021-03-23 | 2021-04-06 | 10 | 2021-04-07 | 11 | 2021-04-09 | 2 | [19 empty] | 2021-04-06 | N/A | [11 empty] | 2021-04-09 | 2021-04-09 | 0 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | 2021-04-10 |  | 0
548 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 | No | 2021-03-19 | 2021-04-02 | 10 | 2021-04-08 | 14 | 2021-04-09 | 1 | [15 empty] | 2021-04-02 | 2021-04-02 | 0 | 2021-04-02 | 2021-04-08 | 4 | [11 empty] | 2021-04-09 | 2021-04-09 | 0 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | 2021-04-10 |  | 0
550 | PGE | Non-NEM | NEMFC | Implementation | FUCE | 262.5 | No | 2021-03-08 | 2021-03-11 | 3 | 2021-03-11 | 3 | 2021-04-16 | 26 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | 2021-04-05 | 17 |  |  |  |  | 2021-03-08 | 2021-05-27 | 58
551 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 59.575 | No | 2021-03-31 | 2021-04-16 | 12 | 4/16/2021 |  | 2021-05-13 | 19 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13
552 | PGE | NEM | NEMMT | IA in Progress | Solar PV, Storage | 31.34 | No | 2021-01-21 | 2021-02-04 | 10 | 2021-05-21 | 85 | 2021-06-02 | 7 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-06-03 | 8
553 | PGE | NEM | NEMMT | Application Review in Progress | Solar PV, Storage | 894.727 | No | 2021-02-08 | 2021-02-22 | 9 | [29 empty] | 2021-02-08
554 | PGE | Non-NEM | NEMFC | IA in Progress | FUCE | 300 | No | 2021-02-17 | 2021-03-02 | 9 | 2021-05-13 | 61 | 2021-06-28 | 31 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28
556 | PGE | NEM | NEMMT | Application Review in Progress | ENGN, FUCE | 900 | No | 2021-03-16 | 2021-03-30 | 10
557 | PGE | NEM | NEMMT | Study in Progress | Solar PV, Turbine | 18500 | No | 2021-01-12 | 2021-01-12 | 0 | 2021-02-03 | 15 | [5 empty] | 2021-02-03 | 2021-03-03 | 19 | 2021-03-03 | 2021-03-18 | 11 | 2021-05-20 |  |  | 2021-03-18 | 2021-04-07 | 14 | [10 empty] | 2021-01-12
558 | PGE | NEM | NEMMT | Study in Progress | Solar PV, Turbine | 106359.791 | No | 2020-12-29 | 2021-01-04 | 3 | 2021-02-10 | 29 | [5 empty] | 2021-02-10 | 2021-03-22 | 27 | 2021-03-22 | 2021-04-12 | 15 | 2021-06-09 |  |  | 2021-04-12 | 2021-05-03 | 15
559 | PGE | NEM | NEMMT | Study in Progress | ENGN, Solar PV, Storage | 4580 | No | 2021-01-29 | 2021-02-01 | 1 | 2021-02-17 | 12 | [5 empty] | 2021-02-17 | 2021-03-15 | 18 | 2021-03-15 | 2021-03-17 | 2 | 2021-03-29 |  |  | 2021-03-17 | 2021-03-17 | 0 | [10 empty] | 2021-01-29
560 | PGE | NEM | NEMMT | Study in Progress | FUCE, Solar PV, WIND | 2600 | No | 2021-02-08 | 2021-02-22 | 9 | 2021-02-22 | 9 | [5 empty] | 2021-02-22 | 2021-04-30 | 49 | 2021-04-30 | 2021-04-30 | 0 | 2021-06-15 |  |  | 2021-04-30 | 2021-05-06 | 4
561 | PGE | NEM | NEMMT | Study in Progress | FUCE, Solar PV, Storage | 2994 | No | 2021-02-11 | 2021-02-16 | 2 | 2021-03-03 | 13 | [5 empty] | 2021-03-03 | 2021-06-07 | 67 | 2021-06-07 | [5 empty] | 7/14/2021 | 2021-07-14 | 0 | [10 empty] | 2021-02-11
562 | PGE | NEM | NEMMT | IA in Progress | FUCE, Solar PV | 1350 | No | 2021-02-01 | 2021-02-17 | 11 | 2021-03-27 | 38 | [5 empty] | 2021-03-27 | 2021-04-23 | 19 | 2021-04-23 |  |  | 4/23/2021 | 2021-07-12 | 54 |  |  |  | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [6 empty] | 2021-04-09 | 2021-05-07 | 20
563 | PGE | NEM | NEMMT | IA in Progress | FUCE, Solar PV | 769 | No | 2021-02-09 | 2021-02-22 | 8 | 2021-03-29 | 33 | 2021-07-07 | 70 | [15 empty] | 2021-07-07
564 | PGE | NEM | NEMMT | Study in Progress | FUCE, Solar PV | 250 | No | 2021-01-21 | 2021-02-04 | 10 | 2021-02-12 | 16 | 2021-03-05 | 14 | 2021-03-05 | 2021-04-02 | 20 | 2021-04-02 | 2021-05-07 | 25 | 2021-05-07 | 2021-05-24 | 11 |  |  |  | 2021-05-24 | [12 empty] | 2021-01-21 |  |  | 2021-06-17
565 | PGE | NEM | NEMMT | Commercial | Solar PV, Storage | 30.104 | No | 2021-03-05 | 2021-03-17 | 8 | 2021-03-17 | 8 | 2021-03-22 | 3 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-04-19 | 23 | [11 empty] | 2021-04-19 | 2021-04-23 | 4 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-23 | 2021-04-23 |  | 0
566 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 140 | No | 2021-02-09 | 2021-02-11 | 2 | 2021-03-03 | 15 | 2021-04-20 | 34 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | [6 empty] | 2021-03-04 | 2021-03-04 | 0
567 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 140 | No | 2021-02-10 | 2021-02-11 | 1 | 2021-03-03 | 14 | 2021-05-19 | 55 | [15 empty] | 2021-05-19 | 2021-05-19 | 0 | 2021-05-19 | [6 empty] | 2021-02-10 | 2021-03-05 | 16
568 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 350 | No | 2021-01-13 | 2021-01-14 | 1 | 2021-02-03 | 14 | 2021-05-27 | 80 | [15 empty] | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27
569 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 210 | No | 2021-01-15 | 2021-01-19 | 1 | 2021-02-03 | 12 | 2021-06-10 | 89 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | [6 empty] | 2021-07-09
570 | PGE | Non-NEM | Non-Export | Implementation | Storage | 350 | No | 2021-02-09 | 2021-02-11 | 2 | 2021-03-03 | 15 | 2021-04-19 | 33 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-06-07 | 34
571 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 350 | No | 2021-02-09 | 2021-02-11 | 2 | 2021-03-03 | 15 | 2021-06-23 | 79 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23
572 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 140 | No | 2021-02-23 | 2021-02-24 | 1 | 2021-03-10 | 11 | 2021-04-15 | 26 | [15 empty] | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | [6 empty] | 2021-02-23 | 2021-05-21 | 63
573 | PGE | Non-NEM | Non-Export | IA in Progress | ENGN, Solar PV | 21944.2 | No | 2021-02-22 | 2021-02-23 | 1 | 2021-03-17 | 17 | 2021-04-15 | 21 | 2021-05-05 | 2021-06-04 | 21 | [12 empty] | 2021-06-04 | 2021-06-23 | 13 | 2021-06-23
574 | PGE | Non-NEM | Non-Export | Withdrawn | Storage | 3000 | No | 2021-03-22 | 2021-03-23 | 1 | 2021-03-31 | 7
575 | PGE | Non-NEM | Non-Export | Withdrawn | Storage – EV | 153.6 | No | 2021-02-08 | 2021-02-09 | 1 | 2021-02-24 | 11 | 2021-03-01 | 3
576 | PGE | Non-NEM | Non-Export | Implementation | Storage | 1287 | No | 2021-02-20 | 2021-02-22 | 0 | 2021-03-03 | 7 | 2021-03-24 | 15 | 2021-04-07 | 2021-05-05 | 20 | [12 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-06-22 | 33 |  |  |  |  | 2021-02-20
577 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 980 | No | 2021-01-04 | 2021-01-05 | 1 | 2021-02-03 | 21 | [17 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | [6 empty] | 2021-01-04
578 | PGE | Non-NEM | Non-Export | Implementation | ENGN, Solar PV | 766.6 | No | 2021-01-12 | 2021-01-14 | 2 | 2021-01-27 | 10 | 2021-03-01 | 22 | [15 empty] | 2021-03-19 | 2021-03-22 | 1 | 2021-03-22 | 2021-06-24 | 67
579 | PGE | Non-NEM | Non-Export | Implementation | Storage | 1287 | No | 2021-02-20 | 2021-02-22 | 0 | 2021-03-03 | 7 | 2021-03-24 | 15 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-06-22 | 63 |  |  |  |  | 2021-02-20
580 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 140 | No | 2021-02-26 | 2021-03-01 | 1 | 2021-03-24 | 18 | [17 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26
581 | PGE | Non-NEM | Non-Export | Implementation | Storage | 140 | No | 2021-03-03 | 2021-03-05 | 2 | 2021-03-24 | 15 | 2021-05-07 | 32 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-07-02 | 69
582 | PGE | Non-NEM | Non-Export | Implementation | Storage | 715 | No | 2021-02-18 | 2021-02-19 | 1 | 2021-03-03 | 9 | 2021-04-13 | 29 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-05-04 | 15
583 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 420 | No | 2021-02-17 | 2021-02-18 | 1 | 2021-03-10 | 15 | 2021-04-14 | 25 | [15 empty] | 2021-04-14 | 2021-04-14 | 0 | 2021-04-14 | 2021-07-13 | 62 |  |  |  |  | 2021-02-17 | 2021-05-07 | 57
584 | PGE | Non-NEM | Non-Export | Withdrawn | Storage | 70 | No | 2021-01-05 | 2021-01-06 | 1 | 2021-01-27 | 15 | 2021-03-09 | 28 | [15 empty] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | [6 empty] | 2021-01-05 | 2021-02-05 | 22
585 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 | No | 2021-01-15 | 2021-01-19 | 1 | 2021-02-03 | 12 | 2021-03-11 | 25 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | 2021-06-02 | 58 |  |  |  |  | 2021-01-15 | 2021-02-09 | 16
586 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 210 | No | 2021-02-11 | 2021-02-16 | 2 | 2021-03-03 | 13 | 2021-06-23 | 79 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | [6 empty] | 2021-02-11 | 2021-03-16 | 22
587 | PGE | Non-NEM | RESBCT | Study in Progress | Solar PV | 5000 | No | 2021-03-30 | 2021-03-30 | 0 | 2021-04-21 | 16 | [5 empty] | 2021-04-21 | 2021-05-11 | 14 | 2021-05-11 | 2021-05-11 | 0 | 2021-05-19 |  |  | 2021-05-11 | 2021-05-12 | 1
588 | PGE | Non-NEM | RESBCT | Study in Progress | Solar PV | 2341.786 | No | 2021-02-16 | 2021-02-17 | 1 | 2021-02-24 | 6 | [5 empty] | 2021-03-03 | 2021-03-24 | 15 | 2021-03-24 | [18 empty] | 2021-02-16
589 | PGE | Non-NEM | RESBCT | Study in Progress | Solar PV | 2782.651 | No | 2021-03-08 | 2021-03-09 | 1 | 2021-03-24 | 12 | 2021-04-13 | 14 | 2021-04-28 | 2021-07-01 | 45 | [22 empty] | 2021-03-08
590 | PGE | NEM | VNEM | IA in Progress | Solar PV | 38.28 | No | 2021-03-24 | 2021-04-05 | 8 | 2021-04-29 | 26 | 2021-05-11 | 8 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2021-06-30 | 35 |  |  |  |  | 2021-03-24 | 2021-05-25 | 44 |  | 2021-05-11 | 2021-05-11 | 0
591 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 30.26 | No | 2021-01-22 | 2021-02-05 | 10
592 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 31.024 | No | 2021-02-27 | 2021-03-10 | 7
593 | PGE | NEM | VNEM | Study in Progress | Solar PV | 86.4 | No | 2021-03-15 | 2021-03-23 | 6 | 2021-06-16 | 66 | [27 empty] | 2021-07-13
594 | PGE | NEM | VNEM | Application Accepted | Solar PV | 38.78 | No | 2021-01-25 | 2021-02-08 | 10 | 2021-03-12 | 33 | 2021-03-24 | 8 | [15 empty] | 2021-03-24 | 2021-04-14 | 15 | 2021-04-14 | [6 empty] | 2021-01-25
595 | PGE | NEM | VNEM | IA in Progress | Solar PV | 217.549 | No | 2021-03-01 | 2021-03-10 | 7 | 2021-03-18 | 13 | 2021-04-29 | 30 | [15 empty] | 2021-04-29 | 2021-05-14 | 11 | 2021-05-14 | [6 empty] | 2021-03-01 | 2021-07-02 | 88 |  | 2021-07-02 | 2021-07-02 | 0
596 | PGE | NEM | VNEM | IA in Progress | Solar PV | 35.595 | No | 2021-03-12 | 2021-03-22 | 6 | 2021-06-23 | 72 | 2021-07-13 | 13 | [15 empty] | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13 | [6 empty] | 2021-03-12 | 2021-04-01 | 14
597 | PGE | NEM | VNEM | Implementation | Solar PV | 150 | No | 2021-01-20 | 2021-02-03 | 10 | 2021-03-05 | 31 | 2021-03-25 | 14 | [15 empty] | 2021-03-25 | 2021-04-15 | 15 | 2021-04-15 | 2021-06-15 | 42 |  |  |  |  | 2021-03-05 | 2021-03-08 | 1 |  | 2021-03-11 | 2021-03-11 | 0
598 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 30.402 | No | 2021-02-18 | 2021-03-05 | 11 | 2021-03-16 | 18 | 2021-03-16 | 0 | [15 empty] | 2021-03-16 | 2021-04-06 | 15 | 2021-04-06 | [6 empty] | 2021-02-18 | 2021-03-12 | 16
599 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 52.493 | No | 2021-02-26 | 2021-03-10 | 8 | 2021-03-16 | 12 | 2021-05-28 | 53 | [15 empty] | 2021-05-28 | 2021-06-08 | 6 | 2021-06-08 | [6 empty] | 2021-02-26 | 2021-03-23 | 17
600 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 43.53 | No | 2021-02-17 | 2021-03-05 | 12 | 2021-05-12 | 60 | 2021-04-02 | 28 | [15 empty] | 2021-04-02 | 2021-06-28 | 60 | 2021-06-28 | [6 empty] | 2021-02-17 | 2021-05-27 | 71
601 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 39.976 | No | 2021-02-26 | 2021-03-11 | 9 | 2021-05-10 | 51 | 2021-07-02 | 38 | [15 empty] | 2021-07-02 | [9 empty] | 2021-02-26 | 2021-05-26 | 63
602 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 39.976 | No | 2021-02-26 | 2021-03-12 | 10 | 2021-05-10 | 51 | 2021-07-02 | 38 | [15 empty] | 2021-07-02 | [9 empty] | 2021-02-26 | 2021-05-26 | 63
603 | PGE | NEM | VNEMMASH | Study in Progress | Solar PV | 39.976 | No | 2021-02-26 | 2021-03-12 | 10 | 2021-05-10 | 51 | [27 empty] | 2021-02-26 | 2021-05-26 | 63
605 | PGE | NEM | VNEMMASH | Study in Progress | Solar PV | 39.976 | No | 2021-02-26 | 2021-03-12 | 10 | 2021-05-10 | 51 | [27 empty] | 2021-02-26 | 2021-05-26 | 63
606 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 39.976 | No | 2021-02-26 | 2021-03-12 | 10 | 2021-03-31 | 23 | 2021-04-21 | 15 | [15 empty] | 2021-04-21 | 2021-05-26 | 25 | 2021-05-26 | [6 empty] | 2021-02-26 | 2021-05-26 | 63
607 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 39.976 | No | 2021-02-26 | 2021-03-12 | 10 | 2021-03-31 | 23 | 2021-04-21 | 15 | [15 empty] | 2021-04-21 | 2021-05-26 | 25 | 2021-05-26 | [6 empty] | 2021-02-26 | 2021-05-26 | 63
608 | PGE | NEM | VNEMMASH | Withdrawn | Solar PV | 42.168 | No | 2021-02-24 | 2021-03-09 | 9 | 2021-03-11 | 11 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-04-16 | 15 | 2021-04-16 | [6 empty] | 2021-02-24 | 2021-03-16 | 14
609 | PGE | NEM | VNEMMASH | Withdrawn | Solar PV | 34.179 | No | 2021-02-24 | 2021-03-09 | 9 | 2021-03-11 | 11 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-04-16 | 15 | 2021-04-16 | [6 empty] | 2021-02-24 | 2021-03-16 | 14
610 | PGE | NEM | VNEMMASH | Withdrawn | Solar PV | 34.179 | No | 2021-02-24 | 2021-03-09 | 9 | 2021-03-11 | 11 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-04-16 | 15 | 2021-04-16 | [6 empty] | 2021-02-24 | 2021-03-16 | 14
611 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 34.121 | No | 2021-02-24 | 2021-03-09 | 9 | 2021-03-15 | 13 | 2021-04-02 | 14 | [15 empty] | 2021-04-02 | 2021-04-08 | 4 | 2021-04-08 | [6 empty] | 2021-02-24
612 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 37.983 | No | 2021-02-26 | 2021-03-10 | 8 | 2021-03-16 | 12 | 2021-03-26 | 8 | [15 empty] | 2021-03-26 | 2021-04-16 | 15 | 2021-04-16 | [6 empty] | 2021-02-26 | 2021-05-06 | 49
613 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 43.53 | No | 2021-03-02 | 2021-03-09 | 5 | 2021-03-17 | 11 | 2021-03-31 | 10 | [15 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | [6 empty] | 2021-03-02 | 2021-03-31 | 21
614 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 37.983 | No | 2021-03-02 | 2021-03-09 | 5 | 2021-03-16 | 10 | 2021-04-01 | 12 | [15 empty] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | [6 empty] | 2021-03-02 | 2021-03-31 | 21
615 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 30.402 | No | 2021-02-17 | 2021-03-05 | 12 | 2021-03-15 | 18 | 2021-03-24 | 7 | [15 empty] | 2021-03-24 | 2021-04-14 | 15 | 2021-04-14 | [6 empty] | 2021-02-17 | 2021-05-27 | 71
616 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 63.72 | No | 2021-02-17 | 2021-03-05 | 12 | 2021-03-15 | 18 | 2021-03-24 | 7 | [15 empty] | 2021-03-24 | 2021-04-14 | 15 | 2021-04-14 | [6 empty] | 2021-02-17 | 2021-03-11 | 16 |  | 2021-03-24 | 2021-04-07 | 10
617 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 68.358 | No | 2021-02-02 | 2021-02-17 | 10 | 2021-02-22 | 13 | 2021-03-16 | 16 | [15 empty] | 2021-03-16 | 2021-04-21 | 26 | 2021-04-21 | [6 empty] | 2021-02-02 | 2021-02-24 | 15 |  | 2021-04-20 | 2021-04-21 | 1
618 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 75.636 | No | 2021-01-28 | 2021-02-11 | 10 | 2021-03-16 | 32 | 2021-05-05 | 36 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | [6 empty] | 2021-01-28 | 2021-03-18 | 34 |  | 2021-04-21 | 2021-04-21 | 0
619 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 60.446 | No | 2021-01-12 | 2021-01-27 | 10 | 2021-03-16 | 43 | 2021-03-28 | 8 | [15 empty] | 2021-05-14 | 2021-05-18 | 2 | 2021-05-18 | [6 empty] | 2021-01-12 | 2021-03-23 | 48 |  | 2021-03-24 | 2021-05-04 | 29
620 | PGE | NEM | VNEMSOMAH | Implementation | Solar PV | 95.363 | No | 2021-03-02 | 2021-03-15 | 9 | 2021-03-17 | 11 | 2021-04-14 | 20 | [15 empty] | 2021-04-14 | 2021-04-14 | 0 | 2021-04-14 | 2021-05-26 | 30 |  |  |  |  | 2021-03-26 | 2021-04-12 | 11 |  | 2021-04-14 | 2021-04-27 | 9
621 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 64.705 | No | 2021-03-30 | 2021-04-08 | 7 | 2021-04-16 | 13 | 2021-05-07 | 15 | [15 empty] | 2021-05-07 | 2021-05-07 | 0 | 2021-05-07 | [6 empty] | 2021-03-30 | 2021-05-25 | 40
622 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 41.246 | No | 2021-02-02 | 2021-02-17 | 10 | [29 empty] | 2021-02-02
623 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 65.629 | No | 2021-02-09 | 2021-02-23 | 9 | [29 empty] | 2021-02-09
624 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 58.04 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
625 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
626 | PGE | NEM | VNEMSOMAH | Withdrawn | Solar PV | 43.53 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
627 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
628 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
629 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
630 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
631 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
632 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
633 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 39.172 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
634 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 38.052 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
635 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 34.867 | No | 2021-02-15 | 2021-03-05 | 13 | [29 empty] | 2021-02-15
636 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 34.8 | No | 2021-02-15 | 2021-03-05 | 13 | [29 empty] | 2021-02-15
637 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 34.281 | No | 2021-02-15 | 2021-03-05 | 13 | [29 empty] | 2021-02-15
638 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 34.22 | No | 2021-02-14 | 2021-03-05 | 13 | [29 empty] | 2021-02-14
639 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 33.93 | No | 2021-02-14 | 2021-03-05 | 13 | [29 empty] | 2021-02-14
640 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 33.35 | No | 2021-02-14 | 2021-03-05 | 13 | [29 empty] | 2021-02-14
641 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 46.766 | No | 2021-01-04 | 2021-01-12 | 6 | 2021-01-12 | 6 | [5 empty] | 2021-01-12 | 2021-01-23 | 7 | 2021-01-23 | [18 empty] | 2021-01-04
642 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 65.584 | No | 2021-02-08 | 2021-02-23 | 10 | 2021-03-30 | 35 | [5 empty] | 2021-03-30 | 2021-06-08 | 49 | 2021-06-08 | 2021-06-18 | 8 | 2021-06-18 |  |  | 2021-06-18 | 2021-06-18 | 0 | [10 empty] | 2021-02-08
643 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 43.2 | No | 2021-02-02 | 2021-02-12 | 8 | 2021-04-02 | 42 | [5 empty] | 2021-04-02 | 2021-06-18 | 54 | 2021-06-18 | 2021-06-18 | 0 | 2021-06-18 |  |  | 2021-06-18 | 2021-06-18 | 0 | [10 empty] | 2021-02-02 | 2021-05-27 | 81
644 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 115.42 | No | 2021-02-16 | 2021-03-05 | 13 | 2021-04-05 | 34 | 2021-04-26 | 15 | [15 empty] | 2021-04-26 | 2021-05-14 | 14 | 2021-05-14 | [6 empty] | 2021-02-16 | 2021-07-08 | 100 |  | 2021-07-08 | 2021-07-08 | 0
645 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 68.358 | No | 2021-03-12 | 2021-03-23 | 7 | 2021-04-13 | 22 | 2021-05-04 | 15 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | [6 empty] | 2021-03-12 | 2021-06-11 | 64 |  | 2021-06-25 | 2021-07-04 | 5
646 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 95.363 | No | 2021-03-12 | 2021-03-26 | 10 | 2021-04-13 | 22 | 2021-05-04 | 15 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | [6 empty] | 2021-03-12 | 2021-05-07 | 40 |  | 2021-05-04 | 2021-05-04 | 0
647 | PGE | NEM | VNEMSOMAH | Application Accepted | Solar PV | 69.12 | No | 2021-02-17 | 2021-03-05 | 12 | 2021-03-05 | 12 | 2021-03-25 | 14 | [25 empty] | 2021-02-17 | 2021-03-11 | 16
648 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.179 | No | 2021-03-12 | 2021-03-23 | 7 | 2021-03-26 | 10 | 2021-04-01 | 4 | [15 empty] | 2021-04-01 | 2021-04-22 | 15 | 2021-04-22 | [6 empty] | 2021-03-12 | 2021-06-15 | 66
649 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 86.4 | No | 2021-02-26 | 2021-03-10 | 8 | 2021-03-16 | 12 | 2021-04-05 | 14 | [15 empty] | 2021-04-05 | 2021-04-26 | 15 | 2021-04-26 | [6 empty] | 2021-04-26 | 2021-05-03 | 5 |  | 2021-04-26 | 2021-04-26 | 0
650 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 61.783 | No | 2021-01-12 | 2021-01-27 | 10 | 2021-03-16 | 43 | 2021-03-28 | 8 | [15 empty] | 2021-05-14 | 2021-05-18 | 2 | 2021-05-18 | [6 empty] | 2021-01-12 | 2021-04-05 | 57 |  | 2021-05-04 | 2021-05-04 | 0
651 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100 | No | 2021-01-25 | 2021-02-08 | 10 | 2021-04-07 | 51 | 2021-04-28 | 15 | [15 empty] | 2021-04-28 | 2021-05-13 | 11 | 2021-05-13 | [6 empty] | 2021-01-25 | 2021-04-07 | 51 | 2021-07-09
652 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 52.868 | No | 2021-03-12 | 2021-03-23 | 7 | 2021-03-26 | 10 | 2021-04-09 | 10 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | [6 empty] | 2021-03-12 | 2021-07-09 | 83 |  | 2021-07-04 | 2021-07-04 | 0
653 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100.91 | No | 2021-02-11 | 2021-02-24 | 8 | 2021-02-24 | 8 | 2021-03-16 | 14 | [15 empty] | 2021-03-16 | 2021-04-06 | 15 | 2021-04-06 | [6 empty] | 2021-02-24 | 2021-02-25 | 1 |  | 2021-03-04 | 2021-03-12 | 6
654 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100.91 | No | 2021-02-11 | 2021-02-26 | 10 | 2021-02-26 | 10 | 2021-03-17 | 13 | [15 empty] | 2021-03-17 | 2021-04-06 | 14 | 2021-04-06 | [6 empty] | 2021-02-26 | 2021-03-01 | 1 |  | 2021-03-04 | 2021-03-12 | 6
655 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 72.22 | No | 2021-02-11 | 2021-02-26 | 10 | 2021-02-26 | 10 | 2021-03-17 | 13 | [15 empty] | 2021-03-17 | 2021-04-06 | 14 | 2021-04-06 | [6 empty] | 2021-03-09 | 2021-03-10 | 1 |  | 2021-03-12 | 2021-03-12 | 0
656 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 115.42 | No | 2021-02-12 | 2021-03-03 | 12 | 2021-03-05 | 14 | 2021-04-12 | 26 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | [6 empty] | 2021-02-12 | 2021-03-10 | 17 |  | 2021-03-24 | 2021-04-07 | 10
657 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 111.038 | No | 2021-03-04 | 2021-03-15 | 7 | 2021-03-15 | 7 | 2021-04-12 | 20 | [15 empty] | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | [6 empty] | 2021-03-04 | 2021-04-05 | 22 |  | 2021-04-12 | 2021-04-12 | 0
658 | PGE | NEM | VNEM | Study in Progress | Solar PV | 67.375 | No | 2021-01-16 | 2021-02-01 | 9 | 2021-02-01 | 9 | 2021-03-29 | 39 | [25 empty] | 2021-01-16
659 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 | No | 2021-02-08 | 2021-02-08 | 0 | 2021-03-03 | 16 | 2021-04-06 | 24 | [15 empty] | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-04-30 | 18
660 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 | No | 2021-02-17 | 2021-02-17 | 0 | 2021-03-03 | 10 | 2021-04-20 | 34 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-04-23 | 3
661 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 | No | 2021-02-17 | 2021-02-18 | 1 | 2021-03-03 | 10 | 2021-04-19 | 33 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-04-20 | 1
662 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 | No | 2021-02-17 | 2021-02-18 | 1 | 2021-03-03 | 10 | 2021-04-23 | 37 | [15 empty] | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | 2021-04-27 | 2
663 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 | No | 2021-02-17 | 2021-02-18 | 1 | 2021-03-03 | 10 | 2021-04-13 | 29 | [15 empty] | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-04-23 | 8
664 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 | No | 2021-02-17 | 2021-02-18 | 1 | 2021-03-03 | 10 | 2021-04-07 | 25 | [15 empty] | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-25 | 12
665 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 | No | 2021-02-18 | 2021-02-19 | 1 | 2021-03-03 | 9 | 2021-03-25 | 16 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-03-31 | 4
666 | PGE | Non-NEM | Make Before Break | IA in Progress | ENGN | 4562 | No | 2021-02-22 | 2021-02-23 | 1 | 2021-03-30 | 26 | 2021-06-11 | 52 | [15 empty] | 2021-06-24
667 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 37.598 | No | 2021-02-26 | 2021-03-11 | 9 | 2021-05-11 | 52 | 2021-06-16 | 25 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | [6 empty] | 2021-02-26 | 2021-05-26 | 63
668 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 54.65 | No | 2021-03-02 | 2021-03-09 | 5 | 2021-06-04 | 67 | 2021-06-04 | 0 | [32 empty] | 2021-06-04 | 2021-06-04 | 0 | [15 empty] | 2021-06-04 |  |  | 2021-06-04 | 2021-06-04 |  | 0
669 | PGE | Non-NEM | Non-Export | Implementation | Storage | 210 | No | 2021-03-11 | 2021-03-19 | 6 | 2021-03-31 | 14 | 2021-04-26 | 18 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-04-28 | 2
670 | PGE | Non-NEM | Make Before Break | IA in Progress | ENGN, Turbine | 40478.4 | No | 2021-03-19 | 2021-03-19 | 0 | 2021-03-31 | 8 | 2021-04-30 | 22 | [15 empty] | 2021-05-26
671 | PGE | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 32.641 | No | 2021-03-19 | 2021-03-24 | 3 | 2021-04-07 | 13 | 2021-04-23 | 12 | [32 empty] | 2021-05-14 | 2021-06-08 | 16 | 2021-05-03 | [14 empty] | 2021-05-14 | 2021-06-08 | 16 | 2021-06-08 |  | 2021-05-18 |  |  |  | 42
672 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 30.402 | No | 2021-03-22 | 2021-04-05 | 10 | 2021-07-07 | 75
673 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 210 | No | 2021-03-23 | 2021-03-23 | 0 | 2021-04-07 | 11 | 2021-06-23 | 54 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-07-14 | 14
674 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.5 | No | 2021-03-23 | 2021-04-06 | 10 | 2021-05-05 | 31 | 2021-05-24 | 13 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-05-18 | 9 | [11 empty] | 2021-05-24 | 2021-05-24 | 0 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24 | 2021-05-25 |  | 1
675 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.355 | No | 2021-03-25 | 2021-04-02 | 6 | [19 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04
676 | PGE | Non-NEM | RESBCT | Study in Progress | Solar PV | 5000 | No | 2021-03-25 | 2021-03-26 | 1 | 2021-03-31 | 4 | [5 empty] | 2021-03-31 | 2021-04-28 | 20 | 2021-04-28 | 2021-04-28 | 0 | 2021-05-06 |  |  | 2021-04-28 | 2021-04-29 | 1
677 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 114.141 | No | 2021-03-25 | 2021-03-26 | 1 | 2021-05-03 | 27 | 2021-05-11 | 6 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11
678 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 60.318 | No | 2021-03-27 | 2021-04-07 | 7 | 2021-07-12 | 73 | 2021-07-14 | 2 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | [6 empty] | 2021-03-27
679 | PGE | NEM | EXPNEM | Commercial | Solar PV | 40.979 | No | 2021-03-29 | 2021-04-06 | 6 | 2021-05-03 | 25 | 2021-05-18 | 11 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | 2021-05-25 | 5 | [11 empty] | 2021-06-02 | 2021-06-10 | 6 | [15 empty] | 2021-06-02 | 2021-06-03 | 1 | 2021-06-10 | 2021-06-17 |  | 5
680 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 57.927 | No | 2021-03-29 | 2021-04-12 | 10 | 6/5/2021 |  | 2021-06-23 | 12 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | [6 empty] | 2021-03-29 | 2021-06-16 | 56
681 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.612 | No | 2021-03-31 | 2021-04-14 | 10 | 2021-04-14 | 10 | 2021-06-11 | 41 | [15 empty] | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19
682 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 44.948 | No | 2021-04-01 | 2021-04-15 | 10 | 2021-04-29 | 20 | 2021-04-21 | 6 | [19 empty] | 2021-04-01 | N/A |  |  |  |  | 2021-04-01 | [6 empty] | 2021-04-29 | 2021-05-05 | 4 | [15 empty] | 2021-04-29 | 2021-04-29 | 0 | 2021-05-05 | 2021-05-05 |  | 0
683 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 166.6 | No | 2021-04-01 | 2021-04-05 | 2 | 2021-05-21 | 36 | 2021-06-08 | 11 | 2021-06-08 | 2021-07-06 | 19 | 2021-07-06 | [21 empty] | 2021-04-01
684 | PGE | NEM | EXPNEM | Implementation | Solar PV | 250 | No | 2021-04-01 | 2021-04-13 | 8 | 2021-04-23 | 16 | 2021-05-11 | 12 | 2021-05-11 | 2021-06-01 | 14 | [12 empty] | 2021-06-01 | 2021-06-02 | 1 | 2021-06-02 | 2021-06-03 | 1 |  |  |  |  | 2021-04-01 | 2021-05-07 | 26
685 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 140 | No | 2021-04-01 | 2021-04-02 | 1 | 2021-04-21 | 14 | 2021-06-11 | 36 | [15 empty] | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | [6 empty] | 2021-04-01
686 | PGE | NEM | EXPNEM | Implementation | Solar PV | 420 | No | 2021-04-01 | 2021-04-15 | 10 | 2021-04-22 | 15 | 2021-05-11 | 13 | 2021-05-11 | 2021-06-03 | 16 | [12 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-11 | 6
687 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 47.27 | No | 2021-04-01 | 2021-04-02 | 1 | 2021-04-07 | 4 | 2021-04-26 | 13 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-06-01 | 25
688 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 80.105 | No | 2021-04-01 | 2021-04-13 | 8 | [29 empty] | 2021-04-01
689 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 715 | No | 2021-03-25 | 2021-04-05 | 7 | 2021-04-14 | 14 | 2021-05-20 | 26 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | [6 empty] | 2021-04-01 | 2021-07-09 | 69
690 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 34.179 | No | 2021-04-02 | 2021-04-14 | 8 | [29 empty] | 2021-04-02
691 | PGE | NEM | EXPNEM | Implementation | Solar PV | 38.78 | No | 2021-04-02 | 2021-04-14 | 8 | 2021-06-03 | 43 | 2021-06-21 | 12 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-07-13 | 15 |  |  |  |  | 2021-04-02 | 2021-07-02 | 64
692 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 43.04 | No | 2021-04-02 | 2021-04-14 | 8 | 2021-04-14 | 8 | 2021-04-20 | 4 | [19 empty] | 2021-04-20 | N/A | [11 empty] | 2021-04-22 | 2021-04-22 | 0 | [15 empty] | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 | 2021-04-23 |  | 1
693 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 1560 | No | 2021-04-02 | 2021-04-02 | 0 | 2021-04-14 | 8 | 2021-05-20 | 26 | [25 empty] | 2021-04-02
694 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 50.396 | No | 2021-04-02 | 2021-04-08 | 4 | 2021-04-16 | 10 | 2021-05-21 | 25 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | [6 empty] | 2021-04-02 | 2021-06-24 | 58
695 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 33.614 | No | 2021-04-02 | 2021-04-13 | 7 | 2021-04-13 | 7 | 2021-05-06 | 17 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 | [6 empty] | 2021-04-02 | 2021-05-26 | 38
696 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 34.179 | No | 2021-04-02 | 2021-04-13 | 7 | 2021-04-13 | 7 | 2021-05-06 | 17 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 | [6 empty] | 2021-04-02 | 2021-05-26 | 38
697 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 38.018 | No | 2021-04-02 | 2021-04-13 | 7 | 2021-04-13 | 7 | 2021-07-16 | 66 | [15 empty] | 2021-07-16 | [9 empty] | 2021-04-02
698 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 30.402 | No | 2021-04-02 | 2021-04-13 | 7 | 2021-04-13 | 7 | 2021-05-06 | 17 | [15 empty] | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 | [6 empty] | 2021-04-02
699 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.804 | No | 2021-04-02 | 2021-04-05 | 1 | 2021-04-05 | 1 | 2021-04-09 | 4 | [15 empty] | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | 2021-04-12 | 1 |  |  |  |  | 2021-07-07 | 2021-07-08 | 1 | [7 empty] | 2021-06-15
700 | PGE | NEM | EXPNEM | Implementation | Solar PV | 33.3 | No | 2021-04-02 | 2021-04-14 | 8 | 2021-05-10 | 26 | 2021-06-28 | 34 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-06-29 | 1
701 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 105.929 | No | 2021-04-02 | 2021-04-12 | 6 | 2021-05-11 | 27 | 2021-06-25 | 32 | [15 empty] | 2021-06-25 | 2021-06-25 | 0 | 2021-06-25 | [6 empty] | 2021-04-02 |  |  | 2021-07-13
702 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 178.024 | No | 2021-04-02 | 2021-04-05 | 1 | 2021-05-06 | 24 | 2021-06-30 | 38 | [15 empty] | 2021-06-30 | 2021-07-06 | 3 | 2021-07-06 | 2021-07-16 | 8
703 | PGE | NEM | VNEM | Implementation | Solar PV | 34.639 | No | 2021-04-05 | 2021-04-14 | 7 | 2021-05-07 | 24 | 2021-06-09 | 22 | [19 empty] | 2021-06-14 | N/A |  |  |  |  | 2021-06-17 | 2021-06-17 | 0 |  | 2021-06-16 | 2021-06-16 | 0
704 | PGE | NEM | VNEM | Implementation | Solar PV | 55.575 | No | 2021-04-05 | 2021-04-14 | 7 | 2021-05-25 | 36 | 2021-06-11 | 12 | [15 empty] | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-06-12 | 0 |  |  |  |  | 2021-06-04 | 2021-06-04 | 0 |  | 2021-06-04 | 2021-06-11 | 5
705 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 36.461 | No | 2021-04-05 | 2021-04-15 | 8 | 2021-04-15 | 8 | 2021-04-19 | 2 | [19 empty] | 2021-04-05 | N/A |  |  |  |  | 2021-04-05 | 2021-06-14 | 49
706 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 429 | No | 2021-04-05 | 2021-04-19 | 10 | 2021-05-12 | 27 | [27 empty] | 2021-06-14 | 2021-07-09 | 18
707 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 123.798 | No | 2021-04-05 | 2021-04-16 | 9 | 2021-05-10 | 25 | 2021-06-01 | 15 | [15 empty] | 2021-06-01 | 2021-06-01 | 0 | 2021-06-01
708 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 1875 | No | 2021-04-05 | 2021-04-06 | 1 | 2021-05-12 | 27 | 2021-06-11 | 21 | 2021-07-06 | [24 empty] | 2021-04-05
709 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 32.178 | No | 2021-04-05 | 2021-04-15 | 8 | 2021-04-23 | 14 | 2021-04-27 | 2
710 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 133.2 | No | 2021-04-06 | 2021-04-08 | 2 | 2021-04-14 | 6 | 2021-04-28 | 10 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-06-30 | 44 | [11 empty] | 2021-07-15 | [17 empty] | 2021-07-15 | 2021-07-15 | 0
711 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.341 | No | 2021-04-06 | 2021-04-20 | 10 | 2021-04-20 | 10 | 2021-05-11 | 15 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-04-20 | 0 |  |  |  |  | 2021-04-06 | 2021-05-25 | 35 |  |  |  |  | 2021-05-28 | 2021-05-28 | 0 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | 2021-05-28 |  | 0
712 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 33.54 | No | 2021-04-06 | 2021-04-08 | 2 | 2021-06-08 | 44 | 2021-07-07 | 20 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | [6 empty] | 2021-04-06 | 2021-04-15 | 7
713 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 420 | No | 2021-04-06 | 2021-04-08 | 2 | 2021-05-12 | 26
714 | PGE | Non-NEM | NEMFC | Study in Progress | FUCE | 525 | No | 2021-04-06 | 2021-04-20 | 10 | 2021-06-09 | 45
715 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 43.732 | No | 2021-04-06 | 2021-04-20 | 10 | 2021-04-20 | 10 | 2021-05-06 | 12 | [15 empty] | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-05-05 | 11
716 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 66.513 | No | 2021-04-06 | 2021-04-20 | 10 | 2021-04-22 | 12 | 2021-05-27 | 25 | [15 empty] | 2021-05-27 | 2021-05-28 | 1 | 2021-05-28 | [6 empty] | 2021-04-06 |  |  | 2021-06-11 | 2021-06-25 | 2021-06-25 | 10
717 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.119 | No | 2021-04-07 | 2021-04-20 | 9 | 2021-04-20 | 9 | 2021-05-06 | 12 | [19 empty] | 2021-04-07 | N/A |  |  |  |  | 2021-04-07 | [6 empty] | 2021-05-18 | 2021-05-18 | 0 | [15 empty] | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | 2021-05-18 |  | 0
718 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 912.4 | No | 2021-04-07 | 2021-04-21 | 10 | [29 empty] | 2021-04-07 | 2021-05-25 | 34 | 2021-05-25
719 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 72.22 | No | 2021-04-07 | 2021-04-13 | 4 | 2021-04-14 | 5 | [27 empty] | 2021-04-07 |  |  | 2021-04-29
720 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 72.22 | No | 2021-04-07 | 2021-04-13 | 4 | 2021-04-14 | 5 | [27 empty] | 2021-04-07 |  |  | 2021-04-29 | 2021-05-13 | 2021-05-13 | 10
721 | PGE | NEM | SNEM | Application Review in Progress | Solar PV | 6570 | No | 2021-04-07 | 2021-04-14 | 5
722 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 72.55 | No | 2021-04-07 | 2021-04-08 | 1 | 2021-04-16 | 7 | 2021-04-27 | 7 | [15 empty] | 2021-04-27 | 2021-04-30 | 3 | 2021-04-30 | [6 empty] | 2021-04-07 | 2021-04-15 | 6
723 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 564.698 | No | 2021-04-07 | 2021-04-22 | 11 | 2021-06-17 | 50 | 2021-07-08 | 14 | [25 empty] | 2021-04-07
724 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 1926.164 | No | 2021-04-08 | 2021-04-14 | 4 | 2021-04-28 | 14 | [5 empty] | 2021-07-02
725 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 224.463 | No | 2021-04-08 | 2021-04-09 | 1 | 2021-04-08 | 0 | 2021-04-29 | 15 | [15 empty] | 2021-04-29 | 2021-05-03 | 2 | 2021-05-03 | [6 empty] | 2021-04-08 | 2021-05-07 | 21
726 | PGE | NEM | NEMMT | Application Accepted | OTHR, Solar PV | 31.393 | No | 2021-04-08 | 2021-04-14 | 4 | 2021-07-09 | 64
727 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.2 | No | 2021-04-08 | 2021-04-17 | 6
728 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 528.528 | No | 2021-04-08 | 2021-04-22 | 10
729 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 124.677 | No | 2021-04-08 | 2021-04-16 | 6 | [23 empty] | 2021-05-13 | N/A
730 | PGE | NEM | EXPNEM | Commercial | Solar PV | 91.863 | No | 2021-04-09 | 2021-04-12 | 1 | 2021-04-13 | 2 | 2021-04-28 | 11 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-04-29 | 1 | [11 empty] | 2021-05-03 | 2021-05-11 | 6 | [15 empty] | 2021-05-03 | 2021-05-04 | 1 | 2021-05-11 | 2021-05-14 |  | 3
731 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.52 | No | 2021-04-09 | 2021-04-22 | 9 | 2021-04-22 | 9 | 2021-04-26 | 2 | [19 empty] | 2021-04-09 | N/A | [11 empty] | 2021-04-26 | 2021-04-26 | 0 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-04-26 |  | 0
732 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 39.593 | No | 2021-04-09 | 2021-04-12 | 1 | 2021-05-11 | 22 | 2021-05-24 | 9 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24
733 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.734 | No | 2021-04-09 | 2021-04-13 | 2 | 2021-04-13 | 2 | 2021-04-14 | 1 | [19 empty] | 2021-04-09 | N/A | [11 empty] | 2021-06-01 | 2021-06-03 | 2 | [15 empty] | 2021-06-01 | 2021-06-01 | 0 | 2021-06-03 | 2021-06-03 |  | 0
734 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 36.83 | No | 2021-04-09 | 2021-04-12 | 1 | 2021-07-01 | 58 | [27 empty] | 2021-04-12
735 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 490 | No | 2021-04-09 | 2021-04-14 | 3 | 2021-04-21 | 8 | 2021-06-15 | 38 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-15 | [6 empty] | 2021-04-09
736 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 32.678 | No | 2021-04-09 | 2021-04-22 | 9 | 2021-05-05 | 18 | 2021-05-18 | 9 | [19 empty] | 2021-04-27 | N/A
737 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 36.403 | No | 2021-04-09 | 2021-04-22 | 9 | 2021-05-05 | 18 | 2021-05-17 | 8 | [19 empty] | 2021-04-23 | N/A
738 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 35.007 | No | 2021-04-09 | 2021-04-13 | 2 | [23 empty] | 2021-05-13 | N/A
739 | PGE | NEM | VNEM | Study in Progress | Solar PV | 46.946 | No | 2021-04-11 | 2021-04-15 | 3 | 2021-07-01 | 57 | [27 empty] | 2021-07-07
740 | PGE | NEM | EXPNEM | Commercial | Solar PV | 193.173 | No | 2021-04-12 | 2021-04-12 | 0 | 2021-04-26 | 10 | 2021-05-12 | 12 | [15 empty] | 2021-05-12 | 2021-05-12 | 0 | 2021-05-12 | 2021-05-17 | 3 |  |  |  |  | 2021-04-12 | 2021-05-10 | 20 |  |  |  |  | 2021-05-19 | 2021-06-16 | 19 | [15 empty] | 2021-05-19 | 2021-06-09 | 14 | 2021-06-16 | 2021-06-23 |  | 5
741 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.48 | No | 2021-04-12 | 2021-04-16 | 4 | 2021-04-22 | 8 | 2021-05-05 | 9 | [19 empty] | 2021-04-12 | N/A | [11 empty] | 2021-05-05 | 2021-05-05 | 0 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-05-05 |  | 0
742 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 | No | 2021-04-12 | 2021-05-05 | 17 | 2021-06-10 | 42 | 2021-06-16 | 4 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | 2021-07-02 | 12 |  |  |  |  | 2021-07-08
743 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 125 | No | 2021-04-12 | 2021-04-23 | 9 | 2021-06-10 | 42 | [17 empty] | 2021-07-02 | [9 empty] | 2021-04-12 | 2021-06-16 | 46
744 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.875 | No | 2021-04-12 | 2021-04-28 | 12 | 2021-05-24 | 30 | 2021-06-08 | 10 | [15 empty] | 2021-06-08 | 2021-06-28 | 14 | 2021-06-28 | [6 empty] | 2021-04-12 | 2021-07-15 | 66
745 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 900 | No | 2021-04-13 | 2021-04-28 | 11 | 2021-04-29 | 12 | [5 empty] | 2021-04-29 | 2021-06-04 | 25 | 2021-06-04
746 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.559 | No | 2021-04-13 | 2021-04-26 | 9 | 2021-04-26 | 9 | 2021-05-11 | 11 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-05-24 | 20 | [11 empty] | 2021-05-25 | 2021-05-26 | 1 | [15 empty] | 2021-05-25 | 2021-05-26 | 1 | 2021-05-26 | 2021-05-26 |  | 0
747 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 300 | No | 2021-04-13 | 2021-04-19 | 4 | 2021-05-20 | 27 | 2021-06-09 | 13 | 2021-06-09 | 2021-07-07 | 19 | [12 empty] | 2021-07-07 | 2021-07-12 | 3 | 2021-07-12 | 2021-07-12 | 0 |  |  |  |  | 2021-04-13 | 2021-05-10 | 19
748 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 37.8 | No | 2021-04-13 | 2021-04-14 | 1 | 2021-04-14 | 1 | 2021-04-30 | 12 | [19 empty] | 2021-04-30 | N/A | [11 empty] | 2021-06-01 | 2021-06-01 | 0 | [15 empty] | 2021-06-01 | 2021-06-01 | 0 | 2021-06-01 | 2021-06-01 |  | 0
749 | PGE | NEM | EXPNEM | Implementation | Solar PV | 165.405 | No | 2021-04-13 | 2021-04-28 | 11 | 2021-05-21 | 28 | 2021-06-04 | 9 | [15 empty] | 2021-06-04 | 2021-06-04 | 0 | 2021-06-04 | 2021-06-07 | 1 |  |  |  |  | 2021-04-13 | 2021-06-03 | 36
750 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.024 | No | 2021-04-13 | 2021-04-15 | 2 | 2021-05-06 | 17 | 2021-07-09 | 44 | [15 empty] | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09 | [6 empty] | 2021-04-13 | 2021-06-15 | 44
751 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.024 | No | 2021-04-13 | 2021-04-15 | 2 | 2021-04-28 | 11 | 2021-05-13 | 11 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13 | [6 empty] | 2021-04-13 | 2021-07-06 | 58
752 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 40.1 | No | 2021-04-13 | 2021-04-14 | 1 | 2021-04-29 | 12 | 2021-05-12 | 9 | [15 empty] | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13 | 2021-05-24 | 7 |  |  |  |  | 2021-07-16 | [6 empty] | 2021-06-05 | [17 empty] | 2021-06-05 | 2021-06-07 | 0
753 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 36 | No | 2021-04-13 | 2021-04-14 | 1 | 2021-04-14 | 1 | 2021-04-28 | 10 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-05-03 | 3
754 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.36 | No | 2021-04-13 | 2021-04-26 | 9 | 2021-04-26 | 9 | 2021-05-11 | 11 | [19 empty] | 2021-04-13 | N/A | [11 empty] | 2021-05-11 | 2021-05-12 | 1 | [15 empty] | 2021-05-11 | 2021-05-12 | 1 | 2021-05-12 | 2021-05-12 |  | 0
755 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 52.33 | No | 2021-04-13 | 2021-04-14 | 1 | 2021-04-23 | 8 | 2021-04-26 | 1 | [15 empty] | 2021-04-26 | 2021-05-12 | 12 | 2021-05-12 | 2021-05-14 | 2 |  |  |  |  | 2021-04-13 | 2021-05-10 | 19
756 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 200 | No | 2021-04-13 | 2021-04-14 | 1 | 2021-04-19 | 4 | 2021-05-04 | 11 | 2021-05-04 | 2021-06-01 | 19 | 2021-06-10 | 2021-07-08 | 19 | 2021-07-08 | 2021-07-14 | 4 |  |  |  | 2021-07-14 | [12 empty] | 2021-04-13 | 2021-05-10 | 19
757 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 69.278 | No | 2021-04-13 | 2021-04-20 | 5 | 2021-04-30 | 13 | 2021-06-16 | 32 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | [6 empty] | 2021-04-13
758 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 31.024 | No | 2021-04-14 | 2021-04-23 | 7 | 2021-05-25 | 29 | [27 empty] | 2021-04-14 | 2021-06-18 | 46
759 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 300 | No | 2021-04-14 | 2021-04-27 | 9 | 2021-06-08 | 38 | [5 empty] | 2021-06-08 | 2021-07-06 | 19 | 2021-07-06
760 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 37.858 | No | 2021-04-14 | 2021-04-26 | 8
761 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.504 | No | 2021-04-14 | 2021-04-26 | 8 | 2021-06-10 | 40 | 2021-07-07 | 18 | [15 empty] | 2021-07-07 | 2021-07-16 | 7 | 2021-07-16 | 2021-07-16 | 0 |  |  |  |  | 2021-04-14 |  |  | 2021-06-17
762 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 215.661 | No | 2021-04-14 | 2021-04-15 | 1 | 2021-05-13 | 21 | 2021-05-28 | 11 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | 2021-07-12 | 29 |  |  |  |  | 2021-04-14 | 2021-06-17 | 45
763 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 375 | No | 2021-04-14 | 2021-04-27 | 9 | [29 empty] | 2021-04-14
764 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 2760 | No | 2021-04-14 | 2021-04-16 | 2 | 2021-04-21 | 5 | 2021-06-16 | 39 | [25 empty] | 2021-04-14
765 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 140 | No | 2021-04-14 | 2021-04-16 | 2 | 2021-05-12 | 20 | 2021-07-15 | 44 | [15 empty] | 2021-07-15 | 2021-07-16 | 1 | 2021-07-16 | [6 empty] | 2021-04-14
766 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 272.254 | No | 2021-04-15 | 2021-04-28 | 9
767 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 300 | No | 2021-04-15 | 2021-04-28 | 9 | 2021-06-04 | 35 | 2021-06-14 | 6 | [15 empty] | 2021-06-14 | 2021-07-01 | 13 | 2021-07-01
768 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 88.18 | No | 2021-04-15 | 2021-04-16 | 1 | 2021-04-28 | 9 | 2021-05-19 | 15 | 2021-05-19 | 2021-07-09 | 35 | [12 empty] | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09
769 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 240 | No | 2021-04-15 | 2021-04-16 | 1 | 2021-05-04 | 13 | 2021-06-28 | 38 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | [6 empty] | 2021-04-15 | 2021-05-28 | 31
770 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 600 | No | 2021-04-15 | 2021-04-16 | 1 | 2021-05-04 | 13 | 2021-07-08 | 45 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [6 empty] | 2021-04-15 | 2021-05-18 | 23
771 | PGE | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 2043.114 | No | 2021-04-15 | 2021-04-20 | 3 | 2021-05-05 | 14 | [27 empty] | 2021-04-15
772 | PGE | Non-NEM | Non-Export | Study in Progress | ENGN | 4500 | No | 2021-04-15 | 2021-04-16 | 1 | 2021-04-21 | 4 | 2021-05-24 | 23
773 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 210 | No | 2021-04-16 | 2021-04-16 | 0 | 2021-04-28 | 8 | 2021-07-02 | 46 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02
774 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 | No | 2021-04-16 | 2021-04-27 | 7 | 2021-05-07 | 15 | 2021-05-10 | 1 | [19 empty] | 2021-05-07 | N/A | [11 empty] | 2021-05-10 | 2021-05-10 | 0 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2021-05-10 |  | 0
775 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 | No | 2021-04-16 | 2021-04-19 | 1 | 2021-05-21 | 25 | 2021-06-05 | 9 | [15 empty] | 2021-06-05 | 2021-06-05 | 0 | 2021-06-05 | 2021-06-11 | 4 |  |  |  |  | 2021-04-16 | 2021-06-15 | 41
776 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 379.1 | No | 2021-04-16 | 2021-04-29 | 9
777 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 98.987 | No | 2021-04-16 | 2021-04-19 | 1 | 2021-04-22 | 4 | 2021-05-04 | 8 | [15 empty] | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | 2021-07-01 | 41 |  |  |  |  | 2021-04-16 | [6 empty] | 2021-07-12 | [17 empty] | 2021-07-12 | 2021-07-12 | 0
778 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 49.565 | No | 2021-04-16 | 2021-04-19 | 1 | 2021-06-16 | 42 | 2021-07-01 | 11 | [15 empty] | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01 | [6 empty] | 2021-04-16 | 2021-06-24 | 48
779 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 86.4 | No | 2021-04-16 | 2021-04-30 | 10 | 2021-06-11 | 39 | 2021-07-02 | 15 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | [6 empty] | 2021-06-28 | 2021-07-15 | 12
780 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 62.5 | No | 2021-04-16 | 2021-04-30 | 10 | [29 empty] | 2021-04-16 | 2021-07-02 | 54
781 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 60 | No | 2021-04-16 | 2021-04-19 | 1 | 2021-04-19 | 1 | 2021-04-23 | 4 | [15 empty] | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | [6 empty] | 2021-04-16 | 2021-05-07 | 15
782 | PGE | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 2012.104 | No | 2021-04-19 | 2021-04-19 | 0 | 2021-05-05 | 12 | [27 empty] | 2021-04-19
783 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 170 | No | 2021-04-19 | 2021-04-19 | 0 | 2021-06-10 | 37 | 2021-06-29 | 13 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | [6 empty] | 2021-04-19
784 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 196 | No | 2021-04-19 | 2021-04-19 | 0 | 2021-06-10 | 37 | 2021-06-29 | 13 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | [6 empty] | 2021-04-19
785 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 210 | No | 2021-04-19 | 2021-04-21 | 2 | 2021-05-05 | 12 | 2021-07-06 | 42 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06
786 | PGE | Non-NEM | NEMFC | Study in Progress | FUCE | 1470 | No | 2021-04-20 | 2021-05-04 | 10 | 2021-05-06 | 12
787 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 300 | No | 2021-04-20 | 2021-05-04 | 10 | 2021-05-14 | 18 | 2021-06-02 | 12 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | [6 empty] | 2021-06-17 | 2021-07-02 | 11
788 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 240 | No | 2021-04-20 | 2021-04-21 | 1 | 2021-04-28 | 6 | 2021-05-10 | 8 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | [6 empty] | 2021-04-20 | 2021-05-07 | 13
789 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 120 | No | 2021-04-20 | 2021-04-21 | 1 | 2021-04-27 | 5 | 2021-05-10 | 9 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | [6 empty] | 2021-04-20 | 2021-05-10 | 14
790 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 117.475 | No | 2021-04-20 | 2021-04-21 | 1 | 2021-04-28 | 6 | 2021-05-12 | 10 | [15 empty] | 2021-05-12 | 2021-05-12 | 0 | 2021-05-12
791 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 91.917 | No | 2021-04-16 | 2021-04-21 | 3
792 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100 | No | 2021-04-20 | 2021-04-21 | 1 | 2021-04-28 | 6 | 2021-05-11 | 9 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | [6 empty] | 2021-04-20 | 2021-05-07 | 13
793 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 60 | No | 2021-04-20 | 2021-04-21 | 1 | 2021-04-28 | 6 | 2021-05-11 | 9 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | [6 empty] | 2021-04-20 | 2021-05-07 | 13
794 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 279.436 | No | 2021-04-21 | 2021-05-06 | 11 | 2021-06-15 | 38 | [30 empty] | 2021-07-08
795 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 32.564 | No | 2021-04-21 | 2021-04-26 | 3 | 2021-05-20 | 21 | 2021-05-24 | 2 | [19 empty] | 2021-05-20 | N/A
796 | PGE | NEM | EXPNEM | Commercial | Solar PV | 50 | No | 2021-04-21 | 2021-04-29 | 6 | 2021-05-04 | 9 | 2021-05-25 | 15 | [15 empty] | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-06-14 | 13 | [11 empty] | 2021-06-14 | 2021-06-23 | 7 | [15 empty] | 2021-06-14 | 2021-06-15 | 1 | 2021-06-23 | 2021-06-24 |  | 1
797 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 | No | 2021-04-21 | 2021-04-22 | 1 | 2021-06-18 | 41 | 2021-07-08 | 13 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-15 | 5 |  |  |  |  | 2021-04-21 | 2021-05-18 | 19 |  |  |  |  | 2021-07-15 | [17 empty] | 2021-07-15 | 2021-07-16 | 1
798 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 61.513 | No | 2021-04-21 | 2021-05-04 | 9
799 | PGE | Non-NEM | NEMFC | IA in Progress | FUCE | 262.5 | No | 2021-04-22 | 2021-05-06 | 10 | 2021-05-06 | 10 | 2021-05-27 | 15 | [15 empty] | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | [6 empty] | 2021-04-22
800 | PGE | NEM | EXPNEM | Implementation | Solar PV | 89.246 | No | 2021-04-22 | 2021-05-04 | 8 | 2021-05-17 | 17 | 2021-06-28 | 29 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-07-12 | 9 |  |  |  |  | 2021-04-22
801 | PGE | Non-NEM | Non-Export | Implementation | Storage | 420 | No | 2021-04-22 | 2021-04-23 | 1 | 2021-05-19 | 19 | 2021-06-18 | 21 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-18 | 2021-06-23 | 3 |  |  |  |  | 2021-04-22
802 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 36.12 | No | 2021-04-22 | 2021-04-27 | 3 | 2021-04-27 | 3 | 2021-04-28 | 1 | [19 empty] | 2021-04-27 | N/A | [11 empty] | 2021-04-28 | 2021-05-05 | 5 | [15 empty] | 2021-04-28 | 2021-04-28 | 0 | 2021-05-05 | 2021-05-06 |  | 1
803 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 326.971 | No | 2021-04-22 | 2021-04-23 | 1 | 2021-04-30 | 6 | 2021-05-19 | 13 | [15 empty] | 2021-05-19 | 2021-05-19 | 0 | 2021-05-19 | 2021-05-25 | 4 |  |  |  |  | 2021-04-22 | 2021-05-07 | 11
804 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.38 | No | 2021-04-22 | 2021-04-30 | 6 | 2021-05-05 | 9 | 2021-05-14 | 7 | [19 empty] | 2021-05-14 | N/A | [11 empty] | 2021-05-14 | 2021-05-14 | 0 | [15 empty] | 2021-05-14 | 2021-05-14 | 0 | 2021-05-14 | 2021-05-17 |  | 1
805 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 | No | 2021-04-22 | 2021-04-23 | 1 | 2021-05-03 | 7 | 2021-05-21 | 14 | [15 empty] | 2021-05-21 | 2021-06-16 | 17 | 2021-06-16
806 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 86 | No | 2021-04-22 | 2021-05-04 | 8 | 2021-05-04 | 8 | 2021-05-26 | 16 | [15 empty] | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 | [6 empty] | 2021-05-26
807 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 116.6 | No | 2021-04-22 | 2021-04-26 | 2 | 2021-06-02 | 28 | 2021-06-21 | 13 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-23 | 2 | [11 empty] | 2021-07-17 | [17 empty] | 2021-07-17
808 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 | No | 2021-04-22 | 2021-04-26 | 2 | 2021-04-28 | 4 | 2021-06-16 | 34 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | 2021-06-22 | 4
809 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 38.019 | No | 2021-04-22 | 2021-05-03 | 7 | 2021-05-03 | 7 | 2021-05-05 | 2 | [19 empty] | 2021-05-03 | N/A | [11 empty] | 2021-05-05 | 2021-05-05 | 0 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-05-10 |  | 3
810 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 572 | No | 2021-04-22 | 2021-04-23 | 1 | 2021-05-19 | 19 | [27 empty] | 2021-04-22 | 2021-06-16 | 38
811 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 35.116 | No | 2021-04-23 | 2021-05-05 | 8 | 2021-06-22 | 41 | 2021-06-23 | 1 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-06-22 | 33
812 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV | 908.3 | No | 2021-04-23 | 2021-04-29 | 4 | 2021-04-30 | 5 | 2021-05-17 | 11 | 2021-07-07
813 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 240 | No | 2021-04-23 | 2021-05-04 | 7 | 2021-05-17 | 16 | 2021-06-01 | 10 | [15 empty] | 2021-06-01 | 2021-06-10 | 7 | 2021-06-10 | [6 empty] | 2021-04-23 | 2021-06-17 | 38
814 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 240 | No | 2021-04-23 | 2021-05-04 | 7 | 2021-05-21 | 20 | 2021-06-02 | 7 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | [6 empty] | 2021-04-23 | 2021-06-17 | 38
815 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 320 | No | 2021-04-23 | 2021-05-04 | 7 | 2021-06-08 | 31 | 2021-06-23 | 11 | [25 empty] | 2021-04-23
816 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 50 | No | 2021-04-23 | 2021-04-26 | 1 | 2021-04-29 | 4 | 2021-05-20 | 15 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2021-05-24 | 2 |  |  |  |  | 2021-04-23 | 2021-05-10 | 11
817 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 140 | No | 2021-04-23 | 2021-04-27 | 2 | 2021-05-19 | 18 | 2021-06-17 | 20 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | [6 empty] | 2021-04-23
818 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 375 | No | 2021-04-23 | 2021-05-05 | 8 | 2021-05-21 | 20 | 2021-06-28 | 25 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | [6 empty] | 2021-04-23 | 2021-06-03 | 28
819 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 300 | No | 2021-04-23 | 2021-04-26 | 1 | 2021-06-05 | 29 | 2021-06-16 | 7 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16
820 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 30.45 | No | 2021-04-23 | 2021-05-04 | 7 | 2021-05-18 | 17 | 2021-06-03 | 11 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-16 | 9 |  |  |  |  | 2021-04-23 | 2021-05-28 | 25
821 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 38.23 | No | 2021-04-23 | 2021-05-05 | 8 | 2021-05-20 | 19 | 2021-05-24 | 2 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-05-25 | 14
822 | PGE | NEM | EXPNEM | Implementation | Solar PV | 100 | No | 2021-04-23 | 2021-05-05 | 8 | 2021-06-02 | 27 | 2021-06-17 | 11 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-06-29 | 8 |  |  |  |  | 2021-04-23 | 2021-06-15 | 36
823 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 52.72 | No | 2021-04-23 | 2021-05-05 | 8 | 2021-05-26 | 23 | 2021-06-03 | 5 | [15 empty] | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05
824 | PGE | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1781.592 | No | 2021-04-23 | 2021-04-27 | 2 | 2021-06-09 | 32 | [27 empty] | 2021-04-23
825 | PGE | NEM | NEMMT | IA in Progress | Solar PV, Storage | 268 | No | 2021-04-23 | 2021-05-10 | 11 | 2021-06-15 | 36 | 2021-07-07 | 15 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07
826 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 30.45 | No | 2021-04-23 | 2021-04-28 | 3 | 2021-05-24 | 21 | 2021-06-10 | 12 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-06-21 | 7 |  |  |  |  | 2021-04-23 | 2021-05-26 | 23
827 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 210 | No | 2021-04-23 | 2021-04-26 | 1 | 2021-05-12 | 13 | 2021-07-12 | 41 | [15 empty] | 2021-07-12
828 | PGE | NEM | EXPNEM | Implementation | Solar PV | 69.457 | No | 2021-04-23 | 2021-05-05 | 8 | 2021-06-08 | 31 | 2021-06-22 | 10 | [15 empty] | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | 2021-06-29 | 5
829 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 32.505 | No | 2021-04-25 | 2021-05-06 | 8 | 2021-05-21 | 19 | 2021-06-09 | 12 | [25 empty] | 2021-04-25
830 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 210 | No | 2021-04-25 | 2021-04-26 | 0 | 2021-05-12 | 12 | 2021-07-02 | 36 | [15 empty] | 2021-07-02
831 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 41.566 | No | 2021-04-26 | 2021-04-27 | 1 | [29 empty] | 2021-05-07
832 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 58.082 | No | 2021-04-26 | 2021-05-07 | 9 | 2021-05-13 | 13 | 2021-05-17 | 2 | [15 empty] | 2021-05-17 | 2021-05-17 | 0 | 2021-05-17 | [6 empty] | 2021-05-17 | 2021-05-28 | 9
833 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 30.165 | No | 2021-04-26 | 2021-04-27 | 1 | 2021-05-05 | 7 | 2021-05-21 | 12 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21
834 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 530 | No | 2021-04-26 | 2021-05-07 | 9 | 2021-06-08 | 30 | 2021-06-24 | 12 | [15 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-24
835 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 520 | No | 2021-04-26 | 2021-05-10 | 10 | 2021-05-18 | 16 | 2021-06-07 | 13 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [6 empty] | 2021-06-09 | 2021-06-17 | 6
836 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2119.8 | No | 2021-04-26 | 2021-04-29 | 3 | 2021-05-26 | 22 | 2021-07-01 | 25 | [25 empty] | 2021-04-26
837 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 60 | No | 2021-04-26 | 2021-04-27 | 1 | 2021-04-27 | 1 | 2021-05-10 | 9 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | [6 empty] | 2021-04-26 | 2021-05-25 | 21
838 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 40.591 | No | 2021-04-26 | 2021-05-07 | 9 | 2021-05-07 | 9 | 2021-05-24 | 11 | [15 empty] | 2021-05-07 | 2021-05-07 | 0 | 2021-05-07 | 2021-05-11 | 2
839 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 58.738 | No | 2021-04-26 | 2021-04-27 | 1 | 2021-04-27 | 1 | 2021-05-10 | 9 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | [6 empty] | 2021-04-26 | 2021-05-25 | 21
840 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 46.99 | No | 2021-04-26 | 2021-04-27 | 1 | 2021-04-27 | 1 | 2021-05-10 | 9 | [15 empty] | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | [6 empty] | 2021-04-26 | 2021-05-26 | 22
841 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 34.179 | No | 2021-04-27 | 2021-04-28 | 1 | 2021-05-18 | 15 | 2021-06-09 | 15 | 2021-06-09 | 2021-07-08 | 20 | [22 empty] | 2021-04-27 |  |  | 2021-05-25
842 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 65.188 | No | 2021-04-27 | 2021-04-28 | 1 | 2021-06-17 | 36 | 2021-07-09 | 15 | [15 empty] | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12
843 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 192 | No | 2021-04-27 | 2021-05-03 | 4 | 2021-05-10 | 9 | 2021-06-03 | 17 | [15 empty] | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | [6 empty] | 2021-04-27
844 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 | No | 2021-04-27 | 2021-05-03 | 4 | 2021-05-03 | 4 | 2021-05-20 | 13 | [32 empty] | 2021-05-21 | 2021-05-21 | 0 | [15 empty] | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-05-21 |  | 0
845 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 410.518 | No | 2021-04-27 | 2021-05-03 | 4 | 2021-06-16 | 35 | 2021-06-28 | 8 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | [6 empty] | 2021-04-27
846 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 177.127 | No | 2021-04-27 | 2021-05-11 | 10
847 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 276.6 | No | 2021-04-27 | 2021-05-10 | 9 | 2021-05-10 | 9 | [27 empty] | 2021-04-27
848 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 206.358 | No | 2021-04-27 | 2021-05-10 | 9 | [29 empty] | 2021-04-27
849 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 36 | No | 2021-04-27 | 2021-04-28 | 1 | 2021-04-28 | 1 | 2021-05-11 | 9 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | [6 empty] | 2021-04-27 | 2021-05-25 | 20
850 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 36 | No | 2021-04-27 | 2021-04-29 | 2 | 2021-04-29 | 2 | 2021-05-11 | 8 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | [6 empty] | 2021-04-27 | 2021-05-10 | 9
851 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 240 | No | 2021-04-27 | 2021-05-03 | 4 | 2021-05-03 | 4 | 2021-05-20 | 13 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20
852 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 56.869 | No | 2021-04-28 | 2021-05-03 | 3 | 2021-05-19 | 15 | 2021-06-02 | 9 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02
853 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 210 | No | 2021-04-28 | 2021-04-28 | 0 | 2021-05-26 | 20 | 2021-06-30 | 24 | [15 empty] | 2021-06-30 | [9 empty] | 2021-04-28 | 2021-06-21 | 37
854 | PGE | Non-NEM | NEMFC | Study in Progress | FUCE | 262.5 | No | 2021-04-28 | 2021-05-12 | 10 | 2021-07-09 | 50 | [27 empty] | 2021-04-28
855 | PGE | NEM | EXPNEM | Implementation | Solar PV | 34.082 | No | 2021-04-28 | 2021-05-03 | 3 | 2021-05-20 | 16 | 2021-06-10 | 14 | [19 empty] | 2021-06-17 | N/A |  |  |  |  | 2021-04-28
856 | PGE | Non-NEM | Non-Export | Study in Progress | Storage | 929.5 | No | 2021-04-28 | 2021-05-03 | 3 | 2021-05-26 | 20 | 2021-06-17 | 15 | [25 empty] | 2021-04-28 | 2021-05-27 | 21
857 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 2077.348 | No | 2021-04-28 | 2021-05-06 | 6
858 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 | No | 2021-04-28 | 2021-04-29 | 1 | 2021-05-28 | 22 | 2021-06-02 | 2 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-06-08 | 4 | [11 empty] | 2021-07-15 | [17 empty] | 2021-07-15 | 2021-07-15 | 0
859 | PGE | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 2127.363 | No | 2021-04-28 | 2021-05-03 | 3 | 2021-05-26 | 20
860 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 53.84 | No | 2021-04-28 | 2021-04-29 | 1 | 2021-05-06 | 6 | 2021-05-25 | 13 | [15 empty] | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-05-27 | 2 |  |  |  |  | 2021-06-02 | 2021-06-15 | 9
861 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 31.024 | No | 2021-04-29 | 2021-04-29 | 0 | 2021-06-08 | 27 | 2021-06-29 | 15 | [32 empty] | 6/29/2021 | 2021-07-15 | 11 | [15 empty] | 6/29/2021 | 2021-06-29 | 0 | 2021-07-15
862 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 600 | No | 2021-04-29 | 2021-05-11 | 8 | 2021-05-13 | 10 | [5 empty] | 2021-05-13 | 2021-06-11 | 20 | 2021-06-11
863 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 45.653 | No | 2021-04-29 | 2021-05-10 | 7
864 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 187.5 | No | 2021-04-29 | 2021-04-29 | 0 | 2021-05-12 | 9 | 2021-05-28 | 12 | [15 empty] | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | 2021-06-09 | 7 |  |  |  |  | 2021-04-29 | 2021-05-26 | 19
865 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 180 | No | 2021-04-29 | 2021-05-10 | 7 | [29 empty] | 2021-04-29
866 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 58.738 | No | 2021-04-29 | 2021-04-30 | 1 | 2021-04-30 | 1 | 2021-05-11 | 7 | [15 empty] | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11
867 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 37.5 | No | 2021-04-29 | 2021-05-12 | 9 | 2021-05-18 | 13 | 2021-06-03 | 11 | [15 empty] | 2021-06-03 | 2021-06-09 | 4 | 2021-06-09 | 2021-06-11 | 2 |  |  |  |  | 2021-04-29 | 2021-06-16 | 33
868 | PGE | NEM | EXPNEM | Commercial | Solar PV | 50 | No | 2021-04-30 | 2021-04-30 | 0 | 2021-05-06 | 4 | 2021-05-24 | 12 | [15 empty] | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24 | 2021-06-01 | 5 |  |  |  |  | 2021-04-30 | 2021-05-25 | 17 |  |  |  |  | 2021-06-21 | 2021-06-29 | 6 | [15 empty] | 2021-06-21 | 2021-06-22 | 1 | 2021-06-29 | 2021-07-07 |  | 5
869 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 156 | No | 2021-04-30 | 2021-05-04 | 2 | 2021-05-05 | 3 | 2021-05-19 | 10 | 2021-05-19 | 2021-06-23 | 24 | 2021-06-23 | 2021-07-16 | 16 | 2021-07-16 | [18 empty] | 2021-04-30 | 2021-05-25 | 17
870 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 540 | No | 2021-04-30 | 2021-05-03 | 1 | [29 empty] | 2021-04-30
871 | PGE | Non-NEM | Non-Export | Implementation | Solar PV | 65.7 | No | 2021-05-02 | 2021-05-04 | 1 | 2021-05-12 | 7 | 2021-05-13 | 1 | [15 empty] | 2021-05-13 | 2021-05-24 | 7 | 2021-05-24 | 2021-06-29 | 25
872 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 40 | No | 2021-05-03 | 2021-05-11 | 6 | 2021-06-17 | 32 | 2021-06-18 | 1 | [28 empty] | 2021-07-08
873 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 132 | No | 2021-05-03 | 2021-05-06 | 3 | 2021-07-08 | 46
874 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 | No | 2021-05-03 | 2021-05-04 | 1 | 2021-05-04 | 1 | 2021-05-20 | 12 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2021-05-24 | 2 |  |  |  |  | 2021-05-03 | 2021-05-28 | 19
875 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 95.8 | No | 2021-05-04 | 2021-05-13 | 7 | 2021-05-21 | 13 | 2021-06-07 | 10 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [6 empty] | 2021-05-04 | 2021-06-03 | 21
876 | PGE | NEM | EXPNEM | Implementation | Solar PV | 140.742 | No | 2021-05-04 | 2021-05-14 | 8 | 2021-05-14 | 8 | 2021-06-02 | 12 | [15 empty] | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-06-24 | 16 |  |  |  |  | 2021-05-04 | 2021-05-28 | 18 |  |  |  |  | 2021-07-12 | [17 empty] | 2021-07-12 | 2021-07-12 | 0
877 | PGE | Non-NEM | Non-Export | Study in Progress | Storage | 140 | No | 2021-05-04 | 2021-05-04 | 0 | 2021-05-26 | 16 | 2021-06-21 | 17 | 2021-07-16 | [24 empty] | 2021-05-04 | 2021-06-15 | 29
878 | PGE | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 34.963 | No | 2021-05-04 | 2021-05-12 | 6 | 2021-05-12 | 6 | 2021-05-13 | 1 | [32 empty] | 2021-06-08 | [17 empty] | 2021-06-08 | 2021-06-08 | 0
879 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 118.695 | No | 2021-05-04 | 2021-05-05 | 1 | 2021-05-12 | 6 | 2021-05-19 | 5 | [15 empty] | 2021-05-19 | 2021-05-19 | 0 | 2021-05-19 | 2021-06-23 | 24
880 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 420 | No | 2021-05-04 | 2021-05-04 | 0 | 2021-05-26 | 16
881 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 250 | No | 2021-05-04 | 2021-05-10 | 4 | 2021-05-10 | 4 | 2021-06-09 | 21 | [15 empty] | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | [6 empty] | 2021-05-04 |  |  | 2021-05-17
882 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 247.184 | No | 2021-05-04 | 2021-05-18 | 10
883 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 185 | No | 2021-05-04 | 2021-05-18 | 10
884 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 440 | No | 2021-05-04 | 2021-05-05 | 1 | 2021-05-07 | 3 | 2021-07-12 | 44 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12
885 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 49.179 | No | 2021-05-04 | 2021-05-12 | 6 | 2021-05-20 | 12 | 2021-05-20 | 0 | [15 empty] | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2021-05-21 | 1
886 | PGE | NEM | NEMMT | Application Review in Progress | FUCE, Solar PV | 800 | No | 2021-05-05 | 2021-05-19 | 10 | [29 empty] | 2021-05-05
887 | PGE | NEM | EXPNEM | Implementation | Solar PV | 300 | No | 2021-05-05 | 2021-05-14 | 7 | 2021-05-14 | 7 | 2021-06-09 | 17 | [15 empty] | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | 2021-07-01 | 16 |  |  |  |  | 2021-05-05 |  |  | 2021-05-17
888 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 45.45 | No | 2021-05-05 | 2021-05-14 | 7
889 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 954.853 | No | 2021-05-06 | 2021-05-11 | 3 | [29 empty] | 2021-05-06
890 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 86.4 | No | 2021-05-06 | 2021-05-10 | 2 | 2021-06-15 | 27 | 2021-06-29 | 10 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | [6 empty] | 2021-05-06 | 2021-06-24 | 34
891 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 210 | No | 2021-05-06 | 2021-05-07 | 1 | 2021-05-26 | 14
892 | PGE | Non-NEM | NEMFC | Study in Progress | FUCE | 2050 | No | 2021-05-07 | 2021-05-14 | 5 | 2021-05-14 | 5 | 2021-07-14 | 41 | [25 empty] | 2021-05-07 | [12 empty] | 2021-06-29
893 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 490 | No | 2021-05-07 | 2021-05-07 | 0 | 2021-05-26 | 13 | 2021-06-25 | 21 | [25 empty] | 2021-05-07 | 2021-05-27 | 14
894 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 35.23 | No | 2021-05-07 | 2021-05-12 | 3 | 2021-05-12 | 3 | 2021-05-13 | 1
895 | PGE | NEM | VNEMMASH | Withdrawn | Solar PV | 114.8 | No | 2021-05-07 | 2021-05-14 | 5 | [29 empty] | 2021-05-07
896 | PGE | NEM | EXPNEM | IA in Progress | ENGN, Solar PV | 40.175 | No | 2021-05-07 | 2021-05-21 | 10 | 2021-06-16 | 27 | 2021-06-29 | 9 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | [6 empty] | 2021-05-07 | 2021-06-28 | 35
897 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 1187.5 | No | 2021-05-07 | 2021-05-10 | 1 | 2021-05-19 | 8 | 2021-06-30 | 29 | [25 empty] | 2021-05-07 | 2021-06-15 | 26
898 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 61.126 | No | 2021-05-07 | 2021-05-14 | 5 | 2021-06-23 | 32 | 2021-07-15 | 15 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | [6 empty] | 2021-05-07
899 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 | No | 2021-05-07 | 2021-05-12 | 3 | 2021-05-26 | 13 | 2021-06-09 | 9 | [25 empty] | 2021-05-07 | 2021-05-28 | 15 | [26 empty] | 2021-06-09
900 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 31.078 | No | 2021-05-10 | 2021-05-13 | 3
901 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 75.105 | No | 2021-05-10 | 2021-05-10 | 0 | 2021-05-27 | 13 | 2021-06-07 | 6 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [6 empty] | 2021-05-10
902 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 120 | No | 2021-05-10 | 2021-05-10 | 0 | 2021-06-04 | 18 | 2021-06-17 | 9 | 2021-06-17 | [24 empty] | 2021-05-10 | 2021-06-15 | 25
903 | PGE | NEM | SNEM | Application Review in Progress | Solar PV | 1603.8 | No | 2021-05-10 | 2021-05-18 | 6
904 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 50 | No | 2021-05-10 | 2021-05-13 | 3 | 2021-05-20 | 8 | 2021-07-12 | 35 | [15 empty] | 2021-07-12 | 2021-07-15 | 3 | 2021-07-15 | [6 empty] | 2021-05-10 | 2021-06-17 | 27
905 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 171.802 | No | 2021-05-10 | 2021-05-12 | 2 | 2021-05-17 | 5 | 2021-06-09 | 16 | 2021-06-09 | 2021-07-08 | 20 | [22 empty] | 2021-05-10 | 2021-05-26 | 12
906 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 32.76 | No | 2021-05-11 | 2021-05-14 | 3 | 2021-07-16 | 46
907 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 224.234 | No | 2021-05-11 | 2021-05-14 | 3
908 | PGE | NEM | NEMMT | Study in Progress | FUCE, Storage | 306.488 | No | 2021-05-11 | 2021-05-17 | 4 | 2021-06-15 | 24
909 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 51.478 | No | 2021-05-11 | 2021-05-18 | 5 | 2021-06-28 | 33
910 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 39.976 | No | 2021-05-11 | 2021-05-14 | 3 | 2021-05-14 | 3 | [27 empty] | 2021-05-11
911 | PGE | NEM | NEM Paired Storage | Study in Progress | ENGN, Solar PV, Storage | 6080 | No | 2021-05-11 | 2021-05-13 | 2 | 2021-05-26 | 11 | [5 empty] | 2021-05-26 | 2021-06-25 | 21 | 2021-06-25 | [5 empty] | 7/12/2021 | 2021-07-12 | 0 | [10 empty] | 2021-05-11
912 | PGE | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 2360 | No | 2021-05-11 | 2021-05-13 | 2 | 2021-05-26 | 11 | [27 empty] | 2021-05-11
913 | PGE | NEM | EXPNEM | Implementation | Solar PV | 99.9 | No | 2021-05-12 | 2021-05-19 | 5 | 2021-05-20 | 6 | 2021-05-25 | 3 | [15 empty] | 2021-06-04 | 2021-06-04 | 0 | 2021-06-04 | 2021-06-07 | 1 |  |  |  |  | 2021-05-12 | 2021-05-28 | 12
914 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 57.054 | No | 2021-05-12 | 2021-05-21 | 7 | 2021-06-17 | 25 | 2021-06-30 | 9 | [15 empty] | 2021-06-30
915 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 30.402 | No | 2021-05-12 | 2021-05-26 | 10 | 2021-06-08 | 18 | 2021-06-24 | 12 | [15 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-24 | [6 empty] | 2021-05-12 | 2021-06-15 | 23
916 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 125 | No | 2021-05-12 | 2021-05-14 | 2 | 2021-05-25 | 9 | 2021-06-10 | 11 | [15 empty] | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-06-14 | 2
917 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 199.172 | No | 2021-05-12 | 2021-05-24 | 8 | 2021-06-07 | 17 | 2021-06-16 | 7 | [15 empty] | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | [6 empty] | 2021-05-12 | 2021-06-16 | 24
918 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 180 | No | 2021-05-12 | 2021-05-17 | 3 | 2021-05-17 | 3 | [27 empty] | 2021-05-12
919 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 900 | No | 2021-05-12 | 2021-05-17 | 3 | 2021-06-23 | 29 | [5 empty] | 2021-07-05
920 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 280 | No | 2021-05-12 | 2021-05-13 | 1 | 2021-06-02 | 14 | 2021-06-21 | 13
921 | PGE | NEM | VNEM | Study in Progress | Solar PV, Storage | 43.53 | No | 2021-05-12 | 2021-05-27 | 11 | 2021-07-01 | 35
922 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 353.35 | No | 2021-05-13 | 2021-05-27 | 10
923 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 247.518 | No | 2021-05-13 | 2021-05-17 | 2 | 2021-05-17 | 2 | [27 empty] | 2021-05-13 | 2021-05-28 | 11
924 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 516.6 | No | 2021-05-13 | 2021-05-27 | 10 | 2021-06-19 | 25 | 2021-07-12 | 14 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [9 empty] | 2021-06-29 | 2021-07-12 | 2021-07-12 | 8
925 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 19692.28 | No | 2021-05-13 | 2021-05-13 | 0 | 2021-06-18 | 25
926 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 1212 | No | 2021-05-13 | 2021-05-26 | 9 | 2021-06-09 | 18 | [5 empty] | 2021-06-14 | 2021-07-12 | 19 | 2021-07-12 | 2021-07-12 | 0 |  |  |  | 2021-07-12 | 2021-07-12 | 0 | [10 empty] | 2021-05-13
927 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 388.8 | No | 2021-05-05 | 2021-05-14 | 7
928 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 98.938 | No | 2021-05-13 | 2021-05-27 | 10
929 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 644.705 | No | 2021-05-13 | 2021-05-18 | 3 | 2021-05-21 | 6 | 2021-06-04 | 9 | 2021-06-04 | 2021-07-02 | 20 | [12 empty] | 2021-07-02 | 2021-07-06 | 1 | 2021-07-06 | 2021-07-13 | 5 |  |  |  |  | 2021-05-13
930 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 50.23 | No | 2021-05-13 | 2021-05-18 | 3 | 2021-05-27 | 10 | 2021-06-01 | 2 | [32 empty] | 2021-06-01 | 2021-06-01 | 0 | [15 empty] | 2021-06-01 |  |  | 2021-06-01 | 2021-06-01 |  | 0
931 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 72 | No | 2021-05-13 | 2021-05-27 | 10
932 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 641.076 | No | 2021-05-14 | 2021-05-18 | 2 | 2021-05-18 | 2 | [27 empty] | 2021-05-14
933 | PGE | Non-NEM | Non-Export | Withdrawn | Solar PV | 44.66 | No | 2021-05-14 | 2021-05-17 | 1 | 2021-06-02 | 12
934 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 985 | No | 2021-05-14 | 2021-05-17 | 1 | 2021-05-26 | 8
935 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 4252.742 | No | 2021-05-14 | 2021-05-17 | 1 | 2021-05-26 | 8 | [5 empty] | 2021-06-14
936 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 865.259 | No | 2021-05-14 | 2021-05-28 | 10 | 2021-06-14 | 20 | 2021-07-01 | 13 | 2021-07-01 | [27 empty] | 2021-07-09
937 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 250 | No | 2021-05-14 | 2021-05-24 | 6 | 2021-05-28 | 10 | 2021-06-07 | 5 | [15 empty] | 2021-06-07 | 2021-06-16 | 7 | 2021-06-16 | [6 empty] | 2021-05-14 | 2021-06-15 | 21
938 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 480 | No | 2021-05-14 | 2021-06-14 | 20 | 2021-07-09 | 38 | [27 empty] | 2021-07-09
939 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 40.75 | No | 2021-05-17 | 2021-05-19 | 2
940 | PGE | NEM | NEMMT | Study in Progress | ENGN, Solar PV, Storage | 985 | No | 2021-05-17 | 2021-05-24 | 5 | 2021-05-24 | 5 | [5 empty] | 2021-05-24 | 2021-06-15 | 15 | 2021-06-15 | 2021-07-01 | 12 |  |  |  | 2021-07-01 | 2021-07-01 | 0
941 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 151.403 | No | 2021-05-17 | 2021-05-20 | 3 | 2021-06-22 | 25 | 2021-07-12 | 13 | 2021-07-12 | [24 empty] | 2021-05-17 | 2021-06-16 | 21
942 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 75 | No | 2021-05-17 | 2021-05-18 | 1 | 2021-05-18 | 1 | 2021-06-15 | 19 | [15 empty] | 2021-06-15 | 2021-06-17 | 2 | 2021-06-17 | 2021-06-17 | 0 |  |  |  |  | 2021-05-17 | 2021-05-28 | 9
943 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 50 | No | 2021-05-18 | 2021-05-20 | 2
944 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 47.351 | No | 2021-05-18 | 2021-05-18 | 0 | 2021-06-05 | 12 | 2021-06-21 | 10 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-25 | 4
945 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 64.643 | No | 2021-05-18 | 2021-05-25 | 5 | 2021-06-29 | 29 | [27 empty] | 2021-05-18 | 2021-06-16 | 20 |  | 2021-06-29 | 2021-06-29 | 0
946 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 53.25 | No | 2021-05-18 | 2021-05-25 | 5 | 2021-06-30 | 30 | [27 empty] | 2021-05-18 | 2021-06-16 | 20 |  | 2021-06-30 | 2021-06-30 | 0
947 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 41.375 | No | 2021-05-18 | 2021-06-02 | 10 | 2021-06-30 | 30 | [27 empty] | 2021-05-18
948 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 55.628 | No | 2021-05-18 | 2021-06-02 | 10 | 2021-06-30 | 30 | [27 empty] | 2021-05-18
949 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 70.798 | No | 2021-05-18 | 2021-06-01 | 9 | 2021-06-29 | 29 | [27 empty] | 2021-05-18
950 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 54.229 | No | 2021-05-18 | 2021-06-02 | 10 | 2021-06-29 | 29 | [27 empty] | 2021-05-18
951 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 74.573 | No | 2021-05-18 | 2021-06-02 | 10 | 2021-06-28 | 28 | [27 empty] | 2021-05-18 |  |  | 2021-06-16
952 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 263.872 | No | 2021-05-18 | 2021-05-20 | 2 | 2021-05-26 | 6 | 2021-06-07 | 7 | [15 empty] | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07
953 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 99.9 | No | 2021-05-18 | 2021-05-20 | 2
954 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 630 | No | 2021-05-18 | 2021-06-02 | 10 | 2021-06-02 | 10 | 2021-07-13 | 28 | [19 empty] | 2021-06-30 | N/A |  |  |  |  | 2021-05-18 | 2021-06-09 | 15
955 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 53.289 | No | 2021-05-19 | 2021-06-17 | 20 | 2021-06-18 | 21 | 2021-07-01 | 9 | [15 empty] | 2021-07-01 | 2021-07-07 | 3 | 2021-07-07 | 2021-07-07 | 0 |  |  |  |  | 2021-05-19 | 2021-06-07 | 12
956 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 37.306 | No | 2021-05-19 | 2021-05-20 | 1 | 2021-06-03 | 10 | 2021-06-21 | 12 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21
957 | PGE | NEM | EXPNEM | Implementation | Solar PV | 31.024 | No | 2021-05-19 | 2021-05-27 | 6 | 2021-06-25 | 26 | 2021-07-12 | 10 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | 2021-07-12 | 0
958 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 80.637 | No | 2021-05-19 | 2021-05-21 | 2 | 2021-06-05 | 11 | 2021-06-23 | 12 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-07-08 | 10 | [11 empty] | 2021-07-13 | [17 empty] | 2021-07-13 | 2021-07-13 | 0
959 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 | No | 2021-05-19 | 2021-06-04 | 11 | 2021-06-21 | 22 | 2021-07-12 | 14 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [6 empty] | 2021-05-19
960 | PGE | Non-NEM | Non-Export | Application Review in Progress | Storage | 929.5 | No | 2021-05-19 | 2021-05-20 | 1 | 2021-06-23 | 24
961 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 74.731 | No | 2021-05-20 | 2021-05-24 | 2 | 2021-06-01 | 7 | 2021-06-15 | 10 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-15 | [6 empty] | 2021-05-20 | 2021-06-15 | 17
962 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 248.292 | No | 2021-05-20 | 2021-06-03 | 9 | [29 empty] | 2021-05-20
963 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.53 | No | 2021-05-20 | 2021-05-24 | 2 | 2021-06-15 | 17 | 2021-07-01 | 12 | [15 empty] | 2021-07-01 | 2021-07-02 | 1 | 2021-07-02 | [6 empty] | 2021-05-20 | 2021-06-24 | 24
964 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 54.72 | No | 2021-05-20 | 2021-05-24 | 2 | 2021-06-17 | 19 | [27 empty] | 2021-05-20 | 2021-06-07 | 11
965 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 508.95 | No | 2021-05-20 | 2021-05-20 | 0 | 2021-06-16 | 18
966 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 | No | 2021-05-20 | 2021-05-20 | 0
967 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 | No | 2021-05-20 | 2021-05-24 | 2 | 2021-06-03 | 9 | 2021-06-17 | 10 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-06-17 | 0 |  |  |  |  | 2021-05-20 | 2021-06-15 | 17
968 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 57.42 | No | 2021-05-20 | 2021-05-24 | 2 | 2021-06-05 | 10
969 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 113.3 | No | 2021-05-20 | 2021-05-27 | 5
970 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 99.869 | No | 2021-05-20 | 2021-05-24 | 2 | 2021-06-01 | 7 | 2021-06-17 | 12 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-06-30 | 9 |  |  |  |  | 2021-05-20 | 2021-06-16 | 18
971 | PGE | NEM | NEMMT | Study in Progress | Solar PV | 250 | No | 2021-05-20 | 2021-06-05 | 10 | [29 empty] | 2021-05-20 |  |  | 2021-07-14
972 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 162.5 | No | 2021-05-20 | 2021-06-01 | 7 | 2021-06-01 | 7 | 2021-07-12 | 28 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [6 empty] | 2021-06-24 | 2021-07-13 | 12
973 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 108.67 | No | 2021-05-20 | 2021-06-01 | 7 | 2021-06-01 | 7
974 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 59.519 | No | 2021-05-21 | 2021-05-25 | 2 | 2021-06-22 | 21 | 2021-07-08 | 11 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-16 | 6 |  |  |  |  | 2021-05-21 | 2021-06-07 | 10
975 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 36.511 | No | 2021-05-21 | 2021-06-03 | 8 | 2021-07-09 | 33
976 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 100 | No | 2021-05-21 | 2021-06-02 | 7 | 2021-06-29 | 26 | [27 empty] | 2021-05-21
977 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 659.212 | No | 2021-05-21 | 2021-06-02 | 7 | [29 empty] | 2021-05-21
978 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 150 | No | 2021-05-21 | 2021-06-03 | 8 | 2021-06-17 | 18 | 2021-07-02 | 11 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | [6 empty] | 2021-05-21 |  |  | 2021-07-01
979 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.408 | No | 2021-05-21 | 2021-05-24 | 1 | 2021-06-07 | 10 | 2021-06-09 | 2 | [32 empty] | 2021-06-10 | 2021-06-10 | 0 | [15 empty] | 2021-06-10 |  |  | 2021-06-10 | 2021-06-10 |  | 0
980 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 150 | No | 2021-05-21 | 2021-05-28 | 5 | 2021-05-28 | 5 | 2021-06-15 | 11 | 2021-06-15 | 2021-07-14 | 20 | [12 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | [6 empty] | 2021-05-21 | 2021-06-15 | 16
981 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 90.925 | No | 2021-05-21 | 2021-06-01 | 6 | 2021-06-07 | 10 | 2021-06-21 | 10 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-30 | 7 |  |  |  |  | 2021-05-21 | 2021-06-15 | 16
982 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 31.305 | No | 2021-05-21 | 2021-05-25 | 2 | 2021-06-08 | 11 | 2021-06-08 | 0 | [25 empty] | 2021-05-21 | [6 empty] | 2021-07-14 | 2021-07-14 | 0 | [15 empty] | 2021-07-14 | 2021-07-01 | 8 | 2021-07-14 | 2021-07-14 |  | 0
983 | PGE | NEM | SNEM | Study in Progress | Solar PV | 43.2 | No | 2021-05-21 | 2021-06-04 | 9 | 2021-07-14 | 36 | 2021-07-14 | 0
984 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 250 | No | 2021-05-21 | 2021-06-04 | 9 | 2021-06-15 | 16 | 2021-07-01 | 12 | 2021-07-01 | [24 empty] | 2021-05-21 |  |  | 2021-07-09
985 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 37.598 | No | 2021-05-21 | 2021-06-07 | 10 | 2021-07-06 | 30 | [27 empty] | 2021-05-21
986 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 | No | 2021-05-21 | 2021-05-25 | 2 | 2021-05-28 | 5 | 2021-06-02 | 2 | [19 empty] | 2021-06-15 | N/A | [11 empty] | 2021-06-15 | 2021-06-15 | 0 | [15 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-15 | 2021-06-15 |  | 0
987 | PGE | NEM | EXPNEM | Study in Progress | Solar PV, WIND | 86.681 | No | 2021-05-21 | 2021-06-05 | 9 | 2021-07-09 | 33
988 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 72.55 | No | 2021-05-21 | 2021-06-07 | 10 | [29 empty] | 2021-05-21
989 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 63.892 | No | 2021-05-21 | 2021-06-01 | 6 | 2021-06-15 | 16 | 2021-06-23 | 6 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23
990 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 72.22 | No | 2021-05-21 | 2021-06-01 | 6 | 2021-06-16 | 17 | 2021-07-01 | 11 | [15 empty] | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01
991 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 72.55 | No | 2021-05-21 | 2021-06-04 | 9 | [29 empty] | 2021-05-21
992 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 31.752 | No | 2021-05-21 | 2021-06-02 | 7 | 2021-06-02 | 7 | 2021-07-12 | 27 | [19 empty] | 2021-05-21 | N/A | [11 empty] | 2021-07-12 | [17 empty] | 2021-07-12 | 2021-07-12 | 0
993 | PGE | Non-NEM | Continuous Uncompensated Export | Application Accepted | Solar PV | 271.284 | No | 2021-05-21 | 2021-05-24 | 1 | 2021-06-02 | 7 | 2021-07-14 | 29
994 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 72.55 | No | 2021-05-21 | 2021-06-04 | 9 | [29 empty] | 2021-05-21
995 | PGE | NEM | NEM Paired Storage | Study in Progress | ENGN, Solar PV, Storage | 1792 | No | 2021-05-21 | 2021-05-28 | 5 | 2021-06-03 | 8 | [27 empty] | 2021-05-21
996 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 35.116 | No | 2021-05-24 | 2021-05-25 | 1 | 2021-06-09 | 11 | 2021-06-10 | 1 | [32 empty] | 2021-06-10 | 2021-06-10 | 0 | [15 empty] | 2021-06-10 |  |  | 2021-06-10 | 2021-06-10 |  | 0
997 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 470 | No | 2021-05-24 | 2021-06-07 | 9 | [7 empty] | 2021-06-08 | 2021-07-01 | 17 | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01 |  |  | 2021-07-01 | 2021-07-01 | 0 | [10 empty] | 2021-05-24 |  |  | 2021-06-17
998 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 34.8 | No | 2021-05-24 | 2021-06-07 | 9
999 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 249.314 | No | 2021-05-24 | 2021-06-03 | 7 | [29 empty] | 2021-05-24 | 2021-06-15 | 15
1000 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 100 | No | 2021-05-24 | 2021-06-04 | 8 | 2021-06-09 | 11 | 2021-06-15 | 4 | 2021-06-15 | 2021-07-14 | 20 | 2021-07-14 | [21 empty] | 2021-05-24 | 2021-06-17 | 17
1001 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 90.477 | No | 2021-05-24 | 2021-06-02 | 6 | [29 empty] | 2021-05-24 | 2021-06-15 | 15
1002 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 | No | 2021-05-24 | 2021-06-08 | 10 | 2021-06-18 | 18 | 2021-07-08 | 13 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08
1003 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 | No | 2021-05-24 | 2021-06-04 | 8
1004 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 40.269 | No | 2021-05-24 | 2021-06-02 | 6 | 2021-07-12 | 33
1005 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 1560 | No | 2021-05-24 | 2021-05-25 | 1 | 2021-06-02 | 6 | [27 empty] | 2021-05-24
1006 | PGE | NEM | EXPNEM | Implementation | Solar PV | 221.358 | No | 2021-05-25 | 2021-06-08 | 9 | 2021-06-15 | 14 | 2021-07-02 | 13 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-07-08 | 3 |  |  |  |  | 2021-05-25
1007 | PGE | NEM | EXPNEM | Implementation | Solar PV | 216 | No | 2021-05-25 | 2021-06-08 | 9 | 2021-06-15 | 14 | 2021-07-06 | 14 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-07-06 | 0 |  |  |  |  | 2021-05-25 |  |  | 2021-07-09
1008 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 85.259 | No | 2021-05-25 | 2021-06-04 | 7 | 2021-06-09 | 10 | 2021-06-21 | 8 | [15 empty] | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-24 | 3 |  |  |  |  | 2021-05-25 | 2021-06-17 | 16
1009 | PGE | NEM | EXPNEM | Implementation | Solar PV | 60 | No | 2021-05-25 | 2021-06-08 | 9 | 2021-06-09 | 10 | 2021-06-18 | 7 | [15 empty] | 2021-06-18 | 2021-06-25 | 5 | 2021-06-25 | 2021-06-28 | 1 |  |  |  |  | 2021-05-25 | 2021-06-24 | 21
1010 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 250 | No | 2021-05-25 | 2021-06-08 | 9 | 2021-06-08 | 9 | 2021-06-23 | 11 | [15 empty] | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23
1011 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 30.402 | No | 2021-05-25 | 2021-06-11 | 12 | 2021-06-25 | 22 | [27 empty] | 2021-05-25
1012 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 34.179 | No | 2021-05-25 | 2021-06-11 | 12 | 2021-06-25 | 22 | [27 empty] | 2021-05-25
1013 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 210 | No | 2021-05-26 | 2021-05-27 | 1 | 2021-06-09 | 9
1014 | PGE | Non-NEM | Non-Export | Application Accepted | Solar PV, Storage | 114.26 | No | 2021-05-25 | 2021-05-26 | 1 | 2021-06-16 | 15
1015 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 1466.6 | No | 2021-05-26 | 2021-06-04 | 6 | [29 empty] | 2021-05-26
1016 | PGE | Non-NEM | Non-Export | IA in Progress | Storage | 140 | No | 2021-05-26 | 2021-05-27 | 1 | 2021-06-23 | 19 | 2021-07-15 | 15 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15
1017 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 750 | No | 2021-05-26 | 2021-06-09 | 9
1018 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 41.246 | No | 2021-05-26 | 2021-06-10 | 10
1019 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 36.905 | No | 2021-05-26 | 2021-06-10 | 10
1020 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 55.756 | No | 2021-05-26 | 2021-06-10 | 10
1021 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 32.125 | No | 2021-05-26 | 2021-06-04 | 6
1022 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 280 | No | 2021-05-26 | 2021-05-27 | 1 | 2021-06-30 | 24 | [27 empty] | 2021-05-26
1023 | PGE | Non-NEM | Non-Export | Application Accepted | ENGN, Storage | 290 | No | 2021-05-27 | 2021-05-27 | 0 | 2021-06-23 | 18 | [27 empty] | 2021-05-27 | 2021-07-07 | 27
1024 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.395 | No | 2021-05-27 | 2021-06-01 | 2 | 2021-06-04 | 5 | 2021-06-08 | 2 | [32 empty] | 2021-06-08 | 2021-06-08 | 0 | [15 empty] | 2021-06-08 |  |  | 2021-06-08 | 2021-06-08 |  | 0
1025 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 37.758 | No | 2021-05-27 | 2021-06-11 | 10 | [29 empty] | 2021-05-27
1026 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.232 | No | 2021-05-27 | 2021-06-01 | 2 | 2021-07-13 | 31 | 2021-07-15 | 2 | [32 empty] | 2021-07-16 | 2021-07-16 | 0 | [15 empty] | 2021-07-16 |  |  | 2021-07-16 | 2021-07-16 |  | 0
1027 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.2 | No | 2021-05-27 | 2021-06-07 | 6 | [29 empty] | 2021-05-27
1028 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 35.187 | No | 2021-05-28 | 2021-06-14 | 10 | 2021-06-17 | 13 | 2021-07-07 | 13 | [15 empty] | 2021-07-07 | [9 empty] | 2021-05-28 | 2021-07-02 | 24
1029 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 90 | No | 2021-05-28 | 2021-06-08 | 6 | 2021-07-02 | 24
1030 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 98.329 | No | 2021-05-28 | 2021-06-23 | 17 | [29 empty] | 2021-05-28
1031 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 36.54 | No | 2021-05-28 | 2021-06-11 | 9 | [29 empty] | 2021-05-28
1032 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 35.356 | No | 2021-05-28 | 2021-06-09 | 7 | [29 empty] | 2021-05-28
1033 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 66.6 | No | 2021-05-28 | 2021-06-09 | 7 | 2021-07-02 | 24
1034 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 36.796 | No | 2021-05-28 | 2021-06-02 | 2 | 2021-06-02 | 2 | 2021-06-07 | 3 | [54 empty] | 2021-06-07
1035 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.116 | No | 2021-05-30 | 2021-06-02 | 1 | 2021-07-12 | 28 | 2021-07-13 | 1 | [32 empty] | 2021-07-14 | 2021-07-14 | 0 | [15 empty] | 2021-07-14 |  |  | 2021-07-14 | 2021-07-14 |  | 0
1036 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 34.179 | No | 2021-06-01 | 2021-06-15 | 10 | [29 empty] | 2021-06-01
1037 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 34.179 | No | 2021-06-01 | 2021-06-15 | 10 | [29 empty] | 2021-06-01
1038 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 42.472 | No | 2021-06-01 | 2021-06-09 | 6 | [29 empty] | 2021-06-01
1039 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 696 | No | 2021-06-01 | 2021-06-15 | 10
1040 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 226.751 | No | 2021-06-01 | 2021-06-14 | 9 | 2021-06-30 | 21 | [27 empty] | 2021-06-01
1041 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 36.186 | No | 2021-06-01 | 2021-06-09 | 6 | 2021-06-28 | 19 | 2021-07-08 | 7 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | [6 empty] | 2021-06-01
1042 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.165 | No | 2021-06-01 | 2021-06-03 | 2
1043 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.657 | No | 2021-06-01 | 2021-06-03 | 2 | 2021-06-15 | 10 | 2021-06-16 | 1 | [32 empty] | 2021-06-16 | 2021-06-16 | 0 | [15 empty] | 2021-06-16 |  |  | 2021-06-16 | 2021-06-16 |  | 0
1044 | PGE | NEM | EXPNEM | Implementation | Solar PV | 75.777 | No | 2021-06-02 | 2021-06-14 | 8 | 2021-06-14 | 8 | 2021-07-02 | 14 | [15 empty] | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-07-02 | 0 |  |  |  |  | 2021-06-02 |  |  | 2021-07-09
1045 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 | No | 2021-06-02 | 2021-06-14 | 8 | 2021-06-16 | 10 | 2021-06-28 | 8 | [15 empty] | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | [6 empty] | 2021-06-02 | 2021-06-28 | 18
1046 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 229.645 | No | 2021-06-02 | 2021-06-09 | 5 | 2021-06-09 | 5 | 2021-06-24 | 11 | 2021-06-24 | 2021-07-06 | 7 | [12 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-07-08 | 2
1047 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 56.965 | No | 2021-06-02 | 2021-06-11 | 7 | 2021-06-11 | 7 | 2021-07-02 | 15 | [15 empty] | 2021-07-02 | [9 empty] | 2021-06-02
1048 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 72.547 | No | 2021-06-02 | 2021-06-09 | 5 | [29 empty] | 2021-06-02
1049 | PGE | Non-NEM | Non-Export | Withdrawn | Solar PV | 50 | No | 2021-06-02 | 2021-06-02 | 0
1050 | PGE | Non-NEM | RESBCT | Study in Progress | Solar PV | 2500 | No | 2021-06-02 | 2021-06-04 | 2 | 2021-06-16 | 10 | [5 empty] | 2021-06-16 | 2021-07-12 | 17 | 2021-07-12 | 2021-07-12 | 0 |  |  |  | 2021-07-12 | 2021-07-12 | 0
1051 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 60.868 | No | 2021-06-02 | 2021-06-10 | 6 | 2021-06-22 | 14 | 2021-07-14 | 15 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14
1052 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.3 | No | 2021-06-02 | 2021-06-10 | 6
1053 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 40.002 | No | 2021-06-02 | 2021-06-10 | 6
1054 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 277.81 | No | 2021-06-03 | 2021-06-17 | 10 | [29 empty] | 2021-06-03
1055 | PGE | NEM | SNEM | Application Submitted | Solar PV | 168.227 | No | 2021-06-03 | 2021-06-15 | 8
1056 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 57.357 | No | 2021-06-03 | 2021-06-17 | 10 | 2021-07-09 | 25
1057 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 38.78 | No | 2021-06-03 | 2021-06-11 | 6 | 2021-06-15 | 8 | 2021-07-06 | 14 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06
1058 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 172.8 | No | 2021-06-03 | 2021-06-17 | 10
1059 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.29 | No | 2021-06-03 | 2021-06-07 | 2
1060 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 35.005 | No | 2021-06-03 | 2021-06-11 | 6 | 2021-06-16 | 9 | 2021-07-08 | 15 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08
1061 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 600 | No | 2021-06-03 | 2021-06-11 | 6
1062 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 312.5 | No | 2021-06-03 | 2021-06-11 | 6 | [29 empty] | 2021-06-03
1063 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 54.494 | No | 2021-06-03 | 2021-06-08 | 3 | 2021-06-16 | 9 | 2021-07-02 | 12
1064 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 | No | 2021-06-03 | 2021-06-11 | 6 | 2021-06-11 | 6 | 2021-06-17 | 4 | [15 empty] | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-07-16 | 20
1065 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 140 | No | 2021-06-04 | 2021-06-04 | 0 | 2021-06-30 | 18 | [27 empty] | 2021-06-04
1066 | PGE | NEM | EXPNEM | Study in Progress | ENGN | 1000 | No | 2021-06-04 | 2021-06-22 | 12 | 2021-06-22 | 12 | 2021-07-09 | 12
1067 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 44.37 | No | 2021-06-04 | 2021-06-12 | 5
1068 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 266.145 | No | 2021-06-04 | 2021-06-15 | 7 | 2021-07-08 | 23
1069 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 140 | No | 2021-06-04 | 2021-06-04 | 0 | 2021-06-30 | 18 | [27 empty] | 2021-06-04 | 2021-07-14 | 27
1070 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 48.363 | No | 2021-06-04 | 2021-06-18 | 10
1071 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 57.71 | No | 2021-06-04 | 2021-06-18 | 10
1072 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 52.163 | No | 2021-06-04 | 2021-06-18 | 10
1073 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 32.436 | No | 2021-06-04 | 2021-06-18 | 10 | 2021-06-25 | 15
1074 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 52.163 | No | 2021-06-04 | 2021-06-18 | 10 | 2021-06-25 | 15
1075 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.791 | No | 2021-06-04 | 2021-06-12 | 5 | 2021-06-16 | 8 | 2021-07-06 | 13 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06
1076 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 42.725 | No | 2021-06-06 | 2021-06-09 | 2
1077 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 38.78 | No | 2021-06-07 | 2021-06-10 | 3
1078 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 162.5 | No | 2021-06-07 | 2021-06-16 | 7 | 2021-06-16 | 7 | [27 empty] | 2021-06-07
1079 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 55.575 | No | 2021-06-07 | 2021-06-12 | 4 | 2021-06-16 | 7 | 2021-07-07 | 14 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | [6 empty] | 2021-06-07 | 2021-06-18 | 9
1080 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 50 | No | 2021-06-07 | 2021-06-12 | 4
1081 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 98.286 | No | 2021-06-07 | 2021-06-12 | 4
1082 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.2 | No | 2021-06-07 | 2021-06-12 | 4
1083 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 900 | No | 2021-06-07 | 2021-06-12 | 4
1084 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 58.63 | No | 2021-06-08 | 2021-06-12 | 3 | [29 empty] | 2021-06-08
1085 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 50 | No | 2021-06-08 | 2021-06-15 | 5 | 2021-06-15 | 5 | 2021-06-18 | 3 | [15 empty] | 2021-06-18 | 2021-06-18 | 0 | 2021-06-18 | 2021-06-22 | 2 |  |  |  |  | 2021-06-08
1086 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 38.138 | No | 2021-06-08 | 2021-07-01 | 17
1087 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 133.3 | No | 2021-06-08 | 2021-06-15 | 5 | 2021-06-15 | 5
1088 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 | No | 2021-06-08 | 2021-06-16 | 6 | 2021-06-22 | 10 | 2021-07-12 | 13 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [6 empty] | 2021-06-08
1089 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 540 | No | 2021-06-08 | 2021-06-18 | 8 | 2021-06-22 | 10 | 2021-06-29 | 5 | 2021-06-29
1090 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 1200 | No | 2021-06-09 | 2021-06-09 | 0 | [29 empty] | 2021-06-09
1091 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 86.4 | No | 2021-06-09 | 2021-06-15 | 4 | 2021-06-28 | 13 | 2021-07-15 | 12 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15
1092 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 57.71 | No | 2021-06-09 | 2021-06-16 | 5
1093 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 34.179 | No | 2021-06-09 | 2021-06-16 | 5
1094 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 1680 | No | 2021-06-09 | 2021-06-10 | 1 | 2021-06-16 | 5 | [27 empty] | 2021-07-08
1095 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 828.528 | No | 2021-06-10 | 2021-06-23 | 9 | [29 empty] | 2021-06-10
1096 | PGE | NEM | NEMMT | Application Review in Progress | ENGN, Solar PV | 625 | No | 2021-06-10 | 2021-06-24 | 10
1097 | PGE | NEM | NEMMT | Application Review in Progress | ENGN, Solar PV | 625 | No | 2021-06-10 | 2021-06-24 | 10
1098 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 60 | No | 2021-06-10 | 2021-06-16 | 4 | 2021-06-29 | 13 | 2021-07-13 | 9 | [15 empty] | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13
1099 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 136 | No | 2021-06-10 | 2021-06-16 | 4 | 2021-06-18 | 6 | 2021-06-29 | 7 | [15 empty] | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | [6 empty] | 2021-06-10 | 2021-07-09 | 20
1100 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 44.415 | No | 2021-06-10 | 2021-06-16 | 4 | [29 empty] | 2021-06-10
1101 | PGE | NEM | NEMMT | Study in Progress | Solar PV, Storage | 8248.335 | No | 2021-06-10 | 2021-06-14 | 2 | 2021-06-23 | 9 | [5 empty] | 2021-07-15 | [21 empty] | 2021-06-10 | 2021-07-08 | 19
1102 | PGE | NEM | VNEM | Study in Progress | Solar PV | 520.277 | No | 2021-06-11 | 2021-06-21 | 6 | 2021-07-09 | 19 | [27 empty] | 2021-06-11
1103 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.75 | No | 2021-06-11 | 2021-06-14 | 1
1104 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 49.035 | No | 2021-06-11 | 2021-06-21 | 6
1105 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 76.036 | No | 2021-06-11 | 2021-06-25 | 10 | 2021-06-30 | 13 | [27 empty] | 2021-06-11 | 2021-07-08 | 18
1106 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 76.036 | No | 2021-06-11 | 2021-06-25 | 10 | 2021-06-30 | 13 | [27 empty] | 2021-06-11 | 2021-07-08 | 18
1107 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 75.4 | No | 2021-06-11 | 2021-06-17 | 4 | 2021-07-12 | 20
1108 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 76.006 | No | 2021-06-11 | 2021-06-25 | 10 | 2021-06-30 | 13 | [27 empty] | 2021-06-11 | 2021-07-08 | 18
1109 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 200 | No | 2021-06-11 | 2021-06-21 | 6
1110 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 64.643 | No | 2021-06-11 | 2021-06-25 | 10 | 2021-06-30 | 13 | [27 empty] | 2021-06-11
1111 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 162.5 | No | 2021-06-11 | 2021-06-22 | 7 | [29 empty] | 2021-06-11
1112 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 500 | No | 2021-06-11 | 2021-06-21 | 6 | 2021-07-08 | 18
1113 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 400 | No | 2021-06-11 | 2021-06-17 | 4 | 2021-06-17 | 4 | 2021-07-09 | 15 | [15 empty] | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12
1114 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 100 | No | 2021-06-11 | 2021-06-17 | 4 | 2021-06-18 | 5
1115 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 35.15 | No | 2021-06-13 | 2021-06-15 | 1 | 2021-07-14 | 21 | [17 empty] | 2021-06-15 | 2021-06-15 | 0 | 2021-06-15 | 2021-07-14 | 20
1116 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.232 | No | 2021-06-14 | 2021-06-16 | 2 | 2021-07-01 | 13 | 2021-07-06 | 2 | [19 empty] | 2021-06-14 | N/A | [11 empty] | 2021-07-06 | 2021-07-06 | 0 | [15 empty] | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-07-06 |  | 0
1117 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 75.463 | No | 2021-06-14 | 2021-06-17 | 3 | 2021-06-17 | 3 | 2021-07-09 | 15 | [15 empty] | 2021-07-09 | 2021-07-12 | 1 | 2021-07-12 | [6 empty] | 2021-06-14 | 2021-07-09 | 18
1118 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 145.8 | No | 2021-06-14 | 2021-06-22 | 6 | 2021-06-22 | 6 | [27 empty] | 2021-06-14
1119 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 40.75 | No | 2021-06-14 | 2021-06-16 | 2
1120 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 109.873 | No | 2021-06-14 | 2021-06-17 | 3 | 2021-07-07 | 16 | [27 empty] | 2021-06-14
1121 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 80.24 | No | 2021-06-14 | 2021-06-17 | 3 | 2021-06-17 | 3 | [27 empty] | 2021-06-14 | 2021-07-12 | 19
1122 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 66.6 | No | 2021-06-14 | 2021-06-18 | 4 | 2021-06-18 | 4 | [27 empty] | 2021-06-14
1123 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 89.187 | No | 2021-06-14 | 2021-06-17 | 3 | 2021-06-21 | 5 | [27 empty] | 2021-06-14 | 2021-07-12 | 19
1124 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 34.921 | No | 2021-06-14 | 2021-06-22 | 6 | 2021-06-23 | 7
1125 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 82.82 | No | 2021-06-15 | 2021-06-25 | 8 | [29 empty] | 2021-06-15 |  |  | 2021-07-09
1126 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 391.919 | No | 2021-06-15 | 2021-06-17 | 2 | 2021-06-17 | 2 | [27 empty] | 2021-06-15
1127 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 133.2 | No | 2021-06-15 | 2021-06-18 | 3 | [29 empty] | 2021-06-15
1128 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 441.315 | No | 2021-06-15 | 2021-06-18 | 3 | [29 empty] | 2021-06-15
1129 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 | No | 2021-06-15 | 2021-06-18 | 3 | [29 empty] | 2021-06-15
1130 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 102 | No | 2021-06-15 | 2021-06-17 | 2
1131 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 420 | No | 2021-06-15 | 2021-06-23 | 6 | 2021-07-01 | 12
1132 | PGE | NEM | NEMMT | Study in Progress | ENGN, Solar PV | 1192 | No | 2021-06-15 | 2021-06-21 | 4 | 2021-07-07 | 15 | [5 empty] | 2021-07-12 | [21 empty] | 2021-06-15
1133 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 | No | 2021-06-15 | 2021-06-18 | 3 | 2021-06-22 | 5 | 2021-07-12 | 13 | [15 empty] | 2021-07-12 | [9 empty] | 2021-06-15 | 2021-07-09 | 17
1134 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 228.528 | No | 2021-06-15 | 2021-06-23 | 6 | 2021-06-30 | 11 | [27 empty] | 2021-06-15
1135 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 58.04 | No | 2021-06-15 | 2021-06-18 | 3
1136 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.2 | No | 2021-06-16 | 2021-06-21 | 3 | 2021-06-29 | 9 | 2021-07-14 | 10 | [15 empty] | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14
1137 | PGE | NEM | EXPNEM | Application Submitted | Solar PV | 47.52 | No | 2021-06-16 | 2021-06-30 | 10
1138 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 57.71 | No | 2021-06-16 | 2021-06-21 | 3 | 2021-06-30 | 10 | [5 empty] | 2021-06-30
1139 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 700 | No | 2021-06-16 | 2021-06-24 | 6 | [29 empty] | 2021-06-16
1140 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 120 | No | 2021-06-16 | 2021-06-28 | 8 | 2021-07-08 | 15
1141 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 31.024 | No | 2021-06-16 | 2021-06-22 | 4
1142 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 720 | No | 2021-06-16 | 2021-06-22 | 4
1143 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 200 | No | 2021-06-16 | 2021-06-25 | 7 | [32 empty] | 2021-07-09
1144 | PGE | Non-NEM | Non-Export | Application Review in Progress | Storage | 145 | No | 2021-06-17 | 2021-06-17 | 0
1145 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 166.5 | No | 2021-06-17 | 2021-07-01 | 10 | [29 empty] | 2021-06-17
1146 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 300 | No | 2021-06-17 | 2021-07-01 | 10 | [29 empty] | 2021-06-17
1147 | PGE | NEM | SNEM Paired Storage | Study in Progress | Solar PV, Storage | 41.099 | No | 2021-06-17 | 2021-06-21 | 2 | 2021-06-30 | 9 | 2021-07-07 | 4 | [25 empty] | 2021-06-17
1148 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 3000 | No | 2021-06-17 | 2021-06-17 | 0 | 2021-06-30 | 9
1149 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 50 | No | 2021-06-17 | 2021-06-22 | 3 | 2021-06-22 | 3 | 2021-07-12 | 13 | [15 empty] | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12
1150 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 480.146 | No | 2021-06-18 | 2021-06-22 | 2 | 2021-06-30 | 8 | 2021-07-12 | 7 | 2021-07-12
1151 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 652.732 | No | 2021-06-18 | 2021-06-30 | 8 | [29 empty] | 2021-06-18
1152 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 53760 | No | 2021-06-18 | 2021-07-02 | 10
1153 | PGE | NEM | NEMMT | Application Review in Progress | Solar PV, Storage | 36.147 | No | 2021-06-22 | 2021-06-22 | 0
1154 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 576.251 | No | 2021-06-18 | 2021-06-25 | 5 | [32 empty] | 2021-07-09
1155 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 520.008 | No | 2021-06-18 | 2021-06-25 | 5 | [32 empty] | 2021-07-09
1156 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.065 | No | 2021-06-18 | 2021-06-22 | 2
1157 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 62.5 | No | 2021-06-18 | 2021-06-28 | 6 | 2021-07-01 | 9 | [27 empty] | 2021-06-18
1158 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 42.054 | No | 2021-06-18 | 2021-06-24 | 4
1159 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 103.603 | No | 2021-06-18 | 2021-06-30 | 8 | 2021-07-07 | 12
1160 | PGE | NEM | EXPNEM | Implementation | Solar PV | 34.179 | No | 2021-06-18 | 2021-06-28 | 6 | 2021-07-01 | 9 | 2021-07-08 | 4 | [15 empty] | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-08 | 0
1161 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 100 | No | 2021-06-20 | 2021-06-23 | 2 | 2021-07-02 | 9 | [27 empty] | 2021-06-20
1162 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 34.486 | No | 2021-06-21 | 2021-06-23 | 2 | 2021-06-23 | 2 | 2021-06-23 | 0 | [32 empty] | 2021-06-25 | 2021-06-25 | 0 | [15 empty] | 2021-06-25 |  |  | 2021-06-25 | 2021-06-25 |  | 0
1163 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 33.173 | No | 2021-06-21 | 2021-06-24 | 3 | 2021-06-24 | 3 | 2021-06-25 | 1 | [32 empty] | 2021-06-29 | 2021-06-29 | 0 | [15 empty] | 2021-06-29 |  |  | 2021-06-29 | 2021-06-29 |  | 0
1164 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 52.163 | No | 2021-06-21 | 2021-06-23 | 2 | 2021-07-07 | 11 | [27 empty] | 2021-06-21
1165 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 336 | No | 2021-06-21 | 2021-06-29 | 6 | 2021-07-13 | 15 | [27 empty] | 2021-06-21
1166 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 49.692 | No | 2021-06-21 | 2021-07-06 | 10
1167 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 42.01 | No | 2021-06-21 | 2021-06-24 | 3
1168 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 433.3 | No | 2021-06-21 | 2021-06-24 | 3 | [29 empty] | 2021-06-21
1169 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 | No | 2021-06-22 | 2021-06-24 | 2 | [29 empty] | 2021-06-22
1170 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 299.6 | No | 2021-06-22 | 2021-06-25 | 3 | 2021-06-25 | 3 | 2021-07-15 | 13 | [15 empty] | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | [6 empty] | 2021-06-22
1171 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.47 | No | 2021-06-22 | 2021-06-25 | 3
1172 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 37.2 | No | 2021-06-22 | 2021-06-29 | 5 | 2021-07-09 | 12
1173 | PGE | Non-NEM | Continuous Uncompensated Export | Application Accepted | ENGN, Micro Turbine | 130 | No | 2021-06-22 | 2021-06-22 | 0 | 2021-07-07 | 10
1174 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.12 | No | 2021-06-22 | 2021-06-28 | 4
1175 | PGE | Non-NEM | Non-Export | Application Accepted | Storage | 280 | No | 2021-06-22 | 2021-06-23 | 1 | 2021-07-14 | 15 | [27 empty] | 2021-06-22
1176 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 600 | No | 2021-06-22 | 2021-06-25 | 3
1177 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 47.431 | No | 2021-06-23 | 2021-06-28 | 3 | 2021-07-07 | 9
1178 | PGE | Non-NEM | Non-Export | Withdrawn | Solar PV | 420 | No | 2021-06-23 | 2021-06-23 | 0 | 2021-06-30 | 5
1179 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 31.272 | No | 2021-06-23 | 2021-07-08 | 10 | [29 empty] | 2021-06-23
1180 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 43.2 | No | 2021-06-23 | 2021-06-28 | 3 | 2021-07-14 | 14 | [27 empty] | 2021-06-23 | 2021-07-15 | 15
1181 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 62.5 | No | 2021-06-23 | 2021-07-01 | 6 | [29 empty] | 2021-06-23
1182 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 44.66 | No | 2021-06-23 | 2021-06-29 | 4
1183 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 129.6 | No | 2021-06-23 | 2021-06-29 | 4 | 2021-07-08 | 10
1184 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 36 | No | 2021-06-24 | 2021-06-30 | 4
1185 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 500 | No | 2021-06-24 | 2021-07-07 | 8 | 2021-07-15 | 14 | [27 empty] | 2021-06-24
1186 | PGE | Non-NEM | Non-Export | Application Review in Progress | Storage | 140 | No | 2021-06-24 | 2021-06-24 | 0 | [29 empty] | 2021-06-24
1187 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.195 | No | 2021-06-24 | 2021-06-30 | 4
1188 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.12 | No | 2021-06-25 | 2021-07-07 | 7
1189 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1305.783 | No | 2021-06-17 | 2021-06-28 | 7 | [29 empty] | 2021-06-25
1190 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 66.6 | No | 2021-06-25 | 2021-06-30 | 3 | [29 empty] | 2021-06-25
1191 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 35.234 | No | 2021-06-25 | 2021-06-29 | 2
1192 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.464 | No | 2021-06-25 | 2021-07-07 | 7 | 2021-07-09 | 9 | 2021-07-12 | 1 | [15 empty] | 2021-06-25 | 2021-07-07 | 7 | 2021-07-07 | 2021-07-13 | 4 |  |  |  |  | 2021-06-25 | [6 empty] | 2021-07-13 | 2021-07-13 | 0 | [15 empty] | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13 | 2021-07-13 |  | 0
1193 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 312.5 | No | 2021-06-25 | 2021-06-30 | 3 | [29 empty] | 2021-06-25
1194 | PGE | Non-NEM | Non-Export | Application Review in Progress | Storage | 490 | No | 2021-06-25 | 2021-06-25 | 0 | [29 empty] | 2021-06-25
1195 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 56.324 | No | 2021-06-25 | 2021-07-02 | 5 | 2021-07-02 | 5
1196 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 45.384 | No | 2021-06-25 | 2021-07-02 | 5 | 2021-07-15 | 13 | [27 empty] | 2021-06-25
1197 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 | No | 2021-06-28 | 2021-06-30 | 2 | 2021-07-01 | 3 | 2021-07-07 | 3 | [15 empty] | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | [6 empty] | 2021-06-28
1198 | PGE | NEM | SNEM Paired Storage | Commercial | Solar PV, Storage | 30.116 | No | 2021-06-28 | 2021-07-07 | 6 | 2021-07-07 | 6 | 2021-07-07 | 0 | [32 empty] | 2021-07-08 | 2021-07-08 | 0 | [15 empty] | 2021-07-08 |  |  | 2021-07-08 | 2021-07-08 |  | 0
1199 | PGE | NEM | SNEM | Application Submitted | Solar PV | 139.826 | No | 2021-06-28 | 2021-07-12 | 9 | [29 empty] | 2021-06-28
1200 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.3 | No | 2021-06-28 | 2021-06-30 | 2 | [29 empty] | 2021-06-28
1201 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 145.153 | No | 2021-06-28 | 2021-06-30 | 2 | [29 empty] | 2021-06-28 | 2021-07-13 | 10
1202 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 627.287 | No | 2021-06-28 | 2021-07-13 | 10 | 2021-07-13 | 10 | [27 empty] | 2021-06-28
1203 | PGE | NEM | SNEM Paired Storage | Application Review in Progress | Solar PV, Storage | 5850 | No | 2021-06-28 | 2021-07-08 | 7
1204 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 72.441 | No | 2021-06-29 | 2021-07-01 | 2 | 2021-07-15 | 11 | [27 empty] | 2021-06-29
1205 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 52.163 | No | 2021-06-29 | 2021-07-06 | 4 | 2021-07-06 | 4 | [27 empty] | 2021-06-29
1206 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 33.3 | No | 2021-06-29 | 2021-07-09 | 7 | 2021-07-12 | 8
1207 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 126.998 | No | 2021-06-29 | 2021-07-06 | 4 | 2021-07-13 | 9 | [27 empty] | 2021-06-29
1208 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 630 | No | 2021-06-29 | 2021-07-12 | 8 | 2021-07-15 | 11 | [27 empty] | 2021-06-29
1209 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 57.443 | No | 2021-06-29 | 2021-07-07 | 5
1210 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 33.3 | No | 2021-06-29 | 2021-07-14 | 10 | 2021-07-14 | 10 | [27 empty] | 2021-06-29
1211 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 500 | No | 2021-06-29 | 2021-07-14 | 10
1212 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 31.909 | No | 2021-06-29 | 2021-07-07 | 5 | 2021-07-15 | 11
1213 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 30.571 | No | 2021-06-29 | 2021-07-07 | 5
1214 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 129.827 | No | 2021-06-29 | 2021-07-13 | 9
1215 | PGE | NEM | SNEM | Application Submitted | Solar PV | 38.78 | No | 2021-06-30 | 2021-07-14 | 9 | [29 empty] | 2021-06-30
1216 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 549.991 | No | 2021-06-30 | 2021-07-08 | 5 | [29 empty] | 2021-06-30
1217 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 131.105 | No | 2021-06-30 | 2021-07-08 | 5 | [29 empty] | 2021-06-30
1218 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 240 | No | 2021-06-30 | 2021-07-08 | 5 | 2021-07-13 | 8 | [27 empty] | 2021-06-30
1219 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 372.261 | No | 2021-06-30 | 2021-07-09 | 6

## OP 22 CT Q1-2021
PG&E Interconnection Timeline Report | [7 empty] | Application Review: |  |  |  |  | Fast Track Initial Review: |  | Fast Track Supplemental Review: |  |  | Electrical Independence Test (EIT): |  |  | Scoping Meeting and Study Agreement: |  |  | System Impact Study (SIS): | [5 empty] | Draft Agreement: |  |  | Agreement Execution: |  |  |  | Material Modification: |  |  | Variance Request Review: |  |  | Net Generating Output Meter (NGOM): | [6 empty] | Minor Upgrades Design: | [5 empty] | Minor Upgrades Construction: | [5 empty] | Commissioning and In-Service:
Document Submission Frequency: Quarterly |  |  |  | Reporting Interval: 12/29/20 - 6/30/21 |  |  |  | ● 10 Business Days for initial application review [E.5.a.] (15 Business Days if Cost Envelope Option is selected [E.5.a.]) | [6 empty] | 20 Business Days [F.2.c.i.] |  |  | 20 Business Days [F.3.a.] |  |  | 5 Business Days [F.3.b.i.] |  |  | 60 Business Days [F.3.b.ii.] | [8 empty] | 90 Calendar Days [F.2.e.][F.3.2.ii.] |  |  |  | 10 Business Days [F.3.b.v] (20 Business Days if Cost Envelope Option is selected [F.3.b.v]) | [12 empty] | 60 Business Days (estimated timeline) | [5 empty] | 60 Business Days (estimated timeline) | [5 empty] | Mutually Agreeable Date with Customer
Proceeding Number: R.17-07-007; Decision Number: D.20-09-035; Ordering Paragraph (OP) Number from the Decision: 22 | [7 empty] | ● 10 Business Days for 1st deficiency cure review [E.5.b.i.] | [21 empty] | ● 15 Business Days for Fast Track [F.2.a] | [12 empty] | ● 20 Business Days to Design
[8 empty] | ● 5 Business Days for 2nd deficiency cure review [E.5.b.ii.] | [21 empty] | ● 30 Calendar Days for Detailed Study [F.3.e.i.] | [12 empty] | ● 20 Business Days to Install
Key | Utility | NEM Type | Project Type | Project Status | Technology Type | SizeTotal Proposed Gen | Cost Envelope Requested? | Application Received | Provide: 1st Written Notice/Invoice | Cycle Time A (Business Days to Acknowledge Interconnection Request Submission ) | Application Deemed Complete | Cycle Time b (Business Days to Deem Complete) | Conduct: Initial Review (IR) | Cycle Time c (Time from Interconnection Request deemed complete to completion of initial review & provision of results) | Conduct: Supplemental Review (SR) | Conduct: Supplemental Review (SR) | Cycle Time d (Time from Supplemental Review start date to completion of Supplemental Review) | Conduct: Screens Q and R | Conduct: Screens Q and R | Cycle Time e (Time from Electrical Interdependence Test start date to its completion) | Scoping Meeting Date | Scoping Meeting Date | Cycle time f (Time from Electrical Interdependence Test completion to EIT results scoping meeting held) | DSA Agreement Executed by PG&E | Conduct: SIS | Cycle Time h (Time from System Impact Study start date to its completion date) | Scoping Meeting Date | Tendered DSA Agreement | Cycle Time g (Time from study scoping meeting until study agreement provided) | Tender Draft IA | Tender Draft IA | Cycle Time I (Time to provide Draft Generator Interconnection Agreement applicable milestone) | Tender Draft IA | IA Negotiations/Customer Signature | Cycle Time J(a) (Time from Draft Generator Interconnection Agreement provided to date Generator Interconnection Agreement Executed) | Cycle Time J(b) (Time from Final Study Report date for Detailed Study to date Generator Interconnection Agreement Executed) | Receive Customer Changes | Determine Material Modifications | Cycle Time M (Time from request to consider modification to determination whether modification is material (F.3.b.v)) | Variance Request Received (typ. From cust) | Conduct: Variance Request Review | Cycle Time N (Time for responding to line-side taps variance requests (for Utilities that require a variance request)) | Conduct: Meter Review | Tender: Meter Invoice | Tender: Meter Invoice | Cycle Time O (Design and invoice of net generation output meter) | Move to FMO | FMO - PASS | Cycle Time P (Installation of net generation output meter) | SP&D Design Start | SP&D Deisgn End | Cycle Time Q(a) Time from customer agreement to proceed to final design and issuance of invoice SP&D | Tender EA Invoice | IT Design End | Cycle Time Q(b)Time from customer agreement to proceed to final design and issuance of invoice Telemetry | SP&D Construction Start | SP&D Construction Finish | Cycle Time R(a) Time from customer payment of invoice and completion of customer work to completion of upgrade construction SP&D | PG&E Construction Start IT | PG&E Construction Complete IT | Cycle Time R(b)Time from customer payment of invoice and completion of customer work to completion of upgrade construction Telemetry | PPI Authorization Letter | PPI Completion | Cycle Time S (Time for scheduling of commissioning test) | FMO - PASS (Move to FMO) | FMO schedule Inspection FMO order | Cycle Time S(b) This is for projects that do not require PPI | FMO - PASS | Permission to Operate - Final (COD) | Permission to Operate - Conditional (COD) | Cycle time K(a)Time from when the customer notifies the utility it has completed all of its obligations under the agreements (F.5.b) including commissioning tests, to when the utility provides the customer Permission to Operate - FMO Inspection: Task 7390 AFD FMO - PASS to Task 7502 AFD Permission to Parallel - Conditional or 7503 AFD Permission to Operate - Final (COD) | Conduct Pre Paralell Inspection (PPI) | Cycle time K(b) This cycle time is for projects that require PPI | Cycle Time L (Total time from submission of Interconnection Request to Permission to Operate (Not in Rule 21, tracked for informational purposes))
1 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 111.324 | No | 2020-12-29 | 2020-12-29 | 0 | 2021-01-28 | 20 | [27 empty] | 2020-12-29
2 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 32.89 | No | 2020-12-29 | 2020-12-29 | 0 | 2020-12-29 | 0 | 2021-01-19 | 13 | [15 empty] | 2021-01-19 | 2021-01-19 | 0 | 2021-01-19 | 2021-01-25 | 4 | [11 empty] | 2021-03-23
3 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 94.943 | No | 2020-12-29 | 2020-12-29 | 0 | 2020-12-30 | 1 | 2021-01-11 | 7 | [15 empty] | 2021-01-11 | 2021-01-11 | 0 | 2021-01-11 | 2021-01-14 | 3 |  |  |  |  | 2020-12-29 | 2021-01-19 | 13
4 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 43.2 | No | 2020-12-29 | 2021-01-11 | 8 | 2021-02-11 | 30 | 2021-02-26 | 10 | [15 empty] | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26
5 | PGE | NEM | VNEMMASH | Study in Progress | Solar PV | 116.34 | No | 2020-12-29 | 2021-01-13 | 10 | 2021-03-31 | 63 | [27 empty] | 2020-12-29 | 2021-03-11 | 49
6 | PGE | NEM | NEM Paired Storage | Withdrawn | Solar PV, Storage | 57.325 | No | 2020-12-29 | 2021-01-05 | 4 | 2021-01-05 | 4 | 2021-01-07 | 2 | [15 empty] | 2021-01-05 | 2021-01-05 | 0 | 2021-01-05 | 2021-02-17 | 29 | [8 empty] | 2021-01-12 | 2021-01-12 | 0
7 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 207.052 | No | 2020-12-29 | 2021-01-12 | 9 | 2021-01-22 | 16 | 2021-02-17 | 17 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | [6 empty] | 2020-12-29
8 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 1320 | No | 2020-12-29 | 2020-12-31 | 2 | 2021-01-13 | 10 | [5 empty] | 2021-01-13 | 2021-02-05 | 16 | 2021-02-05
9 | PGE | NON-NEM | Non-Export | IA in Progress | Storage | 357.5 | No | 2020-12-30 | 2020-12-31 | 1 | 2021-01-27 | 18 | [17 empty] | 2021-02-01 | 2021-02-01 | 0 | 2021-02-01 | [6 empty] | 2020-12-30
10 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 420 | No | 2020-12-30 | 2021-01-28 | 19 | [29 empty] | 2020-12-30
11 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 480 | No | 2020-12-30 | 2021-01-11 | 7 | 2021-01-28 | 19 | [27 empty] | 2020-12-30
12 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 | No | 2020-12-30 | 2021-01-13 | 9 | 2021-01-13 | 9 | 2021-02-03 | 14 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | [6 empty] | 2020-12-30 | 2021-01-27 | 18
13 | PGE | NON-NEM | Non-Export | IA in Progress | Storage | 140 | No | 2020-12-30 | 2020-12-31 | 1 | 2021-01-27 | 18 | 2021-03-02 | 23 | [15 empty] | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | [6 empty] | 2020-12-30 | 2021-02-05 | 25 | [29 empty] | 2021-03-24
14 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 324.18 | No | 2020-12-30 | 2020-12-31 | 1 | 2021-01-05 | 3 | 2021-01-11 | 4
15 | PGE | NON-NEM | Non-Export | Application Accepted | Storage | 140 | No | 2020-12-30 | 2020-12-31 | 1 | 2021-01-27 | 18 | [27 empty] | 2020-12-30
16 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 90.079 | No | 2020-12-30 | 2020-12-31 | 1 | 2021-03-30 | 61
17 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 32.454 | No | 2020-12-31 | 2021-01-07 | 4 | 2021-01-07 | 4 | 2021-01-28 | 14 | [15 empty] | 2021-01-07 | 2021-01-07 | 0 | 2021-01-07 | 2021-02-16 | 26 | [11 empty] | 2021-02-16 | 2021-02-17 | 1 | [15 empty] | 2021-02-17 |  |  | 2021-02-17 |  | 2021-02-17 | 0 |  |  | 31
19 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 58.04 | No | 2020-12-31 | 2021-01-14 | 9 | 2021-01-14 | 9 | 2021-02-11 | 19 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11
20 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 120 | No | 2021-01-04 | 2021-01-05 | 1 | 2021-01-11 | 5 | 2021-01-21 | 7 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | [6 empty] | 2021-01-04
21 | PGE | NEM | EXPNEM | Implementation | Solar PV | 131.497 | No | 2021-01-04 | 2021-01-14 | 8 | 2021-01-14 | 8 | 2021-02-04 | 14 | [15 empty] | 2021-02-04 | 2021-02-04 | 0 | 2021-02-04 | 2021-03-21 | 30 |  |  |  |  | 2021-01-04 | 2021-03-01 | 38
22 | PGE | NEM | EXPNEM | Implementation | Solar PV | 700 | No | 2021-01-04 | 2021-01-15 | 9 | 2021-01-15 | 9 | 2021-02-04 | 13 | [15 empty] | 2021-02-04 | 2021-02-04 | 0 | 2021-02-04 | 2021-02-05 | 1 |  |  |  |  | 2021-02-04 | 2021-02-09 | 3
23 | PGE | NEM | EXPNEM | Commercial | Solar PV | 99.9 | No | 2021-01-04 | 2021-01-07 | 3 | 2021-01-15 | 9 | 2021-02-02 | 11 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-02 | 0 | [11 empty] | 2021-02-03 | 2021-02-09 | 4 | [15 empty] | 2021-02-09 |  |  | 2021-02-09 |  | 2021-02-10 | 1 |  |  | 26
24 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 52.49 | No | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
25 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 61.773 | No | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
26 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 65.263 | No | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
27 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.444 | No | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
28 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 63.867 | No | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
29 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 62.122 | No | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
30 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 41.88 | No | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
31 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 63.169 | No | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
32 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 57.585 | No | 2021-01-04 | 2021-01-19 | 10 | [29 empty] | 2021-01-04
33 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 | No | 2021-01-05 | 2021-01-08 | 3 | 2021-01-08 | 3 | 2021-01-11 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-02-17 | 26 | [11 empty] | 2021-02-17 | 2021-02-17 | 0 | [15 empty] | 2021-02-17 |  |  | 2021-02-17 |  | 2021-02-17 | 0 |  |  | 29
34 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 | No | 2021-01-05 | 2021-01-06 | 1 | 2021-01-19 | 9 | 2021-02-18 | 21 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | [6 empty] | 2021-01-05 | 2021-01-20 | 10
35 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 85.573 | No | 2021-01-05 | 2021-01-06 | 1 | 2021-01-07 | 2 | 2021-01-08 | 1 | [15 empty] | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-03-10 | 41 |  |  |  |  | 2021-01-05 | [6 empty] | 2021-03-12
36 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 53.808 | No | 2021-01-05 | 2021-01-06 | 1 | 2021-01-06 | 1 | 2021-01-21 | 10 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21
37 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 | No | 2021-01-05 | 2021-01-20 | 10 | 2021-01-28 | 16 | 2021-02-02 | 3 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-04 | 2 | [11 empty] | 2021-02-08 | 2021-02-08 | 0 | [15 empty] | 2021-02-08 |  |  | 2021-02-08 |  | 2021-02-10 | 2 |  |  | 25
38 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.886 | No | 2021-01-05 | 2021-01-06 | 1 | 2021-01-27 | 15 | 2021-02-11 | 11 | [15 empty] | 2021-02-11 | 2021-02-16 | 2 | 2021-02-16 | 2021-02-23 | 5 |  |  |  |  | 2021-01-05 | 2021-02-16 | 28
39 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 83.3 | No | 2021-01-05 | 2021-01-19 | 9 | 2021-01-19 | 9 | 2021-02-02 | 10 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | [6 empty] | 2021-01-05 | 2021-01-28 | 16
40 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100 | No | 2021-01-05 | 2021-01-06 | 1 | 2021-01-13 | 6 | 2021-02-02 | 13 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-02 | 0 |  |  |  |  | 2021-01-05 | 2021-01-20 | 10
41 | PGE | NEM | EXPNEM | Implementation | Solar PV | 33.3 | No | 2021-01-05 | 2021-01-19 | 9 | 2021-01-19 | 9 | 2021-02-08 | 14 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-03-01 | 14 | [11 empty] | 2021-03-23
42 | PGE | NEM | VNEMMASH | Study in Progress | Solar PV | 433.597 | No | 2021-01-05 | 2021-01-12 | 5 | 2021-01-12 | 5 | 2021-02-19 | 26 |  |  |  | 2021-03-02
43 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 530 | No | 2021-01-05 | 2021-01-12 | 5 | 2021-01-12 | 5 | 2021-02-24 | 29 | [15 empty] | 2021-02-24 | 2021-02-24 | 0 | 2021-02-24
44 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 2600.5 | No | 2021-01-06 | 2021-01-07 | 1 | 2021-01-27 | 14 | [5 empty] | 2021-01-27 | 2021-03-04 | 25 | 2021-03-04 |  |  | 2021-03-25 |  |  | 2021-03-04 | 2021-03-08 | 2
45 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 69.54 | No | 2021-01-06 | 2021-01-07 | 1 | 2021-02-02 | 18 | 2021-03-04 | 21 | [15 empty] | 2021-03-04 | 2021-03-04 | 0 | 2021-03-04 | 2021-03-04 | 0 |  |  |  |  | 2021-01-06 | 2021-01-20 | 9
46 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 493.369 | No | 2021-01-06 | 2021-01-07 | 1 | 2021-02-23 | 32 | 2021-03-09 | 10 | [15 empty] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09
47 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 1625 | No | 2021-01-06 | 2021-01-07 | 1 | 2021-01-20 | 9 | 2021-03-02 | 28 | 2021-03-08
48 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 52.675 | No | 2021-01-06 | 2021-01-19 | 8 | 2021-01-19 | 8 | 2021-02-08 | 14 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08
49 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.295 | No | 2021-01-06 | 2021-01-11 | 3 | 2021-01-20 | 9 | 2021-02-08 | 13 | [15 empty] | 2021-01-20 | 2021-01-20 | 0 | 2021-01-20 | 2021-02-17 | 19 | [11 empty] | 2021-02-18 | 2021-02-18 | 0 | [15 empty] | 2021-02-18 |  |  | 2021-02-18 |  | 2021-02-24 | 4 |  |  | 33
50 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 53.35 | No | 2021-01-07 | 2021-01-08 | 1 | 2021-01-08 | 1 | 2021-01-26 | 11 | [15 empty] | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 2021-01-29 | 3 |  |  |  |  | 2021-01-07 | 2021-02-08 | 21
51 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 | No | 2021-01-07 | 2021-01-08 | 1 | 2021-01-08 | 1 | 2021-02-08 | 20 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-02-12 | 4 |  |  |  |  | 2021-01-07 | 2021-02-09 | 22
52 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 112.682 | No | 2021-01-07 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-28 | 11 | [15 empty] | 2021-01-28 | [9 empty] | 2021-01-07
53 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 168.87 | No | 2021-01-07 | 2021-01-08 | 1 | 2021-01-11 | 2 | 2021-02-20 | 27 | [15 empty] | 2021-02-20 | 2021-02-20 | 0 | 2021-02-20 | [6 empty] | 2021-01-07 | 2021-03-03 | 37
54 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.741 | No | 2021-01-07 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-03-09 | 38 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-03-10 | 39 | [11 empty] | 2021-03-10 | 2021-03-10 | 0 | [15 empty] | 2021-03-10 |  |  | 2021-03-10 |  | 2021-03-13 | 2 |  |  | 44
55 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 41.331 | No | 2021-01-07 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-14 | 2 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | [6 empty] | 2021-01-07 | 2021-01-26 | 12
56 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 | No | 2021-01-07 | 2021-01-21 | 9 | 2021-01-21 | 9 | 2021-03-10 | 33 | [15 empty] | 2021-03-10 | 2021-03-10 | 0 | 2021-03-10 | [6 empty] | 2021-01-07 | 2021-02-02 | 17
57 | PGE | NEM | EXPNEM | Implementation | Solar PV | 54.229 | No | 2021-01-07 | 2021-01-21 | 9 | 2021-01-21 | 9 | 2021-02-10 | 14 | [15 empty] | 2021-02-10 | 2021-02-10 | 0 | 2021-02-10 | 2021-03-03 | 14 |  |  |  |  | 2021-01-07
58 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.133 | No | 2021-01-08 | 2021-01-21 | 8 | 2021-01-21 | 8 | 2021-02-09 | 13 | [15 empty] | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | 2021-02-09 | 0 | [11 empty] | 2021-02-17 | 2021-02-17 | 0 | [15 empty] | 2021-02-17 |  |  | 2021-02-17 |  | 2021-02-18 | 1 |  |  | 27
59 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 82.091 | No | 2021-01-08 | 2021-01-22 | 9 | 2021-01-22 | 9 | 2021-03-03 | 27 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | [6 empty] | 2021-03-12 | 2021-03-15 | 1
60 | PGE | NEM | EXPNEM | Implementation | Solar PV | 60 | No | 2021-01-08 | 2021-01-22 | 9 | 2021-01-22 | 9 | 2021-02-11 | 14 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-22 | 6 |  |  |  |  | 2021-01-08 | 2021-02-02 | 16
61 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 83.3 | No | 2021-01-08 | 2021-01-23 | 9 | 2021-01-23 | 9 | 2021-02-06 | 9 | [15 empty] | 2021-02-06 | 2021-02-06 | 0 | 2021-02-06 | [6 empty] | 2021-01-08 | 2021-02-02 | 16
62 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 | No | 2021-01-08 | 2021-01-16 | 5 | 2021-02-24 | 31 | 2021-03-15 | 13 | [15 empty] | 2021-02-24 | 2021-02-24 | 0 | 2021-02-24 | 2021-03-10 | 10 | [11 empty] | 2021-03-15 | 2021-03-15 | 0 | [15 empty] | 2021-03-15 |  |  | 2021-03-15 |  | 2021-03-22 | 5 |  |  | 49
63 | PGE | NON-NEM | Non-Export | Application Accepted | Storage | 350 | No | 2021-01-08 | 2021-01-11 | 1 | 2021-02-03 | 17 | [27 empty] | 2021-01-08
64 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 62.5 | No | 2021-01-08 | 2021-01-23 | 9 | 2021-01-23 | 9 | 2021-02-09 | 11 | [15 empty] | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | [6 empty] | 2021-01-08 | 2021-02-02 | 16
65 | PGE | NEM | VNEMSOMAH | Application Accepted | Solar PV | 74.404 | No | 2021-01-08 | 2021-01-14 | 4 | 2021-01-18 | 5 | [27 empty] | 2021-01-08 |  |  | 2021-01-19
66 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 172.8 | No | 2021-01-08 | 2021-01-22 | 9 | [29 empty] | 2021-01-08
67 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 37.68 | No | 2021-01-08 | 2021-01-14 | 4 | 2021-01-21 | 8 | 2021-01-25 | 2 | [15 empty] | 2021-01-14 | 2021-01-14 | 0 | 2021-01-14
68 | PGE | NON-NEM | Non-Export | Study in Progress | Storage | 140 | No | 2021-01-08 | 2021-01-11 | 1 | 2021-02-03 | 17 | 2021-03-30 | 38 | [15 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | [6 empty] | 2021-01-08
69 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 | No | 2021-01-08 | 2021-01-12 | 2 | 2021-01-12 | 2 | 2021-02-25 | 30 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-26 | 21 |  |  |  |  | 2021-01-08 |  |  |  | 2021-03-25 | 2021-03-25
70 | PGE | NEM | NEM Paired Storage | IA in Progress | Engine, Solar PV, Storage | 646.893 | No | 2021-01-08 | 2021-01-20 | 7 | 2021-03-31 | 56 | [27 empty] | 2021-01-08
71 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 30.399 | No | 2021-01-09 | 2021-01-16 | 4 | 2021-01-16 | 4 | 2021-02-04 | 12 | [15 empty] | 2021-01-16 | 2021-01-16 | 0 | 2021-01-16 | 2021-02-16 | 19
72 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 | No | 2021-01-08 | 2021-01-14 | 4 | 2021-01-14 | 4 | 2021-02-03 | 13 | [15 empty] | 2021-01-14 | 2021-01-14 | 0 | 2021-01-14 | 2021-02-03 | 13 | [11 empty] | 2021-02-03 | 2021-02-09 | 4 | [15 empty] | 2021-02-09 |  |  | 2021-02-09 |  | 2021-02-09 | 0 |  |  | 21
73 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 150 | No | 2021-01-09 | 2021-01-11 | 0 | 2021-01-13 | 2 | 2021-03-15 | 41 | [15 empty] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | [6 empty] | 2021-02-23 | 2021-02-23 | 0
74 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 62.048 | No | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
75 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.292 | No | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
76 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 38.78 | No | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
77 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.292 | No | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
79 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 62.048 | No | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
80 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 42.054 | No | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
81 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 35.045 | No | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
82 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 54.292 | No | 2021-01-10 | 2021-01-25 | 9 | [29 empty] | 2021-01-10
83 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 32.032 | No | 2021-01-11 | 2021-01-12 | 1 | 2021-01-12 | 1 | 2021-01-27 | 10 | [15 empty] | 2021-01-27 | 2021-01-27 | 0 | 2021-01-27 | [6 empty] | 2021-01-11 | 2021-01-26 | 10
84 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 66.6 | No | 2021-01-11 | 2021-01-12 | 1 | 2021-01-19 | 5 | 2021-02-03 | 11 | 2021-02-03 | 2021-03-18 | 30 | 2021-03-23 | 2021-03-25 | 2 | 2021-03-25 | [18 empty] | 2021-01-11 | 2021-01-26 | 10
85 | PGE | NEM | EXPNEM | Implementation | Solar PV | 40.1 | No | 2021-01-11 | 2021-01-26 | 10 | 2021-01-26 | 10 | 2021-02-18 | 16 | [15 empty] | 2021-02-16 | 2021-02-16 | 0 | 2021-02-16 | 2021-02-22 | 4 |  |  |  |  | 2021-01-11 | 2021-02-03 | 16
86 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 37.099 | No | 2021-01-11 | 2021-01-12 | 1 | 2021-03-30 | 54 | [27 empty] | 2021-01-11 | 2021-02-05 | 18
87 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 91.918 | No | 2021-01-11 | 2021-01-12 | 1 | 2021-01-19 | 5 | 2021-02-03 | 11 | 2021-02-03 | 2021-03-18 | 30 | 2021-03-24 | 2021-03-25 | 1 | 2021-03-25 | [18 empty] | 2021-01-11 | 2021-02-02 | 15
88 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 55.708 | No | 2021-01-11 | 2021-01-12 | 1 | 2021-01-19 | 5 | 2021-02-02 | 10 | 2021-02-02 | 2021-03-19 | 32 | 2021-03-24 | 2021-03-25 | 1 | 2021-03-25 | [18 empty] | 2021-01-11 | 2021-02-02 | 15
89 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.409 | No | 2021-01-11 | 2021-01-16 | 4 | 2021-01-16 | 4 | 2021-02-01 | 9 | [15 empty] | 2021-01-16 | 2021-01-16 | 0 | 2021-01-16 | 2021-01-19 | 0 | [11 empty] | 2021-02-01 | 2021-02-01 | 0 | [15 empty] | 2021-02-01 |  |  | 2021-02-01 |  | 2021-02-01 | 0 |  |  | 14
90 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.714 | No | 2021-01-11 | 2021-01-19 | 5 | 2021-02-05 | 18 | 2021-02-22 | 10 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | 2021-02-08 | 1 | [11 empty] | 2021-02-22 | 2021-03-03 | 7 | [15 empty] | 2021-03-03 |  |  | 2021-03-03 |  | 2021-03-06 | 2 |  |  | 37
91 | PGE | NON-NEM | Non-Export | IA in Progress | Storage | 280 | No | 2021-01-11 | 2021-01-12 | 1 | 2021-02-03 | 16 | 2021-03-01 | 17 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | [6 empty] | 2021-01-11
92 | PGE | NEM | NEMMT | Study in Progress | Solar PV | 663.66 | No | 2021-01-11 | 2021-01-26 | 10 | 2021-02-19 | 27 | 2021-03-11 | 14 | 2021-03-11 | [24 empty] | 2021-01-11 | 2021-02-03 | 16
93 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 95.8 | No | 2021-01-11 | 2021-01-12 | 1 | 2021-01-13 | 2 | 2021-01-29 | 11 | [15 empty] | 2021-01-29 | 2021-02-14 | 10 | 2021-02-14 | 2021-02-18 | 2
94 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 3858.508 | No | 2021-02-16 | 2021-02-17 | 1 | 2021-03-03 | 11 | [5 empty] | 2021-03-04 | [8 empty] | 2021-04-07 | 2021-04-08 | 1 | [10 empty] | 2021-02-16
95 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 520 | No | 2021-02-01 | 2021-02-12 | 9 | 2021-02-25 | 17 | 2021-03-03 | 4 | 2021-03-03 | 2021-03-31 | 20 | [12 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31
96 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.404 | No | 2021-01-28 | 2021-01-28 | 0 | 2021-02-04 | 5 | 2021-02-11 | 5 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-11 | 0
97 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 200 | No | 2021-01-21 | 2021-01-22 | 1 | 2021-01-22 | 1 | 2021-02-12 | 15 | [15 empty] | 2021-02-12 | 2021-02-12 | 0 | 2021-02-12 | 2021-02-17 | 2
98 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 250 | No | 2021-01-27 | 2021-01-28 | 1 | 2021-01-29 | 2 | 2021-02-14 | 10 | [15 empty] | 2021-02-14 | 2021-02-14 | 0 | 2021-02-14 | 2021-02-18 | 2
99 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 127.683 | No | 2021-02-11 | 2021-02-12 | 1 | 2021-02-16 | 2 | 2021-02-20 | 3 | [15 empty] | 2021-02-20 | 2021-02-20 | 0 | 2021-02-20 | 2021-02-24 | 2 |  |  |  |  | 2021-02-11
100 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 94.803 | No | 2021-01-14 | 2021-01-15 | 1 | 2021-02-18 | 23 | 2021-03-01 | 7 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-03 | 2
101 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.06 | No | 2021-02-03 | 2021-02-04 | 1 | 2021-02-04 | 1 | 2021-02-18 | 9 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-08 | 12
102 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 63.135 | No | 2021-02-11 | 2021-02-12 | 1 | 2021-02-16 | 2 | 2021-03-03 | 11 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-08 | 3
103 | PGE | NEM | EXPNEM | Implementation | Solar PV | 770 | No | 2021-02-18 | 2021-02-23 | 3 | 2021-02-23 | 3 | 2021-03-01 | 4 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-11 | 8
104 | PGE | NEM | EXPNEM | Implementation | Solar PV | 31.062 | No | 2021-02-04 | 2021-02-16 | 7 | 2021-02-16 | 7 | 2021-03-12 | 18 | [15 empty] | 2021-03-12 | 2021-03-12 | 0 | 2021-03-12 | 2021-03-12 | 0
105 | PGE | NEM | EXPNEM | Implementation | Solar PV | 316.555 | No | 2021-01-28 | 2021-02-03 | 4 | 2021-02-17 | 13 | 2021-03-08 | 13 | [15 empty] | 2021-03-08 | 2021-03-17 | 7 | 2021-03-17 | 2021-03-18 | 1 |  |  |  |  | 2021-01-28
106 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 103.592 | No | 2021-02-26 | 2021-03-01 | 1 | 2021-03-04 | 4 | 2021-03-23 | 13 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | 2021-03-24 | 1 |  |  |  |  | 2021-02-26
107 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 40.733 | No | 2021-02-12 | 2021-02-16 | 1 | 2021-02-16 | 1 | 2021-03-02 | 10 | [15 empty] | 2021-03-02 | 2021-03-03 | 1 | 2021-03-03 | 2021-03-26 | 17
108 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 260.887 | No | 2021-02-26 | 2021-03-02 | 2 | 2021-03-09 | 7 | 2021-03-29 | 14 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-03-29 | 0 |  |  |  |  | 2021-02-26
109 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 94.803 | No | 2021-01-14 | 2021-01-15 | 1 | 2021-02-01 | 11 | 2021-02-11 | 8 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-16 | 2 |  |  |  |  | 2021-01-14 | 2021-01-28 | 9
110 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 86.965 | No | 2021-01-26 | 2021-01-26 | 0 | 2021-01-28 | 2 | 2021-02-18 | 14 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-02 | 8 |  |  |  |  | 2021-01-26 | 2021-02-03 | 6
111 | PGE | NEM | EXPNEM | Implementation | Solar PV | 150 | No | 2021-01-20 | 2021-01-28 | 6 | 2021-01-29 | 7 | 2021-01-29 | 0 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-01 | 4 |  |  |  |  | 2021-01-20 | 2021-02-05 | 12
112 | PGE | NEM | EXPNEM | Implementation | Solar PV | 69.6 | No | 2021-01-14 | 2021-01-28 | 9 | 2021-01-28 | 9 | 2021-02-18 | 14 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-23 | 23 |  |  |  |  | 2021-01-14 | 2021-02-05 | 15
113 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 167.045 | No | 2021-01-28 | 2021-01-29 | 1 | 2021-02-01 | 2 | 2021-03-15 | 29 | [15 empty] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | 2021-03-25 | 8 |  |  |  |  | 2021-01-28 | 2021-02-05 | 6
114 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 185.596 | No | 2021-02-03 | 2021-02-04 | 1 | 2021-02-10 | 5 | 2021-02-25 | 10 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-03 | 4 |  |  |  |  | 2021-02-03 | 2021-02-09 | 4
115 | PGE | NEM | EXPNEM | Implementation | Solar PV | 66 | No | 2021-01-28 | 2021-02-08 | 7 | 2021-02-08 | 7 | 2021-03-03 | 16 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-04 | 1 |  |  |  |  | 2021-01-28 | 2021-02-09 | 8
116 | PGE | NEM | EXPNEM | Implementation | Solar PV | 66.6 | No | 2021-01-28 | 2021-02-05 | 6 | 2021-02-10 | 9 | 2021-02-17 | 4 | [15 empty] | 2021-02-17 | 2021-02-17 | 0 | 2021-02-17 | 2021-03-16 | 19 |  |  |  |  | 2021-01-28 | 2021-02-09 | 8
117 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 48.582 | No | 2021-02-03 | 2021-02-04 | 1 | 2021-02-14 | 7 | 2021-03-05 | 13 | [15 empty] | 2021-03-05 | 2021-03-05 | 0 | 2021-03-05 | 2021-03-09 | 2 |  |  |  |  | 2021-02-03 | 2021-02-16 | 8
118 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 147.625 | No | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 0 | 2021-02-11 | 12 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-22 | 6 |  |  |  |  | 2021-01-26 | 2021-03-01 | 23
119 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 175 | No | 2021-01-25 | 2021-01-26 | 1 | 2021-01-28 | 3 | 2021-02-12 | 11 | [15 empty] | 2021-02-12 | 2021-02-12 | 0 | 2021-02-12 | 2021-02-17 | 2 |  |  |  |  | 2021-01-25 | 2021-03-12 | 33
120 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 32.77 | No | 2021-01-28 | 2021-01-29 | 1 | 2021-02-04 | 5 | 2021-03-04 | 19 | [15 empty] | 2021-03-04 | 2021-03-04 | 0 | 2021-03-04 | 2021-03-11 | 5 |  |  |  |  | 2021-01-29 | 2021-03-17 | 32
121 | PGE | NEM | EXPNEM | Implementation | Solar PV | 50 | No | 2021-01-29 | 2021-02-09 | 7 | 2021-02-10 | 8 | 2021-03-02 | 13 | [15 empty] | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | 2021-03-05 | 3 |  |  |  |  | 2021-01-29 | 2021-03-29 | 40 |  |  |  |  | 2021-03-05
122 | PGE | NEM | EXPNEM | Commercial | Solar PV | 47.82 | No | 2021-01-15 | 2021-01-19 | 1 | 2021-01-28 | 8 | 2021-02-02 | 3 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-18 | 11 | [11 empty] | 2021-02-22 | 2021-02-26 | 4 | [15 empty] | 2021-02-26 |  |  | 2021-02-26 |  | 2021-03-03 | 3 |  |  | 31
123 | PGE | NEM | EXPNEM | Commercial | Solar PV | 161.782 | No | 2021-01-14 | 2021-01-15 | 1 | 2021-01-29 | 10 | 2021-02-11 | 9 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-03-11 | 19 |  |  |  |  | 2021-01-14 | 2021-01-28 | 9 |  |  |  |  | 2021-03-15 | 2021-03-24 | 7 | [15 empty] | 2021-03-24 |  |  | 2021-03-24 |  | 2021-03-25 | 1 |  |  | 48
124 | PGE | NEM | EXPNEM | Commercial | Solar PV | 31.024 | No | 2021-02-02 | 2021-02-03 | 1 | 2021-02-03 | 1 | 2021-02-26 | 16 | [15 empty] | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-03-15 | 11 | [11 empty] | 2021-03-18 | 2021-03-24 | 4 | [15 empty] | 2021-03-24 |  |  | 2021-03-24 |  | 2021-03-25 | 1 |  |  | 36
125 | PGE | NEM | EXPNEM | Commercial | Solar PV | 68.358 | No | 2021-01-13 | 2021-01-28 | 10 | 2021-01-28 | 10 | 2021-02-18 | 14 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-10 | 14 | [11 empty] | 2021-03-13 | 2021-03-25 | 8 | [15 empty] | 2021-03-25 |  |  | 2021-03-25 |  | 2021-03-25 | 0 |  |  | 49
126 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 | No | 2021-02-11 | 2021-02-16 | 2 | 2021-03-09 | 17 | 2021-03-24 | 11 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-03-26 | 2 |  |  |  |  | 2021-02-17 | [6 empty] | 2021-03-29
127 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 35.325 | No | 2021-02-02 | 2021-02-03 | 1 | 2021-02-09 | 5 | 2021-03-04 | 16 | [15 empty] | 2021-03-04 | 2021-03-04 | 0 | 2021-03-04 | 2021-03-31 | 19
128 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 70.479 | No | 2021-01-18 | 2021-01-20 | 1 | 2021-03-09 | 34 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-03-31 | 3 |  |  |  |  | 2021-03-02 | 2021-03-12 | 8
129 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 33.7 | No | 2021-01-13 | 2021-01-21 | 5 | 2021-01-21 | 5 | 2021-02-09 | 13 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-01-21 | 0
130 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 35.56 | No | 2021-01-12 | 2021-01-21 | 6 | 2021-01-21 | 6 | 2021-01-26 | 3 | [15 empty] | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-01-22 | 1
131 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 42.99 | No | 2021-01-14 | 2021-01-25 | 6 | 2021-01-25 | 6 | 2021-02-04 | 8 | [15 empty] | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | 2021-02-04 | 8
132 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 32.242 | No | 2021-01-15 | 2021-01-26 | 6 | 2021-01-26 | 6 | 2021-02-04 | 7 | [15 empty] | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 2021-02-09 | 10
133 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 33.747 | No | 2021-02-04 | 2021-02-19 | 10 | 2021-02-19 | 10 | 2021-03-08 | 11 | [15 empty] | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | 2021-02-24 | 3
134 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 40.356 | No | 2021-02-11 | 2021-02-22 | 6 | 2021-03-11 | 19 | 2021-03-17 | 4 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-02-26 | 4
135 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 34.2 | No | 2021-01-28 | 2021-02-10 | 9 | 2021-03-17 | 33 | 2021-03-25 | 6 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-21 | 2
136 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.356 | No | 2021-03-23 | [25 empty] | 2021-03-23 | N/A
137 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 37 | No | 2021-02-25 | 2021-03-09 | 8 | 2021-03-09 | 8 | 2021-03-18 | 7 | [15 empty] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | 2021-03-25 | 12
138 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 35.232 | No | 2021-03-11 | 2021-03-24 | 9 | 2021-03-24 | 9 | 2021-03-25 | 1 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-03-25 | 1
139 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.887 | No | 2021-02-04 | 2021-02-10 | 4 | [23 empty] | 2021-03-29 | N/A
140 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.8 | No | 2021-03-30 | [25 empty] | 2021-03-30 | N/A
141 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 53.626 | No | 2021-02-11 | 2021-02-22 | 6 | 2021-03-11 | 19 | 2021-03-22 | 7 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-01 | 5 |  |  |  |  | 2021-03-22 | 2021-03-25 | 3
142 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 38.86 | No | 2021-01-20 | 2021-02-03 | 10 | 2021-02-03 | 10 | 2021-02-08 | 3 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-02-08 | 3 | [11 empty] | 2021-02-08
143 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 39.361 | No | 2021-01-05 | 2021-01-15 | 8 | 2021-01-19 | 9 | 2021-02-05 | 13 | [15 empty] | 2021-01-19 | 2021-01-19 | 0 | 2021-01-19 | 2021-01-19 | 0 |  |  |  |  | 2021-01-05 | 2021-02-02 | 19 |  |  |  |  | 2021-02-17
144 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 39.988 | No | 2021-02-05 | 2021-02-21 | 9 | 2021-03-16 | 26 | 2021-03-24 | 6 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-16 | 0 | [11 empty] | 2021-03-24
145 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 39.857 | No | 2021-01-15 | 2021-01-25 | 5 | 2021-01-25 | 5 | 2021-01-26 | 1 | [15 empty] | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | 2021-01-28 | 3 | [11 empty] | 2021-01-28 | 2021-01-28 | 0 | [15 empty] | 2021-01-28 |  |  | 2021-01-28 |  | 2021-01-30 | 1 |  |  | 9
146 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 | No | 2020-12-29 | 2021-01-12 | 9 | 2021-01-28 | 20 | 2021-02-02 | 3 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-03 | 1 | [11 empty] | 2021-02-11 | 2021-02-11 | 0 | [15 empty] | 2021-02-11 |  |  | 2021-02-11 |  | 2021-02-17 | 3 |  |  | 33
147 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 | No | 2021-01-21 | 2021-02-03 | 9 | 2021-02-03 | 9 | 2021-02-09 | 4 | [15 empty] | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | 2021-02-09 | 0 | [11 empty] | 2021-02-12 | 2021-02-12 | 0 | [15 empty] | 2021-02-12 |  |  | 2021-02-12 |  | 2021-02-17 | 2 |  |  | 18
148 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 | No | 2021-01-15 | 2021-01-28 | 8 | 2021-01-28 | 8 | 2021-02-08 | 7 | [15 empty] | 2021-01-28 | 2021-01-28 | 0 | 2021-01-28 | 2021-02-08 | 7 | [11 empty] | 2021-02-08 | 2021-02-16 | 5 | [15 empty] | 2021-02-16 |  |  | 2021-02-16 |  | 2021-02-17 | 1 |  |  | 21
149 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.803 | No | 2021-02-09 | 2021-02-18 | 6 | 2021-02-19 | 7 | 2021-02-22 | 1 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-02-23 | 1 |  |  |  |  | 2021-02-09 | 2021-02-22 | 8 |  |  |  |  | 2021-02-23 | 2021-02-23 | 0 | [15 empty] | 2021-02-23 |  |  | 2021-02-23 |  | 2021-02-27 | 3 |  |  | 12
150 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 | No | 2021-02-11 | 2021-02-23 | 7 | 2021-02-23 | 7 | 2021-02-26 | 3 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-02-23 | 0 | [11 empty] | 2021-02-26 | 2021-02-28 | 0 | [15 empty] | 2021-02-28 |  |  | 2021-02-28 |  | 2021-03-06 | 4 |  |  | 15
151 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.729 | No | 2021-02-10 | 2021-02-22 | 7 | 2021-02-22 | 7 | 2021-02-23 | 1 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-01 | 5 | [11 empty] | 2021-03-03 | 2021-03-04 | 1 | [15 empty] | 2021-03-04 |  |  | 2021-03-04 |  | 2021-03-06 | 1 |  |  | 16
152 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.36 | No | 2021-02-16 | 2021-03-01 | 9 | 2021-03-01 | 9 | 2021-03-02 | 1 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-03 | 2 | [11 empty] | 2021-03-04 | 2021-03-04 | 0 | [15 empty] | 2021-03-04 |  |  | 2021-03-04 |  | 2021-03-06 | 1 |  |  | 13
153 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 | No | 2021-02-08 | 2021-02-23 | 10 | 2021-02-23 | 10 | 2021-03-03 | 6 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-02 | 5 | [11 empty] | 2021-03-08 | 2021-03-08 | 0 | [15 empty] | 2021-03-08 |  |  | 2021-03-08 |  | 2021-03-11 | 3 |  |  | 22
154 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.887 | No | 2021-02-08 | 2021-02-23 | 10 | 2021-02-23 | 10 | 2021-03-03 | 6 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-03 | 6 | [11 empty] | 2021-03-08 | 2021-03-08 | 0 | [15 empty] | 2021-03-08 |  |  | 2021-03-08 |  | 2021-03-11 | 3 |  |  | 22
155 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.116 | No | 2021-02-18 | 2021-03-03 | 9 | 2021-03-03 | 9 | 2021-03-04 | 1 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-08 | 3 |  |  |  |  | 2021-02-18 | 2021-03-03 | 9 |  |  |  |  | 2021-03-08 | 2021-03-08 | 0 | [15 empty] | 2021-03-08 |  |  | 2021-03-08 |  | 2021-03-13 | 4 |  |  | 16
156 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 34.88 | No | 2021-01-28 | 2021-02-11 | 10 | 2021-02-11 | 10 | 2021-02-26 | 10 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-25 | 9 | [11 empty] | 2021-03-08 | 2021-03-09 | 1 | [15 empty] | 2021-03-09 |  |  | 2021-03-09 |  | 2021-03-11 | 2 |  |  | 29
157 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.92 | No | 2021-02-11 | 2021-02-23 | 7 | 2021-02-25 | 9 | 2021-03-09 | 8 | [15 empty] | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-02 | 3 | [11 empty] | 2021-03-09 | 2021-03-10 | 1 | [15 empty] | 2021-03-10 |  |  | 2021-03-10 |  | 2021-03-13 | 2 |  |  | 20
158 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.962 | No | 2021-02-17 | 2021-03-02 | 9 | 2021-03-04 | 11 | 2021-03-11 | 5 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-05 | 2 | [11 empty] | 2021-03-11 | 2021-03-11 | 0 | [15 empty] | 2021-03-11 |  |  | 2021-03-11 |  | 2021-03-13 | 1 |  |  | 17
159 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 | No | 2021-02-11 | 2021-02-23 | 7 | 2021-02-23 | 7 | 2021-02-25 | 2 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-08 | 9 | [11 empty] | 2021-03-11 | 2021-03-11 | 0 | [15 empty] | 2021-03-11 |  |  | 2021-03-11 |  | 2021-03-13 | 1 |  |  | 20
160 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.528 | No | 2021-02-22 | 2021-03-06 | 9 | 2021-03-06 | 9 | 2021-03-11 | 3 | [15 empty] | 2021-03-06 | 2021-03-06 | 0 | 2021-03-06 | 2021-03-09 | 1 | [11 empty] | 2021-03-11 | 2021-03-11 | 0 | [15 empty] | 2021-03-11 |  |  | 2021-03-11 |  | 2021-03-13 | 1 |  |  | 14
161 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.337 | No | 2021-01-25 | 2021-02-08 | 10 | 2021-02-08 | 10 | 2021-02-26 | 13 | [15 empty] | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-03-02 | 15 | [11 empty] | 2021-03-17 | 2021-03-17 | 0 | [15 empty] | 2021-03-17 |  |  | 2021-03-17 |  | 2021-03-19 | 2 |  |  | 38
162 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.741 | No | 2021-02-08 | 2021-02-23 | 10 | 2021-02-23 | 10 | 2021-03-01 | 4 | [15 empty] | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-02 | 5 | [11 empty] | 2021-03-17 | 2021-03-17 | 0 | [15 empty] | 2021-03-17 |  |  | 2021-03-17 |  | 2021-03-19 | 2 |  |  | 28
163 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 30.116 | No | 2021-02-23 | 2021-03-06 | 8 | 2021-03-06 | 8 | 2021-03-08 | 0 | [15 empty] | 2021-03-06 | 2021-03-06 | 0 | 2021-03-06 | 2021-03-23 | 11 | [11 empty] | 2021-03-23 | 2021-03-23 | 0 | [15 empty] | 2021-03-23 |  |  | 2021-03-23 |  | 2021-03-27 | 3 |  |  | 23
164 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 35.52 | No | 2021-01-22 | 2021-02-08 | 11 | 2021-03-03 | 27 | 2021-03-11 | 6 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-10 | 5 | [11 empty] | 2021-03-11 | 2021-03-24 | 9 | [15 empty] | 2021-03-24 |  |  | 2021-03-24 |  | 2021-03-25 | 1 |  |  | 43
165 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.646 | No | 2021-02-08 | 2021-02-16 | 5 | 2021-03-02 | 15 | 2021-03-06 | 3 | [15 empty] | 2021-03-06 | 2021-03-06 | 0 | 2021-03-06 | 2021-03-10 | 2 | [11 empty] | 2021-03-24 | 2021-03-25 | 1 | [15 empty] | 2021-03-25 |  |  | 2021-03-25 |  | 2021-03-30 | 3 |  |  | 35
166 | PGE | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 31.393 | No | 2021-01-14 | 2021-01-23 | 5 | 2021-02-25 | 28 | 2021-03-16 | 13 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-16 | 0 | [11 empty] | 2021-03-29 | 2021-03-29 | 0 | [15 empty] | 2021-03-29 |  |  | 2021-03-29 |  | 2021-03-30 | 1 |  |  | 51
167 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 32.75 | No | 2021-03-01 | 2021-03-13 | 9 | 2021-03-13 | 9 | 2021-03-16 | 1 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-29 | 10 | [11 empty] | 2021-03-29 | 2021-03-29 | 0 | [15 empty] | 2021-03-29 |  |  | 2021-03-29
168 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.36 | No | 2021-03-01 | 2021-03-13 | 9 | 2021-03-13 | 9 | 2021-03-23 | 6 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-29 | 10 | [11 empty] | 2021-03-29 | 2021-03-29 | 0 | [15 empty] | 2021-03-29 |  |  | 2021-03-29
169 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.68 | No | 2021-03-16 | 2021-03-29 | 9 | 2021-03-29 | 9 | 2021-03-30 | 1 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-03-30 | 1 | [11 empty] | 2021-03-30 | 2021-03-30 | 0 | [15 empty] | 2021-03-30 |  |  | 2021-03-30
170 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 46.533 | No | 2021-03-02 | 2021-03-13 | 8 | 2021-03-13 | 8 | 2021-03-24 | 7 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-31 | 12 | [11 empty] | 2021-03-31 | 2021-03-31 | 0 | [15 empty] | 2021-03-31 |  |  | 2021-03-31
171 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.116 | No | 2021-03-01 | 2021-03-13 | 9 | 2021-03-13 | 9 | 2021-03-23 | 6 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-29 | 10 | [11 empty] | 2021-03-31
172 | PGE | NEM | NEM Paired Storage | Implementation | Solar PV, Storage | 34.014 | No | 2021-03-03 | 2021-03-13 | 7 | 2021-03-13 | 7 | 2021-03-23 | 6 | [15 empty] | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-18 | 3 | [11 empty] | 2021-03-23
173 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 35.36 | No | 2021-03-15 | 2021-03-27 | 9 | 2021-03-27 | 9 | [17 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | 2021-03-30 | 1
174 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 49.798 | No | 2021-03-16 | 2021-03-30 | 10 | [19 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-03-31 | 1
175 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.171 | No | 2021-03-15 | 2021-03-26 | 9 | 2021-03-26 | 9 | [17 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-03-26 | 0
176 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.734 | No | 2021-03-19 | [25 empty] | 2021-03-19 | N/A
177 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.699 | No | 2021-03-24 | [25 empty] | 2021-03-24 | N/A
178 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 35.116 | No | 2021-02-08 | 2021-02-16 | 5 | 2021-03-17 | 26 | 2021-03-22 | 3 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-03-24 | 2
179 | PGE | NEM | NEMMT | Study in Progress | Fuel Cell, Storage | 2115 | No | 2021-02-10 | 2021-02-22 | 7 | 2021-03-21 | 26 | [27 empty] | 2021-03-21 | 2021-03-25 | 3
180 | PGE | NON-NEM | Non-Export | IA in Progress | Storage | 210 | No | 2021-01-21 | 2021-01-25 | 2 | 2021-03-03 | 28 | 2021-03-22 | 13 | [15 empty] | 2021-03-22 | 2021-03-23 | 1 | 2021-03-23 | [6 empty] | 2021-01-21 | [31 empty] | 2021-03-24
181 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 46.538 | No | 2021-03-10 | 2021-03-24 | 10 | 2021-03-24 | 10 | [17 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-03-30 | 4 | [7 empty] | 2021-03-24 | 2021-03-24 | 2021-03-30 | 4
182 | PGE | NON-NEM | Continuous Uncompensated Export | Application Accepted | Solar PV | 625 | No | 2021-02-19 | 2021-02-22 | 1 | 2021-02-24 | 3 | 2021-03-15 | 13 | [15 empty] | 2021-03-15 | 2021-03-31 | 12 | 2021-03-31 | [9 empty] | 2021-03-31
183 | PGE | NEM | EXPNEM | Application Not Submitted | Solar PV | 133.3 | No
184 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 795.8 | No | 2021-03-18 | [31 empty] | 2021-03-18
185 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 333.3 | No | 2021-03-18 | [31 empty] | 2021-03-18
186 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 62.048 | No | 2021-03-22
187 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 266.363 | No | 2021-03-25
188 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 240 | No | 2021-03-29 | [31 empty] | 2021-03-29
189 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 830 | No | 2021-03-26
190 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 36.913 | No | 2021-03-31 | [31 empty] | 2021-03-31
191 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 150.795 | No | 2021-03-31
192 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 | No | 2021-01-15 | 2021-01-19 | 1
193 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 35.713 | No | 2021-01-19 | 2021-01-20 | 1
194 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 343.39 | No | 2021-01-22 | 2021-01-25 | 1 | [29 empty] | 2021-01-22
195 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 86.4 | No | 2021-01-24 | 2021-01-26 | 1 | [29 empty] | 2021-01-24
196 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 32.88 | No | 2021-01-19 | 2021-01-26 | 5
197 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.128 | No | 2021-01-27 | 2021-01-27 | 0 | [29 empty] | 2021-01-27
198 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 802.107 | No | 2021-01-13 | 2021-01-27 | 9 | [29 empty] | 2021-01-13
199 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 52.78 | No | 2021-01-28 | 2021-01-29 | 1
200 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 62.5 | No | 2021-01-15 | 2021-02-01 | 10
201 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 30.277 | No | 2021-02-03 | 2021-02-04 | 1
202 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 299.7 | No | 2021-02-04 | 2021-02-05 | 1 | [29 empty] | 2021-02-04
203 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 44.198 | No | 2021-02-05 | 2021-02-08 | 1
204 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 36 | No | 2021-01-28 | 2021-02-09 | 8
205 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 114.365 | No | 2021-02-09 | 2021-02-10 | 1
206 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 36.312 | No | 2021-02-01 | 2021-02-10 | 7 | [29 empty] | 2021-02-01
207 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 39.926 | No | 2021-02-16 | 2021-02-17 | 1 | [29 empty] | 2021-02-16
208 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 187.5 | No | 2021-02-04 | 2021-02-17 | 8 | [29 empty] | 2021-02-04
209 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 349.494 | No | 2021-02-15 | 2021-02-18 | 2 | [29 empty] | 2021-02-15
210 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 50 | No | 2021-02-23 | 2021-02-24 | 1
211 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 38.779 | No | 2021-02-24 | 2021-02-25 | 1
212 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 395.208 | No | 2021-02-12 | 2021-02-27 | 9 | [29 empty] | 2021-02-12
213 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 100 | No | 2021-02-15 | 2021-03-01 | 9
214 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 240 | No | 2021-02-16 | 2021-03-02 | 10 | [29 empty] | 2021-02-16
215 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 292.8 | No | 2021-03-01 | 2021-03-04 | 3
216 | PGE | NEM | EXPNEM | Application Review in Progress | Engine | 0 | No | 2021-02-24 | 2021-03-05 | 7 | [29 empty] | 2021-04-21
217 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 60.455 | No | 2021-03-05 | 2021-03-08 | 1
218 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 336 | No | 2021-02-23 | 2021-03-08 | 9
219 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 50.848 | No | 2021-02-23 | 2021-03-09 | 10 | [29 empty] | 2021-02-23
220 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 533.3 | No | 2021-02-23 | 2021-03-09 | 10
221 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 65.56 | No | 2021-03-08 | 2021-03-10 | 2 | [29 empty] | 2021-03-08
222 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 39.196 | No | 2021-03-05 | 2021-03-10 | 3
223 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 378.225 | No | 2021-02-25 | 2021-03-11 | 10
224 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 50 | No | 2021-03-09 | 2021-03-11 | 2
225 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 323.042 | No | 2021-03-10 | 2021-03-12 | 2 | [29 empty] | 2021-03-10
226 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 84.418 | No | 2021-02-26 | 2021-03-12 | 10
227 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 460 | No | 2021-03-01 | 2021-03-13 | 9 | [29 empty] | 2021-03-01
228 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.411 | No | 2021-03-11 | 2021-03-15 | 2
229 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 55.546 | No | 2021-03-12 | 2021-03-16 | 2 | [29 empty] | 2021-03-12
230 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 194.901 | No | 2021-03-03 | 2021-03-17 | 10 | [29 empty] | 2021-03-03
231 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 54.472 | No | 2021-03-12 | 2021-03-17 | 3
232 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.2 | No | 2021-03-12 | 2021-03-17 | 3 | [29 empty] | 2021-03-12
233 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.041 | No | 2021-03-12 | 2021-03-17 | 3
234 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 62.5 | No | 2021-03-12 | 2021-03-17 | 3 | [29 empty] | 2021-03-12
235 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 548.77 | No | 2021-03-17 | 2021-03-18 | 1 | [29 empty] | 2021-03-17
236 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 531.086 | No | 2021-03-14 | 2021-03-18 | 3
237 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 500 | No | 2021-03-17 | 2021-03-18 | 1 | [29 empty] | 2021-03-17
238 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 346.458 | No | 2021-03-04 | 2021-03-18 | 10 | [29 empty] | 2021-03-04
239 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 136.1 | No | 2021-03-17 | 2021-03-18 | 1 | [29 empty] | 2021-03-17
240 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 299.7 | No | 2021-03-05 | 2021-03-19 | 10 | [29 empty] | 2021-03-05
241 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 187.5 | No | 2021-03-05 | 2021-03-19 | 10 | [29 empty] | 2021-03-05
243 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.2 | No | 2021-03-17 | 2021-03-19 | 2
244 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.128 | No | 2021-03-17 | 2021-03-19 | 2
245 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 351.986 | No | 2021-03-17 | 2021-03-19 | 2
246 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 403.913 | No | 2021-03-18 | 2021-03-22 | 2 | [29 empty] | 2021-03-18
247 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 780 | No | 2021-03-18 | 2021-03-22 | 2 | [29 empty] | 2021-03-18
248 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 | No | 2021-03-09 | 2021-03-23 | 10 | [29 empty] | 2021-03-09
249 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.78 | No | 2021-03-20 | 2021-03-23 | 1 | [29 empty] | 2021-03-20
250 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 200 | No | 2021-03-22 | 2021-03-24 | 2
251 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 181.876 | No | 2021-03-23 | 2021-03-24 | 1
252 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 34.363 | No | 2021-03-23 | 2021-03-24 | 1
253 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 | No | 2021-03-22 | 2021-03-24 | 2 | [29 empty] | 2021-03-22
254 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 168 | No | 2021-03-12 | 2021-03-25 | 9
255 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 46.08 | No | 2021-03-23 | 2021-03-25 | 2 | [29 empty] | 2021-03-23
256 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 323.852 | No | 2021-03-23 | 2021-03-25 | 2
257 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 121.259 | No | 2021-03-24 | 2021-03-26 | 2 | [29 empty] | 2021-03-24
258 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 41.76 | No | 2021-03-12 | 2021-03-26 | 10 | [29 empty] | 2021-04-11
259 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 86.4 | No | 2021-03-15 | 2021-03-29 | 10 | [29 empty] | 2021-03-15
260 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 36.34 | No | 2021-03-23 | 2021-03-29 | 4
261 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 500 | No | 2021-03-17 | 2021-03-30 | 9 | [29 empty] | 2021-03-17
262 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 506.226 | No | 2021-03-17 | 2021-03-31 | 10 | [29 empty] | 2021-03-17
263 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 516 | No | 2021-03-17 | 2021-03-31 | 10
264 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 44.78 | No | 2021-03-17 | 2021-03-31 | 10 | [29 empty] | 2021-03-17
265 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 300 | No | 2021-03-17 | 2021-03-31 | 10 | [29 empty] | 2021-03-17
266 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 55.485 | No | 2021-03-30 | 2021-03-31 | 1
267 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 124.183 | No | 2021-01-11 | 2021-01-14 | 3 | 2021-01-28 | 12
268 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 92.482 | No | 2021-01-11 | 2021-01-14 | 3 | 2021-01-28 | 12
269 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 88.073 | No | 2021-01-11 | 2021-01-20 | 6 | 2021-01-28 | 12
270 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 33.3 | No | 2021-02-11 | 2021-02-12 | 1 | 2021-02-16 | 2
271 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 875 | No | 2021-01-26 | 2021-02-08 | 9 | 2021-02-19 | 17 | [5 empty] | 2021-02-08 | 2021-03-10 | 21 | 2021-03-10 | [18 empty] | 2021-01-26 |  |  | 2021-02-10
272 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 900 | No | 2021-02-26 | 2021-03-02 | 2 | 2021-03-09 | 7 | [5 empty] | 2021-03-09
273 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 65.59 | No | 2021-03-04 | 2021-03-08 | 2 | 2021-03-12 | 6
274 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 360.183 | No | 2021-03-09 | 2021-03-11 | 2 | 2021-03-15 | 4 | [27 empty] | 2021-03-09
275 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 754.1 | No | 2021-01-29 | 2021-01-29 | 0 | 2021-03-18 | 33 | [27 empty] | 2021-01-29
276 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 33.3 | No | 2021-02-22 | 2021-02-24 | 2 | 2021-03-24 | 22
277 | PGE | NEM | EXPNEM | Study in Progress | Engine | 0 | No | 2021-03-02 | 2021-03-05 | 3 | 2021-03-24 | 16 | [5 empty] | 2021-03-24
278 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 37.186 | No | 2021-03-17 | 2021-03-19 | 2 | 2021-03-24 | 5
279 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 480 | No | 2021-02-18 | 2021-03-04 | 10 | 2021-03-26 | 26
280 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 87.06 | No | 2021-02-18 | 2021-03-04 | 10 | 2021-03-26 | 26
281 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 348 | No | 2021-03-24 | 2021-03-26 | 2 | 2021-03-26 | 2 | [27 empty] | 2021-03-24
282 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 125 | No | 2021-03-12 | 2021-03-26 | 10 | 2021-03-26 | 10
283 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 687.5 | No | 2021-02-03 | 2021-02-04 | 1 | 2021-03-27 | 36 | [27 empty] | 2021-02-03
284 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 337.5 | No | 2021-02-03 | 2021-02-04 | 1 | 2021-03-27 | 36 | [27 empty] | 2021-02-03
285 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 37.598 | No | 2021-03-17 | 2021-03-19 | 2 | 2021-03-29 | 8
286 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 50.209 | No | 2021-03-27 | 2021-03-29 | 0 | 2021-03-29 | 0
287 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 600 | No | 2021-03-12 | 2021-03-17 | 3 | 2021-03-30 | 12 | [27 empty] | 2021-03-12
288 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 110 | No | 2021-03-29 | 2021-03-30 | 1 | 2021-03-30 | 1 | [27 empty] | 2021-03-29
289 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 43.2 | No | 2021-03-29 | 2021-03-30 | 1 | 2021-03-30 | 1 | [27 empty] | 2021-04-12
290 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 236.419 | No | 2021-03-24 | 2021-03-30 | 4 | 2021-03-30 | 4 | [27 empty] | 2021-03-24
291 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 52.108 | No | 2021-02-18 | 2021-02-19 | 1 | 2021-03-31 | 29
292 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 1250 | No | 2021-03-11 | 2021-03-12 | 1 | 2021-03-31 | 14 | [5 empty] | 2021-03-31 | [21 empty] | 2021-03-11
293 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 1125 | No | 2021-03-12 | 2021-03-15 | 1 | 2021-03-31 | 13 | [27 empty] | 2021-03-12
294 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 275 | No | 2021-03-17 | 2021-03-31 | 10 | 2021-03-31 | 10
295 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 500 | No | 2021-03-17 | 2021-03-18 | 1 | [29 empty] | 2021-03-17
296 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 1937.5 | No | 2021-03-29 | 2021-03-31 | 2 | [29 empty] | 2021-03-29
297 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 445.259 | No | 2021-03-24 | [31 empty] | 2021-03-24
298 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 492.045 | No | 2021-03-26 | [31 empty] | 2021-03-26
299 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 35.406 | No | 2021-03-11 | 2021-03-15 | 2 | [29 empty] | 2021-03-11
300 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 31.97 | No | 2021-02-11 | 2021-02-12 | 1
301 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 114.285 | No | 2021-03-28 | 2021-03-30 | 1 | [29 empty] | 2021-03-28
302 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 114.667 | No | 2021-02-11 | 2021-03-01 | 11 | [29 empty] | 2021-02-11 |  |  | 2021-03-11
303 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 72 | No | 2021-03-30 | [31 empty] | 2021-03-30
304 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 266.6 | No | 2021-03-25 | 2021-03-26 | 1
305 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 400 | No | 2021-01-15 | 2021-01-19 | 1 | 2021-03-12 | 38 | 2021-03-12 | 0
306 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 94.548 | No | 2021-02-16 | 2021-02-17 | 1 | 2021-03-08 | 14 | 2021-03-22 | 10 | [25 empty] | 2021-02-16
307 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 36.513 | No | 2021-03-09 | 2021-03-23 | 10 | 2021-03-23 | 10
308 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 1700 | No | 2021-03-04 | 2021-03-08 | 2 | 2021-03-24 | 14 | [27 empty] | 2021-04-12
309 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 230 | No | 2021-02-23 | 2021-02-24 | 1 | 2021-02-25 | 2 | 2021-03-18 | 15 | 2021-03-18 | [24 empty] | 2021-02-23
310 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 62.5 | No | 2021-01-26 | 2021-01-26 | 0 | 2021-02-02 | 5 | 2021-03-19 | 32 | 2021-03-19 | [24 empty] | 2020-02-04
311 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 160 | No | 2021-03-01 | 2021-03-02 | 1 | 2021-03-02 | 1 | 2021-03-19 | 13 | 2021-03-19 | [24 empty] | 2021-03-01
312 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 167.38 | No | 2021-02-19 | 2021-02-22 | 1 | 2021-03-09 | 12 | 2021-03-31 | 16 | 2021-03-31
313 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 828.528 | No | 2021-02-24 | 2021-03-05 | 7 | 2021-03-16 | 14
314 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 133.2 | No | 2021-02-11 | 2021-02-24 | 8 | 2021-03-12 | 20 | 2021-03-26 | 10 | [15 empty] | 2021-03-26 | [9 empty] | 2021-02-11
315 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 31.461 | No | 2021-01-12 | 2021-01-13 | 1 | 2021-01-19 | 4 | 2021-02-02 | 10 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02
316 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 132 | No | 2021-01-15 | 2021-01-19 | 1 | 2021-01-19 | 1 | 2021-02-03 | 11 | [15 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03
317 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 146.8 | No | 2021-01-11 | 2021-01-20 | 6 | 2021-01-28 | 12 | 2021-02-05 | 6 | [15 empty] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05
318 | PGE | NEM | EXPNEM | Withdrawn | Solar PV | 153.25 | No | 2021-01-11 | 2021-01-14 | 3 | 2021-02-02 | 15 | 2021-02-05 | 3 | [15 empty] | 2021-02-05 | 2021-02-08 | 1 | 2021-02-08
319 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 37.54 | No | 2021-01-12 | 2021-01-13 | 1 | 2021-01-29 | 12 | 2021-02-12 | 10 | [15 empty] | 2021-02-12 | 2021-02-12 | 0 | 2021-02-12
320 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 71.771 | No | 2021-01-14 | 2021-01-29 | 10 | 2021-01-29 | 10 | 2021-02-19 | 14 | [15 empty] | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19
321 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 30.159 | No | 2021-01-22 | 2021-01-30 | 5 | 2021-01-30 | 5 | 2021-02-19 | 13 | [15 empty] | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19
322 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 125 | No | 2021-01-15 | 2021-02-01 | 10 | 2021-02-01 | 10 | 2021-02-22 | 14 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | [6 empty] | 2021-01-15
323 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 85.795 | No | 2021-02-03 | 2021-02-17 | 9 | 2021-02-23 | 13 | 2021-03-01 | 4 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01
324 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 50 | No | 2021-02-11 | 2021-02-12 | 1 | 2021-02-18 | 4 | 2021-03-02 | 8 | [15 empty] | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | [6 empty] | 2021-02-11
325 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 72.381 | No | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 0 | 2021-03-03 | 25 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | [6 empty] | 2021-01-26
326 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 84.718 | No | 2021-01-13 | 2021-01-28 | 10 | 2021-02-13 | 21 | 2021-03-07 | 13 | [15 empty] | 2021-03-07 | 2021-03-07 | 0 | 2021-03-07 | [6 empty] | 2021-01-13
327 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 540 | No | 2021-01-15 | 2021-01-24 | 4 | 2021-01-24 | 4 | 2021-03-08 | 29 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | [6 empty] | 2021-01-15
328 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 90.375 | No | 2021-02-22 | 2021-02-23 | 1 | 2021-02-26 | 4 | 2021-03-08 | 6 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | [6 empty] | 2021-02-22
329 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 46.382 | No | 2021-02-22 | 2021-02-24 | 2 | 2021-02-26 | 4 | 2021-03-08 | 6 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08
330 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 187.5 | No | 2021-02-04 | 2021-02-16 | 7 | 2021-02-16 | 7 | 2021-02-19 | 3 | [15 empty] | 2021-02-19 | 2021-03-09 | 12 | 2021-03-09 | [6 empty] | 2021-02-04
331 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 43.741 | No | 2021-02-24 | 2021-02-25 | 1 | 2021-03-01 | 3 | 2021-03-18 | 13 | [15 empty] | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18
332 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 463.916 | No | 2021-02-09 | 2021-02-10 | 1 | 2021-03-02 | 14 | 2021-03-19 | 13 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | [6 empty] | 2021-02-09
333 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 32.109 | No | 2021-02-18 | 2021-02-19 | 1 | 2021-03-02 | 8 | 2021-03-19 | 13 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19
334 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 166.5 | No | 2021-02-16 | 2021-03-02 | 10 | 2021-03-02 | 10 | 2021-03-19 | 13 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19
335 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 54.148 | No | 2021-02-25 | 2021-02-26 | 1 | 2021-03-03 | 4 | 2021-03-22 | 13 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | [6 empty] | 2021-02-25
336 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 136 | No | 2021-03-02 | 2021-03-04 | 2 | 2021-03-04 | 2 | 2021-03-22 | 12 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22
337 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 | No | 2021-03-02 | 2021-03-04 | 2 | 2021-03-10 | 6 | 2021-03-24 | 10 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24
338 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 65.159 | No | 2021-02-26 | 2021-03-02 | 2 | 2021-03-12 | 10 | 2021-03-24 | 8 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24
339 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 45.6 | No | 2021-02-02 | 2021-02-11 | 7 | 2021-02-11 | 7 | 2021-03-25 | 29 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25
340 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 74.396 | No | 2021-03-02 | 2021-03-04 | 2 | 2021-03-08 | 4 | 2021-03-25 | 13 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25
341 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 480 | No | 2021-01-29 | 2021-02-12 | 10 | 2021-02-24 | 17 | 2021-02-26 | 2 | 2021-02-26 | 2021-03-25 | 19 | [12 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25
342 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 | No | 2021-03-02 | 2021-03-04 | 2 | 2021-03-09 | 5 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26
343 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 | No | 2021-03-02 | 2021-03-04 | 2 | 2021-03-09 | 5 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26
344 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 | No | 2021-03-02 | 2021-03-04 | 2 | 2021-03-09 | 5 | 2021-03-26 | 13 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26
345 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 | No | 2021-03-02 | 2021-03-04 | 2 | 2021-03-11 | 7 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26
346 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 38.78 | No | 2021-03-09 | 2021-03-11 | 2 | 2021-03-11 | 2 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | [6 empty] | 2021-03-09
347 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 | No | 2021-03-02 | 2021-03-04 | 2 | 2021-03-12 | 8 | 2021-03-26 | 10 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26
348 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 420 | No | 2021-02-16 | 2021-02-17 | 1 | 2021-03-11 | 17 | 2021-03-27 | 11 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27
349 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 56.965 | No | 2021-01-25 | 2021-01-26 | 1 | 2021-03-01 | 24 | 2021-03-29 | 20 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | [6 empty] | 2021-01-25
350 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 75.259 | No | 2021-03-01 | 2021-03-02 | 1 | 2021-03-12 | 9 | 2021-03-29 | 11 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | [6 empty] | 2021-03-01
351 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 230 | No | 2021-02-14 | 2021-03-01 | 9 | 2021-03-15 | 19 | 2021-03-29 | 10 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29
352 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 470 | No | 2021-03-12 | 2021-03-16 | 2 | 2021-03-16 | 2 | 2021-03-30 | 10 | [15 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | [6 empty] | 2021-03-12
353 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 61.126 | No | 2021-02-24 | 2021-02-26 | 2 | 2021-03-17 | 15 | 2021-03-30 | 9 | [15 empty] | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | [6 empty] | 2021-03-12
354 | PGE | NEM | EXPNEM | Application Accepted | Solar PV | 710.576 | No | 2021-02-16 | 2021-02-17 | 1 | 2021-03-16 | 20 | 2021-03-31 | 11 | [15 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | [6 empty] | 2021-02-16
355 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 100 | No | 2021-02-15 | 2021-02-16 | 0 | 2021-03-18 | 22
356 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 30.159 | No | 2021-03-08 | 2021-03-10 | 2 | 2021-03-24 | 12
357 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 66.6 | No | 2021-02-24 | 2021-02-26 | 2 | 2021-03-18 | 16
358 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 170 | No | 2021-02-23 | 2021-02-24 | 1 | 2021-02-24 | 1 | [27 empty] | 2021-02-23
359 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 32.907 | No | 2021-03-08 | 2021-03-10 | 2 | 2021-03-17 | 7
360 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 99.586 | No | 2021-03-10 | 2021-03-12 | 2 | 2021-03-17 | 5 | [27 empty] | 2021-03-10
361 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 43.2 | No | 2021-03-23 | 2021-03-25 | 2 | 2021-03-25 | 2
362 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 49.123 | No | 2021-03-18 | 2021-03-22 | 2 | 2021-03-26 | 6
363 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 466.6 | No | 2021-03-25 | 2021-03-29 | 2 | 2021-03-31 | 4
364 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 75.885 | No | 2021-03-04 | 2021-03-05 | 1 | 2021-03-19 | 11
365 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 31.5 | No | 2021-03-17 | 2021-03-19 | 2 | 2021-03-23 | 4
366 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 35.852 | No | 2021-03-26 | 2021-03-29 | 1 | 2021-03-29 | 1
367 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 62.5 | No | 2021-03-12 | 2021-03-17 | 3 | 2021-03-19 | 5
368 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 50 | No | 2021-03-15 | 2021-03-18 | 3 | 2021-03-23 | 6 | [27 empty] | 2021-03-15
369 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 765.9 | No | 2021-03-11 | 2021-03-15 | 2 | 2021-03-24 | 9 | [27 empty] | 2021-03-11
370 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 59.888 | No | 2021-03-18 | 2021-03-22 | 2
371 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 969.737 | No | 2021-02-02 | 2021-02-17 | 10 | 2021-03-09 | 24 | 2021-03-23 | 10 | 2021-03-23
372 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 162.027 | No | 2021-03-02 | 2021-03-04 | 2 | 2021-03-08 | 4
373 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 43.2 | No | 2021-03-16 | 2021-03-30 | 10 | 2021-03-30 | 10
374 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 89.207 | No | 2021-03-08 | 2021-03-10 | 2 | 2021-03-26 | 14
375 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 648.528 | No | 2021-01-26 | 2021-02-09 | 10 | 2021-03-01 | 23 | 2021-03-11 | 8 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11
376 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 33.27 | No | 2021-01-22 | 2021-02-26 | 24 | 2021-03-15 | 35
377 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 95.8 | No | 2021-01-18 | 2021-01-25 | 4 | 2021-01-25 | 4 | 2021-02-11 | 13 | [15 empty] | 2021-02-19 | 2021-03-19 | 20 | 2021-03-19 | [6 empty] | 2021-01-18
378 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 85.387 | No | 2021-01-14 | 2021-01-15 | 1 | 2021-01-19 | 2 | 2021-02-01 | 9 | [15 empty] | 2021-02-01 | 2021-02-01 | 0 | 2021-02-01 | [6 empty] | 2021-01-14 | 2021-01-29 | 10
379 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 490 | No | 2021-01-13 | 2021-01-20 | 4 | 2021-01-20 | 4 | 2021-02-03 | 10 | 2021-02-03 | 2021-03-17 | 29 | 2021-03-17 | 2021-03-23 | 4 | 2021-03-23 | [18 empty] | 2021-01-13 | 2021-02-01 | 12
380 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 720 | No | 2021-01-15 | 2021-01-21 | 3 | 2021-01-21 | 3 | [5 empty] | 2021-01-21 | 2021-02-25 | 24 | 2021-02-25 | [18 empty] | 2021-01-15 | 2021-02-02 | 11
381 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 44.337 | No | 2021-01-19 | 2021-01-28 | 7 | 2021-01-28 | 7 | 2021-03-22 | 36 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | [6 empty] | 2021-01-19 | 2021-02-05 | 13
382 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 41.968 | No | 2021-02-01 | 2021-02-02 | 1 | 2021-02-10 | 7 | 2021-03-22 | 27 | [15 empty] | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | [6 empty] | 2021-02-01 | 2021-02-08 | 5
383 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV, Storage | 33.54 | No | 2021-01-21 | 2021-02-04 | 10 | [29 empty] | 2021-01-21 | 2021-02-09 | 13
384 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 400 | No | 2021-02-03 | 2021-02-03 | 0 | 2021-02-22 | 12 | 2021-03-03 | 7 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | [6 empty] | 2021-02-03 | 2021-02-09 | 4
385 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 41.219 | No | 2021-01-12 | 2021-01-13 | 1 | 2021-02-04 | 16 | 2021-03-24 | 33 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | [6 empty] | 2021-01-12 | 2021-02-09 | 19
386 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 33.3 | No | 2021-01-28 | 2021-01-29 | 1 | 2021-01-29 | 1 | 2021-02-11 | 9 | [15 empty] | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | [6 empty] | 2021-01-28 | 2021-02-11 | 10
387 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 38.78 | No | 2021-01-21 | 2021-01-29 | 6 | 2021-02-12 | 16 | 2021-02-26 | 9 | [15 empty] | 2021-02-26 | 2021-03-16 | 12 | 2021-03-16 | [6 empty] | 2021-01-21 | 2021-02-11 | 15
388 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 250 | No | 2021-02-04 | 2021-02-05 | 1 | 2021-02-12 | 6 | 2021-02-22 | 5 | [15 empty] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | [6 empty] | 2021-02-04 | 2021-02-16 | 7
389 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 49.794 | No | 2021-02-02 | 2021-02-11 | 7 | 2021-02-11 | 7 | 2021-02-26 | 10 | [15 empty] | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | [6 empty] | 2021-02-02 | 2021-02-16 | 9
390 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 94.844 | No | 2021-02-10 | 2021-02-23 | 8 | 2021-02-23 | 8 | 2021-03-11 | 12 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | [6 empty] | 2021-02-10 | 2021-02-23 | 8
391 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 172.8 | No | 2021-02-18 | 2021-02-19 | 1 | 2021-02-25 | 5 | [27 empty] | 2021-02-18 | 2021-02-25 | 5
392 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 46.625 | No | 2021-02-09 | 2021-02-10 | 1 | 2021-02-25 | 11 | 2021-03-11 | 10 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | [6 empty] | 2021-02-09 | 2021-02-25 | 11
393 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 150 | No | 2021-02-23 | 2021-02-24 | 1 | 2021-02-26 | 3 | 2021-03-26 | 20 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | [6 empty] | 2021-02-23 | 2021-03-01 | 4
394 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 132.734 | No | 2021-02-02 | 2021-02-03 | 1 | 2021-03-01 | 18 | 2021-03-17 | 12 | 2021-03-17 | [24 empty] | 2021-02-02 | 2021-03-02 | 19
395 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 625 | No | 2021-01-13 | 2021-01-14 | 1 | 2021-01-20 | 4 | 2021-02-02 | 9 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | [6 empty] | 2021-01-13 | 2021-03-02 | 32
396 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 183.3 | No | 2021-01-13 | 2021-01-14 | 1 | 2021-01-20 | 4 | 2021-02-02 | 9 | [15 empty] | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | [6 empty] | 2021-01-13 | 2021-03-02 | 32
397 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 324.18 | No | 2021-01-13 | 2021-01-21 | 5 | 2021-02-25 | 29 | [27 empty] | 2021-02-25 | 2021-03-04 | 5
398 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 154.954 | No | 2021-02-08 | 2021-02-08 | 0 | 2021-03-08 | 19 | [27 empty] | 2021-02-08 | 2021-03-04 | 17
399 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 125 | No | 2021-02-18 | 2021-03-04 | 10 | 2021-03-23 | 23 | 2021-03-30 | 5 | [25 empty] | 2021-02-18 | 2021-03-05 | 11
400 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 247.461 | No | 2021-02-19 | 2021-03-05 | 10 | 2021-03-23 | 22 | 2021-03-30 | 5 | [25 empty] | 2021-02-19 | 2021-03-05 | 10
401 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 53.611 | No | 2021-02-18 | 2021-03-04 | 10 | 2021-03-04 | 10 | 2021-03-23 | 13 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | [6 empty] | 2021-02-18 | 2021-03-05 | 11
402 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 45.572 | No | 2021-01-21 | 2021-01-22 | 1 | 2021-03-01 | 26 | 2021-03-08 | 5 | [15 empty] | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | [6 empty] | 2021-01-21 | 2021-03-08 | 31
403 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 146.495 | No | 2021-02-22 | 2021-02-23 | 1 | 2021-03-03 | 7 | [27 empty] | 2021-02-22 | 2021-03-12 | 14
404 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 250 | No | 2021-02-23 | 2021-03-09 | 10 | 2021-03-09 | 10 | 2021-03-29 | 14 | [25 empty] | 2021-02-23 | 2021-03-12 | 13
405 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 666.6 | No | 2021-01-29 | 2021-02-01 | 1 | 2021-03-10 | 27 | [27 empty] | 2021-01-29 | 2021-03-12 | 29
406 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 437.5 | No | 2021-01-28 | 2021-02-10 | 9 | 2021-02-22 | 16 | 2021-03-05 | 9 | [15 empty] | 2021-03-05 | 2021-03-05 | 0 | 2021-03-05 | [6 empty] | 2021-01-28 | 2021-03-12 | 30
407 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 36 | No | 2021-02-17 | 2021-02-18 | 1 | 2021-03-01 | 8 | 2021-03-19 | 14 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | [6 empty] | 2021-02-17 | 2021-03-12 | 17
408 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 125 | No | 2021-02-11 | 2021-03-12 | 20 | 2021-03-26 | 30 | [27 empty] | 2021-02-11 | 2021-03-15 | 21
409 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 600 | No | 2021-01-29 | 2021-02-01 | 1 | 2021-03-09 | 26 | 2021-03-27 | 13 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | [6 empty] | 2021-01-29 | 2021-03-15 | 30
410 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 633.3 | No | 2021-01-29 | 2021-02-01 | 1 | 2021-03-09 | 26 | [27 empty] | 2021-01-29 | 2021-03-15 | 30
411 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 150 | No | 2021-02-28 | 2021-03-12 | 9 | [29 empty] | 2021-02-28 | 2021-03-16 | 11
412 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 766.6 | No | 2021-01-29 | 2021-02-01 | 1 | 2021-03-16 | 31 | [27 empty] | 2021-01-29 | 2021-03-18 | 33
413 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 34.8 | No | 2021-03-03 | 2021-03-17 | 10 | [29 empty] | 2021-03-03 | 2021-03-24 | 15
414 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 43.421 | No | 2021-03-03 | 2021-03-17 | 10 | [29 empty] | 2021-03-03 | 2021-03-25 | 16
415 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 92.565 | No | 2021-03-04 | 2021-03-18 | 10 | [29 empty] | 2021-03-04 | 2021-03-25 | 15
416 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 31.024 | No | 2021-03-04 | 2021-03-18 | 10 | [29 empty] | 2021-03-04 | 2021-03-25 | 15
417 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 106.105 | No | 2021-03-05 | 2021-03-19 | 10 | [29 empty] | 2021-03-05 | 2021-03-25 | 14
418 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 375 | No | 2021-03-11 | 2021-03-15 | 2 | 2021-03-18 | 5 | [27 empty] | 2021-03-11 | 2021-03-25 | 10
419 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 800 | No | 2021-01-29 | 2021-02-01 | 1 | 2021-03-25 | 38 | [27 empty] | 2021-01-29 | 2021-03-25 | 38
420 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 78.716 | No | 2021-03-05 | 2021-03-19 | 10 | 2021-03-19 | 10 | [27 empty] | 2021-03-05 | 2021-03-25 | 14
421 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 66.6 | No | 2021-01-27 | 2021-01-28 | 1 | 2021-02-03 | 5 | 2021-02-20 | 11 | [15 empty] | 2021-02-20 | 2021-02-20 | 0 | 2021-02-20 | [6 empty] | 2021-01-27 | 2021-03-25 | 40
422 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 80.457 | No | 2021-03-12 | 2021-03-16 | 2 | 2021-03-23 | 7 | [27 empty] | 2021-03-12 | 2021-03-25 | 9
423 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 100 | No | 2021-02-22 | 2021-02-26 | 4 | 2021-03-11 | 13 | 2021-03-27 | 11 | [15 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | [6 empty] | 2021-02-22 | 2021-03-29 | 25
424 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 250 | No | 2021-03-10 | 2021-03-24 | 10 | 2021-03-24 | 10 | [27 empty] | 2021-03-10 | 2021-03-31 | 15
425 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 100 | No | 2021-03-09 | 2021-03-10 | 1 | 2021-03-16 | 5 | [27 empty] | 2021-03-09 | 2021-03-31 | 16
426 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 420 | No | 2021-03-09 | 2021-03-23 | 10 | [29 empty] | 2021-03-09
427 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 96 | No | 2021-02-09 | 2021-02-10 | 1 | 2021-03-24 | 30 | [27 empty] | 2021-02-09
428 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 600 | No | 2021-03-19 | 2021-03-23 | 2 | 2021-03-29 | 6 | [27 empty] | 2021-03-19
429 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 400 | No | 2021-03-19 | 2021-03-23 | 2 | 2021-03-30 | 7 | [27 empty] | 2021-03-19
430 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 225.94 | No | 2021-03-11 | 2021-03-25 | 10 | [29 empty] | 2021-03-11
431 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 37.529 | No | 2021-03-12 | 2021-03-26 | 10 | [29 empty] | 2021-03-12
432 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 97.651 | No | 2021-03-23 | 2021-03-25 | 2 | [29 empty] | 2021-03-23
433 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 38.528 | No | 2021-02-22 | 2021-02-23 | 1 | 2021-03-25 | 23 | [27 empty] | 2021-02-22
434 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 150 | No | 2021-03-23 | 2021-03-25 | 2 | 2021-03-25 | 2 | [27 empty] | 2021-03-23
435 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 142.054 | No | 2021-03-23 | 2021-03-25 | 2 | 2021-03-25 | 2 | [27 empty] | 2021-03-23
436 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 52.163 | No | 2021-03-12 | 2021-03-16 | 2 | 2021-03-25 | 9 | [27 empty] | 2021-03-12
437 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 720 | No | 2021-02-16 | 2021-03-02 | 10 | [29 empty] | 2021-02-16
438 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 33.3 | No | 2021-03-15 | 2021-03-29 | 10 | [29 empty] | 2021-03-15
439 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 85.259 | No | 2021-02-24 | 2021-03-10 | 10 | 2021-03-27 | 22 | [27 empty] | 2021-02-24
440 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 40.153 | No | 2021-03-22 | 2021-03-24 | 2 | 2021-03-30 | 6 | [27 empty] | 2021-03-22
441 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 220 | No | 2021-03-28 | 2021-03-29 | 0 | 2021-03-30 | 1 | [27 empty] | 2021-03-28
442 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 250 | No | 2021-03-28 | 2021-03-30 | 1 | 2021-03-30 | 1 | [27 empty] | 2021-03-28
443 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 33.3 | No | 2021-02-15 | 2021-02-26 | 8 | 2021-02-26 | 8 | 2021-03-15 | 11 | [25 empty] | 2021-02-15
444 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 46.625 | No | 2021-03-18 | [31 empty] | 2021-03-18
445 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 120 | No | 2021-03-17 | 2021-03-31 | 10 | [29 empty] | 2021-03-17
446 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 66.536 | No | 2021-03-24 | 2021-03-26 | 2 | 2021-03-30 | 4 | [27 empty] | 2021-03-24
447 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 64.427 | No | 2021-03-24 | 2021-03-26 | 2 | 2021-03-30 | 4 | [27 empty] | 2021-03-24
448 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 43.2 | No | 2021-03-24 | 2021-03-26 | 2 | 2021-03-30 | 4 | [27 empty] | 2021-03-24
449 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 100 | No | 2021-03-17 | 2021-03-30 | 9 | 2021-03-30 | 9 | [27 empty] | 2021-03-17
450 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 73.552 | No | 2021-03-25 | 2021-03-26 | 1 | 2021-03-31 | 4 | [27 empty] | 2021-03-25
451 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 76.296 | No | 2021-03-30 | 2021-03-31 | 1 | [29 empty] | 2021-03-30
452 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 93.552 | No | 2021-03-25 | [31 empty] | 2021-03-25
453 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 48.72 | No | 2020-12-30 | 2021-01-06 | 4 | 2021-03-12 | 49 | [27 empty] | 2021-04-01
454 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 118.418 | No | 2021-03-19 | [31 empty] | 2021-03-19
455 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 300 | No | 2021-03-04 | 2021-03-17 | 9 | [29 empty] | 2021-03-04
456 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 125 | No | 2021-03-23 | [31 empty] | 2021-03-23
457 | PGE | NEM | EXPNEM | Study in Progress | Solar PV | 43.593 | No | 2021-02-19 | 2021-03-05 | 10 | 2021-03-22 | 21 | [27 empty] | 2021-02-19
458 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 1100 | No | 2021-03-03 | 2021-03-05 | 2 | 2021-03-31 | 20 | [27 empty] | 2021-03-03
459 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 69.31 | No | 2021-03-17 | 2021-03-19 | 2 | [29 empty] | 2021-03-17
460 | PGE | NEM | EXPNEM | Application Review in Progress | Solar PV | 110 | No | 2021-03-26 | [31 empty] | 2021-04-06
461 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 150 | No | 2021-01-14 | 2021-01-15 | 1 | 2021-01-19 | 2 | 2021-01-26 | 5 | [15 empty] | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | [6 empty] | 2021-01-14 | 2021-01-28 | 9
462 | PGE | NEM | EXPNEM | IA in Progress | Solar PV | 258.2 | No | 2021-03-09 | 2021-03-11 | 2 | 2021-03-17 | 6 | 2021-03-26 | 7 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26
463 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.588 | No | 2021-03-25
464 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.894 | No | 2021-03-26
465 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 860.047 | No | 2021-03-18 | [31 empty] | 2021-03-18
466 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.135 | No | 2021-03-18
467 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 862 | No | 2021-03-17 | [31 empty] | 2021-03-17
468 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.734 | No | 2021-03-26
469 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.424 | No | 2021-01-20 | 2021-02-03 | 10
470 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 87.158 | No | 2021-02-04 | 2021-02-05 | 1
471 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 48.51 | No | 2021-01-25 | 2021-02-08 | 10
472 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 41.683 | No | 2021-02-08 | 2021-02-16 | 5 | [29 empty] | 2021-02-08
473 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 59.865 | No | 2021-02-03 | 2021-02-18 | 10
474 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Engine, Solar PV, Storage | 750 | No | 2021-02-08 | 2021-02-22 | 9
475 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.54 | No | 2021-02-08 | 2021-02-23 | 10
476 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Storage | 116.592 | No | 2021-02-11 | 2021-02-24 | 8 | [29 empty] | 2021-02-11
477 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Storage | 116.592 | No | 2021-02-11 | 2021-02-24 | 8 | [29 empty] | 2021-02-11
478 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 599.179 | No | 2021-02-16 | 2021-02-26 | 8 | [29 empty] | 2021-02-16
479 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 32.254 | No | 2021-02-17 | 2021-03-01 | 8
480 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 52.904 | No | 2021-02-26 | 2021-03-12 | 10
481 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1395.292 | No | 2021-03-04 | 2021-03-17 | 9
482 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.144 | No | 2021-03-08 | 2021-03-22 | 10
483 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.689 | No | 2021-03-09 | 2021-03-23 | 10
484 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 37.6 | No | 2021-03-15 | 2021-03-26 | 9
485 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1161.9 | No | 2021-03-17 | 2021-03-31 | 10 | [29 empty] | 2021-03-17
486 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 761.598 | No | 2021-03-17 | 2021-03-31 | 10
487 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 39.195 | No | 2021-03-25 | 2021-03-31 | 4
488 | PGE | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1572 | No | 2021-02-03 | 2021-02-05 | 2 | 2021-02-10 | 5 | [27 empty] | 2021-02-03
489 | PGE | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1872 | No | 2021-02-03 | 2021-02-05 | 2 | 2021-02-17 | 9 | [27 empty] | 2021-02-03
490 | PGE | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1542.8 | No | 2021-02-03 | 2021-02-05 | 2 | 2021-02-17 | 9 | [27 empty] | 2021-02-03
491 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 41.6 | No | 2021-02-09 | 2021-03-08 | 18 | 2021-03-19 | 27
492 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1315.854 | No | 2021-01-29 | 2021-02-05 | 5 | [29 empty] | 2021-01-29
493 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1236.654 | No | 2021-01-29 | 2021-02-05 | 5 | [29 empty] | 2021-01-29
494 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 1228.354 | No | 2021-02-03 | 2021-02-08 | 3 | [29 empty] | 2021-02-03
495 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.734 | No | 2021-03-26
496 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 1309.5 | No | 2021-01-29 | 2021-02-13 | 10 | [29 empty] | 2021-01-29
497 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 1405.3 | No | 2021-02-03 | 2021-02-16 | 8 | [29 empty] | 2021-02-03
498 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.309 | No | 2021-03-23
499 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.559 | No | 2021-03-31 | [31 empty] | 2021-03-31
500 | PGE | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1547 | No | 2021-02-03 | 2021-02-04 | 1 | 2021-02-10 | 5 | [27 empty] | 2021-02-03
501 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 39.131 | No | 2021-03-27
502 | PGE | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1750.732 | No | 2021-02-08 | 2021-02-10 | 2 | 2021-03-10 | 21 | 2021-03-31 | 15 | [25 empty] | 2021-02-08
503 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 39.319 | No | 2021-03-25 | 2021-03-31 | 4 | [19 empty] | 2021-03-31
504 | PGE | NEM | NEM Paired Storage | Study in Progress | Solar PV, Storage | 84.17 | No | 2021-02-04 | 2021-02-10 | 4 | 2021-03-21 | 30
505 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 39.4 | No | 2021-01-07 | 2021-01-12 | 3 | 2021-01-12 | 3 | 2021-01-15 | 3 | [15 empty] | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12
506 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 32.828 | No | 2021-02-10 | 2021-02-18 | 5 | 2021-02-18 | 5 | 2021-02-22 | 2 | [15 empty] | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18
507 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 33.877 | No | 2021-02-03 | 2021-02-06 | 2 | 2021-02-19 | 11 | 2021-03-03 | 8 | [15 empty] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03
508 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 33.62 | No | 2021-02-22 | 2021-03-06 | 9 | [19 empty] | 2021-03-06 | 2021-03-06 | 0 | 2021-03-06
509 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 42.28 | No | 2021-02-25 | 2021-03-09 | 8 | 2021-03-09 | 8 | 2021-03-24 | 11 | [15 empty] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09
510 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 34.88 | No | 2021-02-02 | 2021-02-16 | 9 | 2021-03-12 | 27 | 2021-03-18 | 4 | [15 empty] | 2021-03-12 | 2021-03-12 | 0 | 2021-03-12
511 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 45.177 | No | 2021-02-08 | 2021-02-23 | 10 | 2021-03-16 | 25 | 2021-03-22 | 4 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16
512 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 34.49 | No | 2021-02-09 | 2021-02-24 | 10 | 2021-03-16 | 24 | 2021-03-24 | 6 | [15 empty] | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16
513 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 32.728 | No | 2021-03-05 | 2021-03-19 | 10 | 2021-03-19 | 10 | 2021-03-22 | 1 | [15 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19
514 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 47.78 | No | 2021-03-08 | 2021-03-19 | 9 | [19 empty] | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19
515 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 31.997 | No | 2021-03-09 | 2021-03-20 | 8 | 2021-03-20 | 8 | [17 empty] | 2021-03-20 | 2021-03-20 | 0 | 2021-03-20
516 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 39.994 | No | 2021-03-10 | 2021-03-23 | 9 | [19 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23
517 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 32.38 | No | 2021-03-10 | 2021-03-23 | 9 | 2021-03-23 | 9 | [17 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23
518 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.08 | No | 2021-03-11 | 2021-03-24 | 9 | [19 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24
519 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 31.82 | No | 2021-03-11 | 2021-03-24 | 9 | 2021-03-24 | 9 | [17 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24
520 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 31.361 | No | 2021-01-20 | 2021-02-03 | 10 | 2021-03-25 | 45 | 2021-03-26 | 1 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25
521 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 42.716 | No | 2021-03-12 | 2021-03-25 | 9 | 2021-03-25 | 9 | 2021-03-29 | 2 | [15 empty] | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25
522 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 36.53 | No | 2021-03-12 | 2021-03-26 | 10 | [19 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26
523 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 35.715 | No | 2021-03-15 | 2021-03-27 | 9 | [19 empty] | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27
524 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 43.665 | No | 2021-03-15 | 2021-03-29 | 10 | 2021-03-29 | 10 | [17 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29
525 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 34.348 | No | 2021-01-13 | 2021-01-23 | 6 | 2021-03-09 | 37 | 2021-03-29 | 14 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29
526 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 34.887 | No | 2021-03-16 | 2021-03-29 | 9 | 2021-03-29 | 9 | 2021-03-30 | 1 | [15 empty] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29
527 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 36.52 | No | 2021-03-19
528 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 38.86 | No | 2021-03-22
529 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.234 | No | 2021-03-22
530 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.427 | No | 2021-03-24 | [31 empty] | 2021-03-24
531 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 58.678 | No | 2021-03-24
532 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 35.116 | No | 2021-03-24
533 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.116 | No | 2021-03-24 | [31 empty] | 2021-03-24
534 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 47.633 | No | 2021-03-25 | [31 empty] | 2021-03-25
535 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.232 | No | 2021-01-27 | 2021-02-10 | 10
536 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 43.429 | No | 2021-03-29 | [31 empty] | 2021-03-29
537 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.08 | No | 2021-03-30
538 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 56.873 | No | 2021-02-23 | 2021-03-06 | 8 | 2021-03-06 | 8 | 2021-03-18 | 8 | [15 empty] | 2021-03-06 | 2021-03-06 | 0 | 2021-03-06
539 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 38.622 | No | 2021-03-22
540 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 31 | No | 2021-02-02 | 2021-02-16 | 9 | 2021-03-17 | 30 | 2021-03-25 | 6 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17
541 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 51.699 | No | 2021-01-12 | 2021-01-23 | 7 | 2021-03-03 | 34 | 2021-03-23 | 14 | [15 empty] | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | [6 empty] | 2021-01-12 | 2021-03-05 | 36
542 | PGE | NEM | NEM Paired Storage | Application Accepted | Solar PV, Storage | 1451.1 | No | 2021-01-29 | 2021-02-02 | 2 | 2021-02-10 | 8 | [27 empty] | 2021-01-29 | 2021-03-23 | 36
543 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 96.54 | No | 2021-03-17 | 2021-03-31 | 10 | [29 empty] | 2021-03-17
544 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 33.558 | No | 2021-03-26 | [31 empty] | 2021-03-26
545 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 37.345 | No | 2021-03-23 | [31 empty] | 2021-03-23
546 | PGE | NEM | NEM Paired Storage | IA in Progress | Solar PV, Storage | 30.36 | No | 2021-03-12 | 2021-03-26 | 10 | 2021-03-26 | 10 | 2021-03-29 | 1 | [15 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26
547 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 30.116 | No | 2021-03-23
548 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 34.734 | No | 2021-03-19
549 | PGE | NEM | NEM Paired Storage | Application Review in Progress | Solar PV, Storage | 31.26 | No | 2021-03-17 | 2021-03-31 | 10 | 2021-03-31 | 10 | [17 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31
550 | PGE | NON-NEM | NEMFC | Study in Progress | Fuel Cell | 262.5 | No | 2021-03-08 | 2021-03-11 | 3 | 2021-03-11 | 3 | [17 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | [6 empty] | 2021-03-08
551 | PGE | NEM | NEMMT | Application Review in Progress | Solar PV, Storage | 60.619 | No | 2021-03-31
552 | PGE | NEM | NEMMT | Application Review in Progress | Solar PV, Storage | 31.34 | No | 2021-01-21 | 2021-02-04 | 10
553 | PGE | NEM | NEMMT | Application Review in Progress | Solar PV, Storage | 894.727 | No | 2021-02-08 | 2021-02-22 | 9 | [29 empty] | 2021-02-08
554 | PGE | NEM | NEMMT | Application Review in Progress | Fuel Cell, Solar PV | 544 | No | 2021-02-17 | 2021-03-02 | 9
555 | PGE | NEM | NEMMT | Application Review in Progress | Fuel Cell, Other, Solar PV | 9958.721 | No | 2021-03-29 | 2021-03-30 | 1
556 | PGE | NEM | NEMMT | Application Review in Progress | Engine, Fuel Cell | 900 | No | 2021-03-16 | 2021-03-30 | 10
557 | PGE | NEM | NEMMT | Study in Progress | Solar PV, Turbine | 11000 | No | 2021-01-12 | 2021-01-12 | 0 | 2021-02-03 | 15 | [5 empty] | 2021-02-03 | 2021-03-03 | 19 | 2021-03-03 | 2021-03-18 | 11 |  |  |  | 2021-03-18 | 2021-04-07 | 14 | [10 empty] | 2021-01-12
558 | PGE | NEM | NEMMT | Study in Progress | Solar PV, Turbine | 28119.791 | No | 2020-12-29 | 2021-01-04 | 3 | 2021-02-10 | 29 | [5 empty] | 2021-02-10 | 2021-03-22 | 27 | 2021-03-22 | [5 empty] | 2021-04-12
559 | PGE | NEM | NEMMT | Study in Progress | Engine, Solar PV, Storage | 4580 | No | 2021-01-29 | 2021-02-01 | 1 | 2021-02-17 | 12 | [5 empty] | 2021-02-17 | 2021-03-15 | 18 | 2021-03-15 | 2021-03-17 | 2 | 2021-03-29 |  |  | 2021-03-17 | 2021-03-17 | 0 | [10 empty] | 2021-01-29
560 | PGE | NEM | NEMMT | Study in Progress | Fuel Cell, Solar PV, Wind | 6689.431 | No | 2021-02-08 | 2021-02-22 | 9 | 2021-02-22 | 9 | [5 empty] | 2021-02-22
561 | PGE | NEM | NEMMT | Application Accepted | Fuel Cell, Solar PV, Storage | 5119 | No | 2021-02-11 | 2021-02-16 | 2 | 2021-03-03 | 13 | [27 empty] | 2021-02-11
562 | PGE | NEM | NEMMT | Study in Progress | Fuel Cell, Solar PV | 2055 | No | 2021-02-01 | 2021-02-17 | 11 | 2021-03-27 | 38 | [5 empty] | 2021-03-27 | [21 empty] | 2021-04-09
563 | PGE | NEM | NEMMT | Study in Progress | Fuel Cell, Solar PV | 769 | No | 2021-02-09 | 2021-02-22 | 8 | 2021-03-29 | 33
564 | PGE | NEM | NEMMT | Study in Progress | Fuel Cell, Solar PV | 1000 | No | 2021-01-21 | 2021-02-04 | 10 | 2021-02-12 | 16 | 2021-03-05 | 14 | 2021-03-05 | [24 empty] | 2021-01-21
565 | PGE | NEM | NEMMT | IA in Progress | Solar PV, Storage | 30.104 | No | 2021-03-05 | 2021-03-17 | 8 | 2021-03-17 | 8 | 2021-03-22 | 3 | [15 empty] | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17
566 | PGE | NON-NEM | Non-Export | Application Accepted | Storage | 140 | No | 2021-02-09 | 2021-02-11 | 2 | 2021-03-03 | 15 | [27 empty] | 2021-03-04 | 2021-03-04 | 0
567 | PGE | NON-NEM | Non-Export | Application Accepted | Storage | 140 | No | 2021-02-10 | 2021-02-11 | 1 | 2021-03-03 | 14 | [27 empty] | 2021-02-10 | 2021-03-05 | 16 |  | 2021-03-22
568 | PGE | NON-NEM | Non-Export | Application Accepted | Storage | 350 | No | 2021-01-13 | 2021-01-14 | 1 | 2021-02-03 | 14
569 | PGE | NON-NEM | Non-Export | Application Accepted | Storage | 210 | No | 2021-01-15 | 2021-01-19 | 1 | 2021-02-03 | 12
570 | PGE | NON-NEM | Non-Export | Application Accepted | Storage | 350 | No | 2021-02-09 | 2021-02-11 | 2 | 2021-03-03 | 15
571 | PGE | NON-NEM | Non-Export | Application Accepted | Storage | 350 | No | 2021-02-09 | 2021-02-11 | 2 | 2021-03-03 | 15
572 | PGE | NON-NEM | Non-Export | Application Accepted | Storage | 140 | No | 2021-02-23 | 2021-02-24 | 1 | 2021-03-10 | 11 | [27 empty] | 2021-02-23
573 | PGE | NON-NEM | Non-Export | Application Accepted | Engine, Solar PV | 23407.2 | No | 2021-02-22 | 2021-02-23 | 1 | 2021-03-17 | 17
574 | PGE | NON-NEM | Non-Export | Application Review in Progress | Storage | 3000 | No | 2021-03-22 | 2021-03-23 | 1 | 2021-03-31 | 7
575 | PGE | NON-NEM | Non-Export | Withdrawn | Storage û EV | 0 | No | 2021-02-08 | 2021-02-09 | 1 | 2021-02-24 | 11 | 2021-03-01 | 3
576 | PGE | NON-NEM | Non-Export | Study in Progress | Storage | 1287 | No | 2021-02-20 | 2021-02-22 | 0 | 2021-03-03 | 7 | 2021-03-24 | 15 | [25 empty] | 2021-02-20
577 | PGE | NON-NEM | Non-Export | IA in Progress | Storage | 980 | No | 2021-01-04 | 2021-01-05 | 1 | 2021-02-03 | 21 | [17 empty] | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | [6 empty] | 2021-01-04
578 | PGE | NON-NEM | Non-Export | IA in Progress | Engine, Solar PV | 266.6 | No | 2021-01-12 | 2021-01-14 | 2 | 2021-01-27 | 10 | 2021-03-01 | 22 | [15 empty] | 2021-03-19 | 2021-03-22 | 1 | 2021-03-22
579 | PGE | NON-NEM | Non-Export | IA in Progress | Storage | 1287 | No | 2021-02-20 | 2021-02-22 | 0 | 2021-03-03 | 7 | 2021-03-24 | 15 | [15 empty] | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | [6 empty] | 2021-02-20
580 | PGE | NON-NEM | Non-Export | IA in Progress | Storage | 140 | No | 2021-02-26 | 2021-03-01 | 1 | 2021-03-24 | 18 | [17 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26
581 | PGE | NON-NEM | Non-Export | IA in Progress | Storage | 140 | No | 2021-03-03 | 2021-03-05 | 2 | 2021-03-24 | 15 | [17 empty] | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26
582 | PGE | NON-NEM | Non-Export | Application Accepted | Storage | 715 | No | 2021-02-18 | 2021-02-19 | 1 | 2021-03-03 | 9
583 | PGE | NON-NEM | Non-Export | Application Accepted | Storage | 420 | No | 2021-02-17 | 2021-02-18 | 1 | 2021-03-10 | 15 | [27 empty] | 2021-02-17
584 | PGE | NON-NEM | Non-Export | IA in Progress | Storage | 140 | No | 2021-01-05 | 2021-01-06 | 1 | 2021-01-27 | 15 | 2021-03-09 | 28 | [15 empty] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | [6 empty] | 2021-01-05 | 2021-02-05 | 22
585 | PGE | NON-NEM | Non-Export | IA in Progress | Storage | 210 | No | 2021-01-15 | 2021-01-19 | 1 | 2021-02-03 | 12 | 2021-03-11 | 25 | [15 empty] | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | [6 empty] | 2021-01-15 | 2021-02-09 | 16
586 | PGE | NON-NEM | Non-Export | Application Accepted | Storage | 210 | No | 2021-02-11 | 2021-02-16 | 2 | 2021-03-03 | 13 | [27 empty] | 2021-02-11 | 2021-03-16 | 22
587 | PGE | NON-NEM | RESBCT | Application Review in Progress | Solar PV | 5000 | No | 2021-03-30 | 2021-03-30 | 0
588 | PGE | NON-NEM | RESBCT | Study in Progress | Solar PV | 2341.786 | No | 2021-02-16 | 2021-02-17 | 1 | 2021-02-24 | 6 | [5 empty] | 2021-03-03 | 2021-03-24 | 15 | 2021-03-24 | [18 empty] | 2021-02-16
589 | PGE | NON-NEM | RESBCT | Application Accepted | Solar PV | 2782.651 | No | 2021-03-08 | 2021-03-09 | 1 | 2021-03-24 | 12 | [27 empty] | 2021-03-08
590 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 38.28 | No | 2021-03-24 | [31 empty] | 2021-03-24
591 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 73.65 | No | 2021-01-22 | 2021-02-05 | 10
592 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 31.024 | No | 2021-02-27 | 2021-03-10 | 7
593 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 86.4 | No | 2021-03-15 | 2021-03-23 | 6
594 | PGE | NEM | VNEM | IA in Progress | Solar PV | 38.78 | No | 2021-01-25 | 2021-02-08 | 10 | 2021-03-12 | 33 | 2021-03-24 | 8 | [15 empty] | 2021-03-24 | [9 empty] | 2021-01-25
595 | PGE | NEM | VNEM | Application Accepted | Solar PV | 212.165 | No | 2021-03-01 | 2021-03-10 | 7 | 2021-03-18 | 13 | [27 empty] | 2021-03-01 | 2021-03-25 | 18
596 | PGE | NEM | VNEM | Application Review in Progress | Solar PV | 41.895 | No | 2021-03-12 | 2021-03-22 | 6 | [29 empty] | 2021-03-12
597 | PGE | NEM | VNEM | IA in Progress | Solar PV | 150 | No | 2021-01-20 | 2021-02-03 | 10 | 2021-03-05 | 31 | 2021-03-25 | 14 | [15 empty] | 2021-03-25 | [9 empty] | 2021-03-05 | 2021-03-08 | 1 |  | 2021-03-11 | 2021-03-11
598 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 30.402 | No | 2021-02-18 | 2021-03-05 | 11 | 2021-03-16 | 18 | 2021-03-16 | 0 | [15 empty] | 2021-03-16 | 2021-04-06 | 15 | [7 empty] | 2021-02-18 | 2021-03-12 | 16 |  | 2021-03-24
599 | PGE | NEM | VNEMMASH | Application Accepted | Solar PV | 52.493 | No | 2021-02-26 | 2021-03-10 | 8 | 2021-03-16 | 12 | [27 empty] | 2021-02-26 | 2021-03-23 | 17 |  | 2021-03-26
600 | PGE | NEM | VNEMMASH | Study in Progress | Solar PV | 43.53 | No | 2021-02-17 | 2021-03-05 | 12 | [29 empty] | 2021-02-17
601 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 39.976 | No | 2021-02-26 | 2021-03-11 | 9 | [29 empty] | 2021-02-26
602 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 39.976 | No | 2021-02-26 | 2021-03-12 | 10 | [29 empty] | 2021-02-26
603 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 39.976 | No | 2021-02-26 | 2021-03-12 | 10 | [29 empty] | 2021-02-26
604 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 39.976 | No | 2021-02-26 | 2021-03-12 | 10 | [29 empty] | 2021-02-26
605 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 39.976 | No | 2021-02-26 | 2021-03-12 | 10 | [29 empty] | 2021-02-26
606 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 39.976 | No | 2021-02-26 | 2021-03-12 | 10 | 2021-03-31 | 23 | [27 empty] | 2021-02-26
607 | PGE | NEM | VNEMMASH | Application Review in Progress | Solar PV | 39.976 | No | 2021-02-26 | 2021-03-12 | 10 | 2021-03-31 | 23 | [27 empty] | 2021-02-26
608 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 42.168 | No | 2021-02-24 | 2021-03-09 | 9 | 2021-03-11 | 11 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | [9 empty] | 2021-02-24 | 2021-03-16 | 14
609 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 34.179 | No | 2021-02-24 | 2021-03-09 | 9 | 2021-03-11 | 11 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | [9 empty] | 2021-02-24 | 2021-03-16 | 14
610 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 34.179 | No | 2021-02-24 | 2021-03-09 | 9 | 2021-03-11 | 11 | 2021-03-26 | 11 | [15 empty] | 2021-03-26 | [9 empty] | 2021-02-24 | 2021-03-16 | 14
611 | PGE | NEM | VNEMMASH | Application Accepted | Solar PV | 34.121 | No | 2021-02-24 | 2021-03-09 | 9 | 2021-03-15 | 13 | [27 empty] | 2021-02-24 | 2021-03-17 | 15
612 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 37.983 | No | 2021-02-26 | 2021-03-10 | 8 | 2021-03-16 | 12 | 2021-03-26 | 8 | [15 empty] | 2021-03-26 | [9 empty] | 2021-02-26 | 2021-03-19 | 15
613 | PGE | NEM | VNEMMASH | Application Accepted | Solar PV | 43.53 | No | 2021-03-02 | 2021-03-09 | 5 | 2021-03-17 | 11 | 2021-03-31 | 10 | [15 empty] | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | [6 empty] | 2021-03-02 | 2021-03-31 | 21
614 | PGE | NEM | VNEMMASH | Application Accepted | Solar PV | 37.983 | No | 2021-03-02 | 2021-03-09 | 5 | 2021-03-16 | 10 | [27 empty] | 2021-03-02 | 2021-03-31 | 21
615 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 30.402 | No | 2021-02-17 | 2021-03-05 | 12 | 2021-03-15 | 18 | 2021-03-24 | 7 | [15 empty] | 2021-03-24 | 2021-04-14 | 15 | [7 empty] | 2021-02-17
616 | PGE | NEM | VNEMMASH | IA in Progress | Solar PV | 63.72 | No | 2021-02-17 | 2021-03-05 | 12 | 2021-03-15 | 18 | 2021-03-24 | 7 | [15 empty] | 2021-03-24 | 2021-04-14 | 15 | [7 empty] | 2021-02-17 | 2021-03-11 | 16 |  | 2021-03-24
617 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 68.358 | No | 2021-02-02 | 2021-02-17 | 10 | 2021-02-22 | 13 | 2021-03-16 | 16 | [15 empty] | 2021-03-16 | [9 empty] | 2021-02-02 | 2021-02-24 | 15 |  | 2021-03-12
618 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 75.636 | No | 2021-01-28 | 2021-02-11 | 10 | 2021-03-16 | 32 | [27 empty] | 2021-01-28 | 2021-03-18 | 34 |  | 2021-03-18
619 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 60.446 | No | 2021-01-12 | 2021-01-27 | 10 | [29 empty] | 2021-01-12 | 2021-03-23 | 48 |  | 2021-03-24
620 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 95.363 | No | 2021-03-02 | 2021-03-15 | 9 | 2021-03-17 | 11 | [27 empty] | 2021-03-26
621 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 64.705 | No | 2021-03-30 | [31 empty] | 2021-03-30
622 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 41.246 | No | 2021-02-02 | 2021-02-17 | 10 | [29 empty] | 2021-02-02
623 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 65.629 | No | 2021-02-09 | 2021-02-23 | 9 | [29 empty] | 2021-02-09
624 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 58.04 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
625 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
626 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
627 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
628 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
629 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
630 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
631 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
632 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.53 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
633 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 39.172 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
634 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 38.052 | No | 2021-02-11 | 2021-02-26 | 10 | [29 empty] | 2021-02-11
635 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 34.867 | No | 2021-02-15 | 2021-03-05 | 13 | [29 empty] | 2021-02-15
636 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 34.8 | No | 2021-02-15 | 2021-03-05 | 13 | [29 empty] | 2021-02-15
637 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 34.281 | No | 2021-02-15 | 2021-03-05 | 13 | [29 empty] | 2021-02-15
638 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 34.22 | No | 2021-02-14 | 2021-03-05 | 13 | [29 empty] | 2021-02-14
639 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 33.93 | No | 2021-02-14 | 2021-03-05 | 13 | [29 empty] | 2021-02-14
640 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 33.35 | No | 2021-02-14 | 2021-03-05 | 13 | [29 empty] | 2021-02-14
641 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 46.766 | No | 2021-01-04 | 2021-01-12 | 6 | 2021-01-12 | 6 | [5 empty] | 2021-01-12 | 2021-01-23 | 7 | 2021-01-23 | [18 empty] | 2021-01-04
642 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 65.584 | No | 2021-02-08 | 2021-02-23 | 10 | 2021-03-30 | 35 | [5 empty] | 2021-03-30 | [21 empty] | 2021-02-08
643 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 43.2 | No | 2021-02-02 | 2021-02-12 | 8 | [29 empty] | 2021-02-02
644 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 115.42 | No | 2021-02-16 | 2021-03-05 | 13 | [29 empty] | 2021-02-16
645 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 68.358 | No | 2021-03-12 | 2021-03-23 | 7 | [29 empty] | 2021-03-12
646 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 93.569 | No | 2021-03-12 | 2021-03-26 | 10 | [29 empty] | 2021-03-12
647 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 69.12 | No | 2021-02-17 | 2021-03-05 | 12 | 2021-03-05 | 12 | 2021-03-25 | 14 | [25 empty] | 2021-02-17 | 2021-03-11 | 16
648 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 34.179 | No | 2021-03-12 | 2021-03-23 | 7 | 2021-03-26 | 10 | [27 empty] | 2021-03-12
649 | PGE | NEM | VNEMSOMAH | Application Accepted | Solar PV | 86.4 | No | 2021-02-26 | 2021-03-10 | 8 | 2021-03-16 | 12 | [27 empty] | 2021-03-10
650 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 61.783 | No | 2021-01-12 | 2021-01-27 | 10 | [29 empty] | 2021-01-12
651 | PGE | NEM | VNEMSOMAH | Application Review in Progress | Solar PV | 100 | No | 2021-01-25 | 2021-02-08 | 10 | [29 empty] | 2021-01-25
652 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 52.868 | No | 2021-03-12 | 2021-03-23 | 7 | 2021-03-26 | 10 | [27 empty] | 2021-03-12
653 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100.91 | No | 2021-02-11 | 2021-02-24 | 8 | 2021-02-24 | 8 | 2021-03-16 | 14 | [15 empty] | 2021-03-16 | 2021-04-06 | 15 | [7 empty] | 2021-02-24 | 2021-02-25 | 1 |  | 2021-03-04 | 2021-03-12
654 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 100.91 | No | 2021-02-11 | 2021-02-26 | 10 | 2021-02-26 | 10 | 2021-03-17 | 13 | [15 empty] | 2021-03-17 | 2021-04-06 | 14 | [7 empty] | 2021-02-26 | 2021-03-01 | 1 |  | 2021-03-04 | 2021-03-12
655 | PGE | NEM | VNEMSOMAH | IA in Progress | Solar PV | 72.22 | No | 2021-02-11 | 2021-02-26 | 10 | 2021-02-26 | 10 | 2021-03-17 | 13 | [15 empty] | 2021-03-17 | 2021-04-06 | 14 | [7 empty] | 2021-02-26 | 2021-03-10 | 8 |  | 2021-03-12 | 2021-03-12
656 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 115.42 | No | 2021-02-12 | 2021-03-03 | 12 | 2021-03-05 | 14 | [27 empty] | 2021-02-12 | 2021-03-10 | 17 |  | 2021-03-24
657 | PGE | NEM | VNEMSOMAH | Study in Progress | Solar PV | 111.038 | No | 2021-03-04 | 2021-03-15 | 7 | 2021-03-15 | 7 | [27 empty] | 2021-03-04

## Delay Notice Report Template
Notification No | Key | Category | Planned finish | Delay Reason Desc
112143413 | 1 | Construction True-up Report Sent | 2021-05-31 | Customer – requirement to provide corrected information
112143413 | 1 | Construction True-up Report Sent | 2021-06-30 | Customer – requirement to provide corrected information
112143413 | 1 | Construction True-up Report Sent | 2021-07-31 | Customer – requirement to provide corrected information
113010764 | 2 | Construction True-up Report Sent | 2021-06-30 | Project Management – requiring more detailed review
113161988 | 3 | Conduct: SIS | 2021-05-24 | Engineering – requiring more detailed review
113161988 | 3 | Conduct: SIS | 2021-05-31 | Engineering – requiring more detailed review
114112849 | 4 | Construction True-up Report Sent | 2021-05-31 | Project Management – requiring more detailed review
114112849 | 4 | Construction True-up Report Sent | 2021-06-30 | Project Management – requiring more detailed review
114112992 | 5 | Construction True-up Report Sent | 2021-09-30 | Engineering – requiring more detailed review
114200622 | 6 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
114200622 | 6 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
114200622 | 6 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
114200622 | 6 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
114202400 | 7 | Construction True-up Report Sent | 2021-06-30 | Project Management – requiring more detailed review
114205350 | 8 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
114205350 | 8 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
114205350 | 8 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
114205350 | 8 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
114205849 | 9 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
114205849 | 9 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
114205849 | 9 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
114205893 | 10 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
114205893 | 10 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-05-13 | Project Management – addressing a human error
114206681 | 11 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
114206681 | 11 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
114206681 | 11 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
114206681 | 11 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
114207158 | 12 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
114207158 | 12 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
114207158 | 12 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
114207158 | 12 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
114207158 | 12 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
114207158 | 12 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
114208382 | 13 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
114208382 | 13 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
114208382 | 13 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
114208382 | 13 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
114208382 | 13 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
114208382 | 13 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
114208927 | 14 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
114208927 | 14 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
114208927 | 14 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
114209588 | 15 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
114210561 | 16 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
114210561 | 16 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
114210561 | 16 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
114210561 | 16 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
114210561 | 16 | Conduct: Initial Review (IR) | 2021-06-08 | Customer – requirement to provide corrected information
114210561 | 16 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
114210561 | 16 | Conduct: Initial Review (IR) | 2021-06-22 | Customer – requirement to provide corrected information
114210561 | 16 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
114210561 | 16 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
114210880 | 17 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
114210928 | 18 | Conduct: Initial Review (IR) | 2021-05-07 | Customer – requirement to provide corrected information
114210928 | 18 | Conduct: Initial Review (IR) | 2021-05-14 | Customer – requirement to provide corrected information
114210928 | 18 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
114210928 | 18 | Conduct: Initial Review (IR) | 2021-05-28 | Customer – requirement to provide corrected information
114210928 | 18 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
114210928 | 18 | Conduct: Initial Review (IR) | 2021-06-14 | Customer – requirement to provide corrected information
114210928 | 18 | Conduct: Initial Review (IR) | 2021-06-21 | Customer – requirement to provide corrected information
114210928 | 18 | Conduct: Initial Review (IR) | 2021-06-28 | Customer – requirement to provide corrected information
114210928 | 18 | Conduct: Initial Review (IR) | 2021-07-06 | Customer – requirement to provide corrected information
114211064 | 19 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
114211816 | 20 | Conduct: Initial Review (IR) | 2021-05-13 | Customer – requirement to provide corrected information
114211816 | 20 | Conduct: Initial Review (IR) | 2021-08-09 | Customer – requesting an extension
114274547 | 21 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
114274547 | 21 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
114274547 | 21 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
114283060 | 22 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
114283060 | 22 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
114283060 | 22 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
114401181 | 23 | Construction True-up Report Sent | 2021-05-31 | Project Management – requiring more detailed review
114401181 | 23 | Construction True-up Report Sent | 2021-06-07 | Project Management – requiring more detailed review
114401181 | 23 | Construction True-up Report Sent | 2021-06-30 | Project Management – requiring more detailed review
114637979 | 24 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
114637979 | 24 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
114637979 | 24 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
114949391 | 25 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
114949391 | 25 | Conduct: Initial Review (IR) | 2021-07-16 | Cus – requirement to provide a response to deficiency notice
115103779 | 26 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
115103779 | 26 | Conduct: Initial Review (IR) | 2021-07-16 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
115279279 | 27 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
115279279 | 27 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
115279279 | 27 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
115279279 | 27 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
115638266 | 28 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
115638266 | 28 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
115638266 | 28 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
116578736 | 29 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
116578736 | 29 | Conduct: Initial Review (IR) | 2021-06-21 | Customer – requirement to provide corrected information
116578736 | 29 | Conduct: Initial Review (IR) | 2021-07-05 | Customer – requirement to provide corrected information
116705746 | 30 | Conduct: Initial Review (IR) | 2021-07-28 | Customer – requirement to provide corrected information
116712346 | 31 | Conduct: Initial Review (IR) | 2021-07-13 | Customer – requirement to provide corrected information
117093843 | 32 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
117093843 | 32 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
117093843 | 32 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
117105024 | 33 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
117105024 | 33 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
117105024 | 33 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
117105024 | 33 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
117105024 | 33 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
117105024 | 33 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
117210165 | 34 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
117210165 | 34 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
117210165 | 34 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
117466243 | 35 | Conduct: SIS | 2021-05-05 | Engineering – addressing a human error
117620632 | 36 | Conduct: Initial Review (IR) | 2021-06-18 | Engineering – addressing project volume surge
117620632 | 36 | Conduct: Initial Review (IR) | 2021-07-02 | Engineering – addressing project volume surge
117628164 | 37 | Conduct: SIS | 2021-06-11 | Customer – requirement to provide corrected information
117628164 | 37 | Conduct: SIS | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
117633795 | 38 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
117633795 | 38 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
117633795 | 38 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
117633795 | 38 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
117633795 | 38 | Conduct: Initial Review (IR) | 2021-06-08 | Customer – requirement to provide corrected information
117633795 | 38 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
117633795 | 38 | Conduct: Initial Review (IR) | 2021-06-22 | Customer – requirement to provide corrected information
117633795 | 38 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
117633795 | 38 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
118138973 | 39 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
118138973 | 39 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
118138973 | 39 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
118138973 | 39 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
118138973 | 39 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
118138973 | 39 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
118384240 | 40 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
118384240 | 40 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
118384240 | 40 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
118384240 | 40 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
118384240 | 40 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
118393242 | 41 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
118393242 | 41 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
118393242 | 41 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
118393242 | 41 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
118393242 | 41 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
118453482 | 42 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
118453482 | 42 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
118453482 | 42 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
118453482 | 42 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
118453482 | 42 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
118453482 | 42 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
118573950 | 43 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
118573950 | 43 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
118573950 | 43 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
118573950 | 43 | Conduct: Initial Review (IR) | 2021-06-01 | Engineering – requiring more detailed review
118581454 | 44 | Conduct: Initial Review (IR) | 2021-06-10 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
118655173 | 45 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
118655173 | 45 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
118655173 | 45 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
118655173 | 45 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
118655173 | 45 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
118710005 | 46 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
118710005 | 46 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
118710005 | 46 | Conduct: Initial Review (IR) | 2021-05-27 | Project Management - addressing project volume surge
118710005 | 46 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
118710005 | 46 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
118715783 | 47 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
118715783 | 47 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
118715783 | 47 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
118715783 | 47 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
118734619 | 48 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering – requiring more detailed review
118740272 | 49 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
118740272 | 49 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
118740272 | 49 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
118740272 | 49 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
118740272 | 49 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
118747458 | 50 | Conduct: Initial Review (IR) | 2021-07-20 | Engineering – requiring more detailed review
118761304 | 51 | Conduct: SIS | 2021-05-31 | Customer – requirement to provide corrected information
118761304 | 51 | Conduct: SIS | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
118761304 | 51 | Conduct: SIS | 2021-06-30 | Customer – requirement to provide corrected information
118951999 | 52 | Conduct: Initial Review (IR) | 2021-05-11 | Customer – requirement to provide corrected information
118951999 | 52 | Conduct: Initial Review (IR) | 2021-05-18 | Customer – requirement to provide corrected information
118951999 | 52 | Conduct: Initial Review (IR) | 2021-05-25 | Customer – requirement to provide corrected information
118951999 | 52 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
118951999 | 52 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
118951999 | 52 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requirement to provide corrected information
119044593 | 53 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
119044593 | 53 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
119044593 | 53 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
119044593 | 53 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
119044593 | 53 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
119044593 | 53 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
119100564 | 54 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
119209123 | 55 | Conduct: Initial Review (IR) | 2021-05-11 | Customer – requesting an extension
119291632 | 56 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
119291632 | 56 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
119291632 | 56 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
119333953 | 57 | Determine Material Modifications | 2021-06-25 | Engineering – requiring more detailed review
119355837 | 58 | Conduct: Supplemental Review (SR) | 2021-06-04 | Engineering – addressing project volume surge
119355837 | 58 | Conduct: Supplemental Review (SR) | 2021-06-11 | Engineering – addressing project volume surge
119355837 | 58 | Conduct: Supplemental Review (SR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
119355837 | 58 | Conduct: Supplemental Review (SR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
119367709 | 59 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
119367709 | 59 | Conduct: Initial Review (IR) | 2021-06-24 | Cus – requirement to provide a response to deficiency notice
119367709 | 59 | Conduct: Initial Review (IR) | 2021-07-01 | Cus – requirement to provide a response to deficiency notice
119472540 | 60 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-05-19 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-06-17 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-06-24 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-07-01 | Customer – requirement to provide corrected information
119478606 | 61 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
119478606 | 61 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
119478606 | 61 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
119478606 | 61 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
119478606 | 61 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
119478606 | 61 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
119505557 | 62 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
119505557 | 62 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119505557 | 62 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
119505557 | 62 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
119505557 | 62 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119505557 | 62 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119519209 | 63 | Conduct: Initial Review (IR) | 2021-05-21 | Project Management – addressing a human error
119519209 | 63 | Conduct: Initial Review (IR) | 2021-06-07 | Engineering – requiring more detailed review
119519209 | 63 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
119519209 | 63 | Conduct: Initial Review (IR) | 2021-06-28 | Engineering – requiring more detailed review
119541435 | 64 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
119549377 | 65 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
119549377 | 65 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
119549377 | 65 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
119549377 | 65 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
119549377 | 65 | Conduct: Initial Review (IR) | 2021-06-04 | Project Management – addressing a human error
119549377 | 65 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
119599059 | 66 | Tender Draft IA | 2021-07-30 | Customer – requirement to provide corrected information
119616069 | 67 | Conduct: Initial Review (IR) | 2021-07-01 | Project Management – requiring more detailed review
119616926 | 68 | Conduct: Initial Review (IR) | 2021-06-02 | Engineering – requiring more detailed review
119625833 | 69 | Conduct: SIS | 2021-06-15 | Engineering – requiring more detailed review
119625833 | 69 | Conduct: SIS | 2021-06-23 | Engineering – requiring more detailed review
119628199 | 70 | Conduct: Supplemental Review (SR) | 2021-05-13 | Engineering – requiring more detailed review
119628199 | 70 | Conduct: Supplemental Review (SR) | 2021-05-27 | Engineering – requiring more detailed review
119628199 | 70 | Conduct: Supplemental Review (SR) | 2021-06-11 | Engineering – requiring more detailed review
119628199 | 70 | Conduct: Supplemental Review (SR) | 2021-06-25 | Engineering – addressing project volume surge
119628199 | 70 | Conduct: Supplemental Review (SR) | 2021-07-12 | Engineering – addressing project volume surge
119636129 | 71 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
119665112 | 72 | Conduct: Initial Review (IR) | 2021-05-06 | Engineering – addressing project volume surge
119665112 | 72 | Conduct: Initial Review (IR) | 2021-05-13 | Project Management – addressing a human error
119665112 | 72 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
119675425 | 73 | Conduct: Initial Review (IR) | 2021-05-07 | Cus – requirement to provide a response to deficiency notice
119675425 | 73 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
119675425 | 73 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
119675425 | 73 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
119675425 | 73 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
119675425 | 73 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
119678775 | 74 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
119678775 | 74 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
119678775 | 74 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
119678775 | 74 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
119678775 | 74 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
119678966 | 75 | Conduct: SIS | 2021-07-12 | Engineering – addressing project volume surge
119681621 | 76 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
119681621 | 76 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119681621 | 76 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
119681621 | 76 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
119681621 | 76 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119681621 | 76 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119712260 | 77 | Conduct: Initial Review (IR) | 2021-05-12 | Cus – requirement to provide a response to deficiency notice
119712260 | 77 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
119712260 | 77 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
119724454 | 78 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering – requiring more detailed review
119724454 | 78 | Conduct: Initial Review (IR) | 2021-05-18 | Engineering – requiring more detailed review
119724454 | 78 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
119727305 | 79 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
119727305 | 79 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
119727305 | 79 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
119727305 | 79 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
119743827 | 80 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119743827 | 80 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
119743827 | 80 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
119743827 | 80 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119743827 | 80 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119752683 | 81 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
119752683 | 81 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
119752683 | 81 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
119752683 | 81 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
119752683 | 81 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119752683 | 81 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
119772541 | 82 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
119772541 | 82 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119772541 | 82 | Conduct: Initial Review (IR) | 2021-05-24 | Project Management - addressing project volume surge
119772541 | 82 | Conduct: Initial Review (IR) | 2021-06-01 | Engineering – requiring more detailed review
119772541 | 82 | Conduct: Initial Review (IR) | 2021-06-08 | Engineering – requiring more detailed review
119808996 | 83 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
119808996 | 83 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119808996 | 83 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
119808996 | 83 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
119808996 | 83 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119808996 | 83 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-05-07 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-06-21 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-07-06 | Cus – requirement to provide a response to deficiency notice
119838415 | 85 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
119838415 | 85 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
119838415 | 85 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
119838415 | 85 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
119838415 | 85 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
119850480 | 86 | Conduct: Initial Review (IR) | 2021-05-07 | Engineering – requiring more detailed review
119850480 | 86 | Conduct: Initial Review (IR) | 2021-05-14 | Engineering – requiring more detailed review
119850480 | 86 | Conduct: Initial Review (IR) | 2021-05-28 | Engineering – requiring more detailed review
119850480 | 86 | Conduct: Initial Review (IR) | 2021-06-14 | Engineering – requiring more detailed review
119850480 | 86 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
119876048 | 87 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
119876048 | 87 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
119876048 | 87 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
119876048 | 87 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
119876048 | 87 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
119876048 | 87 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requirement to provide corrected information
119876048 | 87 | Conduct: Initial Review (IR) | 2021-06-23 | Customer – requirement to provide corrected information
119876048 | 87 | Conduct: Initial Review (IR) | 2021-06-30 | Customer – requirement to provide corrected information
119876048 | 87 | Conduct: Initial Review (IR) | 2021-07-14 | Customer – requirement to provide corrected information
119908241 | 88 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
119908241 | 88 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
119910469 | 89 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
119910469 | 89 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119910469 | 89 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
119910469 | 89 | Conduct: Initial Review (IR) | 2021-06-01 | Project Management - addressing project volume surge
119910469 | 89 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119910469 | 89 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119928016 | 90 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
119928016 | 90 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
119928016 | 90 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-06-18 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-06-25 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-07-02 | Customer – requirement to provide corrected information
119928187 | 91 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-05-18 | Project Management - addressing project volume surge
119928187 | 91 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-06-09 | Project Management - addressing project volume surge
119928187 | 91 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requirement to provide corrected information
119928187 | 91 | Conduct: Initial Review (IR) | 2021-06-23 | Customer – requirement to provide corrected information
119928187 | 91 | Conduct: Initial Review (IR) | 2021-06-30 | Project Management - addressing project volume surge
119928187 | 91 | Conduct: Initial Review (IR) | 2021-07-08 | Cus – requirement to provide a response to deficiency notice
119933328 | 92 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
119933328 | 92 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119933328 | 92 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
119933328 | 92 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
119933328 | 92 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119933328 | 92 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
119933328 | 92 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
119933328 | 92 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
119933328 | 92 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
119941653 | 93 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119941653 | 93 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
119941653 | 93 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
119941653 | 93 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119941653 | 93 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119943292 | 94 | Conduct: SIS | 2021-05-20 | Engineering – addressing project volume surge
119956320 | 95 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
119956320 | 95 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
119956320 | 95 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
119956320 | 95 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
119959836 | 96 | Conduct: Initial Review (IR) | 2021-05-06 | Project Management – requiring more detailed review
119959836 | 96 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
119959836 | 96 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
119959836 | 96 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – requiring more detailed review
119960485 | 97 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119960485 | 97 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
119960485 | 97 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
119960485 | 97 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119960485 | 97 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119967284 | 98 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
119967284 | 98 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
119967284 | 98 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
119967284 | 98 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
119967284 | 98 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
119967284 | 98 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
119967284 | 98 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
119967284 | 98 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
119998942 | 99 | Conduct: Supplemental Review (SR) | 2021-05-18 | Engineering – requiring more detailed review
120000688 | 100 | Conduct: Initial Review (IR) | 2021-05-12 | Engineering – requiring more detailed review
120000688 | 100 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – requiring more detailed review
120000688 | 100 | Conduct: Initial Review (IR) | 2021-06-10 | Engineering – requiring more detailed review
120013081 | 101 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120013081 | 101 | Conduct: Initial Review (IR) | 2021-05-13 | Customer – requirement to provide corrected information
120013081 | 101 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120013081 | 101 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
120013081 | 101 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
120013081 | 101 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120019403 | 102 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
120044316 | 103 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120079860 | 104 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
120079860 | 104 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120079860 | 104 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120079860 | 104 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
120079860 | 104 | Conduct: Initial Review (IR) | 2021-07-01 | Cus – requirement to provide a response to deficiency notice
120080006 | 105 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
120080006 | 105 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120080006 | 105 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120080006 | 105 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120080006 | 105 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120080006 | 105 | Conduct: Initial Review (IR) | 2021-06-22 | Project Management - addressing project volume surge
120080006 | 105 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
120080006 | 105 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
120080007 | 106 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
120080428 | 107 | Conduct: Initial Review (IR) | 2021-05-14 | Engineering – addressing project volume surge
120080428 | 107 | Conduct: Initial Review (IR) | 2021-05-21 | Project Management – addressing a human error
120080428 | 107 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
120080428 | 107 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120090412 | 108 | Conduct: SIS | 2021-05-31 | Customer – requirement to provide corrected information
120090412 | 108 | Conduct: SIS | 2021-06-11 | Engineering – requiring more detailed review
120090412 | 108 | Conduct: SIS | 2021-07-09 | Engineering – requiring more detailed review
120097569 | 109 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120100772 | 110 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120100772 | 110 | Conduct: Initial Review (IR) | 2021-07-19 | Engineering – requiring more detailed review
120100784 | 111 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120108592 | 112 | Conduct: Initial Review (IR) | 2021-05-19 | Project Management – requiring more detailed review
120108592 | 112 | Conduct: Initial Review (IR) | 2021-07-01 | Project Management – requiring more detailed review
120110310 | 113 | Conduct: SIS | 2021-06-02 | Engineering – requiring more detailed review
120110310 | 113 | Conduct: SIS | 2021-06-09 | Engineering – requiring more detailed review
120118148 | 114 | Conduct: Initial Review (IR) | 2021-05-19 | Customer – requirement to provide corrected information
120118148 | 114 | Conduct: Initial Review (IR) | 2021-06-03 | Engineering – requiring more detailed review
120118148 | 114 | Conduct: Initial Review (IR) | 2021-06-10 | Project Management - addressing project volume surge
120138011 | 115 | Conduct: Initial Review (IR) | 2021-05-07 | Cus – requirement to provide a response to deficiency notice
120138011 | 115 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120138011 | 115 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120138011 | 115 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
120138011 | 115 | Conduct: Initial Review (IR) | 2021-07-01 | Cus – requirement to provide a response to deficiency notice
120143175 | 116 | Conduct: Screens Q and R | 2021-06-14 | Engineering – addressing project volume surge
120161122 | 117 | Conduct: Supplemental Review (SR) | 2021-05-25 | Engineering – requiring more detailed review
120161486 | 118 | Conduct: Initial Review (IR) | 2021-05-29 | Engineering – requiring more detailed review
120161486 | 118 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120161486 | 118 | Conduct: Initial Review (IR) | 2021-06-14 | Engineering – requiring more detailed review
120161486 | 118 | Conduct: Initial Review (IR) | 2021-07-12 | Engineering – requiring more detailed review
120163139 | 119 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
120163230 | 120 | Conduct: SIS | 2021-07-07 | Engineering – addressing project volume surge
120163237 | 121 | Conduct: SIS | 2021-07-07 | Engineering – addressing project volume surge
120163262 | 122 | Conduct: SIS | 2021-07-07 | Engineering – addressing project volume surge
120164941 | 123 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120164941 | 123 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120164941 | 123 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120164941 | 123 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120164941 | 123 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120177090 | 124 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120177090 | 124 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120177090 | 124 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
120177090 | 124 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
120192828 | 125 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120192828 | 125 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120192828 | 125 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120192828 | 125 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120192828 | 125 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120205868 | 126 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120205868 | 126 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120205868 | 126 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120210252 | 127 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120210252 | 127 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120210252 | 127 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120210324 | 128 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – addressing project volume surge
120210324 | 128 | Conduct: Initial Review (IR) | 2021-07-05 | Project Management – requiring more detailed review
120210381 | 129 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120210381 | 129 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120210381 | 129 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120210381 | 129 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120210381 | 129 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120210381 | 129 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120216210 | 130 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120216883 | 131 | Conduct: Initial Review (IR) | 2021-05-28 | Customer – requirement to provide corrected information
120216883 | 131 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120217485 | 132 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
120217596 | 133 | Conduct: Initial Review (IR) | 2021-05-11 | Customer – requirement to provide corrected information
120217596 | 133 | Conduct: Initial Review (IR) | 2021-05-18 | Customer – requirement to provide corrected information
120218582 | 134 | Conduct: Initial Review (IR) | 2021-05-07 | Project Management – requiring more detailed review
120218582 | 134 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120218582 | 134 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120218582 | 134 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120218582 | 134 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120218702 | 135 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120218702 | 135 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120218702 | 135 | Conduct: Initial Review (IR) | 2021-06-18 | Customer – requirement to provide corrected information
120218702 | 135 | Conduct: Initial Review (IR) | 2021-07-02 | Customer – requirement to provide corrected information
120219174 | 136 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
120219174 | 136 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120219174 | 136 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120219174 | 136 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120225309 | 137 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
120228564 | 138 | Conduct: Initial Review (IR) | 2021-05-13 | Customer – requirement to provide corrected information
120228564 | 138 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
120228564 | 138 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120228564 | 138 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120231142 | 139 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
120231142 | 139 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120231142 | 139 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120231142 | 139 | Conduct: Initial Review (IR) | 2021-06-21 | Cus – requirement to provide a response to deficiency notice
120231142 | 139 | Conduct: Initial Review (IR) | 2021-07-05 | Customer – requirement to provide corrected information
120242519 | 140 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120242519 | 140 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120242519 | 140 | Conduct: Initial Review (IR) | 2021-06-23 | Customer – requirement to provide corrected information
120242519 | 140 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
120242688 | 141 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering – requiring more detailed review
120256198 | 142 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
120256198 | 142 | Conduct: Initial Review (IR) | 2021-07-01 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-05-19 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-06-17 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-06-24 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-07-01 | Customer – requirement to provide corrected information
120259306 | 144 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
120259306 | 144 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120368266 | 145 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120406445 | 146 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120406445 | 146 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-06-30 | Customer – requirement to provide corrected information
120406445 | 146 | Conduct: Initial Review (IR) | 2021-07-08 | Cus – requirement to provide a response to deficiency notice
120407972 | 147 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120418596 | 148 | Conduct: SIS | 2021-07-16 | Project Management - addressing project volume surge
120418656 | 149 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering – addressing a human error
120418656 | 149 | Conduct: Initial Review (IR) | 2021-05-18 | Project Management - addressing project volume surge
120418656 | 149 | Conduct: Initial Review (IR) | 2021-06-01 | Engineering – requiring more detailed review
120418656 | 149 | Conduct: Initial Review (IR) | 2021-06-15 | Engineering – requiring more detailed review
120418656 | 149 | Conduct: Initial Review (IR) | 2021-06-22 | Customer – requirement to provide corrected information
120418656 | 149 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
120418656 | 149 | Conduct: Initial Review (IR) | 2021-07-07 | Project Management - addressing project volume surge
120419880 | 150 | Conduct: Screens Q and R | 2021-05-20 | Project Management – addressing a human error
120425938 | 151 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – addressing project volume surge
120425938 | 151 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120425938 | 151 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120427556 | 152 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
120427556 | 152 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120427556 | 152 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120433944 | 153 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120433944 | 153 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120433944 | 153 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120433944 | 153 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120433944 | 153 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120433944 | 153 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requesting an extension
120434315 | 154 | Conduct: Initial Review (IR) | 2021-06-03 | Engineering – requiring more detailed review
120434649 | 155 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
120443026 | 156 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120443026 | 156 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120443026 | 156 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
120443026 | 156 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120443026 | 156 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requesting an extension
120447712 | 157 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120447712 | 157 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120447712 | 157 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120447712 | 157 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120447712 | 157 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120448080 | 158 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120450167 | 159 | Conduct: Initial Review (IR) | 2021-05-12 | Cus – requirement to provide a response to deficiency notice
120450167 | 159 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
120450167 | 159 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
120450216 | 160 | Conduct: Initial Review (IR) | 2021-05-17 | Engineering – requiring more detailed review
120450216 | 160 | Conduct: Initial Review (IR) | 2021-05-24 | Project Management – requiring more detailed review
120452644 | 161 | Conduct: Initial Review (IR) | 2021-05-26 | Project Management – requiring more detailed review
120453208 | 162 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
120453208 | 162 | Conduct: Initial Review (IR) | 2021-06-10 | Cus – requirement to provide a response to deficiency notice
120453208 | 162 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120454060 | 163 | Conduct: Screens Q and R | 2021-05-07 | Engineering – requiring more detailed review
120462840 | 164 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120462840 | 164 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120462840 | 164 | Conduct: Initial Review (IR) | 2021-06-01 | Project Management - addressing project volume surge
120463149 | 165 | Conduct: Initial Review (IR) | 2021-05-17 | Engineering – requiring more detailed review
120463149 | 165 | Conduct: Initial Review (IR) | 2021-05-24 | Engineering – addressing a human error
120463149 | 165 | Conduct: Initial Review (IR) | 2021-06-01 | Project Management – requiring more detailed review
120464204 | 166 | Conduct: Screens Q and R | 2021-05-26 | Engineering – addressing project volume surge
120464204 | 166 | Conduct: Screens Q and R | 2021-06-04 | Engineering – addressing project volume surge
120464204 | 166 | Conduct: Screens Q and R | 2021-06-15 | Engineering – requiring more detailed review
120464204 | 166 | Conduct: Screens Q and R | 2021-06-22 | Engineering – requiring more detailed review
120464204 | 166 | Conduct: Screens Q and R | 2021-06-29 | Engineering – requiring more detailed review
120465673 | 167 | Conduct: SIS | 2021-06-11 | Engineering – addressing project volume surge
120467950 | 168 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120467950 | 168 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
120467950 | 168 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requesting an extension
120467950 | 168 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-06-01 | Project Management - addressing project volume surge
120469313 | 169 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
120477883 | 170 | Conduct: Supplemental Review (SR) | 2021-06-15 | Engineering – requiring more detailed review
120477883 | 170 | Conduct: Supplemental Review (SR) | 2021-06-22 | Engineering – requiring more detailed review
120477883 | 170 | Conduct: Supplemental Review (SR) | 2021-06-29 | Engineering – addressing project volume surge
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-05-28 | Engineering – requiring more detailed review
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-06-07 | Engineering – requiring more detailed review
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-06-14 | Engineering – requiring more detailed review
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-06-21 | Engineering – requiring more detailed review
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-06-23 | Project Management - addressing project volume surge
120477970 | 172 | Conduct: Initial Review (IR) | 2021-05-07 | Engineering – addressing project volume surge
120479524 | 173 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-06-02 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – requiring more detailed review
120479525 | 174 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
120479525 | 174 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120479525 | 174 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – requiring more detailed review
120479525 | 174 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – requiring more detailed review
120479812 | 175 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120479812 | 175 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120479812 | 175 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
120479812 | 175 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120479812 | 175 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120479812 | 175 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
120479812 | 175 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
120480244 | 176 | Conduct: SIS | 2021-07-21 | Engineering – addressing project volume surge
120484769 | 177 | Conduct: Initial Review (IR) | 2021-05-18 | Engineering – requiring more detailed review
120491626 | 178 | Conduct: Screens Q and R | 2021-05-14 | Engineering – addressing project volume surge
120491626 | 178 | Conduct: Screens Q and R | 2021-05-24 | Engineering – requiring more detailed review
120491626 | 178 | Conduct: Screens Q and R | 2021-05-31 | Project Management – requiring more detailed review
120491626 | 178 | Conduct: Screens Q and R | 2021-06-04 | Project Management – requiring more detailed review
120491626 | 178 | Conduct: Screens Q and R | 2021-06-18 | Engineering – requiring more detailed review
120493168 | 179 | Conduct: Screens Q and R | 2021-06-10 | Engineering – addressing project volume surge
120493300 | 180 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requesting an extension
120493300 | 180 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120493350 | 181 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120493350 | 181 | Conduct: Initial Review (IR) | 2021-06-14 | Customer – requirement to provide corrected information
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-05-28 | Engineering – requiring more detailed review
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-06-07 | Engineering – requiring more detailed review
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-06-14 | Engineering – requiring more detailed review
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-06-21 | Engineering – requiring more detailed review
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-06-23 | Project Management - addressing project volume surge
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-05-28 | Engineering – requiring more detailed review
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-06-07 | Engineering – requiring more detailed review
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-06-14 | Engineering – requiring more detailed review
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-06-21 | Engineering – requiring more detailed review
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-06-23 | Project Management - addressing project volume surge
120498202 | 184 | Conduct: Supplemental Review (SR) | 2021-06-14 | Engineering – requiring more detailed review
120498202 | 184 | Conduct: Supplemental Review (SR) | 2021-06-21 | Engineering – requiring more detailed review
120498209 | 185 | Conduct: Initial Review (IR) | 2021-05-07 | Engineering – addressing project volume surge
120498260 | 186 | Conduct: Supplemental Review (SR) | 2021-06-03 | Engineering – requiring more detailed review
120498260 | 186 | Conduct: Supplemental Review (SR) | 2021-06-10 | Engineering – requiring more detailed review
120498260 | 186 | Conduct: Supplemental Review (SR) | 2021-06-17 | Engineering – requiring more detailed review
120498260 | 186 | Conduct: Supplemental Review (SR) | 2021-06-24 | Engineering – requiring more detailed review
120498261 | 187 | Conduct: Supplemental Review (SR) | 2021-06-03 | Engineering – requiring more detailed review
120498261 | 187 | Conduct: Supplemental Review (SR) | 2021-06-10 | Engineering – requiring more detailed review
120498261 | 187 | Conduct: Supplemental Review (SR) | 2021-06-17 | Engineering – requiring more detailed review
120498261 | 187 | Conduct: Supplemental Review (SR) | 2021-06-24 | Engineering – requiring more detailed review
120500673 | 188 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
120500673 | 188 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120500673 | 188 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120500854 | 189 | Conduct: Initial Review (IR) | 2021-06-24 | Project Management – requiring more detailed review
120503061 | 190 | Conduct: Initial Review (IR) | 2021-05-17 | Project Management – requiring more detailed review
120503061 | 190 | Conduct: Initial Review (IR) | 2021-05-24 | Project Management – requiring more detailed review
120504102 | 191 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
120506502 | 192 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering – requiring more detailed review
120507331 | 193 | Conduct: Initial Review (IR) | 2021-05-11 | Customer – requesting an extension
120507331 | 193 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120507331 | 193 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120507331 | 193 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
120507331 | 193 | Conduct: Initial Review (IR) | 2021-06-09 | Project Management – requiring more detailed review
120508677 | 194 | Conduct: Screens Q and R | 2021-05-25 | Engineering – requiring more detailed review
120508677 | 194 | Conduct: Screens Q and R | 2021-06-08 | Engineering – requiring more detailed review
120508906 | 195 | Conduct: Initial Review (IR) | 2021-05-17 | Engineering – requiring more detailed review
120508906 | 195 | Conduct: Initial Review (IR) | 2021-05-31 | Engineering – requiring more detailed review
120508906 | 195 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
120508906 | 195 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120508960 | 196 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
120509484 | 197 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120509484 | 197 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120509484 | 197 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120509484 | 197 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120509484 | 197 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120510440 | 198 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120510440 | 198 | Conduct: Initial Review (IR) | 2021-06-19 | Customer – requirement to provide corrected information
120510440 | 198 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
120511830 | 199 | Conduct: Initial Review (IR) | 2021-05-06 | Engineering – requiring more detailed review
120512428 | 200 | Conduct: Initial Review (IR) | 2021-06-24 | Project Management – requiring more detailed review
120522795 | 201 | Conduct: Initial Review (IR) | 2021-05-12 | Engineering – addressing a human error
120525065 | 202 | Conduct: Initial Review (IR) | 2021-05-24 | Engineering – requiring more detailed review
120526554 | 203 | Conduct: Screens Q and R | 2021-05-21 | Engineering – requiring more detailed review
120526554 | 203 | Conduct: Screens Q and R | 2021-05-28 | Engineering – requiring more detailed review
120526554 | 203 | Conduct: Screens Q and R | 2021-06-07 | Engineering – requiring more detailed review
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-05-21 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-01 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-08 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-15 | Engineering – requiring more detailed review
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-22 | Engineering – requiring more detailed review
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-30 | Engineering – addressing project volume surge
120527388 | 205 | Conduct: Initial Review (IR) | 2021-05-07 | Customer – requirement to provide corrected information
120527388 | 205 | Conduct: Initial Review (IR) | 2021-05-14 | Customer – requirement to provide corrected information
120528893 | 206 | Conduct: Initial Review (IR) | 2021-05-07 | Engineering – addressing project volume surge
120529179 | 207 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering – requiring more detailed review
120529412 | 208 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120529412 | 208 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
120529412 | 208 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120530834 | 209 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120530834 | 209 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120530834 | 209 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120530834 | 209 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120530834 | 209 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120532383 | 210 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120534380 | 211 | Conduct: Initial Review (IR) | 2021-05-07 | Project Management – requiring more detailed review
120534380 | 211 | Conduct: Initial Review (IR) | 2021-05-14 | Project Management – addressing a human error
120534380 | 211 | Conduct: Initial Review (IR) | 2021-05-21 | Engineering – requiring more detailed review
120534380 | 211 | Conduct: Initial Review (IR) | 2021-05-28 | Engineering – requiring more detailed review
120534380 | 211 | Conduct: Initial Review (IR) | 2021-06-07 | Project Management - addressing project volume surge
120534380 | 211 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120534380 | 211 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
120537256 | 212 | Conduct: Screens Q and R | 2021-06-16 | Engineering – addressing project volume surge
120537502 | 213 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
120537502 | 213 | Conduct: Initial Review (IR) | 2021-05-17 | Engineering – requiring more detailed review
120537502 | 213 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120537502 | 213 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120540269 | 214 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120540269 | 214 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120540269 | 214 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120540269 | 214 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120540269 | 214 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120540680 | 215 | Conduct: Initial Review (IR) | 2021-06-11 | Project Management – requiring more detailed review
120540680 | 215 | Conduct: Initial Review (IR) | 2021-06-25 | Project Management – requiring more detailed review
120540680 | 215 | Conduct: Initial Review (IR) | 2021-06-28 | Project Management - addressing project volume surge
120552303 | 216 | Conduct: Supplemental Review (SR) | 2021-05-20 | Engineering – addressing project volume surge
120552957 | 217 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120552957 | 217 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120552957 | 217 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120555916 | 218 | Conduct: Screens Q and R | 2021-06-25 | Engineering – requiring more detailed review
120555916 | 218 | Conduct: Screens Q and R | 2021-07-19 | Engineering – requiring more detailed review
120563712 | 219 | Conduct: Initial Review (IR) | 2021-05-07 | Cus – requirement to provide a response to deficiency notice
120563712 | 219 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120563712 | 219 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120563712 | 219 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120563712 | 219 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120563712 | 219 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120563712 | 219 | Conduct: Initial Review (IR) | 2021-06-21 | Cus – requirement to provide a response to deficiency notice
120563712 | 219 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
120563712 | 219 | Conduct: Initial Review (IR) | 2021-07-06 | Cus – requirement to provide a response to deficiency notice
120564923 | 220 | Conduct: Initial Review (IR) | 2021-05-19 | Project Management – addressing a human error
120564923 | 220 | Conduct: Initial Review (IR) | 2021-06-03 | Project Management – addressing a human error
120564923 | 220 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120565433 | 221 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – addressing project volume surge
120565433 | 221 | Conduct: Initial Review (IR) | 2021-06-02 | Engineering – requiring more detailed review
120565433 | 221 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120567150 | 222 | Conduct: Supplemental Review (SR) | 2021-06-28 | Engineering – addressing project volume surge
120567150 | 222 | Conduct: Supplemental Review (SR) | 2021-07-02 | Project Management - addressing project volume surge
120568229 | 223 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – addressing project volume surge
120568229 | 223 | Conduct: Supplemental Review (SR) | 2021-07-07 | Engineering – addressing project volume surge
120571946 | 224 | Conduct: Initial Review (IR) | 2021-06-21 | Cus – requirement to provide a response to deficiency notice
120571946 | 224 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
120571946 | 224 | Conduct: Initial Review (IR) | 2021-07-06 | Cus – requirement to provide a response to deficiency notice
120574009 | 225 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120574009 | 225 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120574009 | 225 | Conduct: Initial Review (IR) | 2021-06-23 | Cus – requirement to provide a response to deficiency notice
120574009 | 225 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
120574360 | 226 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120574894 | 227 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120574894 | 227 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120578039 | 228 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120578514 | 229 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
120578514 | 229 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120578514 | 229 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120578514 | 229 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120578514 | 229 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120578514 | 229 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120580670 | 230 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
120580670 | 230 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requesting an extension
120581661 | 231 | Conduct: Initial Review (IR) | 2201-06-28 | Engineering – requiring more detailed review
120581767 | 232 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – addressing a human error
120581877 | 233 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – addressing a human error
120581960 | 234 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – addressing a human error
120581960 | 234 | Conduct: Initial Review (IR) | 2021-07-14 | Engineering – requiring more detailed review
120582557 | 235 | Conduct: Initial Review (IR) | 2021-05-25 | Project Management – requiring more detailed review
120582557 | 235 | Conduct: Initial Review (IR) | 2021-06-01 | Project Management – requiring more detailed review
120582748 | 236 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – requiring more detailed review
120582748 | 236 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120582785 | 237 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – requiring more detailed review
120582785 | 237 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120582789 | 238 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – requiring more detailed review
120582789 | 238 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120582822 | 239 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120582822 | 239 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
120582822 | 239 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120582822 | 239 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120582822 | 239 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120582840 | 240 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120582840 | 240 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
120582840 | 240 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120582840 | 240 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120582840 | 240 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requirement to provide corrected information
120582840 | 240 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – addressing project volume surge
120582841 | 241 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – requiring more detailed review
120582841 | 241 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120582870 | 242 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120582870 | 242 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – requiring more detailed review
120582870 | 242 | Conduct: Initial Review (IR) | 2021-06-25 | Customer – requirement to provide corrected information
120582870 | 242 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120583050 | 243 | Conduct: Initial Review (IR) | 2021-05-07 | Cus – requirement to provide a response to deficiency notice
120583050 | 243 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120583050 | 243 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
120583050 | 243 | Conduct: Initial Review (IR) | 2021-05-28 | Project Management - addressing project volume surge
120583050 | 243 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120583050 | 243 | Conduct: Initial Review (IR) | 2021-06-14 | Customer – requirement to provide corrected information
120586983 | 244 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – requiring more detailed review
120587079 | 245 | Conduct: Supplemental Review (SR) | 2021-05-10 | Engineering – addressing a human error
120587464 | 246 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120587464 | 246 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requirement to provide corrected information
120590767 | 247 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120590820 | 248 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120590820 | 248 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120590820 | 248 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120590820 | 248 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120590820 | 248 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120590820 | 248 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120597306 | 249 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120597306 | 249 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120598627 | 250 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120598627 | 250 | Conduct: Initial Review (IR) | 2021-07-01 | Engineering – addressing project volume surge
120599578 | 251 | Conduct: Initial Review (IR) | 2021-05-14 | Customer – requirement to provide corrected information
120599578 | 251 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
120601908 | 252 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – addressing project volume surge
120603645 | 253 | Conduct: Initial Review (IR) | 2021-06-28 | Engineering – requiring more detailed review
120604327 | 254 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – requiring more detailed review
120605651 | 255 | Conduct: Initial Review (IR) | 2021-05-12 | Cus – requirement to provide a response to deficiency notice
120606821 | 256 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
120608031 | 257 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – addressing project volume surge
120609943 | 258 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120609943 | 258 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120609943 | 258 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120609943 | 258 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120609943 | 258 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120612553 | 259 | Conduct: Supplemental Review (SR) | 2021-06-09 | Engineering – addressing project volume surge
120612553 | 259 | Conduct: Supplemental Review (SR) | 2021-06-23 | Engineering – addressing project volume surge
120612553 | 259 | Conduct: Supplemental Review (SR) | 2021-07-07 | Engineering – addressing project volume surge
120613132 | 260 | Conduct: Initial Review (IR) | 2021-06-14 | Customer – requirement to provide corrected information
120613132 | 260 | Conduct: Initial Review (IR) | 2021-06-21 | Cus – requirement to provide a response to deficiency notice
120613132 | 260 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
120617582 | 261 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120617582 | 261 | Conduct: Initial Review (IR) | 2021-05-19 | Customer – requirement to provide corrected information
120617612 | 262 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
120618014 | 263 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-06-18 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-07-02 | Project Management – requiring more detailed review
120627845 | 264 | Conduct: Initial Review (IR) | 2021-05-28 | Customer – requirement to provide corrected information
120627845 | 264 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120627845 | 264 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120627845 | 264 | Conduct: Initial Review (IR) | 2021-06-21 | Cus – requirement to provide a response to deficiency notice
120629311 | 265 | Conduct: Initial Review (IR) | 2021-05-14 | Customer – requirement to provide corrected information
120629540 | 266 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120629540 | 266 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120633938 | 267 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
120633938 | 267 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120634838 | 268 | Conduct: Initial Review (IR) | 2021-05-17 | Project Management – requiring more detailed review
120634838 | 268 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120634838 | 268 | Conduct: Initial Review (IR) | 2021-06-01 | Project Management – requiring more detailed review
120634838 | 268 | Conduct: Initial Review (IR) | 2021-06-08 | Customer – requesting an extension
120635852 | 269 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120637461 | 270 | Conduct: Initial Review (IR) | 2021-05-14 | Project Management – addressing a human error
120637461 | 270 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120637461 | 270 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120639109 | 271 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – addressing project volume surge
120639109 | 271 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – addressing project volume surge
120639588 | 272 | Conduct: Initial Review (IR) | 2021-06-18 | Project Management – addressing a human error
120639746 | 273 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120639996 | 274 | Conduct: Initial Review (IR) | 2021-05-11 | Customer – requesting an extension
120639996 | 274 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120639996 | 274 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120640481 | 275 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering – requiring more detailed review
120642515 | 276 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120644669 | 277 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering – requiring more detailed review
120644669 | 277 | Conduct: Initial Review (IR) | 2021-05-17 | Engineering – requiring more detailed review
120645700 | 278 | Conduct: Initial Review (IR) | 2021-05-07 | Cus – requirement to provide a response to deficiency notice
120645700 | 278 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120646368 | 279 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120647160 | 280 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120647192 | 281 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120648046 | 282 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120648046 | 282 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120648046 | 282 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120648046 | 282 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120648046 | 282 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120648046 | 282 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120651436 | 283 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
120651436 | 283 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120651436 | 283 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – requiring more detailed review
120651437 | 284 | Conduct: Supplemental Review (SR) | 2021-05-24 | Engineering – requiring more detailed review
120651437 | 284 | Conduct: Supplemental Review (SR) | 2021-06-01 | Engineering – requiring more detailed review
120652362 | 285 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-05-13 | Customer – requirement to provide corrected information
120652593 | 286 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120652593 | 286 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120652593 | 286 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120652824 | 287 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120653009 | 288 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – requiring more detailed review
120653009 | 288 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – requiring more detailed review
120653129 | 289 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120653129 | 289 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120653129 | 289 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120653129 | 289 | Conduct: Initial Review (IR) | 2021-06-30 | Project Management – requiring more detailed review
120653129 | 289 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – requiring more detailed review
120653359 | 290 | Conduct: Initial Review (IR) | 2021-07-02 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – requiring more detailed review
120654245 | 292 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
120654245 | 292 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120654327 | 293 | Conduct: Initial Review (IR) | 2021-06-10 | Engineering – requiring more detailed review
120654327 | 293 | Conduct: Initial Review (IR) | 2021-06-24 | Engineering – requiring more detailed review
120654327 | 293 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120655150 | 294 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120655150 | 294 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120655254 | 295 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120655254 | 295 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120655254 | 295 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120655254 | 295 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120655254 | 295 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120655753 | 296 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120655753 | 296 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120657295 | 297 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120657295 | 297 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120657885 | 298 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requesting an extension
120658536 | 299 | Conduct: Initial Review (IR) | 2021-05-21 | Engineering – requiring more detailed review
120659150 | 300 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
120659151 | 301 | Conduct: Initial Review (IR) | 2021-06-26 | Engineering – requiring more detailed review
120659151 | 301 | Conduct: Initial Review (IR) | 2021-07-15 | Engineering – requiring more detailed review
120659408 | 302 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120659408 | 302 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120659408 | 302 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120659408 | 302 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120659408 | 302 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120660151 | 303 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120662541 | 304 | Tender Draft IA | 2021-06-30 | Customer – requirement to provide corrected information
120662832 | 305 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120662832 | 305 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120662832 | 305 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120662832 | 305 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
120662832 | 305 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120662832 | 305 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120673056 | 306 | Conduct: Initial Review (IR) | 2021-05-25 | Customer – requirement to provide corrected information
120673056 | 306 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120673056 | 306 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120673056 | 306 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120673056 | 306 | Conduct: Initial Review (IR) | 2021-06-23 | Cus – requirement to provide a response to deficiency notice
120673056 | 306 | Conduct: Initial Review (IR) | 2021-06-30 | Cus – requirement to provide a response to deficiency notice
120673056 | 306 | Conduct: Initial Review (IR) | 2021-07-08 | Cus – requirement to provide a response to deficiency notice
120673323 | 307 | Conduct: Initial Review (IR) | 2021-06-10 | Engineering – requiring more detailed review
120673323 | 307 | Conduct: Initial Review (IR) | 2021-06-24 | Engineering – requiring more detailed review
120673323 | 307 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120674435 | 308 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
120676644 | 309 | Conduct: Initial Review (IR) | 2021-05-24 | Project Management – requiring more detailed review
120676644 | 309 | Conduct: Initial Review (IR) | 2021-06-07 | Project Management – requiring more detailed review
120676644 | 309 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
120676644 | 309 | Conduct: Initial Review (IR) | 2021-07-06 | Project Management – requiring more detailed review
120677457 | 310 | Conduct: Initial Review (IR) | 2021-07-13 | Engineering – requiring more detailed review
120677909 | 311 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
120678397 | 312 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120678397 | 312 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120678397 | 312 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120678397 | 312 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120678397 | 312 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120679519 | 313 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
120680099 | 314 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – addressing project volume surge
120680099 | 314 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – addressing project volume surge
120680099 | 314 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – requiring more detailed review
120680099 | 314 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
120680849 | 315 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120680849 | 315 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120680849 | 315 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120680849 | 315 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120685085 | 316 | Conduct: Initial Review (IR) | 2021-05-14 | Engineering – requiring more detailed review
120685085 | 316 | Conduct: Initial Review (IR) | 2021-05-28 | Engineering – requiring more detailed review
120685085 | 316 | Conduct: Initial Review (IR) | 2021-06-14 | Engineering – requiring more detailed review
120685085 | 316 | Conduct: Initial Review (IR) | 2021-06-28 | Engineering – requiring more detailed review
120687253 | 317 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120687253 | 317 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120687253 | 317 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120687253 | 317 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
120687253 | 317 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120687253 | 317 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120687736 | 318 | Conduct: Initial Review (IR) | 2021-05-06 | Customer – requirement to provide corrected information
120689811 | 319 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
120689811 | 319 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120689811 | 319 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120689811 | 319 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120689811 | 319 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120689811 | 319 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120689917 | 320 | Conduct: Initial Review (IR) | 2021-05-31 | Cus – requirement to provide a response to deficiency notice
120689917 | 320 | Conduct: Initial Review (IR) | 2021-06-07 | Engineering – requiring more detailed review
120689917 | 320 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
120690266 | 321 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – requiring more detailed review
120690266 | 321 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – requiring more detailed review
120690803 | 322 | Conduct: Initial Review (IR) | 2021-05-17 | Project Management – requiring more detailed review
120690803 | 322 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requesting an extension
120690803 | 322 | Conduct: Initial Review (IR) | 2021-06-01 | Project Management – requiring more detailed review
120690803 | 322 | Conduct: Initial Review (IR) | 2021-06-08 | Customer – requesting an extension
120690803 | 322 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120692791 | 323 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120692791 | 323 | Conduct: Initial Review (IR) | 2021-06-02 | Project Management – requiring more detailed review
120692895 | 324 | Conduct: Initial Review (IR) | 2021-05-12 | Cus – requirement to provide a response to deficiency notice
120692895 | 324 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
120692895 | 324 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120692895 | 324 | Conduct: Initial Review (IR) | 2021-06-03 | Cus – requirement to provide a response to deficiency notice
120693911 | 325 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
120693911 | 325 | Conduct: Initial Review (IR) | 2021-05-17 | Project Management - addressing project volume surge
120693911 | 325 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120695606 | 326 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – requiring more detailed review
120695922 | 327 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requesting an extension
120696114 | 328 | Conduct: Initial Review (IR) | 2021-05-17 | Project Management – requiring more detailed review
120696114 | 328 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requesting an extension
120696114 | 328 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120697785 | 329 | Conduct: Initial Review (IR) | 2021-05-18 | Engineering – requiring more detailed review
120697785 | 329 | Conduct: Initial Review (IR) | 2021-05-25 | Project Management – requiring more detailed review
120697785 | 329 | Conduct: Initial Review (IR) | 2021-06-02 | Project Management – requiring more detailed review
120697785 | 329 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requesting an extension
120697785 | 329 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requesting an extension
120702260 | 330 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering – requiring more detailed review
120702643 | 331 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
120707179 | 332 | Conduct: Initial Review (IR) | 2021-05-07 | Cus – requirement to provide a response to deficiency notice
120707179 | 332 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120707179 | 332 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120707179 | 332 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120707179 | 332 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120707179 | 332 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120708164 | 333 | Conduct: Supplemental Review (SR) | 2021-07-01 | Engineering – addressing project volume surge
120708334 | 334 | Conduct: Initial Review (IR) | 2021-05-19 | Customer – requirement to provide corrected information
120708334 | 334 | Conduct: Initial Review (IR) | 2021-05-28 | Engineering – requiring more detailed review
120709190 | 335 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-05-25 | Project Management - addressing project volume surge
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-23 | Project Management - addressing project volume surge
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-30 | Customer – requirement to provide corrected information
120709190 | 335 | Conduct: Initial Review (IR) | 2021-07-08 | Project Management - addressing project volume surge
120710017 | 336 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120710017 | 336 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120711343 | 337 | Conduct: Initial Review (IR) | 2021-05-18 | Engineering – requiring more detailed review
120711343 | 337 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120711343 | 337 | Conduct: Supplemental Review (SR) | 2021-07-16 | Engineering – requiring more detailed review
120712944 | 338 | Conduct: Initial Review (IR) | 2021-07-08 | Customer – requirement to provide corrected information
120713658 | 339 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120713658 | 339 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120713658 | 339 | Conduct: Initial Review (IR) | 2021-06-18 | Engineering – requiring more detailed review
120714094 | 340 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120714094 | 340 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120714094 | 340 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120714094 | 340 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120714094 | 340 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
120714094 | 340 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120714094 | 340 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120714094 | 340 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120714094 | 340 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120714146 | 341 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120714464 | 342 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
120714464 | 342 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120714464 | 342 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – requiring more detailed review
120716128 | 343 | Conduct: Initial Review (IR) | 2021-05-14 | Engineering – requiring more detailed review
120716128 | 343 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
120716128 | 343 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120716128 | 343 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120717762 | 344 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120718201 | 345 | Conduct: Initial Review (IR) | 2021-05-11 | Customer – requirement to provide corrected information
120718201 | 345 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120718201 | 345 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120718201 | 345 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
120718888 | 346 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120718888 | 346 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120718888 | 346 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120719773 | 347 | Conduct: Initial Review (IR) | 2021-05-14 | Engineering – requiring more detailed review
120719773 | 347 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120719773 | 347 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120719773 | 347 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120720576 | 348 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120720576 | 348 | Conduct: Initial Review (IR) | 2021-05-18 | Customer – requirement to provide corrected information
120720576 | 348 | Conduct: Initial Review (IR) | 2021-05-25 | Customer – requirement to provide corrected information
120720576 | 348 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120720576 | 348 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requesting an extension
120720654 | 349 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120720654 | 349 | Conduct: Initial Review (IR) | 2021-05-18 | Customer – requirement to provide corrected information
120720654 | 349 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120720654 | 349 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
120720675 | 350 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120720675 | 350 | Conduct: Initial Review (IR) | 2021-05-18 | Customer – requirement to provide corrected information
120720675 | 350 | Conduct: Initial Review (IR) | 2021-05-25 | Customer – requirement to provide corrected information
120720675 | 350 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120720675 | 350 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requesting an extension
120720699 | 351 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120720699 | 351 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120720699 | 351 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
120720765 | 352 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120720765 | 352 | Conduct: Initial Review (IR) | 2021-05-18 | Customer – requirement to provide corrected information
120720765 | 352 | Conduct: Initial Review (IR) | 2021-05-25 | Customer – requirement to provide corrected information
120720765 | 352 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120720765 | 352 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requesting an extension
120720824 | 353 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120720824 | 353 | Conduct: Initial Review (IR) | 2021-05-18 | Customer – requirement to provide corrected information
120720824 | 353 | Conduct: Initial Review (IR) | 2021-05-25 | Customer – requirement to provide corrected information
120720824 | 353 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120720824 | 353 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requesting an extension
120720858 | 354 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120720858 | 354 | Conduct: Initial Review (IR) | 2021-05-18 | Customer – requirement to provide corrected information
120720858 | 354 | Conduct: Initial Review (IR) | 2021-05-25 | Customer – requirement to provide corrected information
120720858 | 354 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120720858 | 354 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120720858 | 354 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requesting an extension
120721051 | 355 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120721051 | 355 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120721051 | 355 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120721051 | 355 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
120721051 | 355 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120721051 | 355 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120721051 | 355 | Conduct: Initial Review (IR) | 2021-06-18 | Engineering – requiring more detailed review
120722019 | 356 | Conduct: Initial Review (IR) | 2021-05-14 | Customer – requirement to provide corrected information
120722334 | 357 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120722334 | 357 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – requiring more detailed review
120722334 | 357 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120722334 | 357 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120726255 | 358 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
120726255 | 358 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120727154 | 359 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – addressing project volume surge
120727263 | 360 | Conduct: Initial Review (IR) | 2021-05-11 | Customer – requesting an extension
120727263 | 360 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120727263 | 360 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120727263 | 360 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
120727263 | 360 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120727263 | 360 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120728066 | 361 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – requiring more detailed review
120728066 | 361 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requesting an extension
120728066 | 361 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requesting an extension
120728066 | 361 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requesting an extension
120728066 | 361 | Conduct: Initial Review (IR) | 2021-06-17 | Customer – requesting an extension
120735552 | 362 | Conduct: Initial Review (IR) | 2021-05-21 | Engineering – addressing project volume surge
120736376 | 363 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120736376 | 363 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120736376 | 363 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120736376 | 363 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120736376 | 363 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120737045 | 364 | Conduct: Initial Review (IR) | 2021-05-06 | Engineering – requiring more detailed review
120737045 | 364 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120737045 | 364 | Conduct: Initial Review (IR) | 2021-05-27 | Project Management – requiring more detailed review
120737045 | 364 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requesting an extension
120737045 | 364 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120737110 | 365 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
120737110 | 365 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120737110 | 365 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120737110 | 365 | Conduct: Initial Review (IR) | 2021-07-01 | Engineering – requiring more detailed review
120737196 | 366 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120737196 | 366 | Conduct: Initial Review (IR) | 2021-06-10 | Project Management – requiring more detailed review
120737196 | 366 | Conduct: Initial Review (IR) | 2021-06-24 | Engineering – requiring more detailed review
120737196 | 366 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120737208 | 367 | Conduct: Initial Review (IR) | 2021-05-06 | Engineering – requiring more detailed review
120737583 | 368 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120737583 | 368 | Conduct: Initial Review (IR) | 2021-07-01 | Engineering – addressing project volume surge
120737868 | 369 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
120738200 | 370 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120738210 | 371 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – requiring more detailed review
120738210 | 371 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120741508 | 372 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120742267 | 373 | Conduct: Initial Review (IR) | 2021-05-14 | Engineering – requiring more detailed review
120742267 | 373 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120742267 | 373 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120742267 | 373 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requesting an extension
120742267 | 373 | Conduct: Initial Review (IR) | 2021-06-14 | Customer – requesting an extension
120742267 | 373 | Conduct: Initial Review (IR) | 2021-06-21 | Project Management - addressing project volume surge
120742267 | 373 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
120742267 | 373 | Conduct: Initial Review (IR) | 2021-07-06 | Cus – requirement to provide a response to deficiency notice
120742492 | 374 | Conduct: Initial Review (IR) | 2021-05-14 | Engineering – requiring more detailed review
120742492 | 374 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120742492 | 374 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120742492 | 374 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120742492 | 374 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120742852 | 375 | Conduct: Initial Review (IR) | 2021-05-14 | Engineering – requiring more detailed review
120742852 | 375 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120742852 | 375 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120742852 | 375 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120742852 | 375 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120742852 | 375 | Conduct: Initial Review (IR) | 2021-06-21 | Cus – requirement to provide a response to deficiency notice
120743596 | 376 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
120743596 | 376 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120743596 | 376 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120743596 | 376 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120745437 | 377 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120745437 | 377 | Conduct: Initial Review (IR) | 2021-06-23 | Customer – requesting an extension
120745437 | 377 | Conduct: Initial Review (IR) | 2021-06-30 | Cus – requirement to provide a response to deficiency notice
120745437 | 377 | Conduct: Initial Review (IR) | 2021-07-08 | Cus – requirement to provide a response to deficiency notice
120747032 | 378 | Conduct: Initial Review (IR) | 2021-05-24 | Project Management – addressing a human error
120749173 | 379 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120749736 | 380 | Conduct: Initial Review (IR) | 2021-07-12 | Customer – requirement to provide corrected information
120750928 | 381 | Conduct: Initial Review (IR) | 2021-05-12 | Cus – requirement to provide a response to deficiency notice
120750928 | 381 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
120750935 | 382 | Conduct: Initial Review (IR) | 2021-05-12 | Cus – requirement to provide a response to deficiency notice
120750935 | 382 | Conduct: Initial Review (IR) | 2021-05-19 | Project Management - addressing project volume surge
120750935 | 382 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120751083 | 383 | Conduct: Initial Review (IR) | 2021-05-12 | Cus – requirement to provide a response to deficiency notice
120751228 | 384 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – addressing project volume surge
120752027 | 385 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
120752027 | 385 | Conduct: Initial Review (IR) | 2021-05-28 | Customer – requirement to provide corrected information
120752027 | 385 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120752027 | 385 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120753509 | 386 | Conduct: Initial Review (IR) | 2021-05-18 | Engineering – requiring more detailed review
120753509 | 386 | Conduct: Initial Review (IR) | 2021-05-25 | Project Management – addressing a human error
120753509 | 386 | Conduct: Initial Review (IR) | 2021-06-02 | Project Management – requiring more detailed review
120753598 | 387 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120756037 | 388 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – addressing project volume surge
120756037 | 388 | Conduct: Initial Review (IR) | 2021-06-03 | Engineering – requiring more detailed review
120756037 | 388 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120756037 | 388 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120756234 | 389 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – addressing project volume surge
120756234 | 389 | Conduct: Initial Review (IR) | 2021-06-03 | Engineering – requiring more detailed review
120756234 | 389 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120756234 | 389 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120757637 | 390 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120757637 | 390 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120758691 | 391 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120758691 | 391 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120760235 | 392 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requesting an extension
120764186 | 393 | Conduct: Initial Review (IR) | 2021-06-03 | Cus – requirement to provide a response to deficiency notice
120764186 | 393 | Conduct: Initial Review (IR) | 2021-06-10 | Cus – requirement to provide a response to deficiency notice
120764186 | 393 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120766049 | 394 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120766049 | 394 | Conduct: Initial Review (IR) | 2021-06-02 | Project Management – requiring more detailed review
120766049 | 394 | Conduct: Initial Review (IR) | 2021-06-09 | Project Management – requiring more detailed review
120769672 | 395 | Conduct: Initial Review (IR) | 2021-05-07 | Cus – requirement to provide a response to deficiency notice
120769672 | 395 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120769672 | 395 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120769672 | 395 | Conduct: Initial Review (IR) | 2021-05-28 | Customer – requirement to provide corrected information
120769672 | 395 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120769672 | 395 | Conduct: Initial Review (IR) | 2021-06-14 | Customer – requirement to provide corrected information
120769672 | 395 | Conduct: Initial Review (IR) | 2021-06-21 | Customer – requirement to provide corrected information
120769672 | 395 | Conduct: Initial Review (IR) | 2021-06-28 | Customer – requirement to provide corrected information
120770205 | 396 | Conduct: Initial Review (IR) | 2021-05-07 | Cus – requirement to provide a response to deficiency notice
120770205 | 396 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120770205 | 396 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120770205 | 396 | Conduct: Initial Review (IR) | 2021-05-28 | Customer – requirement to provide corrected information
120770205 | 396 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120770205 | 396 | Conduct: Initial Review (IR) | 2021-06-14 | Customer – requirement to provide corrected information
120770205 | 396 | Conduct: Initial Review (IR) | 2021-06-21 | Customer – requirement to provide corrected information
120770524 | 397 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120770629 | 398 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120772942 | 399 | Conduct: Initial Review (IR) | 2021-06-08 | Engineering – addressing project volume surge
120772942 | 399 | Conduct: Initial Review (IR) | 2021-06-15 | Engineering – requiring more detailed review
120792958 | 400 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120792958 | 400 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120792958 | 400 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
120792958 | 400 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120792958 | 400 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120796075 | 401 | Tender Draft IA | 2021-08-06 | Cus – requirement to provide a response to deficiency notice
120803445 | 402 | Conduct: Screens Q and R | 2021-06-04 | Engineering – requiring more detailed review
120803932 | 403 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
120804094 | 404 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
120804094 | 404 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120804094 | 404 | Conduct: Initial Review (IR) | 2021-06-03 | Cus – requirement to provide a response to deficiency notice
120804094 | 404 | Conduct: Initial Review (IR) | 2021-06-10 | Cus – requirement to provide a response to deficiency notice
120804094 | 404 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120804099 | 405 | Conduct: Initial Review (IR) | 2021-05-11 | Project Management – addressing a human error
120804099 | 405 | Conduct: Initial Review (IR) | 2021-05-18 | Engineering – requiring more detailed review
120804099 | 405 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120804288 | 406 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120804288 | 406 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requirement to provide corrected information
120804601 | 407 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – requiring more detailed review
120805475 | 408 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120805475 | 408 | Conduct: Initial Review (IR) | 2021-06-03 | Cus – requirement to provide a response to deficiency notice
120806576 | 409 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120806576 | 409 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120806576 | 409 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
120806576 | 409 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120806576 | 409 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120807656 | 410 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
120807656 | 410 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120808457 | 411 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120808457 | 411 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120808781 | 412 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-06-01 | Project Management - addressing project volume surge
120808781 | 412 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
120809274 | 413 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120809274 | 413 | Conduct: Initial Review (IR) | 2021-05-25 | Customer – requirement to provide corrected information
120809274 | 413 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120809274 | 413 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120809274 | 413 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120809811 | 414 | Conduct: Initial Review (IR) | 2021-06-14 | Project Management – requiring more detailed review
120809811 | 414 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120811257 | 415 | Conduct: Initial Review (IR) | 2021-05-19 | Customer – requirement to provide corrected information
120811257 | 415 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120811257 | 415 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
120811257 | 415 | Conduct: Initial Review (IR) | 2021-06-10 | Cus – requirement to provide a response to deficiency notice
120811257 | 415 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120811257 | 415 | Conduct: Initial Review (IR) | 2021-06-24 | Cus – requirement to provide a response to deficiency notice
120811257 | 415 | Conduct: Initial Review (IR) | 2021-07-01 | Cus – requirement to provide a response to deficiency notice
120812614 | 416 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
120812614 | 416 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120812614 | 416 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
120813323 | 417 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120813323 | 417 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120813323 | 417 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120815687 | 418 | Conduct: Initial Review (IR) | 2021-05-19 | Project Management - addressing project volume surge
120815687 | 418 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120816753 | 419 | Conduct: Initial Review (IR) | 2021-06-17 | Project Management – requiring more detailed review
120816753 | 419 | Conduct: Initial Review (IR) | 2021-07-01 | Project Management – requiring more detailed review
120817699 | 420 | Conduct: Initial Review (IR) | 2021-05-18 | Engineering – requiring more detailed review
120820175 | 421 | Conduct: Initial Review (IR) | 2021-05-27 | Project Management - addressing emergency power outages
120820175 | 421 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120820175 | 421 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120822162 | 422 | Conduct: Initial Review (IR) | 2021-05-24 | Engineering – requiring more detailed review
120822482 | 423 | Conduct: Supplemental Review (SR) | 2021-06-24 | Engineering – addressing project volume surge
120822482 | 423 | Conduct: Supplemental Review (SR) | 2021-07-09 | Engineering – addressing project volume surge
120822490 | 424 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120823102 | 425 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120823102 | 425 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120823102 | 425 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120823257 | 426 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120823257 | 426 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120823257 | 426 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – requiring more detailed review
120823637 | 427 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120824355 | 428 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120824355 | 428 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
120825142 | 429 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120825142 | 429 | Conduct: Initial Review (IR) | 2021-06-18 | Engineering – requiring more detailed review
120825142 | 429 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120825142 | 429 | Conduct: Initial Review (IR) | 2021-07-02 | Engineering – requiring more detailed review
120826026 | 430 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120826026 | 430 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120826026 | 430 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120826026 | 430 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120827715 | 431 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120827715 | 431 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120827715 | 431 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120827715 | 431 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120831493 | 432 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120831493 | 432 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120831493 | 432 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120831493 | 432 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120831493 | 432 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
120831806 | 433 | Conduct: Initial Review (IR) | 2021-06-08 | Customer – requirement to provide corrected information
120837566 | 434 | Conduct: SIS | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
120838405 | 435 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
120838405 | 435 | Conduct: Initial Review (IR) | 2021-05-28 | Customer – requirement to provide corrected information
120838405 | 435 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120838405 | 435 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120839429 | 436 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
120839429 | 436 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120839429 | 436 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120839429 | 436 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120840508 | 437 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120840508 | 437 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120840508 | 437 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120840508 | 437 | Conduct: Initial Review (IR) | 2021-06-14 | Customer – requirement to provide corrected information
120841745 | 438 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
120841815 | 439 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120846340 | 440 | Conduct: Initial Review (IR) | 2021-06-28 | Customer – requesting an extension
120846340 | 440 | Conduct: Initial Review (IR) | 2021-07-06 | Cus – requirement to provide a response to deficiency notice
120847643 | 441 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120847648 | 442 | Conduct: Initial Review (IR) | 2021-05-28 | Customer – requirement to provide corrected information
120850237 | 443 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120851262 | 444 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120851262 | 444 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120851262 | 444 | Conduct: Initial Review (IR) | 2021-07-09 | Customer – requirement to provide corrected information
120851817 | 445 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120851817 | 445 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120851817 | 445 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120851817 | 445 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120852078 | 446 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120852954 | 447 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120852954 | 447 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120852954 | 447 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120852954 | 447 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120853133 | 448 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120853133 | 448 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120853133 | 448 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120853133 | 448 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120853133 | 448 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120853913 | 449 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120853913 | 449 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
120853913 | 449 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120853913 | 449 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
120853913 | 449 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
120853913 | 449 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
120853913 | 449 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
120858177 | 450 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – addressing project volume surge
120859060 | 451 | Conduct: Initial Review (IR) | 2021-05-25 | Customer – requesting an extension
120859231 | 452 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120859231 | 452 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120859231 | 452 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120859231 | 452 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120863572 | 453 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120864590 | 454 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120865092 | 455 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120865801 | 456 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120865801 | 456 | Conduct: Initial Review (IR) | 2021-06-03 | Cus – requirement to provide a response to deficiency notice
120865801 | 456 | Conduct: Initial Review (IR) | 2021-06-10 | Project Management - addressing project volume surge
120865801 | 456 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120865801 | 456 | Conduct: Initial Review (IR) | 2021-06-24 | Cus – requirement to provide a response to deficiency notice
120866052 | 457 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120867210 | 458 | Conduct: Initial Review (IR) | 2021-06-23 | Project Management - addressing project volume surge
120868285 | 459 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120868285 | 459 | Conduct: Initial Review (IR) | 2021-06-03 | Cus – requirement to provide a response to deficiency notice
120868285 | 459 | Conduct: Initial Review (IR) | 2021-06-10 | Cus – requirement to provide a response to deficiency notice
120868285 | 459 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120869063 | 460 | Conduct: Initial Review (IR) | 2021-05-26 | Project Management – addressing a human error
120869063 | 460 | Conduct: Initial Review (IR) | 2021-06-03 | Engineering – requiring more detailed review
120869063 | 460 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120869498 | 461 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
120869498 | 461 | Conduct: Initial Review (IR) | 2021-07-22 | Engineering – requiring more detailed review
120870295 | 462 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120870295 | 462 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
120875063 | 463 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120875131 | 464 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120875910 | 465 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
120875910 | 465 | Conduct: Initial Review (IR) | 2021-06-17 | Customer – requirement to provide corrected information
120875910 | 465 | Conduct: Initial Review (IR) | 2021-07-01 | Customer – requirement to provide corrected information
120875910 | 465 | Conduct: Initial Review (IR) | 2021-07-14 | Engineering – requiring more detailed review
120875984 | 466 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120875984 | 466 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120875984 | 466 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120876755 | 467 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120876755 | 467 | Conduct: Initial Review (IR) | 2021-06-03 | Cus – requirement to provide a response to deficiency notice
120876755 | 467 | Conduct: Initial Review (IR) | 2021-06-10 | Cus – requirement to provide a response to deficiency notice
120876755 | 467 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120876953 | 468 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
120881315 | 469 | Conduct: Initial Review (IR) | 2021-06-10 | Engineering – addressing project volume surge
120881315 | 469 | Conduct: Initial Review (IR) | 2021-06-17 | Customer – requirement to provide corrected information
120881315 | 469 | Conduct: Initial Review (IR) | 2021-07-01 | Engineering – requiring more detailed review
120882957 | 470 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – requiring more detailed review
120883305 | 471 | Conduct: Initial Review (IR) | 2021-06-03 | Cus – requirement to provide a response to deficiency notice
120883305 | 471 | Conduct: Initial Review (IR) | 2021-06-10 | Cus – requirement to provide a response to deficiency notice
120884233 | 472 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
120884233 | 472 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120884233 | 472 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
120888631 | 473 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120888631 | 473 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
120888831 | 474 | Conduct: Initial Review (IR) | 2021-06-09 | Project Management – addressing a human error
120889784 | 475 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
120890756 | 476 | Conduct: Initial Review (IR) | 2021-06-08 | Engineering – requiring more detailed review
120890756 | 476 | Conduct: Initial Review (IR) | 2021-06-22 | Customer – requirement to provide corrected information
120890756 | 476 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
120890756 | 476 | Conduct: Initial Review (IR) | 2021-07-09 | Cus – requirement to provide a response to deficiency notice
120891608 | 477 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120891608 | 477 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120891608 | 477 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120893179 | 478 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120893179 | 478 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120898614 | 479 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120901108 | 480 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120901108 | 480 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120901108 | 480 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120905127 | 481 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120905127 | 481 | Conduct: Initial Review (IR) | 2021-06-22 | Project Management - addressing project volume surge
120907409 | 482 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120907409 | 482 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120908889 | 483 | Conduct: Supplemental Review (SR) | 2021-07-16 | Engineering – requiring more detailed review
120921417 | 484 | Conduct: Initial Review (IR) | 2021-06-08 | Project Management – requiring more detailed review
120921417 | 484 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requesting an extension
120925994 | 485 | Conduct: Initial Review (IR) | 2021-06-03 | Cus – requirement to provide a response to deficiency notice
120925994 | 485 | Conduct: Initial Review (IR) | 2021-06-10 | Cus – requirement to provide a response to deficiency notice
120925994 | 485 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120926268 | 486 | Conduct: Initial Review (IR) | 2021-07-02 | Customer – requesting an extension
120926846 | 487 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requesting an extension
120928902 | 488 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
120929894 | 489 | Conduct: Initial Review (IR) | 2021-06-24 | Cus – requirement to provide a response to deficiency notice
120929894 | 489 | Conduct: Initial Review (IR) | 2021-07-01 | Cus – requirement to provide a response to deficiency notice
120931208 | 490 | Conduct: Initial Review (IR) | 2021-07-16 | Engineering – requiring more detailed review
120931225 | 491 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120932622 | 492 | Conduct: Initial Review (IR) | 2021-06-14 | Engineering – requiring more detailed review
120932622 | 492 | Conduct: Initial Review (IR) | 2021-06-28 | Engineering – requiring more detailed review
120932622 | 492 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120933574 | 493 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120933574 | 493 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120937061 | 494 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120938235 | 495 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
120938235 | 495 | Conduct: Initial Review (IR) | 2021-07-06 | Cus – requirement to provide a response to deficiency notice
120938774 | 496 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120938774 | 496 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120938774 | 496 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120938774 | 496 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120939167 | 497 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120939167 | 497 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120939167 | 497 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120939167 | 497 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120939173 | 498 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120941425 | 499 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120943773 | 500 | Conduct: Initial Review (IR) | 2021-07-01 | Cus – requirement to provide a response to deficiency notice
120943925 | 501 | Conduct: Initial Review (IR) | 2021-06-23 | Cus – requirement to provide a response to deficiency notice
120949009 | 502 | Conduct: Initial Review (IR) | 2021-07-01 | Project Management - addressing project volume surge
121005409 | 503 | Conduct: Initial Review (IR) | 2021-06-16 | Project Management – addressing a human error
121011976 | 504 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
121012813 | 505 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
121039112 | 506 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requesting an extension
121130249 | 507 | Conduct: Initial Review (IR) | 2021-06-11 | Project Management – addressing a human error
121130249 | 507 | Conduct: Initial Review (IR) | 2021-06-18 | Customer – requirement to provide corrected information
121130249 | 507 | Conduct: Initial Review (IR) | 2021-06-25 | Customer – requirement to provide corrected information
121130249 | 507 | Conduct: Initial Review (IR) | 2021-07-02 | Customer – requirement to provide corrected information
121138825 | 508 | Conduct: Initial Review (IR) | 2021-06-15 | Engineering – requiring more detailed review
121320903 | 509 | Conduct: Initial Review (IR) | 2021-07-01 | Cus – requirement to provide a response to deficiency notice
121322259 | 510 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
121322442 | 511 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
121322442 | 511 | Conduct: Initial Review (IR) | 2021-06-22 | Customer – requirement to provide corrected information
121322442 | 511 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
121322442 | 511 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
121324169 | 512 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
121324169 | 512 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
121326382 | 513 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
121326382 | 513 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
121326382 | 513 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
121328387 | 514 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
121328387 | 514 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
121333375 | 515 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-06-23 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-06-30 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-07-08 | Customer – requirement to provide corrected information
121333662 | 516 | Conduct: Initial Review (IR) | 2021-07-17 | Cus – requirement to provide a response to deficiency notice
121334724 | 517 | Conduct: Initial Review (IR) | 2021-07-08 | Cus – requirement to provide a response to deficiency notice
121334766 | 518 | Conduct: Initial Review (IR) | 2021-07-06 | Project Management - addressing emergency power outages
121345515 | 519 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
121345515 | 519 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
121347821 | 520 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
121347821 | 520 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
121348972 | 521 | Conduct: Initial Review (IR) | 2021-06-22 | Project Management - addressing project volume surge
121349220 | 522 | Conduct: Initial Review (IR) | 2021-06-22 | Project Management - addressing project volume surge
121349235 | 523 | Conduct: Initial Review (IR) | 2021-06-22 | Project Management - addressing project volume surge
121351304 | 524 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
121351304 | 524 | Conduct: Initial Review (IR) | 2021-07-02 | Customer – requesting an extension
121353735 | 525 | Conduct: Initial Review (IR) | 2021-06-24 | Cus – requirement to provide a response to deficiency notice
121355547 | 526 | Conduct: Initial Review (IR) | 2021-06-23 | Project Management – requiring more detailed review
121355803 | 527 | Conduct: Initial Review (IR) | 2021-06-30 | Project Management – requiring more detailed review
121355803 | 527 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
121359568 | 528 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
121366889 | 529 | Conduct: Initial Review (IR) | 2021-06-24 | Cus – requirement to provide a response to deficiency notice
121368590 | 530 | Conduct: Initial Review (IR) | 2021-06-24 | Cus – requirement to provide a response to deficiency notice
121368827 | 531 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
121377182 | 532 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
121377182 | 532 | Conduct: Initial Review (IR) | 2021-07-19 | Engineering – requiring more detailed review
121377796 | 533 | Conduct: Initial Review (IR) | 2021-07-03 | Engineering – requiring more detailed review
121386441 | 534 | Conduct: Initial Review (IR) | 2021-06-23 | Cus – requirement to provide a response to deficiency notice
121388061 | 535 | Conduct: Initial Review (IR) | 2021-07-08 | Customer – requirement to provide corrected information
121388233 | 536 | Conduct: Screens Q and R | 2021-07-13 | Engineering – addressing project volume surge
121389551 | 537 | Conduct: Initial Review (IR) | 2021-07-02 | Customer – requesting an extension
121417094 | 538 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
121418155 | 539 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
121418155 | 539 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
121439926 | 540 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information

## Delay Notice
Notification No | Key | Category | Planned finish | Delay Reason Desc
112143413 | 1 | Construction True-up Report Sent | 2021-03-31 | Customer
112143413 | 1 | Construction True-up Report Sent | 2021-04-30 | Customer
112143413 | 1 | Construction True-up Report Sent | 2021-05-31 | Customer – requirement to provide corrected information
112143413 | 1 | Construction True-up Report Sent | 2021-06-30 | Customer – requirement to provide corrected information
112143413 | 1 | Construction True-up Report Sent | 2021-07-31 | Customer – requirement to provide corrected information
112143413 | 1 | Construction True-up Report Sent | 2021-09-30 | Customer – requirement to provide corrected information
112143413 | 1 | Construction True-up Report Sent | 2021-12-30 | Customer – requirement to provide corrected information
113010764 | 2 | Construction True-up Report Sent | 2021-06-30 | Project Management – requiring more detailed review
113010764 | 2 | Construction True-up Report Sent | 2021-07-30 | Project Management – requiring more detailed review
113161988 | 3 | Conduct: SIS | 2021-05-24 | Engineering – requiring more detailed review
113161988 | 3 | Conduct: SIS | 2021-05-31 | Engineering – requiring more detailed review
114112849 | 4 | Construction True-up Report Sent | 2021-05-31 | Project Management – requiring more detailed review
114112849 | 4 | Construction True-up Report Sent | 2021-06-30 | Project Management – requiring more detailed review
114112849 | 4 | Construction True-up Report Sent | 2021-07-30 | Project Management – requiring more detailed review
114112992 | 5 | Construction True-up Report Sent | 2021-09-30 | Engineering – requiring more detailed review
114112992 | 5 | Construction True-up Report Sent | 2021-10-30 | Project Management – requiring more detailed review
114200622 | 6 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
114200622 | 6 | Conduct: Initial Review (IR) | 2020-12-31 | Customer
114200622 | 6 | Conduct: Initial Review (IR) | 2021-01-08 | Customer
114200622 | 6 | Conduct: Initial Review (IR) | 2021-01-15 | Customer
114200622 | 6 | Conduct: Initial Review (IR) | 2021-01-25 | Customer
114200622 | 6 | Conduct: Initial Review (IR) | 2021-02-01 | Customer
114200622 | 6 | Conduct: Initial Review (IR) | 2021-02-08 | Customer
114200622 | 6 | Conduct: Initial Review (IR) | 2021-02-16 | Customer
114200622 | 6 | Conduct: Initial Review (IR) | 2021-02-23 | Customer
114200622 | 6 | Conduct: Initial Review (IR) | 2021-03-02 | Customer
114200622 | 6 | Conduct: Initial Review (IR) | 2021-03-09 | Customer
114200622 | 6 | Conduct: Initial Review (IR) | 2021-03-16 | Customer
114200622 | 6 | Conduct: Initial Review (IR) | 2021-03-23 | Customer
114200622 | 6 | Conduct: Initial Review (IR) | 2021-03-30 | Customer
114200622 | 6 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
114200622 | 6 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
114200622 | 6 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
114200622 | 6 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
114200622 | 6 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
114200622 | 6 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
114200622 | 6 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
114202400 | 7 | Construction True-up Report Sent | 2021-03-19 | EGI
114202400 | 7 | Construction True-up Report Sent | 2021-03-26 | EGI
114202400 | 7 | Construction True-up Report Sent | 2021-04-02 | EGI
114202400 | 7 | Construction True-up Report Sent | 2021-06-30 | Project Management – requiring more detailed review
114205350 | 8 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-07-19 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-08-16 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-08-23 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-08-30 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-09-07 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-09-14 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-09-21 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-09-28 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-10-05 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
114205350 | 8 | Conduct: Initial Review (IR) | 2020-12-31 | Customer
114205350 | 8 | Conduct: Initial Review (IR) | 2021-01-08 | Customer
114205350 | 8 | Conduct: Initial Review (IR) | 2021-01-15 | Customer
114205350 | 8 | Conduct: Initial Review (IR) | 2021-01-25 | Customer
114205350 | 8 | Conduct: Initial Review (IR) | 2021-02-01 | Customer
114205350 | 8 | Conduct: Initial Review (IR) | 2021-02-08 | Customer
114205350 | 8 | Conduct: Initial Review (IR) | 2021-02-16 | Customer
114205350 | 8 | Conduct: Initial Review (IR) | 2021-02-23 | Customer
114205350 | 8 | Conduct: Initial Review (IR) | 2021-03-02 | Customer
114205350 | 8 | Conduct: Initial Review (IR) | 2021-03-09 | Customer
114205350 | 8 | Conduct: Initial Review (IR) | 2021-03-16 | Customer
114205350 | 8 | Conduct: Initial Review (IR) | 2021-03-23 | Customer
114205350 | 8 | Conduct: Initial Review (IR) | 2021-03-30 | Customer
114205350 | 8 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
114205350 | 8 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
114205350 | 8 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
114205350 | 8 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
114205350 | 8 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
114205350 | 8 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
114205350 | 8 | Conduct: Initial Review (IR) | 2021-10-19 | Customer – requirement to provide corrected information
114205849 | 9 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-10-14 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
114205849 | 9 | Conduct: Initial Review (IR) | 2020-12-31 | Customer
114205849 | 9 | Conduct: Initial Review (IR) | 2021-01-08 | Customer
114205849 | 9 | Conduct: Initial Review (IR) | 2021-01-15 | Customer
114205849 | 9 | Conduct: Initial Review (IR) | 2021-01-25 | Customer
114205849 | 9 | Conduct: Initial Review (IR) | 2021-02-01 | Customer
114205849 | 9 | Conduct: Initial Review (IR) | 2021-02-08 | Customer
114205849 | 9 | Conduct: Initial Review (IR) | 2021-02-16 | Customer
114205849 | 9 | Conduct: Initial Review (IR) | 2021-02-23 | Customer
114205849 | 9 | Conduct: Initial Review (IR) | 2021-03-02 | Customer
114205849 | 9 | Conduct: Initial Review (IR) | 2021-03-09 | Customer
114205849 | 9 | Conduct: Initial Review (IR) | 2021-03-16 | Customer
114205849 | 9 | Conduct: Initial Review (IR) | 2021-03-23 | Customer
114205849 | 9 | Conduct: Initial Review (IR) | 2021-03-30 | Customer
114205849 | 9 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
114205849 | 9 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
114205849 | 9 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
114205849 | 9 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
114205849 | 9 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
114205893 | 10 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-07-19 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-08-16 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-08-23 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-08-30 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-09-07 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-09-14 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-09-21 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-09-28 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2021-10-05 | Cus – requirement to provide a response to deficiency notice
114205893 | 10 | Conduct: Initial Review (IR) | 2020-12-31 | Customer
114205893 | 10 | Conduct: Initial Review (IR) | 2021-01-08 | Customer
114205893 | 10 | Conduct: Initial Review (IR) | 2021-01-15 | Customer
114205893 | 10 | Conduct: Initial Review (IR) | 2021-01-25 | Customer
114205893 | 10 | Conduct: Initial Review (IR) | 2021-02-01 | Customer
114205893 | 10 | Conduct: Initial Review (IR) | 2021-02-08 | Customer
114205893 | 10 | Conduct: Initial Review (IR) | 2021-02-16 | Customer
114205893 | 10 | Conduct: Initial Review (IR) | 2021-02-23 | Customer
114205893 | 10 | Conduct: Initial Review (IR) | 2021-03-02 | Customer
114205893 | 10 | Conduct: Initial Review (IR) | 2021-03-09 | Customer
114205893 | 10 | Conduct: Initial Review (IR) | 2021-03-16 | Customer
114205893 | 10 | Conduct: Initial Review (IR) | 2021-03-23 | Customer
114205893 | 10 | Conduct: Initial Review (IR) | 2021-03-30 | Customer
114205893 | 10 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
114205893 | 10 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
114205893 | 10 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
114205893 | 10 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
114205893 | 10 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
114206681 | 11 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-07-19 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-08-16 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-08-23 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-08-30 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-09-07 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-09-14 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-09-21 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-09-28 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-10-05 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
114206681 | 11 | Conduct: Initial Review (IR) | 2020-12-31 | Customer
114206681 | 11 | Conduct: Initial Review (IR) | 2021-01-08 | Customer
114206681 | 11 | Conduct: Initial Review (IR) | 2021-01-15 | Customer
114206681 | 11 | Conduct: Initial Review (IR) | 2021-01-25 | Customer
114206681 | 11 | Conduct: Initial Review (IR) | 2021-02-01 | Customer
114206681 | 11 | Conduct: Initial Review (IR) | 2021-02-08 | Customer
114206681 | 11 | Conduct: Initial Review (IR) | 2021-02-16 | Customer
114206681 | 11 | Conduct: Initial Review (IR) | 2021-02-23 | Customer
114206681 | 11 | Conduct: Initial Review (IR) | 2021-03-02 | Customer
114206681 | 11 | Conduct: Initial Review (IR) | 2021-03-09 | Customer
114206681 | 11 | Conduct: Initial Review (IR) | 2021-03-16 | Customer
114206681 | 11 | Conduct: Initial Review (IR) | 2021-03-23 | Customer
114206681 | 11 | Conduct: Initial Review (IR) | 2021-03-30 | Customer
114206681 | 11 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
114206681 | 11 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
114206681 | 11 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
114206681 | 11 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
114206681 | 11 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
114206681 | 11 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
114206681 | 11 | Conduct: Initial Review (IR) | 2021-10-12 | Customer – requirement to provide corrected information
114206681 | 11 | Conduct: Initial Review (IR) | 2021-10-19 | Customer – requirement to provide corrected information
114206681 | 11 | Conduct: Initial Review (IR) | 2021-05-13 | Project Management – addressing a human error
114207158 | 12 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
114207158 | 12 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
114207158 | 12 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
114207158 | 12 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
114207158 | 12 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
114207158 | 12 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
114207158 | 12 | Conduct: Initial Review (IR) | 2021-01-05 | Customer
114207158 | 12 | Conduct: Initial Review (IR) | 2021-01-12 | Customer
114207158 | 12 | Conduct: Initial Review (IR) | 2021-01-20 | Customer
114207158 | 12 | Conduct: Initial Review (IR) | 2021-01-27 | Customer
114207158 | 12 | Conduct: Initial Review (IR) | 2021-02-03 | Customer
114207158 | 12 | Conduct: Initial Review (IR) | 2021-02-10 | Customer
114207158 | 12 | Conduct: Initial Review (IR) | 2021-02-18 | Customer
114207158 | 12 | Conduct: Initial Review (IR) | 2021-02-25 | Customer
114207158 | 12 | Conduct: Initial Review (IR) | 2021-03-04 | Customer
114207158 | 12 | Conduct: Initial Review (IR) | 2021-03-11 | Customer
114207158 | 12 | Conduct: Initial Review (IR) | 2021-03-18 | Customer
114207158 | 12 | Conduct: Initial Review (IR) | 2021-03-25 | Customer
114207158 | 12 | Conduct: Initial Review (IR) | 2021-04-01 | Customer
114207158 | 12 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
114207158 | 12 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
114208382 | 13 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
114208382 | 13 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
114208382 | 13 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
114208382 | 13 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
114208382 | 13 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
114208382 | 13 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
114208382 | 13 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
114208382 | 13 | Conduct: Initial Review (IR) | 2021-04-26 | Engineering
114208927 | 14 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-07-19 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-08-16 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-08-23 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-08-30 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-09-07 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-09-14 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-09-21 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-09-28 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-10-05 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
114208927 | 14 | Conduct: Initial Review (IR) | 2020-12-31 | Customer
114208927 | 14 | Conduct: Initial Review (IR) | 2021-01-08 | Customer
114208927 | 14 | Conduct: Initial Review (IR) | 2021-01-15 | Customer
114208927 | 14 | Conduct: Initial Review (IR) | 2021-01-25 | Customer
114208927 | 14 | Conduct: Initial Review (IR) | 2021-02-01 | Customer
114208927 | 14 | Conduct: Initial Review (IR) | 2021-02-08 | Customer
114208927 | 14 | Conduct: Initial Review (IR) | 2021-02-16 | Customer
114208927 | 14 | Conduct: Initial Review (IR) | 2021-02-23 | Customer
114208927 | 14 | Conduct: Initial Review (IR) | 2021-03-02 | Customer
114208927 | 14 | Conduct: Initial Review (IR) | 2021-03-09 | Customer
114208927 | 14 | Conduct: Initial Review (IR) | 2021-03-16 | Customer
114208927 | 14 | Conduct: Initial Review (IR) | 2021-03-23 | Customer
114208927 | 14 | Conduct: Initial Review (IR) | 2021-03-30 | Customer
114208927 | 14 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
114208927 | 14 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
114208927 | 14 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
114208927 | 14 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
114208927 | 14 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
114208927 | 14 | Conduct: Initial Review (IR) | 2021-10-12 | Customer – requirement to provide corrected information
114208927 | 14 | Conduct: Initial Review (IR) | 2021-10-19 | Customer – requirement to provide corrected information
114209588 | 15 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
114209588 | 15 | Conduct: Initial Review (IR) | 2020-12-31 | Customer
114209588 | 15 | Conduct: Initial Review (IR) | 2021-01-08 | Customer
114209588 | 15 | Conduct: Initial Review (IR) | 2021-01-15 | Customer
114209588 | 15 | Conduct: Initial Review (IR) | 2021-01-25 | Customer
114209588 | 15 | Conduct: Initial Review (IR) | 2021-02-01 | Customer
114209588 | 15 | Conduct: Initial Review (IR) | 2021-02-08 | Customer
114209588 | 15 | Conduct: Initial Review (IR) | 2021-02-16 | Customer
114209588 | 15 | Conduct: Initial Review (IR) | 2021-02-23 | Customer
114209588 | 15 | Conduct: Initial Review (IR) | 2021-03-02 | Customer
114209588 | 15 | Conduct: Initial Review (IR) | 2021-03-09 | Customer
114209588 | 15 | Conduct: Initial Review (IR) | 2021-03-16 | Customer
114209588 | 15 | Conduct: Initial Review (IR) | 2021-03-23 | Customer
114209588 | 15 | Conduct: Initial Review (IR) | 2021-03-30 | Customer
114209588 | 15 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
114209588 | 15 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
114209588 | 15 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
114210561 | 16 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
114210561 | 16 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
114210561 | 16 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
114210561 | 16 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
114210561 | 16 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
114210561 | 16 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
114210561 | 16 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
114210561 | 16 | Conduct: Initial Review (IR) | 2021-06-08 | Customer – requirement to provide corrected information
114210561 | 16 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
114210561 | 16 | Conduct: Initial Review (IR) | 2021-06-22 | Customer – requirement to provide corrected information
114210561 | 16 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
114210561 | 16 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
114210561 | 16 | Conduct: Initial Review (IR) | 2021-07-14 | Customer – requirement to provide corrected information
114210880 | 17 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
114210880 | 17 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
114210880 | 17 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
114210880 | 17 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
114210928 | 18 | Conduct: Initial Review (IR) | 2021-07-20 | Cus – requirement to provide a response to deficiency notice
114210928 | 18 | Conduct: Initial Review (IR) | 2021-07-27 | Cus – requirement to provide a response to deficiency notice
114210928 | 18 | Conduct: Initial Review (IR) | 2021-08-03 | Cus – requirement to provide a response to deficiency notice
114210928 | 18 | Conduct: Initial Review (IR) | 2021-08-10 | Cus – requirement to provide a response to deficiency notice
114210928 | 18 | Conduct: Initial Review (IR) | 2021-08-17 | Cus – requirement to provide a response to deficiency notice
114210928 | 18 | Conduct: Initial Review (IR) | 2021-08-31 | Cus – requirement to provide a response to deficiency notice
114210928 | 18 | Conduct: Initial Review (IR) | 2021-09-15 | Cus – requirement to provide a response to deficiency notice
114210928 | 18 | Conduct: Initial Review (IR) | 2021-09-29 | Cus – requirement to provide a response to deficiency notice
114210928 | 18 | Conduct: Initial Review (IR) | 2021-10-13 | Cus – requirement to provide a response to deficiency notice
114210928 | 18 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
114210928 | 18 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
114210928 | 18 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
114210928 | 18 | Conduct: Initial Review (IR) | 2021-04-30 | Customer
114210928 | 18 | Conduct: Initial Review (IR) | 2021-05-07 | Customer – requirement to provide corrected information
114210928 | 18 | Conduct: Initial Review (IR) | 2021-05-14 | Customer – requirement to provide corrected information
114210928 | 18 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
114210928 | 18 | Conduct: Initial Review (IR) | 2021-05-28 | Customer – requirement to provide corrected information
114210928 | 18 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
114210928 | 18 | Conduct: Initial Review (IR) | 2021-06-14 | Customer – requirement to provide corrected information
114210928 | 18 | Conduct: Initial Review (IR) | 2021-06-21 | Customer – requirement to provide corrected information
114210928 | 18 | Conduct: Initial Review (IR) | 2021-06-28 | Customer – requirement to provide corrected information
114210928 | 18 | Conduct: Initial Review (IR) | 2021-07-06 | Customer – requirement to provide corrected information
114210928 | 18 | Conduct: Initial Review (IR) | 2021-07-13 | Customer – requirement to provide corrected information
114211064 | 19 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
114211064 | 19 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
114211064 | 19 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
114211064 | 19 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
114211816 | 20 | Conduct: Initial Review (IR) | 2021-01-04 | Customer
114211816 | 20 | Conduct: Initial Review (IR) | 2021-01-11 | Customer
114211816 | 20 | Conduct: Initial Review (IR) | 2021-01-19 | Customer
114211816 | 20 | Conduct: Initial Review (IR) | 2021-01-26 | Customer
114211816 | 20 | Conduct: Initial Review (IR) | 2021-02-02 | Customer
114211816 | 20 | Conduct: Initial Review (IR) | 2021-02-09 | Customer
114211816 | 20 | Conduct: Initial Review (IR) | 2021-02-17 | Customer
114211816 | 20 | Conduct: Initial Review (IR) | 2021-02-24 | Customer
114211816 | 20 | Conduct: Initial Review (IR) | 2021-03-03 | Customer
114211816 | 20 | Conduct: Initial Review (IR) | 2021-03-10 | Customer
114211816 | 20 | Conduct: Initial Review (IR) | 2021-03-17 | Customer
114211816 | 20 | Conduct: Initial Review (IR) | 2021-03-24 | Customer
114211816 | 20 | Conduct: Initial Review (IR) | 2021-03-31 | Customer
114211816 | 20 | Conduct: Initial Review (IR) | 2021-04-30 | Customer
114211816 | 20 | Conduct: Initial Review (IR) | 2021-08-09 | Customer – requesting an extension
114211816 | 20 | Conduct: Initial Review (IR) | 2021-11-01 | Customer – requesting an extension
114211816 | 20 | Conduct: Initial Review (IR) | 2021-05-13 | Customer – requirement to provide corrected information
114274547 | 21 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
114274547 | 21 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
114274547 | 21 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
114274547 | 21 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
114274547 | 21 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
114274547 | 21 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
114274547 | 21 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
114283060 | 22 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-07-19 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-08-16 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-08-23 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-08-30 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-09-07 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-09-14 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-09-21 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-09-28 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-10-05 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
114283060 | 22 | Conduct: Initial Review (IR) | 2020-12-31 | Customer
114283060 | 22 | Conduct: Initial Review (IR) | 2021-01-08 | Customer
114283060 | 22 | Conduct: Initial Review (IR) | 2021-01-15 | Customer
114283060 | 22 | Conduct: Initial Review (IR) | 2021-01-25 | Customer
114283060 | 22 | Conduct: Initial Review (IR) | 2021-02-01 | Customer
114283060 | 22 | Conduct: Initial Review (IR) | 2021-02-08 | Customer
114283060 | 22 | Conduct: Initial Review (IR) | 2021-02-16 | Customer
114283060 | 22 | Conduct: Initial Review (IR) | 2021-02-23 | Customer
114283060 | 22 | Conduct: Initial Review (IR) | 2021-03-02 | Customer
114283060 | 22 | Conduct: Initial Review (IR) | 2021-03-09 | Customer
114283060 | 22 | Conduct: Initial Review (IR) | 2021-03-16 | Customer
114283060 | 22 | Conduct: Initial Review (IR) | 2021-03-23 | Customer
114283060 | 22 | Conduct: Initial Review (IR) | 2021-03-30 | Customer
114283060 | 22 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
114283060 | 22 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
114283060 | 22 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
114283060 | 22 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
114283060 | 22 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
114283060 | 22 | Conduct: Initial Review (IR) | 2021-10-12 | Customer – requirement to provide corrected information
114401181 | 23 | Construction True-up Report Sent | 2021-05-31 | Project Management – requiring more detailed review
114401181 | 23 | Construction True-up Report Sent | 2021-06-07 | Project Management – requiring more detailed review
114401181 | 23 | Construction True-up Report Sent | 2021-06-30 | Project Management – requiring more detailed review
114637979 | 24 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-10-14 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
114637979 | 24 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
114637979 | 24 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
114637979 | 24 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
114637979 | 24 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
114637979 | 24 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
114949391 | 25 | Conduct: Initial Review (IR) | 2021-07-16 | Cus – requirement to provide a response to deficiency notice
114949391 | 25 | Conduct: Initial Review (IR) | 2021-11-30 | Cus – requirement to provide a response to deficiency notice
114949391 | 25 | Conduct: Initial Review (IR) | 2021-05-19 | Customer
114949391 | 25 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
114949391 | 25 | Conduct: Initial Review (IR) | 2021-07-30 | Customer – requirement to provide corrected information
115103779 | 26 | Conduct: Initial Review (IR) | 2021-07-16 | Cus – requirement to provide a response to deficiency notice
115103779 | 26 | Conduct: Initial Review (IR) | 2021-11-30 | Cus – requirement to provide a response to deficiency notice
115103779 | 26 | Conduct: Initial Review (IR) | 2021-05-19 | Customer
115103779 | 26 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
115103779 | 26 | Conduct: Initial Review (IR) | 2021-07-30 | Customer – requirement to provide corrected information
115279279 | 27 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-10-14 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
115279279 | 27 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
115279279 | 27 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
115279279 | 27 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
115279279 | 27 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
115279279 | 27 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
115279279 | 27 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
115279279 | 27 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
115279279 | 27 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
115638266 | 28 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
115638266 | 28 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
115638266 | 28 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
115638266 | 28 | Conduct: Initial Review (IR) | 2021-04-08 | Customer
115638266 | 28 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
115638266 | 28 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
115638266 | 28 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
115638266 | 28 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
116578736 | 29 | Conduct: Initial Review (IR) | 2021-01-04 | Customer
116578736 | 29 | Conduct: Initial Review (IR) | 2021-01-11 | Customer
116578736 | 29 | Conduct: Initial Review (IR) | 2021-01-19 | Customer
116578736 | 29 | Conduct: Initial Review (IR) | 2021-01-26 | Customer
116578736 | 29 | Conduct: Initial Review (IR) | 2021-02-02 | Customer
116578736 | 29 | Conduct: Initial Review (IR) | 2021-02-09 | Customer
116578736 | 29 | Conduct: Initial Review (IR) | 2021-02-17 | Customer
116578736 | 29 | Conduct: Initial Review (IR) | 2021-02-24 | Customer
116578736 | 29 | Conduct: Initial Review (IR) | 2021-03-03 | Customer
116578736 | 29 | Conduct: Initial Review (IR) | 2021-03-10 | Customer
116578736 | 29 | Conduct: Initial Review (IR) | 2021-03-17 | Customer
116578736 | 29 | Conduct: Initial Review (IR) | 2021-03-24 | Customer
116578736 | 29 | Conduct: Initial Review (IR) | 2021-03-31 | Customer
116578736 | 29 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
116578736 | 29 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
116578736 | 29 | Conduct: Initial Review (IR) | 2021-06-21 | Customer – requirement to provide corrected information
116578736 | 29 | Conduct: Initial Review (IR) | 2021-07-05 | Customer – requirement to provide corrected information
116578736 | 29 | Conduct: Initial Review (IR) | 2021-08-05 | Customer – requirement to provide corrected information
116705746 | 30 | Conduct: Initial Review (IR) | 2021-01-14 | Customer
116705746 | 30 | Conduct: Initial Review (IR) | 2021-01-22 | Customer
116705746 | 30 | Conduct: Initial Review (IR) | 2021-03-26 | Customer
116705746 | 30 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
116705746 | 30 | Conduct: Initial Review (IR) | 2021-05-28 | Customer
116705746 | 30 | Conduct: Initial Review (IR) | 2021-07-28 | Customer – requirement to provide corrected information
116705746 | 30 | Conduct: Initial Review (IR) | 2021-08-27 | Customer – requirement to provide corrected information
116705746 | 30 | Conduct: Initial Review (IR) | 2021-09-27 | Customer – requirement to provide corrected information
116705746 | 30 | Conduct: Initial Review (IR) | 2021-10-27 | Customer – requirement to provide corrected information
116712346 | 31 | Conduct: Initial Review (IR) | 2021-07-13 | Customer – requirement to provide corrected information
117093843 | 32 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
117093843 | 32 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
117093843 | 32 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
117093843 | 32 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
117093843 | 32 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
117093843 | 32 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
117105024 | 33 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
117105024 | 33 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
117105024 | 33 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
117105024 | 33 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
117105024 | 33 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
117105024 | 33 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
117105024 | 33 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
117105024 | 33 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
117105024 | 33 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
117105024 | 33 | Conduct: Initial Review (IR) | 2021-05-03 | Engineering
117210165 | 34 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-07-19 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-08-16 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-08-23 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-08-30 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-09-07 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-09-14 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-09-21 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-09-28 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-10-05 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
117210165 | 34 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
117210165 | 34 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
117210165 | 34 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
117210165 | 34 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
117210165 | 34 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
117210165 | 34 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
117210165 | 34 | Conduct: Initial Review (IR) | 2021-10-12 | Customer – requirement to provide corrected information
117210165 | 34 | Conduct: Initial Review (IR) | 2021-10-19 | Customer – requirement to provide corrected information
117466243 | 35 | Conduct: SIS | 2021-05-03 | Engineering
117466243 | 35 | Conduct: SIS | 2021-05-05 | Engineering – addressing a human error
117620632 | 36 | Conduct: Initial Review (IR) | 2021-06-18 | Engineering – addressing project volume surge
117620632 | 36 | Conduct: Initial Review (IR) | 2021-07-02 | Engineering – addressing project volume surge
117628164 | 37 | Conduct: SIS | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
117628164 | 37 | Conduct: SIS | 2021-05-11 | Customer
117628164 | 37 | Conduct: SIS | 2021-06-11 | Customer – requirement to provide corrected information
117628164 | 37 | Conduct: SIS | 2021-08-12 | Customer – requirement to provide corrected information
117628164 | 37 | Conduct: SIS | 2021-09-12 | Customer – requirement to provide corrected information
117628164 | 37 | Conduct: SIS | 2021-10-12 | Customer – requirement to provide corrected information
117628164 | 37 | Conduct: SIS | 2021-11-12 | Customer – requirement to provide corrected information
117633795 | 38 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
117633795 | 38 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
117633795 | 38 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
117633795 | 38 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
117633795 | 38 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
117633795 | 38 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
117633795 | 38 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
117633795 | 38 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
117633795 | 38 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
117633795 | 38 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
117633795 | 38 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
117633795 | 38 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
117633795 | 38 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
117633795 | 38 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
117633795 | 38 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
117633795 | 38 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
117633795 | 38 | Conduct: Initial Review (IR) | 2021-06-08 | Customer – requirement to provide corrected information
117633795 | 38 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
117633795 | 38 | Conduct: Initial Review (IR) | 2021-06-22 | Customer – requirement to provide corrected information
117633795 | 38 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
117633795 | 38 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
117633795 | 38 | Conduct: Initial Review (IR) | 2021-07-14 | Customer – requirement to provide corrected information
118138973 | 39 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
118138973 | 39 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
118138973 | 39 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
118138973 | 39 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
118138973 | 39 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
118138973 | 39 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
118138973 | 39 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
118138973 | 39 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
118384240 | 40 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
118384240 | 40 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
118384240 | 40 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
118384240 | 40 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
118384240 | 40 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
118384240 | 40 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
118384240 | 40 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
118384240 | 40 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
118393242 | 41 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
118393242 | 41 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
118393242 | 41 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
118393242 | 41 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
118393242 | 41 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
118393242 | 41 | Conduct: Initial Review (IR) | 2021-05-10 | Customer
118393242 | 41 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
118393242 | 41 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
118453482 | 42 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
118453482 | 42 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
118453482 | 42 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
118453482 | 42 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
118453482 | 42 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
118453482 | 42 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
118453482 | 42 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
118453482 | 42 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
118453482 | 42 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
118453482 | 42 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
118573950 | 43 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
118573950 | 43 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
118573950 | 43 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
118573950 | 43 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
118573950 | 43 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
118573950 | 43 | Conduct: Initial Review (IR) | 2021-06-01 | Engineering – requiring more detailed review
118581454 | 44 | Conduct: Initial Review (IR) | 2021-06-10 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-10-14 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
118655173 | 45 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
118655173 | 45 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
118655173 | 45 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
118655173 | 45 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
118655173 | 45 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
118655173 | 45 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
118655173 | 45 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
118655173 | 45 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
118655173 | 45 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
118710005 | 46 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
118710005 | 46 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
118710005 | 46 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
118710005 | 46 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
118710005 | 46 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
118710005 | 46 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
118710005 | 46 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
118710005 | 46 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
118710005 | 46 | Conduct: Initial Review (IR) | 2021-05-27 | Project Management - addressing project volume surge
118715783 | 47 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-10-14 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
118715783 | 47 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
118715783 | 47 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
118715783 | 47 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
118715783 | 47 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
118715783 | 47 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
118715783 | 47 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
118715783 | 47 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
118734619 | 48 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
118734619 | 48 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
118734619 | 48 | Conduct: Initial Review (IR) | 2021-04-23 | Engineering
118734619 | 48 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering – requiring more detailed review
118740272 | 49 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
118740272 | 49 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
118740272 | 49 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
118740272 | 49 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
118740272 | 49 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
118740272 | 49 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
118740272 | 49 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
118740272 | 49 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
118747458 | 50 | Conduct: Initial Review (IR) | 2021-07-20 | Engineering – requiring more detailed review
118761304 | 51 | Conduct: SIS | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
118761304 | 51 | Conduct: SIS | 2021-01-21 | Customer
118761304 | 51 | Conduct: SIS | 2021-01-28 | Customer
118761304 | 51 | Conduct: SIS | 2021-02-04 | Customer
118761304 | 51 | Conduct: SIS | 2021-02-11 | Customer
118761304 | 51 | Conduct: SIS | 2021-02-19 | Customer
118761304 | 51 | Conduct: SIS | 2021-02-26 | Customer
118761304 | 51 | Conduct: SIS | 2021-03-05 | Customer
118761304 | 51 | Conduct: SIS | 2021-03-12 | Customer
118761304 | 51 | Conduct: SIS | 2021-03-19 | Customer
118761304 | 51 | Conduct: SIS | 2021-03-26 | Customer
118761304 | 51 | Conduct: SIS | 2021-04-02 | Customer
118761304 | 51 | Conduct: SIS | 2021-05-31 | Customer – requirement to provide corrected information
118761304 | 51 | Conduct: SIS | 2021-06-30 | Customer – requirement to provide corrected information
118761304 | 51 | Conduct: SIS | 2021-07-30 | Customer – requirement to provide corrected information
118761304 | 51 | Conduct: SIS | 2021-10-08 | Engineering – requiring more detailed review
118761304 | 51 | Conduct: SIS | 2021-10-29 | Engineering – requiring more detailed review
118951999 | 52 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
118951999 | 52 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
118951999 | 52 | Conduct: Initial Review (IR) | 2021-04-27 | Customer
118951999 | 52 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
118951999 | 52 | Conduct: Initial Review (IR) | 2021-05-11 | Customer – requirement to provide corrected information
118951999 | 52 | Conduct: Initial Review (IR) | 2021-05-18 | Customer – requirement to provide corrected information
118951999 | 52 | Conduct: Initial Review (IR) | 2021-05-25 | Customer – requirement to provide corrected information
118951999 | 52 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
118951999 | 52 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
118951999 | 52 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requirement to provide corrected information
119044593 | 53 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
119044593 | 53 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
119044593 | 53 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
119044593 | 53 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
119044593 | 53 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
119044593 | 53 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
119044593 | 53 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
119044593 | 53 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
119044593 | 53 | Conduct: Initial Review (IR) | 2021-04-27 | Customer
119044593 | 53 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
119100564 | 54 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
119209123 | 55 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
119209123 | 55 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
119209123 | 55 | Conduct: Initial Review (IR) | 2021-04-27 | Customer
119209123 | 55 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
119209123 | 55 | Conduct: Initial Review (IR) | 2021-05-11 | Customer – requesting an extension
119291632 | 56 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
119291632 | 56 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
119291632 | 56 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
119291632 | 56 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
119291632 | 56 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
119291632 | 56 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
119291632 | 56 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
119333953 | 57 | Determine Material Modifications | 2021-06-25 | Engineering – requiring more detailed review
119355837 | 58 | Conduct: Supplemental Review (SR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
119355837 | 58 | Conduct: Supplemental Review (SR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
119355837 | 58 | Conduct: Supplemental Review (SR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
119355837 | 58 | Conduct: Initial Review (IR) | 2021-08-27 | Customer
119355837 | 58 | Conduct: Supplemental Review (SR) | 2021-06-04 | Engineering – addressing project volume surge
119355837 | 58 | Conduct: Supplemental Review (SR) | 2021-06-11 | Engineering – addressing project volume surge
119355837 | 58 | Conduct: Supplemental Review (SR) | 2021-08-30 | Engineering – requiring more detailed review
119355837 | 58 | Conduct: Supplemental Review (SR) | 2021-09-14 | Project Management – requiring more detailed review
119355837 | 58 | Conduct: Supplemental Review (SR) | 2021-09-28 | Project Management – requiring more detailed review
119355837 | 58 | Conduct: Supplemental Review (SR) | 2021-10-27 | Project Management – requiring more detailed review
119367709 | 59 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
119367709 | 59 | Conduct: Initial Review (IR) | 2021-06-24 | Cus – requirement to provide a response to deficiency notice
119367709 | 59 | Conduct: Initial Review (IR) | 2021-07-01 | Cus – requirement to provide a response to deficiency notice
119472540 | 60 | Conduct: Initial Review (IR) | 2021-07-23 | Cus – requirement to provide a response to deficiency notice
119472540 | 60 | Conduct: Initial Review (IR) | 2021-09-13 | Cus – requirement to provide a response to deficiency notice
119472540 | 60 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-05-19 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-06-17 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-06-24 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-07-01 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-07-09 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-07-16 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-07-30 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-08-06 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-08-13 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-08-20 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-08-27 | Customer – requirement to provide corrected information
119472540 | 60 | Conduct: Initial Review (IR) | 2021-09-03 | Customer – requirement to provide corrected information
119478606 | 61 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
119478606 | 61 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
119478606 | 61 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
119478606 | 61 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
119478606 | 61 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
119478606 | 61 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
119478606 | 61 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
119478606 | 61 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
119478606 | 61 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
119505557 | 62 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119505557 | 62 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119505557 | 62 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119505557 | 62 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
119505557 | 62 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
119505557 | 62 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
119505557 | 62 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
119505557 | 62 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
119505557 | 62 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
119505557 | 62 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
119519209 | 63 | Conduct: Initial Review (IR) | 2021-06-07 | Engineering – requiring more detailed review
119519209 | 63 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
119519209 | 63 | Conduct: Initial Review (IR) | 2021-06-28 | Engineering – requiring more detailed review
119519209 | 63 | Conduct: Initial Review (IR) | 2021-05-21 | Project Management – addressing a human error
119541435 | 64 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
119549377 | 65 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
119549377 | 65 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
119549377 | 65 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
119549377 | 65 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
119549377 | 65 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
119549377 | 65 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
119549377 | 65 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
119549377 | 65 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
119549377 | 65 | Conduct: Initial Review (IR) | 2021-06-04 | Project Management – addressing a human error
119599059 | 66 | Tender Draft IA | 2021-03-31 | Customer
119599059 | 66 | Tender Draft IA | 2021-05-31 | Customer
119599059 | 66 | Tender Draft IA | 2021-07-30 | Customer – requirement to provide corrected information
119599059 | 66 | Tender Draft IA | 2021-09-30 | Customer – requirement to provide corrected information
119599059 | 66 | Tender Draft IA | 2021-11-30 | Customer – requirement to provide corrected information
119616069 | 67 | Conduct: Initial Review (IR) | 2021-07-09 | Cus – requirement to provide a response to deficiency notice
119616069 | 67 | Conduct: Initial Review (IR) | 2021-07-16 | Cus – requirement to provide a response to deficiency notice
119616069 | 67 | Conduct: Initial Review (IR) | 2021-07-23 | Cus – requirement to provide a response to deficiency notice
119616069 | 67 | Conduct: Initial Review (IR) | 2021-07-30 | Cus – requirement to provide a response to deficiency notice
119616069 | 67 | Conduct: Initial Review (IR) | 2021-08-06 | Cus – requirement to provide a response to deficiency notice
119616069 | 67 | Conduct: Initial Review (IR) | 2021-07-01 | Project Management – requiring more detailed review
119616926 | 68 | Conduct: Initial Review (IR) | 2021-06-02 | Engineering – requiring more detailed review
119625833 | 69 | Conduct: SIS | 2021-06-15 | Engineering – requiring more detailed review
119625833 | 69 | Conduct: SIS | 2021-06-23 | Engineering – requiring more detailed review
119628199 | 70 | Conduct: Supplemental Review (SR) | 2021-04-26 | Engineering
119628199 | 70 | Conduct: Supplemental Review (SR) | 2021-06-25 | Engineering – addressing project volume surge
119628199 | 70 | Conduct: Supplemental Review (SR) | 2021-07-12 | Engineering – addressing project volume surge
119628199 | 70 | Conduct: Supplemental Review (SR) | 2021-05-13 | Engineering – requiring more detailed review
119628199 | 70 | Conduct: Supplemental Review (SR) | 2021-05-27 | Engineering – requiring more detailed review
119628199 | 70 | Conduct: Supplemental Review (SR) | 2021-06-11 | Engineering – requiring more detailed review
119636129 | 71 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
119665112 | 72 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
119665112 | 72 | Conduct: Initial Review (IR) | 2021-05-06 | Engineering – addressing project volume surge
119665112 | 72 | Conduct: Initial Review (IR) | 2021-05-13 | Project Management – addressing a human error
119675425 | 73 | Conduct: Initial Review (IR) | 2021-05-07 | Cus – requirement to provide a response to deficiency notice
119675425 | 73 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
119675425 | 73 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
119675425 | 73 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
119675425 | 73 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
119675425 | 73 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
119675425 | 73 | Conduct: Initial Review (IR) | 2021-04-09 | Customer
119675425 | 73 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
119675425 | 73 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
119675425 | 73 | Conduct: Initial Review (IR) | 2021-04-30 | Customer
119678775 | 74 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
119678775 | 74 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
119678775 | 74 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
119678775 | 74 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
119678775 | 74 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
119678775 | 74 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
119678775 | 74 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
119678775 | 74 | Conduct: Initial Review (IR) | 2021-04-30 | Customer
119678966 | 75 | Conduct: SIS | 2021-07-12 | Engineering – addressing project volume surge
119681621 | 76 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
119681621 | 76 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119681621 | 76 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
119681621 | 76 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
119681621 | 76 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119681621 | 76 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119681621 | 76 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
119681621 | 76 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
119681621 | 76 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
119681621 | 76 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
119712260 | 77 | Conduct: Initial Review (IR) | 2021-05-12 | Cus – requirement to provide a response to deficiency notice
119712260 | 77 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
119712260 | 77 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
119712260 | 77 | Conduct: Initial Review (IR) | 2021-04-08 | Customer
119712260 | 77 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
119712260 | 77 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
119712260 | 77 | Conduct: Initial Review (IR) | 2021-04-28 | Customer
119712260 | 77 | Conduct: Initial Review (IR) | 2021-05-05 | Customer
119724454 | 78 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering – requiring more detailed review
119724454 | 78 | Conduct: Initial Review (IR) | 2021-05-18 | Engineering – requiring more detailed review
119724454 | 78 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
119727305 | 79 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
119727305 | 79 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
119727305 | 79 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
119727305 | 79 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
119727305 | 79 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
119727305 | 79 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
119727305 | 79 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
119727305 | 79 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
119743827 | 80 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119743827 | 80 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
119743827 | 80 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
119743827 | 80 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119743827 | 80 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119743827 | 80 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
119743827 | 80 | Conduct: Initial Review (IR) | 2021-05-10 | Customer
119752683 | 81 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
119752683 | 81 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
119752683 | 81 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119752683 | 81 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
119752683 | 81 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
119752683 | 81 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
119752683 | 81 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
119752683 | 81 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
119752683 | 81 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
119752683 | 81 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
119772541 | 82 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
119772541 | 82 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119772541 | 82 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
119772541 | 82 | Conduct: Initial Review (IR) | 2021-04-16 | Engineering
119772541 | 82 | Conduct: Initial Review (IR) | 2021-04-23 | Engineering
119772541 | 82 | Conduct: Initial Review (IR) | 2021-06-01 | Engineering – requiring more detailed review
119772541 | 82 | Conduct: Initial Review (IR) | 2021-06-08 | Engineering – requiring more detailed review
119772541 | 82 | Conduct: Initial Review (IR) | 2021-05-24 | Project Management - addressing project volume surge
119808996 | 83 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
119808996 | 83 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119808996 | 83 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
119808996 | 83 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
119808996 | 83 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119808996 | 83 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119808996 | 83 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
119808996 | 83 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
119808996 | 83 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
119808996 | 83 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
119828297 | 84 | Conduct: Initial Review (IR) | 2021-05-07 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-06-21 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-07-06 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-07-13 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-07-20 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-07-27 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-08-03 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-08-10 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-08-17 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-08-24 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-08-31 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-09-08 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-09-15 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-09-22 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-09-29 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-10-06 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-10-13 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
119828297 | 84 | Conduct: Initial Review (IR) | 2021-04-30 | Customer
119828297 | 84 | Conduct: Initial Review (IR) | 2021-04-09 | Engineering
119828297 | 84 | Conduct: Initial Review (IR) | 2021-04-16 | Engineering
119828297 | 84 | Conduct: Initial Review (IR) | 2021-04-23 | Engineering
119838415 | 85 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
119838415 | 85 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
119838415 | 85 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
119838415 | 85 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
119838415 | 85 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
119838415 | 85 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
119838415 | 85 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
119838415 | 85 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
119850480 | 86 | Conduct: Initial Review (IR) | 2021-04-23 | EGI
119850480 | 86 | Conduct: Initial Review (IR) | 2021-04-30 | EGI
119850480 | 86 | Conduct: Initial Review (IR) | 2021-04-09 | Engineering
119850480 | 86 | Conduct: Initial Review (IR) | 2021-04-16 | Engineering
119850480 | 86 | Conduct: Initial Review (IR) | 2021-05-07 | Engineering – requiring more detailed review
119850480 | 86 | Conduct: Initial Review (IR) | 2021-05-14 | Engineering – requiring more detailed review
119850480 | 86 | Conduct: Initial Review (IR) | 2021-05-28 | Engineering – requiring more detailed review
119850480 | 86 | Conduct: Initial Review (IR) | 2021-06-14 | Engineering – requiring more detailed review
119850480 | 86 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
119876048 | 87 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
119876048 | 87 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
119876048 | 87 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
119876048 | 87 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
119876048 | 87 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
119876048 | 87 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requirement to provide corrected information
119876048 | 87 | Conduct: Initial Review (IR) | 2021-06-23 | Customer – requirement to provide corrected information
119876048 | 87 | Conduct: Initial Review (IR) | 2021-06-30 | Customer – requirement to provide corrected information
119876048 | 87 | Conduct: Initial Review (IR) | 2021-07-14 | Customer – requirement to provide corrected information
119876048 | 87 | Conduct: Initial Review (IR) | 2021-07-28 | Customer – requirement to provide corrected information
119908241 | 88 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
119908241 | 88 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
119910469 | 89 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119910469 | 89 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119910469 | 89 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119910469 | 89 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
119910469 | 89 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
119910469 | 89 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
119910469 | 89 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
119910469 | 89 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
119910469 | 89 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
119910469 | 89 | Conduct: Initial Review (IR) | 2021-06-01 | Project Management - addressing project volume surge
119928016 | 90 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
119928016 | 90 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
119928016 | 90 | Conduct: Initial Review (IR) | 2021-09-21 | Cus – requirement to provide a response to deficiency notice
119928016 | 90 | Conduct: Initial Review (IR) | 2021-09-28 | Cus – requirement to provide a response to deficiency notice
119928016 | 90 | Conduct: Initial Review (IR) | 2021-10-05 | Cus – requirement to provide a response to deficiency notice
119928016 | 90 | Conduct: Initial Review (IR) | 2021-10-12 | Cus – requirement to provide a response to deficiency notice
119928016 | 90 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
119928016 | 90 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
119928016 | 90 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
119928016 | 90 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
119928016 | 90 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-06-18 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-06-25 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-07-02 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-07-12 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-07-19 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-07-26 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-08-02 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-08-09 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-08-16 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-08-23 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-08-30 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-09-07 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-09-14 | Customer – requirement to provide corrected information
119928016 | 90 | Conduct: Initial Review (IR) | 2021-10-19 | Customer – requirement to provide corrected information
119928187 | 91 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-07-08 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-07-15 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-07-22 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-07-29 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-08-05 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-08-12 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-08-19 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-08-26 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-09-02 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-09-17 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-09-24 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-10-01 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-10-08 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
119928187 | 91 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
119928187 | 91 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
119928187 | 91 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
119928187 | 91 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
119928187 | 91 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requirement to provide corrected information
119928187 | 91 | Conduct: Initial Review (IR) | 2021-06-23 | Customer – requirement to provide corrected information
119928187 | 91 | Conduct: Initial Review (IR) | 2021-05-18 | Project Management - addressing project volume surge
119928187 | 91 | Conduct: Initial Review (IR) | 2021-06-09 | Project Management - addressing project volume surge
119928187 | 91 | Conduct: Initial Review (IR) | 2021-06-30 | Project Management - addressing project volume surge
119933328 | 92 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119933328 | 92 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
119933328 | 92 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119933328 | 92 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
119933328 | 92 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
119933328 | 92 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
119933328 | 92 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
119933328 | 92 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
119933328 | 92 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
119933328 | 92 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
119933328 | 92 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
119933328 | 92 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
119933328 | 92 | Conduct: Initial Review (IR) | 2021-05-03 | Engineering
119941653 | 93 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119941653 | 93 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
119941653 | 93 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
119941653 | 93 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119941653 | 93 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119941653 | 93 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
119941653 | 93 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
119941653 | 93 | Conduct: Initial Review (IR) | 2021-05-10 | Customer
119943292 | 94 | Conduct: SIS | 2021-05-20 | Engineering – addressing project volume surge
119956320 | 95 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
119956320 | 95 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
119956320 | 95 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
119956320 | 95 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
119956320 | 95 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
119956320 | 95 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
119956320 | 95 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
119956320 | 95 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
119959836 | 96 | Conduct: Initial Review (IR) | 2021-04-15 | Engineering
119959836 | 96 | Conduct: Initial Review (IR) | 2021-04-22 | Engineering
119959836 | 96 | Conduct: Initial Review (IR) | 2021-04-29 | Engineering
119959836 | 96 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
119959836 | 96 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
119959836 | 96 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – requiring more detailed review
119959836 | 96 | Conduct: Initial Review (IR) | 2021-05-06 | Project Management – requiring more detailed review
119960485 | 97 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
119960485 | 97 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
119960485 | 97 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
119960485 | 97 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
119960485 | 97 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
119960485 | 97 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
119960485 | 97 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
119960485 | 97 | Conduct: Initial Review (IR) | 2021-05-10 | Customer
119967284 | 98 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
119967284 | 98 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
119967284 | 98 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
119967284 | 98 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
119967284 | 98 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
119967284 | 98 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
119967284 | 98 | Conduct: Initial Review (IR) | 2021-07-19 | Cus – requirement to provide a response to deficiency notice
119967284 | 98 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
119967284 | 98 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
119967284 | 98 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
119967284 | 98 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
119967284 | 98 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
119967284 | 98 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
119967284 | 98 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
119967284 | 98 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
119998942 | 99 | Conduct: Supplemental Review (SR) | 2021-05-18 | Engineering – requiring more detailed review
120000688 | 100 | Conduct: Initial Review (IR) | 2021-05-12 | Engineering – requiring more detailed review
120000688 | 100 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – requiring more detailed review
120000688 | 100 | Conduct: Initial Review (IR) | 2021-06-10 | Engineering – requiring more detailed review
120013081 | 101 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120013081 | 101 | Conduct: Initial Review (IR) | 2021-04-09 | Customer
120013081 | 101 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
120013081 | 101 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
120013081 | 101 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
120013081 | 101 | Conduct: Initial Review (IR) | 2021-05-13 | Customer – requirement to provide corrected information
120013081 | 101 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120013081 | 101 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
120013081 | 101 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
120013081 | 101 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120019403 | 102 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
120044316 | 103 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120044316 | 103 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120044316 | 103 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120044316 | 103 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
120079860 | 104 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120079860 | 104 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120079860 | 104 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
120079860 | 104 | Conduct: Initial Review (IR) | 2021-07-01 | Cus – requirement to provide a response to deficiency notice
120079860 | 104 | Conduct: Initial Review (IR) | 2021-07-09 | Cus – requirement to provide a response to deficiency notice
120079860 | 104 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
120079860 | 104 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
120079860 | 104 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
120079860 | 104 | Conduct: Initial Review (IR) | 2021-08-16 | Cus – requirement to provide a response to deficiency notice
120079860 | 104 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
120079860 | 104 | Conduct: Initial Review (IR) | 2021-07-16 | Customer – requirement to provide corrected information
120079860 | 104 | Conduct: Initial Review (IR) | 2021-08-30 | Customer – requirement to provide corrected information
120079860 | 104 | Conduct: Initial Review (IR) | 2021-08-23 | Project Management – requiring more detailed review
120080006 | 105 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120080006 | 105 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120080006 | 105 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120080006 | 105 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
120080006 | 105 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
120080006 | 105 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
120080006 | 105 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
120080006 | 105 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120080006 | 105 | Conduct: Initial Review (IR) | 2021-05-10 | Customer
120080006 | 105 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
120080006 | 105 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120080006 | 105 | Conduct: Initial Review (IR) | 2021-06-22 | Project Management - addressing project volume surge
120080007 | 106 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
120080428 | 107 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120080428 | 107 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
120080428 | 107 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
120080428 | 107 | Conduct: Initial Review (IR) | 2021-02-05 | Engineering
120080428 | 107 | Conduct: Initial Review (IR) | 2021-02-12 | Engineering
120080428 | 107 | Conduct: Initial Review (IR) | 2021-02-22 | Engineering
120080428 | 107 | Conduct: Initial Review (IR) | 2021-03-01 | Engineering
120080428 | 107 | Conduct: Initial Review (IR) | 2021-03-08 | Engineering
120080428 | 107 | Conduct: Initial Review (IR) | 2021-03-15 | Engineering
120080428 | 107 | Conduct: Initial Review (IR) | 2021-03-22 | Engineering
120080428 | 107 | Conduct: Initial Review (IR) | 2021-03-29 | Engineering
120080428 | 107 | Conduct: Initial Review (IR) | 2021-04-26 | Engineering
120080428 | 107 | Conduct: Initial Review (IR) | 2021-05-07 | Engineering
120080428 | 107 | Conduct: Initial Review (IR) | 2021-05-14 | Engineering – addressing project volume surge
120080428 | 107 | Conduct: Initial Review (IR) | 2021-05-21 | Project Management – addressing a human error
120090412 | 108 | Conduct: SIS | 2021-05-31 | Customer – requirement to provide corrected information
120090412 | 108 | Conduct: SIS | 2021-07-16 | Customer – requirement to provide corrected information
120090412 | 108 | Conduct: SIS | 2021-07-23 | Customer – requirement to provide corrected information
120090412 | 108 | Conduct: SIS | 2021-09-03 | Customer – requirement to provide corrected information
120090412 | 108 | Conduct: SIS | 2021-06-11 | Engineering – requiring more detailed review
120090412 | 108 | Conduct: SIS | 2021-07-09 | Engineering – requiring more detailed review
120090412 | 108 | Conduct: SIS | 2021-07-30 | Engineering – requiring more detailed review
120090412 | 108 | Conduct: SIS | 2021-08-13 | Engineering – requiring more detailed review
120090412 | 108 | Conduct: SIS | 2021-08-27 | Engineering – requiring more detailed review
120090412 | 108 | Conduct: SIS | 2021-09-10 | Engineering – requiring more detailed review
120090412 | 108 | Conduct: SIS | 2021-09-17 | Engineering – requiring more detailed review
120090412 | 108 | Conduct: SIS | 2021-10-15 | Engineering – requiring more detailed review
120090412 | 108 | Conduct: SIS | 2021-10-22 | Engineering – requiring more detailed review
120097569 | 109 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120097569 | 109 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
120097569 | 109 | Conduct: Initial Review (IR) | 2021-04-23 | Engineering
120097569 | 109 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
120100772 | 110 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120100772 | 110 | Conduct: Initial Review (IR) | 2021-07-19 | Engineering – requiring more detailed review
120100772 | 110 | Conduct: Initial Review (IR) | 2021-08-09 | Engineering – requiring more detailed review
120100784 | 111 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120108592 | 112 | Conduct: Initial Review (IR) | 2021-05-19 | Project Management – requiring more detailed review
120108592 | 112 | Conduct: Initial Review (IR) | 2021-07-01 | Project Management – requiring more detailed review
120110310 | 113 | Conduct: Screens Q and R | 2021-02-09 | Engineering
120110310 | 113 | Conduct: Screens Q and R | 2021-02-17 | Engineering
120110310 | 113 | Conduct: SIS | 2021-06-02 | Engineering – requiring more detailed review
120110310 | 113 | Conduct: SIS | 2021-06-09 | Engineering – requiring more detailed review
120110310 | 113 | Determine Material Modifications | 2021-09-27 | Engineering – requiring more detailed review
120110310 | 113 | Determine Material Modifications | 2021-09-29 | Engineering – requiring more detailed review
120110310 | 113 | Determine Material Modifications | 2021-10-01 | Engineering – requiring more detailed review
120118148 | 114 | Conduct: Initial Review (IR) | 2021-05-05 | Customer
120118148 | 114 | Conduct: Initial Review (IR) | 2021-05-19 | Customer – requirement to provide corrected information
120118148 | 114 | Conduct: Initial Review (IR) | 2021-04-21 | Engineering
120118148 | 114 | Conduct: Initial Review (IR) | 2021-06-03 | Engineering – requiring more detailed review
120118148 | 114 | Conduct: Supplemental Review (SR) | 2021-08-11 | Engineering – requiring more detailed review
120118148 | 114 | Conduct: Initial Review (IR) | 2021-06-10 | Project Management - addressing project volume surge
120138011 | 115 | Conduct: Initial Review (IR) | 2021-05-07 | Cus – requirement to provide a response to deficiency notice
120138011 | 115 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120138011 | 115 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120138011 | 115 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
120138011 | 115 | Conduct: Initial Review (IR) | 2021-07-01 | Cus – requirement to provide a response to deficiency notice
120138011 | 115 | Conduct: Initial Review (IR) | 2021-07-09 | Cus – requirement to provide a response to deficiency notice
120138011 | 115 | Conduct: Initial Review (IR) | 2021-07-16 | Cus – requirement to provide a response to deficiency notice
120138011 | 115 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
120138011 | 115 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
120138011 | 115 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
120143175 | 116 | Conduct: Supplemental Review (SR) | 2021-04-26 | Customer
120143175 | 116 | Conduct: Supplemental Review (SR) | 2021-04-19 | Engineering
120143175 | 116 | Conduct: Supplemental Review (SR) | 2021-05-03 | Engineering
120143175 | 116 | Conduct: Screens Q and R | 2021-06-14 | Engineering – addressing project volume surge
120161122 | 117 | Conduct: Supplemental Review (SR) | 2021-03-18 | Customer
120161122 | 117 | Conduct: Supplemental Review (SR) | 2021-03-25 | Customer
120161122 | 117 | Conduct: Supplemental Review (SR) | 2021-04-01 | Customer
120161122 | 117 | Conduct: Supplemental Review (SR) | 2021-04-08 | Customer
120161122 | 117 | Conduct: Supplemental Review (SR) | 2021-04-20 | Customer
120161122 | 117 | Conduct: Supplemental Review (SR) | 2021-05-18 | Customer
120161122 | 117 | Conduct: Supplemental Review (SR) | 2021-03-16 | Engineering
120161122 | 117 | Conduct: Supplemental Review (SR) | 2021-05-25 | Engineering – requiring more detailed review
120161486 | 118 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120161486 | 118 | Conduct: Initial Review (IR) | 2021-05-29 | Engineering – requiring more detailed review
120161486 | 118 | Conduct: Initial Review (IR) | 2021-06-14 | Engineering – requiring more detailed review
120161486 | 118 | Conduct: Initial Review (IR) | 2021-07-12 | Engineering – requiring more detailed review
120163139 | 119 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
120163139 | 119 | Conduct: Initial Review (IR) | 2021-05-10 | Customer
120163139 | 119 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
120163230 | 120 | Conduct: SIS | 2021-07-07 | Engineering – addressing project volume surge
120163237 | 121 | Conduct: SIS | 2021-07-07 | Engineering – addressing project volume surge
120163262 | 122 | Conduct: SIS | 2021-07-07 | Engineering – addressing project volume surge
120164941 | 123 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120164941 | 123 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120164941 | 123 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120164941 | 123 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120164941 | 123 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120164941 | 123 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
120164941 | 123 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120164941 | 123 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
120177090 | 124 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120177090 | 124 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120177090 | 124 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
120177090 | 124 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120177090 | 124 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
120177090 | 124 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
120177090 | 124 | Conduct: Initial Review (IR) | 2021-04-14 | Engineering
120192828 | 125 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120192828 | 125 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120192828 | 125 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120192828 | 125 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120192828 | 125 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120192828 | 125 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
120192828 | 125 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120192828 | 125 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
120205868 | 126 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120205868 | 126 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120205868 | 126 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120205868 | 126 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
120205868 | 126 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120205868 | 126 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
120210252 | 127 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
120210252 | 127 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120210252 | 127 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120210252 | 127 | Conduct: Initial Review (IR) | 2021-05-05 | Engineering
120210252 | 127 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120210324 | 128 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – addressing project volume surge
120210324 | 128 | Conduct: Initial Review (IR) | 2021-07-05 | Project Management – requiring more detailed review
120210381 | 129 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120210381 | 129 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120210381 | 129 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120210381 | 129 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120210381 | 129 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120210381 | 129 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120216210 | 130 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120216883 | 131 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120216883 | 131 | Conduct: Initial Review (IR) | 2021-05-28 | Customer – requirement to provide corrected information
120217485 | 132 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
120217485 | 132 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
120217485 | 132 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
120217485 | 132 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
120217485 | 132 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
120217596 | 133 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120217596 | 133 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120217596 | 133 | Conduct: Initial Review (IR) | 2021-04-27 | Customer
120217596 | 133 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120217596 | 133 | Conduct: Initial Review (IR) | 2021-05-11 | Customer – requirement to provide corrected information
120217596 | 133 | Conduct: Initial Review (IR) | 2021-05-18 | Customer – requirement to provide corrected information
120218582 | 134 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120218582 | 134 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120218582 | 134 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120218582 | 134 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120218582 | 134 | Conduct: Initial Review (IR) | 2021-04-09 | Customer
120218582 | 134 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
120218582 | 134 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120218582 | 134 | Conduct: Initial Review (IR) | 2021-04-30 | Customer
120218582 | 134 | Conduct: Initial Review (IR) | 2021-05-07 | Project Management – requiring more detailed review
120218702 | 135 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120218702 | 135 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120218702 | 135 | Conduct: Initial Review (IR) | 2021-04-09 | Customer
120218702 | 135 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120218702 | 135 | Conduct: Initial Review (IR) | 2021-05-07 | Customer
120218702 | 135 | Conduct: Initial Review (IR) | 2021-06-18 | Customer – requirement to provide corrected information
120218702 | 135 | Conduct: Initial Review (IR) | 2021-07-02 | Customer – requirement to provide corrected information
120218702 | 135 | Conduct: Initial Review (IR) | 2021-07-19 | Customer – requirement to provide corrected information
120218702 | 135 | Conduct: Initial Review (IR) | 2021-08-02 | Customer – requirement to provide corrected information
120218702 | 135 | Conduct: Initial Review (IR) | 2021-08-16 | Customer – requirement to provide corrected information
120218702 | 135 | Conduct: Initial Review (IR) | 2021-08-30 | Customer – requirement to provide corrected information
120219174 | 136 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
120219174 | 136 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120219174 | 136 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120219174 | 136 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120219174 | 136 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
120219174 | 136 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
120219174 | 136 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
120219174 | 136 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
120225309 | 137 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
120228564 | 138 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120228564 | 138 | Conduct: Initial Review (IR) | 2021-03-25 | Customer
120228564 | 138 | Conduct: Initial Review (IR) | 2021-04-01 | Customer
120228564 | 138 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
120228564 | 138 | Conduct: Initial Review (IR) | 2021-05-13 | Customer – requirement to provide corrected information
120228564 | 138 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
120228564 | 138 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120231142 | 139 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120231142 | 139 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120231142 | 139 | Conduct: Initial Review (IR) | 2021-06-21 | Cus – requirement to provide a response to deficiency notice
120231142 | 139 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120231142 | 139 | Conduct: Initial Review (IR) | 2021-05-07 | Customer
120231142 | 139 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
120231142 | 139 | Conduct: Initial Review (IR) | 2021-07-05 | Customer – requirement to provide corrected information
120231142 | 139 | Conduct: Initial Review (IR) | 2021-07-19 | Customer – requirement to provide corrected information
120231142 | 139 | Conduct: Initial Review (IR) | 2021-08-09 | Customer – requirement to provide corrected information
120242519 | 140 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120242519 | 140 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120242519 | 140 | Conduct: Initial Review (IR) | 2021-03-25 | Customer
120242519 | 140 | Conduct: Initial Review (IR) | 2021-04-01 | Customer
120242519 | 140 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120242519 | 140 | Conduct: Initial Review (IR) | 2021-05-11 | Customer
120242519 | 140 | Conduct: Initial Review (IR) | 2021-06-23 | Customer – requirement to provide corrected information
120242519 | 140 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
120242519 | 140 | Conduct: Initial Review (IR) | 2021-07-28 | Customer – requirement to provide corrected information
120242519 | 140 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120242519 | 140 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120242519 | 140 | Conduct: Initial Review (IR) | 2021-03-25 | Customer
120242519 | 140 | Conduct: Initial Review (IR) | 2021-04-01 | Customer
120242519 | 140 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120242519 | 140 | Conduct: Initial Review (IR) | 2021-05-11 | Customer
120242519 | 140 | Conduct: Initial Review (IR) | 2021-06-23 | Customer – requirement to provide corrected information
120242519 | 140 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
120242519 | 140 | Conduct: Initial Review (IR) | 2021-07-28 | Customer – requirement to provide corrected information
120242519 | 140 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120242519 | 140 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120242519 | 140 | Conduct: Initial Review (IR) | 2021-03-25 | Customer
120242519 | 140 | Conduct: Initial Review (IR) | 2021-04-01 | Customer
120242519 | 140 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120242519 | 140 | Conduct: Initial Review (IR) | 2021-05-11 | Customer
120242519 | 140 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
120242519 | 140 | Conduct: Initial Review (IR) | 2021-07-28 | Customer – requirement to provide corrected information
120242519 | 140 | Conduct: Initial Review (IR) | 2021-06-23 | Customer – requirement to provide corrected information
120242688 | 141 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120242688 | 141 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120242688 | 141 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering – requiring more detailed review
120242688 | 141 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120242688 | 141 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120242688 | 141 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering – requiring more detailed review
120242688 | 141 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120242688 | 141 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120242688 | 141 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering – requiring more detailed review
120256198 | 142 | Conduct: Initial Review (IR) | 2021-03-04 | Customer
120256198 | 142 | Conduct: Initial Review (IR) | 2021-03-18 | Customer
120256198 | 142 | Conduct: Initial Review (IR) | 2021-04-08 | Customer
120256198 | 142 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
120256198 | 142 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120256198 | 142 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
120256198 | 142 | Conduct: Initial Review (IR) | 2021-07-01 | Customer – requirement to provide corrected information
120256198 | 142 | Conduct: Initial Review (IR) | 2021-07-22 | Customer – requirement to provide corrected information
120256198 | 142 | Conduct: Initial Review (IR) | 2021-03-04 | Customer
120256198 | 142 | Conduct: Initial Review (IR) | 2021-03-18 | Customer
120256198 | 142 | Conduct: Initial Review (IR) | 2021-04-08 | Customer
120256198 | 142 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
120256198 | 142 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120256198 | 142 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
120256198 | 142 | Conduct: Initial Review (IR) | 2021-07-01 | Customer – requirement to provide corrected information
120256198 | 142 | Conduct: Initial Review (IR) | 2021-07-22 | Customer – requirement to provide corrected information
120256198 | 142 | Conduct: Initial Review (IR) | 2021-03-04 | Customer
120256198 | 142 | Conduct: Initial Review (IR) | 2021-03-18 | Customer
120256198 | 142 | Conduct: Initial Review (IR) | 2021-04-08 | Customer
120256198 | 142 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
120256198 | 142 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120256198 | 142 | Conduct: Initial Review (IR) | 2021-07-22 | Customer – requirement to provide corrected information
120256198 | 142 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
120256198 | 142 | Conduct: Initial Review (IR) | 2021-07-01 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
120257223 | 143 | Conduct: Initial Review (IR) | 2021-04-28 | Customer
120257223 | 143 | Conduct: Initial Review (IR) | 2021-05-05 | Customer
120257223 | 143 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-05-19 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-06-17 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-06-24 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-07-01 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-07-09 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-07-16 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-07-23 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-07-30 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-08-06 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-08-13 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-08-20 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-08-27 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-09-03 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-09-13 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-09-17 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-09-24 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-10-01 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-10-08 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-10-15 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-10-22 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
120257223 | 143 | Conduct: Initial Review (IR) | 2021-04-28 | Customer
120257223 | 143 | Conduct: Initial Review (IR) | 2021-05-05 | Customer
120257223 | 143 | Conduct: Initial Review (IR) | 2021-07-30 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-05-19 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-06-17 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-06-24 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-07-01 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-07-09 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-07-16 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-07-23 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-08-06 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-08-13 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-08-20 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-08-27 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-09-03 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-09-13 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-09-17 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-09-24 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-10-01 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-10-08 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-10-15 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-10-22 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-10-29 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-11-05 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-11-15 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-11-22 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-12-01 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-12-08 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-12-15 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-12-22 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-12-30 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2022-01-06 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2022-01-14 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2022-01-24 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2022-01-31 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
120257223 | 143 | Conduct: Initial Review (IR) | 2021-04-28 | Customer
120257223 | 143 | Conduct: Initial Review (IR) | 2021-05-05 | Customer
120257223 | 143 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-06-24 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-07-01 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-07-09 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-07-16 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-07-23 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-07-30 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-05-19 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-06-17 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-08-06 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-08-13 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-08-20 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-08-27 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-09-03 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-09-13 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-09-17 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-09-24 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-10-01 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-10-08 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-10-15 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-10-22 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-10-29 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-11-05 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-11-15 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-11-22 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-12-01 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-12-08 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-12-15 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-12-22 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2021-12-30 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2022-01-06 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2022-01-14 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2022-01-24 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2022-01-31 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2022-02-07 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2022-02-14 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2022-03-14 | Customer – requirement to provide corrected information
120257223 | 143 | Conduct: Initial Review (IR) | 2022-04-26 | Customer – requirement to provide corrected information
120259306 | 144 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
120259306 | 144 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120259306 | 144 | Conduct: Initial Review (IR) | 2021-04-23 | EGI
120259306 | 144 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
120368266 | 145 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120368266 | 145 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120368266 | 145 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120368266 | 145 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
120406445 | 146 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-07-08 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-07-15 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-07-22 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-07-29 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-08-05 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-08-12 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-08-19 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-08-26 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-09-02 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-09-17 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-09-24 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-10-01 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-10-08 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
120406445 | 146 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120406445 | 146 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120406445 | 146 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
120406445 | 146 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120406445 | 146 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120406445 | 146 | Conduct: Initial Review (IR) | 2021-06-30 | Customer – requirement to provide corrected information
120407972 | 147 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120407972 | 147 | Conduct: Initial Review (IR) | 2021-05-05 | Engineering
120407972 | 147 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120407972 | 147 | Conduct: Initial Review (IR) | 2021-05-05 | Engineering
120407972 | 147 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120407972 | 147 | Conduct: Initial Review (IR) | 2021-05-05 | Engineering
120418596 | 148 | Conduct: SIS | 2021-07-16 | Project Management - addressing project volume surge
120418596 | 148 | Conduct: SIS | 2021-07-16 | Project Management - addressing project volume surge
120418596 | 148 | Conduct: SIS | 2021-07-16 | Project Management - addressing project volume surge
120418656 | 149 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
120418656 | 149 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
120418656 | 149 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
120418656 | 149 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
120418656 | 149 | Conduct: Initial Review (IR) | 2021-06-22 | Customer – requirement to provide corrected information
120418656 | 149 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
120418656 | 149 | Conduct: Initial Review (IR) | 2021-07-14 | Customer – requirement to provide corrected information
120418656 | 149 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120418656 | 149 | Conduct: Initial Review (IR) | 2021-05-04 | Engineering
120418656 | 149 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering – addressing a human error
120418656 | 149 | Conduct: Initial Review (IR) | 2021-06-01 | Engineering – requiring more detailed review
120418656 | 149 | Conduct: Initial Review (IR) | 2021-06-15 | Engineering – requiring more detailed review
120418656 | 149 | Conduct: Initial Review (IR) | 2021-05-18 | Project Management - addressing project volume surge
120418656 | 149 | Conduct: Initial Review (IR) | 2021-07-07 | Project Management - addressing project volume surge
120418656 | 149 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
120418656 | 149 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
120418656 | 149 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
120418656 | 149 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
120418656 | 149 | Conduct: Initial Review (IR) | 2021-06-22 | Customer – requirement to provide corrected information
120418656 | 149 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
120418656 | 149 | Conduct: Initial Review (IR) | 2021-07-14 | Customer – requirement to provide corrected information
120418656 | 149 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120418656 | 149 | Conduct: Initial Review (IR) | 2021-05-04 | Engineering
120418656 | 149 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering – addressing a human error
120418656 | 149 | Conduct: Initial Review (IR) | 2021-06-01 | Engineering – requiring more detailed review
120418656 | 149 | Conduct: Initial Review (IR) | 2021-06-15 | Engineering – requiring more detailed review
120418656 | 149 | Conduct: Initial Review (IR) | 2021-05-18 | Project Management - addressing project volume surge
120418656 | 149 | Conduct: Initial Review (IR) | 2021-07-07 | Project Management - addressing project volume surge
120418656 | 149 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
120418656 | 149 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
120418656 | 149 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
120418656 | 149 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
120418656 | 149 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
120418656 | 149 | Conduct: Initial Review (IR) | 2021-06-22 | Customer – requirement to provide corrected information
120418656 | 149 | Conduct: Initial Review (IR) | 2021-07-14 | Customer – requirement to provide corrected information
120418656 | 149 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120418656 | 149 | Conduct: Initial Review (IR) | 2021-05-04 | Engineering
120418656 | 149 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering – addressing a human error
120418656 | 149 | Conduct: Initial Review (IR) | 2021-06-01 | Engineering – requiring more detailed review
120418656 | 149 | Conduct: Initial Review (IR) | 2021-06-15 | Engineering – requiring more detailed review
120418656 | 149 | Conduct: Initial Review (IR) | 2021-05-18 | Project Management - addressing project volume surge
120418656 | 149 | Conduct: Initial Review (IR) | 2021-07-07 | Project Management - addressing project volume surge
120419880 | 150 | Conduct: Screens Q and R | 2021-05-20 | Project Management – addressing a human error
120419880 | 150 | Conduct: Screens Q and R | 2021-05-20 | Project Management – addressing a human error
120419880 | 150 | Conduct: Screens Q and R | 2021-05-20 | Project Management – addressing a human error
120425938 | 151 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – addressing project volume surge
120425938 | 151 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120425938 | 151 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120425938 | 151 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – addressing project volume surge
120425938 | 151 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120425938 | 151 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120425938 | 151 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – addressing project volume surge
120425938 | 151 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120425938 | 151 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120427556 | 152 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
120427556 | 152 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120427556 | 152 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120427556 | 152 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
120433944 | 153 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120433944 | 153 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120433944 | 153 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120433944 | 153 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120433944 | 153 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120433944 | 153 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requesting an extension
120434315 | 154 | Conduct: Initial Review (IR) | 2021-06-03 | Engineering – requiring more detailed review
120434315 | 154 | Conduct: Initial Review (IR) | 2021-06-03 | Engineering – requiring more detailed review
120434315 | 154 | Conduct: Initial Review (IR) | 2021-06-03 | Engineering – requiring more detailed review
120434649 | 155 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
120434649 | 155 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
120434649 | 155 | Conduct: Initial Review (IR) | 2021-04-26 | EGI
120434649 | 155 | Conduct: Initial Review (IR) | 2021-05-03 | Engineering
120443026 | 156 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120443026 | 156 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120443026 | 156 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120443026 | 156 | Conduct: Initial Review (IR) | 2021-05-10 | Customer
120443026 | 156 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requesting an extension
120443026 | 156 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120443026 | 156 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
120447712 | 157 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120447712 | 157 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120447712 | 157 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120447712 | 157 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120447712 | 157 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120447712 | 157 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
120447712 | 157 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120447712 | 157 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
120448080 | 158 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120450167 | 159 | Conduct: Initial Review (IR) | 2021-05-12 | Cus – requirement to provide a response to deficiency notice
120450167 | 159 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
120450167 | 159 | Conduct: Initial Review (IR) | 2021-04-07 | Customer
120450167 | 159 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
120450167 | 159 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
120450216 | 160 | Conduct: Initial Review (IR) | 2021-04-14 | Engineering
120450216 | 160 | Conduct: Initial Review (IR) | 2021-04-20 | Engineering
120450216 | 160 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
120450216 | 160 | Conduct: Initial Review (IR) | 2021-05-17 | Engineering – requiring more detailed review
120450216 | 160 | Conduct: Initial Review (IR) | 2021-05-24 | Project Management – requiring more detailed review
120452644 | 161 | Conduct: Initial Review (IR) | 2021-05-26 | Project Management – requiring more detailed review
120453208 | 162 | Conduct: Initial Review (IR) | 2021-06-10 | Cus – requirement to provide a response to deficiency notice
120453208 | 162 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120453208 | 162 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
120454060 | 163 | Conduct: Screens Q and R | 2021-05-07 | Engineering – requiring more detailed review
120454060 | 163 | Determine Material Modifications | 2021-09-29 | Engineering – requiring more detailed review
120454060 | 163 | Determine Material Modifications | 2021-10-06 | Project Management – requiring more detailed review
120454060 | 163 | Conduct: Screens Q and R | 2021-05-07 | Engineering – requiring more detailed review
120454060 | 163 | Determine Material Modifications | 2021-09-29 | Engineering – requiring more detailed review
120454060 | 163 | Determine Material Modifications | 2021-10-06 | Project Management – requiring more detailed review
120454060 | 163 | Conduct: Screens Q and R | 2021-05-07 | Engineering – requiring more detailed review
120454060 | 163 | Determine Material Modifications | 2021-09-29 | Engineering – requiring more detailed review
120454060 | 163 | Determine Material Modifications | 2021-10-06 | Project Management – requiring more detailed review
120462840 | 164 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120462840 | 164 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120462840 | 164 | Conduct: Initial Review (IR) | 2021-05-10 | Customer
120462840 | 164 | Conduct: Initial Review (IR) | 2021-06-01 | Project Management - addressing project volume surge
120463149 | 165 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
120463149 | 165 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120463149 | 165 | Conduct: Initial Review (IR) | 2021-05-10 | Customer
120463149 | 165 | Conduct: Initial Review (IR) | 2021-05-24 | Engineering – addressing a human error
120463149 | 165 | Conduct: Initial Review (IR) | 2021-05-17 | Engineering – requiring more detailed review
120463149 | 165 | Conduct: Initial Review (IR) | 2021-06-01 | Project Management – requiring more detailed review
120464204 | 166 | Conduct: Screens Q and R | 2021-05-26 | Engineering – addressing project volume surge
120464204 | 166 | Conduct: Screens Q and R | 2021-06-04 | Engineering – addressing project volume surge
120464204 | 166 | Conduct: Screens Q and R | 2021-06-15 | Engineering – requiring more detailed review
120464204 | 166 | Conduct: Screens Q and R | 2021-06-22 | Engineering – requiring more detailed review
120464204 | 166 | Conduct: Screens Q and R | 2021-06-29 | Engineering – requiring more detailed review
120464204 | 166 | Conduct: Screens Q and R | 2021-05-26 | Engineering – addressing project volume surge
120464204 | 166 | Conduct: Screens Q and R | 2021-06-04 | Engineering – addressing project volume surge
120464204 | 166 | Conduct: Screens Q and R | 2021-06-15 | Engineering – requiring more detailed review
120464204 | 166 | Conduct: Screens Q and R | 2021-06-22 | Engineering – requiring more detailed review
120464204 | 166 | Conduct: Screens Q and R | 2021-06-29 | Engineering – requiring more detailed review
120464204 | 166 | Conduct: Screens Q and R | 2021-05-26 | Engineering – addressing project volume surge
120464204 | 166 | Conduct: Screens Q and R | 2021-06-04 | Engineering – addressing project volume surge
120464204 | 166 | Conduct: Screens Q and R | 2021-06-15 | Engineering – requiring more detailed review
120464204 | 166 | Conduct: Screens Q and R | 2021-06-29 | Engineering – requiring more detailed review
120464204 | 166 | Conduct: Screens Q and R | 2021-06-22 | Engineering – requiring more detailed review
120465673 | 167 | Conduct: SIS | 2021-06-11 | Engineering – addressing project volume surge
120465673 | 167 | Conduct: SIS | 2021-06-11 | Engineering – addressing project volume surge
120465673 | 167 | Conduct: SIS | 2021-06-11 | Engineering – addressing project volume surge
120467950 | 168 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-07-19 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-08-16 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-08-23 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-08-30 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-09-07 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-09-14 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-09-21 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-09-28 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-10-05 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
120467950 | 168 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120467950 | 168 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120467950 | 168 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
120467950 | 168 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requesting an extension
120467950 | 168 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120467950 | 168 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
120467950 | 168 | Conduct: Initial Review (IR) | 2021-10-12 | Customer – requirement to provide corrected information
120469313 | 169 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
120469313 | 169 | Conduct: Initial Review (IR) | 2021-06-01 | Project Management - addressing project volume surge
120477883 | 170 | Conduct: Supplemental Review (SR) | 2021-06-29 | Engineering – addressing project volume surge
120477883 | 170 | Conduct: Supplemental Review (SR) | 2021-06-15 | Engineering – requiring more detailed review
120477883 | 170 | Conduct: Supplemental Review (SR) | 2021-06-22 | Engineering – requiring more detailed review
120477883 | 170 | Conduct: Supplemental Review (SR) | 2021-06-29 | Engineering – addressing project volume surge
120477883 | 170 | Conduct: Supplemental Review (SR) | 2021-06-15 | Engineering – requiring more detailed review
120477883 | 170 | Conduct: Supplemental Review (SR) | 2021-06-22 | Engineering – requiring more detailed review
120477883 | 170 | Conduct: Supplemental Review (SR) | 2021-06-29 | Engineering – addressing project volume surge
120477883 | 170 | Conduct: Supplemental Review (SR) | 2021-06-15 | Engineering – requiring more detailed review
120477883 | 170 | Conduct: Supplemental Review (SR) | 2021-06-22 | Engineering – requiring more detailed review
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-05-28 | Engineering – requiring more detailed review
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-06-07 | Engineering – requiring more detailed review
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-06-14 | Engineering – requiring more detailed review
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-06-21 | Engineering – requiring more detailed review
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-06-23 | Project Management - addressing project volume surge
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-05-28 | Engineering – requiring more detailed review
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-06-07 | Engineering – requiring more detailed review
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-06-14 | Engineering – requiring more detailed review
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-06-21 | Engineering – requiring more detailed review
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-06-23 | Project Management - addressing project volume surge
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-05-28 | Engineering – requiring more detailed review
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-06-07 | Engineering – requiring more detailed review
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-06-14 | Engineering – requiring more detailed review
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-06-21 | Engineering – requiring more detailed review
120477907 | 171 | Conduct: Supplemental Review (SR) | 2021-06-23 | Project Management - addressing project volume surge
120477970 | 172 | Conduct: Initial Review (IR) | 2021-05-07 | Engineering – addressing project volume surge
120477970 | 172 | Conduct: Initial Review (IR) | 2021-05-07 | Engineering – addressing project volume surge
120477970 | 172 | Conduct: Initial Review (IR) | 2021-05-07 | Engineering – addressing project volume surge
120479524 | 173 | Conduct: Initial Review (IR) | 2021-04-13 | Engineering
120479524 | 173 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120479524 | 173 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering
120479524 | 173 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-06-02 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-04-13 | Engineering
120479524 | 173 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120479524 | 173 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering
120479524 | 173 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-06-02 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-04-13 | Engineering
120479524 | 173 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120479524 | 173 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering
120479524 | 173 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-06-02 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – requiring more detailed review
120479524 | 173 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120479525 | 174 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
120479525 | 174 | Conduct: Initial Review (IR) | 2021-04-29 | Engineering
120479525 | 174 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
120479525 | 174 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120479525 | 174 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – requiring more detailed review
120479525 | 174 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – requiring more detailed review
120479525 | 174 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
120479525 | 174 | Conduct: Initial Review (IR) | 2021-04-29 | Engineering
120479525 | 174 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
120479525 | 174 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120479525 | 174 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – requiring more detailed review
120479525 | 174 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – requiring more detailed review
120479525 | 174 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
120479525 | 174 | Conduct: Initial Review (IR) | 2021-04-29 | Engineering
120479525 | 174 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
120479525 | 174 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120479525 | 174 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – requiring more detailed review
120479525 | 174 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – requiring more detailed review
120479812 | 175 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120479812 | 175 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120479812 | 175 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120479812 | 175 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
120479812 | 175 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
120479812 | 175 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120479812 | 175 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120479812 | 175 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
120479812 | 175 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
120480244 | 176 | Conduct: SIS | 2021-07-21 | Engineering – addressing project volume surge
120480244 | 176 | Conduct: SIS | 2021-08-11 | Engineering – addressing project volume surge
120480244 | 176 | Conduct: SIS | 2021-09-01 | Engineering – addressing project volume surge
120480244 | 176 | Conduct: SIS | 2021-08-11 | Engineering – addressing project volume surge
120480244 | 176 | Conduct: SIS | 2021-07-21 | Engineering – addressing project volume surge
120480244 | 176 | Conduct: SIS | 2021-09-01 | Engineering – addressing project volume surge
120480244 | 176 | Conduct: SIS | 2021-07-21 | Engineering – addressing project volume surge
120480244 | 176 | Conduct: SIS | 2021-08-11 | Engineering – addressing project volume surge
120480244 | 176 | Conduct: SIS | 2021-09-01 | Engineering – addressing project volume surge
120484769 | 177 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120484769 | 177 | Conduct: Initial Review (IR) | 2021-04-20 | Engineering
120484769 | 177 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120484769 | 177 | Conduct: Initial Review (IR) | 2021-05-04 | Engineering
120484769 | 177 | Conduct: Initial Review (IR) | 2021-05-18 | Engineering – requiring more detailed review
120491626 | 178 | Conduct: Screens Q and R | 2021-05-14 | Engineering – addressing project volume surge
120491626 | 178 | Conduct: Screens Q and R | 2021-05-24 | Engineering – requiring more detailed review
120491626 | 178 | Conduct: Screens Q and R | 2021-06-18 | Engineering – requiring more detailed review
120491626 | 178 | Conduct: SIS | 2021-09-17 | Engineering – requiring more detailed review
120491626 | 178 | Conduct: Screens Q and R | 2021-05-31 | Project Management – requiring more detailed review
120491626 | 178 | Conduct: Screens Q and R | 2021-06-04 | Project Management – requiring more detailed review
120491626 | 178 | Conduct: Screens Q and R | 2021-05-14 | Engineering – addressing project volume surge
120491626 | 178 | Conduct: Screens Q and R | 2021-05-24 | Engineering – requiring more detailed review
120491626 | 178 | Conduct: Screens Q and R | 2021-06-18 | Engineering – requiring more detailed review
120491626 | 178 | Conduct: SIS | 2021-09-17 | Engineering – requiring more detailed review
120491626 | 178 | Conduct: Screens Q and R | 2021-05-31 | Project Management – requiring more detailed review
120491626 | 178 | Conduct: Screens Q and R | 2021-06-04 | Project Management – requiring more detailed review
120491626 | 178 | Conduct: Screens Q and R | 2021-05-14 | Engineering – addressing project volume surge
120491626 | 178 | Conduct: Screens Q and R | 2021-05-24 | Engineering – requiring more detailed review
120491626 | 178 | Conduct: Screens Q and R | 2021-06-18 | Engineering – requiring more detailed review
120491626 | 178 | Conduct: SIS | 2021-09-17 | Engineering – requiring more detailed review
120491626 | 178 | Conduct: Screens Q and R | 2021-05-31 | Project Management – requiring more detailed review
120491626 | 178 | Conduct: Screens Q and R | 2021-06-04 | Project Management – requiring more detailed review
120493168 | 179 | Conduct: Screens Q and R | 2021-06-10 | Engineering – addressing project volume surge
120493168 | 179 | Conduct: Screens Q and R | 2021-06-10 | Engineering – addressing project volume surge
120493168 | 179 | Conduct: Screens Q and R | 2021-06-10 | Engineering – addressing project volume surge
120493300 | 180 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120493300 | 180 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requesting an extension
120493350 | 181 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120493350 | 181 | Conduct: Initial Review (IR) | 2021-06-14 | Customer – requirement to provide corrected information
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-05-28 | Engineering – requiring more detailed review
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-06-07 | Engineering – requiring more detailed review
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-06-14 | Engineering – requiring more detailed review
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-06-21 | Engineering – requiring more detailed review
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-06-23 | Project Management - addressing project volume surge
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-05-28 | Engineering – requiring more detailed review
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-06-07 | Engineering – requiring more detailed review
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-06-14 | Engineering – requiring more detailed review
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-06-21 | Engineering – requiring more detailed review
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-06-23 | Project Management - addressing project volume surge
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-05-28 | Engineering – requiring more detailed review
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-06-07 | Engineering – requiring more detailed review
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-06-14 | Engineering – requiring more detailed review
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-06-21 | Engineering – requiring more detailed review
120498076 | 182 | Conduct: Supplemental Review (SR) | 2021-06-23 | Project Management - addressing project volume surge
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-05-28 | Engineering – requiring more detailed review
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-06-07 | Engineering – requiring more detailed review
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-06-14 | Engineering – requiring more detailed review
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-06-21 | Engineering – requiring more detailed review
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-06-23 | Project Management - addressing project volume surge
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-05-28 | Engineering – requiring more detailed review
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-06-07 | Engineering – requiring more detailed review
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-06-14 | Engineering – requiring more detailed review
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-06-21 | Engineering – requiring more detailed review
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-06-23 | Project Management - addressing project volume surge
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-05-28 | Engineering – requiring more detailed review
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-06-07 | Engineering – requiring more detailed review
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-06-14 | Engineering – requiring more detailed review
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-06-21 | Engineering – requiring more detailed review
120498201 | 183 | Conduct: Supplemental Review (SR) | 2021-06-23 | Project Management - addressing project volume surge
120498202 | 184 | Conduct: Supplemental Review (SR) | 2021-06-14 | Engineering – requiring more detailed review
120498202 | 184 | Conduct: Supplemental Review (SR) | 2021-06-21 | Engineering – requiring more detailed review
120498202 | 184 | Conduct: Supplemental Review (SR) | 2021-06-14 | Engineering – requiring more detailed review
120498202 | 184 | Conduct: Supplemental Review (SR) | 2021-06-21 | Engineering – requiring more detailed review
120498202 | 184 | Conduct: Supplemental Review (SR) | 2021-06-14 | Engineering – requiring more detailed review
120498202 | 184 | Conduct: Supplemental Review (SR) | 2021-06-21 | Engineering – requiring more detailed review
120498209 | 185 | Conduct: Initial Review (IR) | 2021-05-07 | Engineering – addressing project volume surge
120498209 | 185 | Conduct: Initial Review (IR) | 2021-05-07 | Engineering – addressing project volume surge
120498209 | 185 | Conduct: Initial Review (IR) | 2021-05-07 | Engineering – addressing project volume surge
120498260 | 186 | Conduct: Supplemental Review (SR) | 2021-06-03 | Engineering – requiring more detailed review
120498260 | 186 | Conduct: Supplemental Review (SR) | 2021-06-10 | Engineering – requiring more detailed review
120498260 | 186 | Conduct: Supplemental Review (SR) | 2021-06-17 | Engineering – requiring more detailed review
120498260 | 186 | Conduct: Supplemental Review (SR) | 2021-06-24 | Engineering – requiring more detailed review
120498260 | 186 | Conduct: Supplemental Review (SR) | 2021-06-03 | Engineering – requiring more detailed review
120498260 | 186 | Conduct: Supplemental Review (SR) | 2021-06-10 | Engineering – requiring more detailed review
120498260 | 186 | Conduct: Supplemental Review (SR) | 2021-06-17 | Engineering – requiring more detailed review
120498260 | 186 | Conduct: Supplemental Review (SR) | 2021-06-24 | Engineering – requiring more detailed review
120498260 | 186 | Conduct: Supplemental Review (SR) | 2021-06-03 | Engineering – requiring more detailed review
120498260 | 186 | Conduct: Supplemental Review (SR) | 2021-06-10 | Engineering – requiring more detailed review
120498260 | 186 | Conduct: Supplemental Review (SR) | 2021-06-17 | Engineering – requiring more detailed review
120498260 | 186 | Conduct: Supplemental Review (SR) | 2021-06-24 | Engineering – requiring more detailed review
120498261 | 187 | Conduct: Supplemental Review (SR) | 2021-06-03 | Engineering – requiring more detailed review
120498261 | 187 | Conduct: Supplemental Review (SR) | 2021-06-10 | Engineering – requiring more detailed review
120498261 | 187 | Conduct: Supplemental Review (SR) | 2021-06-17 | Engineering – requiring more detailed review
120498261 | 187 | Conduct: Supplemental Review (SR) | 2021-06-24 | Engineering – requiring more detailed review
120498261 | 187 | Conduct: Supplemental Review (SR) | 2021-06-03 | Engineering – requiring more detailed review
120498261 | 187 | Conduct: Supplemental Review (SR) | 2021-06-10 | Engineering – requiring more detailed review
120498261 | 187 | Conduct: Supplemental Review (SR) | 2021-06-17 | Engineering – requiring more detailed review
120498261 | 187 | Conduct: Supplemental Review (SR) | 2021-06-24 | Engineering – requiring more detailed review
120498261 | 187 | Conduct: Supplemental Review (SR) | 2021-06-03 | Engineering – requiring more detailed review
120498261 | 187 | Conduct: Supplemental Review (SR) | 2021-06-10 | Engineering – requiring more detailed review
120498261 | 187 | Conduct: Supplemental Review (SR) | 2021-06-24 | Engineering – requiring more detailed review
120498261 | 187 | Conduct: Supplemental Review (SR) | 2021-06-17 | Engineering – requiring more detailed review
120500673 | 188 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120500673 | 188 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120500673 | 188 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
120500673 | 188 | Conduct: Initial Review (IR) | 2021-04-25 | EGI
120500673 | 188 | Conduct: Initial Review (IR) | 2021-04-11 | Engineering
120500673 | 188 | Conduct: Initial Review (IR) | 2021-05-03 | Engineering
120500854 | 189 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering
120500854 | 189 | Conduct: Initial Review (IR) | 2021-06-24 | Project Management – requiring more detailed review
120500854 | 189 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering
120500854 | 189 | Conduct: Initial Review (IR) | 2021-06-24 | Project Management – requiring more detailed review
120500854 | 189 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering
120500854 | 189 | Conduct: Initial Review (IR) | 2021-06-24 | Project Management – requiring more detailed review
120503061 | 190 | Conduct: Initial Review (IR) | 2021-04-14 | EGI
120503061 | 190 | Conduct: Initial Review (IR) | 2021-04-20 | Engineering
120503061 | 190 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
120503061 | 190 | Conduct: Initial Review (IR) | 2021-05-17 | Project Management – requiring more detailed review
120503061 | 190 | Conduct: Initial Review (IR) | 2021-05-24 | Project Management – requiring more detailed review
120504102 | 191 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
120504102 | 191 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
120504102 | 191 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
120504102 | 191 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
120504102 | 191 | Conduct: Initial Review (IR) | 2021-05-03 | EGI
120506502 | 192 | Conduct: Initial Review (IR) | 2021-04-12 | Engineering
120506502 | 192 | Conduct: Initial Review (IR) | 2021-04-19 | Engineering
120506502 | 192 | Conduct: Initial Review (IR) | 2021-04-26 | Engineering
120506502 | 192 | Conduct: Initial Review (IR) | 2021-05-03 | Engineering
120506502 | 192 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering – requiring more detailed review
120506502 | 192 | Conduct: Initial Review (IR) | 2021-04-12 | Engineering
120506502 | 192 | Conduct: Initial Review (IR) | 2021-04-19 | Engineering
120506502 | 192 | Conduct: Initial Review (IR) | 2021-04-26 | Engineering
120506502 | 192 | Conduct: Initial Review (IR) | 2021-05-03 | Engineering
120506502 | 192 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering – requiring more detailed review
120506502 | 192 | Conduct: Initial Review (IR) | 2021-04-12 | Engineering
120506502 | 192 | Conduct: Initial Review (IR) | 2021-04-19 | Engineering
120506502 | 192 | Conduct: Initial Review (IR) | 2021-04-26 | Engineering
120506502 | 192 | Conduct: Initial Review (IR) | 2021-05-03 | Engineering
120506502 | 192 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering – requiring more detailed review
120507331 | 193 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120507331 | 193 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120507331 | 193 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
120507331 | 193 | Conduct: Initial Review (IR) | 2021-05-11 | Customer – requesting an extension
120507331 | 193 | Conduct: Initial Review (IR) | 2021-06-09 | Project Management – requiring more detailed review
120508677 | 194 | Conduct: Screens Q and R | 2021-05-11 | Engineering
120508677 | 194 | Conduct: Screens Q and R | 2021-05-25 | Engineering – requiring more detailed review
120508677 | 194 | Conduct: Screens Q and R | 2021-06-08 | Engineering – requiring more detailed review
120508677 | 194 | Conduct: Screens Q and R | 2021-05-11 | Engineering
120508677 | 194 | Conduct: Screens Q and R | 2021-05-25 | Engineering – requiring more detailed review
120508677 | 194 | Conduct: Screens Q and R | 2021-06-08 | Engineering – requiring more detailed review
120508677 | 194 | Conduct: Screens Q and R | 2021-05-11 | Engineering
120508677 | 194 | Conduct: Screens Q and R | 2021-05-25 | Engineering – requiring more detailed review
120508677 | 194 | Conduct: Screens Q and R | 2021-06-08 | Engineering – requiring more detailed review
120508906 | 195 | Conduct: Initial Review (IR) | 2021-05-03 | EGI
120508906 | 195 | Conduct: Initial Review (IR) | 2021-05-17 | Engineering – requiring more detailed review
120508906 | 195 | Conduct: Initial Review (IR) | 2021-05-31 | Engineering – requiring more detailed review
120508906 | 195 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
120508906 | 195 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120508906 | 195 | Conduct: Initial Review (IR) | 2021-05-03 | EGI
120508906 | 195 | Conduct: Initial Review (IR) | 2021-05-17 | Engineering – requiring more detailed review
120508906 | 195 | Conduct: Initial Review (IR) | 2021-05-31 | Engineering – requiring more detailed review
120508906 | 195 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
120508906 | 195 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120508906 | 195 | Conduct: Initial Review (IR) | 2021-05-03 | EGI
120508906 | 195 | Conduct: Initial Review (IR) | 2021-05-17 | Engineering – requiring more detailed review
120508906 | 195 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120508906 | 195 | Conduct: Initial Review (IR) | 2021-05-31 | Engineering – requiring more detailed review
120508906 | 195 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
120508960 | 196 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
120508960 | 196 | Conduct: Initial Review (IR) | 2021-07-21 | Project Management - addressing project volume surge
120509484 | 197 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120509484 | 197 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120509484 | 197 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120509484 | 197 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120509484 | 197 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
120509484 | 197 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120509484 | 197 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
120509484 | 197 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120510440 | 198 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120510440 | 198 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
120510440 | 198 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
120510440 | 198 | Conduct: Initial Review (IR) | 2021-09-02 | Cus – requirement to provide a response to deficiency notice
120510440 | 198 | Conduct: Initial Review (IR) | 2021-10-02 | Cus – requirement to provide a response to deficiency notice
120510440 | 198 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
120510440 | 198 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120510440 | 198 | Conduct: Initial Review (IR) | 2021-05-07 | Customer
120510440 | 198 | Conduct: Initial Review (IR) | 2021-06-19 | Customer – requirement to provide corrected information
120511830 | 199 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
120511830 | 199 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
120511830 | 199 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
120511830 | 199 | Conduct: Initial Review (IR) | 2021-05-06 | Engineering – requiring more detailed review
120512428 | 200 | Conduct: Initial Review (IR) | 2021-06-24 | Project Management – requiring more detailed review
120512428 | 200 | Conduct: Initial Review (IR) | 2021-06-24 | Project Management – requiring more detailed review
120512428 | 200 | Conduct: Initial Review (IR) | 2021-06-24 | Project Management – requiring more detailed review
120522795 | 201 | Conduct: Initial Review (IR) | 2021-04-28 | Engineering
120522795 | 201 | Conduct: Initial Review (IR) | 2021-05-05 | Engineering
120522795 | 201 | Conduct: Initial Review (IR) | 2021-05-12 | Engineering – addressing a human error
120525065 | 202 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
120525065 | 202 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
120525065 | 202 | Conduct: Initial Review (IR) | 2021-05-24 | Engineering – requiring more detailed review
120525065 | 202 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
120525065 | 202 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
120525065 | 202 | Conduct: Initial Review (IR) | 2021-05-24 | Engineering – requiring more detailed review
120525065 | 202 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
120525065 | 202 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
120525065 | 202 | Conduct: Initial Review (IR) | 2021-05-24 | Engineering – requiring more detailed review
120526554 | 203 | Conduct: Screens Q and R | 2021-05-21 | Engineering – requiring more detailed review
120526554 | 203 | Conduct: Screens Q and R | 2021-05-28 | Engineering – requiring more detailed review
120526554 | 203 | Conduct: Screens Q and R | 2021-06-07 | Engineering – requiring more detailed review
120526554 | 203 | Conduct: SIS | 2021-12-03 | Engineering – addressing project volume surge
120526554 | 203 | Conduct: SIS | 2021-12-14 | Engineering – addressing project volume surge
120526554 | 203 | Conduct: SIS | 2021-12-21 | Engineering – addressing project volume surge
120526554 | 203 | Conduct: SIS | 2022-01-04 | Engineering – addressing project volume surge
120526554 | 203 | Conduct: Screens Q and R | 2021-05-21 | Engineering – requiring more detailed review
120526554 | 203 | Conduct: Screens Q and R | 2021-05-28 | Engineering – requiring more detailed review
120526554 | 203 | Conduct: Screens Q and R | 2021-06-07 | Engineering – requiring more detailed review
120526554 | 203 | Conduct: SIS | 2021-12-03 | Engineering – addressing project volume surge
120526554 | 203 | Conduct: SIS | 2021-12-14 | Engineering – addressing project volume surge
120526554 | 203 | Conduct: SIS | 2021-12-21 | Engineering – addressing project volume surge
120526554 | 203 | Conduct: SIS | 2022-01-04 | Engineering – addressing project volume surge
120526554 | 203 | Conduct: Screens Q and R | 2021-05-21 | Engineering – requiring more detailed review
120526554 | 203 | Conduct: Screens Q and R | 2021-05-28 | Engineering – requiring more detailed review
120526554 | 203 | Conduct: Screens Q and R | 2021-06-07 | Engineering – requiring more detailed review
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-05-21 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-01 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-08 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-30 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-15 | Engineering – requiring more detailed review
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-22 | Engineering – requiring more detailed review
120527051 | 204 | Conduct: SIS | 2021-10-22 | Engineering – requiring more detailed review
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-05-21 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-01 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-08 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-30 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: SIS | 2021-11-05 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: SIS | 2021-11-12 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: SIS | 2021-11-19 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-15 | Engineering – requiring more detailed review
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-22 | Engineering – requiring more detailed review
120527051 | 204 | Conduct: SIS | 2021-10-22 | Engineering – requiring more detailed review
120527051 | 204 | Conduct: SIS | 2021-10-29 | Engineering – requiring more detailed review
120527051 | 204 | Conduct: SIS | 2021-11-05 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: SIS | 2021-11-12 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: SIS | 2021-11-19 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-05-21 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-01 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-08 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-30 | Engineering – addressing project volume surge
120527051 | 204 | Conduct: SIS | 2021-10-22 | Engineering – requiring more detailed review
120527051 | 204 | Conduct: SIS | 2021-10-29 | Engineering – requiring more detailed review
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-15 | Engineering – requiring more detailed review
120527051 | 204 | Conduct: Supplemental Review (SR) | 2021-06-22 | Engineering – requiring more detailed review
120527388 | 205 | Conduct: Initial Review (IR) | 2021-05-07 | Customer – requirement to provide corrected information
120527388 | 205 | Conduct: Initial Review (IR) | 2021-05-14 | Customer – requirement to provide corrected information
120528893 | 206 | Conduct: Initial Review (IR) | 2021-05-07 | Engineering – addressing project volume surge
120528893 | 206 | Conduct: Initial Review (IR) | 2021-05-07 | Engineering – addressing project volume surge
120528893 | 206 | Conduct: Initial Review (IR) | 2021-05-07 | Engineering – addressing project volume surge
120529179 | 207 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120529179 | 207 | Conduct: Initial Review (IR) | 2021-04-13 | Engineering
120529179 | 207 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120529179 | 207 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering – requiring more detailed review
120529179 | 207 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120529179 | 207 | Conduct: Initial Review (IR) | 2021-04-13 | Engineering
120529179 | 207 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120529179 | 207 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering – requiring more detailed review
120529179 | 207 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120529179 | 207 | Conduct: Initial Review (IR) | 2021-04-13 | Engineering
120529179 | 207 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120529179 | 207 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering – requiring more detailed review
120529412 | 208 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-07-19 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-08-16 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-08-23 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-08-30 | Cus – requirement to provide a response to deficiency notice
120529412 | 208 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
120529412 | 208 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120529412 | 208 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
120530834 | 209 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120530834 | 209 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120530834 | 209 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120530834 | 209 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120530834 | 209 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120530834 | 209 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120530834 | 209 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120530834 | 209 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
120532383 | 210 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120534380 | 211 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120534380 | 211 | Conduct: Initial Review (IR) | 2021-04-09 | Customer
120534380 | 211 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
120534380 | 211 | Conduct: Initial Review (IR) | 2021-04-23 | Engineering
120534380 | 211 | Conduct: Initial Review (IR) | 2021-04-30 | Engineering
120534380 | 211 | Conduct: Initial Review (IR) | 2021-05-21 | Engineering – requiring more detailed review
120534380 | 211 | Conduct: Initial Review (IR) | 2021-05-28 | Engineering – requiring more detailed review
120534380 | 211 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
120534380 | 211 | Conduct: Initial Review (IR) | 2021-05-14 | Project Management – addressing a human error
120534380 | 211 | Conduct: Initial Review (IR) | 2021-06-07 | Project Management - addressing project volume surge
120534380 | 211 | Conduct: Initial Review (IR) | 2021-05-07 | Project Management – requiring more detailed review
120537256 | 212 | Conduct: Screens Q and R | 2021-06-16 | Engineering – addressing project volume surge
120537256 | 212 | Conduct: Screens Q and R | 2021-06-16 | Engineering – addressing project volume surge
120537256 | 212 | Conduct: Screens Q and R | 2021-06-16 | Engineering – addressing project volume surge
120537502 | 213 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
120537502 | 213 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120537502 | 213 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120537502 | 213 | Conduct: Initial Review (IR) | 2021-05-17 | Engineering – requiring more detailed review
120540269 | 214 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120540269 | 214 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120540269 | 214 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120540269 | 214 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120540269 | 214 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120540269 | 214 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
120540269 | 214 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120540269 | 214 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
120540680 | 215 | Conduct: Initial Review (IR) | 2021-06-28 | Project Management - addressing project volume surge
120540680 | 215 | Conduct: Initial Review (IR) | 2021-06-11 | Project Management – requiring more detailed review
120540680 | 215 | Conduct: Initial Review (IR) | 2021-06-25 | Project Management – requiring more detailed review
120540680 | 215 | Conduct: Initial Review (IR) | 2021-06-28 | Project Management - addressing project volume surge
120540680 | 215 | Conduct: Initial Review (IR) | 2021-06-11 | Project Management – requiring more detailed review
120540680 | 215 | Conduct: Initial Review (IR) | 2021-06-25 | Project Management – requiring more detailed review
120540680 | 215 | Conduct: Initial Review (IR) | 2021-06-28 | Project Management - addressing project volume surge
120540680 | 215 | Conduct: Initial Review (IR) | 2021-06-11 | Project Management – requiring more detailed review
120540680 | 215 | Conduct: Initial Review (IR) | 2021-06-25 | Project Management – requiring more detailed review
120552303 | 216 | Conduct: Supplemental Review (SR) | 2021-05-20 | Engineering – addressing project volume surge
120552303 | 216 | Conduct: Supplemental Review (SR) | 2021-05-20 | Engineering – addressing project volume surge
120552303 | 216 | Conduct: Supplemental Review (SR) | 2021-05-20 | Engineering – addressing project volume surge
120552957 | 217 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120552957 | 217 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120552957 | 217 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120555916 | 218 | Conduct: Supplemental Review (SR) | 2021-05-05 | Engineering
120555916 | 218 | Conduct: Screens Q and R | 2021-06-25 | Engineering – requiring more detailed review
120555916 | 218 | Conduct: Screens Q and R | 2021-07-19 | Engineering – requiring more detailed review
120555916 | 218 | Conduct: Supplemental Review (SR) | 2021-05-05 | Engineering
120555916 | 218 | Conduct: Screens Q and R | 2021-06-25 | Engineering – requiring more detailed review
120555916 | 218 | Conduct: Screens Q and R | 2021-07-19 | Engineering – requiring more detailed review
120555916 | 218 | Conduct: Supplemental Review (SR) | 2021-05-05 | Engineering
120555916 | 218 | Conduct: Screens Q and R | 2021-06-25 | Engineering – requiring more detailed review
120555916 | 218 | Conduct: Screens Q and R | 2021-07-19 | Engineering – requiring more detailed review
120563712 | 219 | Conduct: Initial Review (IR) | 2021-05-07 | Cus – requirement to provide a response to deficiency notice
120563712 | 219 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120563712 | 219 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120563712 | 219 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120563712 | 219 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120563712 | 219 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120563712 | 219 | Conduct: Initial Review (IR) | 2021-06-21 | Cus – requirement to provide a response to deficiency notice
120563712 | 219 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
120563712 | 219 | Conduct: Initial Review (IR) | 2021-07-06 | Cus – requirement to provide a response to deficiency notice
120563712 | 219 | Conduct: Initial Review (IR) | 2021-04-09 | Customer
120563712 | 219 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
120563712 | 219 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120563712 | 219 | Conduct: Initial Review (IR) | 2021-04-30 | Customer
120564923 | 220 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
120564923 | 220 | Conduct: Initial Review (IR) | 2021-04-28 | Engineering
120564923 | 220 | Conduct: Initial Review (IR) | 2021-05-05 | Engineering
120564923 | 220 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120564923 | 220 | Conduct: Initial Review (IR) | 2021-05-19 | Project Management – addressing a human error
120564923 | 220 | Conduct: Initial Review (IR) | 2021-06-03 | Project Management – addressing a human error
120564923 | 220 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
120564923 | 220 | Conduct: Initial Review (IR) | 2021-04-28 | Engineering
120564923 | 220 | Conduct: Initial Review (IR) | 2021-05-05 | Engineering
120564923 | 220 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120564923 | 220 | Conduct: Initial Review (IR) | 2021-05-19 | Project Management – addressing a human error
120564923 | 220 | Conduct: Initial Review (IR) | 2021-06-03 | Project Management – addressing a human error
120564923 | 220 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
120564923 | 220 | Conduct: Initial Review (IR) | 2021-04-28 | Engineering
120564923 | 220 | Conduct: Initial Review (IR) | 2021-05-05 | Engineering
120564923 | 220 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120564923 | 220 | Conduct: Initial Review (IR) | 2021-05-19 | Project Management – addressing a human error
120564923 | 220 | Conduct: Initial Review (IR) | 2021-06-03 | Project Management – addressing a human error
120565433 | 221 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120565433 | 221 | Tender Draft IA | 2021-09-03 | Customer – requirement to provide corrected information
120565433 | 221 | Tender Draft IA | 2021-09-17 | Customer – requirement to provide corrected information
120565433 | 221 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – addressing project volume surge
120565433 | 221 | Conduct: Initial Review (IR) | 2021-06-02 | Engineering – requiring more detailed review
120565433 | 221 | Tender Draft IA | 2021-07-23 | Project Management – requiring more detailed review
120565433 | 221 | Tender Draft IA | 2021-07-30 | Project Management – requiring more detailed review
120565433 | 221 | Tender Draft IA | 2021-08-13 | Project Management – requiring more detailed review
120565433 | 221 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120565433 | 221 | Tender Draft IA | 2021-09-03 | Customer – requirement to provide corrected information
120565433 | 221 | Tender Draft IA | 2021-09-17 | Customer – requirement to provide corrected information
120565433 | 221 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – addressing project volume surge
120565433 | 221 | Conduct: Initial Review (IR) | 2021-06-02 | Engineering – requiring more detailed review
120565433 | 221 | Tender Draft IA | 2021-07-30 | Project Management – requiring more detailed review
120565433 | 221 | Tender Draft IA | 2021-07-23 | Project Management – requiring more detailed review
120565433 | 221 | Tender Draft IA | 2021-08-13 | Project Management – requiring more detailed review
120565433 | 221 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120565433 | 221 | Tender Draft IA | 2021-09-03 | Customer – requirement to provide corrected information
120565433 | 221 | Tender Draft IA | 2021-09-17 | Customer – requirement to provide corrected information
120565433 | 221 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – addressing project volume surge
120565433 | 221 | Conduct: Initial Review (IR) | 2021-06-02 | Engineering – requiring more detailed review
120565433 | 221 | Tender Draft IA | 2021-07-23 | Project Management – requiring more detailed review
120565433 | 221 | Tender Draft IA | 2021-07-30 | Project Management – requiring more detailed review
120565433 | 221 | Tender Draft IA | 2021-08-13 | Project Management – requiring more detailed review
120567150 | 222 | Conduct: Supplemental Review (SR) | 2021-06-28 | Engineering – addressing project volume surge
120567150 | 222 | Conduct: Supplemental Review (SR) | 2021-07-02 | Project Management - addressing project volume surge
120567150 | 222 | Conduct: Supplemental Review (SR) | 2021-06-28 | Engineering – addressing project volume surge
120567150 | 222 | Conduct: Supplemental Review (SR) | 2021-07-02 | Project Management - addressing project volume surge
120567150 | 222 | Conduct: Supplemental Review (SR) | 2021-06-28 | Engineering – addressing project volume surge
120567150 | 222 | Conduct: Supplemental Review (SR) | 2021-07-02 | Project Management - addressing project volume surge
120568229 | 223 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – addressing project volume surge
120568229 | 223 | Conduct: Supplemental Review (SR) | 2021-07-07 | Engineering – addressing project volume surge
120568229 | 223 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – addressing project volume surge
120568229 | 223 | Conduct: Supplemental Review (SR) | 2021-07-07 | Engineering – addressing project volume surge
120568229 | 223 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – addressing project volume surge
120568229 | 223 | Conduct: Supplemental Review (SR) | 2021-07-07 | Engineering – addressing project volume surge
120571946 | 224 | Conduct: Initial Review (IR) | 2021-06-21 | Cus – requirement to provide a response to deficiency notice
120571946 | 224 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
120571946 | 224 | Conduct: Initial Review (IR) | 2021-07-06 | Cus – requirement to provide a response to deficiency notice
120571946 | 224 | Conduct: Initial Review (IR) | 2021-07-13 | Cus – requirement to provide a response to deficiency notice
120571946 | 224 | Conduct: Initial Review (IR) | 2021-07-20 | Cus – requirement to provide a response to deficiency notice
120574009 | 225 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120574009 | 225 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120574009 | 225 | Conduct: Initial Review (IR) | 2021-06-23 | Cus – requirement to provide a response to deficiency notice
120574009 | 225 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
120574009 | 225 | Conduct: Initial Review (IR) | 2021-07-21 | Customer – requirement to provide corrected information
120574009 | 225 | Conduct: Initial Review (IR) | 2021-08-04 | Customer – requirement to provide corrected information
120574009 | 225 | Conduct: Initial Review (IR) | 2021-09-04 | Customer – requirement to provide corrected information
120574009 | 225 | Conduct: Initial Review (IR) | 2021-10-04 | Customer – requirement to provide corrected information
120574009 | 225 | Conduct: Initial Review (IR) | 2021-10-18 | Customer – requirement to provide corrected information
120574009 | 225 | Conduct: Initial Review (IR) | 2021-11-01 | Engineering – addressing project volume surge
120574009 | 225 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120574009 | 225 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120574009 | 225 | Conduct: Initial Review (IR) | 2021-06-23 | Cus – requirement to provide a response to deficiency notice
120574009 | 225 | Conduct: Initial Review (IR) | 2021-08-04 | Customer – requirement to provide corrected information
120574009 | 225 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
120574009 | 225 | Conduct: Initial Review (IR) | 2021-07-21 | Customer – requirement to provide corrected information
120574009 | 225 | Conduct: Initial Review (IR) | 2021-09-04 | Customer – requirement to provide corrected information
120574009 | 225 | Conduct: Initial Review (IR) | 2021-10-04 | Customer – requirement to provide corrected information
120574009 | 225 | Conduct: Initial Review (IR) | 2021-10-18 | Customer – requirement to provide corrected information
120574009 | 225 | Conduct: Initial Review (IR) | 2021-11-01 | Engineering – addressing project volume surge
120574009 | 225 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120574009 | 225 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120574009 | 225 | Conduct: Initial Review (IR) | 2021-06-23 | Cus – requirement to provide a response to deficiency notice
120574009 | 225 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
120574009 | 225 | Conduct: Initial Review (IR) | 2021-07-21 | Customer – requirement to provide corrected information
120574009 | 225 | Conduct: Initial Review (IR) | 2021-08-04 | Customer – requirement to provide corrected information
120574009 | 225 | Conduct: Initial Review (IR) | 2021-09-04 | Customer – requirement to provide corrected information
120574009 | 225 | Conduct: Initial Review (IR) | 2021-10-04 | Customer – requirement to provide corrected information
120574009 | 225 | Conduct: Initial Review (IR) | 2021-10-18 | Customer – requirement to provide corrected information
120574009 | 225 | Conduct: Initial Review (IR) | 2021-11-01 | Engineering – addressing project volume surge
120574360 | 226 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120574894 | 227 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120574894 | 227 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120574894 | 227 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120574894 | 227 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
120574894 | 227 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
120578039 | 228 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120578514 | 229 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120578514 | 229 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120578514 | 229 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120578514 | 229 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120578514 | 229 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120578514 | 229 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120578514 | 229 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
120578514 | 229 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
120578514 | 229 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
120578514 | 229 | Conduct: Initial Review (IR) | 2021-05-03 | Engineering
120580670 | 230 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120580670 | 230 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requesting an extension
120580670 | 230 | Conduct: Initial Review (IR) | 2021-05-17 | Customer – requirement to provide corrected information
120580670 | 230 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
120581661 | 231 | Conduct: Initial Review (IR) | 2201-06-28 | Engineering – requiring more detailed review
120581661 | 231 | Conduct: Initial Review (IR) | 2201-06-28 | Engineering – requiring more detailed review
120581661 | 231 | Conduct: Initial Review (IR) | 2201-06-28 | Engineering – requiring more detailed review
120581767 | 232 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – addressing a human error
120581877 | 233 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – addressing a human error
120581877 | 233 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – addressing a human error
120581877 | 233 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – addressing a human error
120581960 | 234 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – addressing a human error
120581960 | 234 | Conduct: Initial Review (IR) | 2021-07-14 | Engineering – requiring more detailed review
120581960 | 234 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
120582557 | 235 | Conduct: Initial Review (IR) | 2021-05-11 | Customer
120582557 | 235 | Conduct: Initial Review (IR) | 2021-05-25 | Project Management – requiring more detailed review
120582557 | 235 | Conduct: Initial Review (IR) | 2021-06-01 | Project Management – requiring more detailed review
120582557 | 235 | Conduct: Initial Review (IR) | 2021-05-11 | Customer
120582557 | 235 | Conduct: Initial Review (IR) | 2021-05-25 | Project Management – requiring more detailed review
120582557 | 235 | Conduct: Initial Review (IR) | 2021-06-01 | Project Management – requiring more detailed review
120582557 | 235 | Conduct: Initial Review (IR) | 2021-05-11 | Customer
120582557 | 235 | Conduct: Initial Review (IR) | 2021-05-25 | Project Management – requiring more detailed review
120582557 | 235 | Conduct: Initial Review (IR) | 2021-06-01 | Project Management – requiring more detailed review
120582748 | 236 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – requiring more detailed review
120582748 | 236 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120582748 | 236 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – requiring more detailed review
120582748 | 236 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120582748 | 236 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – requiring more detailed review
120582748 | 236 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120582785 | 237 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – requiring more detailed review
120582785 | 237 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120582785 | 237 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
120582785 | 237 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
120582785 | 237 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
120582785 | 237 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – requiring more detailed review
120582785 | 237 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120582785 | 237 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
120582785 | 237 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – requiring more detailed review
120582785 | 237 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120582785 | 237 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
120582785 | 237 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
120582789 | 238 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – requiring more detailed review
120582789 | 238 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120582789 | 238 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
120582789 | 238 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
120582789 | 238 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
120582789 | 238 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – requiring more detailed review
120582789 | 238 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120582789 | 238 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
120582789 | 238 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – requiring more detailed review
120582789 | 238 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120582789 | 238 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
120582789 | 238 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
120582822 | 239 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120582822 | 239 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120582822 | 239 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120582822 | 239 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
120582822 | 239 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120582840 | 240 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
120582840 | 240 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120582840 | 240 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120582840 | 240 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120582840 | 240 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requirement to provide corrected information
120582840 | 240 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – addressing project volume surge
120582841 | 241 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – requiring more detailed review
120582841 | 241 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120582841 | 241 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – requiring more detailed review
120582841 | 241 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120582841 | 241 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – requiring more detailed review
120582841 | 241 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120582870 | 242 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120582870 | 242 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120582870 | 242 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
120582870 | 242 | Conduct: Initial Review (IR) | 2021-08-30 | Cus – requirement to provide a response to deficiency notice
120582870 | 242 | Conduct: Initial Review (IR) | 2021-09-21 | Cus – requirement to provide a response to deficiency notice
120582870 | 242 | Conduct: Initial Review (IR) | 2021-06-25 | Customer – requirement to provide corrected information
120582870 | 242 | Conduct: Initial Review (IR) | 2021-07-19 | Customer – requirement to provide corrected information
120582870 | 242 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – requiring more detailed review
120582870 | 242 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120582870 | 242 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120582870 | 242 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
120582870 | 242 | Conduct: Initial Review (IR) | 2021-08-30 | Cus – requirement to provide a response to deficiency notice
120582870 | 242 | Conduct: Initial Review (IR) | 2021-09-21 | Cus – requirement to provide a response to deficiency notice
120582870 | 242 | Conduct: Initial Review (IR) | 2021-06-25 | Customer – requirement to provide corrected information
120582870 | 242 | Conduct: Initial Review (IR) | 2021-07-19 | Customer – requirement to provide corrected information
120582870 | 242 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – requiring more detailed review
120582870 | 242 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120582870 | 242 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120582870 | 242 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
120582870 | 242 | Conduct: Initial Review (IR) | 2021-08-30 | Cus – requirement to provide a response to deficiency notice
120582870 | 242 | Conduct: Initial Review (IR) | 2021-09-21 | Cus – requirement to provide a response to deficiency notice
120582870 | 242 | Conduct: Initial Review (IR) | 2021-06-25 | Customer – requirement to provide corrected information
120582870 | 242 | Conduct: Initial Review (IR) | 2021-07-19 | Customer – requirement to provide corrected information
120582870 | 242 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – requiring more detailed review
120583050 | 243 | Conduct: Initial Review (IR) | 2021-05-07 | Cus – requirement to provide a response to deficiency notice
120583050 | 243 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120583050 | 243 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120583050 | 243 | Conduct: Initial Review (IR) | 2021-04-30 | Customer
120583050 | 243 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
120583050 | 243 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120583050 | 243 | Conduct: Initial Review (IR) | 2021-06-14 | Customer – requirement to provide corrected information
120583050 | 243 | Conduct: Initial Review (IR) | 2021-04-09 | Engineering
120583050 | 243 | Conduct: Initial Review (IR) | 2021-04-16 | Engineering
120583050 | 243 | Conduct: Initial Review (IR) | 2021-05-28 | Project Management - addressing project volume surge
120586983 | 244 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – requiring more detailed review
120586983 | 244 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – requiring more detailed review
120586983 | 244 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – requiring more detailed review
120587079 | 245 | Conduct: Supplemental Review (SR) | 2021-04-23 | Engineering
120587079 | 245 | Conduct: Supplemental Review (SR) | 2021-05-03 | Engineering
120587079 | 245 | Conduct: Supplemental Review (SR) | 2021-05-10 | Engineering – addressing a human error
120587079 | 245 | Conduct: Supplemental Review (SR) | 2021-04-23 | Engineering
120587079 | 245 | Conduct: Supplemental Review (SR) | 2021-05-03 | Engineering
120587079 | 245 | Conduct: Supplemental Review (SR) | 2021-05-10 | Engineering – addressing a human error
120587079 | 245 | Conduct: SIS | 2021-11-22 | Project Management – requiring more detailed review
120587079 | 245 | Conduct: Supplemental Review (SR) | 2021-04-23 | Engineering
120587079 | 245 | Conduct: Supplemental Review (SR) | 2021-05-03 | Engineering
120587079 | 245 | Conduct: Supplemental Review (SR) | 2021-05-10 | Engineering – addressing a human error
120587079 | 245 | Conduct: SIS | 2021-11-22 | Project Management – requiring more detailed review
120587464 | 246 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120587464 | 246 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requirement to provide corrected information
120587464 | 246 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120587464 | 246 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requirement to provide corrected information
120587464 | 246 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120587464 | 246 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requirement to provide corrected information
120590767 | 247 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-07-19 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-08-16 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-08-23 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-08-30 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-09-07 | Cus – requirement to provide a response to deficiency notice
120590767 | 247 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
120590767 | 247 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
120590767 | 247 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
120590820 | 248 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120590820 | 248 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120590820 | 248 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120590820 | 248 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120590820 | 248 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120590820 | 248 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120590820 | 248 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
120590820 | 248 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
120590820 | 248 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
120597306 | 249 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120597306 | 249 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120597306 | 249 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120597306 | 249 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120597306 | 249 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120597306 | 249 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120598627 | 250 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
120598627 | 250 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
120598627 | 250 | Conduct: Initial Review (IR) | 2021-07-16 | Customer – requirement to provide corrected information
120598627 | 250 | Conduct: Initial Review (IR) | 2021-07-01 | Engineering – addressing project volume surge
120598627 | 250 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – addressing project volume surge
120598627 | 250 | Conduct: Initial Review (IR) | 2021-08-09 | Engineering – addressing project volume surge
120598627 | 250 | Conduct: Initial Review (IR) | 2021-08-16 | Engineering – addressing project volume surge
120598627 | 250 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120598627 | 250 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
120598627 | 250 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
120598627 | 250 | Conduct: Initial Review (IR) | 2021-07-16 | Customer – requirement to provide corrected information
120598627 | 250 | Conduct: Initial Review (IR) | 2021-07-01 | Engineering – addressing project volume surge
120598627 | 250 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – addressing project volume surge
120598627 | 250 | Conduct: Initial Review (IR) | 2021-08-09 | Engineering – addressing project volume surge
120598627 | 250 | Conduct: Initial Review (IR) | 2021-08-16 | Engineering – addressing project volume surge
120598627 | 250 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120598627 | 250 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
120598627 | 250 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
120598627 | 250 | Conduct: Initial Review (IR) | 2021-07-16 | Customer – requirement to provide corrected information
120598627 | 250 | Conduct: Initial Review (IR) | 2021-07-01 | Engineering – addressing project volume surge
120598627 | 250 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – addressing project volume surge
120598627 | 250 | Conduct: Initial Review (IR) | 2021-08-09 | Engineering – addressing project volume surge
120598627 | 250 | Conduct: Initial Review (IR) | 2021-08-16 | Engineering – addressing project volume surge
120598627 | 250 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120599578 | 251 | Conduct: Initial Review (IR) | 2021-05-14 | Customer – requirement to provide corrected information
120599578 | 251 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
120601908 | 252 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
120601908 | 252 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
120601908 | 252 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – addressing project volume surge
120603645 | 253 | Conduct: Supplemental Review (SR) | 2021-08-03 | Engineering – addressing project volume surge
120603645 | 253 | Conduct: Supplemental Review (SR) | 2021-08-17 | Engineering – addressing project volume surge
120603645 | 253 | Conduct: Initial Review (IR) | 2021-06-28 | Engineering – requiring more detailed review
120603645 | 253 | Conduct: Supplemental Review (SR) | 2021-08-03 | Engineering – addressing project volume surge
120603645 | 253 | Conduct: Supplemental Review (SR) | 2021-08-17 | Engineering – addressing project volume surge
120603645 | 253 | Conduct: Initial Review (IR) | 2021-06-28 | Engineering – requiring more detailed review
120603645 | 253 | Conduct: Supplemental Review (SR) | 2021-08-03 | Engineering – addressing project volume surge
120603645 | 253 | Conduct: Supplemental Review (SR) | 2021-08-17 | Engineering – addressing project volume surge
120603645 | 253 | Conduct: Initial Review (IR) | 2021-06-28 | Engineering – requiring more detailed review
120604327 | 254 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – requiring more detailed review
120604327 | 254 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – requiring more detailed review
120604327 | 254 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – requiring more detailed review
120605651 | 255 | Conduct: Initial Review (IR) | 2021-05-12 | Cus – requirement to provide a response to deficiency notice
120606821 | 256 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
120606821 | 256 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
120606821 | 256 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
120606821 | 256 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
120606821 | 256 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
120608031 | 257 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – addressing project volume surge
120608031 | 257 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – addressing project volume surge
120608031 | 257 | Conduct: Initial Review (IR) | 2021-06-29 | Engineering – addressing project volume surge
120609943 | 258 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120609943 | 258 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120609943 | 258 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120609943 | 258 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120609943 | 258 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120609943 | 258 | Conduct: Initial Review (IR) | 2021-04-11 | Customer
120609943 | 258 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120609943 | 258 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
120612553 | 259 | Conduct: Supplemental Review (SR) | 2021-06-09 | Engineering – addressing project volume surge
120612553 | 259 | Conduct: Supplemental Review (SR) | 2021-06-23 | Engineering – addressing project volume surge
120612553 | 259 | Conduct: Supplemental Review (SR) | 2021-07-07 | Engineering – addressing project volume surge
120612553 | 259 | Conduct: Supplemental Review (SR) | 2021-06-09 | Engineering – addressing project volume surge
120612553 | 259 | Conduct: Supplemental Review (SR) | 2021-06-23 | Engineering – addressing project volume surge
120612553 | 259 | Conduct: Supplemental Review (SR) | 2021-07-07 | Engineering – addressing project volume surge
120612553 | 259 | Conduct: Supplemental Review (SR) | 2021-06-09 | Engineering – addressing project volume surge
120612553 | 259 | Conduct: Supplemental Review (SR) | 2021-06-23 | Engineering – addressing project volume surge
120612553 | 259 | Conduct: Supplemental Review (SR) | 2021-07-07 | Engineering – addressing project volume surge
120613132 | 260 | Conduct: Initial Review (IR) | 2021-06-21 | Cus – requirement to provide a response to deficiency notice
120613132 | 260 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
120613132 | 260 | Conduct: Initial Review (IR) | 2021-06-14 | Customer – requirement to provide corrected information
120617582 | 261 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
120617582 | 261 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120617582 | 261 | Conduct: Initial Review (IR) | 2021-05-19 | Customer – requirement to provide corrected information
120617582 | 261 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
120617582 | 261 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120617582 | 261 | Conduct: Initial Review (IR) | 2021-05-19 | Customer – requirement to provide corrected information
120617582 | 261 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
120617582 | 261 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120617582 | 261 | Conduct: Initial Review (IR) | 2021-05-19 | Customer – requirement to provide corrected information
120617612 | 262 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
120618014 | 263 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-06-18 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-07-19 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-07-26 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-08-02 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-08-16 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-08-30 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-09-07 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-09-14 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-07-02 | Project Management – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-08-02 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-06-18 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-07-19 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-07-26 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-08-16 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-08-30 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-09-07 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-09-14 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-07-02 | Project Management – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-06-18 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-07-19 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-07-26 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-08-02 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-08-16 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-08-30 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-09-07 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-09-14 | Engineering – requiring more detailed review
120618014 | 263 | Conduct: Initial Review (IR) | 2021-07-02 | Project Management – requiring more detailed review
120627845 | 264 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120627845 | 264 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120627845 | 264 | Conduct: Initial Review (IR) | 2021-06-21 | Cus – requirement to provide a response to deficiency notice
120627845 | 264 | Conduct: Initial Review (IR) | 2021-05-28 | Customer – requirement to provide corrected information
120629311 | 265 | Conduct: Initial Review (IR) | 2021-05-14 | Customer – requirement to provide corrected information
120629540 | 266 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120629540 | 266 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
120629540 | 266 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120633938 | 267 | Conduct: Initial Review (IR) | 2021-04-15 | Engineering
120633938 | 267 | Conduct: Initial Review (IR) | 2021-04-29 | Engineering
120633938 | 267 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
120633938 | 267 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120633938 | 267 | Conduct: Initial Review (IR) | 2021-04-15 | Engineering
120633938 | 267 | Conduct: Initial Review (IR) | 2021-04-29 | Engineering
120633938 | 267 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
120633938 | 267 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120633938 | 267 | Conduct: Initial Review (IR) | 2021-04-15 | Engineering
120633938 | 267 | Conduct: Initial Review (IR) | 2021-04-29 | Engineering
120633938 | 267 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
120633938 | 267 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120634838 | 268 | Conduct: Initial Review (IR) | 2021-06-08 | Customer – requesting an extension
120634838 | 268 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120634838 | 268 | Conduct: Initial Review (IR) | 2021-04-22 | Engineering
120634838 | 268 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
120634838 | 268 | Conduct: Initial Review (IR) | 2021-05-17 | Project Management – requiring more detailed review
120634838 | 268 | Conduct: Initial Review (IR) | 2021-06-01 | Project Management – requiring more detailed review
120635852 | 269 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120635852 | 269 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120635852 | 269 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120637461 | 270 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120637461 | 270 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120637461 | 270 | Conduct: Initial Review (IR) | 2021-05-14 | Project Management – addressing a human error
120639109 | 271 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
120639109 | 271 | Conduct: Initial Review (IR) | 2021-05-21 | Customer
120639109 | 271 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – addressing project volume surge
120639109 | 271 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – addressing project volume surge
120639109 | 271 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
120639109 | 271 | Conduct: Initial Review (IR) | 2021-05-21 | Customer
120639109 | 271 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – addressing project volume surge
120639109 | 271 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – addressing project volume surge
120639109 | 271 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
120639109 | 271 | Conduct: Initial Review (IR) | 2021-05-21 | Customer
120639109 | 271 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – addressing project volume surge
120639109 | 271 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – addressing project volume surge
120639588 | 272 | Conduct: Initial Review (IR) | 2021-06-18 | Project Management – addressing a human error
120639746 | 273 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120639746 | 273 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120639746 | 273 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
120639996 | 274 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120639996 | 274 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120639996 | 274 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120639996 | 274 | Conduct: Initial Review (IR) | 2021-04-27 | Customer
120639996 | 274 | Conduct: Initial Review (IR) | 2021-05-11 | Customer – requesting an extension
120639996 | 274 | Conduct: Initial Review (IR) | 2021-05-04 | EGI
120640481 | 275 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120640481 | 275 | Conduct: Initial Review (IR) | 2021-05-04 | Engineering
120640481 | 275 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering – requiring more detailed review
120640481 | 275 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120640481 | 275 | Conduct: Initial Review (IR) | 2021-05-04 | Engineering
120640481 | 275 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering – requiring more detailed review
120640481 | 275 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120640481 | 275 | Conduct: Initial Review (IR) | 2021-05-04 | Engineering
120640481 | 275 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering – requiring more detailed review
120642515 | 276 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120642515 | 276 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120642515 | 276 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120644669 | 277 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
120644669 | 277 | Conduct: Initial Review (IR) | 2021-04-26 | EGI
120644669 | 277 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering – requiring more detailed review
120644669 | 277 | Conduct: Initial Review (IR) | 2021-05-17 | Engineering – requiring more detailed review
120645700 | 278 | Conduct: Initial Review (IR) | 2021-05-07 | Cus – requirement to provide a response to deficiency notice
120645700 | 278 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120645700 | 278 | Conduct: Initial Review (IR) | 2021-04-30 | Customer
120646368 | 279 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120647160 | 280 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120647160 | 280 | Conduct: Initial Review (IR) | 2021-04-20 | EGI
120647160 | 280 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
120647192 | 281 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120647192 | 281 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
120648046 | 282 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120648046 | 282 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120648046 | 282 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120648046 | 282 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120648046 | 282 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120648046 | 282 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120651436 | 283 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
120651436 | 283 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120651436 | 283 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – requiring more detailed review
120651436 | 283 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
120651436 | 283 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120651436 | 283 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – requiring more detailed review
120651436 | 283 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
120651436 | 283 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120651436 | 283 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – requiring more detailed review
120651437 | 284 | Conduct: Supplemental Review (SR) | 2021-05-24 | Engineering – requiring more detailed review
120651437 | 284 | Conduct: Supplemental Review (SR) | 2021-06-01 | Engineering – requiring more detailed review
120651437 | 284 | Conduct: Supplemental Review (SR) | 2021-05-24 | Engineering – requiring more detailed review
120651437 | 284 | Conduct: Supplemental Review (SR) | 2021-06-01 | Engineering – requiring more detailed review
120651437 | 284 | Conduct: Supplemental Review (SR) | 2021-05-24 | Engineering – requiring more detailed review
120651437 | 284 | Conduct: Supplemental Review (SR) | 2021-06-01 | Engineering – requiring more detailed review
120652362 | 285 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-07-19 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-08-16 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-08-23 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-08-30 | Cus – requirement to provide a response to deficiency notice
120652593 | 286 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120652593 | 286 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
120652593 | 286 | Conduct: Initial Review (IR) | 2021-05-13 | Customer – requirement to provide corrected information
120652593 | 286 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120652593 | 286 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120652824 | 287 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120653009 | 288 | Conduct: Initial Review (IR) | 2021-04-28 | Engineering
120653009 | 288 | Conduct: Initial Review (IR) | 2021-05-12 | Engineering
120653009 | 288 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – requiring more detailed review
120653009 | 288 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – requiring more detailed review
120653009 | 288 | Conduct: Initial Review (IR) | 2021-04-28 | Engineering
120653009 | 288 | Conduct: Initial Review (IR) | 2021-05-12 | Engineering
120653009 | 288 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – requiring more detailed review
120653009 | 288 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – requiring more detailed review
120653009 | 288 | Conduct: Initial Review (IR) | 2021-04-28 | Engineering
120653009 | 288 | Conduct: Initial Review (IR) | 2021-05-12 | Engineering
120653009 | 288 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – requiring more detailed review
120653009 | 288 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – requiring more detailed review
120653129 | 289 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120653129 | 289 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120653129 | 289 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120653129 | 289 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – requiring more detailed review
120653129 | 289 | Conduct: Initial Review (IR) | 2021-06-30 | Project Management – requiring more detailed review
120653359 | 290 | Conduct: Initial Review (IR) | 2021-08-17 | Customer – requirement to provide corrected information
120653359 | 290 | Conduct: Initial Review (IR) | 2021-07-02 | Engineering – requiring more detailed review
120653359 | 290 | Conduct: Initial Review (IR) | 2021-07-16 | Engineering – requiring more detailed review
120653359 | 290 | Conduct: Initial Review (IR) | 2021-08-17 | Customer – requirement to provide corrected information
120653359 | 290 | Conduct: Initial Review (IR) | 2021-07-02 | Engineering – requiring more detailed review
120653359 | 290 | Conduct: Initial Review (IR) | 2021-07-16 | Engineering – requiring more detailed review
120653359 | 290 | Conduct: Initial Review (IR) | 2021-08-17 | Customer – requirement to provide corrected information
120653359 | 290 | Conduct: Initial Review (IR) | 2021-07-02 | Engineering – requiring more detailed review
120653359 | 290 | Conduct: Initial Review (IR) | 2021-07-16 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120653625 | 291 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – requiring more detailed review
120654245 | 292 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120654245 | 292 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
120654245 | 292 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
120654245 | 292 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
120654245 | 292 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
120654327 | 293 | Conduct: Initial Review (IR) | 2021-06-10 | Engineering – requiring more detailed review
120654327 | 293 | Conduct: Initial Review (IR) | 2021-06-24 | Engineering – requiring more detailed review
120654327 | 293 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120654327 | 293 | Conduct: Initial Review (IR) | 2021-06-10 | Engineering – requiring more detailed review
120654327 | 293 | Conduct: Initial Review (IR) | 2021-06-24 | Engineering – requiring more detailed review
120654327 | 293 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120654327 | 293 | Conduct: Initial Review (IR) | 2021-06-10 | Engineering – requiring more detailed review
120654327 | 293 | Conduct: Initial Review (IR) | 2021-06-24 | Engineering – requiring more detailed review
120654327 | 293 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120655150 | 294 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120655150 | 294 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120655150 | 294 | Conduct: Initial Review (IR) | 2021-05-06 | Engineering
120655150 | 294 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120655254 | 295 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120655254 | 295 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120655254 | 295 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120655254 | 295 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120655254 | 295 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120655254 | 295 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120655254 | 295 | Conduct: Initial Review (IR) | 2021-05-10 | Customer
120655753 | 296 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120655753 | 296 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120655753 | 296 | Conduct: Initial Review (IR) | 2021-05-04 | EGI
120657295 | 297 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120657295 | 297 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120657885 | 298 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requesting an extension
120658536 | 299 | Conduct: Initial Review (IR) | 2021-05-21 | Engineering – requiring more detailed review
120658536 | 299 | Conduct: Initial Review (IR) | 2021-05-21 | Engineering – requiring more detailed review
120658536 | 299 | Conduct: Initial Review (IR) | 2021-05-21 | Engineering – requiring more detailed review
120659150 | 300 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
120659150 | 300 | Conduct: Initial Review (IR) | 2021-08-05 | Engineering – requiring more detailed review
120659150 | 300 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
120659150 | 300 | Conduct: Initial Review (IR) | 2021-08-05 | Engineering – requiring more detailed review
120659150 | 300 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
120659150 | 300 | Conduct: Initial Review (IR) | 2021-08-05 | Engineering – requiring more detailed review
120659151 | 301 | Conduct: Initial Review (IR) | 2021-06-26 | Engineering – requiring more detailed review
120659151 | 301 | Conduct: Initial Review (IR) | 2021-07-15 | Engineering – requiring more detailed review
120659151 | 301 | Conduct: Initial Review (IR) | 2021-06-26 | Engineering – requiring more detailed review
120659151 | 301 | Conduct: Initial Review (IR) | 2021-07-15 | Engineering – requiring more detailed review
120659151 | 301 | Conduct: Initial Review (IR) | 2021-06-26 | Engineering – requiring more detailed review
120659151 | 301 | Conduct: Initial Review (IR) | 2021-07-15 | Engineering – requiring more detailed review
120659408 | 302 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120659408 | 302 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120659408 | 302 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120659408 | 302 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120659408 | 302 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120659408 | 302 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120659408 | 302 | Conduct: Initial Review (IR) | 2021-05-10 | Customer
120660151 | 303 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120660151 | 303 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120660151 | 303 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120662541 | 304 | Schedule: Scoping Meeting | 2021-10-21 | Customer – requesting an extension
120662541 | 304 | Tender Draft IA | 2021-06-30 | Customer – requirement to provide corrected information
120662541 | 304 | Tender Draft IA | 2021-08-31 | Customer – requirement to provide corrected information
120662541 | 304 | Conduct: Initial Review (IR) | 2021-04-30 | Engineering
120662541 | 304 | Conduct: Screens Q and R | 2021-10-14 | Engineering – addressing project volume surge
120662541 | 304 | Tender Draft IA | 2021-07-30 | Project Management – requiring more detailed review
120662541 | 304 | Schedule: Scoping Meeting | 2021-10-21 | Customer – requesting an extension
120662541 | 304 | Tender Draft IA | 2021-06-30 | Customer – requirement to provide corrected information
120662541 | 304 | Tender Draft IA | 2021-08-31 | Customer – requirement to provide corrected information
120662541 | 304 | Conduct: Initial Review (IR) | 2021-04-30 | Engineering
120662541 | 304 | Conduct: Screens Q and R | 2021-10-14 | Engineering – addressing project volume surge
120662541 | 304 | Tender Draft IA | 2021-07-30 | Project Management – requiring more detailed review
120662541 | 304 | Schedule: Scoping Meeting | 2021-10-21 | Customer – requesting an extension
120662541 | 304 | Tender Draft IA | 2021-06-30 | Customer – requirement to provide corrected information
120662541 | 304 | Tender Draft IA | 2021-08-31 | Customer – requirement to provide corrected information
120662541 | 304 | Conduct: Initial Review (IR) | 2021-04-30 | Engineering
120662541 | 304 | Conduct: Screens Q and R | 2021-10-14 | Engineering – addressing project volume surge
120662541 | 304 | Conduct: SIS | 2022-02-28 | Engineering – requiring more detailed review
120662541 | 304 | Conduct: SIS | 2022-03-31 | Engineering – requiring more detailed review
120662541 | 304 | Conduct: SIS | 2022-04-29 | Engineering – requiring more detailed review
120662541 | 304 | Tender Draft IA | 2021-07-30 | Project Management – requiring more detailed review
120662832 | 305 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120662832 | 305 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120662832 | 305 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120662832 | 305 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
120662832 | 305 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120662832 | 305 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120662832 | 305 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120662832 | 305 | Conduct: Initial Review (IR) | 2021-04-27 | Customer
120662832 | 305 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120673056 | 306 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120673056 | 306 | Conduct: Initial Review (IR) | 2021-06-23 | Cus – requirement to provide a response to deficiency notice
120673056 | 306 | Conduct: Initial Review (IR) | 2021-06-30 | Cus – requirement to provide a response to deficiency notice
120673056 | 306 | Conduct: Initial Review (IR) | 2021-07-08 | Cus – requirement to provide a response to deficiency notice
120673056 | 306 | Conduct: Initial Review (IR) | 2021-07-15 | Cus – requirement to provide a response to deficiency notice
120673056 | 306 | Conduct: Initial Review (IR) | 2021-07-22 | Cus – requirement to provide a response to deficiency notice
120673056 | 306 | Conduct: Initial Review (IR) | 2021-07-29 | Cus – requirement to provide a response to deficiency notice
120673056 | 306 | Conduct: Initial Review (IR) | 2021-05-25 | Customer – requirement to provide corrected information
120673056 | 306 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120673056 | 306 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120673323 | 307 | Conduct: Initial Review (IR) | 2021-06-10 | Engineering – requiring more detailed review
120673323 | 307 | Conduct: Initial Review (IR) | 2021-06-24 | Engineering – requiring more detailed review
120673323 | 307 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120673323 | 307 | Conduct: Initial Review (IR) | 2021-06-10 | Engineering – requiring more detailed review
120673323 | 307 | Conduct: Initial Review (IR) | 2021-06-24 | Engineering – requiring more detailed review
120673323 | 307 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120673323 | 307 | Conduct: Initial Review (IR) | 2021-06-10 | Engineering – requiring more detailed review
120673323 | 307 | Conduct: Initial Review (IR) | 2021-06-24 | Engineering – requiring more detailed review
120673323 | 307 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120674435 | 308 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
120674435 | 308 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
120674435 | 308 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
120676644 | 309 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
120676644 | 309 | Conduct: Initial Review (IR) | 2021-05-24 | Project Management – requiring more detailed review
120676644 | 309 | Conduct: Initial Review (IR) | 2021-06-07 | Project Management – requiring more detailed review
120676644 | 309 | Conduct: Initial Review (IR) | 2021-07-06 | Project Management – requiring more detailed review
120676644 | 309 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
120676644 | 309 | Conduct: Initial Review (IR) | 2021-05-24 | Project Management – requiring more detailed review
120676644 | 309 | Conduct: Initial Review (IR) | 2021-06-07 | Project Management – requiring more detailed review
120676644 | 309 | Conduct: Initial Review (IR) | 2021-07-06 | Project Management – requiring more detailed review
120676644 | 309 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
120676644 | 309 | Conduct: Initial Review (IR) | 2021-05-24 | Project Management – requiring more detailed review
120676644 | 309 | Conduct: Initial Review (IR) | 2021-06-07 | Project Management – requiring more detailed review
120676644 | 309 | Conduct: Initial Review (IR) | 2021-07-06 | Project Management – requiring more detailed review
120677457 | 310 | Conduct: Initial Review (IR) | 2021-07-13 | Engineering – requiring more detailed review
120677457 | 310 | Conduct: Initial Review (IR) | 2021-07-20 | Engineering – requiring more detailed review
120677457 | 310 | Conduct: Initial Review (IR) | 2021-07-27 | Engineering – requiring more detailed review
120677457 | 310 | Conduct: Initial Review (IR) | 2021-08-03 | Engineering – requiring more detailed review
120677457 | 310 | Conduct: Initial Review (IR) | 2021-07-27 | Engineering – requiring more detailed review
120677457 | 310 | Conduct: Initial Review (IR) | 2021-07-13 | Engineering – requiring more detailed review
120677457 | 310 | Conduct: Initial Review (IR) | 2021-07-20 | Engineering – requiring more detailed review
120677457 | 310 | Conduct: Initial Review (IR) | 2021-08-03 | Engineering – requiring more detailed review
120677457 | 310 | Conduct: Initial Review (IR) | 2021-07-13 | Engineering – requiring more detailed review
120677457 | 310 | Conduct: Initial Review (IR) | 2021-07-20 | Engineering – requiring more detailed review
120677457 | 310 | Conduct: Initial Review (IR) | 2021-07-27 | Engineering – requiring more detailed review
120677457 | 310 | Conduct: Initial Review (IR) | 2021-08-03 | Engineering – requiring more detailed review
120677909 | 311 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
120678397 | 312 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120678397 | 312 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120678397 | 312 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120678397 | 312 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120678397 | 312 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120679519 | 313 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
120680099 | 314 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – addressing project volume surge
120680099 | 314 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – addressing project volume surge
120680099 | 314 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – requiring more detailed review
120680099 | 314 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
120680099 | 314 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – addressing project volume surge
120680099 | 314 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – addressing project volume surge
120680099 | 314 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – requiring more detailed review
120680099 | 314 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
120680099 | 314 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – addressing project volume surge
120680099 | 314 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – addressing project volume surge
120680099 | 314 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – requiring more detailed review
120680099 | 314 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
120680849 | 315 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120680849 | 315 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120680849 | 315 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120680849 | 315 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120680849 | 315 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120680849 | 315 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120680849 | 315 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120680849 | 315 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120680849 | 315 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120680849 | 315 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120680849 | 315 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120680849 | 315 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120685085 | 316 | Conduct: Initial Review (IR) | 2021-04-30 | Engineering
120685085 | 316 | Conduct: Initial Review (IR) | 2021-05-14 | Engineering – requiring more detailed review
120685085 | 316 | Conduct: Initial Review (IR) | 2021-05-28 | Engineering – requiring more detailed review
120685085 | 316 | Conduct: Initial Review (IR) | 2021-06-14 | Engineering – requiring more detailed review
120685085 | 316 | Conduct: Initial Review (IR) | 2021-06-28 | Engineering – requiring more detailed review
120685085 | 316 | Conduct: Initial Review (IR) | 2021-04-30 | Engineering
120685085 | 316 | Conduct: Initial Review (IR) | 2021-05-14 | Engineering – requiring more detailed review
120685085 | 316 | Conduct: Initial Review (IR) | 2021-05-28 | Engineering – requiring more detailed review
120685085 | 316 | Conduct: Initial Review (IR) | 2021-06-14 | Engineering – requiring more detailed review
120685085 | 316 | Conduct: Initial Review (IR) | 2021-06-28 | Engineering – requiring more detailed review
120685085 | 316 | Conduct: Initial Review (IR) | 2021-04-30 | Engineering
120685085 | 316 | Conduct: Initial Review (IR) | 2021-05-14 | Engineering – requiring more detailed review
120685085 | 316 | Conduct: Initial Review (IR) | 2021-05-28 | Engineering – requiring more detailed review
120685085 | 316 | Conduct: Initial Review (IR) | 2021-06-14 | Engineering – requiring more detailed review
120685085 | 316 | Conduct: Initial Review (IR) | 2021-06-28 | Engineering – requiring more detailed review
120687253 | 317 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120687253 | 317 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120687253 | 317 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120687253 | 317 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
120687253 | 317 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120687253 | 317 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120687253 | 317 | Conduct: Initial Review (IR) | 2021-04-27 | Customer
120687253 | 317 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120687736 | 318 | Conduct: Initial Review (IR) | 2021-05-06 | Customer – requirement to provide corrected information
120689811 | 319 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120689811 | 319 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120689811 | 319 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120689811 | 319 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120689811 | 319 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120689811 | 319 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
120689811 | 319 | Conduct: Initial Review (IR) | 2021-05-03 | Engineering
120689917 | 320 | Conduct: Initial Review (IR) | 2021-05-31 | Cus – requirement to provide a response to deficiency notice
120689917 | 320 | Conduct: Initial Review (IR) | 2021-05-24 | Engineering
120689917 | 320 | Conduct: Initial Review (IR) | 2021-06-07 | Engineering – requiring more detailed review
120689917 | 320 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
120689917 | 320 | Conduct: Initial Review (IR) | 2021-05-31 | Cus – requirement to provide a response to deficiency notice
120689917 | 320 | Conduct: Initial Review (IR) | 2021-05-24 | Engineering
120689917 | 320 | Conduct: Initial Review (IR) | 2021-06-07 | Engineering – requiring more detailed review
120689917 | 320 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
120689917 | 320 | Conduct: Initial Review (IR) | 2021-05-31 | Cus – requirement to provide a response to deficiency notice
120689917 | 320 | Conduct: Initial Review (IR) | 2021-05-24 | Engineering
120689917 | 320 | Conduct: Initial Review (IR) | 2021-06-07 | Engineering – requiring more detailed review
120689917 | 320 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
120690266 | 321 | Conduct: Initial Review (IR) | 2021-04-28 | Engineering
120690266 | 321 | Conduct: Initial Review (IR) | 2021-05-12 | Engineering
120690266 | 321 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – requiring more detailed review
120690266 | 321 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – requiring more detailed review
120690266 | 321 | Conduct: Initial Review (IR) | 2021-04-28 | Engineering
120690266 | 321 | Conduct: Initial Review (IR) | 2021-05-12 | Engineering
120690266 | 321 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – requiring more detailed review
120690266 | 321 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – requiring more detailed review
120690266 | 321 | Conduct: Initial Review (IR) | 2021-04-28 | Engineering
120690266 | 321 | Conduct: Initial Review (IR) | 2021-05-12 | Engineering
120690266 | 321 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – requiring more detailed review
120690266 | 321 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – requiring more detailed review
120690803 | 322 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120690803 | 322 | Conduct: Initial Review (IR) | 2021-05-10 | Customer
120690803 | 322 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requesting an extension
120690803 | 322 | Conduct: Initial Review (IR) | 2021-06-08 | Customer – requesting an extension
120690803 | 322 | Conduct: Initial Review (IR) | 2021-05-17 | Project Management – requiring more detailed review
120690803 | 322 | Conduct: Initial Review (IR) | 2021-06-01 | Project Management – requiring more detailed review
120692791 | 323 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120692791 | 323 | Conduct: Initial Review (IR) | 2021-06-02 | Project Management – requiring more detailed review
120692895 | 324 | Conduct: Initial Review (IR) | 2021-05-12 | Cus – requirement to provide a response to deficiency notice
120692895 | 324 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
120692895 | 324 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120692895 | 324 | Conduct: Initial Review (IR) | 2021-06-03 | Cus – requirement to provide a response to deficiency notice
120692895 | 324 | Conduct: Initial Review (IR) | 2021-04-28 | Customer
120692895 | 324 | Conduct: Initial Review (IR) | 2021-05-05 | Customer
120693911 | 325 | Conduct: Initial Review (IR) | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
120693911 | 325 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120693911 | 325 | Conduct: Initial Review (IR) | 2021-05-03 | EGI
120693911 | 325 | Conduct: Initial Review (IR) | 2021-05-17 | Project Management - addressing project volume surge
120695606 | 326 | Conduct: Initial Review (IR) | 2021-05-05 | Engineering
120695606 | 326 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – requiring more detailed review
120695606 | 326 | Conduct: Initial Review (IR) | 2021-05-05 | Engineering
120695606 | 326 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – requiring more detailed review
120695606 | 326 | Conduct: Initial Review (IR) | 2021-05-05 | Engineering
120695606 | 326 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – requiring more detailed review
120695922 | 327 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requesting an extension
120696114 | 328 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120696114 | 328 | Conduct: Initial Review (IR) | 2021-05-10 | Customer
120696114 | 328 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requesting an extension
120696114 | 328 | Conduct: Initial Review (IR) | 2021-05-17 | Project Management – requiring more detailed review
120697785 | 329 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requesting an extension
120697785 | 329 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requesting an extension
120697785 | 329 | Conduct: Initial Review (IR) | 2021-05-04 | Engineering
120697785 | 329 | Conduct: Initial Review (IR) | 2021-05-18 | Engineering – requiring more detailed review
120697785 | 329 | Conduct: Initial Review (IR) | 2021-05-25 | Project Management – requiring more detailed review
120697785 | 329 | Conduct: Initial Review (IR) | 2021-06-02 | Project Management – requiring more detailed review
120702260 | 330 | Conduct: Initial Review (IR) | 2021-04-26 | Engineering
120702260 | 330 | Conduct: Initial Review (IR) | 2021-05-03 | Engineering
120702260 | 330 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering – requiring more detailed review
120702643 | 331 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
120702643 | 331 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
120702643 | 331 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
120702643 | 331 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
120707179 | 332 | Conduct: Initial Review (IR) | 2021-05-07 | Cus – requirement to provide a response to deficiency notice
120707179 | 332 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120707179 | 332 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120707179 | 332 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120707179 | 332 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120707179 | 332 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120707179 | 332 | Conduct: Initial Review (IR) | 2021-04-30 | Customer
120708164 | 333 | Conduct: Supplemental Review (SR) | 2021-07-01 | Engineering – addressing project volume surge
120708164 | 333 | Conduct: Supplemental Review (SR) | 2021-07-02 | Engineering – addressing project volume surge
120708164 | 333 | Conduct: Supplemental Review (SR) | 2021-07-07 | Engineering – addressing project volume surge
120708164 | 333 | Conduct: Supplemental Review (SR) | 2021-07-08 | Engineering – addressing project volume surge
120708164 | 333 | Conduct: Supplemental Review (SR) | 2021-07-01 | Engineering – addressing project volume surge
120708164 | 333 | Conduct: Supplemental Review (SR) | 2021-07-02 | Engineering – addressing project volume surge
120708164 | 333 | Conduct: Supplemental Review (SR) | 2021-07-07 | Engineering – addressing project volume surge
120708164 | 333 | Conduct: Supplemental Review (SR) | 2021-07-08 | Engineering – addressing project volume surge
120708164 | 333 | Conduct: Supplemental Review (SR) | 2021-07-01 | Engineering – addressing project volume surge
120708164 | 333 | Conduct: Supplemental Review (SR) | 2021-07-02 | Engineering – addressing project volume surge
120708164 | 333 | Conduct: Supplemental Review (SR) | 2021-07-07 | Engineering – addressing project volume surge
120708164 | 333 | Conduct: Supplemental Review (SR) | 2021-07-08 | Engineering – addressing project volume surge
120708334 | 334 | Conduct: Initial Review (IR) | 2021-05-19 | Customer – requirement to provide corrected information
120708334 | 334 | Conduct: Initial Review (IR) | 2021-05-28 | Engineering – requiring more detailed review
120708334 | 334 | Conduct: Initial Review (IR) | 2021-05-19 | Customer – requirement to provide corrected information
120708334 | 334 | Conduct: Initial Review (IR) | 2021-05-28 | Engineering – requiring more detailed review
120708334 | 334 | Conduct: Initial Review (IR) | 2021-05-19 | Customer – requirement to provide corrected information
120708334 | 334 | Conduct: Initial Review (IR) | 2021-05-28 | Engineering – requiring more detailed review
120709190 | 335 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-08-05 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-08-12 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-08-19 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-08-26 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-09-02 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-09-17 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-09-24 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-10-01 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-30 | Customer – requirement to provide corrected information
120709190 | 335 | Conduct: Initial Review (IR) | 2021-07-15 | Customer – requirement to provide corrected information
120709190 | 335 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120709190 | 335 | Conduct: Initial Review (IR) | 2021-07-29 | Engineering – addressing project volume surge
120709190 | 335 | Conduct: Initial Review (IR) | 2021-10-08 | Engineering – requiring more detailed review
120709190 | 335 | Conduct: Initial Review (IR) | 2021-05-25 | Project Management - addressing project volume surge
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-23 | Project Management - addressing project volume surge
120709190 | 335 | Conduct: Initial Review (IR) | 2021-07-08 | Project Management - addressing project volume surge
120709190 | 335 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-08-05 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-08-12 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-08-19 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-08-26 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-09-02 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-09-17 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-09-24 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-10-01 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-10-29 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-11-05 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-11-12 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-30 | Customer – requirement to provide corrected information
120709190 | 335 | Conduct: Initial Review (IR) | 2021-07-15 | Customer – requirement to provide corrected information
120709190 | 335 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120709190 | 335 | Conduct: Initial Review (IR) | 2021-07-29 | Engineering – addressing project volume surge
120709190 | 335 | Conduct: Initial Review (IR) | 2021-12-03 | Engineering – addressing project volume surge
120709190 | 335 | Conduct: Initial Review (IR) | 2021-10-08 | Engineering – requiring more detailed review
120709190 | 335 | Conduct: Initial Review (IR) | 2021-11-19 | Engineering – requiring more detailed review
120709190 | 335 | Conduct: Initial Review (IR) | 2021-11-26 | Engineering – requiring more detailed review
120709190 | 335 | Conduct: Initial Review (IR) | 2021-05-25 | Project Management - addressing project volume surge
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-23 | Project Management - addressing project volume surge
120709190 | 335 | Conduct: Initial Review (IR) | 2021-07-08 | Project Management - addressing project volume surge
120709190 | 335 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-08-05 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-08-12 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-08-19 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-08-26 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-09-02 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-09-17 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-09-24 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-10-01 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-10-29 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-11-05 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-11-12 | Cus – requirement to provide a response to deficiency notice
120709190 | 335 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-30 | Customer – requirement to provide corrected information
120709190 | 335 | Conduct: Initial Review (IR) | 2021-07-15 | Customer – requirement to provide corrected information
120709190 | 335 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120709190 | 335 | Conduct: Initial Review (IR) | 2021-12-03 | Engineering – addressing project volume surge
120709190 | 335 | Conduct: Initial Review (IR) | 2021-07-29 | Engineering – addressing project volume surge
120709190 | 335 | Conduct: Initial Review (IR) | 2021-10-08 | Engineering – requiring more detailed review
120709190 | 335 | Conduct: Initial Review (IR) | 2021-11-19 | Engineering – requiring more detailed review
120709190 | 335 | Conduct: Initial Review (IR) | 2021-11-26 | Engineering – requiring more detailed review
120709190 | 335 | Conduct: Initial Review (IR) | 2021-05-25 | Project Management - addressing project volume surge
120709190 | 335 | Conduct: Initial Review (IR) | 2021-06-23 | Project Management - addressing project volume surge
120709190 | 335 | Conduct: Initial Review (IR) | 2021-07-08 | Project Management - addressing project volume surge
120710017 | 336 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120710017 | 336 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120711343 | 337 | Conduct: Supplemental Review (SR) | 2021-07-23 | Engineering – addressing project volume surge
120711343 | 337 | Conduct: Initial Review (IR) | 2021-05-18 | Engineering – requiring more detailed review
120711343 | 337 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120711343 | 337 | Conduct: Supplemental Review (SR) | 2021-07-16 | Engineering – requiring more detailed review
120711343 | 337 | Conduct: Supplemental Review (SR) | 2021-07-23 | Engineering – addressing project volume surge
120711343 | 337 | Conduct: Initial Review (IR) | 2021-05-18 | Engineering – requiring more detailed review
120711343 | 337 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120711343 | 337 | Conduct: Supplemental Review (SR) | 2021-07-16 | Engineering – requiring more detailed review
120712944 | 338 | Conduct: Initial Review (IR) | 2021-07-08 | Customer – requirement to provide corrected information
120713658 | 339 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120713658 | 339 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120713658 | 339 | Conduct: Initial Review (IR) | 2021-06-18 | Engineering – requiring more detailed review
120713658 | 339 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120713658 | 339 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120713658 | 339 | Conduct: Initial Review (IR) | 2021-06-18 | Engineering – requiring more detailed review
120713658 | 339 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120713658 | 339 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120713658 | 339 | Conduct: Initial Review (IR) | 2021-06-18 | Engineering – requiring more detailed review
120714094 | 340 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120714094 | 340 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120714094 | 340 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120714094 | 340 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120714094 | 340 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120714094 | 340 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120714094 | 340 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120714094 | 340 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
120714094 | 340 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120714146 | 341 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-07-19 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
120714146 | 341 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120714464 | 342 | Conduct: Initial Review (IR) | 2021-04-29 | Engineering
120714464 | 342 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
120714464 | 342 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120714464 | 342 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – requiring more detailed review
120714464 | 342 | Conduct: Initial Review (IR) | 2021-04-29 | Engineering
120714464 | 342 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
120714464 | 342 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120714464 | 342 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – requiring more detailed review
120714464 | 342 | Conduct: Initial Review (IR) | 2021-04-29 | Engineering
120714464 | 342 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
120714464 | 342 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120714464 | 342 | Conduct: Initial Review (IR) | 2021-06-04 | Engineering – requiring more detailed review
120716128 | 343 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120716128 | 343 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
120716128 | 343 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120716128 | 343 | Conduct: Initial Review (IR) | 2021-05-14 | Engineering – requiring more detailed review
120717762 | 344 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120718201 | 345 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120718201 | 345 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120718201 | 345 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
120718201 | 345 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120718201 | 345 | Conduct: Initial Review (IR) | 2021-05-11 | Customer – requirement to provide corrected information
120718888 | 346 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120718888 | 346 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120718888 | 346 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120718888 | 346 | Conduct: Initial Review (IR) | 2021-05-10 | Customer
120719773 | 347 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120719773 | 347 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120719773 | 347 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120719773 | 347 | Conduct: Initial Review (IR) | 2021-05-14 | Engineering – requiring more detailed review
120720576 | 348 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120720576 | 348 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120720576 | 348 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requesting an extension
120720576 | 348 | Conduct: Initial Review (IR) | 2021-05-18 | Customer – requirement to provide corrected information
120720576 | 348 | Conduct: Initial Review (IR) | 2021-05-25 | Customer – requirement to provide corrected information
120720576 | 348 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120720654 | 349 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120720654 | 349 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120720654 | 349 | Conduct: Initial Review (IR) | 2021-05-18 | Customer – requirement to provide corrected information
120720654 | 349 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120720654 | 349 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
120720675 | 350 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120720675 | 350 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120720675 | 350 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requesting an extension
120720675 | 350 | Conduct: Initial Review (IR) | 2021-05-18 | Customer – requirement to provide corrected information
120720675 | 350 | Conduct: Initial Review (IR) | 2021-05-25 | Customer – requirement to provide corrected information
120720675 | 350 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120720699 | 351 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120720699 | 351 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120720699 | 351 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120720699 | 351 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
120720765 | 352 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120720765 | 352 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120720765 | 352 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requesting an extension
120720765 | 352 | Conduct: Initial Review (IR) | 2021-05-18 | Customer – requirement to provide corrected information
120720765 | 352 | Conduct: Initial Review (IR) | 2021-05-25 | Customer – requirement to provide corrected information
120720765 | 352 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120720824 | 353 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120720824 | 353 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120720824 | 353 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requesting an extension
120720824 | 353 | Conduct: Initial Review (IR) | 2021-05-18 | Customer – requirement to provide corrected information
120720824 | 353 | Conduct: Initial Review (IR) | 2021-05-25 | Customer – requirement to provide corrected information
120720824 | 353 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120720858 | 354 | Conduct: Initial Review (IR) | 2021-05-11 | Cus – requirement to provide a response to deficiency notice
120720858 | 354 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120720858 | 354 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120720858 | 354 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requesting an extension
120720858 | 354 | Conduct: Initial Review (IR) | 2021-05-18 | Customer – requirement to provide corrected information
120720858 | 354 | Conduct: Initial Review (IR) | 2021-05-25 | Customer – requirement to provide corrected information
120720858 | 354 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120721051 | 355 | Conduct: Initial Review (IR) | 2021-05-06 | Cus – requirement to provide a response to deficiency notice
120721051 | 355 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120721051 | 355 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120721051 | 355 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120721051 | 355 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120721051 | 355 | Conduct: Initial Review (IR) | 2021-05-27 | Customer – requirement to provide corrected information
120721051 | 355 | Conduct: Initial Review (IR) | 2021-06-18 | Engineering – requiring more detailed review
120722019 | 356 | Conduct: Initial Review (IR) | 2021-05-14 | Customer – requirement to provide corrected information
120722019 | 356 | Conduct: Initial Review (IR) | 2021-05-14 | Customer – requirement to provide corrected information
120722019 | 356 | Conduct: Initial Review (IR) | 2021-05-14 | Customer – requirement to provide corrected information
120722334 | 357 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120722334 | 357 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120722334 | 357 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – requiring more detailed review
120722334 | 357 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120722334 | 357 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120722334 | 357 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120722334 | 357 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – requiring more detailed review
120722334 | 357 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120722334 | 357 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120722334 | 357 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120722334 | 357 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – requiring more detailed review
120722334 | 357 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120726255 | 358 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
120726255 | 358 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120726255 | 358 | Conduct: Initial Review (IR) | 2021-05-12 | Engineering
120727154 | 359 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – addressing project volume surge
120727154 | 359 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – addressing project volume surge
120727154 | 359 | Conduct: Initial Review (IR) | 2021-06-11 | Engineering – addressing project volume surge
120727263 | 360 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120727263 | 360 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120727263 | 360 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
120727263 | 360 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120727263 | 360 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120727263 | 360 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120727263 | 360 | Conduct: Initial Review (IR) | 2021-05-11 | Customer – requesting an extension
120728066 | 361 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requesting an extension
120728066 | 361 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requesting an extension
120728066 | 361 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requesting an extension
120728066 | 361 | Conduct: Initial Review (IR) | 2021-06-17 | Customer – requesting an extension
120728066 | 361 | Conduct: Initial Review (IR) | 2021-05-12 | Engineering
120728066 | 361 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – requiring more detailed review
120735552 | 362 | Conduct: Initial Review (IR) | 2021-05-21 | Engineering – addressing project volume surge
120735552 | 362 | Conduct: Initial Review (IR) | 2021-05-21 | Engineering – addressing project volume surge
120735552 | 362 | Conduct: Initial Review (IR) | 2021-05-21 | Engineering – addressing project volume surge
120736376 | 363 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120736376 | 363 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120736376 | 363 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120736376 | 363 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120736376 | 363 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120737045 | 364 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requesting an extension
120737045 | 364 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120737045 | 364 | Conduct: Initial Review (IR) | 2021-05-06 | Engineering – requiring more detailed review
120737045 | 364 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120737045 | 364 | Conduct: Initial Review (IR) | 2021-05-27 | Project Management – requiring more detailed review
120737110 | 365 | Conduct: Initial Review (IR) | 2021-05-13 | Engineering – requiring more detailed review
120737110 | 365 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120737110 | 365 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120737110 | 365 | Conduct: Initial Review (IR) | 2021-07-01 | Engineering – requiring more detailed review
120737110 | 365 | Conduct: Initial Review (IR) | 2021-07-30 | Engineering – requiring more detailed review
120737196 | 366 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120737196 | 366 | Conduct: Initial Review (IR) | 2021-06-24 | Engineering – requiring more detailed review
120737196 | 366 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120737196 | 366 | Conduct: Initial Review (IR) | 2021-07-16 | Engineering – requiring more detailed review
120737196 | 366 | Tender Draft IA | 2021-08-27 | Project Management - addressing project volume surge
120737196 | 366 | Conduct: Initial Review (IR) | 2021-06-10 | Project Management – requiring more detailed review
120737196 | 366 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120737196 | 366 | Conduct: Initial Review (IR) | 2021-06-24 | Engineering – requiring more detailed review
120737196 | 366 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120737196 | 366 | Conduct: Initial Review (IR) | 2021-07-16 | Engineering – requiring more detailed review
120737196 | 366 | Tender Draft IA | 2021-08-27 | Project Management - addressing project volume surge
120737196 | 366 | Conduct: Initial Review (IR) | 2021-06-10 | Project Management – requiring more detailed review
120737196 | 366 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120737196 | 366 | Conduct: Initial Review (IR) | 2021-06-24 | Engineering – requiring more detailed review
120737196 | 366 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120737196 | 366 | Conduct: Initial Review (IR) | 2021-07-16 | Engineering – requiring more detailed review
120737196 | 366 | Tender Draft IA | 2021-08-27 | Project Management - addressing project volume surge
120737196 | 366 | Conduct: Initial Review (IR) | 2021-06-10 | Project Management – requiring more detailed review
120737208 | 367 | Conduct: Initial Review (IR) | 2021-05-06 | Engineering – requiring more detailed review
120737583 | 368 | Conduct: Initial Review (IR) | 2021-07-01 | Engineering – addressing project volume surge
120737583 | 368 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120737583 | 368 | Conduct: Initial Review (IR) | 2021-07-01 | Engineering – addressing project volume surge
120737583 | 368 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120737583 | 368 | Conduct: Initial Review (IR) | 2021-07-01 | Engineering – addressing project volume surge
120737583 | 368 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120737868 | 369 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
120738200 | 370 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120738200 | 370 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120738200 | 370 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120738210 | 371 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – requiring more detailed review
120738210 | 371 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120738210 | 371 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – requiring more detailed review
120738210 | 371 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120738210 | 371 | Conduct: Initial Review (IR) | 2021-06-16 | Engineering – requiring more detailed review
120738210 | 371 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120741508 | 372 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120741508 | 372 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120741508 | 372 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120742267 | 373 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120742267 | 373 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120742267 | 373 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
120742267 | 373 | Conduct: Initial Review (IR) | 2021-07-06 | Cus – requirement to provide a response to deficiency notice
120742267 | 373 | Conduct: Initial Review (IR) | 2021-07-13 | Cus – requirement to provide a response to deficiency notice
120742267 | 373 | Conduct: Initial Review (IR) | 2021-07-20 | Cus – requirement to provide a response to deficiency notice
120742267 | 373 | Conduct: Initial Review (IR) | 2021-07-27 | Cus – requirement to provide a response to deficiency notice
120742267 | 373 | Conduct: Initial Review (IR) | 2021-08-03 | Cus – requirement to provide a response to deficiency notice
120742267 | 373 | Conduct: Initial Review (IR) | 2021-08-10 | Cus – requirement to provide a response to deficiency notice
120742267 | 373 | Conduct: Initial Review (IR) | 2021-08-17 | Cus – requirement to provide a response to deficiency notice
120742267 | 373 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requesting an extension
120742267 | 373 | Conduct: Initial Review (IR) | 2021-06-14 | Customer – requesting an extension
120742267 | 373 | Conduct: Initial Review (IR) | 2021-05-14 | Engineering – requiring more detailed review
120742267 | 373 | Conduct: Initial Review (IR) | 2021-06-21 | Project Management - addressing project volume surge
120742492 | 374 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120742492 | 374 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120742492 | 374 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120742492 | 374 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120742492 | 374 | Conduct: Initial Review (IR) | 2021-05-14 | Engineering – requiring more detailed review
120742852 | 375 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120742852 | 375 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120742852 | 375 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120742852 | 375 | Conduct: Initial Review (IR) | 2021-06-21 | Cus – requirement to provide a response to deficiency notice
120742852 | 375 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120742852 | 375 | Conduct: Initial Review (IR) | 2021-05-14 | Engineering – requiring more detailed review
120743596 | 376 | Conduct: Initial Review (IR) | 2021-05-17 | Cus – requirement to provide a response to deficiency notice
120743596 | 376 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120743596 | 376 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120743596 | 376 | Conduct: Initial Review (IR) | 2021-05-10 | Customer – requirement to provide corrected information
120745437 | 377 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120745437 | 377 | Conduct: Initial Review (IR) | 2021-06-30 | Cus – requirement to provide a response to deficiency notice
120745437 | 377 | Conduct: Initial Review (IR) | 2021-07-08 | Cus – requirement to provide a response to deficiency notice
120745437 | 377 | Conduct: Initial Review (IR) | 2021-06-23 | Customer – requesting an extension
120747032 | 378 | Conduct: Initial Review (IR) | 2021-05-24 | Project Management – addressing a human error
120749173 | 379 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120749173 | 379 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120749173 | 379 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120749736 | 380 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
120749736 | 380 | Conduct: Initial Review (IR) | 2021-07-12 | Customer – requirement to provide corrected information
120749736 | 380 | Conduct: Initial Review (IR) | 2021-08-09 | Customer – requirement to provide corrected information
120749736 | 380 | Conduct: Initial Review (IR) | 2021-08-30 | Customer – requirement to provide corrected information
120749736 | 380 | Conduct: Initial Review (IR) | 2021-09-14 | Customer – requirement to provide corrected information
120749736 | 380 | Conduct: Initial Review (IR) | 2021-10-05 | Customer – requirement to provide corrected information
120749736 | 380 | Conduct: Initial Review (IR) | 2021-10-12 | Engineering – requiring more detailed review
120749736 | 380 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
120749736 | 380 | Conduct: Initial Review (IR) | 2021-07-12 | Customer – requirement to provide corrected information
120749736 | 380 | Conduct: Initial Review (IR) | 2021-08-09 | Customer – requirement to provide corrected information
120749736 | 380 | Conduct: Initial Review (IR) | 2021-08-30 | Customer – requirement to provide corrected information
120749736 | 380 | Conduct: Initial Review (IR) | 2021-09-14 | Customer – requirement to provide corrected information
120749736 | 380 | Conduct: Initial Review (IR) | 2021-10-05 | Customer – requirement to provide corrected information
120749736 | 380 | Conduct: Initial Review (IR) | 2021-10-12 | Engineering – requiring more detailed review
120749736 | 380 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
120749736 | 380 | Conduct: Initial Review (IR) | 2021-07-12 | Customer – requirement to provide corrected information
120749736 | 380 | Conduct: Initial Review (IR) | 2021-08-09 | Customer – requirement to provide corrected information
120749736 | 380 | Conduct: Initial Review (IR) | 2021-08-30 | Customer – requirement to provide corrected information
120749736 | 380 | Conduct: Initial Review (IR) | 2021-09-14 | Customer – requirement to provide corrected information
120749736 | 380 | Conduct: Initial Review (IR) | 2021-10-05 | Customer – requirement to provide corrected information
120749736 | 380 | Conduct: Initial Review (IR) | 2021-10-12 | Engineering – requiring more detailed review
120750928 | 381 | Conduct: Initial Review (IR) | 2021-05-12 | Cus – requirement to provide a response to deficiency notice
120750928 | 381 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
120750935 | 382 | Conduct: Initial Review (IR) | 2021-05-12 | Cus – requirement to provide a response to deficiency notice
120750935 | 382 | Conduct: Initial Review (IR) | 2021-05-05 | Customer
120750935 | 382 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120750935 | 382 | Conduct: Initial Review (IR) | 2021-05-19 | Project Management - addressing project volume surge
120751083 | 383 | Conduct: Initial Review (IR) | 2021-05-12 | Cus – requirement to provide a response to deficiency notice
120751083 | 383 | Conduct: Initial Review (IR) | 2021-05-05 | Customer
120751228 | 384 | Conduct: Initial Review (IR) | 2021-07-22 | Cus – requirement to provide a response to deficiency notice
120751228 | 384 | Conduct: Initial Review (IR) | 2021-08-05 | Cus – requirement to provide a response to deficiency notice
120751228 | 384 | Conduct: Initial Review (IR) | 2021-08-26 | Cus – requirement to provide a response to deficiency notice
120751228 | 384 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
120751228 | 384 | Conduct: Initial Review (IR) | 2021-10-01 | Customer – requirement to provide corrected information
120751228 | 384 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – addressing project volume surge
120751228 | 384 | Conduct: Initial Review (IR) | 2021-10-21 | Project Management – requiring more detailed review
120751228 | 384 | Conduct: Initial Review (IR) | 2021-08-05 | Cus – requirement to provide a response to deficiency notice
120751228 | 384 | Conduct: Initial Review (IR) | 2021-07-22 | Cus – requirement to provide a response to deficiency notice
120751228 | 384 | Conduct: Initial Review (IR) | 2021-08-26 | Cus – requirement to provide a response to deficiency notice
120751228 | 384 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
120751228 | 384 | Conduct: Initial Review (IR) | 2021-10-01 | Customer – requirement to provide corrected information
120751228 | 384 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – addressing project volume surge
120751228 | 384 | Conduct: Initial Review (IR) | 2021-10-21 | Project Management – requiring more detailed review
120751228 | 384 | Conduct: Initial Review (IR) | 2021-07-22 | Cus – requirement to provide a response to deficiency notice
120751228 | 384 | Conduct: Initial Review (IR) | 2021-08-05 | Cus – requirement to provide a response to deficiency notice
120751228 | 384 | Conduct: Initial Review (IR) | 2021-08-26 | Cus – requirement to provide a response to deficiency notice
120751228 | 384 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
120751228 | 384 | Conduct: Initial Review (IR) | 2021-10-01 | Customer – requirement to provide corrected information
120751228 | 384 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – addressing project volume surge
120751228 | 384 | Conduct: Initial Review (IR) | 2021-10-21 | Project Management – requiring more detailed review
120752027 | 385 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120752027 | 385 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
120752027 | 385 | Conduct: Initial Review (IR) | 2021-05-28 | Customer – requirement to provide corrected information
120752027 | 385 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120753509 | 386 | Conduct: Initial Review (IR) | 2021-05-18 | Engineering – requiring more detailed review
120753509 | 386 | Conduct: Initial Review (IR) | 2021-05-25 | Project Management – addressing a human error
120753509 | 386 | Conduct: Initial Review (IR) | 2021-06-02 | Project Management – requiring more detailed review
120753598 | 387 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120753598 | 387 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120753598 | 387 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120756037 | 388 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – addressing project volume surge
120756037 | 388 | Conduct: Initial Review (IR) | 2021-06-03 | Engineering – requiring more detailed review
120756037 | 388 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120756037 | 388 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120756037 | 388 | Conduct: Initial Review (IR) | 2021-08-09 | Engineering – requiring more detailed review
120756037 | 388 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – addressing project volume surge
120756037 | 388 | Conduct: Initial Review (IR) | 2021-06-03 | Engineering – requiring more detailed review
120756037 | 388 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120756037 | 388 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120756037 | 388 | Conduct: Initial Review (IR) | 2021-08-09 | Engineering – requiring more detailed review
120756037 | 388 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – addressing project volume surge
120756037 | 388 | Conduct: Initial Review (IR) | 2021-06-03 | Engineering – requiring more detailed review
120756037 | 388 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120756037 | 388 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120756037 | 388 | Conduct: Initial Review (IR) | 2021-08-09 | Engineering – requiring more detailed review
120756234 | 389 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – addressing project volume surge
120756234 | 389 | Conduct: Initial Review (IR) | 2021-06-03 | Engineering – requiring more detailed review
120756234 | 389 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120756234 | 389 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120756234 | 389 | Conduct: Initial Review (IR) | 2021-08-09 | Engineering – requiring more detailed review
120756234 | 389 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – addressing project volume surge
120756234 | 389 | Conduct: Initial Review (IR) | 2021-06-03 | Engineering – requiring more detailed review
120756234 | 389 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120756234 | 389 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120756234 | 389 | Conduct: Initial Review (IR) | 2021-08-09 | Engineering – requiring more detailed review
120756234 | 389 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – addressing project volume surge
120756234 | 389 | Conduct: Initial Review (IR) | 2021-06-03 | Engineering – requiring more detailed review
120756234 | 389 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120756234 | 389 | Conduct: Initial Review (IR) | 2021-07-09 | Engineering – requiring more detailed review
120756234 | 389 | Conduct: Initial Review (IR) | 2021-08-09 | Engineering – requiring more detailed review
120757637 | 390 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120757637 | 390 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120758691 | 391 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120758691 | 391 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120760235 | 392 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requesting an extension
120764186 | 393 | Conduct: Initial Review (IR) | 2021-06-03 | Cus – requirement to provide a response to deficiency notice
120764186 | 393 | Conduct: Initial Review (IR) | 2021-06-10 | Cus – requirement to provide a response to deficiency notice
120764186 | 393 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120766049 | 394 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120766049 | 394 | Conduct: Initial Review (IR) | 2021-06-02 | Project Management – requiring more detailed review
120766049 | 394 | Conduct: Initial Review (IR) | 2021-06-09 | Project Management – requiring more detailed review
120769672 | 395 | Conduct: Initial Review (IR) | 2021-05-07 | Cus – requirement to provide a response to deficiency notice
120769672 | 395 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120769672 | 395 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120769672 | 395 | Conduct: Initial Review (IR) | 2021-05-28 | Customer – requirement to provide corrected information
120769672 | 395 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120769672 | 395 | Conduct: Initial Review (IR) | 2021-06-14 | Customer – requirement to provide corrected information
120769672 | 395 | Conduct: Initial Review (IR) | 2021-06-21 | Customer – requirement to provide corrected information
120769672 | 395 | Conduct: Initial Review (IR) | 2021-06-28 | Customer – requirement to provide corrected information
120770205 | 396 | Conduct: Initial Review (IR) | 2021-05-07 | Cus – requirement to provide a response to deficiency notice
120770205 | 396 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120770205 | 396 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120770205 | 396 | Conduct: Initial Review (IR) | 2021-05-28 | Customer – requirement to provide corrected information
120770205 | 396 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120770205 | 396 | Conduct: Initial Review (IR) | 2021-06-14 | Customer – requirement to provide corrected information
120770205 | 396 | Conduct: Initial Review (IR) | 2021-06-21 | Customer – requirement to provide corrected information
120770524 | 397 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120770629 | 398 | Conduct: Initial Review (IR) | 2021-05-14 | Cus – requirement to provide a response to deficiency notice
120772942 | 399 | Conduct: Initial Review (IR) | 2021-06-08 | Engineering – addressing project volume surge
120772942 | 399 | Conduct: Initial Review (IR) | 2021-06-15 | Engineering – requiring more detailed review
120772942 | 399 | Conduct: Initial Review (IR) | 2021-06-08 | Engineering – addressing project volume surge
120772942 | 399 | Conduct: Initial Review (IR) | 2021-06-15 | Engineering – requiring more detailed review
120772942 | 399 | Conduct: Initial Review (IR) | 2021-06-08 | Engineering – addressing project volume surge
120772942 | 399 | Conduct: Initial Review (IR) | 2021-06-15 | Engineering – requiring more detailed review
120792958 | 400 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120792958 | 400 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120792958 | 400 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
120792958 | 400 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120792958 | 400 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120796075 | 401 | Tender Draft IA | 2021-08-06 | Cus – requirement to provide a response to deficiency notice
120796075 | 401 | Tender Draft IA | 2021-08-06 | Cus – requirement to provide a response to deficiency notice
120796075 | 401 | Tender Draft IA | 2021-08-06 | Cus – requirement to provide a response to deficiency notice
120803445 | 402 | Conduct: Screens Q and R | 2021-06-04 | Engineering – requiring more detailed review
120803445 | 402 | Conduct: SIS | 2021-09-21 | Engineering – requiring more detailed review
120803445 | 402 | Conduct: Screens Q and R | 2021-06-04 | Engineering – requiring more detailed review
120803445 | 402 | Conduct: SIS | 2021-09-21 | Engineering – requiring more detailed review
120803445 | 402 | Conduct: Screens Q and R | 2021-06-04 | Engineering – requiring more detailed review
120803445 | 402 | Conduct: SIS | 2021-09-21 | Engineering – requiring more detailed review
120803932 | 403 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-08-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-09-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-10-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-08-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-09-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-10-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-11-30 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-12-29 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-08-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-09-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-10-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-11-30 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-12-29 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2022-01-08 | Engineering – addressing project volume surge
120803932 | 403 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-08-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-09-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-10-28 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-11-30 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2021-12-29 | Cus – requirement to provide a response to deficiency notice
120803932 | 403 | Conduct: Initial Review (IR) | 2022-01-08 | Engineering – addressing project volume surge
120804094 | 404 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
120804094 | 404 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120804094 | 404 | Conduct: Initial Review (IR) | 2021-06-03 | Cus – requirement to provide a response to deficiency notice
120804094 | 404 | Conduct: Initial Review (IR) | 2021-06-10 | Cus – requirement to provide a response to deficiency notice
120804094 | 404 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120804099 | 405 | Conduct: Initial Review (IR) | 2021-05-18 | Engineering – requiring more detailed review
120804099 | 405 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120804099 | 405 | Conduct: Initial Review (IR) | 2021-05-11 | Project Management – addressing a human error
120804288 | 406 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120804288 | 406 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requirement to provide corrected information
120804601 | 407 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering – requiring more detailed review
120805475 | 408 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120805475 | 408 | Conduct: Initial Review (IR) | 2021-06-03 | Cus – requirement to provide a response to deficiency notice
120806576 | 409 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120806576 | 409 | Conduct: Initial Review (IR) | 2021-05-25 | Cus – requirement to provide a response to deficiency notice
120806576 | 409 | Conduct: Initial Review (IR) | 2021-06-02 | Cus – requirement to provide a response to deficiency notice
120806576 | 409 | Conduct: Initial Review (IR) | 2021-06-09 | Cus – requirement to provide a response to deficiency notice
120806576 | 409 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120807656 | 410 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
120807656 | 410 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120807656 | 410 | Conduct: Initial Review (IR) | 2021-07-13 | Engineering – requiring more detailed review
120807656 | 410 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
120807656 | 410 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120807656 | 410 | Conduct: Initial Review (IR) | 2021-07-13 | Engineering – requiring more detailed review
120807656 | 410 | Conduct: Initial Review (IR) | 2021-06-21 | Engineering – requiring more detailed review
120807656 | 410 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120807656 | 410 | Conduct: Initial Review (IR) | 2021-07-13 | Engineering – requiring more detailed review
120808457 | 411 | Conduct: Initial Review (IR) | 2021-05-20 | Engineering – requiring more detailed review
120808457 | 411 | Conduct: Initial Review (IR) | 2021-05-27 | Engineering – requiring more detailed review
120808781 | 412 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
120808781 | 412 | Conduct: Initial Review (IR) | 2021-06-01 | Project Management - addressing project volume surge
120809274 | 413 | Conduct: Initial Review (IR) | 2021-05-18 | Cus – requirement to provide a response to deficiency notice
120809274 | 413 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120809274 | 413 | Conduct: Initial Review (IR) | 2021-05-25 | Customer – requirement to provide corrected information
120809274 | 413 | Conduct: Initial Review (IR) | 2021-06-02 | Customer – requirement to provide corrected information
120809274 | 413 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120809811 | 414 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120809811 | 414 | Conduct: Initial Review (IR) | 2021-06-14 | Project Management – requiring more detailed review
120809811 | 414 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120809811 | 414 | Conduct: Initial Review (IR) | 2021-06-14 | Project Management – requiring more detailed review
120809811 | 414 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120809811 | 414 | Conduct: Initial Review (IR) | 2021-06-14 | Project Management – requiring more detailed review
120811257 | 415 | Conduct: Initial Review (IR) | 2021-06-10 | Cus – requirement to provide a response to deficiency notice
120811257 | 415 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120811257 | 415 | Conduct: Initial Review (IR) | 2021-06-24 | Cus – requirement to provide a response to deficiency notice
120811257 | 415 | Conduct: Initial Review (IR) | 2021-07-01 | Cus – requirement to provide a response to deficiency notice
120811257 | 415 | Conduct: Initial Review (IR) | 2021-05-19 | Customer – requirement to provide corrected information
120811257 | 415 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120811257 | 415 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
120812614 | 416 | Conduct: Initial Review (IR) | 2021-05-19 | Cus – requirement to provide a response to deficiency notice
120812614 | 416 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120812614 | 416 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
120813323 | 417 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120813323 | 417 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120813323 | 417 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120815687 | 418 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120815687 | 418 | Conduct: Initial Review (IR) | 2021-05-19 | Project Management - addressing project volume surge
120816753 | 419 | Conduct: Initial Review (IR) | 2021-07-15 | Engineering – requiring more detailed review
120816753 | 419 | Conduct: Initial Review (IR) | 2021-06-17 | Project Management – requiring more detailed review
120816753 | 419 | Conduct: Initial Review (IR) | 2021-07-01 | Project Management – requiring more detailed review
120816753 | 419 | Conduct: Initial Review (IR) | 2021-07-15 | Engineering – requiring more detailed review
120816753 | 419 | Conduct: Initial Review (IR) | 2021-06-17 | Project Management – requiring more detailed review
120816753 | 419 | Conduct: Initial Review (IR) | 2021-07-01 | Project Management – requiring more detailed review
120816753 | 419 | Conduct: Initial Review (IR) | 2021-07-15 | Engineering – requiring more detailed review
120816753 | 419 | Conduct: Initial Review (IR) | 2021-06-17 | Project Management – requiring more detailed review
120816753 | 419 | Conduct: Initial Review (IR) | 2021-07-01 | Project Management – requiring more detailed review
120817699 | 420 | Conduct: Initial Review (IR) | 2021-05-18 | Engineering – requiring more detailed review
120820175 | 421 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120820175 | 421 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120820175 | 421 | Conduct: Initial Review (IR) | 2021-05-27 | Project Management - addressing emergency power outages
120822162 | 422 | Conduct: Initial Review (IR) | 2021-05-24 | Engineering – requiring more detailed review
120822482 | 423 | Conduct: Supplemental Review (SR) | 2021-06-24 | Engineering – addressing project volume surge
120822482 | 423 | Conduct: Supplemental Review (SR) | 2021-07-09 | Engineering – addressing project volume surge
120822482 | 423 | Conduct: Supplemental Review (SR) | 2021-06-24 | Engineering – addressing project volume surge
120822482 | 423 | Conduct: Supplemental Review (SR) | 2021-07-09 | Engineering – addressing project volume surge
120822482 | 423 | Conduct: Supplemental Review (SR) | 2021-06-24 | Engineering – addressing project volume surge
120822482 | 423 | Conduct: Supplemental Review (SR) | 2021-07-09 | Engineering – addressing project volume surge
120822490 | 424 | Conduct: Initial Review (IR) | 2021-05-13 | Cus – requirement to provide a response to deficiency notice
120823102 | 425 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120823102 | 425 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120823102 | 425 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120823102 | 425 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120823102 | 425 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120823102 | 425 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120823102 | 425 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120823102 | 425 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120823102 | 425 | Conduct: Initial Review (IR) | 2021-06-30 | Engineering – requiring more detailed review
120823257 | 426 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120823257 | 426 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120823257 | 426 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – requiring more detailed review
120823257 | 426 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120823257 | 426 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120823257 | 426 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – requiring more detailed review
120823257 | 426 | Conduct: Initial Review (IR) | 2021-06-09 | Engineering – requiring more detailed review
120823257 | 426 | Conduct: Initial Review (IR) | 2021-06-23 | Engineering – requiring more detailed review
120823257 | 426 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – requiring more detailed review
120823637 | 427 | Conduct: Initial Review (IR) | 2021-05-18 | Customer
120823637 | 427 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120823637 | 427 | Conduct: Supplemental Review (SR) | 2021-08-20 | Engineering – requiring more detailed review
120823637 | 427 | Conduct: Initial Review (IR) | 2021-05-18 | Customer
120823637 | 427 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120823637 | 427 | Conduct: Supplemental Review (SR) | 2021-08-20 | Engineering – requiring more detailed review
120823637 | 427 | Conduct: Initial Review (IR) | 2021-05-18 | Customer
120823637 | 427 | Conduct: Initial Review (IR) | 2021-05-25 | Engineering – requiring more detailed review
120823637 | 427 | Conduct: Supplemental Review (SR) | 2021-08-20 | Engineering – requiring more detailed review
120824355 | 428 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120824355 | 428 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
120825142 | 429 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120825142 | 429 | Conduct: Initial Review (IR) | 2021-06-18 | Engineering – requiring more detailed review
120825142 | 429 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120825142 | 429 | Conduct: Initial Review (IR) | 2021-07-02 | Engineering – requiring more detailed review
120825142 | 429 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120825142 | 429 | Conduct: Initial Review (IR) | 2021-06-18 | Engineering – requiring more detailed review
120825142 | 429 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120825142 | 429 | Conduct: Initial Review (IR) | 2021-07-02 | Engineering – requiring more detailed review
120825142 | 429 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120825142 | 429 | Conduct: Initial Review (IR) | 2021-06-18 | Engineering – requiring more detailed review
120825142 | 429 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
120825142 | 429 | Conduct: Initial Review (IR) | 2021-07-02 | Engineering – requiring more detailed review
120826026 | 430 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120826026 | 430 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120826026 | 430 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120826026 | 430 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120827715 | 431 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120827715 | 431 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120827715 | 431 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120827715 | 431 | Conduct: Initial Review (IR) | 2021-06-11 | Customer – requirement to provide corrected information
120831493 | 432 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120831493 | 432 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120831493 | 432 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120831493 | 432 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120831493 | 432 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
120831806 | 433 | Conduct: Initial Review (IR) | 2021-06-08 | Customer – requirement to provide corrected information
120837566 | 434 | Conduct: SIS | 2021-05-10 | Cus – requirement to provide a response to deficiency notice
120837566 | 434 | Conduct: Initial Review (IR) | 2021-04-30 | Project Management – requiring more detailed review
120838405 | 435 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120838405 | 435 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
120838405 | 435 | Conduct: Initial Review (IR) | 2021-05-28 | Customer – requirement to provide corrected information
120838405 | 435 | Conduct: Initial Review (IR) | 2021-06-07 | Customer – requirement to provide corrected information
120839429 | 436 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120839429 | 436 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120839429 | 436 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120839429 | 436 | Conduct: Initial Review (IR) | 2021-05-21 | Customer – requirement to provide corrected information
120840508 | 437 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120840508 | 437 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120840508 | 437 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120840508 | 437 | Conduct: Initial Review (IR) | 2021-06-14 | Customer – requirement to provide corrected information
120841745 | 438 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
120841745 | 438 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
120841745 | 438 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
120841745 | 438 | Conduct: Initial Review (IR) | 2021-06-04 | Customer – requirement to provide corrected information
120841815 | 439 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120846340 | 440 | Conduct: Initial Review (IR) | 2021-07-06 | Cus – requirement to provide a response to deficiency notice
120846340 | 440 | Conduct: Initial Review (IR) | 2021-06-28 | Customer – requesting an extension
120847643 | 441 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120847643 | 441 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120847643 | 441 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120847648 | 442 | Conduct: Initial Review (IR) | 2021-05-28 | Customer – requirement to provide corrected information
120850237 | 443 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120851262 | 444 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120851262 | 444 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120851262 | 444 | Conduct: Initial Review (IR) | 2021-07-27 | Cus – requirement to provide a response to deficiency notice
120851262 | 444 | Conduct: Initial Review (IR) | 2021-07-09 | Customer – requirement to provide corrected information
120851262 | 444 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120851262 | 444 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120851262 | 444 | Conduct: Initial Review (IR) | 2021-07-27 | Cus – requirement to provide a response to deficiency notice
120851262 | 444 | Conduct: Initial Review (IR) | 2021-07-09 | Customer – requirement to provide corrected information
120851262 | 444 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120851262 | 444 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120851262 | 444 | Conduct: Initial Review (IR) | 2021-07-27 | Cus – requirement to provide a response to deficiency notice
120851262 | 444 | Conduct: Initial Review (IR) | 2021-07-09 | Customer – requirement to provide corrected information
120851817 | 445 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120851817 | 445 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120851817 | 445 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120851817 | 445 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120852078 | 446 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120852954 | 447 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120852954 | 447 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120852954 | 447 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120852954 | 447 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120853133 | 448 | Conduct: Initial Review (IR) | 2021-05-20 | Cus – requirement to provide a response to deficiency notice
120853133 | 448 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120853133 | 448 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120853133 | 448 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120853133 | 448 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120853913 | 449 | Conduct: Initial Review (IR) | 2021-05-24 | Cus – requirement to provide a response to deficiency notice
120853913 | 449 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120853913 | 449 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
120853913 | 449 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
120853913 | 449 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
120853913 | 449 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
120853913 | 449 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
120858177 | 450 | Conduct: Initial Review (IR) | 2021-05-26 | Engineering – addressing project volume surge
120859060 | 451 | Conduct: Initial Review (IR) | 2021-05-25 | Customer – requesting an extension
120859231 | 452 | Conduct: Initial Review (IR) | 2021-05-21 | Cus – requirement to provide a response to deficiency notice
120859231 | 452 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120859231 | 452 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120859231 | 452 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120863572 | 453 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120863572 | 453 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120863572 | 453 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
120864590 | 454 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120865092 | 455 | Conduct: Initial Review (IR) | 2021-06-16 | Cus – requirement to provide a response to deficiency notice
120865801 | 456 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120865801 | 456 | Conduct: Initial Review (IR) | 2021-06-03 | Cus – requirement to provide a response to deficiency notice
120865801 | 456 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120865801 | 456 | Conduct: Initial Review (IR) | 2021-06-24 | Cus – requirement to provide a response to deficiency notice
120865801 | 456 | Conduct: Initial Review (IR) | 2021-06-10 | Project Management - addressing project volume surge
120866052 | 457 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120867210 | 458 | Conduct: Initial Review (IR) | 2021-06-23 | Project Management - addressing project volume surge
120867210 | 458 | Conduct: Initial Review (IR) | 2021-06-23 | Project Management - addressing project volume surge
120867210 | 458 | Conduct: Initial Review (IR) | 2021-06-23 | Project Management - addressing project volume surge
120868285 | 459 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120868285 | 459 | Conduct: Initial Review (IR) | 2021-06-03 | Cus – requirement to provide a response to deficiency notice
120868285 | 459 | Conduct: Initial Review (IR) | 2021-06-10 | Cus – requirement to provide a response to deficiency notice
120868285 | 459 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120869063 | 460 | Conduct: Initial Review (IR) | 2021-06-03 | Engineering – requiring more detailed review
120869063 | 460 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120869063 | 460 | Conduct: Initial Review (IR) | 2021-05-26 | Project Management – addressing a human error
120869498 | 461 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
120869498 | 461 | Conduct: Initial Review (IR) | 2021-08-19 | Cus – requirement to provide a response to deficiency notice
120869498 | 461 | Conduct: Initial Review (IR) | 2021-09-02 | Cus – requirement to provide a response to deficiency notice
120869498 | 461 | Conduct: Initial Review (IR) | 2021-07-22 | Engineering – requiring more detailed review
120869498 | 461 | Conduct: Initial Review (IR) | 2021-09-13 | Project Management – requiring more detailed review
120869498 | 461 | Conduct: Initial Review (IR) | 2021-08-19 | Cus – requirement to provide a response to deficiency notice
120869498 | 461 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
120869498 | 461 | Conduct: Initial Review (IR) | 2021-09-02 | Cus – requirement to provide a response to deficiency notice
120869498 | 461 | Conduct: Initial Review (IR) | 2021-07-22 | Engineering – requiring more detailed review
120869498 | 461 | Conduct: Initial Review (IR) | 2021-09-13 | Project Management – requiring more detailed review
120869498 | 461 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
120869498 | 461 | Conduct: Initial Review (IR) | 2021-08-19 | Cus – requirement to provide a response to deficiency notice
120869498 | 461 | Conduct: Initial Review (IR) | 2021-09-02 | Cus – requirement to provide a response to deficiency notice
120869498 | 461 | Conduct: Initial Review (IR) | 2021-07-22 | Engineering – requiring more detailed review
120869498 | 461 | Conduct: Initial Review (IR) | 2021-09-13 | Project Management – requiring more detailed review
120870295 | 462 | Conduct: Initial Review (IR) | 2021-05-24 | Customer – requirement to provide corrected information
120870295 | 462 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
120875063 | 463 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120875063 | 463 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120875063 | 463 | Conduct: Initial Review (IR) | 2021-06-17 | Engineering – requiring more detailed review
120875131 | 464 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120875131 | 464 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120875131 | 464 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120875910 | 465 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
120875910 | 465 | Conduct: Initial Review (IR) | 2021-06-17 | Customer – requirement to provide corrected information
120875910 | 465 | Conduct: Initial Review (IR) | 2021-07-01 | Customer – requirement to provide corrected information
120875910 | 465 | Conduct: Initial Review (IR) | 2021-07-01 | Customer – requirement to provide corrected information
120875910 | 465 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
120875910 | 465 | Conduct: Initial Review (IR) | 2021-06-17 | Customer – requirement to provide corrected information
120875910 | 465 | Conduct: Initial Review (IR) | 2021-07-14 | Engineering – requiring more detailed review
120875910 | 465 | Conduct: Initial Review (IR) | 2021-07-14 | Engineering – requiring more detailed review
120875910 | 465 | Conduct: Initial Review (IR) | 2021-07-01 | Customer – requirement to provide corrected information
120875910 | 465 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
120875910 | 465 | Conduct: Initial Review (IR) | 2021-06-17 | Customer – requirement to provide corrected information
120875910 | 465 | Conduct: Initial Review (IR) | 2021-07-14 | Engineering – requiring more detailed review
120875910 | 465 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
120875910 | 465 | Conduct: Initial Review (IR) | 2021-07-01 | Customer – requirement to provide corrected information
120875910 | 465 | Conduct: Initial Review (IR) | 2021-06-17 | Customer – requirement to provide corrected information
120875910 | 465 | Conduct: Initial Review (IR) | 2021-07-14 | Engineering – requiring more detailed review
120875984 | 466 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120875984 | 466 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120875984 | 466 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120876755 | 467 | Conduct: Initial Review (IR) | 2021-05-26 | Cus – requirement to provide a response to deficiency notice
120876755 | 467 | Conduct: Initial Review (IR) | 2021-06-03 | Cus – requirement to provide a response to deficiency notice
120876755 | 467 | Conduct: Initial Review (IR) | 2021-06-10 | Cus – requirement to provide a response to deficiency notice
120876755 | 467 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120876953 | 468 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
120876953 | 468 | Conduct: Initial Review (IR) | 2021-07-14 | Engineering – addressing project volume surge
120876953 | 468 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
120876953 | 468 | Conduct: Initial Review (IR) | 2021-07-14 | Engineering – addressing project volume surge
120876953 | 468 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
120876953 | 468 | Conduct: Initial Review (IR) | 2021-07-14 | Engineering – addressing project volume surge
120881315 | 469 | Conduct: Initial Review (IR) | 2021-06-17 | Customer – requirement to provide corrected information
120881315 | 469 | Conduct: Initial Review (IR) | 2021-06-10 | Engineering – addressing project volume surge
120881315 | 469 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – addressing project volume surge
120881315 | 469 | Conduct: Initial Review (IR) | 2021-07-01 | Engineering – requiring more detailed review
120881315 | 469 | Conduct: Initial Review (IR) | 2021-06-17 | Customer – requirement to provide corrected information
120881315 | 469 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – addressing project volume surge
120881315 | 469 | Conduct: Initial Review (IR) | 2021-06-10 | Engineering – addressing project volume surge
120881315 | 469 | Conduct: Initial Review (IR) | 2021-07-01 | Engineering – requiring more detailed review
120881315 | 469 | Conduct: Initial Review (IR) | 2021-06-17 | Customer – requirement to provide corrected information
120881315 | 469 | Conduct: Initial Review (IR) | 2021-06-10 | Engineering – addressing project volume surge
120881315 | 469 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – addressing project volume surge
120881315 | 469 | Conduct: Initial Review (IR) | 2021-07-01 | Engineering – requiring more detailed review
120882957 | 470 | Conduct: Initial Review (IR) | 2021-07-08 | Engineering – requiring more detailed review
120883305 | 471 | Conduct: Initial Review (IR) | 2021-06-03 | Cus – requirement to provide a response to deficiency notice
120883305 | 471 | Conduct: Initial Review (IR) | 2021-06-10 | Cus – requirement to provide a response to deficiency notice
120884233 | 472 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120884233 | 472 | Conduct: Initial Review (IR) | 2021-06-01 | Customer – requirement to provide corrected information
120884233 | 472 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
120888631 | 473 | Conduct: Initial Review (IR) | 2021-05-26 | Customer – requirement to provide corrected information
120888631 | 473 | Conduct: Initial Review (IR) | 2021-06-03 | Customer – requirement to provide corrected information
120888831 | 474 | Conduct: Initial Review (IR) | 2021-06-09 | Project Management – addressing a human error
120888831 | 474 | Conduct: Initial Review (IR) | 2021-06-09 | Project Management – addressing a human error
120888831 | 474 | Conduct: Initial Review (IR) | 2021-06-09 | Project Management – addressing a human error
120889784 | 475 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
120889784 | 475 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
120889784 | 475 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
120890756 | 476 | Conduct: Initial Review (IR) | 2021-07-09 | Cus – requirement to provide a response to deficiency notice
120890756 | 476 | Conduct: Initial Review (IR) | 2021-07-16 | Cus – requirement to provide a response to deficiency notice
120890756 | 476 | Conduct: Initial Review (IR) | 2021-07-23 | Cus – requirement to provide a response to deficiency notice
120890756 | 476 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
120890756 | 476 | Conduct: Initial Review (IR) | 2021-06-22 | Customer – requirement to provide corrected information
120890756 | 476 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
120890756 | 476 | Conduct: Initial Review (IR) | 2021-06-08 | Engineering – requiring more detailed review
120890756 | 476 | Conduct: Initial Review (IR) | 2021-07-30 | Engineering – requiring more detailed review
120890756 | 476 | Conduct: Initial Review (IR) | 2021-08-13 | Engineering – requiring more detailed review
120890756 | 476 | Conduct: Initial Review (IR) | 2021-08-20 | Engineering – requiring more detailed review
120890756 | 476 | Conduct: Initial Review (IR) | 2021-07-09 | Cus – requirement to provide a response to deficiency notice
120890756 | 476 | Conduct: Initial Review (IR) | 2021-07-16 | Cus – requirement to provide a response to deficiency notice
120890756 | 476 | Conduct: Initial Review (IR) | 2021-07-23 | Cus – requirement to provide a response to deficiency notice
120890756 | 476 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
120890756 | 476 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
120890756 | 476 | Conduct: Initial Review (IR) | 2021-06-22 | Customer – requirement to provide corrected information
120890756 | 476 | Conduct: Initial Review (IR) | 2021-07-30 | Engineering – requiring more detailed review
120890756 | 476 | Conduct: Initial Review (IR) | 2021-06-08 | Engineering – requiring more detailed review
120890756 | 476 | Conduct: Initial Review (IR) | 2021-08-13 | Engineering – requiring more detailed review
120890756 | 476 | Conduct: Initial Review (IR) | 2021-08-20 | Engineering – requiring more detailed review
120890756 | 476 | Conduct: Initial Review (IR) | 2021-07-09 | Cus – requirement to provide a response to deficiency notice
120890756 | 476 | Conduct: Initial Review (IR) | 2021-07-16 | Cus – requirement to provide a response to deficiency notice
120890756 | 476 | Conduct: Initial Review (IR) | 2021-07-23 | Cus – requirement to provide a response to deficiency notice
120890756 | 476 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
120890756 | 476 | Conduct: Initial Review (IR) | 2021-06-22 | Customer – requirement to provide corrected information
120890756 | 476 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
120890756 | 476 | Conduct: Initial Review (IR) | 2021-06-08 | Engineering – requiring more detailed review
120890756 | 476 | Conduct: Initial Review (IR) | 2021-07-30 | Engineering – requiring more detailed review
120890756 | 476 | Conduct: Initial Review (IR) | 2021-08-13 | Engineering – requiring more detailed review
120890756 | 476 | Conduct: Initial Review (IR) | 2021-08-20 | Engineering – requiring more detailed review
120891608 | 477 | Conduct: Initial Review (IR) | 2021-06-01 | Cus – requirement to provide a response to deficiency notice
120891608 | 477 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120891608 | 477 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120893179 | 478 | Conduct: Initial Review (IR) | 2021-05-27 | Cus – requirement to provide a response to deficiency notice
120893179 | 478 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120898614 | 479 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120901108 | 480 | Conduct: Initial Review (IR) | 2021-05-28 | Cus – requirement to provide a response to deficiency notice
120901108 | 480 | Conduct: Initial Review (IR) | 2021-06-07 | Cus – requirement to provide a response to deficiency notice
120901108 | 480 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120905127 | 481 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120905127 | 481 | Conduct: Initial Review (IR) | 2021-06-22 | Project Management - addressing project volume surge
120907409 | 482 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
120907409 | 482 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120908889 | 483 | Conduct: Supplemental Review (SR) | 2021-07-16 | Engineering – requiring more detailed review
120908889 | 483 | Conduct: Supplemental Review (SR) | 2021-07-16 | Engineering – requiring more detailed review
120908889 | 483 | Conduct: Supplemental Review (SR) | 2021-07-16 | Engineering – requiring more detailed review
120921417 | 484 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requesting an extension
120921417 | 484 | Conduct: Initial Review (IR) | 2021-06-08 | Project Management – requiring more detailed review
120925994 | 485 | Conduct: Initial Review (IR) | 2021-06-03 | Cus – requirement to provide a response to deficiency notice
120925994 | 485 | Conduct: Initial Review (IR) | 2021-06-10 | Cus – requirement to provide a response to deficiency notice
120925994 | 485 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120926268 | 486 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
120926268 | 486 | Conduct: Initial Review (IR) | 2021-07-02 | Customer – requesting an extension
120926846 | 487 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requesting an extension
120928902 | 488 | Conduct: Initial Review (IR) | 2021-06-10 | Customer – requirement to provide corrected information
120929894 | 489 | Conduct: Initial Review (IR) | 2021-06-24 | Cus – requirement to provide a response to deficiency notice
120929894 | 489 | Conduct: Initial Review (IR) | 2021-07-01 | Cus – requirement to provide a response to deficiency notice
120929894 | 489 | Conduct: Initial Review (IR) | 2021-07-09 | Cus – requirement to provide a response to deficiency notice
120931208 | 490 | Conduct: Initial Review (IR) | 2021-07-16 | Engineering – requiring more detailed review
120931208 | 490 | Conduct: Initial Review (IR) | 2021-07-16 | Engineering – requiring more detailed review
120931208 | 490 | Conduct: Initial Review (IR) | 2021-07-16 | Engineering – requiring more detailed review
120931225 | 491 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
120932622 | 492 | Conduct: Initial Review (IR) | 2021-06-14 | Engineering – requiring more detailed review
120932622 | 492 | Conduct: Initial Review (IR) | 2021-06-28 | Engineering – requiring more detailed review
120932622 | 492 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120932622 | 492 | Conduct: Initial Review (IR) | 2021-07-13 | Engineering – requiring more detailed review
120932622 | 492 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120932622 | 492 | Conduct: Initial Review (IR) | 2021-07-13 | Engineering – requiring more detailed review
120932622 | 492 | Conduct: Initial Review (IR) | 2021-06-14 | Engineering – requiring more detailed review
120932622 | 492 | Conduct: Initial Review (IR) | 2021-06-28 | Engineering – requiring more detailed review
120932622 | 492 | Conduct: Initial Review (IR) | 2021-06-14 | Engineering – requiring more detailed review
120932622 | 492 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
120932622 | 492 | Conduct: Initial Review (IR) | 2021-06-28 | Engineering – requiring more detailed review
120932622 | 492 | Conduct: Initial Review (IR) | 2021-07-13 | Engineering – requiring more detailed review
120933574 | 493 | Conduct: Initial Review (IR) | 2021-06-04 | Cus – requirement to provide a response to deficiency notice
120933574 | 493 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120937061 | 494 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
120938235 | 495 | Conduct: Initial Review (IR) | 2021-06-28 | Cus – requirement to provide a response to deficiency notice
120938235 | 495 | Conduct: Initial Review (IR) | 2021-07-06 | Cus – requirement to provide a response to deficiency notice
120938235 | 495 | Conduct: Initial Review (IR) | 2021-07-13 | Cus – requirement to provide a response to deficiency notice
120938774 | 496 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120938774 | 496 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120938774 | 496 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120938774 | 496 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120938774 | 496 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
120938774 | 496 | Conduct: Initial Review (IR) | 2021-07-19 | Cus – requirement to provide a response to deficiency notice
120938774 | 496 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
120938774 | 496 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
120938774 | 496 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
120938774 | 496 | Conduct: Initial Review (IR) | 2021-08-16 | Cus – requirement to provide a response to deficiency notice
120938774 | 496 | Conduct: Initial Review (IR) | 2021-08-23 | Cus – requirement to provide a response to deficiency notice
120938774 | 496 | Conduct: Initial Review (IR) | 2021-08-30 | Cus – requirement to provide a response to deficiency notice
120938774 | 496 | Conduct: Initial Review (IR) | 2021-09-07 | Cus – requirement to provide a response to deficiency notice
120939167 | 497 | Conduct: Initial Review (IR) | 2021-06-11 | Cus – requirement to provide a response to deficiency notice
120939167 | 497 | Conduct: Initial Review (IR) | 2021-06-18 | Cus – requirement to provide a response to deficiency notice
120939167 | 497 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
120939167 | 497 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
120939173 | 498 | Conduct: Initial Review (IR) | 2021-06-14 | Cus – requirement to provide a response to deficiency notice
120941425 | 499 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
120943773 | 500 | Conduct: Initial Review (IR) | 2021-07-01 | Cus – requirement to provide a response to deficiency notice
120943773 | 500 | Conduct: Initial Review (IR) | 2021-07-09 | Cus – requirement to provide a response to deficiency notice
120943773 | 500 | Conduct: Initial Review (IR) | 2021-07-16 | Cus – requirement to provide a response to deficiency notice
120943925 | 501 | Conduct: Initial Review (IR) | 2021-06-23 | Cus – requirement to provide a response to deficiency notice
120949009 | 502 | Conduct: Initial Review (IR) | 2021-07-01 | Project Management - addressing project volume surge
120949009 | 502 | Conduct: Initial Review (IR) | 2021-07-01 | Project Management - addressing project volume surge
120949009 | 502 | Conduct: Initial Review (IR) | 2021-07-01 | Project Management - addressing project volume surge
121005409 | 503 | Conduct: Initial Review (IR) | 2021-06-16 | Project Management – addressing a human error
121011976 | 504 | Conduct: Initial Review (IR) | 2021-06-17 | Cus – requirement to provide a response to deficiency notice
121012813 | 505 | Conduct: Initial Review (IR) | 2021-06-09 | Customer – requirement to provide corrected information
121039112 | 506 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requesting an extension
121130249 | 507 | Conduct: Initial Review (IR) | 2021-06-18 | Customer – requirement to provide corrected information
121130249 | 507 | Conduct: Initial Review (IR) | 2021-06-25 | Customer – requirement to provide corrected information
121130249 | 507 | Conduct: Initial Review (IR) | 2021-07-02 | Customer – requirement to provide corrected information
121130249 | 507 | Conduct: Initial Review (IR) | 2021-07-12 | Customer – requirement to provide corrected information
121130249 | 507 | Conduct: Initial Review (IR) | 2021-06-11 | Project Management – addressing a human error
121130249 | 507 | Conduct: Initial Review (IR) | 2021-06-25 | Customer – requirement to provide corrected information
121130249 | 507 | Conduct: Initial Review (IR) | 2021-07-02 | Customer – requirement to provide corrected information
121130249 | 507 | Conduct: Initial Review (IR) | 2021-07-12 | Customer – requirement to provide corrected information
121130249 | 507 | Conduct: Initial Review (IR) | 2021-06-18 | Customer – requirement to provide corrected information
121130249 | 507 | Conduct: Initial Review (IR) | 2021-06-11 | Project Management – addressing a human error
121130249 | 507 | Conduct: Initial Review (IR) | 2021-06-18 | Customer – requirement to provide corrected information
121130249 | 507 | Conduct: Initial Review (IR) | 2021-06-25 | Customer – requirement to provide corrected information
121130249 | 507 | Conduct: Initial Review (IR) | 2021-07-02 | Customer – requirement to provide corrected information
121130249 | 507 | Conduct: Initial Review (IR) | 2021-07-12 | Customer – requirement to provide corrected information
121130249 | 507 | Conduct: Initial Review (IR) | 2021-06-11 | Project Management – addressing a human error
121138825 | 508 | Conduct: Initial Review (IR) | 2021-06-15 | Engineering – requiring more detailed review
121138825 | 508 | Conduct: Initial Review (IR) | 2021-06-15 | Engineering – requiring more detailed review
121138825 | 508 | Conduct: Initial Review (IR) | 2021-06-15 | Engineering – requiring more detailed review
121320903 | 509 | Conduct: Initial Review (IR) | 2021-07-01 | Cus – requirement to provide a response to deficiency notice
121320903 | 509 | Conduct: Initial Review (IR) | 2021-07-09 | Cus – requirement to provide a response to deficiency notice
121322259 | 510 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering – requiring more detailed review
121322442 | 511 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
121322442 | 511 | Conduct: Initial Review (IR) | 2021-06-22 | Customer – requirement to provide corrected information
121322442 | 511 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
121322442 | 511 | Conduct: Initial Review (IR) | 2021-09-16 | Engineering – requiring more detailed review
121322442 | 511 | Conduct: Initial Review (IR) | 2021-09-23 | Engineering – requiring more detailed review
121322442 | 511 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
121322442 | 511 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
121322442 | 511 | Conduct: Initial Review (IR) | 2021-06-22 | Customer – requirement to provide corrected information
121322442 | 511 | Conduct: Initial Review (IR) | 2021-09-16 | Engineering – requiring more detailed review
121322442 | 511 | Conduct: Initial Review (IR) | 2021-09-23 | Engineering – requiring more detailed review
121322442 | 511 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
121322442 | 511 | Conduct: Initial Review (IR) | 2021-06-15 | Customer – requirement to provide corrected information
121322442 | 511 | Conduct: Initial Review (IR) | 2021-06-22 | Customer – requirement to provide corrected information
121322442 | 511 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
121322442 | 511 | Conduct: Initial Review (IR) | 2021-09-16 | Engineering – requiring more detailed review
121322442 | 511 | Conduct: Initial Review (IR) | 2021-09-23 | Engineering – requiring more detailed review
121324169 | 512 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
121324169 | 512 | Conduct: Initial Review (IR) | 2021-07-14 | Customer – requesting an extension
121324169 | 512 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
121324169 | 512 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
121324169 | 512 | Conduct: Initial Review (IR) | 2021-08-04 | Engineering – requiring more detailed review
121324169 | 512 | Conduct: Initial Review (IR) | 2021-08-18 | Engineering – requiring more detailed review
121324169 | 512 | Conduct: Initial Review (IR) | 2021-08-25 | Engineering – requiring more detailed review
121324169 | 512 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
121324169 | 512 | Conduct: Initial Review (IR) | 2021-07-14 | Customer – requesting an extension
121324169 | 512 | Conduct: Initial Review (IR) | 2021-08-04 | Engineering – requiring more detailed review
121324169 | 512 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
121324169 | 512 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
121324169 | 512 | Conduct: Initial Review (IR) | 2021-08-18 | Engineering – requiring more detailed review
121324169 | 512 | Conduct: Initial Review (IR) | 2021-08-25 | Engineering – requiring more detailed review
121324169 | 512 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
121324169 | 512 | Conduct: Initial Review (IR) | 2021-07-14 | Customer – requesting an extension
121324169 | 512 | Conduct: Initial Review (IR) | 2021-06-22 | Engineering – requiring more detailed review
121324169 | 512 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
121324169 | 512 | Conduct: Initial Review (IR) | 2021-08-04 | Engineering – requiring more detailed review
121324169 | 512 | Conduct: Initial Review (IR) | 2021-08-18 | Engineering – requiring more detailed review
121324169 | 512 | Conduct: Initial Review (IR) | 2021-08-25 | Engineering – requiring more detailed review
121326382 | 513 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
121326382 | 513 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
121326382 | 513 | Conduct: Initial Review (IR) | 2021-07-07 | Cus – requirement to provide a response to deficiency notice
121328387 | 514 | Conduct: Initial Review (IR) | 2021-06-22 | Cus – requirement to provide a response to deficiency notice
121328387 | 514 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
121333375 | 515 | Conduct: Initial Review (IR) | 2021-07-22 | Cus – requirement to provide a response to deficiency notice
121333375 | 515 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-06-23 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-06-30 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-07-08 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-07-15 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-07-29 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-08-12 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-08-19 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-08-05 | Project Management - addressing project volume surge
121333375 | 515 | Conduct: Initial Review (IR) | 2021-07-22 | Cus – requirement to provide a response to deficiency notice
121333375 | 515 | Conduct: Initial Review (IR) | 2021-07-29 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-06-30 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-07-08 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-07-15 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-06-23 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-08-12 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-08-19 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-08-05 | Project Management - addressing project volume surge
121333375 | 515 | Conduct: Initial Review (IR) | 2021-07-22 | Cus – requirement to provide a response to deficiency notice
121333375 | 515 | Conduct: Initial Review (IR) | 2021-06-16 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-06-23 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-06-30 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-07-08 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-07-15 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-07-29 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-08-12 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-08-19 | Customer – requirement to provide corrected information
121333375 | 515 | Conduct: Initial Review (IR) | 2021-08-05 | Project Management - addressing project volume surge
121333662 | 516 | Conduct: Initial Review (IR) | 2021-07-17 | Cus – requirement to provide a response to deficiency notice
121333662 | 516 | Conduct: Initial Review (IR) | 2021-08-05 | Engineering – requiring more detailed review
121333662 | 516 | Conduct: Supplemental Review (SR) | 2021-09-30 | Engineering – requiring more detailed review
121333662 | 516 | Conduct: Initial Review (IR) | 2021-07-17 | Cus – requirement to provide a response to deficiency notice
121333662 | 516 | Conduct: Initial Review (IR) | 2021-08-05 | Engineering – requiring more detailed review
121333662 | 516 | Conduct: Supplemental Review (SR) | 2021-09-30 | Engineering – requiring more detailed review
121333662 | 516 | Conduct: Initial Review (IR) | 2021-07-17 | Cus – requirement to provide a response to deficiency notice
121333662 | 516 | Conduct: Initial Review (IR) | 2021-08-05 | Engineering – requiring more detailed review
121333662 | 516 | Conduct: Supplemental Review (SR) | 2021-09-30 | Engineering – requiring more detailed review
121334724 | 517 | Conduct: Initial Review (IR) | 2021-07-08 | Cus – requirement to provide a response to deficiency notice
121334724 | 517 | Conduct: Initial Review (IR) | 2021-07-15 | Cus – requirement to provide a response to deficiency notice
121334766 | 518 | Conduct: Initial Review (IR) | 2021-07-06 | Project Management - addressing emergency power outages
121345515 | 519 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
121345515 | 519 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
121347821 | 520 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
121347821 | 520 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
121347821 | 520 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
121347821 | 520 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
121347821 | 520 | Conduct: Initial Review (IR) | 2021-06-08 | Cus – requirement to provide a response to deficiency notice
121347821 | 520 | Conduct: Initial Review (IR) | 2021-06-15 | Cus – requirement to provide a response to deficiency notice
121348972 | 521 | Conduct: Initial Review (IR) | 2021-06-22 | Project Management - addressing project volume surge
121349220 | 522 | Conduct: Initial Review (IR) | 2021-06-22 | Project Management - addressing project volume surge
121349235 | 523 | Conduct: Initial Review (IR) | 2021-06-22 | Project Management - addressing project volume surge
121351304 | 524 | Conduct: Initial Review (IR) | 2021-06-25 | Cus – requirement to provide a response to deficiency notice
121351304 | 524 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
121351304 | 524 | Conduct: Initial Review (IR) | 2021-07-19 | Cus – requirement to provide a response to deficiency notice
121351304 | 524 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
121351304 | 524 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
121351304 | 524 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
121351304 | 524 | Conduct: Initial Review (IR) | 2021-07-02 | Customer – requesting an extension
121353735 | 525 | Conduct: Initial Review (IR) | 2021-06-24 | Cus – requirement to provide a response to deficiency notice
121355547 | 526 | Conduct: Initial Review (IR) | 2021-06-23 | Project Management – requiring more detailed review
121355803 | 527 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
121355803 | 527 | Conduct: Supplemental Review (SR) | 2021-09-07 | Engineering – requiring more detailed review
121355803 | 527 | Conduct: Initial Review (IR) | 2021-06-30 | Project Management – requiring more detailed review
121355803 | 527 | Conduct: Initial Review (IR) | 2021-07-13 | Project Management – requiring more detailed review
121355803 | 527 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
121355803 | 527 | Conduct: Supplemental Review (SR) | 2021-09-07 | Engineering – requiring more detailed review
121355803 | 527 | Conduct: Initial Review (IR) | 2021-06-30 | Project Management – requiring more detailed review
121355803 | 527 | Conduct: Initial Review (IR) | 2021-07-13 | Project Management – requiring more detailed review
121355803 | 527 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
121355803 | 527 | Conduct: Supplemental Review (SR) | 2021-09-07 | Engineering – requiring more detailed review
121355803 | 527 | Conduct: Initial Review (IR) | 2021-06-30 | Project Management – requiring more detailed review
121355803 | 527 | Conduct: Initial Review (IR) | 2021-07-13 | Project Management – requiring more detailed review
121359568 | 528 | Conduct: Initial Review (IR) | 2021-06-29 | Cus – requirement to provide a response to deficiency notice
121366889 | 529 | Conduct: Initial Review (IR) | 2021-06-24 | Cus – requirement to provide a response to deficiency notice
121368590 | 530 | Conduct: Initial Review (IR) | 2021-06-24 | Cus – requirement to provide a response to deficiency notice
121368827 | 531 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
121368827 | 531 | Conduct: Initial Review (IR) | 2021-07-19 | Engineering – requiring more detailed review
121368827 | 531 | Conduct: Initial Review (IR) | 2021-07-26 | Engineering – requiring more detailed review
121368827 | 531 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
121368827 | 531 | Conduct: Initial Review (IR) | 2021-07-19 | Engineering – requiring more detailed review
121368827 | 531 | Conduct: Initial Review (IR) | 2021-07-26 | Engineering – requiring more detailed review
121368827 | 531 | Conduct: Initial Review (IR) | 2021-07-02 | Cus – requirement to provide a response to deficiency notice
121368827 | 531 | Conduct: Initial Review (IR) | 2021-07-19 | Engineering – requiring more detailed review
121368827 | 531 | Conduct: Initial Review (IR) | 2021-07-26 | Engineering – requiring more detailed review
121377182 | 532 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
121377182 | 532 | Conduct: Initial Review (IR) | 2021-07-19 | Engineering – requiring more detailed review
121377182 | 532 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
121377182 | 532 | Conduct: Initial Review (IR) | 2021-07-19 | Engineering – requiring more detailed review
121377182 | 532 | Conduct: Initial Review (IR) | 2021-07-07 | Engineering – requiring more detailed review
121377182 | 532 | Conduct: Initial Review (IR) | 2021-07-19 | Engineering – requiring more detailed review
121377796 | 533 | Conduct: Initial Review (IR) | 2021-07-12 | Customer – requirement to provide corrected information
121377796 | 533 | Conduct: Initial Review (IR) | 2021-07-03 | Engineering – requiring more detailed review
121377796 | 533 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
121377796 | 533 | Conduct: Initial Review (IR) | 2021-07-16 | Engineering – requiring more detailed review
121377796 | 533 | Conduct: Initial Review (IR) | 2021-07-23 | Engineering – requiring more detailed review
121377796 | 533 | Conduct: Initial Review (IR) | 2021-07-12 | Customer – requirement to provide corrected information
121377796 | 533 | Conduct: Initial Review (IR) | 2021-07-03 | Engineering – requiring more detailed review
121377796 | 533 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
121377796 | 533 | Conduct: Initial Review (IR) | 2021-07-16 | Engineering – requiring more detailed review
121377796 | 533 | Conduct: Initial Review (IR) | 2021-07-23 | Engineering – requiring more detailed review
121377796 | 533 | Conduct: Initial Review (IR) | 2021-07-12 | Customer – requirement to provide corrected information
121377796 | 533 | Conduct: Initial Review (IR) | 2021-07-03 | Engineering – requiring more detailed review
121377796 | 533 | Conduct: Initial Review (IR) | 2021-07-06 | Engineering – requiring more detailed review
121377796 | 533 | Conduct: Initial Review (IR) | 2021-07-16 | Engineering – requiring more detailed review
121377796 | 533 | Conduct: Initial Review (IR) | 2021-07-23 | Engineering – requiring more detailed review
121386441 | 534 | Conduct: Initial Review (IR) | 2021-06-23 | Cus – requirement to provide a response to deficiency notice
121388061 | 535 | Conduct: Initial Review (IR) | 2021-07-08 | Customer – requirement to provide corrected information
121388233 | 536 | Conduct: Screens Q and R | 2021-07-13 | Engineering – addressing project volume surge
121388233 | 536 | Conduct: Screens Q and R | 2021-07-13 | Engineering – addressing project volume surge
121388233 | 536 | Conduct: Screens Q and R | 2021-07-13 | Engineering – addressing project volume surge
121389551 | 537 | Conduct: Initial Review (IR) | 2021-07-02 | Customer – requesting an extension
121417094 | 538 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
121418155 | 539 | Conduct: Initial Review (IR) | 2021-06-29 | Customer – requirement to provide corrected information
121418155 | 539 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
121439926 | 540 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
121439926 | 540 | Conduct: Initial Review (IR) | 2021-07-07 | Customer – requirement to provide corrected information
121439926 | 540 | Conduct: Initial Review (IR) | 2021-07-14 | Customer – requirement to provide corrected information
119626368 | 541 | Conduct: SIS | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
119626368 | 541 | Conduct: SIS | 2021-10-15 | Customer – requirement to provide corrected information
119626368 | 541 | Conduct: SIS | 2021-05-07 | Engineering
119626368 | 541 | Conduct: SIS | 2021-05-14 | Engineering
119626368 | 541 | Conduct: SIS | 2021-05-21 | Engineering
119626368 | 541 | Conduct: SIS | 2021-05-28 | Engineering
119626368 | 541 | Conduct: SIS | 2021-06-07 | Engineering
119626368 | 541 | Conduct: SIS | 2021-06-14 | Engineering
119626368 | 541 | Conduct: SIS | 2021-06-21 | Engineering
119626368 | 541 | Conduct: SIS | 2021-06-28 | Engineering
119626368 | 541 | Conduct: SIS | 2021-07-06 | Engineering
119626368 | 541 | Conduct: SIS | 2021-07-13 | Engineering
119626368 | 541 | Conduct: SIS | 2021-07-20 | Engineering
119626368 | 541 | Conduct: SIS | 2021-07-27 | Engineering
119626368 | 541 | Conduct: SIS | 2021-08-03 | Engineering
119626368 | 541 | Conduct: SIS | 2021-08-10 | Engineering
119626368 | 541 | Conduct: SIS | 2021-08-17 | Engineering
119626368 | 541 | Conduct: SIS | 2021-08-24 | Engineering
119626368 | 541 | Conduct: SIS | 2021-09-07 | Engineering – addressing project volume surge
119626368 | 541 | Conduct: SIS | 2021-09-14 | Engineering – addressing project volume surge
119626368 | 541 | Conduct: SIS | 2021-09-21 | Engineering – addressing project volume surge
119626368 | 541 | Conduct: SIS | 2021-09-28 | Engineering – addressing project volume surge
119626368 | 541 | Conduct: SIS | 2021-10-05 | Engineering – addressing project volume surge
120140849 | 542 | Conduct: Initial Review (IR) | 2021-07-09 | Cus – requirement to provide a response to deficiency notice
120140849 | 542 | Conduct: Initial Review (IR) | 2021-07-16 | Cus – requirement to provide a response to deficiency notice
120140849 | 542 | Conduct: Initial Review (IR) | 2021-07-23 | Cus – requirement to provide a response to deficiency notice
120140849 | 542 | Conduct: Initial Review (IR) | 2021-07-30 | Cus – requirement to provide a response to deficiency notice
120140849 | 542 | Conduct: Initial Review (IR) | 2021-08-06 | Cus – requirement to provide a response to deficiency notice
120140849 | 542 | Conduct: Initial Review (IR) | 2021-08-13 | Cus – requirement to provide a response to deficiency notice
120140849 | 542 | Conduct: Initial Review (IR) | 2021-08-20 | Cus – requirement to provide a response to deficiency notice
120140849 | 542 | Conduct: Initial Review (IR) | 2021-08-27 | Cus – requirement to provide a response to deficiency notice
120140849 | 542 | Conduct: Initial Review (IR) | 2021-09-07 | Cus – requirement to provide a response to deficiency notice
120140849 | 542 | Conduct: Initial Review (IR) | 2021-09-14 | Cus – requirement to provide a response to deficiency notice
120140849 | 542 | Conduct: Initial Review (IR) | 2021-09-21 | Cus – requirement to provide a response to deficiency notice
120140849 | 542 | Conduct: Initial Review (IR) | 2021-09-28 | Cus – requirement to provide a response to deficiency notice
120140849 | 542 | Conduct: Initial Review (IR) | 2021-10-05 | Cus – requirement to provide a response to deficiency notice
120140849 | 542 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
120140849 | 542 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
120140849 | 542 | Conduct: Initial Review (IR) | 2021-10-12 | Customer – requirement to provide corrected information
121420299 | 543 | Conduct: Initial Review (IR) | 2021-07-09 | Cus – requirement to provide a response to deficiency notice
121420299 | 543 | Conduct: Initial Review (IR) | 2021-07-16 | Cus – requirement to provide a response to deficiency notice
121420299 | 543 | Conduct: Initial Review (IR) | 2021-07-23 | Cus – requirement to provide a response to deficiency notice
121420299 | 543 | Conduct: Initial Review (IR) | 2021-07-30 | Cus – requirement to provide a response to deficiency notice
121420299 | 543 | Conduct: Initial Review (IR) | 2021-08-06 | Cus – requirement to provide a response to deficiency notice
121420299 | 543 | Conduct: Initial Review (IR) | 2021-08-13 | Cus – requirement to provide a response to deficiency notice
121420299 | 543 | Conduct: Initial Review (IR) | 2021-08-20 | Cus – requirement to provide a response to deficiency notice
121420299 | 543 | Conduct: Initial Review (IR) | 2021-08-27 | Cus – requirement to provide a response to deficiency notice
121420299 | 543 | Conduct: Initial Review (IR) | 2021-09-03 | Cus – requirement to provide a response to deficiency notice
121420299 | 543 | Conduct: Initial Review (IR) | 2021-09-13 | Cus – requirement to provide a response to deficiency notice
121420299 | 543 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
121420299 | 543 | Conduct: Initial Review (IR) | 2021-09-27 | Cus – requirement to provide a response to deficiency notice
121420299 | 543 | Conduct: Initial Review (IR) | 2021-10-04 | Cus – requirement to provide a response to deficiency notice
121420299 | 543 | Conduct: Initial Review (IR) | 2021-10-11 | Engineering – requiring more detailed review
121420299 | 543 | Conduct: Initial Review (IR) | 2021-10-18 | Engineering – requiring more detailed review
120007842 | 544 | Conduct: Initial Review (IR) | 2021-07-09 | Cus – requirement to provide a response to deficiency notice
121434143 | 545 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
121445488 | 546 | Conduct: Initial Review (IR) | 2021-07-12 | Cus – requirement to provide a response to deficiency notice
120743046 | 547 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
120743046 | 547 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
120743046 | 547 | Conduct: Initial Review (IR) | 2021-08-23 | Engineering – requiring more detailed review
120743046 | 547 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
120743046 | 547 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
120743046 | 547 | Conduct: Initial Review (IR) | 2021-08-23 | Engineering – requiring more detailed review
120743046 | 547 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
120743046 | 547 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
120743046 | 547 | Conduct: Initial Review (IR) | 2021-08-23 | Engineering – requiring more detailed review
121521355 | 548 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
121448319 | 549 | Conduct: Initial Review (IR) | 2021-07-14 | Cus – requirement to provide a response to deficiency notice
121448319 | 549 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
121448319 | 549 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
121448319 | 549 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
121448319 | 549 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
121328319 | 550 | Conduct: Initial Review (IR) | 2021-07-15 | Cus – requirement to provide a response to deficiency notice
121444834 | 551 | Conduct: Initial Review (IR) | 2021-07-15 | Cus – requirement to provide a response to deficiency notice
121444739 | 552 | Conduct: Initial Review (IR) | 2021-07-15 | Cus – requirement to provide a response to deficiency notice
120637986 | 553 | Conduct: Initial Review (IR) | 2021-07-15 | Cus – requirement to provide a response to deficiency notice
120637986 | 553 | Conduct: Initial Review (IR) | 2021-07-22 | Cus – requirement to provide a response to deficiency notice
120637986 | 553 | Conduct: Initial Review (IR) | 2021-07-29 | Cus – requirement to provide a response to deficiency notice
120637986 | 553 | Conduct: Initial Review (IR) | 2021-07-29 | Cus – requirement to provide a response to deficiency notice
120637986 | 553 | Conduct: Initial Review (IR) | 2021-07-15 | Cus – requirement to provide a response to deficiency notice
120637986 | 553 | Conduct: Initial Review (IR) | 2021-07-22 | Cus – requirement to provide a response to deficiency notice
120637986 | 553 | Conduct: Initial Review (IR) | 2021-07-15 | Cus – requirement to provide a response to deficiency notice
120637986 | 553 | Conduct: Initial Review (IR) | 2021-07-22 | Cus – requirement to provide a response to deficiency notice
120637986 | 553 | Conduct: Initial Review (IR) | 2021-07-29 | Cus – requirement to provide a response to deficiency notice
120643625 | 554 | Conduct: Initial Review (IR) | 2021-07-29 | Cus – requirement to provide a response to deficiency notice
120643625 | 554 | Conduct: Initial Review (IR) | 2021-08-12 | Cus – requirement to provide a response to deficiency notice
120643625 | 554 | Conduct: Initial Review (IR) | 2021-08-26 | Cus – requirement to provide a response to deficiency notice
120643625 | 554 | Conduct: Initial Review (IR) | 2021-07-15 | Customer – requirement to provide corrected information
120643625 | 554 | Conduct: Initial Review (IR) | 2021-09-10 | Customer – requirement to provide corrected information
120643625 | 554 | Conduct: Initial Review (IR) | 2021-07-29 | Cus – requirement to provide a response to deficiency notice
120643625 | 554 | Conduct: Initial Review (IR) | 2021-08-12 | Cus – requirement to provide a response to deficiency notice
120643625 | 554 | Conduct: Initial Review (IR) | 2021-08-26 | Cus – requirement to provide a response to deficiency notice
120643625 | 554 | Conduct: Initial Review (IR) | 2021-07-15 | Customer – requirement to provide corrected information
120643625 | 554 | Conduct: Initial Review (IR) | 2021-09-10 | Customer – requirement to provide corrected information
120643625 | 554 | Conduct: Initial Review (IR) | 2021-07-29 | Cus – requirement to provide a response to deficiency notice
120643625 | 554 | Conduct: Initial Review (IR) | 2021-08-12 | Cus – requirement to provide a response to deficiency notice
120643625 | 554 | Conduct: Initial Review (IR) | 2021-08-26 | Cus – requirement to provide a response to deficiency notice
120643625 | 554 | Conduct: Initial Review (IR) | 2021-07-15 | Customer – requirement to provide corrected information
120643625 | 554 | Conduct: Initial Review (IR) | 2021-09-10 | Customer – requirement to provide corrected information
121482348 | 555 | Conduct: Initial Review (IR) | 2021-07-16 | Cus – requirement to provide a response to deficiency notice
121367736 | 556 | Conduct: Initial Review (IR) | 2021-07-16 | Cus – requirement to provide a response to deficiency notice
121367736 | 556 | Conduct: Initial Review (IR) | 2021-07-23 | Engineering – requiring more detailed review
121367736 | 556 | Conduct: Initial Review (IR) | 2021-07-16 | Cus – requirement to provide a response to deficiency notice
121367736 | 556 | Conduct: Initial Review (IR) | 2021-07-23 | Engineering – requiring more detailed review
121367736 | 556 | Conduct: Initial Review (IR) | 2021-07-16 | Cus – requirement to provide a response to deficiency notice
121367736 | 556 | Conduct: Initial Review (IR) | 2021-07-23 | Engineering – requiring more detailed review
121488744 | 557 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
121488744 | 557 | Conduct: Initial Review (IR) | 2021-07-19 | Customer – requesting an extension
121535352 | 558 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
121535352 | 558 | Conduct: Initial Review (IR) | 2021-08-16 | Cus – requirement to provide a response to deficiency notice
121535352 | 558 | Conduct: Initial Review (IR) | 2021-07-26 | Engineering – requiring more detailed review
121535352 | 558 | Conduct: Initial Review (IR) | 2021-08-02 | Engineering – requiring more detailed review
121535352 | 558 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
121535352 | 558 | Conduct: Initial Review (IR) | 2021-08-16 | Cus – requirement to provide a response to deficiency notice
121535352 | 558 | Conduct: Initial Review (IR) | 2021-08-02 | Engineering – requiring more detailed review
121535352 | 558 | Conduct: Initial Review (IR) | 2021-07-26 | Engineering – requiring more detailed review
121535352 | 558 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
121535352 | 558 | Conduct: Initial Review (IR) | 2021-08-16 | Cus – requirement to provide a response to deficiency notice
121535352 | 558 | Conduct: Initial Review (IR) | 2021-07-26 | Engineering – requiring more detailed review
121535352 | 558 | Conduct: Initial Review (IR) | 2021-08-02 | Engineering – requiring more detailed review
121496211 | 559 | Conduct: Initial Review (IR) | 2021-07-20 | Cus – requirement to provide a response to deficiency notice
121496211 | 559 | Conduct: Initial Review (IR) | 2021-07-27 | Cus – requirement to provide a response to deficiency notice
121496211 | 559 | Conduct: Initial Review (IR) | 2021-08-03 | Cus – requirement to provide a response to deficiency notice
121496211 | 559 | Conduct: Initial Review (IR) | 2021-08-10 | Cus – requirement to provide a response to deficiency notice
121496211 | 559 | Conduct: Initial Review (IR) | 2021-08-17 | Cus – requirement to provide a response to deficiency notice
121496211 | 559 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
121496211 | 559 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
121496211 | 559 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
121496211 | 559 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
121496211 | 559 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
121496211 | 559 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
121496211 | 559 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
121496211 | 559 | Conduct: Initial Review (IR) | 2021-10-14 | Cus – requirement to provide a response to deficiency notice
121496211 | 559 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
120876757 | 560 | Conduct: Initial Review (IR) | 2021-07-27 | Cus – requirement to provide a response to deficiency notice
120876757 | 560 | Conduct: Initial Review (IR) | 2021-08-10 | Cus – requirement to provide a response to deficiency notice
120876757 | 560 | Conduct: Initial Review (IR) | 2021-08-24 | Cus – requirement to provide a response to deficiency notice
120876757 | 560 | Conduct: Initial Review (IR) | 2021-09-14 | Cus – requirement to provide a response to deficiency notice
120876757 | 560 | Conduct: Initial Review (IR) | 2021-10-05 | Engineering – requiring more detailed review
120876757 | 560 | Conduct: Initial Review (IR) | 2021-10-19 | Engineering – requiring more detailed review
120876757 | 560 | Conduct: Initial Review (IR) | 2021-08-10 | Cus – requirement to provide a response to deficiency notice
120876757 | 560 | Conduct: Initial Review (IR) | 2021-07-27 | Cus – requirement to provide a response to deficiency notice
120876757 | 560 | Conduct: Initial Review (IR) | 2021-08-24 | Cus – requirement to provide a response to deficiency notice
120876757 | 560 | Conduct: Initial Review (IR) | 2021-09-14 | Cus – requirement to provide a response to deficiency notice
120876757 | 560 | Conduct: Initial Review (IR) | 2021-10-05 | Engineering – requiring more detailed review
120876757 | 560 | Conduct: Initial Review (IR) | 2021-10-19 | Engineering – requiring more detailed review
120876757 | 560 | Conduct: Supplemental Review (SR) | 2021-12-13 | Engineering – requiring more detailed review
120876757 | 560 | Conduct: Supplemental Review (SR) | 2021-12-16 | Engineering – requiring more detailed review
120876757 | 560 | Conduct: Supplemental Review (SR) | 2021-12-23 | Engineering – requiring more detailed review
120876757 | 560 | Conduct: Supplemental Review (SR) | 2021-12-30 | Engineering – requiring more detailed review
120876757 | 560 | Conduct: Initial Review (IR) | 2021-07-27 | Cus – requirement to provide a response to deficiency notice
120876757 | 560 | Conduct: Initial Review (IR) | 2021-08-10 | Cus – requirement to provide a response to deficiency notice
120876757 | 560 | Conduct: Initial Review (IR) | 2021-08-24 | Cus – requirement to provide a response to deficiency notice
120876757 | 560 | Conduct: Initial Review (IR) | 2021-09-14 | Cus – requirement to provide a response to deficiency notice
120876757 | 560 | Conduct: Initial Review (IR) | 2021-10-05 | Engineering – requiring more detailed review
120876757 | 560 | Conduct: Initial Review (IR) | 2021-10-19 | Engineering – requiring more detailed review
120876757 | 560 | Conduct: Supplemental Review (SR) | 2021-12-13 | Engineering – requiring more detailed review
120876757 | 560 | Conduct: Supplemental Review (SR) | 2021-12-16 | Engineering – requiring more detailed review
120876757 | 560 | Conduct: Supplemental Review (SR) | 2021-12-23 | Engineering – requiring more detailed review
120876757 | 560 | Conduct: Supplemental Review (SR) | 2021-12-30 | Engineering – requiring more detailed review
121448017 | 561 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
121448017 | 561 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
121448017 | 561 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
121562523 | 562 | Conduct: Initial Review (IR) | 2021-07-21 | Cus – requirement to provide a response to deficiency notice
120231866 | 563 | Conduct: Initial Review (IR) | 2021-07-22 | Cus – requirement to provide a response to deficiency notice
120231866 | 563 | Conduct: Initial Review (IR) | 2021-07-29 | Cus – requirement to provide a response to deficiency notice
120231866 | 563 | Conduct: Initial Review (IR) | 2021-08-05 | Cus – requirement to provide a response to deficiency notice
120231866 | 563 | Conduct: Initial Review (IR) | 2021-08-12 | Project Management - addressing project volume surge
121407586 | 564 | Conduct: Initial Review (IR) | 2021-08-13 | Cus – requirement to provide a response to deficiency notice
121407586 | 564 | Conduct: Initial Review (IR) | 2021-08-13 | Cus – requirement to provide a response to deficiency notice
121407586 | 564 | Conduct: Initial Review (IR) | 2021-08-13 | Cus – requirement to provide a response to deficiency notice
121578208 | 565 | Conduct: Initial Review (IR) | 2021-07-26 | Cus – requirement to provide a response to deficiency notice
121545682 | 566 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
121545682 | 566 | Conduct: Initial Review (IR) | 2021-07-21 | Project Management – requiring more detailed review
121552626 | 567 | Conduct: Initial Review (IR) | 2021-07-28 | Cus – requirement to provide a response to deficiency notice
121552626 | 567 | Conduct: Initial Review (IR) | 2021-08-04 | Cus – requirement to provide a response to deficiency notice
121552626 | 567 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
121552626 | 567 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
121552626 | 567 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
121552626 | 567 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
121561281 | 568 | Conduct: Initial Review (IR) | 2021-07-29 | Cus – requirement to provide a response to deficiency notice
121561281 | 568 | Conduct: Initial Review (IR) | 2021-08-05 | Cus – requirement to provide a response to deficiency notice
121561281 | 568 | Conduct: Initial Review (IR) | 2021-08-12 | Cus – requirement to provide a response to deficiency notice
121561281 | 568 | Conduct: Initial Review (IR) | 2021-08-19 | Cus – requirement to provide a response to deficiency notice
120534647 | 569 | Conduct: Initial Review (IR) | 2021-07-30 | Cus – requirement to provide a response to deficiency notice
120534647 | 569 | Conduct: Initial Review (IR) | 2021-08-06 | Cus – requirement to provide a response to deficiency notice
120534647 | 569 | Conduct: Initial Review (IR) | 2021-08-13 | Cus – requirement to provide a response to deficiency notice
120534647 | 569 | Conduct: Initial Review (IR) | 2021-08-20 | Cus – requirement to provide a response to deficiency notice
120534647 | 569 | Conduct: Initial Review (IR) | 2021-08-27 | Cus – requirement to provide a response to deficiency notice
120534647 | 569 | Conduct: Initial Review (IR) | 2021-09-03 | Cus – requirement to provide a response to deficiency notice
120534647 | 569 | Conduct: Initial Review (IR) | 2021-09-13 | Cus – requirement to provide a response to deficiency notice
120534647 | 569 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
120534647 | 569 | Conduct: Initial Review (IR) | 2021-09-27 | Cus – requirement to provide a response to deficiency notice
120534647 | 569 | Conduct: Initial Review (IR) | 2021-10-04 | Cus – requirement to provide a response to deficiency notice
120534647 | 569 | Conduct: Initial Review (IR) | 2021-10-11 | Cus – requirement to provide a response to deficiency notice
120534647 | 569 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
120534647 | 569 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
121602986 | 570 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
121578306 | 571 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
121578306 | 571 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
121580814 | 572 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
121580814 | 572 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
121580814 | 572 | Conduct: Initial Review (IR) | 2021-08-16 | Cus – requirement to provide a response to deficiency notice
120750301 | 573 | Conduct: Initial Review (IR) | 2021-08-02 | Cus – requirement to provide a response to deficiency notice
120750301 | 573 | Conduct: Initial Review (IR) | 2021-08-09 | Cus – requirement to provide a response to deficiency notice
121545926 | 574 | Conduct: Initial Review (IR) | 2021-08-03 | Cus – requirement to provide a response to deficiency notice
121545926 | 574 | Conduct: Initial Review (IR) | 2021-08-10 | Cus – requirement to provide a response to deficiency notice
121545926 | 574 | Conduct: Initial Review (IR) | 2021-08-17 | Cus – requirement to provide a response to deficiency notice
121545926 | 574 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
121545926 | 574 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
121545926 | 574 | Conduct: Initial Review (IR) | 2021-09-09 | Engineering – requiring more detailed review
121623512 | 575 | Conduct: Initial Review (IR) | 2021-08-06 | Cus – requirement to provide a response to deficiency notice
121623512 | 575 | Conduct: Initial Review (IR) | 2021-08-13 | Cus – requirement to provide a response to deficiency notice
121623512 | 575 | Conduct: Initial Review (IR) | 2021-08-20 | Cus – requirement to provide a response to deficiency notice
121623512 | 575 | Conduct: Initial Review (IR) | 2021-08-27 | Cus – requirement to provide a response to deficiency notice
121623512 | 575 | Conduct: Initial Review (IR) | 2021-09-03 | Cus – requirement to provide a response to deficiency notice
121597322 | 576 | Conduct: Initial Review (IR) | 2021-08-06 | Cus – requirement to provide a response to deficiency notice
121597322 | 576 | Conduct: Initial Review (IR) | 2021-08-13 | Cus – requirement to provide a response to deficiency notice
121624065 | 577 | Conduct: Initial Review (IR) | 2021-08-06 | Cus – requirement to provide a response to deficiency notice
121624065 | 577 | Conduct: Initial Review (IR) | 2021-08-13 | Cus – requirement to provide a response to deficiency notice
121439950 | 578 | Conduct: Initial Review (IR) | 2021-08-10 | Cus – requirement to provide a response to deficiency notice
121645203 | 579 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
120930832 | 580 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
120930832 | 580 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
121513478 | 581 | Conduct: Initial Review (IR) | 2021-08-11 | Cus – requirement to provide a response to deficiency notice
121513478 | 581 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
121513478 | 581 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
121582507 | 582 | Conduct: Initial Review (IR) | 2021-11-04 | Cus – requirement to provide a response to deficiency notice
121582507 | 582 | Conduct: Initial Review (IR) | 2021-10-06 | Engineering – requiring more detailed review
121582507 | 582 | Conduct: Initial Review (IR) | 2021-11-04 | Cus – requirement to provide a response to deficiency notice
121582507 | 582 | Conduct: Initial Review (IR) | 2021-11-15 | Engineering – addressing project volume surge
121582507 | 582 | Conduct: Initial Review (IR) | 2021-10-06 | Engineering – requiring more detailed review
121582507 | 582 | Conduct: Initial Review (IR) | 2021-11-10 | Engineering – requiring more detailed review
121582507 | 582 | Conduct: Initial Review (IR) | 2021-11-04 | Cus – requirement to provide a response to deficiency notice
121582507 | 582 | Conduct: Initial Review (IR) | 2021-11-15 | Engineering – addressing project volume surge
121582507 | 582 | Conduct: Initial Review (IR) | 2021-10-06 | Engineering – requiring more detailed review
121582507 | 582 | Conduct: Initial Review (IR) | 2021-11-10 | Engineering – requiring more detailed review
121661266 | 583 | Conduct: Initial Review (IR) | 2021-08-12 | Cus – requirement to provide a response to deficiency notice
121661266 | 583 | Conduct: Initial Review (IR) | 2021-08-19 | Cus – requirement to provide a response to deficiency notice
121661266 | 583 | Conduct: Initial Review (IR) | 2021-08-26 | Cus – requirement to provide a response to deficiency notice
121661266 | 583 | Conduct: Initial Review (IR) | 2021-09-02 | Cus – requirement to provide a response to deficiency notice
121661266 | 583 | Conduct: Initial Review (IR) | 2021-09-10 | Engineering – requiring more detailed review
121661373 | 584 | Conduct: Initial Review (IR) | 2021-08-12 | Cus – requirement to provide a response to deficiency notice
121661373 | 584 | Conduct: Initial Review (IR) | 2021-08-19 | Cus – requirement to provide a response to deficiency notice
121661373 | 584 | Conduct: Initial Review (IR) | 2021-08-26 | Cus – requirement to provide a response to deficiency notice
121661373 | 584 | Conduct: Initial Review (IR) | 2021-09-02 | Cus – requirement to provide a response to deficiency notice
121686152 | 585 | Conduct: Initial Review (IR) | 2021-08-13 | Cus – requirement to provide a response to deficiency notice
121679681 | 586 | Conduct: Initial Review (IR) | 2021-08-13 | Cus – requirement to provide a response to deficiency notice
121682862 | 587 | Conduct: Initial Review (IR) | 2021-08-16 | Cus – requirement to provide a response to deficiency notice
121682862 | 587 | Conduct: Initial Review (IR) | 2021-08-23 | Cus – requirement to provide a response to deficiency notice
121682862 | 587 | Conduct: Initial Review (IR) | 2021-08-30 | Cus – requirement to provide a response to deficiency notice
121682862 | 587 | Conduct: Initial Review (IR) | 2021-09-07 | Cus – requirement to provide a response to deficiency notice
121682862 | 587 | Conduct: Initial Review (IR) | 2021-09-14 | Cus – requirement to provide a response to deficiency notice
121682862 | 587 | Conduct: Initial Review (IR) | 2021-09-21 | Cus – requirement to provide a response to deficiency notice
121682862 | 587 | Conduct: Initial Review (IR) | 2021-09-28 | Cus – requirement to provide a response to deficiency notice
121682862 | 587 | Conduct: Initial Review (IR) | 2021-10-05 | Cus – requirement to provide a response to deficiency notice
121746445 | 588 | Conduct: Initial Review (IR) | 2021-08-16 | Cus – requirement to provide a response to deficiency notice
121328554 | 589 | Conduct: Initial Review (IR) | 2021-08-17 | Cus – requirement to provide a response to deficiency notice
121588450 | 590 | Conduct: Initial Review (IR) | 2021-08-18 | Cus – requirement to provide a response to deficiency notice
121588450 | 590 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
121588450 | 590 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
121588450 | 590 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
121588450 | 590 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
121588450 | 590 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
121588450 | 590 | Conduct: Initial Review (IR) | 2021-09-30 | Engineering – requiring more detailed review
121677853 | 591 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
121677853 | 591 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
121677853 | 591 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
120639417 | 592 | Conduct: Initial Review (IR) | 2021-08-27 | Cus – requirement to provide a response to deficiency notice
120639417 | 592 | Conduct: Initial Review (IR) | 2021-09-03 | Cus – requirement to provide a response to deficiency notice
120639417 | 592 | Conduct: Initial Review (IR) | 2021-09-13 | Cus – requirement to provide a response to deficiency notice
120639417 | 592 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
120639417 | 592 | Conduct: Initial Review (IR) | 2021-09-27 | Cus – requirement to provide a response to deficiency notice
120639417 | 592 | Conduct: Initial Review (IR) | 2021-10-04 | Cus – requirement to provide a response to deficiency notice
120639417 | 592 | Conduct: Initial Review (IR) | 2021-10-11 | Cus – requirement to provide a response to deficiency notice
120639417 | 592 | Conduct: Initial Review (IR) | 2021-10-18 | Cus – requirement to provide a response to deficiency notice
120639417 | 592 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
120639417 | 592 | Conduct: Initial Review (IR) | 2021-08-20 | Project Management - addressing project volume surge
121624066 | 593 | Conduct: Initial Review (IR) | 2021-08-23 | Cus – requirement to provide a response to deficiency notice
121624066 | 593 | Conduct: Initial Review (IR) | 2021-08-30 | Cus – requirement to provide a response to deficiency notice
121624066 | 593 | Conduct: Initial Review (IR) | 2021-09-07 | Cus – requirement to provide a response to deficiency notice
121624066 | 593 | Conduct: Initial Review (IR) | 2021-09-14 | Cus – requirement to provide a response to deficiency notice
121624066 | 593 | Conduct: Initial Review (IR) | 2021-09-21 | Cus – requirement to provide a response to deficiency notice
121624066 | 593 | Conduct: Initial Review (IR) | 2021-09-28 | Cus – requirement to provide a response to deficiency notice
121624066 | 593 | Conduct: Initial Review (IR) | 2021-10-05 | Cus – requirement to provide a response to deficiency notice
121624066 | 593 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
121624066 | 593 | Conduct: Initial Review (IR) | 2021-10-12 | Customer – requirement to provide corrected information
121498671 | 594 | Conduct: Initial Review (IR) | 2021-08-31 | Cus – requirement to provide a response to deficiency notice
121498671 | 594 | Conduct: Initial Review (IR) | 2021-08-24 | Project Management - addressing project volume surge
121498671 | 594 | Conduct: Initial Review (IR) | 2021-08-31 | Cus – requirement to provide a response to deficiency notice
121498671 | 594 | Conduct: Initial Review (IR) | 2021-08-24 | Project Management - addressing project volume surge
121498671 | 594 | Conduct: Initial Review (IR) | 2021-08-31 | Cus – requirement to provide a response to deficiency notice
121498671 | 594 | Conduct: Initial Review (IR) | 2021-08-24 | Project Management - addressing project volume surge
121759553 | 595 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
121712490 | 596 | Conduct: Initial Review (IR) | 2021-08-25 | Cus – requirement to provide a response to deficiency notice
118585073 | 597 | Conduct: Initial Review (IR) | 2021-08-27 | Cus – requirement to provide a response to deficiency notice
118585073 | 597 | Conduct: Initial Review (IR) | 2021-09-03 | Cus – requirement to provide a response to deficiency notice
118585073 | 597 | Conduct: Initial Review (IR) | 2021-09-13 | Cus – requirement to provide a response to deficiency notice
121602847 | 598 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
121602847 | 598 | Conduct: Initial Review (IR) | 2021-10-11 | Customer – requirement to provide corrected information
121602847 | 598 | Conduct: Initial Review (IR) | 2021-11-03 | Customer – requirement to provide corrected information
121602847 | 598 | Conduct: Initial Review (IR) | 2021-09-06 | Engineering – addressing project volume surge
121602847 | 598 | Conduct: Initial Review (IR) | 2021-09-27 | Engineering – requiring more detailed review
121602847 | 598 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
121602847 | 598 | Conduct: Initial Review (IR) | 2021-11-24 | Cus – requirement to provide a response to deficiency notice
121602847 | 598 | Conduct: Supplemental Review (SR) | 2022-02-03 | Cus – requirement to provide a response to deficiency notice
121602847 | 598 | Conduct: Initial Review (IR) | 2021-10-11 | Customer – requirement to provide corrected information
121602847 | 598 | Conduct: Initial Review (IR) | 2021-11-03 | Customer – requirement to provide corrected information
121602847 | 598 | Conduct: Initial Review (IR) | 2021-09-06 | Engineering – addressing project volume surge
121602847 | 598 | Conduct: Initial Review (IR) | 2021-12-01 | Engineering – addressing project volume surge
121602847 | 598 | Conduct: Initial Review (IR) | 2021-12-08 | Engineering – addressing project volume surge
121602847 | 598 | Conduct: Initial Review (IR) | 2021-09-27 | Engineering – requiring more detailed review
121602847 | 598 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
121602847 | 598 | Conduct: Initial Review (IR) | 2021-11-24 | Cus – requirement to provide a response to deficiency notice
121602847 | 598 | Conduct: Supplemental Review (SR) | 2022-02-03 | Cus – requirement to provide a response to deficiency notice
121602847 | 598 | Conduct: Supplemental Review (SR) | 2022-02-17 | Cus – requirement to provide a response to deficiency notice
121602847 | 598 | Conduct: Initial Review (IR) | 2021-10-11 | Customer – requirement to provide corrected information
121602847 | 598 | Conduct: Initial Review (IR) | 2021-11-03 | Customer – requirement to provide corrected information
121602847 | 598 | Conduct: Initial Review (IR) | 2021-09-06 | Engineering – addressing project volume surge
121602847 | 598 | Conduct: Initial Review (IR) | 2021-12-01 | Engineering – addressing project volume surge
121602847 | 598 | Conduct: Initial Review (IR) | 2021-12-08 | Engineering – addressing project volume surge
121602847 | 598 | Conduct: Initial Review (IR) | 2021-09-27 | Engineering – requiring more detailed review
121723503 | 599 | Conduct: Initial Review (IR) | 2021-08-31 | Cus – requirement to provide a response to deficiency notice
121723503 | 599 | Conduct: Initial Review (IR) | 2021-09-22 | Cus – requirement to provide a response to deficiency notice
121723503 | 599 | Conduct: Initial Review (IR) | 2021-09-29 | Cus – requirement to provide a response to deficiency notice
121723503 | 599 | Conduct: Initial Review (IR) | 2021-10-06 | Cus – requirement to provide a response to deficiency notice
121723503 | 599 | Conduct: Initial Review (IR) | 2021-10-13 | Cus – requirement to provide a response to deficiency notice
121723503 | 599 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
121723503 | 599 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
121723503 | 599 | Conduct: Initial Review (IR) | 2021-09-08 | Customer – requirement to provide corrected information
121723503 | 599 | Conduct: Initial Review (IR) | 2021-09-15 | Customer – requirement to provide corrected information
121574567 | 600 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
121574567 | 600 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
121574567 | 600 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-10-14 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-10-14 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-10-28 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-11-04 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-11-11 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-11-18 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-11-25 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-12-03 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-12-10 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-12-17 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-12-24 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-12-31 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2022-01-07 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2022-01-14 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-12-03 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-10-14 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-10-28 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-11-04 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-11-11 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-11-18 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-11-25 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-12-10 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-12-17 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-12-24 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2021-12-31 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2022-01-07 | Cus – requirement to provide a response to deficiency notice
121354483 | 601 | Conduct: Initial Review (IR) | 2022-01-14 | Cus – requirement to provide a response to deficiency notice
121783637 | 602 | Conduct: Initial Review (IR) | 2021-09-01 | Cus – requirement to provide a response to deficiency notice
121726607 | 603 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
121726607 | 603 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
121726607 | 603 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
121726607 | 603 | Conduct: Initial Review (IR) | 2021-09-01 | Customer – requirement to provide corrected information
121726607 | 603 | Conduct: Initial Review (IR) | 2021-09-09 | Customer – requirement to provide corrected information
121726607 | 603 | Conduct: Initial Review (IR) | 2021-10-07 | Engineering – requiring more detailed review
121726607 | 603 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
121726607 | 603 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
121726607 | 603 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
121726607 | 603 | Conduct: Initial Review (IR) | 2021-09-01 | Customer – requirement to provide corrected information
121726607 | 603 | Conduct: Initial Review (IR) | 2021-09-09 | Customer – requirement to provide corrected information
121726607 | 603 | Conduct: Initial Review (IR) | 2021-10-07 | Engineering – requiring more detailed review
121726607 | 603 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
121726607 | 603 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
121726607 | 603 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
121726607 | 603 | Conduct: Initial Review (IR) | 2021-09-01 | Customer – requirement to provide corrected information
121726607 | 603 | Conduct: Initial Review (IR) | 2021-09-09 | Customer – requirement to provide corrected information
121726607 | 603 | Conduct: Initial Review (IR) | 2021-10-07 | Engineering – requiring more detailed review
121669762 | 604 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
121669762 | 604 | Conduct: Initial Review (IR) | 2021-09-30 | Project Management – requiring more detailed review
121669762 | 604 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
121669762 | 604 | Conduct: Initial Review (IR) | 2021-09-30 | Project Management – requiring more detailed review
121669762 | 604 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
121669762 | 604 | Conduct: Initial Review (IR) | 2021-09-30 | Project Management – requiring more detailed review
121805463 | 605 | Conduct: Initial Review (IR) | 2021-09-03 | Cus – requirement to provide a response to deficiency notice
121805463 | 605 | Conduct: Initial Review (IR) | 2021-09-13 | Cus – requirement to provide a response to deficiency notice
121805463 | 605 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
121805643 | 606 | Conduct: Initial Review (IR) | 2021-09-03 | Cus – requirement to provide a response to deficiency notice
121805643 | 606 | Conduct: Initial Review (IR) | 2021-09-13 | Cus – requirement to provide a response to deficiency notice
121805643 | 606 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
121805691 | 607 | Conduct: Initial Review (IR) | 2021-09-03 | Cus – requirement to provide a response to deficiency notice
121805691 | 607 | Conduct: Initial Review (IR) | 2021-09-13 | Cus – requirement to provide a response to deficiency notice
121805691 | 607 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
121805756 | 608 | Conduct: Initial Review (IR) | 2021-09-03 | Cus – requirement to provide a response to deficiency notice
121805756 | 608 | Conduct: Initial Review (IR) | 2021-09-13 | Cus – requirement to provide a response to deficiency notice
121805756 | 608 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
121815328 | 609 | Conduct: Initial Review (IR) | 2021-09-03 | Cus – requirement to provide a response to deficiency notice
121815328 | 609 | Conduct: Initial Review (IR) | 2021-09-13 | Cus – requirement to provide a response to deficiency notice
121815328 | 609 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
121815328 | 609 | Conduct: Initial Review (IR) | 2021-09-27 | Cus – requirement to provide a response to deficiency notice
121815328 | 609 | Conduct: Initial Review (IR) | 2021-10-04 | Cus – requirement to provide a response to deficiency notice
121547272 | 610 | Conduct: Initial Review (IR) | 2021-09-03 | Cus – requirement to provide a response to deficiency notice
121547272 | 610 | Conduct: Initial Review (IR) | 2021-09-13 | Cus – requirement to provide a response to deficiency notice
121547272 | 610 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
121547272 | 610 | Conduct: Initial Review (IR) | 2021-09-27 | Cus – requirement to provide a response to deficiency notice
121547272 | 610 | Conduct: Initial Review (IR) | 2021-10-04 | Cus – requirement to provide a response to deficiency notice
121547272 | 610 | Conduct: Initial Review (IR) | 2021-10-11 | Cus – requirement to provide a response to deficiency notice
121547272 | 610 | Conduct: Initial Review (IR) | 2021-10-18 | Cus – requirement to provide a response to deficiency notice
121816017 | 611 | Conduct: Initial Review (IR) | 2021-09-03 | Cus – requirement to provide a response to deficiency notice
121816017 | 611 | Conduct: Initial Review (IR) | 2021-09-13 | Cus – requirement to provide a response to deficiency notice
121816017 | 611 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
121814594 | 612 | Conduct: Initial Review (IR) | 2021-09-14 | Cus – requirement to provide a response to deficiency notice
121814594 | 612 | Conduct: Initial Review (IR) | 2021-10-05 | Engineering – requiring more detailed review
121814594 | 612 | Conduct: Initial Review (IR) | 2021-10-12 | Engineering – requiring more detailed review
121814594 | 612 | Conduct: Initial Review (IR) | 2021-10-26 | Engineering – requiring more detailed review
121814594 | 612 | Conduct: Initial Review (IR) | 2021-09-07 | Project Management - addressing project volume surge
121814594 | 612 | Conduct: Initial Review (IR) | 2021-09-21 | Project Management - addressing project volume surge
121814594 | 612 | Conduct: Initial Review (IR) | 2021-09-14 | Cus – requirement to provide a response to deficiency notice
121814594 | 612 | Conduct: Initial Review (IR) | 2021-10-05 | Engineering – requiring more detailed review
121814594 | 612 | Conduct: Initial Review (IR) | 2021-10-12 | Engineering – requiring more detailed review
121814594 | 612 | Conduct: Initial Review (IR) | 2021-10-26 | Engineering – requiring more detailed review
121814594 | 612 | Conduct: Initial Review (IR) | 2021-09-07 | Project Management - addressing project volume surge
121814594 | 612 | Conduct: Initial Review (IR) | 2021-09-21 | Project Management - addressing project volume surge
121814594 | 612 | Conduct: Initial Review (IR) | 2021-09-14 | Cus – requirement to provide a response to deficiency notice
121814594 | 612 | Conduct: Initial Review (IR) | 2021-10-05 | Engineering – requiring more detailed review
121814594 | 612 | Conduct: Initial Review (IR) | 2021-10-12 | Engineering – requiring more detailed review
121814594 | 612 | Conduct: Initial Review (IR) | 2021-10-26 | Engineering – requiring more detailed review
121814594 | 612 | Conduct: Initial Review (IR) | 2021-09-07 | Project Management - addressing project volume surge
121814594 | 612 | Conduct: Initial Review (IR) | 2021-09-21 | Project Management - addressing project volume surge
121833051 | 613 | Conduct: Initial Review (IR) | 2021-09-08 | Cus – requirement to provide a response to deficiency notice
121833051 | 613 | Conduct: Initial Review (IR) | 2021-09-15 | Cus – requirement to provide a response to deficiency notice
121836998 | 614 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
121836998 | 614 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
121836998 | 614 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
121836998 | 614 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
121836998 | 614 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
121836998 | 614 | Conduct: Initial Review (IR) | 2021-10-14 | Cus – requirement to provide a response to deficiency notice
121834255 | 615 | Conduct: Initial Review (IR) | 2021-09-09 | Cus – requirement to provide a response to deficiency notice
121834255 | 615 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
121834255 | 615 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
121771821 | 616 | Conduct: Initial Review (IR) | 2021-09-16 | Cus – requirement to provide a response to deficiency notice
121771821 | 616 | Conduct: Initial Review (IR) | 2021-09-09 | Project Management – requiring more detailed review
121778481 | 617 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
121778481 | 617 | Conduct: Initial Review (IR) | 2021-09-17 | Cus – requirement to provide a response to deficiency notice
121778481 | 617 | Conduct: Initial Review (IR) | 2021-09-24 | Cus – requirement to provide a response to deficiency notice
121778481 | 617 | Conduct: Initial Review (IR) | 2021-10-01 | Cus – requirement to provide a response to deficiency notice
121778481 | 617 | Conduct: Initial Review (IR) | 2021-10-08 | Cus – requirement to provide a response to deficiency notice
121778481 | 617 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
121778481 | 617 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
121778329 | 618 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
121778329 | 618 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
121778329 | 618 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
121562533 | 619 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
121562533 | 619 | Conduct: Supplemental Review (SR) | 2021-10-22 | Engineering – addressing project volume surge
121562533 | 619 | Conduct: Initial Review (IR) | 2021-09-17 | Engineering – requiring more detailed review
121562533 | 619 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
121562533 | 619 | Conduct: Supplemental Review (SR) | 2021-10-22 | Engineering – addressing project volume surge
121562533 | 619 | Conduct: Initial Review (IR) | 2021-09-17 | Engineering – requiring more detailed review
121562533 | 619 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
121562533 | 619 | Conduct: Supplemental Review (SR) | 2021-10-22 | Engineering – addressing project volume surge
121562533 | 619 | Conduct: Initial Review (IR) | 2021-09-17 | Engineering – requiring more detailed review
121818758 | 620 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
121689606 | 621 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
121553894 | 622 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
121553894 | 622 | Conduct: Initial Review (IR) | 2021-09-17 | Cus – requirement to provide a response to deficiency notice
121553894 | 622 | Conduct: Initial Review (IR) | 2021-09-24 | Cus – requirement to provide a response to deficiency notice
121623389 | 623 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
121787509 | 624 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
121707018 | 625 | Conduct: Initial Review (IR) | 2021-08-27 | Cus – requirement to provide a response to deficiency notice
121707018 | 625 | Conduct: Initial Review (IR) | 2021-09-10 | Cus – requirement to provide a response to deficiency notice
121707018 | 625 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
121707018 | 625 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
121707018 | 625 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
121707018 | 625 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
121707018 | 625 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
121692466 | 626 | Conduct: Initial Review (IR) | 2021-09-13 | Cus – requirement to provide a response to deficiency notice
121692466 | 626 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
121692466 | 626 | Conduct: Initial Review (IR) | 2021-09-27 | Cus – requirement to provide a response to deficiency notice
121735939 | 627 | Conduct: Initial Review (IR) | 2021-09-13 | Cus – requirement to provide a response to deficiency notice
121735939 | 627 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
121735939 | 627 | Conduct: Initial Review (IR) | 2021-09-27 | Cus – requirement to provide a response to deficiency notice
121735939 | 627 | Conduct: Initial Review (IR) | 2021-10-04 | Cus – requirement to provide a response to deficiency notice
121735939 | 627 | Conduct: Initial Review (IR) | 2021-10-11 | Cus – requirement to provide a response to deficiency notice
121735939 | 627 | Conduct: Initial Review (IR) | 2021-10-18 | Cus – requirement to provide a response to deficiency notice
121735939 | 627 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
121728482 | 628 | Conduct: Initial Review (IR) | 2021-09-13 | Cus – requirement to provide a response to deficiency notice
121865600 | 629 | Conduct: Initial Review (IR) | 2021-09-13 | Cus – requirement to provide a response to deficiency notice
121865600 | 629 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
121865600 | 629 | Conduct: Initial Review (IR) | 2021-09-27 | Cus – requirement to provide a response to deficiency notice
121786105 | 630 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
121786105 | 630 | Conduct: Initial Review (IR) | 2021-10-11 | Cus – requirement to provide a response to deficiency notice
121786105 | 630 | Conduct: Initial Review (IR) | 2021-11-01 | Engineering – requiring more detailed review
121786105 | 630 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
121786105 | 630 | Conduct: Initial Review (IR) | 2021-10-11 | Cus – requirement to provide a response to deficiency notice
121786105 | 630 | Conduct: Initial Review (IR) | 2021-11-01 | Engineering – requiring more detailed review
121786105 | 630 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
121786105 | 630 | Conduct: Initial Review (IR) | 2021-10-11 | Cus – requirement to provide a response to deficiency notice
121786105 | 630 | Conduct: Initial Review (IR) | 2021-11-01 | Engineering – requiring more detailed review
120573922 | 631 | Conduct: Initial Review (IR) | 2021-09-13 | Cus – requirement to provide a response to deficiency notice
121759601 | 632 | Conduct: Initial Review (IR) | 2021-09-13 | Cus – requirement to provide a response to deficiency notice
121759601 | 632 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
121759601 | 632 | Conduct: Initial Review (IR) | 2021-09-27 | Cus – requirement to provide a response to deficiency notice
121866227 | 633 | Conduct: Initial Review (IR) | 2021-09-14 | Cus – requirement to provide a response to deficiency notice
121866227 | 633 | Conduct: Initial Review (IR) | 2021-09-21 | Cus – requirement to provide a response to deficiency notice
121692314 | 634 | Conduct: Initial Review (IR) | 2021-09-15 | Cus – requirement to provide a response to deficiency notice
121692314 | 634 | Conduct: Initial Review (IR) | 2021-09-22 | Cus – requirement to provide a response to deficiency notice
121692314 | 634 | Conduct: Initial Review (IR) | 2021-09-29 | Cus – requirement to provide a response to deficiency notice
121845997 | 635 | Conduct: Initial Review (IR) | 2021-09-15 | Cus – requirement to provide a response to deficiency notice
121794704 | 636 | Conduct: Initial Review (IR) | 2021-09-15 | Cus – requirement to provide a response to deficiency notice
121794704 | 636 | Conduct: Initial Review (IR) | 2021-09-22 | Cus – requirement to provide a response to deficiency notice
121794704 | 636 | Conduct: Initial Review (IR) | 2021-09-29 | Engineering – requiring more detailed review
121733545 | 637 | Conduct: Initial Review (IR) | 2021-09-15 | Cus – requirement to provide a response to deficiency notice
121688173 | 638 | Conduct: Initial Review (IR) | 2021-09-15 | Cus – requirement to provide a response to deficiency notice
121688173 | 638 | Conduct: Initial Review (IR) | 2021-09-22 | Cus – requirement to provide a response to deficiency notice
121688173 | 638 | Conduct: Initial Review (IR) | 2021-09-29 | Cus – requirement to provide a response to deficiency notice
121688173 | 638 | Conduct: Initial Review (IR) | 2021-10-06 | Cus – requirement to provide a response to deficiency notice
121688173 | 638 | Conduct: Initial Review (IR) | 2021-10-13 | Cus – requirement to provide a response to deficiency notice
121688173 | 638 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
121688173 | 638 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
121551515 | 639 | Conduct: Initial Review (IR) | 2021-09-15 | Cus – requirement to provide a response to deficiency notice
121551515 | 639 | Conduct: Initial Review (IR) | 2021-09-22 | Cus – requirement to provide a response to deficiency notice
121551515 | 639 | Conduct: Initial Review (IR) | 2021-09-29 | Cus – requirement to provide a response to deficiency notice
119051461 | 640 | Conduct: Initial Review (IR) | 2021-09-15 | Cus – requirement to provide a response to deficiency notice
120464886 | 641 | Conduct: Initial Review (IR) | 2021-09-17 | Cus – requirement to provide a response to deficiency notice
120464886 | 641 | Conduct: Initial Review (IR) | 2021-09-24 | Cus – requirement to provide a response to deficiency notice
120464886 | 641 | Conduct: Initial Review (IR) | 2021-10-01 | Cus – requirement to provide a response to deficiency notice
120464886 | 641 | Conduct: Initial Review (IR) | 2021-10-08 | Cus – requirement to provide a response to deficiency notice
120464886 | 641 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
120464886 | 641 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
121886079 | 642 | Conduct: Initial Review (IR) | 2021-09-17 | Cus – requirement to provide a response to deficiency notice
121886079 | 642 | Conduct: Initial Review (IR) | 2021-09-24 | Cus – requirement to provide a response to deficiency notice
121861994 | 643 | Conduct: Initial Review (IR) | 2021-09-17 | Cus – requirement to provide a response to deficiency notice
121886398 | 644 | Conduct: Initial Review (IR) | 2021-09-17 | Cus – requirement to provide a response to deficiency notice
121898995 | 645 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
121898995 | 645 | Conduct: Initial Review (IR) | 2021-09-27 | Cus – requirement to provide a response to deficiency notice
121898995 | 645 | Conduct: Initial Review (IR) | 2021-10-04 | Cus – requirement to provide a response to deficiency notice
121898995 | 645 | Conduct: Initial Review (IR) | 2021-10-11 | Cus – requirement to provide a response to deficiency notice
121898995 | 645 | Conduct: Initial Review (IR) | 2021-10-18 | Cus – requirement to provide a response to deficiency notice
121898995 | 645 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
121896755 | 646 | Conduct: Initial Review (IR) | 2021-09-20 | Cus – requirement to provide a response to deficiency notice
121388860 | 647 | Conduct: Initial Review (IR) | 2021-09-21 | Cus – requirement to provide a response to deficiency notice
121388860 | 647 | Conduct: Initial Review (IR) | 2021-09-28 | Engineering – requiring more detailed review
121902629 | 648 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
121902629 | 648 | Conduct: Initial Review (IR) | 2021-09-20 | Engineering – requiring more detailed review
121902629 | 648 | Conduct: Initial Review (IR) | 2021-09-27 | Engineering – requiring more detailed review
121902629 | 648 | Conduct: Initial Review (IR) | 2021-10-11 | Engineering – requiring more detailed review
121902629 | 648 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
121902629 | 648 | Conduct: Initial Review (IR) | 2021-11-15 | Cus – requirement to provide a response to deficiency notice
121902629 | 648 | Conduct: Initial Review (IR) | 2021-11-08 | Customer – requirement to provide corrected information
121902629 | 648 | Conduct: Initial Review (IR) | 2021-09-20 | Engineering – requiring more detailed review
121902629 | 648 | Conduct: Initial Review (IR) | 2021-09-27 | Engineering – requiring more detailed review
121902629 | 648 | Conduct: Initial Review (IR) | 2021-10-11 | Engineering – requiring more detailed review
121902629 | 648 | Conduct: Initial Review (IR) | 2021-11-30 | Engineering – requiring more detailed review
121902629 | 648 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
121902629 | 648 | Conduct: Initial Review (IR) | 2021-11-15 | Cus – requirement to provide a response to deficiency notice
121902629 | 648 | Conduct: Initial Review (IR) | 2021-11-08 | Customer – requirement to provide corrected information
121902629 | 648 | Conduct: Initial Review (IR) | 2021-09-20 | Engineering – requiring more detailed review
121902629 | 648 | Conduct: Initial Review (IR) | 2021-09-27 | Engineering – requiring more detailed review
121902629 | 648 | Conduct: Initial Review (IR) | 2021-10-11 | Engineering – requiring more detailed review
121902629 | 648 | Conduct: Initial Review (IR) | 2021-11-30 | Engineering – requiring more detailed review
121845602 | 649 | Conduct: Initial Review (IR) | 2021-09-22 | Cus – requirement to provide a response to deficiency notice
121655441 | 650 | Conduct: Initial Review (IR) | 2021-09-22 | Cus – requirement to provide a response to deficiency notice
121655441 | 650 | Conduct: Initial Review (IR) | 2021-09-29 | Cus – requirement to provide a response to deficiency notice
121655441 | 650 | Conduct: Initial Review (IR) | 2021-10-13 | Cus – requirement to provide a response to deficiency notice
121655441 | 650 | Conduct: Initial Review (IR) | 2021-10-06 | Project Management - addressing project volume surge
121799926 | 651 | Conduct: Initial Review (IR) | 2021-10-06 | Cus – requirement to provide a response to deficiency notice
121799926 | 651 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
121799926 | 651 | Conduct: Initial Review (IR) | 2021-10-06 | Cus – requirement to provide a response to deficiency notice
121799926 | 651 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
121799926 | 651 | Conduct: Initial Review (IR) | 2021-11-18 | Cus – requirement to provide a response to deficiency notice
121799926 | 651 | Conduct: Initial Review (IR) | 2021-10-06 | Cus – requirement to provide a response to deficiency notice
121799926 | 651 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
121799926 | 651 | Conduct: Initial Review (IR) | 2021-11-18 | Cus – requirement to provide a response to deficiency notice
121891416 | 652 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
121891416 | 652 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
121891416 | 652 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
121891416 | 652 | Conduct: Initial Review (IR) | 2021-10-14 | Cus – requirement to provide a response to deficiency notice
121891416 | 652 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
121913957 | 653 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
121913957 | 653 | Conduct: Initial Review (IR) | 2021-10-14 | Cus – requirement to provide a response to deficiency notice
121913957 | 653 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
121913957 | 653 | Conduct: Initial Review (IR) | 2021-10-14 | Cus – requirement to provide a response to deficiency notice
121913957 | 653 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
121913957 | 653 | Conduct: Initial Review (IR) | 2021-10-14 | Cus – requirement to provide a response to deficiency notice
121757252 | 654 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
121757252 | 654 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
121757252 | 654 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
121677750 | 655 | Conduct: Initial Review (IR) | 2021-09-23 | Cus – requirement to provide a response to deficiency notice
121677750 | 655 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
121677750 | 655 | Conduct: Initial Review (IR) | 2021-10-07 | Cus – requirement to provide a response to deficiency notice
121677750 | 655 | Conduct: Initial Review (IR) | 2021-10-14 | Cus – requirement to provide a response to deficiency notice
121677750 | 655 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
119124637 | 656 | Conduct: Initial Review (IR) | 2021-09-27 | Cus – requirement to provide a response to deficiency notice
121913626 | 657 | Conduct: Initial Review (IR) | 2021-09-27 | Cus – requirement to provide a response to deficiency notice
121925834 | 658 | Conduct: Initial Review (IR) | 2021-09-28 | Cus – requirement to provide a response to deficiency notice
121925834 | 658 | Conduct: Initial Review (IR) | 2021-10-05 | Cus – requirement to provide a response to deficiency notice
121925834 | 658 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
121925834 | 658 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
121925834 | 658 | Conduct: Initial Review (IR) | 2021-10-12 | Customer – requirement to provide corrected information
121809853 | 659 | Conduct: Initial Review (IR) | 2021-09-29 | Cus – requirement to provide a response to deficiency notice
121809853 | 659 | Conduct: Initial Review (IR) | 2021-10-13 | Cus – requirement to provide a response to deficiency notice
121809853 | 659 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
121646426 | 660 | Conduct: Initial Review (IR) | 2021-09-29 | Cus – requirement to provide a response to deficiency notice
121439435 | 661 | Conduct: Initial Review (IR) | 2021-09-30 | Cus – requirement to provide a response to deficiency notice
121439435 | 661 | Conduct: Initial Review (IR) | 2021-09-23 | Project Management – requiring more detailed review
121953249 | 662 | Conduct: Initial Review (IR) | 2021-10-05 | Cus – requirement to provide a response to deficiency notice
121953249 | 662 | Conduct: Initial Review (IR) | 2021-10-12 | Engineering – requiring more detailed review
121953249 | 662 | Conduct: Initial Review (IR) | 2021-10-05 | Cus – requirement to provide a response to deficiency notice
121953249 | 662 | Conduct: Initial Review (IR) | 2021-10-12 | Engineering – requiring more detailed review
121953249 | 662 | Conduct: Initial Review (IR) | 2021-10-05 | Cus – requirement to provide a response to deficiency notice
121953249 | 662 | Conduct: Initial Review (IR) | 2021-10-12 | Engineering – requiring more detailed review
121820385 | 663 | Conduct: Initial Review (IR) | 2021-10-05 | Cus – requirement to provide a response to deficiency notice
121820385 | 663 | Conduct: Initial Review (IR) | 2021-10-12 | Cus – requirement to provide a response to deficiency notice
121820385 | 663 | Conduct: Initial Review (IR) | 2021-10-19 | Customer – requirement to provide corrected information
121907680 | 664 | Conduct: Initial Review (IR) | 2021-10-06 | Cus – requirement to provide a response to deficiency notice
121907680 | 664 | Conduct: Initial Review (IR) | 2021-10-13 | Engineering – requiring more detailed review
121907680 | 664 | Conduct: Initial Review (IR) | 2021-10-06 | Cus – requirement to provide a response to deficiency notice
121907680 | 664 | Conduct: Supplemental Review (SR) | 2021-12-24 | Cus – requirement to provide a response to deficiency notice
121907680 | 664 | Conduct: Supplemental Review (SR) | 2021-12-08 | Engineering – addressing project volume surge
121907680 | 664 | Conduct: Supplemental Review (SR) | 2021-12-14 | Engineering – addressing project volume surge
121907680 | 664 | Conduct: Supplemental Review (SR) | 2021-12-17 | Engineering – addressing project volume surge
121907680 | 664 | Conduct: Initial Review (IR) | 2021-10-13 | Engineering – requiring more detailed review
121907680 | 664 | Conduct: Initial Review (IR) | 2021-10-06 | Cus – requirement to provide a response to deficiency notice
121907680 | 664 | Conduct: Supplemental Review (SR) | 2021-12-24 | Cus – requirement to provide a response to deficiency notice
121907680 | 664 | Conduct: Supplemental Review (SR) | 2021-12-08 | Engineering – addressing project volume surge
121907680 | 664 | Conduct: Supplemental Review (SR) | 2021-12-14 | Engineering – addressing project volume surge
121907680 | 664 | Conduct: Supplemental Review (SR) | 2021-12-17 | Engineering – addressing project volume surge
121907680 | 664 | Conduct: Initial Review (IR) | 2021-10-13 | Engineering – requiring more detailed review
121336829 | 665 | Conduct: Initial Review (IR) | 2021-10-08 | Cus – requirement to provide a response to deficiency notice
121336829 | 665 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
121958033 | 666 | Conduct: Initial Review (IR) | 2021-10-08 | Cus – requirement to provide a response to deficiency notice
121958033 | 666 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
121958033 | 666 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
121984003 | 667 | Conduct: Initial Review (IR) | 2021-10-12 | Cus – requirement to provide a response to deficiency notice
121959988 | 668 | Conduct: Initial Review (IR) | 2021-11-01 | Cus – requirement to provide a response to deficiency notice
121959988 | 668 | Conduct: Initial Review (IR) | 2021-10-18 | Engineering – requiring more detailed review
121959988 | 668 | Conduct: Initial Review (IR) | 2021-11-01 | Cus – requirement to provide a response to deficiency notice
121959988 | 668 | Conduct: Initial Review (IR) | 2021-10-18 | Engineering – requiring more detailed review
121959988 | 668 | Conduct: Initial Review (IR) | 2021-11-01 | Cus – requirement to provide a response to deficiency notice
121959988 | 668 | Conduct: Initial Review (IR) | 2021-10-18 | Engineering – requiring more detailed review
121939027 | 669 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
121939027 | 669 | Conduct: Initial Review (IR) | 2021-10-22 | Engineering – addressing project volume surge
120673552 | 670 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
120673552 | 670 | Conduct: Initial Review (IR) | 2021-10-22 | Customer – requirement to provide corrected information
120673552 | 670 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
120673552 | 670 | Conduct: Initial Review (IR) | 2021-10-22 | Customer – requirement to provide corrected information
120673552 | 670 | Conduct: Initial Review (IR) | 2021-11-05 | Customer – requirement to provide corrected information
120673552 | 670 | Conduct: Initial Review (IR) | 2021-10-29 | Engineering – addressing project volume surge
120673552 | 670 | Conduct: Initial Review (IR) | 2021-11-12 | Engineering – addressing project volume surge
120673552 | 670 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
120673552 | 670 | Conduct: Initial Review (IR) | 2021-10-22 | Customer – requirement to provide corrected information
120673552 | 670 | Conduct: Initial Review (IR) | 2021-11-05 | Customer – requirement to provide corrected information
120673552 | 670 | Conduct: Initial Review (IR) | 2021-10-29 | Engineering – addressing project volume surge
120673552 | 670 | Conduct: Initial Review (IR) | 2021-11-12 | Engineering – addressing project volume surge
121845177 | 671 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
121845177 | 671 | Conduct: Initial Review (IR) | 2021-10-22 | Engineering – requiring more detailed review
121845177 | 671 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
121845177 | 671 | Conduct: Initial Review (IR) | 2021-10-29 | Cus – requirement to provide a response to deficiency notice
121845177 | 671 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – addressing project volume surge
121845177 | 671 | Conduct: Initial Review (IR) | 2021-10-22 | Engineering – requiring more detailed review
121845177 | 671 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
121845177 | 671 | Conduct: Initial Review (IR) | 2021-10-29 | Cus – requirement to provide a response to deficiency notice
121845177 | 671 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – addressing project volume surge
121845177 | 671 | Conduct: Initial Review (IR) | 2021-10-22 | Engineering – requiring more detailed review
121899639 | 672 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-10-29 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-11-05 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-11-12 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-11-26 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-12-03 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-12-10 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-12-17 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-12-24 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-12-31 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-01-07 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-01-14 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-01-21 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-01-28 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-11-19 | Engineering – requiring more detailed review
121899639 | 672 | Conduct: Initial Review (IR) | 2021-12-03 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-10-29 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-11-05 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-11-12 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-11-26 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-12-10 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-12-17 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-12-24 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-12-31 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-01-07 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-01-14 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-01-21 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-01-28 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-02-04 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-02-11 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-02-18 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-02-25 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-03-04 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-03-11 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-03-18 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-03-25 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-04-01 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-04-08 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-04-15 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2022-04-22 | Cus – requirement to provide a response to deficiency notice
121899639 | 672 | Conduct: Initial Review (IR) | 2021-11-19 | Engineering – requiring more detailed review
121927303 | 673 | Conduct: Initial Review (IR) | 2021-10-15 | Cus – requirement to provide a response to deficiency notice
121927303 | 673 | Conduct: Initial Review (IR) | 2021-10-22 | Project Management – requiring more detailed review
121982119 | 674 | Conduct: Initial Review (IR) | 2021-10-18 | Cus – requirement to provide a response to deficiency notice
121982119 | 674 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
121982363 | 675 | Conduct: Initial Review (IR) | 2021-10-18 | Cus – requirement to provide a response to deficiency notice
121985591 | 676 | Conduct: Initial Review (IR) | 2021-10-18 | Cus – requirement to provide a response to deficiency notice
121985591 | 676 | Conduct: Initial Review (IR) | 2021-10-25 | Customer – requirement to provide corrected information
122017193 | 677 | Conduct: Initial Review (IR) | 2021-10-18 | Cus – requirement to provide a response to deficiency notice
122017193 | 677 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
122018360 | 678 | Conduct: Initial Review (IR) | 2021-10-18 | Cus – requirement to provide a response to deficiency notice
122018360 | 678 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
122020797 | 679 | Conduct: Initial Review (IR) | 2021-10-18 | Cus – requirement to provide a response to deficiency notice
122020797 | 679 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
119983262 | 680 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
122015269 | 681 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
122015269 | 681 | Conduct: Initial Review (IR) | 2021-10-18 | Customer – requirement to provide corrected information
122016917 | 682 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
122016917 | 682 | Conduct: Initial Review (IR) | 2021-10-18 | Customer – requirement to provide corrected information
122018583 | 683 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
122018583 | 683 | Conduct: Initial Review (IR) | 2021-10-18 | Customer – requirement to provide corrected information
122018691 | 684 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
122018691 | 684 | Conduct: Initial Review (IR) | 2021-10-18 | Customer – requirement to provide corrected information
122016171 | 685 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
122016171 | 685 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122034666 | 686 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
122034666 | 686 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122035525 | 687 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
122035525 | 687 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122036433 | 688 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
122036433 | 688 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122036670 | 689 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
122036670 | 689 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122037831 | 690 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
122037831 | 690 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122042110 | 691 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
122042110 | 691 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122042399 | 692 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
122042399 | 692 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
121985967 | 693 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
121985967 | 693 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
120260211 | 694 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
120260211 | 694 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
121993819 | 695 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
121993819 | 695 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122019489 | 696 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
122019489 | 696 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
121990090 | 697 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
121990090 | 697 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
121991357 | 698 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
121991357 | 698 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122034572 | 699 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
122034572 | 699 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122035833 | 700 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
122035833 | 700 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122037120 | 701 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
122037120 | 701 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122037838 | 702 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
122037838 | 702 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122041244 | 703 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
122041244 | 703 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122041472 | 704 | Conduct: Initial Review (IR) | 2021-10-19 | Cus – requirement to provide a response to deficiency notice
122041472 | 704 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
121992389 | 705 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
121992389 | 705 | Conduct: Initial Review (IR) | 2021-10-19 | Customer – requirement to provide corrected information
121995772 | 706 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
121995772 | 706 | Conduct: Initial Review (IR) | 2021-10-19 | Customer – requirement to provide corrected information
121960301 | 707 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
121960301 | 707 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
121973879 | 708 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
121973879 | 708 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122034267 | 709 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
122034267 | 709 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122041057 | 710 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
122041057 | 710 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122042858 | 711 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
122042858 | 711 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122044208 | 712 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
122044208 | 712 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122048298 | 713 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
122048298 | 713 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122052420 | 714 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
122052420 | 714 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
121591063 | 715 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
121591063 | 715 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
121978133 | 716 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
121978133 | 716 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122042811 | 717 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
122042811 | 717 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122046216 | 718 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
122046216 | 718 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122047071 | 719 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
122047071 | 719 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122047566 | 720 | Conduct: Initial Review (IR) | 2021-10-20 | Cus – requirement to provide a response to deficiency notice
122047566 | 720 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122051190 | 721 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122051190 | 721 | Conduct: Initial Review (IR) | 2021-10-20 | Engineering – requiring more detailed review
121961940 | 722 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
122009738 | 723 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
122012698 | 724 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
122041164 | 725 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
122045278 | 726 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
122045478 | 727 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
122048313 | 728 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
122053156 | 729 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
122053322 | 730 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
122056284 | 731 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
122056674 | 732 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
122058292 | 733 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
121986370 | 734 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
121993177 | 735 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
121996381 | 736 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
121996776 | 737 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
122009847 | 738 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
122012452 | 739 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
122056885 | 740 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
122057471 | 741 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
122048245 | 742 | Conduct: Initial Review (IR) | 2021-10-21 | Cus – requirement to provide a response to deficiency notice
122014720 | 743 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
122057175 | 744 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
122057178 | 745 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
122061575 | 746 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
122063551 | 747 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
122064150 | 748 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
122064175 | 749 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
122065886 | 750 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
122067816 | 751 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
122067959 | 752 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
122071964 | 753 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
122073771 | 754 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
122058957 | 755 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
122049855 | 756 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
122050996 | 757 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
122065735 | 758 | Conduct: Initial Review (IR) | 2021-10-22 | Cus – requirement to provide a response to deficiency notice
120463098 | 759 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
122059094 | 760 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
122067205 | 761 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
122070328 | 762 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
122071695 | 763 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
122071751 | 764 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
122073214 | 765 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
122076572 | 766 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
122065447 | 767 | Conduct: Initial Review (IR) | 2021-10-25 | Cus – requirement to provide a response to deficiency notice
122059587 | 768 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122073218 | 769 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122060441 | 770 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122077673 | 771 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122079190 | 772 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122080743 | 773 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122082656 | 774 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122083195 | 775 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122083270 | 776 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122085725 | 777 | Conduct: Initial Review (IR) | 2021-10-26 | Cus – requirement to provide a response to deficiency notice
122086369 | 778 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122086444 | 779 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122086978 | 780 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122087552 | 781 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122087608 | 782 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122063917 | 783 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122087758 | 784 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122087879 | 785 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122088017 | 786 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122090677 | 787 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
122091304 | 788 | Conduct: Initial Review (IR) | 2021-10-27 | Cus – requirement to provide a response to deficiency notice
114207721 | 789 | Conduct: Initial Review (IR) | 2021-01-05 | Customer
114207721 | 789 | Conduct: Initial Review (IR) | 2021-01-12 | Customer
114207721 | 789 | Conduct: Initial Review (IR) | 2021-01-20 | Customer
114207721 | 789 | Conduct: Initial Review (IR) | 2021-01-27 | Customer
114207721 | 789 | Conduct: Initial Review (IR) | 2021-02-03 | Customer
114207721 | 789 | Conduct: Initial Review (IR) | 2021-02-10 | Customer
114207721 | 789 | Conduct: Initial Review (IR) | 2021-02-18 | Customer
114207721 | 789 | Conduct: Initial Review (IR) | 2021-02-25 | Customer
114207721 | 789 | Conduct: Initial Review (IR) | 2021-03-04 | Customer
114207721 | 789 | Conduct: Initial Review (IR) | 2021-03-11 | Customer
114207721 | 789 | Conduct: Initial Review (IR) | 2021-03-18 | Customer
114207721 | 789 | Conduct: Initial Review (IR) | 2021-03-25 | Customer
114207721 | 789 | Conduct: Initial Review (IR) | 2021-04-01 | Customer
114207721 | 789 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
114208128 | 790 | Conduct: Initial Review (IR) | 2021-01-05 | Customer
114208128 | 790 | Conduct: Initial Review (IR) | 2021-01-12 | Customer
114208128 | 790 | Conduct: Initial Review (IR) | 2021-01-20 | Customer
114208128 | 790 | Conduct: Initial Review (IR) | 2021-01-27 | Customer
114208128 | 790 | Conduct: Initial Review (IR) | 2021-02-03 | Customer
114208128 | 790 | Conduct: Initial Review (IR) | 2021-02-10 | Customer
114208128 | 790 | Conduct: Initial Review (IR) | 2021-02-18 | Customer
114208128 | 790 | Conduct: Initial Review (IR) | 2021-02-25 | Customer
114208128 | 790 | Conduct: Initial Review (IR) | 2021-03-04 | Customer
114208128 | 790 | Conduct: Initial Review (IR) | 2021-03-11 | Customer
114208128 | 790 | Conduct: Initial Review (IR) | 2021-03-18 | Customer
114208128 | 790 | Conduct: Initial Review (IR) | 2021-03-25 | Customer
114208128 | 790 | Conduct: Initial Review (IR) | 2021-04-01 | Customer
114208128 | 790 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
114210878 | 791 | Conduct: Initial Review (IR) | 2021-01-05 | Customer
114210878 | 791 | Conduct: Initial Review (IR) | 2021-01-12 | Customer
114210878 | 791 | Conduct: Initial Review (IR) | 2021-01-20 | Customer
114210878 | 791 | Conduct: Initial Review (IR) | 2021-01-27 | Customer
114210878 | 791 | Conduct: Initial Review (IR) | 2021-02-03 | Customer
114210878 | 791 | Conduct: Initial Review (IR) | 2021-02-10 | Customer
114210878 | 791 | Conduct: Initial Review (IR) | 2021-02-18 | Customer
114210878 | 791 | Conduct: Initial Review (IR) | 2021-02-25 | Customer
114210878 | 791 | Conduct: Initial Review (IR) | 2021-03-04 | Customer
114210878 | 791 | Conduct: Initial Review (IR) | 2021-03-11 | Customer
114210878 | 791 | Conduct: Initial Review (IR) | 2021-03-18 | Customer
114210878 | 791 | Conduct: Initial Review (IR) | 2021-03-25 | Customer
114210878 | 791 | Conduct: Initial Review (IR) | 2021-04-01 | Customer
114210878 | 791 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
114211098 | 792 | Conduct: Initial Review (IR) | 2020-12-31 | Customer
114211098 | 792 | Conduct: Initial Review (IR) | 2021-01-08 | Customer
114211098 | 792 | Conduct: Initial Review (IR) | 2021-01-15 | Customer
114211098 | 792 | Conduct: Initial Review (IR) | 2021-01-25 | Customer
114211098 | 792 | Conduct: Initial Review (IR) | 2021-02-01 | Customer
114211098 | 792 | Conduct: Initial Review (IR) | 2021-02-08 | Customer
114211098 | 792 | Conduct: Initial Review (IR) | 2021-02-16 | Customer
114211098 | 792 | Conduct: Initial Review (IR) | 2021-02-23 | Customer
114211098 | 792 | Conduct: Initial Review (IR) | 2021-03-02 | Customer
114211098 | 792 | Conduct: Initial Review (IR) | 2021-03-09 | Customer
114211098 | 792 | Conduct: Initial Review (IR) | 2021-03-16 | Customer
114211098 | 792 | Conduct: Initial Review (IR) | 2021-03-23 | Customer
114211098 | 792 | Conduct: Initial Review (IR) | 2021-03-30 | Customer
114210835 | 793 | Conduct: Initial Review (IR) | 2021-01-05 | Customer
114210835 | 793 | Conduct: Initial Review (IR) | 2021-01-12 | Customer
114210835 | 793 | Conduct: Initial Review (IR) | 2021-01-20 | Customer
114210835 | 793 | Conduct: Initial Review (IR) | 2021-01-27 | Customer
114210835 | 793 | Conduct: Initial Review (IR) | 2021-02-03 | Customer
114210835 | 793 | Conduct: Initial Review (IR) | 2021-02-10 | Customer
114210835 | 793 | Conduct: Initial Review (IR) | 2021-02-18 | Customer
114210835 | 793 | Conduct: Initial Review (IR) | 2021-02-25 | Customer
114210835 | 793 | Conduct: Initial Review (IR) | 2021-03-04 | Customer
114210835 | 793 | Conduct: Initial Review (IR) | 2021-03-11 | Customer
114210835 | 793 | Conduct: Initial Review (IR) | 2021-03-18 | Customer
114210835 | 793 | Conduct: Initial Review (IR) | 2021-03-25 | Customer
114210835 | 793 | Conduct: Initial Review (IR) | 2021-04-01 | Customer
114210835 | 793 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
114210835 | 793 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
114205191 | 794 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
114205191 | 794 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
114211375 | 795 | Conduct: Initial Review (IR) | 2020-12-30 | Customer
114211375 | 795 | Conduct: Initial Review (IR) | 2021-01-07 | Customer
114211375 | 795 | Conduct: Initial Review (IR) | 2021-01-14 | Customer
114211375 | 795 | Conduct: Initial Review (IR) | 2021-01-22 | Customer
114211375 | 795 | Conduct: Initial Review (IR) | 2021-01-29 | Customer
114211375 | 795 | Conduct: Initial Review (IR) | 2021-02-05 | Customer
114211375 | 795 | Conduct: Initial Review (IR) | 2021-02-12 | Customer
114211375 | 795 | Conduct: Initial Review (IR) | 2021-02-22 | Customer
114211375 | 795 | Conduct: Initial Review (IR) | 2021-03-01 | Customer
114211375 | 795 | Conduct: Initial Review (IR) | 2021-03-08 | Customer
114211375 | 795 | Conduct: Initial Review (IR) | 2021-03-15 | Customer
114211375 | 795 | Conduct: Initial Review (IR) | 2021-03-22 | Customer
114211375 | 795 | Conduct: Initial Review (IR) | 2021-03-29 | Customer
114211375 | 795 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
114210155 | 796 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
114211216 | 797 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
114211235 | 798 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
114211237 | 799 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
114231363 | 800 | Conduct: Initial Review (IR) | 2020-12-31 | Customer
114231363 | 800 | Conduct: Initial Review (IR) | 2021-01-08 | Customer
114231363 | 800 | Conduct: Initial Review (IR) | 2021-01-15 | Customer
114231363 | 800 | Conduct: Initial Review (IR) | 2021-01-25 | Customer
114231363 | 800 | Conduct: Initial Review (IR) | 2021-02-01 | Customer
114231363 | 800 | Conduct: Initial Review (IR) | 2021-02-08 | Customer
114231363 | 800 | Conduct: Initial Review (IR) | 2021-02-16 | Customer
114231363 | 800 | Conduct: Initial Review (IR) | 2021-02-23 | Customer
114231363 | 800 | Conduct: Initial Review (IR) | 2021-03-02 | Customer
114231363 | 800 | Conduct: Initial Review (IR) | 2021-03-09 | Customer
114231363 | 800 | Conduct: Initial Review (IR) | 2021-03-16 | Customer
114231363 | 800 | Conduct: Initial Review (IR) | 2021-03-23 | Customer
114231363 | 800 | Conduct: Initial Review (IR) | 2021-03-30 | Customer
114210512 | 801 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
114210516 | 802 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
114210516 | 802 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
114211045 | 803 | Conduct: Initial Review (IR) | 2021-01-05 | Customer
114211045 | 803 | Conduct: Initial Review (IR) | 2021-01-12 | Customer
114211045 | 803 | Conduct: Initial Review (IR) | 2021-01-20 | Customer
114211045 | 803 | Conduct: Initial Review (IR) | 2021-01-27 | Customer
114211045 | 803 | Conduct: Initial Review (IR) | 2021-02-03 | Customer
114211045 | 803 | Conduct: Initial Review (IR) | 2021-02-10 | Customer
114211045 | 803 | Conduct: Initial Review (IR) | 2021-02-18 | Customer
114211045 | 803 | Conduct: Initial Review (IR) | 2021-02-25 | Customer
114211045 | 803 | Conduct: Initial Review (IR) | 2021-03-04 | Customer
114211045 | 803 | Conduct: Initial Review (IR) | 2021-03-11 | Customer
114211045 | 803 | Conduct: Initial Review (IR) | 2021-03-18 | Customer
114211045 | 803 | Conduct: Initial Review (IR) | 2021-03-25 | Customer
114211045 | 803 | Conduct: Initial Review (IR) | 2021-04-01 | Customer
114211045 | 803 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
114211045 | 803 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
114258453 | 804 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
114258453 | 804 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
114211346 | 805 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
114211328 | 806 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
114211283 | 807 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
114211303 | 808 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
114211324 | 809 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
114211427 | 810 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
114457817 | 811 | Conduct: Initial Review (IR) | 2020-12-31 | Customer
114457817 | 811 | Conduct: Initial Review (IR) | 2021-01-08 | Customer
114457817 | 811 | Conduct: Initial Review (IR) | 2021-01-15 | Customer
114457817 | 811 | Conduct: Initial Review (IR) | 2021-01-25 | Customer
114457817 | 811 | Conduct: Initial Review (IR) | 2021-02-01 | Customer
114457817 | 811 | Conduct: Initial Review (IR) | 2021-02-08 | Customer
114457817 | 811 | Conduct: Initial Review (IR) | 2021-02-16 | Customer
114457817 | 811 | Conduct: Initial Review (IR) | 2021-02-23 | Customer
114457817 | 811 | Conduct: Initial Review (IR) | 2021-03-02 | Customer
114457817 | 811 | Conduct: Initial Review (IR) | 2021-03-09 | Customer
114457817 | 811 | Conduct: Initial Review (IR) | 2021-03-16 | Customer
114457817 | 811 | Conduct: Initial Review (IR) | 2021-03-23 | Customer
114457817 | 811 | Conduct: Initial Review (IR) | 2021-03-30 | Customer
114457817 | 811 | Conduct: Initial Review (IR) | 2021-09-08 | Engineering – requiring more detailed review
115388307 | 812 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
115388307 | 812 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
114949568 | 813 | Conduct: Initial Review (IR) | 2021-01-05 | Customer
114949568 | 813 | Conduct: Initial Review (IR) | 2021-01-20 | Customer
114949568 | 813 | Conduct: Initial Review (IR) | 2021-01-28 | Customer
117464489 | 814 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
114211760 | 815 | Conduct: Initial Review (IR) | 2021-01-04 | Customer
114211760 | 815 | Conduct: Initial Review (IR) | 2021-01-11 | Customer
114211760 | 815 | Conduct: Initial Review (IR) | 2021-01-19 | Customer
114211760 | 815 | Conduct: Initial Review (IR) | 2021-01-26 | Customer
114211760 | 815 | Conduct: Initial Review (IR) | 2021-02-02 | Customer
114211760 | 815 | Conduct: Initial Review (IR) | 2021-02-09 | Customer
114211760 | 815 | Conduct: Initial Review (IR) | 2021-02-17 | Customer
114211760 | 815 | Conduct: Initial Review (IR) | 2021-02-24 | Customer
114211760 | 815 | Conduct: Initial Review (IR) | 2021-03-03 | Customer
114211760 | 815 | Conduct: Initial Review (IR) | 2021-03-10 | Customer
114211760 | 815 | Conduct: Initial Review (IR) | 2021-03-17 | Customer
114211760 | 815 | Conduct: Initial Review (IR) | 2021-03-24 | Customer
114211760 | 815 | Conduct: Initial Review (IR) | 2021-03-31 | Customer
114211796 | 816 | Conduct: Initial Review (IR) | 2021-01-04 | Customer
114211796 | 816 | Conduct: Initial Review (IR) | 2021-01-11 | Customer
114211796 | 816 | Conduct: Initial Review (IR) | 2021-01-19 | Customer
114211796 | 816 | Conduct: Initial Review (IR) | 2021-01-26 | Customer
114211796 | 816 | Conduct: Initial Review (IR) | 2021-02-02 | Customer
114211796 | 816 | Conduct: Initial Review (IR) | 2021-02-09 | Customer
114211796 | 816 | Conduct: Initial Review (IR) | 2021-02-17 | Customer
114211796 | 816 | Conduct: Initial Review (IR) | 2021-02-24 | Customer
114211796 | 816 | Conduct: Initial Review (IR) | 2021-03-03 | Customer
114211796 | 816 | Conduct: Initial Review (IR) | 2021-03-10 | Customer
114211796 | 816 | Conduct: Initial Review (IR) | 2021-03-17 | Customer
114211796 | 816 | Conduct: Initial Review (IR) | 2021-03-24 | Customer
114211796 | 816 | Conduct: Initial Review (IR) | 2021-03-31 | Customer
114211796 | 816 | Conduct: Initial Review (IR) | 2021-04-27 | Customer
114211796 | 816 | Conduct: Initial Review (IR) | 2021-08-27 | Customer
117882412 | 817 | Conduct: Initial Review (IR) | 2021-01-05 | Customer
117882412 | 817 | Conduct: Initial Review (IR) | 2021-01-20 | Customer
117882412 | 817 | Conduct: Initial Review (IR) | 2021-01-27 | Customer
117882412 | 817 | Conduct: Initial Review (IR) | 2021-02-03 | Customer
117882412 | 817 | Conduct: Initial Review (IR) | 2021-02-10 | Customer
117882412 | 817 | Conduct: Initial Review (IR) | 2021-03-03 | Customer
117882412 | 817 | Conduct: Initial Review (IR) | 2021-03-10 | Customer
118021850 | 818 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
118133962 | 819 | Conduct: Initial Review (IR) | 2021-04-09 | Customer
118577446 | 820 | Conduct: Initial Review (IR) | 2020-12-31 | Customer
118577446 | 820 | Conduct: Initial Review (IR) | 2021-01-29 | Customer
118715869 | 821 | Conduct: Screens Q and R | 2021-01-05 | Customer
118715869 | 821 | Conduct: Screens Q and R | 2021-01-12 | Customer
118715869 | 821 | Conduct: Screens Q and R | 2021-01-20 | Customer
118715869 | 821 | Conduct: Screens Q and R | 2021-01-27 | Customer
118715869 | 821 | Conduct: Screens Q and R | 2021-02-03 | Customer
118715869 | 821 | Conduct: Screens Q and R | 2021-02-10 | Customer
118715869 | 821 | Conduct: Screens Q and R | 2021-02-18 | Customer
118715869 | 821 | Conduct: Screens Q and R | 2021-02-25 | Customer
118715869 | 821 | Conduct: Screens Q and R | 2021-03-04 | Customer
118715869 | 821 | Conduct: Screens Q and R | 2021-03-11 | Customer
118715869 | 821 | Conduct: Screens Q and R | 2021-03-18 | Customer
115785439 | 822 | Tender Draft IA | 2021-04-30 | Customer
119064736 | 823 | Conduct: Initial Review (IR) | 2021-01-05 | Customer
119064736 | 823 | Conduct: Initial Review (IR) | 2021-01-26 | Customer
119064736 | 823 | Conduct: Initial Review (IR) | 2021-02-02 | Customer
119064736 | 823 | Conduct: Initial Review (IR) | 2021-02-09 | Customer
119108125 | 824 | Conduct: Supplemental Review (SR) | 2021-01-05 | Customer
119108125 | 824 | Conduct: Supplemental Review (SR) | 2021-01-08 | Customer
119108125 | 824 | Conduct: Supplemental Review (SR) | 2021-02-01 | Customer
119108125 | 824 | Conduct: Supplemental Review (SR) | 2021-02-08 | Customer
119680540 | 825 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
119680540 | 825 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
119680540 | 825 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
119572463 | 826 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
119572463 | 826 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
119572463 | 826 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
118925322 | 827 | Conduct: SIS | 2021-02-26 | Customer
118925322 | 827 | Conduct: SIS | 2021-04-05 | Engineering
118925322 | 827 | Conduct: SIS | 2021-04-12 | Engineering
118925322 | 827 | Conduct: SIS | 2021-04-19 | Engineering
118925322 | 827 | Conduct: SIS | 2021-05-17 | Engineering
118925322 | 827 | Conduct: SIS | 2021-05-24 | Engineering
118925322 | 827 | Conduct: SIS | 2021-06-01 | Engineering
118925322 | 827 | Conduct: SIS | 2021-06-08 | Engineering
118925322 | 827 | Conduct: SIS | 2021-06-15 | Engineering
118925322 | 827 | Conduct: SIS | 2021-06-22 | Engineering
118925322 | 827 | Conduct: SIS | 2021-06-29 | Engineering
118925322 | 827 | Conduct: SIS | 2021-07-07 | Engineering
118925322 | 827 | Conduct: SIS | 2021-07-14 | Engineering
118925322 | 827 | Conduct: SIS | 2021-09-14 | Engineering – addressing project volume surge
118925322 | 827 | Conduct: SIS | 2021-09-21 | Engineering – addressing project volume surge
118925322 | 827 | Conduct: SIS | 2021-09-28 | Engineering – addressing project volume surge
118925322 | 827 | Conduct: SIS | 2021-10-20 | Engineering – addressing project volume surge
118925322 | 827 | Conduct: SIS | 2021-10-25 | Engineering – addressing project volume surge
119769033 | 828 | Conduct: Initial Review (IR) | 2021-01-11 | Customer
119769033 | 828 | Conduct: Initial Review (IR) | 2021-03-10 | Customer
119769033 | 828 | Conduct: Initial Review (IR) | 2021-03-17 | Customer
119769033 | 828 | Conduct: Initial Review (IR) | 2021-03-24 | Customer
119769033 | 828 | Conduct: Initial Review (IR) | 2021-04-01 | Customer
119769033 | 828 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
119769033 | 828 | Conduct: Initial Review (IR) | 2021-12-13 | Customer
119712209 | 829 | Conduct: EIT | 2021-02-12 | Customer
119712209 | 829 | Conduct: EIT | 2021-02-22 | Customer
119712209 | 829 | Conduct: SIS | 2021-07-01 | Engineering – addressing project volume surge
119712209 | 829 | Conduct: SIS | 2021-07-15 | Engineering – addressing project volume surge
119712209 | 829 | Conduct: SIS | 2021-07-22 | Engineering – addressing project volume surge
119763998 | 830 | Conduct: EIT | 2021-01-28 | Customer
119763998 | 830 | Conduct: EIT | 2021-02-04 | Customer
119763998 | 830 | Conduct: EIT | 2021-02-11 | Customer
119763998 | 830 | Conduct: EIT | 2021-02-19 | Customer
119763998 | 830 | Conduct: EIT | 2021-02-25 | Customer
119763998 | 830 | Conduct: EIT | 2021-03-04 | Customer
119763998 | 830 | Conduct: SIS | 2021-09-17 | Engineering – addressing project volume surge
119763998 | 830 | Conduct: SIS | 2021-09-24 | Engineering – addressing project volume surge
119820936 | 831 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
119648243 | 832 | Tender Draft IA | 2021-12-15 | Customer
119523097 | 833 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
119523097 | 833 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
119950820 | 834 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
119950820 | 834 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
119950820 | 834 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
119960166 | 835 | Conduct: Initial Review (IR) | 2021-01-29 | Customer
119960166 | 835 | Conduct: Initial Review (IR) | 2021-02-05 | Customer
119960166 | 835 | Conduct: Initial Review (IR) | 2021-02-12 | Customer
119960166 | 835 | Conduct: Initial Review (IR) | 2021-02-22 | Customer
119960166 | 835 | Conduct: Initial Review (IR) | 2021-03-01 | Customer
119977704 | 836 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
119977704 | 836 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
119994073 | 837 | Conduct: Initial Review (IR) | 2020-12-29 | Customer
119994073 | 837 | Conduct: Initial Review (IR) | 2021-01-06 | Customer
119994073 | 837 | Conduct: Initial Review (IR) | 2021-02-06 | Customer
118767104 | 838 | Conduct: Initial Review (IR) | 2021-01-09 | Customer
118767104 | 838 | Conduct: Initial Review (IR) | 2021-02-06 | Customer
118767104 | 838 | Conduct: Initial Review (IR) | 2021-02-12 | Customer
118767104 | 838 | Conduct: Initial Review (IR) | 2021-02-22 | Customer
118767104 | 838 | Conduct: Initial Review (IR) | 2021-03-01 | Customer
118767104 | 838 | Conduct: Initial Review (IR) | 2021-03-08 | Customer
118767104 | 838 | Conduct: Initial Review (IR) | 2021-03-15 | Customer
118767104 | 838 | Conduct: Initial Review (IR) | 2021-03-22 | Customer
118767104 | 838 | Conduct: Initial Review (IR) | 2021-03-29 | Customer
118767104 | 838 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
119949812 | 839 | Conduct: Initial Review (IR) | 2021-01-11 | Customer
116683496 | 840 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
119956977 | 841 | Conduct: Initial Review (IR) | 2021-01-14 | Customer
119956977 | 841 | Conduct: Initial Review (IR) | 2021-02-03 | Customer
119956977 | 841 | Conduct: Initial Review (IR) | 2021-02-10 | Customer
119954894 | 842 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
119954894 | 842 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
119954894 | 842 | Conduct: Initial Review (IR) | 2021-04-29 | Engineering
119521381 | 843 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
119984246 | 844 | Conduct: Initial Review (IR) | 2021-01-21 | Customer
119984246 | 844 | Conduct: Initial Review (IR) | 2021-01-28 | Customer
119984246 | 844 | Conduct: Initial Review (IR) | 2021-02-04 | Customer
119984246 | 844 | Conduct: Initial Review (IR) | 2021-02-11 | Customer
119984246 | 844 | Conduct: Initial Review (IR) | 2021-02-19 | Customer
119984246 | 844 | Conduct: Initial Review (IR) | 2021-02-26 | Customer
119984246 | 844 | Conduct: Initial Review (IR) | 2021-03-05 | Customer
119984246 | 844 | Conduct: Initial Review (IR) | 2021-03-12 | Customer
119984246 | 844 | Conduct: Initial Review (IR) | 2021-03-19 | Customer
119984246 | 844 | Conduct: Initial Review (IR) | 2021-03-26 | Customer
119984246 | 844 | Conduct: Initial Review (IR) | 2021-04-02 | Customer
119984246 | 844 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
119984246 | 844 | Conduct: Initial Review (IR) | 2021-05-14 | Customer
119805412 | 845 | Tender Draft IA | 2020-12-29 | Customer
119805412 | 845 | Tender Draft IA | 2021-01-26 | Customer
119805412 | 845 | Tender Draft IA | 2021-02-25 | Customer
119980930 | 846 | Conduct: Initial Review (IR) | 2021-01-14 | Customer
119980930 | 846 | Conduct: Initial Review (IR) | 2021-01-22 | Customer
119980930 | 846 | Conduct: Initial Review (IR) | 2021-02-05 | Customer
119980930 | 846 | Conduct: Initial Review (IR) | 2021-02-12 | Customer
119985746 | 847 | Conduct: Initial Review (IR) | 2021-02-10 | Customer
119985746 | 847 | Conduct: Initial Review (IR) | 2021-02-18 | Customer
119985746 | 847 | Conduct: Initial Review (IR) | 2021-03-02 | Customer
119985746 | 847 | Conduct: Initial Review (IR) | 2021-03-09 | Customer
119985746 | 847 | Conduct: Initial Review (IR) | 2021-03-16 | Customer
119985746 | 847 | Conduct: Initial Review (IR) | 2021-04-01 | Customer
119985746 | 847 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
119955348 | 848 | Tender Draft IA | 2022-12-22 | Customer
119990430 | 849 | Conduct: Initial Review (IR) | 2021-01-21 | Customer
119990430 | 849 | Conduct: Initial Review (IR) | 2021-02-04 | EGI
120081352 | 850 | Conduct: Initial Review (IR) | 2021-02-01 | Customer
120032112 | 851 | Conduct: Initial Review (IR) | 2021-01-14 | Customer
120032112 | 851 | Conduct: Initial Review (IR) | 2021-01-29 | Customer
120032112 | 851 | Conduct: Initial Review (IR) | 2021-02-05 | Customer
120032112 | 851 | Conduct: Initial Review (IR) | 2021-02-12 | Customer
120032112 | 851 | Conduct: Initial Review (IR) | 2021-02-22 | Customer
120032112 | 851 | Conduct: Initial Review (IR) | 2021-03-01 | Customer
120032112 | 851 | Conduct: Initial Review (IR) | 2021-03-02 | Customer
120032112 | 851 | Conduct: Initial Review (IR) | 2021-03-17 | Customer
120191697 | 852 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120191697 | 852 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
120016382 | 853 | Tender Draft IA | 2022-01-20 | Customer
120216061 | 854 | Conduct: Initial Review (IR) | 2021-04-09 | Customer
120216061 | 854 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
120216061 | 854 | Conduct: Initial Review (IR) | 2021-04-30 | Customer
120216061 | 854 | Conduct: Initial Review (IR) | 2021-04-23 | Engineering
120227960 | 855 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
120227960 | 855 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120138434 | 856 | Conduct: Initial Review (IR) | 2021-02-09 | Customer
120138434 | 856 | Conduct: Initial Review (IR) | 2021-02-17 | Customer
120138434 | 856 | Conduct: Initial Review (IR) | 2021-02-24 | Customer
120138434 | 856 | Conduct: Initial Review (IR) | 2021-03-03 | Customer
120138434 | 856 | Conduct: Initial Review (IR) | 2021-03-10 | Customer
120138434 | 856 | Conduct: Initial Review (IR) | 2021-03-17 | Customer
120138434 | 856 | Conduct: Initial Review (IR) | 2021-03-24 | Customer
120138434 | 856 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
120236829 | 857 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
120244366 | 858 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120178728 | 859 | Conduct: Initial Review (IR) | 2021-02-18 | Customer
120178728 | 859 | Conduct: Initial Review (IR) | 2021-02-25 | Customer
120178728 | 859 | Conduct: Initial Review (IR) | 2021-03-04 | Customer
120178728 | 859 | Conduct: Initial Review (IR) | 2021-03-11 | Customer
120178728 | 859 | Conduct: Initial Review (IR) | 2021-03-18 | Customer
120178728 | 859 | Conduct: Initial Review (IR) | 2021-03-25 | Customer
120178728 | 859 | Conduct: Initial Review (IR) | 2021-04-01 | Customer
120178728 | 859 | Conduct: Initial Review (IR) | 2021-04-07 | Engineering
120320324 | 860 | Conduct: Initial Review (IR) | 2021-04-09 | Customer
120320324 | 860 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
120237575 | 861 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
120237575 | 861 | Conduct: Initial Review (IR) | 2021-04-12 | Engineering
120231470 | 862 | Conduct: Initial Review (IR) | 2021-03-22 | Customer
120231470 | 862 | Conduct: Initial Review (IR) | 2021-03-29 | Customer
120231470 | 862 | Conduct: Initial Review (IR) | 2021-04-05 | Customer
120231470 | 862 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120231470 | 862 | Conduct: Initial Review (IR) | 2021-04-27 | Customer
119556126 | 863 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
119538807 | 864 | Conduct: Initial Review (IR) | 2021-02-23 | Customer
120416899 | 865 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
120416899 | 865 | Conduct: Initial Review (IR) | 2021-04-21 | Engineering
120240818 | 866 | Conduct: Initial Review (IR) | 2021-03-04 | Customer
120240818 | 866 | Conduct: Initial Review (IR) | 2021-03-18 | Customer
120240818 | 866 | Conduct: Initial Review (IR) | 2021-04-08 | Customer
120240818 | 866 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
120240818 | 866 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120240818 | 866 | Conduct: Initial Review (IR) | 2021-02-25 | Engineering
120240818 | 866 | Conduct: Initial Review (IR) | 2021-03-04 | Customer
120240818 | 866 | Conduct: Initial Review (IR) | 2021-03-18 | Customer
120240818 | 866 | Conduct: Initial Review (IR) | 2021-04-08 | Customer
120240818 | 866 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
120240818 | 866 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120240818 | 866 | Conduct: Initial Review (IR) | 2021-02-25 | Engineering
120240818 | 866 | Conduct: Initial Review (IR) | 2021-03-04 | Customer
120240818 | 866 | Conduct: Initial Review (IR) | 2021-03-18 | Customer
120240818 | 866 | Conduct: Initial Review (IR) | 2021-04-08 | Customer
120240818 | 866 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
120240818 | 866 | Conduct: Initial Review (IR) | 2021-05-20 | Customer – requirement to provide corrected information
120240818 | 866 | Conduct: Initial Review (IR) | 2021-02-25 | Engineering
120425321 | 867 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
120425321 | 867 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
120425321 | 867 | Conduct: Initial Review (IR) | 2021-04-28 | Customer
120425321 | 867 | Conduct: Initial Review (IR) | 2021-05-12 | Customer – requirement to provide corrected information
120458772 | 868 | Conduct: Initial Review (IR) | 2021-04-09 | Customer
120458772 | 868 | Conduct: Initial Review (IR) | 2021-04-23 | Engineering
120147619 | 869 | Conduct: Initial Review (IR) | 2021-03-03 | Customer
120147619 | 869 | Conduct: Initial Review (IR) | 2021-03-10 | Customer
120147619 | 869 | Conduct: Initial Review (IR) | 2021-03-26 | Customer
118056930 | 870 | Conduct: Initial Review (IR) | 2021-03-12 | Customer
118056930 | 870 | Conduct: Initial Review (IR) | 2021-03-26 | Customer
118056930 | 870 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
118056930 | 870 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
118056930 | 870 | Conduct: Initial Review (IR) | 2021-05-20 | Customer
118056930 | 870 | Conduct: Initial Review (IR) | 2021-02-26 | Engineering
119761888 | 871 | Conduct: Supplemental Review (SR) | 2021-04-14 | Customer
120407891 | 872 | Conduct: Initial Review (IR) | 2021-03-04 | Customer
120407891 | 872 | Conduct: Initial Review (IR) | 2021-03-18 | Customer
120407891 | 872 | Conduct: Initial Review (IR) | 2021-04-08 | Customer
120407891 | 872 | Conduct: Initial Review (IR) | 2021-03-04 | Customer
120407891 | 872 | Conduct: Initial Review (IR) | 2021-03-18 | Customer
120407891 | 872 | Conduct: Initial Review (IR) | 2021-04-08 | Customer
120407891 | 872 | Conduct: Initial Review (IR) | 2021-03-04 | Customer
120407891 | 872 | Conduct: Initial Review (IR) | 2021-03-18 | Customer
120407891 | 872 | Conduct: Initial Review (IR) | 2021-04-08 | Customer
120503516 | 873 | Conduct: Initial Review (IR) | 2021-04-09 | Customer
120503516 | 873 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
120491349 | 874 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120491349 | 874 | Conduct: Initial Review (IR) | 2021-04-27 | Customer
120491349 | 874 | Conduct: Initial Review (IR) | 2021-05-25 | Customer
120508474 | 875 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120508474 | 875 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120508474 | 875 | Conduct: Initial Review (IR) | 2021-04-27 | Customer
120508474 | 875 | Conduct: Initial Review (IR) | 2021-05-04 | EGI
120418685 | 876 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
120418685 | 876 | Conduct: Initial Review (IR) | 2021-04-13 | Engineering
120418685 | 876 | Conduct: Initial Review (IR) | 2021-04-20 | Engineering
120461336 | 877 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
120461336 | 877 | Conduct: Initial Review (IR) | 2021-04-26 | EGI
120528864 | 878 | Conduct: Initial Review (IR) | 2021-04-09 | Customer
120528864 | 878 | Conduct: Initial Review (IR) | 2021-04-23 | Engineering
120528864 | 878 | Conduct: Initial Review (IR) | 2021-05-07 | Engineering
119753241 | 879 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
119753241 | 879 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
119753241 | 879 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
119753241 | 879 | Conduct: Initial Review (IR) | 2021-05-03 | Engineering
120530915 | 880 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120530915 | 880 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120530915 | 880 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120530915 | 880 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120462160 | 881 | Conduct: Initial Review (IR) | 2021-04-12 | Customer
120476059 | 882 | Conduct: Initial Review (IR) | 2021-04-09 | Customer
120476059 | 882 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
120574430 | 883 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120574430 | 883 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
120569017 | 884 | Conduct: Initial Review (IR) | 2021-04-09 | Customer
120114272 | 885 | Conduct: Initial Review (IR) | 2021-04-09 | Customer
120114272 | 885 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
120555436 | 886 | Conduct: Initial Review (IR) | 2021-04-09 | Customer
120555436 | 886 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
120506337 | 887 | Conduct: Initial Review (IR) | 2021-04-06 | Customer
120506337 | 887 | Conduct: Initial Review (IR) | 2021-04-06 | Customer
120506337 | 887 | Conduct: Initial Review (IR) | 2021-04-06 | Customer
120244597 | 888 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120244597 | 888 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120539333 | 889 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
120539333 | 889 | Conduct: Initial Review (IR) | 2021-04-23 | Engineering
120539333 | 889 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
120539333 | 889 | Conduct: Initial Review (IR) | 2021-04-23 | Engineering
120539333 | 889 | Conduct: Initial Review (IR) | 2021-04-14 | Customer
120539333 | 889 | Conduct: Initial Review (IR) | 2021-04-23 | Engineering
120178888 | 890 | Conduct: Initial Review (IR) | 2021-04-15 | Customer
120178888 | 890 | Conduct: Initial Review (IR) | 2021-04-22 | Engineering
120178888 | 890 | Conduct: Initial Review (IR) | 2021-05-07 | Engineering
120568376 | 891 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
120568376 | 891 | Conduct: Initial Review (IR) | 2021-04-02 | EGI
120568376 | 891 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
120568376 | 891 | Conduct: Initial Review (IR) | 2021-04-02 | EGI
120568376 | 891 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
120568376 | 891 | Conduct: Initial Review (IR) | 2021-04-02 | EGI
119783862 | 892 | Conduct: Initial Review (IR) | 2021-04-16 | Customer
119783862 | 892 | Conduct: Initial Review (IR) | 2021-04-30 | Customer
119783862 | 892 | Conduct: Initial Review (IR) | 2021-04-09 | Engineering
119783862 | 892 | Conduct: Initial Review (IR) | 2021-04-23 | Engineering
120478508 | 893 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120478508 | 893 | Conduct: Initial Review (IR) | 2021-04-13 | Engineering
120567472 | 894 | Conduct: Initial Review (IR) | 2021-04-30 | Customer
120451968 | 895 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120451968 | 895 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120614144 | 896 | Conduct: Initial Review (IR) | 2021-04-11 | Customer
120614144 | 896 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120613656 | 897 | Conduct: Initial Review (IR) | 2021-04-11 | Customer
120613656 | 897 | Conduct: Initial Review (IR) | 2021-04-25 | Customer
120613656 | 897 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
120509580 | 898 | Conduct: Initial Review (IR) | 2021-04-11 | Customer
120509580 | 898 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120509580 | 898 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
120210340 | 899 | Conduct: Initial Review (IR) | 2021-04-13 | Customer
120210340 | 899 | Conduct: Initial Review (IR) | 2021-04-20 | Customer
120210340 | 899 | Conduct: Initial Review (IR) | 2021-04-27 | Customer
120210340 | 899 | Conduct: Initial Review (IR) | 2021-05-04 | EGI
119358303 | 900 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120608432 | 901 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
120080568 | 902 | Conduct: Initial Review (IR) | 2021-05-14 | Customer
120458832 | 903 | Conduct: Initial Review (IR) | 2021-04-19 | Customer
120458832 | 903 | Conduct: Initial Review (IR) | 2021-04-26 | Customer
120458832 | 903 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
120618015 | 904 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
120627243 | 905 | Conduct: Initial Review (IR) | 2021-04-30 | Customer
120566066 | 906 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
120566066 | 906 | Conduct: Initial Review (IR) | 2021-04-28 | Engineering
120566066 | 906 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
120566066 | 906 | Conduct: Initial Review (IR) | 2021-04-28 | Engineering
120566066 | 906 | Conduct: Initial Review (IR) | 2021-04-21 | Customer
120566066 | 906 | Conduct: Initial Review (IR) | 2021-04-28 | Engineering
120633924 | 907 | Conduct: Initial Review (IR) | 2021-04-30 | Customer
120592739 | 908 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
120674850 | 909 | Conduct: Initial Review (IR) | 2021-04-22 | Customer
120651427 | 910 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120696896 | 911 | Conduct: Initial Review (IR) | 2021-04-23 | Customer
120696896 | 911 | Conduct: Initial Review (IR) | 2021-04-30 | EGI
119495957 | 912 | Conduct: Initial Review (IR) | 2021-04-29 | Customer
120566512 | 913 | Conduct: Initial Review (IR) | 2021-04-27 | Customer
120688178 | 914 | Conduct: Initial Review (IR) | 2021-04-27 | Customer
120688178 | 914 | Conduct: Initial Review (IR) | 2021-05-04 | Customer
120430073 | 915 | Conduct: Initial Review (IR) | 2021-05-06 | Customer
120581884 | 916 | Conduct: Initial Review (IR) | 2021-04-30 | Customer
120652722 | 917 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
120652722 | 917 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
120652722 | 917 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
120637816 | 918 | Conduct: Initial Review (IR) | 2021-05-03 | Customer
120698794 | 919 | Conduct: Initial Review (IR) | 2021-05-12 | Customer
120698794 | 919 | Conduct: Initial Review (IR) | 2021-05-12 | Customer
120698794 | 919 | Conduct: Initial Review (IR) | 2021-05-12 | Customer
120695587 | 920 | Conduct: EIT | 2021-05-11 | Customer
120695587 | 920 | Conduct: EIT | 2021-05-18 | Customer
117247246 | 921 | Construction True-up Report Sent | 2021-10-21 | Customer – requesting an extension
117247246 | 921 | Construction True-up Report Sent | 2021-09-21 | Project Management – requiring more detailed review
121191139 | 922 | Schedule: Scoping Meeting | 2021-07-09 | Customer – requesting an extension
121191139 | 922 | Schedule: Scoping Meeting | 2021-07-16 | Customer – requesting an extension
121191139 | 922 | Conduct: SIS | 2021-10-26 | Engineering – requiring more detailed review
121191139 | 922 | Schedule: Scoping Meeting | 2021-07-09 | Customer – requesting an extension
121191139 | 922 | Schedule: Scoping Meeting | 2021-07-16 | Customer – requesting an extension
121191139 | 922 | Conduct: SIS | 2021-10-26 | Engineering – requiring more detailed review
121191139 | 922 | Conduct: SIS | 2021-11-05 | Engineering – requiring more detailed review
121191139 | 922 | Conduct: SIS | 2021-11-12 | Engineering – requiring more detailed review
121191139 | 922 | Schedule: Scoping Meeting | 2021-07-09 | Customer – requesting an extension
121191139 | 922 | Schedule: Scoping Meeting | 2021-07-16 | Customer – requesting an extension
121191139 | 922 | Conduct: SIS | 2021-10-26 | Engineering – requiring more detailed review
121191139 | 922 | Conduct: SIS | 2022-02-22 | Engineering – requiring more detailed review
121191139 | 922 | Conduct: SIS | 2021-11-05 | Engineering – requiring more detailed review
121191139 | 922 | Conduct: SIS | 2021-11-12 | Engineering – requiring more detailed review
121191139 | 922 | Conduct: SIS | 2022-03-08 | Engineering – requiring more detailed review
121191139 | 922 | Conduct: SIS | 2022-03-11 | Engineering – requiring more detailed review
121191139 | 922 | Conduct: SIS | 2022-03-18 | Engineering – requiring more detailed review
121191139 | 922 | Conduct: SIS | 2022-03-25 | Engineering – requiring more detailed review
121593561 | 923 | Conduct: Initial Review (IR) | 2021-09-16 | Customer – requesting an extension
121593561 | 923 | Conduct: Initial Review (IR) | 2021-09-22 | Engineering – requiring more detailed review
121593561 | 923 | Conduct: Initial Review (IR) | 2021-09-16 | Customer – requesting an extension
121593561 | 923 | Conduct: Initial Review (IR) | 2021-09-22 | Engineering – requiring more detailed review
121593561 | 923 | Conduct: Initial Review (IR) | 2021-09-16 | Customer – requesting an extension
121593561 | 923 | Conduct: Initial Review (IR) | 2021-09-22 | Engineering – requiring more detailed review
120745382 | 924 | Schedule: Scoping Meeting | 2021-10-15 | Customer – requesting an extension
120745382 | 924 | Conduct: Screens Q and R | 2021-10-12 | Engineering – requiring more detailed review
120745382 | 924 | Schedule: Scoping Meeting | 2021-10-15 | Customer – requesting an extension
120745382 | 924 | Conduct: Screens Q and R | 2021-10-12 | Engineering – requiring more detailed review
120745382 | 924 | Conduct: SIS | 2022-01-17 | Engineering – requiring more detailed review
120745382 | 924 | Conduct: SIS | 2022-02-04 | Engineering – requiring more detailed review
120745382 | 924 | Conduct: SIS | 2022-01-21 | Project Management - addressing project volume surge
120745382 | 924 | Schedule: Scoping Meeting | 2021-10-15 | Customer – requesting an extension
120745382 | 924 | Conduct: Screens Q and R | 2021-10-12 | Engineering – requiring more detailed review
120745382 | 924 | Conduct: SIS | 2022-01-17 | Engineering – requiring more detailed review
120745382 | 924 | Conduct: SIS | 2022-02-04 | Engineering – requiring more detailed review
120745382 | 924 | Conduct: SIS | 2022-02-18 | Engineering – requiring more detailed review
120745382 | 924 | Conduct: SIS | 2022-01-21 | Project Management - addressing project volume surge
119994501 | 925 | Conduct: Initial Review (IR) | 2021-09-28 | Customer – requirement to provide corrected information
119994501 | 925 | Conduct: Initial Review (IR) | 2021-10-19 | Customer – requirement to provide corrected information
119994501 | 925 | Conduct: Initial Review (IR) | 2021-09-09 | Engineering – addressing project volume surge
119994501 | 925 | Conduct: Initial Review (IR) | 2021-09-16 | Engineering – addressing project volume surge
120162863 | 926 | Conduct: SIS | 2021-08-04 | Customer – requirement to provide corrected information
120162863 | 926 | Conduct: SIS | 2021-08-18 | Customer – requirement to provide corrected information
120421365 | 927 | Conduct: SIS | 2021-10-29 | Customer – requirement to provide corrected information
120421365 | 927 | Conduct: SIS | 2021-10-29 | Customer – requirement to provide corrected information
120421365 | 927 | Conduct: SIS | 2022-01-06 | Customer – requirement to provide corrected information
120421365 | 927 | Conduct: SIS | 2022-01-27 | Engineering – addressing project volume surge
120421365 | 927 | Conduct: SIS | 2022-02-18 | Engineering – addressing project volume surge
120421365 | 927 | Conduct: SIS | 2021-10-29 | Customer – requirement to provide corrected information
120421365 | 927 | Conduct: SIS | 2022-01-06 | Customer – requirement to provide corrected information
120421365 | 927 | Conduct: SIS | 2022-01-27 | Engineering – addressing project volume surge
120421365 | 927 | Conduct: SIS | 2022-02-18 | Engineering – addressing project volume surge
120421365 | 927 | Conduct: SIS | 2022-03-04 | Engineering – requiring more detailed review
120421365 | 927 | Conduct: SIS | 2022-03-07 | Engineering – requiring more detailed review
121438435 | 928 | Conduct: Initial Review (IR) | 2021-07-12 | Customer – requirement to provide corrected information
121189607 | 929 | Conduct: Initial Review (IR) | 2021-07-23 | Customer – requirement to provide corrected information
121189607 | 929 | Conduct: Initial Review (IR) | 2021-07-30 | Customer – requirement to provide corrected information
121189607 | 929 | Conduct: Initial Review (IR) | 2021-07-14 | Engineering – requiring more detailed review
121189607 | 929 | Conduct: Initial Review (IR) | 2021-07-30 | Customer – requirement to provide corrected information
121189607 | 929 | Conduct: Initial Review (IR) | 2021-07-23 | Customer – requirement to provide corrected information
121189607 | 929 | Conduct: Initial Review (IR) | 2021-07-14 | Engineering – requiring more detailed review
121189607 | 929 | Conduct: Initial Review (IR) | 2021-07-23 | Customer – requirement to provide corrected information
121189607 | 929 | Conduct: Initial Review (IR) | 2021-07-30 | Customer – requirement to provide corrected information
121189607 | 929 | Conduct: Initial Review (IR) | 2021-07-14 | Engineering – requiring more detailed review
120237635 | 930 | Conduct: SIS | 2021-11-01 | Customer – requirement to provide corrected information
120237635 | 930 | Conduct: Screens Q and R | 2021-03-19 | Engineering
120237635 | 930 | Conduct: Screens Q and R | 2021-03-26 | Engineering
120237635 | 930 | Conduct: SIS | 2021-11-01 | Customer – requirement to provide corrected information
120237635 | 930 | Conduct: SIS | 2021-12-01 | Customer – requirement to provide corrected information
120237635 | 930 | Conduct: SIS | 2022-01-07 | Customer – requirement to provide corrected information
120237635 | 930 | Conduct: Screens Q and R | 2021-03-19 | Engineering
120237635 | 930 | Conduct: Screens Q and R | 2021-03-26 | Engineering
120237635 | 930 | Conduct: SIS | 2022-02-21 | Engineering – requiring more detailed review
120237635 | 930 | Conduct: SIS | 2021-11-01 | Customer – requirement to provide corrected information
120237635 | 930 | Conduct: SIS | 2021-12-01 | Customer – requirement to provide corrected information
120237635 | 930 | Conduct: SIS | 2022-01-07 | Customer – requirement to provide corrected information
120237635 | 930 | Conduct: SIS | 2022-03-21 | Customer – requirement to provide corrected information
120237635 | 930 | Conduct: SIS | 2022-04-21 | Customer – requirement to provide corrected information
120237635 | 930 | Conduct: Screens Q and R | 2021-03-19 | Engineering
120237635 | 930 | Conduct: Screens Q and R | 2021-03-26 | Engineering
120237635 | 930 | Conduct: SIS | 2022-02-21 | Engineering – requiring more detailed review
120237635 | 930 | Conduct: SIS | 2022-06-29 | Engineering – requiring more detailed review
121535968 | 931 | Conduct: Initial Review (IR) | 2021-08-20 | Customer – requirement to provide corrected information
121535968 | 931 | Conduct: Initial Review (IR) | 2021-08-20 | Customer – requirement to provide corrected information
121535968 | 931 | Conduct: Initial Review (IR) | 2021-08-20 | Customer – requirement to provide corrected information
121581648 | 932 | Conduct: Initial Review (IR) | 2021-07-26 | Customer – requirement to provide corrected information
121581648 | 932 | Conduct: Initial Review (IR) | 2021-08-02 | Customer – requirement to provide corrected information
121581648 | 932 | Conduct: Initial Review (IR) | 2021-08-09 | Customer – requirement to provide corrected information
121581648 | 932 | Conduct: Initial Review (IR) | 2021-08-16 | Customer – requirement to provide corrected information
121581648 | 932 | Conduct: Initial Review (IR) | 2021-08-30 | Engineering – requiring more detailed review
120792184 | 933 | Conduct: Initial Review (IR) | 2021-08-06 | Customer – requirement to provide corrected information
120792184 | 933 | Conduct: Initial Review (IR) | 2021-08-06 | Customer – requirement to provide corrected information
120792184 | 933 | Conduct: Initial Review (IR) | 2021-08-06 | Customer – requirement to provide corrected information
121323269 | 934 | Conduct: Initial Review (IR) | 2021-08-06 | Customer – requirement to provide corrected information
121323269 | 934 | Conduct: Initial Review (IR) | 2021-08-06 | Customer – requirement to provide corrected information
121323269 | 934 | Conduct: Initial Review (IR) | 2021-08-06 | Customer – requirement to provide corrected information
121631449 | 935 | Conduct: Initial Review (IR) | 2021-08-06 | Customer – requirement to provide corrected information
121631449 | 935 | Conduct: Initial Review (IR) | 2021-08-13 | Customer – requirement to provide corrected information
121631449 | 935 | Conduct: Initial Review (IR) | 2021-08-20 | Customer – requirement to provide corrected information
121631449 | 935 | Conduct: Initial Review (IR) | 2021-08-27 | Customer – requirement to provide corrected information
121631449 | 935 | Conduct: Initial Review (IR) | 2021-09-03 | Customer – requirement to provide corrected information
120897331 | 936 | Conduct: Initial Review (IR) | 2021-08-13 | Customer – requirement to provide corrected information
120897331 | 936 | Conduct: Initial Review (IR) | 2021-09-02 | Customer – requirement to provide corrected information
120897331 | 936 | Conduct: Initial Review (IR) | 2021-08-13 | Customer – requirement to provide corrected information
120897331 | 936 | Conduct: Initial Review (IR) | 2021-09-02 | Customer – requirement to provide corrected information
120897331 | 936 | Conduct: Initial Review (IR) | 2021-08-13 | Customer – requirement to provide corrected information
120897331 | 936 | Conduct: Initial Review (IR) | 2021-09-02 | Customer – requirement to provide corrected information
121539277 | 937 | Conduct: Initial Review (IR) | 2021-08-03 | Customer – requirement to provide corrected information
121539277 | 937 | Conduct: Initial Review (IR) | 2021-07-23 | Engineering – requiring more detailed review
121539277 | 937 | Conduct: Initial Review (IR) | 2021-08-03 | Customer – requirement to provide corrected information
121539277 | 937 | Conduct: Initial Review (IR) | 2021-07-23 | Engineering – requiring more detailed review
121539277 | 937 | Conduct: Initial Review (IR) | 2021-08-03 | Customer – requirement to provide corrected information
121539277 | 937 | Conduct: Initial Review (IR) | 2021-07-23 | Engineering – requiring more detailed review
119929097 | 938 | Conduct: Initial Review (IR) | 2021-08-10 | Customer – requirement to provide corrected information
121679712 | 939 | Conduct: Initial Review (IR) | 2021-09-07 | Customer – requirement to provide corrected information
121679712 | 939 | Conduct: Initial Review (IR) | 2021-09-28 | Customer – requirement to provide corrected information
121679712 | 939 | Conduct: Initial Review (IR) | 2021-09-07 | Customer – requirement to provide corrected information
121679712 | 939 | Conduct: Initial Review (IR) | 2021-09-28 | Customer – requirement to provide corrected information
121679712 | 939 | Conduct: Initial Review (IR) | 2021-09-07 | Customer – requirement to provide corrected information
121679712 | 939 | Conduct: Initial Review (IR) | 2021-09-28 | Customer – requirement to provide corrected information
120668012 | 940 | Conduct: Initial Review (IR) | 2021-08-25 | Customer – requirement to provide corrected information
120668012 | 940 | Conduct: Initial Review (IR) | 2021-09-09 | Engineering – requiring more detailed review
120668012 | 940 | Conduct: Initial Review (IR) | 2021-09-23 | Engineering – requiring more detailed review
120668012 | 940 | Conduct: Initial Review (IR) | 2021-10-07 | Engineering – requiring more detailed review
120668012 | 940 | Conduct: Initial Review (IR) | 2021-10-21 | Engineering – requiring more detailed review
120668012 | 940 | Conduct: Initial Review (IR) | 2021-08-18 | Project Management - addressing project volume surge
120668012 | 940 | Conduct: Initial Review (IR) | 2021-08-25 | Customer – requirement to provide corrected information
120668012 | 940 | Conduct: Initial Review (IR) | 2021-09-09 | Engineering – requiring more detailed review
120668012 | 940 | Conduct: Initial Review (IR) | 2021-09-23 | Engineering – requiring more detailed review
120668012 | 940 | Conduct: Initial Review (IR) | 2021-10-07 | Engineering – requiring more detailed review
120668012 | 940 | Conduct: Initial Review (IR) | 2021-10-21 | Engineering – requiring more detailed review
120668012 | 940 | Conduct: Initial Review (IR) | 2021-10-28 | Engineering – requiring more detailed review
120668012 | 940 | Conduct: Initial Review (IR) | 2021-08-18 | Project Management - addressing project volume surge
120668012 | 940 | Conduct: Initial Review (IR) | 2021-11-04 | Project Management - addressing project volume surge
120668012 | 940 | Conduct: Initial Review (IR) | 2021-08-25 | Customer – requirement to provide corrected information
120668012 | 940 | Conduct: Initial Review (IR) | 2021-09-09 | Engineering – requiring more detailed review
120668012 | 940 | Conduct: Initial Review (IR) | 2021-09-23 | Engineering – requiring more detailed review
120668012 | 940 | Conduct: Initial Review (IR) | 2021-10-07 | Engineering – requiring more detailed review
120668012 | 940 | Conduct: Initial Review (IR) | 2021-10-21 | Engineering – requiring more detailed review
120668012 | 940 | Conduct: Initial Review (IR) | 2021-10-28 | Engineering – requiring more detailed review
120668012 | 940 | Conduct: Initial Review (IR) | 2021-08-18 | Project Management - addressing project volume surge
120668012 | 940 | Conduct: Initial Review (IR) | 2021-11-04 | Project Management - addressing project volume surge
121557379 | 941 | Conduct: Initial Review (IR) | 2021-08-19 | Customer – requirement to provide corrected information
121723959 | 942 | Conduct: Initial Review (IR) | 2021-09-07 | Customer – requirement to provide corrected information
121723959 | 942 | Conduct: Initial Review (IR) | 2021-09-14 | Engineering – requiring more detailed review
121655489 | 943 | Conduct: Initial Review (IR) | 2021-09-08 | Customer – requirement to provide corrected information
121655489 | 943 | Conduct: Initial Review (IR) | 2021-09-15 | Engineering – requiring more detailed review
121655489 | 943 | Conduct: Initial Review (IR) | 2021-09-01 | Project Management – requiring more detailed review
121655489 | 943 | Conduct: Initial Review (IR) | 2021-09-08 | Customer – requirement to provide corrected information
121655489 | 943 | Conduct: Initial Review (IR) | 2021-09-15 | Engineering – requiring more detailed review
121655489 | 943 | Conduct: Initial Review (IR) | 2021-09-01 | Project Management – requiring more detailed review
121655489 | 943 | Conduct: Initial Review (IR) | 2021-09-08 | Customer – requirement to provide corrected information
121655489 | 943 | Conduct: Initial Review (IR) | 2021-09-15 | Engineering – requiring more detailed review
121655489 | 943 | Conduct: Initial Review (IR) | 2021-09-01 | Project Management – requiring more detailed review
121808551 | 944 | Conduct: Initial Review (IR) | 2021-09-27 | Customer – requirement to provide corrected information
121808551 | 944 | Conduct: Initial Review (IR) | 2021-09-27 | Customer – requirement to provide corrected information
121808551 | 944 | Conduct: Initial Review (IR) | 2021-09-27 | Customer – requirement to provide corrected information
121746544 | 945 | Conduct: Initial Review (IR) | 2021-09-30 | Customer – requirement to provide corrected information
121845137 | 946 | Conduct: Screens Q and R | 2021-10-28 | Customer – requirement to provide corrected information
121845137 | 946 | Conduct: Screens Q and R | 2022-02-04 | Cus – requirement to provide a response to deficiency notice
121845137 | 946 | Conduct: Screens Q and R | 2022-01-04 | Customer – requesting an extension
121845137 | 946 | Conduct: Screens Q and R | 2021-10-28 | Customer – requirement to provide corrected information
121845137 | 946 | Conduct: Screens Q and R | 2021-11-30 | Engineering – requiring more detailed review
121845137 | 946 | Conduct: Screens Q and R | 2022-02-04 | Cus – requirement to provide a response to deficiency notice
121845137 | 946 | Conduct: Screens Q and R | 2022-03-08 | Cus – requirement to provide a response to deficiency notice
121845137 | 946 | Conduct: Screens Q and R | 2022-01-04 | Customer – requesting an extension
121845137 | 946 | Conduct: Screens Q and R | 2021-10-28 | Customer – requirement to provide corrected information
121845137 | 946 | Conduct: Screens Q and R | 2021-11-30 | Engineering – requiring more detailed review
121845137 | 946 | Conduct: Screens Q and R | 2022-04-05 | Engineering – requiring more detailed review
121845137 | 946 | Conduct: Screens Q and R | 2022-04-19 | Project Management – requiring more detailed review
120887117 | 947 | Tender Draft IA | 2021-10-20 | Customer – requirement to provide corrected information
120887117 | 947 | Tender Draft IA | 2021-11-03 | Customer – requirement to provide corrected information
120887117 | 947 | Conduct: Supplemental Review (SR) | 2021-08-26 | Engineering – requiring more detailed review
120887117 | 947 | Tender Draft IA | 2021-10-20 | Customer – requirement to provide corrected information
120887117 | 947 | Tender Draft IA | 2021-11-03 | Customer – requirement to provide corrected information
120887117 | 947 | Tender Draft IA | 2021-11-24 | Customer – requirement to provide corrected information
120887117 | 947 | Tender Draft IA | 2021-12-08 | Customer – requirement to provide corrected information
120887117 | 947 | Tender Draft IA | 2021-12-29 | Customer – requirement to provide corrected information
120887117 | 947 | Conduct: Supplemental Review (SR) | 2021-08-26 | Engineering – requiring more detailed review
120887117 | 947 | Tender Draft IA | 2021-10-20 | Customer – requirement to provide corrected information
120887117 | 947 | Tender Draft IA | 2021-11-03 | Customer – requirement to provide corrected information
120887117 | 947 | Tender Draft IA | 2021-11-24 | Customer – requirement to provide corrected information
120887117 | 947 | Tender Draft IA | 2021-12-08 | Customer – requirement to provide corrected information
120887117 | 947 | Tender Draft IA | 2021-12-29 | Customer – requirement to provide corrected information
120887117 | 947 | Conduct: Supplemental Review (SR) | 2021-08-26 | Engineering – requiring more detailed review
120715337 | 948 | Conduct: SIS | 2021-10-21 | Customer – requirement to provide corrected information
120715337 | 948 | Conduct: SIS | 2021-10-21 | Customer – requirement to provide corrected information
120715337 | 948 | Conduct: SIS | 2021-10-21 | Customer – requirement to provide corrected information
121578259 | 949 | Conduct: Initial Review (IR) | 2021-10-22 | Customer – requirement to provide corrected information
121578259 | 949 | Conduct: Initial Review (IR) | 2021-10-22 | Customer – requirement to provide corrected information
121578259 | 949 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – requiring more detailed review
121578259 | 949 | Conduct: Initial Review (IR) | 2021-11-12 | Engineering – requiring more detailed review
121578259 | 949 | Conduct: Initial Review (IR) | 2021-10-22 | Customer – requirement to provide corrected information
121578259 | 949 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – requiring more detailed review
121578259 | 949 | Conduct: Initial Review (IR) | 2021-11-12 | Engineering – requiring more detailed review
122050122 | 950 | Conduct: Initial Review (IR) | 2021-10-22 | Customer – requirement to provide corrected information
122050122 | 950 | Conduct: Initial Review (IR) | 2021-10-22 | Customer – requirement to provide corrected information
122050122 | 950 | Conduct: Initial Review (IR) | 2021-10-22 | Customer – requirement to provide corrected information
121982494 | 951 | Conduct: Initial Review (IR) | 2021-10-18 | Customer – requirement to provide corrected information
121912981 | 952 | Conduct: Initial Review (IR) | 2021-11-01 | Customer – requirement to provide corrected information
121912981 | 952 | Conduct: Initial Review (IR) | 2021-12-07 | Cus – requirement to provide a response to deficiency notice
121912981 | 952 | Conduct: Initial Review (IR) | 2021-12-31 | Cus – requirement to provide a response to deficiency notice
121912981 | 952 | Conduct: Initial Review (IR) | 2021-11-01 | Customer – requirement to provide corrected information
121912981 | 952 | Conduct: Initial Review (IR) | 2021-11-16 | Customer – requirement to provide corrected information
121912981 | 952 | Conduct: Initial Review (IR) | 2021-12-07 | Cus – requirement to provide a response to deficiency notice
121912981 | 952 | Conduct: Initial Review (IR) | 2021-12-31 | Cus – requirement to provide a response to deficiency notice
121912981 | 952 | Conduct: Initial Review (IR) | 2021-11-01 | Customer – requirement to provide corrected information
121912981 | 952 | Conduct: Initial Review (IR) | 2021-11-16 | Customer – requirement to provide corrected information
121885645 | 953 | Conduct: Initial Review (IR) | 2021-11-03 | Customer – requirement to provide corrected information
121885645 | 953 | Conduct: Initial Review (IR) | 2021-10-20 | Engineering – addressing project volume surge
121885645 | 953 | Conduct: Initial Review (IR) | 2021-11-03 | Customer – requirement to provide corrected information
121885645 | 953 | Conduct: Initial Review (IR) | 2021-10-20 | Engineering – addressing project volume surge
121885645 | 953 | Conduct: Initial Review (IR) | 2021-11-17 | Engineering – addressing project volume surge
121885645 | 953 | Conduct: Initial Review (IR) | 2021-11-03 | Customer – requirement to provide corrected information
121885645 | 953 | Conduct: Initial Review (IR) | 2021-10-20 | Engineering – addressing project volume surge
121885645 | 953 | Conduct: Initial Review (IR) | 2021-11-17 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-10-22 | Customer – requirement to provide corrected information
121808625 | 954 | Conduct: Initial Review (IR) | 2022-01-07 | Cus – requirement to provide a response to deficiency notice
121808625 | 954 | Conduct: Initial Review (IR) | 2022-01-14 | Cus – requirement to provide a response to deficiency notice
121808625 | 954 | Conduct: Initial Review (IR) | 2021-10-22 | Customer – requirement to provide corrected information
121808625 | 954 | Conduct: Initial Review (IR) | 2021-10-29 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-11-12 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-11-19 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-11-26 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-12-03 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-12-10 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-12-17 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2022-01-24 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2022-01-31 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-12-24 | Project Management - addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2022-01-07 | Cus – requirement to provide a response to deficiency notice
121808625 | 954 | Conduct: Initial Review (IR) | 2022-01-14 | Cus – requirement to provide a response to deficiency notice
121808625 | 954 | Conduct: Initial Review (IR) | 2021-10-22 | Customer – requirement to provide corrected information
121808625 | 954 | Conduct: Initial Review (IR) | 2021-12-03 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-10-29 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-11-12 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-11-19 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-11-26 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-12-10 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-12-17 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2022-01-24 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2022-01-31 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2022-02-07 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2022-02-14 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2022-02-21 | Engineering – addressing project volume surge
121808625 | 954 | Conduct: Initial Review (IR) | 2021-12-24 | Project Management - addressing project volume surge
121973995 | 955 | Conduct: Initial Review (IR) | 2021-11-02 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2021-11-10 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2021-11-24 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2021-12-03 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2021-12-10 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2021-12-17 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2021-11-10 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2021-11-24 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2021-12-03 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2021-12-10 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2021-12-17 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2021-12-31 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2022-01-07 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2022-01-14 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2022-01-24 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2022-01-31 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2021-12-03 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2021-11-10 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2021-11-24 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2021-12-10 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2021-12-17 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2021-12-31 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2022-01-07 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2022-01-14 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2022-01-24 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2022-01-31 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2022-02-07 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2022-02-14 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2022-03-14 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2022-04-01 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2022-04-15 | Customer – requirement to provide corrected information
122084815 | 956 | Conduct: Initial Review (IR) | 2022-04-29 | Customer – requirement to provide corrected information
106960642 | 957 | Construction True-up Report Sent | 2020-12-30 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-02-13 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-02-22 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-03-01 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-03-08 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-03-15 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-03-22 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-03-29 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-04-05 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-04-12 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-04-19 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-04-26 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-05-03 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-05-10 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-05-17 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-05-24 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-06-01 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-06-08 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-06-15 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-06-22 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-06-29 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-07-07 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-07-14 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-07-21 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-07-28 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-08-04 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-08-11 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-08-18 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-08-25 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-09-01 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-09-09 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-09-16 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-09-23 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-09-30 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-10-07 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-10-14 | EGI
106960642 | 957 | Construction True-up Report Sent | 2021-10-21 | EGI
110157311 | 958 | Construction True-up Report Sent | 2020-12-29 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-01-06 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-01-13 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-01-21 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-01-28 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-02-04 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-02-11 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-02-19 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-02-26 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-03-05 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-03-12 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-03-19 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-03-26 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-04-02 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-04-09 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-04-16 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-04-23 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-04-30 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-05-07 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-05-14 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-05-21 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-05-28 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-06-07 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-06-14 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-06-21 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-06-28 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-07-06 | EGI
110157311 | 958 | Construction True-up Report Sent | 2021-07-13 | EGI
113020188 | 959 | Construction True-up Report Sent | 2020-12-30 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-01-07 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-01-14 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-01-22 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-01-29 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-02-05 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-02-12 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-02-22 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-03-01 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-03-08 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-03-15 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-03-22 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-03-29 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-04-05 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-04-12 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-04-19 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-04-26 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-05-03 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-05-10 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-05-17 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-05-24 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-06-01 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-06-08 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-06-15 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-06-22 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-06-29 | EGI
113020188 | 959 | Construction True-up Report Sent | 2021-07-07 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-01-01 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-02-13 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-02-22 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-03-01 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-03-08 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-03-15 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-03-22 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-03-29 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-04-05 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-04-12 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-04-19 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-04-26 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-05-03 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-05-10 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-05-17 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-05-24 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-06-01 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-06-08 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-06-15 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-06-22 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-06-29 | EGI
112431234 | 960 | Construction True-up Report Sent | 2021-07-07 | EGI
113074347 | 961 | Construction True-up Report Sent | 2020-12-30 | EGI
113074347 | 961 | Construction True-up Report Sent | 2021-01-31 | EGI
114070738 | 962 | Construction True-up Report Sent | 2021-01-01 | EGI
114070738 | 962 | Construction True-up Report Sent | 2021-02-13 | EGI
114070738 | 962 | Construction True-up Report Sent | 2021-02-22 | EGI
112158523 | 963 | Construction True-up Report Sent | 2020-12-30 | EGI
114483663 | 964 | Construction True-up Report Sent | 2020-12-31 | EGI
114483663 | 964 | Construction True-up Report Sent | 2021-01-08 | EGI
114483663 | 964 | Construction True-up Report Sent | 2021-01-23 | EGI
111962988 | 965 | Construction True-up Report Sent | 2020-12-31 | EGI
111962988 | 965 | Construction True-up Report Sent | 2021-01-08 | EGI
111962988 | 965 | Construction True-up Report Sent | 2021-01-23 | EGI
111963082 | 966 | Construction True-up Report Sent | 2020-12-31 | EGI
111963082 | 966 | Construction True-up Report Sent | 2021-01-08 | EGI
111963082 | 966 | Construction True-up Report Sent | 2021-01-23 | EGI
114211749 | 967 | Construction True-up Report Sent | 2020-12-31 | EGI
114211749 | 967 | Construction True-up Report Sent | 2021-01-31 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-01-01 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-01-08 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-01-15 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-01-25 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-02-01 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-02-08 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-02-16 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-02-23 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-03-02 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-03-09 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-03-16 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-03-23 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-03-30 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-04-06 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-04-13 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-04-20 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-04-27 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-05-04 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-05-11 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-05-18 | EGI
113183686 | 968 | Construction True-up Report Sent | 2021-05-25 | EGI
112747620 | 969 | Construction True-up Report Sent | 2021-01-31 | EGI
115467374 | 970 | Construction True-up Report Sent | 2021-06-25 | EGI
112670708 | 971 | Construction True-up Report Sent | 2020-12-29 | EGI
112670708 | 971 | Construction True-up Report Sent | 2021-01-06 | EGI
112670708 | 971 | Construction True-up Report Sent | 2021-01-13 | EGI
112670708 | 971 | Construction True-up Report Sent | 2021-01-21 | EGI
112670708 | 971 | Construction True-up Report Sent | 2021-01-28 | EGI
112670708 | 971 | Construction True-up Report Sent | 2021-02-04 | EGI
112670708 | 971 | Construction True-up Report Sent | 2021-02-11 | EGI
112670708 | 971 | Construction True-up Report Sent | 2021-02-19 | EGI
112670708 | 971 | Construction True-up Report Sent | 2021-03-19 | EGI
112683566 | 972 | Construction True-up Report Sent | 2020-12-31 | EGI
112683566 | 972 | Construction True-up Report Sent | 2021-01-08 | EGI
112683566 | 972 | Construction True-up Report Sent | 2021-01-15 | EGI
112683566 | 972 | Construction True-up Report Sent | 2021-01-25 | EGI
112683566 | 972 | Construction True-up Report Sent | 2021-02-01 | EGI
112683566 | 972 | Construction True-up Report Sent | 2021-02-08 | EGI
112683566 | 972 | Construction True-up Report Sent | 2021-02-16 | EGI
112683566 | 972 | Construction True-up Report Sent | 2021-02-23 | EGI
112683566 | 972 | Construction True-up Report Sent | 2021-03-02 | EGI
112683566 | 972 | Construction True-up Report Sent | 2021-03-09 | EGI
112683566 | 972 | Construction True-up Report Sent | 2021-03-16 | EGI
112683566 | 972 | Construction True-up Report Sent | 2021-03-23 | EGI
112683566 | 972 | Construction True-up Report Sent | 2021-03-30 | EGI
114848095 | 973 | Construction True-up Report Sent | 2021-05-12 | EGI
113255318 | 974 | Construction True-up Report Sent | 2020-12-30 | EGI
113073903 | 975 | Construction True-up Report Sent | 2021-02-27 | EGI
113073903 | 975 | Construction True-up Report Sent | 2021-03-05 | EGI
114547275 | 976 | Construction True-up Report Sent | 2021-03-19 | EGI
114547275 | 976 | Construction True-up Report Sent | 2021-03-26 | EGI
114547275 | 976 | Construction True-up Report Sent | 2021-04-02 | EGI
119664810 | 977 | Conduct: Initial Review (IR) | 2020-12-31 | EGI
119664810 | 977 | Conduct: Initial Review (IR) | 2021-01-08 | EGI
119664810 | 977 | Conduct: Initial Review (IR) | 2021-01-15 | EGI
119664810 | 977 | Conduct: Initial Review (IR) | 2021-01-25 | EGI
119664810 | 977 | Conduct: Initial Review (IR) | 2021-02-01 | EGI
119664810 | 977 | Conduct: Initial Review (IR) | 2021-02-08 | EGI
119664810 | 977 | Conduct: Initial Review (IR) | 2021-02-16 | EGI
114884408 | 978 | Construction True-up Report Sent | 2021-11-03 | EGI
119673849 | 979 | Conduct: Screens Q and R | 2021-01-12 | EGI
119673849 | 979 | Conduct: Screens Q and R | 2021-01-20 | EGI
119673849 | 979 | Conduct: Screens Q and R | 2021-01-27 | EGI
119673842 | 980 | Conduct: Screens Q and R | 2021-01-12 | EGI
119673842 | 980 | Conduct: Screens Q and R | 2021-01-20 | EGI
119673842 | 980 | Conduct: Screens Q and R | 2021-01-27 | EGI
118714831 | 981 | Conduct: SIS | 2021-04-26 | EGI
120497543 | 982 | Conduct: Initial Review (IR) | 2021-04-26 | EGI
120434535 | 983 | Conduct: Initial Review (IR) | 2021-04-26 | EGI
120434535 | 983 | Conduct: Initial Review (IR) | 2021-05-03 | Engineering
120129965 | 984 | Conduct: Initial Review (IR) | 2021-04-16 | EGI
120129965 | 984 | Conduct: Initial Review (IR) | 2021-04-14 | Engineering
120538819 | 985 | Conduct: Initial Review (IR) | 2021-04-04 | EGI
120538819 | 985 | Conduct: Initial Review (IR) | 2021-04-19 | Engineering
120538819 | 985 | Conduct: Initial Review (IR) | 2021-04-04 | EGI
120538819 | 985 | Conduct: Initial Review (IR) | 2021-04-19 | Engineering
120538819 | 985 | Conduct: Initial Review (IR) | 2021-04-04 | EGI
120538819 | 985 | Conduct: Initial Review (IR) | 2021-04-19 | Engineering
120542018 | 986 | Conduct: Initial Review (IR) | 2021-04-06 | EGI
120542018 | 986 | Conduct: Initial Review (IR) | 2021-04-06 | EGI
120542018 | 986 | Conduct: Initial Review (IR) | 2021-04-06 | EGI
120479888 | 987 | Tender Draft IA | 2021-04-15 | EGI
120479888 | 987 | Tender Draft IA | 2021-04-22 | EGI
120679442 | 988 | Conduct: Initial Review (IR) | 2021-04-30 | EGI
120679442 | 988 | Conduct: Initial Review (IR) | 2021-04-23 | Engineering
120680970 | 989 | Conduct: Initial Review (IR) | 2021-04-30 | EGI
120680970 | 989 | Conduct: Initial Review (IR) | 2021-04-23 | Engineering
114202896 | 990 | Conduct: Supplemental Review (SR) | 2020-12-31 | Engineering
114202896 | 990 | Conduct: Supplemental Review (SR) | 2021-01-08 | Engineering
114202896 | 990 | Conduct: Supplemental Review (SR) | 2021-01-15 | Engineering
114202896 | 990 | Conduct: Supplemental Review (SR) | 2021-01-25 | Engineering
114202896 | 990 | Conduct: Supplemental Review (SR) | 2021-02-01 | Engineering
114202896 | 990 | Conduct: Supplemental Review (SR) | 2021-02-08 | Engineering
114202896 | 990 | Conduct: Supplemental Review (SR) | 2021-02-16 | Engineering
114202896 | 990 | Conduct: Supplemental Review (SR) | 2021-02-23 | Engineering
114202896 | 990 | Conduct: Supplemental Review (SR) | 2021-03-02 | Engineering
114202896 | 990 | Conduct: Supplemental Review (SR) | 2021-03-09 | Engineering
114202896 | 990 | Conduct: Supplemental Review (SR) | 2021-03-16 | Engineering
114202896 | 990 | Conduct: Supplemental Review (SR) | 2021-03-23 | Engineering
114202896 | 990 | Conduct: Supplemental Review (SR) | 2021-03-30 | Engineering
118749669 | 991 | Conduct: Initial Review (IR) | 2021-03-31 | Engineering
117013354 | 992 | Conduct: ODA/FC Phase I Study | 2021-02-17 | Engineering
118758903 | 993 | Conduct: SIS | 2021-01-27 | Engineering
118758903 | 993 | Conduct: SIS | 2021-03-04 | Engineering
118758903 | 993 | Conduct: SIS | 2021-04-08 | Engineering
118142441 | 994 | Conduct: FAS | 2020-12-31 | Engineering
118142441 | 994 | Conduct: FAS | 2021-01-08 | Engineering
118142441 | 994 | Conduct: FAS | 2021-01-15 | Engineering
118142441 | 994 | Conduct: FAS | 2021-01-25 | Engineering
119016704 | 995 | Conduct: SIS | 2021-02-03 | Engineering
119016704 | 995 | Conduct: SIS | 2021-02-10 | Engineering
119016704 | 995 | Conduct: SIS | 2021-02-18 | Engineering
119841543 | 996 | Conduct: Initial Review (IR) | 2021-04-15 | Engineering
119065489 | 997 | Conduct: SIS | 2021-01-20 | Engineering
119065489 | 997 | Conduct: SIS | 2021-01-27 | Engineering
114211080 | 998 | Conduct: Initial Review (IR) | 2021-02-02 | Engineering
114211080 | 998 | Conduct: Initial Review (IR) | 2021-02-09 | Engineering
114211080 | 998 | Conduct: Initial Review (IR) | 2021-02-17 | Engineering
114211080 | 998 | Conduct: Initial Review (IR) | 2021-02-24 | Engineering
119956982 | 999 | Conduct: Initial Review (IR) | 2021-04-15 | Engineering
119956982 | 999 | Conduct: Initial Review (IR) | 2021-04-22 | Engineering
119907055 | 1000 | Conduct: SIS | 2021-03-26 | Engineering
119907055 | 1000 | Conduct: SIS | 2021-04-02 | Engineering
119184545 | 1001 | Conduct: SIS | 2021-03-17 | Engineering
119867901 | 1002 | Conduct: Initial Review (IR) | 2021-01-13 | Engineering
119867901 | 1002 | Conduct: Initial Review (IR) | 2021-01-21 | Engineering
120019974 | 1003 | Conduct: Initial Review (IR) | 2021-02-02 | Engineering
120019974 | 1003 | Conduct: Initial Review (IR) | 2021-02-09 | Engineering
119026209 | 1004 | Conduct: SIS | 2021-04-21 | Engineering
119687649 | 1005 | Conduct: Supplemental Review (SR) | 2021-01-29 | Engineering
119687649 | 1005 | Conduct: Supplemental Review (SR) | 2021-02-05 | Engineering
120224429 | 1006 | Conduct: Initial Review (IR) | 2021-04-12 | Engineering
120224429 | 1006 | Conduct: Initial Review (IR) | 2021-04-19 | Engineering
120224429 | 1006 | Conduct: Initial Review (IR) | 2021-04-26 | Engineering
120216117 | 1007 | Conduct: Screens Q and R | 2021-02-19 | Engineering
120216117 | 1007 | Determine Material Modifications | 2021-09-03 | Engineering – requiring more detailed review
120216117 | 1007 | Determine Material Modifications | 2021-10-03 | Project Management – requiring more detailed review
120216117 | 1007 | Determine Material Modifications | 2021-10-29 | Project Management – requiring more detailed review
120403503 | 1008 | Conduct: EIT | 2021-03-11 | Engineering
120403503 | 1008 | Conduct: EIT | 2021-04-12 | Engineering
120403503 | 1008 | Conduct: EIT | 2021-06-08 | Engineering
120403503 | 1008 | Conduct: EIT | 2021-06-15 | Engineering
120403503 | 1008 | Conduct: EIT | 2021-06-22 | Engineering
120403503 | 1008 | Conduct: EIT | 2021-06-29 | Engineering
120143746 | 1009 | Conduct: Initial Review (IR) | 2021-04-23 | Engineering
120143746 | 1009 | Conduct: Initial Review (IR) | 2021-05-12 | Engineering
119927046 | 1010 | Conduct: Supplemental Review (SR) | 2021-02-24 | Engineering
119927046 | 1010 | Conduct: Supplemental Review (SR) | 2021-03-03 | Engineering
118991454 | 1011 | Conduct: SIS | 2021-04-27 | Engineering
120258785 | 1012 | Conduct: Initial Review (IR) | 2021-02-24 | Engineering
120258785 | 1012 | Conduct: Initial Review (IR) | 2021-03-03 | Engineering
120258785 | 1012 | Conduct: Initial Review (IR) | 2021-03-10 | Engineering
120258785 | 1012 | Conduct: Initial Review (IR) | 2021-03-30 | Engineering
120258785 | 1012 | Conduct: Initial Review (IR) | 2021-02-24 | Engineering
120258785 | 1012 | Conduct: Initial Review (IR) | 2021-03-03 | Engineering
120258785 | 1012 | Conduct: Initial Review (IR) | 2021-03-10 | Engineering
120258785 | 1012 | Conduct: Initial Review (IR) | 2021-03-30 | Engineering
120258785 | 1012 | Conduct: Initial Review (IR) | 2021-02-24 | Engineering
120258785 | 1012 | Conduct: Initial Review (IR) | 2021-03-03 | Engineering
120258785 | 1012 | Conduct: Initial Review (IR) | 2021-03-10 | Engineering
120258785 | 1012 | Conduct: Initial Review (IR) | 2021-03-30 | Engineering
120178634 | 1013 | Conduct: Initial Review (IR) | 2021-03-11 | Engineering
120178634 | 1013 | Conduct: Initial Review (IR) | 2021-03-18 | Engineering
120178634 | 1013 | Conduct: Initial Review (IR) | 2021-04-01 | Engineering
120242384 | 1014 | Conduct: Initial Review (IR) | 2021-03-11 | Engineering
120242384 | 1014 | Conduct: Initial Review (IR) | 2021-03-11 | Engineering
120242384 | 1014 | Conduct: Initial Review (IR) | 2021-03-11 | Engineering
119766595 | 1015 | Conduct: Initial Review (IR) | 2021-04-09 | Engineering
119766595 | 1015 | Conduct: Initial Review (IR) | 2021-04-16 | Engineering
119766595 | 1015 | Conduct: Initial Review (IR) | 2021-04-23 | Engineering
118533780 | 1016 | Conduct: Initial Review (IR) | 2021-04-02 | Engineering
118533780 | 1016 | Conduct: Initial Review (IR) | 2021-06-25 | Engineering
120043078 | 1017 | Conduct: Initial Review (IR) | 2021-04-06 | Engineering
120043078 | 1017 | Conduct: Initial Review (IR) | 2021-04-20 | Engineering
120508895 | 1018 | Conduct: Initial Review (IR) | 2021-04-15 | Engineering
120098063 | 1019 | Conduct: Initial Review (IR) | 2021-04-09 | Engineering
120098063 | 1019 | Conduct: Initial Review (IR) | 2021-04-16 | Engineering
120507711 | 1020 | Conduct: Screens Q and R | 2021-04-07 | Engineering
120507711 | 1020 | Conduct: Screens Q and R | 2021-04-14 | Engineering
120507711 | 1020 | Conduct: Screens Q and R | 2021-04-23 | Engineering
120507711 | 1020 | Conduct: Screens Q and R | 2021-05-07 | Engineering
120507711 | 1020 | Conduct: SIS | 2021-09-17 | Engineering – requiring more detailed review
120507711 | 1020 | Conduct: SIS | 2021-09-24 | Engineering – requiring more detailed review
120507711 | 1020 | Conduct: Screens Q and R | 2021-04-07 | Engineering
120507711 | 1020 | Conduct: Screens Q and R | 2021-04-14 | Engineering
120507711 | 1020 | Conduct: Screens Q and R | 2021-04-23 | Engineering
120507711 | 1020 | Conduct: Screens Q and R | 2021-05-07 | Engineering
120507711 | 1020 | Conduct: SIS | 2021-09-17 | Engineering – requiring more detailed review
120507711 | 1020 | Conduct: SIS | 2021-09-24 | Engineering – requiring more detailed review
120507711 | 1020 | Conduct: Screens Q and R | 2021-04-07 | Engineering
120507711 | 1020 | Conduct: Screens Q and R | 2021-04-14 | Engineering
120507711 | 1020 | Conduct: Screens Q and R | 2021-04-23 | Engineering
120507711 | 1020 | Conduct: Screens Q and R | 2021-05-07 | Engineering
120507711 | 1020 | Conduct: SIS | 2021-09-17 | Engineering – requiring more detailed review
120507711 | 1020 | Conduct: SIS | 2021-09-24 | Engineering – requiring more detailed review
119895709 | 1021 | Conduct: Supplemental Review (SR) | 2021-04-07 | Engineering
119895709 | 1021 | Conduct: Supplemental Review (SR) | 2021-04-14 | Engineering
120210179 | 1022 | Conduct: Initial Review (IR) | 2021-04-14 | Engineering
120425293 | 1023 | Conduct: Initial Review (IR) | 2021-04-15 | Engineering
120425293 | 1023 | Conduct: Initial Review (IR) | 2021-04-29 | Engineering
120425293 | 1023 | Conduct: Initial Review (IR) | 2021-04-15 | Engineering
120425293 | 1023 | Conduct: Initial Review (IR) | 2021-04-29 | Engineering
120425293 | 1023 | Conduct: Initial Review (IR) | 2021-04-15 | Engineering
120425293 | 1023 | Conduct: Initial Review (IR) | 2021-04-29 | Engineering
120553203 | 1024 | Conduct: Initial Review (IR) | 2021-04-15 | Engineering
120553203 | 1024 | Conduct: Initial Review (IR) | 2021-04-15 | Engineering
120553203 | 1024 | Conduct: Initial Review (IR) | 2021-04-15 | Engineering
120512635 | 1025 | Conduct: Initial Review (IR) | 2021-04-20 | Engineering
120512635 | 1025 | Conduct: Initial Review (IR) | 2021-04-20 | Engineering
120512635 | 1025 | Conduct: Initial Review (IR) | 2021-04-20 | Engineering
120536314 | 1026 | Conduct: Screens Q and R | 2021-04-08 | Engineering
120536314 | 1026 | Conduct: Screens Q and R | 2021-04-08 | Engineering
120536314 | 1026 | Conduct: Screens Q and R | 2021-04-08 | Engineering
120531980 | 1027 | Conduct: Initial Review (IR) | 2021-04-16 | Engineering
120531980 | 1027 | Conduct: Initial Review (IR) | 2021-04-16 | Engineering
120531980 | 1027 | Conduct: Initial Review (IR) | 2021-04-16 | Engineering
120592266 | 1028 | Conduct: Initial Review (IR) | 2021-04-12 | Engineering
120592266 | 1028 | Conduct: Initial Review (IR) | 2021-04-12 | Engineering
120592266 | 1028 | Conduct: Initial Review (IR) | 2021-04-12 | Engineering
120479518 | 1029 | Conduct: Initial Review (IR) | 2021-04-13 | Engineering
120479518 | 1029 | Conduct: Initial Review (IR) | 2021-04-13 | Engineering
120479518 | 1029 | Conduct: Initial Review (IR) | 2021-04-13 | Engineering
120479413 | 1030 | Conduct: Initial Review (IR) | 2021-04-14 | Engineering
120479413 | 1030 | Conduct: Initial Review (IR) | 2021-04-14 | Engineering
120479413 | 1030 | Conduct: Initial Review (IR) | 2021-04-14 | Engineering
120611966 | 1031 | Conduct: Initial Review (IR) | 2021-04-15 | Engineering
120611966 | 1031 | Conduct: Initial Review (IR) | 2021-04-15 | Engineering
120611966 | 1031 | Conduct: Initial Review (IR) | 2021-04-15 | Engineering
118944936 | 1032 | Conduct: Initial Review (IR) | 2021-04-22 | Engineering
120602200 | 1033 | Conduct: Initial Review (IR) | 2021-04-16 | Engineering
120602200 | 1033 | Conduct: Initial Review (IR) | 2021-04-30 | Engineering
120602200 | 1033 | Conduct: Initial Review (IR) | 2021-04-16 | Engineering
120602200 | 1033 | Conduct: Initial Review (IR) | 2021-04-30 | Engineering
120602200 | 1033 | Conduct: Initial Review (IR) | 2021-04-16 | Engineering
120602200 | 1033 | Conduct: Initial Review (IR) | 2021-04-30 | Engineering
120601849 | 1034 | Conduct: Initial Review (IR) | 2021-04-12 | Engineering
120601849 | 1034 | Conduct: Initial Review (IR) | 2021-04-12 | Engineering
120601849 | 1034 | Conduct: Initial Review (IR) | 2021-04-12 | Engineering
120617291 | 1035 | Conduct: Initial Review (IR) | 2021-04-12 | Engineering
120617291 | 1035 | Conduct: Initial Review (IR) | 2021-04-19 | Engineering
120617291 | 1035 | Conduct: Initial Review (IR) | 2021-04-26 | Engineering
120617291 | 1035 | Conduct: Initial Review (IR) | 2021-04-12 | Engineering
120617291 | 1035 | Conduct: Initial Review (IR) | 2021-04-19 | Engineering
120617291 | 1035 | Conduct: Initial Review (IR) | 2021-04-26 | Engineering
120617291 | 1035 | Conduct: Initial Review (IR) | 2021-04-12 | Engineering
120617291 | 1035 | Conduct: Initial Review (IR) | 2021-04-19 | Engineering
120617291 | 1035 | Conduct: Initial Review (IR) | 2021-04-26 | Engineering
120591196 | 1036 | Conduct: Initial Review (IR) | 2021-04-14 | Engineering
120591196 | 1036 | Conduct: Initial Review (IR) | 2021-04-14 | Engineering
120591196 | 1036 | Conduct: Initial Review (IR) | 2021-04-14 | Engineering
120651788 | 1037 | Conduct: Initial Review (IR) | 2021-04-14 | Engineering
120477924 | 1038 | Conduct: Initial Review (IR) | 2021-04-22 | Engineering
120477924 | 1038 | Conduct: Initial Review (IR) | 2021-05-06 | Engineering
120477924 | 1038 | Conduct: Initial Review (IR) | 2021-05-18 | Engineering
120477924 | 1038 | Conduct: Initial Review (IR) | 2021-04-22 | Engineering
120477924 | 1038 | Conduct: Initial Review (IR) | 2021-05-06 | Engineering
120477924 | 1038 | Conduct: Initial Review (IR) | 2021-05-18 | Engineering
120477924 | 1038 | Conduct: Initial Review (IR) | 2021-04-22 | Engineering
120477924 | 1038 | Conduct: Initial Review (IR) | 2021-05-06 | Engineering
120477924 | 1038 | Conduct: Initial Review (IR) | 2021-05-18 | Engineering
120585023 | 1039 | Conduct: Initial Review (IR) | 2021-04-22 | Engineering
120585023 | 1039 | Conduct: Initial Review (IR) | 2021-04-29 | Engineering
120585023 | 1039 | Conduct: Initial Review (IR) | 2021-04-22 | Engineering
120585023 | 1039 | Conduct: Initial Review (IR) | 2021-04-29 | Engineering
120585023 | 1039 | Conduct: Initial Review (IR) | 2021-04-22 | Engineering
120585023 | 1039 | Conduct: Initial Review (IR) | 2021-04-29 | Engineering
120567198 | 1040 | Conduct: Supplemental Review (SR) | 2021-04-22 | Engineering
120567198 | 1040 | Conduct: Supplemental Review (SR) | 2021-04-29 | Engineering
120567198 | 1040 | Conduct: Supplemental Review (SR) | 2021-04-22 | Engineering
120567198 | 1040 | Conduct: Supplemental Review (SR) | 2021-04-29 | Engineering
120567198 | 1040 | Conduct: Supplemental Review (SR) | 2021-04-22 | Engineering
120567198 | 1040 | Conduct: Supplemental Review (SR) | 2021-04-29 | Engineering
120174538 | 1041 | Conduct: Supplemental Review (SR) | 2021-04-22 | Engineering
120174538 | 1041 | Conduct: Supplemental Review (SR) | 2021-04-29 | Engineering
120049327 | 1042 | Conduct: Supplemental Review (SR) | 2021-04-22 | Engineering
120049327 | 1042 | Conduct: Supplemental Review (SR) | 2021-05-06 | Engineering
120474545 | 1043 | Conduct: Initial Review (IR) | 2021-04-23 | Engineering
120612319 | 1044 | Conduct: Initial Review (IR) | 2021-04-19 | Engineering
120617490 | 1045 | Conduct: Initial Review (IR) | 2021-04-26 | Engineering
120617490 | 1045 | Conduct: Initial Review (IR) | 2021-05-03 | Engineering
120554661 | 1046 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
120554661 | 1046 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
120554661 | 1046 | Conduct: Initial Review (IR) | 2021-05-10 | Engineering
120538796 | 1047 | Conduct: Initial Review (IR) | 2021-04-20 | Engineering
120538796 | 1047 | Conduct: Initial Review (IR) | 2021-04-20 | Engineering
120538796 | 1047 | Conduct: Initial Review (IR) | 2021-04-20 | Engineering
120658969 | 1048 | Conduct: Initial Review (IR) | 2021-04-20 | Engineering
120606763 | 1049 | Conduct: Initial Review (IR) | 2021-04-23 | Engineering
120606763 | 1049 | Conduct: Initial Review (IR) | 2021-04-30 | Engineering
120498232 | 1050 | Conduct: Initial Review (IR) | 2021-04-30 | Engineering
120498232 | 1050 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering
120498232 | 1050 | Conduct: Initial Review (IR) | 2021-04-30 | Engineering
120498232 | 1050 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering
120498232 | 1050 | Conduct: Initial Review (IR) | 2021-04-30 | Engineering
120498232 | 1050 | Conduct: Initial Review (IR) | 2021-05-19 | Engineering
120653902 | 1051 | Conduct: Initial Review (IR) | 2021-04-26 | Engineering
120653902 | 1051 | Conduct: Initial Review (IR) | 2021-04-26 | Engineering
120653902 | 1051 | Conduct: Initial Review (IR) | 2021-04-26 | Engineering
120689568 | 1052 | Conduct: Initial Review (IR) | 2021-04-27 | Engineering
120690329 | 1053 | Conduct: Screens Q and R | 2021-05-05 | Engineering
120690329 | 1053 | Conduct: SIS | 2021-08-09 | Engineering – addressing project volume surge
120690329 | 1053 | Determine Material Modifications | 2021-09-17 | Engineering – addressing project volume surge
120690329 | 1053 | Conduct: Screens Q and R | 2021-05-05 | Engineering
120690329 | 1053 | Conduct: SIS | 2021-08-09 | Engineering – addressing project volume surge
120690329 | 1053 | Determine Material Modifications | 2021-09-17 | Engineering – addressing project volume surge
120690329 | 1053 | Conduct: Screens Q and R | 2021-05-05 | Engineering
120690329 | 1053 | Conduct: SIS | 2021-08-09 | Engineering – addressing project volume surge
120690329 | 1053 | Determine Material Modifications | 2021-09-17 | Engineering – addressing project volume surge
120616157 | 1054 | Conduct: Initial Review (IR) | 2021-05-11 | Engineering
120693351 | 1055 | Conduct: Initial Review (IR) | 2021-05-03 | Engineering
120712036 | 1056 | Conduct: Initial Review (IR) | 2021-05-03 | Engineering
120659600 | 1057 | Conduct: Initial Review (IR) | 2021-05-04 | Engineering
119926766 | 1058 | Conduct: SIS | 2021-06-16 | Engineering – addres
119926766 | 1058 | Conduct: SIS | 2021-06-23 | Engineering – addres
119926766 | 1058 | Conduct: SIS | 2021-06-30 | Engineering – addres
119926766 | 1058 | Conduct: SIS | 2021-06-09 | Engineering – addressing project volume surge
119294847 | 1059 | Conduct: SIS | 2021-06-24 | Engineering – addres
119294847 | 1059 | Conduct: SIS | 2021-06-17 | Engineering – addressing project volume surge
120685223 | 1060 | Conduct: EIT | 2021-06-16 | Engineering – addres
120685223 | 1060 | Conduct: EIT | 2021-06-23 | Engineering – addres
120685223 | 1060 | Conduct: EIT | 2021-06-30 | Engineering – addres
120685223 | 1060 | Conduct: EIT | 2021-07-08 | Engineering – addres
120685223 | 1060 | Conduct: EIT | 2021-07-15 | Engineering – addres
120685223 | 1060 | Conduct: EIT | 2021-06-09 | Engineering – addressing project volume surge
121582468 | 1061 | Conduct: Initial Review (IR) | 2021-08-03 | Engineering – addressing a human error
120229651 | 1062 | Conduct: Initial Review (IR) | 2021-08-31 | Engineering – addressing a human error
120229651 | 1062 | Conduct: Initial Review (IR) | 2021-09-21 | Engineering – requiring more detailed review
120658687 | 1063 | Conduct: EIT | 2021-07-30 | Engineering – addressing project volume surge
120658687 | 1063 | Conduct: EIT | 2021-08-06 | Engineering – addressing project volume surge
120658687 | 1063 | Conduct: EIT | 2021-08-13 | Engineering – addressing project volume surge
120658687 | 1063 | Conduct: EIT | 2021-08-20 | Engineering – addressing project volume surge
120746179 | 1064 | Conduct: Initial Review (IR) | 2021-07-02 | Engineering – addressing project volume surge
120746179 | 1064 | Conduct: Supplemental Review (SR) | 2021-09-17 | Engineering – requiring more detailed review
120746179 | 1064 | Conduct: Supplemental Review (SR) | 2021-09-24 | Engineering – requiring more detailed review
120461724 | 1065 | Conduct: SIS | 2021-08-06 | Engineering – addressing project volume surge
120745319 | 1066 | Conduct: EIT | 2021-06-09 | Engineering – addressing project volume surge
120746335 | 1067 | Conduct: Initial Review (IR) | 2021-07-02 | Engineering – addressing project volume surge
120746335 | 1067 | Conduct: Supplemental Review (SR) | 2021-09-17 | Engineering – requiring more detailed review
120746335 | 1067 | Conduct: Supplemental Review (SR) | 2021-09-24 | Engineering – requiring more detailed review
120719906 | 1068 | Conduct: SIS | 2021-09-03 | Engineering – addressing project volume surge
120719906 | 1068 | Conduct: SIS | 2021-09-13 | Engineering – addressing project volume surge
120719906 | 1068 | Conduct: SIS | 2021-09-20 | Engineering – addressing project volume surge
120719906 | 1068 | Conduct: SIS | 2021-09-27 | Engineering – addressing project volume surge
120719906 | 1068 | Conduct: SIS | 2021-10-04 | Engineering – addressing project volume surge
120719906 | 1068 | Conduct: SIS | 2021-10-11 | Engineering – requiring more detailed review
120719906 | 1068 | Conduct: SIS | 2021-10-18 | Engineering – requiring more detailed review
120719906 | 1068 | Conduct: SIS | 2021-10-25 | Engineering – requiring more detailed review
120601459 | 1069 | Conduct: SIS | 2021-09-18 | Engineering – addressing project volume surge
120601459 | 1069 | Conduct: SIS | 2021-09-24 | Engineering – addressing project volume surge
120601459 | 1069 | Conduct: SIS | 2021-10-01 | Engineering – addressing project volume surge
120601459 | 1069 | Conduct: SIS | 2021-10-08 | Engineering – addressing project volume surge
120886724 | 1070 | Conduct: EIT | 2021-07-12 | Engineering – addressing project volume surge
120886724 | 1070 | Conduct: EIT | 2021-07-19 | Engineering – addressing project volume surge
120886724 | 1070 | Conduct: EIT | 2021-07-26 | Engineering – addressing project volume surge
120886724 | 1070 | Conduct: EIT | 2021-08-02 | Engineering – addressing project volume surge
120886724 | 1070 | Conduct: EIT | 2021-08-09 | Engineering – addressing project volume surge
120886724 | 1070 | Conduct: EIT | 2021-08-16 | Engineering – addressing project volume surge
120886724 | 1070 | Conduct: EIT | 2021-08-23 | Engineering – addressing project volume surge
121334398 | 1071 | Conduct: Screens Q and R | 2021-07-27 | Engineering – addressing project volume surge
121334398 | 1071 | Conduct: Screens Q and R | 2021-07-27 | Engineering – addressing project volume surge
121334398 | 1071 | Determine Material Modifications | 2021-12-29 | Engineering – addressing project volume surge
121334398 | 1071 | Conduct: Screens Q and R | 2021-07-27 | Engineering – addressing project volume surge
121334398 | 1071 | Determine Material Modifications | 2021-12-29 | Engineering – addressing project volume surge
120856990 | 1072 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – addressing project volume surge
120856990 | 1072 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – addressing project volume surge
120856990 | 1072 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – addressing project volume surge
120872738 | 1073 | Conduct: Supplemental Review (SR) | 2021-08-06 | Engineering – addressing project volume surge
120872738 | 1073 | Conduct: Supplemental Review (SR) | 2021-08-06 | Engineering – addressing project volume surge
120872738 | 1073 | Conduct: Supplemental Review (SR) | 2021-08-06 | Engineering – addressing project volume surge
120929636 | 1074 | Conduct: Supplemental Review (SR) | 2021-08-17 | Engineering – addressing project volume surge
120929636 | 1074 | Conduct: Supplemental Review (SR) | 2021-08-23 | Engineering – requiring more detailed review
120929636 | 1074 | Conduct: Supplemental Review (SR) | 2021-08-17 | Engineering – addressing project volume surge
120929636 | 1074 | Conduct: Supplemental Review (SR) | 2021-08-23 | Engineering – requiring more detailed review
120929636 | 1074 | Conduct: Supplemental Review (SR) | 2021-08-17 | Engineering – addressing project volume surge
120929636 | 1074 | Conduct: Supplemental Review (SR) | 2021-08-23 | Engineering – requiring more detailed review
120932558 | 1075 | Conduct: Initial Review (IR) | 2021-08-16 | Engineering – addressing project volume surge
120932558 | 1075 | Conduct: Initial Review (IR) | 2021-08-16 | Engineering – addressing project volume surge
120932558 | 1075 | Conduct: Initial Review (IR) | 2021-08-16 | Engineering – addressing project volume surge
119775609 | 1076 | Conduct: Supplemental Review (SR) | 2021-08-23 | Engineering – addressing project volume surge
120950094 | 1077 | Conduct: Supplemental Review (SR) | 2021-08-27 | Engineering – addressing project volume surge
120950094 | 1077 | Conduct: Supplemental Review (SR) | 2021-08-27 | Engineering – addressing project volume surge
120950094 | 1077 | Conduct: Supplemental Review (SR) | 2021-08-27 | Engineering – addressing project volume surge
121322455 | 1078 | Conduct: Initial Review (IR) | 2021-08-13 | Engineering – addressing project volume surge
121322455 | 1078 | Conduct: Initial Review (IR) | 2021-08-13 | Engineering – addressing project volume surge
121322455 | 1078 | Conduct: Initial Review (IR) | 2021-08-13 | Engineering – addressing project volume surge
121736818 | 1079 | Conduct: Initial Review (IR) | 2021-08-25 | Engineering – addressing project volume surge
121736818 | 1079 | Conduct: Initial Review (IR) | 2021-09-01 | Engineering – addressing project volume surge
121736818 | 1079 | Conduct: Initial Review (IR) | 2021-09-09 | Engineering – addressing project volume surge
121736818 | 1079 | Conduct: Initial Review (IR) | 2021-09-16 | Engineering – addressing project volume surge
121736818 | 1079 | Conduct: Initial Review (IR) | 2021-09-23 | Engineering – addressing project volume surge
121403946 | 1080 | Conduct: Initial Review (IR) | 2021-09-18 | Engineering – addressing project volume surge
121403946 | 1080 | Conduct: Initial Review (IR) | 2021-09-15 | Engineering – requiring more detailed review
121403946 | 1080 | Conduct: Initial Review (IR) | 2021-09-18 | Engineering – addressing project volume surge
121403946 | 1080 | Conduct: Initial Review (IR) | 2021-09-15 | Engineering – requiring more detailed review
121403946 | 1080 | Conduct: Initial Review (IR) | 2021-09-18 | Engineering – addressing project volume surge
121403946 | 1080 | Conduct: Initial Review (IR) | 2021-09-15 | Engineering – requiring more detailed review
121780249 | 1081 | Conduct: Initial Review (IR) | 2021-09-09 | Engineering – addressing project volume surge
121780249 | 1081 | Conduct: Initial Review (IR) | 2021-09-16 | Engineering – requiring more detailed review
121780249 | 1081 | Conduct: Initial Review (IR) | 2021-09-09 | Engineering – addressing project volume surge
121780249 | 1081 | Conduct: Initial Review (IR) | 2021-09-16 | Engineering – requiring more detailed review
121780249 | 1081 | Conduct: Initial Review (IR) | 2021-09-09 | Engineering – addressing project volume surge
121780249 | 1081 | Conduct: Initial Review (IR) | 2021-09-16 | Engineering – requiring more detailed review
121645055 | 1082 | Conduct: Supplemental Review (SR) | 2021-09-17 | Engineering – addressing project volume surge
121645055 | 1082 | Conduct: Supplemental Review (SR) | 2021-09-24 | Engineering – addressing project volume surge
121645055 | 1082 | Conduct: Supplemental Review (SR) | 2021-10-01 | Engineering – addressing project volume surge
121645055 | 1082 | Conduct: Supplemental Review (SR) | 2021-10-08 | Engineering – addressing project volume surge
121645055 | 1082 | Conduct: Initial Review (IR) | 2021-08-04 | Engineering – requiring more detailed review
121645055 | 1082 | Conduct: Supplemental Review (SR) | 2021-09-17 | Engineering – addressing project volume surge
121645055 | 1082 | Conduct: Supplemental Review (SR) | 2021-09-24 | Engineering – addressing project volume surge
121645055 | 1082 | Conduct: Supplemental Review (SR) | 2021-10-01 | Engineering – addressing project volume surge
121645055 | 1082 | Conduct: Supplemental Review (SR) | 2021-10-08 | Engineering – addressing project volume surge
121645055 | 1082 | Conduct: Initial Review (IR) | 2021-08-04 | Engineering – requiring more detailed review
121645055 | 1082 | Conduct: Supplemental Review (SR) | 2021-09-17 | Engineering – addressing project volume surge
121645055 | 1082 | Conduct: Supplemental Review (SR) | 2021-09-24 | Engineering – addressing project volume surge
121645055 | 1082 | Conduct: Supplemental Review (SR) | 2021-10-01 | Engineering – addressing project volume surge
121645055 | 1082 | Conduct: Supplemental Review (SR) | 2021-10-08 | Engineering – addressing project volume surge
121645055 | 1082 | Conduct: Initial Review (IR) | 2021-08-04 | Engineering – requiring more detailed review
121716853 | 1083 | Conduct: Supplemental Review (SR) | 2021-09-22 | Engineering – addressing project volume surge
121716853 | 1083 | Conduct: Supplemental Review (SR) | 2021-09-22 | Engineering – addressing project volume surge
121716853 | 1083 | Conduct: SIS | 2022-02-03 | Engineering – requiring more detailed review
121716853 | 1083 | Conduct: Supplemental Review (SR) | 2021-09-22 | Engineering – addressing project volume surge
121716853 | 1083 | Conduct: SIS | 2022-02-03 | Engineering – requiring more detailed review
120910554 | 1084 | Conduct: Supplemental Review (SR) | 2021-09-23 | Engineering – addressing project volume surge
120910554 | 1084 | Conduct: Supplemental Review (SR) | 2021-09-30 | Engineering – addressing project volume surge
120910554 | 1084 | Conduct: Supplemental Review (SR) | 2021-09-23 | Engineering – addressing project volume surge
120910554 | 1084 | Conduct: Supplemental Review (SR) | 2021-09-30 | Engineering – addressing project volume surge
120910554 | 1084 | Conduct: Supplemental Review (SR) | 2021-09-23 | Engineering – addressing project volume surge
120910554 | 1084 | Conduct: Supplemental Review (SR) | 2021-09-30 | Engineering – addressing project volume surge
121807295 | 1085 | Conduct: Supplemental Review (SR) | 2021-09-25 | Engineering – addressing project volume surge
121807295 | 1085 | Conduct: Supplemental Review (SR) | 2021-10-01 | Engineering – requiring more detailed review
121807295 | 1085 | Conduct: Supplemental Review (SR) | 2021-09-25 | Engineering – addressing project volume surge
121807295 | 1085 | Conduct: Supplemental Review (SR) | 2021-10-01 | Engineering – requiring more detailed review
121807295 | 1085 | Conduct: SIS | 2022-01-26 | Project Management – addressing a human error
121807295 | 1085 | Conduct: Supplemental Review (SR) | 2021-09-25 | Engineering – addressing project volume surge
121807295 | 1085 | Conduct: Supplemental Review (SR) | 2021-10-01 | Engineering – requiring more detailed review
121807295 | 1085 | Conduct: SIS | 2022-01-26 | Project Management – addressing a human error
121644536 | 1086 | Conduct: Supplemental Review (SR) | 2021-10-01 | Engineering – addressing project volume surge
121644536 | 1086 | Conduct: Supplemental Review (SR) | 2021-10-08 | Engineering – addressing project volume surge
121644536 | 1086 | Conduct: Supplemental Review (SR) | 2021-10-15 | Engineering – addressing project volume surge
121644536 | 1086 | Conduct: Supplemental Review (SR) | 2021-10-22 | Engineering – addressing project volume surge
121925307 | 1087 | Conduct: Initial Review (IR) | 2021-10-29 | Engineering – addressing project volume surge
121925307 | 1087 | Conduct: Initial Review (IR) | 2021-10-15 | Engineering – requiring more detailed review
121925307 | 1087 | Conduct: Initial Review (IR) | 2021-10-29 | Engineering – addressing project volume surge
121925307 | 1087 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – addressing project volume surge
121925307 | 1087 | Conduct: Initial Review (IR) | 2021-11-19 | Engineering – addressing project volume surge
121925307 | 1087 | Conduct: Initial Review (IR) | 2021-10-15 | Engineering – requiring more detailed review
121925307 | 1087 | Conduct: Initial Review (IR) | 2021-11-30 | Engineering – requiring more detailed review
121925307 | 1087 | Conduct: Initial Review (IR) | 2021-12-14 | Engineering – requiring more detailed review
121925307 | 1087 | Conduct: Initial Review (IR) | 2021-10-29 | Engineering – addressing project volume surge
121925307 | 1087 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – addressing project volume surge
121925307 | 1087 | Conduct: Initial Review (IR) | 2021-11-19 | Engineering – addressing project volume surge
121925307 | 1087 | Conduct: Initial Review (IR) | 2021-10-15 | Engineering – requiring more detailed review
121925307 | 1087 | Conduct: Initial Review (IR) | 2021-11-30 | Engineering – requiring more detailed review
121925307 | 1087 | Conduct: Initial Review (IR) | 2021-12-14 | Engineering – requiring more detailed review
120935441 | 1088 | Conduct: Initial Review (IR) | 2021-10-11 | Engineering – addressing project volume surge
120935441 | 1088 | Conduct: Initial Review (IR) | 2021-10-18 | Engineering – requiring more detailed review
120935441 | 1088 | Conduct: Initial Review (IR) | 2021-11-04 | Engineering – requiring more detailed review
120935441 | 1088 | Conduct: Initial Review (IR) | 2021-10-11 | Engineering – addressing project volume surge
120935441 | 1088 | Conduct: Supplemental Review (SR) | 2021-12-14 | Engineering – addressing project volume surge
120935441 | 1088 | Conduct: Supplemental Review (SR) | 2021-12-21 | Engineering – addressing project volume surge
120935441 | 1088 | Conduct: Supplemental Review (SR) | 2021-12-27 | Engineering – addressing project volume surge
120935441 | 1088 | Conduct: Initial Review (IR) | 2021-10-18 | Engineering – requiring more detailed review
120935441 | 1088 | Conduct: Initial Review (IR) | 2021-11-04 | Engineering – requiring more detailed review
120935441 | 1088 | Conduct: Initial Review (IR) | 2021-10-11 | Engineering – addressing project volume surge
120935441 | 1088 | Conduct: Supplemental Review (SR) | 2021-12-14 | Engineering – addressing project volume surge
120935441 | 1088 | Conduct: Supplemental Review (SR) | 2021-12-21 | Engineering – addressing project volume surge
120935441 | 1088 | Conduct: Supplemental Review (SR) | 2021-12-27 | Engineering – addressing project volume surge
120935441 | 1088 | Conduct: Initial Review (IR) | 2021-10-18 | Engineering – requiring more detailed review
120935441 | 1088 | Conduct: Initial Review (IR) | 2021-11-04 | Engineering – requiring more detailed review
121911636 | 1089 | Conduct: Initial Review (IR) | 2021-10-27 | Engineering – addressing project volume surge
121911636 | 1089 | Conduct: Initial Review (IR) | 2021-10-20 | Engineering – requiring more detailed review
121911636 | 1089 | Conduct: Initial Review (IR) | 2021-10-27 | Engineering – addressing project volume surge
121911636 | 1089 | Conduct: Initial Review (IR) | 2021-10-20 | Engineering – requiring more detailed review
121911636 | 1089 | Conduct: Initial Review (IR) | 2021-10-27 | Engineering – addressing project volume surge
121911636 | 1089 | Conduct: Initial Review (IR) | 2021-10-20 | Engineering – requiring more detailed review
120897509 | 1090 | Conduct: Supplemental Review (SR) | 2021-11-04 | Engineering – addressing project volume surge
120897509 | 1090 | Conduct: Supplemental Review (SR) | 2021-11-04 | Engineering – addressing project volume surge
120897509 | 1090 | Conduct: Supplemental Review (SR) | 2021-11-18 | Engineering – addressing project volume surge
120897509 | 1090 | Conduct: Supplemental Review (SR) | 2021-12-09 | Engineering – addressing project volume surge
120897509 | 1090 | Conduct: SIS | 2022-05-05 | Engineering – addressing emergency power outages
120897509 | 1090 | Conduct: Supplemental Review (SR) | 2021-11-04 | Engineering – addressing project volume surge
120897509 | 1090 | Conduct: Supplemental Review (SR) | 2021-11-18 | Engineering – addressing project volume surge
120897509 | 1090 | Conduct: Supplemental Review (SR) | 2021-12-09 | Engineering – addressing project volume surge
122073071 | 1091 | Conduct: Initial Review (IR) | 2021-10-25 | Engineering – addressing project volume surge
121940872 | 1092 | Conduct: Supplemental Review (SR) | 2021-11-01 | Engineering – addressing project volume surge
121940872 | 1092 | Conduct: Supplemental Review (SR) | 2021-11-01 | Engineering – addressing project volume surge
121940872 | 1092 | Conduct: Supplemental Review (SR) | 2021-11-01 | Engineering – addressing project volume surge
122077215 | 1093 | Conduct: Initial Review (IR) | 2021-10-26 | Engineering – addressing project volume surge
122077819 | 1094 | Conduct: Initial Review (IR) | 2021-10-26 | Engineering – addressing project volume surge
122070534 | 1095 | Conduct: Initial Review (IR) | 2021-10-26 | Engineering – addressing project volume surge
121368198 | 1096 | EIT Customer Change Process (Cluster) | 2021-10-13 | Engineering – addressing project volume surge
122063796 | 1097 | Conduct: Initial Review (IR) | 2021-10-27 | Engineering – addressing project volume surge
118955812 | 1098 | Conduct: SIS | 2021-07-20 | Engineering – requiring more detailed review
119825563 | 1099 | Conduct: Supplemental Review (SR) | 2021-06-07 | Engineering – requiring more detailed review
121377527 | 1100 | Conduct: Initial Review (IR) | 2021-07-19 | Engineering – requiring more detailed review
121377527 | 1100 | Conduct: Initial Review (IR) | 2021-07-19 | Engineering – requiring more detailed review
121377527 | 1100 | Conduct: Initial Review (IR) | 2021-07-19 | Engineering – requiring more detailed review
120948228 | 1101 | Conduct: Initial Review (IR) | 2021-07-13 | Engineering – requiring more detailed review
120948228 | 1101 | Conduct: Initial Review (IR) | 2021-07-13 | Engineering – requiring more detailed review
120948228 | 1101 | Conduct: Initial Review (IR) | 2021-07-13 | Engineering – requiring more detailed review
121490418 | 1102 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
121490418 | 1102 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
121490418 | 1102 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
121490418 | 1102 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
121490418 | 1102 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
121490418 | 1102 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
120608844 | 1103 | Conduct: Initial Review (IR) | 2021-07-29 | Engineering – requiring more detailed review
120608844 | 1103 | Conduct: Initial Review (IR) | 2021-07-29 | Engineering – requiring more detailed review
120608844 | 1103 | Conduct: Initial Review (IR) | 2021-07-29 | Engineering – requiring more detailed review
120691162 | 1104 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
120691162 | 1104 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
120691162 | 1104 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
121535307 | 1105 | Conduct: Initial Review (IR) | 2021-07-23 | Engineering – requiring more detailed review
121535307 | 1105 | Conduct: Initial Review (IR) | 2021-07-23 | Engineering – requiring more detailed review
121535307 | 1105 | Conduct: Initial Review (IR) | 2021-07-23 | Engineering – requiring more detailed review
121008816 | 1106 | Conduct: Supplemental Review (SR) | 2021-07-26 | Engineering – requiring more detailed review
121008816 | 1106 | Conduct: Supplemental Review (SR) | 2021-07-26 | Engineering – requiring more detailed review
121008816 | 1106 | Conduct: Supplemental Review (SR) | 2021-07-26 | Engineering – requiring more detailed review
120708558 | 1107 | Conduct: Initial Review (IR) | 2021-08-02 | Engineering – requiring more detailed review
120708558 | 1107 | Conduct: Initial Review (IR) | 2021-08-02 | Engineering – requiring more detailed review
120708558 | 1107 | Conduct: Initial Review (IR) | 2021-08-02 | Engineering – requiring more detailed review
120793050 | 1108 | Conduct: Initial Review (IR) | 2021-07-16 | Engineering – requiring more detailed review
120793050 | 1108 | Conduct: Initial Review (IR) | 2021-07-16 | Engineering – requiring more detailed review
120793050 | 1108 | Conduct: Initial Review (IR) | 2021-07-16 | Engineering – requiring more detailed review
120793050 | 1108 | Conduct: Initial Review (IR) | 2021-07-16 | Engineering – requiring more detailed review
121523564 | 1109 | Conduct: Initial Review (IR) | 2021-07-26 | Engineering – requiring more detailed review
121523564 | 1109 | Conduct: Initial Review (IR) | 2021-07-26 | Engineering – requiring more detailed review
121523564 | 1109 | Conduct: Initial Review (IR) | 2021-07-26 | Engineering – requiring more detailed review
121535461 | 1110 | Conduct: Initial Review (IR) | 2021-07-20 | Engineering – requiring more detailed review
121535461 | 1110 | Conduct: Initial Review (IR) | 2021-07-27 | Engineering – requiring more detailed review
121535461 | 1110 | Conduct: Initial Review (IR) | 2021-08-10 | Engineering – requiring more detailed review
121535461 | 1110 | Conduct: Initial Review (IR) | 2021-08-17 | Engineering – requiring more detailed review
121535461 | 1110 | Conduct: Initial Review (IR) | 2021-07-27 | Engineering – requiring more detailed review
121535461 | 1110 | Conduct: Initial Review (IR) | 2021-07-20 | Engineering – requiring more detailed review
121535461 | 1110 | Conduct: Initial Review (IR) | 2021-08-10 | Engineering – requiring more detailed review
121535461 | 1110 | Conduct: Initial Review (IR) | 2021-08-17 | Engineering – requiring more detailed review
121535461 | 1110 | Conduct: Initial Review (IR) | 2021-07-20 | Engineering – requiring more detailed review
121535461 | 1110 | Conduct: Initial Review (IR) | 2021-07-27 | Engineering – requiring more detailed review
121535461 | 1110 | Conduct: Initial Review (IR) | 2021-08-10 | Engineering – requiring more detailed review
121535461 | 1110 | Conduct: Initial Review (IR) | 2021-08-17 | Engineering – requiring more detailed review
120656083 | 1111 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
120656083 | 1111 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
120656083 | 1111 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
120656083 | 1111 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
120656083 | 1111 | Conduct: Initial Review (IR) | 2021-07-21 | Engineering – requiring more detailed review
120656083 | 1111 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
119803178 | 1112 | Conduct: Initial Review (IR) | 2021-07-22 | Engineering – requiring more detailed review
119803178 | 1112 | Conduct: Initial Review (IR) | 2021-07-29 | Engineering – requiring more detailed review
119803178 | 1112 | Conduct: Initial Review (IR) | 2021-08-12 | Engineering – requiring more detailed review
118762492 | 1113 | Conduct: SIS | 2021-08-24 | Engineering – requiring more detailed review
121352460 | 1114 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
121352460 | 1114 | Conduct: Initial Review (IR) | 2021-08-11 | Engineering – requiring more detailed review
121352460 | 1114 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
121352460 | 1114 | Conduct: Initial Review (IR) | 2021-08-11 | Engineering – requiring more detailed review
121352460 | 1114 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
121352460 | 1114 | Conduct: Initial Review (IR) | 2021-08-11 | Engineering – requiring more detailed review
121351986 | 1115 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
121351986 | 1115 | Conduct: Initial Review (IR) | 2021-08-11 | Engineering – requiring more detailed review
121351986 | 1115 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
121351986 | 1115 | Conduct: Initial Review (IR) | 2021-08-11 | Engineering – requiring more detailed review
121351986 | 1115 | Conduct: Initial Review (IR) | 2021-07-28 | Engineering – requiring more detailed review
121351986 | 1115 | Conduct: Initial Review (IR) | 2021-08-11 | Engineering – requiring more detailed review
121352364 | 1116 | Conduct: Initial Review (IR) | 2021-07-29 | Engineering – requiring more detailed review
121352364 | 1116 | Conduct: Initial Review (IR) | 2021-08-12 | Engineering – requiring more detailed review
121352364 | 1116 | Conduct: Initial Review (IR) | 2021-08-12 | Project Management – requiring more detailed review
121352364 | 1116 | Conduct: Initial Review (IR) | 2021-07-29 | Engineering – requiring more detailed review
121352364 | 1116 | Conduct: Initial Review (IR) | 2021-08-12 | Engineering – requiring more detailed review
121352364 | 1116 | Conduct: Initial Review (IR) | 2021-08-12 | Project Management – requiring more detailed review
121352364 | 1116 | Conduct: Initial Review (IR) | 2021-07-29 | Engineering – requiring more detailed review
121352364 | 1116 | Conduct: Initial Review (IR) | 2021-08-12 | Engineering – requiring more detailed review
121352364 | 1116 | Conduct: Initial Review (IR) | 2021-08-12 | Project Management – requiring more detailed review
121352351 | 1117 | Conduct: Initial Review (IR) | 2021-07-29 | Engineering – requiring more detailed review
121352351 | 1117 | Conduct: Initial Review (IR) | 2021-08-12 | Engineering – requiring more detailed review
121352351 | 1117 | Conduct: Initial Review (IR) | 2021-07-29 | Engineering – requiring more detailed review
121352351 | 1117 | Conduct: Initial Review (IR) | 2021-08-12 | Engineering – requiring more detailed review
121352351 | 1117 | Conduct: Initial Review (IR) | 2021-07-29 | Engineering – requiring more detailed review
121352351 | 1117 | Conduct: Initial Review (IR) | 2021-08-12 | Engineering – requiring more detailed review
121322443 | 1118 | Conduct: Screens Q and R | 2021-08-10 | Engineering – requiring more detailed review
121322443 | 1118 | Conduct: Screens Q and R | 2021-08-10 | Engineering – requiring more detailed review
121322443 | 1118 | Conduct: Screens Q and R | 2021-08-10 | Engineering – requiring more detailed review
121541287 | 1119 | Conduct: Initial Review (IR) | 2021-08-17 | Engineering – requiring more detailed review
121541287 | 1119 | Conduct: Initial Review (IR) | 2021-09-10 | Engineering – requiring more detailed review
121541287 | 1119 | Conduct: Initial Review (IR) | 2021-08-17 | Engineering – requiring more detailed review
121541287 | 1119 | Conduct: Initial Review (IR) | 2021-09-10 | Engineering – requiring more detailed review
121541287 | 1119 | Conduct: Initial Review (IR) | 2021-08-17 | Engineering – requiring more detailed review
121541287 | 1119 | Conduct: Initial Review (IR) | 2021-09-10 | Engineering – requiring more detailed review
121533362 | 1120 | Conduct: Initial Review (IR) | 2021-08-11 | Engineering – requiring more detailed review
121533362 | 1120 | Conduct: Initial Review (IR) | 2021-08-25 | Engineering – requiring more detailed review
121533362 | 1120 | Conduct: Initial Review (IR) | 2021-08-11 | Engineering – requiring more detailed review
121533362 | 1120 | Conduct: Initial Review (IR) | 2021-08-25 | Engineering – requiring more detailed review
121533362 | 1120 | Conduct: Initial Review (IR) | 2021-08-11 | Engineering – requiring more detailed review
121533362 | 1120 | Conduct: Initial Review (IR) | 2021-08-25 | Engineering – requiring more detailed review
121590274 | 1121 | Conduct: Initial Review (IR) | 2021-08-12 | Engineering – requiring more detailed review
121590274 | 1121 | Conduct: Initial Review (IR) | 2021-08-19 | Engineering – requiring more detailed review
121590274 | 1121 | Conduct: Initial Review (IR) | 2021-08-12 | Engineering – requiring more detailed review
121590274 | 1121 | Conduct: Initial Review (IR) | 2021-08-19 | Engineering – requiring more detailed review
121590274 | 1121 | Conduct: Initial Review (IR) | 2021-08-12 | Engineering – requiring more detailed review
121590274 | 1121 | Conduct: Initial Review (IR) | 2021-08-19 | Engineering – requiring more detailed review
121347262 | 1122 | Conduct: Supplemental Review (SR) | 2021-08-16 | Engineering – requiring more detailed review
121347262 | 1122 | Conduct: Supplemental Review (SR) | 2021-08-16 | Engineering – requiring more detailed review
121347262 | 1122 | Conduct: Supplemental Review (SR) | 2021-08-16 | Engineering – requiring more detailed review
121630590 | 1123 | Conduct: Initial Review (IR) | 2021-08-23 | Engineering – requiring more detailed review
121630590 | 1123 | Conduct: Initial Review (IR) | 2021-08-23 | Engineering – requiring more detailed review
121630590 | 1123 | Conduct: Initial Review (IR) | 2021-08-23 | Engineering – requiring more detailed review
121624979 | 1124 | Conduct: Initial Review (IR) | 2021-08-17 | Engineering – requiring more detailed review
121624979 | 1124 | Conduct: Initial Review (IR) | 2021-08-31 | Engineering – requiring more detailed review
121624979 | 1124 | Conduct: Initial Review (IR) | 2021-08-17 | Engineering – requiring more detailed review
121624979 | 1124 | Conduct: Initial Review (IR) | 2021-08-31 | Engineering – requiring more detailed review
121624979 | 1124 | Conduct: Initial Review (IR) | 2021-08-17 | Engineering – requiring more detailed review
121624979 | 1124 | Conduct: Initial Review (IR) | 2021-08-31 | Engineering – requiring more detailed review
121632075 | 1125 | Conduct: Initial Review (IR) | 2021-08-17 | Engineering – requiring more detailed review
121632075 | 1125 | Conduct: Initial Review (IR) | 2021-08-17 | Engineering – requiring more detailed review
121632075 | 1125 | Conduct: Initial Review (IR) | 2021-08-17 | Engineering – requiring more detailed review
119523213 | 1126 | Conduct: Initial Review (IR) | 2021-08-17 | Engineering – requiring more detailed review
119523213 | 1126 | Conduct: Initial Review (IR) | 2021-08-03 | Project Management – addressing a human error
120531348 | 1127 | Conduct: Screens Q and R | 2021-08-23 | Engineering – requiring more detailed review
120531348 | 1127 | Conduct: Screens Q and R | 2021-08-31 | Engineering – requiring more detailed review
121630100 | 1128 | Conduct: Initial Review (IR) | 2021-08-19 | Engineering – requiring more detailed review
121630100 | 1128 | Conduct: Initial Review (IR) | 2021-09-02 | Engineering – requiring more detailed review
121630100 | 1128 | Conduct: Initial Review (IR) | 2021-08-19 | Engineering – requiring more detailed review
121630100 | 1128 | Conduct: Initial Review (IR) | 2021-09-02 | Engineering – requiring more detailed review
121630100 | 1128 | Conduct: SIS | 2022-03-22 | Cus – requirement to provide a response to deficiency notice
121630100 | 1128 | Conduct: Initial Review (IR) | 2021-08-19 | Engineering – requiring more detailed review
121630100 | 1128 | Conduct: Initial Review (IR) | 2021-09-02 | Engineering – requiring more detailed review
121630100 | 1128 | Conduct: SIS | 2022-03-08 | Engineering – requiring more detailed review
121630100 | 1128 | Conduct: SIS | 2022-03-15 | Engineering – requiring more detailed review
121593388 | 1129 | Conduct: Initial Review (IR) | 2021-08-19 | Engineering – requiring more detailed review
121593388 | 1129 | Conduct: Initial Review (IR) | 2021-08-19 | Engineering – requiring more detailed review
121593388 | 1129 | Conduct: Initial Review (IR) | 2021-08-19 | Engineering – requiring more detailed review
121554184 | 1130 | Conduct: Screens Q and R | 2021-08-23 | Engineering – requiring more detailed review
121554184 | 1130 | Conduct: Screens Q and R | 2021-08-23 | Engineering – requiring more detailed review
121554184 | 1130 | Conduct: SIS | 2021-12-01 | Engineering – requiring more detailed review
121554184 | 1130 | Conduct: Screens Q and R | 2021-08-23 | Engineering – requiring more detailed review
121554184 | 1130 | Conduct: SIS | 2021-12-01 | Engineering – requiring more detailed review
121655443 | 1131 | Conduct: Initial Review (IR) | 2021-08-24 | Engineering – requiring more detailed review
121655443 | 1131 | Conduct: Initial Review (IR) | 2021-08-31 | Engineering – requiring more detailed review
121655443 | 1131 | Conduct: Initial Review (IR) | 2021-09-08 | Engineering – requiring more detailed review
121655443 | 1131 | Conduct: Initial Review (IR) | 2021-08-10 | Project Management – addressing a human error
121655443 | 1131 | Conduct: Initial Review (IR) | 2021-08-24 | Engineering – requiring more detailed review
121655443 | 1131 | Conduct: Initial Review (IR) | 2021-08-31 | Engineering – requiring more detailed review
121655443 | 1131 | Conduct: Initial Review (IR) | 2021-09-08 | Engineering – requiring more detailed review
121655443 | 1131 | Conduct: Initial Review (IR) | 2021-08-10 | Project Management – addressing a human error
121655443 | 1131 | Conduct: Initial Review (IR) | 2021-08-24 | Engineering – requiring more detailed review
121655443 | 1131 | Conduct: Initial Review (IR) | 2021-08-31 | Engineering – requiring more detailed review
121655443 | 1131 | Conduct: Initial Review (IR) | 2021-09-08 | Engineering – requiring more detailed review
121655443 | 1131 | Conduct: Initial Review (IR) | 2021-08-10 | Project Management – addressing a human error
120460496 | 1132 | Conduct: Initial Review (IR) | 2021-08-27 | Engineering – requiring more detailed review
120460496 | 1132 | Conduct: Initial Review (IR) | 2021-09-20 | Engineering – requiring more detailed review
120460496 | 1132 | Conduct: Initial Review (IR) | 2021-09-27 | Engineering – requiring more detailed review
120460496 | 1132 | Conduct: Initial Review (IR) | 2021-10-04 | Engineering – requiring more detailed review
120460496 | 1132 | Conduct: Initial Review (IR) | 2021-10-11 | Engineering – requiring more detailed review
120460496 | 1132 | Conduct: Initial Review (IR) | 2021-09-03 | Project Management – requiring more detailed review
120460496 | 1132 | Conduct: Initial Review (IR) | 2021-08-27 | Engineering – requiring more detailed review
120460496 | 1132 | Conduct: Initial Review (IR) | 2021-09-20 | Engineering – requiring more detailed review
120460496 | 1132 | Conduct: Initial Review (IR) | 2021-09-27 | Engineering – requiring more detailed review
120460496 | 1132 | Conduct: Initial Review (IR) | 2021-10-04 | Engineering – requiring more detailed review
120460496 | 1132 | Conduct: Initial Review (IR) | 2021-10-11 | Engineering – requiring more detailed review
120460496 | 1132 | Conduct: Initial Review (IR) | 2021-09-03 | Project Management – requiring more detailed review
120460496 | 1132 | Conduct: Initial Review (IR) | 2021-08-27 | Engineering – requiring more detailed review
120460496 | 1132 | Conduct: Initial Review (IR) | 2021-09-20 | Engineering – requiring more detailed review
120460496 | 1132 | Conduct: Initial Review (IR) | 2021-09-27 | Engineering – requiring more detailed review
120460496 | 1132 | Conduct: Initial Review (IR) | 2021-10-04 | Engineering – requiring more detailed review
120460496 | 1132 | Conduct: Initial Review (IR) | 2021-10-11 | Engineering – requiring more detailed review
120460496 | 1132 | Conduct: Initial Review (IR) | 2021-09-03 | Project Management – requiring more detailed review
121482058 | 1133 | Conduct: Supplemental Review (SR) | 2021-09-03 | Engineering – requiring more detailed review
121390538 | 1134 | Conduct: Initial Review (IR) | 2021-08-23 | Engineering – requiring more detailed review
121390538 | 1134 | Conduct: Initial Review (IR) | 2021-08-23 | Engineering – requiring more detailed review
121390538 | 1134 | Conduct: Initial Review (IR) | 2021-08-23 | Engineering – requiring more detailed review
121678999 | 1135 | Conduct: Initial Review (IR) | 2021-08-30 | Engineering – requiring more detailed review
121678999 | 1135 | Conduct: Initial Review (IR) | 2021-09-13 | Engineering – requiring more detailed review
121678996 | 1136 | Conduct: Initial Review (IR) | 2021-08-30 | Engineering – requiring more detailed review
121678996 | 1136 | Conduct: Initial Review (IR) | 2021-09-13 | Engineering – requiring more detailed review
121678996 | 1136 | Conduct: Initial Review (IR) | 2021-08-30 | Engineering – requiring more detailed review
121678996 | 1136 | Conduct: Initial Review (IR) | 2021-09-13 | Engineering – requiring more detailed review
121678996 | 1136 | Conduct: Initial Review (IR) | 2021-08-30 | Engineering – requiring more detailed review
121678996 | 1136 | Conduct: Initial Review (IR) | 2021-09-13 | Engineering – requiring more detailed review
121664160 | 1137 | Conduct: Initial Review (IR) | 2021-09-08 | Engineering – requiring more detailed review
121664160 | 1137 | Conduct: Initial Review (IR) | 2021-09-08 | Engineering – requiring more detailed review
121664160 | 1137 | Conduct: Initial Review (IR) | 2021-09-08 | Engineering – requiring more detailed review
121336530 | 1138 | Conduct: Supplemental Review (SR) | 2021-09-21 | Engineering – requiring more detailed review
121336530 | 1138 | Conduct: Supplemental Review (SR) | 2021-09-21 | Engineering – requiring more detailed review
121336530 | 1138 | Conduct: Supplemental Review (SR) | 2021-09-21 | Engineering – requiring more detailed review
121536344 | 1139 | Conduct: Supplemental Review (SR) | 2021-08-31 | Engineering – requiring more detailed review
121536334 | 1140 | Conduct: Supplemental Review (SR) | 2021-08-31 | Engineering – requiring more detailed review
121536133 | 1141 | Conduct: Supplemental Review (SR) | 2021-08-31 | Engineering – requiring more detailed review
121716126 | 1142 | Conduct: Initial Review (IR) | 2021-09-01 | Engineering – requiring more detailed review
121716126 | 1142 | Conduct: Initial Review (IR) | 2021-09-01 | Engineering – requiring more detailed review
121716126 | 1142 | Conduct: Initial Review (IR) | 2021-09-01 | Engineering – requiring more detailed review
120227273 | 1143 | Conduct: Initial Review (IR) | 2021-09-01 | Engineering – requiring more detailed review
120227273 | 1143 | Conduct: Initial Review (IR) | 2021-09-16 | Engineering – requiring more detailed review
120227273 | 1143 | Conduct: Initial Review (IR) | 2021-09-30 | Engineering – requiring more detailed review
120227273 | 1143 | Conduct: Initial Review (IR) | 2021-10-07 | Engineering – requiring more detailed review
120227273 | 1143 | Conduct: Initial Review (IR) | 2021-10-14 | Engineering – requiring more detailed review
120227273 | 1143 | Conduct: Initial Review (IR) | 2021-08-18 | Project Management – addressing a human error
121626896 | 1144 | Conduct: Initial Review (IR) | 2021-09-02 | Engineering – requiring more detailed review
121626896 | 1144 | Conduct: Initial Review (IR) | 2021-09-20 | Engineering – requiring more detailed review
121626896 | 1144 | Conduct: Initial Review (IR) | 2021-08-26 | Project Management – addressing a human error
121626896 | 1144 | Conduct: Initial Review (IR) | 2021-09-02 | Engineering – requiring more detailed review
121626896 | 1144 | Conduct: Initial Review (IR) | 2021-09-20 | Engineering – requiring more detailed review
121626896 | 1144 | Conduct: Initial Review (IR) | 2021-08-26 | Project Management – addressing a human error
121626896 | 1144 | Conduct: Initial Review (IR) | 2021-09-02 | Engineering – requiring more detailed review
121626896 | 1144 | Conduct: Initial Review (IR) | 2021-09-20 | Engineering – requiring more detailed review
121626896 | 1144 | Conduct: Initial Review (IR) | 2021-08-26 | Project Management – addressing a human error
121552131 | 1145 | Conduct: Initial Review (IR) | 2021-09-10 | Engineering – requiring more detailed review
121552131 | 1145 | Conduct: Initial Review (IR) | 2021-09-10 | Engineering – requiring more detailed review
121552131 | 1145 | Conduct: Initial Review (IR) | 2021-09-10 | Engineering – requiring more detailed review
120433597 | 1146 | Conduct: Initial Review (IR) | 2021-09-07 | Engineering – requiring more detailed review
120433597 | 1146 | Conduct: Initial Review (IR) | 2021-08-23 | Project Management – requiring more detailed review
120433597 | 1146 | Conduct: Initial Review (IR) | 2021-08-30 | Project Management – requiring more detailed review
120433597 | 1146 | Conduct: Initial Review (IR) | 2021-09-07 | Engineering – requiring more detailed review
120433597 | 1146 | Conduct: Initial Review (IR) | 2021-08-23 | Project Management – requiring more detailed review
120433597 | 1146 | Conduct: Initial Review (IR) | 2021-08-30 | Project Management – requiring more detailed review
120433597 | 1146 | Conduct: Initial Review (IR) | 2021-09-07 | Engineering – requiring more detailed review
120433597 | 1146 | Conduct: Initial Review (IR) | 2021-08-23 | Project Management – requiring more detailed review
120433597 | 1146 | Conduct: Initial Review (IR) | 2021-08-30 | Project Management – requiring more detailed review
121678407 | 1147 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – requiring more detailed review
121678407 | 1147 | Conduct: Initial Review (IR) | 2021-09-27 | Project Management – requiring more detailed review
121678407 | 1147 | Conduct: Initial Review (IR) | 2021-10-18 | Project Management – requiring more detailed review
121678407 | 1147 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – requiring more detailed review
121678407 | 1147 | Conduct: Initial Review (IR) | 2021-09-27 | Project Management – requiring more detailed review
121678407 | 1147 | Conduct: Initial Review (IR) | 2021-10-18 | Project Management – requiring more detailed review
121678407 | 1147 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – requiring more detailed review
121678407 | 1147 | Conduct: Initial Review (IR) | 2021-09-27 | Project Management – requiring more detailed review
121678407 | 1147 | Conduct: Initial Review (IR) | 2021-10-18 | Project Management – requiring more detailed review
121639356 | 1148 | Conduct: Initial Review (IR) | 2021-09-08 | Engineering – requiring more detailed review
121639356 | 1148 | Conduct: Initial Review (IR) | 2021-09-08 | Engineering – requiring more detailed review
121639356 | 1148 | Conduct: Screens Q and R | 2021-11-08 | Engineering – requiring more detailed review
121639356 | 1148 | Conduct: SIS | 2022-02-10 | Engineering – addressing project volume surge
121639356 | 1148 | Conduct: Initial Review (IR) | 2021-09-08 | Engineering – requiring more detailed review
121639356 | 1148 | Conduct: Screens Q and R | 2021-11-08 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-08-31 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-09-14 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-09-24 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-10-08 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-10-15 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-10-22 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-08-31 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-09-14 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-09-24 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-10-08 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-10-15 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-10-22 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-10-29 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-08-31 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-09-14 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-09-24 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-10-08 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-10-15 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-10-22 | Engineering – requiring more detailed review
121646778 | 1149 | Conduct: Initial Review (IR) | 2021-10-29 | Engineering – requiring more detailed review
121754384 | 1150 | Conduct: Initial Review (IR) | 2021-09-16 | Engineering – requiring more detailed review
121754384 | 1150 | Conduct: Screens Q and R | 2022-01-07 | Engineering – addressing a human error
121754384 | 1150 | Conduct: Initial Review (IR) | 2021-09-16 | Engineering – requiring more detailed review
121754384 | 1150 | Conduct: Supplemental Review (SR) | 2021-11-05 | Engineering – requiring more detailed review
121754384 | 1150 | Conduct: Screens Q and R | 2022-01-07 | Engineering – addressing a human error
121754384 | 1150 | Conduct: Initial Review (IR) | 2021-09-16 | Engineering – requiring more detailed review
121754384 | 1150 | Conduct: SIS | 2022-04-29 | Engineering – requiring more detailed review
121754384 | 1150 | Conduct: Supplemental Review (SR) | 2021-11-05 | Engineering – requiring more detailed review
121496977 | 1151 | Conduct: Initial Review (IR) | 2021-10-18 | Engineering – requiring more detailed review
121496977 | 1151 | Conduct: Initial Review (IR) | 2021-10-18 | Engineering – requiring more detailed review
121496977 | 1151 | Conduct: Initial Review (IR) | 2021-10-18 | Engineering – requiring more detailed review
121552919 | 1152 | Conduct: Initial Review (IR) | 2021-09-09 | Engineering – requiring more detailed review
121552919 | 1152 | Conduct: Initial Review (IR) | 2021-09-09 | Engineering – requiring more detailed review
121552919 | 1152 | Conduct: Initial Review (IR) | 2021-09-09 | Engineering – requiring more detailed review
121830404 | 1153 | Conduct: Initial Review (IR) | 2021-09-21 | Engineering – requiring more detailed review
121830404 | 1153 | Conduct: Initial Review (IR) | 2021-09-21 | Engineering – requiring more detailed review
121830404 | 1153 | Conduct: Initial Review (IR) | 2021-09-21 | Engineering – requiring more detailed review
121676464 | 1154 | Conduct: Screens Q and R | 2021-10-05 | Engineering – requiring more detailed review
121676464 | 1154 | Conduct: Screens Q and R | 2021-10-05 | Engineering – requiring more detailed review
121676464 | 1154 | Conduct: Screens Q and R | 2021-10-05 | Engineering – requiring more detailed review
121717607 | 1155 | Conduct: Supplemental Review (SR) | 2021-09-10 | Engineering – requiring more detailed review
121717607 | 1155 | Conduct: Supplemental Review (SR) | 2021-09-10 | Engineering – requiring more detailed review
121717607 | 1155 | Conduct: SIS | 2022-01-19 | Engineering – requiring more detailed review
121717607 | 1155 | Conduct: SIS | 2022-01-19 | Engineering – requiring more detailed review
121717607 | 1155 | Conduct: Supplemental Review (SR) | 2021-09-10 | Engineering – requiring more detailed review
117295590 | 1156 | Conduct: Initial Review (IR) | 2021-09-16 | Engineering – requiring more detailed review
120746268 | 1157 | Conduct: Supplemental Review (SR) | 2021-09-17 | Engineering – requiring more detailed review
120746268 | 1157 | Conduct: Supplemental Review (SR) | 2021-09-24 | Engineering – requiring more detailed review
121583458 | 1158 | Conduct: Initial Review (IR) | 2021-09-20 | Engineering – requiring more detailed review
121583458 | 1158 | Conduct: Initial Review (IR) | 2021-10-04 | Engineering – requiring more detailed review
121583458 | 1158 | Conduct: Initial Review (IR) | 2021-10-11 | Engineering – requiring more detailed review
121583458 | 1158 | Conduct: Initial Review (IR) | 2021-09-20 | Engineering – requiring more detailed review
121583458 | 1158 | Conduct: Initial Review (IR) | 2021-10-04 | Engineering – requiring more detailed review
121583458 | 1158 | Conduct: Initial Review (IR) | 2021-10-11 | Engineering – requiring more detailed review
121583458 | 1158 | Conduct: Initial Review (IR) | 2021-09-20 | Engineering – requiring more detailed review
121583458 | 1158 | Conduct: Initial Review (IR) | 2021-10-04 | Engineering – requiring more detailed review
121583458 | 1158 | Conduct: Initial Review (IR) | 2021-10-11 | Engineering – requiring more detailed review
121401104 | 1159 | Conduct: Initial Review (IR) | 2021-09-24 | Engineering – requiring more detailed review
121401104 | 1159 | Conduct: Initial Review (IR) | 2021-09-24 | Engineering – requiring more detailed review
121401104 | 1159 | Conduct: Supplemental Review (SR) | 2021-10-26 | Project Management – requiring more detailed review
121401104 | 1159 | Conduct: Initial Review (IR) | 2021-09-24 | Engineering – requiring more detailed review
121401104 | 1159 | Conduct: Supplemental Review (SR) | 2021-10-26 | Project Management – requiring more detailed review
121730121 | 1160 | Conduct: Initial Review (IR) | 2021-09-27 | Engineering – requiring more detailed review
121730121 | 1160 | Conduct: Initial Review (IR) | 2021-10-08 | Engineering – requiring more detailed review
121730121 | 1160 | Conduct: Initial Review (IR) | 2021-09-27 | Engineering – requiring more detailed review
121730121 | 1160 | Conduct: Initial Review (IR) | 2021-10-08 | Engineering – requiring more detailed review
121730121 | 1160 | Conduct: Initial Review (IR) | 2021-09-27 | Engineering – requiring more detailed review
121730121 | 1160 | Conduct: Initial Review (IR) | 2021-10-08 | Engineering – requiring more detailed review
121742796 | 1161 | Conduct: Supplemental Review (SR) | 2021-09-17 | Engineering – requiring more detailed review
121742796 | 1161 | Conduct: Supplemental Review (SR) | 2021-09-24 | Engineering – requiring more detailed review
121742796 | 1161 | Conduct: Supplemental Review (SR) | 2021-09-17 | Engineering – requiring more detailed review
121742796 | 1161 | Conduct: Supplemental Review (SR) | 2021-09-24 | Engineering – requiring more detailed review
121742796 | 1161 | Conduct: SIS | 2022-02-09 | Engineering – requiring more detailed review
121742796 | 1161 | Conduct: SIS | 2022-02-09 | Engineering – requiring more detailed review
121742796 | 1161 | Conduct: SIS | 2022-02-16 | Engineering – requiring more detailed review
121742796 | 1161 | Conduct: Supplemental Review (SR) | 2021-09-17 | Engineering – requiring more detailed review
121742796 | 1161 | Conduct: Supplemental Review (SR) | 2021-09-24 | Engineering – requiring more detailed review
121841040 | 1162 | Conduct: Initial Review (IR) | 2021-09-21 | Engineering – requiring more detailed review
121841040 | 1162 | Conduct: Initial Review (IR) | 2021-10-05 | Engineering – requiring more detailed review
121841040 | 1162 | Conduct: Initial Review (IR) | 2021-10-12 | Engineering – requiring more detailed review
121841040 | 1162 | Conduct: Initial Review (IR) | 2021-09-21 | Engineering – requiring more detailed review
121841040 | 1162 | Conduct: Initial Review (IR) | 2021-10-05 | Engineering – requiring more detailed review
121841040 | 1162 | Conduct: Initial Review (IR) | 2021-10-12 | Engineering – requiring more detailed review
121841040 | 1162 | Conduct: Initial Review (IR) | 2021-09-21 | Engineering – requiring more detailed review
121841040 | 1162 | Conduct: Initial Review (IR) | 2021-10-05 | Engineering – requiring more detailed review
121841040 | 1162 | Conduct: Initial Review (IR) | 2021-10-12 | Engineering – requiring more detailed review
121864229 | 1163 | Conduct: Initial Review (IR) | 2021-09-22 | Engineering – requiring more detailed review
121864229 | 1163 | Conduct: Initial Review (IR) | 2021-09-29 | Engineering – requiring more detailed review
121864229 | 1163 | Conduct: Initial Review (IR) | 2021-10-06 | Engineering – requiring more detailed review
121864229 | 1163 | Conduct: Initial Review (IR) | 2021-09-22 | Engineering – requiring more detailed review
121864229 | 1163 | Conduct: Initial Review (IR) | 2021-09-29 | Engineering – requiring more detailed review
121864229 | 1163 | Conduct: Initial Review (IR) | 2021-10-06 | Engineering – requiring more detailed review
121864229 | 1163 | Conduct: Initial Review (IR) | 2021-09-22 | Engineering – requiring more detailed review
121864229 | 1163 | Conduct: Initial Review (IR) | 2021-09-29 | Engineering – requiring more detailed review
121864229 | 1163 | Conduct: Initial Review (IR) | 2021-10-06 | Engineering – requiring more detailed review
121822650 | 1164 | Conduct: Initial Review (IR) | 2021-09-16 | Engineering – requiring more detailed review
121822650 | 1164 | Conduct: Supplemental Review (SR) | 2021-11-18 | Customer – requirement to provide corrected information
121822650 | 1164 | Conduct: Supplemental Review (SR) | 2021-11-30 | Customer – requirement to provide corrected information
121822650 | 1164 | Conduct: Initial Review (IR) | 2021-09-16 | Engineering – requiring more detailed review
121822650 | 1164 | Conduct: Supplemental Review (SR) | 2021-12-03 | Engineering – requiring more detailed review
121822650 | 1164 | Conduct: Supplemental Review (SR) | 2021-12-10 | Engineering – requiring more detailed review
121822650 | 1164 | Conduct: Supplemental Review (SR) | 2021-11-18 | Customer – requirement to provide corrected information
121822650 | 1164 | Conduct: Supplemental Review (SR) | 2021-11-30 | Customer – requirement to provide corrected information
121822650 | 1164 | Conduct: Initial Review (IR) | 2021-09-16 | Engineering – requiring more detailed review
121822650 | 1164 | Conduct: Supplemental Review (SR) | 2021-12-03 | Engineering – requiring more detailed review
121822650 | 1164 | Conduct: Supplemental Review (SR) | 2021-12-10 | Engineering – requiring more detailed review
121848713 | 1165 | Conduct: Initial Review (IR) | 2021-09-23 | Engineering – requiring more detailed review
121848713 | 1165 | Conduct: Initial Review (IR) | 2021-09-23 | Engineering – requiring more detailed review
121848713 | 1165 | Conduct: Initial Review (IR) | 2021-09-23 | Engineering – requiring more detailed review
121845210 | 1166 | Conduct: Initial Review (IR) | 2021-09-23 | Engineering – requiring more detailed review
121845210 | 1166 | Conduct: Initial Review (IR) | 2021-09-30 | Engineering – requiring more detailed review
121845210 | 1166 | Conduct: Initial Review (IR) | 2021-10-07 | Engineering – requiring more detailed review
121845210 | 1166 | Conduct: Initial Review (IR) | 2021-10-14 | Engineering – requiring more detailed review
121845210 | 1166 | Conduct: Initial Review (IR) | 2021-09-23 | Engineering – requiring more detailed review
121845210 | 1166 | Conduct: Initial Review (IR) | 2021-09-30 | Engineering – requiring more detailed review
121845210 | 1166 | Conduct: Initial Review (IR) | 2021-10-07 | Engineering – requiring more detailed review
121845210 | 1166 | Conduct: Initial Review (IR) | 2021-10-14 | Engineering – requiring more detailed review
121845210 | 1166 | Conduct: Initial Review (IR) | 2021-09-23 | Engineering – requiring more detailed review
121845210 | 1166 | Conduct: Initial Review (IR) | 2021-09-30 | Engineering – requiring more detailed review
121845210 | 1166 | Conduct: Initial Review (IR) | 2021-10-07 | Engineering – requiring more detailed review
121845210 | 1166 | Conduct: Initial Review (IR) | 2021-10-14 | Engineering – requiring more detailed review
121402560 | 1167 | Conduct: Initial Review (IR) | 2021-09-28 | Engineering – requiring more detailed review
121402560 | 1167 | Conduct: Initial Review (IR) | 2021-10-12 | Engineering – requiring more detailed review
121402560 | 1167 | Conduct: Initial Review (IR) | 2021-09-28 | Engineering – requiring more detailed review
121402560 | 1167 | Conduct: Initial Review (IR) | 2021-10-12 | Engineering – requiring more detailed review
121402560 | 1167 | Conduct: Initial Review (IR) | 2021-09-28 | Engineering – requiring more detailed review
121402560 | 1167 | Conduct: Initial Review (IR) | 2021-10-12 | Engineering – requiring more detailed review
121426881 | 1168 | Conduct: Initial Review (IR) | 2021-09-30 | Engineering – requiring more detailed review
121426881 | 1168 | Conduct: Initial Review (IR) | 2021-09-30 | Engineering – requiring more detailed review
121426881 | 1168 | Conduct: Initial Review (IR) | 2021-09-30 | Engineering – requiring more detailed review
121848826 | 1169 | Conduct: Initial Review (IR) | 2021-09-24 | Engineering – requiring more detailed review
121848826 | 1169 | Conduct: Initial Review (IR) | 2021-10-01 | Engineering – requiring more detailed review
121848826 | 1169 | Conduct: Initial Review (IR) | 2021-10-08 | Engineering – requiring more detailed review
121848826 | 1169 | Conduct: Initial Review (IR) | 2021-09-24 | Engineering – requiring more detailed review
121848826 | 1169 | Conduct: Initial Review (IR) | 2021-10-01 | Engineering – requiring more detailed review
121848826 | 1169 | Conduct: Initial Review (IR) | 2021-10-08 | Engineering – requiring more detailed review
121848826 | 1169 | Conduct: Initial Review (IR) | 2021-09-24 | Engineering – requiring more detailed review
121848826 | 1169 | Conduct: Initial Review (IR) | 2021-10-01 | Engineering – requiring more detailed review
121848826 | 1169 | Conduct: Initial Review (IR) | 2021-10-08 | Engineering – requiring more detailed review
121786333 | 1170 | Conduct: Initial Review (IR) | 2021-09-27 | Engineering – requiring more detailed review
121786333 | 1170 | Conduct: Initial Review (IR) | 2021-10-04 | Engineering – requiring more detailed review
121786333 | 1170 | Conduct: Initial Review (IR) | 2021-09-27 | Engineering – requiring more detailed review
121786333 | 1170 | Conduct: Initial Review (IR) | 2021-10-04 | Engineering – requiring more detailed review
121786333 | 1170 | Conduct: Initial Review (IR) | 2021-09-27 | Engineering – requiring more detailed review
121786333 | 1170 | Conduct: Initial Review (IR) | 2021-10-04 | Engineering – requiring more detailed review
121795513 | 1171 | Conduct: Supplemental Review (SR) | 2021-10-06 | Engineering – requiring more detailed review
121911825 | 1172 | Conduct: Initial Review (IR) | 2021-10-06 | Engineering – requiring more detailed review
121911825 | 1172 | Conduct: Initial Review (IR) | 2021-10-06 | Engineering – requiring more detailed review
121911825 | 1172 | Conduct: Initial Review (IR) | 2021-10-06 | Engineering – requiring more detailed review
121841534 | 1173 | Conduct: Initial Review (IR) | 2021-09-24 | Engineering – requiring more detailed review
121841534 | 1173 | Conduct: Initial Review (IR) | 2021-09-24 | Engineering – requiring more detailed review
121841534 | 1173 | Conduct: Initial Review (IR) | 2021-09-24 | Engineering – requiring more detailed review
121843079 | 1174 | Conduct: Initial Review (IR) | 2021-10-04 | Engineering – requiring more detailed review
121843079 | 1174 | Conduct: Initial Review (IR) | 2021-10-11 | Engineering – requiring more detailed review
121843079 | 1174 | Conduct: Initial Review (IR) | 2021-10-04 | Engineering – requiring more detailed review
121843079 | 1174 | Conduct: Initial Review (IR) | 2021-10-11 | Engineering – requiring more detailed review
121843079 | 1174 | Conduct: Initial Review (IR) | 2021-10-04 | Engineering – requiring more detailed review
121843079 | 1174 | Conduct: Initial Review (IR) | 2021-10-11 | Engineering – requiring more detailed review
121428277 | 1175 | Conduct: Supplemental Review (SR) | 2021-10-05 | Engineering – requiring more detailed review
121428277 | 1175 | Conduct: Supplemental Review (SR) | 2021-10-05 | Engineering – requiring more detailed review
121428277 | 1175 | Conduct: SIS | 2022-02-09 | Engineering – requiring more detailed review
121428277 | 1175 | Conduct: SIS | 2022-02-09 | Engineering – requiring more detailed review
121428277 | 1175 | Conduct: Supplemental Review (SR) | 2021-10-05 | Engineering – requiring more detailed review
120823543 | 1176 | Conduct: Supplemental Review (SR) | 2021-10-05 | Engineering – requiring more detailed review
120823543 | 1176 | Conduct: Supplemental Review (SR) | 2021-10-13 | Engineering – requiring more detailed review
120823543 | 1176 | Conduct: Supplemental Review (SR) | 2021-10-05 | Engineering – requiring more detailed review
120823543 | 1176 | Conduct: Supplemental Review (SR) | 2021-10-13 | Engineering – requiring more detailed review
120823543 | 1176 | Conduct: SIS | 2022-04-14 | Engineering – requiring more detailed review
120823543 | 1176 | Conduct: SIS | 2022-04-21 | Engineering – requiring more detailed review
120823543 | 1176 | Conduct: Supplemental Review (SR) | 2021-10-05 | Engineering – requiring more detailed review
120823543 | 1176 | Conduct: Supplemental Review (SR) | 2021-10-13 | Engineering – requiring more detailed review
120842473 | 1177 | Conduct: Supplemental Review (SR) | 2021-10-05 | Engineering – requiring more detailed review
120842473 | 1177 | Conduct: Supplemental Review (SR) | 2021-10-13 | Engineering – requiring more detailed review
120842473 | 1177 | Conduct: Supplemental Review (SR) | 2021-10-05 | Engineering – requiring more detailed review
120842473 | 1177 | Conduct: Supplemental Review (SR) | 2021-10-13 | Engineering – requiring more detailed review
120842473 | 1177 | Conduct: Supplemental Review (SR) | 2021-10-05 | Engineering – requiring more detailed review
120842473 | 1177 | Conduct: Supplemental Review (SR) | 2021-10-13 | Engineering – requiring more detailed review
120897470 | 1178 | Conduct: Screens Q and R | 2021-10-01 | Engineering – requiring more detailed review
120897470 | 1178 | Conduct: Screens Q and R | 2021-10-01 | Engineering – requiring more detailed review
120897470 | 1178 | Conduct: SIS | 2021-11-12 | Project Management – requiring more detailed review
120897470 | 1178 | Conduct: SIS | 2021-11-30 | Project Management – requiring more detailed review
120897470 | 1178 | Conduct: Screens Q and R | 2021-10-01 | Engineering – requiring more detailed review
120897470 | 1178 | Conduct: SIS | 2021-11-12 | Project Management – requiring more detailed review
120897470 | 1178 | Conduct: SIS | 2021-11-30 | Project Management – requiring more detailed review
121762277 | 1179 | Conduct: Initial Review (IR) | 2021-10-04 | Engineering – requiring more detailed review
121762277 | 1179 | Conduct: Initial Review (IR) | 2021-10-04 | Engineering – requiring more detailed review
121762277 | 1179 | Conduct: Initial Review (IR) | 2021-10-04 | Engineering – requiring more detailed review
121880104 | 1180 | Conduct: Supplemental Review (SR) | 2021-10-11 | Engineering – requiring more detailed review
121880104 | 1180 | Conduct: Supplemental Review (SR) | 2021-10-11 | Engineering – requiring more detailed review
121880104 | 1180 | Conduct: SIS | 2022-02-23 | Engineering – requiring more detailed review
121880104 | 1180 | Conduct: Supplemental Review (SR) | 2021-10-11 | Engineering – requiring more detailed review
121435809 | 1181 | Conduct: Initial Review (IR) | 2021-10-12 | Engineering – requiring more detailed review
121435809 | 1181 | Conduct: Initial Review (IR) | 2021-10-12 | Engineering – requiring more detailed review
121435809 | 1181 | Conduct: Initial Review (IR) | 2021-10-12 | Engineering – requiring more detailed review
121971360 | 1182 | Conduct: Initial Review (IR) | 2021-10-08 | Engineering – requiring more detailed review
121971360 | 1182 | Conduct: Initial Review (IR) | 2021-10-15 | Engineering – requiring more detailed review
121971360 | 1182 | Conduct: Initial Review (IR) | 2021-10-22 | Project Management - addressing project volume surge
121887284 | 1183 | Conduct: Supplemental Review (SR) | 2021-10-15 | Engineering – requiring more detailed review
121887284 | 1183 | Conduct: Supplemental Review (SR) | 2021-10-15 | Engineering – requiring more detailed review
121887284 | 1183 | Conduct: SIS | 2022-03-09 | Engineering – requiring more detailed review
121887284 | 1183 | Conduct: Supplemental Review (SR) | 2021-10-15 | Engineering – requiring more detailed review
121880753 | 1184 | Conduct: Supplemental Review (SR) | 2021-10-15 | Engineering – requiring more detailed review
121880753 | 1184 | Conduct: Supplemental Review (SR) | 2021-10-15 | Engineering – requiring more detailed review
121880753 | 1184 | Conduct: Supplemental Review (SR) | 2021-10-15 | Engineering – requiring more detailed review
121863035 | 1185 | Conduct: Initial Review (IR) | 2021-11-01 | Engineering – requiring more detailed review
121863035 | 1185 | Conduct: Initial Review (IR) | 2021-11-01 | Engineering – requiring more detailed review
121863035 | 1185 | Conduct: Initial Review (IR) | 2021-11-01 | Engineering – requiring more detailed review
121851470 | 1186 | Conduct: Initial Review (IR) | 2021-10-25 | Engineering – requiring more detailed review
121851470 | 1186 | Conduct: Initial Review (IR) | 2021-10-25 | Engineering – requiring more detailed review
121851470 | 1186 | Conduct: Initial Review (IR) | 2021-11-01 | Engineering – requiring more detailed review
121851470 | 1186 | Conduct: Initial Review (IR) | 2021-11-08 | Engineering – requiring more detailed review
121851470 | 1186 | Conduct: Initial Review (IR) | 2021-11-15 | Engineering – requiring more detailed review
121851470 | 1186 | Conduct: Initial Review (IR) | 2021-10-25 | Engineering – requiring more detailed review
121851470 | 1186 | Conduct: Initial Review (IR) | 2021-11-01 | Engineering – requiring more detailed review
121851470 | 1186 | Conduct: Initial Review (IR) | 2021-11-08 | Engineering – requiring more detailed review
121851470 | 1186 | Conduct: Initial Review (IR) | 2021-11-15 | Engineering – requiring more detailed review
121974926 | 1187 | Conduct: Initial Review (IR) | 2021-10-28 | Engineering – requiring more detailed review
121974926 | 1187 | Conduct: Initial Review (IR) | 2021-10-28 | Engineering – requiring more detailed review
121974926 | 1187 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – requiring more detailed review
121974926 | 1187 | Conduct: Initial Review (IR) | 2021-10-28 | Engineering – requiring more detailed review
121974926 | 1187 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – requiring more detailed review
121961252 | 1188 | Conduct: Initial Review (IR) | 2021-11-11 | Engineering – requiring more detailed review
121961252 | 1188 | Conduct: Initial Review (IR) | 2021-11-11 | Engineering – requiring more detailed review
121961252 | 1188 | Conduct: Initial Review (IR) | 2021-11-11 | Engineering – requiring more detailed review
122014354 | 1189 | Conduct: Initial Review (IR) | 2021-10-28 | Engineering – requiring more detailed review
122014354 | 1189 | Conduct: Initial Review (IR) | 2021-10-28 | Engineering – requiring more detailed review
122014354 | 1189 | Conduct: Initial Review (IR) | 2021-11-09 | Engineering – requiring more detailed review
122014354 | 1189 | Conduct: Initial Review (IR) | 2021-10-28 | Engineering – requiring more detailed review
122014354 | 1189 | Conduct: Initial Review (IR) | 2021-11-09 | Engineering – requiring more detailed review
121920657 | 1190 | Conduct: Initial Review (IR) | 2021-10-21 | Engineering – requiring more detailed review
122060253 | 1191 | Conduct: Initial Review (IR) | 2021-10-22 | Engineering – requiring more detailed review
122060253 | 1191 | Conduct: Initial Review (IR) | 2021-10-22 | Engineering – requiring more detailed review
122060253 | 1191 | Conduct: Initial Review (IR) | 2021-10-29 | Engineering – requiring more detailed review
122011894 | 1192 | Conduct: Initial Review (IR) | 2021-10-22 | Engineering – requiring more detailed review
122008395 | 1193 | Conduct: Initial Review (IR) | 2021-10-22 | Engineering – requiring more detailed review
121921312 | 1194 | Conduct: Initial Review (IR) | 2021-10-22 | Engineering – requiring more detailed review
120718813 | 1195 | Conduct: Initial Review (IR) | 2021-10-11 | Engineering – requiring more detailed review
121982767 | 1196 | Conduct: Initial Review (IR) | 2021-10-18 | Engineering – requiring more detailed review
121982767 | 1196 | Conduct: Initial Review (IR) | 2021-10-25 | Project Management - addressing project volume surge
121972858 | 1197 | Conduct: Supplemental Review (SR) | 2021-10-26 | Engineering – requiring more detailed review
121972858 | 1197 | Conduct: Supplemental Review (SR) | 2021-10-26 | Engineering – requiring more detailed review
121972858 | 1197 | Conduct: Supplemental Review (SR) | 2021-11-02 | Engineering – requiring more detailed review
121972858 | 1197 | Conduct: Supplemental Review (SR) | 2021-11-09 | Engineering – requiring more detailed review
121972858 | 1197 | Conduct: Supplemental Review (SR) | 2021-11-24 | Engineering – requiring more detailed review
121972858 | 1197 | Conduct: SIS | 2022-04-06 | Engineering – requiring more detailed review
121972858 | 1197 | Conduct: Supplemental Review (SR) | 2021-10-26 | Engineering – requiring more detailed review
121972858 | 1197 | Conduct: Supplemental Review (SR) | 2021-11-02 | Engineering – requiring more detailed review
121972858 | 1197 | Conduct: Supplemental Review (SR) | 2021-11-09 | Engineering – requiring more detailed review
121972858 | 1197 | Conduct: Supplemental Review (SR) | 2021-11-24 | Engineering – requiring more detailed review
122012026 | 1198 | Conduct: Initial Review (IR) | 2021-10-21 | Engineering – requiring more detailed review
121693828 | 1199 | Conduct: Initial Review (IR) | 2021-10-22 | Engineering – requiring more detailed review
121693828 | 1199 | Conduct: Initial Review (IR) | 2021-11-15 | Engineering – requiring more detailed review
121693828 | 1199 | Conduct: Initial Review (IR) | 2021-10-22 | Engineering – requiring more detailed review
121693828 | 1199 | Conduct: Initial Review (IR) | 2021-11-15 | Engineering – requiring more detailed review
121693828 | 1199 | Conduct: Initial Review (IR) | 2021-12-01 | Project Management – requiring more detailed review
121693828 | 1199 | Conduct: Initial Review (IR) | 2021-10-22 | Engineering – requiring more detailed review
121693828 | 1199 | Conduct: Initial Review (IR) | 2021-11-15 | Engineering – requiring more detailed review
121693828 | 1199 | Conduct: Initial Review (IR) | 2021-12-01 | Project Management – requiring more detailed review
122052566 | 1200 | Conduct: Initial Review (IR) | 2021-10-22 | Engineering – requiring more detailed review
120858418 | 1201 | Conduct: Initial Review (IR) | 2021-10-25 | Engineering – requiring more detailed review
122069538 | 1202 | Conduct: Initial Review (IR) | 2021-10-25 | Engineering – requiring more detailed review
121989866 | 1203 | Conduct: Initial Review (IR) | 2021-11-01 | Engineering – requiring more detailed review
121989866 | 1203 | Conduct: Initial Review (IR) | 2021-11-01 | Engineering – requiring more detailed review
121989866 | 1203 | Conduct: Initial Review (IR) | 2021-11-01 | Engineering – requiring more detailed review
121763000 | 1204 | Conduct: Initial Review (IR) | 2021-10-27 | Engineering – requiring more detailed review
121763000 | 1204 | Conduct: Initial Review (IR) | 2021-10-27 | Engineering – requiring more detailed review
121763000 | 1204 | Conduct: Initial Review (IR) | 2021-11-03 | Engineering – requiring more detailed review
121763000 | 1204 | Conduct: Initial Review (IR) | 2021-10-27 | Engineering – requiring more detailed review
121763000 | 1204 | Conduct: Initial Review (IR) | 2021-11-03 | Engineering – requiring more detailed review
121884706 | 1205 | Conduct: Initial Review (IR) | 2021-10-27 | Engineering – requiring more detailed review
121884706 | 1205 | Conduct: Initial Review (IR) | 2021-10-27 | Engineering – requiring more detailed review
121884706 | 1205 | Conduct: Initial Review (IR) | 2021-10-27 | Engineering – requiring more detailed review
121882510 | 1206 | Conduct: Initial Review (IR) | 2021-11-11 | Engineering – requiring more detailed review
121882510 | 1206 | Conduct: Initial Review (IR) | 2021-11-11 | Engineering – requiring more detailed review
121882510 | 1206 | Conduct: Initial Review (IR) | 2021-11-12 | Project Management - addressing project volume surge
121882510 | 1206 | Conduct: Initial Review (IR) | 2021-11-11 | Engineering – requiring more detailed review
121882510 | 1206 | Conduct: Initial Review (IR) | 2021-11-12 | Project Management - addressing project volume surge
121190694 | 1207 | Conduct: Initial Review (IR) | 2021-07-29 | Project Management – addressing a human error
121190694 | 1207 | Conduct: Initial Review (IR) | 2021-07-29 | Project Management – addressing a human error
121190694 | 1207 | Conduct: Initial Review (IR) | 2021-07-29 | Project Management – addressing a human error
120772377 | 1208 | Conduct: Initial Review (IR) | 2021-08-02 | Project Management – addressing a human error
120772377 | 1208 | Conduct: Initial Review (IR) | 2021-08-02 | Project Management – addressing a human error
120772377 | 1208 | Conduct: Initial Review (IR) | 2021-08-02 | Project Management – addressing a human error
121642659 | 1209 | Conduct: Initial Review (IR) | 2021-08-26 | Project Management – addressing a human error
121642659 | 1209 | Conduct: Initial Review (IR) | 2021-08-26 | Project Management – addressing a human error
121642659 | 1209 | Conduct: Initial Review (IR) | 2021-08-26 | Project Management – addressing a human error
121690217 | 1210 | Conduct: Initial Review (IR) | 2021-08-20 | Project Management – addressing a human error
121690217 | 1210 | Conduct: Initial Review (IR) | 2021-08-20 | Project Management – addressing a human error
121690217 | 1210 | Conduct: Initial Review (IR) | 2021-08-20 | Project Management – addressing a human error
121544191 | 1211 | Conduct: Initial Review (IR) | 2021-08-27 | Project Management – addressing a human error
121397682 | 1212 | Conduct: Initial Review (IR) | 2021-08-30 | Project Management – addressing a human error
121373517 | 1213 | Conduct: Supplemental Review (SR) | 2021-09-01 | Project Management – addressing a human error
121373517 | 1213 | Conduct: Supplemental Review (SR) | 2021-09-01 | Project Management – addressing a human error
121373517 | 1213 | Conduct: Supplemental Review (SR) | 2021-09-01 | Project Management – addressing a human error
122157522 | 1214 | Conduct: Screens Q and R | 2021-11-17 | Project Management – addressing a human error
122157522 | 1214 | Conduct: Screens Q and R | 2021-11-17 | Project Management – addressing a human error
122157522 | 1214 | Conduct: Screens Q and R | 2021-11-17 | Project Management – addressing a human error
122048269 | 1215 | Conduct: Initial Review (IR) | 2021-10-21 | Project Management - addressing project volume surge
122067274 | 1216 | Conduct: Initial Review (IR) | 2021-10-25 | Project Management - addressing project volume surge
122085959 | 1217 | Conduct: Initial Review (IR) | 2021-10-27 | Project Management - addressing project volume surge
114118371 | 1218 | Construction True-up Report Sent | 2021-08-31 | Project Management – requiring more detailed review
114118371 | 1218 | Construction True-up Report Sent | 2021-09-30 | Project Management – requiring more detailed review
112044081 | 1219 | Construction True-up Report Sent | 2021-12-31 | Project Management – requiring more detailed review
112044191 | 1220 | Construction True-up Report Sent | 2021-12-31 | Project Management – requiring more detailed review
115412804 | 1221 | Construction True-up Report Sent | 2021-08-31 | Project Management – requiring more detailed review
115412804 | 1221 | Construction True-up Report Sent | 2021-09-30 | Project Management – requiring more detailed review
115412804 | 1221 | Construction True-up Report Sent | 2021-10-29 | Project Management – requiring more detailed review
114230223 | 1222 | Construction True-up Report Sent | 2021-08-23 | Project Management – requiring more detailed review
114230223 | 1222 | Construction True-up Report Sent | 2021-09-30 | Project Management – requiring more detailed review
114230223 | 1222 | Construction True-up Report Sent | 2021-11-04 | Project Management – requiring more detailed review
114366753 | 1223 | Construction True-up Report Sent | 2021-09-10 | Project Management – requiring more detailed review
114366753 | 1223 | Construction True-up Report Sent | 2021-10-01 | Project Management – requiring more detailed review
114366753 | 1223 | Construction True-up Report Sent | 2021-11-01 | Project Management – requiring more detailed review
112990984 | 1224 | Construction True-up Report Sent | 2021-09-30 | Project Management – requiring more detailed review
112990984 | 1224 | Construction True-up Report Sent | 2021-10-29 | Project Management – requiring more detailed review
114971313 | 1225 | Construction True-up Report Sent | 2021-10-07 | Project Management – requiring more detailed review
114971313 | 1225 | Construction True-up Report Sent | 2021-11-04 | Project Management – requiring more detailed review
114212256 | 1226 | Construction True-up Report Sent | 2021-09-30 | Project Management – requiring more detailed review
120812930 | 1227 | Conduct: SIS | 2021-10-13 | Project Management – requiring more detailed review
120812930 | 1227 | Conduct: SIS | 2021-11-03 | Project Management – requiring more detailed review
120812930 | 1227 | Conduct: SIS | 2021-11-29 | Engineering – requiring more detailed review
120812930 | 1227 | Conduct: SIS | 2021-10-13 | Project Management – requiring more detailed review
120812930 | 1227 | Conduct: SIS | 2021-11-03 | Project Management – requiring more detailed review
120812930 | 1227 | Conduct: SIS | 2021-11-29 | Engineering – requiring more detailed review
120812930 | 1227 | Conduct: SIS | 2021-10-13 | Project Management – requiring more detailed review
120812930 | 1227 | Conduct: SIS | 2021-11-03 | Project Management – requiring more detailed review
120019706 | 1228 | Conduct: Initial Review (IR) | 2021-08-25 | Project Management – requiring more detailed review
120019706 | 1228 | Conduct: Initial Review (IR) | 2021-08-30 | Project Management – requiring more detailed review
121638301 | 1229 | Conduct: Initial Review (IR) | 2021-08-20 | Project Management – requiring more detailed review
121363258 | 1230 | Conduct: Initial Review (IR) | 2021-09-08 | Project Management – requiring more detailed review
120827507 | 1231 | Conduct: Initial Review (IR) | 2021-09-03 | Project Management – requiring more detailed review
121779332 | 1232 | Conduct: Initial Review (IR) | 2021-09-03 | Project Management – requiring more detailed review
121764199 | 1233 | Conduct: Initial Review (IR) | 2021-09-16 | Project Management – requiring more detailed review
121809296 | 1234 | Conduct: Initial Review (IR) | 2021-09-28 | Project Management – requiring more detailed review
121967154 | 1235 | Conduct: Initial Review (IR) | 2021-10-26 | Project Management – requiring more detailed review
121967154 | 1235 | Conduct: Supplemental Review (SR) | 2021-11-29 | Engineering – addressing project volume surge
121967154 | 1235 | Conduct: Initial Review (IR) | 2021-10-26 | Project Management – requiring more detailed review
121967154 | 1235 | Conduct: Supplemental Review (SR) | 2021-11-29 | Engineering – addressing project volume surge
121967154 | 1235 | Conduct: Initial Review (IR) | 2021-10-26 | Project Management – requiring more detailed review
122031190 | 1236 | Conduct: Initial Review (IR) | 2021-10-12 | Project Management – requiring more detailed review
121958032 | 1237 | Conduct: Initial Review (IR) | 2021-10-18 | Project Management – requiring more detailed review
121958032 | 1237 | Conduct: Initial Review (IR) | 2021-10-18 | Project Management – requiring more detailed review
121958032 | 1237 | Conduct: Initial Review (IR) | 2021-10-18 | Project Management – requiring more detailed review
121394998 | 1238 | Conduct: Initial Review (IR) | 2021-10-28 | Project Management – requiring more detailed review
120647383 | 1239 | Conduct: SIS | 2021-11-29 | Cus – requirement to provide a response to deficiency notice
120647383 | 1239 | Conduct: SIS | 2021-11-29 | Cus – requirement to provide a response to deficiency notice
120728241 | 1240 | Conduct: Supplemental Review (SR) | 2022-01-05 | Engineering – requiring more detailed review
120728241 | 1240 | Conduct: Supplemental Review (SR) | 2022-01-27 | Engineering – requiring more detailed review
120728241 | 1240 | Conduct: Supplemental Review (SR) | 2022-01-05 | Engineering – requiring more detailed review
120728241 | 1240 | Conduct: Supplemental Review (SR) | 2022-01-27 | Engineering – requiring more detailed review
120728241 | 1240 | Conduct: Supplemental Review (SR) | 2022-02-03 | Engineering – requiring more detailed review
120755133 | 1241 | Conduct: Initial Review (IR) | 2021-12-30 | Engineering – requiring more detailed review
120755133 | 1241 | Conduct: Initial Review (IR) | 2022-01-31 | Project Management – requiring more detailed review
120755133 | 1241 | Conduct: Initial Review (IR) | 2022-02-28 | Customer – requirement to provide corrected information
120755133 | 1241 | Conduct: Initial Review (IR) | 2021-12-30 | Engineering – requiring more detailed review
120755133 | 1241 | Conduct: Initial Review (IR) | 2022-02-18 | Engineering – requiring more detailed review
120755133 | 1241 | Conduct: Initial Review (IR) | 2022-01-31 | Project Management – requiring more detailed review
120771059 | 1242 | Conduct: Initial Review (IR) | 2021-11-19 | Cus – requirement to provide a response to deficiency notice
120771059 | 1242 | Conduct: Initial Review (IR) | 2021-11-12 | Engineering – requiring more detailed review
120771059 | 1242 | Conduct: Initial Review (IR) | 2021-11-26 | Engineering – requiring more detailed review
120771059 | 1242 | Conduct: Initial Review (IR) | 2021-11-19 | Cus – requirement to provide a response to deficiency notice
120771059 | 1242 | Conduct: Initial Review (IR) | 2021-11-12 | Engineering – requiring more detailed review
120771059 | 1242 | Conduct: Initial Review (IR) | 2021-11-26 | Engineering – requiring more detailed review
120897974 | 1243 | Conduct: Initial Review (IR) | 2021-11-18 | Customer – requirement to provide corrected information
120897974 | 1243 | Conduct: Initial Review (IR) | 2021-10-28 | Engineering – requiring more detailed review
120897974 | 1243 | Conduct: Initial Review (IR) | 2021-12-06 | Engineering – requiring more detailed review
120897974 | 1243 | Conduct: Initial Review (IR) | 2021-12-10 | Engineering – requiring more detailed review
120897974 | 1243 | Conduct: Initial Review (IR) | 2021-11-18 | Customer – requirement to provide corrected information
120897974 | 1243 | Conduct: Initial Review (IR) | 2021-10-28 | Engineering – requiring more detailed review
120897974 | 1243 | Conduct: Initial Review (IR) | 2021-12-06 | Engineering – requiring more detailed review
120897974 | 1243 | Conduct: Initial Review (IR) | 2021-12-10 | Engineering – requiring more detailed review
121191864 | 1244 | Conduct: SIS | 2021-12-15 | Engineering – addressing project volume surge
121191864 | 1244 | Conduct: SIS | 2021-12-29 | Engineering – addressing project volume surge
121191864 | 1244 | Conduct: SIS | 2021-12-15 | Engineering – addressing project volume surge
121191864 | 1244 | Conduct: SIS | 2021-12-29 | Engineering – addressing project volume surge
121323768 | 1245 | Conduct: Initial Review (IR) | 2022-01-03 | Cus – requirement to provide a response to deficiency notice
121323768 | 1245 | Conduct: Initial Review (IR) | 2022-01-18 | Cus – requirement to provide a response to deficiency notice
121323768 | 1245 | Conduct: Initial Review (IR) | 2022-02-08 | Cus – requirement to provide a response to deficiency notice
121323768 | 1245 | Conduct: Initial Review (IR) | 2022-01-03 | Cus – requirement to provide a response to deficiency notice
121323768 | 1245 | Conduct: Initial Review (IR) | 2022-01-18 | Cus – requirement to provide a response to deficiency notice
121323768 | 1245 | Conduct: Initial Review (IR) | 2022-02-08 | Cus – requirement to provide a response to deficiency notice
121323768 | 1245 | Conduct: Initial Review (IR) | 2022-02-23 | Engineering – requiring more detailed review
121323768 | 1245 | Conduct: Initial Review (IR) | 2022-03-09 | Engineering – requiring more detailed review
121323768 | 1245 | Conduct: Initial Review (IR) | 2022-03-23 | Engineering – requiring more detailed review
121323768 | 1245 | Conduct: Initial Review (IR) | 2022-04-12 | Engineering – requiring more detailed review
121325067 | 1246 | Conduct: Initial Review (IR) | 2021-12-20 | Cus – requirement to provide a response to deficiency notice
121325067 | 1246 | Conduct: Initial Review (IR) | 2022-01-17 | Customer – requirement to provide corrected information
121325067 | 1246 | Conduct: Initial Review (IR) | 2021-11-29 | Engineering – requiring more detailed review
121325067 | 1246 | Conduct: Initial Review (IR) | 2021-12-20 | Cus – requirement to provide a response to deficiency notice
121325067 | 1246 | Conduct: Initial Review (IR) | 2022-01-17 | Customer – requirement to provide corrected information
121325067 | 1246 | Conduct: Initial Review (IR) | 2021-11-29 | Engineering – requiring more detailed review
121325832 | 1247 | Conduct: SIS | 2021-11-03 | Engineering – addressing project volume surge
121325832 | 1247 | Conduct: SIS | 2021-11-03 | Engineering – addressing project volume surge
121346000 | 1248 | Conduct: SIS | 2021-11-11 | Engineering – requiring more detailed review
121346000 | 1248 | Conduct: SIS | 2021-11-18 | Engineering – requiring more detailed review
121346000 | 1248 | Conduct: SIS | 2021-11-30 | Engineering – requiring more detailed review
121346000 | 1248 | Conduct: SIS | 2021-12-03 | Engineering – requiring more detailed review
121346000 | 1248 | Conduct: SIS | 2021-12-10 | Engineering – requiring more detailed review
121346000 | 1248 | Conduct: SIS | 2021-12-17 | Engineering – requiring more detailed review
121346000 | 1248 | Conduct: SIS | 2021-11-11 | Engineering – requiring more detailed review
121346000 | 1248 | Conduct: SIS | 2021-11-18 | Engineering – requiring more detailed review
121346000 | 1248 | Conduct: SIS | 2021-11-30 | Engineering – requiring more detailed review
121346000 | 1248 | Conduct: SIS | 2021-12-03 | Engineering – requiring more detailed review
121346000 | 1248 | Conduct: SIS | 2021-12-10 | Engineering – requiring more detailed review
121346000 | 1248 | Conduct: SIS | 2021-12-17 | Engineering – requiring more detailed review
121368174 | 1249 | Conduct: Initial Review (IR) | 2021-10-27 | Project Management – requiring more detailed review
121368174 | 1249 | Conduct: Initial Review (IR) | 2021-10-27 | Project Management – requiring more detailed review
121389545 | 1250 | Conduct: SIS | 2021-11-09 | Engineering – requiring more detailed review
121389545 | 1250 | Conduct: SIS | 2021-11-24 | Engineering – requiring more detailed review
121389545 | 1250 | Conduct: SIS | 2021-11-09 | Engineering – requiring more detailed review
121389545 | 1250 | Conduct: SIS | 2021-11-24 | Engineering – requiring more detailed review
121454801 | 1251 | Conduct: Supplemental Review (SR) | 2022-01-14 | Engineering – addressing project volume surge
121454801 | 1251 | Conduct: Supplemental Review (SR) | 2022-01-31 | Project Management - addressing project volume surge
121454801 | 1251 | Conduct: Supplemental Review (SR) | 2022-01-14 | Engineering – addressing project volume surge
121454801 | 1251 | Conduct: Supplemental Review (SR) | 2022-03-01 | Engineering – addressing project volume surge
121454801 | 1251 | Conduct: Supplemental Review (SR) | 2022-01-31 | Project Management - addressing project volume surge
121454801 | 1251 | Conduct: Supplemental Review (SR) | 2022-02-14 | Project Management - addressing project volume surge
121454804 | 1252 | Conduct: Supplemental Review (SR) | 2022-02-03 | Engineering – addressing project volume surge
121454804 | 1252 | Conduct: Initial Review (IR) | 2021-12-23 | Engineering – requiring more detailed review
121454804 | 1252 | Conduct: Initial Review (IR) | 2021-12-09 | Project Management – requiring more detailed review
121454804 | 1252 | Conduct: Supplemental Review (SR) | 2022-02-03 | Engineering – addressing project volume surge
121454804 | 1252 | Conduct: Supplemental Review (SR) | 2022-02-10 | Engineering – addressing project volume surge
121454804 | 1252 | Conduct: Initial Review (IR) | 2021-12-23 | Engineering – requiring more detailed review
121454804 | 1252 | Conduct: Initial Review (IR) | 2021-12-09 | Project Management – requiring more detailed review
121516212 | 1253 | Determine Material Modifications | 2021-12-06 | Engineering – addressing project volume surge
121516212 | 1253 | Determine Material Modifications | 2021-12-06 | Engineering – addressing project volume surge
121541983 | 1254 | Conduct: SIS | 2021-11-22 | Engineering – addressing project volume surge
121541983 | 1254 | Conduct: SIS | 2021-11-22 | Engineering – addressing project volume surge
121547611 | 1255 | Conduct: Initial Review (IR) | 2021-11-10 | Engineering – requiring more detailed review
121547611 | 1255 | Conduct: Initial Review (IR) | 2021-11-17 | Engineering – requiring more detailed review
121547611 | 1255 | Conduct: Initial Review (IR) | 2021-11-24 | Engineering – requiring more detailed review
121547611 | 1255 | Conduct: Initial Review (IR) | 2021-12-02 | Engineering – requiring more detailed review
121547611 | 1255 | Conduct: Initial Review (IR) | 2021-12-09 | Engineering – requiring more detailed review
121547611 | 1255 | Conduct: Initial Review (IR) | 2021-12-16 | Engineering – requiring more detailed review
121547611 | 1255 | Conduct: Initial Review (IR) | 2021-12-23 | Engineering – requiring more detailed review
121547611 | 1255 | Conduct: Initial Review (IR) | 2021-12-02 | Engineering – requiring more detailed review
121547611 | 1255 | Conduct: Initial Review (IR) | 2021-11-10 | Engineering – requiring more detailed review
121547611 | 1255 | Conduct: Initial Review (IR) | 2021-11-17 | Engineering – requiring more detailed review
121547611 | 1255 | Conduct: Initial Review (IR) | 2021-11-24 | Engineering – requiring more detailed review
121547611 | 1255 | Conduct: Initial Review (IR) | 2021-12-09 | Engineering – requiring more detailed review
121547611 | 1255 | Conduct: Initial Review (IR) | 2021-12-16 | Engineering – requiring more detailed review
121547611 | 1255 | Conduct: Initial Review (IR) | 2021-12-23 | Engineering – requiring more detailed review
121548990 | 1256 | Conduct: Initial Review (IR) | 2022-01-10 | Engineering – requiring more detailed review
121548990 | 1256 | Conduct: Initial Review (IR) | 2022-01-17 | Engineering – requiring more detailed review
121548990 | 1256 | Conduct: Initial Review (IR) | 2022-01-03 | Project Management – requiring more detailed review
121548990 | 1256 | Conduct: Initial Review (IR) | 2022-01-10 | Engineering – requiring more detailed review
121548990 | 1256 | Conduct: Initial Review (IR) | 2022-01-17 | Engineering – requiring more detailed review
121548990 | 1256 | Conduct: Initial Review (IR) | 2022-01-03 | Project Management – requiring more detailed review
121550219 | 1257 | Conduct: Supplemental Review (SR) | 2021-11-05 | Project Management – requiring more detailed review
121550219 | 1257 | Conduct: Screens Q and R | 2021-12-22 | Project Management – requiring more detailed review
121550219 | 1257 | Conduct: SIS | 2022-03-24 | Engineering – requiring more detailed review
121550219 | 1257 | Conduct: Screens Q and R | 2021-12-22 | Project Management – requiring more detailed review
121550219 | 1257 | Conduct: Supplemental Review (SR) | 2021-11-05 | Project Management – requiring more detailed review
121622681 | 1258 | Conduct: Initial Review (IR) | 2021-12-02 | Engineering – addressing project volume surge
121622681 | 1258 | Conduct: Initial Review (IR) | 2021-12-02 | Engineering – addressing project volume surge
121681799 | 1259 | Conduct: Supplemental Review (SR) | 2021-11-04 | Engineering – requiring more detailed review
121681799 | 1259 | Conduct: Supplemental Review (SR) | 2021-11-04 | Engineering – requiring more detailed review
121743879 | 1260 | Conduct: Initial Review (IR) | 2021-12-09 | Cus – requirement to provide a response to deficiency notice
121743879 | 1260 | Conduct: Initial Review (IR) | 2021-12-23 | Cus – requirement to provide a response to deficiency notice
121743879 | 1260 | Conduct: Initial Review (IR) | 2021-12-16 | Engineering – requiring more detailed review
121743879 | 1260 | Conduct: Initial Review (IR) | 2021-12-09 | Cus – requirement to provide a response to deficiency notice
121743879 | 1260 | Conduct: Initial Review (IR) | 2021-12-23 | Cus – requirement to provide a response to deficiency notice
121743879 | 1260 | Conduct: Initial Review (IR) | 2021-12-16 | Engineering – requiring more detailed review
121754976 | 1261 | Conduct: Initial Review (IR) | 2021-11-19 | Cus – requirement to provide a response to deficiency notice
121754976 | 1261 | Conduct: Initial Review (IR) | 2021-11-19 | Cus – requirement to provide a response to deficiency notice
121757817 | 1262 | Schedule: Scoping Meeting | 2021-10-28 | Project Management – addressing a human error
121757817 | 1262 | Schedule: Scoping Meeting | 2021-10-28 | Project Management – addressing a human error
121770192 | 1263 | Conduct: Initial Review (IR) | 2021-11-10 | Engineering – requiring more detailed review
121770192 | 1263 | Conduct: Initial Review (IR) | 2021-11-24 | Engineering – requiring more detailed review
121770192 | 1263 | Conduct: Initial Review (IR) | 2021-11-10 | Engineering – requiring more detailed review
121770192 | 1263 | Conduct: Initial Review (IR) | 2021-11-24 | Engineering – requiring more detailed review
121798064 | 1264 | Conduct: Supplemental Review (SR) | 2021-11-03 | Engineering – addressing project volume surge
121798064 | 1264 | Conduct: Supplemental Review (SR) | 2021-11-03 | Engineering – addressing project volume surge
121798064 | 1264 | Conduct: SIS | 2022-03-09 | Engineering – requiring more detailed review
121802186 | 1265 | Conduct: SIS | 2022-01-26 | Engineering – requiring more detailed review
121802186 | 1265 | Conduct: SIS | 2022-01-26 | Engineering – requiring more detailed review
121806780 | 1266 | Conduct: Supplemental Review (SR) | 2021-12-08 | Engineering – addressing project volume surge