121806780 | 1266 | Conduct: Supplemental Review (SR) | 2021-12-08 | Engineering – addressing project volume surge
121813359 | 1267 | Conduct: SIS | 2022-01-07 | Engineering – addressing project volume surge
121813359 | 1267 | Conduct: SIS | 2022-01-14 | Engineering – addressing project volume surge
121813359 | 1267 | Conduct: SIS | 2022-01-07 | Engineering – addressing project volume surge
121813359 | 1267 | Conduct: SIS | 2022-01-14 | Engineering – addressing project volume surge
121851471 | 1268 | Conduct: Initial Review (IR) | 2021-12-17 | Cus – requirement to provide a response to deficiency notice
121851471 | 1268 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – addressing project volume surge
121851471 | 1268 | Conduct: Initial Review (IR) | 2022-01-07 | Engineering – requiring more detailed review
121851471 | 1268 | Conduct: Initial Review (IR) | 2021-12-24 | Project Management – requiring more detailed review
121851471 | 1268 | Conduct: Initial Review (IR) | 2021-12-17 | Cus – requirement to provide a response to deficiency notice
121851471 | 1268 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – addressing project volume surge
121851471 | 1268 | Conduct: Initial Review (IR) | 2022-01-07 | Engineering – requiring more detailed review
121851471 | 1268 | Conduct: Initial Review (IR) | 2021-12-24 | Project Management – requiring more detailed review
121906537 | 1269 | Conduct: Initial Review (IR) | 2021-11-08 | Engineering – requiring more detailed review
121906537 | 1269 | Conduct: Initial Review (IR) | 2021-11-15 | Engineering – requiring more detailed review
121906537 | 1269 | Conduct: Initial Review (IR) | 2021-11-22 | Engineering – requiring more detailed review
121906537 | 1269 | Conduct: Initial Review (IR) | 2021-11-29 | Engineering – requiring more detailed review
121906537 | 1269 | Conduct: Initial Review (IR) | 2021-12-06 | Engineering – requiring more detailed review
121906537 | 1269 | Conduct: Initial Review (IR) | 2021-12-13 | Engineering – requiring more detailed review
121906537 | 1269 | Conduct: Initial Review (IR) | 2021-11-08 | Engineering – requiring more detailed review
121906537 | 1269 | Conduct: Initial Review (IR) | 2021-11-15 | Engineering – requiring more detailed review
121906537 | 1269 | Conduct: Initial Review (IR) | 2021-11-22 | Engineering – requiring more detailed review
121906537 | 1269 | Conduct: Initial Review (IR) | 2021-11-29 | Engineering – requiring more detailed review
121906537 | 1269 | Conduct: Initial Review (IR) | 2021-12-06 | Engineering – requiring more detailed review
121906537 | 1269 | Conduct: Initial Review (IR) | 2021-12-13 | Engineering – requiring more detailed review
121912801 | 1270 | Conduct: Initial Review (IR) | 2021-11-19 | Cus – requirement to provide a response to deficiency notice
121912801 | 1270 | Conduct: Initial Review (IR) | 2021-11-29 | Engineering – addressing project volume surge
121912801 | 1270 | Conduct: Initial Review (IR) | 2021-12-03 | Engineering – addressing project volume surge
121912801 | 1270 | Conduct: Initial Review (IR) | 2021-12-10 | Engineering – addressing project volume surge
121912801 | 1270 | Conduct: Initial Review (IR) | 2021-12-15 | Engineering – addressing project volume surge
121912801 | 1270 | Conduct: Initial Review (IR) | 2021-11-19 | Cus – requirement to provide a response to deficiency notice
121912801 | 1270 | Conduct: Initial Review (IR) | 2021-11-29 | Engineering – addressing project volume surge
121912801 | 1270 | Conduct: Initial Review (IR) | 2021-12-03 | Engineering – addressing project volume surge
121912801 | 1270 | Conduct: Initial Review (IR) | 2021-12-10 | Engineering – addressing project volume surge
121912801 | 1270 | Conduct: Initial Review (IR) | 2021-12-15 | Engineering – addressing project volume surge
121928646 | 1271 | Conduct: Supplemental Review (SR) | 2021-12-16 | Engineering – addressing project volume surge
121928646 | 1271 | Conduct: Supplemental Review (SR) | 2021-12-09 | Engineering – requiring more detailed review
121928646 | 1271 | Conduct: Supplemental Review (SR) | 2021-12-16 | Engineering – addressing project volume surge
121928646 | 1271 | Conduct: Supplemental Review (SR) | 2021-12-09 | Engineering – requiring more detailed review
121960026 | 1272 | Conduct: Initial Review (IR) | 2021-11-25 | Engineering – addressing project volume surge
121960026 | 1272 | Conduct: Initial Review (IR) | 2021-11-25 | Engineering – addressing project volume surge
121962644 | 1273 | Conduct: Supplemental Review (SR) | 2021-11-23 | Engineering – requiring more detailed review
121962644 | 1273 | Conduct: Supplemental Review (SR) | 2021-11-23 | Engineering – requiring more detailed review
121967150 | 1274 | Conduct: Screens Q and R | 2021-11-22 | Engineering – requiring more detailed review
121967150 | 1274 | Conduct: Screens Q and R | 2021-11-22 | Engineering – requiring more detailed review
121987918 | 1275 | Conduct: Initial Review (IR) | 2021-11-16 | Cus – requirement to provide a response to deficiency notice
121987918 | 1275 | Conduct: Initial Review (IR) | 2021-11-23 | Engineering – requiring more detailed review
121987918 | 1275 | Conduct: Initial Review (IR) | 2021-11-30 | Engineering – requiring more detailed review
121987918 | 1275 | Conduct: Initial Review (IR) | 2021-11-09 | Project Management - addressing project volume surge
121987918 | 1275 | Conduct: Initial Review (IR) | 2021-12-07 | Project Management – requiring more detailed review
121987918 | 1275 | Conduct: Initial Review (IR) | 2021-11-16 | Cus – requirement to provide a response to deficiency notice
121987918 | 1275 | Conduct: Initial Review (IR) | 2021-11-23 | Engineering – requiring more detailed review
121987918 | 1275 | Conduct: Initial Review (IR) | 2021-11-30 | Engineering – requiring more detailed review
121987918 | 1275 | Conduct: Initial Review (IR) | 2021-11-09 | Project Management - addressing project volume surge
121987918 | 1275 | Conduct: Initial Review (IR) | 2021-12-07 | Project Management – requiring more detailed review
121988538 | 1276 | Conduct: Initial Review (IR) | 2021-12-20 | Engineering – requiring more detailed review
121988538 | 1276 | Conduct: Initial Review (IR) | 2022-01-03 | Engineering – requiring more detailed review
121988538 | 1276 | Conduct: Initial Review (IR) | 2021-12-20 | Engineering – requiring more detailed review
121988538 | 1276 | Conduct: Initial Review (IR) | 2022-01-03 | Engineering – requiring more detailed review
121990859 | 1277 | Conduct: SIS | 2022-01-25 | Engineering – requiring more detailed review
121990859 | 1277 | Conduct: SIS | 2022-02-08 | Engineering – requiring more detailed review
121990859 | 1277 | Conduct: SIS | 2022-01-25 | Engineering – requiring more detailed review
121990859 | 1277 | Conduct: SIS | 2022-02-08 | Engineering – requiring more detailed review
121990859 | 1277 | Conduct: SIS | 2022-03-02 | Engineering – requiring more detailed review
121997476 | 1278 | Conduct: Initial Review (IR) | 2022-02-08 | Customer – requirement to provide corrected information
121997476 | 1278 | Conduct: Initial Review (IR) | 2022-02-08 | Customer – requirement to provide corrected information
121997476 | 1278 | Conduct: Initial Review (IR) | 2022-03-08 | Customer – requirement to provide corrected information
122012800 | 1279 | Conduct: Initial Review (IR) | 2021-11-15 | Engineering – requiring more detailed review
122012800 | 1279 | Conduct: Initial Review (IR) | 2021-11-19 | Project Management – requiring more detailed review
122012800 | 1279 | Conduct: Initial Review (IR) | 2021-11-15 | Engineering – requiring more detailed review
122012800 | 1279 | Conduct: Initial Review (IR) | 2021-11-19 | Project Management – requiring more detailed review
122012802 | 1280 | Conduct: Initial Review (IR) | 2021-11-15 | Engineering – requiring more detailed review
122012802 | 1280 | Conduct: Initial Review (IR) | 2021-11-19 | Project Management – requiring more detailed review
122012802 | 1280 | Conduct: Initial Review (IR) | 2021-11-15 | Engineering – requiring more detailed review
122012802 | 1280 | Conduct: Initial Review (IR) | 2021-11-19 | Project Management – requiring more detailed review
122014821 | 1281 | Conduct: Initial Review (IR) | 2021-11-18 | Project Management - addressing project volume surge
122014821 | 1281 | Conduct: Initial Review (IR) | 2021-11-18 | Project Management - addressing project volume surge
122020637 | 1282 | Conduct: Supplemental Review (SR) | 2022-01-10 | Engineering – addressing project volume surge
122020637 | 1282 | Conduct: Screens Q and R | 2022-02-04 | Project Management – addressing a human error
122020637 | 1282 | Conduct: Supplemental Review (SR) | 2022-01-10 | Engineering – addressing project volume surge
122020637 | 1282 | Conduct: Screens Q and R | 2022-02-04 | Project Management – addressing a human error
122020675 | 1283 | Conduct: Initial Review (IR) | 2021-11-18 | Customer – requirement to provide corrected information
122020675 | 1283 | Conduct: Initial Review (IR) | 2021-10-28 | Engineering – addressing project volume surge
122020675 | 1283 | Conduct: Supplemental Review (SR) | 2022-01-12 | Engineering – addressing project volume surge
122020675 | 1283 | Conduct: Initial Review (IR) | 2021-11-18 | Customer – requirement to provide corrected information
122020675 | 1283 | Conduct: Initial Review (IR) | 2021-10-28 | Engineering – addressing project volume surge
122020675 | 1283 | Conduct: Supplemental Review (SR) | 2022-01-12 | Engineering – addressing project volume surge
122020818 | 1284 | Conduct: Initial Review (IR) | 2021-11-22 | Cus – requirement to provide a response to deficiency notice
122020818 | 1284 | Conduct: Initial Review (IR) | 2021-11-29 | Cus – requirement to provide a response to deficiency notice
122020818 | 1284 | Conduct: Initial Review (IR) | 2021-12-06 | Cus – requirement to provide a response to deficiency notice
122020818 | 1284 | Conduct: Initial Review (IR) | 2021-12-13 | Engineering – addressing project volume surge
122020818 | 1284 | Conduct: Initial Review (IR) | 2021-11-22 | Cus – requirement to provide a response to deficiency notice
122020818 | 1284 | Conduct: Initial Review (IR) | 2021-11-29 | Cus – requirement to provide a response to deficiency notice
122020818 | 1284 | Conduct: Initial Review (IR) | 2021-12-06 | Cus – requirement to provide a response to deficiency notice
122020818 | 1284 | Conduct: Initial Review (IR) | 2021-12-13 | Engineering – addressing project volume surge
122044521 | 1285 | Conduct: Initial Review (IR) | 2021-12-17 | Cus – requirement to provide a response to deficiency notice
122044521 | 1285 | Conduct: Initial Review (IR) | 2022-01-07 | Cus – requirement to provide a response to deficiency notice
122044521 | 1285 | Conduct: Initial Review (IR) | 2022-01-14 | Cus – requirement to provide a response to deficiency notice
122044521 | 1285 | Conduct: Initial Review (IR) | 2021-12-10 | Engineering – requiring more detailed review
122044521 | 1285 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – requiring more detailed review
122044521 | 1285 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – requiring more detailed review
122044521 | 1285 | Conduct: Initial Review (IR) | 2021-12-24 | Project Management – requiring more detailed review
122044521 | 1285 | Conduct: Initial Review (IR) | 2021-12-17 | Cus – requirement to provide a response to deficiency notice
122044521 | 1285 | Conduct: Initial Review (IR) | 2022-01-07 | Cus – requirement to provide a response to deficiency notice
122044521 | 1285 | Conduct: Initial Review (IR) | 2022-01-14 | Cus – requirement to provide a response to deficiency notice
122044521 | 1285 | Conduct: Initial Review (IR) | 2022-02-11 | Cus – requirement to provide a response to deficiency notice
122044521 | 1285 | Conduct: Initial Review (IR) | 2021-12-10 | Engineering – requiring more detailed review
122044521 | 1285 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – requiring more detailed review
122044521 | 1285 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – requiring more detailed review
122044521 | 1285 | Conduct: Initial Review (IR) | 2021-12-24 | Project Management – requiring more detailed review
122058605 | 1286 | Conduct: Initial Review (IR) | 2021-11-10 | Engineering – addressing project volume surge
122058605 | 1286 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – requiring more detailed review
122058605 | 1286 | Conduct: Initial Review (IR) | 2021-11-19 | Engineering – requiring more detailed review
122058605 | 1286 | Conduct: Initial Review (IR) | 2021-11-30 | Engineering – requiring more detailed review
122058605 | 1286 | Conduct: Initial Review (IR) | 2021-11-10 | Engineering – addressing project volume surge
122058605 | 1286 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – requiring more detailed review
122058605 | 1286 | Conduct: Initial Review (IR) | 2021-11-19 | Engineering – requiring more detailed review
122058605 | 1286 | Conduct: Initial Review (IR) | 2021-11-30 | Engineering – requiring more detailed review
122060257 | 1287 | Conduct: Initial Review (IR) | 2021-12-02 | Engineering – requiring more detailed review
122060257 | 1287 | Conduct: Initial Review (IR) | 2021-12-17 | Engineering – requiring more detailed review
122060257 | 1287 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – requiring more detailed review
122060257 | 1287 | Conduct: Initial Review (IR) | 2022-01-14 | Engineering – requiring more detailed review
122060257 | 1287 | Conduct: Initial Review (IR) | 2021-12-02 | Engineering – requiring more detailed review
122060257 | 1287 | Conduct: Initial Review (IR) | 2021-12-17 | Engineering – requiring more detailed review
122060257 | 1287 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – requiring more detailed review
122060257 | 1287 | Conduct: Initial Review (IR) | 2022-01-14 | Engineering – requiring more detailed review
122082268 | 1288 | Conduct: Initial Review (IR) | 2021-12-02 | Cus – requirement to provide a response to deficiency notice
122082268 | 1288 | Conduct: Initial Review (IR) | 2021-11-24 | Engineering – addressing project volume surge
122082268 | 1288 | Conduct: Initial Review (IR) | 2021-12-02 | Cus – requirement to provide a response to deficiency notice
122082268 | 1288 | Conduct: Initial Review (IR) | 2021-11-24 | Engineering – addressing project volume surge
122085445 | 1289 | Conduct: Initial Review (IR) | 2021-11-19 | Engineering – requiring more detailed review
122085445 | 1289 | Conduct: Initial Review (IR) | 2021-11-19 | Engineering – requiring more detailed review
122089083 | 1290 | Conduct: Supplemental Review (SR) | 2021-12-20 | Engineering – requiring more detailed review
122089083 | 1290 | Conduct: Screens Q and R | 2022-01-24 | Engineering – requiring more detailed review
122089083 | 1290 | Conduct: Screens Q and R | 2022-01-24 | Engineering – requiring more detailed review
122089083 | 1290 | Conduct: Supplemental Review (SR) | 2021-12-20 | Engineering – requiring more detailed review
122089561 | 1291 | Schedule: Scoping Meeting | 2021-12-28 | Customer – requesting an extension
122089561 | 1291 | Schedule: Scoping Meeting | 2022-01-11 | Customer – requesting an extension
122089561 | 1291 | Schedule: Scoping Meeting | 2021-12-28 | Customer – requesting an extension
122089561 | 1291 | Schedule: Scoping Meeting | 2022-01-11 | Customer – requesting an extension
122103113 | 1292 | Conduct: Initial Review (IR) | 2022-01-18 | Cus – requirement to provide a response to deficiency notice
122103113 | 1292 | Conduct: Initial Review (IR) | 2021-12-29 | Customer – requirement to provide corrected information
122103113 | 1292 | Conduct: Initial Review (IR) | 2021-12-08 | Engineering – addressing project volume surge
122103113 | 1292 | Conduct: Initial Review (IR) | 2022-01-18 | Cus – requirement to provide a response to deficiency notice
122103113 | 1292 | Conduct: Initial Review (IR) | 2021-12-29 | Customer – requirement to provide corrected information
122103113 | 1292 | Conduct: Initial Review (IR) | 2021-12-08 | Engineering – addressing project volume surge
122109151 | 1293 | Conduct: Initial Review (IR) | 2021-11-19 | Project Management – requiring more detailed review
122109642 | 1294 | Conduct: Initial Review (IR) | 2021-12-24 | Cus – requirement to provide a response to deficiency notice
122109642 | 1294 | Conduct: Supplemental Review (SR) | 2022-02-01 | Engineering – requiring more detailed review
122109642 | 1294 | Conduct: Initial Review (IR) | 2021-12-24 | Cus – requirement to provide a response to deficiency notice
122109642 | 1294 | Conduct: Supplemental Review (SR) | 2022-02-01 | Engineering – requiring more detailed review
122112221 | 1295 | Conduct: Initial Review (IR) | 2021-12-08 | Engineering – requiring more detailed review
122112221 | 1295 | Conduct: Initial Review (IR) | 2021-12-08 | Engineering – requiring more detailed review
122123584 | 1296 | Conduct: Initial Review (IR) | 2022-01-10 | Cus – requirement to provide a response to deficiency notice
122123584 | 1296 | Conduct: Initial Review (IR) | 2021-12-30 | Customer – requirement to provide corrected information
122123584 | 1296 | Conduct: Initial Review (IR) | 2022-01-18 | Project Management – requiring more detailed review
122123584 | 1296 | Conduct: Initial Review (IR) | 2022-01-25 | Project Management – requiring more detailed review
122123584 | 1296 | Conduct: Initial Review (IR) | 2022-01-10 | Cus – requirement to provide a response to deficiency notice
122123584 | 1296 | Conduct: Initial Review (IR) | 2022-02-08 | Cus – requirement to provide a response to deficiency notice
122123584 | 1296 | Conduct: Initial Review (IR) | 2021-12-30 | Customer – requirement to provide corrected information
122123584 | 1296 | Conduct: Initial Review (IR) | 2022-02-15 | Customer – requirement to provide corrected information
122123584 | 1296 | Conduct: Initial Review (IR) | 2022-01-18 | Project Management – requiring more detailed review
122123584 | 1296 | Conduct: Initial Review (IR) | 2022-01-25 | Project Management – requiring more detailed review
122127005 | 1297 | Conduct: Initial Review (IR) | 2021-11-30 | Engineering – requiring more detailed review
122127005 | 1297 | Conduct: Initial Review (IR) | 2021-12-03 | Project Management – requiring more detailed review
122127005 | 1297 | Conduct: Initial Review (IR) | 2021-11-30 | Engineering – requiring more detailed review
122127005 | 1297 | Conduct: Initial Review (IR) | 2021-12-03 | Project Management – requiring more detailed review
122128598 | 1298 | Conduct: Initial Review (IR) | 2021-11-24 | Engineering – requiring more detailed review
122128598 | 1298 | Conduct: Initial Review (IR) | 2021-11-24 | Engineering – requiring more detailed review
122130667 | 1299 | Conduct: Initial Review (IR) | 2022-01-12 | Cus – requirement to provide a response to deficiency notice
122130667 | 1299 | Conduct: Initial Review (IR) | 2022-01-19 | Customer – requirement to provide corrected information
122130667 | 1299 | Conduct: Initial Review (IR) | 2021-12-29 | Engineering – addressing project volume surge
122130667 | 1299 | Conduct: Initial Review (IR) | 2022-02-07 | Engineering – requiring more detailed review
122130667 | 1299 | Conduct: Initial Review (IR) | 2022-01-12 | Cus – requirement to provide a response to deficiency notice
122130667 | 1299 | Conduct: Initial Review (IR) | 2022-01-19 | Customer – requirement to provide corrected information
122130667 | 1299 | Conduct: Initial Review (IR) | 2021-12-29 | Engineering – addressing project volume surge
122130667 | 1299 | Conduct: Initial Review (IR) | 2022-02-07 | Engineering – requiring more detailed review
122130667 | 1299 | Conduct: Initial Review (IR) | 2022-02-22 | Engineering – requiring more detailed review
122130667 | 1299 | Conduct: Initial Review (IR) | 2022-02-25 | Engineering – requiring more detailed review
122134505 | 1300 | Conduct: Initial Review (IR) | 2021-11-22 | Engineering – addressing project volume surge
122134505 | 1300 | Conduct: Initial Review (IR) | 2021-12-06 | Engineering – requiring more detailed review
122134505 | 1300 | Conduct: Initial Review (IR) | 2021-12-20 | Engineering – requiring more detailed review
122134505 | 1300 | Conduct: Initial Review (IR) | 2022-01-03 | Engineering – requiring more detailed review
122134505 | 1300 | Conduct: Initial Review (IR) | 2022-01-10 | Engineering – requiring more detailed review
122134505 | 1300 | Conduct: Initial Review (IR) | 2021-11-22 | Engineering – addressing project volume surge
122134505 | 1300 | Conduct: Initial Review (IR) | 2021-12-06 | Engineering – requiring more detailed review
122134505 | 1300 | Conduct: Initial Review (IR) | 2021-12-20 | Engineering – requiring more detailed review
122134505 | 1300 | Conduct: Initial Review (IR) | 2022-01-03 | Engineering – requiring more detailed review
122134505 | 1300 | Conduct: Initial Review (IR) | 2022-01-10 | Engineering – requiring more detailed review
122134922 | 1301 | Conduct: Initial Review (IR) | 2021-11-22 | Engineering – addressing project volume surge
122134922 | 1301 | Conduct: Initial Review (IR) | 2021-12-06 | Engineering – requiring more detailed review
122134922 | 1301 | Conduct: Initial Review (IR) | 2021-12-20 | Engineering – requiring more detailed review
122134922 | 1301 | Conduct: Initial Review (IR) | 2022-01-03 | Engineering – requiring more detailed review
122134922 | 1301 | Conduct: Initial Review (IR) | 2022-01-10 | Engineering – requiring more detailed review
122134922 | 1301 | Conduct: Initial Review (IR) | 2021-11-22 | Engineering – addressing project volume surge
122134922 | 1301 | Conduct: Initial Review (IR) | 2021-12-06 | Engineering – requiring more detailed review
122134922 | 1301 | Conduct: Initial Review (IR) | 2021-12-20 | Engineering – requiring more detailed review
122134922 | 1301 | Conduct: Initial Review (IR) | 2022-01-03 | Engineering – requiring more detailed review
122134922 | 1301 | Conduct: Initial Review (IR) | 2022-01-10 | Engineering – requiring more detailed review
122137345 | 1302 | Conduct: Initial Review (IR) | 2021-11-04 | Engineering – requiring more detailed review
122137345 | 1302 | Conduct: Initial Review (IR) | 2021-11-18 | Engineering – requiring more detailed review
122137345 | 1302 | Conduct: Initial Review (IR) | 2021-11-26 | Engineering – requiring more detailed review
122137345 | 1302 | Conduct: Initial Review (IR) | 2021-11-04 | Engineering – requiring more detailed review
122137345 | 1302 | Conduct: Initial Review (IR) | 2021-11-18 | Engineering – requiring more detailed review
122137345 | 1302 | Conduct: Initial Review (IR) | 2021-11-26 | Engineering – requiring more detailed review
122143207 | 1303 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – requiring more detailed review
122143207 | 1303 | Conduct: Initial Review (IR) | 2021-12-03 | Engineering – requiring more detailed review
122143207 | 1303 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – requiring more detailed review
122143207 | 1303 | Conduct: Initial Review (IR) | 2021-12-03 | Engineering – requiring more detailed review
122143420 | 1304 | Conduct: Initial Review (IR) | 2021-11-09 | Engineering – requiring more detailed review
122143420 | 1304 | Conduct: Initial Review (IR) | 2021-12-01 | Engineering – requiring more detailed review
122143420 | 1304 | Conduct: Initial Review (IR) | 2021-11-09 | Engineering – requiring more detailed review
122143420 | 1304 | Conduct: Initial Review (IR) | 2021-12-01 | Engineering – requiring more detailed review
122144546 | 1305 | Conduct: Initial Review (IR) | 2021-12-22 | Engineering – requiring more detailed review
122144546 | 1305 | Conduct: Initial Review (IR) | 2021-12-22 | Engineering – requiring more detailed review
122144589 | 1306 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – requiring more detailed review
122144589 | 1306 | Conduct: Initial Review (IR) | 2021-11-26 | Engineering – requiring more detailed review
122144589 | 1306 | Conduct: Initial Review (IR) | 2021-11-05 | Engineering – requiring more detailed review
122144589 | 1306 | Conduct: Initial Review (IR) | 2021-11-26 | Engineering – requiring more detailed review
122144594 | 1307 | Conduct: Initial Review (IR) | 2021-11-26 | Engineering – requiring more detailed review
122144594 | 1307 | Conduct: Initial Review (IR) | 2021-11-26 | Engineering – requiring more detailed review
122147302 | 1308 | Conduct: Initial Review (IR) | 2021-11-24 | Engineering – requiring more detailed review
122147302 | 1308 | Conduct: Initial Review (IR) | 2021-12-13 | Engineering – requiring more detailed review
122147302 | 1308 | Conduct: Initial Review (IR) | 2021-12-13 | Engineering – requiring more detailed review
122147302 | 1308 | Conduct: Initial Review (IR) | 2021-11-24 | Engineering – requiring more detailed review
122147527 | 1309 | Conduct: Supplemental Review (SR) | 2021-12-27 | Engineering – requiring more detailed review
122147527 | 1309 | Conduct: Supplemental Review (SR) | 2022-01-03 | Engineering – requiring more detailed review
122147527 | 1309 | Conduct: Supplemental Review (SR) | 2022-01-10 | Engineering – requiring more detailed review
122147527 | 1309 | Conduct: Supplemental Review (SR) | 2022-01-24 | Engineering – requiring more detailed review
122147527 | 1309 | Conduct: Supplemental Review (SR) | 2022-02-07 | Engineering – requiring more detailed review
122147527 | 1309 | Conduct: Supplemental Review (SR) | 2021-12-27 | Engineering – requiring more detailed review
122147527 | 1309 | Conduct: Supplemental Review (SR) | 2022-01-03 | Engineering – requiring more detailed review
122147527 | 1309 | Conduct: Supplemental Review (SR) | 2022-01-10 | Engineering – requiring more detailed review
122147527 | 1309 | Conduct: Supplemental Review (SR) | 2022-01-24 | Engineering – requiring more detailed review
122147527 | 1309 | Conduct: Supplemental Review (SR) | 2022-02-07 | Engineering – requiring more detailed review
122151929 | 1310 | Conduct: Initial Review (IR) | 2021-12-21 | Engineering – requiring more detailed review
122151929 | 1310 | Conduct: Initial Review (IR) | 2022-01-04 | Engineering – requiring more detailed review
122151929 | 1310 | Conduct: Initial Review (IR) | 2022-01-18 | Engineering – requiring more detailed review
122151929 | 1310 | Conduct: Initial Review (IR) | 2021-12-21 | Engineering – requiring more detailed review
122151929 | 1310 | Conduct: Initial Review (IR) | 2022-01-04 | Engineering – requiring more detailed review
122151929 | 1310 | Conduct: Initial Review (IR) | 2022-01-18 | Engineering – requiring more detailed review
122152224 | 1311 | Conduct: Initial Review (IR) | 2021-11-17 | Engineering – requiring more detailed review
122152224 | 1311 | Conduct: Initial Review (IR) | 2021-11-17 | Engineering – requiring more detailed review
122153620 | 1312 | Conduct: Supplemental Review (SR) | 2022-01-26 | Engineering – requiring more detailed review
122153620 | 1312 | Conduct: Supplemental Review (SR) | 2022-01-26 | Engineering – requiring more detailed review
122160594 | 1313 | Conduct: Supplemental Review (SR) | 2022-01-05 | Engineering – addressing project volume surge
122160594 | 1313 | Conduct: Supplemental Review (SR) | 2022-01-19 | Engineering – addressing project volume surge
122160594 | 1313 | Conduct: Supplemental Review (SR) | 2022-02-02 | Engineering – addressing project volume surge
122160594 | 1313 | Conduct: Supplemental Review (SR) | 2022-01-05 | Engineering – addressing project volume surge
122160594 | 1313 | Conduct: Supplemental Review (SR) | 2022-01-19 | Engineering – addressing project volume surge
122160594 | 1313 | Conduct: Supplemental Review (SR) | 2022-02-02 | Engineering – addressing project volume surge
122169773 | 1314 | Conduct: Initial Review (IR) | 2022-02-11 | Engineering – requiring more detailed review
122169773 | 1314 | Conduct: Initial Review (IR) | 2022-02-11 | Engineering – requiring more detailed review
122169773 | 1314 | Conduct: Initial Review (IR) | 2022-02-25 | Engineering – requiring more detailed review
122184074 | 1315 | Conduct: Initial Review (IR) | 2021-12-10 | Engineering – requiring more detailed review
122184074 | 1315 | Conduct: Initial Review (IR) | 2021-12-10 | Engineering – requiring more detailed review
122185032 | 1316 | Conduct: Initial Review (IR) | 2021-12-15 | Engineering – requiring more detailed review
122185032 | 1316 | Conduct: Initial Review (IR) | 2021-12-15 | Engineering – requiring more detailed review
122185382 | 1317 | Conduct: Initial Review (IR) | 2021-12-08 | Engineering – requiring more detailed review
122185382 | 1317 | Conduct: Initial Review (IR) | 2021-12-15 | Engineering – requiring more detailed review
122185382 | 1317 | Conduct: Initial Review (IR) | 2021-12-22 | Engineering – requiring more detailed review
122185382 | 1317 | Conduct: Initial Review (IR) | 2021-12-08 | Engineering – requiring more detailed review
122185382 | 1317 | Conduct: Initial Review (IR) | 2021-12-15 | Engineering – requiring more detailed review
122185382 | 1317 | Conduct: Initial Review (IR) | 2021-12-22 | Engineering – requiring more detailed review
122186309 | 1318 | Conduct: Initial Review (IR) | 2021-12-13 | Cus – requirement to provide a response to deficiency notice
122186309 | 1318 | Conduct: Initial Review (IR) | 2021-12-20 | Engineering – requiring more detailed review
122186309 | 1318 | Conduct: Initial Review (IR) | 2021-12-27 | Engineering – requiring more detailed review
122186309 | 1318 | Conduct: Initial Review (IR) | 2021-12-13 | Cus – requirement to provide a response to deficiency notice
122186309 | 1318 | Conduct: Initial Review (IR) | 2021-12-20 | Engineering – requiring more detailed review
122186309 | 1318 | Conduct: Initial Review (IR) | 2021-12-27 | Engineering – requiring more detailed review
122186521 | 1319 | Conduct: Initial Review (IR) | 2022-02-02 | Cus – requirement to provide a response to deficiency notice
122186521 | 1319 | Conduct: Initial Review (IR) | 2022-01-11 | Engineering – requiring more detailed review
122186521 | 1319 | Conduct: Initial Review (IR) | 2022-01-19 | Engineering – requiring more detailed review
122186521 | 1319 | Conduct: Initial Review (IR) | 2022-02-02 | Cus – requirement to provide a response to deficiency notice
122186521 | 1319 | Conduct: Initial Review (IR) | 2022-01-11 | Engineering – requiring more detailed review
122186521 | 1319 | Conduct: Initial Review (IR) | 2022-01-19 | Engineering – requiring more detailed review
122190165 | 1320 | Conduct: Initial Review (IR) | 2022-01-20 | Engineering – addressing project volume surge
122190165 | 1320 | Conduct: Initial Review (IR) | 2022-01-27 | Engineering – addressing project volume surge
122190165 | 1320 | Conduct: Initial Review (IR) | 2022-01-20 | Engineering – addressing project volume surge
122190165 | 1320 | Conduct: Initial Review (IR) | 2022-01-27 | Engineering – addressing project volume surge
122190665 | 1321 | Conduct: Screens Q and R | 2022-01-07 | Engineering – requiring more detailed review
122190665 | 1321 | Conduct: SIS | 2022-04-11 | Engineering – addressing project volume surge
122190665 | 1321 | Conduct: SIS | 2022-04-15 | Engineering – addressing project volume surge
122190665 | 1321 | Conduct: Screens Q and R | 2022-01-07 | Engineering – requiring more detailed review
122190665 | 1321 | Conduct: SIS | 2022-04-04 | Engineering – requiring more detailed review
122192180 | 1322 | Conduct: Initial Review (IR) | 2021-12-02 | Cus – requirement to provide a response to deficiency notice
122192180 | 1322 | Conduct: Initial Review (IR) | 2021-12-02 | Cus – requirement to provide a response to deficiency notice
122199719 | 1323 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – requiring more detailed review
122199719 | 1323 | Conduct: Supplemental Review (SR) | 2022-03-29 | Engineering – addressing project volume surge
122199719 | 1323 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – requiring more detailed review
122199719 | 1323 | Conduct: Initial Review (IR) | 2022-02-14 | Engineering – requiring more detailed review
122200118 | 1324 | Conduct: Initial Review (IR) | 2021-12-10 | Engineering – requiring more detailed review
122200118 | 1324 | Conduct: Initial Review (IR) | 2021-12-24 | Engineering – requiring more detailed review
122200118 | 1324 | Conduct: Initial Review (IR) | 2021-12-10 | Engineering – requiring more detailed review
122200118 | 1324 | Conduct: Initial Review (IR) | 2021-12-24 | Engineering – requiring more detailed review
122206225 | 1325 | Conduct: Screens Q and R | 2022-01-14 | Engineering – requiring more detailed review
122206225 | 1325 | Conduct: Screens Q and R | 2022-01-14 | Engineering – requiring more detailed review
122206852 | 1326 | Conduct: Initial Review (IR) | 2021-12-07 | Engineering – requiring more detailed review
122206852 | 1326 | Conduct: Initial Review (IR) | 2021-12-28 | Engineering – requiring more detailed review
122206852 | 1326 | Conduct: Initial Review (IR) | 2021-12-07 | Engineering – requiring more detailed review
122206852 | 1326 | Conduct: Initial Review (IR) | 2021-12-28 | Engineering – requiring more detailed review
122208568 | 1327 | Conduct: Supplemental Review (SR) | 2022-02-01 | Engineering – addressing project volume surge
122208568 | 1327 | Conduct: Supplemental Review (SR) | 2022-01-10 | Engineering – requiring more detailed review
122208568 | 1327 | Conduct: Supplemental Review (SR) | 2022-02-01 | Engineering – addressing project volume surge
122208568 | 1327 | Conduct: Supplemental Review (SR) | 2022-02-23 | Engineering – addressing project volume surge
122208568 | 1327 | Conduct: Supplemental Review (SR) | 2022-01-10 | Engineering – requiring more detailed review
122210450 | 1328 | Conduct: Initial Review (IR) | 2021-12-09 | Engineering – requiring more detailed review
122210450 | 1328 | Conduct: Initial Review (IR) | 2021-12-09 | Engineering – requiring more detailed review
122211918 | 1329 | Conduct: Initial Review (IR) | 2021-12-23 | Engineering – requiring more detailed review
122211918 | 1329 | Conduct: Initial Review (IR) | 2021-12-23 | Engineering – requiring more detailed review
122213809 | 1330 | Conduct: Initial Review (IR) | 2021-11-26 | Cus – requirement to provide a response to deficiency notice
122213809 | 1330 | Conduct: Initial Review (IR) | 2021-12-01 | Engineering – addressing project volume surge
122213809 | 1330 | Conduct: Initial Review (IR) | 2021-12-08 | Engineering – addressing project volume surge
122213809 | 1330 | Conduct: Initial Review (IR) | 2021-11-26 | Cus – requirement to provide a response to deficiency notice
122213809 | 1330 | Conduct: Initial Review (IR) | 2021-12-01 | Engineering – addressing project volume surge
122213809 | 1330 | Conduct: Initial Review (IR) | 2021-12-08 | Engineering – addressing project volume surge
122222153 | 1331 | Conduct: Initial Review (IR) | 2021-11-26 | Engineering – requiring more detailed review
122222153 | 1331 | Conduct: Initial Review (IR) | 2021-11-26 | Engineering – requiring more detailed review
122225940 | 1332 | Conduct: Initial Review (IR) | 2021-12-06 | Engineering – requiring more detailed review
122225940 | 1332 | Conduct: Initial Review (IR) | 2021-12-20 | Engineering – requiring more detailed review
122225940 | 1332 | Conduct: Initial Review (IR) | 2021-12-06 | Engineering – requiring more detailed review
122225940 | 1332 | Conduct: Initial Review (IR) | 2021-12-20 | Engineering – requiring more detailed review
122227723 | 1333 | Conduct: Initial Review (IR) | 2021-12-17 | Engineering – addressing project volume surge
122227723 | 1333 | Conduct: Initial Review (IR) | 2021-12-17 | Engineering – addressing project volume surge
122227723 | 1333 | Conduct: Supplemental Review (SR) | 2022-02-16 | Engineering – addressing project volume surge
122232722 | 1334 | Conduct: Initial Review (IR) | 2022-01-06 | Cus – requirement to provide a response to deficiency notice
122232722 | 1334 | Conduct: Initial Review (IR) | 2022-01-21 | Cus – requirement to provide a response to deficiency notice
122232722 | 1334 | Conduct: Initial Review (IR) | 2022-01-28 | Project Management - addressing project volume surge
122232722 | 1334 | Conduct: Initial Review (IR) | 2022-01-06 | Cus – requirement to provide a response to deficiency notice
122232722 | 1334 | Conduct: Initial Review (IR) | 2022-01-21 | Cus – requirement to provide a response to deficiency notice
122232722 | 1334 | Conduct: Initial Review (IR) | 2022-02-11 | Cus – requirement to provide a response to deficiency notice
122232722 | 1334 | Conduct: Initial Review (IR) | 2022-02-28 | Cus – requirement to provide a response to deficiency notice
122232722 | 1334 | Conduct: Initial Review (IR) | 2022-01-28 | Project Management - addressing project volume surge
122239546 | 1335 | Conduct: Initial Review (IR) | 2021-12-10 | Engineering – requiring more detailed review
122239546 | 1335 | Conduct: Initial Review (IR) | 2021-12-10 | Engineering – requiring more detailed review
122241073 | 1336 | Conduct: Supplemental Review (SR) | 2022-01-12 | Engineering – requiring more detailed review
122241073 | 1336 | Conduct: Supplemental Review (SR) | 2022-01-12 | Engineering – requiring more detailed review
122245084 | 1337 | Conduct: Supplemental Review (SR) | 2022-01-03 | Engineering – requiring more detailed review
122245084 | 1337 | Conduct: Supplemental Review (SR) | 2022-01-03 | Engineering – requiring more detailed review
122245209 | 1338 | Conduct: Initial Review (IR) | 2021-12-22 | Engineering – addressing project volume surge
122245209 | 1338 | Conduct: Initial Review (IR) | 2021-12-22 | Engineering – addressing project volume surge
122245421 | 1339 | Conduct: Initial Review (IR) | 2021-11-30 | Cus – requirement to provide a response to deficiency notice
122245421 | 1339 | Conduct: Initial Review (IR) | 2021-11-30 | Cus – requirement to provide a response to deficiency notice
122245498 | 1340 | Conduct: Initial Review (IR) | 2021-12-22 | Engineering – addressing project volume surge
122245498 | 1340 | Conduct: Initial Review (IR) | 2021-12-22 | Engineering – addressing project volume surge
122246869 | 1341 | Conduct: Supplemental Review (SR) | 2022-01-05 | Engineering – addressing project volume surge
122246869 | 1341 | Conduct: Supplemental Review (SR) | 2022-01-06 | Engineering – addressing project volume surge
122246869 | 1341 | Conduct: Supplemental Review (SR) | 2022-01-13 | Engineering – addressing project volume surge
122246869 | 1341 | Conduct: Supplemental Review (SR) | 2022-01-05 | Engineering – addressing project volume surge
122246869 | 1341 | Conduct: Supplemental Review (SR) | 2022-01-06 | Engineering – addressing project volume surge
122246869 | 1341 | Conduct: Supplemental Review (SR) | 2022-01-13 | Engineering – addressing project volume surge
122256451 | 1342 | Conduct: Initial Review (IR) | 2021-12-03 | Engineering – requiring more detailed review
122256451 | 1342 | Conduct: Initial Review (IR) | 2021-12-17 | Engineering – requiring more detailed review
122256451 | 1342 | Conduct: Initial Review (IR) | 2021-12-03 | Engineering – requiring more detailed review
122256451 | 1342 | Conduct: Initial Review (IR) | 2021-12-17 | Engineering – requiring more detailed review
122257456 | 1343 | Conduct: Initial Review (IR) | 2021-12-03 | Engineering – requiring more detailed review
122257456 | 1343 | Conduct: Initial Review (IR) | 2021-12-03 | Engineering – requiring more detailed review
122257674 | 1344 | Conduct: Initial Review (IR) | 2022-01-04 | Engineering – requiring more detailed review
122257674 | 1344 | Conduct: Initial Review (IR) | 2022-01-18 | Engineering – requiring more detailed review
122257674 | 1344 | Conduct: Supplemental Review (SR) | 2022-03-02 | Engineering – addressing project volume surge
122257674 | 1344 | Conduct: Supplemental Review (SR) | 2022-03-09 | Engineering – addressing project volume surge
122257674 | 1344 | Conduct: Supplemental Review (SR) | 2022-03-16 | Engineering – addressing project volume surge
122257674 | 1344 | Conduct: Initial Review (IR) | 2022-01-04 | Engineering – requiring more detailed review
122257674 | 1344 | Conduct: Initial Review (IR) | 2022-01-18 | Engineering – requiring more detailed review
122257746 | 1345 | Conduct: Supplemental Review (SR) | 2021-12-28 | Engineering – requiring more detailed review
122257746 | 1345 | Conduct: Supplemental Review (SR) | 2021-12-28 | Engineering – requiring more detailed review
122258242 | 1346 | Conduct: Initial Review (IR) | 2021-12-22 | Engineering – requiring more detailed review
122258242 | 1346 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – requiring more detailed review
122258242 | 1346 | Conduct: Initial Review (IR) | 2021-12-22 | Engineering – requiring more detailed review
122258242 | 1346 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – requiring more detailed review
122260218 | 1347 | Conduct: Initial Review (IR) | 2021-12-24 | Engineering – requiring more detailed review
122260218 | 1347 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – requiring more detailed review
122260218 | 1347 | Conduct: Initial Review (IR) | 2022-01-07 | Engineering – requiring more detailed review
122260218 | 1347 | Conduct: Initial Review (IR) | 2022-01-14 | Engineering – requiring more detailed review
122260218 | 1347 | Conduct: Initial Review (IR) | 2021-12-24 | Engineering – requiring more detailed review
122260218 | 1347 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – requiring more detailed review
122260218 | 1347 | Conduct: Initial Review (IR) | 2022-01-07 | Engineering – requiring more detailed review
122260218 | 1347 | Conduct: Initial Review (IR) | 2022-01-14 | Engineering – requiring more detailed review
122261060 | 1348 | Conduct: Initial Review (IR) | 2021-12-17 | Engineering – requiring more detailed review
122261060 | 1348 | Conduct: Initial Review (IR) | 2021-12-24 | Engineering – requiring more detailed review
122261060 | 1348 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – requiring more detailed review
122261060 | 1348 | Conduct: Initial Review (IR) | 2022-01-07 | Engineering – requiring more detailed review
122261060 | 1348 | Conduct: Initial Review (IR) | 2022-01-14 | Engineering – requiring more detailed review
122261060 | 1348 | Conduct: Initial Review (IR) | 2022-01-24 | Engineering – requiring more detailed review
122261060 | 1348 | Conduct: Initial Review (IR) | 2021-12-17 | Engineering – requiring more detailed review
122261060 | 1348 | Conduct: Initial Review (IR) | 2021-12-24 | Engineering – requiring more detailed review
122261060 | 1348 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – requiring more detailed review
122261060 | 1348 | Conduct: Initial Review (IR) | 2022-01-07 | Engineering – requiring more detailed review
122261060 | 1348 | Conduct: Initial Review (IR) | 2022-01-14 | Engineering – requiring more detailed review
122261060 | 1348 | Conduct: Initial Review (IR) | 2022-01-24 | Engineering – requiring more detailed review
122262346 | 1349 | Conduct: Initial Review (IR) | 2021-12-20 | Engineering – requiring more detailed review
122262346 | 1349 | Conduct: Initial Review (IR) | 2021-12-20 | Engineering – requiring more detailed review
122265254 | 1350 | Conduct: Initial Review (IR) | 2021-12-20 | Engineering – requiring more detailed review
122265254 | 1350 | Conduct: Initial Review (IR) | 2022-01-10 | Engineering – requiring more detailed review
122265254 | 1350 | Conduct: Initial Review (IR) | 2021-12-20 | Engineering – requiring more detailed review
122265254 | 1350 | Conduct: Initial Review (IR) | 2022-01-10 | Engineering – requiring more detailed review
122266609 | 1351 | Conduct: Initial Review (IR) | 2021-12-24 | Customer – requirement to provide corrected information
122266609 | 1351 | Conduct: Initial Review (IR) | 2022-01-03 | Customer – requirement to provide corrected information
122266609 | 1351 | Conduct: Initial Review (IR) | 2022-01-14 | Customer – requirement to provide corrected information
122266609 | 1351 | Conduct: Initial Review (IR) | 2022-02-07 | Engineering – requiring more detailed review
122266609 | 1351 | Conduct: Initial Review (IR) | 2021-12-24 | Customer – requirement to provide corrected information
122266609 | 1351 | Conduct: Initial Review (IR) | 2022-01-03 | Customer – requirement to provide corrected information
122266609 | 1351 | Conduct: Initial Review (IR) | 2022-01-14 | Customer – requirement to provide corrected information
122266609 | 1351 | Conduct: Initial Review (IR) | 2022-02-24 | Engineering – addressing project volume surge
122266609 | 1351 | Conduct: Initial Review (IR) | 2022-02-07 | Engineering – requiring more detailed review
122269543 | 1352 | Conduct: Initial Review (IR) | 2022-01-10 | Customer – requirement to provide corrected information
122269543 | 1352 | Conduct: Initial Review (IR) | 2022-01-17 | Engineering – requiring more detailed review
122269543 | 1352 | Conduct: Initial Review (IR) | 2022-01-10 | Customer – requirement to provide corrected information
122269543 | 1352 | Conduct: Initial Review (IR) | 2022-01-17 | Engineering – requiring more detailed review
122273152 | 1353 | Conduct: Initial Review (IR) | 2021-12-10 | Engineering – requiring more detailed review
122273152 | 1353 | Conduct: Initial Review (IR) | 2021-12-17 | Engineering – requiring more detailed review
122273152 | 1353 | Conduct: Initial Review (IR) | 2021-12-24 | Engineering – requiring more detailed review
122273152 | 1353 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – requiring more detailed review
122273152 | 1353 | Conduct: Initial Review (IR) | 2021-12-10 | Engineering – requiring more detailed review
122273152 | 1353 | Conduct: Initial Review (IR) | 2021-12-17 | Engineering – requiring more detailed review
122273152 | 1353 | Conduct: Initial Review (IR) | 2021-12-24 | Engineering – requiring more detailed review
122273152 | 1353 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – requiring more detailed review
122275509 | 1354 | Conduct: Initial Review (IR) | 2021-12-09 | Engineering – requiring more detailed review
122275509 | 1354 | Conduct: Initial Review (IR) | 2021-12-23 | Engineering – requiring more detailed review
122275509 | 1354 | Conduct: Initial Review (IR) | 2021-12-09 | Engineering – requiring more detailed review
122275509 | 1354 | Conduct: Initial Review (IR) | 2021-12-23 | Engineering – requiring more detailed review
122276275 | 1355 | Conduct: Initial Review (IR) | 2022-01-06 | Engineering – requiring more detailed review
122276275 | 1355 | Conduct: Initial Review (IR) | 2022-01-06 | Engineering – requiring more detailed review
122289045 | 1356 | Conduct: Initial Review (IR) | 2022-01-06 | Cus – requirement to provide a response to deficiency notice
122289045 | 1356 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – requiring more detailed review
122289045 | 1356 | Conduct: Initial Review (IR) | 2022-01-06 | Cus – requirement to provide a response to deficiency notice
122289045 | 1356 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – requiring more detailed review
122289470 | 1357 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – requiring more detailed review
122289470 | 1357 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – requiring more detailed review
122292177 | 1358 | Conduct: Initial Review (IR) | 2022-01-17 | Customer – requirement to provide corrected information
122292177 | 1358 | Conduct: Initial Review (IR) | 2022-01-17 | Customer – requirement to provide corrected information
122292335 | 1359 | Conduct: Initial Review (IR) | 2021-12-21 | Engineering – requiring more detailed review
122292335 | 1359 | Conduct: Initial Review (IR) | 2021-12-21 | Engineering – requiring more detailed review
122292559 | 1360 | Conduct: Initial Review (IR) | 2021-12-21 | Engineering – requiring more detailed review
122292559 | 1360 | Conduct: Initial Review (IR) | 2021-12-21 | Engineering – requiring more detailed review
122312879 | 1361 | Conduct: Initial Review (IR) | 2021-12-30 | Engineering – requiring more detailed review
122312879 | 1361 | Conduct: Initial Review (IR) | 2021-12-30 | Engineering – requiring more detailed review
122320434 | 1362 | Conduct: Initial Review (IR) | 2021-12-21 | Engineering – requiring more detailed review
122320434 | 1362 | Conduct: Initial Review (IR) | 2021-12-28 | Engineering – requiring more detailed review
122320434 | 1362 | Conduct: Initial Review (IR) | 2022-01-04 | Engineering – requiring more detailed review
122320434 | 1362 | Conduct: Initial Review (IR) | 2021-12-21 | Engineering – requiring more detailed review
122320434 | 1362 | Conduct: Initial Review (IR) | 2021-12-28 | Engineering – requiring more detailed review
122320434 | 1362 | Conduct: Initial Review (IR) | 2022-01-04 | Engineering – requiring more detailed review
122322362 | 1363 | Conduct: Initial Review (IR) | 2022-01-13 | Engineering – requiring more detailed review
122322362 | 1363 | Conduct: Initial Review (IR) | 2022-01-13 | Engineering – requiring more detailed review
122340008 | 1364 | Conduct: Supplemental Review (SR) | 2022-02-02 | Engineering – addressing project volume surge
122340008 | 1364 | Conduct: Supplemental Review (SR) | 2022-02-02 | Engineering – addressing project volume surge
122344267 | 1365 | Conduct: Initial Review (IR) | 2022-01-03 | Engineering – requiring more detailed review
122344267 | 1365 | Conduct: Supplemental Review (SR) | 2022-02-03 | Engineering – addressing project volume surge
122344267 | 1365 | Conduct: Initial Review (IR) | 2022-01-03 | Engineering – requiring more detailed review
122346045 | 1366 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – requiring more detailed review
122346045 | 1366 | Conduct: Initial Review (IR) | 2022-01-13 | Engineering – requiring more detailed review
122346045 | 1366 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – requiring more detailed review
122346045 | 1366 | Conduct: Initial Review (IR) | 2022-01-13 | Engineering – requiring more detailed review
122346070 | 1367 | Conduct: Initial Review (IR) | 2022-01-08 | Cus – requirement to provide a response to deficiency notice
122346070 | 1367 | Conduct: Initial Review (IR) | 2022-01-27 | Project Management – requiring more detailed review
122346070 | 1367 | Conduct: Initial Review (IR) | 2022-01-31 | Project Management – requiring more detailed review
122346070 | 1367 | Conduct: Initial Review (IR) | 2022-01-08 | Cus – requirement to provide a response to deficiency notice
122346070 | 1367 | Conduct: Initial Review (IR) | 2022-02-14 | Engineering – addressing project volume surge
122346070 | 1367 | Conduct: Initial Review (IR) | 2022-01-27 | Project Management – requiring more detailed review
122346070 | 1367 | Conduct: Initial Review (IR) | 2022-01-31 | Project Management – requiring more detailed review
122357831 | 1368 | Conduct: Supplemental Review (SR) | 2022-01-31 | Engineering – addressing project volume surge
122357831 | 1368 | Conduct: Supplemental Review (SR) | 2022-01-31 | Engineering – addressing project volume surge
122357935 | 1369 | Conduct: Supplemental Review (SR) | 2022-01-26 | Engineering – requiring more detailed review
122357935 | 1369 | Conduct: Supplemental Review (SR) | 2022-01-26 | Engineering – requiring more detailed review
122358306 | 1370 | Conduct: Initial Review (IR) | 2021-12-27 | Engineering – requiring more detailed review
122358306 | 1370 | Conduct: Initial Review (IR) | 2021-12-27 | Engineering – requiring more detailed review
122359708 | 1371 | Conduct: Initial Review (IR) | 2022-01-05 | Engineering – addressing project volume surge
122359708 | 1371 | Conduct: Initial Review (IR) | 2022-01-06 | Engineering – addressing project volume surge
122359708 | 1371 | Conduct: Initial Review (IR) | 2022-01-27 | Engineering – requiring more detailed review
122359708 | 1371 | Conduct: Initial Review (IR) | 2022-01-05 | Engineering – addressing project volume surge
122359708 | 1371 | Conduct: Initial Review (IR) | 2022-01-06 | Engineering – addressing project volume surge
122359708 | 1371 | Conduct: Initial Review (IR) | 2022-01-27 | Engineering – requiring more detailed review
122359708 | 1371 | Conduct: Initial Review (IR) | 2022-03-04 | Engineering – requiring more detailed review
122359708 | 1371 | Conduct: Supplemental Review (SR) | 2022-04-01 | Engineering – requiring more detailed review
122359873 | 1372 | Conduct: Initial Review (IR) | 2022-01-05 | Engineering – addressing project volume surge
122359873 | 1372 | Conduct: Initial Review (IR) | 2022-01-06 | Engineering – addressing project volume surge
122359873 | 1372 | Conduct: Initial Review (IR) | 2022-01-27 | Engineering – requiring more detailed review
122359873 | 1372 | Conduct: Initial Review (IR) | 2022-01-05 | Engineering – addressing project volume surge
122359873 | 1372 | Conduct: Initial Review (IR) | 2022-01-06 | Engineering – addressing project volume surge
122359873 | 1372 | Conduct: Initial Review (IR) | 2022-01-27 | Engineering – requiring more detailed review
122359873 | 1372 | Conduct: Supplemental Review (SR) | 2022-03-28 | Engineering – requiring more detailed review
122359873 | 1372 | Conduct: Supplemental Review (SR) | 2022-04-01 | Engineering – requiring more detailed review
122361048 | 1373 | Conduct: Initial Review (IR) | 2022-01-12 | Cus – requirement to provide a response to deficiency notice
122361048 | 1373 | Conduct: Initial Review (IR) | 2021-12-29 | Engineering – addressing project volume surge
122361048 | 1373 | Conduct: Initial Review (IR) | 2022-01-19 | Engineering – requiring more detailed review
122361048 | 1373 | Conduct: Initial Review (IR) | 2022-01-12 | Cus – requirement to provide a response to deficiency notice
122361048 | 1373 | Conduct: Initial Review (IR) | 2021-12-29 | Engineering – addressing project volume surge
122361048 | 1373 | Conduct: Initial Review (IR) | 2022-01-19 | Engineering – requiring more detailed review
122362390 | 1374 | Conduct: Initial Review (IR) | 2022-01-11 | Engineering – requiring more detailed review
122362390 | 1374 | Conduct: Initial Review (IR) | 2022-01-18 | Engineering – requiring more detailed review
122362390 | 1374 | Conduct: Initial Review (IR) | 2022-01-25 | Engineering – requiring more detailed review
122362390 | 1374 | Conduct: Initial Review (IR) | 2022-01-11 | Engineering – requiring more detailed review
122362390 | 1374 | Conduct: Initial Review (IR) | 2022-01-18 | Engineering – requiring more detailed review
122362390 | 1374 | Conduct: Initial Review (IR) | 2022-01-25 | Engineering – requiring more detailed review
122365323 | 1375 | Conduct: Supplemental Review (SR) | 2022-01-27 | Engineering – requiring more detailed review
122365323 | 1375 | Conduct: Screens Q and R | 2022-03-09 | Engineering – requiring more detailed review
122365323 | 1375 | Conduct: Supplemental Review (SR) | 2022-01-27 | Engineering – requiring more detailed review
122371948 | 1376 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – requiring more detailed review
122371948 | 1376 | Conduct: Initial Review (IR) | 2022-01-14 | Project Management – requiring more detailed review
122371948 | 1376 | Conduct: Initial Review (IR) | 2021-12-31 | Engineering – requiring more detailed review
122371948 | 1376 | Conduct: Supplemental Review (SR) | 2022-02-18 | Engineering – requiring more detailed review
122371948 | 1376 | Conduct: Initial Review (IR) | 2022-01-14 | Project Management – requiring more detailed review
122373708 | 1377 | Conduct: Supplemental Review (SR) | 2022-01-17 | Engineering – requiring more detailed review
122373708 | 1377 | Conduct: Supplemental Review (SR) | 2022-01-17 | Engineering – requiring more detailed review
122374080 | 1378 | Conduct: Initial Review (IR) | 2022-01-04 | Customer – requirement to provide corrected information
122374080 | 1378 | Conduct: Initial Review (IR) | 2022-02-01 | Customer – requirement to provide corrected information
122374080 | 1378 | Conduct: Initial Review (IR) | 2022-01-18 | Engineering – requiring more detailed review
122374080 | 1378 | Conduct: Initial Review (IR) | 2022-02-15 | Cus – requirement to provide a response to deficiency notice
122374080 | 1378 | Conduct: Initial Review (IR) | 2022-01-04 | Customer – requirement to provide corrected information
122374080 | 1378 | Conduct: Initial Review (IR) | 2022-02-01 | Customer – requirement to provide corrected information
122374080 | 1378 | Conduct: Initial Review (IR) | 2022-03-15 | Customer – requirement to provide corrected information
122374080 | 1378 | Conduct: Initial Review (IR) | 2022-04-15 | Customer – requirement to provide corrected information
122374080 | 1378 | Conduct: Initial Review (IR) | 2022-05-13 | Customer – requirement to provide corrected information
122374080 | 1378 | Conduct: Initial Review (IR) | 2022-01-18 | Engineering – requiring more detailed review
122377980 | 1379 | Conduct: Initial Review (IR) | 2022-02-02 | Engineering – requiring more detailed review
122377980 | 1379 | Conduct: Initial Review (IR) | 2022-02-02 | Engineering – requiring more detailed review
122378365 | 1380 | Conduct: Initial Review (IR) | 2022-01-10 | Engineering – requiring more detailed review
122378365 | 1380 | Conduct: Initial Review (IR) | 2022-01-10 | Engineering – requiring more detailed review
122381009 | 1381 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – requiring more detailed review
122381009 | 1381 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – requiring more detailed review
122384366 | 1382 | Conduct: Initial Review (IR) | 2022-01-06 | Engineering – requiring more detailed review
122384366 | 1382 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – requiring more detailed review
122384366 | 1382 | Conduct: Initial Review (IR) | 2022-01-06 | Engineering – requiring more detailed review
122384366 | 1382 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – requiring more detailed review
122384366 | 1382 | Conduct: Initial Review (IR) | 2022-02-04 | Engineering – requiring more detailed review
122389193 | 1383 | Conduct: Initial Review (IR) | 2022-01-11 | Engineering – requiring more detailed review
122389193 | 1383 | Conduct: Initial Review (IR) | 2022-01-25 | Engineering – requiring more detailed review
122389193 | 1383 | Conduct: Initial Review (IR) | 2022-02-08 | Engineering – requiring more detailed review
122389193 | 1383 | Conduct: Initial Review (IR) | 2022-01-11 | Engineering – requiring more detailed review
122389193 | 1383 | Conduct: Initial Review (IR) | 2022-01-25 | Engineering – requiring more detailed review
122389193 | 1383 | Conduct: Initial Review (IR) | 2022-02-08 | Engineering – requiring more detailed review
122389193 | 1383 | Conduct: Initial Review (IR) | 2022-03-08 | Engineering – requiring more detailed review
122390785 | 1384 | Conduct: Initial Review (IR) | 2021-12-27 | Cus – requirement to provide a response to deficiency notice
122390785 | 1384 | Conduct: Initial Review (IR) | 2022-01-03 | Cus – requirement to provide a response to deficiency notice
122390785 | 1384 | Conduct: Initial Review (IR) | 2022-01-10 | Cus – requirement to provide a response to deficiency notice
122390785 | 1384 | Conduct: Initial Review (IR) | 2022-01-17 | Cus – requirement to provide a response to deficiency notice
122390785 | 1384 | Conduct: Initial Review (IR) | 2022-01-24 | Cus – requirement to provide a response to deficiency notice
122390785 | 1384 | Conduct: Initial Review (IR) | 2022-01-31 | Cus – requirement to provide a response to deficiency notice
122390785 | 1384 | Conduct: Initial Review (IR) | 2021-12-27 | Cus – requirement to provide a response to deficiency notice
122390785 | 1384 | Conduct: Initial Review (IR) | 2022-01-03 | Cus – requirement to provide a response to deficiency notice
122390785 | 1384 | Conduct: Initial Review (IR) | 2022-01-10 | Cus – requirement to provide a response to deficiency notice
122390785 | 1384 | Conduct: Initial Review (IR) | 2022-01-17 | Cus – requirement to provide a response to deficiency notice
122390785 | 1384 | Conduct: Initial Review (IR) | 2022-01-24 | Cus – requirement to provide a response to deficiency notice
122390785 | 1384 | Conduct: Initial Review (IR) | 2022-01-31 | Cus – requirement to provide a response to deficiency notice
122390785 | 1384 | Conduct: Initial Review (IR) | 2022-02-07 | Cus – requirement to provide a response to deficiency notice
122390785 | 1384 | Conduct: Initial Review (IR) | 2022-02-14 | Cus – requirement to provide a response to deficiency notice
122390785 | 1384 | Conduct: Initial Review (IR) | 2022-02-21 | Cus – requirement to provide a response to deficiency notice
122390785 | 1384 | Conduct: Initial Review (IR) | 2022-02-28 | Cus – requirement to provide a response to deficiency notice
122390785 | 1384 | Conduct: Initial Review (IR) | 2022-03-07 | Cus – requirement to provide a response to deficiency notice
122391766 | 1385 | Conduct: Initial Review (IR) | 2022-01-04 | Engineering – requiring more detailed review
122391766 | 1385 | Conduct: Initial Review (IR) | 2022-01-04 | Engineering – requiring more detailed review
122393193 | 1386 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – requiring more detailed review
122393193 | 1386 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – requiring more detailed review
122393193 | 1386 | Conduct: Initial Review (IR) | 2022-02-18 | Engineering – requiring more detailed review
122399798 | 1387 | Conduct: Initial Review (IR) | 2022-02-15 | Engineering – requiring more detailed review
122399798 | 1387 | Conduct: Initial Review (IR) | 2022-02-15 | Engineering – requiring more detailed review
122401791 | 1388 | Conduct: Initial Review (IR) | 2022-01-14 | Engineering – addressing project volume surge
122401791 | 1388 | Conduct: Initial Review (IR) | 2022-01-24 | Engineering – addressing project volume surge
122401791 | 1388 | Conduct: Initial Review (IR) | 2022-01-14 | Engineering – addressing project volume surge
122401791 | 1388 | Conduct: Initial Review (IR) | 2022-01-24 | Engineering – addressing project volume surge
122409453 | 1389 | Conduct: Initial Review (IR) | 2022-01-12 | Customer – requirement to provide corrected information
122409453 | 1389 | Conduct: Initial Review (IR) | 2022-01-26 | Customer – requirement to provide corrected information
122409453 | 1389 | Conduct: Initial Review (IR) | 2022-01-12 | Customer – requirement to provide corrected information
122409453 | 1389 | Conduct: Initial Review (IR) | 2022-01-26 | Customer – requirement to provide corrected information
122409453 | 1389 | Conduct: Supplemental Review (SR) | 2022-03-03 | Engineering – requiring more detailed review
122414877 | 1390 | Conduct: Initial Review (IR) | 2022-01-17 | Engineering – requiring more detailed review
122414877 | 1390 | Conduct: Initial Review (IR) | 2022-02-01 | Engineering – requiring more detailed review
122414877 | 1390 | Conduct: Initial Review (IR) | 2022-03-15 | Engineering – addressing project volume surge
122414877 | 1390 | Conduct: Initial Review (IR) | 2022-01-17 | Engineering – requiring more detailed review
122414877 | 1390 | Conduct: Initial Review (IR) | 2022-02-01 | Engineering – requiring more detailed review
122414877 | 1390 | Conduct: Initial Review (IR) | 2022-02-15 | Engineering – requiring more detailed review
122418632 | 1391 | Conduct: Initial Review (IR) | 2022-02-03 | Engineering – requiring more detailed review
122418632 | 1391 | Conduct: Initial Review (IR) | 2022-02-03 | Engineering – requiring more detailed review
122418632 | 1391 | Conduct: Initial Review (IR) | 2022-02-17 | Engineering – requiring more detailed review
122418632 | 1391 | Conduct: Initial Review (IR) | 2022-02-25 | Engineering – requiring more detailed review
122418632 | 1391 | Conduct: Initial Review (IR) | 2022-03-04 | Engineering – requiring more detailed review
122418632 | 1391 | Conduct: Initial Review (IR) | 2022-03-11 | Engineering – requiring more detailed review
122418632 | 1391 | Conduct: Initial Review (IR) | 2022-03-25 | Engineering – requiring more detailed review
122418632 | 1391 | Conduct: Initial Review (IR) | 2022-04-08 | Engineering – requiring more detailed review
122418632 | 1391 | Conduct: Initial Review (IR) | 2022-04-22 | Engineering – requiring more detailed review
122418762 | 1392 | Conduct: Initial Review (IR) | 2022-01-26 | Engineering – requiring more detailed review
122418762 | 1392 | Conduct: Initial Review (IR) | 2022-01-26 | Engineering – requiring more detailed review
122418762 | 1392 | Conduct: Initial Review (IR) | 2022-02-16 | Engineering – requiring more detailed review
122419192 | 1393 | Conduct: Initial Review (IR) | 2021-12-29 | Engineering – addressing project volume surge
122419192 | 1393 | Conduct: Initial Review (IR) | 2021-12-29 | Engineering – addressing project volume surge
122420366 | 1394 | Conduct: Initial Review (IR) | 2022-01-19 | Engineering – addressing project volume surge
122420366 | 1394 | Conduct: Initial Review (IR) | 2022-01-19 | Engineering – addressing project volume surge
122421728 | 1395 | Conduct: Initial Review (IR) | 2022-01-21 | Engineering – requiring more detailed review
122421728 | 1395 | Conduct: Initial Review (IR) | 2022-01-21 | Engineering – requiring more detailed review
122423461 | 1396 | Conduct: Initial Review (IR) | 2022-01-14 | Engineering – addressing project volume surge
122423461 | 1396 | Conduct: Initial Review (IR) | 2022-01-14 | Engineering – addressing project volume surge
122423677 | 1397 | Conduct: Screens Q and R | 2022-02-08 | Engineering – requiring more detailed review
122423677 | 1397 | Conduct: Screens Q and R | 2022-02-08 | Engineering – requiring more detailed review
122425730 | 1398 | Conduct: Initial Review (IR) | 2022-01-04 | Cus – requirement to provide a response to deficiency notice
122425730 | 1398 | Conduct: Initial Review (IR) | 2022-01-19 | Cus – requirement to provide a response to deficiency notice
122425730 | 1398 | Conduct: Initial Review (IR) | 2022-01-11 | Customer – requirement to provide corrected information
122425730 | 1398 | Conduct: Initial Review (IR) | 2022-01-26 | Customer – requirement to provide corrected information
122425730 | 1398 | Conduct: Initial Review (IR) | 2022-01-04 | Cus – requirement to provide a response to deficiency notice
122425730 | 1398 | Conduct: Initial Review (IR) | 2022-01-19 | Cus – requirement to provide a response to deficiency notice
122425730 | 1398 | Conduct: Initial Review (IR) | 2022-02-24 | Cus – requirement to provide a response to deficiency notice
122425730 | 1398 | Conduct: Initial Review (IR) | 2022-03-10 | Cus – requirement to provide a response to deficiency notice
122425730 | 1398 | Conduct: Initial Review (IR) | 2022-03-17 | Cus – requirement to provide a response to deficiency notice
122425730 | 1398 | Conduct: Initial Review (IR) | 2022-04-14 | Cus – requirement to provide a response to deficiency notice
122425730 | 1398 | Conduct: Initial Review (IR) | 2022-04-28 | Cus – requirement to provide a response to deficiency notice
122425730 | 1398 | Conduct: Initial Review (IR) | 2022-01-11 | Customer – requirement to provide corrected information
122425730 | 1398 | Conduct: Initial Review (IR) | 2022-01-26 | Customer – requirement to provide corrected information
122425730 | 1398 | Conduct: Initial Review (IR) | 2022-02-02 | Customer – requirement to provide corrected information
122425730 | 1398 | Conduct: Initial Review (IR) | 2022-02-09 | Customer – requirement to provide corrected information
122425730 | 1398 | Conduct: Initial Review (IR) | 2022-02-16 | Customer – requirement to provide corrected information
122425730 | 1398 | Conduct: Initial Review (IR) | 2022-03-31 | Engineering – requiring more detailed review
122430318 | 1399 | Conduct: Initial Review (IR) | 2022-01-19 | Engineering – addressing project volume surge
122430318 | 1399 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – addressing project volume surge
122430318 | 1399 | Conduct: Initial Review (IR) | 2022-01-19 | Engineering – addressing project volume surge
122430318 | 1399 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – addressing project volume surge
122431149 | 1400 | Conduct: Initial Review (IR) | 2022-02-08 | Engineering – requiring more detailed review
122431149 | 1400 | Conduct: Initial Review (IR) | 2022-02-08 | Engineering – requiring more detailed review
122431149 | 1400 | Conduct: Initial Review (IR) | 2022-02-22 | Engineering – requiring more detailed review
122431149 | 1400 | Conduct: Initial Review (IR) | 2022-02-25 | Engineering – requiring more detailed review
122438529 | 1401 | Conduct: Initial Review (IR) | 2022-01-18 | Engineering – requiring more detailed review
122438529 | 1401 | Conduct: Initial Review (IR) | 2022-01-18 | Engineering – requiring more detailed review
122443347 | 1402 | Conduct: Initial Review (IR) | 2022-01-07 | Engineering – requiring more detailed review
122443347 | 1402 | Conduct: Initial Review (IR) | 2022-01-07 | Engineering – requiring more detailed review
122444142 | 1403 | Conduct: Initial Review (IR) | 2022-01-18 | Engineering – requiring more detailed review
122444142 | 1403 | Conduct: Initial Review (IR) | 2022-02-08 | Engineering – requiring more detailed review
122444142 | 1403 | Conduct: Initial Review (IR) | 2022-01-18 | Engineering – requiring more detailed review
122444142 | 1403 | Conduct: Initial Review (IR) | 2022-02-08 | Engineering – requiring more detailed review
122444142 | 1403 | Conduct: Initial Review (IR) | 2022-02-23 | Engineering – requiring more detailed review
122444142 | 1403 | Conduct: Initial Review (IR) | 2022-02-25 | Engineering – requiring more detailed review
122445478 | 1404 | Conduct: Initial Review (IR) | 2022-01-03 | Engineering – addressing project volume surge
122445478 | 1404 | Conduct: Initial Review (IR) | 2022-01-03 | Engineering – addressing project volume surge
122447589 | 1405 | Conduct: Initial Review (IR) | 2022-01-24 | Engineering – requiring more detailed review
122447589 | 1405 | Conduct: Initial Review (IR) | 2022-01-31 | Engineering – requiring more detailed review
122447589 | 1405 | Conduct: Initial Review (IR) | 2022-02-24 | Engineering – addressing project volume surge
122447589 | 1405 | Conduct: Initial Review (IR) | 2022-01-24 | Engineering – requiring more detailed review
122447589 | 1405 | Conduct: Initial Review (IR) | 2022-01-31 | Engineering – requiring more detailed review
122447589 | 1405 | Conduct: Initial Review (IR) | 2022-02-14 | Engineering – requiring more detailed review
122447774 | 1406 | Conduct: Initial Review (IR) | 2022-01-18 | Engineering – requiring more detailed review
122447774 | 1406 | Conduct: Initial Review (IR) | 2022-01-18 | Engineering – requiring more detailed review
122447830 | 1407 | Conduct: Initial Review (IR) | 2022-01-17 | Engineering – requiring more detailed review
122447830 | 1407 | Conduct: Initial Review (IR) | 2022-01-31 | Engineering – requiring more detailed review
122447830 | 1407 | Conduct: Initial Review (IR) | 2022-01-17 | Engineering – requiring more detailed review
122447830 | 1407 | Conduct: Initial Review (IR) | 2022-01-31 | Engineering – requiring more detailed review
122447830 | 1407 | Conduct: Initial Review (IR) | 2022-02-07 | Engineering – requiring more detailed review
122447854 | 1408 | Conduct: Supplemental Review (SR) | 2022-02-10 | Engineering – requiring more detailed review
122447854 | 1408 | Conduct: Supplemental Review (SR) | 2022-02-17 | Engineering – addressing project volume surge
122447854 | 1408 | Conduct: Supplemental Review (SR) | 2022-02-10 | Engineering – requiring more detailed review
122447961 | 1409 | Conduct: Initial Review (IR) | 2022-01-21 | Engineering – requiring more detailed review
122447961 | 1409 | Conduct: Initial Review (IR) | 2022-02-04 | Engineering – requiring more detailed review
122447961 | 1409 | Conduct: Initial Review (IR) | 2022-01-21 | Engineering – requiring more detailed review
122447961 | 1409 | Conduct: Initial Review (IR) | 2022-02-04 | Engineering – requiring more detailed review
122447961 | 1409 | Conduct: Initial Review (IR) | 2022-02-18 | Engineering – requiring more detailed review
122447961 | 1409 | Conduct: Initial Review (IR) | 2022-03-14 | Engineering – requiring more detailed review
122449399 | 1410 | Conduct: Initial Review (IR) | 2022-01-19 | Engineering – requiring more detailed review
122449399 | 1410 | Conduct: Initial Review (IR) | 2022-01-19 | Engineering – requiring more detailed review
122449427 | 1411 | Conduct: Screens Q and R | 2022-01-27 | Engineering – requiring more detailed review
122449427 | 1411 | Conduct: Screens Q and R | 2022-01-27 | Engineering – requiring more detailed review
122449427 | 1411 | Conduct: SIS | 2022-04-26 | Engineering – requiring more detailed review
122449600 | 1412 | Conduct: Initial Review (IR) | 2022-01-19 | Engineering – requiring more detailed review
122449600 | 1412 | Conduct: Initial Review (IR) | 2022-01-19 | Engineering – requiring more detailed review
122453826 | 1413 | Conduct: Initial Review (IR) | 2022-01-25 | Engineering – requiring more detailed review
122453826 | 1413 | Conduct: Initial Review (IR) | 2022-02-15 | Engineering – requiring more detailed review
122453826 | 1413 | Conduct: Initial Review (IR) | 2022-01-25 | Engineering – requiring more detailed review
122453826 | 1413 | Conduct: Initial Review (IR) | 2022-02-15 | Engineering – requiring more detailed review
122455318 | 1414 | Conduct: Initial Review (IR) | 2022-01-13 | Engineering – requiring more detailed review
122455318 | 1414 | Conduct: Initial Review (IR) | 2022-01-21 | Engineering – requiring more detailed review
122455318 | 1414 | Conduct: Initial Review (IR) | 2022-01-13 | Engineering – requiring more detailed review
122455318 | 1414 | Conduct: Initial Review (IR) | 2022-01-21 | Engineering – requiring more detailed review
122456319 | 1415 | Conduct: Initial Review (IR) | 2022-01-25 | Engineering – requiring more detailed review
122456319 | 1415 | Conduct: Initial Review (IR) | 2022-02-08 | Engineering – requiring more detailed review
122456319 | 1415 | Conduct: Initial Review (IR) | 2022-01-25 | Engineering – requiring more detailed review
122456319 | 1415 | Conduct: Initial Review (IR) | 2022-02-08 | Engineering – requiring more detailed review
122456319 | 1415 | Conduct: Initial Review (IR) | 2022-03-08 | Engineering – requiring more detailed review
122456319 | 1415 | Conduct: Initial Review (IR) | 2022-03-31 | Project Management – addressing a human error
122456683 | 1416 | Conduct: Initial Review (IR) | 2022-01-17 | Engineering – requiring more detailed review
122456683 | 1416 | Conduct: Initial Review (IR) | 2022-02-01 | Engineering – requiring more detailed review
122456683 | 1416 | Conduct: Initial Review (IR) | 2022-03-16 | Customer – requirement to provide corrected information
122456683 | 1416 | Conduct: Initial Review (IR) | 2022-03-30 | Customer – requirement to provide corrected information
122456683 | 1416 | Conduct: Initial Review (IR) | 2022-04-08 | Customer – requirement to provide corrected information
122456683 | 1416 | Conduct: Initial Review (IR) | 2022-04-22 | Customer – requirement to provide corrected information
122456683 | 1416 | Conduct: Initial Review (IR) | 2022-01-17 | Engineering – requiring more detailed review
122456683 | 1416 | Conduct: Initial Review (IR) | 2022-02-01 | Engineering – requiring more detailed review
122456683 | 1416 | Conduct: Initial Review (IR) | 2022-02-16 | Engineering – requiring more detailed review
122456683 | 1416 | Conduct: Initial Review (IR) | 2022-03-02 | Engineering – requiring more detailed review
122456753 | 1417 | Conduct: Initial Review (IR) | 2022-01-25 | Engineering – requiring more detailed review
122456753 | 1417 | Conduct: Initial Review (IR) | 2022-01-25 | Engineering – requiring more detailed review
122458202 | 1418 | Conduct: Initial Review (IR) | 2022-02-02 | Engineering – requiring more detailed review
122458202 | 1418 | Conduct: Initial Review (IR) | 2022-02-02 | Engineering – requiring more detailed review
122458202 | 1418 | Conduct: Initial Review (IR) | 2022-02-11 | Engineering – requiring more detailed review
122460351 | 1419 | Conduct: Initial Review (IR) | 2022-01-14 | Engineering – addressing project volume surge
122460351 | 1419 | Conduct: Initial Review (IR) | 2022-01-14 | Engineering – addressing project volume surge
122461054 | 1420 | Conduct: Initial Review (IR) | 2022-01-27 | Cus – requirement to provide a response to deficiency notice
122461054 | 1420 | Conduct: Initial Review (IR) | 2022-01-27 | Cus – requirement to provide a response to deficiency notice
122461188 | 1421 | Conduct: Initial Review (IR) | 2022-01-27 | Cus – requirement to provide a response to deficiency notice
122461188 | 1421 | Conduct: Initial Review (IR) | 2022-01-27 | Cus – requirement to provide a response to deficiency notice
122462191 | 1422 | Conduct: Initial Review (IR) | 2022-01-27 | Cus – requirement to provide a response to deficiency notice
122462191 | 1422 | Conduct: Initial Review (IR) | 2022-01-27 | Cus – requirement to provide a response to deficiency notice
122462263 | 1423 | Conduct: Initial Review (IR) | 2022-01-27 | Cus – requirement to provide a response to deficiency notice
122462263 | 1423 | Conduct: Initial Review (IR) | 2022-01-27 | Cus – requirement to provide a response to deficiency notice
122473450 | 1424 | Conduct: Initial Review (IR) | 2022-02-01 | Engineering – addressing project volume surge
122473450 | 1424 | Conduct: Initial Review (IR) | 2022-02-01 | Engineering – addressing project volume surge
122473450 | 1424 | Conduct: Initial Review (IR) | 2022-02-21 | Engineering – requiring more detailed review
122473450 | 1424 | Conduct: Initial Review (IR) | 2022-02-25 | Engineering – requiring more detailed review
122474322 | 1425 | Conduct: Initial Review (IR) | 2022-01-25 | Engineering – requiring more detailed review
122474322 | 1425 | Conduct: Initial Review (IR) | 2022-01-25 | Engineering – requiring more detailed review
122475090 | 1426 | Conduct: Initial Review (IR) | 2022-01-28 | Project Management - addressing project volume surge
122475090 | 1426 | Conduct: Initial Review (IR) | 2022-01-28 | Project Management - addressing project volume surge
122478327 | 1427 | Conduct: Initial Review (IR) | 2022-01-25 | Customer – requirement to provide corrected information
122478327 | 1427 | Conduct: Initial Review (IR) | 2022-01-11 | Engineering – addressing project volume surge
122478327 | 1427 | Conduct: Initial Review (IR) | 2022-01-28 | Cus – requirement to provide a response to deficiency notice
122478327 | 1427 | Conduct: Initial Review (IR) | 2022-01-25 | Customer – requirement to provide corrected information
122478327 | 1427 | Conduct: Initial Review (IR) | 2022-01-11 | Engineering – addressing project volume surge
122478327 | 1427 | Conduct: Initial Review (IR) | 2022-02-14 | Engineering – addressing project volume surge
122478327 | 1427 | Conduct: Initial Review (IR) | 2022-02-04 | Engineering – requiring more detailed review
122481053 | 1428 | Conduct: Initial Review (IR) | 2022-02-03 | Engineering – requiring more detailed review
122481053 | 1428 | Conduct: Initial Review (IR) | 2022-02-03 | Engineering – requiring more detailed review
122481170 | 1429 | Conduct: Initial Review (IR) | 2022-01-21 | Engineering – requiring more detailed review
122481170 | 1429 | Conduct: Initial Review (IR) | 2022-02-10 | Engineering – requiring more detailed review
122481170 | 1429 | Conduct: Initial Review (IR) | 2022-01-21 | Engineering – requiring more detailed review
122481170 | 1429 | Conduct: Initial Review (IR) | 2022-02-10 | Engineering – requiring more detailed review
122481691 | 1430 | Conduct: Initial Review (IR) | 2022-02-01 | Cus – requirement to provide a response to deficiency notice
122481691 | 1430 | Conduct: Initial Review (IR) | 2022-02-01 | Cus – requirement to provide a response to deficiency notice
122481691 | 1430 | Conduct: Initial Review (IR) | 2022-03-02 | Cus – requirement to provide a response to deficiency notice
122481691 | 1430 | Conduct: Initial Review (IR) | 2022-02-15 | Customer – requirement to provide corrected information
122485208 | 1431 | Conduct: Initial Review (IR) | 2022-02-07 | Engineering – requiring more detailed review
122485208 | 1431 | Conduct: Initial Review (IR) | 2022-02-07 | Engineering – requiring more detailed review
122485880 | 1432 | Conduct: Initial Review (IR) | 2022-02-11 | Engineering – requiring more detailed review
122485880 | 1432 | Conduct: Initial Review (IR) | 2022-02-11 | Engineering – requiring more detailed review
122486138 | 1433 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – requiring more detailed review
122486138 | 1433 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – requiring more detailed review
122486138 | 1433 | Conduct: Initial Review (IR) | 2022-02-15 | Engineering – requiring more detailed review
122487225 | 1434 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – requiring more detailed review
122487225 | 1434 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – requiring more detailed review
122487225 | 1434 | Conduct: Initial Review (IR) | 2022-02-18 | Engineering – requiring more detailed review
122487225 | 1434 | Conduct: Initial Review (IR) | 2022-02-28 | Engineering – requiring more detailed review
122492548 | 1435 | Conduct: Initial Review (IR) | 2022-02-09 | Customer – requirement to provide corrected information
122492548 | 1435 | Conduct: Initial Review (IR) | 2022-02-09 | Customer – requirement to provide corrected information
122492548 | 1435 | Conduct: Initial Review (IR) | 2022-03-02 | Customer – requirement to provide corrected information
122492548 | 1435 | Conduct: Initial Review (IR) | 2022-03-22 | Customer – requirement to provide corrected information
122492548 | 1435 | Conduct: Initial Review (IR) | 2022-04-12 | Customer – requirement to provide corrected information
122502997 | 1436 | Conduct: Screens Q and R | 2022-01-26 | Engineering – addressing project volume surge
122502997 | 1436 | Conduct: Screens Q and R | 2022-01-26 | Engineering – addressing project volume surge
122502997 | 1436 | Conduct: SIS | 2022-05-04 | Engineering – addressing project volume surge
122505677 | 1437 | Conduct: Initial Review (IR) | 2022-02-01 | Engineering – requiring more detailed review
122505677 | 1437 | Conduct: Initial Review (IR) | 2022-02-01 | Engineering – requiring more detailed review
122505677 | 1437 | Conduct: Initial Review (IR) | 2022-02-15 | Engineering – requiring more detailed review
122505677 | 1437 | Conduct: Initial Review (IR) | 2022-02-23 | Engineering – requiring more detailed review
122509911 | 1438 | Conduct: Initial Review (IR) | 2022-02-15 | Engineering – requiring more detailed review
122509911 | 1438 | Conduct: Initial Review (IR) | 2022-02-15 | Engineering – requiring more detailed review
122512792 | 1439 | Conduct: Initial Review (IR) | 2022-02-01 | Cus – requirement to provide a response to deficiency notice
122512792 | 1439 | Conduct: Initial Review (IR) | 2022-02-01 | Cus – requirement to provide a response to deficiency notice
122514852 | 1440 | Conduct: Initial Review (IR) | 2022-02-08 | Engineering – requiring more detailed review
122514852 | 1440 | Conduct: Initial Review (IR) | 2022-02-22 | Cus – requirement to provide a response to deficiency notice
122514852 | 1440 | Conduct: Initial Review (IR) | 2022-03-22 | Cus – requirement to provide a response to deficiency notice
122514852 | 1440 | Conduct: Initial Review (IR) | 2022-02-08 | Engineering – requiring more detailed review
122522670 | 1441 | Conduct: Initial Review (IR) | 2022-02-10 | Customer – requirement to provide corrected information
122522670 | 1441 | Conduct: Initial Review (IR) | 2022-02-10 | Customer – requirement to provide corrected information
122530741 | 1442 | Conduct: Initial Review (IR) | 2022-01-28 | Engineering – addressing project volume surge
120529036 | 1443 | Conduct: Initial Review (IR) | 2022-03-09 | Cus – requirement to provide a response to deficiency notice
120529036 | 1443 | Conduct: Initial Review (IR) | 2022-03-25 | Engineering – addressing project volume surge
120529036 | 1443 | Conduct: Initial Review (IR) | 2022-04-01 | Engineering – addressing project volume surge
120529036 | 1443 | Conduct: Initial Review (IR) | 2022-04-08 | Engineering – addressing project volume surge
120529036 | 1443 | Conduct: Initial Review (IR) | 2022-05-06 | Engineering – requiring more detailed review
120529038 | 1444 | Conduct: Initial Review (IR) | 2022-03-09 | Cus – requirement to provide a response to deficiency notice
120529038 | 1444 | Conduct: Initial Review (IR) | 2022-05-06 | Cus – requirement to provide a response to deficiency notice
120529038 | 1444 | Conduct: Initial Review (IR) | 2022-03-25 | Engineering – addressing project volume surge
120529038 | 1444 | Conduct: Initial Review (IR) | 2022-04-01 | Engineering – addressing project volume surge
120529038 | 1444 | Conduct: Initial Review (IR) | 2022-04-08 | Engineering – addressing project volume surge
121864242 | 1445 | Conduct: Initial Review (IR) | 2022-03-23 | Cus – requirement to provide a response to deficiency notice
122357937 | 1446 | Conduct: Initial Review (IR) | 2022-05-06 | Cus – requirement to provide a response to deficiency notice
122357937 | 1446 | Conduct: Initial Review (IR) | 2022-03-25 | Customer – requirement to provide corrected information
122357937 | 1446 | Conduct: Initial Review (IR) | 2022-04-15 | Customer – requirement to provide corrected information
122360302 | 1447 | Conduct: Initial Review (IR) | 2022-03-02 | Cus – requirement to provide a response to deficiency notice
122360302 | 1447 | Conduct: Initial Review (IR) | 2022-03-16 | Customer – requirement to provide corrected information
122360302 | 1447 | Conduct: Initial Review (IR) | 2022-03-30 | Customer – requirement to provide corrected information
122360302 | 1447 | Conduct: Initial Review (IR) | 2022-04-08 | Customer – requirement to provide corrected information
122360302 | 1447 | Conduct: Initial Review (IR) | 2022-04-22 | Customer – requirement to provide corrected information
122448335 | 1448 | Conduct: Initial Review (IR) | 2022-02-25 | Cus – requirement to provide a response to deficiency notice
122448335 | 1448 | Conduct: Initial Review (IR) | 2022-03-15 | Cus – requirement to provide a response to deficiency notice
122448335 | 1448 | Conduct: Initial Review (IR) | 2022-03-31 | Cus – requirement to provide a response to deficiency notice
122448335 | 1448 | Conduct: Initial Review (IR) | 2022-04-21 | Cus – requirement to provide a response to deficiency notice
122449792 | 1449 | Conduct: Initial Review (IR) | 2022-02-24 | Cus – requirement to provide a response to deficiency notice
122449792 | 1449 | Conduct: Initial Review (IR) | 2022-03-03 | Cus – requirement to provide a response to deficiency notice
122449792 | 1449 | Conduct: Initial Review (IR) | 2022-03-11 | Engineering – requiring more detailed review
122449792 | 1449 | Conduct: Initial Review (IR) | 2022-03-18 | Engineering – requiring more detailed review
122453709 | 1450 | Conduct: Initial Review (IR) | 2022-03-11 | Cus – requirement to provide a response to deficiency notice
122453709 | 1450 | Conduct: Initial Review (IR) | 2022-02-25 | Engineering – requiring more detailed review
122453709 | 1450 | Conduct: Initial Review (IR) | 2022-03-18 | Engineering – requiring more detailed review
122458061 | 1451 | Conduct: Initial Review (IR) | 2022-03-28 | Cus – requirement to provide a response to deficiency notice
122458061 | 1451 | Conduct: Initial Review (IR) | 2022-04-29 | Engineering – requiring more detailed review
122458072 | 1452 | Conduct: Initial Review (IR) | 2022-02-15 | Cus – requirement to provide a response to deficiency notice
122461737 | 1453 | Conduct: Initial Review (IR) | 2022-04-12 | Cus – requirement to provide a response to deficiency notice
122461737 | 1453 | Conduct: Initial Review (IR) | 2022-05-03 | Cus – requirement to provide a response to deficiency notice
122461885 | 1454 | Conduct: Initial Review (IR) | 2022-02-09 | Cus – requirement to provide a response to deficiency notice
122461885 | 1454 | Conduct: Initial Review (IR) | 2022-02-16 | Cus – requirement to provide a response to deficiency notice
122461885 | 1454 | Conduct: Initial Review (IR) | 2022-02-02 | Customer – requirement to provide corrected information
122461885 | 1454 | Conduct: Initial Review (IR) | 2022-03-03 | Engineering – requiring more detailed review
122462225 | 1455 | Conduct: Initial Review (IR) | 2022-03-01 | Cus – requirement to provide a response to deficiency notice
122462225 | 1455 | Conduct: Initial Review (IR) | 2022-03-08 | Cus – requirement to provide a response to deficiency notice
122462225 | 1455 | Conduct: Initial Review (IR) | 2022-03-29 | Cus – requirement to provide a response to deficiency notice
122462225 | 1455 | Conduct: Initial Review (IR) | 2022-04-12 | Cus – requirement to provide a response to deficiency notice
122462225 | 1455 | Conduct: Initial Review (IR) | 2022-04-26 | Cus – requirement to provide a response to deficiency notice
122462225 | 1455 | Conduct: Initial Review (IR) | 2022-02-22 | Customer – requirement to provide corrected information
122462225 | 1455 | Conduct: Initial Review (IR) | 2022-03-15 | Engineering – requiring more detailed review
122476350 | 1456 | Conduct: Initial Review (IR) | 2022-03-14 | Cus – requirement to provide a response to deficiency notice
122476350 | 1456 | Conduct: Initial Review (IR) | 2022-03-28 | Customer – requirement to provide corrected information
122476350 | 1456 | Conduct: Initial Review (IR) | 2022-04-18 | Customer – requirement to provide corrected information
122476350 | 1456 | Conduct: Initial Review (IR) | 2022-05-02 | Customer – requirement to provide corrected information
122476375 | 1457 | Conduct: Initial Review (IR) | 2022-03-24 | Cus – requirement to provide a response to deficiency notice
122476375 | 1457 | Conduct: Initial Review (IR) | 2022-03-03 | Customer – requirement to provide corrected information
122476375 | 1457 | Conduct: Initial Review (IR) | 2022-04-14 | Customer – requirement to provide corrected information
122476375 | 1457 | Conduct: Initial Review (IR) | 2022-04-28 | Customer – requirement to provide corrected information
122481934 | 1458 | Conduct: Initial Review (IR) | 2022-04-14 | Cus – requirement to provide a response to deficiency notice
122481934 | 1458 | Conduct: Initial Review (IR) | 2022-05-05 | Cus – requirement to provide a response to deficiency notice
122481934 | 1458 | Conduct: Initial Review (IR) | 2022-03-24 | Customer – requirement to provide corrected information
122483483 | 1459 | Conduct: Initial Review (IR) | 2022-03-23 | Cus – requirement to provide a response to deficiency notice
122483483 | 1459 | Conduct: Initial Review (IR) | 2022-02-23 | Engineering – requiring more detailed review
122483483 | 1459 | Conduct: Initial Review (IR) | 2022-03-02 | Engineering – requiring more detailed review
122483483 | 1459 | Conduct: Initial Review (IR) | 2022-04-13 | Engineering – requiring more detailed review
122483483 | 1459 | Conduct: Initial Review (IR) | 2022-04-20 | Engineering – requiring more detailed review
122498451 | 1460 | Conduct: Initial Review (IR) | 2022-02-14 | Cus – requirement to provide a response to deficiency notice
122498451 | 1460 | Conduct: Initial Review (IR) | 2022-02-28 | Cus – requirement to provide a response to deficiency notice
122498451 | 1460 | Conduct: Initial Review (IR) | 2022-03-07 | Cus – requirement to provide a response to deficiency notice
122498451 | 1460 | Conduct: Initial Review (IR) | 2022-03-14 | Cus – requirement to provide a response to deficiency notice
122498451 | 1460 | Conduct: Initial Review (IR) | 2022-03-21 | Cus – requirement to provide a response to deficiency notice
122498451 | 1460 | Conduct: Initial Review (IR) | 2022-03-28 | Cus – requirement to provide a response to deficiency notice
122498451 | 1460 | Conduct: Initial Review (IR) | 2022-04-04 | Cus – requirement to provide a response to deficiency notice
122498451 | 1460 | Conduct: Initial Review (IR) | 2022-04-11 | Cus – requirement to provide a response to deficiency notice
122498451 | 1460 | Conduct: Initial Review (IR) | 2022-04-18 | Cus – requirement to provide a response to deficiency notice
122498451 | 1460 | Conduct: Initial Review (IR) | 2022-04-25 | Cus – requirement to provide a response to deficiency notice
122503040 | 1461 | Conduct: Initial Review (IR) | 2022-03-24 | Cus – requirement to provide a response to deficiency notice
122504181 | 1462 | Conduct: Initial Review (IR) | 2022-03-10 | Cus – requirement to provide a response to deficiency notice
122504181 | 1462 | Conduct: Initial Review (IR) | 2022-02-16 | Engineering – requiring more detailed review
122504181 | 1462 | Conduct: Initial Review (IR) | 2022-03-03 | Engineering – requiring more detailed review
122504181 | 1462 | Conduct: Initial Review (IR) | 2022-03-17 | Engineering – requiring more detailed review
122504181 | 1462 | Conduct: Initial Review (IR) | 2022-04-07 | Engineering – requiring more detailed review
122505443 | 1463 | Conduct: Initial Review (IR) | 2022-03-11 | Cus – requirement to provide a response to deficiency notice
122505443 | 1463 | Conduct: Initial Review (IR) | 2022-03-18 | Cus – requirement to provide a response to deficiency notice
122505443 | 1463 | Conduct: Initial Review (IR) | 2022-04-01 | Engineering – requiring more detailed review
122505443 | 1463 | Conduct: Initial Review (IR) | 2022-04-15 | Engineering – requiring more detailed review
122505443 | 1463 | Conduct: Initial Review (IR) | 2022-04-29 | Engineering – requiring more detailed review
122506555 | 1464 | Conduct: Initial Review (IR) | 2022-03-14 | Cus – requirement to provide a response to deficiency notice
122506555 | 1464 | Conduct: Initial Review (IR) | 2022-03-31 | Customer – requirement to provide corrected information
122506555 | 1464 | Conduct: Initial Review (IR) | 2022-04-20 | Customer – requirement to provide corrected information
122511738 | 1465 | Conduct: Initial Review (IR) | 2022-03-14 | Cus – requirement to provide a response to deficiency notice
122511738 | 1465 | Conduct: Initial Review (IR) | 2022-03-28 | Customer – requirement to provide corrected information
122511738 | 1465 | Conduct: Initial Review (IR) | 2022-04-11 | Customer – requirement to provide corrected information
122511738 | 1465 | Conduct: Initial Review (IR) | 2022-02-28 | Engineering – requiring more detailed review
122512311 | 1466 | Conduct: Initial Review (IR) | 2022-02-25 | Cus – requirement to provide a response to deficiency notice
122512311 | 1466 | Conduct: Initial Review (IR) | 2022-03-25 | Customer – requirement to provide corrected information
122512311 | 1466 | Conduct: Initial Review (IR) | 2022-04-06 | Customer – requirement to provide corrected information
122512311 | 1466 | Conduct: Initial Review (IR) | 2022-04-22 | Customer – requirement to provide corrected information
122512311 | 1466 | Conduct: Initial Review (IR) | 2022-03-11 | Engineering – requiring more detailed review
122512746 | 1467 | Conduct: Initial Review (IR) | 2022-03-29 | Cus – requirement to provide a response to deficiency notice
122512746 | 1467 | Conduct: Initial Review (IR) | 2022-04-12 | Cus – requirement to provide a response to deficiency notice
122512746 | 1467 | Conduct: Initial Review (IR) | 2022-04-26 | Engineering – requiring more detailed review
122512747 | 1468 | Conduct: Initial Review (IR) | 2022-02-21 | Cus – requirement to provide a response to deficiency notice
122512747 | 1468 | Conduct: Initial Review (IR) | 2022-03-08 | Cus – requirement to provide a response to deficiency notice
122512879 | 1469 | Conduct: Initial Review (IR) | 2022-02-21 | Cus – requirement to provide a response to deficiency notice
122512913 | 1470 | Conduct: Initial Review (IR) | 2022-03-01 | Cus – requirement to provide a response to deficiency notice
122512913 | 1470 | Conduct: Initial Review (IR) | 2022-03-15 | Cus – requirement to provide a response to deficiency notice
122512918 | 1471 | Conduct: Initial Review (IR) | 2022-02-21 | Cus – requirement to provide a response to deficiency notice
122513083 | 1472 | Conduct: Initial Review (IR) | 2022-03-17 | Cus – requirement to provide a response to deficiency notice
122521904 | 1473 | Conduct: Initial Review (IR) | 2022-02-02 | Cus – requirement to provide a response to deficiency notice
122521904 | 1473 | Conduct: Initial Review (IR) | 2022-03-02 | Cus – requirement to provide a response to deficiency notice
122521904 | 1473 | Conduct: Supplemental Review (SR) | 2022-03-29 | Engineering – requiring more detailed review
122521904 | 1473 | Conduct: Supplemental Review (SR) | 2022-04-05 | Engineering – requiring more detailed review
122521904 | 1473 | Conduct: Supplemental Review (SR) | 2022-04-12 | Engineering – requiring more detailed review
122523440 | 1474 | Conduct: Initial Review (IR) | 2022-05-06 | Cus – requirement to provide a response to deficiency notice
122523794 | 1475 | Conduct: Initial Review (IR) | 2022-04-14 | Cus – requirement to provide a response to deficiency notice
122523855 | 1476 | Conduct: Initial Review (IR) | 2022-02-09 | Cus – requirement to provide a response to deficiency notice
122523855 | 1476 | Conduct: Initial Review (IR) | 2022-03-02 | Cus – requirement to provide a response to deficiency notice
122523855 | 1476 | Conduct: Initial Review (IR) | 2022-03-08 | Customer – requirement to provide corrected information
122523998 | 1477 | Conduct: Initial Review (IR) | 2022-04-18 | Cus – requirement to provide a response to deficiency notice
122523998 | 1477 | Conduct: Initial Review (IR) | 2022-03-28 | Engineering – requiring more detailed review
122523998 | 1477 | Conduct: Initial Review (IR) | 2022-05-09 | Engineering – requiring more detailed review
122526121 | 1478 | Conduct: Initial Review (IR) | 2022-03-02 | Cus – requirement to provide a response to deficiency notice
122533579 | 1479 | Conduct: Initial Review (IR) | 2022-02-11 | Cus – requirement to provide a response to deficiency notice
122533579 | 1479 | Conduct: Initial Review (IR) | 2022-02-18 | Cus – requirement to provide a response to deficiency notice
122533579 | 1479 | Conduct: Initial Review (IR) | 2022-02-28 | Cus – requirement to provide a response to deficiency notice
122533579 | 1479 | Conduct: Initial Review (IR) | 2022-03-07 | Cus – requirement to provide a response to deficiency notice
122533579 | 1479 | Conduct: Initial Review (IR) | 2022-03-14 | Cus – requirement to provide a response to deficiency notice
122533579 | 1479 | Conduct: Initial Review (IR) | 2022-03-28 | Cus – requirement to provide a response to deficiency notice
122545527 | 1480 | Conduct: Initial Review (IR) | 2022-03-28 | Cus – requirement to provide a response to deficiency notice
122545527 | 1480 | Conduct: Initial Review (IR) | 2022-04-18 | Cus – requirement to provide a response to deficiency notice
122563740 | 1481 | Conduct: Initial Review (IR) | 2022-05-10 | Cus – requirement to provide a response to deficiency notice
122602210 | 1482 | Conduct: Initial Review (IR) | 2022-04-20 | Cus – requirement to provide a response to deficiency notice
122602210 | 1482 | Conduct: Initial Review (IR) | 2022-04-13 | Engineering – requiring more detailed review
122625393 | 1483 | Conduct: Initial Review (IR) | 2022-02-18 | Cus – requirement to provide a response to deficiency notice
122625704 | 1484 | Conduct: Initial Review (IR) | 2022-04-11 | Cus – requirement to provide a response to deficiency notice
122625704 | 1484 | Conduct: Initial Review (IR) | 2022-04-25 | Engineering – requiring more detailed review
122856030 | 1485 | Conduct: Initial Review (IR) | 2022-03-23 | Cus – requirement to provide a response to deficiency notice
122856030 | 1485 | Conduct: Initial Review (IR) | 2022-04-13 | Cus – requirement to provide a response to deficiency notice
122856030 | 1485 | Conduct: Initial Review (IR) | 2022-05-04 | Cus – requirement to provide a response to deficiency notice
122857106 | 1486 | Conduct: Initial Review (IR) | 2022-04-13 | Cus – requirement to provide a response to deficiency notice
122857106 | 1486 | Conduct: Initial Review (IR) | 2022-05-04 | Cus – requirement to provide a response to deficiency notice
122857106 | 1486 | Conduct: Initial Review (IR) | 2022-03-23 | Customer – requesting an extension
122880394 | 1487 | Conduct: Initial Review (IR) | 2022-04-29 | Cus – requirement to provide a response to deficiency notice
122881515 | 1488 | Conduct: Initial Review (IR) | 2022-04-27 | Cus – requirement to provide a response to deficiency notice
122927327 | 1489 | Conduct: Initial Review (IR) | 2022-04-13 | Cus – requirement to provide a response to deficiency notice
122927327 | 1489 | Conduct: Initial Review (IR) | 2022-05-04 | Cus – requirement to provide a response to deficiency notice
122927327 | 1489 | Conduct: Initial Review (IR) | 2022-03-23 | Customer – requesting an extension
122927341 | 1490 | Conduct: Initial Review (IR) | 2022-03-23 | Cus – requirement to provide a response to deficiency notice
122927341 | 1490 | Conduct: Initial Review (IR) | 2022-04-13 | Cus – requirement to provide a response to deficiency notice
122927341 | 1490 | Conduct: Initial Review (IR) | 2022-05-04 | Cus – requirement to provide a response to deficiency notice
122948257 | 1491 | Conduct: Initial Review (IR) | 2022-04-06 | Cus – requirement to provide a response to deficiency notice
122948257 | 1491 | Conduct: Initial Review (IR) | 2022-04-29 | Cus – requirement to provide a response to deficiency notice
122966865 | 1492 | Conduct: Initial Review (IR) | 2022-04-15 | Cus – requirement to provide a response to deficiency notice
122969937 | 1493 | Conduct: Initial Review (IR) | 2022-04-08 | Cus – requirement to provide a response to deficiency notice
122969937 | 1493 | Conduct: Initial Review (IR) | 2022-04-15 | Cus – requirement to provide a response to deficiency notice
122969937 | 1493 | Conduct: Initial Review (IR) | 2022-04-22 | Cus – requirement to provide a response to deficiency notice
122993764 | 1494 | Conduct: Initial Review (IR) | 2022-04-15 | Cus – requirement to provide a response to deficiency notice
122994148 | 1495 | Conduct: Initial Review (IR) | 2022-04-29 | Cus – requirement to provide a response to deficiency notice
123001266 | 1496 | Conduct: Initial Review (IR) | 2022-03-22 | Cus – requirement to provide a response to deficiency notice
123001266 | 1496 | Conduct: Initial Review (IR) | 2022-03-29 | Cus – requirement to provide a response to deficiency notice
123001266 | 1496 | Conduct: Initial Review (IR) | 2022-04-05 | Cus – requirement to provide a response to deficiency notice
123001266 | 1496 | Conduct: Initial Review (IR) | 2022-04-12 | Cus – requirement to provide a response to deficiency notice
123002694 | 1497 | Conduct: Initial Review (IR) | 2022-04-25 | Cus – requirement to provide a response to deficiency notice
123005597 | 1498 | Conduct: Initial Review (IR) | 2022-04-25 | Cus – requirement to provide a response to deficiency notice
123005672 | 1499 | Conduct: Initial Review (IR) | 2022-04-25 | Cus – requirement to provide a response to deficiency notice
123005722 | 1500 | Conduct: Initial Review (IR) | 2022-04-25 | Cus – requirement to provide a response to deficiency notice
123037498 | 1501 | Conduct: Initial Review (IR) | 2022-03-29 | Cus – requirement to provide a response to deficiency notice
123037498 | 1501 | Conduct: Initial Review (IR) | 2022-04-05 | Cus – requirement to provide a response to deficiency notice
123037498 | 1501 | Conduct: Initial Review (IR) | 2022-04-12 | Cus – requirement to provide a response to deficiency notice
123037498 | 1501 | Conduct: Initial Review (IR) | 2022-04-19 | Cus – requirement to provide a response to deficiency notice
123054326 | 1502 | Conduct: Initial Review (IR) | 2022-04-29 | Cus – requirement to provide a response to deficiency notice
122623481 | 1503 | Conduct: Screens Q and R | 2022-05-05 | Cus – requirement to provide a response to deficiency notice
122554853 | 1504 | Tender Draft IA | 2022-03-31 | Cus – requirement to provide a response to deficiency notice
122582723 | 1505 | Tender Draft IA | 2022-03-31 | Cus – requirement to provide a response to deficiency notice
122626504 | 1506 | Tender Draft IA | 2022-03-28 | Cus – requirement to provide a response to deficiency notice
122482704 | 1507 | Conduct: Initial Review (IR) | 2022-05-20 | Customer – requesting an extension
122482704 | 1507 | Conduct: Initial Review (IR) | 2022-04-15 | Engineering – requiring more detailed review
122284822 | 1508 | Conduct: Initial Review (IR) | 2022-04-05 | Customer – requirement to provide corrected information
122341708 | 1509 | Conduct: Initial Review (IR) | 2022-02-25 | Customer – requirement to provide corrected information
122341708 | 1509 | Conduct: Initial Review (IR) | 2022-03-25 | Engineering – addressing project volume surge
122341708 | 1509 | Conduct: Initial Review (IR) | 2022-03-04 | Engineering – requiring more detailed review
122379318 | 1510 | Conduct: Initial Review (IR) | 2022-03-08 | Customer – requirement to provide corrected information
122379318 | 1510 | Conduct: Initial Review (IR) | 2022-03-22 | Engineering – requiring more detailed review
122379318 | 1510 | Conduct: Initial Review (IR) | 2022-03-15 | Project Management – requiring more detailed review
122458016 | 1511 | Conduct: Initial Review (IR) | 2022-04-04 | Customer – requirement to provide corrected information
122458016 | 1511 | Conduct: Initial Review (IR) | 2022-04-25 | Customer – requirement to provide corrected information
122460118 | 1512 | Conduct: Initial Review (IR) | 2022-04-28 | Customer – requirement to provide corrected information
122476517 | 1513 | Conduct: Initial Review (IR) | 2022-03-02 | Customer – requirement to provide corrected information
122476517 | 1513 | Conduct: Initial Review (IR) | 2022-02-17 | Engineering – requiring more detailed review
122476517 | 1513 | Conduct: Initial Review (IR) | 2022-03-10 | Engineering – requiring more detailed review
122476517 | 1513 | Conduct: Initial Review (IR) | 2022-03-17 | Engineering – requiring more detailed review
122476573 | 1514 | Conduct: Initial Review (IR) | 2022-02-18 | Customer – requirement to provide corrected information
122482424 | 1515 | Conduct: Initial Review (IR) | 2022-03-10 | Customer – requirement to provide corrected information
122482861 | 1516 | Conduct: Initial Review (IR) | 2022-03-03 | Customer – requirement to provide corrected information
122482861 | 1516 | Conduct: Initial Review (IR) | 2022-03-24 | Customer – requirement to provide corrected information
122482861 | 1516 | Conduct: Initial Review (IR) | 2022-04-07 | Customer – requirement to provide corrected information
122482861 | 1516 | Conduct: Initial Review (IR) | 2022-04-28 | Customer – requirement to provide corrected information
122482861 | 1516 | Conduct: Initial Review (IR) | 2022-02-11 | Engineering – requiring more detailed review
122484497 | 1517 | Conduct: Initial Review (IR) | 2022-04-15 | Customer – requirement to provide corrected information
122484497 | 1517 | Conduct: Initial Review (IR) | 2022-03-17 | Engineering – requiring more detailed review
122484497 | 1517 | Conduct: Initial Review (IR) | 2022-05-06 | Project Management – addressing a human error
122485081 | 1518 | Conduct: Initial Review (IR) | 2022-03-31 | Customer – requirement to provide corrected information
122485081 | 1518 | Conduct: Initial Review (IR) | 2022-04-28 | Customer – requirement to provide corrected information
122486570 | 1519 | Conduct: Initial Review (IR) | 2022-03-28 | Customer – requirement to provide corrected information
122510002 | 1520 | Conduct: Initial Review (IR) | 2022-03-01 | Customer – requirement to provide corrected information
122510002 | 1520 | Conduct: Initial Review (IR) | 2022-03-17 | Customer – requirement to provide corrected information
122547603 | 1521 | Conduct: Initial Review (IR) | 2022-04-29 | Customer – requirement to provide corrected information
122547603 | 1521 | Conduct: Initial Review (IR) | 2022-03-29 | Engineering – requiring more detailed review
122565527 | 1522 | Conduct: Initial Review (IR) | 2022-04-08 | Customer – requirement to provide corrected information
122565527 | 1522 | Conduct: Initial Review (IR) | 2022-05-06 | Engineering – requiring more detailed review
122607062 | 1523 | Conduct: Initial Review (IR) | 2022-04-01 | Customer – requirement to provide corrected information
122607062 | 1523 | Conduct: Initial Review (IR) | 2022-04-08 | Engineering – requiring more detailed review
122614018 | 1524 | Conduct: Initial Review (IR) | 2022-03-10 | Customer – requirement to provide corrected information
122773420 | 1525 | Conduct: Initial Review (IR) | 2022-03-24 | Customer – requirement to provide corrected information
122773420 | 1525 | Conduct: Initial Review (IR) | 2022-04-05 | Customer – requirement to provide corrected information
122883241 | 1526 | Conduct: Initial Review (IR) | 2022-04-15 | Customer – requirement to provide corrected information
122883241 | 1526 | Conduct: Initial Review (IR) | 2022-03-25 | Engineering – requiring more detailed review
122886391 | 1527 | Conduct: Initial Review (IR) | 2022-04-06 | Customer – requirement to provide corrected information
122907924 | 1528 | Conduct: Initial Review (IR) | 2022-03-25 | Customer – requirement to provide corrected information
122907924 | 1528 | Conduct: Initial Review (IR) | 2022-04-08 | Customer – requirement to provide corrected information
122917567 | 1529 | Conduct: Initial Review (IR) | 2022-04-05 | Customer – requirement to provide corrected information
122917567 | 1529 | Conduct: Initial Review (IR) | 2022-04-12 | Customer – requirement to provide corrected information
122925143 | 1530 | Conduct: Initial Review (IR) | 2022-03-21 | Customer – requirement to provide corrected information
122925143 | 1530 | Conduct: Initial Review (IR) | 2022-04-07 | Customer – requirement to provide corrected information
122925143 | 1530 | Conduct: Initial Review (IR) | 2022-04-28 | Customer – requirement to provide corrected information
122985125 | 1531 | Conduct: Initial Review (IR) | 2022-04-20 | Customer – requirement to provide corrected information
122985231 | 1532 | Conduct: Initial Review (IR) | 2022-04-20 | Customer – requirement to provide corrected information
123164145 | 1533 | Conduct: Initial Review (IR) | 2022-05-13 | Customer – requirement to provide corrected information
122414280 | 1534 | Conduct: Initial Review (IR) | 2022-01-21 | Engineering – addressing project volume surge
122475824 | 1535 | Conduct: Initial Review (IR) | 2022-03-11 | Engineering – addressing project volume surge
122475824 | 1535 | Conduct: Initial Review (IR) | 2022-02-25 | Engineering – requiring more detailed review
122491719 | 1536 | Conduct: Initial Review (IR) | 2022-01-12 | Engineering – addressing project volume surge
122491719 | 1536 | Conduct: Initial Review (IR) | 2022-01-19 | Engineering – addressing project volume surge
122493833 | 1537 | Conduct: Initial Review (IR) | 2022-03-16 | Engineering – addressing project volume surge
122495745 | 1538 | Conduct: Initial Review (IR) | 2022-01-31 | Engineering – addressing project volume surge
122501601 | 1539 | Conduct: Initial Review (IR) | 2022-03-24 | Engineering – addressing project volume surge
122501601 | 1539 | Conduct: Initial Review (IR) | 2022-03-09 | Engineering – requiring more detailed review
122512508 | 1540 | Conduct: Initial Review (IR) | 2022-03-16 | Engineering – addressing project volume surge
122514586 | 1541 | Conduct: Initial Review (IR) | 2022-02-02 | Engineering – addressing project volume surge
122516525 | 1542 | Conduct: Initial Review (IR) | 2022-02-03 | Engineering – addressing project volume surge
122516525 | 1542 | Conduct: Initial Review (IR) | 2022-02-10 | Engineering – addressing project volume surge
122518112 | 1543 | Conduct: Initial Review (IR) | 2022-02-04 | Engineering – addressing project volume surge
122518112 | 1543 | Conduct: Initial Review (IR) | 2022-02-11 | Engineering – addressing project volume surge
122518209 | 1544 | Conduct: Initial Review (IR) | 2022-02-04 | Engineering – addressing project volume surge
122518209 | 1544 | Conduct: Initial Review (IR) | 2022-02-11 | Engineering – addressing project volume surge
122525007 | 1545 | Conduct: Initial Review (IR) | 2022-02-08 | Engineering – addressing project volume surge
122525007 | 1545 | Conduct: Initial Review (IR) | 2022-02-15 | Engineering – addressing project volume surge
122601545 | 1546 | Conduct: Initial Review (IR) | 2022-03-30 | Engineering – addressing project volume surge
122601545 | 1546 | Conduct: Initial Review (IR) | 2022-03-03 | Engineering – requiring more detailed review
122601545 | 1546 | Conduct: Initial Review (IR) | 2022-03-10 | Engineering – requiring more detailed review
122601545 | 1546 | Conduct: Initial Review (IR) | 2022-03-17 | Engineering – requiring more detailed review
122601545 | 1546 | Conduct: Initial Review (IR) | 2022-03-23 | Engineering – requiring more detailed review
122624631 | 1547 | Conduct: Initial Review (IR) | 2022-04-20 | Engineering – addressing project volume surge
122920877 | 1548 | Conduct: Initial Review (IR) | 2022-03-16 | Engineering – addressing project volume surge
122503044 | 1549 | Conduct: Screens Q and R | 2022-02-22 | Engineering – addressing project volume surge
122503047 | 1550 | Conduct: Screens Q and R | 2022-02-22 | Engineering – addressing project volume surge
121814237 | 1551 | Conduct: SIS | 2022-03-01 | Engineering – addressing project volume surge
121814237 | 1551 | Conduct: SIS | 2022-03-08 | Engineering – requiring more detailed review
121955755 | 1552 | Conduct: SIS | 2022-03-17 | Engineering – addressing project volume surge
121967204 | 1553 | Conduct: SIS | 2022-03-17 | Engineering – addressing project volume surge
122169882 | 1554 | Conduct: SIS | 2022-03-16 | Engineering – addressing project volume surge
121833944 | 1555 | Conduct: Supplemental Review (SR) | 2022-02-11 | Engineering – addressing project volume surge
121833944 | 1555 | Conduct: Supplemental Review (SR) | 2022-02-18 | Engineering – addressing project volume surge
121833944 | 1555 | Conduct: Supplemental Review (SR) | 2022-02-25 | Engineering – addressing project volume surge
121833944 | 1555 | Conduct: Supplemental Review (SR) | 2022-03-04 | Engineering – addressing project volume surge
121956158 | 1556 | Conduct: Supplemental Review (SR) | 2022-03-04 | Engineering – addressing project volume surge
121956158 | 1556 | Conduct: Supplemental Review (SR) | 2022-03-11 | Engineering – addressing project volume surge
122368682 | 1557 | Conduct: Supplemental Review (SR) | 2022-03-01 | Engineering – addressing project volume surge
122369244 | 1558 | Conduct: Supplemental Review (SR) | 2022-04-19 | Engineering – addressing project volume surge
122436825 | 1559 | Conduct: Supplemental Review (SR) | 2022-02-17 | Engineering – addressing project volume surge
122444072 | 1560 | Conduct: Supplemental Review (SR) | 2022-03-30 | Engineering – addressing project volume surge
122444072 | 1560 | Conduct: Supplemental Review (SR) | 2022-04-13 | Engineering – addressing project volume surge
122446314 | 1561 | Conduct: Supplemental Review (SR) | 2022-02-17 | Engineering – addressing project volume surge
122446314 | 1561 | Conduct: Supplemental Review (SR) | 2022-03-04 | Engineering – addressing project volume surge
122446357 | 1562 | Conduct: Supplemental Review (SR) | 2022-02-17 | Engineering – addressing project volume surge
122446357 | 1562 | Conduct: Supplemental Review (SR) | 2022-03-04 | Engineering – addressing project volume surge
122458155 | 1563 | Conduct: Supplemental Review (SR) | 2022-03-09 | Engineering – addressing project volume surge
122458155 | 1563 | Conduct: Supplemental Review (SR) | 2022-02-09 | Engineering – requiring more detailed review
122458192 | 1564 | Conduct: Supplemental Review (SR) | 2022-03-03 | Engineering – addressing project volume surge
122458192 | 1564 | Conduct: Supplemental Review (SR) | 2022-03-17 | Engineering – addressing project volume surge
122458192 | 1564 | Conduct: Supplemental Review (SR) | 2022-03-31 | Engineering – addressing project volume surge
122458192 | 1564 | Conduct: Supplemental Review (SR) | 2022-03-10 | Engineering – requiring more detailed review
122473448 | 1565 | Conduct: Supplemental Review (SR) | 2022-03-30 | Engineering – addressing project volume surge
122473497 | 1566 | Conduct: Supplemental Review (SR) | 2022-03-04 | Engineering – addressing project volume surge
122473497 | 1566 | Conduct: Supplemental Review (SR) | 2022-03-25 | Engineering – requiring more detailed review
122473508 | 1567 | Conduct: Supplemental Review (SR) | 2022-03-30 | Engineering – addressing project volume surge
122473944 | 1568 | Conduct: Supplemental Review (SR) | 2022-03-04 | Engineering – addressing project volume surge
122473944 | 1568 | Conduct: Screens Q and R | 2022-05-02 | Engineering – requiring more detailed review
122473944 | 1568 | Conduct: Supplemental Review (SR) | 2022-03-18 | Engineering – requiring more detailed review
122473944 | 1568 | Conduct: Supplemental Review (SR) | 2022-04-01 | Engineering – requiring more detailed review
122473980 | 1569 | Conduct: Supplemental Review (SR) | 2022-03-02 | Engineering – addressing project volume surge
122473980 | 1569 | Conduct: Supplemental Review (SR) | 2022-03-16 | Engineering – requiring more detailed review
122481072 | 1570 | Conduct: Supplemental Review (SR) | 2022-02-23 | Engineering – addressing project volume surge
122488892 | 1571 | Conduct: Supplemental Review (SR) | 2022-03-14 | Engineering – addressing project volume surge
122503274 | 1572 | Conduct: Supplemental Review (SR) | 2022-03-15 | Engineering – addressing project volume surge
122503274 | 1572 | Conduct: Supplemental Review (SR) | 2022-03-22 | Engineering – addressing project volume surge
122503274 | 1572 | Conduct: Supplemental Review (SR) | 2022-03-29 | Engineering – addressing project volume surge
122533771 | 1573 | Conduct: Supplemental Review (SR) | 2022-03-15 | Engineering – addressing project volume surge
122533771 | 1573 | Conduct: Supplemental Review (SR) | 2022-03-22 | Engineering – addressing project volume surge
122533771 | 1573 | Conduct: Supplemental Review (SR) | 2022-04-05 | Engineering – addressing project volume surge
122533771 | 1573 | Conduct: Supplemental Review (SR) | 2022-04-12 | Engineering – addressing project volume surge
122534699 | 1574 | Conduct: Supplemental Review (SR) | 2022-04-05 | Engineering – addressing project volume surge
122547209 | 1575 | Conduct: Supplemental Review (SR) | 2022-04-06 | Engineering – addressing project volume surge
122547209 | 1575 | Conduct: Initial Review (IR) | 2022-02-16 | Engineering – requiring more detailed review
122547209 | 1575 | Conduct: Supplemental Review (SR) | 2022-03-30 | Engineering – requiring more detailed review
122618214 | 1576 | Conduct: Supplemental Review (SR) | 2022-03-10 | Engineering – addressing project volume surge
122618214 | 1576 | Conduct: Screens Q and R | 2022-05-02 | Engineering – requiring more detailed review
122618214 | 1576 | Conduct: Supplemental Review (SR) | 2022-03-17 | Engineering – requiring more detailed review
122618214 | 1576 | Conduct: Supplemental Review (SR) | 2022-03-31 | Engineering – requiring more detailed review
122618591 | 1577 | Conduct: Supplemental Review (SR) | 2022-04-05 | Engineering – addressing project volume surge
122618591 | 1577 | Conduct: Supplemental Review (SR) | 2022-04-12 | Engineering – addressing project volume surge
120605545 | 1578 | Conduct: Initial Review (IR) | 2022-03-15 | Engineering – requiring more detailed review
120605545 | 1578 | Conduct: Initial Review (IR) | 2022-03-08 | Project Management – requiring more detailed review
121896536 | 1579 | Conduct: Initial Review (IR) | 2022-02-17 | Engineering – requiring more detailed review
122275616 | 1580 | Conduct: Initial Review (IR) | 2022-03-01 | Engineering – requiring more detailed review
122326379 | 1581 | Conduct: Initial Review (IR) | 2022-02-22 | Engineering – requiring more detailed review
122326379 | 1581 | Conduct: Initial Review (IR) | 2022-03-08 | Engineering – requiring more detailed review
122365068 | 1582 | Conduct: Initial Review (IR) | 2022-04-21 | Engineering – requiring more detailed review
122365287 | 1583 | Conduct: Initial Review (IR) | 2022-05-09 | Engineering – requiring more detailed review
122374758 | 1584 | Conduct: Initial Review (IR) | 2022-03-09 | Engineering – requiring more detailed review
122374758 | 1584 | Conduct: Initial Review (IR) | 2022-04-06 | Engineering – requiring more detailed review
122374758 | 1584 | Conduct: Initial Review (IR) | 2022-04-27 | Engineering – requiring more detailed review
122374758 | 1584 | Conduct: Initial Review (IR) | 2022-03-23 | Project Management – requiring more detailed review
122392748 | 1585 | Conduct: Initial Review (IR) | 2022-03-01 | Engineering – requiring more detailed review
122409987 | 1586 | Conduct: Initial Review (IR) | 2022-04-29 | Engineering – requiring more detailed review
122426646 | 1587 | Conduct: Initial Review (IR) | 2022-03-04 | Engineering – requiring more detailed review
122452790 | 1588 | Conduct: Initial Review (IR) | 2022-05-04 | Engineering – requiring more detailed review
122455092 | 1589 | Conduct: Initial Review (IR) | 2022-02-16 | Engineering – requiring more detailed review
122455618 | 1590 | Conduct: Initial Review (IR) | 2022-01-26 | Engineering – requiring more detailed review
122456934 | 1591 | Conduct: Initial Review (IR) | 2022-03-23 | Engineering – requiring more detailed review
122459390 | 1592 | Conduct: Initial Review (IR) | 2022-03-24 | Engineering – requiring more detailed review
122459390 | 1592 | Conduct: Initial Review (IR) | 2022-04-14 | Engineering – requiring more detailed review
122459390 | 1592 | Conduct: Initial Review (IR) | 2022-06-09 | Engineering – requiring more detailed review
122480663 | 1593 | Conduct: Initial Review (IR) | 2022-03-03 | Engineering – requiring more detailed review
122480663 | 1593 | Conduct: Initial Review (IR) | 2022-03-24 | Engineering – requiring more detailed review
122482067 | 1594 | Conduct: Initial Review (IR) | 2022-03-17 | Engineering – requiring more detailed review
122482067 | 1594 | Conduct: Initial Review (IR) | 2022-04-07 | Engineering – requiring more detailed review
122483891 | 1595 | Conduct: Initial Review (IR) | 2022-03-09 | Engineering – requiring more detailed review
122483891 | 1595 | Conduct: Initial Review (IR) | 2022-03-16 | Engineering – requiring more detailed review
122483891 | 1595 | Conduct: Initial Review (IR) | 2022-03-30 | Engineering – requiring more detailed review
122483891 | 1595 | Conduct: Initial Review (IR) | 2022-04-06 | Engineering – requiring more detailed review
122483891 | 1595 | Conduct: Initial Review (IR) | 2022-04-13 | Engineering – requiring more detailed review
122483891 | 1595 | Conduct: Initial Review (IR) | 2022-04-27 | Engineering – requiring more detailed review
122490280 | 1596 | Conduct: Initial Review (IR) | 2022-05-03 | Engineering – requiring more detailed review
122495134 | 1597 | Conduct: Initial Review (IR) | 2022-03-09 | Engineering – requiring more detailed review
122499720 | 1598 | Conduct: Initial Review (IR) | 2022-02-03 | Engineering – requiring more detailed review
122500918 | 1599 | Conduct: Initial Review (IR) | 2022-03-25 | Engineering – requiring more detailed review
122504768 | 1600 | Conduct: Initial Review (IR) | 2022-03-14 | Engineering – requiring more detailed review
122506381 | 1601 | Conduct: Initial Review (IR) | 2022-02-21 | Engineering – requiring more detailed review
122507236 | 1602 | Conduct: Initial Review (IR) | 2022-04-14 | Engineering – requiring more detailed review
122507236 | 1602 | Conduct: Initial Review (IR) | 2022-04-19 | Engineering – requiring more detailed review
122507924 | 1603 | Conduct: Initial Review (IR) | 2022-03-30 | Engineering – requiring more detailed review
122510240 | 1604 | Conduct: Initial Review (IR) | 2022-03-02 | Engineering – requiring more detailed review
122510240 | 1604 | Conduct: Initial Review (IR) | 2022-03-30 | Engineering – requiring more detailed review
122510240 | 1604 | Conduct: Initial Review (IR) | 2022-04-27 | Engineering – requiring more detailed review
122512103 | 1605 | Conduct: Initial Review (IR) | 2022-03-30 | Engineering – requiring more detailed review
122512203 | 1606 | Conduct: Initial Review (IR) | 2022-03-09 | Engineering – requiring more detailed review
122512644 | 1607 | Conduct: Initial Review (IR) | 2022-02-11 | Engineering – requiring more detailed review
122514976 | 1608 | Conduct: Initial Review (IR) | 2022-02-11 | Engineering – requiring more detailed review
122514976 | 1608 | Conduct: Initial Review (IR) | 2022-03-11 | Engineering – requiring more detailed review
122523757 | 1609 | Conduct: Initial Review (IR) | 2022-02-22 | Engineering – requiring more detailed review
122524890 | 1610 | Conduct: Initial Review (IR) | 2022-02-28 | Engineering – requiring more detailed review
122525379 | 1611 | Conduct: Initial Review (IR) | 2022-03-22 | Engineering – requiring more detailed review
122525379 | 1611 | Conduct: Initial Review (IR) | 2022-04-08 | Engineering – requiring more detailed review
122525379 | 1611 | Conduct: Initial Review (IR) | 2022-04-29 | Engineering – requiring more detailed review
122526058 | 1612 | Conduct: Initial Review (IR) | 2022-05-13 | Engineering – requiring more detailed review
122526655 | 1613 | Conduct: Initial Review (IR) | 2022-03-07 | Engineering – requiring more detailed review
122527874 | 1614 | Conduct: Initial Review (IR) | 2022-03-04 | Engineering – requiring more detailed review
122527874 | 1614 | Conduct: Initial Review (IR) | 2022-03-11 | Engineering – requiring more detailed review
122528010 | 1615 | Conduct: Initial Review (IR) | 2022-05-03 | Engineering – requiring more detailed review
122530575 | 1616 | Conduct: Initial Review (IR) | 2022-03-07 | Engineering – requiring more detailed review
122530703 | 1617 | Conduct: Initial Review (IR) | 2022-03-07 | Engineering – requiring more detailed review
122548205 | 1618 | Conduct: Initial Review (IR) | 2022-03-07 | Engineering – requiring more detailed review
122549907 | 1619 | Conduct: Initial Review (IR) | 2022-04-29 | Engineering – requiring more detailed review
122549978 | 1620 | Conduct: Initial Review (IR) | 2022-03-04 | Engineering – requiring more detailed review
122549978 | 1620 | Conduct: Initial Review (IR) | 2022-04-01 | Engineering – requiring more detailed review
122549978 | 1620 | Conduct: Initial Review (IR) | 2022-04-25 | Engineering – requiring more detailed review
122551842 | 1621 | Conduct: Initial Review (IR) | 2022-02-14 | Engineering – requiring more detailed review
122551842 | 1621 | Conduct: Initial Review (IR) | 2022-02-28 | Engineering – requiring more detailed review
122558596 | 1622 | Conduct: Initial Review (IR) | 2022-03-25 | Engineering – requiring more detailed review
122561656 | 1623 | Conduct: Initial Review (IR) | 2022-03-04 | Engineering – requiring more detailed review
122562650 | 1624 | Conduct: Initial Review (IR) | 2022-03-04 | Engineering – requiring more detailed review
122562650 | 1624 | Conduct: Initial Review (IR) | 2022-04-01 | Engineering – requiring more detailed review
122562650 | 1624 | Conduct: Initial Review (IR) | 2022-04-25 | Engineering – requiring more detailed review
122594158 | 1625 | Conduct: Initial Review (IR) | 2022-03-04 | Engineering – requiring more detailed review
122594619 | 1626 | Conduct: Initial Review (IR) | 2022-02-25 | Engineering – requiring more detailed review
122603115 | 1627 | Conduct: Initial Review (IR) | 2022-03-11 | Engineering – requiring more detailed review
122603646 | 1628 | Conduct: Initial Review (IR) | 2022-03-23 | Engineering – requiring more detailed review
122603646 | 1628 | Conduct: Initial Review (IR) | 2022-03-30 | Engineering – requiring more detailed review
122603646 | 1628 | Conduct: Initial Review (IR) | 2022-04-13 | Engineering – requiring more detailed review
122603646 | 1628 | Conduct: Initial Review (IR) | 2022-04-29 | Engineering – requiring more detailed review
122605772 | 1629 | Conduct: Initial Review (IR) | 2022-03-11 | Engineering – requiring more detailed review
122605782 | 1630 | Conduct: Initial Review (IR) | 2022-03-16 | Engineering – requiring more detailed review
122610444 | 1631 | Conduct: Initial Review (IR) | 2022-03-09 | Engineering – requiring more detailed review
122610704 | 1632 | Conduct: Initial Review (IR) | 2022-02-28 | Engineering – requiring more detailed review
122613819 | 1633 | Conduct: Initial Review (IR) | 2022-04-29 | Engineering – requiring more detailed review
122614504 | 1634 | Conduct: Initial Review (IR) | 2022-02-28 | Engineering – requiring more detailed review
122614630 | 1635 | Conduct: Initial Review (IR) | 2022-05-09 | Engineering – requiring more detailed review
122615583 | 1636 | Conduct: Initial Review (IR) | 2022-03-30 | Engineering – requiring more detailed review
122615583 | 1636 | Conduct: Initial Review (IR) | 2022-04-13 | Engineering – requiring more detailed review
122617089 | 1637 | Conduct: Initial Review (IR) | 2022-03-08 | Engineering – requiring more detailed review
122617089 | 1637 | Conduct: Initial Review (IR) | 2022-03-15 | Engineering – requiring more detailed review
122617089 | 1637 | Conduct: Initial Review (IR) | 2022-03-29 | Engineering – requiring more detailed review
122618464 | 1638 | Conduct: Initial Review (IR) | 2022-04-08 | Engineering – requiring more detailed review
122621454 | 1639 | Conduct: Initial Review (IR) | 2022-03-02 | Engineering – requiring more detailed review
122621454 | 1639 | Conduct: Initial Review (IR) | 2022-03-09 | Engineering – requiring more detailed review
122621454 | 1639 | Conduct: Initial Review (IR) | 2022-03-16 | Engineering – requiring more detailed review
122621454 | 1639 | Conduct: Supplemental Review (SR) | 2022-04-20 | Engineering – requiring more detailed review
122623058 | 1640 | Conduct: Initial Review (IR) | 2022-03-17 | Engineering – requiring more detailed review
122623058 | 1640 | Conduct: Initial Review (IR) | 2022-03-31 | Project Management – requiring more detailed review
122624084 | 1641 | Conduct: Initial Review (IR) | 2022-03-09 | Engineering – requiring more detailed review
122625653 | 1642 | Conduct: Initial Review (IR) | 2022-03-17 | Engineering – requiring more detailed review
122625653 | 1642 | Conduct: Initial Review (IR) | 2022-03-31 | Engineering – requiring more detailed review
122625714 | 1643 | Conduct: Initial Review (IR) | 2022-03-30 | Engineering – requiring more detailed review
122774580 | 1644 | Conduct: Initial Review (IR) | 2022-02-26 | Engineering – requiring more detailed review
122775766 | 1645 | Conduct: Initial Review (IR) | 2022-04-15 | Engineering – requiring more detailed review
122786578 | 1646 | Conduct: Initial Review (IR) | 2022-03-17 | Engineering – requiring more detailed review
122786578 | 1646 | Conduct: Initial Review (IR) | 2022-03-31 | Engineering – requiring more detailed review
122786578 | 1646 | Conduct: Initial Review (IR) | 2022-04-22 | Engineering – requiring more detailed review
122795966 | 1647 | Conduct: Initial Review (IR) | 2022-03-14 | Engineering – requiring more detailed review
122796074 | 1648 | Conduct: Initial Review (IR) | 2022-03-10 | Engineering – requiring more detailed review
122796381 | 1649 | Conduct: Initial Review (IR) | 2022-03-18 | Engineering – requiring more detailed review
122796381 | 1649 | Conduct: Initial Review (IR) | 2022-04-01 | Engineering – requiring more detailed review
122796381 | 1649 | Conduct: Initial Review (IR) | 2022-04-22 | Engineering – requiring more detailed review
122796381 | 1649 | Conduct: Initial Review (IR) | 2022-04-29 | Engineering – requiring more detailed review
122796413 | 1650 | Conduct: Initial Review (IR) | 2022-03-17 | Engineering – requiring more detailed review
122849068 | 1651 | Conduct: Initial Review (IR) | 2022-04-01 | Engineering – requiring more detailed review
122849068 | 1651 | Conduct: Initial Review (IR) | 2022-05-06 | Engineering – requiring more detailed review
122866452 | 1652 | Conduct: Initial Review (IR) | 2022-03-09 | Engineering – requiring more detailed review
122866452 | 1652 | Conduct: Initial Review (IR) | 2022-03-16 | Engineering – requiring more detailed review
122881409 | 1653 | Conduct: Initial Review (IR) | 2022-04-05 | Engineering – requiring more detailed review
122881409 | 1653 | Conduct: Initial Review (IR) | 2022-04-26 | Engineering – requiring more detailed review
122881569 | 1654 | Conduct: Initial Review (IR) | 2022-04-01 | Engineering – requiring more detailed review
122881569 | 1654 | Conduct: Initial Review (IR) | 2022-04-07 | Engineering – requiring more detailed review
122881686 | 1655 | Conduct: Initial Review (IR) | 2022-04-05 | Engineering – requiring more detailed review
122885211 | 1656 | Conduct: Initial Review (IR) | 2022-04-29 | Engineering – requiring more detailed review
122885483 | 1657 | Conduct: Initial Review (IR) | 2022-04-29 | Engineering – requiring more detailed review
122886025 | 1658 | Conduct: Initial Review (IR) | 2022-04-21 | Engineering – requiring more detailed review
122887556 | 1659 | Conduct: Initial Review (IR) | 2022-04-19 | Engineering – requiring more detailed review
122891969 | 1660 | Conduct: Initial Review (IR) | 2022-05-06 | Engineering – requiring more detailed review
122895636 | 1661 | Conduct: Initial Review (IR) | 2022-03-18 | Engineering – requiring more detailed review
122895636 | 1661 | Conduct: Initial Review (IR) | 2022-04-01 | Engineering – requiring more detailed review
122902946 | 1662 | Conduct: Initial Review (IR) | 2022-04-15 | Engineering – requiring more detailed review
122916389 | 1663 | Conduct: Initial Review (IR) | 2022-03-28 | Engineering – requiring more detailed review
122917042 | 1664 | Conduct: Initial Review (IR) | 2022-03-22 | Engineering – requiring more detailed review
122917042 | 1664 | Conduct: Initial Review (IR) | 2022-04-07 | Engineering – requiring more detailed review
122918489 | 1665 | Conduct: Initial Review (IR) | 2022-04-06 | Engineering – requiring more detailed review
122918545 | 1666 | Conduct: Initial Review (IR) | 2022-04-12 | Engineering – requiring more detailed review
122945154 | 1667 | Conduct: Initial Review (IR) | 2022-05-05 | Engineering – requiring more detailed review
122945407 | 1668 | Conduct: Initial Review (IR) | 2022-05-05 | Engineering – requiring more detailed review
122951192 | 1669 | Conduct: Initial Review (IR) | 2022-03-30 | Engineering – requiring more detailed review
123042799 | 1670 | Conduct: Initial Review (IR) | 2022-04-27 | Engineering – requiring more detailed review
123042919 | 1671 | Conduct: Initial Review (IR) | 2022-04-20 | Engineering – requiring more detailed review
123042922 | 1672 | Conduct: Initial Review (IR) | 2022-04-20 | Engineering – requiring more detailed review
123042942 | 1673 | Conduct: Initial Review (IR) | 2022-05-13 | Engineering – requiring more detailed review
123044913 | 1674 | Conduct: Initial Review (IR) | 2022-04-30 | Engineering – requiring more detailed review
123053068 | 1675 | Conduct: Initial Review (IR) | 2022-05-16 | Engineering – requiring more detailed review
123063316 | 1676 | Conduct: Initial Review (IR) | 2022-05-16 | Engineering – requiring more detailed review
123063498 | 1677 | Conduct: Initial Review (IR) | 2022-05-18 | Engineering – requiring more detailed review
123063656 | 1678 | Conduct: Initial Review (IR) | 2022-05-12 | Engineering – requiring more detailed review
122322701 | 1679 | Conduct: Screens Q and R | 2022-04-18 | Engineering – requiring more detailed review
122322701 | 1679 | Conduct: Supplemental Review (SR) | 2022-02-17 | Engineering – requiring more detailed review
122322701 | 1679 | Conduct: Supplemental Review (SR) | 2022-03-04 | Engineering – requiring more detailed review
122455602 | 1680 | Conduct: Screens Q and R | 2022-02-28 | Engineering – requiring more detailed review
122455602 | 1680 | Conduct: Screens Q and R | 2022-03-14 | Engineering – requiring more detailed review
122461346 | 1681 | Conduct: Screens Q and R | 2022-02-17 | Engineering – requiring more detailed review
122492038 | 1682 | Conduct: Screens Q and R | 2022-03-04 | Engineering – requiring more detailed review
122503055 | 1683 | Conduct: Screens Q and R | 2022-03-03 | Engineering – requiring more detailed review
122514454 | 1684 | Conduct: Screens Q and R | 2022-04-18 | Engineering – requiring more detailed review
122552082 | 1685 | Conduct: Screens Q and R | 2022-04-18 | Engineering – requiring more detailed review
122786258 | 1686 | Conduct: Screens Q and R | 2022-04-04 | Engineering – requiring more detailed review
121391712 | 1687 | Conduct: SIS | 2022-03-09 | Engineering – requiring more detailed review
121391712 | 1687 | Conduct: SIS | 2022-03-16 | Engineering – requiring more detailed review
122167420 | 1688 | Conduct: SIS | 2022-03-14 | Engineering – requiring more detailed review
122167420 | 1688 | Conduct: SIS | 2022-03-21 | Engineering – requiring more detailed review
122187180 | 1689 | Conduct: SIS | 2022-03-28 | Engineering – requiring more detailed review
122220601 | 1690 | Conduct: SIS | 2022-04-28 | Engineering – requiring more detailed review
122438919 | 1691 | Conduct: SIS | 2022-04-15 | Engineering – requiring more detailed review
122459247 | 1692 | Conduct: SIS | 2022-04-29 | Engineering – requiring more detailed review
122240356 | 1693 | Conduct: Supplemental Review (SR) | 2022-03-09 | Engineering – requiring more detailed review
122443031 | 1694 | Conduct: Supplemental Review (SR) | 2022-02-18 | Engineering – requiring more detailed review
122443211 | 1695 | Conduct: Supplemental Review (SR) | 2022-02-17 | Engineering – requiring more detailed review
122443211 | 1695 | Conduct: Supplemental Review (SR) | 2022-02-25 | Engineering – requiring more detailed review
122443619 | 1696 | Conduct: Supplemental Review (SR) | 2022-02-17 | Engineering – requiring more detailed review
122443619 | 1696 | Conduct: Supplemental Review (SR) | 2022-02-25 | Engineering – requiring more detailed review
122443747 | 1697 | Conduct: Supplemental Review (SR) | 2022-02-17 | Engineering – requiring more detailed review
122443747 | 1697 | Conduct: Supplemental Review (SR) | 2022-02-25 | Engineering – requiring more detailed review
122454118 | 1698 | Conduct: Supplemental Review (SR) | 2022-03-11 | Engineering – requiring more detailed review
122520288 | 1699 | Conduct: Supplemental Review (SR) | 2022-04-20 | Engineering – requiring more detailed review
122614506 | 1700 | Conduct: Supplemental Review (SR) | 2022-03-28 | Engineering – requiring more detailed review
122624149 | 1701 | Conduct: Supplemental Review (SR) | 2022-03-17 | Engineering – requiring more detailed review
122980995 | 1702 | Conduct: Supplemental Review (SR) | 2022-04-26 | Engineering – requiring more detailed review
122409262 | 1703 | Conduct: Initial Review (IR) | 2022-04-01 | Project Management - addressing project volume surge
122533974 | 1704 | Conduct: Supplemental Review (SR) | 2022-03-02 | Project Management - addressing project volume surge
121398274 | 1705 | Conduct: Initial Review (IR) | 2022-02-16 | Project Management – requiring more detailed review
121398274 | 1705 | Conduct: Initial Review (IR) | 2022-03-02 | Project Management – requiring more detailed review

## Notes
Questions | Milestone as written in OP 22 | Milestone as tracked by PG&E | Reporting Notes
a) | Time from submission of Interconnection Request to utility’s acknowledgement of receipt | Time from submission of Interconnection Request to 1st Written notice/invoice. | Under the "Project Status" Column, "Commerial" projects = projects that have received their PTO
b) | Time from submission of Interconnection Request to time deemed complete | Time from receipt of an interconnection request to application deemed complete. | Note: This timeline should be informational only as it includes customer and utility timelines.
c) | Time from Interconnection Request deemed complete to completion of initial review and provision of results | Time from Interconnection Request deemed complete to completion of IR results
d) | Time from Supplemental Review start date to completion of Supplemental Review | Time from Supplemental Review start to completion of Supplemental review.
e) | Time from Electrical Interdependence Test start date to its completion | Time from receipt of Detailed Study Deposit to perform Electrical Independence Test (Screens Q and R) and issue Electrical Independence Test results (if Electrical Independence Test required)
f) | Time from Electrical Interdependence Test completion to Electrical Interdependence Test results scoping meeting held (F.3.b.i) | Time from Electrical Independence Test results issuance to scheduling of Electrical Independence Test Scoping meeting | Note: This timeline should be informational only as it includes customer and utility timelines.
g) | Time from study scoping meeting until study agreement provided | Time from Detailed Study Scoping Meeting held to issuance of draft Detailed Study Agreement (if Detailed Study required)
h) | Time from System Impact Study start date to its completion date | Time from Detailed Study Agreement execution to issuance of System Impact Study results/report (if Detailed Study required)
i) | Time to provide Draft Generator Interconnection Agreement applicable milestone | Time from completion of study to Tender Draft IA
j) | Time from Draft Generator Interconnection Agreement provided or Final Study Report date for Detailed Study to date Generator Interconnection Agreement executed | Time from issuance of draft Generator Interconnection Agreement to date Generator Interconnection Agreement executed | Note: This timeline should be informational only as it includes customer and utility timelines. Cycle Time J(a) contains "N/A" because some customers provided the IA to PG&E, therefore PG&E did not issue any IA for these projects.
k) | Time from when the customer notifies the utility it has completed all of its obligations under the agreements (F.5.b) including commissioning tests, to when the utility provides the customer Permission to Operate | Time from FMO inspection to FMO inspection Pass. For projects with PPI, conduct PPI to PTO (CPTO or Final PTO) date.
l) | Total time from submission of Interconnection Request to Permission to Operate (Not in Rule 21, tracked for informational purposes) | Total time from receipt of Interconnection Request to issuance of Permission to Operate | Note: This timeline should be informational only as it includes customer and utility timelines.
m) | Time from request to consider modification to determination whether modification is material (F.3.b.v) | Time from customer request to consider whether a proposed modification is material to issuance of material modification analysis/results by utility | Note: as set forth in F.3.b.v, customers are not limited in the number of material modification requests, so it is possible for a project to have multiple iterations of this timeline
n) | Time for responding to line-side taps variance requests (for Utilities that require a variance request) | Time from Variance request received to completion of variance request review. | 1. PG&E does not currently distinguish between line side tap variance and other variances, so report reflects all variance requests 2. This timeline should be informational only as it includes customer and utility timelines. 3. PG&E and other IOUs differs for this section because other IOUs may not perform variance requests
o) | Design and invoice of net generation output meter | Time from the date PG&E receives NGOM requests to completion of NGOM invoice.
p) | Installation of net generation output meter | Time from the date EGI requests for the NGOM install to completion of NGOM install. | Note: Self-contained meters represent the vast majority and are reflected in reporting.
q) | Time from customer agreement to proceed to final design and issuance of invoice | Time from PG&E issue EA and customer readiness to PG&E received payments/signed contracts. | 1. This timeline should be informational only as it includes customer and utility timelines. 2. PG&E differs from other IOU on this section because PG&E seperated Service planning and IT/Telemetry type mitigation work
r) | Time from customer payment of invoice and completion of customer work to completion of upgrade construction | Time from when PG&E receives payment and customer readiness to PG&E completes construction | 1. This timeline should be informational only as it includes customer and utility timelines. 2. PG&E differs from other IOU on this section because PG&E seperated Service planning and IT/Telemetry type mitigation work
s) | Time for scheduling of commissioning test | Time from when PG&E schedules commissioning test | Note: This timeline should be informational only as it includes customer and utility timelines.

## OP 22 CT Header Reference
PG&E Interconnection Timeline Report | [8 empty] | Application Review: |  |  |  |  | Fast Track Initial Review: |  | Fast Track Supplemental Review: |  |  | Electrical Independence Test (EIT): |  |  | Scoping Meeting and Study Agreement: |  |  | System Impact Study (SIS): | [5 empty] | Draft Agreement: |  |  | Agreement Execution: |  |  |  | Material Modification: |  |  | Variance Request Review: |  |  | Net Generating Output Meter (NGOM): | [6 empty] | Minor Upgrades Design: | [5 empty] | Minor Upgrades Construction: | [5 empty] | Commissioning and In-Service:
Document Submission Frequency: Quarterly |  |  |  |  | Reporting Interval: 12/29/20 - 6/30/21 |  |  |  | ● 10 Business Days for initial application review [E.5.a.] (15 Business Days if Cost Envelope Option is selected [E.5.a.]) | [6 empty] | 20 Business Days [F.2.c.i.] |  |  | 20 Business Days [F.3.a.] |  |  | 5 Business Days [F.3.b.i.] |  |  | 60 Business Days [F.3.b.ii.] | [8 empty] | 90 Calendar Days [F.2.e.][F.3.2.ii.] |  |  |  | 10 Business Days [F.3.b.v] (20 Business Days if Cost Envelope Option is selected [F.3.b.v]) | [12 empty] | 60 Business Days (estimated timeline) | [5 empty] | 60 Business Days (estimated timeline) | [5 empty] | Mutually Agreeable Date with Customer
Proceeding Number: R.17-07-007; Decision Number: D.20-09-035; Ordering Paragraph (OP) Number from the Decision: 22 | [8 empty] | ● 10 Business Days for 1st deficiency cure review [E.5.b.i.] | [21 empty] | ● 15 Business Days for Fast Track [F.2.a] | [12 empty] | ● 20 Business Days to Design
[9 empty] | ● 5 Business Days for 2nd deficiency cure review [E.5.b.ii.] | [21 empty] | ● 30 Calendar Days for Detailed Study [F.3.e.i.] | [12 empty] | ● 20 Business Days to Install
Key | Utility | Zip Code | NEM Type | Project Type | Project Status | Technology Type | SizeTotal Proposed Gen | Cost Envelope Requested? | Application Received | Provide: 1st Written Notice/Invoice | Cycle Time A (Business Days to Acknowledge Interconnection Request Submission) | Application Deemed Complete | Cycle Time b (Business Days to Deem Complete) | Conduct: Initial Review (IR) | Cycle Time c (Time from Interconnection Request deemed complete to completion of initial review & provision of results) | Conduct: Supplemental Review (SR) | Conduct: Supplemental Review (SR) | Cycle Time d (Time from Supplemental Review start date to completion of Supplemental Review) | Conduct: Screens Q and R | Conduct: Screens Q and R | Cycle Time e (Time from Electrical Interdependence Test start date to its completion) | Scoping Meeting Date | Scoping Meeting Date | Cycle time f (Time from Electrical Interdependence Test completion to EIT results scoping meeting held) | DSA Agreement Executed by PG&E | Conduct: SIS | Cycle Time h (Time from System Impact Study start date to its completion date) | Scoping Meeting Date | Tendered DSA Agreement | Cycle Time g (Time from study scoping meeting until study agreement provided) | Tender Draft IA | Tender Draft IA | Cycle Time I (Time to provide Draft Generator Interconnection Agreement applicable milestone) | Tender Draft IA | IA Negotiations/Customer Signature | Cycle Time J(a) (Time from Draft Generator Interconnection Agreement provided to date Generator Interconnection Agreement Executed) | Cycle Time J(b) (Time from Final Study Report date for Detailed Study to date Generator Interconnection Agreement Executed) | Receive Customer Changes | Determine Material Modifications | Cycle Time M (Time from request to consider modification to determination whether modification is material (F.3.b.v)) | Variance Request Received (typ. From cust) | Conduct: Variance Request Review | Cycle Time N (Time for responding to line-side taps variance requests (for Utilities that require a variance request)) | Conduct: Meter Review | Tender: Meter Invoice | Tender: Meter Invoice | Cycle Time O (Design and invoice of net generation output meter) | Move to FMO | FMO - PASS | Cycle Time P (Installation of net generation output meter) | SP&D Design Start | SP&D Deisgn End | Cycle Time Q(a) Time from customer agreement to proceed to final design and issuance of invoice SP&D | Tender EA Invoice | IT Design End | Cycle Time Q(b)Time from customer agreement to proceed to final design and issuance of invoice Telemetry | SP&D Construction Start | SP&D Construction Finish | Cycle Time R(a) Time from customer payment of invoice and completion of customer work to completion of upgrade construction SP&D | PG&E Construction Start IT | PG&E Construction Complete IT | Cycle Time R(b)Time from customer payment of invoice and completion of customer work to completion of upgrade construction Telemetry | PPI Authorization Letter | PPI Completion | Cycle Time S (Time for scheduling of commissioning test) | FMO - PASS (Move to FMO) | FMO schedule Inspection FMO order | Cycle Time S(b) This is for projects that do not require PPI | FMO - PASS | Permission to Operate - Final (COD) | Permission to Operate - Conditional (COD) | Cycle time K(a)Time from when the customer notifies the utility it has completed all of its obligations under the agreements (F.5.b) including commissioning tests, to when the utility provides the customer Permission to Operate | Conduct Pre Paralell Inspection (PPI) | Cycle time K(b) This cycle time is for projects that require PPI | Cycle Time L (Total time from submission of Interconnection Request to Permission to Operate (Not in Rule 21, tracked for informational purposes))
165 | PGE |  | NEM | NEM Paired Storage | Commercial | Solar PV, Storage | 33.646 | No | 2021-02-08 | 2021-02-16 | 5 | 2021-03-02 | 15 | 2021-03-06 | 3 | [15 empty] | 2021-03-06 | 2021-03-06 | 0 | 2021-03-06 | 2021-03-10 | 2 | [11 empty] | 2021-03-24 | 2021-03-25 | 1 | [15 empty] | 2021-03-24 | 2021-03-25 | 1 | 2021-03-25 | 2021-03-30 |  | 3
204 | PGE |  | NEM | EXPNEM | Implementation | Solar PV | 37.009 | No | 2021-01-28 | 2021-02-09 | 8 | 2021-04-21 | 58 | 2021-04-26 | 3 | [15 empty] | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-05-14 | 14 |  |  |  |  | 2021-05-19 | 2021-05-28 | 7 |  |  |  |  | 2021-06-24 | 2021-06-30 | 4 | 2021-06-30 | [14 empty] | 2021-06-24 | 2021-06-24 | 0 | 2021-06-30 |  | 2021-07-07 | 4 |  |  | 111
323 | PGE |  | NEM | EXPNEM | IA in Progress | Solar PV | 85.795 | No | 2021-02-03 | 2021-02-17 | 9 | 2021-02-23 | 13 | 2021-03-01 | 4 | [15 empty] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | [16 empty] | 2019-08-26 | 2020-04-02 | 150 |  |  |  | 2021-01-19 | 2021-03-16 | 39

## Holidays
Holiday List
Christmas Day | 2021-12-25
Day after Thanksgiving | 2021-11-26
Thanksgiving Day | 2021-11-25
Veterans' Day | 2021-11-11
Labor Day | 2021-09-06
Independence Day | 2021-07-05
Memorial Day | 2021-05-31
Presidents' Day | 2021-02-15
Martin Luther King Day | 2021-01-18
New Year's Day | 2021-01-01
Christmas Day | 2020-12-25
Day after Thanksgiving | 2020-11-27
Thanksgiving Day | 2020-11-26
Veterans' Day | 2020-11-11
Labor Day | 2020-09-07
Independence Day | 2020-07-06
Memorial Day | 2020-05-25
Presidents' Day | 2020-02-17
Martin Luther King Day | 2020-01-20
New Year's Day | 2020-01-01
Christmas Day | 2019-12-25
Day after Thanksgiving | 2019-11-29
Thanksgiving Day | 2019-11-28
Veterans' Day | 2019-11-11
Labor Day | 2019-09-02
Independence Day | 2019-07-04
Memorial Day | 2019-05-27
Presidents' Day | 2019-02-18
Martin Luther King Day | 2019-01-21
New Year's Day | 2019-01-01
Christmas Day | 2018-12-25
Day after Thanksgiving | 2018-11-23
Thanksgiving Day | 2018-11-22
Veterans' Day | 2018-11-12
Labor Day | 2018-09-03
Independence Day | 2018-07-04
Memorial Day | 2018-05-28
Presidents' Day | 2018-02-19
Martin Luther King Day | 2018-01-15
New Year's Day | 2018-01-01
Christmas Day | 2017-12-25
Day after Thanksgiving | 2017-11-23
Thanksgiving Day | 2017-11-24
Veterans' Day | 2017-11-10
Labor Day | 2017-09-04
Independence Day | 2017-07-04
Memorial Day | 2017-05-29
Presidents' Day | 2017-02-20
Martin Luther King Day | 2017-01-16
New Year's Day | 2017-01-01
Christmas Day | 2016-12-26
Day after Thanksgiving | 2016-11-24
Thanksgiving Day | 2016-11-25
Veterans' Day | 2016-11-11
Labor Day | 2016-09-05
Independence Day | 2016-07-04
Memorial Day | 2016-05-30
Presidents' Day | 2016-02-15
Martin Luther King Day | 2016-01-18
New Year's Day | 2016-01-01
Christmas Day | 2015-12-25
Day after Thanksgiving | 2015-11-27
Thanksgiving Day | 2015-11-26
Veterans' Day | 2015-11-11
Labor Day | 2015-09-07
Independence Day | 2015-07-03
Memorial Day | 2015-05-25
Presidents' Day | 2015-02-16
Martin Luther King Day | 2015-01-19
New Year's Day | 2015-01-01
Christmas Day | 2014-12-25
Day after Thanksgiving | 2014-11-28
Thanksgiving Day | 2014-11-27
Veterans' Day | 2014-11-11
Labor Day | 2014-09-01
Independence Day | 2014-07-04
Memorial Day | 2014-05-26
Presidents' Day | 2014-02-17
Martin Luther King Day | 2014-01-20
New Year's Day | 2014-01-01
Christmas Day | 2013-12-25
Day after Thanksgiving | 2013-11-29
Thanksgiving Day | 2013-11-28
Veterans' Day | 2013-11-11
Labor Day | 2013-09-02
Independence Day | 2013-07-04
Memorial Day | 2013-05-27
Presidents' Day | 2013-02-18
Martin Luther King Day | 2013-01-21
New Year's Day | 2013-01-01
Christmas Day | 2012-12-25
Day after Thanksgiving | 2012-11-23
Thanksgiving Day | 2012-11-22
Veterans' Day | 2012-11-11
Labor Day | 2012-09-03
Independence Day | 2012-07-04
Memorial Day | 2012-05-28
Presidents' Day | 2012-02-20
Martin Luther King Day | 2012-01-16
New Year's Day | 2012-01-02
Christmas Day | 2011-12-26
Day after Thanksgiving | 2011-11-25
Thanksgiving Day | 2011-11-24
Veterans' Day | 2011-11-11
Labor Day | 2011-09-05
Independence Day | 2011-07-04
Memorial Day | 2011-05-30
Presidents' Day | 2011-02-21
Martin Luther King Day | 2011-01-17
New Year's Day | 2011-01-03
Christmas Day | 2010-12-27
Day after Thanksgiving | 2010-11-26
Thanksgiving Day | 2010-11-25
Veterans' Day | 2010-11-11
Labor Day | 2010-09-06
Independence Day | 2010-07-05
Memorial Day | 2010-05-31
Presidents' Day | 2010-02-15
Martin Luther King Day | 2010-01-18
New Year's Day | 2010-01-01
Christmas Day | 2009-12-25
Day after Thanksgiving | 2009-11-27
Thanksgiving Day | 2009-11-26
Veterans' Day | 2009-11-11
Labor Day | 2009-09-07
Independence Day | 2009-07-06
Memorial Day | 2009-05-25
Presidents' Day | 2009-02-16
Martin Luther King Day | 2009-01-19
New Year's Day | 2009-01-01
Christmas Day | 2008-12-25
Day after Thanksgiving | 2008-11-28
Thanksgiving Day | 2008-11-27
Veterans' Day | 2008-11-11
Labor Day | 2008-09-01
Independence Day | 2008-07-04
Memorial Day | 2008-05-26
Presidents' Day | 2008-02-18
Martin Luther King Day | 2008-01-21
New Year's Day | 2008-01-01
Christmas Day | 2007-12-25
Day after Thanksgiving | 2007-11-23
Thanksgiving Day | 2007-11-22
Veterans' Day | 2007-11-11
Labor Day | 2007-09-03
Independence Day | 2007-07-04
Memorial Day | 2007-05-28
Presidents' Day | 2007-02-19
Martin Luther King Day | 2007-01-15
New Year's Day | 2007-01-01
Christmas Day | 2006-12-25
Day after Thanksgiving | 2006-11-24
Thanksgiving Day | 2006-11-23
Veterans' Day | 2006-11-11
Labor Day | 2006-09-04
Independence Day | 2006-07-04
Memorial Day | 2006-05-29
Presidents' Day | 2006-02-20
Martin Luther King Day | 2006-01-16
New Year's Day | 2006-01-02
Christmas Day | 2005-12-26
Day after Thanksgiving | 2005-11-25
Thanksgiving Day | 2005-11-24
Veterans' Day | 2005-11-11
Labor Day | 2005-09-05
Independence Day | 2005-07-04
Memorial Day | 2005-05-30
Presidents' Day | 2005-02-21
Martin Luther King Day | 2005-01-17
New Year's Day | 2005-01-03
Christmas Day | 2004-12-27
Day after Thanksgiving | 2004-11-26
Thanksgiving Day | 2004-11-25
Veterans' Day | 2004-11-11
Labor Day | 2004-09-06
Independence Day | 2004-07-05
Memorial Day | 2004-05-31
Presidents' Day | 2004-02-16
Martin Luther King Day | 2004-01-19
New Year's Day | 2004-01-01
Christmas Day | 2003-12-25
Day after Thanksgiving | 2003-11-28
Thanksgiving Day | 2003-11-27
Veterans' Day | 2003-11-11
Labor Day | 2003-09-01
Independence Day | 2003-07-04
Memorial Day | 2003-05-26
Presidents' Day | 2003-02-17
Martin Luther King Day | 2003-01-20
New Year's Day | 2003-01-01
Christmas Day | 2002-12-25
Day after Thanksgiving | 2002-11-29
Thanksgiving Day | 2002-11-28
Veterans' Day | 2002-11-11
Labor Day | 2002-09-02
Independence Day | 2002-07-04
Memorial Day | 2002-05-27
Presidents' Day | 2002-02-18
Martin Luther King Day | 2002-01-21
New Year's Day | 2002-01-01
Christmas Day | 2001-12-25
Day after Thanksgiving | 2001-11-23
Thanksgiving Day | 2001-11-22
Veterans' Day | 2001-11-11
Labor Day | 2001-09-03
Independence Day | 2001-07-04
Memorial Day | 2001-05-28
Presidents' Day | 2001-02-19
Martin Luther King Day | 2001-01-15
New Year's Day | 2001-01-01
Christmas Day | 2000-12-25
Day after Thanksgiving | 2000-11-24
Thanksgiving Day | 2000-11-23
Veterans' Day | 2000-11-11
Labor Day | 2000-09-04
Independence Day | 2000-07-04
Memorial Day | 2000-05-29
Presidents' Day | 2000-02-21
Martin Luther King Day | 2000-01-17
New Year's Day | 2000-01-03
Christmas Day | 1999-12-27
Day after Thanksgiving | 1999-11-26
Thanksgiving Day | 1999-11-25
Veterans' Day | 1999-11-11
Labor Day | 1999-09-06
Independence Day | 1999-07-05
Memorial Day | 1999-05-31
Presidents' Day | 1999-02-15
Martin Luther King Day | 1999-01-18
New Year's Day | 1999-01-01
Christmas Day | 1998-12-25
Day after Thanksgiving | 1998-11-27
Thanksgiving Day | 1998-11-26
Veterans' Day | 1998-11-11
Labor Day | 1998-09-07
Independence Day | 1998-07-06
Memorial Day | 1998-05-25
Presidents' Day | 1998-02-16
Martin Luther King Day | 1998-01-19
New Year's Day | 1998-01-01
Christmas Day | 1997-12-25
Day after Thanksgiving | 1997-11-28
Thanksgiving Day | 1997-11-27
Veterans' Day | 1997-11-11
Labor Day | 1997-09-01
Independence Day | 1997-07-04
Memorial Day | 1997-05-26
Presidents' Day | 1997-02-17
Martin Luther King Day | 1997-01-20
New Year's Day | 1997-01-01
Christmas Day | 1996-12-25
Day after Thanksgiving | 1996-11-29
Thanksgiving Day | 1996-11-28
Veterans' Day | 1996-11-11
Labor Day | 1996-09-02
Independence Day | 1996-07-04
Memorial Day | 1996-05-27
Presidents' Day | 1996-02-19
Martin Luther King Day | 1996-01-15
New Year's Day | 1996-01-01